## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II , SM/07464 | Retrofitting | Retrofitting Joypur | W/154 | 09/08/2021 | 0 | N. G ENGINEERING | 37.09 | 0 | 0 | 0
2 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II , SM/07464 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A)[Dakshin Jaypur Mouza] [Number of FHTC to be provided (Approx) : 227] | 46/HD | 05/01/2021 | 30 | MAHARAJ CONSTRUCTION CO | 14.33 | 11.81 | 82.44 | 0
3 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II , SM/07464 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) [Jaypur Mouza part] [Number of FHTC to be provided (Approx) : 650] | BP-2021-22-378 | 03/03/2022 | 0 | M/S ASHIRBAD (INDIA) | 39.42 | 0 | 0 | 0
4 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II , SM/07464 | Retrofitting | Construction of Pump House of additional Tube well site of Joypur PWSS at Amta-II Development Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1410/HD | 17/03/2025 | 60 | JSZ GLOBAL | 7.93 | 0 | 0 | 0
5 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II , SM/07464 | Retrofitting | Sinking of 1 (One) No. additional Tubewell of size 250 X 150 mm Dia and 230 m deep drilling by Direct Rotary method with UPVC Pipes all complete at 3rd Site of Joypur PWSS of Amta-II Block under Uluberia Sub-Divison under Howrah Division, P.H.E. Dte. | 786/HD | 04/02/2025 | 100 | ACME CONSTRUCTION | 14.55 | 0 | 0 | 100
6 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. , SM/07931 | Anganwadi | Work Order for Providing Tap Connection to Schools & ANGANWADI centers under Kulgachia PWSS under Uluberia-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. | 735/HD | 23/02/2023 | 45 | DEVEN ENTERPRISE | 1.99 | 0 | 0 | 0
7 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. , SM/07931 | Anganwadi | Work Order for Providing Tap Connection to Schools & ANGANWADI centers under Shyampur-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. | 736/HD | 23/02/2023 | 45 | S.M. CONSTRUCTION | 3.83 | 1.98 | 100 | 100
8 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. , SM/07931 | Anganwadi | Work Order for Providing Tap Connection to Schools & ANGANWADI centers under Shyampur-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. | 864/HD | 01/03/2023 | 45 | PRADIP KUMAR JATI | 9.13 | 3.44 | 100 | 100
9 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. , SM/07931 | Anganwadi | Work Order for Providing Tap Connection to various awangari within Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. | 1102/HD | 17/03/2023 | 15 | LOKENATH ENTERPRISES | 2.78 | 2.48 | 100 | 100
10 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. , SM/07931 | Anganwadi | Work Order for Providing Tap Connection to various Schools within Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. | 1103/HD | 17/03/2023 | 15 | LOKENATH ENTERPRISES | 6.65 | 6.62 | 100 | 100
11 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. , SM/07931 | Anganwadi | Making provision of Running water arrangement with sinking of Tube well (100 x 40mm), 180 mtr deep along with installation of 1.0 HP Submersible pump including making water supply plumbing arrangement at Kandua AWC & Kandua Primary School under Amta-I Block under Uluberia Sub-Division under Howrah Division PHE Dte. | 3103/AE/USD | 29/02/2024 | 45 | CHANDRANI ENTERPRISE | 1.84 | 1.82 | 100 | 100
12 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. , SM/07931 | Anganwadi | Making provision of Running water arrangement with sinking of Tube well (100 x 40mm), 201 mtr deep alongwith installation of 1.0 HP Sub mersible pump including making water supply plumbing arrangement at Solbaga Primary School under Amta-II Block under Uluberia Sub-Division under Howrah Division PHE Dte. | 783/AE/USD | 05/09/2024 | 80 | CHANDRANI ENTERPRISE | 2.48 | 0 | 0 | 100
13 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. , SM/07931 | Anganwadi | Making provision of Running water arrangement with sinking of Tube well (100 x 40mm), 201 mtr deep alongwith installation of 1.0 HP Sub mersible pump including making water supply plumbing arrangement at Dadpur AWC &DadpurPrimary School under Amta-II Block under Uluberia Sub-Division under Howrah Division PHE Dte. | 766/AE/USD | 04/09/2024 | 80 | CHANDRANI ENTERPRISE | 2.48 | 0 | 0 | 100
14 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) , SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-B) (for Dhurkhali Mouza part) | 1622/HD | 09/11/2020 | 30 | GHOSH CONCERN | 28.9 | 0 | 0 | 0
15 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) , SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-A) (for Purba Bajepratap Mouza) | 1621/HD | 09/11/2020 | 30 | GHOSH CONCERN | 25.92 | 0 | 0 | 0
16 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) , SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-C) (for Dhurkhali Mouza part) | 1623/HD | 09/11/2020 | 30 | N. G ENGINEERING | 22.81 | 0 | 0 | 0
17 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) , SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme. | 8443107 | 30/03/2021 | 0 | P B ENTERPRISE | 23.52 | 0 | 0 | 0
18 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) , SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme. | 844334 | 25/02/2021 | 0 | GHOSH CONCERN | 25.85 | 0 | 0 | 0
19 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) , SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply Scheme. | 844329 | 17/03/2021 | 0 | M/S CHANDIMATA CONSTRUCTION | 18.39 | 0 | 0 | 0
20 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) , SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply Scheme. | 84433 | 01/03/2021 | 0 | P B ENTERPRISE | 27.61 | 0 | 0 | 0
21 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme , SM/06713 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-D) (for Chaltakhali (Part) & Jotsadar Mouza) | 1505/HD | 04/11/2020 | 30 | M/S ASHIRBAD (INDIA) | 29.03 | 0 | 0 | 0
22 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme , SM/06713 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-E) for Chaltakhali Mouza (Part) | 1506/HD | 04/11/2020 | 30 | M/S ASHIRBAD (INDIA) | 28.82 | 0 | 0 | 0
23 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme , SM/06713 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | 8443108 | 30/03/2021 | 0 | PRADIP KUMAR JATI | 25.73 | 0 | 0 | 0
24 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme , SM/06713 | Retrofitting | Retrofitting Khosalpur Water Supply Scheme | 84435 | 01/03/2021 | 0 | PRADIP KUMAR JATI | 24.12 | 0 | 0 | 0
25 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme , SM/06713 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | 844327 | 17/03/2021 | 0 | JAHANGIR ALAM | 26.44 | 0 | 0 | 0
26 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme , SM/06713 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme. | 8443106 | 30/03/2021 | 0 | NATURAL RESOURCES CONSORTIUM | 21.16 | 0 | 0 | 0
27 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block , SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte.on, PHE Dte. (Part-D) [Sirol Mouza] | 1805/HD | 27/11/2020 | 30 | JAHANGIR ALAM | 36.58 | 0 | 0 | 0
28 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block , SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte.on, PHE Dte. (Part-A) [Narit Mouza part] | 1802/HD | 27/11/2020 | 30 | M/S MANABESH ROY | 22.53 | 0 | 0 | 0
29 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block , SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte.on, PHE Dte. (Part-B) [Narit Mouza part] | 1803/HD | 27/11/2020 | 30 | SUNIRMAN ENTERPRISE | 19.47 | 32.41 | 166.4 | 0
30 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block , SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte.on, PHE Dte. (Part-C) [Narit Mouza part] | 1804/HD | 27/11/2020 | 30 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 14.53 | 0 | 0 | 0
31 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block , SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | W/538 | 30/01/2021 | 0 | JAHANGIR ALAM | 36.57 | 0 | 0 | 0
32 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block , SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | 844352 | 22/03/2021 | 0 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 14.34 | 0 | 0 | 0
33 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block , SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | 844343 | 20/03/2021 | 0 | M/S MANABESH ROY | 15.07 | 0 | 0 | 0
34 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block , SM/07010 | Retrofitting | Hiring of Vehicle | W/579 | 16/12/2021 | 0 | DIPANKAR GHOSH | 3.71 | 0 | 0 | 0
35 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-D) | 1536/HD | 05/11/2020 | 30 | JDJ ENTERPRISE A UNIT OF JDJ TRADERS PRIVATE LIMITED | 18.83 | 0 | 0 | 0
36 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-F | 1538/HD | 05/11/2020 | 30 | BUILT INDIA | 18.12 | 0 | 0 | 0
37 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Laying of 50 mm & 75 mm dia.,Total 1948 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) (Part-M) | 1434/HD | 13/07/2021 | 30 | A.P. POWER & CONCRETE | 4.8 | 0 | 0 | 0
38 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-E) | 1537/HD | 05/11/2020 | 30 | BUILT INDIA | 18.06 | 0 | 0 | 0
39 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Laying of 90 mm dia 470 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) (Part-O) | 1436HD | 13/07/2021 | 30 | BUILT INDIA | 2.41 | 0 | 0 | 0
40 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Laying of 63 mm dia. 1615 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) (Part-N) | 1435HD | 13/07/2021 | 30 | A.P. POWER & CONCRETE | 4.31 | 0 | 0 | 0
41 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Gobindapur PWSS at Howrah Sub Division under Howrah Division , PHE Dte. | 1441/HD | 13/07/2021 | 30 | MONIRUL ISLAM | 4.76 | 8.03 | 100 | 0
42 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-V) | 1437HD | 13/07/2021 | 30 | MONIRUL ISLAM | 4.27 | 0 | 0 | 0
43 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Laying of 50 mm ,63 mm & 75 mm dia. 110mm dia 125mm dia,Total 1034 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) (Part-S) | 1440/HD | 13/07/2021 | 30 | BUILT INDIA | 3.34 | 0 | 0 | 0
44 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-X) | 1438/HD | 13/07/2021 | 30 | BUILT INDIA | 4.34 | 0 | 0 | 0
45 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under J.B Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-W) | 1439/HD | 13/07/2021 | 30 | BUILT INDIA | 2.61 | 0 | 0 | 0
46 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Gobindapur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-L) | 1433/HD | 13/07/2021 | 30 | A.P. POWER & CONCRETE | 4.79 | 0 | 0 | 0
47 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 844356 | 23/03/2021 | 0 | BUILT INDIA | 15.55 | 0 | 0 | 0
48 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | W/428 | 08/10/2021 | 0 | A.P. POWER & CONCRETE | 4 | 0 | 0 | 0
49 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 844357 | 23/03/2021 | 0 | BUILT INDIA | 15.66 | 0 | 0 | 0
50 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | W/427 | 08/10/2021 | 0 | A.P. POWER & CONCRETE | 8.92 | 0 | 0 | 0
51 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 84439 | 16/11/2021 | 0 | A.P. POWER & CONCRETE | 1.43 | 0 | 0 | 0
52 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Work Order for Retrofitting work for Supply, delivery & installation of CIDF Sluice Valve in different Node point and construction of Sluice Valve chamber for providing Functional Household Tap Connection (FHTC) from existing distribution system of Gobindapur PWSS under Howrah Sub Division of Howrah Division , PHE Dte. | 340/HD | 17/02/2022 | 30 | MONIRUL ISLAM | 4.77 | 0 | 0 | 0
53 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under J.B Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-W) | 844315 | 17/03/2022 | 0 | BUILT INDIA | 2.57 | 0 | 0 | 0
54 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting Gobindapur W/S Scheme. | 844334 | 30/03/2022 | 0 | ALOK ENTERPRISE | 15.52 | 0 | 0 | 0
55 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 844318 | 20/01/2022 | 0 | MS ARPAN ENTERPRISE | 4.26 | 0 | 0 | 0
56 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 627/21/2022 | 15/08/2020 | 0 | RAKESH ENTERPRISE | 4.35 | 2.9 | 200 | 0
57 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 27/21/2022 | 15/08/2020 | 0 | BUILT INDIA | 1.77 | 3.55 | 200 | 0
58 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II , SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 645/21/2022 | 15/08/2020 | 0 | BUILT INDIA | 11.53 | 23.06 | 200 | 0
59 | HOWRAH | Howrah Division | Sinking of Eight (08) Nos DWP ( Mark-II) Hand Tube Wells 100 mm x 40 mm dia 230 mtr deep within Sankrail Panchayat Samity under Howrah Division, PHE Dte in connection with super cyclone YAAS , SM/09352 | Disaster | Work Order for Sinking of Eight (8) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 230 mtr deep within Sankrail Panchayet Samity under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' | 186/HD | 31/01/2022 | 45 | MAITY CONSTRUCTIONS | 7.91 | 7.87 | 100 | 0
60 | HOWRAH | Howrah Division | Sinking of Eight (08) Nos DWP ( Mark-II) Hand Tube Wells 100 mm x 40 mm dia 230 mtr deep within Sankrail Panchayat Samity under Howrah Division, PHE Dte in connection with super cyclone YAAS , SM/09352 | Disaster | Work Order for Sinking of ten (10) nos DWP (Mark-II) Hand Pump Tube well 100mm x 40mm dia 250 mtr deep within different habitation of 178 Uluberia Dakshin Assembly Constituency under Howrah Division PHE Dte. (Group-K). | 2447/HD | 28/11/2022 | 45 | M/S AHAMED CONSTRUCTION | 18.45 | 6.42 | 100 | 0
61 | HOWRAH | Howrah Division | Sinking of Eight (08) Nos DWP ( Mark-II) Hand Tube Wells 100 mm x 40 mm dia 230 mtr deep within Sankrail Panchayat Samity under Howrah Division, PHE Dte in connection with super cyclone YAAS , SM/09352 | Disaster | Material Requisition To Resource Division | 406/HD | 24/02/2022 | 0 | Resource Division | 16.28 | 0 | 0 | 0
62 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-G) No. of House Hold= 110 nos. | 2286/HD | 10/12/2021 | 30 | GHOSH ENTERPRISE. | 4.78 | 4.63 | 96.69 | 0
63 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-D) No. of House Hold= 110 nos. | 2283/HD | 10/12/2021 | 30 | APEX ENGINEERING | 4.74 | 4.67 | 98.55 | 0
64 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-F) No. of House Hold= 110 nos. | 2285/HD | 10/12/2021 | 30 | SUNIL ENTERPRISE | 4.74 | 4.54 | 95.71 | 0
65 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte.(Part-A) No. of House Hold= 110 nos. | 2280/HD | 10/12/2021 | 30 | N. G ENGINEERING | 4.76 | 4.64 | 97.68 | 0
66 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-C) No. of House Hold= 110 nos. | 2282/HD | 10/12/2021 | 30 | S.B. ENTERPRISE | 4.74 | 4.63 | 97.67 | 0
67 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-E) No. of House Hold= 110 nos. | 2284/HD | 10/12/2021 | 30 | DEBABRATA CHAKRABORTY | 4.74 | 4.53 | 95.72 | 0
68 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-B) No. of House Hold= 110 nos. | 2281/HD | 10/12/2021 | 30 | M/S ASHIRBAD (INDIA) | 4.76 | 4.65 | 97.81 | 0
69 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Jagadispur Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-G) No. of House Hold(Approx)= 3500 nos. | 1315/HD | 24/06/2021 | 45 | VISHAL CONSTRUCTION CO. | 176.21 | 266.72 | 167.28 | 0
70 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Uncovered bally jagcha | W/252 | 19/08/2021 | 0 | SUSHANTA MONDAL | 1.03 | 0 | 0 | 0
71 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Uncoverd Bally Jagcha | W/228 | 19/08/2021 | 0 | ASHOKE ENGINEERING WORKS | 4.47 | 0 | 0 | 0
72 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered area of Surface Water Based Water supply project for Bally Jagacha Block | W/133-136 | 09/08/2021 | 0 | NIRMAL UDYOG | 13.94 | 0 | 0 | 0
73 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block | W/365 | 07/10/2021 | 0 | GHOSH ENTERPRISE. | 4.78 | 0 | 0 | 0
74 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS Uncovered Bally Jagacha |  | 03/06/2021 | 0 | MAA TARA CONSTRUCTION | 16.77 | 0 | 0 | 0
75 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block | W/112 | 20/07/2021 | 0 | UNIVERSAL CONSTRUCTION | 3.89 | 0 | 0 | 0
76 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block | W/366 | 07/10/2021 | 0 | GHOSH ENTERPRISE. | 4.81 | 0 | 0 | 0
77 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS uncovered Bally Jagacha | W/137-142 | 09/08/2021 | 0 | USHA CONCERN | 20.51 | 0 | 0 | 0
78 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS Uncovered area Surface Water Based Water supply Project Bally Jagacha Block | W/164 | 09/08/2021 | 0 | PRAGATI CONSTRUCTION & CO | 18.44 | 0 | 0 | 0
79 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block | W/105 | 19/07/2021 | 0 | S.M. CONSTRUCTION | 3.39 | 0 | 0 | 0
80 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block | BP-2021-22-217 | 11/10/2021 | 0 | N.N. CONSTRUCTION | 3.54 | 0 | 0 | 0
81 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block | W/364 | 07/10/2021 | 0 | GHOSH ENTERPRISE. | 4.83 | 0 | 0 | 0
82 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block | W/370 | 07/10/2021 | 0 | MA TARA CONSTRUCTION | 4.66 | 0 | 0 | 0
83 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block | BP-2021-22-184 | 07/10/2021 | 0 | SK ENTERPRISE | 2.21 | 0 | 0 | 0
84 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS Uncovered Bally Jagacha | W/143 | 09/08/2021 | 0 | PRADIP KUMAR JATI | 29.38 | 0 | 0 | 0
85 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Retrofitting Bally Jagacha |  | 28/06/2021 | 0 | S.B. ENTERPRISE | 12.29 | 0 | 0 | 0
86 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block | W/104 | 19/07/2021 | 0 | SAIKAT ENTERPRISE | 3.49 | 0 | 0 | 0
87 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered araes of Surface Water Based Water Supply Project for Bally Jagacha Block | W/106 | 19/07/2021 | 0 | SAIKAT ENTERPRISE | 3.84 | 0 | 0 | 0
88 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block | W/118, 119 | 19/07/2021 | 0 | N. G ENGINEERING | 5.52 | 0 | 0 | 0
89 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Uncovered bally jagcha | W/251 | 19/08/2021 | 0 | ABONTICA ENTERPRISE | 1.59 | 0 | 0 | 0
90 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Uncoverd Bally Jagcha | W/229-233 | 19/08/2021 | 0 | SUSHANTA MONDAL | 7.82 | 0 | 0 | 0
91 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block | W/363 | 07/10/2021 | 0 | GHOSH ENTERPRISE. | 4.37 | 0 | 0 | 0
92 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block | BP-2021-22-186 | 07/10/2021 | 0 | SK ENTERPRISE | 4.84 | 0 | 0 | 0
93 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS of uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block | W/99-103 | 19/07/2021 | 0 | MITHU BUILDERS | 16.75 | 0 | 0 | 0
94 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Scheme Bally Jagacha Block | 107-111 113-117 | 20/07/2021 | 0 | ADITYA HAZRA | 25.5 | 0 | 0 | 0
95 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Uncoverd Bally jagacha | W/250 | 19/08/2021 | 0 | ABONTICA ENTERPRISE | 3.22 | 0 | 0 | 0
96 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Uncovered Bally Jagach | W/159-160 | 19/08/2021 | 0 | MAA TARA CONSTRUCTION | 16.77 | 0 | 0 | 0
97 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block | W/362 | 07/10/2021 | 0 | GHOSH ENTERPRISE. | 4.8 | 0 | 0 | 0
98 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS Uncovered Bally Jagacha Surface Water Based Water Supply Project Bally Jagacha block | W/149-153 | 09/08/2021 | 0 | S.B. ENTERPRISE | 12.29 | 0 | 0 | 0
99 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Uncovered bally jagcha | W/249 | 19/08/2021 | 0 | ABONTICA ENTERPRISE | 1.94 | 0 | 0 | 0
100 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block | W/368 | 07/10/2021 | 0 | MA TARA CONSTRUCTION | 4.81 | 0 | 0 | 0
101 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block | BP-2021-22-182 | 07/10/2021 | 0 | GHOSH ENTERPRISE. | 4.14 | 0 | 0 | 0
102 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Based Water Supply Project Bally Jagach Block | W/400 | 11/10/2021 | 0 | M/S. SREE HARI CONSTRUCTION | 3.33 | 0 | 0 | 0
103 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block | BP-2021-22-187 | 07/10/2021 | 0 | SAIKAT ENTERPRISE | 4.48 | 0 | 0 | 0
104 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Supply of different types of Specials for conveyance of Treated Water from Off Take Point (Phase-I) to GLR (Phase-II) and LDS at Zone-1&2 under Bally-Jagacha (Phase-II) Surface based water supply Project under Howrah Division PHE Dte. (Part-B) | 416/HD | 11/02/2021 | 15 | GHOSH ENTERPRISE. | 4.5 | 6.34 | 140.77 | 0
105 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Supply of different types of Specials for conveyance of Treated Water from Off Take Point (Phase-I) to GLR (Phase-II) and LDS at Zone-1&2 under Bally-Jagacha (Phase-II) Surface based water supply Project under Howrah Division PHE Dte. | 418/HD | 11/02/2021 | 15 | GHOSH ENTERPRISE. | 1.16 | 0.83 | 71.06 | 0
106 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Cutting of concrete road with restoration of concrete road for laying of UPVC Pipe (90 mm dia) Zone-I of surface water based water supply Project (Phase-II) for Bally Jagacha Block under Howrah Division PHE Dte. (Length of Road = 1300 m) (Part-6) | 334/HD | 05/02/2021 | 10 | SK ENTERPRISE | 4.26 | 2.41 | 56.47 | 0
107 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Cutting of concrete road with restoration of concrete road for laying of UPVC Pipe (90 mm dia) Zone-II of surface water based water supply Project (Phase-II) for Bally Jagacha Block under Howrah Division PHE Dte. (Length of Road = 1300 Mtr) (Part-3) | 341/HD | 05/02/2021 | 10 | SK ENTERPRISE | 4.21 | 3.05 | 72.51 | 0
108 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Cutting of concrete road with restoration of concrete road for laying of UPVC Pipe (90 mm dia) Zone-II of surface water based water supply Project (Phase-II) for Bally Jagacha Block under Howrah Division PHE Dte. (Length of Road = 1250Mtr) (Part-4) | 342/HD | 05/02/2021 | 10 | SK ENTERPRISE | 4.05 | 3.3 | 81.41 | 0
109 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara. G.P Area) Zone-10 Length= 539.00mtr.(PART-C) | 1104/HD | 25/09/2020 | 30 | PRADIP KUMAR JATI | 4.04 | 0 | 0 | 0
110 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Supply of different types of Specials for conveyance of Treated Water from Off Take Point (Phase-I) to GLR (Phase-II) and LDS at Zone-1&2 under Bally-Jagacha (Phase-II) Surface based water supply Project under Howrah Division PHE Dte. (Part-A) | 415/HD | 11/02/2021 | 15 | MA TARA CONSTRUCTION | 4.68 | 4.83 | 103.2 | 0
111 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Barbed wire fencing with angle for Boundary wall & 450mm dia Sluice valve chamber at Lakhanpur CWR site & Raghabpur site of Bally jagacha (phase-II) Surface based water supply scheme under Howrah Division P.H.E. Dte. | 541/HD | 25/02/2021 | 30 | SK ENTERPRISE | 3.56 | 0.76 | 21.39 | 0
112 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 660.00mtr.(PART-4) | 513/HD | 25/02/2021 | 30 | MENOKA ENGINEERING WORKS | 3.65 | 2.41 | 66.07 | 0
113 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 649.00mtr.(PART-5) | 514/HD | 25/02/2021 | 30 | MENOKA ENGINEERING WORKS | 3.51 | 2.37 | 67.68 | 0
114 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Restoration of road in uncovered areas in Zone-1 & 2. under Bally Jagacha (Phase-II) Surface based water supply Project under Howrah Division PHE Dte. Howrah Length- 750m. (Part-I) | 1368/HD | 29/06/2021 | 30 | SK ENTERPRISE | 4.33 | 3.42 | 78.94 | 0
115 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 732.00mtr.(PART-6) | 515/HD | 25/02/2021 | 30 | MENOKA ENGINEERING WORKS | 4.22 | 2.62 | 62.05 | 0
116 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chakpara Anandanagar Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-F) No of Household (Approx)= 5000 nos | 2388/HD | 27/12/2021 | 30 | MAHAVIR PUMPS MFG.PVT.LTD | 2.48 | 2.48 | 100 | 0
117 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Jagadishpur Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-G) No of Household (Approx)= 3500 nos | 2389/HD | 27/12/2021 | 30 | VISHAL CONSTRUCTION CO. | 1.74 | 1.74 | 100 | 0
118 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Nischinda Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-A) No of Household (Approx)= 4500 nos | 2384/HD | 27/12/2021 | 30 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 2.24 | 2.06 | 91.93 | 0
119 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Bally Gram Panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. No. of House Hold= 5000 nos. | 57/HD | 10/01/2022 | 150 | N. G ENGINEERING | 167.83 | 62.04 | 36.97 | 0
120 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Duegapur-Abhoynagar-II Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-D) No of Household (Approx)= 4500 nos | 2387/HD | 27/12/2021 | 30 | ALOK ENTERPRISE | 2.24 | 1.4 | 62.62 | 0
121 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Sapuipara Basukati Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-B) No of Household (Approx)= 5500 nos | 2385/HD | 27/12/2021 | 30 | JAYANTA KUMAR MONDAL | 2.73 | 0 | 0 | 0
122 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chamrail Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-1) No of Household (Approx)= 850 nos | 2390/HD | 27/12/2021 | 30 | M/S ASHIRBAD (INDIA) | 0.42 | 0.42 | 100 | 0
123 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chamrail Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-2) No of Household (Approx)= 850 nos | 2391/HD | 27/12/2021 | 30 | S.B. ENTERPRISE | 0.42 | 0.42 | 100 | 0
124 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chamrail Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-3) No of Household (Approx)= 850 nos | 2392/HD | 27/12/2021 | 30 | N. G ENGINEERING | 0.42 | 0.42 | 100 | 0
125 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chamrail Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-4) No of Household (Approx)= 950 nos | 2393/HD | 27/12/2021 | 30 | GHOSH ENTERPRISE. | 0.47 | 0.47 | 100 | 0
126 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Construction of MS Pipe Line at Lakshmanpur Boosting Station Site under Bally Jagacha Surface Based Water Supply Project (Phase-II) under Howrah Division, PHE Dte. | 306/HD | 15/02/2022 | 20 | GHOSH ENTERPRISE. | 3.05 | 0 | 0 | 0
127 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 809.00mtr.(PART-1)(Near Burma colony) | 653/HD | 23/03/2022 | 30 | PRADIP KUMAR JATI | 3.05 | 3.03 | 99.55 | 0
128 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 913.00mtr. (PART-4) | 656/HD | 23/03/2022 | 30 | MAA TARA CONSTRUCTION | 2.94 | 2.92 | 99.35 | 0
129 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Bally G.P Area) Zone-6A & 7 Length= 715.00mtr.(PART-3)(Location Bally near 7no pole) | 657/HD | 23/03/2022 | 30 | SAIKAT ENTERPRISE | 3.32 | 3.22 | 97.04 | 0
130 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Bally G.P Area) Zone-6A & 7 Length= 385.00mtr.(PART-4)(Location Bally Ghosh para) | 658/HD | 23/03/2022 | 30 | SAIKAT ENTERPRISE | 2.08 | 2.03 | 97.36 | 0
131 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 792.00mtr.(PART-2)(Near Chakpara Milony club) | 654/HD | 23/03/2022 | 30 | PRADIP KUMAR JATI | 3.18 | 2.63 | 82.78 | 0
132 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Withdrawing & relaying in the damaged part of pipeline for extension of Saorapotakhal(From Anandanagar sitala tala to Jhautala more) at Chakpara Anandanagar G.P. areas of Surface water based water supply project for Bally-Jagacha block,(Phase-1) under Howrah Division PHE Dte. Zone-9( N.P-197 to 15) Length= 1600.00mtr. | 476/HD | 04/03/2022 | 45 | S.B. ENTERPRISE | 15.39 | 5.57 | 36.17 | 0
133 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Supply of Materials at Lakshmanpur Boosting Station Site under Bally Jagacha Surface based water supply project (Phase-II) under Howrah Division, PHE Dte. | 698/HD | 24/03/2022 | 15 | SK ENTERPRISE | 1.69 | 1.59 | 94.61 | 0
134 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 440.00mtr.(PART-5)(Near Chakpara Market & Khal par) | 652/HD | 23/03/2022 | 30 | BISWAJIT SAMANTA | 2.49 | 2.11 | 84.67 | 0
135 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 796.00mtr.(PART-3)(Near Anandanagar khal par) | 655/HD | 23/03/2022 | 30 | MAA TARA CONSTRUCTION | 3.15 | 3.14 | 99.9 | 0
136 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Sapuipara Basukati G.P Area) Zone-7,8 Length= 736.00mtr.(PART-J) | 1179/HD | 30/09/2020 | 30 | NIRMAL UDYOG | 4.5 | 1.76 | 39.12 | 0
137 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Material Requisition To Resource Division | 2113/HD | 09/11/2022 | 0 | Resource Division | 61.6 | 0 | 0 | 0
138 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 743.00mtr.(PART-3) | BP-2021-22-344 | 28/02/2022 | 0 | N. G ENGINEERING | 3.23 | 0 | 0 | 0
139 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-2. Grampanchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-D) No. of House Hold(Approx)= 4500 nos | BP-2021-22-350 | 28/02/2022 | 0 | ALOK ENTERPRISE | 76.01 | 0 | 0 | 0
140 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-1. Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-C) No. of House Hold(Approx)= 4000 nos. | BP-2021-22-419 | 21/03/2022 | 0 | GHOSH CONCERN | 39.01 | 0 | 0 | 0
141 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Sapuipara G.P Area) Zone-7/8 Length= 1100.00mtr.(PART-1) | BP-2021-22-455 | 26/03/2022 | 0 | CHOWDHUARY & CO | 3.51 | 0 | 0 | 0
142 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 737.00mtr.(PART-2) | BP-2021-22-345 | 28/02/2022 | 0 | N. G ENGINEERING | 3.26 | 0 | 0 | 0
143 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Railway permission | BP-2022-23-84 | 23/06/2022 | 0 | EASTERN RAILWAY, HOWRAH DIVISION | 9.05 | 0 | 0 | 0
144 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Sapuipara Basukati Gram panchyetunder Bally Jagachha Block under Howrah Division, PHE Dte. (Part-B) No. of House Hold(Approx)= 5500 nos. | BP-2022-23-28 | 11/05/2022 | 0 | JAYANTA KUMAR MONDAL | 2.73 | 0 | 0 | 0
145 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chamrail Gram panchyet under ballyjagachha Block under Howrah Division, PHE Dte. (Part-3) No. of House Hold= 850 nos | BP-2021-22-349 | 28/02/2022 | 0 | N. G ENGINEERING | 34.98 | 0 | 0 | 0
146 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Indent of materials | BP-2021-22-309 | 02/02/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 36.59 | 0 | 0 | 0
147 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chamrail Gram panchyet under ballyjagachha Block under Howrah Division, PHE Dte. (Part-2) No. of House Hold= 850 nos. | BP-2021-22-347 | 28/02/2022 | 0 | M/S ASHIRBAD (INDIA) | 34.95 | 0 | 0 | 0
148 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 743.00mtr.(PART-8) | BP-2021-22-342 | 28/02/2022 | 0 | M/S ASHIRBAD (INDIA) | 3.21 | 0 | 0 | 0
149 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Sapuipara G.P Area) Zone-7/8 Length= 1100.00mtr.(PART-2) | BP-2021-22-456 | 26/03/2022 | 0 | CHOWDHUARY & CO | 3.48 | 0 | 0 | 0
150 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Special repairing works in different location( at Lock down period) in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Bally G.P Area) Zone-6A, 6B.Length=66m. | BP-2022-23-31 | 11/05/2022 | 0 | CONSCORP | 0.48 | 0 | 0 | 0
151 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-1. Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-C) No. of House Hold(Approx)= 4000 nos. | BP-2021-22-323 | 18/02/2022 | 0 | GHOSH CONCERN | 116.13 | 0 | 0 | 0
152 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chamrail Gram panchyet under ballyjagachha Block under Howrah Division, PHE Dte. (Part-1) No. of House Hold= 850 nos. | BP-2021-22-348 | 28/02/2022 | 0 | MENOKA ENGINEERING WORKS | 34.94 | 0 | 0 | 0
153 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 738.00mtr.(PART-9) | BP-2021-22-341 | 28/02/2022 | 0 | M/S ASHIRBAD (INDIA) | 3.52 | 0 | 0 | 0
154 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Nischinda Gram panchyet under BallyJagachha Block under Howrah Division, PHE Dte. (Part-A) No. of House Hold(Approx)=4500 nos. | BP-2021-22-360 | 28/02/2022 | 0 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 104.97 | 0 | 0 | 0
155 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chakpara Gram panchyet under BallyJagachha Block under Howrah Division, PHE Dte. (Part-F) No. of House Hold(Approx)=5000 nos. | BP-2021-22-485 | 30/03/2022 | 0 | MAHAVIR PUMPS MFG.PVT.LTD | 10.99 | 0 | 0 | 0
156 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chamrail Gram panchyet under ballyjagachha Block under Howrah Division, PHE Dte. (Part-4) No. of House Hold= 950 nos. | BP-2021-22-351 | 28/02/2022 | 0 | GHOSH ENTERPRISE. | 13.09 | 0 | 0 | 0
157 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Bally Gram Panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. No. of House Hold= 5000 nos. | BP-2021-22-478 | 27/03/2022 | 0 | N. G ENGINEERING | 96.53 | 0 | 0 | 0
158 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Sapuipara Basukati Gram panchyetunder Bally Jagachha Block under Howrah Division, PHE Dte. (Part-B) No. of House Hold(Approx)= 5500 nos. | W/796 | 03/03/2022 | 0 | JAYANTA KUMAR MONDAL | 24.79 | 0 | 0 | 0
159 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 732.00mtr. (PART-1) | BP-2021-22-346 | 03/03/2022 | 0 | N. G ENGINEERING | 3.43 | 0 | 0 | 0
160 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Working area Development for Administrative Building (At Salap Zone-VII) for Surface Water Based Water Supply Scheme Bally Jagacha (Phase-II) under Howrah Division, PHE Dte. | 2276/HD | 10/12/2021 | 21 | KRISHNA CONSTRUCTION | 3.14 | 3.13 | 100 | 0
161 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface Water Based Project for Bally-Jagacha block under Howrah Division, PHE Dte (Chakpara, G.P. Area) Zone-10 Length=900.00mtr. | 2272/HD | 10/12/2021 | 30 | USHA CONCERN | 4.13 | 0.91 | 30.88 | 0
162 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Dismantling of concrete road for laying of pipe line in Zone-4 under Bally Jagacha (Phase-II) Surface based water supply Project under Howrah Division, PHE Dte. (Part-A) | 1139/HD | 27/05/2022 | 20 | A.G.S ENTERPRISE | 3.93 | 0 | 0 | 0
163 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Dismantling of concrete road for laying of pipe line in Zone-4 under Bally Jagacha (Phase-II) Surface based water supply Project under Howrah Division, PHE Dte. (Part-B) | 1140/HD | 27/05/2022 | 20 | A.G.S ENTERPRISE | 3.75 | 0 | 0 | 0
164 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Detail study of existing Bally Jagacha Surface Based Water Supply Scheme (Phase-1) to develop Innovative Sustainable Solutions which are field relevant and address the challenges faced by the consumer, under Howrah Division, PHE Dte. | 2211/HD | 02/11/2022 | 90 | AJIVAM WATER PRIVATE | 34.09 | 34.09 | 100 | 100
165 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Measuring water flow of pipe under the ground level by portable flow meter (Endress & Hauser make) after thorough cleaning the outer surface of the pipe line and installing the measuring device as per manufacturer¿s procedure including mobilization of portable flow meter by hired vehicle at point to point engaging skilled technician and labours for pipe line size up to 450mm to 900mm diameter. | 2054/HD | 28/09/2022 | 15 | EASTERN INDIA SALES & SERVICE | 0.28 | 0.28 | 100 | 0
166 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Measuring water flow of pipe under the ground level by portable flow meter (Endress & Hauser make) after thorough cleaning the outer surface of the pipe line and installing the measuring device as per manufacturer¿s procedure including mobilization of portable flow meter by hired vehicle at point to point engaging skilled technician and labours for pipe line size up to 400mm diameter. | 2009/HD | 27/09/2022 | 15 | EASTERN INDIA SALES & SERVICE | 1.26 | 1.26 | 100 | 0
167 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Construction of Boundary Wall at Tube Well Site of Chakpara Anandanagar Football Ground under Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte.(12M X12M) | 569/HD | 13/02/2023 | 30 | FUTURE CONSTRUCTION | 3.98 | 0 | 0 | 0
168 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Restoration of road damaged for providing FHTC Works in Nischinda G.P in Bally Jagacha Block under Howrah Division, PHE Dte. (Part-C) | 1891/HD | 15/09/2022 | 10 | M/S HOWRAH CONSTRUCTION | 4.53 | 4.33 | 95.5 | 0
169 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Interconnection from Tube well to Distribution line at Chakpara site in Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. | 573/HD | 13/02/2023 | 30 | S.B. ENTERPRISE | 1.68 | 0 | 0 | 0
170 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Special repairing works in different location( at Lock down period) in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Nischinda G.P Area) Zone-6A, 6B. | 1172/HD | 30/09/2020 | 30 | MENOKA ENGINEERING WORKS | 1.77 | 1.27 | 100 | 0
171 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Nischinda Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-A) No. of House Hold(Approx)=4500 nos. | 1310/HD | 24/06/2021 | 45 | JDJ ENTERPRISE A UNIT OF JDJ TRADERS PRIVATE LIMITED | 198.75 | 68.97 | 100 | 0
172 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Sapuipara Basukati Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-B) No. of House Hold(Approx)= 5500 nos. | 1311/HD | 24/06/2021 | 45 | JAYANTA KUMAR MONDAL | 239.97 | 204.66 | 100 | 0
173 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-2. Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-D) No. of House Hold(Approx)= 4500 nos | 1313/HD | 24/06/2021 | 45 | ALOK ENTERPRISE | 232 | 37.12 | 100 | 0
174 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Jagadispur Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. No of House hold-1600 Nos | 2429/HD | 29/12/2021 | 45 | N. G ENGINEERING | 54.6 | 51.86 | 100 | 0
175 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Remaining part of laying distribution system of Pipe water supply at Zone-III/IV.(pal para,mondal para, kote para, Rupnagar)for Surface water based water supply project for Bally-Jagacha(PH-II), under Howrah Division, PHE Dte.(Part-B). | 817/HD | 08/04/2022 | 30 | M/S MOINAK POREL | 19.5 | 0 | 0 | 100
176 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Withdrawing & relaying distribution system pipe line from Makaltala to Bally station (N.P.- 155 to 4) in the uncovered areas of Surface water based water supply project for Bally Jagacha block, under Howrah Division PHE Dte.(D.A-1 G.P Area) Zone-5 Length= 1.05km.nos. | 818/HD | 08/04/2022 | 30 | BISWAJIT SAMANTA | 7.94 | 7.25 | 100 | 100
177 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Sinking of 2 (two) nos PVC big dia Tube well 300 mm x 200 mm dia of 240 mtr deep near i)Chamrail OHR Site Zone-13 & ii) Bally Jagacha Block Office OHR Site Zone-12 under Bally-Jagacha Surface Based W/S scheme(Phase-I) under Howrah Division P.H.E Dte. | 1597/HD | 01/08/2022 | 30 | MUNSHI ENTERPRISE | 32.38 | 25.21 | 100 | 0
178 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(D.A -2. G.P Area) Zone-1. Length= 55.00 mtr. | 1867/H.D | 12/09/2022 | 10 | SKYLINE CONSTRUCTION | 0.48 | 0.4 | 100 | 0
179 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Interconnection from Existing Tube well to Distribution line at Baigachi (Zone-14) in Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. | 516/HD | 09/02/2023 | 30 | SUNIL ENTERPRISE | 2.71 | 1.24 | 100 | 100
180 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Interconnection from Tube well to Jagadispur OHR in Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. | 574/HD | 13/02/2023 | 30 | S.B. ENTERPRISE | 2.2 | 1.27 | 100 | 100
181 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Construction of Clorination Room ( 5.40m x 3.60 m) at Bhaskur Zone-III OHR Site under Bally jagacha(phase-2) surface Based water supply project under Howrah Division, P.H.E. Dte. at Lakhanpur CWR Site under Bally jagacha(phase-2) surface Based water supply project under Howrah Division, P.H.E. Dte. | 515/HD | 09/02/2023 | 60 | KUNDU CONSTRUCTION | 6.16 | 5.82 | 100 | 100
182 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Interconnection from Tube well to Bally jagacha OHR in Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. | 572/HD | 13/02/2023 | 30 | MA-DURGA ENTERPRISE | 1.78 | 0.74 | 100 | 100
183 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for two months from 01/09/2023 to 31/10/2023) under Howrah Division, PHE Dte.. | 3134/HD | 29/08/2023 | 61 | INDRAJIT GHOSAL | 0.8 | 0.54 | 100 | 30
184 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-1. Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-C) No. of House Hold(Approx)= 4000 nos. | 1312/HD | 24/06/2021 | 45 | GHOSH CONCERN | 176.91 | 12.56 | 100 | 0
185 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Excavation of Pipe Trenches in different location for Testing of Rising main pipe line under Bally Jagacha (PH-I) Water supply Project in Bally Jagacha Block under Howrah Sadar Sub- Division, P.H.E. Dte. | 1869/HD | 12/09/2022 | 10 | S.B. ENTERPRISE | 2.39 | 2.01 | 100 | 0
186 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Material Requisition To Resource Division | 2375/HD | 24/12/2021 | 0 | Resource Division | 16.5 | 0 | 0 | 0
187 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Material Requisition To Resource Division | 435/HD | 28/02/2022 | 0 | Resource Division | 21.45 | 0 | 0 | 0
188 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Eastern Railway, Howrah Division | BP-2021-22-623 | 30/03/2023 | 0 | EASTERN RAILWAY, HOWRAH DIVISION | 1.11 | 0 | 0 | 0
189 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Sample Test |  | 24/03/2023 | 0 | NATIONAL TEST HOUSE | 0.09 | 0 | 0 | 0
190 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | National Test House | BP-2022-23-691 | 16/03/2023 | 0 | NATIONAL TEST HOUSE | 0.09 | 0 | 0 | 0
191 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Bally Jagacha Phase -I |  | 20/01/2023 | 0 | EASTERN RAILWAY, HOWRAH DIVISION | 15.58 | 0 | 0 | 0
192 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Railway Permission | BP-2022-23-624 | 30/03/2023 | 0 | EASTERN RAILWAY, HOWRAH DIVISION | 11.93 | 0 | 0 | 0
193 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | 1. Clear water rising main from GLR to different Zonal OHR, 2. Laying distribution system of piped water supply at (Zone-VI) and 3. Construction of Administrative Building, Store & Stack Yard at Domjur Boosting Station for surface water based water supply scheme for Bally-Jagacha (Phase-II) under Howrah Division, P.H.E. Dte. | 1597/HD | 09/11/2020 | 546 | SUBHASH BOSE | 267 | 27.55 | 46.25 | 50
194 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for providing Functional Household Tap Connection(FHTC) from existing distribution system at uncovered areas of Durgapur Abhoynagar-1 & 2 Gram Panchyet under bally Jagachha Block under Howrah Division, PHE Dte.(Part-2) | 1051/HD | 15/03/2023 | 60 | SONAR BANGLA ENTERPRISE | 6.71 | 4.54 | 67.61 | 70
195 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying of Distribution system for uncovered areas at Boluhati mouza(Booth no-7,8,9), under Bally Jagacha (Ph-II) Surface based Water Supply Scheme at Domjur Block under Howrah Division, P.H.E. Dte. | 4577/HD | 18/12/2023 | 30 | CONSTRUCTION CORNER | 10.25 | 0 | 0 | 0
196 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for the period from 01/10/2023 to 30/11/2023) | 3482/HD | 29/09/2023 | 61 | SUMANTA DEY | 0.79 | 0.51 | 65.12 | 100
197 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (from 01/01/2024 to 31/03/2024) under Howrah Division, PHE Dte. | 4765/HD | 29/12/2023 | 91 | INDRAJIT GHOSAL | 0.98 | 0.81 | 82.46 | 50
198 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for the period from 01/12/2023 to 31/01/2024) | 4303/HD | 30/11/2023 | 62 | SUMANTA DEY | 0.79 | 0.63 | 78.98 | 100
199 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Construction of Retaining Wall at Narna Zone-V OHR Site under Bally Jagacha(phase-II) surface Based water supply project under Howrah Division, P.H.E. Dte. | 3463/HD | 02/08/2024 | 30 | GUPTA ENTERPRISE | 4.76 | 0 | 0 | 0
200 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Construction of Chlorination Room (5.5m x 4.5m) at Narna Zone-V OHR Site under Bally Jagacha(Phase-2) Surface Based water supply project under Howrah Division, P.H.E. Dte. | 4833/HD | 20/11/2024 | 45 | GUPTA ENTERPRISE | 4.85 | 0 | 0 | 0
201 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Construction of Guard Room with WC (4.35m X 3.60m) at Narna Zone-V OHR Site under Bally Jagacha(Ph-II) Surface Based water supply project under Howrah Division, P.H.E. Dte. | 4834/HD | 20/11/2024 | 45 | GUPTA ENTERPRISE | 4.85 | 0 | 0 | 0
202 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/02/2024 to 31/03/2024) | 420/HD | 31/01/2024 | 60 | AVINABA ENGINEERING CONCERN | 0.79 | 0.73 | 91.35 | 0
203 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/04/2024 to 31/05/2024) | 1672/HD | 28/03/2024 | 61 | AVINABA ENGINEERING CONCERN | 0.79 | 0.76 | 96.29 | 0
204 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/04/2024 to 30/06/2024) under Howrah Division, PHE Dte. | 1363/HD | 15/03/2024 | 91 | MD KADIR | 0.99 | 0.96 | 96.49 | 0
205 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/07/2024 to 30/09/2024) under Howrah Division, PHE Dte. | 2924/HD | 27/06/2024 | 92 | MD KADIR | 1 | 0.96 | 96.78 | 0
206 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/08/2024 to 30/09/2024) | 3362/HD | 30/07/2024 | 61 | AVINABA ENGINEERING CONCERN | 0.79 | 0.78 | 97.86 | 0
207 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/08/2024 to 31/10/2024) under Howrah Division, PHE Dte. | 3379/HD | 30/07/2024 | 92 | SUMANTA DEY | 1 | 0.82 | 82.5 | 0
208 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/05/2024 to 31/07/2024) under Howrah Division, PHE Dte. | 2219/HD | 30/04/2024 | 92 | SUMANTA DEY | 1 | 0.91 | 91.76 | 0
209 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/06/2024 to 31/07/2024) | 2566/HD | 30/05/2024 | 61 | AVINABA ENGINEERING CONCERN | 0.79 | 0.78 | 98.67 | 0
210 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Construction of partition wall and Earth filling in passage at Narna Zone-V OHR Site under Bally Jagacha(phase-II) surface Based water supply project under Howrah Division, P.H.E. Dte. | 3464/HD | 02/08/2024 | 30 | GUPTA ENTERPRISE | 4.48 | 0 | 0 | 0
211 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chakpara Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-F) No. of House Hold(Approx)=5000 nos. | 1314/HD | 24/06/2021 | 45 | MAHAVIR PUMPS MFG.PVT.LTD | 220.68 | 158.01 | 142.53 | 100
212 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Duegapur-Abhoynagar-I Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-C) No of Household (Approx)= 4000 nos | 2386/HD | 27/12/2021 | 30 | GHOSH CONCERN | 1.98 | 0 | 0 | 100
213 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Sinking of 2 (two) nos PVC big dia Tube well 300 mm x 200 mm dia of 240 mtr deep near i)Bally Ghosh Para OHR Site Zone-6A & ii)Jagadishpur OHR Site Zone-14 under BallyJagacha Surface Based W/S scheme (Phase-I) under Howrah Division P.H.E Dte. | 1596/HD | 01/08/2022 | 30 | MUNSHI ENTERPRISE | 32.38 | 24.54 | 100 | 30
214 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Construction of Pump House (5.40m x 3.60 m) at Tube Well Site of Chakpara Anandanagar Football Ground under Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. | 571/HD | 13/02/2023 | 60 | MAITY CONSTRUCTIONS | 6.12 | 5.82 | 100 | 100
215 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Providing Functional Household Tap Connection(FHTC) from existing distribution system at uncovered areas of Durgapur Abhoynagar-1 & 2 Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte.(Part-1) | 1050/HD | 15/03/2023 | 90 | M/S SUPROVAT GHOSH | 6.79 | 6.75 | 100 | 100
216 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface Based Water Supply Project for Bally-Jagacha Block, under HowrahDivision,PHEDte. (D.A-1G.PArea) Zone-5 | 1707/HD | 24/04/2023 | 10 | S.B. ENTERPRISE | 0.88 | 0.85 | 100 | 100
217 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Carrying charges office CE Office (HQ) NS Building to Bally WTP Site & WTP Site to Howrah Division office under Howrah Division, PHE Dte. | 1708/HD | 24/04/2023 | 7 | MENOKA ENGINEERING WORKS | 0.82 | 0.82 | 100 | 100
218 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Work Order for Adopting Jack Pushing of 813 mm Dia 10 mm thick M.S pipe as Casing to Cross Water carrier Pipe on Tentulkuli rail crossing work of Bally Jagacha (PH-II) Surface Water Supply Scheme under Howrah Division P.H.E. Dte. | 1963/HD | 11/05/2023 | 45 | SUBHASH BOSE | 95.69 | 95.69 | 100 | 100
219 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Development of Road at Pakuria OHR in Zone-VI under Bally Jagacha (PH-II) Surface water supply scheme under Howrah Division, PHE Dte. | 2818/HD | 03/08/2023 | 15 | M/S HOWRAH CONSTRUCTION | 0.88 | 0.86 | 100 | 100
220 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation Order for Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme Government of West Bengal (for two months from 01/11/2023 to 31/12/2023) under Howrah Division, PHE Dte.. | 3902/HD | 30/10/2023 | 61 | INDRAJIT GHOSAL | 0.8 | 0.52 | 100 | 50
221 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying of Distribution system at uncovered areas of Daffarpur mouza(part no-18/19) under Bally Jagacha (Ph-II) Surface based Water Supply Scheme at Domjur Block under Howrah Division, P.H.E. Dte. | 4437/HD | 08/12/2023 | 30 | USHA CONCERN | 12.51 | 10.34 | 100 | 100
222 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Bally Jagacha Block of Howrah Sadar Sub Division under Howrah Division PHE Dte. | 845/HD | 22/02/2024 | 15 | M&M GRAPHICS | 2.04 | 2.04 | 100 | 100
223 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Restoration of damaged concrete roads due to laying of pipe line at Salap 1 & 2 GP of Bally-Jagacha surface based water supply scheme Phase-II under Howrah Division PHE Dte. (Part-B). | 1316/HD | 14/03/2024 | 60 | BISWAJIT SAMANTA | 11.22 | 0 | 0 | 100
224 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying Distribution Pipeline For Uncovered area at Lakshmanpur (Zone-I) of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. | 1154/HD | 07/03/2024 | 226 | SAIKAT ENTERPRISE | 31.53 | 27.63 | 87.68 | 100
225 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Material Requisition To Resource Division | 467/HD | 02/02/2024 | 0 | Resource Division | 5.18 | 0 | 0 | 0
226 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Material Requisition To Resource Division | 134/HD | 10/01/2024 | 0 | Resource Division | 12.94 | 0 | 0 | 0
227 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Material Requisition To Resource Division | 467/HD | 02/02/2024 | 0 | Resource Division | 1.49 | 0 | 0 | 0
228 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Material Requisition To Resource Division | 3594/HD | 13/08/2024 | 0 | Resource Division | 5.64 | 0 | 0 | 0
229 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Material Requisition To Resource Division | 467/HD | 02/02/2024 | 0 | Resource Division | 2.19 | 0 | 0 | 0
230 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/02/2024 to 30/04/2024).¿ under Howrah Division, PHE Dte. | 421/HD | 31/01/2024 | 90 | SUMANTA DEY | 1 | 0.86 | 86.6 | 20
231 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/10/2024 to 31/12/2024) under Howrah Division, PHE Dte. | 4365/HD | 30/09/2024 | 92 | MD KADIR | 1 | 0.92 | 91.92 | 0
232 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/12/2024 to 31/01/2025) | 4960/HD | 29/11/2024 | 62 | AVINABA ENGINEERING CONCERN | 0.79 | 0.78 | 98.85 | 0
233 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/01/2025 to 31/03/2025) under Howrah Division, PHE Dte. | 5417/HD | 30/12/2024 | 90 | MD KADIR | 1 | 0.94 | 94.09 | 0
234 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying Distribution Pipeline For Uncovered area at Jotgiri (Zone-I) of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. | 1244/HD | 12/03/2024 | 450 | COSMO ENTERPRISE | 28.36 | 20.7 | 72.97 | 100
235 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/10/2024 to 30/11/2024) | 4188/HD | 26/09/2024 | 61 | AVINABA ENGINEERING CONCERN | 0.79 | 0.63 | 79.09 | 0
236 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/04/2025 to 30/06/2025) under Howrah Division, PHE Dte. | 1627/HD | 26/03/2025 | 91 | MD KADIR | 1 | 0.64 | 64.09 | 0
237 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/11/2024 to 31/01/2025) under Howrah Division, PHE Dte. | 4627/HD | 30/10/2024 | 92 | SUMANTA DEY | 1 | 0.86 | 85.88 | 0
238 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/05/2025 to 31/07/2025) under Howrah Division, PHE Dte. | 2103/HD | 29/04/2025 | 92 | SUMANTA DEY | 0.99 | 0.3 | 30.28 | 0
239 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/02/2025 to 30/04/2025) under Howrah Division, PHE Dte. | 699/HD | 30/01/2025 | 90 | SUMANTA DEY | 0.99 | 0.83 | 83.75 | 0
240 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/02/2025 to 31/03/2025) | 640/HD | 28/01/2025 | 59 | AVINABA ENGINEERING CONCERN | 0.79 | 0.76 | 95.23 | 0
241 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/04/2025 to 31/05/2025) | 1626/HD | 26/03/2025 | 61 | AVINABA ENGINEERING CONCERN | 0.79 | 0.76 | 96.7 | 0
242 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/07/2025 to 30/09/2025) under Howrah Division, PHE Dte. | 2952/HD | 26/06/2025 | 92 | MD KADIR | 1 | 0 | 0 | 0
243 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bally Jagacha & Panchla Block) | 4118/HD | 14/10/2025 | 30 | JHARNA ENTERPRISE | 4.79 | 0 | 0 | 0
244 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Land Development for Approach to OHR Site at Narna Zone-V of Surface water supply scheme Bally Jagacha (Phase-II) under Howrah Division, PHE Dte. | 2819/HD | 03/08/2023 | 15 | GUPTA ENTERPRISE | 0.79 | 0 | 0 | 100
245 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying of Distribution system at Narna mouza under Bally Jagacha (Ph-II) Surface based Water Supply Scheme at Domjur Block under Howrah Division, P.H.E. Dte. | 4468/HD | 12/12/2023 | 30 | PBA INFRASTRUCTURE | 11.44 | 0 | 0 | 100
246 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying of Distribution system at uncovered areas of Pipli & Gayespur mouza under Bally Jagacha (Ph-II) Surface based Water Supply Scheme at Domjur Block under Howrah Division, P.H.E. Dte. | 4363/HD | 05/12/2023 | 135 | SAIKAT ENTERPRISE | 14.52 | 10.42 | 71.91 | 100
247 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Special repairing for Distribution system and brusting of rising main at Lakshmanpur, Jotgiri & Narna of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. | 3465/HD | 02/08/2024 | 15 | COSMO ENTERPRISE | 3.91 | 0 | 0 | 100
248 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying Distribution Pipeline For Uncovered area at Zone-IV of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. | 2892/HD | 26/06/2024 | 240 | S.B ENTERPRISE | 18.4 | 0 | 0 | 100
249 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4817/HD | 19/11/2024 | 510 | TECH VISION | 8.36 | 0.82 | 100 | 95
250 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Laying Distribution Pipeline For Uncovered area at Zone-VII (Salap-2 GP) of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. | 1133/HD | 06/03/2024 | 544 | UNIVERSAL CONSTRUCTION | 38.43 | 29.21 | 76.03 | 90
251 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Supplying,fitting,fixing and erecting of Display Board at Tantulkuli PWSS, and Joypur CT PWSS of Bally Jagacha block ,under Howrah Division, P.H.E Dte. | 234/HSSD | 28/02/2025 | 15 | JHARNA ENTERPRISE | 0.57 | 0 | 0 | 100
252 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) , SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/10/2025 to 31/12/2025) under Howrah Division, PHE Dte. | 4021/HD | 25/09/2025 | 92 | MD KADIR | 1 | 0 | 0 | 0
253 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Work Order for Preparation of DPR for new piped water supply scheme of Haturie Kandarpur PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 248/HD | 07/02/2022 | 15 | STEELCONC AND ASSOCIATES | 3.61 | 3.61 | 100 | 0
254 | HOWRAH | Central Drilling | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 300 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCHEME (REPLACEMENT TW-I), BASANTI BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. | 57/CDD | 08/04/2022 | 30 | PADMA ENGINEERING & CO. | 14.55 | 12.42 | 100 | 0
255 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Material Requisition To Resource Division | 2639/HD | 09/12/2022 | 0 | Resource Division | 46.12 | 0 | 0 | 0
256 | HOWRAH | Electrical | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haturie-Kandarpur water supply scheme, T.W. No.- I, II & III, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 3510/ED | 30/12/2022 | 90 | MAHADEV ENTERPRISE | 32.2 | 31.14 | 96.73 | 40
257 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at 2nd TW site at Haturie Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1055/HD | 15/03/2023 | 90 | SR TRADING CORPORATION | 7.18 | 7.18 | 100 | 100
258 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Haturia Kandarpur PWSS of Bagnan-I Block Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 2718/HD | 14/12/2022 | 60 | LOKENATH ENTERPRISES | 54.06 | 52.07 | 100 | 100
259 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site at Haturie Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1052/HD | 15/03/2023 | 90 | M/S M.R ENTERPRISE | 7.14 | 7.14 | 100 | 100
260 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at 3rd TW site at Haturie Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1057/HD | 15/03/2023 | 90 | MARUTI CONSTRUCTION | 7.19 | 6.92 | 50 | 100
261 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 45.57 | 0 | 0 | 0
262 | HOWRAH | Electrical | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | New service connection at Haturie Kandarpur W/S. Sch. PH-II | 171 | 28/02/2023 | 0 | WBSEDCL | 0.55 | 0 | 0 | 0
263 | HOWRAH | Electrical | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | NEW SERVICE CONNECTION FOR HATURIA KANDARPUR PWSS, PUMP HOUSE-III | 109 | 19/07/2023 | 0 | WBSEDCL | 0.76 | 0 | 0 | 0
264 | HOWRAH | Electrical | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | New service connection at Haturie Kandarpur W/S. Sch. PH-I | 171 | 28/02/2023 | 0 | WBSEDCL | 0.55 | 0 | 0 | 0
265 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Haturia Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Natibpur (Jl-52) (Part-D) | 2058/HD | 29/09/2022 | 45 | MAA TARA CONSTRUCTION | 61.1 | 57.31 | 100 | 100
266 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Haturia Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza- JOTE BIRESWAR(Jl-51) (Part-C) | 2057/HD | 29/09/2022 | 812 | NIRMAL UDYOG | 74.66 | 38.61 | 68.6 | 100
267 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Haturia Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Singara (Jl-53) (Part-E) | 2059/HD | 29/09/2022 | 45 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 39.47 | 38.34 | 100 | 100
268 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Work Order for Interconnection for 2nd TW and 1st Tube well (HW site) at Haturia Kandarpopur Piped Water Supply scheme in Bagnan-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 2060/HD | 29/09/2022 | 30 | ASHOKE ENGINEERING WORKS | 15.63 | 5.78 | 100 | 95
269 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Work Order for Laying Additional Distribution System(HDPE & DI) & providing Functional Household Tap Connections (FHTC) of Haturia Kandarpur PWSS within Mouza-Singara(53) of Haturia-I GP under Bagnan-I block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1049/HD | 15/03/2023 | 90 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 11.44 | 10.89 | 100 | 100
270 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Additional Laying Distribution system (HDPE & DI) & providing Functional Household Tap connection (FHTC) of Haturia Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 4341/HD | 04/12/2023 | 60 | MAA TARA CONSTRUCTION | 18.77 | 18.36 | 100 | 100
271 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 10.47 | 0 | 0 | 0
272 | HOWRAH | Electrical | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Quotation for new service connection for Ground Water Based Pwss Haturie Kandarpur, in the district Howrah under Electrical Division, PHE Dte. Reference Id- 106616946, Application no- 1007818648 ( SM/11000) | 246 | 24/06/2024 | 0 | WBSEDCL | 3.19 | 0 | 0 | 0
273 | HOWRAH | Electrical | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Quotation for new service connection for Haturie Kandarpur w/s scheme in the district Howrah under Electrical Division, PHE Dte. Reference Id- 106616939, Application no- 1007818619 | 249 | 24/06/2024 | 0 | WBSEDCL | 16.08 | 0 | 0 | 0
274 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Construction of 450 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection, Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC) for HATURIA KANDARPUR PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Haturia Kandarpur (Jl-49) & Khanpur (Jl-50)) [No. of FHTC = 2433] | 3197/HD | 04/09/2023 | 880 | B.M. ENTERPRISE | 481.61 | 229.93 | 47.74 | 65
275 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 1.46 | 100 | 100
276 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
277 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. , SM/11000 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
278 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 20.31 | 0 | 0 | 0
279 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Makardah PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | 83/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 4.15 | 0 | 0 | 0
280 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Work Order for Land Development work at Makardaha Head Work Site For Makardaha PWSS under Howrah Divnision PHE Dte. | 1927/HD | 10/05/2023 | 60 | NATURAL RESOURCES CONSORTIUM | 2.97 | 2.96 | 100 | 100
281 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Material Requisition To Resource Division | 593/HD | 13/02/2023 | 0 | Resource Division | 53.91 | 0 | 0 | 0
282 | HOWRAH | Electrical | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Quotation Bill for for New Service Connection at Makardaha W/S. Sch. PH-II | 424 | 17/11/2023 | 0 | WBSEDCL | 9.12 | 0 | 0 | 0
283 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Augmentation of Makardaha | BP-2022-23-534 | 09/03/2023 | 0 | WBSEDCL | 0.66 | 0 | 0 | 0
284 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Work Order for Laying Distribution System Pipeleine (Node No. 503 to 662 & 669) & FHTC work [Mouza: Ankurhati (CT) : PART-2] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division P.H.E Dte. | 2382/HD | 18/11/2022 | 30 | ANUSKA ENTERPRISE | 86.39 | 75.8 | 87.75 | 90
285 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Work Order for Laying Distribution System Pipeleine (Node No. 232 to 357) & FHTC work [Mouza: Jhaluarber] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division P.H.E Dte. | 2991/HD | 29/12/2022 | 30 | QUICK CONCRETE PROJECT | 66.11 | 33.18 | 50.19 | 95
286 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Work Order for Laying Distribution System Pipeleine (Node No. 358 to 502 & 545) & FHTC work [Mouza: Ankurhati (CT) : PART-1] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division P.H.E Dte. | 2319/HD | 11/11/2022 | 30 | MENOKA ENGINEERING WORKS | 82.16 | 38.12 | 46.4 | 70
287 | HOWRAH | Electrical | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Makardaha water supply scheme, T.W. No. III & IV, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 935/ED | 22/02/2023 | 90 | GLACIER ENGINEERING CO. | 21.83 | 21.55 | 98.72 | 30
288 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Makardha PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte | 1999/HD | 26/09/2022 | 40 | M/S SYCHROTECH INDUSTRY | 26.39 | 25.79 | 100 | 100
289 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Sinking of 01 (One) No. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Makardha PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | 805/HD | 20/02/2024 | 30 | AUXILIARY TUBEWELL DRILLERS | 14.12 | 13.95 | 100 | 100
290 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Emergency Restoration of damaged concrete road due to laying of pipe line at Ankurhati stadium of Makardaha PWSS under Howrah Sadar Sub-Division PHE Dte. | 639/HSSD | 25/06/2024 | 30 | UNIVERSAL CORPORATION | 2.16 | 2.09 | 100 | 100
291 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Shifting of LT Cable from transformer to Makardaha pwss P.H.No.-I, on full deposite scheme , Dist.-Howrah under PHE Dte. Application No- 100000106104 Reference ID- 860298084 SM Code- 11159 | BP-2024-25-46 | 07/05/2024 | 0 | WBSEDCL | 20.94 | 0 | 0 | 0
292 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Payment for Way Leave Plan and Survey Charges Makardaha PWSS | BP-2023-24-737 | 27/03/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.14 | 0 | 0 | 0
293 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Bill Document for Payment of Wayleave facility charges | BP-2024-25-154 | 08/07/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 5.01 | 0 | 0 | 0
294 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Bill Document for Payment of Wayleave Plan & Survey charges | BP-2024-25-98 | 28/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.09 | 0 | 0 | 0
295 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Bill Document for Payment of Wayleave facility charges | BP-2024-25-56 | 10/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 8.04 | 0 | 0 | 0
296 | HOWRAH | Electrical | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Quotation money deposition for new service connection at Makardah water supply scheme , P.H No-III, Dist- Howrah under ED PHED. App. No.-1007939058 SM/11159 | 409 | 21/08/2024 | 0 | WBSEDCL | 13.4 | 0 | 0 | 0
297 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Work Order for Laying of Distribution Pipeline (Node No. 663 To 944) & FHTC work [Mouza: Ankurhati (CT) : PART-3] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division, P. H. E. Dte. (Part-7) | 2100/HD | 12/10/2022 | 813 | UNIVERSAL CORPORATION | 153.73 | 72.51 | 47.17 | 15
298 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Work Order for Construction of 3 (three) nos of Boundary Wall for Augmentation of Makardah PWSS at Domjur Block under Howrah Division PHE Dte | 1991/HD | 26/09/2022 | 796 | JOY GURU TRADING | 17.93 | 0 | 0 | 60
299 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Work Order for Construction of 450 cum Capacity OHR, Rising Main Pipe line, Laying of Distribution Pipeline (Node No. R-1 To 231) & FHTC work [Mouza: Makardah (CT)] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division, P. H. E. Dte. (Part-3) | 2099/HD | 12/10/2022 | 964 | NATURAL RESOURCES CONSORTIUM | 349.1 | 176.92 | 50.68 | 50
300 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Work Order for Construction of 3 (Three) Nos. of Pump House for Augmentation of Makardah PWSS at Domjur Block under Howrah Division P.H.E Dte. | 1990/HD | 26/09/2022 | 45 | S.B. ENTERPRISE | 17.72 | 0 | 0 | 100
301 | HOWRAH | Electrical | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Makardaha water supply scheme, T.W. No.- New, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 3432/ED | 11/08/2023 | 690 | GLACIER ENGINEERING CO. | 10.75 | 0 | 0 | 50
302 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Piped Water Supply Schemes in different Blocks in the District of Howrah under Howrah Division, PHE Dte. | 3730/HD | 29/08/2024 | 30 | HORIZEN | 4.93 | 0 | 0 | 100
303 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4817/HD | 19/11/2024 | 510 | TECH VISION | 8.36 | 0.69 | 99.98 | 95
304 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Supplying fabrication of 600 mm dia 10 mm thick MS casing pipe and pushing of casing pipe by Hydraulic Jack pushing method to Cross Water carrier Pipe (Between Node Point 624 to 708 of LDS drawing) between Makardaha-Jhallurbar Station at KM HA-9/21-22 (WL-35) and (Between Node Point 574 to 576 of LDS drawing) between Makardaha Jhallurbar Station at KM HA-9/2-9/3 (WL-85) of Makardaha Water Supply Scheme of Howrah Sadar Sub-Division, under Howrah Division P.H.E. Dte. (SM/11159) | 2338/HD | 14/05/2025 | 180 | JOY GURU TRADING | 90.94 | 0 | 0 | 50
305 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block , SM/11159 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Domjur (Zone -II) Uttar Jhapardaha PWSS [SM/17175], Baniara PWSS [SM/11722], Makardaha PWSS [SM/11159] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 222-A/HSSD | 25/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
306 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Work Order for Preparation of DPR for piped water supply scheme of Kumirmora PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 255/HD | 07/02/2022 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.61 | 100 | 0
307 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Kumirmora PWSS of Udaynarayanpur Block of Howrah RWS Sub- Division under Howrah Division, P. H. E. Dte. | 2489/HD | 30/11/2022 | 45 | JYOTY SOLAR POWER | 27.45 | 24.63 | 89.74 | 0
308 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Material Requisition To Resource Division | 421/HD | 03/02/2023 | 0 | Resource Division | 0.69 | 0 | 0 | 0
309 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Material Requisition To Resource Division | 1552/HD | 05/04/2023 | 0 | Resource Division | 0.69 | 0 | 0 | 0
310 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Material Requisition To Resource Division | 2234/HD | 14/06/2023 | 0 | Resource Division | 10.36 | 0 | 0 | 0
311 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Material Requisition To Resource Division | 2830/HD | 04/08/2023 | 0 | Resource Division | 9.79 | 0 | 0 | 0
312 | HOWRAH | Electrical | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-I & PH-II Howrah | 212 | 24/03/2023 | 0 | WBSEDCL | 15.82 | 0 | 0 | 0
313 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Work Order for Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation) along with part Laying of Distribution and Providing Functional Household Tap Connection(FHTC)for Kumirmora Piped Water Supply scheme of Udayanarayanpur Block under Howrah Division P.H.E. Dte. in the District of Howrah. (Part-A) | 2164/HD | 21/10/2022 | 810 | PRAVAT SARKAR | 194.98 | 137.1 | 79.12 | 60
314 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Kumirmora W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 2810/HD | 21/12/2022 | 60 | SAMANTA BUILDERS | 8.5 | 8.36 | 100 | 100
315 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Work Order for Raising main & Inter Connection with both tube wells of Kumirmora PWSS In Udaynarayanpur Block under Howrah Division, PHE Dte. | 1922/HD | 08/05/2023 | 566 | LOKENATH ENTERPRISES | 5.34 | 0 | 0 | 70
316 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Kumirmora W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 2807/HD | 21/12/2022 | 60 | CHINMOY SAMANTA | 8.5 | 8.37 | 100 | 100
317 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Material Requisition To Resource Division | 30/HD | 03/01/2024 | 0 | Resource Division | 1.75 | 0 | 0 | 0
318 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Material Requisition To Resource Division | 3884/HD | 05/09/2024 | 0 | Resource Division | 0.32 | 0 | 0 | 0
319 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Kumirmora Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-B) | 1988/HD | 26/09/2022 | 45 | TANMOY ROY CHOUDHURY | 88.86 | 54.86 | 61.73 | 60
320 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Kumirmora Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-C) | 1989/HD | 26/09/2022 | 871 | FARID UDDIN AHMED | 93.98 | 49.76 | 52.95 | 5
321 | HOWRAH | Electrical | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumirmora water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 3514/ED | 30/12/2022 | 549 | M/S S R ENTERPRISE | 20.38 | 19.62 | 97.28 | 90
322 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Additional Laying of Distribution Pipe Lines and Providing Functional Household Tap Connection(FHTC) for leftout area of KUMIRMORA Piped Water Supply Scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 4723/HD | 12/11/2024 | 217 | MISHRA ENTERPRISE | 48.16 | 0 | 0 | 85
323 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. , SM/11221 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4813/HD | 19/11/2024 | 510 | HORIZEN | 13.59 | 0 | 0 | 70
324 | HOWRAH | Central Drilling | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT Udaynarayanpur Block UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 380/CMSD-I | 05/08/2022 | 15 | DEY ENTERPRISE | 4.67 | 0 | 0 | 0
325 | HOWRAH | Central Drilling | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT UDAYNARAYANPUR W/S SCH, UDAYNARAYANPUR BLOCK UNDER HOWRAH DIVISION, PHE DTE. | 379/CMSD-I | 05/08/2022 | 15 | DEY ENTERPRISE | 4.51 | 0 | 0 | 0
326 | HOWRAH | Central Drilling | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | PROVIDING DRILLING CREW AND OTHERS MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR UDAYNARAYANPUR W/S SCH, UDAYNARAYANPUR BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 378/CMSD-I | 05/08/2022 | 15 | DEY ENTERPRISE | 4.57 | 0 | 0 | 0
327 | HOWRAH | Central Drilling | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | PROVIDING DRILLING CREWS AND OTHERS MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR GAURANGA CHAK W/S SCH, UDAYNARAYANPUR BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 378/ CMSD-I | 05/08/2022 | 15 | DEY ENTERPRISE | 4.57 | 4.35 | 100 | 0
328 | HOWRAH | Central Drilling | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT GAURANGA CHAK W/S SCH, UDAYNARAYANPUR BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 380/ CMSD-I | 05/08/2022 | 15 | DEY ENTERPRISE | 4.67 | 3.92 | 100 | 0
329 | HOWRAH | Central Drilling | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT GAURANGA CHAK W/S SCH, UDAYNARAYANPUR BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 379/ CMSD-I | 05/08/2022 | 15 | DEY ENTERPRISE | 4.51 | 4.51 | 100 | 0
330 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Gaurangachak PWSS of RWS Howrah Sub-Division under Howrah Division, P. H. E. Dte. | 2487/HD | 30/11/2022 | 45 | PRANTIK DRILLING AGENCY | 36.08 | 31.75 | 88 | 0
331 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Preparation of DPR for new piped water supply scheme of Gourangachak PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 331/AE/USD | 16/08/2022 | 45 | STEELCONC AND ASSOCIATES | 3.29 | 3.15 | 100 | 0
332 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Material Requisition To Resource Division | 421/HD | 03/02/2023 | 0 | Resource Division | 2.38 | 0 | 0 | 0
333 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Material Requisition To Resource Division | 1552/HD | 05/04/2023 | 0 | Resource Division | 3.11 | 0 | 0 | 0
334 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Material Requisition To Resource Division | 2234/HD | 14/06/2023 | 0 | Resource Division | 8.22 | 0 | 0 | 0
335 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Material Requisition To Resource Division | 2830/HD | 04/08/2023 | 0 | Resource Division | 15.87 | 0 | 0 | 0
336 | HOWRAH | Electrical | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Quotation Bill for New Service Connection at Gourangachak Pwss I & II | 227 | 29/03/2023 | 0 | WBSEDCL | 11.63 | 0 | 0 | 0
337 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Work Order Construction of Pump House ( 5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Gourangachak W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 2801/HD | 21/12/2022 | 60 | SAIKAT ENTERPRISE | 7.84 | 7.31 | 100 | 100
338 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Gourangachak W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 2804/HD | 21/12/2022 | 60 | SONAR BANGLA ENTERPRISE | 7.6 | 7.49 | 100 | 100
339 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Work Order for Raising main & Inter Connection with both tube wells of Gauranga Chak PWSS In Udaynarayanpur Block under Howrah Division, PHE Dte. | 1921/HD | 08/05/2023 | 30 | SONAR BANGLA ENTERPRISE | 5.19 | 5.08 | 100 | 100
340 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Material Requisition To Resource Division | 27/HD | 03/01/2024 | 0 | Resource Division | 0.52 | 0 | 0 | 0
341 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Material Requisition To Resource Division | 3884/HD | 05/09/2024 | 0 | Resource Division | 3.7 | 0 | 0 | 0
342 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site and Additional Laying of Distribution Pipe Lines with providing FHTC at GOURANGACHAK Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte.(SM/11573) | 2884/HD | 25/06/2024 | 479 | PRADIP KUMAR JATI | 149.89 | 0 | 0 | 40
343 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Additional Laying of Distribution Pipe Lines for leftout area of GOURANGACHAK Piped Water Supply Scheme in Udaynarayanpur Block under Howrah Division, PHE Dte. | 1938/HD | 22/04/2025 | 60 | PRADIP KUMAR JATI | 61.73 | 0 | 0 | 0
344 | HOWRAH | Electrical | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gauranga Chak water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 3508/ED | 30/12/2022 | 427 | P.P. CONCERN | 20.36 | 19.97 | 98.65 | 30
345 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) of GAURANGA CHAK Piped Water Supply Scheme under Udaynaryanpur block under Howrah Division, PHE Dte. (Part-B). | 1992/HD | 26/09/2022 | 1330 | MUKHERJEE CONSTRUCTION | 94.6 | 29.91 | 31.61 | 20
346 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Work Order for Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation) along with part Laying of Distribution and Providing Functional Household Tap Connection(FHTC) for Gauranga Chak Piped Water Supply scheme of Udayanarayanpur Block under Howrah Division P.H.E. Dte. in the District of Howrah.(Part-A) | 2171/HD | 21/10/2022 | 1068 | PRADIP KUMAR JATI | 319.68 | 289.97 | 90.71 | 95
347 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. , SM/11573 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4813/HD | 19/11/2024 | 510 | HORIZEN | 13.59 | 0 | 0 | 70
348 | HOWRAH | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13750 | New | Preparation of DPR for Barram Nagar PWSS, Uluberia-II Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | 457/AE/USD | 15/09/2022 | 45 | APEX ENGINEERING | 3.29 | 2.88 | 87.36 | 100
349 | HOWRAH | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13750 | New | Material Requisition To Resource Division | 1754/HD | 26/04/2023 | 0 | Resource Division | 21.56 | 0 | 0 | 0
350 | HOWRAH | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13750 | New | Material Requisition To Resource Division | 4695/HD | 26/12/2023 | 0 | Resource Division | 12.29 | 0 | 0 | 0
351 | HOWRAH | Electrical | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13750 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Barramnagar water supply scheme, T.W. No.- I & II, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | 3534/ED | 30/12/2022 | 805 | M/S S R ENTERPRISE | 20.38 | 19.75 | 96.94 | 60
352 | HOWRAH | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13750 | New | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 3.14 | 0 | 0 | 0
353 | HOWRAH | Electrical | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13750 | New | Quotation money deposition for new service connection at Barramnagar pwss , P.H No.-II, Dist-Howrah under PHED. App. No.-1007576971 Ref.ID: 106502484 SM/13750 | 865 | 12/03/2024 | 0 | WBSEDCL | 27.26 | 0 | 0 | 0
354 | HOWRAH | Electrical | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13750 | New | Quotation Bill for New Service Connection at Barramnagar W/S. Sch. PH-I | 728 | 05/02/2024 | 0 | WBSEDCL | 8.74 | 0 | 0 | 0
355 | HOWRAH | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13750 | New | Work Order for Sinking of 7 (Seven) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Bamunhati PWSS (3 nos) & Kamina PWSS (2 nos) & Barramnagar PWSS (2 nos) of Uluberia - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 1195/HD | 23/03/2023 | 847 | ACME CONSTRUCTION | 90.87 | 0 | 0 | 85
356 | HOWRAH | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13750 | New | Construction of Culvert over the Drainage Chanal at Head Work site of Barramnagar PWSS of Uluberia-II Block under Uluberia Sub Division under Howrah Division PHED. | 1350/HD | 11/03/2025 | 45 | PRADIP KUMAR JATI | 29.62 | 0 | 0 | 0
357 | HOWRAH | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13750 | New | Construction of 2nos switch room (5.4x 3.6) at HW & 2nd TW site and boundary wall at HW Site and Interconnection between TW's of Barramnagar PWSS under Uluberia-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 4397/HD | 06/12/2023 | 425 | A. R. CONSTRUCTION | 39.66 | 25.26 | 82.28 | 100
358 | HOWRAH | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13750 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
359 | HOWRAH | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13750 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir (Drawing No- PC I/O.H.R/7/2012)with necessary soil investigation with foundation design as per soil test report for Barramnagar Piped Water Supply Scheme in Uluberia-II Block under Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 1691/HD | 20/04/2023 | 1095 | PRADIP KUMAR JATI | 316.16 | 55.68 | 17.61 | 100
360 | HOWRAH | Howrah Division | Sibpur Piped Water Supply Scheme. , SM/13769 | New | Work Order for Preparation of DPR for new piped water supply scheme of Sibpur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 252/HD | 07/02/2022 | 15 | APEX ENGINEERING | 2.7 | 2.7 | 100 | 100
361 | HOWRAH | Howrah Division | Sibpur Piped Water Supply Scheme. , SM/13769 | New | Material Requisition To Resource Division | 3217/HD | 05/09/2023 | 0 | Resource Division | 14.7 | 0 | 0 | 0
362 | HOWRAH | Howrah Division | Sibpur Piped Water Supply Scheme. , SM/13769 | New | Material Requisition To Resource Division | 1049/HD | 04/03/2024 | 0 | Resource Division | 0.83 | 0 | 0 | 0
363 | HOWRAH | Electrical | Sibpur Piped Water Supply Scheme. , SM/13769 | New | Quotation bill for new service connection charge for Shibpur PWSS TW - I | 496 | 07/12/2023 | 0 | WBSEDCL | 12.3 | 0 | 0 | 0
364 | HOWRAH | Electrical | Sibpur Piped Water Supply Scheme. , SM/13769 | New | Quotation Bill for New Service Connection at Sibpur W/S. Sch. PH-II | 511 | 08/12/2023 | 0 | WBSEDCL | 10.12 | 0 | 0 | 0
365 | HOWRAH | Howrah Division | Sibpur Piped Water Supply Scheme. , SM/13769 | New | Work Order for Sinking of 2nos 250 X 150mm dia Tube Well 230 mtr,Construction of 2nos Pump House cum switch room with sanitary arrangement, Laying Distribution system (LDS) with necessaery inter-connections with OHR and bypass arrangemnet etc. all complete, Functional Household Tap Connection (FHTC) works, Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Drawing No-PC-I/O.H.R/9/2012) with necessary soil investigation with foundation design as per soil test report For SIBPUR PWSS at Udaynarayanpur Block under uluberia Sub Division under Howrah Division, P. H. E. Dte. | 1652/HD | 18/04/2023 | 1095 | SANJOY GHOSH | 328.49 | 198.99 | 60.58 | 55
366 | HOWRAH | Howrah Division | Sibpur Piped Water Supply Scheme. , SM/13769 | New | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site of SHIBPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | 2888/HD | 25/06/2024 | 480 | SANJOY GHOSH | 62.98 | 0 | 0 | 22
367 | HOWRAH | Electrical | Sibpur Piped Water Supply Scheme. , SM/13769 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sibpur water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 925/ED | 22/02/2023 | 587 | ESENCE ENGINEERING CONCERN | 21.35 | 20.59 | 97.34 | 90
368 | HOWRAH | Howrah Division | Sibpur Piped Water Supply Scheme. , SM/13769 | New | Rising Main & Inter Connection with both tube wells of SIBPUR PWSS in Udaynarayanpur Block under Howrah Division, PHE Dte. | 3166/HD | 12/07/2024 | 180 | TIYASA ENTERPRISE | 5.17 | 0 | 0 | 100
369 | HOWRAH | Howrah Division | Sibpur Piped Water Supply Scheme. , SM/13769 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4813/HD | 19/11/2024 | 510 | HORIZEN | 13.59 | 0 | 0 | 70
370 | HOWRAH | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Nimabalia PWSS (Mouza-Moulagachhi, Finga Gachhi, Marghurali & Nimabalia) of Jagatballavpur Block under Howrah Division PHE Dte. | 1017/HD | 05/05/2022 | 15 | ENVIROTECH SOLUTIONS | 3.31 | 3.31 | 100 | 100
371 | HOWRAH | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nimabalia PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P. H. E. Dte. | 313/HD | 20/01/2023 | 30 | R CONSTRUCTION | 25.64 | 25.52 | 100 | 100
372 | HOWRAH | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Work Order for Construction of Culvert & Approach Road at Nimabalia OHR Site under Nimabalia PWSS in J.B Pur Block under Howrah Division PHE Dte. Howrah. | 1932/HD | 10/05/2023 | 60 | TRADE GREEN | 7.11 | 7.11 | 100 | 100
373 | HOWRAH | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Material Requisition To Resource Division | 446/HD | 06/02/2023 | 0 | Resource Division | 18.43 | 0 | 0 | 0
374 | HOWRAH | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Quotation Bill for New Service Connection at Nimabalia W/S. Sch. PH-I | 189 | 16/03/2023 | 0 | WBSEDCL | 7.62 | 0 | 0 | 0
375 | HOWRAH | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Quotation Bill for New Service Connection at Nimabalia W/S. Sch. PH-2 | 04 | 13/04/2023 | 0 | WBSEDCL | 3.17 | 0 | 0 | 0
376 | HOWRAH | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Additional quotation money deposit for Nimabalia w/s scheme. P.H-I, dist-howrah under ED/PHED. | 35 | 12/05/2023 | 0 | WBSEDCL | 3.97 | 0 | 0 | 0
377 | HOWRAH | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nimabalia water supply scheme, T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 3544/ED | 30/12/2022 | 90 | GHOSE ENGINEERING SYNDICATE | 22.59 | 21.67 | 95.9 | 75
378 | HOWRAH | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Construction of 2 Nos. Pump House (5.40m x 3.60 m) at 1st & 2nd Tube Well Sites Construction of Boundary Wall at 1st Tube Well Site, Construction of Boundary Wall at 2nd Tube Well Site, Laying Distribution Pipeline, providing Functional Household Tap Connection(FHTC) & Rising Main Pipeline Work From 2nd Pump House to 1st Pump House & OHR for NIMABALIA PWSS at J.B. PUR Block of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC=850] | 3257/HD | 11/09/2023 | 180 | GHOSH ENTERPRISE. | 175.9 | 174.53 | 100 | 60
379 | HOWRAH | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Land Development at OHR site & allied works at Nimabalia PWSS of J.B.Pur Block under Howrah Sadar Sub-Division under Howrah Division, PHE Dte. | 640/HSSD | 25/06/2024 | 30 | TRADE GREEN | 4.8 | 4.8 | 100 | 100
380 | HOWRAH | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 15.21 | 0 | 0 | 0
381 | HOWRAH | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Quotation money deposition for shifting of L.T O.H along with service cable at Nimabalia P.H No-I , Dist-Howrah under ED PHED. App. No.-100000101729 Ref I.D : 860293289 SM/13770 | 879 | 13/03/2024 | 0 | WBSEDCL | 0.63 | 0 | 0 | 0
382 | HOWRAH | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Work Order for Construction Of 300 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/11/2012) Including All pipe Connection For Augmentation Of Nimabalia PWSS at Jagatballavpur Block Of Howrah District under Howrah Division, P. H. E. Dte. | 1697/HD | 21/04/2023 | 900 | RAYCON CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 121.92 | 30.11 | 24.69 | 10
383 | HOWRAH | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Making of T.W. Foundation at Nimabalia water supply scheme, P.H No.- II, Dist-Howrah under Electrical Division, PHE Dte. | 3455/HMSD | 20/12/2023 | 7 | GHOSE ENGINEERING SYNDICATE | 0.96 | 0.96 | 100 | 0
384 | HOWRAH | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Laying distribution system (LDS) of existing drawing for 225 mm dia from (Node point J127-J488), for 200 mm dia (Node point J136-J144), for 180 mm dia (Node point J144-J148), for 160 mm dia (Node point J148-J508 & J10-J17), for 140 mm dia (Node point J152-J510 & J10-J01), for 125 mm dia (Node point J160-J167 & J17-J21), for 110 mm dia (Node point J17-J552), for 90 mm dia (Node point J330-J187) with 712 nos. Functional household tap connection (FHTC) and aproach road with land development at 2nd tube well site & allied works of Nimabalia PWSS at J.B. Pur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division PHE Dte. (SM/13770) | 2820/HD | 20/06/2024 | 210 | GHOSH ENTERPRISE | 127.58 | 76.14 | 59.87 | 40
385 | HOWRAH | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Jagatballavpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4814/HD | 19/11/2024 | 510 | HORIZEN | 10.11 | 0 | 0 | 56
386 | HOWRAH | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. , SM/13770 | New | Supplying,fitting,fixing and erecting of Display Board at Shekrahati PWSS [SM/09586], Nimabalia PWSS [SM/13770], Shyampur PWSS [SM/11790] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 231-A/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
387 | HOWRAH | Howrah Division | Khadinan Piped Water Supply Scheme , SM/13847 | New | Preparation of DPR for Khadinan PWSS, Bagnan-I Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | 458/AE/USD | 15/09/2022 | 45 | DULAL MAJUMDER | 3.16 | 2.98 | 100 | 100
388 | HOWRAH | Howrah Division | Khadinan Piped Water Supply Scheme , SM/13847 | New | Work Order for Renovation of 2nd Pump House along with Land Development work for Khadinan piped water supply scheme of Bagnan-I Block under Uluberia Sub-Division under Howrah Division PHE Dte. | 1776/HD | 27/04/2023 | 45 | LOKENATH ENTERPRISES | 4.2 | 4.19 | 100 | 100
389 | HOWRAH | Howrah Division | Khadinan Piped Water Supply Scheme , SM/13847 | New | Material Requisition To Resource Division | 1754/HD | 26/04/2023 | 0 | Resource Division | 13.49 | 0 | 0 | 0
390 | HOWRAH | Howrah Division | Khadinan Piped Water Supply Scheme , SM/13847 | New | Shifting and stacking of serviceable and unserviceable pipes and specials within the campus ofUluberia Sub-Division office campus including construction of wall racks and shelves almirah for keeping the office records in safe position in connection with "Khadinan PWSS" of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 3223/AE/USD | 12/03/2024 | 30 | S R TRADING CORPORATION | 2.16 | 2.16 | 100 | 100
391 | HOWRAH | Howrah Division | Khadinan Piped Water Supply Scheme , SM/13847 | New | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 7.95 | 0 | 0 | 0
392 | HOWRAH | Electrical | Khadinan Piped Water Supply Scheme , SM/13847 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khadinan water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 3543/ED | 30/12/2022 | 792 | ANJAN ENTERPRISE | 22.15 | 10.79 | 48.72 | 50
393 | HOWRAH | Howrah Division | Khadinan Piped Water Supply Scheme , SM/13847 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells & Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir (Drawing No- PC-I/O.H.R/7/2012) including Pipe connection & soil investigation with foundation design as per soil test report for Khadinan PWSS of Bagnan-I Block under Uluberia Sub Division under Howrah Division PHE Dte. | 2074/HD | 24/05/2023 | 1043 | D D CONSTRUCTION | 384.72 | 98.51 | 25.61 | 65
394 | HOWRAH | Howrah Division | Khadinan Piped Water Supply Scheme , SM/13847 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bagnan-I Block) | 4127/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
395 | HOWRAH | Howrah Division | Khadinan Piped Water Supply Scheme , SM/13847 | New | Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep Replace HW site tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Khadian PWSS of Bagnan-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 4062/HD | 18/09/2024 | 75 | LOKENATH ENTERPRISES | 14.58 | 0 | 0 | 100
396 | HOWRAH | Howrah Division | Khadinan Piped Water Supply Scheme , SM/13847 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
397 | HOWRAH | Electrical | Matinala Piped Water Supply Scheme , SM/15285 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Matinala water supply scheme, T.W. No.- I & II, Block: Bagnan-II, District- Howrah under Electrical Division, PHE Dte. | 928/ED | 22/02/2023 | 90 | R.M.D TRADING. | 20.38 | 0 | 0 | 0
398 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Preparation of DPR for Augmentation of Matinala (Mellock Zone-I) PWSS, Bagnan-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 317/AE/USD | 16/08/2022 | 45 | MS SOBHA AND CO | 3.61 | 3.51 | 100 | 100
399 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Material Requisition To Resource Division | 1754/HD | 26/04/2023 | 0 | Resource Division | 27.35 | 0 | 0 | 0
400 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Material Requisition To Resource Division | 2979/HD | 17/08/2023 | 0 | Resource Division | 26.58 | 0 | 0 | 0
401 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) at Matinala PWSS of Bagnan-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-A) | 1436/HD | 29/03/2023 | 120 | BISWAJIT BAG | 163 | 145.04 | 100 | 100
402 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Sinking of 5 (Five) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Harop PWSS Zone -I (1 no) & Zone-II (2 nos) & Matinala PWSS (2 nos) of Bagnan-I Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 3533/HD | 04/10/2023 | 60 | AQUATECH ENGINEERS | 64.95 | 15.01 | 100 | 40
403 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Balance Laying of distribution pipeline Matinala PWSS of Bagnan-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Mellock) | 3104/AE/USD | 29/02/2024 | 45 | BISWAJIT BAG | 13 | 12.36 | 100 | 100
404 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Balance Laying of distribution pipeline Matinala PWSS of Bagnan-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Matinala) | 3242/AE/USD | 12/03/2024 | 45 | SUNIRMAN ENTERPRISE | 11.92 | 11.92 | 100 | 100
405 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Site preparation and partial land Development at HW site of Matinala PWSS of Bagnan-II Block under Uluberia Sub Division under Howrah Divison PHED. | 797/AE/USD | 09/09/2024 | 30 | ADITYA HAZRA | 4.8 | 0 | 0 | 100
406 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Construction of switch room ( 3.60 m x 3.0 m) with water supply sanitary arrangement at 2nd tube well site of Matinala PWSS of Bagnan-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | 769/AE/USD | 05/09/2024 | 45 | D.C. CONSTRUCTION | 4.68 | 4.68 | 100 | 100
407 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 10.29 | 0 | 0 | 0
408 | HOWRAH | Electrical | Matinala Piped Water Supply Scheme , SM/15285 | New | Quotation for new service connection for Matinala Water Supply Scheme, PH NO- II, in the district Howrah under Electrical Division, PHE Dte. ( SM/15285), Reference Id- 106538620 , Application no- 1007634961 | 40 | 09/04/2024 | 0 | WBSEDCL | 4.07 | 0 | 0 | 0
409 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bagnan-II & Uluberia-II Block) | 4120/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
410 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of MATINALA PWSS OF BAGNAN-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. (PART-C) | 705/HD | 22/02/2023 | 721 | SUNIRMAN ENTERPRISE | 66.28 | 33.04 | 43.65 | 90
411 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) MATINALA PWSS OF BAGNAN-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. (PART-D) | 706/HD | 22/02/2023 | 781 | USHA CONCERN | 73.23 | 54.63 | 74.62 | 100
412 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube well & Construction of 450 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation for MATINALA PWSS OF BAGNAN-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. (PART-B) | 1141/HD | 21/03/2023 | 720 | ADITYA HAZRA | 218.71 | 177.59 | 81.2 | 100
413 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 1.06 | 100 | 100
414 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Approach road at 2nd TW site of Matinala PWSS of Bagnan-II under Uluberia Sub Division under Howrah Divison PHED. | 702/AE/USD | 28/08/2024 | 25 | SUNIRMAN ENTERPRISE | 3.18 | 0.84 | 20.94 | 100
415 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.85 | 0 | 0 | 0
416 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme , SM/15285 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
417 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block , SM/07880 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 2452 nos. | 443/HD | 02/03/2022 | 92 | SAMIRON GHOSH | 126.42 | 0 | 0 | 0
418 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block , SM/07880 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 2452 nos. | BP-2022-23-100 | 29/06/2022 | 0 | SAMIRON GHOSH | 126.96 | 0 | 0 | 0
419 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block , SM/07880 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. (Phase-2) | 345/AE/USD | 22/08/2022 | 45 | SK ENTERPRISE | 4.83 | 4.83 | 100 | 0
420 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block , SM/07880 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. (Phase-3) | 354/AE/USD | 22/08/2022 | 45 | SK ENTERPRISE | 3.33 | 3.04 | 100 | 0
421 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block , SM/07880 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. (Phase-1) | 344/AE/USD | 22/08/2022 | 45 | SK ENTERPRISE | 4.8 | 4.16 | 100 | 0
422 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block , SM/07880 | Retrofitting | Work Order for Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Phase-D) | 1934/HD | 10/05/2023 | 45 | S.M. CONSTRUCTION | 4.96 | 4.96 | 100 | 100
423 | HOWRAH | Howrah Division | Ghuteghari Piped Water Supply Scheme , SM/17198 | New | Continuation order for r Preparation of DPR for new piped water supply scheme of Ghutegari PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 1508/HD | 21/07/2022 | 15 | APEX ENGINEERING | 3.17 | 0 | 0 | 0
424 | HOWRAH | Electrical | Ghuteghari Piped Water Supply Scheme , SM/17198 | New | Quotation for new connection of Ghuteghari water supply scheme (Mini), Amta-I, Howrah Application No. 5004019125 Reference id: 503565825 SM/17198 UNDER JANGIPARA CCC, HOOGHLY | 858 | 11/03/2024 | 0 | WBSEDCL | 0.3 | 0 | 0 | 0
425 | HOWRAH | Howrah Division | Ghuteghari Piped Water Supply Scheme , SM/17198 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0.06 | 100 | 100
426 | HOWRAH | Howrah Division | Ghuteghari Piped Water Supply Scheme , SM/17198 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 0.31 | 0 | 0 | 0
427 | HOWRAH | Howrah Division | Ghuteghari Piped Water Supply Scheme , SM/17198 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
428 | HOWRAH | Howrah Division | Ghuteghari Piped Water Supply Scheme , SM/17198 | New | Work Order for Sinking of 1 (One) No. Tubewell (150mmx100mm), Construction of Switch Room (3750mmx3750mm) & Laying Distribution System for providing Functional House hold Tap Connection (FHTC) at Ghutegari Mini PWSS under Amta-I Block under Uluberia Sub- Division under Howrah Division PHE Dte. | 1534/HD | 04/04/2023 | 1000 | M/S AHAMED CONSTRUCTION | 27.24 | 0 | 0 | 50
429 | HOWRAH | Electrical | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Quotation Bill for New Service Connection at Debandi W/S. Sch. PH-II | 513 | 08/12/2023 | 0 | WBSEDCL | 4.08 | 0 | 0 | 0
430 | HOWRAH | Electrical | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Quotation Bill for New Service Connection at Debandi W/S. Sch. PH-I | 514 | 08/12/2023 | 0 | WBSEDCL | 3.75 | 0 | 0 | 0
431 | HOWRAH | Electrical | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Quotation Bill for New Service Connection at Debandi W/S. Sch. PH-III | 512 | 08/12/2023 | 0 | WBSEDCL | 4.27 | 0 | 0 | 0
432 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC-1030 nos) FOR DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-C-Debandi | 2948/HD | 14/08/2023 | 360 | JOY CHANDI CONSTRUCTION | 166.89 | 57.32 | 34.34 | 50
433 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Laying Distribution System(HDPE & DI) & Providing Functional Household Tap Connection (FHTC-1450 nos) FOR DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-D-Uttar Ramchandrapur & Anule | 3194/HD | 04/09/2023 | 575 | A P POWER & CONCRETE | 182.91 | 58.43 | 31.94 | 30
434 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Work Order for Preparation of DPR for new piped water supply scheme of Debandi PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 240/HD | 07/02/2022 | 15 | RADIANT | 4.4 | 4.4 | 100 | 100
435 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Debandi PWSS of Amta-I Block Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 3126/HD | 29/08/2023 | 45 | SPG ENTERPRISES | 52.15 | 49.47 | 100 | 100
436 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Construction of Kiosk (one no) at Debandi PWSS under uluberia Sub-Division, under Howrah DivisionP.H.E.Dte.(Size in side 3.0x1.8m)at 2nd TW Site at Baneswarpur Mouza. | 3234/AE/USD | 12/03/2024 | 30 | NOBLE ENTERPRISE | 1.13 | 1.13 | 100 | 100
437 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Construction of Kiosk (one no) at Debandi PWSS under uluberia Sub-Division, under Howrah Division P.H.E.Dte.(Size in side 3.0x1.8m) at 3rd TW Site at Debandi Mouza | 3232/AE/USD | 12/03/2024 | 30 | PRADIP KUMAR HAJRA | 1.13 | 1.13 | 100 | 100
438 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Construction of Kiosk (one no) at Debandi PWSS underuluberia Sub-Division, under Howrah Division P.H.E Dte.(Size in side 3.0x1.8m) at HW Site at Sarpota Mouza | 3233/AE/USD | 12/03/2024 | 30 | MAA TARA ENTERPRISE | 1.13 | 1.13 | 100 | 100
439 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 12.87 | 0 | 0 | 0
440 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Material Requisition To Resource Division | 447/HD | 01/02/2024 | 0 | Resource Division | 52.51 | 0 | 0 | 0
441 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Road Restoration work due to road cutting by PHED for laying water pipe line at Howrah Amta Road from 37.40 Km to 41.30 Km under Howrah Division, PWD during the year 2024-2025 | BP-2024-25-479 | 06/11/2024 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 11.45 | 0 | 0 | 0
442 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC-470 nos) FOR DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-E-Kandua | 3531/HD | 04/10/2023 | 720 | M/S. BHOWMICK ENTERPRISE | 68.87 | 0 | 0 | 0
443 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Construction of Boundary Wall (284 m Length), Land development, approach road etc at Head Work Site including alternative laying of DI(K-9) & DI (K-7) pipeline etc of 2nd T.Well & 3rd T.Well site of Debandi W/S scheme at Amta-I Block in Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 3233/HD | 23/07/2025 | 60 | MAA TARA CONSTRUCTION | 53.51 | 0 | 0 | 0
444 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Sinking of 1 (one) No. Additional 250 X 150 mm Dia and 250 m deep Drilling by Direct Rotary method with UPVC Pipes all complete at Debandi PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Location: Darapur) | 3232/HD | 23/07/2025 | 30 | AUXILIARY TUBEWELL DRILLERS | 15.45 | 0 | 0 | 0
445 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Amta-I Block) (PART-B) | 4126/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
446 | HOWRAH | Electrical | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Debandi water supply scheme, T.W. No.- I, II & III, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | 3580/ED | 28/08/2023 | 672 | S.S. ENTERPRISES | 34.16 | 8.91 | 25.12 | 60
447 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC 690 nos) DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-B-Sarpota & Chalunia | 2999/HD | 18/08/2023 | 690 | M/S SARADA UDYOG | 138.83 | 87.06 | 58.31 | 60
448 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 1.07 | 100 | 100
449 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 0.92 | 0 | 0 | 0
450 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC-530 nos) and Interconnection between tubewells & Construction of 500 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including foundation design for DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-A-Baneswarpur | 2840/HD | 07/08/2023 | 911 | SHANTA COLIBRI (INDIA) PVT. LTD | 276.9 | 108.69 | 39.25 | 75
451 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH , SM/18562 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
452 | HOWRAH | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme , SM/18490 | New | Preparation of DPR for new piped water supply scheme of Bedhichandrapur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 328/AE/USD | 16/08/2022 | 45 | APEX ENGINEERING | 2.81 | 2.8 | 99.52 | 100
453 | HOWRAH | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme , SM/18490 | New | Material Requisition To Resource Division | 3217/HD | 05/09/2023 | 0 | Resource Division | 16.59 | 0 | 0 | 0
454 | HOWRAH | Electrical | Bedhi Chandrapur Piped Water Supply Scheme , SM/18490 | New | Quotation bill for new service connection charge for Bedhi Chandrapur PWSS TW - I | 498 | 07/12/2023 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
455 | HOWRAH | Electrical | Bedhi Chandrapur Piped Water Supply Scheme , SM/18490 | New | Quotation bill for new service connection charge for Bedhi Chandrapur PWSS TW - II | 497 | 07/12/2023 | 0 | WBSEDCL | 10.33 | 0 | 0 | 0
456 | HOWRAH | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme , SM/18490 | New | Sinking of 2nos 250 X 150mm dia Tube Well 230 mtr,Construction of 2nos Pump House cum switch room with sanitary arrangement, Laying Distribution system (LDS) with necessary inter-connections with OHR and bypass arrangement etc. all complete, Functional Household Tap Connection (FHTC) works, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Drawing No- PC-I/O.H.R/7/2012)with necessary soil investigation with foundation design as per soil test report for BEDHI CHANDRAPUR PWSS at Udaynarayanpur Block under Uluberia Sub-Division under, Howrah Division, P. H. E. Dte. | 2758/HD | 31/07/2023 | 1097 | JAHANGIR ALAM | 335.32 | 152.52 | 45.48 | 42
457 | HOWRAH | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme , SM/18490 | New | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site along with restoration work of damaged pipeline of BEDHICHANDRAPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | 1939/HD | 22/04/2025 | 45 | JAHANGIR ALAM | 47.81 | 0 | 0 | 0
458 | HOWRAH | Electrical | Bedhi Chandrapur Piped Water Supply Scheme , SM/18490 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bedhi Chandrapur water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 3177/ED | 28/07/2023 | 431 | NEW RANBEE ENGINEERING | 21.38 | 20.91 | 98.71 | 85
459 | HOWRAH | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme , SM/18490 | New | Rising Main & Inter Connection with both tube wells of BEDHICHANDRAPUR PWSS in Udaynarayanpur Block under Howrah Division, PHE Dte. | 3224/HD | 22/07/2025 | 15 | MJ ENTERPRISE | 9.94 | 0 | 0 | 100
460 | HOWRAH | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme , SM/18490 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4813/HD | 19/11/2024 | 510 | HORIZEN | 13.59 | 0 | 0 | 70
461 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) , SM/07074 | Retrofitting | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) | 8443104 | 30/03/2021 | 0 | UNIVERSAL CORPORATION | 15.35 | 0 | 0 | 0
462 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) , SM/07074 | Retrofitting | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) | 84437 | 12/11/2021 | 0 | UNIVERSAL CORPORATION | 7.85 | 0 | 0 | 0
463 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) , SM/07074 | Retrofitting | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) | 844317 | 20/01/2022 | 0 | UNIVERSAL CORPORATION | 4.67 | 0 | 0 | 0
464 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) , SM/07074 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributin system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) | 844325 | 24/03/2022 | 0 | M/S ASHIRBAD (INDIA) | 55.24 | 0 | 0 | 0
465 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) , SM/07074 | Retrofitting | Mass Awarness generation and IEC activities. | 844313 | 23/12/2021 | 0 | PRADIP KUMAR JATI | 42 | 0 | 0 | 0
466 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) , SM/07074 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-I) | 424/HD | 11/02/2021 | 30 | UNIVERSAL CORPORATION | 93.25 | 47.72 | 51.18 | 0
467 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block , SM/07396 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur PipedWater Supply Scheme under Amta-I Block under Howrah Division, PHE Dte. (PART-B) [CHANDRAPUR GP PART] | BP-2021-22-370 | 28/02/2022 | 0 | QUICK CONCRETE PROJECT | 35.83 | 0 | 0 | 0
468 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block , SM/07396 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block under Howrah Division, PHE Dte. (PART-D) [CHANDRAPUR GP PART] | BP-2021-22-417 | 14/03/2022 | 0 | MAA TARA CONSTRUCTION | 24.68 | 0 | 0 | 0
469 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block , SM/07396 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block under Howrah Division, PHE Dte. (PART-A) [MAHISHGOHA GP] | BP-2021-22-388 | 08/03/2022 | 0 | PRADIP KUMAR JATI | 38.13 | 0 | 0 | 0
470 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block , SM/07396 | Retrofitting | Work Order for Additional pipe line work for providing Functional Household Tap Connection(FHTC) from existing distribution system (moksed para, Hazra para, molla para) at CHANDRAPUR W/S scheme under AMTA-I Block under Howrah Division, PHE Dte. (Part-I) | 2378/HD | 24/12/2021 | 30 | MAA TARA CONSTRUCTION | 4.82 | 0 | 0 | 0
471 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block , SM/07396 | Retrofitting | Work Order for Additional pipe line work for providing Functional Household Tap Connection(FHTC) from existing distribution system ( Mirpara, Bodok para, Khapara, Adolpara) at CHANDRAPUR W/S scheme under AMTA-I Block under Howrah Division, PHE Dte. (part-II) | 2379/HD | 24/12/2021 | 30 | QUICK CONCRETE PROJECT | 4.82 | 0 | 0 | 0
472 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block , SM/07396 | Retrofitting | Work Order for Additional pipeline work for providing Functional Household Tap Connection(FHTC) from existing distribution system (Hazari para, Beg para, Molla para, Chandrapur primary school) at CHANDRAPUR W/S scheme under AMTA-I Block under Howrah Division, PHE Dte. (Part-I) (Phase-B) | 132/AE/USD | 20/06/2022 | 45 | DDD CONSTRUCTION | 4.78 | 0 | 0 | 0
473 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block , SM/07396 | Retrofitting | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) all complete at Chandrapur PWSS at Amta-I Block under Uluberia Sub Division within Howrah Division, P.H.E. Dte.(Location-Chatra) | 784/HD | 04/02/2025 | 20 | AUXILIARY TUBEWELL DRILLERS | 14.4 | 0 | 0 | 0
474 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block , SM/07396 | Retrofitting | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) all complete at Chandrapur PWSS at Amta-I Block under Uluberia Sub Division within Howrah Division, P.H.E. Dte.(Location-Maheshguha) | 785/HD | 04/02/2025 | 20 | AUXILIARY TUBEWELL DRILLERS | 14.4 | 0 | 0 | 0
475 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-I) , SM/07885 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Zone-I) 1505 nos | 318/HD | 16/02/2022 | 45 | GHOSH CONCERN | 58.39 | 51.23 | 100 | 0
476 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-I) , SM/07885 | Retrofitting | Work Order for Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site (2nd TW site) at Uttar & Dakhin Bhatora Zone-I of Amta-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1848/HD | 02/05/2023 | 60 | SUNIL ENTERPRISE | 3.76 | 3.76 | 100 | 100
477 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-I) , SM/07885 | Retrofitting | Additional laying distribution pipeline and Road restoration at Village-Moyrachack of Amta-II Block under Uttar & Dakhin Bhatora PWSS under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 2762/HD | 12/06/2025 | 60 | RANA ENTERPRISE | 56.75 | 0 | 0 | 0
478 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Work Order for Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 700m3 Staging Height 20 mtr. for Kalyanpur Birampur W/S Scheme under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 386/HD | 22/02/2022 | 20 | PROSENJIT DAS | 0.65 | 0.65 | 100 | 0
479 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Work Order for Sinking of 2 (Two) nos PVC big dia Tube well 300 mm x 200 mm dia of 250 mtr deep for Augmentation of Kalyanpur-Birampur W/S scheme at Bagnan-I Block in Uluberia SubDivision P.H.E. Dte. Under Howrah Division, P.H.E Dte. | 1009/HD | 05/05/2022 | 30 | AQUATECH ENGINEERS | 35.2 | 33.27 | 94.5 | 0
480 | HOWRAH | Electrical | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipments etc. including allied works for Kalyanpur Birampur W/S. Sch.PH-II | 2101/HMSD | 24/11/2022 | 30 | DIPA CHHETRI | 4.25 | 4.25 | 100 | 0
481 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Material Requisition To Resource Division | 2639/HD | 09/12/2022 | 0 | Resource Division | 12.08 | 0 | 0 | 0
482 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
483 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Kalyanpur Birampur, Bagnan-I under Uluberia Sub-Division of Howrah Division PHE Dte. | BP-2021-22-408 | 14/03/2022 | 0 | RADIANT | 3.68 | 0 | 0 | 0
484 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | WBSRDA PAYMENT |  | 07/09/2022 | 0 | WBSRDA | 13.77 | 0 | 0 | 0
485 | HOWRAH | Electrical | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Kalyanpur Birampur water supply scheme, P.H. No.-II, District- Howrah under Electrical Division, PHE Dte. | 1245/HMSD | 14/07/2021 | 21 | A.G. ENTERPRISE | 2.74 | 2.74 | 100 | 0
486 | HOWRAH | Electrical | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Supply, delivery of electro mechanical equipments for Kalyanpur Birampur water supply scheme, P.H. No. II (Replacement tubewell), District- Howrah under Electrical Division, PHE Dte. | 36/HMSD | 05/01/2023 | 30 | P.K. ENTERPRISE | 3.55 | 3.49 | 100 | 0
487 | HOWRAH | Electrical | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Supply, delivery of electro mechanical equipments for Kalyanpur Birampur water supply scheme, P.H. No. I (Replacement tubewell), District- Howrah under Electrical Division, PHE Dte. | 35/HMSD | 05/01/2023 | 30 | J.K. ENGINEERING CO. | 2.87 | 2.69 | 100 | 0
488 | HOWRAH | Electrical | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kalyanpur Birampur water supply scheme, P.H. No. - I (Replacement Tubewell), Block Bagnan-I District - Howrah under Electrical Division, PHE Dte. | 2100/HMSD | 24/11/2022 | 30 | OSMAN SEKH | 4.12 | 4.03 | 100 | 0
489 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 18.99 | 0 | 0 | 0
490 | HOWRAH | Electrical | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Shifting of LT OH Line | 144 | 30/01/2023 | 0 | WBSEDCL | 0.27 | 0 | 0 | 0
491 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Payment against requirement of fund for restoration of PMGSY Road WB-09-250 (T032- Malick Pukur ) | BP-2023-24-115 | 27/06/2023 | 0 | WBSRDA | 10.14 | 0 | 0 | 0
492 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Payment against requestion of fund for restoration of PMGSY road Package No- WB-09-250 (TO-32- Mallick Pukur) of Augmentation of Kalyanpur and Birampur Water Supply Scheme | BP-2023-24-259 | 31/08/2023 | 0 | WBSRDA | 10.14 | 0 | 0 | 0
493 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Work Order for Augmentation of Kalyanpur Birampur Water Supply Schemem with LDS, Rising Main, FHTC work, at Bagnan-I Block of Howrah Division, PHE Dte. | 966/HD | 29/04/2022 | 244 | M/S EL-CON | 714.88 | 461.75 | 100 | 100
494 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Work order for Additional laying of pipeline at Augmentation of Kalyanpur Birampur Water Supply Scheme at Bagnan-I Block under Uluberia Sub-Division PHE Dte of Howrah Division PHE Dte. | 1987/HD | 15/05/2023 | 120 | M/S EL-CON | 247.87 | 187.71 | 100 | 100
495 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Interconnection between 5 nos Old existing pump of Kalyanpur Panchyat with delivery line and 1no construction of Kiosk (inside 3.0m x 3.0m) at Ratai Village for Augmentation of Kalyanpur Birampur Piped Water Supply scheme (SM/10145) in Bagnan-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 4035/HD | 17/09/2024 | 120 | BISWAJIT BAG | 45.01 | 0 | 0 | 100
496 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Additional FHTC and Road Restoration work for Augmentation of Kalyanpur Birampur Piped Water Supply scheme (SM/10145) in Bagnan-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 4132/HD | 23/09/2024 | 180 | BISWAJIT BAG | 96.59 | 14.41 | 12.98 | 100
497 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
498 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC , SM/10145 | Augmentation | Construction of 700 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection at Augmentation of Kalyanpur Birampur PWSS of Bagnan-I Block under Uluberia Sub-Divison under Howrah Division, PHE Dte. | 2645/HD | 07/06/2024 | 720 | UNIQUE AGENCY | 191 | 0 | 0 | 90
499 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Khalatpur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 2147/HD | 01/12/2021 | 15 | APEX ENGINEERING | 3.65 | 3.65 | 100 | 0
500 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Material Requisition To Resource Division | 2113/HD | 09/11/2022 | 0 | Resource Division | 16.9 | 0 | 0 | 0
501 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/10/2023 to 30/11/2023) | 392/RWS | 29/09/2023 | 61 | DEB KUMAR DAS | 0.79 | 0.72 | 100 | 50
502 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Material Requisition To Resource Division | 1552/HD | 05/04/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
503 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-E) | 1854/HD | 09/09/2022 | 60 | M/S CARE | 155.84 | 155.12 | 99.54 | 50
504 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/12/2023 to 31/01/2024) | 493/RWS | 30/11/2023 | 62 | DEB KUMAR DAS | 0.79 | 0.79 | 99.64 | 50
505 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/02/2024 to 31/03/2024) | 69/RWS | 31/01/2024 | 60 | DEB KUMAR DAS | 0.79 | 0.78 | 99.04 | 100
506 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Continuation order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/09/2024 to 31/10/2024) | 423/RWS | 30/08/2024 | 61 | REKHA GUCHAIT | 0.79 | 0.65 | 82.37 | 0
507 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Hiring of 01 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage permit from Regional Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/04/2024 to 30/09/2024) | 225/RWS | 28/03/2024 | 183 | M/S STAR CONSTRUCTION | 2.37 | 2.37 | 100.02 | 0
508 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Hiring of 1 no. Inspection Vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. for different PWSS in Udayanaryanpur Dev. Block, PHE Dte. Government of West Bengal (for the period from 01/07/2024 to 31/08/2024) | 347/RWS | 28/06/2024 | 62 | REKHA GUCHAIT | 0.79 | 0.69 | 86.62 | 0
509 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) | 1753/HD | 30/08/2022 | 30 | LAKSHMI IRON | 28.41 | 26.14 | 100 | 10
510 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-D) | 1754/HD | 30/08/2022 | 30 | ARINDAM ENTERPRISE | 21.71 | 18.99 | 100 | 30
511 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-B) | 1752/HD | 30/08/2022 | 30 | BISWAJIT SAMANTA | 13.32 | 10.81 | 100 | 30
512 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Work Order for Repairing of OHR & 2 nos Pump House(H/W & 2nd TW site) of KHALATPUR PWSS scheme in Udayanarayanpur Block, under Howrah Division P.H.E. Dte | 1777/HD | 27/04/2023 | 45 | CHANDRANI ENTERPRISE | 6.64 | 5.91 | 100 | 100
513 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Work Order for Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around 2nd Pump House site of KHALATPUR PWSS scheme in Udayanarayanpur Block, under Howrah Division P.H.E. Dte.. | 1774/HD | 27/04/2023 | 45 | BINOY KOLEY | 5.16 | 4.71 | 100 | 100
514 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme in Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) | 2101/HD | 12/10/2022 | 45 | A.K. SIKDAR | 111.19 | 103.3 | 100 | 30
515 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Udaynarayanpur Block of Uluberia Sub Division under Howrah Division PHE Dte. | 1210/HD | 11/03/2024 | 15 | TRIMARV SOLUTIONS PRIVATE LIMITED | 1.39 | 1.39 | 100 | 100
516 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Material Requisition To Resource Division | 3884/HD | 05/09/2024 | 0 | Resource Division | 1.85 | 0 | 0 | 0
517 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Continuation order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/11/2024 to 31/12/2024) | 493/RWS | 30/10/2024 | 61 | REKHA GUCHAIT | 0.79 | 0.66 | 84.4 | 0
518 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Continuation order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/01/2025 to 28/02/2025) | 550/RWS | 31/12/2024 | 59 | REKHA GUCHAIT | 0.78 | 0.68 | 87.4 | 0
519 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Land Development and Additional Laying of Distribution Pipe Lines with providing FHTC for leftout area for Augmentation of Khalatpur Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte.(SM/11271) | 2862/HD | 24/06/2024 | 360 | BISWAJIT BAG | 113.86 | 0 | 0 | 50
520 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Continuous work order for hiring of 01 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage permit from Regional Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/10/2024 to 31/03/2025) | 470/RWS | 30/09/2024 | 183 | M/S STAR CONSTRUCTION | 2.36 | 2.21 | 93.76 | 0
521 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Continuous work order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/05/2025 to 30/06/2025) | 123/RWS | 22/04/2025 | 61 | REKHA GUCHAIT | 0.79 | 0.66 | 84.28 | 0
522 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Hiring of 01 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage permit from Regional Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/04/2025 to 31/05/2025) | 103/RWS | 28/03/2025 | 61 | SANJIB BARMAN | 0.79 | 0.39 | 49.74 | 0
523 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Continuation order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/03/2025 to 30/04/2025) | 57/RWS | 27/02/2025 | 61 | REKHA GUCHAIT | 0.79 | 0.72 | 91.18 | 0
524 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Work order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/06/2025 to 31/07/2025) | 178/A/RWS | 27/05/2025 | 61 | SANJIB BARMAN | 0.79 | 0.39 | 49.93 | 0
525 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Construction of Boundary Wall, Land Development at HEAD WORK Site, Additional Laying of Distribution Pipe Lines at UTTAR MANASRI Piped Water Supply Scheme and Additional Laying of Distribution Pipe Lines at KHALATPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P. H. E. Dte. | 1855/HD | 16/04/2025 | 300 | SAMIRON GHOSH | 96.34 | 0 | 0 | 40
526 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Continuous work order for hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/07/2025 to 31/08/2025) | 215/RWS | 30/06/2025 | 62 | REKHA GUCHAIT | 0.79 | 0 | 0 | 0
527 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Continuous work order for hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/09/2025 to 31/10/2025) | 276/RWS | 21/08/2025 | 61 | REKHA GUCHAIT | 0.79 | 0 | 0 | 0
528 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS , SM/11271 | Augmentation | Work Order for Constrcution of 1.5 mtrs. Height Boundary Wall along with 750mm Height 3 layer barbed wire around head work site of KHALATPUR PWSS scheme in Udayanarayanpur Block, under Howrah Division P.H.E. Dte. | 1775/HD | 27/04/2023 | 502 | MAITY CONSTRUCTIONS | 13.8 | 0 | 0 | 90
529 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/224 | 13/08/2021 | 0 | N. G ENGINEERING | 8.24 | 0 | 0 | 0
530 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/180 | 06/08/2021 | 0 | M/S ASHIRBAD (INDIA) | 8.42 | 0 | 0 | 0
531 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/172 | 14/08/2021 | 0 | DEV DAS SHAW | 16.14 | 0 | 0 | 0
532 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Laying additional UPVC pipe line for FHTC Laskarpur Water Supply Scheme | 84432 | 01/11/2021 | 0 | M/S ASHIRBAD (INDIA) | 3.45 | 0 | 0 | 0
533 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/315 | 01/10/2021 | 0 | DEV DAS SHAW | 11.97 | 0 | 0 | 0
534 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/173 | 06/08/2021 | 0 | DEV DAS SHAW | 8.08 | 0 | 0 | 0
535 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/181 | 06/08/2021 | 0 | N. G ENGINEERING | 4.29 | 0 | 0 | 0
536 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | 844342 | 28/09/2021 | 0 | PRADIP KUMAR JATI | 10.19 | 0 | 0 | 0
537 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Survey and Collection of hous hold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme | 844374 | 25/03/2021 | 0 | STEELCONC AND ASSOCIATES | 4.73 | 0 | 0 | 0
538 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | 844320 | 20/01/2022 | 0 | MONIRUL ISLAM | 3.87 | 0 | 0 | 0
539 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/592 | 21/12/2021 | 0 | MONIRUL ISLAM | 3.32 | 0 | 0 | 0
540 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Supply Delivery & Installation of 250 mm dia valve with valve Chamber and Retrofitting work for existing Laskarpur Water Supply Scheme of Howrah Sadar Sub-Division, under Howrah Division P.H.E. Dte. | 1795/HD | 05/09/2022 | 30 | ADRIJA ENTERPRISE | 2 | 1.99 | 100 | 0
541 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Laskarpur | W/791 | 02/03/2023 | 0 | WBSEDCL | 2.68 | 0 | 0 | 0
542 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Bill for Power Connect in Bhurshit Bamunpara Water Supply Scheme | W/887 | 29/03/2023 | 0 | WBSEDCL | 11.77 | 0 | 0 | 0
543 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Laskarpur |  | 03/03/2023 | 0 | WBSEDCL | 2.68 | 0 | 0 | 0
544 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) , SM/06777 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | 647/21/2022 | 15/08/2020 | 0 | N. G ENGINEERING | 3.16 | 6.32 | 200 | 0
545 | HOWRAH | Electrical | Shyamchak Mini Piped water Supply Scheme , SM/15284 | New | Quotation Bill for New Service Connection at Shyam Chak Mini PWSS | 687 | 19/01/2024 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
546 | HOWRAH | Howrah Division | Shyamchak Mini Piped water Supply Scheme , SM/15284 | New | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | 2155/H.D | 07/06/2023 | 1021 | MONDAL PRECISION PVT. LTD. | 330.32 | 21.3 | 58.05 | 80
547 | HOWRAH | Howrah Division | Sankhali Piped Water Supply Scheme , SM/15289 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Shankhali PWSS of Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 999/HD | 13/03/2023 | 45 | SPG ENTERPRISES | 25.7 | 23.41 | 100 | 100
548 | HOWRAH | Howrah Division | Sankhali Piped Water Supply Scheme , SM/15289 | New | Continuation order for Preparation of DPR with Route Survey for new piped water supply scheme of Shankhali PWSS of Panchla Block under Howrah Division PHE Dte. | 1456/HD | 13/07/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.63 | 2.59 | 100 | 100
549 | HOWRAH | Howrah Division | Sankhali Piped Water Supply Scheme , SM/15289 | New | Material Requisition To Resource Division | 446/HD | 06/02/2023 | 0 | Resource Division | 4.34 | 0 | 0 | 0
550 | HOWRAH | Electrical | Sankhali Piped Water Supply Scheme , SM/15289 | New | NEW SERVICE CONNECTION AT SANKHALI PWSS P.H No.-II | 207 | 24/08/2023 | 0 | WBSEDCL | 3.51 | 0 | 0 | 0
551 | HOWRAH | Electrical | Sankhali Piped Water Supply Scheme , SM/15289 | New | NEW SERVICE CONNECTION AT SANKHALI PWSS P.H No.-I | 205 | 24/08/2023 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
552 | HOWRAH | Electrical | Sankhali Piped Water Supply Scheme , SM/15289 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sankhali water supply scheme, T.W. No.- I & II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 927/ED | 22/02/2023 | 45 | SRI KRISHNA NIRMAN | 20.35 | 19.65 | 96.56 | 90
553 | HOWRAH | Howrah Division | Sankhali Piped Water Supply Scheme , SM/15289 | New | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 6.52 | 0 | 0 | 0
554 | HOWRAH | Howrah Division | Sankhali Piped Water Supply Scheme , SM/15289 | New | Work Order for Construction of 2 (Two) Nos.Pump House (5.40m x 3.60m),Construction of Boundary Wall at Head work Site, Others site Boundary Wall, Construction of 200 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/2/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work, Estimate of Providing FHTC (Functional Household Tap Connection) For Sankhali PWSS at Panchla Block of Howrah District under Howrah Division, P. H. E. Dte. | 1595/HD | 12/04/2023 | 894 | REALIENCE CONSTRUCTION | 236.2 | 127.02 | 53.78 | 20
555 | HOWRAH | Howrah Division | Sankhali Piped Water Supply Scheme , SM/15289 | New | Additional Laying Distribution Pipe line for providing (FHTC), Land development and allied works of Shankhali PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 999/HD | 01/03/2024 | 270 | REALIENCE CONSTRUCTION | 41.91 | 34.6 | 85.01 | 100
556 | HOWRAH | Howrah Division | Sankhali Piped Water Supply Scheme , SM/15289 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4816/HD | 19/11/2024 | 510 | TECH VISION | 12.48 | 0 | 0 | 78
557 | HOWRAH | Electrical | Senpur Dwitiya Piped Water Supply Scheme , SM/15199 | New | Quotation Bill for New Service Connection at Senpur Dwitiya W/S. Sch. | 729 | 05/02/2024 | 0 | WBSEDCL | 0.71 | 0 | 0 | 0
558 | HOWRAH | Howrah Division | Senpur Dwitiya Piped Water Supply Scheme , SM/15199 | New | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | 2155/H.D | 07/06/2023 | 1021 | MONDAL PRECISION PVT. LTD. | 330.32 | 21.02 | 57.27 | 80
559 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Work Order for Preparation of DPR for new piped water supply scheme of Jikira PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 242/HD | 07/02/2022 | 15 | VOYAGER | 3.36 | 3.36 | 100 | 0
560 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Jagadishpur G.P Area) Zone-14 Length= 536.00mtr.(PART-A) | 1194/HD | 30/09/2020 | 30 | ADITYA HAZRA | 3.12 | 0 | 0 | 0
561 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 21.53 | 0 | 0 | 0
562 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nawapara PWSS (2nos) & Ajangachi PWSS (2nos) & Jhikira PWSS (2nos) of Amta-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 3440/HD | 26/09/2023 | 60 | PRANTIK DRILLING AGENCY | 77.89 | 23.53 | 100 | 100
563 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 8.13 | 0 | 0 | 0
564 | HOWRAH | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Quotation Bill for New Service Connection at Jhikira W/S. Sch. PH-I | 619 | 08/01/2024 | 0 | WBSEDCL | 3.86 | 0 | 0 | 0
565 | HOWRAH | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Quotation Bill for New Service Connection at Jhikira W/S. Sch. PH-III | 709 | 25/01/2024 | 0 | WBSEDCL | 12.37 | 0 | 0 | 0
566 | HOWRAH | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Quotation for Pole Shifting of Jhikira w/s Scheme,PH No-I under Electrical Division,PHE Dte(SM/11719) Application Id-100000105833. Reference Id-860297815. | 84 | 22/04/2024 | 0 | WBSEDCL | 0.36 | 0 | 0 | 0
567 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Work Order for Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation,Construction of Two storied switch room (5.4 x 3.6) & (3.6 x3.0) with water supply & sanitary arrangement cum godown at Head Work site & 2nd Tube well site, Laying Distribution Pipeline & Providing FHTC (3205 nos) for Jhikira Water Supply Scheme In Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 2501/HD | 30/11/2022 | 900 | K.P. CONSTRUCTION | 616.01 | 311.05 | 50.49 | 62
568 | HOWRAH | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JHIKIRA water supply scheme, TW No. III, Block: Amta-II, District - Howrah under Electrical Division PHE Dte. | 486/ED | 18/03/2025 | 90 | STANDARD ELECTRICALS | 11.3 | 0 | 0 | 0
569 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Construction of Boundary Wall (120 m Length) at 1st Tubewell Site, (66 m Length) at 2nd Tubewell Site & (52 m Length) at 3rd Tubewell Site, Construction of Approach Road with Paver Block from existing road to Head Work Site, Land Development of 3rd TW Site, construction of 1 nos switch room (3.6m x 3.00m) with water supply & sanitary arrangement at 3rd Tubewell site and Interconnection work with 3rd T. well of Jhikra PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 2885/HD | 23/06/2025 | 90 | K.P. CONSTRUCTION | 75.36 | 0 | 0 | 0
570 | HOWRAH | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jhikira water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | 923/ED | 22/02/2023 | 584 | STANDARD ELECTRICALS | 22.61 | 21.89 | 97.52 | 70
571 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 1.41 | 100 | 100
572 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Sinking of additional 1 (One) Nos. (250 X 150 mm) Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Jhikira PWSS at Amta-II Block in Uluberia Sub-Division, under Howrah Division PHE Dte. (Location: Jhikira) | 1175/HD | 03/03/2025 | 45 | PRANTIK DRILLING AGENCY | 14.71 | 0 | 0 | 100
573 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Quotation money deposition for new service connection at Jhikira w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008321273 Reference ID- 106898029 SM Code- 11719 |  | 31/10/2025 | 0 | WBSEDCL | 18.22 | 0 | 0 | 0
574 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Land Development of Head work site with laying of distribution pipe line within Jhikra PWSS at Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 2884/HD | 23/06/2025 | 270 | K.P. CONSTRUCTION | 81.48 | 0 | 0 | 15
575 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. , SM/11719 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
576 | HOWRAH | Electrical | Source Augmentation of Nakubar Water Supply Scheme , SM/18847 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Nakubar Water Supply Scheme Block- Amta-II District- Howrah under JJM Program under Electrical Division PHE Dte. | 4539/ED | 23/11/2023 | 494 | DEY ENTERPRISE | 21.5 | 0 | 0 | 40
577 | HOWRAH | Howrah Division | Source Augmentation of Nakubar Water Supply Scheme , SM/18847 | Augmentation | Work Order for Sinking of 1 (one) no PVC big dia additional Tube well 250 mm x 150 mm dia of 240 mtr deep at Nakubar W/S scheme at Amta-II Block in Uluberia Sub-Division under Howrah Division P.H.E Dte. | 1513/HD | 22/07/2022 | 20 | NADIA TUBEWELLS | 12.71 | 11.44 | 100 | 100
578 | HOWRAH | Electrical | Source Augmentation of Nakubar Water Supply Scheme , SM/18847 | Augmentation | Quotation money deposition for new service connection at Nakubar 3 w/s scheme, Dist.-Howrah under PHE Dte. Application No- 1007699722 Reference ID- 106569868 SM Code- 18847 | 176 | 30/05/2024 | 0 | WBSEDCL | 9.56 | 0 | 0 | 0
579 | HOWRAH | Howrah Division | Source Augmentation of Nakubar Water Supply Scheme , SM/18847 | Augmentation | Work Order for Construction of switch room (3.60 m x 3.0 m) with water supply & sanitary arrangement at 3rd tube well site of Nakubar PWSS of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | 2600/HD | 07/12/2022 | 781 | S.M. CONSTRUCTION | 4.7 | 0 | 0 | 100
580 | HOWRAH | Howrah Division | Source Augmentation of Nakubar Water Supply Scheme , SM/18847 | Augmentation | Balance laying distribution pipeline with FHTC at Chakkundalia and Ranjoybar Mouza of Nakubar PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 5018/HD | 04/12/2024 | 120 | UNIVERSAL CONSTRUCTION | 52.59 | 0 | 0 | 100
581 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Preparation of DPR for new piped W/S scheme of Ajangachi PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 315/AE/USD | 16/08/2022 | 45 | VOYAGER | 3.85 | 3.85 | 100 | 0
582 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nawapara PWSS (2nos) & Ajangachi PWSS (2nos) & Jhikira PWSS (2nos) of Amta-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 3440/HD | 26/09/2023 | 60 | PRANTIK DRILLING AGENCY | 77.89 | 25.28 | 100 | 100
583 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Material Requisition To Resource Division | 1286/HD | 13/03/2024 | 0 | Resource Division | 58.29 | 0 | 0 | 0
584 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Material Requisition To Resource Division | 4864/HD | 22/11/2024 | 0 | Resource Division | 5.54 | 0 | 0 | 0
585 | HOWRAH | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Quotation for new service connection at TW no. 2 of Ajangachi w/s scheme, Amta-II, Howrah Application No. 1007513650 Ref id:106459509 SM/18561 | 749 | 16/02/2024 | 0 | WBSEDCL | 4.16 | 0 | 0 | 0
586 | HOWRAH | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Quotation Bill for New Service Connection at Ajangachi W/S. Sch.PH-I | 707 | 25/01/2024 | 0 | WBSEDCL | 10.69 | 0 | 0 | 0
587 | HOWRAH | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Additional Quotation money for new service connection of Ajangachi w/s scheme, PH No. 2, Block- Amta-II, Howrah Application ID: 100000103588 Reference ID: 860295388 SM/18561 | 25 | 05/04/2024 | 0 | WBSEDCL | 3.39 | 0 | 0 | 0
588 | HOWRAH | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Quotation for new service connection at TW no. 2 of Ajangachi w/s scheme, Amta-II, Howrah | 750 | 16/02/2024 | 0 | WBSEDCL | 4.33 | 0 | 0 | 0
589 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Laying Distribution System & Providing House Hold Tap Connection (FHTC) & 450 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including foundation design of AJANGACHI PWSS in AMTA-II Block of Howrah District under Howrah Division, P.H.E. Dte. | 2949/HD | 16/08/2023 | 730 | GEE BEE NIRMAN CO PVT LTD | 817.6 | 299.94 | 36.69 | 60
590 | HOWRAH | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ajangachhi water supply scheme, T.W. No.- I, II & III, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | 3595/ED | 28/08/2023 | 581 | P.K. ENGINEERING | 32.24 | 0 | 0 | 60
591 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Construction of approach Road including restoration of CC road with Bullah piling and shifting of DI(K-7/K-9) pipes near TantiparaHazrapara of Ajangachi PWSS of Amta-II Block under Uluberia Sub Division under Howrah Divison PHE Dte. | 1763/AE/USD | 05/03/2025 | 30 | S R TRADING CORPORATION | 4.61 | 0 | 0 | 0
592 | HOWRAH | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for AJANGACHI water supply scheme, TW No. IV, Block: Amta-II, District - Howrah under Electrical Division PHE Dte. | 488/ED | 18/03/2025 | 90 | MAA KALI ENTERPRISE | 11.29 | 0 | 0 | 0
593 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Additional laying distribution pipeline with DI(K-7) and HDPE(PE-100,PN6) at Ajangachi PWSS of Amta-II Block in Uluberia Sub Division, under Howrah Division, P.H.E. Dte. | 4414/HD | 25/11/2025 | 60 | GEE BEE NIRMAN COMPANY PVT. LTD. | 65.24 | 0 | 0 | 0
594 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 250m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ajangachhi PWSS (SM/18561) of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E.Dte. | 4061/HD | 18/09/2024 | 60 | LOKENATH ENTERPRISES | 12.81 | 0 | 0 | 100
595 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Sinking of 1(One) No. additional T.Well size (250 X 150mm) Dia and 230m deep, Drilling by Direct Rotary method with UPVC Pipes all complete at Ajangachi PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Location: Solbaga) | 270/HD | 15/01/2025 | 90 | PRANTIK DRILLING AGENCY | 14.6 | 0 | 0 | 100
596 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Construction of 2 storied switch room SLOPE ROOF ( 5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site of Ajangachi PWSS of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 5019/HD | 04/12/2024 | 60 | M/S M.R ENTERPRISE | 11.25 | 0 | 0 | 100
597 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Construction of boundary wall at 3rd Tube Well site Ajangachi PWSS (SM/18561) scheme under Amta-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 5059/HD | 09/12/2024 | 90 | SUNIL ENTERPRISE | 7.62 | 0 | 0 | 100
598 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Construction of boundary wall at 2nd Tube Well site Ajangachi PWSS (SM/18561) scheme under Amta-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 5208/HD | 12/12/2024 | 45 | M/S MJA ENTERPRISE | 7.62 | 7.59 | 100 | 100
599 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Construction of boundary wall at HW Site Ajangachi PWSS (SM/18561) scheme under Amta-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 5209/HD | 12/12/2024 | 60 | A.N ROY & CO | 14.8 | 0 | 0 | 100
600 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Construction of switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement at Head Work site of Ajangachi PWSS (2nd Tube well) of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 4733/HD | 12/11/2024 | 45 | NOBLE ENTERPRISE | 5.81 | 5.57 | 100 | 100
601 | HOWRAH | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | NPC IRO-Assistant Engg HMSD PHE Ajangachi w/s scheme at Ajangachi Application No- 100000127092 Reference ID- 860322152 SM Code- 18561 | 672 | 21/01/2025 | 0 | WBSEDCL | 0.33 | 0 | 0 | 0
602 | HOWRAH | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS , SM/18561 | New | Quotation money deposition for new service connection at Ajangachi w/s scheme, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1008418424 Reference ID- 106964930 SM Code- 18561 | 743 | 27/03/2025 | 0 | WBSEDCL | 5.2 | 0 | 0 | 0
603 | HOWRAH | Electrical | Source Augmentation of Sarda Water Supply Scheme , SM/18884 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Sarda Water Supply Scheme Block- Amta-II District- Howrah under JJM Program under Electrical Division PHE Dte. | 4532/ED | 23/11/2023 | 90 | S.B.ENTERPRISE | 10.74 | 0 | 0 | 0
604 | HOWRAH | Electrical | Source Augmentation of Sarda Water Supply Scheme , SM/18884 | Augmentation | Supply delivery and installation of Chlorinator for Sarda w/s scheme PH No. IV District Howrah under Electrical Division, PHE dte. | 721/HMSD | 23/03/2023 | 7 | TRIO CONCERN | 0.8 | 0.8 | 100 | 100
605 | HOWRAH | Howrah Division | Source Augmentation of Sarda Water Supply Scheme , SM/18884 | Augmentation | Additional construction of 1nos switch room (5.4x 3.6) at TW site at Sarda PWSS SM/18884 of Amta-II Block in Uluberia Sub Division, under Howrah Division, P.H.E. Dte. | 2911/HD | 26/06/2024 | 30 | RANI CONSTRUCTION | 6.28 | 0 | 0 | 0
606 | HOWRAH | Howrah Division | Source Augmentation of Sarda Water Supply Scheme , SM/18884 | Augmentation | Preparation of DPR for Source Strengthning at Sarda PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 517/AE/USD | 05/10/2023 | 30 | APEX TECHNOLOGIES | 0.78 | 0.78 | 100 | 100
607 | HOWRAH | Howrah Division | Source Augmentation of Sarda Water Supply Scheme , SM/18884 | Augmentation | Additional laying distribution pipeline with FHTC at Sarda PWSS SM/18884 of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 2901/HD | 26/06/2024 | 525 | S.S. ENTERPRISE | 43.21 | 0 | 0 | 45
608 | HOWRAH | Howrah Division | Source Augmentation of Sarda Water Supply Scheme , SM/18884 | Augmentation | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sarda PWSS SM/18884 of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1308/HD | 14/03/2024 | 376 | WESTERN WATER SUPPLY AGENCY | 14.64 | 0 | 0 | 100
609 | HOWRAH | Electrical | Source Augmentation of Sarda Water Supply Scheme , SM/18884 | Augmentation | Quotation money deposition for new service connection at Sarda w/s scheme, T.W. No.IV, Dist.-Howrah under PHE Dte. Application No- 1008244862 Reference ID- 106848150 SM Code- 18884 | 648 | 09/01/2025 | 0 | WBSEDCL | 3.32 | 0 | 0 | 0
610 | HOWRAH | Howrah Division | Augmentation of Ground water PWSS for Islampur , SM/09428 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Islampur, JagatBallavpur under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | 2152/HD | 01/12/2021 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.03 | 4.03 | 100 | 0
611 | HOWRAH | Howrah Division | Augmentation of Ground water PWSS for Islampur , SM/09428 | Augmentation | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 27.6 | 0 | 0 | 0
612 | HOWRAH | Howrah Division | Augmentation of Ground water PWSS for Islampur , SM/09428 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
613 | HOWRAH | Electrical | Augmentation of Ground water PWSS for Islampur , SM/09428 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Islampur (Replacement) water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 711/ED | 03/02/2023 | 90 | T.N. BANERJEE | 21.42 | 19.22 | 89.7 | 1
614 | HOWRAH | Howrah Division | Augmentation of Ground water PWSS for Islampur , SM/09428 | Augmentation | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Islampur PWSS at Jagatballavpur Block of Howrah District under Howrah Division, P. H. E. Dte. | 1834/HD | 08/09/2022 | 40 | B K ENTERPRISE | 35.33 | 32.54 | 100 | 0
615 | HOWRAH | Electrical | Augmentation of Ground water PWSS for Islampur , SM/09428 | Augmentation | Car hiring bill for Car No. WB15C5554 for the month of July 2023 | 215_AE_II_ED | 24/03/2023 | 31 | DILIP KUMAR GHOSH | 0.15 | 0.15 | 100 | 5
616 | HOWRAH | Electrical | Augmentation of Ground water PWSS for Islampur , SM/09428 | Augmentation | Car hiring & fuel bill for the month of July 2023 | 0444_0445_0447 | 31/07/2023 | 31 | JAMECO AGENCIES PRIVATE LIMITED. | 0.73 | 0.73 | 100 | 5
617 | HOWRAH | Electrical | Augmentation of Ground water PWSS for Islampur , SM/09428 | Augmentation | Hire charges bill of vehicle no. WB04G2822 for the month of july 2023 | 203_AE_I_ED | 23/03/2023 | 31 | DASHRATH KUMAR PRAJAPATI | 0.15 | 0.15 | 100 | 5
618 | HOWRAH | Electrical | Augmentation of Ground water PWSS for Islampur , SM/09428 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | 958/HMSD | 20/04/2023 | 184 | ARINDAM AUDDY | 0.15 | 0.15 | 100 | 5
619 | HOWRAH | Howrah Division | Augmentation of Ground water PWSS for Islampur , SM/09428 | Augmentation | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 95.73 | 0 | 0 | 0
620 | HOWRAH | Howrah Division | Augmentation of Ground water PWSS for Islampur , SM/09428 | Augmentation | Work Order for Construction of Pump House, Boundary Wall, 450 cum Capacity OHR, Rising Main , Laying Distribution Pipeline & Providing FHTC (4480 nos) For AUGMENTATION OF Islampur PWSS at Jagatballavpur Block under Howrah Sadar Sub Division of HOWRAH DIVISION, P. H. E. DTE.. | 2256/HD | 04/11/2022 | 180 | SUBHASH BOSE | 571.07 | 301.6 | 52.81 | 25
621 | HOWRAH | Howrah Division | Augmentation of Ground water PWSS for Islampur , SM/09428 | Augmentation | Quotation money deposition for new service connection at Islampur w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008765950 Reference ID- 107173030 SM Code- 09428 |  | 04/09/2025 | 0 | WBSEDCL | 12.4 | 0 | 0 | 0
622 | HOWRAH | Howrah Division | Sherpur Piped Water Supply Scheme , SM/18426 | New | Material Requisition To Resource Division | 964/HD | 28/02/2024 | 0 | Resource Division | 65.52 | 0 | 0 | 0
623 | HOWRAH | Howrah Division | Sherpur Piped Water Supply Scheme , SM/18426 | New | Material Requisition To Resource Division | 4864/HD | 22/11/2024 | 0 | Resource Division | 12.32 | 0 | 0 | 0
624 | HOWRAH | Electrical | Sherpur Piped Water Supply Scheme , SM/18426 | New | Quotation for New Service Connection at Sherpur W/S. Sch. PH-II, Amta-I | 640 | 09/01/2024 | 0 | WBSEDCL | 4.17 | 0 | 0 | 0
625 | HOWRAH | Electrical | Sherpur Piped Water Supply Scheme , SM/18426 | New | Quotation for New Service Connection at Sherpur W/S. Sch. PH-I, Amta-I | 643 | 09/01/2024 | 0 | WBSEDCL | 3.9 | 0 | 0 | 0
626 | HOWRAH | Electrical | Sherpur Piped Water Supply Scheme , SM/18426 | New | Quotation for New Service Connection at Sherpur W/S. Sch. PH-III, Amta-I | 641 | 09/01/2024 | 0 | WBSEDCL | 6.98 | 0 | 0 | 0
627 | HOWRAH | Electrical | Sherpur Piped Water Supply Scheme , SM/18426 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sherpur water supply scheme, T.W. No. I, II & III, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | 63/ED | 08/01/2024 | 720 | MAA KALI ENTERPRISE | 34.21 | 25.37 | 74.16 | 60
628 | HOWRAH | Howrah Division | Sherpur Piped Water Supply Scheme , SM/18426 | New | Construction of switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement of Sherpur PWSS (4th Tube well) of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 2102/HD | 29/04/2025 | 45 | MANAS MALICK | 5.95 | 0 | 0 | 0
629 | HOWRAH | Howrah Division | Sherpur Piped Water Supply Scheme , SM/18426 | New | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) all complete at Sherpur PWSS at Amta-I Block under Uluberia Sub Division within Howrah Division, P.H.E.Dte.(Location-Kumarchak) | 869/HD | 10/02/2025 | 40 | AQUATECH ENGINEER | 14.16 | 0 | 0 | 100
630 | HOWRAH | Howrah Division | Sherpur Piped Water Supply Scheme , SM/18426 | New | Road restoration work with Bullah piling at Sherpur PWSS under Uluberia Sub Division under Howrah Division PHED. | 2494/HD | 26/05/2025 | 120 | S.M. CONSTRUCTION | 16.06 | 0 | 0 | 100
631 | HOWRAH | Howrah Division | Sherpur Piped Water Supply Scheme , SM/18426 | New | Material Requisition To Resource Division | 157/HD | 10/01/2025 | 0 | Resource Division | 37.03 | 0 | 0 | 0
632 | HOWRAH | Electrical | Sherpur Piped Water Supply Scheme , SM/18426 | New | Quotation money deposition for new service connection at Sherpur w/s scheme, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1008517850 Reference ID- 107030108 SM Code- 18426 |  | 16/04/2025 | 0 | WBSEDCL | 17.69 | 0 | 0 | 0
633 | HOWRAH | Howrah Division | Sherpur Piped Water Supply Scheme , SM/18426 | New | Sinking of 05 (Five) nos Big dia Tube wells, Construction of Switch rooms(5.4x3.6) for HW site and other TW sites, Boundary walls, Land Developments, Laying distribution system (UPVC & HDPE & DI) & Providing Functional Household Tap Connection (FHTC), Interconnection between tubewells and OHR and Construction of OHR of 700 cum and 400 cum capacity 20.0 m staging height along with pipe connection etc for SHERPUR PWSS in Amta-I Block and Augmentation of JOARGARH PWSS in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC=8807] | 3488/HD | 29/09/2023 | 900 | S.P. CONSTRUCTION | 1926.07 | 352.73 | 28.02 | 65
634 | HOWRAH | Howrah Division | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district , SM/13747 | New | Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Hizlok Head Work Site and 2nd TW Site at Hizlok PWSS of Bagnan-I Block of Howrah District under Howrah Division, P.H.E. Dte. (SM/13747) | 4034/HD | 17/09/2024 | 90 | AQUATECH ENGINEER | 28.95 | 3.84 | 13.27 | 45
635 | HOWRAH | Howrah Division | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district , SM/13747 | New | Preparation of DPR for Hijlok PWSS, Bagnan-I Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | 461/AE/USD | 15/09/2022 | 45 | DULAL MAJUMDER | 2.97 | 0 | 0 | 100
636 | HOWRAH | Howrah Division | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district , SM/13747 | New | Additional laying distribution pipeline with FHTC at Bagur & Paschim Bainan Mouza part of Paschim Bainan PWSS adjoining to Hizlak PWSS of Bagnan-I Block in Uluberia Sub-Division under Howrah Division, PHE Dte. | 4514/HD | 04/10/2024 | 45 | JOY CHANDI CONSTRUCTION | 48.54 | 34.23 | 41.35 | 100
637 | HOWRAH | Howrah Division | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district , SM/13747 | New | Material Requisition To Resource Division | 4864/HD | 22/11/2024 | 0 | Resource Division | 1.54 | 0 | 0 | 0
638 | HOWRAH | Electrical | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district , SM/13747 | New | Quotation for new service connection for Hijlak Piped Water Supply Scheme, PH NO- I in the district Howrah under Electrical Division, PHE Dte. (SM/13747), Reference Id- 106636949, Application no- 1007864377 | 257 | 03/07/2024 | 0 | WBSEDCL | 5.55 | 0 | 0 | 0
639 | HOWRAH | Electrical | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district , SM/13747 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hijlak water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 924/ED | 22/02/2023 | 922 | MENAKA ENTERPRISE | 20.27 | 0 | 0 | 40
640 | HOWRAH | Howrah Division | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district , SM/13747 | New | Work order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells & 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design & Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site HIjlak PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | 2696/HD | 24/07/2023 | 1096 | PRADIP KUMAR JATI | 293.89 | 75.84 | 25.81 | 1
641 | HOWRAH | Howrah Division | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district , SM/13747 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
642 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block , SM/07395 | Retrofitting | Retrofitting Chitnan Water Supply Scheme | W/120 | 20/07/2021 | 0 | ASHOKE GHOSH AND BROTHERS | 15.46 | 0 | 0 | 0
643 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block , SM/07395 | Retrofitting | Retrofitting Chitnan Water Supply Scheme |  | 19/04/2021 | 0 | JAHANGIR ALAM | 23.87 | 0 | 0 | 0
644 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block , SM/07395 | Retrofitting | Retrofitting Chitnan |  | 03/06/2021 | 0 | S.N ENTERPRISE | 26.88 | 0 | 0 | 0
645 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block , SM/07395 | Retrofitting | Retrofitting Chitnan Water Supply scheme | W/170 | 09/08/2021 | 0 | PRASANTA SANA | 19.78 | 0 | 0 | 0
646 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block , SM/07395 | Retrofitting | Retrofitting Chitnan | W/171 | 09/08/2021 | 0 | BOSE AND CO. | 26.83 | 0 | 0 | 0
647 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block , SM/07395 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) [Beral Mouza] [Number of FHTC to be provided (Approx) : 387] | 45/HD | 05/01/2021 | 30 | MS ASOKE GHOSH AND BROTHERS | 22.44 | 0 | 0 | 0
648 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block , SM/07395 | Retrofitting | Construction of Bounadry wall Chitnan Water supply scheme | BP-2022-23-71 | 14/06/2022 | 0 | M/S SARADA UDYOG | 2.14 | 0 | 0 | 0
649 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block , SM/07395 | Retrofitting | Construction of 35 nos stand post at in various place of Chitnan Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Part-I) | BP-2021-22-339 | 17/02/2022 | 0 | ANUP PAUL | 3.28 | 0 | 0 | 0
650 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block , SM/07395 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) [Mirgram Mouza] [Number of FHTC to be provided (Approx) : 415] | BP-2021-22-472 | 30/03/2022 | 0 | PRASANTA SANA | 4.79 | 0 | 0 | 0
651 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block , SM/07395 | Retrofitting | Work Order for Riverine effect over Construction of 400 m3 capacity and 20 mtr staging height RCC Over Head Reservoir including pile foundation & delivery inlet & outlet and overflow pipe connection and allied works as per departmental drawing (DRG No. ¿ PC-I/OHR/11/2012) at Chitnan water supply scheme under Uluberia Sub-Division, under Howrah Division PHE Dte |  | 20/07/2022 | 0 | S.N ENTERPRISE | 3.52 | 0 | 0 | 0
652 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block , SM/07395 | Retrofitting | Construction of 28 nos stand post at in various place of Chitnan Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Part-II) | BP-2021-22-338 | 17/02/2022 | 0 | ANUP PAUL | 2.63 | 0 | 0 | 0
653 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block , SM/07395 | Retrofitting | Work Order for Riverine effect over Construction of 400 m3 capacity and 20 mtr staging height RCC Over Head Reservoir including pile foundation & delivery inlet & outlet and overflow pipe connection and allied works as per departmental drawing (DRG No. ¿ PC-I/OHR/11/2012) at Chitnan water supply scheme under Uluberia Sub-Division, under Howrah Division PHE Dte | 160/HD | 25/01/2022 | 45 | S.N ENTERPRISE | 4.55 | 4.55 | 100 | 0
654 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Kanupat PWSS, Udaynarayanpur Block Under Uluberia Sub-Division of Howrah Division PHE Dte. | 2109/HD | 24/11/2021 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.05 | 3.05 | 100 | 0
655 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KANUPAT PWSS, UDAYNARAYANPUR BLOCK, HOWRAH DIST, UNDER CDD, PHE DTE. | 307/CMSD-I | 08/07/2022 | 15 | INDIA ENTERPRISE | 4.98 | 4.11 | 100 | 0
656 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT KANUPAT PWSS, UDAYNARAYANPUR BLOCK, HOWRAH DISTRICT UNDER CDD, PHE DTE. | 306/CMSD-I | 08/07/2022 | 15 | INDIA ENTERPRISE | 3.89 | 3.74 | 100 | 0
657 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBEWELL AT KANUPAT PWSS, UDAYNARAYANPUR BLOCK, HOWRAH DISTRICT UNDER CDD, PHE DTE. | 308/CMSD-I | 08/07/2022 | 15 | INDIA ENTERPRISE | 1.8 | 1.52 | 100 | 0
658 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
659 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kanupat water supply scheme, T.W. No. II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 1404/ED | 22/03/2023 | 90 | MAA KALI ENTERPRISE | 8.27 | 8.07 | 97.58 | 0
660 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 11.87 | 0 | 0 | 0
661 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | Construction of approach road cum internal pathway at HW site of Kanupat PWSS Udaynarayanpur Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 4133/HD | 23/09/2024 | 15 | BISWAJIT BAG | 6.64 | 0 | 0 | 0
662 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | Work Order for Augmentation of Kanupat Water Supply scheme by laying distribution system, providing functional house hold tap connection (FHTC) work with geo tagging by using Jal Swapna app, construction of RCC elevated reservior of capacity 200 m3 of staging height 20 mtr including soil investigation under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 1339/HD | 27/06/2022 | 548 | JAHANGIR ALAM | 216.52 | 216.5 | 100 | 90
663 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | Shifting and stacking of serviceable DI pipes and specials within the campus at Kanupat Store under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 737/AE/USD | 30/08/2024 | 25 | BISWAJIT BAG | 2.43 | 0.64 | 20.94 | 100
664 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | Display Board at different PWSS at Uluberia-II Udaynarayanpur Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 3218/AE/USD | 12/03/2024 | 30 | ABONTICA ENTERPRISE | 4.26 | 4.26 | 100 | 100
665 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Udaynarayanpur Block) (PART-A) | 4123/HD | 14/10/2025 | 30 | JHARNA ENTERPRISE | 4.79 | 0 | 0 | 0
666 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Kanupat. , SM/09350 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 0.92 | 0 | 0 | 0
667 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme , SM/06714 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) (for Kasmali Mouza(part) | 1617/HD | 09/11/2020 | 30 | S RAHA ENTERPRISE | 16.6 | 0 | 0 | 0
668 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme , SM/06714 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | 844363 | 25/03/2021 | 0 | BANERJEE ENTERPRISE | 8.99 | 0 | 0 | 0
669 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme , SM/06714 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | 844386 | 26/03/2021 | 0 | S RAHA ENTERPRISE | 15.64 | 0 | 0 | 0
670 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme , SM/06714 | Retrofitting | Survey and Collection of houshold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme | 844375 | 25/03/2021 | 0 | STEELCONC AND ASSOCIATES | 2.17 | 0 | 0 | 0
671 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme , SM/06714 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection (FHTC) from existing distribution system of Kasmali pipe water supply scheme under Amta-II Block under Howrah Division, PHE Dte. | 844320 | 24/03/2022 | 0 | S RAHA ENTERPRISE | 1.51 | 0 | 0 | 0
672 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme , SM/06714 | Retrofitting | Construction of balance portion of boundary wall at 2nd TW site of Kasmali W/S scheme in Uluberia Sub-division, under Howrah Division P.H.E Dte. | 477/AE/USD | 16/09/2022 | 45 | M/S HOWRAH CONSTRUCTION | 3.34 | 3.29 | 98.58 | 0
673 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme , SM/06714 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) (for Kasmali Mouza (part) | 1607/HD | 09/11/2020 | 30 | CONSTRUCTION CORNER | 28.68 | 5.44 | 100 | 100
674 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme , SM/06714 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) (for Kasmali Mouza(part) | 1608/HD | 09/11/2020 | 30 | CONSTRUCTION CORNER | 28.67 | 1.76 | 100 | 100
675 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme , SM/06714 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) & School, AWC from existing distribution system at Kharigeria mouza of Kasmali W/S scheme under Amta-II Block under Howrah Division, PHE Dte. | 353/AE/USD | 22/08/2022 | 45 | BANERJEE ENTERPRISE | 1.85 | 1.74 | 100 | 0
676 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme , SM/06714 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-3). | 435/AE/USD | 13/09/2022 | 45 | MA MANASA CONSTRUCTION | 4.78 | 4.47 | 100 | 0
677 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme , SM/06714 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-6). | 438/AE/USD | 13/09/2022 | 45 | MA MANASA CONSTRUCTION | 4.81 | 4.83 | 100 | 0
678 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme , SM/06714 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-7). | 439/AE/USD | 13/09/2022 | 45 | MA MANASA CONSTRUCTION | 4.77 | 4.75 | 100 | 0
679 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme , SM/06715 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-F) (for Khari Geria Mouza part) | 1620/HD | 09/11/2020 | 30 | BANERJEE ENTERPRISE | 9.49 | 0 | 0 | 0
680 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme , SM/06715 | Retrofitting | Mass Awarness generation and IEC activities. | 844313 | 23/12/2021 | 0 | PRADIP KUMAR JATI | 42 | 0 | 0 | 0
681 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme , SM/06715 | Retrofitting | Development of land, plinth protection of boundary wall construction of pathway and other allied works of Chitanan W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 2173/HD | 01/12/2021 | 30 | S.N ENTERPRISE | 4.13 | 3.54 | 85.73 | 0
682 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme , SM/06715 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (for Nignan Mouza(Part) | 1618/HD | 09/11/2020 | 30 | M/S ASHIRBAD (INDIA) | 29.09 | 2.05 | 100 | 100
683 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme , SM/06715 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (for Khari Geria Mouza part) | 1619/HD | 09/11/2020 | 30 | N. G ENGINEERING | 29.1 | 1.97 | 100 | 100
684 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme , SM/06715 | Retrofitting | Work Order for Replacement of distribution network with higher dia pipes at the closed vicinity of the Head work site of Uttar Khoriop Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 1057/HD | 06/05/2022 | 30 | JAHANGIR ALAM | 4.83 | 4.8 | 100 | 0
685 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme , SM/06715 | Retrofitting | Work Order for construction of outlet drawing system with 160 mm dia HDPE pipe including interconnection of overflow & washout of newly constructed OHR of Uttar Khoriop w/s Scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 1058/HD | 06/05/2022 | 30 | JAHANGIR ALAM | 3.04 | 3.02 | 100 | 0
686 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme , SM/06715 | Retrofitting | Supplying, fitting, fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division, P.H.E. Dte. | 4832/HD | 20/11/2024 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
687 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 79-80-81-82-92, 79-49-29 under Uluberia-II block under Howrah Division, PHE Dte. (Part-C) | 827/HD | 11/04/2022 | 30 | A.N ROY & CO | 4.72 | 3.39 | 100 | 0
688 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for providing Functional Household Tap Connection (FHTC) at Augumentation of Surikhali Water Supply Scheme (Zone-II) at under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) | 841/HD | 11/04/2022 | 30 | SK ANISUR | 4.98 | 4.52 | 100 | 0
689 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 92-93-94-95-96-97-98, 96-99-100-101-102-103 under Uluberia-II block under Howrah Division, PHE Dte. (Part-B) | 826/HD | 11/04/2022 | 30 | ARINDAM ENTERPRISE | 4.77 | 3.13 | 100 | 0
690 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 34-35-36-37-38-39, 38-40-41-42-44-45-47-48 under Uluberia-II block under Howrah Division, PHE Dte. (Part-G) | 831/HD | 11/04/2022 | 30 | A.B. ENTERPRISE | 4.81 | 2.78 | 100 | 0
691 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 8-9-10-11-12-13-14-15-16-17, 9-21-18-19-20 under Uluberia-II block under Howrah Division, PHE Dte. (Part-E) | 829/HD | 11/04/2022 | 30 | SUNIL ENTERPRISE | 4.71 | 4.38 | 100 | 0
692 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 21-26-31-32-33-34, 13-18 under Uluberia-II block under Howrah Division, PHE Dte. (Part-F) | 830/HD | 11/04/2022 | 30 | MONIRUL ISLAM | 4.82 | 2.55 | 49.6 | 0
693 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 43-46-50 under Uluberia-II block under Howrah Division, PHE Dte. (Part-J) | 834/HD | 11/04/2022 | 30 | JOY GURU TRADING | 4.54 | 3.11 | 100 | 0
694 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 87-88-89-91-90-, 85-87, 83-85-86, 83-84, 79-83under Uluberia-II block under Howrah Division, PHE Dte. (Part-A) | 825/HD | 11/04/2022 | 30 | DEBABRATA CHAKRABORTY | 4.37 | 3.72 | 100 | 0
695 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 11-23-25-29-30 under Uluberia-II block under Howrah Division, PHE Dte. (Part-D) | 828/HD | 11/04/2022 | 30 | BINOY KOLEY | 4.83 | 2.68 | 100 | 0
696 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 56-57-54-52, 54-55, 57-62-64, 56-58-59-60-61-65-62, 65-66 under Uluberia-II block under Howrah Division, PHE Dte. (Part-K) | 835/HD | 11/04/2022 | 30 | SHIV SHAKTI CONSTRUCTION | 4.75 | 2.2 | 100 | 0
697 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section62-68-69-72-75-76-77-78, 61-63, under Uluberia-II block under Howrah Division, PHE Dte. (Part-L) | 836/HD | 11/04/2022 | 30 | CONSTRUCTION UDOUG | 4.67 | 1.95 | 100 | 0
698 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for providing Functional Household Tap Connection (FHTC) at Augumentation of Surikhali Water Supply Scheme (Zone-II) at under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) | 839/HD | 11/04/2022 | 30 | APEX ENGINEERING | 4.97 | 4.43 | 100 | 0
699 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for providing Functional Household Tap Connection (FHTC) at Augumentation of Surikhali Water Supply Scheme (Zone-II) at under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-B) | 840/HD | 11/04/2022 | 30 | S.M. CONSTRUCTION | 4.97 | 4.39 | 100 | 0
700 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 73-74-75-76-70-73-67-70-71-67-47-71 under Uluberia-II block under Howrah Division, PHE Dte. (Part-M) | 837/HD | 11/04/2022 | 30 | NAUTANDAS & CO. | 4.8 | 4.1 | 100 | 0
701 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 1-2-3-4-5-6-7-8, 2-22-23-24-25 under Uluberia-II block under Howrah Division, PHE Dte. (Part-H) | 832/HD | 11/04/2022 | 30 | S.S ENTERPRISE | 4.83 | 4.12 | 100 | 0
702 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Surikhali PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | BP-2021-22-364 | 28/02/2022 | 0 | APEX ENGINEERING | 3.47 | 0 | 0 | 0
703 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
704 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 24-27-28, 27-43-51-52-53, 51-56 under Uluberia-II block under Howrah Division, PHE Dte. (Part-I) | 833/HD | 11/04/2022 | 30 | NAG ENTERPRISE | 4.73 | 3.49 | 73.89 | 0
705 | HOWRAH | Electrical | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Surikhali water supply scheme, Zone-I, P.H. No. II, District- Howrah under Electrical Division, PHE Dte. | 604/ED | 02/02/2023 | 90 | D. K. ELECTRIC | 10.99 | 10.51 | 95.69 | 0
706 | HOWRAH | Electrical | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Surikhali water supply scheme, Zone-I, P.H. No. III & IV, District- Howrah under Electrical Division, PHE Dte. | 3443/ED | 11/08/2023 | 90 | D. K. ELECTRIC | 21.98 | 0 | 0 | 0
707 | HOWRAH | Electrical | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Hiring of 1 (One) Diesel Luxury Taxi on contract carriage for office of the Assistant Engineer-II, ED, PHED | 215_ae_ed | 24/03/2023 | 365 | DILIP KUMAR GHOSH | 5 | 0.39 | 7.84 | 20
708 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC & DI pipeline & providing Functional Household Tap Connection (FHTC) at Augmentation of Surikhali Water Supply Scheme (Zone-I) under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) | 563/HD | 14/03/2022 | 45 | MODERN CONSTRUCTION | 84.8 | 82.68 | 100 | 100
709 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Interconnection for 2nd TW and 1st Tube well (HW site) at Augumentation of Surikhali Water Supply scheme (Zone-I) in Uluberia-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 838/HD | 11/04/2022 | 30 | MONIRUL ISLAM | 3.45 | 3.02 | 100 | 100
710 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Sinking of 3 (three) nos PVC big dia Tube well 250 mm x 150 mm dia of 250 mtr deep for Augmentation of Surikhali W/S scheme at Uluberia-II Block in Uluberia Sub-Division under Howrah Division P.H.E Dte. | 1515/HD | 22/07/2022 | 30 | NADIA TUBEWELLS | 39.12 | 21.8 | 100 | 0
711 | HOWRAH | Electrical | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Surikhali water supply scheme, Zone-I, P.H. No. I, District- Howrah under Electrical Division, PHE Dte. | 2104/HMSD | 24/11/2022 | 30 | M.G. CONSTRUCTIONS & CO. | 4.94 | 4.86 | 100 | 0
712 | HOWRAH | Electrical | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Supply, Delivery of actuator operated butterfly valvefor Augmentation of Surikhali W/S. Sch. Z-I, PH-I | 2156//HMSD | 30/11/2022 | 90 | M.G. CONSTRUCTIONS & CO. | 0.99 | 0.99 | 100 | 100
713 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Material Requisition To Resource Division | 407/HD | 24/02/2022 | 0 | Resource Division | 7.99 | 0 | 0 | 0
714 | HOWRAH | Electrical | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Hiring of diesel car | 05 | 13/04/2023 | 0 | TRIDIP SARKAR | 0.4 | 0 | 0 | 0
715 | HOWRAH | Electrical | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Hire Charges Bill of V.No.- WB-15C-5554 for office of the E/E. PHED | 591*AE-II/ED | 18/08/2023 | 365 | DILIP KUMAR GHOSH | 5 | 2.29 | 45.72 | 30
716 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Work Order for Laying UPVC pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Surikhali Water Supply Scheme (Zone-I) at section (103-106-109-113-126-129-130-137-140-143-148-153-107-104) under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte.(Part-B) | 564/HD | 14/03/2022 | 30 | JOY GURU TRADING | 12.27 | 11.34 | 100 | 100
717 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Extension of HDPE pipe line with FHTC connections at Vill - Surikhali under Surikhali Piped Water Supply Scheme under Uluberia-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1308/AE/USD | 20/12/2024 | 20 | CREATIVE CONSTRUCTION | 0.96 | 0 | 0 | 100
718 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali , SM/09429 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
719 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Mankur & Deulgram PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 2121/HD | 24/11/2021 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.58 | 4.58 | 100 | 0
720 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
721 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Work Order for alternative laying of damaged UPVC pipe,construction of RCC stand post, valve chamber and other allied work at Mankur Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 670/HD | 23/03/2022 | 30 | S.S ENTERPRISE | 4.9 | 4.86 | 99.23 | 0
722 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mankur Deulgram water supply scheme, T.W. No. III, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 3441/ED | 11/08/2023 | 90 | M.S.C. ENTERPRISE | 11.5 | 0 | 0 | 0
723 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Material Requisition To Resource Division | 2753/HD | 28/07/2023 | 0 | Resource Division | 15.4 | 0 | 0 | 0
724 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Material Requisition To Resource Division | 4695/HD | 26/12/2023 | 0 | Resource Division | 48.28 | 0 | 0 | 0
725 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mankur Deulgram water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 914/ ED | 22/02/2023 | 90 | A.G. ENTERPRISE | 23.02 | 11.14 | 48.39 | 50
726 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Mankur Deulgram PWSS at Bagnan-I Block of Howrah District under Howrah Division, P. H. E. Dte. | 1833/HD | 08/09/2022 | 40 | AUXILIARY TUBEWELL DRILLERS | 35.39 | 32.28 | 100 | 100
727 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Temporary Approach road towards Head works site for Augmentation of Makur Deulgram PWSS of Bagnan-I Block under Uluberia Sub Division under Howrah Divison PHE Dte. | 2037/AE/USD | 13/02/2024 | 60 | NOBLE ENTERPRISE | 2 | 1.91 | 100 | 100
728 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at 3rd tube well site of Mankur Deulgram PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | 2036/AE/USD | 13/02/2024 | 60 | JSZ GLOBAL | 4.85 | 4.65 | 100 | 100
729 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Manku Bakshihat Road from 0.00 Km to 1.50 Km (in streches) Restoration of Head Crust due to laying of water Pipelines from PHE dte end for Augmentation of Mankur Deulgram piped water supply scheme under Highway Division P.W Roads Dte in the district Howrah during the year 2023-2024 | BP-2024-25-124 | 11/06/2024 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 2.08 | 0 | 0 | 0
730 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Quotation for new service connection for Augmentation of Mankur Deulgram Water Supply Scheme, PH NO- II in the district Howrah under Electrical Division, PHE Dte. ( SM/09349), Reference Id- 106530323, Application no- 1007620510 | 38 | 09/04/2024 | 0 | WBSEDCL | 10.4 | 0 | 0 | 0
731 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Quotation for new service connection of Mankur Deulgram W/S. Sch. PH-II | 745 | 08/02/2024 | 0 | WBSEDCL | 6.67 | 0 | 0 | 0
732 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Work Order for Laying of Distribution Pipe Lines(UPVC & DI) with allied works and Providing Functional Household Tap Connection(FHTC). Interconnection between Tube wells and construction of switch room (5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site for Augmentation of MANKUR-DEULGRAM Water Supply Scheme In Bagnan-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 2746/HD | 15/12/2022 | 961 | S.P. CONSTRUCTION | 674.25 | 437.38 | 64.87 | 60
733 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.85 | 0 | 0 | 0
734 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram , SM/09349 | Augmentation | Construction of 750 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation at Mankur Deulgram PWSS at Bagnan-I Block under Uluberia Sub-Division PHE Dte under Howrah Division PHE Dte. | 895/HD | 27/02/2024 | 960 | KALPANA TRADERS | 192.53 | 13.82 | 7.18 | 20
735 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Mahishadal Block of Purbo Midnapore District under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Mayachar (Part-1) | 1207/HD | 03/06/2021 | 15 | PRADIP KUMAR JATI | 4.79 | 4.79 | 100 | 0
736 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order of Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Shyampur-I & II Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Saibania under DM Ghat-II GP | 1216/HD | 04/06/2021 | 15 | NEW MAA TARA CONSTRUCTION | 4.62 | 4.62 | 100 | 0
737 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Amrajole under Kalyanpur GP | 1217/HD | 04/06/2021 | 15 | UNIVERSAL CONSTRUCTION | 4.83 | 4.83 | 100 | 0
738 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Kalyanpur Masjid, Rotai under Kalyanpur GP | 1219/HD | 04/06/2021 | 15 | UNIVERSAL CONSTRUCTION | 4.83 | 4.83 | 100 | 0
739 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Paschim Bainan & Purba Bainan under Bainan GP (Part-2) | 1253/HD | 07/06/2021 | 15 | ADITYA HAZRA | 1.42 | 1.42 | 100 | 0
740 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Temporary Supply of Drinking Water by PVC Water Tanks from different PWSS of various locations affected due to 'YASSH' Supercyclone at Domjur, Panchla, Jagatballavpur Block under Howrah Division, PHE Dte. | Camp-02/HD | 01/06/2021 | 5 | M/S ASHIRBAD (INDIA) | 2.31 | 2.31 | 100 | 0
741 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Special renovation of damaged distribution Pipeline due to Cyclone YASH within the command area of Dakhin Durgapur w/s scheme under Howrah Division P.H.E Dte. | 220/AE/USD | 11/07/2022 | 30 | PRADIP KUMAR JATI | 2.75 | 2.75 | 100 | 0
742 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Renovation of Pipeline damaged due to "Yash Cyclone" under Katagachi w/s scheme under Howrah Division P.H.E Dte. | 222/AE/USD | 11/07/2022 | 30 | ASHOKE ENGINEERING WORKS | 1.18 | 1.18 | 100 | 0
743 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Renovation of Pipeline damaged due to "Yash Cyclone" under Bhagabanpur w/s scheme under Howrah Division P.H.E Dte. | 221/AE/USD | 11/07/2022 | 30 | FARID UDDIN AHMED | 1.86 | 1.86 | 100 | 0
744 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site due to severe Cyclone "Yassh" of Shyampur Zone- II w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | 204/AE/USD | 11/07/2022 | 30 | NAG ENTERPRISE | 3.95 | 3.84 | 97.06 | 0
745 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Renovation of Pipeline damaged due to "Yash Cyclone" under Silampur w/s scheme under Uluberia Sub-Division under Howrah Division P.H.E Dte. | 216/AE/USD | 11/07/2022 | 30 | MA- SITALA ENGINEERING WORKS. | 0.81 | 0.66 | 81.59 | 0
746 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for repairing of Pump house and Store room, boundary wall and ancillary work at 2nd TW site due to severe Cyclone "Yassh" of Belari w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | 206/AE/USD | 11/07/2022 | 30 | KALIDAS ENTERPRISE | 3.83 | 3.67 | 95.84 | 0
747 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Renovation of Pipeline damaged due to "Yash Cyclone" under Nischintapur w/s scheme under Howrah Division P.H.E Dte. | 218/AE/USD | 11/07/2022 | 30 | DEV DAS SHAW | 1.76 | 1.75 | 99.52 | 0
748 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Special renovation of pipeline due to Cyclonic YASH at Deora High School to Renasa KG school, Deora Keopara pond side, Deora Atbala Bridge of Deora Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 219/AE/USD | 11/07/2022 | 30 | S.S ENTERPRISE | 1.55 | 1.55 | 100 | 0
749 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Shyampur-I & II Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Bania under DM Ghat-I GP | 1209/HD | 03/06/2021 | 15 | NEW MAA TARA CONSTRUCTION | 4.83 | 4.83 | 100 | 0
750 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Baramahal under Kalyanpur GP | 1218/HD | 04/06/2021 | 15 | UNIVERSAL CONSTRUCTION | 4.83 | 4.83 | 100 | 0
751 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Mahishamori under Tajpur GP | 1254/HD | 07/06/2021 | 15 | ADITYA HAZRA | 4.44 | 4.44 | 100 | 0
752 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Renovation of Pipeline damaged due to "Yash Cyclone" under Belari w/s scheme under Howrah Division P.H.E Dte. | 217/AE/USD | 11/07/2022 | 30 | MA- SITALA ENGINEERING WORKS. | 1.17 | 1.17 | 100 | 0
753 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Mahishadal Block of Purbo Midnapore District under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Mayachar (Part-2) | 1208/HD | 03/06/2021 | 15 | PRADIP KUMAR JATI | 1.77 | 1.77 | 100 | 0
754 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Alternative laying of distribution pipe line of Hallyan w/s scheme due to new construction of PMGSY Road / BGSY Road under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 2326/HD | 20/12/2021 | 30 | JAHANGIR ALAM | 10.94 | 10.29 | 100 | 0
755 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Paschim Bainan & Purba Bainan under Bainan GP (Part-1) | 1252/HD | 07/06/2021 | 15 | ADITYA HAZRA | 4.8 | 4.8 | 100 | 0
756 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Laying of distribution pipe line for providing emergent water supply within the Howrah Zilla Parisad Bunglow campus for Silampur Water Supply Scheme under Shyampur-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. ( SL NO.-3 ) | 374/AE/USD | 30/08/2022 | 45 | MJ ENTERPRISE | 1.88 | 1.87 | 100 | 0
757 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site due to severe Cyclone "Yassh" of Mellock Zone-I w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | 202/AE/USD | 11/07/2022 | 30 | SR TRADING CORPORATION | 3.47 | 3.45 | 100 | 0
758 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Sinking of 1 (one) no Replaced PVC big dia Tube well 300 mm x 200 mm dia of 240 mtr deep at Bagnan (Zone-I) under Bagnan Water Supply Scheme under Uluberia Sub-Division under Howrah Division P.H.E Dte. | 1514/HD | 22/07/2022 | 20 | LOKENATH ENTERPRISES | 15.23 | 14.62 | 100 | 0
759 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Big Dia Tube at Mugkalyan Water Supply Scheme |  | 13/09/2022 | 0 | EXEECUTIVE ENGINEER, CENTRAL DRILLING DIVISION, PHE DTE | 11.2 | 0 | 0 | 0
760 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for repairing of boundary wall, drain and internal pathway at Head work site damaged due to Cyclonic Yassh of Bagnan W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | BP-2022-23-110 | 06/07/2022 | 0 | BISWAJIT BAG | 4.95 | 0 | 0 | 0
761 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Supply of Temporary drinking water supply by PVC water tankers(capacity 1000 liters) to flood affected areas of Tajpur GP under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -August 2021] | AE/USD(CAMP)/14 | 06/08/2021 | 7 | DEBABRATA CHAKRABORTY | 0.42 | 0 | 0 | 0
762 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Disinfection of different type Hand tube wells in flood affected areas of Debipur GP & Harishpur GP of Udaynarayanpur Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/USD(CAMP)/22 | 08/10/2021 | 7 | ADITYA HAZRA | 2.37 | 0 | 0 | 0
763 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Disinfection of different type hand tube wells in flood affected areas of Kanupat Monsukha GP & Sonatala GP of Udaynarayanpur Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood October 2021] | AE/USD(CAMP)/23 | 08/10/2021 | 7 | BINOY KOLEY | 3.41 | 0 | 0 | 0
764 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Gazipur GP, Tajpur GP & Nopara(Part) and minor Repair of Hand Tube well of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood (2nd Phase) -August 2021] | AE/USD(CAMP)/13 | 06/08/2021 | 7 | SITALAMATA PUMP CENTRE | 0.81 | 0 | 0 | 0
765 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Binola Krishna Bati GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/USD(CAMP)/25 | 08/10/2021 | 7 | M/S AHAMED CONSTRUCTION | 1.28 | 0 | 0 | 0
766 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Bhatora GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/USD(CAMP)/18 | 08/10/2021 | 7 | DEV DAS SHAW | 1.33 | 0 | 0 | 0
767 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Thalia GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood(2nd Phase) -August 2021] | AE/USD(CAMP)/09 | 06/08/2021 | 7 | DEV DAS SHAW | 1.28 | 0 | 0 | 0
768 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work order for Disinfection of different type of Hand tube wells in flood affected areas of Amragori GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood(2nd Phase) -August 2021] | AE/USD(CAMP)/10 | 06/08/2021 | 7 | M/S AHAMED CONSTRUCTION | 1.71 | 0 | 0 | 0
769 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Ghoraberia Chitnan GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/USD(CAMP)/19 | 08/10/2021 | 7 | DEV DAS SHAW | 1.33 | 0 | 0 | 0
770 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Jhamti GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/USD(CAMP)/28 | 08/10/2021 | 7 | ADITYA HAZRA | 0.95 | 0 | 0 | 0
771 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work order for Disinfection of different type of Hand tube wells in flood affected areas of Thalia GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/USD(CAMP)/26 | 08/10/2021 | 7 | DEV DAS SHAW | 1.23 | 0 | 0 | 0
772 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Amragori GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/USD(CAMP)/27 | 08/10/2021 | 7 | DEV DAS SHAW | 1.33 | 0 | 0 | 0
773 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work order for Disinfection of different type of Hand tube wells in flood affected areas of Binola Krishna Bati GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood(2nd Phase) -August 2021] | AE/USD(CAMP)/08 | 06/08/2021 | 7 | DEV DAS SHAW | 1.04 | 0 | 0 | 0
774 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Disinfection of different type Hand tube wells in flood affected areas of Harali and RDA GP of Udaynarayanpur Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/USD(CAMP)/24 | 08/10/2021 | 7 | BINOY KOLEY | 4.82 | 0 | 0 | 0
775 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Supply of Temporary drinking water supply by PVC water tankers(capacity 1000 liters) to flood affected areas of Bagnan-II GP under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -August 2021] | AE/USD(CAMP)/16 | 06/08/2021 | 7 | JAHANGIR ALAM | 0.42 | 0 | 0 | 0
776 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Bhatora GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -August 2021] | AE/USD(CAMP)/01 | 05/08/2021 | 7 | M/S AHAMED CONSTRUCTION | 1.23 | 0 | 0 | 0
777 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for repairing of Pump house and Store room boundary wall and ancillary work of HW site due to severe Cyclone "Yassh" of Belari w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | 205/AE/USD | 11/07/2022 | 30 | SHRI RANISATI VENTURES | 3.25 | 0 | 0 | 0
778 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for renovation of boundary wall of boundary wall at 3rd TW Site due to severe Cyclone "Yassh" of Baikhali W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 213/AE/USD | 11/07/2022 | 30 | S RAHA ENTERPRISE | 3.08 | 3.03 | 100 | 0
779 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for renovation of boundary wall at 2nd TW Site due to severe Cyclone "Yassh" of Mellock (Z-I) W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 214/AE/USD | 11/07/2022 | 30 | BANERJEE ENTERPRISE | 4.14 | 4.25 | 100 | 0
780 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for Reparing of Pipeline damaged due to "Yash Cyclone" under Shyampur w/s scheme under Howrah Division P.H.E Dte. | 223/AE/USD | 11/07/2022 | 30 | NAG ENTERPRISE | 1.78 | 1.73 | 100 | 0
781 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for repairing of boundary wall and Pump Houses at HW, 2nd TW and 3rd TW Site due to severe Cyclone "Yassh" of Dakhin Durgapur W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 207/AE/USD | 11/07/2022 | 30 | S.M. CONSTRUCTION | 4.83 | 4.28 | 100 | 0
782 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site due to severe Cyclone "Yassh" of kalinagar w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | 208/AE/USD | 11/07/2022 | 30 | SK ANISUR | 4.83 | 2.9 | 100 | 0
783 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for renovation of Pump house and boundary wall at HW Site & 2nd Tw site due to severe Cyclone "Yassh" of Deuli W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 211/AE/USD | 11/07/2022 | 30 | NEW MAA TARA CONSTRUCTION | 4.84 | 4.91 | 100 | 0
784 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Repairing of Pump house and Store room and ancillary work of 3rd TW site due to severe Cyclone ¿Yassh¿ of Baikhali w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | 412/AE/USD | 07/09/2022 | 45 | S RAHA ENTERPRISE | 2.04 | 1.97 | 100 | 0
785 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Emergent repairing of Sub-Division office building and Rest shade within the campus of Uluberia Sub-Division office which were badly damaged due to Super cyclone Amphan & Yash of Bagnan W/S scheme in Uluberia Sub-Division, under Howrah Division P.H.E Dte. (SL NO.-3) | 385/AE/USD | 30/08/2022 | 45 | PRIYANKA ENTERPRISE | 4.58 | 4.52 | 100 | 0
786 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for repairing of Pump house and Store room, Boundary wall and ancillary work of HW site and 2nd TW site due to severe Cyclone "Yassh" of Bhagabanpur w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | 209/AE/USD | 11/07/2022 | 30 | A.B. ENTERPRISE | 4.75 | 3.65 | 100 | 0
787 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Repairing of pipeline damaged due to "Yash Cyclone" under Shyampur Zone-II w/s scheme under Howrah Division P.H.E. Dte.( SL NO.- 1 ) | 372/AE/USD | 30/08/2022 | 45 | NAG ENTERPRISE | 2.51 | 2.48 | 100 | 0
788 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Repairing of the Sub-Divisional office building and Rest shade which were damaged due to cyclonic storm "Yash" under Uluberia Sub-Division, under Howrah Division P.H.E Dte. (Phase-II). (SL NO.- 2) | 384/AE/USD | 30/08/2022 | 45 | BISWAJIT BAG | 4.85 | 4.84 | 100 | 0
789 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for repairing of boundary wall, drain and internal pathway at Head work site damaged due to Cyclonic Yassh of Bagnan W/S scheme in Uluberia Sub-Division under Howrah Division P.H.E. Dte. | 164/AE/USD | 28/06/2022 | 45 | BISWAJIT BAG | 4.85 | 4.91 | 100 | 0
790 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for renovation of boundary wall and Pump houses at HW Site & 2nd TW site due to severe Cyclone "Yassh" of Katagachi W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 212/AE/USD | 11/07/2022 | 30 | ASHOKE ENGINEERING WORKS | 4.82 | 3.33 | 100 | 0
791 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site due to severe Cyclone "Yassh" of Baikhali w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | 411/AE/USD | 07/09/2022 | 45 | KALIDAS ENTERPRISE | 4.84 | 4.65 | 100 | 0
792 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for renovation of boundary wall at HW Site due to severe Cyclone "Yassh" of Mellock (Z-I) W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 215/AE/USD | 11/07/2022 | 30 | ALLSOMA CONSTRUCTION | 4.16 | 4.17 | 100 | 0
793 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site due to severe Cyclone "Yassh" of Shyampur Zone-I w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | 203/AE/USD | 11/07/2022 | 30 | JAHANGIR ALAM | 3.5 | 3.38 | 100 | 0
794 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte , SM/09002 | Disaster | Work Order for renovation of boundary wall at 2nd Tw Site due to severe Cyclone "Yassh" of Silampur W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 210/AE/USD | 11/07/2022 | 30 | MA- SITALA ENGINEERING WORKS. | 4.38 | 4.37 | 100 | 0
795 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 35.16 | 0 | 0 | 0
796 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
797 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Maju PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte | BP-2021-22-407 | 14/03/2022 | 0 | STEELCONC AND ASSOCIATES | 4.28 | 0 | 0 | 0
798 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Maju PWSS at Jagatballavpur Block of Howrah District under Howrah Division, P. H. E. Dte. | 1835/HD | 08/09/2022 | 40 | B K ENTERPRISE | 35.32 | 33.02 | 100 | 0
799 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 62.17 | 0 | 0 | 0
800 | HOWRAH | Electrical | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Quotation bill for new service connection at Aug. of Maju Khetra W/S. Sch. TW-III | 172 | 28/02/2023 | 0 | WBSEDCL | 3.58 | 0 | 0 | 0
801 | HOWRAH | Electrical | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Quotation Bill for New Service Connection at Maju W/S. Sch. TW-IV | 187 | 13/03/2023 | 0 | WBSEDCL | 3.06 | 0 | 0 | 0
802 | HOWRAH | Electrical | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAJU PIPED W/S SCHEME, T.W. No. I (Replacement), Block: Jagatballavpur, District - Howrah under JJM Program under Electrical Division PHE Dte. | 1461/ED | 25/07/2024 | 90 | BISALAXMI ENTERPRISE | 11.31 | 10.08 | 89.18 | 30
803 | HOWRAH | Electrical | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Maju water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 913/ED | 22/02/2023 | 90 | POLYCON ENGINEERS | 21.5 | 21.49 | 100 | 30
804 | HOWRAH | Electrical | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Maju water supply scheme, T.W. No. III, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 3440/ED | 11/08/2023 | 90 | POLYCON ENGINEERS | 10.75 | 10.47 | 100 | 40
805 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Construction of R.C.C Slab Culvert, Construction of 1(one) no. Pump House (5.40m x 3.60m), construction of 2(Two) nos. boundary wall, construction of approach road and land Development at 2nd tubewell site and allied pipe laying work (DI) for connecting tubewell with the distribution main at Maju PWSS under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 2836/HD | 20/06/2024 | 180 | SAMIRON GHOSH | 51.95 | 40.2 | 86.79 | 50
806 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Sinking 2 nos. 250 X 150 mm dia and 240 m deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30 m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Maju PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. | 1309/HD | 14/03/2024 | 60 | ACME CONSTRUCTION | 29.18 | 27.65 | 100 | 100
807 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Work Order for Construction Of 700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir with Rising Main Pipeline Work & Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) with Boundary Wall and Pump House and 2 nos. Canal Crossing of Augmentation of Maju PWSS Jagatballavpur Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | 2095/HD | 12/10/2022 | 910 | SAMIRON GHOSH | 838.17 | 572.01 | 71.84 | 50
808 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Work Order for Additional Laying Distribution Pipeline & allied works of Maju PWSS at J.Bpur Block of Howrah District under Howrah Division, P. H. E. Dte. | 1785/HD | 28/04/2023 | 479 | SAMIRON GHOSH | 322.25 | 305.79 | 97.72 | 100
809 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Fedder line from Node Point J-257 to J-248 of Maju PWSS at J.B.Pur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. | 1121/HSSD | 30/10/2024 | 60 | SAMIRON GHOSH | 4.4 | 0 | 0 | 100
810 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Jagatballavpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4814/HD | 19/11/2024 | 510 | HORIZEN | 10.11 | 0 | 0 | 56
811 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. , SM/10035 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Sealdanga PWSS [SM/14866], Maju PWSS [SM/10035], Islampur PWSS [SM/09428] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 231/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
812 | HOWRAH | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | FUEL CHARGES FOR CAR NO. WB-25H-1114, WB-05-2798, WB-04H-6870 & WB-25H-5187. | 713/CDD | 26/07/2022 | 30 | MIRA SERVICE STATION | 1.08 | 1.08 | 100 | 0
813 | HOWRAH | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) (AMBASSADOR / EQUIVALENT) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE SEMC-II, PHE DTE. | 236/CMSD-I (D) | 14/12/2021 | 15 | SIDDHARTHA CHATTERJEE | 0.95 | 0.86 | 90.93 | 0
814 | HOWRAH | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | PROVIDING ADDITIONAL BENTONITE FOR CONSTRUCTION OF TUBE WELL AT KANPUR W/S SCHEME (Z-II, TW-II) AMTA-I BLOCK AND OTHERS UNDER CDD, PHE DTE. | 198/CMSD-I(D) | 16/06/2022 | 3 | M/S PRACHI ENGINEERING | 0.89 | 0.59 | 66.67 | 0
815 | HOWRAH | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 220 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AUG OF KANPUR W/S SCHEME (Z-II, TW-II) AMTA-I BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 450/CDD | 24/05/2022 | 30 | M/S SAIKAT ENTERPRISE | 13.21 | 11.74 | 100 | 0
816 | HOWRAH | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 220 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AUG. OF KANPUR W/S SCHEME (Z-II, HW) AMTA-I BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 451/CDD | 24/05/2022 | 30 | M/S SAIKAT ENTERPRISE | 13.21 | 11.57 | 100 | 0
817 | HOWRAH | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | PROVIDING TUBE WELL MATERIALS OF 200 MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KANPUR (Z-II) W/S SCHEME, UNDER HOWRAH DISTRICT, CMSD-II (D), CDD, PHE DTE. | 273/CMSD-II (D) | 01/06/2022 | 15 | M/S PRACHI ENGINEERING | 4.83 | 3.63 | 100 | 0
818 | HOWRAH | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 220 MTRS DEPTH) BY KORES RIG MACHINE FOR KANPUR (Z-II) W/S SCH, AMTA BLOCK UNDER HOWRAH DISTRICT, CMSD-II (D), CDD, PHE DTE. | 271/CMSD-II (D) | 01/06/2022 | 15 | M/S PRACHI ENGINEERING | 3.53 | 3.38 | 100 | 0
819 | HOWRAH | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | PROVIDING TUBE WELL MATERIALS OF 300 MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KANPUR (Z-II) W/S SCH, UNDER HOWRAH DISTRICT, CMSD-II (D), CDD, PHE DTE. | 272/CMSD-II (D) | 01/06/2022 | 15 | M/S PRACHI ENGINEERING | 4.81 | 4.63 | 100 | 0
820 | HOWRAH | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR HANRAL W/S SCH, POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 293/CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 11.23 | 0.15 | 100 | 100
821 | HOWRAH | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT AUG. OF MELLOCK PWSS, BAGNAN-II BLOCK, HOWRAH DISTRICT UNDER CDD, PHE DTE. | 393/CMSD-II (D) | 01/08/2022 | 15 | M/S PRACHI ENGINEERING | 1.88 | 0.02 | 100 | 0
822 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Material Requisition To Resource Division | 2639/HD | 09/12/2022 | 0 | Resource Division | 33.45 | 0 | 0 | 0
823 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
824 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Kanpur PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | BP-2021-22-367 | 28/02/2022 | 0 | STEELCONC AND ASSOCIATES | 3.86 | 0 | 0 | 0
825 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Work Order for Construction of switch room (3.60m x 3.0m) with water supply & sanitary arrangement at 3rd tube well site of Augmentation of Kanpur(Zone-II) PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | 2595/HD | 07/12/2022 | 60 | A.N ROY & CO | 4.79 | 4.58 | 100 | 100
826 | HOWRAH | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipment's etc. including allied works for Kanpur water supply scheme, T.W. No. I (Replacement tubewell), Block - Amta - I District- Howrah under Electrical Division, PHE Dte. | 2105/HMSD | 24/11/2022 | 30 | MOITRA ENGINEERING CO. | 4.82 | 4.81 | 100 | 0
827 | HOWRAH | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBEWELL BY DEPARTMENTAL RIG MACHINE AT AMODGHATA W/S SCH TW-II, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 377/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 2.93 | 0.02 | 100 | 0
828 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Work Order for Interconnection between tube wells & OHR at Augmentation of Kanpur Zone-II PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1843/HD | 02/05/2023 | 60 | PRADIP KUMAR JATI | 9.35 | 9.43 | 100 | 100
829 | HOWRAH | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 2.27 | 100 | 0
830 | HOWRAH | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Supply, Delivery & Installation of S/M/P & other E/M equipments etc. Including allied works for Kanpur W/S. Sch. Z-II, TW-II | 1549/ED | 20/09/2022 | 90 | D. K. ELECTRIC | 10.14 | 10.13 | 100 | 1
831 | HOWRAH | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | "Supply, Delivery & Installation of S/M/P & other E/M equipments etc. Including allied works for Kanpur W/S. Sch. Z-II, TW-II Howarah" | 1549//ED | 20/09/2022 | 7 | D. K. ELECTRIC | 10.13 | 0 | 0 | 1
832 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Material Requisition To Resource Division | 2753/HD | 28/07/2023 | 0 | Resource Division | 18.48 | 0 | 0 | 0
833 | HOWRAH | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Quotation Bill for New Service Connection at Kanpur W/S. Sch. TW-VI | 405 | 09/11/2023 | 0 | WBSEDCL | 3.34 | 0 | 0 | 0
834 | HOWRAH | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Quotation bill for New Service connection at Aug. of Kanpur W/S. Sch. | 159 | 10/02/2023 | 0 | WBSEDCL | 6.45 | 0 | 0 | 0
835 | HOWRAH | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Hire & Fuel Charges Bills | 230 | 29/03/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 1.72 | 0 | 0 | 0
836 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Additional Laying of pipeline Augmentation of Kanpur Zone-II PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Basantapur part mouza). | 683/AE/USD | 06/11/2023 | 60 | PRADIP KUMAR JATI | 3.51 | 0 | 0 | 0
837 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Additional Laying of pipeline Augmentation of Kanpur Zone-II PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Pearapur & Habla Mouza) | 5290/HD | 17/12/2024 | 45 | SUNIRMAN ENTERPRISE | 13.41 | 0 | 0 | 0
838 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) Mouza-Habla | 1714/HD | 24/08/2022 | 45 | USHA CONCERN | 33.16 | 33.13 | 100 | 20
839 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-D) Mouza-Bhetkepara | 1712/HD | 24/08/2022 | 45 | BISWAJIT BAG | 50.4 | 50.4 | 100 | 100
840 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Work Order for Laying HDPE pipeline & Providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) Mouza-Basantapur. | 1855/HD | 09/09/2022 | 60 | M/S EL-CON | 225.77 | 190.08 | 100 | 100
841 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-B) Mouza-PearapurHowrah. | 1713/HD | 24/08/2022 | 45 | SUNIRMAN ENTERPRISE | 38.67 | 38.59 | 100 | 100
842 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Work Order for Construction of 500 cum Capacity 20 Mtr. staging height RCC Over Head Reservoir (Ref. Drawing No.PC-I/OHR/09/2012 (Sheet No.1&2) & Laying HDPE & DI pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-E) | 1908/HD | 15/09/2022 | 180 | PRADIP KUMAR JATI | 155.22 | 155.09 | 100 | 100
843 | HOWRAH | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kanpur water supply scheme, T.W. No.-II, Block: Amta-I, District - Howrah under Electrical Division, PHE Dte. | 4737/ED | 15/12/2023 | 90 | D. K. ELECTRIC | 10.74 | 10.74 | 100 | 100
844 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Additional Laying of pipeline Augmentation of Kanpur Zone-II PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Bhetkepara mouza) | 216/HD | 17/01/2024 | 60 | BISWAJIT BAG | 13.11 | 12.75 | 100 | 100
845 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. on smooth durable wall surface preferably of Govt. premises boundary wall under Amta-I and Amta-II Block of Uluberia Sub Division under Howrah Division PHE Dte. | 847/HD | 22/02/2024 | 15 | TRIMARV SOLUTIONS PRIVATE LIMITED | 4.1 | 4.02 | 100 | 100
846 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Sinking of additonal 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Kanpur Zone-II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 1307/HD | 14/03/2024 | 30 | AUXILIARY TUBEWELL DRILLERS | 14.71 | 13.91 | 100 | 100
847 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Emergent Road restoration work at Basantapur Mouza of Kanpur Zone II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (SM/10021) | 1483/AE/USD | 16/01/2025 | 20 | BISWAJIT BAG | 4.83 | 0 | 0 | 0
848 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Balance laying distribution pipeline at Kanpur Zone II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte.(Basantapur part) | 2807/HD | 17/06/2025 | 90 | PRADIP KUMAR JATI | 96.92 | 0 | 0 | 0
849 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Construction of boundary wall at HW Site and additional pipeline at Basantupur Mouza of Augmentation of Kanpur Zone-II PWSS under Amta-I in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 246/HD | 18/01/2024 | 60 | PRADIP KUMAR JATI | 52.5 | 33.31 | 63.48 | 70
850 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | 1 no Kiosk (Size inside 2.44 x 1.52m) and additional laying distribution pipeline with FHTC at Kanpur Zone-II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 2904/HD | 26/06/2024 | 420 | MAITY CONSTRUCTION | 22.06 | 0 | 0 | 100
851 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Additional laying distribution pipeline with FHTC at Kanpur Zone II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte.(Basantapur part) | 4425/HD | 30/09/2024 | 120 | PRADIP KUMAR JATI | 96.97 | 0 | 0 | 90
852 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Providing Scheme Information Board at Head works site of different PWSS under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 61/AE/USD | 07/04/2025 | 25 | ABONTICA ENTERPRISE | 3.76 | 0 | 0 | 100
853 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Providing Scheme Information Board at Head works site of different PWSS under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1475/AE/USD | 15/01/2025 | 20 | ABONTICA ENTERPRISE | 4.26 | 0 | 0 | 100
854 | HOWRAH | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KANPUR water supply scheme, Zone-II, TW No. IV, Block: Amta-I, District - Howrah under Electrical Division PHE Dte. | 485/ED | 18/03/2025 | 90 | APEX ENGINEERING & PROJECT CO. | 10.94 | 0 | 0 | 95
855 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Providing and erection of land Information Board (size 0.9m x 0.6m) at different demarcated Lands possessed by PHED for different PWSS under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 2867/HD | 20/06/2025 | 30 | ABONTICA ENTERPRISE | 23.31 | 0 | 0 | 100
856 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
857 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) , SM/10021 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
858 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Bipro Noapara PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | 79/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.89 | 3.89 | 100 | 0
859 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 21.49 | 0 | 0 | 0
860 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Material Requisition To Resource Division | 1748/HD | 25/04/2023 | 0 | Resource Division | 43.47 | 0 | 0 | 0
861 | HOWRAH | Electrical | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bipra Noapara water supply scheme, T.W. No.- I & II, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 3507/ED | 30/12/2022 | 90 | MAA KALI ENTERPRISE | 22.83 | 21.41 | 93.8 | 40
862 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Work Order for Sinking of 4 (Four) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bipra Noapara PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 171/HD | 13/01/2023 | 45 | M DHARA AND BROTHERS | 51.16 | 12.21 | 23.87 | 25
863 | HOWRAH | Electrical | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bipra Noapara water supply scheme, T.W. No.- III & IV, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 3433/ED | 11/08/2023 | 90 | MAA KALI ENTERPRISE | 21.49 | 0 | 0 | 30
864 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Jagatballavpur and Domjur Block of Howrah Sadar Sub Division under Howrah Division PHE Dte. | 846/HD | 22/02/2024 | 15 | TRIMARV SOLUTIONS PRIVATE LIMITED | 4.85 | 4.85 | 100 | 100
865 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Material Requisition To Resource Division | 4769/HD | 14/11/2024 | 0 | Resource Division | 33.74 | 0 | 0 | 0
866 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Material Requisition To Resource Division | 3589/HD | 13/08/2024 | 0 | Resource Division | 6.33 | 0 | 0 | 0
867 | HOWRAH | Electrical | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Quotation money deposition for new service connection at P.H No.-II of Bipra Noapara pwss, Dist- Howrah under ED PHED. App. No.-1007764053 SM/11711 | 134 | 17/05/2024 | 0 | WBSEDCL | 7.48 | 0 | 0 | 0
868 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Restoration work of Bituminous Road and Shoulder with allied work of Makardah Bazar to Begri Road from 2.1 kmp to 3.5 kmp( due to Cutting for PHE water line) under Howrah Division in the dist of Howrah during the year 2024-2025 | BP-2024-25-494 | 27/11/2024 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 5.33 | 0 | 0 | 0
869 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | 2Nos Construction of Pump House (5.40m x 3.60 m) at 1st & 2nd Tube Well Site, Reparing of 2 nos ExistingPump House 3rd & 4th TW site (3.60m x 3.00 m), Construction of Boundary Wall at 1st Tube Well Site (30 m X 20 m), 3 nos Boundary Wall at 2nd, 3rd & 4th Tube Well Site (12 m X 12 m), Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Rising Main Pipeline Work From 4th Pump House, 3rd Pump House, 2nd Pump House to 1st Pump House & OHR, Laying Distribution of Pipeline & Providing FHTC (Functional Household Tap Connection) Augmentation of Bipra Noapara at PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | 2713/HD | 25/07/2023 | 1095 | B.B.C ENTERPRISE | 556.42 | 238.94 | 42.94 | 82
870 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Laying of additional distribution pipeline and road restoration at Bipro Naopara PWSS at Domjur Block under Howrah Sadar Sub Division of Howrah Division, PHE Dte. (SM/11711) | 1322/HD | 10/03/2025 | 60 | B.B.C ENTERPRISE | 106.17 | 0 | 0 | 30
871 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Domjur - Andul Road from 0.00 Km to 4.129 Km, Restoration work of PHE Cutting for laying pipe line under Howrah Highway Division in the district of Howrah (Dakshin Jhapardaha PWSS Zone-II, Dakshin Jhapardaha PWSS Zone-I, Bhandardaha PWSS, Bipranoapara PWSS). |  | 28/03/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 101.31 | 0 | 0 | 0
872 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Permanent restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road "Wadhipur - Makardaha Bazar" of Domjur Block, Howrah under W.B.S.R.D.A. Howrah Division-I. (Package No WB/09/08). |  | 19/05/2025 | 0 | WBSRDA | 21.82 | 0 | 0 | 0
873 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Restoration work of Bituminous road and shoulder with allied work of Makardah bazar to Begri road from 2.10 K.M. to 3.5 K.M. ( Due to cutting for PHE water line-2nd phase) Under Howrah Division in the District of Howrah during the year 2025-26. |  | 13/06/2025 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 11.08 | 0 | 0 | 0
874 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Dhulagarh Domjur via Begri Road from 2.6 km to 6.341 km, Restoration work of PHE cutting for laying pipe line under Howrah Highway Division in the District of Howrah. | BP-2024-25-531 | 22/01/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 98.16 | 0 | 0 | 0
875 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4817/HD | 19/11/2024 | 510 | TECH VISION | 8.36 | 1.54 | 99.98 | 95
876 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. , SM/11711 | New | Supplying,fitting,fixing and erecting of Display Board at Bipra Noapara PWSS [SM/11711], Domjur Zone-I (Mahisnala) PWSS [SM/11894], and Domjur Zone-III (Khasmara) PWSS [SM/11893] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 224-A/HSSD | 27/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
877 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. , SM/11222 | New | Work Order for Preparation of DPR for new piped water supply scheme of Saoria PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 244/HD | 07/02/2022 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.86 | 2.86 | 100 | 0
878 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. , SM/11222 | New | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 24.23 | 0 | 0 | 0
879 | HOWRAH | Electrical | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. , SM/11222 | New | Quotation Bill for New Service Connection at Sauria W/S. Sch. TW-I | 558 | 21/12/2023 | 0 | WBSEDCL | 3.59 | 0 | 0 | 0
880 | HOWRAH | Electrical | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. , SM/11222 | New | Quotation Bill for New Service Connection at Sauria W/S. Sch. TW-II | 557 | 21/12/2023 | 0 | WBSEDCL | 7.61 | 0 | 0 | 0
881 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. , SM/11222 | New | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Saoria PWSS at Amta-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 1836/HD | 08/09/2022 | 40 | DIBAKAR SHAW | 26.67 | 26.66 | 100 | 100
882 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. , SM/11222 | New | Construction of Kiosk (Two nos.) at Saoria PWSS of Amta-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Size inside 3.0 x 2.4m). | 1109/AE/USD | 05/11/2024 | 15 | MAA TARA ENTERPRISE | 2.18 | 2.17 | 100 | 100
883 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. , SM/11222 | New | Work Order for Laying of Distribution System(UPVC & DI), Providing Functional Household Tap Connection (FHTC), Interconnection between tube wells, Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials at HW site and construction of Two storied switch room ( 5.4 x 3.6) & (3.6 x3.0) with water supply & sanitary arrangement cum godown at Head Work site & 2nd Tube well site of SAORIA PWSS of Amta-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 2085/HD | 11/10/2022 | 1319 | KAMIRUL SK AND CO. | 370.75 | 181.56 | 48.97 | 63
884 | HOWRAH | Electrical | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. , SM/11222 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Saoria water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | 3521/ED | 30/12/2022 | 702 | GLACIER ENGINEERING CO. | 20.25 | 19.45 | 96.96 | 90
885 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. , SM/11222 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 1.25 | 100 | 100
886 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. , SM/11222 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
887 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. , SM/11222 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
888 | HOWRAH | Electrical | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. , SM/11641 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nayachak water supply scheme, T.W. No.- I & II, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | 3518/ED | 30/12/2022 | 90 | JAGANNATH ENTERPRISE | 21.36 | 0 | 0 | 0
889 | HOWRAH | Electrical | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. , SM/11641 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nayachak water supply scheme, T.W. No. III, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | 3455/ED | 11/08/2023 | 90 | TAMAL ENTERPRISE | 10.76 | 0 | 0 | 0
890 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. , SM/11641 | New | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 160.85 | 0 | 0 | 0
891 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. , SM/11641 | New | Material Requisition To Resource Division | 1754/HD | 26/04/2023 | 0 | Resource Division | 159.48 | 0 | 0 | 0
892 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. , SM/11641 | New | Material Requisition To Resource Division | 4864/HD | 22/11/2024 | 0 | Resource Division | 7.39 | 0 | 0 | 0
893 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. , SM/11641 | New | Laying Distribution Pipe Lines(UPVC & DI) With Allied Works and Providing Household Functional Tap Connection & Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials including foundation design for NAYACHAK PWSS OF ULUBERIA-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | 2808/HD | 03/08/2023 | 730 | GUPTA ENTERPRISE | 775.72 | 257.45 | 33.19 | 60
894 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. , SM/11641 | New | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nayachak PWSS of Uluberia-II block of Uluberia Sub Division under Howrah Division, P. H. E. Dte. | 2717/HD | 14/12/2022 | 841 | AQUATECH ENGINEERS | 54.31 | 0 | 0 | 100
895 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. , SM/11641 | New | Material Requisition To Resource Division | 494/HD | 24/01/2025 | 0 | Resource Division | 12.32 | 0 | 0 | 0
896 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. , SM/11641 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
897 | HOWRAH | Electrical | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. , SM/11641 | New | Quotation money deposition for new service connection at Nayachak w/s scheme, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008292212 Reference ID- 106877189 SM Code- 11641 | 676 | 31/01/2025 | 0 | WBSEDCL | 3.98 | 0 | 0 | 0
898 | HOWRAH | Electrical | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. , SM/11641 | New | Quotation money deposition for new service connection at Nayachak w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008293364 Reference ID- 106877855 SM Code- 11641 | 677 | 31/01/2025 | 0 | WBSEDCL | 3.81 | 0 | 0 | 0
899 | HOWRAH | Electrical | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. , SM/11641 | New | Quotation money deposition for new service connection at Nayachak w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008296018 Reference ID- 106879922 SM Code- 11641 |  | 20/03/2025 | 0 | WBSEDCL | 6.67 | 0 | 0 | 0
900 | HOWRAH | Howrah Division | Jaynagar Piped Water Supply Scheme , SM/14865 | New | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 18.97 | 0 | 0 | 0
901 | HOWRAH | Howrah Division | Jaynagar Piped Water Supply Scheme , SM/14865 | New | Construction of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/6/2012) including Soil Investigation, Foundation Design & All pipe Connection, 2(Two) Nos. Pump House (5.40m x 3.60 m), Construction of Boundary Wall at Head work Site, Construction of Boundary Wall of 2nd Tube well site, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work, Providing FHTC (Functional Household Tap Connection-3079) for Jaynagar PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte. | 3278/HD | 13/09/2023 | 335 | REALIENCE CONSTRUCTION | 529.89 | 0 | 0 | 0
902 | HOWRAH | Howrah Division | Jaynagar Piped Water Supply Scheme , SM/14865 | New | Continuation order for Preparation of DPR with Route Survey for new piped water supply scheme of Joynagar PWSS of Panchla Block under Howrah Division PHE Dte. | 1459/HD | 14/07/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.13 | 3.11 | 100 | 100
903 | HOWRAH | Howrah Division | Jaynagar Piped Water Supply Scheme , SM/14865 | New | Material Requisition To Resource Division | 446/HD | 06/02/2023 | 0 | Resource Division | 54.61 | 0 | 0 | 0
904 | HOWRAH | Electrical | Jaynagar Piped Water Supply Scheme , SM/14865 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jaynagar water supply scheme, T.W. No. I & II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 1704/ED | 18/04/2023 | 90 | DIPALI CONSTRUCTION | 22.8 | 15.41 | 67.61 | 30
905 | HOWRAH | Howrah Division | Jaynagar Piped Water Supply Scheme , SM/14865 | New | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Jaynagar PWSS(2 nos) & Banharishpur PWSS(2 nos) of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 1000/HD | 13/03/2023 | 977 | PRANTIK DRILLING AGENCY | 68.83 | 0 | 0 | 25
906 | HOWRAH | Howrah Division | Jaynagar Piped Water Supply Scheme , SM/14865 | New | Sinking 1 no. 300 X 200 mm dia and 240 m deep tube well drilling by direct rotary method with 200 mm. dia. PVC. strainer of 30m. length having 300 mm dia. 60 mtr. long PVC housing pipe & 200 mm dia. 150 mtr. long well pipe alongwith 3m blank pipe all complete including cost of materials under Jaynagar PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 2681/HD | 05/06/2025 | 240 | AQUATECH ENGINEERS | 19.16 | 0 | 0 | 0
907 | HOWRAH | Electrical | Jaynagar Piped Water Supply Scheme , SM/14865 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JAYNAGAR water supply scheme, TW No. III, Block: Panchla, District - Howrah under Electrical Division PHE Dte. | 489/ED | 18/03/2025 | 90 | DIPALI CONSTRUCTION | 11.3 | 0 | 0 | 0
908 | HOWRAH | Electrical | Jaynagar Piped Water Supply Scheme , SM/14865 | New | Quotation money deposition for new service connection at Jaynagar w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008311317 Reference ID- 106889678 SM Code- 14865 | 681 | 31/01/2025 | 0 | WBSEDCL | 16.63 | 0 | 0 | 0
909 | HOWRAH | Electrical | Mollar Chak Piped Water Supplu scheme , SM/15288 | New | Quotation for new service connection of Mollarchak Mini water supply scheme, Amta- I , Howrah | 735 | 07/02/2024 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
910 | HOWRAH | Howrah Division | Mollar Chak Piped Water Supplu scheme , SM/15288 | New | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | 2155/H.D | 07/06/2023 | 1021 | MONDAL PRECISION PVT. LTD. | 330.32 | 21.47 | 58.51 | 80
911 | HOWRAH | Howrah Division | Mollar Chak Piped Water Supplu scheme , SM/15288 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 0.12 | 0 | 0 | 0
912 | HOWRAH | Electrical | Sankardari Mini Piped Water Supply Scheme , SM/15189 | New | Quotation for New Service Connection at Shankardari Mini W/S. Sch. | 651 | 10/01/2024 | 0 | WBSEDCL | 0.08 | 0 | 0 | 0
913 | HOWRAH | Howrah Division | Sankardari Mini Piped Water Supply Scheme , SM/15189 | New | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | 2155/H.D | 07/06/2023 | 1021 | MONDAL PRECISION PVT. LTD. | 330.32 | 21.85 | 59.52 | 80
914 | HOWRAH | Howrah Division | Sankardari Mini Piped Water Supply Scheme , SM/15189 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 0.12 | 0 | 0 | 0
915 | HOWRAH | Electrical | Chakur water supply scheme. , SM/08987 | New | Supply, Delivery & Installation of S/P/M & other Electrical/Mechanical equipments etc. including allied works for Chakur W/S. Sch. Howrah | 781/ED | 05/05/2022 | 365 | D. K. ELECTRIC | 10.41 | 9.61 | 92.31 | 0
916 | HOWRAH | Central Drilling | Chakur water supply scheme. , SM/08987 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 230 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHAKUR W/S SCH (Z-II), BAGNAN-I BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 308/CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 10.33 | 9.15 | 100 | 0
917 | HOWRAH | Howrah Division | Chakur water supply scheme. , SM/08987 | New | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-D) No. of House Hold= 110 nos. | BP-2021-22-365 | 28/02/2022 | 0 | APEX ENGINEERING | 2.77 | 0 | 0 | 0
918 | HOWRAH | Howrah Division | Chakur water supply scheme. , SM/08987 | New | WBSRDA |  | 07/09/2022 | 0 | WBSRDA | 17.22 | 0 | 0 | 0
919 | HOWRAH | Howrah Division | Chakur water supply scheme. , SM/08987 | New | Chakur W/S Scheme. | BP-2021-22-482 | 30/03/2022 | 0 | JAHANGIR ALAM | 58.28 | 0 | 0 | 0
920 | HOWRAH | Electrical | Chakur water supply scheme. , SM/08987 | New | Chakur water supply scheme. | 21-22/134 | 22/03/2022 | 0 | WBSEDCL | 7.32 | 0 | 0 | 0
921 | HOWRAH | Howrah Division | Chakur water supply scheme. , SM/08987 | New | WBSRDA PAYMENT |  | 07/09/2022 | 0 | WBSRDA | 17.22 | 0 | 0 | 0
922 | HOWRAH | Electrical | Chakur water supply scheme. , SM/08987 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chakur water supply scheme, T.W. No. I, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 3528/ED | 30/12/2022 | 90 | DAS ENTERPRISE | 10.66 | 10.38 | 97.31 | 0
923 | HOWRAH | Howrah Division | Chakur water supply scheme. , SM/08987 | New | Development of 2nd Tube well at Chakur PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 942/AE/USD | 22/03/2023 | 30 | LOKENATH ENTERPRISES | 0.71 | 0.71 | 100 | 100
924 | HOWRAH | Howrah Division | Chakur water supply scheme. , SM/08987 | New | Material Requisition To Resource Division | 408/HD | 24/02/2022 | 0 | Resource Division | 11.59 | 0 | 0 | 0
925 | HOWRAH | Howrah Division | Chakur water supply scheme. , SM/08987 | New | Material Requisition To Resource Division | 1222/HD | 09/06/2022 | 0 | Resource Division | 1.35 | 0 | 0 | 0
926 | HOWRAH | Electrical | Chakur water supply scheme. , SM/08987 | New | Quotation Bill for New Service Connection at of Chakur W/S. Sch. PH-I | 02 | 11/04/2023 | 0 | WBSEDCL | 0.69 | 0 | 0 | 0
927 | HOWRAH | Electrical | Chakur water supply scheme. , SM/08987 | New | Quotation bill for new service connection of WBSEDC at Chakur w/s scheme, T.W. No.-I | 150 | 08/02/2023 | 0 | WBSEDCL | 2.74 | 0 | 0 | 0
928 | HOWRAH | Howrah Division | Chakur water supply scheme. , SM/08987 | New | Balance work in connection with water supply & sanitary arrangement of Pump House at Head Work site of Chakur Pipes water supply scheme of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 366/AE/USD | 21/08/2023 | 30 | M.K.ENTERPRISE | 0.4 | 0 | 0 | 100
929 | HOWRAH | Howrah Division | Chakur water supply scheme. , SM/08987 | New | Work order for Ground Water Based Water Supply Scheme for Village CHAKUR of Bagnan I Block under Uluberia Sub-Division of Howrah Division, PHE Dte. | 69/HD | 11/01/2022 | 1201 | JAHANGIR ALAM | 162.65 | 77.42 | 82.74 | 83
930 | HOWRAH | Howrah Division | Chakur water supply scheme. , SM/08987 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
931 | HOWRAH | Howrah Division | Augmentation of Keshabpur Water supply scheme , SM/16947 | Augmentation | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 8.7 | 0 | 0 | 0
932 | HOWRAH | Howrah Division | Augmentation of Keshabpur Water supply scheme , SM/16947 | Augmentation | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Keshabpur PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | 84/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.64 | 3.64 | 100 | 100
933 | HOWRAH | Howrah Division | Augmentation of Keshabpur Water supply scheme , SM/16947 | Augmentation | Material Requisition To Resource Division | 4718/HD | 27/12/2023 | 0 | Resource Division | 88.18 | 0 | 0 | 0
934 | HOWRAH | Howrah Division | Augmentation of Keshabpur Water supply scheme , SM/16947 | Augmentation | Work Order for Construction of Boundary Wall, Repairing of Pump House (3.60 m x 3.00 m), Laying of Distribution Pipeline & Providing FHTC (1413 nos) for Augmentation of Keshabpur PWSS of Domjur Block under Howrah Division, PHE Dte. (Part-II) | 1547/HD | 04/04/2023 | 60 | MA MANASA CONSTRUCTION | 152.7 | 90.49 | 59.26 | 20
935 | HOWRAH | Howrah Division | Augmentation of Keshabpur Water supply scheme , SM/16947 | Augmentation | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Keshabpur PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 1529/HD | 04/04/2023 | 765 | GARHBETA-I UNEMPLOYED YOUTH ENGINEERS CO OP | 25.31 | 0 | 0 | 100
936 | HOWRAH | Electrical | Augmentation of Keshabpur Water supply scheme , SM/16947 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Keshabpur water supply scheme, T.W. No. I, II & III, Block: Domjur, District - Howrah under Electrical Division, PHE Dte. | 4694/ED | 08/12/2023 | 571 | DAS ENTERPRISE | 32.91 | 0 | 0 | 40
937 | HOWRAH | Howrah Division | Augmentation of Keshabpur Water supply scheme , SM/16947 | Augmentation | Laying of additional distribution pipe line and Road restoration at Keshabpur PWSS at Domjur Block under Howrah Sadar Sub-Division of Howrah Division PHE. | 1250/HD | 06/03/2025 | 60 | MA MANASA CONSTRUCTION | 27.71 | 0 | 0 | 0
938 | HOWRAH | Howrah Division | Augmentation of Keshabpur Water supply scheme , SM/16947 | Augmentation | Construction of Pump House (5.40m x 3.60m) at 1st Tube Well Site, Laying of Rising main from Tube well including Road restoration & specials, Laying of Distribution system & providing Functional Household Tap Connection (FHTC) for Augmentation of KESHABPUR PWSS at Domjur Block under Howrah Division P.H.E Dte. (PART-1) [No. of FHTC = 1413] | 217/HD | 17/01/2024 | 540 | UNIQUE AGENCY | 194 | 66.24 | 29.44 | 10
939 | HOWRAH | Howrah Division | Augmentation of Keshabpur Water supply scheme , SM/16947 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Piped Water Supply Schemes in different Blocks in the District of Howrah under Howrah Division, PHE Dte. | 3730/HD | 29/08/2024 | 30 | HORIZEN | 4.93 | 0 | 0 | 100
940 | HOWRAH | Howrah Division | Augmentation of Keshabpur Water supply scheme , SM/16947 | Augmentation | Permanent restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road "Wadhipur - Makardaha Bazar" of Domjur Block, Howrah under W.B.S.R.D.A. Howrah Division-I. (Package No WB/09/08). |  | 19/05/2025 | 0 | WBSRDA | 21.82 | 0 | 0 | 0
941 | HOWRAH | Electrical | Augmentation of Keshabpur Water supply scheme , SM/16947 | Augmentation | Quotation money deposition for new service connection at Keshabpur w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008296223 Reference ID- 106880704 SM Code- 16947 | 682 | 31/01/2025 | 0 | WBSEDCL | 8.98 | 0 | 0 | 0
942 | HOWRAH | Howrah Division | Augmentation of Keshabpur Water supply scheme , SM/16947 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Domjur (Zone-IV) Dakshin Jhapardaha (Zone-I) PWSS [SM/13751], Domjur (Zone-IV) Dakshin Jhapardaha (Zone-II) PWSS [SM/13752], Keshabpur PWSS [SM/16947] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 222/HSSD | 25/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
943 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme , SM/18565 | Augmentation | Preparation of DPR for Augmentation of Harop PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 316/AE/USD | 16/08/2022 | 45 | MS SOBHA AND CO | 3.48 | 3.44 | 100 | 90
944 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme , SM/18565 | Augmentation | Sinking of 5 (Five) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Harop PWSS Zone -I (1 no) & Zone-II (2 nos) & Matinala PWSS (2 nos) of Bagnan-I Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 3533/HD | 04/10/2023 | 60 | AQUATECH ENGINEERS | 64.95 | 40.2 | 100 | 40
945 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme , SM/18565 | Augmentation | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 11.4 | 0 | 0 | 0
946 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme , SM/18565 | Augmentation | Material Requisition To Resource Division | 4864/HD | 22/11/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
947 | HOWRAH | Electrical | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme , SM/18565 | Augmentation | Quotation for new service connection of Harop W/S. Sch. PH-I | 753 | 16/02/2024 | 0 | WBSEDCL | 4.08 | 0 | 0 | 0
948 | HOWRAH | Electrical | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme , SM/18565 | Augmentation | Quotation for new service connection of Harop W/S. Sch. PH-II | 746 | 08/02/2024 | 0 | WBSEDCL | 6.37 | 0 | 0 | 0
949 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme , SM/18565 | Augmentation | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells & Construction of 4 nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement and 400 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design of HAROP (ZONE-II) PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | 2846/HD | 07/08/2023 | 968 | SUBHASH BOSE | 506.25 | 0 | 0 | 35
950 | HOWRAH | Electrical | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme , SM/18565 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Harop (Zone-I & II) water supply scheme, T.W. No. I, II & III, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 3593/ED | 28/08/2023 | 612 | SUBHRA ENTERPRISE | 32.24 | 16.52 | 51.24 | 50
951 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme , SM/18565 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
952 | HOWRAH | Electrical | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme , SM/18565 | Augmentation | SHIFTING OF ELECTRIC POLE NEAR PUMP HOUSE NO-I OF HAROP WATER SUPPLY SCHEME FOR OPTIMUM LAND USE. (SM/18565 ) Reference Id- 860347503, Application ID- 100000147243 |  | 08/09/2025 | 0 | WBSEDCL | 1.87 | 0 | 0 | 0
953 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme , SM/18565 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
954 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme , SM/18565 | Augmentation | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells HAROP (ZONE-I) PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | 2837/HD | 07/08/2023 | 814 | N. G ENGINEERING | 249.55 | 44.69 | 17.93 | 18
955 | HOWRAH | Electrical | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Udang water supply scheme, T.W. No. I & II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | 3594/ED | 28/08/2023 | 90 | EMCON | 21.49 | 0 | 0 | 0
956 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Work for Preparation of DPR for Augmentation of Udong PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 314/AE/USD | 16/08/2022 | 45 | MS SOBHA AND CO | 3.83 | 3.83 | 100 | 100
957 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Material Requisition To Resource Division | 4864/HD | 22/11/2024 | 0 | Resource Division | 9.24 | 0 | 0 | 0
958 | HOWRAH | Electrical | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Quotation money deposition for new service connection at Udang w/s scheme, Zone- II, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008049557 Reference ID- 106726236 SM Code- 18567 | 557 | 05/11/2024 | 0 | WBSEDCL | 25.4 | 0 | 0 | 0
959 | HOWRAH | Electrical | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Quotation money deposition for new service connection at Udang w/s scheme, Zone- I, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1007772514 Reference ID- 106595797 SM Code- 18567 | 165 | 28/05/2024 | 0 | WBSEDCL | 5.3 | 0 | 0 | 0
960 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells, construction of 2 nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at TW Sites and 450 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design for UDANG (ZONE-II) PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | 2839/HD | 07/08/2023 | 966 | NATURAL RESOURCES CONSORTIUM | 501.82 | 50.69 | 10.1 | 45
961 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Land Development and Approach Road at HW site of Udong Zone-II PWSS of Amta-I Block under Uluberia Sub Division under Howrah Division PHED. | 987/HD | 20/02/2025 | 30 | NATURAL RESOURCES CONSORTIUM | 12.13 | 0 | 0 | 0
962 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Providing Additional Pipeline and repairing/ reconnection of existing FHTCs at Vill: Ranapara & Deorah of Udong-II G.P of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 989/HD | 20/02/2025 | 60 | ADITYA HAZRA | 29.76 | 0 | 0 | 0
963 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Construction of boundary wall at HW Site of Udong Zone-II W/S scheme within Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 964/HD | 19/02/2025 | 60 | NATURAL RESOURCES CONSORTIUM | 20.46 | 0 | 0 | 0
964 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Construction of boundary wall at 2nd T/W Site of Udong Zone-II W/S scheme within Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 705/HD | 30/01/2025 | 315 | TIYASA ENTERPRISE | 7.68 | 0 | 0 | 0
965 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Land Development & Approach Road at 2nd TW site of Udong Zone-II PWSS of Amta-I Block under Uluberia Sub Division under Howrah Divison PHED. | 1482/AE/USD | 15/01/2025 | 20 | NOBLE ENTERPRISE | 1.24 | 0 | 0 | 0
966 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Road restoration work with Bullah piling at Udong Zone-II PWSS of Amta-I Block under Uluberia Sub Division under Howrah Division PHED. | 986/HD | 20/02/2025 | 45 | NATURAL RESOURCES CONSORTIUM | 20.08 | 0 | 0 | 0
967 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Sinking of 3(Three) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Udang Zone-I & Zone-II 2 nos under Amta-I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 3133/HD | 29/08/2023 | 564 | NADIA TUBEWELLS | 38.94 | 24.67 | 66.7 | 68
968 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Laying Distribution System(HDPE & DI) & Providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells UDONG (ZONE-I) PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | 2977/HD | 17/08/2023 | 600 | TAPU SAHA | 410.47 | 302.44 | 73.68 | 100
969 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at 4th tube well (Replaced) site of Udang Zone-I PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | 786/AE/USD | 09/09/2024 | 181 | DEBANANDA CONSTRUCTION | 4.72 | 0 | 0 | 100
970 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 1.02 | 100 | 100
971 | HOWRAH | Electrical | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for UDANG water supply scheme, Zone-II, TW No. III, Block: Amta-I, District - Howrah under Electrical Division PHE Dte. | 484/ED | 18/03/2025 | 90 | D. K. ELECTRIC | 11.3 | 0 | 0 | 90
972 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Structural repairing and renovation of the 4.50 lakh liter capacity OHR at HW site of Udong (Zone-I) PWSS under Amta-I block, under Uluberia Sub-Division PHE Dte under Howrah Division PHE Dte. | 2365/HD | 16/05/2025 | 45 | SAIKAT ENTERPRISE | 13.75 | 0 | 0 | 100
973 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Material Requisition To Resource Division | 157/HD | 10/01/2025 | 0 | Resource Division | 34.46 | 0 | 0 | 0
974 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
975 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Material Requisition To Resource Division | 3688/HD | 04/09/2025 | 0 | Resource Division | 15.4 | 0 | 0 | 0
976 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme , SM/18567 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
977 | HOWRAH | Howrah Division | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Construction of Remaining of 550 cum capacity, 20 mtr. staging height Over Head Reservoir including all allied works as per Departmental drawing at Amragori W/S Scheme under Howrah Division, P.H.E. Dte. | 542/HD | 15/06/2020 | 90 | UNIQUE AGENCY | 31.5 | 0 | 0 | 0
978 | HOWRAH | Howrah Division | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Preparation of DPR for Source Strengthening at Amragori PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 826/AE/USD | 08/12/2023 | 30 | APEX ENGINEERING | 2.76 | 0 | 0 | 0
979 | HOWRAH | Electrical | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Amragori water supply scheme, T.W. No. III, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | 1796/ED | 02/11/2022 | 90 | MENAKA ENTERPRISE | 10.84 | 10.81 | 100 | 100
980 | HOWRAH | Howrah Division | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (SM/18883) | 1311/HD | 14/03/2024 | 60 | DEV DAS SHAW | 29.68 | 28.38 | 100 | 100
981 | HOWRAH | Electrical | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Quotation money deposition for new service connection at Amoragori w/s scheme, T.W. No.-V, Dist.-Howrah under PHE Dte. Application No- 1008024188 Reference ID- 106715771 SM Code- 18883 | 566 | 13/11/2024 | 0 | WBSEDCL | 10.4 | 0 | 0 | 0
982 | HOWRAH | Electrical | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Quotation money deposition for new service connection at Amoragori w/s scheme, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1008024177 Reference ID- 106715773 SM Code- 18883 | 565 | 13/11/2024 | 0 | WBSEDCL | 11.33 | 0 | 0 | 0
983 | HOWRAH | Howrah Division | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Construction of boundary wall with approach road at 3rd Site of Amragori PWSS in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1299/HD | 13/03/2024 | 420 | MANAS MALICK | 8.25 | 0 | 0 | 100
984 | HOWRAH | Howrah Division | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Laying distribution pipeline with FHTC at Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (SM/18883) | 3323/HD | 24/07/2024 | 420 | MODERN CONSTRUCTION | 136.25 | 0 | 0 | 75
985 | HOWRAH | Electrical | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Amragari Water Supply Scheme Block- Amta-II District- Howrah under JJM Program under Electrical Division PHE Dte. | 4531/ED | 23/11/2023 | 596 | DAS ENTERPRISE | 21.49 | 15.91 | 74.54 | 40
986 | HOWRAH | Howrah Division | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Construction of 2nos switch room (5.4x 3.6) at TW site at Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (SM/18883) | 3120/HD | 09/07/2024 | 300 | S S CONSTRUCTION | 12.56 | 0 | 0 | 100
987 | HOWRAH | Howrah Division | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Connection between 3rd TW with delivery pipeline, special repairing and allied works at Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E.Dte. | 698/AE/USD | 27/08/2024 | 25 | DEV DAS SHAW | 2.88 | 0.74 | 20.94 | 100
988 | HOWRAH | Howrah Division | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep Tube Well by Drilling by Direct Rotary method with UPVC Pipes all complete under Source Augmentation of Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 5289/HD | 17/12/2024 | 60 | G.T.AGRO CENTRE | 14.55 | 0 | 0 | 100
989 | HOWRAH | Electrical | Source Augmentation of Amragari Water Supply Scheme , SM/18883 | Augmentation | Shifting of Ltoh line near Amoragori 4 PHE Application No- 100000128110 Reference ID- 860323060 SM Code- 18883 | 694 | 31/01/2025 | 0 | WBSEDCL | 0.38 | 0 | 0 | 0
990 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Additional work in connection with commissioning of Water Treatment Plant under SANKRAIL SURFACE WATER BASED WATER SUPPLY PROJECT of Howrah District under Howrah Division, P.H.E. Dte. (TSM/019257) | 3105/HD | 08/07/2024 | 630 | GBC INFRASTRUCTURE PRIVATE LIMITED | 405.4 | 173.88 | 42.89 | 10
991 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Design, Construction, supply, erection and commissioning of additional fixed type intake jetty of Raw Water pipe carrying RCC walkway with all necessary components from 35 Mtr chainage of carriageway to connecting metal road of RAW WATER INTAKE near Manikpur ferry ghat on Hooghly river along with other allied works of Augmentation of surface water based Sankrail Piped Water Supply Scheme of SANKRAIL BLOCK (including Sankrail Food Park) and part of Domjur, Panchla & Uluberia-II Blocks of Howrah District under Howrah Division, PHE Dte. (SM/19187) | 3925/HD | 09/09/2024 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 2185.5 | 1623.02 | 74.26 | 10
992 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 233.2 | 0 | 0 | 0
993 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 177.21 | 0 | 0 | 0
994 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 93.64 | 0 | 0 | 0
995 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 33.48 | 0 | 0 | 0
996 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 329.84 | 0 | 0 | 0
997 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 56.03 | 0 | 0 | 0
998 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 160.35 | 0 | 0 | 0
999 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 240.65 | 0 | 0 | 0
1000 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 113.45 | 0 | 0 | 0
1001 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 98.37 | 0 | 0 | 0
1002 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 5224/HD | 13/12/2024 | 0 | Resource Division | 3852.02 | 0 | 0 | 0
1003 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 255.11 | 0 | 0 | 0
1004 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 93.99 | 0 | 0 | 0
1005 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 4718/HD | 12/11/2024 | 0 | Resource Division | 120.02 | 0 | 0 | 0
1006 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 5380/HD | 26/12/2024 | 0 | Resource Division | 124.66 | 0 | 0 | 0
1007 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-6A for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 3997] | 1188/HD | 09/03/2024 | 753 | M/S. GHOSH CONSTRUCTION | 750.92 | 0 | 0 | 80
1008 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-7 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 6811] | 1189/HD | 09/03/2024 | 663 | MAHI ENTERPRISE | 825.27 | 0 | 0 | 20
1009 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Surveying, designing, laying, commissioning of two separate rising mains for conveyance of treated water from CWR at Sankrail WTP premises to 14 nos. OHRs (12 nos. new, 02 no. existing) falling under jurisdiction of PHE Dte. at Sankrail, Domjur (Part), Panchla (Part), Uluberia-II (Part) block and 09 nos. overhead reservoirs falling under jurisdiction of KMDA (erstwhile KMW&SA) at Sankrail (Part) and Domjur (Part) block and to 01 no. GLR at Sankrail Food Park. Design of foundation, construction and commissioning of foundation and superstructure of 12 nos. OHRs of different capacity, 1No. GLR, minor repair, maintenance and painting of 02 nos. existing OHRs, and other allied works along with Trial run of 3 months and 6 (six) months operation and maintenance of the entire system. | 1288/HD | 13/03/2024 | 365 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 10463 | 40.17 | 0.38 | 2
1010 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-3 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 3325] | 1187/HD | 09/03/2024 | 663 | M/S SARADA CONSTRUCTION | 1010.66 | 0 | 0 | 10
1011 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-5 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 8336] | 1170/HD | 07/03/2024 | 665 | SAMIRON GHOSH | 1396.13 | 0 | 0 | 30
1012 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-10 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 7772] | 1192/HD | 09/03/2024 | 662 | DEBAPRIYA DUTTA | 981.48 | 0 | 0 | 50
1013 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-9B for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 5717] | 1174/HD | 07/03/2024 | 846 | MONDAL ENTERPISE | 947 | 0 | 0 | 30
1014 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-1 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 7417] | 1185/HD | 09/03/2024 | 663 | THE UNICON ENGINEERS | 1192.14 | 0 | 0 | 45
1015 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-2 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 5396] | 1186/HD | 09/03/2024 | 936 | LIMRA CONSTRUCTION AND INDUSTRIAL DEVELOPMENT | 907.2 | 0 | 0 | 30
1016 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-6B for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 3997] | 1171/HD | 07/03/2024 | 665 | GUPTA ENTERPRISE | 589.74 | 0 | 0 | 30
1017 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-11 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 8889] | 1165/HD | 07/03/2024 | 846 | M/S R.S. CONSTRUCTION | 1341.84 | 0 | 0 | 10
1018 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-9A for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 5719] | 1190/HD | 09/03/2024 | 844 | MONDAL PRECISION PRIVATE LIMITED | 617.29 | 0 | 0 | 10
1019 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 1890/HD | 17/04/2025 | 0 | Resource Division | 367.99 | 0 | 0 | 0
1020 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Way leave facility charge for laying 1000 mm dia casing pipe with 800 mm carrier pipe along the Railway track near SANKRAIL Rail station under Augmentation of surface water based SANKRAIL piped water supply scheme.(SM /19187) | W/145 | 10/07/2025 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 168.06 | 0 | 0 | 0
1021 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Permanent Restoration for probable damage stretches, from Ch.0.000 Km to 3.190 Km, due to Laying pipe line along Bauria Feeder Road for LDS work in Zone-5 under Sankrail Surface project, Block-Uluberia under Howrah Highway Division in the district of Howrah. |  | 19/05/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 28.44 | 0 | 0 | 0
1022 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Sarenga Bridge approach at Hirapur to Nalpur Station Road from 1.70 km to 2.70 km Permanent Restoration of PHE cutting for laying pipe line under Howrah Highway Division in the district of Howrah. |  | 19/05/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 24.96 | 0 | 0 | 0
1023 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Andul feeder Road from 0.00 km to 0.300 km, permanent restoration work of PHE cutting for laying pipe line under Howrah Highway Division,P.W(Roads) Directorate in the district of Howrah during the year of 2025-26(Deposit Head) under Augmentation of surface water based Sankrail pipe water supply scheme. (SM/19187) |  | 12/08/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 8.07 | 0 | 0 | 0
1024 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Dhulagarh domjur via begri road from 0.00 km to 1.00 km, Restoration work of PHE cutting for laying pipe line under Howrah Highway Division in the District of Howrah. under Augmentation of surface water based Sankrail pipe water supply scheme. (SM/19187) |  | 12/08/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 4.3 | 0 | 0 | 0
1025 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-8 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 9861] | 1172/HD | 07/03/2024 | 755 | BALAJI UDDYOG | 915.09 | 0 | 0 | 25
1026 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-4 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 1810] | 1191/HD | 09/03/2024 | 479 | M/S SHIBAM ENTERPRISE | 763.31 | 0 | 0 | 0
1027 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme , SM/19187 | Augmentation | Material Requisition To Resource Division | 402/HD | 13/02/2026 | 0 | Resource Division | 32.6 | 0 | 0 | 0
1028 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) , SM/06784 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-E) for Balichak mouza part) | 1625/HD | 09/11/2020 | 30 | P B ENTERPRISE | 26.26 | 0 | 0 | 0
1029 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) , SM/06784 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-D) (for Banuchak mouza) | 1624/HD | 09/11/2020 | 30 | M/S. CHANDIMATA CONSTRUCTION | 18.4 | 0 | 0 | 0
1030 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) , SM/06784 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-F) for Balichak mouza part) | 1626/HD | 09/11/2020 | 30 | P B ENTERPRISE | 27.61 | 0 | 0 | 0
1031 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) , SM/06784 | Retrofitting | Survey and Collection of houshold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme | W/39 | 11/06/2021 | 0 | STEELCONC AND ASSOCIATES | 4.73 | 0 | 0 | 0
1032 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) , SM/06784 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme. | 8443120 | 30/03/2021 | 0 | GHOSH CONCERN | 27.96 | 0 | 0 | 0
1033 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) , SM/06784 | Retrofitting | Retrofitting BalichakWater Supply Scheme | 844383 | 26/03/2021 | 0 | N. G ENGINEERING | 21.63 | 0 | 0 | 0
1034 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) , SM/06784 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme. | 8443107 | 30/03/2021 | 0 | P B ENTERPRISE | 23.52 | 0 | 0 | 0
1035 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) , SM/06784 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply | W/594 | 21/12/2021 | 0 | RANA ENTERPRISE | 7.58 | 0 | 0 | 0
1036 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) , SM/06784 | Retrofitting | Material Requisition To Resource Division | 495/HD | 07/03/2022 | 0 | Resource Division | 8.01 | 0 | 0 | 0
1037 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Manikara, Purash & Kanpur (part) of kanpur Rejuvenation piped water supply scheme (Phase-II) , SM/06787 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | 844333 | 17/03/2021 | 0 | MAA LAXMI ENTERPRISE | 8.15 | 0 | 0 | 0
1038 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Manikara, Purash & Kanpur (part) of kanpur Rejuvenation piped water supply scheme (Phase-II) , SM/06787 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | 844342 | 17/03/2021 | 0 | MAA LAXMI ENTERPRISE | 21.27 | 0 | 0 | 0
1039 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Manikara, Purash & Kanpur (part) of kanpur Rejuvenation piped water supply scheme (Phase-II) , SM/06787 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | 844391 | 26/03/2021 | 0 | NATURAL RESOURCES CONSORTIUM | 18.79 | 0 | 0 | 0
1040 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Manikara, Purash & Kanpur (part) of kanpur Rejuvenation piped water supply scheme (Phase-II) , SM/06787 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | 844392 | 26/03/2021 | 0 | PIKASU BOSE | 25.48 | 0 | 0 | 0
1041 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Manikara, Purash & Kanpur (part) of kanpur Rejuvenation piped water supply scheme (Phase-II) , SM/06787 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | 844328 | 29/03/2022 | 0 | PIKASU BOSE | 3.17 | 0 | 0 | 0
1042 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Manikara, Purash & Kanpur (part) of kanpur Rejuvenation piped water supply scheme (Phase-II) , SM/06787 | Retrofitting | Mass Awarness generation and IEC activities. | 844313 | 23/12/2021 | 0 | PRADIP KUMAR JATI | 42 | 0 | 0 | 0
1043 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Manikara, Purash & Kanpur (part) of kanpur Rejuvenation piped water supply scheme (Phase-II) , SM/06787 | Retrofitting | Additional laying distribution pipeline with repairing/ Refixing of FHTC at Kanpur Rejuvenation PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1234/HD | 05/03/2025 | 270 | S.S. ENTERPRISE | 12.46 | 0 | 0 | 80
1044 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) , SM/06779 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-A) | 1533/HD | 05/11/2020 | 30 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 18.84 | 0 | 0 | 0
1045 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) , SM/06779 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-B) | 1534/HD | 05/11/2020 | 30 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 18.84 | 0 | 0 | 0
1046 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) , SM/06779 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-C) | 1535/HD | 05/11/2020 | 30 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 18.84 | 0 | 0 | 0
1047 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) , SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 844356 | 23/03/2021 | 0 | BUILT INDIA | 15.55 | 0 | 0 | 0
1048 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) , SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 844345 | 28/09/2021 | 0 | UNIQUE AGENCY | 9.35 | 0 | 0 | 0
1049 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) , SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 844343 | 28/09/2021 | 0 | RAKESH ENTERPRISE | 4.11 | 0 | 0 | 0
1050 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) , SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 84431 | 01/03/2021 | 0 | UNIQUE AGENCY | 16.13 | 0 | 0 | 0
1051 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) , SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 84432 | 01/03/2021 | 0 | UNIQUE AGENCY | 16.15 | 0 | 0 | 0
1052 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) , SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | W/217 | 18/08/2021 | 0 | ALOK ENTERPRISE | 16.11 | 0 | 0 | 0
1053 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) , SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 627/21/2022 | 15/08/2020 | 0 | RAKESH ENTERPRISE | 4.35 | 5.8 | 200 | 0
1054 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Mellock Brahman Dhakuria PWSS, Bagnan-II Block Under Uluberia Sub-Division of Howrah Division PHE Dte. | 2122/HD | 24/11/2021 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.32 | 3.32 | 100 | 0
1055 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS CONSUMBLES AT SITE FOR CONSTRUCTION OF TUBE WELL IN DIFFERENT DISTRICT IN WEST BENGAL UNDER CMSD-I (D), CDD, PHE DTE. | 189/ CMSD-I (D) | 30/09/2021 | 15 | CHANDA ENTERPRISE | 4.8 | 1.08 | 100 | 0
1056 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | SUPPLY & DELIVERY OF BENTONITE POWDER SODIUM BASED CONSUMBLES AT SITE FOR CONSTRUCTION OF TUBE WELL IN DIFFERENT DISTRICT IN WEST BENGAL UNDER CMSD-I (D), CDD, PHE DTE. | 190/ CMSD-I (D) | 30/09/2021 | 15 | CHANDA ENTERPRISE | 2.93 | 0.59 | 20 | 0
1057 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR AMRAGORI PWSS, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 299/CMSD-I (D) | 08/07/2022 | 15 | DIPALI CONSTUCTION | 3.11 | 1.98 | 100 | 0
1058 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | PROVIDING TUBE WWLL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF MELLOCK PWSS, BANGAN-II BLOCK, HOWRAH DISTRICT UNDER CDD, PHE DTE. | 392/CMSD-II (D) | 01/08/2022 | 15 | M/S PRACHI ENGINEERING | 4.99 | 4.67 | 100 | 0
1059 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF MELLOCK, BAGNAN-II BLOCK, HOWRAH DISTRICT UNDER CDD, PHE DTE. | 391/CMSD-II (D) | 01/08/2022 | 15 | M/S PRACHI ENGINEERING | 4.04 | 3.86 | 100 | 0
1060 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | CONSTRUCTION OF TUBE WELL IN HOWRAH DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | 239/CMSD-II (D) | 20/05/2022 | 15 | CHANDA ENTERPRISE | 4.83 | 3.87 | 100 | 0
1061 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT MELLOK, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 298/CMSD-I (D) | 08/07/2022 | 15 | DIPALI CONSTUCTION | 2.09 | 1.79 | 100 | 0
1062 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT AUG. OF MELLOCK PWSS, BAGNAN-II BLOCK, HOWRAH DISTRICT UNDER CDD, PHE DTE. | 393/CMSD-II (D) | 01/08/2022 | 15 | M/S PRACHI ENGINEERING | 1.88 | 1.79 | 100 | 0
1063 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
1064 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mellok Brahmandakuria water supply scheme, Head work site, District- Howrah under Electrical Division, PHE Dte. | 783/ED | 09/02/2023 | 90 | DIPALI CONSTRUCTION | 10.79 | 10.42 | 96.55 | 1
1065 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. | 933/HMSD | 18/04/2023 | 153 | S.P. CONSTRUCTION | 0.4 | 0.4 | 100 | 40
1066 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District) | 959/HMSD | 20/04/2023 | 184 | SANJIB PRADHAN | 0.38 | 0.38 | 100 | 40
1067 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mellok Brahmandakuria water supply scheme, T.W. No.- II, Block: Bagnan, District- Howrah under Electrical Division, PHE Dte. | 3434/ED | 11/08/2023 | 90 | DIPALI CONSTRUCTION | 10.74 | 10.42 | 97 | 50
1068 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | CONSTRUCTION OF TUBE WELL (250MM X 150MM X DEPTH 220 MTRS) FOR IIEST (TW-I), MELLOK, HOWRAH DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | 400/CDD | 20/05/2022 | 30 | ASHUTOSH DAS & CO | 10.05 | 4.61 | 100 | 0
1069 | HOWRAH | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 230 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MELLOCK W/S SCH (Z-II, HW), BAGNAN-I BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 307/CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 10.33 | 9.7 | 100 | 0
1070 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Development of 2nd Tube well at Mellock Bramhan Dkhakuria PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 941/AE/USD | 22/03/2023 | 30 | LOKENATH ENTERPRISES | 0.71 | 0.71 | 100 | 100
1071 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Material Requisition To Resource Division | 775/HD | 24/02/2023 | 0 | Resource Division | 46.08 | 0 | 0 | 0
1072 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Material Requisition To Resource Division | 2753/HD | 28/07/2023 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1073 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Mellock Brahmandakuria P-III W/S. Sch. | 141 | 20/01/2023 | 0 | WBSEDCL | 2.6 | 0 | 0 | 0
1074 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | NEW SERVICE CONNECTION FOR AUGMENTATION OF MELLOK BRAHMANDAKURIA PH NO-II | 41 | 17/05/2023 | 0 | WBSEDCL | 2.74 | 0 | 0 | 0
1075 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Work Order for Construction of switch room (5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site of Augumentation of Mellock Brahman Dakuria PWSS of Bagnan-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | 2596/HD | 07/12/2022 | 60 | LOKENATH ENTERPRISES | 6.24 | 6.14 | 100 | 100
1076 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Work Order for Laying of Distribution System with providing FHTC for Augmentation of Mellock Brahman Dakuria PWSS of Bagnan-I & Bagnan-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. [Mouza-Masiyara, Sondail, Bramhan Dhakuria- House Hold- 950 nos] (Part-B) | 1996/HD | 26/09/2022 | 45 | CREATION CONSTRUCTION | 107.55 | 47.08 | 43.77 | 100
1077 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Work Order for Interconnection between tube wells & OHR at Mellock Bramhan Dkhakuria PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1844/HD | 02/05/2023 | 60 | GLOBUS CONSULTANCY | 7.34 | 4.63 | 100 | 100
1078 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Additional Laying of pipeline Mellock Brahman Dhakuria PWSS of Bagnan-I & II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Sondail & Masiyara) | 2033/AE/USD | 13/02/2024 | 60 | DUNCON INDIA | 16.52 | 16.51 | 100 | 100
1079 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Work Order for Laying of Distribution System with providing FHTC and Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), for Augumentation of Mellock Brahman Dakuria PWSS of Bagnan-I & Bagnan-II Block under Uluberia Sub Division under Howrah Division P.H.E. Dte. in the District of Howrah.[Mouza-Subsit, House Hold- 1454] (Part-A) | 2170/HD | 21/10/2022 | 893 | GHOSH CONCERN | 310.35 | 200.23 | 64.52 | 70
1080 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria , SM/09347 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
1081 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
1082 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Nischintapur PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | BP-2021-22-366 | 28/02/2022 | 0 | STEELCONC AND ASSOCIATES | 3.86 | 0 | 0 | 0
1083 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Work Order for Laying Distribution system, & FHTC (3145 nos) for Augmentation of Nischintapur PWSS under Amta-II Block under Uluberia Sub-Division under Howrah Division PHE Dte. | 184/HD | 31/01/2022 | 120 | VISHAL CONSTRUCTION CO. | 348.97 | 345.67 | 100 | 100
1084 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Material Requisition To Resource Division | 204/HD | 01/02/2022 | 0 | Resource Division | 19.32 | 0 | 0 | 0
1085 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Material Requisition To Resource Division | 1222/HD | 09/06/2022 | 0 | Resource Division | 6.21 | 0 | 0 | 0
1086 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Work Order for Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Nischintapur PWSS of Amta-II Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 2724/HD | 14/12/2022 | 30 | DEV DAS SHAW | 13.64 | 12.89 | 100 | 100
1087 | HOWRAH | Electrical | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nischintapur water supply scheme T.W. No. New, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | 1713/ED | 18/04/2023 | 90 | PADMA ENGINEERING CO. | 10.74 | 10.4 | 97.44 | 80
1088 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Interconnection between 3rd TW with LDS for Augmentation of Nischintapur Piped Water Supply scheme in Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 4858/HD | 22/11/2024 | 20 | DEV DAS SHAW | 15.37 | 4 | 20.94 | 100
1089 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Quotation money depostion for new service connection at Nischintapur Water Supply Scheme | BP-2023-24-775 | 29/03/2024 | 0 | WBSEDCL | 15.58 | 0 | 0 | 0
1090 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Additional LDS work to reduce water scanty problem from 3rd TW to Ghoshpara at Mouza Sheoraberia of Nischintapur PWSS under Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 3145/HD | 15/07/2025 | 45 | KALIDAS ENTERPRISE | 21.67 | 0 | 0 | 80
1091 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Amta-II Block) (PART-B) | 4117/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
1092 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Additional LDS work to reduce water scanty problem from 4th TW to Nischintapur at Mouza Nischintapur of Nischintapur PWSS under Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 4413/HD | 25/11/2025 | 45 | A. R. CONSTRUCTION | 22.93 | 0 | 0 | 0
1093 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Construction of Two storied switch room (3.6 x3.0)with water supply & sanitary arrangement at 3rd Tube well site of Nischintapur W/S scheme (SM/09720) of Amta-II Block under Uluberia Sub-Division under the Howrah Division, P.H.E. Dte. | 4859/HD | 22/11/2024 | 60 | DEV DAS SHAW | 7.79 | 0 | 0 | 100
1094 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Retrofitting of Pump house and ancillary work of HW Site, 2nd TW, 3rd TW site of Nischintapur W/S scheme at Amta-II Block under Uluberia Sub-Division of Howrah Division P.H.E Dte. | 1473/AE/USD | 14/01/2025 | 30 | MANIRUL ISLAM | 2.39 | 0 | 0 | 100
1095 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Structural repairing and renovation of the 3.50 lakh liter capacity OHR at HW site of Nischintapur PWSS under Amta-II block, under Uluberia Sub-Division PHE Dte under Howrah Division PHE Dte. (SM/09720) | 2764/HD | 12/06/2025 | 30 | MANIRUL ISLAM | 11.36 | 0 | 0 | 100
1096 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Retrofitting work of boundary wall along with Approach Road and other ancillary works at HW Site of Nischintapur W/S scheme within Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 2765/HD | 12/06/2025 | 45 | MANIRUL ISLAM | 10.71 | 0 | 0 | 100
1097 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. , SM/09720 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
1098 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Work Order for Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 1000m3 Staging Height 20 mtr. For Paschim Bainan W/S Scheme under Uluberia Sub-Division, under Howrah Division, P.H.E.Dte. | 221/HD | 03/02/2022 | 20 | PROSENJIT DAS | 0.65 | 0 | 0 | 0
1099 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Paschim Bainan PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 2146/HD | 01/12/2021 | 15 | RADIANT | 3.89 | 3.89 | 100 | 0
1100 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Work Order for Sinking of 3 (Three) nos PVC big dia Tube well 300 mm x 200 mm dia of 250 mtr deep for Augmentation of Paschim Bainan W/S scheme at Bagnan-I Block in Uluberia SubDivision P.H.E. Dte. under Howrah Division, P.H.E Dte. | 1010/HD | 05/05/2022 | 30 | AUXILIARY TUBEWELL DRILLERS | 49.48 | 45.68 | 92.33 | 0
1101 | HOWRAH | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Service connection for P.H. No.-III of Ground Based Piped Water Supply Scheme for Paschim Bainan | 1006615110/Quot/03 | 10/08/2022 | 365 | WBSEDCL | 0.68 | 0 | 0 | 0
1102 | HOWRAH | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | GO2122007937PH | 05/01/2022 | 365 | WBSEDCL | 0.68 | 0 | 0 | 0
1103 | HOWRAH | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Quotation bill for service connection P.H. No.-III at Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | 1046/ED | 21/08/2022 | 365 | WBSEDCL | 0.68 | 0 | 0 | 0
1104 | HOWRAH | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipments etc. including allied works fo Paschim Bainan W/S. Sch. TW-I | 2103/HMSD | 24/11/2022 | 30 | KARUNAMOY ENGINEERING | 4.87 | 4.87 | 100 | 0
1105 | HOWRAH | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Electric Supply at Bagnan | 46 | 22/08/2022 | 0 | WBSEDCL | 0.68 | 0 | 0 | 0
1106 | HOWRAH | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Electric Supply at Paschim Bainan | 53 | 23/08/2022 | 0 | WBSEDCL | 0.68 | 0 | 0 | 0
1107 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
1108 | HOWRAH | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | New Connection in for Paschim Bainan W/S. Sch. | 94 | 20/10/2022 | 0 | WBSEDCL | 4.12 | 0 | 0 | 0
1109 | HOWRAH | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | New Connection at Paschim Bainan W/S. Sch. |  | 17/10/2022 | 0 | WBSEDCL | 4.12 | 0 | 0 | 0
1110 | HOWRAH | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipments etc. including allied works fo Paschim Bainan W/S. Sch. RW-IV | 1793/ED | 02/11/2022 | 90 | HINDUSTAN ENGINEERING CORPORATION ( E & M ) | 10.84 | 10.83 | 99.95 | 0
1111 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Construction of switch room (3.60m X 3.0m) with water supply & sanitary arrangement at 4th tube well site of Augmentation of Paschim Bainan PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E Dte. (As per approved drawing of Howrah Division, PHE Dte). | 510/AE/USD | 27/09/2022 | 45 | K.N ENTERPRISE | 4.45 | 4.24 | 100 | 0
1112 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Development of 5th Tube well at Augmentation of Paschim Bainan PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 943/AE/USD | 22/03/2023 | 30 | LOKENATH ENTERPRISES | 0.71 | 0.71 | 100 | 100
1113 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Material Requisition To Resource Division | 1955/HD | 21/09/2022 | 0 | Resource Division | 0.05 | 0 | 0 | 0
1114 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Material Requisition To Resource Division | 1402/HD | 07/07/2022 | 0 | Resource Division | 87.96 | 0 | 0 | 0
1115 | HOWRAH | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Quotation Bill for New Service Connection at Paschim Bainan W/S. Sch. PH-V | 231 | 01/09/2023 | 0 | WBSEDCL | 4.96 | 0 | 0 | 0
1116 | HOWRAH | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Paschim Bainan water supply scheme, T.W. No. V, VI & VII, Block: Bagnan-I, District - Howrah under Electrical Division, PHE Dte. | 3456/ED | 11/08/2023 | 90 | SANKAR PRASAD DUTTA & CO. | 33.21 | 10.59 | 31.89 | 35
1117 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Work Order for Augmentation of Paschim Bainan Water Supply scheme with LDS, Laying of Rising main & FHTC work at Bagnan-I Block of Howrah District under Howrah Division, PHE Dte. | 592/HD | 15/03/2022 | 306 | S.P. CONSTRUCTION | 1002.85 | 899.81 | 100 | 100
1118 | HOWRAH | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Paschim Bainan water supply scheme, T.W. No. III, Block: Bagnan-I, District - Howrah under Electrical Division, PHE Dte. | 1915/ED | 21/11/2022 | 90 | MAA KALI ENTERPRISE | 10.01 | 9.74 | 97.26 | 97
1119 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Connection with 5th Tube well site to distribution line with providing FHTC at Paschim Bainan PWSS under Bagnan-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 248/AE/USD | 12/06/2024 | 30 | S R TRADING CORPORATION | 4.71 | 4.63 | 100 | 100
1120 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Construction of 1000 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection at Augmentation of Paschim Bainan PWSS of Bagnan-I Block under Uluberia Sub Division under Howrah Division PHE Dte. | 607/HD | 09/02/2024 | 720 | PIKASU BOSE | 239.3 | 17.56 | 7.34 | 24
1121 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bagnan-I Block) | 4127/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
1122 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Construction of switch room (5.40m X 3.60m) with water supply & sanitary arrangement at Head Work site of Augmentation of Paschim Bainan PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E Dte. (As per approved drawing of Howrah Division, PHE Dte). | 509/AE/USD | 27/09/2022 | 45 | S.P. CONSTRUCTION | 4.99 | 0 | 0 | 100
1123 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0.85 | 100 | 100
1124 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Additional laying distribution pipeline with FHTC at Paschim Bainan PWSS of Bagnan-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1137/HD | 06/03/2024 | 300 | JOY CHANDI CONSTRUCTION | 96.07 | 72.74 | 69.62 | 100
1125 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.85 | 0 | 0 | 0
1126 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Quotation for providing dedicated transformer at Paschim Bainan Water Supply Scheme, PH NO- I in the district Howrah under Electrical Division, PHE Dte. ( SM/10020), Reference Id- 860321509, Application ID- 100000126309 | BP-2024-25-547 | 13/03/2025 | 0 | WBSEDCL | 12.61 | 0 | 0 | 0
1127 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Quotation for new service connection for Augmentation of paschim w/s scheme, Ph No- VII (koria), in the district Howrah under Electrical Division, PHE Dte. ( SM/10020 ) Reference Id- 106993987, Application no- 1008460992 | W/176 | 30/07/2025 | 0 | WBSEDCL | 8.63 | 0 | 0 | 0
1128 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Quotation for new service connection for Augmentation of paschim w/s scheme, Ph No- VI (khajutty), in the district Howrah under Electrical Division, PHE Dte. ( SM/10020 ) Reference Id- 106992039, Application no- 1008456690 | W/175 | 31/07/2025 | 0 | WBSEDCL | 13.44 | 0 | 0 | 0
1129 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. , SM/10020 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
1130 | HOWRAH | Howrah Division | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. , SM/11718 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ulanpara PWSS of Bagnan I Block Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 2714/HD | 14/12/2022 | 45 | AUXILIARY TUBEWELL DRILLERS | 36.22 | 0 | 0 | 0
1131 | HOWRAH | Electrical | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. , SM/11718 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ulanpara water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 3526/ED | 30/12/2022 | 90 | M/S, GHOSH ENTERPRISE | 21.37 | 0 | 0 | 0
1132 | HOWRAH | Howrah Division | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. , SM/11718 | New | Work Order for Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC), Interconnection for 2nd TW and 1st Tube well (HW site) & Construction Of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref: Dept. Super Struc. DRG. No. PC I/OHR/11/2012) Including All pipe Connection including foundation design for ULANPARA PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE | 1651/HD | 18/04/2023 | 365 | SUDHAMAY MAJUMDAR | 361.15 | 0 | 0 | 0
1133 | HOWRAH | Howrah Division | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. , SM/11718 | New | Work Order for Preparation of DPR for new piped water supply scheme of Ulanpara PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 250/HD | 07/02/2022 | 15 | DULAL MAJUMDER | 2.69 | 2.69 | 100 | 100
1134 | HOWRAH | Howrah Division | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. , SM/11718 | New | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 48.67 | 0 | 0 | 0
1135 | HOWRAH | Howrah Division | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. , SM/11718 | New | Material Requisition To Resource Division | 1754/HD | 26/04/2023 | 0 | Resource Division | 42.67 | 0 | 0 | 0
1136 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Preparation of DPR with Route Survey for new piped water supply scheme of Banharishpur PWSS Under Panchla Block of Howrah Sadar Sub-Division PHE Dte. | 1929/HD | 19/09/2022 | 30 | STEELCONC AND ASSOCIATES | 2.91 | 2.91 | 100 | 0
1137 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Material Requisition To Resource Division | 446/HD | 06/02/2023 | 0 | Resource Division | 33.65 | 0 | 0 | 0
1138 | HOWRAH | Electrical | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Quotation Bill for New Service Connection at Banharishpur W/S. Sch. | 148 | 28/07/2023 | 0 | WBSEDCL | 6.77 | 0 | 0 | 0
1139 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Work Order for Laying of Distribution Pipeline with Functional Household Tap Connection (FHTC) of Banharishpur PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte.(Part-C) From Node Point-22-31 to Node Point- 64-65. | 2419/HD | 23/11/2022 | 45 | MANAS CHATTERJEE | 129.55 | 60.91 | 47.01 | 80
1140 | HOWRAH | Electrical | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Banharishpur water supply scheme, T.W. No. III & IV, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 933/ED | 22/02/2023 | 90 | A.G. ENTERPRISE | 21.49 | 10.4 | 48.4 | 50
1141 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Work Order for Construction of 2 nos (5.40Mx 3.60M) Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at 2nos T/well sites of Banharishpur PWSS at Panchla Block of Howrah District under Howrah Division, PHE Dte.. | 1773/HD | 27/04/2023 | 60 | ADRIJA ENTERPRISE | 13.25 | 6.63 | 50 | 50
1142 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Additional laying distribution pipe line and allied works at Banharishpur PWSS under Shyamchak mouza at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | 998/HD | 01/03/2024 | 75 | S RAHA ENTERPRISE | 74.68 | 44.35 | 59.39 | 60
1143 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 27.73 | 0 | 0 | 0
1144 | HOWRAH | Electrical | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Quotation money deposition for new service connection at Banharishpur pwss, P.H No.-I Dist-Howrah under ED PHED. App. No.-1007561303 Ref. ID.- 106491239 SM/11723 | 851 | 07/03/2024 | 0 | WBSEDCL | 25.8 | 0 | 0 | 0
1145 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Jaynagar PWSS(2 nos) & Banharishpur PWSS(2 nos) of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 1000/HD | 13/03/2023 | 977 | PRANTIK DRILLING AGENCY | 68.83 | 15.17 | 44.09 | 25
1146 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Work Order for Laying Distribution Pipe Lines With Functional Household Tap Connection(FHTC) for Augmentation of Banharishpur PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, PHE Dte.(Part-B) From Node Point-8-22 to Node Point-54-61. | 2257/HD | 04/11/2022 | 815 | MITHU BUILDERS | 129.62 | 101.3 | 78.32 | 100
1147 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Special repairing work for restoration of damage pavement caused by laying of pipe line from Node section 42 to 17 & Node section 27 to 21 for the 1.55 km (PMGSY/PWD) road at Banharishpur PWSS Under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 4199/HD | 27/09/2024 | 135 | COSMO ENTERPRISE | 22.92 | 0 | 0 | 80
1148 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Work Order for Construction Of 500 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir with Rising Main Pipeline Work and Laying Distribution Pipeline (From Node Point-1-R1 to Node Point- 10-11)with Providing FHTC (Functional Household Tap Connection) for Augmentation of Banharishpur PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | 2420/HD | 23/11/2022 | 1080 | COSMO ENTERPRISE | 227.02 | 82 | 36.12 | 30
1149 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4816/HD | 19/11/2024 | 510 | TECH VISION | 12.48 | 0.02 | 4.09 | 78
1150 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Laying of additional distribution pipe line adjoining to 2nd tubewell site and allied works at Banharishpur PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | 1217/HD | 11/03/2024 | 362 | JHARNA ENTERPRISE | 27.15 | 14.14 | 52.08 | 100
1151 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Banharishpur PWSS [SM/11723], Jujarsah PWSS [SM/10146], Samanti PWSS [SM/12562] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 229/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
1152 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah , SM/11723 | Augmentation | Additional Pipe distribution system, Construction of R.C.C Slab Culvert, construction of approach Road with land development & boundary wall at 2nd T/W Site at Banharishpur piped water supply scheme under Banharishpur Mouza Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 1245/HD | 12/03/2024 | 420 | COSMO ENTERPRISE | 51.65 | 17.1 | 37.51 | 25
1153 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Mato PWSS, Amta-I Block Under Uluberia SubDivision of Howrah Division PHE Dte. | 2150/HD | 01/12/2021 | 15 | RADIANT | 3.07 | 3.07 | 100 | 0
1154 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
1155 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Mato Water Supply Scheme under Amta-I block under Uluberia SubDivision under Howrah Division, PHE Dte. (Part-C) Mouza-GHORADAHA | 806/HD | 07/04/2022 | 45 | JOY CHANDI CONSTRUCTION | 64.62 | 66.51 | 100 | 100
1156 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Mato Water Supply Scheme under Amta-I block under Uluberia SubDivision under Howrah Division, PHE Dte. (Part-B) Mouza-BARUE | 805/HD | 07/04/2022 | 45 | BISWAJIT BAG | 65.21 | 67.16 | 100 | 100
1157 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Work Order for Dismantling, Demolition and Disposal of Rubbish, reinforcement, broken pipes & specials, Debris and filling the site upto existing ground level and clearing properly including complete in all respect of 136 cum capacity & 20.0 m staging height dilapidated RCC Over head Reservoir of Mato water supply scheme of Amta-I Blockunder Uluberia Sub-Division of Howrah Divsion PHE Dte. | 328/HD | 24/01/2023 | 60 | BISWAJIT BAG | 3.89 | 3.89 | 100 | 0
1158 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-1) | 524/AE/USD | 27/09/2022 | 45 | BISWAJIT BAG | 4.99 | 4.91 | 100 | 0
1159 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-2) | 525/AE/USD | 27/09/2022 | 45 | BISWAJIT BAG | 4.99 | 5.11 | 100 | 0
1160 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-3) | 526/AE/USD | 27/09/2022 | 45 | BISWAJIT BAG | 4.8 | 4.9 | 100 | 0
1161 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-4) | 527/AE/USD | 27/09/2022 | 45 | BISWAJIT BAG | 4.98 | 5.13 | 100 | 0
1162 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-2) | 531/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.94 | 5.07 | 100 | 0
1163 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-5) | 534/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.97 | 5.11 | 100 | 0
1164 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-6) | 535/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.98 | 5.09 | 100 | 0
1165 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-5) | 528/AE/USD | 27/09/2022 | 45 | BISWAJIT BAG | 5 | 5.09 | 100 | 0
1166 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-6) | 529/AE/USD | 27/09/2022 | 45 | BISWAJIT BAG | 4.98 | 5.09 | 100 | 0
1167 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-1) | 530/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.99 | 5.13 | 100 | 0
1168 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-3) | 532/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.92 | 5.06 | 100 | 0
1169 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-4) | 533/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.97 | 5.07 | 100 | 0
1170 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-7) | 536/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.99 | 5.14 | 100 | 0
1171 | HOWRAH | Electrical | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MATO PIPED W/S SCHEME, T.W. No. V, Block: Amta-I, District - Howrah under JJM Program under Electrical Division PHE Dte. | 423/ED | 29/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 10.16 | 97.45 | 85
1172 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Sinking of 1 (one) Nos. replaced & 1 (one) Nos new (4th) Tube Well 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 1214/HD | 11/03/2024 | 60 | LOKENATH ENTERPRISES | 30.28 | 27.64 | 100 | 100
1173 | HOWRAH | Electrical | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Quotation for new service connection for Mato w/s scheme, P/H No. 5, near Ghoradaha Primary School Block- Amta- I, Dist. - Howrah. Application No. 1007444170 Ref. id: 106409240 SM/09930 | 798 | 23/02/2024 | 0 | WBSEDCL | 14.15 | 0 | 0 | 0
1174 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Additional laying distribution pipeline with FHTC at Mato PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Location: Ghoradaha, Barui & Mato part) | 1226/HD | 05/03/2025 | 45 | MA DURGA ENTERPRISE | 26.57 | 0 | 0 | 0
1175 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Construction of Kiosk (one no (Size inside 3.0 x 3.0m)) at 5th TW Site and interconnection with 5thTW and ancilary works at Mato PWSS under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1751/AE/USD | 04/03/2025 | 30 | MA DURGA ENTERPRISE | 3.35 | 0 | 0 | 100
1176 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
1177 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. , SM/09930 | Augmentation | Work Order for Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Ref.OHR Drawing No.PC-I/OHR/07/2012 , Sheet No.1&2) (pile foundation)& Laying of HDPE & DI pipeline at (Part-A) Mouza-MATO & providing Functional Household Tap Connection (FHTC) at Augumentation of Mato Pipe Water Supply Scheme at Amta-I block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 1928/HD | 19/09/2022 | 1158 | KAMRULA CONSTRUCTION CO | 164.72 | 94.92 | 57.62 | 92
1178 | HOWRAH | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Work Order for Preparation of DPR for new piped water supply scheme of Nawapara PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 245/HD | 07/02/2022 | 15 | VOYAGER | 3.2 | 3.3 | 100 | 0
1179 | HOWRAH | Electrical | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nawapara water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | 3517/ED | 30/12/2022 | 90 | T S CONSTRUCTION | 22.49 | 21.64 | 96.2 | 80
1180 | HOWRAH | Electrical | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Uttar Khariop water supply scheme, T.W. No. III, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | 2076/ED | 31/05/2023 | 90 | D. K. ELECTRIC | 10.72 | 10.72 | 100 | 100
1181 | HOWRAH | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nawapara PWSS (2nos) & Ajangachi PWSS (2nos) & Jhikira PWSS (2nos) of Amta-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 3440/HD | 26/09/2023 | 60 | PRANTIK DRILLING AGENCY | 77.89 | 24.74 | 100 | 100
1182 | HOWRAH | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 10.04 | 0 | 0 | 0
1183 | HOWRAH | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Material Requisition To Resource Division | 1286/HD | 13/03/2024 | 0 | Resource Division | 22.35 | 0 | 0 | 0
1184 | HOWRAH | Electrical | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Quotation Bill for New Service Connection at Nowpara W/S. Sch. PH-II | 617 | 08/01/2024 | 0 | WBSEDCL | 4.22 | 0 | 0 | 0
1185 | HOWRAH | Electrical | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Quotation Bill for New Service Connection at Nowpara W/S. Sch. PH-I | 618 | 08/01/2024 | 0 | WBSEDCL | 7.8 | 0 | 0 | 0
1186 | HOWRAH | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation & foundation design, Laying Distribution Pipeline & Providing FHTC (3243 nos) for Nawapara Water Supply Scheme In Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 2947/HD | 14/08/2023 | 1005 | ORIENT CONSTRUCTION | 675.07 | 189.55 | 28.08 | 60
1187 | HOWRAH | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Construction of boundary wall & Land Development at HW Site Nawpara PWSS scheme under Amta-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (SM/11793) | 1510/HD | 21/03/2025 | 60 | APEX ENGINEERING | 21.55 | 0 | 0 | 0
1188 | HOWRAH | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Construction of boundary wall & Land Development at 2nd TW Site Nawpara PWSS scheme under Amta-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (SM/11793) | 1072/HD | 27/02/2025 | 225 | M/S KANIKA ROY ENTERPRISE | 12.37 | 0 | 0 | 80
1189 | HOWRAH | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Construction of switch room SLOPE ROOF (5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site of Nawpara PWSS (H/W) of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte | 4557/HD | 22/10/2024 | 120 | RAJ ENTERPRISE | 6.91 | 0 | 0 | 100
1190 | HOWRAH | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Construction of switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement at Nawpara PWSS (2nd Tube well) of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 4558/HD | 22/10/2024 | 120 | RAJ ENTERPRISE | 5.8 | 0 | 0 | 100
1191 | HOWRAH | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
1192 | HOWRAH | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. , SM/11793 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
1193 | HOWRAH | Howrah Division | Sonatala Piped Water Supply Scheme , SM/14949 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sonatala PWSS of Udaynarayanpur Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 664/HD | 17/02/2023 | 30 | LOKENATH ENTERPRISES | 26.22 | 22.69 | 100 | 100
1194 | HOWRAH | Howrah Division | Sonatala Piped Water Supply Scheme , SM/14949 | New | Material Requisition To Resource Division | 421/HD | 03/02/2023 | 0 | Resource Division | 7.84 | 0 | 0 | 0
1195 | HOWRAH | Howrah Division | Sonatala Piped Water Supply Scheme , SM/14949 | New | Material Requisition To Resource Division | 2830/HD | 04/08/2023 | 0 | Resource Division | 14.77 | 0 | 0 | 0
1196 | HOWRAH | Howrah Division | Sonatala Piped Water Supply Scheme , SM/14949 | New | Material Requisition To Resource Division | 3217/HD | 05/09/2023 | 0 | Resource Division | 29.9 | 0 | 0 | 0
1197 | HOWRAH | Electrical | Sonatala Piped Water Supply Scheme , SM/14949 | New | QUOTATION OF NEW SERVICE CONNECTION FOR SONATALA W/S SCHEME, PH-II | 126 | 20/07/2023 | 0 | WBSEDCL | 4.2 | 0 | 0 | 0
1198 | HOWRAH | Electrical | Sonatala Piped Water Supply Scheme , SM/14949 | New | QUOTATION OF NEW SERVICE CONNECTION FOR SONATALA W/S SCHEME, PH NO-I | 125 | 20/07/2023 | 0 | WBSEDCL | 2.58 | 0 | 0 | 0
1199 | HOWRAH | Electrical | Sonatala Piped Water Supply Scheme , SM/14949 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sonatala water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 929/ED | 22/02/2023 | 90 | TRIO CONCERN | 20.88 | 20.81 | 100 | 80
1200 | HOWRAH | Howrah Division | Sonatala Piped Water Supply Scheme , SM/14949 | New | Material Requisition To Resource Division | 3884/HD | 05/09/2024 | 0 | Resource Division | 2.77 | 0 | 0 | 0
1201 | HOWRAH | Howrah Division | Sonatala Piped Water Supply Scheme , SM/14949 | New | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site along with restoration work of damaged pipeline of SONATOLA Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | 2276/HD | 07/05/2025 | 60 | GUPTA ENTERPRISE | 63.76 | 0 | 0 | 0
1202 | HOWRAH | Howrah Division | Sonatala Piped Water Supply Scheme , SM/14949 | New | Rising Main & Inter Connection with both tube wells of SONATOLA Pipe Water Supply Scheme (SM/14949) at Udaynarayanpur Block under Howrah Division, PHE Dte. | 2280/HD | 07/05/2025 | 45 | GUPTA ENTERPRISE | 18.62 | 0 | 0 | 0
1203 | HOWRAH | Howrah Division | Sonatala Piped Water Supply Scheme , SM/14949 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Udaynarayanpur Block) (PART-B) | 4124/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
1204 | HOWRAH | Howrah Division | Sonatala Piped Water Supply Scheme , SM/14949 | New | Work Order for Construction of 500 Cum OHR including soil investigation, LDS with FHTC, Two Nos Pump House of SONATALA PWSS at Udaynarayanpur Block of Howrah District under Howrah Division, P. H. E. Dte. | 1689/HD | 20/04/2023 | 1275 | GUPTA ENTERPRISE | 450.11 | 272.43 | 60.53 | 30
1205 | HOWRAH | Howrah Division | Sonatala Piped Water Supply Scheme , SM/14949 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4813/HD | 19/11/2024 | 510 | HORIZEN | 13.59 | 1.04 | 99.97 | 70
1206 | HOWRAH | Electrical | Dakshin Panchla Piped Water Supply Scheme , SM/17196 | New | upply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dakshin Panchla water supply scheme, T.W. No. I & II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 1731/ED | 19/04/2023 | 90 | SANKAR PRASAD DUTTA & CO. | 10.91 | 0 | 0 | 0
1207 | HOWRAH | Howrah Division | Dakshin Panchla Piped Water Supply Scheme , SM/17196 | New | Work Order for Construction of 100 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/6/2012) including Soil Investigation, Foundation Design & All pipe Connection, Pump House (5.40m x 3.60 m), Construction of Boundary Wall at Head work Site, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work ,Providing FHTC (Functional Household Tap Connection) for Dakshin Panchla PWSS at Panchla Block of Howrah District under Howrah Division, P. H. E. Dte. | 1735/HD | 25/04/2023 | 335 | BISWAJIT BAG | 180.62 | 0 | 0 | 0
1208 | HOWRAH | Electrical | Dakshin Panchla Piped Water Supply Scheme , SM/17196 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dakshin Panchla water supply scheme, T.W. No. II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 3447/ED | 11/08/2023 | 90 | BARISAL TRADING CO. | 10.74 | 0 | 0 | 0
1209 | HOWRAH | Howrah Division | Dakshin Panchla Piped Water Supply Scheme , SM/17196 | New | Continuation order for Preparation of DPR for augmentation of existing piped water supply scheme of Dakshin Panchla PWSS, Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | 1460/HD | 14/07/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.63 | 2.6 | 100 | 100
1210 | HOWRAH | Howrah Division | Dakshin Panchla Piped Water Supply Scheme , SM/17196 | New | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 4.98 | 0 | 0 | 0
1211 | HOWRAH | Howrah Division | Dakshin Panchla Piped Water Supply Scheme , SM/17196 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Dakshin Panchla PWSS of Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 1528/HD | 04/04/2023 | 855 | ZEOLITE FRESH INDIA | 25.71 | 0 | 0 | 100
1212 | HOWRAH | Electrical | Dakshin Panchla Piped Water Supply Scheme , SM/17196 | New | Quotation money deposition for new service connection at Dakshin Panchla w/s scheme, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008774356 Reference ID- 107177936 SM Code- 17196 |  | 11/09/2025 | 0 | WBSEDCL | 19.96 | 0 | 0 | 0
1213 | HOWRAH | Electrical | Dakshin Panchla Piped Water Supply Scheme , SM/17196 | New | Quotation money deposition for new service connection at Daskhin Panchla w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008652604 Reference ID- 107105969 SM Code- 17196 |  | 30/06/2025 | 0 | WBSEDCL | 9.62 | 0 | 0 | 0
1214 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Preparation of DPR for Augmentation of Udaynarayanpur (Zone-I) PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 326/AE/USD | 16/08/2022 | 45 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.2 | 3.19 | 100 | 100
1215 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Preparation of DPR for Augmentation of Udaynarayanpur (Zone-II) PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 327/AE/USD | 16/08/2022 | 45 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.18 | 4.18 | 100 | 100
1216 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Material Requisition To Resource Division | 421/HD | 03/02/2023 | 0 | Resource Division | 70.86 | 0 | 0 | 0
1217 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Material Requisition To Resource Division | 2830/HD | 04/08/2023 | 0 | Resource Division | 49.53 | 0 | 0 | 0
1218 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Construction of Boundary Wall, Construction of Approach Road and Land Development and Additional Laying of Distribution Pipe Lines with providing FHTC for leftout area for UDAYNARAYANPUR ZONE-I of UDAYNARAYANPUR ZONE-I & II Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. (SM/18398) | 2861/HD | 24/06/2024 | 60 | M/S B.S.P. ENTERPRISES | 171.67 | 24.1 | 14.04 | 40
1219 | HOWRAH | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF UDAYNARAYANPUR PIPED W/S SCHEME, Zone - I & II, T.W. No. III, District - Howrah under JJM Program under Electrical Division PHE Dte. | 425/ED | 29/02/2024 | 90 | PERFECT AIRCONDITION | 10.75 | 0 | 0 | 0
1220 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Udaynarayanpur PWSS Zone -I (2 nos) and Zone-II (1 no) of Augmentation Udaynarayanpur Block Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 3618/HD | 09/10/2023 | 45 | MUNSHI ENTERPRISE | 52.12 | 43.76 | 100 | 90
1221 | HOWRAH | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Udaynarayanpur water supply scheme, Zone- I, T.W. No. III, Dist.- Howrah under Electrical Division, PHE Dte. | 539/HMSD | 17/03/2022 | 21 | C.M. ENTERPRISE | 2.74 | 2.72 | 100 | 90
1222 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at different PWSS of Udaynarayanpur Block under Howrah R.W.S Sub-Division, under Howrah Division, P.H.E. Dte.(Part-D) | 85/RWS | 08/02/2024 | 15 | ABONTICA ENTERPRISE | 0.57 | 0.57 | 100 | 80
1223 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at different PWSS of Udaynarayanpur Block under Howrah R.W.S Sub-Division, under Howrah Division, P.H.E. Dte. (Part-C) | 84/RWS | 08/02/2024 | 15 | ABONTICA ENTERPRISE | 0.91 | 0.91 | 100 | 80
1224 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at different PWSS of Udaynarayanpur Block under Howrah R.W.S Sub-Division, under Howrah Division, P.H.E. Dte.(Part-B) | 83/RWS | 08/02/2024 | 15 | ABONTICA ENTERPRISE | 0.91 | 0.91 | 100 | 80
1225 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at different PWSS of Udaynarayanpur Block under Howrah R.W.S Sub-Division, under Howrah Division, P.H.E. Dte.(part-A) | 82/RWS | 08/02/2024 | 15 | ABONTICA ENTERPRISE | 0.91 | 0.91 | 100 | 80
1226 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Material Requisition To Resource Division | 1049/HD | 04/03/2024 | 0 | Resource Division | 132.58 | 0 | 0 | 0
1227 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Permanent restoration work of probable damage stretches of Udaynarayanpur-Pancharul road, from ch. 0.00 km to 0.50 km & Amta-Rajapur-Dihibhurshut road from 15.50 km to 16.20 km, due to laying of water supply pipe line by P.H.E. i.c.w. rejuvenation of Udaynarayanpur water supply project under Howrah highway division, P.W.(Roads) Dte. in the district of Howrah. | BP-2024-25-241 | 06/08/2024 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 6.65 | 0 | 0 | 0
1228 | HOWRAH | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Quotation for new service connection for Augmentation of Udaynaraynpur Zone-I & II Water Supply Scheme, PH NO- II in the district Howrah under Electrical Division, PHE Dte. ( SM/18398), Reference Id- 106420105, Application no- 1007452865 | 910 | 21/03/2024 | 0 | WBSEDCL | 3.9 | 0 | 0 | 0
1229 | HOWRAH | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Quotation for new service connection for source Augmentation of Udaynarayanpur Water Supply Scheme, Zone- I & II, TW NO- III in the district Howrah under Electrical Division, PHE Dte. (SM/18398), Reference Id- 106743785 Application no- 1008083381 |  | 03/10/2024 | 0 | WBSEDCL | 7.68 | 0 | 0 | 0
1230 | HOWRAH | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Quotation for new service connection for source Augmentation of Udaynarayanpur Water Supply Scheme, Zone- I & II, TW NO- III in the district Howrah under Electrical Division, PHE Dte. (SM/18398), Reference Id- 106743785 Application no- 1008083381 | 498 | 21/10/2024 | 0 | WBSEDCL | 6.9 | 0 | 0 | 0
1231 | HOWRAH | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of MARCH,2024 | 225 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.16 | 0 | 0 | 0
1232 | HOWRAH | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of April,2024 | 227 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.2 | 0 | 0 | 0
1233 | HOWRAH | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Quotation for new service connection for Augmentation of Udaynaraynpur Zone-I & II Water Supply Scheme, PH NO- I in the district Howrah under Electrical Division, PHE Dte. ( SM/18398), Reference Id- 106420083, Application no- 1007452782 | 912 | 21/03/2024 | 0 | WBSEDCL | 3.14 | 0 | 0 | 0
1234 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | NDT for OHR of Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | BP-2024-25-216 | 26/07/2024 | 0 | JADAVPUR UNIVERSITY | 1.77 | 0 | 0 | 0
1235 | HOWRAH | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of February,2024 | 224 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.2 | 0 | 0 | 0
1236 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) and construction of 2 nos Pump House (H/W Site & 2nd T/W Site) for UDAYNARAYANPUR Agumentation Zone-I Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. | 2645/HD | 18/07/2023 | 978 | M/S B.S.P. ENTERPRISES | 378.71 | 325.97 | 86.07 | 75
1237 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) & construction of 750 cum capacity 20mtr staging height RCC Over head Reservoir (including pile foundation), pipe connection & cost of pipes & soil investigation with design for pile foundation & construction of 1no Pump house at HW site for Udaynarayanpur Augmentation Zone-II Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. | 2759/HD | 31/07/2023 | 899 | GHOSH CONCERN | 723.52 | 371.6 | 51.36 | 30
1238 | HOWRAH | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Udaynarayanpur (Zone-I & II) water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 3845/ED | 04/10/2023 | 606 | M/S, GHOSH ENTERPRISE | 23.17 | 0 | 0 | 80
1239 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Work order for temporary staging, welding arrangements and some allied works for conducting NDT for Udaynarayanpur OHR of Udaynarayanpur Zone-I & II PWSS at Udaynarayanpur block under Howrah Division, PHE Dte. | 529/RWS | 10/12/2024 | 15 | BINOY KOLEY | 0.85 | 0 | 0 | 95
1240 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4813/HD | 19/11/2024 | 510 | HORIZEN | 13.59 | 3.12 | 100 | 70
1241 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme , SM/18398 | Augmentation | Additional Laying of Distribution Pipe Lines for leftout area of UDAYNARAYANPUR ZONE-II Piped Water Supply Scheme, Rising Main & Inter Connection with PH-1 & PH-5 of UDAYNARAYANPUR ZONE-I & II PWSS, Rising Main & Inter Connection with both PH-3 & PH-4 and Repairing of Pump House & Construction of W/C at H/W Site of UDAYNARAYANPUR ZONE-I & II PWSS at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. [SM/18398] | 3872/HD | 04/09/2024 | 525 | GHOSH CONCERN | 197.8 | 0 | 0 | 80
1242 | HOWRAH | Electrical | Source Augmentation of Majhu Khetra Water Supply Scheme , SM/18841 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of MajhuKhetra Water Supply Scheme Block- Jagatballavpur District- Howrah under JJM Program under Electrical Division PHE Dte. | 4529/ED | 23/11/2023 | 90 | APEX ENGINEERING & PROJECT CO. | 10.74 | 0 | 0 | 0
1243 | HOWRAH | Howrah Division | Source Augmentation of Majhu Khetra Water Supply Scheme , SM/18841 | Augmentation | Reconnection of FHTC& Allied Works at Maju khetra PWSS at Jagatballavpur Block under Howrah sadar Sub-Division of Howrah Division PHE Dte. | 160/HSSD | 12/02/2024 | 60 | KUNAL BANERJEE | 0.9 | 0.89 | 100 | 100
1244 | HOWRAH | Howrah Division | Source Augmentation of Majhu Khetra Water Supply Scheme , SM/18841 | Augmentation | Construction of Boundary Wall at Head work Site of Size-(50.00 m x 40.00 m), Reconnection of FHTC & distribution pipe line and Allied Works at Majhu Khetra PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 1215/HD | 11/03/2024 | 420 | ENVOTECH INFRA SOLUTION | 56.71 | 15.2 | 26.8 | 80
1245 | HOWRAH | Howrah Division | Source Augmentation of Majhu Khetra Water Supply Scheme , SM/18841 | Augmentation | Preparation of DPR for Source Augmentation for Maju Khetra PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. | 828/HSSD | 09/08/2024 | 15 | APEX ENGINEERING | 0.78 | 0 | 0 | 0
1246 | HOWRAH | Howrah Division | Source Augmentation of Majhu Khetra Water Supply Scheme , SM/18841 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Source Augmentation of Gobindapur Piped Water Supply Scheme [SM/18843],Source Augmentation of Laskarpur Piped Water Supply Scheme [SM/18842], and Source Augmentation of Majhu Khetra Water Supply Scheme [SM/18841] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 233-A/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
1247 | HOWRAH | Howrah Division | Source Augmentation of Majhu Khetra Water Supply Scheme , SM/18841 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Gobindapur PWSS [SM/18843], Laskarpur PWSS [SM/18842], and Majhu Khetra PWSS [SM/18841] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 232/HSSD | 28/02/2025 | 15 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
1248 | HOWRAH | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme , SM/18845 | Augmentation | Sinking 1No. 250 X 150 mm Dia and 240 m deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Beldubi PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 997/HD | 01/03/2024 | 30 | AUXILIARY TUBEWELL DRILLERS | 14.59 | 0 | 0 | 100
1249 | HOWRAH | Electrical | Source Augmentation of Beldubi Water Supply Scheme , SM/18845 | Augmentation | Quotation money deposition for new service connection at Beldubi w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008188704 Reference ID- 106812203 SM Code- 18845 | BP-24-25-583 | 19/11/2024 | 0 | WBSEDCL | 4.19 | 0 | 0 | 0
1250 | HOWRAH | Electrical | Source Augmentation of Beldubi Water Supply Scheme , SM/18845 | Augmentation | Quotation money deposition for additional work at Beldubi w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 100000124155 Reference ID- 860319335 SM Code- 18845 | 610 | 05/12/2024 | 0 | WBSEDCL | 0.02 | 0 | 0 | 0
1251 | HOWRAH | Electrical | Source Augmentation of Beldubi Water Supply Scheme , SM/18845 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Beldubi Water Supply Scheme Block- Panchla District- Howrah under JJM Program under Electrical Division PHE Dte. | 4537/ED | 23/11/2023 | 554 | D. K. ELECTRIC | 10.74 | 0 | 0 | 95
1252 | HOWRAH | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme , SM/18845 | Augmentation | Reconnection of FHTC & distribution pipe line and allied works, Construction of 1 (One) no.pump house (5.40m x 3.60 m), Construction of 1 (One) no. Boundary wall at Beldubi piped water supply scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 1139/HD | 06/03/2024 | 361 | BISWAJIT BAG | 50.57 | 29.53 | 62.14 | 40
1253 | HOWRAH | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme , SM/18845 | Augmentation | Reconnection of FHTC& Allied Works at Beldubi PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | 161/HSSD | 12/02/2024 | 60 | KUNAL BANERJEE | 0.9 | 0 | 0 | 100
1254 | HOWRAH | Electrical | Source Augmentation of Beldubi Water Supply Scheme , SM/18845 | Augmentation | Shifting of HT oh line along with dp installed for placing DTR for PHE at village Beldubi under Burikhali CCC Application No- 100000126831 Reference ID- 860322111 SM Code- 18845 | 667 | 21/01/2025 | 0 | WBSEDCL | 0.59 | 0 | 0 | 0
1255 | HOWRAH | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme , SM/18845 | Augmentation | Preparation of DPR for Source Augmentation for Beldubi PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. | 827/HSSD | 09/08/2024 | 15 | APEX ENGINEERING | 0.78 | 0 | 0 | 0
1256 | HOWRAH | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme , SM/18845 | Augmentation | Design,drawing,construction including rcc foundation and commissioning of iron elimination plant of capacity 50.00 cum per hour including 3(three) month trial run in the premises of Beldubi PWSS Under Howrah Sadar Sub-Division of Howrah Division P.H.E Dte. | 2889/HD | 25/06/2024 | 540 | NEER UDYOG | 24.38 | 0 | 0 | 100
1257 | HOWRAH | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme , SM/18845 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Sahapur PWSS [SM/18844], and Beldubi PWSS [SM/04274] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 230/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.57 | 0 | 0 | 100
1258 | HOWRAH | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme , SM/18845 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Source Augmentation of Beldubi Water Supply Scheme [SM/18845], Source Augmentation of Bikihakola Water Supply Scheme [SM/18846], Source Augmentation of Sahapur Piped Water Supply Scheme [SM/18844] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 233/HSSD | 28/02/2025 | 15 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
1259 | HOWRAH | Howrah Division | Source Augmentation of Bauria Water Supply Scheme , SM/18850 | Augmentation | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at at 3rd tube well site of Bauria PWSS of Uluberia-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | 1841/HD | 02/05/2023 | 90 | CREATION | 6.95 | 6.69 | 100 | 100
1260 | HOWRAH | Howrah Division | Source Augmentation of Bauria Water Supply Scheme , SM/18850 | Augmentation | Work Order for Connection between 3rd TW with distribution pipeline to built up pressure for Bauria w/s scheme under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 1842/HD | 02/05/2023 | 60 | PRADIP KUMAR JATI | 48.41 | 41.43 | 100 | 100
1261 | HOWRAH | Howrah Division | Source Augmentation of Bauria Water Supply Scheme , SM/18850 | Augmentation | Preparation of DPR for Source Strengthning at Bauria PWSS, Uluberia-I Block under Uluberia Sub-Division of Howrah Division PHE Dte | 495/AE/USD | 29/09/2023 | 30 | APEX ENGINEERING | 0.78 | 0 | 0 | 100
1262 | HOWRAH | Howrah Division | Source Augmentation of Bauria Water Supply Scheme , SM/18850 | Augmentation | Work Order for construction of Guard wall cum boundary wall, Land Development, Barbed wire protection at HW site Site & allied works of Bauria W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 570/HD | 13/02/2023 | 45 | MJA ENTERPRISE | 37.38 | 31.02 | 100 | 60
1263 | HOWRAH | Electrical | Source Augmentation of Bauria Water Supply Scheme , SM/18850 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bauria water supply scheme, T.W. No. III, Block: Uluberia-I, District - Howrah under Electrical Division, PHE Dte. | 3878/ED | 06/10/2023 | 209 | MAA KALI ENTERPRISE | 10.74 | 10.4 | 97.43 | 70
1264 | HOWRAH | Electrical | Baniban Zone-I Piped Water Supply Scheme , SM/18566 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniban (Zone-I) water supply scheme, T.W. No.- I, II, III & IV, Block: Uluberia-II District- Howrah under Electrical Division, PHE Dte. | 3582/ED | 28/08/2023 | 90 | D. K. ELECTRIC | 42.71 | 0 | 0 | 0
1265 | HOWRAH | Howrah Division | Baniban Zone-I Piped Water Supply Scheme , SM/18566 | New | Sinking of 4 (Four) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete, 4no 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement, Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around head work site, Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site, land development of Head work site and other Tube well sites, Laying distribution system (HDPE & DI) & Providing Household Connection, Interconnection between Tube wells & 700 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design For Baniban Piped Water Supply Scheme (Zone-I) in Uluberia-II Block of Howrah District under Howrah Division, P.H.E. Dte. | 2963/HD | 16/08/2023 | 900 | SAMIRON GHOSH | 1019.91 | 0 | 0 | 0
1266 | HOWRAH | Howrah Division | Uttar Manasri Piped Water Supply Scheme. , SM/18914 | New | Material Requisition To Resource Division | 4024/HD | 07/11/2023 | 0 | Resource Division | 116.49 | 0 | 0 | 0
1267 | HOWRAH | Howrah Division | Uttar Manasri Piped Water Supply Scheme. , SM/18914 | New | Material Requisition To Resource Division | 1049/HD | 04/03/2024 | 0 | Resource Division | 36.78 | 0 | 0 | 0
1268 | HOWRAH | Howrah Division | Uttar Manasri Piped Water Supply Scheme. , SM/18914 | New | Material Requisition To Resource Division | 3884/HD | 05/09/2024 | 0 | Resource Division | 9.98 | 0 | 0 | 0
1269 | HOWRAH | Electrical | Uttar Manasri Piped Water Supply Scheme. , SM/18914 | New | Quotation Bill for New Service Connection at Uttar Manashree W/S. Sch. | 703 | 24/01/2024 | 0 | WBSEDCL | 14.99 | 0 | 0 | 0
1270 | HOWRAH | Electrical | Uttar Manasri Piped Water Supply Scheme. , SM/18914 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Uttar Manasri water supply scheme, T.W. No. I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 4542/ED | 23/11/2023 | 586 | M/S DAS ENTERPRISE | 22.04 | 2.8 | 12.72 | 50
1271 | HOWRAH | Howrah Division | Uttar Manasri Piped Water Supply Scheme. , SM/18914 | New | Construction of 600 cum capacity RCC OHR with 20.0 mtr. staging height including soil investigation, Sinking of 2 nos. 300 mm X 200 mm dia X 230 m deep Tubewell, Construction of 2 nos Switch Room with sanitary arrangement, Laying Distribution System, providing Functional Household Tap Connection (FHTC) for UTTAR MANASRI Piped Water Supply Scheme under Udaynarayanpur block under Howrah Division, PHE Dte. [No. of FHTC=3307] | 3825/HD | 16/10/2023 | 900 | SAMIRON GHOSH | 825.77 | 354.83 | 42.97 | 25
1272 | HOWRAH | Howrah Division | Uttar Manasri Piped Water Supply Scheme. , SM/18914 | New | Construction of Boundary Wall, Land Development at HEAD WORK Site, Additional Laying of Distribution Pipe Lines at UTTAR MANASRI Piped Water Supply Scheme and Additional Laying of Distribution Pipe Lines at KHALATPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P. H. E. Dte. | 1855/HD | 16/04/2025 | 300 | SAMIRON GHOSH | 96.34 | 0 | 0 | 40
1273 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) , SM/07075 | Retrofitting | Interconnection of Pump1 and 2 with proposed 700 cum reservoir for Bikihakola Water Supply scheme at Panchla Block under Howrah Division, P.H.E. Dte. | W/597 | 28/12/2021 | 0 | UNIVERSAL CORPORATION | 23.22 | 0 | 0 | 0
1274 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) , SM/07075 | Retrofitting | Trial Run and Operation & maintenance of pipe lines (LDS & Risingmain) sluice valve & street stand post etc. including operation of sluice valves at Bikihakola w/s scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. (90 days from issue of Work Order) | W/598 | 24/12/2021 | 0 | UNIVERSAL CORPORATION | 1.15 | 0 | 0 | 0
1275 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) , SM/07075 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributin system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) | 844325 | 24/03/2022 | 0 | M/S ASHIRBAD (INDIA) | 55.24 | 0 | 0 | 0
1276 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) , SM/07075 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-III) | 844326 | 24/03/2022 | 0 | PRADIP KUMAR JATI | 89.17 | 0 | 0 | 0
1277 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) , SM/07075 | Retrofitting | FHTC of Bikihakola W/SScheme under Panchla Block under Howrah Sadar Sub-Division PHE Dte. (Phase-IV) | 844323 | 24/03/2022 | 0 | G.B. CONSTRUCTION AND CO | 62.79 | 0 | 0 | 0
1278 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) , SM/07075 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikihakola piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) Part- A | 349/HD | 17/02/2022 | 30 | UNIVERSAL CORPORATION | 4.3 | 0 | 0 | 0
1279 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) , SM/07075 | Retrofitting | Work Order for Retrofitting work for Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola PWSS under Panchla Block of Howrah Sadar Sub Division under Howrah Division, PHE Dte.(Phase-II) (Part-A) No of House Hold= 100 nos. | 661/HD | 23/03/2022 | 20 | UNIQUE CONSTRUCTION | 3.82 | 0 | 0 | 100
1280 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) , SM/07075 | Retrofitting | Work Order for Retrofitting work for Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola PWSS under Panchla Block of Howrah Sadar Sub Division under Howrah Division, PHE Dte.(Phase-II) (Part-B)No of House Hold= 100 nos. | 662/HD | 23/03/2022 | 20 | UNIQUE CONSTRUCTION | 3.67 | 0 | 0 | 100
1281 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-3) , SM/07076 | Retrofitting | FHTC of Bikihakola W/SScheme under Panchla Block under Howrah Sadar Sub-Division PHE Dte. (Phase-IV) | 844323 | 24/03/2022 | 0 | G.B. CONSTRUCTION AND CO | 62.79 | 0 | 0 | 0
1282 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-3) , SM/07076 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributin system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) | 844325 | 24/03/2022 | 0 | M/S ASHIRBAD (INDIA) | 55.24 | 0 | 0 | 0
1283 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-3) , SM/07076 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-III) | 844326 | 24/03/2022 | 0 | PRADIP KUMAR JATI | 89.17 | 0 | 0 | 0
1284 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-3) , SM/07076 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-III) | 400/HD | 10/02/2021 | 30 | PRADIP KUMAR JATI | 92.36 | 0 | 0 | 0
1285 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-L) | 1544/HD | 05/11/2020 | 30 | GHOSH CONCERN | 18.86 | 0 | 0 | 0
1286 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-J) | 1542/HD | 05/11/2020 | 30 | A P POWER & CONCRETE | 18.83 | 0 | 0 | 0
1287 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Gobindapur piped water supply scheme under Jagatballavpur Blockunder Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Part-M) | 1406/HD | 16/10/2020 | 30 | MONIRUL ISLAM | 4.79 | 0 | 0 | 0
1288 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-K) | 1543/HD | 05/11/2020 | 30 | GHOSH CONCERN | 18.88 | 0 | 0 | 0
1289 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | W/217 | 18/08/2021 | 0 | ALOK ENTERPRISE | 16.11 | 0 | 0 | 0
1290 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | W/183 | 18/08/2021 | 0 | A.P. POWER & CONCRETE | 16.29 | 0 | 0 | 0
1291 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | W/218 | 18/08/2021 | 0 | ALOK ENTERPRISE | 11.75 | 0 | 0 | 0
1292 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Work Order for Laying of 90 mm dia 490 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-V) (Part-B) | 344/HD | 17/02/2022 | 30 | A.P. POWER & CONCRETE | 2.13 | 0 | 0 | 0
1293 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-V)Part C | 345/HD | 17/02/2022 | 30 | M/S ASHIRBAD (INDIA) | 4.01 | 0 | 0 | 0
1294 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Work Order for Laying of 75 mm dia at node piont 41-27 and 20-15 node point for. 110mm dia,Total 1265 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-IV) | 504/HD | 08/03/2022 | 20 | A.P. POWER & CONCRETE | 4.92 | 0 | 0 | 0
1295 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Retrofitting Gobindapur W/S Scheme. | 844334 | 30/03/2022 | 0 | ALOK ENTERPRISE | 15.52 | 0 | 0 | 0
1296 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Consumption of Laying of 75 mm dia at node point 41-15 and 20-15 node point for 110 mm dia total 1265 mtr length additional UPVC pipe line for FHTC within the command area of Gobindapur PWSS (Phase-IV) | 84438 | 22/09/2022 | 0 | A P POWER & CONCRETE | 4.91 | 0 | 0 | 0
1297 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 844333 | 30/03/2022 | 0 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 13.74 | 0 | 0 | 0
1298 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Laying of 90mm dia 490 mtr lenght additional UPVC pipe line for retrofitting work for FHTC of Gobindapur PWSS. | 84439 | 22/09/2022 | 0 | A P POWER & CONCRETE | 2.12 | 0 | 0 | 0
1299 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Work Order for Retrofitting work for Supply, delivery & installation of CIDF Sluice Valve in different Node point and construction of Sluice Valve chamber for providing Functional Household Tap Connection (FHTC) from existing distribution system of Gobindapur PWSS under Howrah Sub Division of Howrah Division , PHE Dte. | 844310 | 22/09/2022 | 0 | MONIRUL ISLAM | 4.62 | 0 | 0 | 0
1300 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Relaying of pipe line of 110 mm dia 75 mm at node point for Retrofitting Gobindapur W/S Scheme under HSSD. | 844313 | 26/09/2022 | 0 | BUILT INDIA | 3.42 | 0 | 0 | 0
1301 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) , SM/06782 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) | 335/HD | 17/02/2022 | 30 | MS ARPAN ENTERPRISE | 2.97 | 0 | 0 | 0
1302 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) , SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | 844342 | 17/03/2021 | 0 | MAA LAXMI ENTERPRISE | 21.27 | 0 | 0 | 0
1303 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) , SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | W/255 | 03/09/2021 | 0 | PIKASU BOSE | 25.21 | 0 | 0 | 0
1304 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) , SM/06786 | Retrofitting | Retrofitting of Kanpur Reju Water Supply Scheme | 844321 | 12/03/2021 | 0 | NATURAL RESOURCES CONSORTIUM | 24.79 | 0 | 0 | 0
1305 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) , SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | 844328 | 29/03/2022 | 0 | PIKASU BOSE | 3.17 | 0 | 0 | 0
1306 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) , SM/06786 | Retrofitting | Alternative relaying pipeline at Reju of Kanpur PWSS. | 844329 | 29/03/2022 | 0 | PIKASU BOSE | 2.87 | 0 | 0 | 0
1307 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) , SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-F) (for Kanpur Mouza (part) | 95/HD | 14/01/2021 | 30 | PIKASU BOSE | 28.49 | 0 | 0 | 0
1308 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) , SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-B) (for Kanpur Mouza (part) | 1341/HD | 13/10/2020 | 30 | NATURAL RESOURCES CONSORTIUM | 28.2 | 0 | 0 | 0
1309 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) , SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-C) (for Kanpur Mouza (part) | 93/HD | 14/01/2021 | 30 | PIKASU BOSE | 21.97 | 0 | 0 | 0
1310 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) , SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-E) (for Kanpur Mouza (part) | 94/HD | 14/01/2021 | 30 | MAA LAXMI ENTERPRISE | 28.63 | 0 | 0 | 0
1311 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) , SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-G) | 96/HD | 14/01/2021 | 30 | PIKASU BOSE | 26.97 | 0 | 0 | 0
1312 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) , SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-A) (for Kanpur Mouza (part) | 1340/HD | 13/10/2020 | 30 | NATURAL RESOURCES CONSORTIUM | 28.42 | 0 | 0 | 0
1313 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme , SM/06717 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte.(Part-I) (for Kurit Mouza(Part) | 1510/HD | 04/11/2020 | 30 | DEV DAS SHOW | 29.1 | 0 | 0 | 0
1314 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme , SM/06717 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-K) (for Darapur Mouza) | 1512/HD | 04/11/2020 | 30 | JAHANGIR ALAM | 16.23 | 0 | 0 | 0
1315 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme , SM/06717 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-J) (for Kurit Mouza(Part) | 1511/HD | 04/11/2020 | 30 | DEV DAS SHOW | 28.89 | 0 | 0 | 0
1316 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme , SM/06717 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | W/279 | 06/09/2021 | 0 | N. G ENGINEERING | 28.67 | 0 | 0 | 0
1317 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme , SM/06717 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | W/276 | 06/09/2021 | 0 | JAHANGIR ALAM | 25.62 | 0 | 0 | 0
1318 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme , SM/06717 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | 8443108 | 30/03/2021 | 0 | PRADIP KUMAR JATI | 25.73 | 0 | 0 | 0
1319 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme , SM/06717 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-F) (for Kotalpara Mouza & Khosalpur Mouza(Part) | W/602 | 28/12/2021 | 0 | MONDAL PRECISION PVT. LTD. | 5.16 | 0 | 0 | 0
1320 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme , SM/06717 | Retrofitting | Mass Awarness generation and IEC activities. | 844313 | 23/12/2021 | 0 | PRADIP KUMAR JATI | 42 | 0 | 0 | 0
1321 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme , SM/06717 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-J) (for Kurit Mouza(Part) | 844311 | 14/03/2022 | 0 | DEV DAS SHAW | 29.01 | 0 | 0 | 0
1322 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme , SM/06721 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) | W/347 | 07/10/2021 | 0 | USHA CONCERN | 3.52 | 0 | 0 | 0
1323 | HOWRAH | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme , SM/06721 | Retrofitting | PROVIDINMG STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMRAGORI PWSS, AMTA-II, BLOCK UNDER HOWAH DIVISION, CDD, PHE DTE. | 297/CMSD-I (D) | 08/07/2022 | 15 | DIPALI CONSTUCTION | 4.76 | 4.58 | 100 | 0
1324 | HOWRAH | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme , SM/06721 | Retrofitting | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT SARDA W/S SCHEME, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 206/CMSD-I (D) | 20/06/2022 | 15 | DIPALI CONSTUCTION | 2.09 | 1.73 | 100 | 0
1325 | HOWRAH | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme , SM/06721 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (300 MM X 200 MM X 230 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR SARDA W/S, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 205/CMSD-I (D) | 20/06/2022 | 15 | DIPALI CONSTUCTION | 3.11 | 2.94 | 100 | 0
1326 | HOWRAH | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme , SM/06721 | Retrofitting | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMRAGORI PWSS, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 300/CMSD-I (D) | 08/07/2022 | 15 | DIPALI CONSTUCTION | 3.44 | 3.44 | 100 | 0
1327 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme , SM/06721 | Retrofitting | Additional Retrofitting Sarda | BP-2021-22-423 | 21/03/2022 | 0 | SUMANA ENTERPRISE | 2.17 | 0 | 0 | 0
1328 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme , SM/06721 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at SARDA W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) | BP-2021-22-362 | 28/02/2022 | 0 | BISWAJIT BAG | 4.76 | 0 | 0 | 0
1329 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme , SM/06721 | Retrofitting | Supplying, fitting, fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division, P.H.E. Dte. | 4832/HD | 20/11/2024 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
1330 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block , SM/07881 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 1744 nos. | 790/HD | 06/04/2022 | 91 | GHOSH ENTERPRISE. | 95.49 | 0 | 0 | 0
1331 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block , SM/07881 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 1744 nos. | 1244/HD | 14/06/2022 | 92 | GHOSH ENTERPRISE. | 95.49 | 90.64 | 100 | 0
1332 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block , SM/07886 | Retrofitting | Work order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. for 2721 | 87/HD | 14/01/2022 | 45 | PRADIP KUMAR JATI | 114.31 | 92.79 | 81.17 | 0
1333 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block , SM/07886 | Retrofitting | Work Order for Additional pipeline laying for left out portion (Sibu house to burning ghat, Sk sifuddin to Sabir mollah, Sala Mudi shop to Moti mallick, Sk Faire to Sk Faiul, Das's Badh to Saidul mir, , indian petrol pump, dey builder, sikha dey, rajkumar mondal, porimal santra) in Sehagori Water Supply Scheme (Part-B) under Amtra-II block under Howrah Division, PHE Dte. (Phase-I) | 229/HD | 03/02/2022 | 45 | PRADIP KUMAR JATI | 4.82 | 4.69 | 97.15 | 0
1334 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block , SM/07886 | Retrofitting | Work order for Additional pipeline laying for left out portion (Tarun Sangha to Sanat roy, umbrella factory, sk para masjid to sk billu, sala modi shop, sova dolui, Bharat Petrolium, biswa mondal, haru dey, joydev dye, ibrahim mir, moonlight club) in Sehagori Water Supply Scheme (Part-B) under Amtra-II block under Howrah Division, PHE Dte. (Phase-II) | 230/HD | 03/02/2022 | 45 | PRADIP KUMAR JATI | 4.84 | 4.79 | 98.85 | 0
1335 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block , SM/07886 | Retrofitting | Work order for Additional pipeline laying for left out portion (naba santra, ganesh santra, judhistir khanra, sourav khanra's house, Vai Vai milan sangha, kabir roy, avijit roy, Ashoke roy, kashinath middey) in Sehagori Water Supply Scheme (Part-A&B) under Amtra-II block under Howrah Division, PHE Dte. | 217/HD | 03/02/2022 | 45 | PRADIP KUMAR JATI | 4.84 | 0 | 0 | 0
1336 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block , SM/07886 | Retrofitting | Work order for Additional pipeline laying for left out portion (naba santra, ganesh santra, judhistir khanra, sourav khanra's house, Vai Vai milan sangha, kabir roy, avijit roy, Ashoke roy, kashinath middey) in Sehagori Water Supply Scheme (Part-A&B) under Amtra-II block under Howrah Division, PHE Dte. | BP-2022-23-263 | 28/09/2022 | 0 | PRADIP KUMAR JATI | 4.06 | 0 | 0 | 0
1337 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block , SM/07886 | Retrofitting | Withdrawing and re-laying of UPVC pipeline damaged due to irrigation embarkment protection work at section 118-117-115-114-113-147-145-148 in Sehagori Water Supply Scheme(Part-B) under Amta-II block under Howrah Division , PHE Dte. (SL NO.-2 ) | 373/AE/USD | 30/08/2022 | 45 | PRADIP KUMAR JATI | 4.85 | 4.84 | 100 | 100
1338 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block , SM/07886 | Retrofitting | Material Requisition To Resource Division | 495/HD | 07/03/2022 | 0 | Resource Division | 3.08 | 0 | 0 | 0
1339 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block , SM/07886 | Retrofitting | Work Order for Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system at Sehagori W/S scheme under Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 737/HD | 23/02/2023 | 60 | JHARNA ENTERPRISE | 19.04 | 19.04 | 100 | 40
1340 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block , SM/07887 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 2275 nos. | 733/HD | 31/03/2022 | 91 | MITHU BUILDERS | 96.62 | 97.77 | 100 | 0
1341 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block , SM/07887 | Retrofitting | Construction of 2 storied switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement at 3rd TW site of Garbhabanipur PWSS of Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 1936/HD | 21/04/2025 | 45 | S.S ENTERPRISE | 8.81 | 0 | 0 | 100
1342 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block , SM/07887 | Retrofitting | Construction of boundary wall & Land Development at 2nd Tube well Site Garbhabanipur PWSS scheme under Udaynarayanpur Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1037/HD | 24/02/2025 | 90 | A.N ROY & CO | 9.67 | 0 | 0 | 100
1343 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block , SM/07887 | Retrofitting | Construction of boundary wall & Land Development at HW Site Garbhabanipur PWSS scheme under Udaynarayanpur Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1035/HD | 24/02/2025 | 120 | BINOY KOLEY | 14.11 | 0 | 0 | 100
1344 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Continuation order for survey & collection of hopuse hold details through mobile app and geo-tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme juridiction in different pipe water supply scheme of Uluberia Sub-Division under Howrah Division, PHE Dte. |  | 15/12/2020 | 0 | STEELCONC AND ASSOCIATES | 4.73 | 0 | 0 | 0
1345 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Laskarpur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) (PartC) | 1606/HD | 09/11/2020 | 30 | DEV DAS SHOW | 18.9 | 0 | 0 | 0
1346 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Laskarpur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) (PartA) | 1604/HD | 09/11/2020 | 30 | M/S ASHIRBAD (INDIA) | 18.83 | 0 | 0 | 0
1347 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Laskarpur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) (Part-B) | 1605/HD | 09/11/2020 | 30 | PRADIP KUMAR JATI | 18.84 | 0 | 0 | 0
1348 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Laying of 75mm & 140 mm dia.,Total 300 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Laskarpur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) | 1443/HD | 13/07/2021 | 30 | MONIRUL ISLAM | 1.67 | 0 | 0 | 0
1349 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/172 | 14/08/2021 | 0 | DEV DAS SHAW | 16.14 | 0 | 0 | 0
1350 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F), (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-C) | W/460 | 28/12/2020 | 0 | M/S ASHIRBAD (INDIA) | 4.49 | 0 | 0 | 0
1351 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | 844381 | 26/03/2021 | 0 | KRISH CONSTRUCTION | 19.99 | 0 | 0 | 0
1352 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F), (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-D) | W/459 | 28/12/2020 | 0 | M/S ASHIRBAD (INDIA) | 4.5 | 0 | 0 | 0
1353 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F), (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-E) | W/461 | 06/01/2021 | 0 | M/S ASHIRBAD (INDIA) | 4.49 | 0 | 0 | 0
1354 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | 844381 | 26/03/2021 | 0 | STEELCONC AND ASSOCIATES | 15.18 | 0 | 0 | 0
1355 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | 844353 | 22/03/2021 | 0 | M/S ASHIRBAD (INDIA) | 15.24 | 0 | 0 | 0
1356 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I) | W/466 | 30/12/2020 | 0 | PRADIP KUMAR JATI | 4.49 | 0 | 0 | 0
1357 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Survey and Collection of houshold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme | W/508 | 18/01/2021 | 0 | STEELCONC AND ASSOCIATES | 4.73 | 0 | 0 | 0
1358 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | 844389 | 26/03/2021 | 0 | PRADIP KUMAR JATI | 15.2 | 0 | 0 | 0
1359 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) , SM/06776 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F), (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-B) | W/458 | 29/12/2020 | 0 | M/S ASHIRBAD (INDIA) | 4.5 | 0 | 0 | 0
1360 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-A) | 2394/HD | 27/12/2021 | 45 | ANATH BANDHU ENTERPRISE | 4.21 | 3.83 | 100 | 0
1361 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-C) | 2396/HD | 27/12/2021 | 45 | M/S S.M ENTERPRISE | 4.2 | 3.83 | 100 | 0
1362 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-E) | 2398/HD | 27/12/2021 | 45 | RADHA KRISHNA ENTERPRISE | 4.2 | 3.83 | 100 | 0
1363 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-J) | 2403/HD | 27/12/2021 | 45 | DEV DAS SHAW | 4.21 | 3.79 | 100 | 0
1364 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-L) | 2405/HD | 27/12/2021 | 45 | MAITY CONSTRUCTIONS | 4.22 | 3.97 | 100 | 0
1365 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (2) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-M) | 2406/HD | 27/12/2021 | 30 | SK ANISUR | 2.11 | 1.9 | 100 | 0
1366 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-B) | 2395/HD | 27/12/2021 | 45 | A.B. CONSTRUCTION | 4.2 | 3.79 | 100 | 0
1367 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-D) | 2397/HD | 27/12/2021 | 45 | 786 ENTERPRISE | 4.2 | 3.81 | 100 | 0
1368 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-F) | 2399/HD | 27/12/2021 | 45 | M/S M.R ENTERPRISE | 4.2 | 3.83 | 100 | 0
1369 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-G) | 2400/HD | 27/12/2021 | 45 | M/S AHAMED CONSTRUCTION | 4.21 | 3.76 | 100 | 0
1370 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-I) | 2402/HD | 27/12/2021 | 45 | DEV DAS SHAW | 4.21 | 3.78 | 100 | 0
1371 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-K) | 2404/HD | 27/12/2021 | 45 | DEV DAS SHAW | 4.21 | 3.82 | 100 | 0
1372 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-H) | 2401/HD | 27/12/2021 | 45 | SK ANISUR | 4.21 | 3.82 | 100 | 0
1373 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Material Requisition To Resource Division | 95/HD | 17/01/2022 | 0 | Resource Division | 76.03 | 0 | 0 | 0
1374 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Material Requisition To Resource Division | 2374/HD | 24/12/2021 | 0 | Resource Division | 8.03 | 0 | 0 | 0
1375 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Material Requisition To Resource Division | 1158/HD | 31/05/2022 | 0 | Resource Division | 51.06 | 0 | 0 | 0
1376 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09424 | Disaster | Material Requisition To Resource Division | 953/HD | 28/04/2022 | 0 | Resource Division | 24.64 | 0 | 0 | 0
1377 | HOWRAH | Howrah Division | Sinking of Eleven (11 ) Nos DWP Mark-II Hand Tube Well 100 mm x 40 mm dia 250 mtr Pipes within 179 Shyampur Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09353 | Disaster | Work Order for Sinking of Eleven (11) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr Pipes within 179 Shyampur Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS | 185/HD | 31/01/2022 | 45 | M/S AHAMED CONSTRUCTION | 11.48 | 11.05 | 100 | 0
1378 | HOWRAH | Howrah Division | Sinking of Eleven (11 ) Nos DWP Mark-II Hand Tube Well 100 mm x 40 mm dia 250 mtr Pipes within 179 Shyampur Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09353 | Disaster | Work Order for Sinking of ten (10) nos DWP (Mark-II) Hand Pump Tube well 100mm x 40mm dia 250 mtr deep within different habitation of 178 Uluberia Dakshin Assembly Constituency under Howrah Division PHE Dte. (Group-K). | 2447/HD | 28/11/2022 | 45 | M/S AHAMED CONSTRUCTION | 18.45 | 11.44 | 100 | 0
1379 | HOWRAH | Howrah Division | Sinking of Eleven (11 ) Nos DWP Mark-II Hand Tube Well 100 mm x 40 mm dia 250 mtr Pipes within 179 Shyampur Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. , SM/09353 | Disaster | Material Requisition To Resource Division | 405/HD | 24/02/2022 | 0 | Resource Division | 23.77 | 0 | 0 | 0
1380 | HOWRAH | Howrah Division | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. , SM/11717 | New | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Chandrapur PWSS of Bagnan-I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 2719/HD | 14/12/2022 | 45 | SPG ENTERPRISES | 27.49 | 13.25 | 48.18 | 50
1381 | HOWRAH | Electrical | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. , SM/11717 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chandrapur water supply scheme, T.W. No. I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 934/ED | 22/02/2023 | 90 | KARUNAMOY ENGINEERING | 21.49 | 0 | 0 | 0
1382 | HOWRAH | Howrah Division | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. , SM/11717 | New | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 31.28 | 0 | 0 | 0
1383 | HOWRAH | Howrah Division | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. , SM/11717 | New | Material Requisition To Resource Division | 1754/HD | 26/04/2023 | 0 | Resource Division | 29.1 | 0 | 0 | 0
1384 | HOWRAH | Electrical | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. , SM/11717 | New | QUOTATION FOR NEW POWER CONNECTION FOR CHANDRAPUR PWSS PH NO-II | 216 | 24/08/2023 | 0 | WBSEDCL | 7.33 | 0 | 0 | 0
1385 | HOWRAH | Howrah Division | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. , SM/11717 | New | Work Order for Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC)(Mouza-Chandrapur (58) & Interconnection for 2nd TW and 1st Tube well (HW site)& Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials (Drawing No.PC-I/OHR/07/2012 (Sheet No.1&2) with Soil test & Design for Chandrapur PWSS of Bagnan-I Block under Uluberia Sub Division under Howrah Division P.H.E. Dte. | 1746/HD | 25/04/2023 | 1200 | K.M. ENTERPRISE | 300.94 | 0 | 0 | 0
1386 | HOWRAH | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Work Order for Preparation of DPR for new piped water supply scheme of Ghoraberia PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 243/HD | 07/02/2022 | 15 | VOYAGER | 4.25 | 2.89 | 68.17 | 0
1387 | HOWRAH | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 10.2 | 0 | 0 | 0
1388 | HOWRAH | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Quotation Bill for New Service Connection at Ghoraberia W/S. Sch. PH-I | 556 | 21/12/2023 | 0 | WBSEDCL | 6.69 | 0 | 0 | 0
1389 | HOWRAH | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Quotation Bill for New Service Connection at Ghoraberia W/S. Sch. PH-II | 555 | 21/12/2023 | 0 | WBSEDCL | 4.24 | 0 | 0 | 0
1390 | HOWRAH | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghoraberia water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | 3509/ED | 30/12/2022 | 90 | NUPUR CHANDRA HALDER | 21.45 | 21.3 | 100 | 80
1391 | HOWRAH | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ghoraberia PWSS of Amta - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 662/HD | 17/02/2023 | 30 | LOKENATH ENTERPRISES | 28.39 | 24.13 | 100 | 100
1392 | HOWRAH | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Display Board at different PWSS at Amta-I Amta-II Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 3221/AE/USD | 12/03/2024 | 30 | ABONTICA ENTERPRISE | 4.26 | 4.26 | 100 | 100
1393 | HOWRAH | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 3.7 | 0 | 0 | 0
1394 | HOWRAH | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Construction of Two storied switch room (5.4 x 3.6) & (3.6 x3.0) with water supply & sanitary arrangement cum godown & 300 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (1707 nos) for Ghoraberia PWSS of Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 2698/HD | 24/07/2023 | 1025 | SUJATA CONSTRUCTION | 435.07 | 119.01 | 27.35 | 52
1395 | HOWRAH | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Making of T.W. Foundation at Ghoberia water supply scheme, P.H No.- I, Dist-Howrah under Electrical Division, PHE Dte. | 3976/HMSD | 21/08/2024 | 7 | NUPUR CHANDRA HALDER | 0.97 | 0.97 | 100 | 0
1396 | HOWRAH | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Additional works for Making of T.W. Foundation at Ghoraberia water supply scheme, P.H No.- II, Dist-Howrah under Electrical Division, PHE Dte. | 5014/HMSD | 30/08/2024 | 7 | NUPUR CHANDRA HALDER | 0.68 | 0.59 | 100 | 0
1397 | HOWRAH | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Making of T.W. Foundation at Ghoraberia water supply scheme, P.H No.- II, Dist-Howrah under Electrical Division, PHE Dte. | 5015/HMSD | 30/08/2024 | 7 | NUPUR CHANDRA HALDER | 0.94 | 0.94 | 100 | 0
1398 | HOWRAH | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Additional works for Making of T.W. Foundation at Ghoberia water supply scheme, P.H No.- I, Dist-Howrah under Electrical Division, PHE Dte. | 3973/HMSD | 21/08/2024 | 7 | NUPUR CHANDRA HALDER | 0.62 | 0.53 | 100 | 0
1399 | HOWRAH | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. , SM/11720 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
1400 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Work Order for LDS (Part-2) & FHTC (Part-2) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) In DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P. H. E. DTE. | 722/HD | 23/02/2023 | 90 | FAITH ENTERPRISE | 135.21 | 64.34 | 47.59 | 50
1401 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-IV) Dakshin Jhapardaha (Zone-II) of Domjur Block of Howrah Division PHE Dte. | 87/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.7 | 3.7 | 100 | 100
1402 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-IV) Dakshin Jhapardaha (Zone-I) of Domjur Block of Howrah Division PHE Dte. | 86/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.04 | 3.04 | 100 | 100
1403 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-II) PWSS (Mouza-Mollar Chak, Chak Narna, Parbatipur, Uttar Jhapardaha (CT) of Domjur Block of Howrah Division PHE Dte. | 88/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.86 | 3.81 | 100 | 100
1404 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Material Requisition To Resource Division | 1748/HD | 25/04/2023 | 0 | Resource Division | 87.43 | 0 | 0 | 0
1405 | HOWRAH | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Deposition of quotation money for domjur(zone-iv) dakshin jhapardaha( zone-ii) water supply scheme , P.H No.-I,Dist-Howrah umder ED, PHED. |  | 12/05/2023 | 0 | WBSEDCL | 0.73 | 0 | 0 | 0
1406 | HOWRAH | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | New service connection | 108 | 19/07/2023 | 0 | WBSEDCL | 4.03 | 0 | 0 | 0
1407 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (Pipe Dia. 90mm Node No. 557, 562 to 667) [PART-4]. | 162/HD | 13/01/2023 | 955 | CHAKRABORTY ENTERPRISE | 50.34 | 48.39 | 96.12 | 15
1408 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (Pipe Dia. 90mm Node No. 350 to 530) [PART-3]. | 161/HD | 13/01/2023 | 60 | BUILT INDIA | 77.96 | 68.65 | 88.06 | 50
1409 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Land Development Works (1st, 2nd & 3rd T/W Site) & RCC Retaining Wall of Dakshin Jhapardaha (Zone-4) PWSS (Zone-II) at 2nd & 3rd Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | 1213/HD | 11/03/2024 | 45 | CHANDIMATA CONSTRUCTION | 15.45 | 0 | 0 | 100
1410 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 22.21 | 0 | 0 | 0
1411 | HOWRAH | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Quotation Bill for New Service Connection at Dakshin Jhapardaha W/S. Sch. | 629 | 08/01/2024 | 0 | WBSEDCL | 3.61 | 0 | 0 | 0
1412 | HOWRAH | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Quotation money deposition for new service connection at Domjur(Zone-IV) w/s scheme, Dakshin Jhapordaha(Zone-II), Pwss, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008185043 Reference ID- 106810747 SM Code- 13752 | 571 | 13/11/2024 | 0 | WBSEDCL | 5.47 | 0 | 0 | 0
1413 | HOWRAH | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-IV) Dakshin Jhapardaha(Z-II) water supply scheme, T.W. No. I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 916/ED | 22/02/2023 | 820 | M.S. ENTERPRISE | 32.73 | 21.13 | 64.57 | 40
1414 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Work Order for CONSTRUCTION FOR 3 NOS. PUMP HOUSE, 3 NOS. BOUNDARY WALL, RISING MAIN, LDS (Part-1) & FHTC (Part-1) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) In DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P. H. E. DTE. | 812/HD | 28/02/2023 | 726 | M/S CHANDIMATA CONSTRUCTION | 151.7 | 110.54 | 79.07 | 40
1415 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Piped Water Supply Schemes in different Blocks in the District of Howrah under Howrah Division, PHE Dte. | 3730/HD | 29/08/2024 | 30 | HORIZEN | 4.93 | 0 | 0 | 100
1416 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Rising Main Pipeline Work From 2nd Pump House to 1st Pump House Domjur (Zone-IV) Dakshin Jhapardaha (Zone-II) PWSS at Domjur Block Of Howrah District under Howrah Division, P.H.E. Dte. | 4129/HD | 23/09/2024 | 45 | M/S. CHANDIMATA CONSTRUCTION | 36.07 | 0 | 0 | 100
1417 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Domjur - Andul Road from 0.00 Km to 4.129 Km, Restoration work of PHE Cutting for laying pipe line under Howrah Highway Division in the district of Howrah (Dakshin Jhapardaha PWSS Zone-II, Dakshin Jhapardaha PWSS Zone-I, Bhandardaha PWSS, Bipranoapara PWSS). |  | 28/03/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 101.31 | 0 | 0 | 0
1418 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Work Order for Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone-IV) Dakshin Jhapordaha (Zone-I) & (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 175/HD | 13/01/2023 | 1197 | B K ENTERPRISE | 77.78 | 25.23 | 64.86 | 85
1419 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (Pipe Dia. 90mm Node No. 530 to 561) [PART-5]. | 270/HD | 19/01/2023 | 560 | PBA INFRASTRUCTURE | 15.34 | 14.62 | 95.3 | 100
1420 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4817/HD | 19/11/2024 | 510 | TECH VISION | 8.36 | 1.27 | 100 | 95
1421 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13752 | New | Supplying,fitting,fixing and erecting of Display Board at Domjur (Zone-IV) Dakshin Jhapardaha (Zone-I) PWSS [SM/13751], Domjur (Zone-IV) Dakshin Jhapardaha (Zone-II) PWSS [SM/13752], Keshabpur PWSS [SM/16947] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 222/HSSD | 25/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
1422 | HOWRAH | Howrah Division | Patinan Piped Water Supply Scheme , SM/13848 | New | Work Order for Sinking of 4 (Four) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Gopalpur PWSS 2nos & Patinan PWSS 2 Nos of Bagnan - I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 663/HD | 17/02/2023 | 45 | AQUATECH ENGINEER | 52.06 | 23.58 | 100 | 100
1423 | HOWRAH | Howrah Division | Patinan Piped Water Supply Scheme , SM/13848 | New | Material Requisition To Resource Division | 1754/HD | 26/04/2023 | 0 | Resource Division | 22.05 | 0 | 0 | 0
1424 | HOWRAH | Howrah Division | Patinan Piped Water Supply Scheme , SM/13848 | New | Material Requisition To Resource Division | 4695/HD | 26/12/2023 | 0 | Resource Division | 16.37 | 0 | 0 | 0
1425 | HOWRAH | Electrical | Patinan Piped Water Supply Scheme , SM/13848 | New | Quotation Bill for New Service Connection at Patinan W/S. Sch. PH-II | 574 | 27/12/2023 | 0 | WBSEDCL | 4.2 | 0 | 0 | 0
1426 | HOWRAH | Electrical | Patinan Piped Water Supply Scheme , SM/13848 | New | Quotation Bill for New Service Connection at Patinan W/S. Sch. | 316 | 03/10/2023 | 0 | WBSEDCL | 8.55 | 0 | 0 | 0
1427 | HOWRAH | Electrical | Patinan Piped Water Supply Scheme , SM/13848 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Patinan water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 3546/ED | 30/12/2022 | 90 | M/S CHANDIMATA ELECTRICALS | 20.27 | 13.36 | 65.9 | 40
1428 | HOWRAH | Howrah Division | Patinan Piped Water Supply Scheme , SM/13848 | New | Preparation of DPR for Patinan PWSS, Bagnan-I Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | 460/AE/USD | 15/09/2022 | 45 | DULAL MAJUMDER | 2.98 | 0 | 0 | 100
1429 | HOWRAH | Howrah Division | Patinan Piped Water Supply Scheme , SM/13848 | New | Display Board at different PWSS at Bagnan-I Bagnan-II Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 3219/AE/USD | 12/03/2024 | 30 | ABONTICA ENTERPRISE | 4.76 | 4.76 | 100 | 100
1430 | HOWRAH | Howrah Division | Patinan Piped Water Supply Scheme , SM/13848 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells (Part-A) & Construction of Swtich Room with Sanitary and water Supply arrangement at Head Work Site and Construction of 250 cum. capacity 20 mtr staging height RCC Over Head Reservoir (Drawing No:PC-I/OHR/10/2012) including Pipe connection & soil investigation and design at PATINAN PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | 1553/HD | 05/04/2023 | 1341 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 217.39 | 147.67 | 67.93 | 32
1431 | HOWRAH | Howrah Division | Patinan Piped Water Supply Scheme , SM/13848 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells at Patinan PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-B) | 513/HD | 09/02/2023 | 817 | MENOKA ENGINEERING WORKS | 58.94 | 26.43 | 58.08 | 75
1432 | HOWRAH | Howrah Division | Patinan Piped Water Supply Scheme , SM/13848 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 1.96 | 100 | 100
1433 | HOWRAH | Howrah Division | Patinan Piped Water Supply Scheme , SM/13848 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
1434 | HOWRAH | Howrah Division | Patinan Piped Water Supply Scheme , SM/13848 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
1435 | HOWRAH | Electrical | Purbba Gazipur Piped Water Supply Scheme , SM/15287 | New | Quotation Bill for New Service Connection at Purba Gazipur W/S. Sch. | 708 | 25/01/2024 | 0 | WBSEDCL | 0.08 | 0 | 0 | 0
1436 | HOWRAH | Howrah Division | Purbba Gazipur Piped Water Supply Scheme , SM/15287 | New | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | 2155/H.D | 07/06/2023 | 1021 | MONDAL PRECISION PVT. LTD. | 330.32 | 21.92 | 59.72 | 80
1437 | HOWRAH | Howrah Division | Purbba Gazipur Piped Water Supply Scheme , SM/15287 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 0.12 | 0 | 0 | 0
1438 | HOWRAH | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh , SM/15186 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Joargarh water supply scheme, T.W. No. I, II & III, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | 1703/ED | 18/04/2023 | 90 | H.K.DAS & CO. | 32.55 | 0 | 0 | 0
1439 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh , SM/15186 | Augmentation | Preparation of DPR for Augmentation of Joargori PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 319/AE/USD | 16/08/2022 | 45 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.83 | 3.83 | 100 | 100
1440 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh , SM/15186 | Augmentation | Material Requisition To Resource Division | 1754/HD | 26/04/2023 | 0 | Resource Division | 74.81 | 0 | 0 | 0
1441 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh , SM/15186 | Augmentation | Material Requisition To Resource Division | 4864/HD | 22/11/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
1442 | HOWRAH | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh , SM/15186 | Augmentation | Quotation money deposition for new service connection at Joargarh pwss ,T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007613302 Reference ID- 106525750 SM Code- 15186 | 23 | 05/04/2024 | 0 | WBSEDCL | 5.13 | 0 | 0 | 0
1443 | HOWRAH | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh , SM/15186 | Augmentation | Quotation money deposition for new service connection at Joargarh pwss ,T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1007614302 Reference ID- 106526159 SM Code- 15186 |  | 28/03/2024 | 0 | WBSEDCL | 4.9 | 0 | 0 | 0
1444 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh , SM/15186 | Augmentation | Material Requisition To Resource Division | 494/HD | 24/01/2025 | 0 | Resource Division | 9.86 | 0 | 0 | 0
1445 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh , SM/15186 | Augmentation | Sinking of 05 (Five) nos Big dia Tube wells, Construction of Switch rooms(5.4x3.6) for HW site and other TW sites, Boundary walls, Land Developments, Laying distribution system (UPVC & HDPE & DI) & Providing Functional Household Tap Connection (FHTC), Interconnection between tubewells and OHR and Construction of OHR of 700 cum and 400 cum capacity 20.0 m staging height along with pipe connection etc for SHERPUR PWSS in Amta-I Block and Augmentation of JOARGARH PWSS in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC=8807] | 3488/HD | 29/09/2023 | 900 | S.P. CONSTRUCTION | 1926.07 | 188.68 | 28.27 | 65
1446 | HOWRAH | Electrical | Manirampur Piped Water Supply Scheme , SM/15200 | New | Quotation for New Service Connection at Manirampur Mini W/S. Sch. | 650 | 10/01/2024 | 0 | WBSEDCL | 0.08 | 0 | 0 | 0
1447 | HOWRAH | Howrah Division | Manirampur Piped Water Supply Scheme , SM/15200 | New | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | 2155/H.D | 07/06/2023 | 1021 | MONDAL PRECISION PVT. LTD. | 330.32 | 21.89 | 59.65 | 80
1448 | HOWRAH | Howrah Division | Manirampur Piped Water Supply Scheme , SM/15200 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 0.12 | 0 | 0 | 0
1449 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pulgustia , SM/10143 | Augmentation | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 28.08 | 0 | 0 | 0
1450 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pulgustia , SM/10143 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Palgustia PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | BP-2021-22-406 | 14/03/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.7 | 0 | 0 | 0
1451 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pulgustia , SM/10143 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
1452 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Pulgustia , SM/10143 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Poulgusthia (Replacement) water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 719/ED | 03/02/2023 | 90 | A.G. ENTERPRISE | 21.49 | 19.13 | 89.02 | 0
1453 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pulgustia , SM/10143 | Augmentation | Work Order for Sinking of 2(Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Polgustia PWSS of Jagatballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 168/HD | 13/01/2023 | 45 | B K ENTERPRISE | 34.7 | 33.4 | 100 | 0
1454 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pulgustia , SM/10143 | Augmentation | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 34.87 | 0 | 0 | 0
1455 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pulgustia , SM/10143 | Augmentation | Work Order for Laying Distribution System, Rising main , FHTC (4559 nos), Construction of Pump House at OHR site (5.4mX3.6m ) with water supply & sanitary arrangement, 2 (Two) nos Construction of Pump House(3.6 mX3.0m) with water supply & sanitary arrangement, 2(Two) nos Boundary Wall (OHR & Other tubewell site), Construction of of 450 Cum OHR with 20 mtr Staging Height with pile foundation for Augumention of PULGUSTIA Water Supply Scheme of JAGABALLAVPUR Block under Howrah Division, PHE Dte. | 1437/HD | 12/07/2022 | 549 | GHOSH CONCERN | 474.21 | 466.26 | 98.32 | 30
1456 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pulgustia , SM/10143 | Augmentation | Sinking 1No. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with 150 mm. dia. PVC. Strainer of 30m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Pulgustia PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 995/HD | 01/03/2024 | 30 | ACME CONSTRUCTION | 14.58 | 0 | 0 | 100
1457 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pulgustia , SM/10143 | Augmentation | Work Order for Additional Laying Distribution Pipeline & allied works of Pulgustia PWSS at J.Bpur Block of Howrah District under Howrah Division, P.H.E. Dte. | 1926/HD | 10/05/2023 | 60 | GHOSH CONCERN | 65.53 | 63.73 | 100 | 50
1458 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Pulgustia , SM/10143 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Poulgusthia (Replacement) water supply scheme, T.W. No. III, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 3457/ED | 11/08/2023 | 90 | M/S G P ENTERPRISE | 10.76 | 10.46 | 97.38 | 90
1459 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Pulgustia , SM/10143 | Augmentation | Power connection of reorganization at Polgustia w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 100000104716 Reference ID- 860294676 SM Code- 10143 | 36 | 09/04/2024 | 0 | WBSEDCL | 0.5 | 0 | 0 | 0
1460 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Pulgustia , SM/10143 | Augmentation | Quotation money deposition for new service connection at Polgustia w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1007622375 Reference ID- 106532179 SM Code- 00343 | 56 | 12/04/2024 | 0 | WBSEDCL | 10.94 | 0 | 0 | 0
1461 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Bangalpur(Jl-43) (Part-E) | 1097/HD | 16/03/2023 | 30 | JYOTY SOLAR POWER | 16.21 | 0 | 0 | 0
1462 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Adra (Jl-44) (Part-A) | 1093/HD | 16/03/2023 | 30 | SAIKAT ENTERPRISE | 11.88 | 0 | 0 | 0
1463 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Joka(Jl-42) (Part-B) | 1094/HD | 16/03/2023 | 30 | BHOLA NATH CONSTRUCTION | 11.78 | 0 | 0 | 0
1464 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Bangalpur(Jl-43) (Part-D) | 1096/HD | 16/03/2023 | 30 | AYUSH ENTERPRISE | 16.14 | 0 | 0 | 0
1465 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Bangalpur(Jl-43) (Part-C) | 1095/HD | 16/03/2023 | 30 | M/S BANERJEE ENGINEERING SYSTEM | 11.7 | 0 | 0 | 0
1466 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Material Requisition To Resource Division | 1754/HD | 26/04/2023 | 0 | Resource Division | 45.94 | 0 | 0 | 0
1467 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Work Order for Preparation of DPR for new piped water supply scheme of Bangalpur PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 247/HD | 07/02/2022 | 15 | DULAL MAJUMDER | 3.1 | 0 | 0 | 100
1468 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Material Requisition To Resource Division | 4864/HD | 22/11/2024 | 0 | Resource Division | 7.39 | 0 | 0 | 0
1469 | HOWRAH | Electrical | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Quotation for new service connection for Bangalpur w/s scheme, Ph No-I, in the district Howrah under Electrical Division, PHE Dte. ( SM/16760 ) Reference Id- 106680402, Application no- 1007951594 | 333 | 30/07/2024 | 0 | WBSEDCL | 6.26 | 0 | 0 | 0
1470 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bangalpur PWSS of Bagnan I Block Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 1091/HD | 16/03/2023 | 940 | ZEOLITE FRESH INDIA | 52.14 | 0 | 0 | 30
1471 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Work Order for Interconnection for 2nd TW and 1st Tube well (HW site) at Bangalpur Piped Water Supply scheme in Bagnan-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 1098/HD | 16/03/2023 | 1037 | SUNIL ENTERPRISE | 10.66 | 0 | 0 | 0
1472 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia SubDivision, under Howrah Division P.H.E. Dte. (MouzaAdra (Jl-44)) (Part-A) and Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir with pipe connection and cost of pipes, specials with Soil test & Design for Augmentation of Bangalpur Piped Water Supply scheme of Bagnan-I Block under Howrah Division P.H.E. Dte. in the District of Howrah | 1592/HD | 12/04/2023 | 1097 | SUBHAS TRADING CO. | 368.95 | 51.3 | 13.91 | 46
1473 | HOWRAH | Electrical | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bangalpur water supply scheme, T.W. No.- I, II & III, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 1997/ED | 19/05/2023 | 958 | C.M.S. ENGINEERING CONCERN | 35.16 | 0 | 0 | 35
1474 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Work Order for Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia SubDivision, under Howrah Division P.H.E. Dte. (Mouza Bangalpur(Jl-43) (Part-B) | 1449/HD | 30/03/2023 | 789 | DEV DAS SHAW | 192.05 | 33.27 | 17.36 | 19
1475 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Construction of switch room SLOPE ROOF (5.40m x 3.60m) with water supply & sanitary arrangement at Head work site of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | 4463/HD | 03/10/2024 | 60 | SUBHAS TRADING CO. | 7.13 | 0 | 0 | 85
1476 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
1477 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. , SM/16760 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Joka(Jl-42)) (Part-C) | 1688/HD | 20/04/2023 | 1030 | UNIVERSAL CONSTRACTION | 100.01 | 0 | 0 | 45
1478 | HOWRAH | Howrah Division | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Material Requisition To Resource Division | 2639/HD | 09/12/2022 | 0 | Resource Division | 68.93 | 0 | 0 | 0
1479 | HOWRAH | Howrah Division | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
1480 | HOWRAH | Electrical | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rejuvenation of Amta water supply scheme, Zone - I, T.W. No. II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | 587/ED | 02/02/2023 | 90 | D. K. ELECTRIC | 11.25 | 11.15 | 100 | 30
1481 | HOWRAH | Electrical | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rejuvenation of Amta water supply scheme, Zone - I, T.W. No. I, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | 588/ED | 02/02/2023 | 90 | D. K. ELECTRIC | 11.25 | 11.16 | 100 | 30
1482 | HOWRAH | Electrical | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rejuvenation of Amta water supply scheme, T.W. No.- III, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | 1612/ED | 10/04/2023 | 90 | D. K. ELECTRIC | 11.18 | 11.18 | 100 | 1
1483 | HOWRAH | Electrical | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Quotation Bill for New Service Connection at Ranapara W/S. Sch. Amta-I | 298 | 21/09/2023 | 0 | WBSEDCL | 5.12 | 0 | 0 | 0
1484 | HOWRAH | Electrical | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Quotation bill for New Service Connection at Rej. of Amta W/S. Sch. PH-I | 160 | 15/02/2023 | 0 | WBSEDCL | 11.41 | 0 | 0 | 0
1485 | HOWRAH | Electrical | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Quotation Bill For New Service Connection at Rej. Amta. PH-II | 160 | 15/02/2023 | 0 | WBSEDCL | 0.36 | 0 | 0 | 0
1486 | HOWRAH | Electrical | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Quotation Bill for New Service Connection at Rej. of Amta W/S. Sch. | 200 | 17/03/2023 | 0 | WBSEDCL | 2.7 | 0 | 0 | 0
1487 | HOWRAH | Electrical | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Quotation Bill for New Service Connection at Rej. of Amta W/S. Sch. | 200 | 17/03/2023 | 0 | WBSEDCL | 2.48 | 0 | 0 | 0
1488 | HOWRAH | Howrah Division | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Work Order for 1 (One) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at 3rd TW site, Additional laying of pipeline and ancilary works for Zone-I, II, III and Construction of 2nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Augmentation of Rejuvenation of Amta PWSS Zone-II & III 3rd TW site FOR ADDITIONAL WORK AT REJUVENATION OF AMTA PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | 1352/HD | 27/03/2023 | 120 | SAMIRON GHOSH | 399.6 | 393.86 | 100 | 100
1489 | HOWRAH | Electrical | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Rejuvenation of AMTA water supply scheme, T.W. No. II (Replacement tubwell at PWD premises), Block: Amta-I, District - Howrah under Electrical Division, PHE Dte. | 1837/ED | 28/04/2023 | 90 | D. K. ELECTRIC | 8.36 | 8.36 | 100 | 25
1490 | HOWRAH | Electrical | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Amta (Ranapara) water supply scheme, T.W. No.-II, Block: Amta-II, District - Howrah under Electrical Division, PHE Dte. | 4736/ED | 15/12/2023 | 90 | D. K. ELECTRIC | 10.74 | 10.74 | 100 | 100
1491 | HOWRAH | Howrah Division | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Permanent restoration work of portable damage stretches of Ranihati-Haridaspur Amta Road from 15.40 Km to 16.70 Km due to laying of Water Supply Pipe Line by PHE i.c.w Rejuvenation of Amta Water Supply Scheme (Zone-II) | BP-2024-25-9 | 08/04/2024 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 20.73 | 0 | 0 | 0
1492 | HOWRAH | Howrah Division | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Work Order for Sinking of Big dia Rig Bored Tube well 4 nos (300 x 250 mm x 250 mtr)for Zone-I, II & III, Land development of Head work site and 2nd Tube well site , Construction of boundary wall at 2nd Tube well Site (Zone-I), HW Site (Zone-I & III), Laying Distribution System Zone-I, Zone-II and Zone-III , FHTC Zone-I(3227), Zone-II(4732), Zone-III(2022), Construction of Two storied switch room ( 5.4 x 3.6) with water supply & sanitary arrangement cum godown at Head Work site of Zone-I,& Zone-III,Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at 2nd tube well Zone-I, Construction of 600 Cum OHR 20 mtr Staging Height (Zone-I) with pile foundation including soil test &design of piles, Constructionof 400 Cum OHR 20 mtr Staging Height (Zone-III) with pile foundation including soil test & design of piles, Interconnection 2nd Tube Well and First Tube Well ( Zone-I and Zone-III)of Rejuvenation of Amta Water Supply Scheme of Amta- I Block under Howrah Division, PHE Dte | 1637/HD | 10/08/2022 | 549 | SAMIRON GHOSH | 1572.76 | 1490.1 | 95.85 | 50
1493 | HOWRAH | Howrah Division | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Additional FHTC at Rejuvenation of Amta PWSS (Zone-I) of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte.(SM/08966) | 3958/HD | 10/09/2024 | 180 | ADITYA HAZRA | 54.31 | 11.5 | 19.54 | 100
1494 | HOWRAH | Howrah Division | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Additional FHTC at Rejuvenation of Amta PWSS (Zone-II) of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte.(SM/08966) | 2795/HD | 19/06/2024 | 375 | BUILT INDIA | 55.4 | 26.89 | 51.54 | 100
1495 | HOWRAH | Howrah Division | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 2.46 | 0 | 0 | 0
1496 | HOWRAH | Howrah Division | Rejuvenation of Amta Piped water supply scheme. , SM/08966 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Amta-I Block) (PART-A) | 4125/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 100
1497 | HOWRAH | Electrical | Source Augmentation of Chitnan Water Supply Scheme , SM/18848 | Augmentation | Quotation Bill for New Service Connection at Chitnan W/S. Sch. TW-III | 562 | 22/12/2023 | 0 | WBSEDCL | 4.85 | 0 | 0 | 0
1498 | HOWRAH | Electrical | Source Augmentation of Chitnan Water Supply Scheme , SM/18848 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chitnan water supply scheme, T.W. No. III, Block: Amta-II, District: Howrah under Electrical Division, PHE Dte. | 336/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0 | 0
1499 | HOWRAH | Howrah Division | Source Augmentation of Chitnan Water Supply Scheme , SM/18848 | Augmentation | Work Order for Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep additional tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Chitnan PWSS of Amta-II Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 2750/HD | 16/12/2022 | 30 | LOKENATH ENTERPRISES | 15.12 | 12.73 | 100 | 100
1500 | HOWRAH | Howrah Division | Source Augmentation of Chitnan Water Supply Scheme , SM/18848 | Augmentation | Preparation of DPR for Source Strengthning at Chitnan PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 494/AE/USD | 29/09/2023 | 30 | APEX ENGINEERING | 0.78 | 0 | 0 | 100
1501 | HOWRAH | Howrah Division | Source Augmentation of Chitnan Water Supply Scheme , SM/18848 | Augmentation | Inter connection and distribution pipe line, construction of boundary wall with two storied switch room (1 Nos.) (3.6 x 3.0) at 3rd Tube well site of Chitnan PWSS of Amta-II Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 2314/HD | 13/05/2025 | 90 | LOKENATH ENTERPRISES | 30.25 | 0 | 0 | 100
1502 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Preparation of DPR for Augmentation of Par-Radhanagar PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte | 330/AE/USD | 16/08/2022 | 45 | STEELCONC AND ASSOCIATES | 3.29 | 3.16 | 100 | 0
1503 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at PerRadhanagar PWSS of RWS Howrah Sub-Division under Howrah Division, P. H. E. Dte. | 2491/HD | 30/11/2022 | 45 | WATER TECH | 36.22 | 30.78 | 100 | 100
1504 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Material Requisition To Resource Division | 421/HD | 03/02/2023 | 0 | Resource Division | 14.26 | 0 | 0 | 0
1505 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Material Requisition To Resource Division | 2716/HD | 25/07/2023 | 0 | Resource Division | 13.78 | 0 | 0 | 0
1506 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Material Requisition To Resource Division | 2830/HD | 04/08/2023 | 0 | Resource Division | 19.05 | 0 | 0 | 0
1507 | HOWRAH | Electrical | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Quotation bill for New Service Connection at Par-Radhanagar Water Supply Scheme. | 331 | 06/10/2023 | 0 | WBSEDCL | 2.67 | 0 | 0 | 0
1508 | HOWRAH | Electrical | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Quotation Bill for New Service Connection at Par-Radhanagar | 228 | 29/03/2023 | 0 | WBSEDCL | 8.72 | 0 | 0 | 0
1509 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Per-radhanagar W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 2802/HD | 21/12/2022 | 60 | BINOY KOLEY | 7.83 | 7.29 | 100 | 98
1510 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Work Order for Construction of Pump House (5.40m x 3.60m) with water supply & sanitary arrangement at HW site Per Radhanagar W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 2805/HD | 21/12/2022 | 60 | M/S M.K. MONDAL | 7.83 | 7.3 | 100 | 95
1511 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Material Requisition To Resource Division | 29/HD | 03/01/2024 | 0 | Resource Division | 0.87 | 0 | 0 | 0
1512 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Material Requisition To Resource Division | 3884/HD | 05/09/2024 | 0 | Resource Division | 1.13 | 0 | 0 | 0
1513 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) of PER RADHANAGAR Piped Water Supply Scheme under Udaynaryanpur block under Howrah Division, PHE Dte. (Part-B) Mouza-Peruhareshpur | 2108/HD | 13/10/2022 | 901 | GHOSH ENTERPRISE. | 149.58 | 67.7 | 56.4 | 65
1514 | HOWRAH | Electrical | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Per Radhanagr water supply scheme, T.W. No. III & IV, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 922/ED | 22/02/2023 | 404 | GLACIER ENGINEERING CO. | 21.83 | 21.58 | 100 | 80
1515 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Rising main & Inter Connection with both tube wells of Per Radhanagar PWSS In Udaynarayanpur Block under Howrah Division, PHE Dte. | 904/HD | 27/02/2024 | 89 | KUNAL BANERJEE | 6.28 | 5.56 | 88.97 | 100
1516 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Construction of Boundary Wall, Construction of Approach Road and Land Development at 2nd TW Site and Estimate for Additional Laying of Distribution Pipe Lines for leftout area of PER RADHANAGAR (Part-B) Piped Water Supply Scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 4118/HD | 23/09/2024 | 120 | GHOSH ENTERPRISE | 72.21 | 0 | 0 | 100
1517 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Work Order for Construction of 350 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), along with part Laying of distribution and Providing Functional Household Tap Connection(FHTC) for Per Radhanagar Piped Water Supply scheme of Udayanarayanpur Block under Howrah Division P.H.E. Dte. in the District of Howrah.(Part-A) | 2172/HD | 21/10/2022 | 1257 | BALAJI UDDYOG | 318.57 | 130.91 | 41.09 | 92
1518 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4813/HD | 19/11/2024 | 510 | HORIZEN | 13.59 | 1.32 | 96.79 | 70
1519 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Construction of Boundary Wall and Culvert at HW Site and Estimate for Additional Laying of Distribution Pipe Lines and Providing Functional Household Tap Connection(FHTC) for leftout area of PER RADHANAGAR (Part-A) Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | 4117/HD | 23/09/2024 | 675 | BALAJI UDDYOG | 89.33 | 0 | 0 | 50
1520 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Work order for repairing work of damaged distribution pipelines at Penro Harispur Mouja under Par Radhanagar PWSS at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 115/RWS | 11/04/2025 | 15 | MANIRUL ISLAM | 0.73 | 0 | 0 | 100
1521 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Restoration of damage road due to laying of pipeline of different schemes in Udaynarayanpur unader Howrah Division PHE Dte. Road Name - L035-T02 Mandalpara to Baruipara L035 Penro Pucca |  | 08/01/2026 | 0 | WBSRDA-II | 4.34 | 0 | 0 | 0
1522 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC , SM/11572 | New | Restoration of damage road due to laying of pipeline of different schemes in Udaynarayanpur unader Howrah Division PHE Dte. Road Name - T02 Muslimpara to Patrapara L034 Road. |  | 08/01/2026 | 0 | WBSRDA-II | 13.27 | 0 | 0 | 0
1523 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-II, PHE Dte. | 3300/HMSD | 11/12/2023 | 182 | DEBASHISH GHOSH | 0.86 | 0.15 | 17.03 | 0
1524 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of drain using 1000 mm dia hume pipe and other allied works at Ichapur (Zone-12) of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 1176/HD | 07/03/2024 | 15 | SKYLINE ENTERPRISE | 0.96 | 0 | 0 | 0
1525 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Pump House cum Guard room (5.5m x 3.6m) with Water Supply & Sanitary arrangement for Kalinagar PWSS at Purba Kalinagar (Janapara New Park) at Uluberia-I Block Of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2692/HD | 10/06/2024 | 90 | SUBRATA MONDAL | 7.65 | 0 | 0 | 0
1526 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Hiring of Luxury Car (BS-IV) for the Official use of the Executive Engineer, Electrical Division, PHE Dte. w.e.f. 01.06.2024 to 30.11.2024. VEHICLE No. WB-02AB-3954 | 999/AE-I/ED | 16/05/2024 | 183 | TRIDIP SARKAR | 0.87 | 2.39 | 275.38 | 0
1527 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Shyampur-I & II Block of Uluberia Sub-Division under Howrah Division PHE Dte. | 1209/HD | 11/03/2024 | 15 | KULTIKARI MOTHER TERESA SOCIAL WELLFARE SOCIETY | 2.45 | 2.45 | 100 | 100
1528 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of boundary wall at Manikpur H/W site (OHR 5A H/S) of Uluberia-I block of surface-based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 739/HD | 16/02/2024 | 60 | S R TRADING CORPORATION | 23.75 | 23.58 | 100 | 100
1529 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Bullah piling for bank protection of canal to the right side of Ghat at Ichapur (Zone 12) for Surface Based W/S Scheme of Shyampur-I & II, Bagnan-I & II & Uluberia -I Block under of Howrah Division, PHE Dte. | 1177/HD | 07/03/2024 | 15 | SKYLINE CONSTRUCTION | 0.96 | 0.93 | 100 | 100
1530 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Approach Road (PHASE-1) at Nakol of surface based water supply scheme of Shyampur-I & II , Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2891/HD | 26/06/2024 | 30 | KALIDAS ENTERPRISE | 4.61 | 4.58 | 100 | 100
1531 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Approach Way at the premises of Camp Office Building of the Executive Engineer, Howrah Division of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3096/HD | 08/07/2024 | 30 | K.N ENTERPRISE | 2.68 | 2.67 | 100 | 100
1532 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Kiosk (one no)(Size inside 3.0 x 1.8m) for Kalinagar PWSS at Janapara & temporary approach way of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. (Size inside 3.0 x 1.8m) | 3786/HD | 02/09/2024 | 15 | ZUNAID ENTERPRISE | 2.03 | 1.96 | 100 | 100
1533 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of18 mtr boundary wall from the Bandh road (chainage 0 mtr to 18 mtr) upto the mid point of Right side of the Substation building at Kajiakhali of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3364/HD | 30/07/2024 | 45 | RINKU SAU | 4.84 | 4.77 | 100 | 100
1534 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Approach Road (PHASE-2) at Nakol of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2903/HD | 26/06/2024 | 15 | KALIDAS ENTERPRISE | 5.72 | 5.63 | 100 | 100
1535 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of boundary wall at Choto Joynagar tubewell site under Belari PWSS( Zone 13) of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2902/HD | 26/06/2024 | 45 | KALIDAS ENTERPRISE | 9.71 | 9.69 | 100 | 100
1536 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Temporary Approach Road at Kamardaha (Zone- 37) of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3094/HD | 08/07/2024 | 150 | K.N ENTERPRISE | 5.1 | 4.92 | 100 | 100
1537 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of boundary wall, Bank Protection at Dalsalap (Zone No. 03) (J.L No. 45) & Interconnection between Tubewell & Distribution Pipeline of Belari PWSS at Choto Jaynagar of Shyampur I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2841/HD | 21/06/2024 | 60 | K.N ENTERPRISE | 40.28 | 37.54 | 100 | 100
1538 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Slab Culvert for Kalinagar PWSS at Alipukur of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 4115/HD | 23/09/2024 | 7 | ZUNAID ENTERPRISE | 0.97 | 0.93 | 100 | 100
1539 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Bullah piling for bank protection of canal to the left side of Ghat at Ichapur (Zone 12) for Surface Based W/S Scheme of Shyampur-I & II, Bagnan-I & II & Uluberia-I Block under of Howrah Division, PHE Dte. | 1178/HD | 07/03/2024 | 15 | SKYLINE CONSTRUCTION | 0.96 | 0.93 | 100 | 100
1540 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Supply & Delivery of different types of DI Specials for Surface Based W/S Scheme of Shyampur-I & II, Part of Bagnan-I & II & Uluberia-I Block Under Howrah Division, PHE Dte. | 2689/HD | 07/06/2024 | 15 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 86.34 | 86.34 | 100 | 100
1541 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of drain beside Dhoramanna khal (Zone No. 35) of Bagnan-II block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3543/HD | 09/08/2024 | 7 | SIDDHARTH ENTERPRISE | 0.97 | 0.96 | 100 | 100
1542 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Approach Road for Second H/W site of Baikhai PWSS under Uluberia-I block of Surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3095/HD | 08/07/2024 | 15 | K.N ENTERPRISE | 2.57 | 2.51 | 100 | 100
1543 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Approach Road for Kalinagar PWSS at Alipukur of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 4113/HD | 23/09/2024 | 7 | ZUNAID ENTERPRISE | 0.92 | 0.9 | 100 | 100
1544 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Temporary Approach Road at Ghatampur (Zone- 4) of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 4114/HD | 23/09/2024 | 7 | RINKU SAU | 0.94 | 0.92 | 100 | 100
1545 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Kiosk (one no) for Kalinagar PWSS at Alipukur of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte | 4116/HD | 23/09/2024 | 7 | ZUNAID ENTERPRISE | 0.89 | 0.8 | 100 | 100
1546 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Boundary wall at Moubeshia tubewell site under Baikhali PWSS(Zone-7) of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3097/HD | 08/07/2024 | 30 | K.N ENTERPRISE | 9.7 | 9.68 | 100 | 100
1547 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SHYAMPUR PIPED W/S SCHEME, Zone-I, T.W. No. I (Replacement), Block: Shyampur-I, District - Howrah under JJM Program under Electrical Division PHE Dte. | 1463/ED | 25/07/2024 | 90 | DIPALI CONSTRUCTION | 11.1 | 10.8 | 100 | 90
1548 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Approach Road for alternate entrance of Camp office under Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3544/HD | 09/08/2024 | 7 | SIDDHARTH ENTERPRISE | 0.97 | 0.96 | 100 | 100
1549 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Rest Shed & Other Allied Works at Ghanashyampur (Zone 11) beside OHR site under Shyampur-II Block of Surface Based Water Supply Scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3324/HD | 24/07/2024 | 30 | S R TRADING CORPORATION | 3.71 | 3.69 | 100 | 100
1550 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of 18 mtr boundary wall (chainage 18 mtr to 36 mtr) from the midpoint & upto the end point of Right side of the Substation building at Kajiakhali of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3380/HD | 30/07/2024 | 45 | RINKU SAU | 4.84 | 4.77 | 100 | 100
1551 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Material Requisition To Resource Division | 5140/HD | 11/12/2024 | 0 | Resource Division | 4159.12 | 0 | 0 | 0
1552 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Material Requisition To Resource Division | 4561/HD | 23/10/2024 | 0 | Resource Division | 1803.32 | 0 | 0 | 0
1553 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Material Requisition To Resource Division | 4673/HD | 06/11/2024 | 0 | Resource Division | 39.57 | 0 | 0 | 0
1554 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. Car No. WB-19J-7094 From 01.06.2024 to 30.06.2024 | 514 | 21/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.26 | 0 | 0 | 0
1555 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No.- WB-02AT-8617 01.08.2024 to 31.08.2024 | BP-24-25-589 | 19/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.14 | 0 | 0 | 0
1556 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. Car No. WB-19J-7094 From 01.07.2024 to 31.07.2024 | 515 | 21/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
1557 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No.- WB-02AT-8617 01.06.2024 to 30.06.2024 | 450 | 10/09/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0 | 0
1558 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. Car No. WB-04G-2822 From 01.09.2024 to 30.09.2024 | 530 | 28/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.17 | 0 | 0 | 0
1559 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Quotation for new service connection in the district Howrah under Electrical Division, PHE Dte. ( SM/19186), Reference Id- 106776950 Application no- 1008136524 | BP-24-25-592 | 21/11/2024 | 0 | WBSEDCL | 17.75 | 0 | 0 | 0
1560 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks . App. No.-1008024203 Ref. ID.-106715772 SM/19186 | 568 | 13/11/2024 | 0 | WBSEDCL | 10.03 | 0 | 0 | 0
1561 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Quotation money deposition for new service connection Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, Dist.-Howrah under PHE Dte. Application No- 1008027751 Reference ID- 106717103 SM Code- 19186 | 555 | 05/11/2024 | 0 | WBSEDCL | 14.39 | 0 | 0 | 0
1562 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Quotation money deposition for new service connection Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, Dist.-Howrah under PHE Dte. Application No- 1008027768 Reference ID- 106717102 SM Code- 19186 | 554 | 05/11/2024 | 0 | WBSEDCL | 14.39 | 0 | 0 | 0
1563 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No.- WB-02AT-8617 01.07.2024 to 31.07.2024 | BP-24-25-588 | 19/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0 | 0
1564 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. Car No.- WB-04G-2822 From - 01.09.2024 to 30.09.2024 | 528 | 28/10/2024 | 0 | DASHRATH KUMAR PRAJAPATI | 0.07 | 0 | 0 | 0
1565 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, P.H No.-IV of Amritsal. App. No.-1007859284 Ref. ID.-106635058 SM/19186 | 259 | 03/07/2024 | 0 | WBSEDCL | 4.5 | 0 | 0 | 0
1566 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. WB-04G-2822 01.08.2024 to 31.08.2024 | 470 | 01/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.21 | 0 | 0 | 0
1567 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks . App. No.-1007900847 Ref. ID.-106654842 SM/19186 | 569 | 13/11/2024 | 0 | WBSEDCL | 24.34 | 0 | 0 | 0
1568 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From:- 01/05/2024 to 31/05/2024 Bill No.- 0246 | BP-24-25-587 | 19/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
1569 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, P.H No.-III of Amritsal. App. No.-1007867663 SM/19186 | 258 | 03/07/2024 | 0 | WBSEDCL | 3.82 | 0 | 0 | 0
1570 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. WB-04G-2822 01/07/2024 to 31/07/2024 | 364 | 12/08/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
1571 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. Car No. WB-19J-7094 From 01.08.2024 to 31.08.2024 | 512 | 21/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
1572 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From:- 01/04/2024 to 30/04/2024 Bill No.- 0107 | BP-24-25-586 | 19/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.26 | 0 | 0 | 0
1573 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. Car No. WB-04G-2822 From 01/10/2024 to 31/10/2024 | 622 | 06/12/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
1574 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Quotation money deposition for new service connection Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, Dist.-Howrah under PHE Dte. Application No- 1007786607 Reference ID- 106603564 SM Code- 19186 | 553 | 05/11/2024 | 0 | WBSEDCL | 9.85 | 0 | 0 | 0
1575 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. | 1359/AE-I/ED | 21/06/2024 | 184 | DASHRATH KUMAR PRAJAPATI | 0.87 | 0.73 | 83.15 | 0
1576 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Hiring of 1(One) no. Inspection vehicle no-2 (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Surface Based Water Supply Scheme for "Shyampur", PHE Dte. Government of West Bengal(for the period from 13.10.2024 to 12.10.2025). | 4445/HD | 03/10/2024 | 365 | MR SAP ENTERPRISE | 4.78 | 2.97 | 62.05 | 0
1577 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Hiring of 1 (One) no. Inspection vehicle no-1 (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Surface Based Water Supply Scheme for "Shyampur", PHE Dte. Government of West Bengal (for the period from 13.10.2024 to 12.10.2025). | 4444/HD | 03/10/2024 | 365 | M/S ANIMESH ENTERPRISE | 4.78 | 2.97 | 62 | 15
1578 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of counterfort retaining wall at backend & left side of Substation building at Kajiakhali under Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 4364/HD | 30/09/2024 | 360 | S R TRADING CORPORATION | 32.44 | 0 | 0 | 5
1579 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of boundary wall at Nakol H/W site of Shyampur-II block under Surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 4462/HD | 03/10/2024 | 120 | KALIDAS ENTERPRISE | 21.69 | 0 | 0 | 80
1580 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of boundary wall and land development at Khalore H/W site (OHR 40A) under Bagnan-I block of Surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 1248/HD | 06/03/2025 | 180 | K.N ENTERPRISE | 16.57 | 0 | 0 | 75
1581 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5 m) at Hallyan (Zone -29) at Bagnan¿II Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2801/HD | 17/06/2025 | 60 | SIDDHARTH ENTERPRISE | 7.73 | 0 | 0 | 0
1582 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5 m) at Ramchandrapur (Zone-40) at Bagnan¿I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2802/HD | 17/06/2025 | 300 | K.N ENTERPRISE | 7.73 | 0 | 0 | 80
1583 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5 m) at Kulgachia (Zone -5) at Uluberia¿I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2575/HD | 02/06/2025 | 180 | S S CONSTRUCTION | 9.77 | 0 | 0 | 75
1584 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of boundary wall, land development and other allied works at Amritashal (Zone No. 09) (J.L No. 38) of Uluberia I block of surface-based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 1073/HD | 27/02/2025 | 120 | SK. MOMTAJUR RAHAMAN | 26.59 | 0 | 0 | 78
1585 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Extension of boundary wall and land development at Mugkalyan H/W site (OHR 32 & 32A) under Bagnan-II block of Surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 991/HD | 20/02/2025 | 375 | S R TRADING CORPORATION | 42.84 | 0 | 0 | 70
1586 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of boundary wall at Barunda H/W site (Zone 38) of Bagnan-II block of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2663/HD | 05/06/2025 | 180 | K.N ENTERPRISE | 24.86 | 0 | 0 | 75
1587 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Shyampur-I & II Block) | 4119/HD | 14/10/2025 | 30 | JHARNA ENTERPRISE | 4.79 | 0 | 0 | 0
1588 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Uluberia-I Block) (PART-B) | 4122/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
1589 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Interconnection between Tubewell & Distribution Pipeline of Kalinagar PWSS at Alipukur & Fencing at the front side of entry of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3542/HD | 09/08/2024 | 7 | SIDDHARTH ENTERPRISE | 0.83 | 0.64 | 100 | 100
1590 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of boundary wall, land development & other alied work for Kalinagar PWSS at Alipukur of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 4876/HD | 25/11/2024 | 135 | S.S CONSTRUCTION | 7.55 | 0 | 0 | 100
1591 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Chakkamala Samsan Chulli beside Chakkamala OHR Site (Zone No.-35) of Bagnan-II block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3718/HD | 28/08/2024 | 150 | S.S ENTERPRISE | 2.77 | 0 | 0 | 100
1592 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Balance work of boundary wall at Manikpur H/W site (OHR 5A) of Uluberia-I Block under Surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 4917/HD | 27/11/2024 | 180 | S R TRADING CORPORATION | 17.03 | 0 | 0 | 100
1593 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Plastering, Painting, Supplying, Fitting & fixing of iron post & Barbid wire at the Right Side Wall (Chainage 0 mtr to 36 mtr) of Substation Building at kajiakhali of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3363/HD | 30/07/2024 | 135 | RINKU SAU | 1.27 | 0 | 0 | 100
1594 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5 m) at Barberia (Zone -8) at Uluberia¿I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2576/HD | 02/06/2025 | 60 | USHA CONCERN | 7.7 | 0 | 0 | 100
1595 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5m) at Amritsal (Zone-9) at Uluberia¿ I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2500/HD | 26/05/2025 | 60 | SK. MOMTAJUR RAHAMAN | 7.69 | 0 | 0 | 100
1596 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Extension of boundary wall, land development and other allied works at Orphuli (Zone No. 34) of Bagnan-II block of Surface-based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 990/HD | 20/02/2025 | 60 | M/S MJA ENTERPRISE | 18.47 | 0 | 0 | 100
1597 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Hume Pipe Culvert, Land development & Protection work at Mongrajpur(OHR 6) of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 922/HD | 17/02/2025 | 45 | SAIKAT ENTERPRISE | 7.5 | 0 | 0 | 100
1598 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5 m) at Radhapur (Zone -19) at Shyampur¿ I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2803/HD | 17/06/2025 | 60 | MARUTI CONSTRUCTION | 7.73 | 0 | 0 | 100
1599 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Balance work for Construction of retaining Wall, drain and others allied works at Chakkamala of Bagnana II block of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 2766/HD | 12/06/2025 | 30 | S.S ENTERPRISE | 3.13 | 0 | 0 | 100
1600 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Material Requisition To Resource Division | 985/HD | 20/02/2025 | 0 | Resource Division | 770 | 0 | 0 | 0
1601 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Material Requisition To Resource Division | 3961/HD | 22/09/2025 | 0 | Resource Division | 967.61 | 0 | 0 | 0
1602 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Material Requisition To Resource Division | 3621/HD | 28/08/2025 | 0 | Resource Division | 34.87 | 0 | 0 | 0
1603 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Material Requisition To Resource Division | 2177/HD | 30/04/2025 | 0 | Resource Division | 56.64 | 0 | 0 | 0
1604 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | New Connection of Electricity (WBSEDCL) for Camp office of Executive Engineer, Howrah Division PHE Dte for Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks. Application No- 1008331661 Reference ID- 106904440 SM Code- 19186 | 669 | 21/01/2025 | 0 | WBSEDCL | 0.72 | 0 | 0 | 0
1605 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Supply of Fuel for 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. (JJM Work for Hooghly District) for the Month of October 2024. |  | 09/09/2025 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
1606 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Upgradation of PMGSY road from MRL 07-Kalinagar (Maniktala Stoppage) to Hirapur under Uluberia-I Block in the district of Howrah |  | 07/04/2025 | 0 | WBSRDA | 26.88 | 0 | 0 | 0
1607 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. Car No. WB-04G-2822 Bill No. 1071 Bill Date: 30/11/2024 | 643 | 09/01/2025 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
1608 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Shifiting of LTOH LINE near OHR-III under Shyampur project Application No- 100000141270 Reference ID- 860340560 SM Code- 19186 | 42151 | 30/07/2025 | 0 | WBSEDCL | 0.64 | 0 | 0 | 0
1609 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of OCTOBER,2024 |  | 29/01/2025 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.08 | 0 | 0 | 0
1610 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Surveying, Designing, Supplying, Laying & Commissioning of Distribution System for 28 nos Zones including construction of all pipe supporting structure & FHTC under Shyampur-I, II, & Part of Bagnan-I & II Block of Howrah District with 3 months trial run & Operation & Maintenance of all the works for a period of 3 (Three) years under Augmentation of Surface Based W/S scheme for Shyampur-I & II, Uluberia I and Part of Bagnan I & II Block ("Contract Package-3" as per detail scope of works.), District- Howrah | 1160/HD | 07/03/2024 | 665 | WPIL LIMITED | 29388.95 | 0 | 0 | 15
1611 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. (JJM Work for Hooghly District) | 5589/HMSD | 27/09/2024 | 151 | SANJIB PRADHAN | 0.72 | 0 | 0 | 0
1612 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of boundary wall at Kamardaha (Zone No. 37) of Bagnan-II block of surface-based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 1880/HD | 17/04/2025 | 60 | S.S CONSTRUCTION | 26.72 | 0 | 0 | 0
1613 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Hiring of 1 (One) no. Inspection vehicle no-3 (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Surface Based Water Supply Scheme for "Shyampur", PHE Dte. Government of West Bengal (for the period from 365 days) (w.e.f.,01/02/2025 to 31/01/2026) | 696/HD | 29/01/2025 | 365 | BIJITA TRAVELS | 4.78 | 1.57 | 32.88 | 0
1614 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Proposed Surface Based Water Supply Scheme for Part of Malancha Beria, Rauta, Harinarayanpur and Kaijuri of Uluberia I Block under "Surface Based Water Supply Scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block" [No. of FHTC=1723] (SM/19186) | 1488/HD | 20/03/2025 | 300 | APRJ CONSTRUCTIONS | 707.58 | 0 | 0 | 0
1615 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Additional Work of Laying Distribution system (LDS) & Road Restoration Work at Uluberia-1 & Shyampur-1 Block of Surface Based W/S scheme for Shyampur-I & II, Uluberia I and Part of Bagnan I & II Block under Howrah Division, PHE Dte. (SM/06386 & SM/19186) | 994/HD | 20/02/2025 | 496 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 1950.12 | 180.54 | 9.26 | 60
1616 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Uluberia-I Block) (PART-A) | 4121/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
1617 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5 m) at Gouripur (Zone -1) at Uluberia¿ I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | 3025/HD | 03/07/2025 | 120 | BISWAJIT BAG | 7.74 | 0 | 0 | 100
1618 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | PHE Restoration work of road from L026-T01 Mahamayatola to Tiorpara L026 Baikhali Bridge to Tiorpara Bridge via Palpara Madai at Dhulasimla, Hirapur GP under Ulubria-I block in the district of Howrah vide Pckg no. WB-09-303 |  | 26/05/2026 | 0 | WBSRDA-II | 12.78 | 0 | 0 | 0
1619 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | PHE Restoration work of road from L046-t06 Damodarpur to Paschimkalinagarkachari L046 at Bahira & Kalinagar GP under Uluberia-I block in the district of Howrah vide Pkg no-WB-09-209 |  | 26/05/2026 | 0 | WBSRDA-II | 4.02 | 0 | 0 | 0
1620 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | PHE Restoration work of road from T03 Uttar Konranrapara to Khalpara Daspara 1053 at Hatgachha-I GP under Uluberia-1 block in the district of Howrah. vide pkg no WB-09-204 |  | 26/05/2026 | 0 | WBSRDA-II | 1.75 | 0 | 0 | 0
1621 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Supply of Fuel of 1(One) no Diesel luxury Taxi on contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division PHE Dte(JJM work for Hooghly District) for the Month of December 2024 Car No-WB04H1945 |  | 25/02/2026 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
1622 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | PHE Restoration work of road from L043-L042 Khandarpara to Mahisalibagdipara L043 at Hatgachha-l, Bahira GP under Uluberia-I block in the district of Howrah. vide Pkg No- WB-09-203 |  | 26/05/2026 | 0 | WBSRDA-II | 5.63 | 0 | 0 | 0
1623 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | PHE Restoration work of road from L044-1043 Aymachandpur to Badakhal 1 L043 at Balichaturi GP under Shyampur-i block in the district of Howrah vide Pkg No-WB-09-270. |  | 26/05/2026 | 0 | WBSRDA-II | 12.04 | 0 | 0 | 0
1624 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Supply of Fuel of 1(One) no Diesel luxury Taxi on contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division PHE Dte(JJM work for Hooghly District) for the Month of November 2024. Car No-WB04H 1945. |  | 25/02/2026 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
1625 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Repair of L030-L027 Mirpara to Ayma Hallyan L030 road damaged by PHE Dept. Package No. WB-09-240 |  | 26/05/2026 | 0 | WBSRDA-II | 18.15 | 0 | 0 | 0
1626 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Repair ofL029-L027 Uttar Hallyan to Enayetpur L029road damaged by PHE Dept. Package No. WB-09-239 |  | 26/05/2026 | 0 | WBSRDA-II | 7.86 | 0 | 0 | 0
1627 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | PHE Restoration work of road from L033-T03 Lolitagari to Uttarpara L033 Gadaipur kheyag hat to Lalita gori at Hatgachha-I GP under Uluberia-I block in the district of Howrah vide Pkg no- WB-09-218 |  | 26/05/2026 | 0 | WBSRDA-II | 25.18 | 0 | 0 | 0
1628 | HOWRAH | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks , SM/19186 | Augmentation | Diesel Charges Billing month of september, 2024 |  | 08/12/2025 | 0 | S.P. CONSTRUCTION | 0.11 | 0 | 0 | 0
1629 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block , SM/07466 | Retrofitting | Retrofitting for Nakubar W/S Scheme. | W/263 | 03/09/2021 | 0 | N. G ENGINEERING | 35.84 | 0 | 0 | 0
1630 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block , SM/07466 | Retrofitting | Retrofitting Nakubar | W/155 | 06/08/2021 | 0 | M/S ASHIRBAD (INDIA) | 20.86 | 0 | 0 | 0
1631 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block , SM/07466 | Retrofitting | Retrofitting of Nakubar. | W/93 | 19/07/2021 | 0 | SWASTIK ENTERPRISE | 14.6 | 0 | 0 | 0
1632 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block , SM/07466 | Retrofitting | Retrofitting for Nakubar W/S Scheme. |  | 24/08/2021 | 0 | M/S ASHIRBAD (INDIA) | 38.07 | 0 | 0 | 0
1633 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block , SM/07466 | Retrofitting | Work Order for Additional laying of pipeline for retrofitting work for providing Functional Household Tap Connection(FHTC) at Nakubar Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 2368/HD | 23/12/2021 | 30 | M/S ASHIRBAD (INDIA) | 4.57 | 4.54 | 99.37 | 0
1634 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block , SM/07466 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block under Howrah Division, PHE Dte. (PART-D) [Ranjoybar MOUZA PART & Nakubar MOUZA PART] | W/797 | 03/03/2022 | 0 | N. G ENGINEERING | 34.83 | 0 | 0 | 0
1635 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block , SM/07466 | Retrofitting | Alternative laying of distribution pipe line damaged due to improvement of road work by WBSRDA Howrah under PMGSY programme for restoration of FHTC's at Nakubar W/S scheme under Amta-II Block under Howrah Division, PHE Dte. Near Manuchack Zilla parisad pole | 949/AE/USD | 22/03/2023 | 30 | M/S ASHIRBAD (INDIA) | 0.97 | 0.79 | 100 | 100
1636 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block , SM/07466 | Retrofitting | Alternative laying of distribution pipe line damaged due to improvement of road work by WBSRDA Howrah under PMGSY programme for restoration of FHTC's at Nakubar W/S scheme under Amta-II Block under Howrah Division, PHE Dte. near Kalimata Club and various places. | 950/AE/USD | 22/03/2023 | 30 | M/S ASHIRBAD (INDIA) | 0.96 | 0.96 | 100 | 100
1637 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block , SM/07466 | Retrofitting | Alternative laying of distribution pipe line damaged due to improvement of road work by WBSRDA Howrah under PMGSY programme for restoration of FHTC's at Nakubar W/S scheme under Amta-II Block under Howrah Division, PHE Dte. At different places of Boalia mouza | 939/AE/USD | 22/03/2023 | 30 | M/S ASHIRBAD (INDIA) | 0.97 | 0.78 | 100 | 100
1638 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Bhursit Bamunpara PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | 2156/HD | 01/12/2021 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.7 | 3.7 | 100 | 0
1639 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 23.41 | 0 | 0 | 0
1640 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
1641 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhursit Bamunpara water supply scheme T.W. No. New, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 917/ED | 22/02/2023 | 90 | ANIK & CO. | 10.69 | 10.41 | 97.39 | 70
1642 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bhursit Bamunpara PWSS of Jagatballavpur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 2713/HD | 14/12/2022 | 45 | BALAJI UDDYOG | 27.45 | 25.21 | 100 | 100
1643 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Work Order for Construction of 2 NOS 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at 3RD & 4TH Tube well SiteS of Bhusit Bamun para PWSS at J.B.PUR Block of Howrah District under Howrah Division, PHE Dte. | 1054/HD | 15/03/2023 | 90 | BASU CONSTRUCTION | 13.5 | 13.5 | 100 | 100
1644 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 73.96 | 0 | 0 | 0
1645 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation |  |  | 14/07/2023 | 0 | WBSEDCL | 5 | 0 | 0 | 0
1646 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Payment for WBSEDCL of Bhurshit Bamunpara Water Supply Scheme Pump House No-IV | BP-2023-24-171 | 24/07/2023 | 0 | WBSEDCL | 5 | 0 | 0 | 0
1647 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Additional Quotation money deposition for Bhurshit Bamunpara PWSS, P.H No.-III |  | 17/08/2023 | 0 | WBSEDCL | 21.59 | 0 | 0 | 0
1648 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Quotation Bill for New Service Connection at Bhursit Bamunpara, TW-III |  | 09/03/2023 | 0 | WBSEDCL | 11.77 | 0 | 0 | 0
1649 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Additional Quotation money deposition for Bhurshit Bamunpara PWSS Pump House No- III | BP-2023-24-237 | 23/08/2023 | 0 | WBSEDCL | 21.59 | 0 | 0 | 0
1650 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Work Order for Laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah sadar Sub-division under Howrah Division, PHE Dte (Part-A) | 586/HD | 15/03/2022 | 45 | B.B.C ENTERPRISE | 65.18 | 64.94 | 100 | 40
1651 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Work Order for Laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah sadar Sub-division under Howrah Division, PHE Dte. (Part-B) | 587/HD | 15/03/2022 | 45 | DEV DAS SHAW | 75.85 | 37.64 | 49.8 | 60
1652 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhursit Bamunpara water supply scheme, T.W. No. IV, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 3221/ED | 03/08/2023 | 90 | ALAK KUMAR CHAKRABORTY | 10.85 | 10.77 | 100 | 70
1653 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Additional Laying of Distribution system at Dhasa mouza under Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah Sadar Sub-division under Howrah Division, Phe Dte. | 1300/HD | 13/03/2024 | 45 | M/S ASHIRBAD (INDIA) | 13.41 | 12.74 | 100 | 100
1654 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Work Order for Construction Of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/11/2012) Including All pipe Connection For Augmentation Of Bhurshit Bamunpara W/S Scheme In Jagatballavpur Block Of Howrah Division, P. H. E. Dte. | 1884/HD | 14/09/2022 | 180 | SUDHAMAY MAJUMDAR | 123.64 | 106.75 | 73.24 | 90
1655 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Work Oder for laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah Sadar Sub-division under Howrah Division, PHE Dte. (start node- 276 to 373) (Part-D) | 589/HD | 15/03/2022 | 1113 | M/S. CHANDIMATA CONSTRUCTION | 71.69 | 63.87 | 89.09 | 100
1656 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Work Order for Laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah sadar Sub-division under Howrah Division, PHE Dte. (start node- 188 to 274) (Part-C) | 588/HD | 15/03/2022 | 1023 | N. G ENGINEERING | 93.7 | 90.42 | 97.07 | 100
1657 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara , SM/09351 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Jagatballavpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4814/HD | 19/11/2024 | 510 | HORIZEN | 10.11 | 0.03 | 99.8 | 56
1658 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme , SM/06788 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Paschim Gazipur piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (for Paschim Gazipur mouza part) | 1305/HD | 12/10/2020 | 30 | MENOKA ENGINEERING WORKS | 27.03 | 0 | 0 | 0
1659 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme , SM/06788 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Paschim Gazipur piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) (for Bargazipur Mouza) | 1302/HD | 12/10/2020 | 30 | ARINDAM ENTERPRISE | 9.05 | 0 | 0 | 0
1660 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme , SM/06788 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Paschim Gazipur piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) (for Paschim Gazipur mouza part) | 1303/HD | 12/10/2020 | 30 | CONSTRUCTION CORNER | 27.51 | 0 | 0 | 0
1661 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme , SM/06788 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Paschim Gazipur piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) (for Paschim Gazipur mouza part) | 1304/HD | 12/10/2020 | 30 | NIRMAL UDYOG | 27.33 | 0 | 0 | 0
1662 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme , SM/06788 | Retrofitting | Retrofitting Paschim Gazipur Water Supply Scheme | W/518 | 15/01/2021 | 0 | ARINDAM ENTERPRISE | 8.92 | 0 | 0 | 0
1663 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme , SM/06788 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water sup | 844384 | 26/03/2021 | 0 | CONSTRUCTION CORNER | 22.55 | 0 | 0 | 0
1664 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme , SM/06788 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water SUPPLY SCHEME. | 844344 | 20/03/2021 | 0 | NIRMAL UDYOG | 25.48 | 0 | 0 | 0
1665 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme , SM/06788 | Retrofitting | Retrofitting of Paschim Gazipur Water Supply Scheme | 844319 | 11/03/2021 | 0 | MENOKA ENGINEERING WORKS | 22.15 | 0 | 0 | 0
1666 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme , SM/06718 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Uttar Pirpur piped water supply scheme under Uluberia-II Block under Howrah Division, PHE Dte. (Part-A) (for Uttar Pirpur (CT)(Part) | 1306/HD | 12/10/2020 | 30 | JAHANGIR ALAM | 26.59 | 0 | 0 | 0
1667 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme , SM/06718 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Uttar Pirpur piped water supply scheme under Uluberia-II Block under Howrah Division, PHE Dte. (Part-B) (for Uttar Pirpur (CT)(Part) | 1307/HD | 12/10/2020 | 30 | MANAS CHATTERJEE | 27.1 | 0 | 0 | 0
1668 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme , SM/06718 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Uttar Pirpur piped water supply scheme under Uluberia-II Block under Howrah Division, PHE Dte. (Part-C) (for Uttar Pirpur (CT)(Part) | 1308/HD | 12/10/2020 | 30 | TANMOY ROY CHOUDHURY | 24.01 | 0 | 0 | 0
1669 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme , SM/06718 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Uttar Pirpur piped water supply scheme under Uluberia-II Block under Howrah Division, PHE Dte.(Part-D) (for Uttar Pirpur (CT)(Part) | 1309/HD | 12/10/2020 | 30 | S.S ENTERPRISE | 9.71 | 0 | 0 | 0
1670 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme , SM/06718 | Retrofitting | Retrofitting of Uttar Pirpur Water Supply Scheme. | 844315 | 09/03/2021 | 0 | S.S ENTERPRISE | 9.53 | 0 | 0 | 0
1671 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme , SM/06718 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme | 844335 | 25/02/2021 | 0 | JAHANGIR ALAM | 26.02 | 0 | 0 | 0
1672 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme , SM/06718 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme | 8443105 | 30/03/2021 | 0 | MANAS CHATTERJEE | 16.39 | 0 | 0 | 0
1673 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme , SM/06718 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Uttar Pirpur PWSS | 84437 | 09/02/2021 | 0 | TANMOY ROY CHOUDHURY | 18.74 | 0 | 0 | 0
1674 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme , SM/06718 | Retrofitting | Const of 300 m3 RCC Over head Reservoir of Uttar Pirpur W/S Scheme. | 844335 | 30/03/2022 | 0 | JAHANGIR ALAM | 12.27 | 0 | 0 | 0
1675 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme , SM/06718 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme | 387/21/2022 | 15/08/2020 | 0 | MANAS CHATTERJEE | 2.8 | 5.61 | 200 | 0
1676 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme , SM/06720 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) | 1311/HD | 12/10/2020 | 30 | BISWAJIT BAG | 28.88 | 0 | 0 | 0
1677 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme , SM/06720 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) | 1312/HD | 12/10/2020 | 30 | M/S SARADA UDYOG | 28.69 | 0 | 0 | 0
1678 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme , SM/06720 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (for Sarda Mouza(part) | 1313/HD | 12/10/2020 | 30 | USHA CONCERN | 28.61 | 0 | 0 | 0
1679 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme , SM/06720 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (for Sarda Mouza(part) | 1314/HD | 12/10/2020 | 30 | S. NAG CHOWDHURY | 28.6 | 0 | 0 | 0
1680 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme , SM/06720 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) (for Sarda Mouza(part) | 1310/HD | 12/10/2020 | 30 | JAHANGIR ALAM | 28.16 | 0 | 0 | 0
1681 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme , SM/06720 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme | 84434 | 09/02/2021 | 0 | BISWAJIT BAG | 28.46 | 0 | 0 | 0
1682 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme , SM/06720 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | 84438 | 09/02/2021 | 0 | USHA CONCERN | 26.17 | 0 | 0 | 0
1683 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme , SM/06720 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | 84439 | 03/03/2021 | 0 | MAA TARA CONSTRUCTION | 6.38 | 0 | 0 | 0
1684 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme , SM/06720 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | 84439 | 09/02/2021 | 0 | S. NAG CHOWDHURY | 28.56 | 0 | 0 | 0
1685 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme , SM/06720 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) | 2240/HD | 09/12/2021 | 30 | SUMANA ENTERPRISE | 2.17 | 0 | 0 | 0
1686 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme , SM/06720 | Retrofitting | Mass Awarness generation and IEC activities. | 844313 | 23/12/2021 | 0 | PRADIP KUMAR JATI | 42 | 0 | 0 | 0
1687 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block , SM/07883 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. 2184 nos | 93/HD | 17/01/2022 | 45 | MA MANASA CONSTRUCTION | 84.61 | 86.67 | 100 | 0
1688 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block , SM/07883 | Retrofitting | Work Order for Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Phase-2) | 166/AE/USD | 28/06/2022 | 45 | MA MANASA CONSTRUCTION | 4.78 | 0 | 0 | 0
1689 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block , SM/07883 | Retrofitting | Work Order for Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Phase-1) | 165/AE/USD | 28/06/2022 | 45 | MA MANASA CONSTRUCTION | 4.84 | 0 | 0 | 0
1690 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block , SM/07883 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-1). | 433/AE/USD | 13/09/2022 | 45 | MA MANASA CONSTRUCTION | 4.85 | 4.81 | 100 | 0
1691 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block , SM/07883 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-4). | 436/AE/USD | 13/09/2022 | 45 | MA MANASA CONSTRUCTION | 4.8 | 4.76 | 100 | 0
1692 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block , SM/07883 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-5). | 437/AE/USD | 13/09/2022 | 45 | MA MANASA CONSTRUCTION | 4.79 | 4.76 | 100 | 0
1693 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block , SM/07883 | Retrofitting | Material Requisition To Resource Division | 114/HD | 20/01/2022 | 0 | Resource Division | 15.98 | 0 | 0 | 0
1694 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block , SM/07883 | Retrofitting | Construction of boundary wall at HW site of Jhamtia W/S scheme in Uluberia Sub-division, under Howrah Division P.H.E Dte. ( Phase-1 ) | 472/AE/USD | 16/09/2022 | 45 | TIYASA ENTERPRISE | 4.82 | 2.16 | 100 | 50
1695 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block , SM/07883 | Retrofitting | Inter Connection work for 3rd & 4th TW with delivery pipeline at village Selnepara & Kalasdihi within the command area of Jhamtia PWSS under Amta-II Block under Uluberia Sub-Division Under Howrah Division. PHE Dte. | 4014/HD | 13/09/2024 | 120 | LOKENATH ENTERPRISES | 14.73 | 0 | 0 | 100
1696 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) , SM/07884 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Zone-II) 2203 nos | 96/HD | 17/01/2022 | 45 | DEV DAS SHAW | 82.22 | 82.72 | 100 | 0
1697 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) , SM/07884 | Retrofitting | Additional laying of pipeline and internal pathway at Uttar & Dakhin Bhatora (Zone-II) Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 2440/HD | 29/12/2021 | 30 | P B ENTERPRISE | 4.84 | 4.37 | 90.3 | 0
1698 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) , SM/07884 | Retrofitting | Construction of boundary wall at 2nd TW site of Uttar & Dakhin Bhatora Zone-II w/s scheme in Uluberia Sub-Division under Howrah Division, P.H.E Dte. | 522/AE/USD | 27/09/2022 | 45 | P B ENTERPRISE | 4.84 | 4.36 | 89.92 | 0
1699 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) , SM/07884 | Retrofitting | Additional laying distribution pipeline and Road restoration at Village-Moyrachack of Amta-II Block under Uttar & Dakhin Bhatora PWSS under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 2762/HD | 12/06/2025 | 60 | RANA ENTERPRISE | 56.75 | 0 | 0 | 0
1700 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) , SM/07884 | Retrofitting | Additional Tube well of 250 X 150 mm Dia and 230 m deep by Direct Rotary method with UPVC Pipes all complete at vill-Moyrachack of Amta-II Block under Uttar & Dakhin Bhatora PWSS under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 2557/HD | 30/05/2025 | 30 | PRANTIK DRILLING AGENCY | 14.71 | 0 | 0 | 0
1701 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) , SM/07884 | Retrofitting | Construction of 1 no switch room (3.6m x 3.00 m ) with water supply & sanitary arrangement at TW sites of Moyrachack village under Uttar & Dakhin Bhatora PWSS under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 2763/HD | 12/06/2025 | 60 | RANA ENTERPRISE | 6.86 | 0 | 0 | 0
1702 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) , SM/07884 | Retrofitting | Supplying, fitting, fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Amta-II Block) (PART-A) | 4116/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 100
1703 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Work Order for Laying Distribution Pipeline At Narendrapur Mouza Node No. 367 to 450 (Part-3) of Shekrahati Water Supply Scheme in Jagatballavpur Block Of Howrah District. | 629/HD | 22/03/2022 | 45 | BUILT INDIA | 37.92 | 38.47 | 100 | 0
1704 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 23.04 | 0 | 0 | 0
1705 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Sekrahati PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | BP-2021-22-403 | 14/03/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.18 | 0 | 0 | 0
1706 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
1707 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Work Order for Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep additional tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Shekrahati PWSS of Jagat Ballavpur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 169/HD | 13/01/2023 | 45 | MUNSHI ENTERPRISE | 12.98 | 12.68 | 97.7 | 100
1708 | HOWRAH | Electrical | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shekrahati water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 915/ED | 22/02/2023 | 90 | A.G. ENTERPRISE | 21.49 | 10.47 | 48.7 | 65
1709 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Work Order for Laying Distribution Pipeline At Sekrahati Mouza Node No. 220 to 366 (Part-2) of Shekrahati Water Supply Scheme In Jagatballavpur Block Of Howrah District. | 803/HD | 07/04/2022 | 45 | SWASTIK ENTERPRISE | 56.88 | 57.38 | 100 | 100
1710 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Work Order for Restoration of damaged concrete branch roads due to laying of pipe line at Narendrapur Mouza (Node No. 367 to 450) of Sekrahati PWSS under Howrah Divnision PHE Dte. | 273/HD | 19/01/2023 | 45 | BUILT INDIA | 10.4 | 10.18 | 100 | 0
1711 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Work Order for Construction of Pump House ( 5.40m x 3.60 m) at 3rd Tube Well Site of Sekrahati PWSS at J.B.Pur Block of Howrah District under Howrah Division, P. H. E. Dte. | 1851/HD | 02/05/2023 | 90 | M.K ENTERPRISE | 6.19 | 5.61 | 100 | 100
1712 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Work Order for Pipeline Work From 3rd Tubewell to Delivery line (Node No 326 to 312) at Sekrahati PWSS at J.B.Pur Block under Howrah Sadar Suv-Division, P.H.E. Dte. | 1853/HD | 02/05/2023 | 30 | DEBABRATA CHAKRABORTY | 4.33 | 3.64 | 100 | 100
1713 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Work Order for Construction of Boundary Wall at 3rd Tube Well Site of Sekrahati PWSS at J.B.Pur Block of Howrah District under Howrah Division, P. H. E. Dte. (12 m X 12 m) | 1931/HD | 10/05/2023 | 60 | M/S RAJBALLOVI CONSTRUCTION | 4.13 | 4.08 | 100 | 100
1714 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 20.07 | 0 | 0 | 0
1715 | HOWRAH | Electrical | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Quotation Bill for New Service Connection at Sekrahati W/S. Sch. TW-III, Howrah | 213 | 24/03/2023 | 0 | WBSEDCL | 2.98 | 0 | 0 | 0
1716 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Work Order for Providing FHTC (Functional Household Tap Connection) At Sekrahati Mouza (Part-2) of Shekrahati Water Supply Scheme isn Jagatballavpur Block Of Howrah District (PART-B) | 628/HD | 22/03/2022 | 45 | SUSHANTA MONDAL | 26.5 | 25.85 | 97.52 | 100
1717 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Work Order for Providing FHTC (Functional Household Tap Connection) At Narendrapur Mouza (Part-3) of Shekrahati Water Supply Scheme In Jagatballavpur Block Of Howrah District. | 804/HD | 07/04/2022 | 45 | KAMIRUL SK AND CO. | 56.29 | 54.4 | 100 | 98
1718 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Laying Distribution Pipeline at Uncovered Area Near 3rd Tubewell (Node 326 to 309, 312 to 315 & 313 to 331) For Providing FHTC of Sekrahati Water Supply Scheme under Howrah Sadar Sub-Division PHE Dte. | 209/HSSD | 29/02/2024 | 30 | MA-DURGA ENTERPRISE | 1.61 | 1.6 | 100 | 100
1719 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Road Restoration work due to road cutting by PHE for laying water pipeline at Howrah Amta Road from 32.50 Km to 35.70 Km (Both side) Under Howrah Division, P.W.D. during the year 2024-25. | BP-2024-25-493 | 27/11/2024 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 13.23 | 0 | 0 | 0
1720 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Work Order for Construction Of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref :Dept. Super Struc. DRG. No. PCI/OHR/11/2012) Including All pipe Connection, Design od piles and soil test, Laying Distribution Pipeline At Krishnandapur Mouza Node No. 1 to 219 (Part-1) and Providing FHTC (Functional Household Tap Connection) at Krishnandapur Mouza (Part-1) for Augmentation Of SEKRAHATI Water Supply Scheme In Jagatballavpur Block Of Howrah Division PHED. | 1340/HD | 27/06/2022 | 1374 | JAHANGIR ALAM | 204.08 | 114.66 | 56.18 | 80
1721 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Restoration of damaged concrete branch roads due to laying of pipe line at Sekrahati Mouza of Sekrahati PWSS under Howrah Divnision PHE Dte. | 208/HSSD | 29/02/2024 | 30 | SWASTIK ENTERPRISE | 3.69 | 0 | 0 | 100
1722 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Dismantling of Boundary wall of OHR site at Sekrahati PWSS Block Jagatballavpur under Howrah sadar sub-Division of Howrah Division PHE,Dte. | 1172/HSSD | 19/11/2024 | 60 | M/S ASHIRBAD (INDIA) | 0.7 | 0 | 0 | 100
1723 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Shifting of existing Rising main pipe line & construction of temporary approch road of OHR site at Sekrahati PWSS Block Jagatballavpur,under Howrah sadar sub-Division of Howrah Division PHE,Dte. | 1117/HSSD | 30/10/2024 | 30 | M/S ASHIRBAD (INDIA) | 1.17 | 0 | 0 | 100
1724 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Special repair work (Bituminous Portion) for restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road "Chakrabatypara - Midyapara L042" at Jagatballavpur Block, Pkg No WB/09/145, Howrah undert W.B.S.R.D.A. Howrah Division-I. |  | 28/04/2025 | 0 | WBSRDA | 5.89 | 0 | 0 | 0
1725 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Work Order for Rising Main Pipeline Work From 2nd Pump House to 1st Pump House & OHR of Shekrahati Water Supply Scheme In Jagatballavpur Block Of Howrah District. | 2605/HD | 07/12/2022 | 45 | JAHANGIR ALAM | 2.62 | 0 | 0 | 100
1726 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati , SM/09586 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Shekrahati PWSS [SM/09586], Nimabalia PWSS [SM/13770], Shyampur PWSS [SM/11790] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 231-A/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
1727 | HOWRAH | Howrah Division | Retrofitting work for providing functional household tap connection (FHTC) from existing distribution system at Balichak PWSS. , SM/09105 | Retrofitting | Work Order for Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at 4th tube well site of Balichack PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | 2598/HD | 07/12/2022 | 60 | BINOY KOLEY | 4.7 | 4.48 | 100 | 100
1728 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Work Order for Preparation of DPR for new piped water supply scheme of Murgaberia PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 249/HD | 07/02/2022 | 15 | STEELCONC AND ASSOCIATES | 3.11 | 3.11 | 100 | 0
1729 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Material Requisition To Resource Division | 2639/HD | 09/12/2022 | 0 | Resource Division | 32.55 | 0 | 0 | 0
1730 | HOWRAH | Electrical | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Murgaberia water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 3516/ED | 30/12/2022 | 90 | BIJAN ENTERPRISE | 20.25 | 19.56 | 96.56 | 70
1731 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Murgaberia PWSS at Bagnan-I Block of Howrah District under Howrah Division, P. H. E. Dte. | 1971/HD | 22/09/2022 | 40 | ACME CONSTRUCTION | 35.36 | 32.9 | 100 | 0
1732 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site at Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1053/HD | 15/03/2023 | 90 | KALIDAS ENTERPRISE | 7.18 | 7.18 | 100 | 100
1733 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at 2nd TW site at Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1056/HD | 15/03/2023 | 90 | GRAVITA ENTERPRISE | 7.17 | 7.17 | 100 | 100
1734 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 36.79 | 0 | 0 | 0
1735 | HOWRAH | Electrical | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Quotation Bill for New Service Connection at Murgaberia W/S. Sch. PH-I | 170 | 28/02/2023 | 0 | WBSEDCL | 0.55 | 0 | 0 | 0
1736 | HOWRAH | Electrical | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Quotation Bill for New service connection at Murgaberia W/S. Sch. PH-II | 170 | 28/02/2023 | 0 | WBSEDCL | 0.55 | 0 | 0 | 0
1737 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Laying Distribution System(UPVC & DI) & providing Functional Household Tap Connection (FHTC) of Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte.(Mouza-Chak monohar(54) | 4469/HD | 12/12/2023 | 75 | M/S. GHOSH CONSTRUCTION | 74.17 | 50.42 | 100 | 100
1738 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Restoration of Road at Murgaberia under Murgaberia PWSS under Uluberia Sub-Division of Howrah Division,PHEDte. | 239/AE/USD | 10/06/2024 | 45 | BISWAJIT BAG | 19.58 | 19.58 | 100 | 100
1739 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 5.73 | 0 | 0 | 0
1740 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Work Order for Construction of 300 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (1350 nos ) for Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-I) | 2649/HD | 09/12/2022 | 1088 | B.B.C ENTERPRISE | 338.67 | 178.42 | 52.68 | 60
1741 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Additional Laying distribution system at Chakmanohar mouza under Murgaberia PWSS of Bagnan-I Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 3883/HD | 05/09/2024 | 135 | MANIRUL ISLAM | 17.29 | 0 | 0 | 100
1742 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0.87 | 100 | 100
1743 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Construction of boundary wall & Land Development at 2nd TW Site Murgaberia PWSS scheme under Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1235/HD | 05/03/2025 | 90 | M/S ARPAN ENTERPRISE | 11.14 | 0 | 0 | 100
1744 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.85 | 0 | 0 | 0
1745 | HOWRAH | Electrical | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Quotation for new service connection for Murgaberia water supply scheme, Ph No- III, in the district Howrah under Electrical Division, PHE Dte. (SM/11007 ) Reference Id- 107155669, Application no- 1008738120 |  | 09/09/2025 | 0 | WBSEDCL | 4.32 | 0 | 0 | 0
1746 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Work Order for Laying Distribution System(UPVC & DI) & providing Functional Household Tap Connection (FHTC) (Part-2 , Mouza-Nahala(56)) & Interconnection for 2nd TW and 1st Tube well (HW site) of Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Nahala(56) | 1949/HD | 10/05/2023 | 967 | JAI BHARAT COMMERCIAL CORPORATION | 63.31 | 25.68 | 40.56 | 100
1747 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. , SM/11007 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
1748 | HOWRAH | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Preparation of DPR with Route Survey for new piped water supply scheme of Samanti PWSS Under Panchla Block of Howrah Sadar Sub-Division PHE Dte. | 1947/HD | 20/09/2022 | 30 | STEELCONC AND ASSOCIATES | 3.98 | 3.98 | 100 | 0
1749 | HOWRAH | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Material Requisition To Resource Division | 446/HD | 06/02/2023 | 0 | Resource Division | 307.14 | 0 | 0 | 0
1750 | HOWRAH | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Samanti PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 311/HD | 20/01/2023 | 30 | ZEOLITE FRESH INDIA | 34.42 | 34.11 | 100 | 100
1751 | HOWRAH | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 42.29 | 0 | 0 | 0
1752 | HOWRAH | Electrical | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Quotation money deposition for new service connection at Samanti PWSS P.H No- III , Dist-Howrah under ED PHED. Application No.-1007542321 dated- 17/02/2024 Ref. ID.- 106478203 | 797 | 23/02/2024 | 0 | WBSEDCL | 3.59 | 0 | 0 | 0
1753 | HOWRAH | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Work Order for Construction of Pump House, Boundary Wall,700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/6/2012) including Soil Investigation, Rising Main , Laying Distribution Pipeline & Provinding FHTC (6865 nos) For Samanti PWSS at Panchla Block under Howrah Sadar sub Division of Howrah Division, P. H. E. DTE. | 2500/HD | 30/11/2022 | 1085 | M/S S.S. ENTERPRISE | 789.11 | 433.49 | 54.93 | 40
1754 | HOWRAH | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Additional Laying Distribution Pipeline & Adopting 2 nos Jack Pushing of 700 mm Dia M.S pipe as Casing to Cross Water carrier Pipe(Between Node Point 198-200 & 53-200 of LDS drawing) on Ranihati-Amta Road of Samanti PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte. (SM/12562) | 3106/HD | 08/07/2024 | 450 | M/S S.S. ENTERPRISE | 459.55 | 228.52 | 49.73 | 65
1755 | HOWRAH | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Sinking 2nos. 300 X 200 mm dia and 230 m deep tube well drilling by direct rotary method with 200 mm. dia. PVC. strainer of 30m. length having 300 mm dia. 45m. long PVC housing pipe & 200 mm dia. 155m. long well pipe alongwith 3m blank pipe all complete including cost of materials for Samanti PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 2574/HD | 02/06/2025 | 180 | G.T.AGRO CENTRE | 36.04 | 0 | 0 | 0
1756 | HOWRAH | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Panchla Block of Howrah Sadar Sub Division under Howrah Division PHE Dte. | 1207/HD | 11/03/2024 | 15 | M/S SUPROVAT GHOSH | 1.54 | 1.31 | 100 | 100
1757 | HOWRAH | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Special repairing work for restoration of damage pavement caused by laying of pipe line from Node section 54 to 200 for the 4.05 km (PMGSY/PWD) road at Samanti PWSS under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte | 4200/HD | 27/09/2024 | 120 | WALL FORT INDIA | 59.86 | 0 | 0 | 100
1758 | HOWRAH | Electrical | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Samanti water supply scheme, T.W. No.- I, II, III & IV, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 3520/ED | 30/12/2022 | 1260 | R.N.S. TRADING | 43.41 | 0 | 0 | 50
1759 | HOWRAH | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4816/HD | 19/11/2024 | 510 | TECH VISION | 12.48 | 5.39 | 177.9 | 78
1760 | HOWRAH | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. , SM/12562 | New | Supplying,fitting,fixing and erecting of Display Board at Banharishpur PWSS [SM/11723], Jujarsah PWSS [SM/10146], Samanti PWSS [SM/12562] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 229/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
1761 | HOWRAH | Howrah Division | Baniara PWSS with provision of FHTC connection , SM/11722 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Baniara PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | 81/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.86 | 3.86 | 100 | 100
1762 | HOWRAH | Howrah Division | Baniara PWSS with provision of FHTC connection , SM/11722 | New | Material Requisition To Resource Division | 1748/HD | 25/04/2023 | 0 | Resource Division | 28.1 | 0 | 0 | 0
1763 | HOWRAH | Electrical | Baniara PWSS with provision of FHTC connection , SM/11722 | New | Quotation Bill for New Service Connection at Baniyara W/S. Sch. TW-I & II | 256,257 | 05/09/2023 | 0 | WBSEDCL | 23.59 | 0 | 0 | 0
1764 | HOWRAH | Electrical | Baniara PWSS with provision of FHTC connection , SM/11722 | New | Quotation Bill for New Service Connection at Baniyara W/S. Sch. TW-I | 383 | 25/10/2023 | 0 | WBSEDCL | 3.52 | 0 | 0 | 0
1765 | HOWRAH | Electrical | Baniara PWSS with provision of FHTC connection , SM/11722 | New | Quotation Bill for for New Service Connection at Baniyara Porel W/S. Sch. TW-I | 429 | 17/11/2023 | 0 | WBSEDCL | 0.73 | 0 | 0 | 0
1766 | HOWRAH | Howrah Division | Baniara PWSS with provision of FHTC connection , SM/11722 | New | Work Order for Sinking of 3 (Three) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Baniara PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 170/HD | 13/01/2023 | 630 | ACME CONSTRUCTION | 38.56 | 28.8 | 70.13 | 60
1767 | HOWRAH | Howrah Division | Baniara PWSS with provision of FHTC connection , SM/11722 | New | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 13.68 | 0 | 0 | 0
1768 | HOWRAH | Electrical | Baniara PWSS with provision of FHTC connection , SM/11722 | New | Quotation money deposition for new service connection at Baniara w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008236708 Reference ID- 106843119 SM Code- 11722 | 632 | 18/12/2024 | 0 | WBSEDCL | 19.17 | 0 | 0 | 0
1769 | HOWRAH | Electrical | Baniara PWSS with provision of FHTC connection , SM/11722 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniara water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 1996/ED | 19/05/2023 | 1170 | SANKAR PRASAD DUTTA & CO. | 35.9 | 22.74 | 63.37 | 60
1770 | HOWRAH | Howrah Division | Baniara PWSS with provision of FHTC connection , SM/11722 | New | Dhulagarh Domjur via Begri Road from 2.6 km to 6.341 km, Restoration work of PHE cutting for laying pipe line under Howrah Highway Division in the District of Howrah. | BP-2024-25-531 | 22/01/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 98.16 | 0 | 0 | 0
1771 | HOWRAH | Howrah Division | Baniara PWSS with provision of FHTC connection , SM/11722 | New | Work Order for Construction of Pump House, Boundary Wall,450 cum Capacity of 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Rising Main, Laying Distribution Pipeline & Providing FHTC (2221 nos) For Augmentation of Baniara PWSS at Domjur Block under Howrah Sadar sub Division of Howrah Division , P. H. E. DTE. | 2630/HD | 08/12/2022 | 1260 | UNIQUE AGENCY | 563.14 | 307.41 | 54.59 | 50
1772 | HOWRAH | Howrah Division | Baniara PWSS with provision of FHTC connection , SM/11722 | New | Supplying,fitting,fixing and erecting of Display Board at Domjur (Zone -II) Uttar Jhapardaha PWSS [SM/17175], Baniara PWSS [SM/11722], Makardaha PWSS [SM/11159] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 222-A/HSSD | 25/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
1773 | HOWRAH | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Material Requisition To Resource Division | 421/HD | 03/02/2023 | 0 | Resource Division | 1.84 | 0 | 0 | 0
1774 | HOWRAH | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Material Requisition To Resource Division | 2830/HD | 04/08/2023 | 0 | Resource Division | 21.67 | 0 | 0 | 0
1775 | HOWRAH | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Material Requisition To Resource Division | 3217/HD | 05/09/2023 | 0 | Resource Division | 25.95 | 0 | 0 | 0
1776 | HOWRAH | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sitapur PWSS of RWS Howrah Sub-Division under Howrah Division, P. H. E. Dte. | 2548/HD | 02/12/2022 | 45 | MUNSHI ENTERPRISE | 36.53 | 31.35 | 100 | 90
1777 | HOWRAH | Electrical | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Quotation Bill for New Service Connection at Sitapur W/S. Sch. PH-II | 590 | 29/12/2023 | 0 | WBSEDCL | 7.22 | 0 | 0 | 0
1778 | HOWRAH | Electrical | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Quotation Bill for New Service Connection at Sitapur W/S. Sch. PH-I | 591 | 29/12/2023 | 0 | WBSEDCL | 6.37 | 0 | 0 | 0
1779 | HOWRAH | Electrical | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sitapur water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 3523/ED | 30/12/2022 | 1006 | DIPALI CONSTRUCTION | 21.37 | 17.74 | 83 | 60
1780 | HOWRAH | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Work Order for Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (1759 nos) for Sitapur PWSS of Udaynarayanpur Block under Howrah Division, PHE Dte. | 380/HD | 01/02/2023 | 905 | GUPTA ENTERPRISE | 566.63 | 173.53 | 30.62 | 35
1781 | HOWRAH | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site of SITAPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | 2853/HD | 21/06/2024 | 456 | K.N ENTERPRISE | 78.61 | 0 | 0 | 15
1782 | HOWRAH | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Rising Main & Inter Connection with both tube wells of SITAPUR PWSS in Udaynarayanpur Block under Howrah Division, PHE Dte. | 2279/HD | 07/05/2025 | 30 | GUPTA ENTERPRISE | 9.41 | 0 | 0 | 0
1783 | HOWRAH | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Additional Laying of Distribution Pipe Lines & Functional Household Tap Connection(FHTC) for leftout area of SITAPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | 860/HD | 07/02/2025 | 150 | GUPTA ENTERPRISE | 92.73 | 0 | 0 | 0
1784 | HOWRAH | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Sitapur W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 2808/HD | 21/12/2022 | 840 | APEX ENGINEERING | 8.51 | 0 | 0 | 100
1785 | HOWRAH | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Work order for construction of Pump House ( 5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Sitapur W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 166/HD | 13/01/2023 | 840 | APEX ENGINEERING | 8.52 | 0 | 0 | 100
1786 | HOWRAH | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. , SM/11853 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4813/HD | 19/11/2024 | 510 | HORIZEN | 13.59 | 0.78 | 99.99 | 70
1787 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Rampur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 2148/HD | 01/12/2021 | 15 | APEX ENGINEERING | 3.17 | 6.35 | 100 | 0
1788 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Material Requisition To Resource Division | 2113/HD | 09/11/2022 | 0 | Resource Division | 10.38 | 0 | 0 | 0
1789 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site at Rampur w/s scheme at Udaynarayanpur Block under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | 347/AE/USD | 22/08/2022 | 45 | S RAHA ENTERPRISE | 3.5 | 3.49 | 99.62 | 0
1790 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Work Order for Repairing of OHR including land development of Rampur PWSS scheme in Udayanarayanpur Block, under Howrah Division P.H.E. Dte. Dte. | 790/H.D | 27/02/2023 | 30 | MAITY CONSTRUCTIONS | 6.6 | 6.24 | 100 | 100
1791 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Rampur Water Supply Scheme in Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) (Section-A) | 1853/HD | 09/09/2022 | 60 | DEV DAS SHAW | 144.42 | 141.01 | 100 | 40
1792 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Work order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Rampur Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-D) | 225/RWS | 01/09/2022 | 30 | MAITY CONSTRUCTIONS | 4.75 | 4.38 | 100 | 100
1793 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Rampur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) | 1711/HD | 24/08/2022 | 30 | NANDY UDYOG | 9.36 | 7.59 | 100 | 50
1794 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Rampur Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-E) | 226 / RWS | 01/09/2022 | 30 | MAITY CONSTRUCTIONS | 4.75 | 4.38 | 100 | 100
1795 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Work Order for Laying Additional Distribution Pipe Lines With Allied Works of leftout area for RAMPUR Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte.(Part-A) | 1867/HD | 03/05/2023 | 60 | DEV DAS SHAW | 26.22 | 26.17 | 100 | 100
1796 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Work Order for Laying Additional Distribution Pipe Lines With Allied Works of leftout area for RAMPUR Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte.(Part-B) | 1933/HD | 10/05/2023 | 60 | CONSTRUCTION CORNER | 29.82 | 29.55 | 100 | 50
1797 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Rampur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte.(Part-B) (Section-A) | 1909/HD | 15/09/2022 | 45 | CONSTRUCTION CORNER | 114.82 | 114.14 | 100 | 35
1798 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Material Requisition To Resource Division | 3884/HD | 05/09/2024 | 0 | Resource Division | 7.39 | 0 | 0 | 0
1799 | HOWRAH | Howrah Division | Rampur PWSS , SM/11168 | Augmentation | Additional Laying of Distribution Pipe Lines and Providing Functional Household Tap Connection(FHTC) for leftout area of RAMPUR Water Supply Scheme in Udaynarayanpur Block under Howrah Division, PHE Dte. | 2830/HD | 20/06/2024 | 263 | AMBIAN INFRASTRUCTURE | 29.75 | 0 | 0 | 70
1800 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme , SM/06716 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-G) (for Khosalpur Mouza(Part) | 1508/HD | 04/11/2020 | 30 | N. G ENGINEERING | 29.1 | 0 | 0 | 0
1801 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme , SM/06716 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-H) (for Khosalpur Mouza(Part) | 1509/HD | 04/11/2020 | 30 | N. G ENGINEERING | 29.1 | 0 | 0 | 0
1802 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme , SM/06716 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-F) (for Kotalpara Mouza & Khosalpur Mouza(Part) | 1507/HD | 04/11/2020 | 30 | MONDAL PRECISION PVT. LTD. | 28.5 | 0 | 0 | 0
1803 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme , SM/06716 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | 844330 | 17/03/2021 | 0 | M/S ASHIRBAD (INDIA) | 27.58 | 0 | 0 | 0
1804 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme , SM/06716 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | W/278 | 06/09/2021 | 0 | M/S ASHIRBAD (INDIA) | 27.77 | 0 | 0 | 0
1805 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme , SM/06716 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | 844328 | 17/03/2021 | 0 | N. G ENGINEERING | 28.31 | 0 | 0 | 0
1806 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme , SM/06716 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | W/277 | 06/09/2021 | 0 | JAHANGIR ALAM | 16.09 | 0 | 0 | 0
1807 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme , SM/06716 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-F) (for Kotalpara Mouza & Khosalpur Mouza(Part) | W/602 | 28/12/2021 | 0 | MONDAL PRECISION PVT. LTD. | 5.16 | 0 | 0 | 0
1808 | HOWRAH | Howrah Division | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 10.53 | 0 | 0 | 0
1809 | HOWRAH | Howrah Division | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Sial Danga PWSS (Mouza-Sial Danga, Kumarpur, & Chak Patmura) of Jagatballavpur Block under Howrah Division PHE Dte. | 1018/HD | 05/05/2022 | 15 | ENVIROTECH SOLUTIONS | 3.04 | 3.04 | 100 | 0
1810 | HOWRAH | Howrah Division | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Work Order for Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection, soil investigation & foundation design of Sealdanga PWSS at J.B.PUR Block of Howrah District under Howrah Division, P.H.E. Dte. | 1736/HD | 25/04/2023 | 335 | BISWAJIT BAG | 110.36 | 0 | 0 | 0
1811 | HOWRAH | Howrah Division | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Work Order for Laying Distribution Pipeline of Sealdanga PWSS at J.B.PUR Block of Howrah District under Howrah Division, P. H. E. Dte.(part-3) | 1546/HD | 04/04/2023 | 120 | BUILT INDIA | 93.16 | 32.91 | 35.32 | 35
1812 | HOWRAH | Electrical | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sealdanga water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 1705/ED | 18/04/2023 | 90 | PADMA ENGINEERING CO. | 21.49 | 0 | 0 | 0
1813 | HOWRAH | Howrah Division | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Material Requisition To Resource Division | 446/HD | 06/02/2023 | 0 | Resource Division | 14.14 | 0 | 0 | 0
1814 | HOWRAH | Howrah Division | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Work Order for Laying Distribution Pipeline & Providing Functional Household Tap Connection((part-2), 550 nos of Sealdanga PWSS at J.B.PUR Blockof Howrah District under Howrah Division, P. H. E. Dte. | 1545/HD | 04/04/2023 | 1200 | M/S ASHIRBAD (INDIA) | 86.98 | 14.3 | 16.44 | 15
1815 | HOWRAH | Howrah Division | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Construction of 2 nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at Head Work Site& other tubewell site, Construction of Boundary Wall at 1st Tube Well Site, Construction of Boundary Wall at 2nd Tube Well Site, Rising Main Pipeline Work From 2nd Pump House to 1st Pump House & OHR Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) (550 Nos) For Sealdanga PWSS at J.B.PUR Blockof Howrah District under Howrah Division, P. H. E. Dte. | 2736/HD | 26/07/2023 | 1066 | SWASTIK ENTERPRISE | 123.64 | 0 | 0 | 20
1816 | HOWRAH | Howrah Division | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sealdanga PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P. H. E. Dte. | 1001/H.D | 13/03/2023 | 780 | R CONSTRUCTION | 25.64 | 0 | 0 | 100
1817 | HOWRAH | Howrah Division | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Material Requisition To Resource Division | 2019/HD | 24/04/2025 | 0 | Resource Division | 1.48 | 0 | 0 | 0
1818 | HOWRAH | Electrical | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Quotation money deposition for new service connection at Sealdanga w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008562054 Reference ID- 107054560 SM Code- 14866 | 42151 | 30/07/2025 | 0 | WBSEDCL | 24.72 | 0 | 0 | 0
1819 | HOWRAH | Electrical | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Quotation money deposition for new service connection at Sealdanga w/s scheme, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008295853 Reference ID- 106880627 SM Code- 14866 | 692 | 31/01/2025 | 0 | WBSEDCL | 14.99 | 0 | 0 | 0
1820 | HOWRAH | Howrah Division | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Construction of approach road and land Development at OHR site for Sealdanga PWSS at Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 3131/HD | 14/07/2025 | 179 | M/S SRIKANTA PATRA | 77.22 | 0 | 0 | 0
1821 | HOWRAH | Howrah Division | Sealdanga Piped Water Supply Scheme , SM/14866 | New | Supplying,fitting,fixing and erecting of Display Board at Sealdanga PWSS [SM/14866], Maju PWSS [SM/10035], Islampur PWSS [SM/09428] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 231/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
1822 | HOWRAH | Howrah Division | Charkata Pukuria Piped Water Supply Scheme , SM/15290 | New | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | 2155/H.D | 07/06/2023 | 1021 | MONDAL PRECISION PVT. LTD. | 330.32 | 0 | 0 | 80
1823 | HOWRAH | Howrah Division | Charkata Pukuria Piped Water Supply Scheme , SM/15290 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 0.12 | 0 | 0 | 0
1824 | HOWRAH | Howrah Division | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 21.73 | 0 | 0 | 0
1825 | HOWRAH | Howrah Division | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | Material Requisition To Resource Division | 593/HD | 13/02/2023 | 0 | Resource Division | 88.98 | 0 | 0 | 0
1826 | HOWRAH | Electrical | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | new service connection | 127 | 20/07/2023 | 0 | WBSEDCL | 2.85 | 0 | 0 | 0
1827 | HOWRAH | Electrical | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | Quotation money deposition for new service connection at P.H No.-III of Bhandardah Pwss , Dist- howrah under ED PHED. App. No.-1007763810 SM/14197 | 120 | 17/05/2024 | 0 | WBSEDCL | 6.68 | 0 | 0 | 0
1828 | HOWRAH | Howrah Division | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | Restoration Work of Bituminous Road and Shoulder with allied work of Makardah Bazar to Begri Road from 0.00 Kmp to 1.90 Kmp (Due to Cutting for PHE water line) under Howrah Division in th e dist of Howrah during the year 2024-25. | BP-2024-25-496 | 27/11/2024 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 9.52 | 0 | 0 | 0
1829 | HOWRAH | Howrah Division | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | Work Order for Laying distribution pipe line, Providing FHTC , Repairing of RCC Over Head Reservoir of capacity 350cum with allied work including supply of all labour & materials for Augmentation Of BHANDARDAH Water Supply Scheme at Domjur Block under Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 998/HD | 13/03/2023 | 1110 | P B ENTERPRISE | 754.4 | 487.37 | 64.6 | 80
1830 | HOWRAH | Howrah Division | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | Work Order for Sinking of 3 (Three) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bhandardaha PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 603/HD | 16/02/2023 | 45 | M DHARA AND BROTHERS | 38.37 | 25.02 | 65.2 | 100
1831 | HOWRAH | Howrah Division | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | Permanent restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road "Ankurhati-Purba Noapara Mukherjeepara" of Domjur Block, Howrah under W.B.S.R.D.A. Howrah Division-I. (Package No WB/09/52). |  | 28/04/2025 | 0 | WBSRDA | 22.46 | 0 | 0 | 0
1832 | HOWRAH | Howrah Division | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | Domjur - Andul Road from 0.00 Km to 4.129 Km, Restoration work of PHE Cutting for laying pipe line under Howrah Highway Division in the district of Howrah (Dakshin Jhapardaha PWSS Zone-II, Dakshin Jhapardaha PWSS Zone-I, Bhandardaha PWSS, Bipranoapara PWSS). |  | 28/03/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 101.31 | 0 | 0 | 0
1833 | HOWRAH | Howrah Division | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | Restoration work of Bituminous Road and Shoulder with allied work of Makardah Bazar to Begri Road from 0.00 Kmp to 0.53 Kmp (Due to cutting for PHE water line - 2nd Phase) under Howrah Division in the District of Howrah during the year 2025-26. |  | 12/06/2025 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 8.01 | 0 | 0 | 0
1834 | HOWRAH | Howrah Division | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | Supplying,fitting,fixing and erecting of Display Board at Domjur Zone -VIII PWSS [SM/14155], Rudrapur PWSS [SM/14515], Bhandardaha PWSS [SM/14197] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 224/HSSD | 27/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
1835 | HOWRAH | Electrical | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhandardah water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 926/ED | 22/02/2023 | 900 | S.P. CONSTRUCTION | 34.3 | 22.21 | 65.83 | 30
1836 | HOWRAH | Howrah Division | Bhandardah PWSS with provision of FHTC connection , SM/14197 | New | Restoration Work of Bituminous Road and Shoulder with allied work of Makardah Bazar to Begri Road from 0.00 Kmp to 1.90 Kmp (Due to Cutting for PHE water line) under Howrah Division in the dist of Howrah during the year 2024-25. |  | 06/01/2026 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 9.45 | 0 | 0 | 0
1837 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting of Amragori. | W/97 | 19/07/2021 | 0 | TANMOY ROY CHOUDHURY | 21.4 | 0 | 0 | 0
1838 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting of Amragori. | W/95 | 19/07/2021 | 0 | MAA TARA CONSTRUCTION | 17.11 | 0 | 0 | 0
1839 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting of Amragori. | W/95 | 19/07/2021 | 0 | RANA ENTERPRISE | 10.33 | 0 | 0 | 0
1840 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting of Amragori. |  | 24/03/2021 | 0 | UNIQUE AGENCY | 21.75 | 0 | 0 | 0
1841 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting of Amragori. | W/386 | 19/07/2021 | 0 | GHOSH ENTERPRISE. | 30.3 | 0 | 0 | 0
1842 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting of Amragori. |  | 24/03/2021 | 0 | TANMOY ROY CHOUDHURY | 22.54 | 0 | 0 | 0
1843 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting of providing Functional Household Tap Connection from existing distribution system of Amragori & adj Mouzas piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) | BP-2021-22-164 | 07/10/2021 | 0 | TANMOY ROY CHOUDHURY | 11.83 | 0 | 0 | 0
1844 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Special maintenance of pipeline at Amragori Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Phase-I) | 1820/HD | 17/09/2021 | 30 | UNIQUE AGENCY | 2.27 | 2.1 | 92.49 | 0
1845 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) to Schools, AWC's & Public Institution of Amragori, Nakubar, Sarda, Tajpur, Joypur, Narit, Kanpur, Paschim Gazipur, Balichack, Uttar Pirpur W/S scheme under under Howrah Division, PHE Dte. | 2175/HD | 01/12/2021 | 30 | JOY CHANDI CONSTRUCTION | 4.28 | 4.14 | 96.77 | 0
1846 | HOWRAH | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | FUEL CHARGES FOR CAR NO. WB-05-2798, WB-04H-6870 & WB-25H-5187. | 789/CDD | 23/08/2022 | 7 | MIRA SERVICE STATION | 0.65 | 0 | 0 | 0
1847 | HOWRAH | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR AMRAGORI PWSS, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 299/CMSD-I (D) | 08/07/2022 | 15 | DIPALI CONSTUCTION | 3.11 | 0.96 | 100 | 0
1848 | HOWRAH | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT SARDA W/S SCH, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 233/CMSD-I (D) | 20/06/2022 | 15 | DIPALI CONSTUCTION | 4.76 | 4.27 | 100 | 0
1849 | HOWRAH | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT SARDA W/S SCH, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | 232/CMSD-I (D) | 20/06/2022 | 15 | DIPALI CONSTUCTION | 3.44 | 3.27 | 100 | 0
1850 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Amragori W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) | BP-2021-22-422 | 23/03/2022 | 0 | RANA ENTERPRISE | 2.3 | 0 | 0 | 0
1851 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | WBSEDCL |  | 13/09/2022 | 0 | WBSEDCL | 3.02 | 0 | 0 | 0
1852 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Amragori W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) | BP-2021-22-422 | 06/04/2022 | 0 | RANA ENTERPRISE | 2.3 | 0 | 0 | 0
1853 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-B) [Amragari MOUZA PART & Rautara MOUZA PART] | BP-2021-22-321 | 18/02/2022 | 0 | UNIQUE AGENCY | 4.01 | 0 | 0 | 0
1854 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Amragori W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) | BP-2021-22-421 | 21/03/2022 | 0 | MAA TARA CONSTRUCTION | 2.05 | 0 | 0 | 0
1855 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Alternative laying of pipeline due to construction of PMGSY road for Amragori w/s scheme (from Danda's Misti's shop to Chacksalika Vimtala) at section (100-101-101B-101C-103-105-107-111-113-118-120-121-127-128-128B-135-136-141) under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | BP-2021-22-322 | 18/02/2022 | 0 | UNIQUE AGENCY | 3.38 | 0 | 0 | 0
1856 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-C) [Rautara MOUZA PART] | 157/HD | 19/01/2021 | 30 | GHOSH ENTERPRISE. | 42.22 | 11.05 | 200 | 0
1857 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-B) [Amragari MOUZA PART & Rautara MOUZA PART] | 156/HD | 19/01/2021 | 30 | UNIQUE AGENCY | 28.9 | 43.49 | 200 | 0
1858 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-E) [Kakrol MOUZA PART] | 159/HD | 19/01/2021 | 30 | TANMOY ROY CHOUDHURY | 38.98 | 80.93 | 200 | 0
1859 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block , SM/07467 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-F) [Kakrol MOUZA PART] | 160/HD | 19/01/2021 | 30 | DEV DAS SHAW | 39.02 | 72.73 | 200 | 0
1860 | HOWRAH | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. , SM/17175 | New | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 22.24 | 0 | 0 | 0
1861 | HOWRAH | Electrical | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. , SM/17175 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-II) Uttar Jhapardaha water supply scheme, T.W. No. I, II, III & IV, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 1801/ED | 24/04/2023 | 90 | DEY ENTERPRISE | 42.99 | 0 | 0 | 0
1862 | HOWRAH | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. , SM/17175 | New | Material Requisition To Resource Division | 1748/HD | 25/04/2023 | 0 | Resource Division | 163.76 | 0 | 0 | 0
1863 | HOWRAH | Electrical | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. , SM/17175 | New | Quotation Bill for New Service Connection at Uttar Jhapordah W/S. Sch. Z-II, PH-I | 438 | 23/11/2023 | 0 | WBSEDCL | 3.72 | 0 | 0 | 0
1864 | HOWRAH | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. , SM/17175 | New | Work Order for Construction of 4 Nos Pump House (5.40m x 3.60m) at 1st 2nd,3rd &4th Tube Well Site, Construction of Boundary Wall at 1st Tube Well Site, 3 nos Boundary Wall at 2nd , 3rd & 4th Tube Well SiteConstruction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Rising Main Pipeline Work From 3rd Pump House, 2nd Pump House to 1st Pump House & OHR, Laying Distribution of Pipeline & Providing FHTC (Functional Household Tap Connection) for Augmentation of Domjur (Zone-II) Uttar Jhapardaha PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | 1831/HD | 02/05/2023 | 784 | PRAVAT SARKAR | 607.14 | 233.33 | 38.43 | 10
1865 | HOWRAH | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. , SM/17175 | New | Work Order for Sinking of 7 (Seven) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone 1) Mahisnala PWSS & Domjur (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 1530/HD | 04/04/2023 | 45 | BALAJI UDDYOG | 89.53 | 0 | 0 | 70
1866 | HOWRAH | Electrical | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. , SM/17175 | New | Quotation money deposition for new service connection at Uttar Jhapordah pwss, T.W No.-I , Dist-Howrah under ED PHED. App. No.-1007533769 Ref. ID.: 106472906 SM/17175 | 813 | 28/02/2024 | 0 | WBSEDCL | 6.94 | 0 | 0 | 0
1867 | HOWRAH | Electrical | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. , SM/17175 | New | Quotation money deposition for new service connection at UTTAR JHAPORDAH pwss, T.W No.-III Dist-Howrah, under PHED. App. No.-1007553536 Ref. ID.-106486515 SM/17175 | 816 | 01/03/2024 | 0 | WBSEDCL | 15.45 | 0 | 0 | 0
1868 | HOWRAH | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. , SM/17175 | New | Land Development Works of Uttar Jhapardaha (Zone-2) PWSS 1st, 2nd, 3rd & 4th Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | 975/HD | 19/02/2025 | 45 | SONAR BANGLA ENTERPRISE | 15.11 | 0 | 0 | 0
1869 | HOWRAH | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. , SM/17175 | New | Pernamnent restoration of damaged pavement caused by laying of Public Helath Engineering Directorate's pipe line for the PMGSY Road 57A Bus stand to Narna more of Domjur Block, Howrah under WBSRDA HOwrah Division -I (Package No. WB-09-01) under Domjur Zone - II Uttar Jhapardaha PWSS (SM Code - SM/17175) |  | 12/09/2025 | 0 | WBSRDA-I | 20.05 | 0 | 0 | 0
1870 | HOWRAH | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. , SM/17175 | New | Supplying,fitting,fixing and erecting of Display Board at Domjur (Zone -II) Uttar Jhapardaha PWSS [SM/17175], Baniara PWSS [SM/11722], Makardaha PWSS [SM/11159] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 222-A/HSSD | 25/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
1871 | HOWRAH | Electrical | Source Augmentation of Laskarpur Piped Water Supply Scheme , SM/18842 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Laskarpur water supply scheme, T.W. No.- IV, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 3879/ED | 06/10/2023 | 90 | GHOSH AND GHOSH | 10.74 | 0 | 0 | 0
1872 | HOWRAH | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme , SM/18842 | Augmentation | Connection with 4th Tubewell to existing Laying Distribution Pipeline & Allied work for Laskarpur PWSS at JBpur Block of Howrah Sadar Sub Division under Howrah Division,P. H. E. Dte. | 643/HSSD | 26/06/2024 | 30 | ADRIJA ENTERPRISE | 4.9 | 4.88 | 100 | 100
1873 | HOWRAH | Electrical | Source Augmentation of Laskarpur Piped Water Supply Scheme , SM/18842 | Augmentation | Quotation money deposition for new service connection at Laskarpur w/s scheme, Zone- T.W. No.-VI, Dist.-Howrah under PHE Dte. Application No- 1007900745 Reference ID- 106654843 SM Code- 18842 | 332 | 30/07/2024 | 0 | WBSEDCL | 23.11 | 0 | 0 | 0
1874 | HOWRAH | Electrical | Source Augmentation of Laskarpur Piped Water Supply Scheme , SM/18842 | Augmentation | Quotation money deposition for new service connection at Laskarpur w/s scheme, T.W. No.-V, Dist.-Howrah under PHE Dte. Application No- 1007772477 Reference ID- 106595815 SM Code- 18842 | 269 | 08/07/2024 | 0 | WBSEDCL | 19.44 | 0 | 0 | 0
1875 | HOWRAH | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme , SM/18842 | Augmentation | Construction of approach road and land Development of 4th tubewell site, Construction of 1(one) nos. boundary wall, Construction of 4th Pump House (5.40m x 3.60m) for Laskarpur PWSS at Jagatballavpur at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 892/HD | 11/02/2025 | 45 | ADRIJA ENTERPRISE | 13.66 | 0 | 0 | 0
1876 | HOWRAH | Electrical | Source Augmentation of Laskarpur Piped Water Supply Scheme , SM/18842 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Laskarpur Piped Water Supply Scheme Block- Jagatballavpur District- Howrah under JJM Program under Electrical Division PHE Dte. | 4534/ED | 23/11/2023 | 540 | DIPALI CONSTRUCTION | 21.49 | 15.92 | 74.13 | 30
1877 | HOWRAH | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme , SM/18842 | Augmentation | Reconnection of FHTC& Allied Works at Laskarpur PWSS at Jagatballavpur Block under Howrah sadar Sub-Division of Howrah Division PHE Dte. | 158/HSSD | 12/02/2024 | 60 | MANIRUL ISLAM | 0.94 | 0 | 0 | 100
1878 | HOWRAH | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme , SM/18842 | Augmentation | Preparation of DPR for Source Augmentation for Laskarpur PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. | 817/HSSD | 07/08/2024 | 15 | APEX ENGINEERING | 0.77 | 0 | 0 | 0
1879 | HOWRAH | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme , SM/18842 | Augmentation | Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method, connection with distribution system and Reconnection of FHTC & Allied Works, Construction of 2 (Two) Nos.Pump House (5.40m x 3.60m), Construction of 2 (Two) nos. Boundary Wall at Laskarpur Piped Water Supply Scheme Under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 966/HD | 28/02/2024 | 630 | M/S SUMAN SHIL | 102.48 | 27.44 | 26.78 | 80
1880 | HOWRAH | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme , SM/18842 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Source Augmentation of Gobindapur Piped Water Supply Scheme [SM/18843],Source Augmentation of Laskarpur Piped Water Supply Scheme [SM/18842], and Source Augmentation of Majhu Khetra Water Supply Scheme [SM/18841] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 233-A/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
1881 | HOWRAH | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme , SM/18842 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Gobindapur PWSS [SM/18843], Laskarpur PWSS [SM/18842], and Majhu Khetra PWSS [SM/18841] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 232/HSSD | 28/02/2025 | 15 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
1882 | HOWRAH | Electrical | Source Augmentation of Gobindapur Piped Water Supply Scheme , SM/18843 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No.- III, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 3880/ED | 06/10/2023 | 90 | ANIK & CO. | 10.75 | 0 | 0 | 40
1883 | HOWRAH | Electrical | Source Augmentation of Gobindapur Piped Water Supply Scheme , SM/18843 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Gobindapur Piped Water Supply Scheme Block- Jagatballavpur District- Howrah under JJM Program under Electrical Division PHE Dte. | 4535/ED | 23/11/2023 | 90 | P.K. ENGINEERING | 10.74 | 9.03 | 84.09 | 30
1884 | HOWRAH | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme , SM/18843 | Augmentation | Sinking 1No. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with 150mm. dia. PVC. Strainer of 30m. length having 250 mm dia. 60 m. long PVC housing pipe & 150mm dia. 150m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Gobindapur PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 996/HD | 01/03/2024 | 30 | ACME CONSTRUCTION | 14.58 | 13.81 | 100 | 100
1885 | HOWRAH | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme , SM/18843 | Augmentation | Additional Pipline & connection with 3rd Tubewell to existing Laying Distribution Pipeline & Allied work for Gobindapur PWSS at JBpur Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | 644/HSSD | 26/06/2024 | 30 | ADRIJA ENTERPRISE | 5.42 | 5.38 | 100 | 100
1886 | HOWRAH | Electrical | Source Augmentation of Gobindapur Piped Water Supply Scheme , SM/18843 | Augmentation | Quotation money deposition for new service connection at Gobindapur w/s scheme, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1007622411 Reference ID- 106532178 SM Code- 18843 | 54 | 12/04/2024 | 0 | WBSEDCL | 10.89 | 0 | 0 | 0
1887 | HOWRAH | Electrical | Source Augmentation of Gobindapur Piped Water Supply Scheme , SM/18843 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No.- I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 3881/ED | 06/10/2023 | 90 | OSMAN SEKH | 10.75 | 0 | 0 | 60
1888 | HOWRAH | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme , SM/18843 | Augmentation | Construction of approach road and land Development of 3rd tubewell site, Construction of 1(one) nos. boundary wall, Construction of 3rd Pump House (5.40m x 3.60m) for Gobindapur PWSS at Jagatballavpur at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 893/HD | 11/02/2025 | 45 | ADRIJA ENTERPRISE | 13.76 | 0 | 0 | 0
1889 | HOWRAH | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme , SM/18843 | Augmentation | Connection with distribution system and Reconnection of FHTC & allied Works, Construction of 1(One) No Pump House (5.40m x 3.60 m), Construction of 1(One) no Boundary Wall at Gobindapur Piped Water Supply Scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 1000/HD | 01/03/2024 | 300 | LAKSHMI IRON | 59.38 | 37.26 | 55.64 | 10
1890 | HOWRAH | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme , SM/18843 | Augmentation | Reconnection of FHTC& Allied Works at Gabindapur PWSS at Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | 159/HSSD | 12/02/2024 | 60 | MANIRUL ISLAM | 0.92 | 0 | 0 | 100
1891 | HOWRAH | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme , SM/18843 | Augmentation | Sinking 1 no. 250 X 150 mm dia and 240 m Replacement deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30 m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials for Gobindapur PWSS at Jagatballavpur Block under Howrah Sadar Sub-Division under Howrah Division, P.H.E. Dte.. | 2682/HD | 05/06/2025 | 330 | AQUATECH ENGINEERS | 14.53 | 0 | 0 | 100
1892 | HOWRAH | Electrical | Source Augmentaion of kulgacchi Water Supply Scheme , SM/18882 | Augmentation | Quotation Bill for New Service Connection at Kulgachia W/S. Sch. TW-IV | 409 | 09/11/2023 | 0 | WBSEDCL | 4.35 | 0 | 0 | 0
1893 | HOWRAH | Electrical | Source Augmentaion of kulgacchi Water Supply Scheme , SM/18882 | Augmentation | Quotation Bill for New Service Connection at Kulgachia W/S. Sch. TW-III | 421 | 10/11/2023 | 0 | WBSEDCL | 29.37 | 0 | 0 | 0
1894 | HOWRAH | Electrical | Source Augmentaion of kulgacchi Water Supply Scheme , SM/18882 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentaion of Kulgacchi Water Supply Scheme Block- Uluberia - I District- Howrah under JJM Program under Electrical Division PHE Dte. | 4530/ED | 23/11/2023 | 90 | D. K. ELECTRIC | 32.23 | 20.93 | 64.94 | 35
1895 | HOWRAH | Howrah Division | Source Augmentaion of kulgacchi Water Supply Scheme , SM/18882 | Augmentation | Re-Laying distribution system (HDPE & DI) & Shifting HouseHold Connection(FHTC) at Kulgachi PWSS of Uluberia -I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 3240/AE/USD | 12/03/2024 | 45 | PRADIP KUMAR JATI | 28.64 | 28.5 | 100 | 100
1896 | HOWRAH | Howrah Division | Source Augmentaion of kulgacchi Water Supply Scheme , SM/18882 | Augmentation | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Uluberia-I block of Uluberia Sub Division under Howrah Division, P.H.E. Dte. | 1211/HD | 11/03/2024 | 15 | TRIMARV SOLUTIONS PRIVATE LIMITED | 1.85 | 1.85 | 100 | 100
1897 | HOWRAH | Howrah Division | Source Augmentaion of kulgacchi Water Supply Scheme , SM/18882 | Augmentation | Additional Laying of pipeline in addition to providing FHTC Kulgachi PWSS of Uluberia-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 2039/AE/USD | 13/02/2024 | 30 | MA DURGA ENTERPRISE | 6.05 | 6.05 | 100 | 100
1898 | HOWRAH | Howrah Division | Source Augmentaion of kulgacchi Water Supply Scheme , SM/18882 | Augmentation | Sinking of additional 3 (three) Nos. 250 X 150 mm Dia and 250 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete for Kulgachi PWSS of Uluberia-I Block of Howrah Division, P.H.E. Dte. | 2860/HD | 24/06/2024 | 60 | G.T.AGRO CENTRE | 46.21 | 43.4 | 100 | 100
1899 | HOWRAH | Electrical | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. , SM/18747 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniban (Zone-IV) water supply scheme, New Tubewell, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | 3616/ED | 29/08/2023 | 90 | MAA TARA ENTERPRISE. | 10.17 | 0 | 0 | 0
1900 | HOWRAH | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. , SM/18747 | New | Preparation of DPR for new piped water supply scheme of Brindabanpur PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte.(Baniban, Zone-IV) | 323/AE/USD | 16/08/2022 | 45 | APEX ENGINEERING | 3.8 | 3.72 | 100 | 100
1901 | HOWRAH | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. , SM/18747 | New | Material Requisition To Resource Division | 4864/HD | 22/11/2024 | 0 | Resource Division | 7.39 | 0 | 0 | 0
1902 | HOWRAH | Electrical | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. , SM/18747 | New | Quotation money deposition for new service connection at Baniban w/s scheme, Zone- IV, T.W. No.-03, Dist.-Howrah under PHE Dte. Application No- 1007829643 Reference ID- 106621794 SM Code- 18747 | 314 | 22/07/2024 | 0 | WBSEDCL | 8.04 | 0 | 0 | 0
1903 | HOWRAH | Electrical | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. , SM/18747 | New | Quotation money deposition for new service connection at Baniban w/s scheme, Zone- IV, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1007629084 Reference ID- 106535440 SM Code- 18747 | 109 | 09/05/2024 | 0 | WBSEDCL | 3.93 | 0 | 0 | 0
1904 | HOWRAH | Electrical | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. , SM/18747 | New | Deposition of quotation money for new service connection at P.H No.-I of Baniban W/S scheme, Zone-IV, Dist- Howrah under ED PHED. App. No.-1007628595 SM/18747 | 132 | 17/05/2024 | 0 | WBSEDCL | 4.15 | 0 | 0 | 0
1905 | HOWRAH | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. , SM/18747 | New | BANIBAN (Zone-II & IV) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Uluberia-II Block, District:- Howrah [NEW SCHEME] | 4553/HD | 18/12/2023 | 365 | LUKE ENGICON | 1736.09 | 71.73 | 9.09 | 35
1906 | HOWRAH | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. , SM/18747 | New | Continuation order for Hiring of 01 (One) no. (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer, Uluberia Sub-Division, PHE Dte. (for the period from 01.01.2024 to 31.12.2024). Car No.:-WB-135078 In continuation to the order under reference and your application dated 26/12/2023, you are requested to continue the above mentioned 'work in consultation with the Assistant Engineer, Uluberia Sub-Division, PHE Dte. | 4785/HD | 29/12/2023 | 366 | PUTUL TRAVELS | 4.79 | 3.7 | 91.84 | 25
1907 | HOWRAH | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. , SM/18747 | New | Restoration of Black top Road along with alternative laying of DI & HDPE (PE100, PN6) pipes from Basudevpur Bazar to Nurillapara to Bridabanpur Primary School under Baniban (Zone-IV) PWSS under Uluberia Sub-Division of Howrah Division, PHE Dte. (SM/18747) | 2502/HD | 26/05/2025 | 30 | SANJOY GHOSH | 7.65 | 0 | 0 | 100
1908 | HOWRAH | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. , SM/18747 | New | Hiring of 1 (One) no. Luxury Taxi/Maxi cab/Motor cab on daily basis under monthly hiring category for the Assistant Engineer,Uluberia Sub- Division , PHE Dte of the Government of West Bengal (for Twelve months) under Howrah Division,PHEdte. (Period of 365 Days) | 791/AE/USD | 29/11/2023 | 366 | NOBLE ENTERPRISE | 4.81 | 3.56 | 85.41 | 40
1909 | HOWRAH | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. , SM/18747 | New | Continuation order for Hiring of 01 (One) no. (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer, Uluberia Sub-Division, PHE Dte. (for the period from 01.01.2025 to 31.12.2025). Car No.:-WB-135078 In continuation to the order under reference and your application dated 24/12/2023, you are requested to continue the above mentioned 'work in consultation with the Assistant Engineer, Uluberia Sub-Division, PHE Dte. | 5428/HD | 31/12/2024 | 365 | PUTUL TRAVELS | 4.78 | 1.87 | 39.18 | 30
1910 | HOWRAH | Electrical | Ground Water Based Water Supply Scheme For Baniban (Zone-II) and its adjoining areas to Accommodate FHTC in Uluberia-II Block, District - Howrah. , SM/18748 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniban (Zone-II) water supply scheme, T.W. No.- I, II, III & IV, Block: Uluberia-II District- Howrah under Electrical Division, PHE Dte. | 3617/ED | 29/08/2023 | 90 | DEY ENTERPRISE | 45.74 | 0 | 0 | 0
1911 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme For Baniban (Zone-II) and its adjoining areas to Accommodate FHTC in Uluberia-II Block, District - Howrah. , SM/18748 | New | Preparation of DPR for new piped water supply scheme of Kantaberia PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte.(Baniban, Zone-II) | 322/AE/USD | 16/08/2022 | 45 | APEX ENGINEERING | 3.55 | 3.55 | 100 | 100
1912 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme For Baniban (Zone-II) and its adjoining areas to Accommodate FHTC in Uluberia-II Block, District - Howrah. , SM/18748 | New | BANIBAN (Zone-II & IV) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Uluberia-II Block, District:- Howrah [NEW SCHEME] | 4553/HD | 18/12/2023 | 365 | LUKE ENGICON | 1736.09 | 0 | 0 | 35
1913 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Supply Based Piped Water Supply Scheme For Uttar Khariop under Amta-II Block , SM/07465 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Supply Based Piped Water Supply Scheme For Uttar Khariop PWSS under Amta-II Block under Howrah Division, PHE Dte.(No of FHTC to be provided (Approx:- 1711) | 1198/HD | 31/05/2021 | 60 | N. G ENGINEERING | 112.54 | 112.83 | 100 | 0
1914 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Supply Based Piped Water Supply Scheme For Uttar Khariop under Amta-II Block , SM/07465 | Retrofitting | Survey & collection of house hold details through mobile app and geo tagging the same of water tap connection in each house hold from existing distribution system within scheme juridiction in Nakubar, Amragori, Joypur & Uttar Khorip and others Pipe Water Supply Scheme of Uluberia Sub-Division under Howrah Division, PHE Dte. | BP-2022-23-44 | 11/05/2022 | 0 | M/S ASHIRBAD (INDIA) | 4.87 | 0 | 0 | 0
1915 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sital Chak & Bankura Mouza of Sarda piped water supply scheme , SM/06719 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | 84438 | 09/02/2021 | 0 | USHA CONCERN | 26.17 | 0 | 0 | 0
1916 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sital Chak & Bankura Mouza of Sarda piped water supply scheme , SM/06719 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | 844347 | 22/03/2021 | 0 | M/S SARADA UDYOG | 25.7 | 0 | 0 | 0
1917 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sital Chak & Bankura Mouza of Sarda piped water supply scheme , SM/06719 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme | 84433 | 09/02/2021 | 0 | JAHANGIR ALAM | 25.63 | 0 | 0 | 0
1918 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sital Chak & Bankura Mouza of Sarda piped water supply scheme , SM/06719 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-H) (for Sarda Mouza(part) | 1316/HD | 12/10/2020 | 30 | MITHU BUILDERS | 25.87 | 0 | 0 | 0
1919 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sital Chak & Bankura Mouza of Sarda piped water supply scheme , SM/06719 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-I) (for Sarda Mouza(part) | 1317/HD | 12/10/2020 | 30 | MAA TARA CONSTRUCTION | 7.07 | 0 | 0 | 0
1920 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sital Chak & Bankura Mouza of Sarda piped water supply scheme , SM/06719 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-G) (for Sarda Mouza(part) | 1315/HD | 12/10/2020 | 30 | B.M ENTERPRISE | 29.28 | 16 | 196.42 | 0
1921 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) , SM/07009 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) [Tajpur Mouza part] | 1801/HD | 27/11/2020 | 30 | MITHU BUILDERS | 30.95 | 43.7 | 175.97 | 0
1922 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) , SM/07009 | Retrofitting | Work Order for Additional laying of pipeline for retrofitting work for providing Functional Household Tap Connection(FHTC) at Tajpur Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Part-C) (Phase-II) | 1049/HD | 06/05/2022 | 30 | JAHANGIR ALAM | 3.76 | 3.68 | 97.84 | 0
1923 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) , SM/07009 | Retrofitting | Cons of Balance work for boundary wall at HW Site and interconnection between OHR to LDS and rising main of Tajpur | 844332 | 30/03/2022 | 0 | KANIKA CONSTRUCTION | 2.16 | 0 | 0 | 0
1924 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) , SM/07009 | Retrofitting | Cons of approach road of Tajpur W/S Scheme. | 844330 | 29/03/2022 | 0 | PIKASU BOSE | 2.46 | 0 | 0 | 0
1925 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) , SM/07009 | Retrofitting | Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at tube well site of Vill Bansbagan of Tajpur PWSS of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (SM/07009) | 1168/AE/USD | 25/11/2024 | 45 | ALI ENTERPRISE | 4.84 | 0 | 0 | 100
1926 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) , SM/07009 | Retrofitting | Alternative laying of distribution pipe line with repairing of FHTC's at village-Mahishamuri, Tajpur G.P. of Tajpur PWSS of Amta-II Development Block in Uluberia Sub Division under Howrah Division, P.H.E. Dte. | 1463/HD | 19/03/2025 | 181 | MANIRUL ISLAM | 19.22 | 0 | 0 | 100
1927 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block , SM/07882 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block under Howrah Division, PHE Dte. for 2697 nos. | 789/HD | 06/04/2022 | 91 | SAMIRON GHOSH | 139.78 | 124.4 | 100 | 100
1928 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block , SM/07882 | Retrofitting | Work Order for Additional laying of HDPE pipe for Providing Functional Household Tap Connection(FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 517/HD | 09/02/2023 | 30 | SAMIRON GHOSH | 40.57 | 25.18 | 100 | 100
1929 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block , SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Panpur Dakhinpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 3247/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0.94 | 100 | 100
1930 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block , SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Panpur Uttarpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 3248/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0.93 | 100 | 100
1931 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block , SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection (FHTC) from existing distribution system in Dadpur Bamunpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 3253/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0.95 | 100 | 100
1932 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block , SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dakhin Ramchandrapur Hazrapara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 3251/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0.93 | 100 | 100
1933 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block , SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dadpur Paschimpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 3255/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0.97 | 100 | 100
1934 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block , SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Panpur Ghoshpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 3249/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0.95 | 100 | 100
1935 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block , SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dakhin Ramchandrapur Purbapara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 3250/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0.93 | 100 | 100
1936 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block , SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dadpur Majhipara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 3254/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0.93 | 100 | 100
1937 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block , SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dakhin Ramchandrapur Chatterjeepara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 3252/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0.93 | 100 | 100
1938 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block , SM/07882 | Retrofitting | Road Restoration work in connection with FHTC at DakhinHarishpur PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 1646/AE/USD | 11/02/2025 | 15 | MMS CONSTRUCTIONS PVT. LTD. | 1.52 | 0 | 0 | 100
1939 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS , SM/06774 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Maju Khetra piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-C) | 1550/HD | 05/11/2020 | 30 | M/S ASHIRBAD (INDIA) | 18.96 | 0 | 0 | 0
1940 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS , SM/06774 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Maju Khetra piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-A) | 1551/HD | 05/11/2020 | 30 | N. G ENGINEERING | 18.82 | 0 | 0 | 0
1941 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS , SM/06774 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Maju Khetra piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-B) | 1554/HD | 05/11/2020 | 30 | M/S ASHIRBAD (INDIA) | 18.8 | 0 | 0 | 0
1942 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS , SM/06774 | Retrofitting | Ground Water Based Piped Water Supply Scheme For Majhu Khetra | 844339 | 19/03/2021 | 0 | DEV DAS SHAW | 5.64 | 0 | 0 | 0
1943 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS , SM/06774 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | 84432 | 09/02/2021 | 0 | N. G ENGINEERING | 16.5 | 0 | 0 | 0
1944 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS , SM/06774 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | 84435 | 09/02/2021 | 0 | M/S ASHIRBAD (INDIA) | 16.65 | 0 | 0 | 0
1945 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS , SM/06774 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | 84436 | 09/02/2021 | 0 | M/S ASHIRBAD (INDIA) | 16.38 | 0 | 0 | 0
1946 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS , SM/06774 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. and Laying of additional UPVC pipe line of 63 mm & 75 mm dia. Total 1500 mtr. Length within the Command area of Majukhtra PWSS under Howrah Sadar Sub Division of Howrah Division , PHE Dte. (Phase-II) | 343/HD | 17/02/2022 | 30 | KRISH CONSTRUCTION | 4.53 | 0 | 0 | 0
1947 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS , SM/06774 | Retrofitting | Construction of Septic tank chamber with soak well at Head work site in Maju Khetra w/s scheme under Howrah Sadar Sub-Division, PHE Dte. | 844347 | 22/02/2022 | 0 | ABONTICA ENTERPRISE | 0.59 | 0 | 0 | 0
1948 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Preparation of DPR for new piped water supply scheme of Khila PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 329/AE/USD | 16/08/2022 | 45 | STEELCONC AND ASSOCIATES | 4.01 | 3.89 | 100 | 0
1949 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Material Requisition To Resource Division | 421/HD | 03/02/2023 | 0 | Resource Division | 8.77 | 0 | 0 | 0
1950 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Material Requisition To Resource Division | 2830/HD | 04/08/2023 | 0 | Resource Division | 29.79 | 0 | 0 | 0
1951 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Material Requisition To Resource Division | 3217/HD | 05/09/2023 | 0 | Resource Division | 38.86 | 0 | 0 | 0
1952 | HOWRAH | Electrical | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | QUOTATION OF NEW SERVICE CONNECTION FOR KHILA W/S SCHEME, PH NO-III | 124 | 20/07/2023 | 0 | WBSEDCL | 6.1 | 0 | 0 | 0
1953 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection(FHTC) of KHILA Piped Water Supply Scheme under Udaynaryanpur block under Howrah Division, PHE Dte. (Part-B). | 1104/HD | 17/03/2023 | 863 | JAHANGIR ALAM | 113 | 71.45 | 63.23 | 35
1954 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Construction of Boundary Wall, Approach Road, Land Development and Pump house at HEAD WORK Site, 2nd Tube Well Site and 3rd Tube Well Site of KHILA Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte.[SM/12270] | 4130/HD | 23/09/2024 | 525 | JAHANGIR ALAM | 102.93 | 26.65 | 25.89 | 50
1955 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Khila PWSS of RWS Howrah Sub-Division under Howrah Division, P. H.E. Dte. | 2488/HD | 30/11/2022 | 60 | M/S SYCHROTECH INDUSTRY | 54.33 | 46.35 | 100 | 100
1956 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 3rd TW site Khila W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 2803/HD | 21/12/2022 | 60 | MAITY CONSTRUCTIONS | 7.7 | 6.68 | 100 | 60
1957 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | NDT of OHR of of Khila PWSSS | BP-2024-25-197 | 22/07/2024 | 0 | JADAVPUR UNIVERSITY | 1.77 | 0 | 0 | 0
1958 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Acceptance cum Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) of KHILA Piped Water Supply Scheme under Udaynaryanpur block under Uluberia Sub- Division, PHE Dte.(Part-A) | 1450/HD | 30/03/2023 | 908 | M/S EL-CON | 620.6 | 185.88 | 29.95 | 50
1959 | HOWRAH | Electrical | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khila water supply scheme, T.W. No.- I, II & III, Block: Udaynaraynpur, District- Howrah under Electrical Division, PHE Dte. | 3554/ED | 30/12/2022 | 1037 | M/S P.P. ELECTRICALS | 30.54 | 12.6 | 41.28 | 50
1960 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Construction of 600 cum capacity 20 mtr. Staging height RCC Elevated Reservoir as per Departmental Design Drawing including Soil Investigation, Design of Pile foundation & all pipe connections for KHILA PWSS of Udaynarayanpur Block under Howrah Division, P.H.E. Dte. (SM/12270) | 3083/HD | 08/07/2025 | 365 | ABDUL HAI | 158.66 | 0 | 0 | 0
1961 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Work order for temporary Staging arrangements and some allied works for conducting NDT of KHILA Existing OHR of KHILA Pipe W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 77/RWS | 07/03/2025 | 15 | BISWAJIT BAG | 1.35 | 0 | 0 | 100
1962 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. , SM/12270 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4813/HD | 19/11/2024 | 510 | HORIZEN | 13.59 | 0 | 0 | 70
1963 | HOWRAH | Howrah Division | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Work Order for Preparation of DPR for new piped water supply scheme of Khorda Etarai PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 253/HD | 07/02/2022 | 15 | APEX ENGINEERING | 2.91 | 2.61 | 100 | 0
1964 | HOWRAH | Howrah Division | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Khorda Etarai W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 2809/HD | 21/12/2022 | 60 | SR TRADING CORPORATION | 8.5 | 7.77 | 100 | 100
1965 | HOWRAH | Howrah Division | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Khordah Etarai PWSS of Udaynarayanpur Block of Howrah RWS Sub- Division under Howrah Division, P. H. E. Dte. | 2490/HD | 30/11/2022 | 45 | DEV DAS SHAW | 27.37 | 22.53 | 100 | 100
1966 | HOWRAH | Howrah Division | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Material Requisition To Resource Division | 421/HD | 03/02/2023 | 0 | Resource Division | 2.18 | 0 | 0 | 0
1967 | HOWRAH | Howrah Division | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Material Requisition To Resource Division | 2830/HD | 04/08/2023 | 0 | Resource Division | 4.52 | 0 | 0 | 0
1968 | HOWRAH | Howrah Division | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Material Requisition To Resource Division | 2716/HD | 25/07/2023 | 0 | Resource Division | 13.78 | 0 | 0 | 0
1969 | HOWRAH | Electrical | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Quotation bill for new service connection of Kharda Itarai PWSS, P.H-II | 17 | 02/05/2023 | 0 | WBSEDCL | 7.81 | 0 | 0 | 0
1970 | HOWRAH | Electrical | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | QUOTATION FOR NEW SERVICE CONNECTION OF KHORDA ETARAI W/S SCHEME PH NO-I, ELECTRICAL DIVISION, PHE DTE | 39 | 15/05/2023 | 0 | WBSEDCL | 7.36 | 0 | 0 | 0
1971 | HOWRAH | Howrah Division | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Raising main & Inter Connection with both tube wells of Khodra Etarai PWSS in Udaynarayanpur Block under Howrah Division, PHE Dte. | 4636/HD | 21/12/2023 | 15 | UNIVERSAL CONSTRUCTION | 6.87 | 5.33 | 100 | 100
1972 | HOWRAH | Howrah Division | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Khorda Etarai W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | 2806/HD | 21/12/2022 | 60 | JAHANGIR ALAM | 8.42 | 7.54 | 100 | 98
1973 | HOWRAH | Howrah Division | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Material Requisition To Resource Division | 28/HD | 03/01/2024 | 0 | Resource Division | 0.87 | 0 | 0 | 0
1974 | HOWRAH | Howrah Division | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Work Order for Construction of 100 cum Capacity 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (733 nos) for KHORDA ETARAI PWSS of Udaynarayanpur Block under Howrah Division, PHE Dte. | 2784/HD | 20/12/2022 | 900 | AJAY MONDAL | 191.45 | 95.65 | 49.96 | 55
1975 | HOWRAH | Electrical | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khorda Etarai water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 3513/ED | 30/12/2022 | 611 | MAHAMAYA ENTERPRISE | 20.36 | 19.58 | 97.55 | 90
1976 | HOWRAH | Howrah Division | Khorda Etarai Piped Water Supply Scheme , SM/11892 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4813/HD | 19/11/2024 | 510 | HORIZEN | 13.59 | 1.78 | 99.98 | 70
1977 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Khasmara (Zone-III) PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | 78/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.42 | 3.42 | 100 | 0
1978 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Material Requisition To Resource Division | 1748/HD | 25/04/2023 | 0 | Resource Division | 130.95 | 0 | 0 | 0
1979 | HOWRAH | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Quotation Bill for New Service Connection at Khasmara W/S. Sch. PWSS-II | 377 | 25/10/2023 | 0 | WBSEDCL | 15.25 | 0 | 0 | 0
1980 | HOWRAH | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Quotation Bill for New Service Connection at Khasmara W/S. Sch. Howrah | 167 | 04/08/2023 | 0 | WBSEDCL | 0.22 | 0 | 0 | 0
1981 | HOWRAH | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Quotation Bill for New Service Connection at Domjur, Khasmara W/S. Sch. Z-III | 65 | 08/06/2023 | 0 | WBSEDCL | 2.34 | 0 | 0 | 0
1982 | HOWRAH | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Deposition of additional quotation money for domjur zone-III ( KHASMARA) w/s scheme P.H No.-I ,Dist- Howrah under ED PHED. |  | 07/06/2023 | 0 | WBSEDCL | 2.34 | 0 | 0 | 0
1983 | HOWRAH | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Quotation money deposit for Domjur (Zone-III) Khasmara W/S ,P.H No.-I | 21 | 04/05/2023 | 0 | WBSEDCL | 0.69 | 0 | 0 | 0
1984 | HOWRAH | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khasmara Domjur (Zone-III) water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 3512/ED | 30/12/2022 | 90 | H.K.DAS & CO. | 34.31 | 24.52 | 71.49 | 65
1985 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Work Order for Sinking of 3 (Three) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (ZoneIII) Khasmara PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 174/HD | 13/01/2023 | 45 | BALAJI UDDYOG | 38.37 | 36.78 | 100 | 100
1986 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Concrete Approach Road at 1st Tubewell Site at Domjur (Zone-III) Khashmora PWSS under Howrah Sadar Sub-Division, P.H.E. Dte. | 2725/HD | 11/06/2024 | 45 | SUJATA CONSTRUCTION | 9.63 | 9.57 | 100 | 100
1987 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 14.79 | 0 | 0 | 0
1988 | HOWRAH | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Quotation money deposition for new service connection at Khasmara (Domjur Zone-III) Pwss P.H No-III , Dist-Howrah under ED, PHED. | 752 | 16/02/2024 | 0 | WBSEDCL | 12.75 | 0 | 0 | 0
1989 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Work Order for 3 nos Construction of Pump House (5.40m x 3.60 m) at 1st , 2nd &3rd Tube Well Site ,Construction of Boundary Wall at 1st Tube Well Site,Construction of 2 nos Boundary Wall at 2nd & 3rd Tube Well Site,Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) Augmentation of Domjur (Zone-III) Khasmara PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | 1698/HD | 21/04/2023 | 925 | SUJATA CONSTRUCTION | 452.67 | 313.36 | 69.23 | 45
1990 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Emergency Restoration of CI/DI Pipeline along with damaged main road due to laying of pipe line From Node No. 149 to 292 of Domjur (Zome-3) Khasmora PWSS under Howrah Sadar Sub-Division PHE Dte. | 2942/HD | 25/06/2025 | 120 | SUJATA CONSTRUCTION | 59.8 | 0 | 0 | 0
1991 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Pipe Carrying Structure for Crossing of Keto Pol at Khasmora PWSS Under Howrah Sadar Sub-Division, P.H.E. Dte. | 1014/HD | 21/02/2025 | 60 | GUPTA ENTERPRISE | 37.95 | 0 | 0 | 0
1992 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Domjur Block) | 4128/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
1993 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Land Development Works (1st, 2nd & 3rd T/W Site) & RCC Retaining Wall of Khasmora (Zone-3) PWSS at 3rd Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | 2726/HD | 11/06/2024 | 356 | SUJATA CONSTRUCTION | 11.55 | 0 | 0 | 100
1994 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Piped Water Supply Schemes in different Blocks in the District of Howrah under Howrah Division, PHE Dte. | 3730/HD | 29/08/2024 | 30 | HORIZEN | 4.93 | 0 | 0 | 100
1995 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Emergency Restoration of CI/DI Pipeline along with damaged main road due to laying of pipe line of Domjur (Zome-3) Khasmora PWSS under Howrah Sadar Sub-Divnision PHE Dte. | 2940/HD | 25/06/2025 | 45 | SUJATA CONSTRUCTION | 19.31 | 0 | 0 | 100
1996 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur , SM/11893 | New | Supplying,fitting,fixing and erecting of Display Board at Bipra Noapara PWSS [SM/11711], Domjur Zone-I (Mahisnala) PWSS [SM/11894], and Domjur Zone-III (Khasmara) PWSS [SM/11893] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 224-A/HSSD | 27/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
1997 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Tulsiberia PWSS of Uluberia-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 2715/HD | 14/12/2022 | 45 | ACME CONSTRUCTION | 36.15 | 34.31 | 100 | 0
1998 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Preparation of DPR for new piped water supply scheme of Tulshiberia PWSS, Uluberia-II Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | 456/AE/USD | 15/09/2022 | 45 | DULAL MAJUMDER | 3.13 | 3.01 | 100 | 0
1999 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Work order for Interconnection between Tube wells & OHR at Tulsiberia Water Supply scheme at Uluberia-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 1948/HD | 10/05/2023 | 60 | SUNIL ENTERPRISE | 10.42 | 9.19 | 100 | 100
2000 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 20.18 | 0 | 0 | 0
2001 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Material Requisition To Resource Division | 1698/HD | 21/04/2023 | 0 | Resource Division | 5.48 | 0 | 0 | 0
2002 | HOWRAH | Electrical | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Deposition of Quotation money for Tulshiberia w/s scheme, P.H No-I ,Dist-howrah under ED PHED. | 76 | 15/06/2023 | 0 | WBSEDCL | 4.24 | 0 | 0 | 0
2003 | HOWRAH | Electrical | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Quotation Bill for New Service Connection at Tulsiberia Kalimandir W/S. Sch. PH-I & II | 18 | 02/05/2023 | 0 | WBSEDCL | 11.36 | 0 | 0 | 0
2004 | HOWRAH | Electrical | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). | 2830/HMSD | 30/10/2023 | 182 | SANJIB PRADHAN | 0.86 | 1.83 | 253.83 | 42
2005 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Material Requisition To Resource Division | 530/HD | 06/02/2024 | 0 | Resource Division | 11.09 | 0 | 0 | 0
2006 | HOWRAH | Electrical | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Supply of Fuel for 1(One) no Diesel Luxury taxi on contract Carriage for the Office of the Assistant Engineer,Howrah Mechanical Sub Division PHE Dte.(JJM Work for Hooghly District) for the Month of March 2024. | 106 | 07/05/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
2007 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Construction of boundary wall at HW Site of Tulsiberia W/S scheme within Uluberia-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 988/HD | 20/02/2025 | 60 | SANJOY GHOSH | 27.81 | 0 | 0 | 0
2008 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Construction of 2.50 mtrs. Height Boundary Wall with double column after 15 mtrs interval along with 750 mm Height 4 layer barbed wire fencing around 2nd. TW site including with land development & approach road of Kamina adjacent to Tulshiberia PWSS at Uluberia-II Block under Uluberia Sub-Division under Howrah Division, PHE. Dte. | 1353/HD | 11/03/2025 | 358 | A.A ENTERPRISE | 9.3 | 0 | 0 | 85
2009 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Land Development and Approach Road at HW site of Tulsiberia PWSS of Uluberia-II Block under Uluberia Sub Division under Howrah Divison PHED. | 1826/HD | 09/04/2025 | 30 | MUKHERJEE CONSTRUCTION | 9.01 | 0 | 0 | 0
2010 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Land Development & Approach Road at 2nd TW site of Tulsiberia PWSS of Uluberia-II Block under Uluberia Sub Division under Howrah Divison PHED. | 1491/AE/USD | 16/01/2025 | 20 | MM ENTERPRISE | 1.19 | 0 | 0 | 0
2011 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Construction of Pump House (3.60m x 3.30m) with water supply arrangement at Head Work site of Kamina adjacent to Tulshiberia PWSS at Uluberia-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. | 1811/HD | 08/04/2025 | 45 | ARUP NANDY | 6.47 | 0 | 0 | 15
2012 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Construction of 1.8 mtrs. Height Boundary Wall with double column after 15 mtrs interval along with 750 mm Height 4 layer barbed wire fencing around head work site including land development & approach road of Kamina adjacent to Tulshiberia PWSS at Uluberia-II Block under Uluberia Sub Division under Howrah Division, PHE. Dte. | 1812/HD | 08/04/2025 | 60 | ARUP NANDY | 24.85 | 0 | 0 | 10
2013 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bagnan-II & Uluberia-II Block) | 4120/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
2014 | HOWRAH | Electrical | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Tulsiberia water supply scheme, T.W. No.- I & II, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | 3525/ED | 30/12/2022 | 663 | TAMAL ENTERPRISE | 20.35 | 19.73 | 97.3 | 30
2015 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Construction of boundary wall at 2nd T/W Site of Tulsiberia W/S scheme within Uluberia-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1034/HD | 24/02/2025 | 180 | M/S HOWRAH CONSTRUCTION | 8.01 | 0 | 0 | 100
2016 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
2017 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. , SM/11574 | New | Work Order for Construction of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation,Construction of switch room (5.4 x 3.6) & (3.6 x3.0) with water supply & sanitary arrangement at Head Work site & 2nd Tube well site, Laying Distribution Pipeline & Provinding FHTC (2070 nos) for Tulsiberia Water Supply Scheme In Uluberia-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | 2677/HD | 12/12/2022 | 1080 | MUKHERJEE CONSTRUCTION | 476.04 | 346.82 | 72.86 | 95
2018 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Ichhapur PWSS (Mouza-Ichhapur, Ranmahal & Tripurapur) of Jagatballavpur Block under Howrah Division PHE Dte. | 1016/HD | 05/05/2022 | 15 | ENVIROTECH SOLUTIONS | 3.04 | 3.04 | 100 | 0
2019 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2020 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ichapur PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P. H. E. Dte. | 312/HD | 20/01/2023 | 30 | ALLIED TUBEWELLS PRIVATE LIMITED | 25.64 | 0 | 0 | 0
2021 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Material Requisition To Resource Division | 446/HD | 06/02/2023 | 0 | Resource Division | 12.27 | 0 | 0 | 0
2022 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Work Order for Laying Distribution Pipeline (PART-2) & Providing FHTC (PART-2) of Ichapur PWSS at J.B. PUR Block of Howrah District under Howrah Division, P. H. E. Dte. | 1674/HD | 19/04/2023 | 60 | PIKASU BOSE | 149.08 | 89.99 | 60.36 | 60
2023 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Work Order for Construction of 200 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection For Ichapur PWSS at J.B. PUR Block of Howrah District under Howrah Division, P. H. E. Dte. | 1347/HD | 27/03/2023 | 600 | RANI CONSTRUCTION | 91.61 | 23.52 | 25.67 | 10
2024 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Continuation order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ichapur PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P.H.E. Dte. | 4254/HD | 28/11/2023 | 30 | AUXILIARY TUBEWELL DRILLERS | 25.64 | 24.35 | 100 | 100
2025 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Material Requisition To Resource Division | 1317/HD | 14/03/2024 | 0 | Resource Division | 17.52 | 0 | 0 | 0
2026 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Material Requisition To Resource Division | 4348/HD | 30/09/2024 | 0 | Resource Division | 24.66 | 0 | 0 | 0
2027 | HOWRAH | Electrical | ICHAPUR PWSS , SM/13629 | New | Quotation money deposition for new service connection at Ichhapur pwss , P.H No.-II, Dist-Howrah under PHED. App. No.-1007566560 Ref.ID: 106496241 SM/13629 | 859 | 11/03/2024 | 0 | WBSEDCL | 17.26 | 0 | 0 | 0
2028 | HOWRAH | Electrical | ICHAPUR PWSS , SM/13629 | New | Quotation Money deposition for new service connection at Ichapur pwss, P.H No.-I , Dist-Howrah under ED PHED. Application No.- 1007513772 Ref. ID- 106460039 | 761 | 16/02/2024 | 0 | WBSEDCL | 17.39 | 0 | 0 | 0
2029 | HOWRAH | Electrical | ICHAPUR PWSS , SM/13629 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ichapur water supply scheme, T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 3541/ED | 30/12/2022 | 1080 | KASHINATH PAL & CO. | 21.15 | 0 | 0 | 60
2030 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Work Order for Construction of 2 nos Pump House ( 5.40m x 3.60 m), 2nos Construction of Boundary Walls, Rising Main Pipeline Work, Laying Distribution Pipeline (Part-1) & Providing FHTC(Part-1) of Ichapur PWSS at J.B. PUR Block of Howrah District under Howrah Division,PHE DTE (PART-I) | 977/HD | 10/03/2023 | 900 | D D CONSTRUCTION | 110.53 | 6.73 | 6.09 | 10
2031 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Restoration of road and Ancillary work for Ichapur PWSS at Jagatballavpur Block of Howrah District under Howrah Division, P.H.E. Dte. | 1068/HD | 27/02/2025 | 120 | MAITY CONSTRUCTION | 20.84 | 0 | 0 | 0
2032 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Construction of Concrete road for movement of vehicle for construction of Over Head reservoir site (PH 1) at Ichapur PWSS under Jagatballavpur Block under Howrah Sadar Sub Division, P.H.E. Dte. | 1298/HD | 13/03/2024 | 360 | RANI CONSTRUCTION | 11.27 | 0 | 0 | 10
2033 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Piped Water Supply Schemes in different Blocks in the District of Howrah under Howrah Division, PHE Dte. | 3730/HD | 29/08/2024 | 30 | HORIZEN | 4.93 | 4.4 | 100 | 100
2034 | HOWRAH | Howrah Division | ICHAPUR PWSS , SM/13629 | New | Supplying,fitting,fixing and erecting of Display Board at Bhursit Bamunpara PWSS [SM/09351], Pulgustia PWSS [SM/10143], Ichapur PWSS [SM/13629] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 230-A/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
2035 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Material Requisition To Resource Division | 1748/HD | 25/04/2023 | 0 | Resource Division | 47.46 | 0 | 0 | 0
2036 | HOWRAH | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Quotation Bill for New Service Connection at Dakshin Jhapardaha W/S. Sch. Z-i | 546 | 19/12/2023 | 0 | WBSEDCL | 9.63 | 0 | 0 | 0
2037 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Work Order for LDS (Part-2) & FHTC (Part-2) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-I) In DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P.H.E. DTE | 795/HD | 27/02/2023 | 90 | UNIVERSAL CORPORATION | 143.99 | 103.61 | 71.96 | 50
2038 | HOWRAH | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) water supply scheme, T.W. No. I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 918/ED | 22/02/2023 | 90 | D. K. ELECTRIC | 32.22 | 10.46 | 32.47 | 30
2039 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Work Order for CONSTRUCTION FOR 3 NOS. PUMP HOUSE, 3 NOS. BOUNDARY WALL, RISING MAIN, LDS (Part-1) & FHTC (Part-1) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-I) in DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P. H. E. DTE. | 981/HD | 13/03/2023 | 180 | MA MANASA CONSTRUCTION | 148.59 | 70.33 | 47.33 | 48
2040 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 19.07 | 0 | 0 | 0
2041 | HOWRAH | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Shifting of 1 (No.) 25kva DISTRIBUTION SUB-STATATION at Dakshin Jhapordah (Zone-I) PWSS, P.H No.-I under ED, PHED. Ref. ID.-860318414 SM/13751 | BP-24-25-595 | 21/11/2024 | 0 | WBSEDCL | 1.71 | 0 | 0 | 0
2042 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Emergency Restoration of CI/DI Pipeline along with damaged main road due to laying of pipe line from Panchanantala to Taruner Ahaban Club Road & Radharani Laha Memorial School to bisalaxmitala Road of Domjur (Zone-4) Dakshin Jhapardaha (Zone-I) PWSS under Howrah Sadar Sub-Divnision PHE Dte. | 2955/HD | 26/06/2025 | 90 | USHA CONCERN | 39.78 | 0 | 0 | 100
2043 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Domjur - Andul Road from 0.00 Km to 4.129 Km, Restoration work of PHE Cutting for laying pipe line under Howrah Highway Division in the district of Howrah (Dakshin Jhapardaha PWSS Zone-II, Dakshin Jhapardaha PWSS Zone-I, Bhandardaha PWSS, Bipranoapara PWSS). |  | 28/03/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 101.31 | 0 | 0 | 0
2044 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Dhulagarh Domjur via Begri Road from 2.6 km to 6.341 km, Restoration work of PHE cutting for laying pipe line under Howrah Highway Division in the District of Howrah. | BP-2024-25-531 | 22/01/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 98.16 | 0 | 0 | 0
2045 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Work Order for Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone-IV) Dakshin Jhapordaha (Zone-I) & (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 175/HD | 13/01/2023 | 1197 | B K ENTERPRISE | 77.78 | 12.73 | 32.72 | 85
2046 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-I) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (PART-4 : Node No. 340 to 370, 374) | 163/HD | 13/01/2023 | 941 | NAG ENTERPRISE | 12.81 | 0 | 0 | 65
2047 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4817/HD | 19/11/2024 | 510 | TECH VISION | 8.36 | 1.32 | 99.99 | 95
2048 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Supplying,fitting,fixing and erecting of Display Board at Domjur (Zone-IV) Dakshin Jhapardaha (Zone-I) PWSS [SM/13751], Domjur (Zone-IV) Dakshin Jhapardaha (Zone-II) PWSS [SM/13752], Keshabpur PWSS [SM/16947] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 222/HSSD | 25/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
2049 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/13751 | New | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-I) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (PART-3 : Node No. 371 to 388) | 353/HD | 30/01/2023 | 937 | M/S HOWRAH CONSTRUCTION | 6.71 | 5.93 | 88.48 | 100
2050 | HOWRAH | Electrical | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. , SM/13749 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gabberia Mallik Bagan water supply scheme, T.W. No.- I, II & III, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 3538/ED | 30/12/2022 | 90 | INDIA ENTERPRISE | 30.58 | 0 | 0 | 0
2051 | HOWRAH | Howrah Division | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. , SM/13749 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Gabberia PWSS (Mouza-Gabberia(CT) & Mallik Bagan (CT) of Panchla Block under Howrah Division PHE Dte. | 1022/HD | 05/05/2022 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.04 | 3.04 | 100 | 0
2052 | HOWRAH | Howrah Division | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. , SM/13749 | New | Material Requisition To Resource Division | 446/HD | 06/02/2023 | 0 | Resource Division | 59.98 | 0 | 0 | 0
2053 | HOWRAH | Howrah Division | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. , SM/13749 | New | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 21.47 | 0 | 0 | 0
2054 | HOWRAH | Howrah Division | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. , SM/13749 | New | Work Order for Additional laying distribution Pipeline work of Gabberia Mallickbagan PWSS at Panchla Block,of Howrah Sadar Sub Division under Howrah Division , PHE Dte. | 1930/HD | 10/05/2023 | 723 | ADITYA HAZRA | 52.7 | 0 | 0 | 30
2055 | HOWRAH | Howrah Division | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. , SM/13749 | New | Different Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, and Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Panchla Block, District:-Howrah [NEW SCHEME][Name of Schemes:-1)Paschim Panchla PWSS 2) Panchla PWSS 3) Gabberia-Mallik Bagan PWSS]. | 2866/HD | 08/08/2023 | 910 | SAMIRON GHOSH | 1986.19 | 12.25 | 2.1 | 30
2056 | HOWRAH | Howrah Division | Paschim Panchla Piped Water Supply Scheme. , SM/13768 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Paschim Panchla PWSS (Mouza-Paschim Panchla(CT) & Dakshin Panchla) of Panchla Block under Howrah Division PHE Dte. | 1021/HD | 05/05/2022 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.13 | 3.13 | 100 | 100
2057 | HOWRAH | Electrical | Paschim Panchla Piped Water Supply Scheme. , SM/13768 | New | Quotation Bill for New Service Connection at Paschim Panchla W/S. Sch. PH-II | 446 | 28/11/2023 | 0 | WBSEDCL | 22.73 | 0 | 0 | 0
2058 | HOWRAH | Electrical | Paschim Panchla Piped Water Supply Scheme. , SM/13768 | New | Quotation Bill for New Service Connection at Paschim Panchla W/S. Sch. PH-I | 445 | 28/11/2023 | 0 | WBSEDCL | 23.36 | 0 | 0 | 0
2059 | HOWRAH | Electrical | Paschim Panchla Piped Water Supply Scheme. , SM/13768 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Paschim Panchla water supply scheme, T.W. No. I, II & III, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 1714/ED | 18/04/2023 | 90 | S.P. CONSTRUCTION | 30.56 | 19.82 | 64.84 | 40
2060 | HOWRAH | Howrah Division | Paschim Panchla Piped Water Supply Scheme. , SM/13768 | New | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 12.18 | 0 | 0 | 0
2061 | HOWRAH | Howrah Division | Paschim Panchla Piped Water Supply Scheme. , SM/13768 | New | Material Requisition To Resource Division | 1094/HD | 05/03/2024 | 0 | Resource Division | 45.31 | 0 | 0 | 0
2062 | HOWRAH | Howrah Division | Paschim Panchla Piped Water Supply Scheme. , SM/13768 | New | Material Requisition To Resource Division | 1094/HD | 05/03/2024 | 0 | Resource Division | 29.4 | 0 | 0 | 0
2063 | HOWRAH | Howrah Division | Paschim Panchla Piped Water Supply Scheme. , SM/13768 | New | Material Requisition To Resource Division | 843/HD | 22/02/2024 | 0 | Resource Division | 22.18 | 0 | 0 | 0
2064 | HOWRAH | Howrah Division | Paschim Panchla Piped Water Supply Scheme. , SM/13768 | New | Different Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, and Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Panchla Block, District:-Howrah [NEW SCHEME][Name of Schemes:-1)Paschim Panchla PWSS 2) Panchla PWSS 3) Gabberia-Mallik Bagan PWSS]. | 2866/HD | 08/08/2023 | 910 | SAMIRON GHOSH | 1986.19 | 241.58 | 59.61 | 30
2065 | HOWRAH | Howrah Division | Paschim Panchla Piped Water Supply Scheme. , SM/13768 | New | Additional Laying Distribution Pipeline & approach road with land development at OHR site & allied works of Paschim Panchla PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. (SM/13768) | 2828/HD | 20/06/2024 | 420 | SAMIRON GHOSH | 130.84 | 0 | 0 | 20
2066 | HOWRAH | Electrical | Paschim Panchla Piped Water Supply Scheme. , SM/13768 | New | Quotation money deposition for new service connection at Paschim Panchla w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008418445 Reference ID- 106964843 SM Code- 13768 | 709 | 17/03/2025 | 0 | WBSEDCL | 4.54 | 0 | 0 | 0
2067 | HOWRAH | Howrah Division | Paschim Panchla Piped Water Supply Scheme. , SM/13768 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4816/HD | 19/11/2024 | 510 | TECH VISION | 12.48 | 0 | 0 | 78
2068 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Supply, delivery of clamp on type portable Flowmeter set for different OHR site of Bargachia water supply scheme, Howrah under Electrical Division, PHE Dte. | 2157/ED | 16/06/2023 | 60 | SHANTA COLIBRI (INDIA) PVT. LTD | 17.68 | 17.68 | 100 | 100
2069 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Work Order for Sinking of 2 (One) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS ZONE -X (TW I,II) of Jagatballavpur Block under Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 309/HD | 20/01/2023 | 30 | NADIA TUBEWELLS | 34.37 | 31.55 | 100 | 100
2070 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Material Requisition To Resource Division | 1748/HD | 25/04/2023 | 0 | Resource Division | 282.87 | 0 | 0 | 0
2071 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | new service connection | 243 | 01/09/2023 | 0 | WBSEDCL | 5.82 | 0 | 0 | 0
2072 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation Bill for New Service Connection at Bargachia W/S. Sch. Z-V | 570 | 27/12/2023 | 0 | WBSEDCL | 4.23 | 0 | 0 | 0
2073 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | New service connection | 106 | 19/07/2023 | 0 | WBSEDCL | 7.45 | 0 | 0 | 0
2074 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | new service connection | 244 | 01/09/2023 | 0 | WBSEDCL | 5.93 | 0 | 0 | 0
2075 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Payment for WBSEDCL Augmentation of Bargachia Water Supply Scheme (Zone-IV) Pump house no -II | BP-2023-24-74 | 13/06/2023 | 0 | WBSEDCL | 3.37 | 0 | 0 | 0
2076 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation Bill for New Service Connection at Bargachi W/S. Sch. Z-X, PH-I | 435 | 23/11/2023 | 0 | WBSEDCL | 1.81 | 0 | 0 | 0
2077 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation Bill for New Service Connection at Bargachia W/S. Sch. Z-I | 571 | 27/12/2023 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
2078 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation Bill for New Service Connection at Bargachia PH-I, Z-VI W/S. Sch. | 146 | 26/07/2023 | 0 | WBSEDCL | 4.96 | 0 | 0 | 0
2079 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Deposition of quotation money for Aug.of Baragachia w/s scheme , zone-vi, P.H No-II Dist-Howrah under ED/PHED. | 24 | 11/05/2023 | 0 | WBSEDCL | 11.06 | 0 | 0 | 0
2080 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | New service connection | 107 | 19/07/2023 | 0 | WBSEDCL | 3.43 | 0 | 0 | 0
2081 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Payment for WBSEDCL Augmentation of Bargachia Water Supply Scheme (Zone-IV) Pump house no -I | BP-2023-24-74 | 13/06/2023 | 0 | WBSEDCL | 3.91 | 0 | 0 | 0
2082 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone VI (TW-1 &TW-II), Zone-VII (TW I&II) at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 307/HD | 20/01/2023 | 120 | B K ENTERPRISE | 69.42 | 15.67 | 22.57 | 50
2083 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone 1 (TW-1 &TW-II), Zone-II TW I&II at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 304/HD | 20/01/2023 | 60 | CARBON SERVICES INDIA | 68.08 | 46.31 | 68.03 | 50
2084 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Construction of Pump House, Boundary Wall, 400 cum Capacity OHR, Rising Main, Laying Distribution Pipeline & Providing FHTC (2554 nos) For Augmentation of Bargachia PWSS (Zone-VII) in Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 454/HD | 01/02/2024 | 180 | M/S ASHA CONSTRUCTION | 442.08 | 48.36 | 10.94 | 12
2085 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Construction of R.C.C. Culvert at OHR site, Approach Road and Land Development at OHR Site, Retaining Wall at OHR site of Bargachia PWSS(Zone-VII) in J.B. Pur Block of Howrah Sadar Sub-Division under Howrah Division, PHE Dte. | 4195/HD | 26/09/2024 | 120 | COSMO ENTERPRISE | 65.1 | 0 | 0 | 0
2086 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Road restoration work, approach road and Land development at Over Head Reservoir Site, Construction of 1no Hume pipe culvert, RCC Retaining Wall & Jack Pushing of 700 mm dia M.S pipe as Casing Pipe to Cross Water carrier pipe (Between Node Point 81-82 of LDS drawing) at Bargachia zone-V & VI PWSS under Howrah Sadar Sub-Division of Howrah Division P.H.E.Dte. (SM/14095) | 3871/HD | 04/09/2024 | 270 | S.P. CONSTRUCTION | 227.58 | 0 | 0 | 30
2087 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone VIII (TW-1 &TW-II), Zone-IX (TW I&II) at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 308/HD | 20/01/2023 | 60 | WATER TECH | 68.83 | 63.37 | 100 | 50
2088 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 176.2 | 0 | 0 | 0
2089 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Material Requisition To Resource Division | 1956/HD | 16/04/2024 | 0 | Resource Division | 17.78 | 0 | 0 | 0
2090 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Material Requisition To Resource Division | 843/HD | 22/02/2024 | 0 | Resource Division | 31.83 | 0 | 0 | 0
2091 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation for New Service Connection at Bargachia W/S. Sch. Z=IX | 609 | 04/01/2024 | 0 | WBSEDCL | 13.16 | 0 | 0 | 0
2092 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Payment of Way Leave Plan and Survey charges Bargachia Zone-II PWSS | BP-2024-25-19 | 26/04/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.3 | 0 | 0 | 0
2093 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Restoration Work of Bituminous Road and Shoulder with allied work Bargachia Boharia Road from 2.30 kmp to 6.30 kmp (Due to cutting for PHE water line) under Howrah Division in the dist of Howrah during the year 2024-2025. | BP-2024-25-495 | 27/11/2024 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 34.15 | 0 | 0 | 0
2094 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Payment of Way Leave Plan and Survey charges Bargachia Zone-II PWSS, | BP-2024-25-20 | 23/04/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.12 | 0 | 0 | 0
2095 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Bill Document for Payment of Wayleave Plan & Survey Charges | BP-2024-25-68 | 16/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.03 | 0 | 0 | 0
2096 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Bill Document for Payment of Wayleave facility charges | BP-2024-25-121 | 11/06/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 8.37 | 0 | 0 | 0
2097 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Bill Document for Payment of Wayleave facility charges | BP-2024-25-100 | 28/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 17.55 | 0 | 0 | 0
2098 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quatation for shifting of H.T.O.H. Line DP to the PHE No- I, Zone- VI, Hantal sashan , Howrah under Bargachia CCC. Application No- 100000113194 Reference ID- 860304044 SM Code- 14095 | 331 | 30/07/2024 | 0 | WBSEDCL | 5.83 | 0 | 0 | 0
2099 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- 8, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1007566516 Reference ID- 106496242 SM Code- 14095 | 881 | 13/03/2024 | 0 | WBSEDCL | 15.65 | 0 | 0 | 0
2100 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- II, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008229574 Reference ID- 106837719 SM Code- 14095 | 627 | 18/12/2024 | 0 | WBSEDCL | 16.23 | 0 | 0 | 0
2101 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- 9, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007604360 Reference ID- 106521117 SM Code- 14095 | 114 | 13/05/2024 | 0 | WBSEDCL | 10.29 | 0 | 0 | 0
2102 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Bill Document for payment of wayleave facility charges for Application ID : SER-KGP-2024-WL-34, Bargachia Zone-v | BP-2024-25-50 | 07/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 7.37 | 0 | 0 | 0
2103 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Bill Document for Payment of Wayleave facility charges | BP-2024-25-99 | 28/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 6.22 | 0 | 0 | 0
2104 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Payment for Way Leave and Survey Charges Bargachia PWSS | BP-2023-24-735 | 27/03/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.13 | 0 | 0 | 0
2105 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- 4b, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1007682963 Reference ID- 106564006 SM Code- 14095 | 130 | 17/05/2024 | 0 | WBSEDCL | 17.99 | 0 | 0 | 0
2106 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Post 5 years maintenance works for the road Begpara - Godaripara T06 at Jagatballavpur Block, Howrah under W.B.S.R.D.A. Howrah Division-I, Package No. WB/09/105. | BP-2024-25-504 | 09/12/2024 | 0 | WBSRDA | 9.5 | 0 | 0 | 0
2107 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation Money deposition for new service connection at Bargachia water supply scheme, Zone-8 ,P.H No.-I , Dist- Howrah under ED , PHED. | 736 | 07/02/2024 | 0 | WBSEDCL | 10.61 | 0 | 0 | 0
2108 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- III, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007550896 Reference ID- 106484781 SM Code- 14095 | 880 | 13/03/2024 | 0 | WBSEDCL | 25.65 | 0 | 0 | 0
2109 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Payment of Way Leave Plan and Survey charges Bargachia Zone-II PWSS, | BP-2024-25-21 | 23/04/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.11 | 0 | 0 | 0
2110 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Work Order for Construction of Pump House, Boundary Wall, 500 cum Capacity OHR (2 nos), Rising Main, Laying Distribution Pipeline & Providing FHTC For AUGMENTATION OF Bargachia (ZONE-V and ZONE-VI) PWSS in Jagatballavpur Block under Howrah Sadar Sub-Division of HOWRAH DIVISION, P. H. E. DTE.. | 05/HD | 02/01/2023 | 1080 | S.P. CONSTRUCTION | 1271.27 | 749.32 | 58.94 | 80
2111 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Work Order for Construction of Pump House, Boundary Wall, 400 cum Capacity OHR, Rising Main, Laying Distribution Pipeline & Providing FHTC (2554 nos) For AUGMENTATION OF Bargachia PWSS (ZONE-IX) in Jagatballavpur Block under Howrah Sadar Sub-Division of HOWRAH DIVISION, P.H.E. DTE. | 379/HD | 01/02/2023 | 900 | G.B. CONSTRUCTION AND CO | 462.97 | 133.51 | 28.84 | 15
2112 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Work Order for Construction of Pump House, Boundary Wall, 450 cum Capacity OHR, Rising Main, Laying Distribution Pipeline & Providing FHTC (3187 nos) For Augmentation of Bargachia PWSS (Zone-VIII) in Jagatballavpur Block under Howrah Sadar sub Division of Howrah Division, P. H. E. Dte. | 336/HD | 24/01/2023 | 1170 | MONDAL PRECISION PVT. LTD. | 566.01 | 208.71 | 36.87 | 35
2113 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Work Order for Construction of Pump House, Boundary Wall, 400 cum Capacity OHR , Rising Main , Laying Distribution Pipeline & Providing FHTC (1615 nos) For Augmentation of Bargachia PWSS (Zone-X) In Jagatballavpur Block under Howrah Sadar sub Division of Howrah Division, P. H. E. Dte. | 682/HD | 20/02/2023 | 1157 | B.B.C ENTERPRISE | 339 | 173.54 | 51.19 | 20
2114 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Work Order for Construction of Pump House, Boundary Wall, 300, 400 & 500 cum capacity OHR, Rising Main Laying Distribution System & Providing FHTC for Augmentation of Bargachia (Zone-I, II, III, IV-A, IV-B) Piped Water Supply Scheme at Jagatballavpur Block under Howrah Division, PHE Dte in connection with JJM. | 1559/HD | 06/04/2023 | 814 | GREEN ROYAL INFRA CON PRIVATE LIMITED | 2577.67 | 1338.14 | 51.91 | 25
2115 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of BARGACHIA Water Supply Scheme, Zone-I, II, III, IV(A), IV(B), V, VI, VII, VIII, IX, X. T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 2185/ED | 22/06/2023 | 731 | J.D.J ENTERPRISE | 250.01 | 153.6 | 61.44 | 35
2116 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Hiring of 1 (One) no. (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer Howrah Sadar Sub-Division, PHE Dte. Government of West Bengal. (for the period of 1 year)(for 365 days) | 809/HSSD | 06/08/2024 | 365 | MD KADIR | 4.73 | 3.57 | 82.29 | 8
2117 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Construction of 1 no. Slab culvert,Construction of RCC Retaining Wall, construction of approch road and land Devlopment at Over Head Reservoir Site at Bargachia (Zone -VIII) PWSS Under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 1246/HD | 12/03/2024 | 480 | REALIENCE CONSTRUCTION | 36.2 | 0 | 0 | 11
2118 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Additional work related to Augmentation of Bargachia PWSS (For Zone-X) under JJM for land development for Jagatballavpur Block of Howrah District under Howrah Division, P. H. E. Dte. | 193/HSSD | 23/02/2024 | 390 | S.B ENTERPRISE | 4.38 | 0 | 0 | 0
2119 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone IVB (TW-1 &TW-II), Zone-V (TW I&II) at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 306/HD | 20/01/2023 | 817 | CARBON SERVICES INDIA | 68.08 | 48.38 | 71.05 | 100
2120 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Road Restoration, Supply and Fabrication of 700 mm Dia, 7.10 mm thick MS Casing Pipe and Pushing of Casing Pipe by Hydraulic Jack Pushing Method, Construction of RCC Retaining Wall, Land Development, Construction of 1 No. Culvert and ancillary works at Bargachia PWSS (Zone-VII, VIII & IX) of J.B. Pur Block under Howrah Sadar Sub-Division, Howrah Division, P.H.E. Dte.(SM/14095) | 3057/HD | 08/07/2025 | 75 | REALIENCE CONSTRUCTION | 413.83 | 0 | 0 | 0
2121 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Piped Water Supply Schemes in different Blocks in the District of Howrah under Howrah Division, PHE Dte. | 3730/HD | 29/08/2024 | 30 | HORIZEN | 4.93 | 0 | 0 | 100
2122 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- V, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008227628 Reference ID- 106835520 SM Code- 14095 | 655 | 09/01/2025 | 0 | WBSEDCL | 9.41 | 0 | 0 | 0
2123 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Sifting Quotation as per as approval from DM HDD-II IRO E Office No.-400759 Application No- 100000138749 Reference ID- 860336080 SM Code- 14095 | 42151 | 30/07/2025 | 0 | WBSEDCL | 1.88 | 0 | 0 | 0
2124 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Special repair work (Bituminous Portion) for restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road Jagatballavpur Munsirhat to Ichanagari at Jagatballavpur Block, Pacakage No-WB/09/17 Howrah under WBSRDA Howrah Division-I. |  | 06/11/2025 | 0 | WBSRDA-I | 16.68 | 0 | 0 | 0
2125 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Special repair work (Bituminous Portion) for restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road "Godaripara - Dulepara L047" at Jagatballavpur Block, Pkg No WB/09/135, Howrah undert W.B.S.R.D.A. Howrah Division-I. |  | 28/04/2025 | 0 | WBSRDA | 15.84 | 0 | 0 | 0
2126 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Special repair work for restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipeline for the PMGSY road "Ghoshpara to Khadarghat" at Jagatballavpur Block, Howrah under W.B.S.R.D.A. Howrah Division-I Package No. - WB/09/46. |  | 25/06/2025 | 0 | WBSRDA-I | 26.01 | 0 | 0 | 0
2127 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Special repair work (Bituminous Portion) for restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road "T05 Bramhapara - Aimachak and Naikul to Nabason Road L044" at Jagatballavpur Block, Pkg No WB/09/144, Howrah under W.B.S.R.D.A. Howrah Division-I. |  | 28/04/2025 | 0 | WBSRDA | 14.89 | 0 | 0 | 0
2128 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | The Augmentation Scheme Of Bargachia Pwss Under Howrah Division Application No- 100000128111 Reference ID- 860323061 SM Code- 14095 | 693 | 31/01/2025 | 0 | WBSEDCL | 1.67 | 0 | 0 | 0
2129 | HOWRAH | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Quotation money deposition for new service connection at Amoragori w/s scheme, T.W. No.-VI, Dist.-Howrah under PHE Dte. Application No- 1008321283 Reference ID- 106898028 SM Code- 14095 | 42151 | 30/07/2025 | 0 | WBSEDCL | 25.1 | 0 | 0 | 0
2130 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone III (TW-1 &TW-II), Zone-IVA (TW I&II) at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 305/HD | 20/01/2023 | 917 | B K ENTERPRISE | 69.42 | 50.09 | 72.16 | 100
2131 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Jagatballavpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4814/HD | 19/11/2024 | 510 | HORIZEN | 10.11 | 4.33 | 72.62 | 56
2132 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Supplying fabrication of 600 mm dia 10 mm thick MS casing pipe and pushing of casing pipe by Hydraulic Jack pushing method to Cross Water carrier Pipe (Between Node Point 134 to 153 of LDS drawing) between Patihal-Bargachia Station at KM HA-22/15-16 (35/15-16) (WL-58) and Pipe (Between Node Point 242 to 259 of LDS drawing) between Patihal-Bargachia Station at KM HA-22/23-24 (35/23-24) (WL-59) of Bargachia Zone-II Water Supply Scheme of Howrah Sadar Sub-Division, under Howrah Division P.H.E. Dte. (SM/14095) | 2339/HD | 14/05/2025 | 180 | JOY GURU TRADING | 109.35 | 0 | 0 | 50
2133 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Bargachia Zone-4A, Bargachia Zone-4B, Bargachia Zone-5 PWSS [SM/14059] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 218-A/HSSD | 24/02/2025 | 15 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
2134 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Bargachia Zone-9, Bargachia Zone-10 PWSS [SM/14059] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 221-A/HSSD | 25/02/2025 | 15 | JHARNA ENTERPRISE | 0.57 | 0 | 0 | 100
2135 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Bargachia Zone-1, Bargachia Zone-2, Bargachia Zone-3 PWSS [SM/14059] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 218/HSSD | 24/02/2025 | 15 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
2136 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division , SM/14095 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Jagatballavpur Block) | 4129/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.78 | 0 | 0 | 100
2137 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Solarisation of WBSEDCL energised electrical installation at different PWSS in the district of Howrah under Electrical Division, PHE Dte. | 3085/ED | 17/07/2023 | 184 | A.K. INDUSTRIES | 119.89 | 80.39 | 67.06 | 80
2138 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Gouripur w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008708286 Consumer ID- 103301846 SM Code- 16446 |  | 07/08/2025 | 0 | WBSEDCL | 0.22 | 0 | 0 | 0
2139 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Bauria w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008481242 Consumer ID- 103988694 SM Code : 16446 | 42151 | 30/07/2025 | 0 | WBSEDCL | 0.33 | 0 | 0 | 0
2140 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Hallyan w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007859351 Consumer ID- 133191636 SM Code- 16446 |  | 19/08/2025 | 0 | WBSEDCL | 0.5 | 0 | 0 | 0
2141 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Kanupat w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008688598 Consumer ID- 135073173 SM Code- 16446 |  | 07/08/2025 | 0 | WBSEDCL | 0.45 | 0 | 0 | 0
2142 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Deposit of application fees money for Solar Power Plant Application No- 1008132714 Consumer ID- 103286247 SM Code- 16446 |  | 30/05/2025 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2143 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Deposit of application fees money for Solar Power Plant Application No- 1008376696 Consumer ID- 135110959 SM Code- 16446 |  | 30/05/2025 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2144 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Benapur w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007859432 Consumer ID- 101325135 SM Code- 16446 |  | 19/08/2025 | 0 | WBSEDCL | 0.22 | 0 | 0 | 0
2145 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Deposit of application fees money for Solar Power Plant Application No- 1008376628 Consumer ID- 100567011 SM Code- 16446 |  | 30/05/2025 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2146 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Majukhetra w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007608539 Consumer ID- 104645481 SM Code- 16446 |  | 30/05/2025 | 0 | WBSEDCL | 0.31 | 0 | 0 | 0
2147 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Jagannathpur w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007608590 Consumer ID- 106026058 SM Code- 16446 |  | 30/05/2025 | 0 | WBSEDCL | 0.31 | 0 | 0 | 0
2148 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Kashmoli w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008132714 Consumer ID- 103286247 SM Code- 16446 |  | 12/11/2025 | 0 | WBSEDCL | 0.3 | 0 | 0 | 0
2149 | HOWRAH | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. , SM/16446 | Solarisation | Deposit of application fees for Solar Power Plant Application No- 1008176341 Consumer ID- 104525267 SM Code : 16446 | 42151 | 30/07/2025 | 0 | WBSEDCL | 0.26 | 0 | 0 | 0
2150 | HOWRAH | Howrah Division | Chak Kadamtala Piped Water Supply scheme , SM/16557 | New | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | 2155/H.D | 07/06/2023 | 1021 | MONDAL PRECISION PVT. LTD. | 330.32 | 0 | 0 | 80
2151 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Material Requisition To Resource Division | 1754/HD | 26/04/2023 | 0 | Resource Division | 44.93 | 0 | 0 | 0
2152 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Material Requisition To Resource Division | 4414/HD | 07/12/2023 | 0 | Resource Division | 45.12 | 0 | 0 | 0
2153 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Material Requisition To Resource Division | 3396/HD | 21/09/2023 | 0 | Resource Division | 48.32 | 0 | 0 | 0
2154 | HOWRAH | Electrical | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Quotation Bill for New Service Connection at Kamina W/S. Sch. TW-II | 422 | 10/11/2023 | 0 | WBSEDCL | 18 | 0 | 0 | 0
2155 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Original quotation of WBSEDCL for Kamina Water Supply Scheme | BP-2023-24-485 | 23/11/2023 | 0 | WBSEDCL | 22.69 | 0 | 0 | 0
2156 | HOWRAH | Electrical | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kamina water supply scheme, T.W. No.- I & II, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | 1998/ED | 19/05/2023 | 90 | MENAKA ENTERPRISE | 22.87 | 14.9 | 65.13 | 40
2157 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Work Order for Preparation of DPR for new piped water supply scheme of Kamina PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 246/HD | 07/02/2022 | 15 | DULAL MAJUMDER | 3.44 | 0 | 0 | 100
2158 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
2159 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Work Order for Sinking of 7 (Seven) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Bamunhati PWSS (3 nos) & Kamina PWSS (2 nos) & Barramnagar PWSS (2 nos) of Uluberia - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 1195/HD | 23/03/2023 | 847 | ACME CONSTRUCTION | 90.87 | 25.73 | 98.96 | 85
2160 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Work Order for Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials for in Kamina PWSS of Uluberia-II Block under Uluberia Sub Division under Howrah Division P.H.E. Dte. in the District of Howrah. | 1593/HD | 12/04/2023 | 1200 | ARUP NANDY | 138.34 | 37.81 | 27.33 | 90
2161 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Kamina PWSS of Uluberia-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-B) | 1190/HD | 23/03/2023 | 45 | M/S ANUBHAB CONSTRUCTION | 92.63 | 21.9 | 23.64 | 100
2162 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Kamina PWSS of Uluberia-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-C) | 1191/HD | 23/03/2023 | 758 | SUSHANTA MONDAL | 27.98 | 13.23 | 51.22 | 100
2163 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Kamina PWSS of Uluberia-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-A) | 1690/HD | 20/04/2023 | 721 | JAHANGIR ALAM | 263.67 | 233.49 | 96.38 | 100
2164 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
2165 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC , SM/16927 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4816/HD | 19/11/2024 | 510 | TECH VISION | 12.48 | 0 | 0 | 78
2166 | HOWRAH | Howrah Division | Shibgachhia Piped Water Supply Scheme , SM/18193 | New | Preparation of DPR for new piped water supply scheme of Shibgachia PWSS, Amta-II Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | 455/AE/USD | 15/09/2022 | 45 | VOYAGER | 3.2 | 2.72 | 84.87 | 0
2167 | HOWRAH | Howrah Division | Shibgachhia Piped Water Supply Scheme , SM/18193 | New | Material Requisition To Resource Division | 4184/HD | 22/11/2023 | 0 | Resource Division | 23.18 | 0 | 0 | 0
2168 | HOWRAH | Electrical | Shibgachhia Piped Water Supply Scheme , SM/18193 | New | Quotation Bill for New Service Connection at Sibgachia W/S. Sch. | 550 | 21/12/2023 | 0 | WBSEDCL | 5.62 | 0 | 0 | 0
2169 | HOWRAH | Electrical | Shibgachhia Piped Water Supply Scheme , SM/18193 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Shibgachhia water supply scheme, T.W. No. I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | 1909/ED | 12/05/2023 | 90 | A.G. ENTERPRISE | 20.49 | 9.96 | 48.6 | 50
2170 | HOWRAH | Howrah Division | Shibgachhia Piped Water Supply Scheme , SM/18193 | New | Display Board at different PWSS at Amta-II Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 3220/AE/USD | 12/03/2024 | 30 | ABONTICA ENTERPRISE | 4.76 | 4.76 | 100 | 100
2171 | HOWRAH | Howrah Division | Shibgachhia Piped Water Supply Scheme , SM/18193 | New | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 2.4 | 0 | 0 | 0
2172 | HOWRAH | Electrical | Shibgachhia Piped Water Supply Scheme , SM/18193 | New | Quotation for new service connection for Shibgachchia water supply scheme, Tubewell No. II, Block: Amta-II, Howrah SM/18193 Application No. 1007523518 Reference id: 106465462 | 756 | 16/02/2024 | 0 | WBSEDCL | 7.89 | 0 | 0 | 0
2173 | HOWRAH | Howrah Division | Shibgachhia Piped Water Supply Scheme , SM/18193 | New | Sinking of 2 nos Tube Well, Laying Distribution System & Construction of 100 cum RCC OHR & Interconnection between Tubewells & OHR for SHIBGACHHIA PWSS OF AMTA-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE | 2646/HD | 18/07/2023 | 1006 | MITHU BUILDERS | 262.08 | 126.66 | 48.33 | 70
2174 | HOWRAH | Howrah Division | Shibgachhia Piped Water Supply Scheme , SM/18193 | New | Construction of 2nos switch room (5.40m x 3.60m) with water supply & sanitary arrangement at Head Work site & 2nd TW site of Shibgachia PWSS [SM/18193] of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 4340/HD | 04/12/2023 | 660 | KALIDAS ENTERPRISE | 12.56 | 6.1 | 48.68 | 100
2175 | HOWRAH | Howrah Division | Shibgachhia Piped Water Supply Scheme , SM/18193 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0.67 | 100 | 100
2176 | HOWRAH | Howrah Division | Shibgachhia Piped Water Supply Scheme , SM/18193 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
2177 | HOWRAH | Howrah Division | Shibgachhia Piped Water Supply Scheme , SM/18193 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
2178 | HOWRAH | Electrical | Source Augmentation of Sahapur Piped Water Supply Scheme , SM/18844 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Sahapur Piped Water Supply Scheme Block- Panchla District- Howrah under JJM Program under Electrical Division PHE Dte. | 4536/ED | 23/11/2023 | 90 | MUKHERJEE ART CENTRE | 10.68 | 0 | 0 | 0
2179 | HOWRAH | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme , SM/18844 | Augmentation | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Sahapur piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) | 337/HD | 17/02/2022 | 30 | UNIVERSAL CONSTRUCTION | 2.98 | 1.31 | 100 | 100
2180 | HOWRAH | Electrical | Source Augmentation of Sahapur Piped Water Supply Scheme , SM/18844 | Augmentation | Quotation money deposition for new service connection at Sahapur w/s scheme, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008116886 Reference ID- 106763473 SM Code- 18844 | 474 | 01/10/2024 | 0 | WBSEDCL | 5.78 | 0 | 0 | 0
2181 | HOWRAH | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme , SM/18844 | Augmentation | Connection with distribution system and reconnection of FHTC & allied works, construction of 1 (One) no.pump house (5.40m x 3.60m),construction of 1 (One) no. boundary wall at Sahapur piped water supply scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 1067/HD | 04/03/2024 | 60 | ADITYA HAZRA | 50.59 | 0 | 0 | 30
2182 | HOWRAH | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme , SM/18844 | Augmentation | Sinking 1No. 250 X 150 mm Dia and 240 m deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30m. length having 250 mm dia. 60m. long PVC housing pipe & 150 mm dia. 150m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Sahapur PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 1009/HD | 01/03/2024 | 270 | AUXILIARY TUBEWELL DRILLERS | 14.59 | 0 | 0 | 100
2183 | HOWRAH | Electrical | Source Augmentation of Sahapur Piped Water Supply Scheme , SM/18844 | Augmentation | Shifting of oh line along with dp installed for placing DTR for PHE at village Sahapur under Burikhali CCC. Application No- 100000126832 Reference ID- 860322112 SM Code- 18844 | 668 | 21/01/2025 | 0 | WBSEDCL | 0.48 | 0 | 0 | 0
2184 | HOWRAH | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme , SM/18844 | Augmentation | Preparation of DPR for Source Augmentation for Sahapur PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. | 826/HSSD | 09/08/2024 | 15 | APEX ENGINEERING | 0.78 | 0 | 0 | 0
2185 | HOWRAH | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme , SM/18844 | Augmentation | Design,drawing, construction including rcc foundation and commissioning of iron elimination plant of capacity 50.00 cum per hours including 3(three) month trial run in the premises, construction of 3.60m X 3.00m size Blower room of compressure for IEP, at Sahapur PWSS Under Howrah Sadar Sub-Division of Howrah division P.H.E Dte. | 2890/HD | 25/06/2024 | 540 | NEER UDYOG | 24.38 | 0 | 0 | 100
2186 | HOWRAH | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme , SM/18844 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Sahapur PWSS [SM/18844], and Beldubi PWSS [SM/04274] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 230/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.57 | 0 | 0 | 100
2187 | HOWRAH | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme , SM/18844 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Source Augmentation of Beldubi Water Supply Scheme [SM/18845], Source Augmentation of Bikihakola Water Supply Scheme [SM/18846], Source Augmentation of Sahapur Piped Water Supply Scheme [SM/18844] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 233/HSSD | 28/02/2025 | 15 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
2188 | HOWRAH | Howrah Division | Source Augmentation of Balichak Water Supply Scheme , SM/18885 | Augmentation | Additional Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Balichack PWSS SM/18885 of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1305/HD | 14/03/2024 | 60 | ACME CONSTRUCTION | 29.98 | 28.06 | 100 | 100
2189 | HOWRAH | Electrical | Source Augmentation of Balichak Water Supply Scheme , SM/18885 | Augmentation | Quotation money deposition for new service connection at Ballychak(Khalrah High School) w/s scheme, T.W. No.-VI, Dist.-Howrah under PHE Dte. Application No- 1008185087 Reference ID- 106811234 SM Code- 18885 | BP-24-25-580 | 19/11/2024 | 0 | WBSEDCL | 25.61 | 0 | 0 | 0
2190 | HOWRAH | Electrical | Source Augmentation of Balichak Water Supply Scheme , SM/18885 | Augmentation | Quotation money deposition for new service connection at Balichak w/s scheme, T.W. No.-V, Dist.-Howrah under PHE Dte. Application No- 1007772492 Reference ID- 106595796 SM Code- 18885 | 164 | 28/05/2024 | 0 | WBSEDCL | 5.63 | 0 | 0 | 0
2191 | HOWRAH | Electrical | Source Augmentation of Balichak Water Supply Scheme , SM/18885 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Balichak Water Supply Scheme Block- Amta-I District- Howrah under JJM Program under Electrical Division PHE Dte. | 4533/ED | 23/11/2023 | 571 | GHOSE ENGINEERING SYNDICATE | 21.91 | 0 | 0 | 50
2192 | HOWRAH | Howrah Division | Source Augmentation of Balichak Water Supply Scheme , SM/18885 | Augmentation | Additional laying distribution pipeline with FHTC at Balichack PWSS SM/18885 of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 3164/HD | 12/07/2024 | 420 | RANA ENTERPRISE | 34.95 | 0 | 0 | 100
2193 | HOWRAH | Howrah Division | Source Augmentation of Balichak Water Supply Scheme , SM/18885 | Augmentation | Additional construction of 1nos switch room (5.4x 3.6) at 4th TW site and laying distribution pipeline with FHTC at Balichack PWSS SM/18885 of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 2858/HD | 24/06/2024 | 210 | RANI CONSTRUCTION | 6.28 | 0 | 0 | 100
2194 | HOWRAH | Howrah Division | Source Augmentation of Balichak Water Supply Scheme , SM/18885 | Augmentation | Additional construction of 1nos switch room (5.4x 3.6) at 5th TW site and laying distribution pipeline with FHTC at Balichack PWSS SM/18885 of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 3165/HD | 12/07/2024 | 540 | ARUSHI CONSTRUCTION | 6.28 | 0 | 0 | 100
2195 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-B) (for Kasra Mouza (Part) | 1503/HD | 04/11/2020 | 30 | PRADIP KUMAR JATI | 28.98 | 0 | 0 | 0
2196 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-A) (for Bara Mahara Mouza) | 1515/HD | 04/11/2020 | 30 | PRADIP KUMAR JATI | 30.15 | 3.19 | 10.57 | 0
2197 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-C) (for Kasra Mouza (Part) | 1504/HD | 04/11/2020 | 30 | DEV DAS SHOW | 18.74 | 0 | 0 | 0
2198 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | 844327 | 17/03/2021 | 0 | JAHANGIR ALAM | 26.44 | 0 | 0 | 0
2199 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | 844330 | 17/03/2021 | 0 | M/S ASHIRBAD (INDIA) | 27.58 | 0 | 0 | 0
2200 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme. | 8443106 | 30/03/2021 | 0 | NATURAL RESOURCES CONSORTIUM | 21.16 | 0 | 0 | 0
2201 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | 84434 | 01/03/2021 | 0 | DEV DAS SHAW | 27.09 | 0 | 0 | 0
2202 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Retrofitting Khosalpur Water Supply Scheme | 84435 | 01/03/2021 | 0 | PRADIP KUMAR JATI | 24.12 | 0 | 0 | 0
2203 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) (Phase-1) | BP-2021-22-451 | 25/03/2022 | 0 | N. G ENGINEERING | 3.11 | 0 | 0 | 0
2204 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Additional Retrofitting Khoshalpur | BP-2021-22-387 | 07/03/2022 | 0 | JAHANGIR ALAM | 3.45 | 0 | 0 | 0
2205 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Additional Retrofitting Khoshalpur | BP-2021-22-385 | 08/03/2022 | 0 | JAHANGIR ALAM | 3.44 | 0 | 0 | 0
2206 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) | BP-2021-22-449 | 30/03/2022 | 0 | M/S ASHIRBAD (INDIA) | 4.52 | 0 | 0 | 0
2207 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (Phase-3) | 2231/HD | 09/12/2021 | 30 | PRADIP KUMAR JATI | 4.07 | 3.92 | 100 | 0
2208 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) , SM/06785 | Retrofitting | Work Order for Additional Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte.(Part-G) (Phase-I) | 111/AE/USD | 15/06/2022 | 45 | MAITY CONSTRUCTIONS | 4.89 | 0.6 | 100 | 100
2209 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) , SM/07008 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) [Tajpur Mouza part] | 1800/HD | 27/11/2020 | 30 | AYUSH ENTERPRISE | 12.97 | 0 | 0 | 0
2210 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) , SM/07008 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | 844341 | 20/03/2021 | 0 | AYUSH ENTERPRISE | 12.66 | 0 | 0 | 0
2211 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) , SM/07008 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | 8443110 | 30/03/2021 | 0 | JOY CHANDI CONSTRUCTION | 30.29 | 0 | 0 | 0
2212 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) , SM/07008 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | W/176 | 06/08/2021 | 0 | JAHANGIR ALAM | 29.23 | 0 | 0 | 0
2213 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) , SM/07008 | Retrofitting | Work Order for Additional laying of pipeline for retrofitting work for providing Functional Household Tap Connection(FHTC) at Tajpur Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Part-C) (Phase-I) | 1048/HD | 06/05/2022 | 30 | JAHANGIR ALAM | 4.33 | 4.13 | 95.48 | 0
2214 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) , SM/07008 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | 84437 | 04/01/2022 | 0 | JOY CHANDI CONSTRUCTION | 5.88 | 0 | 0 | 0
2215 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) , SM/07008 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) | 844330 | 21/02/2022 | 0 | AYUSH ENTERPRISE | 2.24 | 0 | 0 | 0
2216 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) , SM/07008 | Retrofitting | Work order for interconnection between Replaced new Tube Well and existing OHR at Udong W/s scheme of Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1059/HD | 06/05/2022 | 30 | JAHANGIR ALAM | 0.91 | 0.87 | 95.61 | 0
2217 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) , SM/06781 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-G) | 1539/HD | 05/11/2020 | 30 | UNIQUE AGENCY | 18.89 | 0 | 0 | 0
2218 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) , SM/06781 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-H) | 1540/HD | 05/11/2020 | 30 | UNIQUE AGENCY | 18.88 | 0 | 0 | 0
2219 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) , SM/06781 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-I) | 1541/HD | 05/11/2020 | 30 | A P POWER & CONCRETE | 18.85 | 0 | 0 | 0
2220 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) , SM/06781 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 8443116 | 30/03/2021 | 0 | MONIRUL ISLAM | 4.71 | 0 | 0 | 0
2221 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) , SM/06781 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 8443103 | 30/03/2021 | 0 | A.P. POWER & CONCRETE | 16.16 | 0 | 0 | 0
2222 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) , SM/06781 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 844318 | 20/01/2022 | 0 | MS ARPAN ENTERPRISE | 4.26 | 0 | 0 | 0
2223 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) , SM/06781 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | 844321 | 20/01/2022 | 0 | MONIRUL ISLAM | 4.31 | 0 | 0 | 0
2224 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) , SM/06781 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-X) | 844317 | 21/03/2022 | 0 | BUILT INDIA | 4.07 | 0 | 0 | 0
2225 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) , SM/06781 | Retrofitting | Retrofitting Gobindapur W/S Scheme. | 844334 | 30/03/2022 | 0 | ALOK ENTERPRISE | 15.52 | 0 | 0 | 0
2226 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) , SM/06781 | Retrofitting | Mass Awarness generation and IEC activities. | 844313 | 23/12/2021 | 0 | PRADIP KUMAR JATI | 42 | 0 | 0 | 0
2227 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) , SM/06781 | Retrofitting | Work Order for Laying of additional UPVC pipe line of 75 mm & 110mm dia,Total 450 mtr. Length for Retrofitting work for providing Functional Household Tap Connection (FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. within the Command area of Gobindapur PWSS under Howrah Sadar Sub Division of Howrah Division , PHE Dte. (Phase-III) | 338/HD | 17/02/2022 | 30 | BUILT INDIA | 2.52 | 0 | 0 | 0
2228 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-M) (for Ratanpota & Kashtasangara(Part) Mouza) | 1514/HD | 04/11/2020 | 30 | JAHANGIR ALAM | 25.61 | 0 | 0 | 0
2229 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-L) (for Kashtasangara(Part) | 1513/HD | 04/11/2020 | 30 | JAHANGIR ALAM | 27.43 | 0 | 0 | 0
2230 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Work Order for Additional Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte.(Part-G) (Phase-II) | 112/AE/USD | 15/06/2022 | 45 | BUNBA CONSTRUCTION | 4.9 | 4.9 | 99.9 | 0
2231 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Work Order for Additional laying of pipeline work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system (Majipara, Khosalpur, Kastosangra, Ratanpota) at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-F1) | 133/AE/USD | 20/06/2022 | 45 | JAHANGIR ALAM | 4.71 | 4.69 | 100 | 0
2232 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) (Phase-2) | BP-2021-22-451 | 25/03/2022 | 0 | N. G ENGINEERING | 3.1 | 0 | 0 | 0
2233 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) | BP-2021-22-449 | 30/03/2022 | 0 | M/S ASHIRBAD (INDIA) | 4.52 | 0 | 0 | 0
2234 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-C) (for Kasra Mouza (Part) | BP-2021-22-383 | 07/03/2022 | 0 | DEV DAS SHAW | 18.73 | 0 | 0 | 0
2235 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Cons of OHR Khoshalpur | BP-2021-22-324 | 16/02/2022 | 0 | NATURAL RESOURCES CONSORTIUM | 8.49 | 0 | 0 | 0
2236 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Construction of delivery spouts for filling movable water tanker in connection with flood prepardeness measure alongwith lying of tube well wash out with HDPE pipe of 4 nos Tube Wells of Khoshalpur Water Supply Scheme | BP-2021-22-384 | 07/03/2022 | 0 | JAHANGIR ALAM | 1.08 | 0 | 0 | 0
2237 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (Phase-2) | 2230/HD | 09/12/2021 | 30 | PRADIP KUMAR JATI | 4.07 | 4.05 | 100 | 0
2238 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (Phase-1) | 2229/HD | 09/12/2021 | 30 | PRADIP KUMAR JATI | 4.07 | 3.94 | 100 | 0
2239 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (Phase-2) | 2233/HD | 09/12/2021 | 30 | DEV DAS SHAW | 3.49 | 3.23 | 100 | 0
2240 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (Phase-1) | 2232/HD | 09/12/2021 | 30 | DEV DAS SHAW | 3.49 | 3.5 | 100 | 0
2241 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme , SM/06789 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (Phase-3) | 2243/HD | 09/12/2021 | 30 | DEV DAS SHAW | 3.49 | 3.4 | 100 | 0
2242 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-B) | 840/HD | 25/08/2020 | 30 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0 | 0
2243 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-C) | 841/HD | 25/08/2020 | 30 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0 | 0
2244 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-D) | 842/HD | 25/08/2020 | 30 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0 | 0
2245 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-G) | 845/HD | 25/08/2020 | 30 | N. G ENGINEERING | 4.56 | 0 | 0 | 0
2246 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-K) | 849/HD | 25/08/2020 | 30 | TIYASA ENTERPRISE | 4.56 | 0 | 0 | 0
2247 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-R) | 856/HD | 25/08/2020 | 30 | PRADIP KUMAR JATI | 4.56 | 0 | 0 | 0
2248 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-T) | 858/HD | 25/08/2020 | 30 | PRADIP KUMAR JATI | 4.56 | 0 | 0 | 0
2249 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-U) | 859/HD | 25/08/2020 | 30 | PRADIP KUMAR JATI | 4.56 | 0 | 0 | 0
2250 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-V) | 860/HD | 25/08/2020 | 30 | PRADIP KUMAR JATI | 4.56 | 0 | 0 | 0
2251 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-N) | 852/HD | 25/08/2020 | 30 | DEV DAS SHOW | 4.56 | 0 | 0 | 0
2252 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-X) | 862/HD | 25/08/2020 | 30 | TIYASA ENTERPRISE | 4.56 | 0 | 0 | 0
2253 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-Y) | 863/HD | 25/08/2020 | 30 | S.B. ENTERPRISE | 4.56 | 0 | 0 | 0
2254 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-Z) | 864/HD | 25/08/2020 | 30 | S.B. ENTERPRISE | 4.56 | 0 | 0 | 0
2255 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-Q) | 855/HD | 25/08/2020 | 30 | DEV DAS SHOW | 4.56 | 0 | 0 | 0
2256 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-E) | 843/HD | 25/08/2020 | 30 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0 | 0
2257 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-W) | 861/HD | 25/08/2020 | 30 | PRADIP KUMAR JATI | 4.56 | 0 | 0 | 0
2258 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-H) | 846/HD | 25/08/2020 | 30 | N. G ENGINEERING | 4.56 | 0 | 0 | 0
2259 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-I) | 847/HD | 25/08/2020 | 30 | N. G ENGINEERING | 4.56 | 0 | 0 | 0
2260 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-O) | 853/HD | 25/08/2020 | 30 | DEV DAS SHOW | 4.56 | 0 | 0 | 0
2261 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-P) | 854/HD | 25/08/2020 | 30 | DEV DAS SHOW | 4.56 | 0 | 0 | 0
2262 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-S) | 857/HD | 25/08/2020 | 30 | PRADIP KUMAR JATI | 4.56 | 0 | 0 | 0
2263 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-A) | 839/HD | 25/08/2020 | 30 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0 | 0
2264 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-J) | 848/HD | 25/08/2020 | 30 | N. G ENGINEERING | 4.56 | 0 | 0 | 0
2265 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-L) | 850/HD | 25/08/2020 | 30 | DEV DAS SHOW | 4.56 | 0 | 0 | 0
2266 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-M) | 851/HD | 25/08/2020 | 30 | DEV DAS SHOW | 4.56 | 0 | 0 | 0
2267 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-F) | 844/HD | 25/08/2020 | 30 | N. G ENGINEERING | 4.56 | 0 | 0 | 0
2268 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-Q | W/456 | 28/12/2020 | 0 | DEV DAS SHOW | 4.46 | 0 | 0 | 0
2269 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-S |  | 02/12/2020 | 0 | PRADIP KUMAR JATI | 4.49 | 0 | 0 | 0
2270 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-O | W/455 | 28/12/2020 | 0 | DEV DAS SHOW | 4.49 | 0 | 0 | 0
2271 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-L | W/452 | 28/12/2020 | 0 | DEV DAS SHOW | 4.43 | 0 | 0 | 0
2272 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/463 | 28/12/2020 | 0 | TIYASA ENTERPRISE | 4.45 | 0 | 0 | 0
2273 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-J) | W/465 | 29/12/2020 | 0 | N. G ENGINEERING | 4.47 | 0 | 0 | 0
2274 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Survey and Collection of houshold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme | W/508 | 18/01/2021 | 0 | STEELCONC AND ASSOCIATES | 4.73 | 0 | 0 | 0
2275 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-I) | W/464/4 | 30/12/2020 | 0 | N. G ENGINEERING | 4.47 | 0 | 0 | 0
2276 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F) | W/464 | 30/12/2020 | 0 | N. G ENGINEERING | 4.45 | 0 | 0 | 0
2277 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-H) | W/464/3 | 30/12/2020 | 0 | N. G ENGINEERING | 4.49 | 0 | 0 | 0
2278 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P | W/453 | 28/12/2020 | 0 | DEV DAS SHOW | 4.49 | 0 | 0 | 0
2279 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-W | W/466 | 30/12/2020 | 0 | PRADIP KUMAR JATI | 4.47 | 0 | 0 | 0
2280 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-G) | W/464/2 | 30/12/2020 | 0 | N. G ENGINEERING | 4.5 | 0 | 0 | 0
2281 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)Part-K | W/462 | 28/12/2020 | 0 | TIYASA ENTERPRISE | 4.46 | 0 | 0 | 0
2282 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F), (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-A) | W/457 | 28/12/2020 | 0 | M/S ASHIRBAD (INDIA) | 4.5 | 0 | 0 | 0
2283 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-N | W/454 | 28/12/2020 | 0 | DEV DAS SHOW | 4.49 | 0 | 0 | 0
2284 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-R | W/466 | 30/12/2020 | 0 | PRADIP KUMAR JATI | 4.47 | 0 | 0 | 0
2285 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-V | W/466/2 | 30/12/2020 | 0 | PRADIP KUMAR JATI | 4.46 | 0 | 0 | 0
2286 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) (Part-Z) | W/451 | 29/12/2020 | 0 | S.B. ENTERPRISE | 4.46 | 0 | 0 | 0
2287 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-Y) | W/451/1 | 29/12/2020 | 0 | S.B. ENTERPRISE | 4.44 | 0 | 0 | 0
2288 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-M | W/452/2 | 28/12/2020 | 0 | DEV DAS SHOW | 4.47 | 0 | 0 | 0
2289 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-T | W/466/4 | 30/12/2020 | 0 | PRADIP KUMAR JATI | 4.47 | 0 | 0 | 0
2290 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-U | W/466/3 | 30/12/2020 | 0 | PRADIP KUMAR JATI | 4.48 | 0 | 0 | 0
2291 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) , SM/06775 | Retrofitting | Work Order for Retrofitting work for Supply, delivery & installation of CIDF Sluice Valve in different Node point and construction of Sluice Valve chamber for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur PWSS under Howrah Sub Division of Howrah Division , PHE Dte. | 341/HD | 17/02/2022 | 30 | MONIRUL ISLAM | 4.47 | 0 | 0 | 0
2292 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-A) | 1390/HD | 16/10/2020 | 30 | DEV DAS SHOW | 4.57 | 0 | 0 | 0
2293 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-D) | 1393/HD | 16/10/2020 | 30 | PRADIP KUMAR JATI | 4.27 | 0 | 0 | 0
2294 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-F) | 1395/HD | 16/10/2020 | 30 | N. G ENGINEERING | 4.65 | 0 | 0 | 0
2295 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-G) | 1396/HD | 16/10/2020 | 30 | N. G ENGINEERING | 4.65 | 0 | 0 | 0
2296 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-L) | 1401/HD | 16/10/2020 | 30 | S.B. ENTERPRISE | 1.56 | 0 | 0 | 0
2297 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-E) | 1394/HD | 16/10/2020 | 30 | PRADIP KUMAR JATI | 2.81 | 0 | 0 | 0
2298 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-B) | 1391/HD | 16/10/2020 | 30 | DEV DAS SHOW | 4.5 | 0 | 0 | 0
2299 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-I) | 1398/HD | 16/10/2020 | 30 | M/S ASHIRBAD (INDIA) | 3.97 | 0 | 0 | 0
2300 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-J) | 1399/HD | 16/10/2020 | 30 | M/S ASHIRBAD (INDIA) | 3.78 | 0 | 0 | 0
2301 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-K) | 1400/HD | 16/10/2020 | 30 | S.B. ENTERPRISE | 2.3 | 0 | 0 | 0
2302 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-C) | 1392/HD | 16/10/2020 | 30 | PRADIP KUMAR JATI | 4.31 | 0 | 0 | 0
2303 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-H) | 1397/HD | 16/10/2020 | 30 | N. G ENGINEERING | 3.97 | 0 | 0 | 0
2304 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/178 | 14/08/2021 | 0 | S.B. ENTERPRISE | 11.99 | 0 | 0 | 0
2305 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/179 | 14/08/2021 | 0 | M/S ASHIRBAD (INDIA) | 21.8 | 0 | 0 | 0
2306 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/172 | 14/08/2021 | 0 | DEV DAS SHAW | 16.14 | 0 | 0 | 0
2307 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/177 | 14/08/2021 | 0 | PRADIP KUMAR JATI | 12.13 | 0 | 0 | 0
2308 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Work Order for Laying of 90mm dia,Node point 53-55, 55-57, 57-101, Total 940 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Laskarpur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-V) Part ¿A | 347/HD | 17/02/2022 | 30 | MONIRUL ISLAM | 4.07 | 0 | 0 | 0
2309 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-V) (Part-B) | 348/HD | 17/02/2022 | 30 | KRISH CONSTRUCTION | 2.53 | 0 | 0 | 0
2310 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) | 336/HD | 17/02/2022 | 30 | MONIRUL ISLAM | 3.96 | 2.34 | 100 | 0
2311 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | W/592 | 21/12/2021 | 0 | MONIRUL ISLAM | 3.32 | 0 | 0 | 0
2312 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Work Order for Retrofitting work for Supply, delivery & installation of CIDF Sluice Valve in different Node point and construction of Sluice Valve chamber for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur PWSS under Howrah Sub Division of Howrah Division , PHE Dte. | 84438 | 22/09/2022 | 0 | MONIRUL ISLAM | 8.49 | 0 | 0 | 0
2313 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Development Internal pathway and allied work at H/W of Laskarpur PWSS. | 844318 | 27/09/2022 | 0 | RAJLAKSHMI ENTERPRISE | 3.44 | 0 | 0 | 0
2314 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) , SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-K) | 844323 | 29/09/2022 | 0 | S.B. ENTERPRISE | 3.63 | 0 | 0 | 0
2315 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Pancharul PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 2110/HD | 24/11/2021 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.16 | 4.16 | 100 | 0
2316 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Work Order for Sinking of 2 (Two) nos PVC big dia Tube well 300 mm x 200 mm dia of 250 mtr deep for Augmentation of Pancharul W/S scheme at Udaynarayanpur Block in Uluberia Sub-Division P.H.E. Dte. under Howrah Division, P.H.E Dte. | 1268/HD | 17/06/2022 | 30 | M/S SYCHROTECH INDUSTRY | 34.92 | 32.83 | 94.01 | 0
2317 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Material Requisition To Resource Division | 2639/HD | 09/12/2022 | 0 | Resource Division | 21.34 | 0 | 0 | 0
2318 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
2319 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Work Order for Laying Distribution System & providing Functional Household Tap Connection(FHTC) Kakraipota Mouza (570 nos) from existing distribution system at Augementation of Pancharul Piped Water Supply Scheme under Udaynaraunpur Block under Howrah Division, PHE Dte. (Part-B). | 627/HD | 22/03/2022 | 45 | ADITYA HAZRA | 95.54 | 95.52 | 99.98 | 0
2320 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Pancharul water supply scheme, T.W. No. II (Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 496/HMSD | 02/03/2023 | 30 | SUDIKSHA CONSTRUCTION | 3.95 | 2.8 | 100 | 100
2321 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pancharul water supply scheme, T.W. No.- II (Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 2106/HMSD | 24/11/2022 | 30 | WIZARDTECH SOLUTION | 4.67 | 4.67 | 100 | 0
2322 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Installation of departmentally supplied submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pancharul water supply scheme, T.W. No. I(Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 2147/HMSD | 29/11/2022 | 7 | DAS ENTERPRISE | 0.63 | 0.6 | 100 | 0
2323 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Supply, delivery of submersible pumping machinery and other electrical/ mechanical equipments etc. for Pancharul water supply scheme, T.W. No. I(Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 2064/HMSD | 22/11/2022 | 7 | DAS ENTERPRISE | 0.97 | 0.97 | 100 | 0
2324 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Supply, delivery of electrical/ mechanical equipments for Pancharul water supply scheme, T.W. No. I(Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | 2063/HMSD | 22/11/2022 | 7 | DAS ENTERPRISE | 0.96 | 0.96 | 100 | 0
2325 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 21.34 | 0 | 0 | 0
2326 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Material Requisition To Resource Division | 2753/HD | 28/07/2023 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2327 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Work Order for Laying Distribution System & providing Functional Household Tap Connection(FHTC) Pancharul Mouza for (1567 nos) from existing distribution system at Augmentation of Pancharul Piped Water Supply Scheme under Udaynaraunpur Block under Howrah Division, PHE Dte. Pancharul Mouza for 1567 nos (Part-C) | 1002/HD | 02/05/2022 | 45 | CREATION CONSTRUCTION | 121.95 | 121.94 | 100 | 100
2328 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Work Order for Laying Distribution System & providing Functional Household Tap Connection(FHTC) Subal Chack Mouza for (372 nos) from existing distribution system at Augmentation of Pancharul Piped Water Supply Scheme under Udaynaraunpur Block under Howrah Division, PHE Dte. (Part-D) | 626/HD | 22/03/2022 | 45 | MODERN CONSTRUCTION | 59.54 | 58.1 | 100 | 100
2329 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Additional Laying of distribution pipeline with FHTC at Mouza-Kakraipota for Augmentation of Pancharul PWSS of Udaynarayanpur Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 2646/HD | 07/06/2024 | 60 | ADITYA HAZRA | 50.3 | 43.92 | 100 | 100
2330 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Work Order for "Augmentation of Pancharul Water Supply scheme by Laying Distribution System, providing Functional Household Tap Connection(FHTC) work with GEO tagging of using Jal Swapna App, Construction of R.C.C Elevated Reservoir of Capacity 500 m3 of Staging Height 20 mtr including Soil Investigation, interconnection & Rising main between 2nd TW, 1st Tube well (HW site) & OHR under Howrah Division, P.H.E. Dte. (Part-A)" | 1338/HD | 27/06/2022 | 947 | JAHANGIR ALAM | 232.99 | 124.52 | 63.2 | 100
2331 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul , SM/09348 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4813/HD | 19/11/2024 | 510 | HORIZEN | 13.59 | 0 | 0 | 70
2332 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Rudrapur PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | 80/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.29 | 3.29 | 100 | 100
2333 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Work Order for Sinking of 3 (Three) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Rudrapur PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 176/HD | 13/01/2023 | 45 | DEV DAS SHAW | 37.79 | 37.48 | 100 | 100
2334 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Material Requisition To Resource Division | 1748/HD | 25/04/2023 | 0 | Resource Division | 53.99 | 0 | 0 | 0
2335 | HOWRAH | Electrical | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Quotation money deposition for Rudrapur W/S , P.H No-I | 22 | 04/05/2023 | 0 | WBSEDCL | 0.69 | 0 | 0 | 0
2336 | HOWRAH | Electrical | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Quotation bill for service connection charge for Rudrapur w/s scheme, TW III | 500 | 07/12/2023 | 0 | WBSEDCL | 11.71 | 0 | 0 | 0
2337 | HOWRAH | Electrical | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | New service connection for Rudrapur pwss P.H No.-II | 159 | 03/08/2023 | 0 | WBSEDCL | 3.44 | 0 | 0 | 0
2338 | HOWRAH | Electrical | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Quotation Bill for New Service Connection at Rudrapur W/S. Sch. | 168 | 04/08/2023 | 0 | WBSEDCL | 0.33 | 0 | 0 | 0
2339 | HOWRAH | Electrical | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Deposition of additional quotation money for Rudrapur w/s scheme P.H No.-I ,Dist- Howrah under ED PHED. |  | 07/06/2023 | 0 | WBSEDCL | 1.86 | 0 | 0 | 0
2340 | HOWRAH | Electrical | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Quotation Bill for New Service Connection at Domjur, Rudrapur W/S. Sch. PH-I | 64 | 08/06/2023 | 0 | WBSEDCL | 1.86 | 0 | 0 | 0
2341 | HOWRAH | Electrical | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | new service connection for Rudrapur pwss , P.H No.-III | 157 | 03/08/2023 | 0 | WBSEDCL | 14.97 | 0 | 0 | 0
2342 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Additional carriage of OHR materials & allied works of Rurdrapur PWSS at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | 1239/HD | 12/03/2024 | 45 | N. G ENGINEERING | 6.67 | 6.46 | 100 | 100
2343 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 17.01 | 0 | 0 | 0
2344 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Work Order for Construction for 3(Three) Nos.Pump House (5.40m x 3.60 m), Boundary Wall at Head work Site, 2(Two) nos. Boundary Walls (other sites), Rising Main Pipeline Work & Laying Distribution Pipeline work with Functional Household Tap Connection of Rudrapur PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | 723/HD | 23/02/2023 | 904 | PRADIP KUMAR JATI | 290 | 263.25 | 90.78 | 70
2345 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Restoration of damaged concrete roads due to laying of pipe line at Rudrapur PWSS under Howrah Sadar Sub-Division PHE Dte. | 923/HD | 17/02/2025 | 375 | PRADIP KUMAR JATI | 70.93 | 0 | 0 | 0
2346 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Emergency Restoration of CI/DI Pipeline (Node No. 2 to 101) along with damaged main road due to laying of pipe line of Rudrapur PWSS under Howrah Sadar Sub-Divnision PHE Dte. | 891/HD | 11/02/2025 | 150 | REALIENCE CONSTRUCTION | 96.76 | 0 | 0 | 70
2347 | HOWRAH | Electrical | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rudrapur water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 3519/ED | 30/12/2022 | 450 | ORIENTAL ENGINEERING CO. | 34.24 | 33.19 | 97.58 | 98
2348 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Work Order for Construction Of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/06/2012) Including All pipe Connection Of Rudrapur PWSS In Domjur Block Of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | 1740/HD | 25/04/2023 | 707 | N. G ENGINEERING | 147.33 | 59.18 | 37.55 | 21
2349 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Additional Laying Distribution Pipeline with FHTC For Uncovered Area of Rudrapur Piped Water Supply Scheme under Howrah Sadar Sub-Division PHE Dte. | 4186/HD | 26/09/2024 | 116 | PRADIP KUMAR JATI | 41.95 | 0 | 0 | 100
2350 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Permanent restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road "Wadhipur - Makardaha Bazar" of Domjur Block, Howrah under W.B.S.R.D.A. Howrah Division-I. (Package No WB/09/08). |  | 19/05/2025 | 0 | WBSRDA | 21.82 | 0 | 0 | 0
2351 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. , SM/11515 | New | Supplying,fitting,fixing and erecting of Display Board at Domjur Zone -VIII PWSS [SM/14155], Rudrapur PWSS [SM/14515], Bhandardaha PWSS [SM/14197] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 224/HSSD | 27/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
2352 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Preparation of DPR for new piped water supply scheme of Sonamui PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 238/HD | 07/02/2022 | 15 | RADIANT | 3.61 | 3.61 | 100 | 0
2353 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sonamui PWSS of Amta-I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 2716/HD | 14/12/2022 | 45 | AQUATECH ENGINEERS | 36.21 | 35.81 | 100 | 0
2354 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Laying Distribution Pipe Lines With Allied Works For Sonamoui Water Supply Scheme In Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-D) | 2368/HD | 18/11/2022 | 45 | M/S MOINAK POREL | 90 | 81.22 | 100 | 100
2355 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Laying Distribution Pipe Lines With Allied Works For Sonamoui Water Supply Scheme In Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-B) | 2366/HD | 18/11/2022 | 45 | S RAHA ENTERPRISE | 82.51 | 78.81 | 100 | 100
2356 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Laying Distribution Pipe Lines With Allied Works For Sonamoui Water Supply Scheme In Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) | 2367/HD | 18/11/2022 | 45 | BISWAJIT BAG | 86.2 | 85.57 | 100 | 100
2357 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at 2nd TW site at Sonamui PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1946/HD | 10/05/2023 | 60 | KALIDAS ENTERPRISE | 7.18 | 7.18 | 100 | 100
2358 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 56.07 | 0 | 0 | 0
2359 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Material Requisition To Resource Division | 1698/HD | 21/04/2023 | 0 | Resource Division | 3.22 | 0 | 0 | 0
2360 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Material Requisition To Resource Division | 2753/HD | 28/07/2023 | 0 | Resource Division | 15.4 | 0 | 0 | 0
2361 | HOWRAH | Electrical | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Quotation Bill for New Service Connection at Sonamui W/S. Sch. PH-I | 59 | 05/06/2023 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2362 | HOWRAH | Electrical | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | New Service Connection at Sonamui W/S. SCh. PH-I | 47 | 24/05/2023 | 0 | WBSEDCL | 17.81 | 0 | 0 | 0
2363 | HOWRAH | Electrical | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Quotation Bill for New Service Connection at Sonamui W/S. Sch. PH-II | 47 | 24/05/2023 | 0 | WBSEDCL | 10.43 | 0 | 0 | 0
2364 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-21) | 2379/HD | 18/11/2022 | 30 | A.N ROY & CO | 10.15 | 8.67 | 100 | 100
2365 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-11) | 2254/HD | 04/11/2022 | 30 | ABONTICA ENTERPRISE | 20.83 | 15.33 | 100 | 100
2366 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-2) | 2245/HD | 04/11/2022 | 30 | AMIT CONSTRUCTION | 32.09 | 22.13 | 100 | 100
2367 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Laying Distribution Pipe Lines With Allied Works For Sonamoui Water Supply Scheme In Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-E) | 2369/HD | 18/11/2022 | 45 | JAI BHARAT COMMERCIAL CORPORATION | 79.6 | 43.03 | 100 | 100
2368 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-13) | 2371/HD | 18/11/2022 | 30 | BINOY KOLEY | 10.13 | 8.67 | 100 | 100
2369 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Oder for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-9) | 2252/HD | 04/11/2022 | 30 | ABONTICA ENTERPRISE | 20.76 | 18.9 | 100 | 100
2370 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-10) | 2253/HD | 04/11/2022 | 30 | UNIVERSAL CONSTRUCTION | 20.72 | 15.14 | 100 | 100
2371 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme in Amta-I Block under Howrah Division, PHE Dte.(Part-5) | 2248/HD | 04/11/2022 | 30 | M/S B.S.P. ENTERPRISES | 33.03 | 23.98 | 100 | 100
2372 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-12) | 2370/HD | 18/11/2022 | 30 | S.M. CONSTRUCTION | 10.15 | 9.02 | 100 | 100
2373 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-14) | 2372/HD | 18/11/2022 | 30 | M/S AHAMED CONSTRUCTION | 10.06 | 7.62 | 100 | 100
2374 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-15) | 2373/HD | 18/11/2022 | 30 | MONIRUL ISLAM | 10.01 | 7.62 | 100 | 100
2375 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-16) | 2374/HD | 18/11/2022 | 30 | MAITY CONSTRUCTIONS | 9.7 | 8.11 | 100 | 100
2376 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Oder for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-8) | 2251/HD | 04/11/2022 | 30 | MS ARPAN ENTERPRISE | 20.64 | 17.62 | 100 | 100
2377 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-18) | 2376/HD | 18/11/2022 | 30 | ADRIJA ENTERPRISE | 10.09 | 7.62 | 100 | 100
2378 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-6) | 2249/HD | 04/11/2022 | 30 | S.S ENTERPRISE | 20.52 | 17.25 | 100 | 100
2379 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-19) | 2377/HD | 18/11/2022 | 30 | KRISH CONSTRUCTION | 10.16 | 8.74 | 100 | 100
2380 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-20) | 2378/HD | 18/11/2022 | 30 | DEBABRATA CHAKRABORTY | 10.16 | 9.01 | 100 | 100
2381 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-1)Number of FHTC to be provided (Approx):320 | 2990/HD | 29/12/2022 | 30 | RANA ENTERPRISE | 34.79 | 22.01 | 100 | 100
2382 | HOWRAH | Electrical | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sonamui water supply scheme, T.W. No.- I & II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | 3524/ED | 30/12/2022 | 90 | SANKAR PRASAD DUTTA & CO. | 22.35 | 22.35 | 100 | 100
2383 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-7) | 2250/HD | 04/11/2022 | 30 | ABONTICA ENTERPRISE | 20.72 | 19.13 | 100 | 100
2384 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site at Sonamui PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1945/HD | 10/05/2023 | 60 | M/S KANIKA ROY ENTERPRISE | 7.18 | 7.18 | 100 | 100
2385 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work order for Interconnection between Tube wells & OHR at Sonamui Water Supply scheme at Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | 1947/HD | 10/05/2023 | 60 | BHOLA NATH CONSTRUCTION | 13.13 | 12.03 | 100 | 100
2386 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-17) | 2375/HD | 18/11/2022 | 30 | APEX ENGINEERING | 10.12 | 8.08 | 100 | 95
2387 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Land Development & Approach Road at 2nd TW site of Sonamoi PWSS of Amta-I Block under Uluberia Sub Division under Howrah Divison PHED. | 1294/AE/USD | 17/12/2024 | 100 | APST TASTIC DEVELOPERS PRIVATE LIMITED | 0.86 | 0 | 0 | 100
2388 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Construction of boundary wall at HW Site of Sonamoi W/S scheme within Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1810/HD | 08/04/2025 | 60 | M/S JOY | 29.15 | 0 | 0 | 0
2389 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-3) | 2246/HD | 04/11/2022 | 638 | N. G ENGINEERING | 32.94 | 0 | 0 | 100
2390 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir as Per Departmental Design including Soil Investigation, Laying Distribution Pipeline for Sonamui PWSS of Amta-I Block under Howrah Division, PHE Dte. (Part-A) | 2676/HD | 12/12/2022 | 720 | M/S JOY | 244.66 | 175.48 | 72.79 | 100
2391 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-4) | 2247/HD | 04/11/2022 | 720 | M/S ASHIRBAD (INDIA) | 32.95 | 0 | 0 | 100
2392 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 5.98 | 100 | 100
2393 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Land Development and Approach Road at HW site of Sonamoi PWSS of Amta-I Block under Uluberia Sub Division under Howrah Divison PHED. | 1809/HD | 08/04/2025 | 60 | M/S JOY | 12.64 | 0 | 0 | 100
2394 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Construction of boundary wall at 2nd T/W Site of Sonamoi W/S scheme within Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1409/HD | 17/03/2025 | 45 | DEBANANDA CONSTRUCTION | 8.61 | 0 | 0 | 100
2395 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
2396 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. , SM/11458 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
2397 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-I) PWSS (Mouza-Mahisgote, Chak Mahisjol, Chal Hari, Mahisnala, Nanakundu & Chak Kadamtala) of Domjur Block of Howrah Division PHE Dte. | 89/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.19 | 3.19 | 100 | 0
2398 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Material Requisition To Resource Division | 1748/HD | 25/04/2023 | 0 | Resource Division | 50.64 | 0 | 0 | 0
2399 | HOWRAH | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Quotation Bill for New Service Connection at Mahishnala W/S. Sch. PWSS-II | 379 | 25/10/2023 | 0 | WBSEDCL | 9.03 | 0 | 0 | 0
2400 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Work Order for Sinking of 7 (Seven) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone 1) Mahisnala PWSS & Domjur (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 1530/HD | 04/04/2023 | 45 | BALAJI UDDYOG | 89.53 | 61.84 | 100 | 70
2401 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Material Requisition To Resource Division | 135/HD | 10/01/2024 | 0 | Resource Division | 12.09 | 0 | 0 | 0
2402 | HOWRAH | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Quotation money deposition for new service connection at Mohisnala w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007840878 Reference ID- 106627061 SM Code- 11894 | 231 | 20/06/2024 | 0 | WBSEDCL | 13.93 | 0 | 0 | 0
2403 | HOWRAH | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Quotation money deposition for new service connection at Mahisnala (Domjur Zone-I) Pwss P.H No-III , Dist-Howrah under ED, PHED. | 757 | 16/02/2024 | 0 | WBSEDCL | 7.55 | 0 | 0 | 0
2404 | HOWRAH | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. From 01.05.2024 to 31.05.2024 WB-04G-2822 Bill No : 0240 Bill Date : 31/05/2024 | 241 | 20/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
2405 | HOWRAH | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahisnala Domjur (Zone-I) water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 3515/ED | 30/12/2022 | 990 | DAS ENTERPRISE | 34.26 | 0 | 0 | 75
2406 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Emergency Restoration of CI/DI Pipeline along with damaged at Node No. 22 to 270 main road due to laying of pipe line of Domjur (Zone-1) Mahishnala PWSS under Howrah Sadar Sub-Division PHE Dte. | 3130/HD | 14/07/2025 | 45 | MONDAL ENTERPISE | 42.03 | 0 | 0 | 0
2407 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Pipe Carrying Structure for Crossing at Node No. 104 to 109 of Mahishnala PWSS Under Howrah Sadar Sub-Division, P.H.E. Dte. | 867/HD | 10/02/2025 | 60 | GUPTA ENTERPRISE | 36.93 | 0 | 0 | 0
2408 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Land Development Works (1st, 2nd & 3rd T/W Site) & RCC Retaining Wall of Mahishnala (Zone-1) PWSS at 3rd Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | 1135/HD | 06/03/2024 | 187 | KALIDAS ENTERPRISE | 12.66 | 7.72 | 38.9 | 50
2409 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Permanent restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road "T01-57A Bus stand to Amta Road via Nonakundu Sluice Gate" of Domjur Block, Howrah under W.B.S.R.D.A. Howrah Division-I. (Package No WB/09/551). |  | 28/04/2025 | 0 | WBSRDA | 7.38 | 0 | 0 | 0
2410 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Permanent restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road "MRL01-Nonakundu Sluice Gate to Anupnagar Hooghly Border" of Domjur Block, Howrah under W.B.S.R.D.A. Howrah Division-I. (Package No WB/09/552). |  | 28/04/2025 | 0 | WBSRDA | 0.96 | 0 | 0 | 0
2411 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | 3 Nos Construction of Pump House (5.40m x 3.60 m), 3 nos Construction of Boundary Wall at 1st, 2nd &3rd Tube Well Sites, Construction of 350 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Rising Main Pipeline Work From 3rd Pump House, 2nd Pump House to 1st Pump House & OHR, Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) for Augmentation of Domjur (Zone-I) Mahisnala PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | 2622/HD | 17/07/2023 | 1085 | MONDAL PRECISION PVT. LTD. | 411.41 | 143.15 | 34.8 | 40
2412 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4817/HD | 19/11/2024 | 510 | TECH VISION | 8.36 | 0.87 | 99.96 | 95
2413 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur , SM/11894 | New | Supplying,fitting,fixing and erecting of Display Board at Bipra Noapara PWSS [SM/11711], Domjur Zone-I (Mahisnala) PWSS [SM/11894], and Domjur Zone-III (Khasmara) PWSS [SM/11893] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 224-A/HSSD | 27/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
2414 | HOWRAH | Howrah Division | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Work Order for Sinking of 4 (Four) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Gopalpur PWSS 2nos & Patinan PWSS 2 Nos of Bagnan - I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 663/HD | 17/02/2023 | 45 | AQUATECH ENGINEER | 52.06 | 23.58 | 100 | 100
2415 | HOWRAH | Howrah Division | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Material Requisition To Resource Division | 1754/HD | 26/04/2023 | 0 | Resource Division | 36.34 | 0 | 0 | 0
2416 | HOWRAH | Electrical | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Quotation Bill for New Service Connection at Uttar Gpalpur W/S. Sch. PH-I | 441 | 24/11/2023 | 0 | WBSEDCL | 3.46 | 0 | 0 | 0
2417 | HOWRAH | Electrical | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Quotation Bill for New Service Connection at Gopalpur W/S. Sch. TW-I | 387 | 01/11/2023 | 0 | WBSEDCL | 4.27 | 0 | 0 | 0
2418 | HOWRAH | Howrah Division | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells & 300 cu.m. capacity 20mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design & Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site GOPALPUR PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | 1917/HD | 08/05/2023 | 599 | PRAVAT SARKAR | 335.59 | 0 | 0 | 16
2419 | HOWRAH | Howrah Division | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Preparation of DPR for Gopalpur PWSS, Bagnan-I Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | 459/AE/USD | 15/09/2022 | 45 | DULAL MAJUMDER | 3.14 | 0 | 0 | 100
2420 | HOWRAH | Howrah Division | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Site clearence of HW site of Gopalpur & Patinan PWSS under Uluberia Sub Division under Howrah Division, PHE Dte. | 3244/AE/USD | 12/03/2024 | 30 | S R TRADING CORPORATION | 0.96 | 0.96 | 100 | 100
2421 | HOWRAH | Howrah Division | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Bagnan-I & II Block of Uluberia Sub-Division under Howrah Division PHE Dte. | 1206/HD | 11/03/2024 | 15 | KULTIKARI MOTHER TERESA SOCIAL WELLFARE SOCIETY | 2.01 | 2.01 | 100 | 100
2422 | HOWRAH | Howrah Division | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Material Requisition To Resource Division | 170/HD | 15/01/2024 | 0 | Resource Division | 4.87 | 0 | 0 | 0
2423 | HOWRAH | Electrical | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Quotation bill for service connection charges at Gopalpur w/s scheme, Zone-II, P.H. No.-II, Dist: Hooghly Application No.- 5004035005 Ref Id: 503576015 | 864 | 12/03/2024 | 0 | WBSEDCL | 4.15 | 0 | 0 | 0
2424 | HOWRAH | Electrical | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopalpur water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | 3539/ED | 30/12/2022 | 1037 | KARTICK BAL | 20.35 | 13.72 | 67.42 | 60
2425 | HOWRAH | Howrah Division | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0.67 | 100 | 100
2426 | HOWRAH | Howrah Division | Gopalpur Piped Water Supply Scheme , SM/13748 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | 3670/HD | 02/09/2025 | 240 | TECH VISION | 21.25 | 0 | 0 | 22
2427 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Shyampur PWSS (Mouza-Shyampur) of Jagatballavpur Block under Howrah Division PHE Dte. | 1019/HD | 05/05/2022 | 15 | ENVIROTECH SOLUTIONS | 2.53 | 2.53 | 100 | 0
2428 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 4.58 | 0 | 0 | 0
2429 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Shyampur PWSS (Mouza-Shyampur) of Jagatballavpur Block under Howrah Division PHE Dte. |  | 20/10/2022 | 0 | ENVIROTECH SOLUTIONS | 2.53 | 0 | 0 | 0
2430 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Shyampur PWSS of Jagatballavpur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 177/HD | 13/01/2023 | 45 | MUNSHI ENTERPRISE | 25.96 | 25.02 | 100 | 100
2431 | HOWRAH | Electrical | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shyampur water supply scheme, Zone-I, P.H. No. II (Replaced tubewell), District- Howrah under Electrical Division, PHE Dte. | 2099/HMSD | 24/11/2022 | 30 | D. K. ELECTRIC | 4.3 | 4.3 | 100 | 0
2432 | HOWRAH | Electrical | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Quotation Bill for New Service Connection at Shyampur PH-I | 188 | 13/03/2023 | 0 | WBSEDCL | 2.57 | 0 | 0 | 0
2433 | HOWRAH | Electrical | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Quotation Bill for New Service Connection at Shyampur W/S. Sch. PH-II | 229 | 29/03/2023 | 0 | WBSEDCL | 2.69 | 0 | 0 | 0
2434 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) At 2nd T/Well site at Shyampur PWSS In J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. (Part-4) | 2617/HD | 08/12/2022 | 60 | MONIRUL ISLAM | 6.14 | 5.78 | 100 | 100
2435 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Work Order for Laying Distribution Pipeline With FHTC of Shyampur PWSS at Jagatballavpur Block of Howrah Sadar Sub Division within Howrah Division, P. H. E. Dte. From Section J-9- J-10 to Section J-140 - J-141 (Part-2) | 2260/HD | 04/11/2022 | 45 | BUILT INDIA | 18.8 | 17.8 | 100 | 100
2436 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Work Order for Laying Distribution Pipeline With FHTC of Shyampur PWSS at Jagatballavpur Block of Howrah Sadar Sub Division within Howrah Division, P. H. E. Dte. From Section J-16- J-17 to Section J-157-J-158 (Part-1) | 2604/HD | 07/12/2022 | 45 | MA DURGA ENTERPRISE | 15.61 | 15.42 | 100 | 50
2437 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) at 2nd T/Well site at Shyampur PWSS In J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. (Part-4) | 2603/HD | 07/12/2022 | 60 | NAG ENTERPRISE | 6.17 | 5.8 | 100 | 100
2438 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Work order for Laying Additional DI Pipe line LDS Pipeline Work of Shyampur PWSS at J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. | 1928/HD | 10/05/2023 | 60 | MONIRUL ISLAM | 4.11 | 4.03 | 100 | 100
2439 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Work Order for Laying Rising Main Pipeline Work of Shyampur PWSS at J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. | 1929/HD | 10/05/2023 | 60 | KUNAL BANERJEE | 3.96 | 3.79 | 100 | 100
2440 | HOWRAH | Electrical | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shyampur water supply scheme, T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | 3522/ED | 30/12/2022 | 90 | S P ENTERPRISE | 20.28 | 20.27 | 100 | 11
2441 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Construction of 2 nos. Boundary Wall at pump house of Shyampur PWSS at J.B Pur Block of Howrah District under Howrah Division, P. H. E. Dte. Size-(25.00 m x 20.00 m) | 4318/HD | 01/12/2023 | 60 | ADRIJA ENTERPRISE | 15.43 | 15.39 | 100 | 100
2442 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Work order for Laying Distribution Pipeline With FHTC of Shyampur PWSS at Jagatballavpur Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte.From Section R-1 - J-1 to Section J-134 - J-136 (Part-3) | 2259/HD | 04/11/2022 | 45 | AQUATECH ENGINEERS | 30.98 | 27.46 | 88.61 | 100
2443 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Construction of approach road and land Development at 1st tubewell site for Shyampur PWSS at J.B.PUR Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 3086/HD | 08/07/2025 | 30 | ADRIJA ENTERPRISE | 5.55 | 0 | 0 | 0
2444 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Laying distribution pipe line (DI) between node point J34 to J46 of Shyampur PWSS at Jagatballavpur Block of Howrah District under Howrah sadar sub division of Howrah Division, P. H. E. Dte. | 1186/HSSD | 20/11/2024 | 60 | MANIRUL ISLAM | 0.96 | 0 | 0 | 100
2445 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Laying of additional distribution pipe line for providing FHTC at Shyampur PWSS at Jagatballavpur Block under Howrah sadar Sub-Division of Howrah Division PHE.Dte. | 1355/HSSD | 27/12/2024 | 45 | MA DURGA ENTERPRISE | 1.92 | 0 | 0 | 100
2446 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Reconnection of FHTC and C.C.Road restoration for Shyampur PWSS at J.B.PUR Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 1177/HD | 03/03/2025 | 60 | M/S SUPROVAT GHOSH | 7.19 | 0 | 0 | 100
2447 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. , SM/11790 | New | Supplying,fitting,fixing and erecting of Display Board at Shekrahati PWSS [SM/09586], Nimabalia PWSS [SM/13770], Shyampur PWSS [SM/11790] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 231-A/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
2448 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Preparation of DPR for Augmentation of Bamunhati PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 321/AE/USD | 16/08/2022 | 45 | APEX ENGINEERING | 4.04 | 4.01 | 99.38 | 100
2449 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part F :- LDS & FHTC of Southern Part of Palera Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 651/HD | 17/02/2023 | 45 | M/S MITRA CONSTRUCTION | 35.66 | 0 | 0 | 0
2450 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part H :- LDS & FHTC of Part II of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 653/HD | 17/02/2023 | 45 | SUPRIYA MAHANTI MISRA | 22.76 | 0 | 0 | 0
2451 | HOWRAH | Electrical | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bamunhati water supply scheme, T.W. No.- I, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | 911/ED | 22/02/2023 | 45 | SAIKAT ENTERPRISE | 11.51 | 0 | 0 | 0
2452 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part L :- LDS & FHTC of Part VI of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 657/HD | 17/02/2023 | 45 | BISWAJIT SAMANTA | 15.72 | 0 | 0 | 0
2453 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Material Requisition To Resource Division | 1754/HD | 26/04/2023 | 0 | Resource Division | 120.09 | 0 | 0 | 0
2454 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Laying Distribution System & Providing House Hold Tap Connection (FHTC) for Augmentation of Bamunhati Piped Water Supply Scheme (Part C :- LDS & FHTC of Srirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 2749/HD | 28/07/2023 | 600 | CREATION CONSTRUCTION | 176.47 | 0 | 0 | 0
2455 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Renovation of boundary wall at old Headwork Site of Bamunhati W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E.Dte. | 3235/AE/USD | 12/03/2024 | 30 | A.A ENTERPRISE | 3.07 | 3.02 | 100 | 100
2456 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part B :- LDS & FHTC of Barbangalpur Village) in Uluberia-II Block of Howrah District under Howrah Division, P.H.E. Dte. | 649/HD | 17/02/2023 | 1260 | S. R. ENTERPRISE | 76.95 | 0 | 0 | 60
2457 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part I :- LDS & FHTC of Part III of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 654/HD | 17/02/2023 | 1169 | ASHOKE ENGINEERING WORKS | 11.31 | 0 | 0 | 0
2458 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part E :- LDS & FHTC of Norther Part of Palera Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 650/HD | 17/02/2023 | 763 | B.M ENTERPRISE | 63.69 | 0 | 0 | 0
2459 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part Q:- FHTC of Part XI ) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 661/HD | 17/02/2023 | 855 | SR TRADING CORPORATION | 3.98 | 0 | 0 | 0
2460 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part G :- LDS & FHTC of Part I of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 652/HD | 17/02/2023 | 958 | JOY GURU TRADING | 38.68 | 0 | 0 | 75
2461 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Sinking of 7 (Seven) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Bamunhati PWSS (3 nos) & Kamina PWSS (2 nos) & Barramnagar PWSS (2 nos) of Uluberia - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | 1195/HD | 23/03/2023 | 847 | ACME CONSTRUCTION | 90.87 | 36.38 | 93.63 | 85
2462 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Laying Distribution System & Providing House Hold Tap Connection (FHTC) & AugmeConstruction of 500cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including foundation design of Bamunhati Piped Water Supply Scheme (Part A :- Bamunhati Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 1594/HD | 12/04/2023 | 960 | M/S SRIKANTA PATRA | 219.51 | 0 | 0 | 30
2463 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Laying Distribution System & Providing Household Tap Connection (FHTC) for Augmentation of Bamunhati Piped Water Supply Scheme (Part D :-LDS & FHTC of Mahishrekha Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 2697/HD | 24/07/2023 | 1080 | CONSTRUCTION CORNER | 104.49 | 0 | 0 | 60
2464 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Construction of switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement of Bamunhati PWSS (2nd Tube well) of Uluberia-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 1464/HD | 19/03/2025 | 45 | NOBLE ENTERPRISE | 5.9 | 0 | 0 | 0
2465 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Construction of switch room SLOPE ROOF (5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site of Bamunhati PWSS of Uluberia-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | 1207/HD | 04/03/2025 | 45 | M/S SRIKANTA PATRA | 7.05 | 0 | 0 | 0
2466 | HOWRAH | Electrical | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Bamunhati water supply scheme, T.W. No. III & IV, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | 3465/ED | 11/08/2023 | 90 | B.T. PROJECT PVT. LTD. | 23.5 | 0 | 0 | 0
2467 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part J :- LDS & FHTC of Part IV of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 655/HD | 17/02/2023 | 868 | ABONTICA ENTERPRISE | 27.96 | 0 | 0 | 100
2468 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part O:-LDS & FHTC of Part-IX of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 648/HD | 17/02/2023 | 854 | JHARNA ENTERPRISE | 11.08 | 0 | 0 | 100
2469 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part P:- LDS & FHTC of Part X of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 660/HD | 17/02/2023 | 960 | KALIDAS ENTERPRISE | 3.99 | 0 | 0 | 100
2470 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part K :- LDS & FHTC of Part V of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 656/HD | 17/02/2023 | 778 | LOKENATH ENTERPRISES | 13.99 | 0 | 0 | 100
2471 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part M :- LDS & FHTC of Part VII of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 658/HD | 17/02/2023 | 765 | ARINDAM ENTERPRISE | 22.22 | 0 | 0 | 100
2472 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part N:- LDS & FHTC of Part VIII of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 659/HD | 17/02/2023 | 855 | S.B ENTERPRISE | 10.66 | 0 | 0 | 100
2473 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Interconnection with existing distribution pipeline and newly sunk replaced T.Well at old Head works site of Bamunhati PWSS of Uluberia-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1075/AE/USD | 22/10/2024 | 160 | KALIDAS ENTERPRISE | 4.14 | 0 | 0 | 100
2474 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Retrofitting of Pump house and ancillary work of HW Site, 2nd TW site of Bamunhati W/S scheme at Uluberia-II Block under Uluberia Sub-Division of Howrah Division P.H.E Dte. (SM/12874) | 60/AE/USD | 07/04/2025 | 25 | MJ ENTERPRISE | 3.35 | 0 | 0 | 100
2475 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Material Requisition To Resource Division | 3688/HD | 04/09/2025 | 0 | Resource Division | 18.48 | 0 | 0 | 0
2476 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Material Requisition To Resource Division | 4146/HD | 15/10/2025 | 0 | Resource Division | 1.23 | 0 | 0 | 0
2477 | HOWRAH | Electrical | Augmentation of Bamunhati Water Supply Scheme , SM/12874 | Augmentation | Quotation money deposition for new service connection at Augmentation Of Bamunhati w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008636783 Reference ID- 107096884 SM Code- 12874 |  | 10/06/2025 | 0 | WBSEDCL | 12.25 | 0 | 0 | 0
2478 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 22.21 | 0 | 0 | 0
2479 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-VIII) Domjur (CT) of Domjur Block of Howrah Division PHE Dte. | 85/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.88 | 3.88 | 100 | 100
2480 | HOWRAH | Electrical | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-VIII) Domjur (CT) water supply scheme, T.W. No.- III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 3429/ED | 11/08/2023 | 90 | D. K. ELECTRIC | 10.74 | 10.46 | 100 | 100
2481 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Material Requisition To Resource Division | 1748/HD | 25/04/2023 | 0 | Resource Division | 99.73 | 0 | 0 | 0
2482 | HOWRAH | Electrical | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | new service connetion | 129 | 20/07/2023 | 0 | WBSEDCL | 4.04 | 0 | 0 | 0
2483 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Work Order for Sinking of 3 (Three) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone-VIII) of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 167/HD | 13/01/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 38.56 | 38.42 | 100 | 40
2484 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Material Requisition To Resource Division | 4768/HD | 14/11/2024 | 0 | Resource Division | 13.96 | 0 | 0 | 0
2485 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Bill Document for payment of Wayleave facility charges for Application id: SER-KGP-2024-WL-37,Domjur-CT | BP-2024-25-48 | 07/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 5.2 | 0 | 0 | 0
2486 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Payment for Way Leave and Survey Charges Domjur Zone-VIII | BP-2023-24-734 | 27/03/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.09 | 0 | 0 | 0
2487 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Bill Document for Payment of Wayleave facility charges for Application ID: SER-KGP-2024-WL-36,Domjur CT Bill Id-WL0051767 | BP-2024-25-49 | 07/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 5.28 | 0 | 0 | 0
2488 | HOWRAH | Electrical | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Quotation money deposition for new service connection at Domjur(Zone-VIII) w/s scheme, Domjur(CT),Pwss, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008185198 Reference ID- 106810746 SM Code- 14155 | 570 | 13/11/2024 | 0 | WBSEDCL | 9.33 | 0 | 0 | 0
2489 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Payment for Way Leave and Survey Charges Domjur Zone-VIII | BP-2023-24-736 | 27/03/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.09 | 0 | 0 | 0
2490 | HOWRAH | Electrical | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-VIII) Domjur (CT) water supply scheme, T.W. No. I & II, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | 920/ED | 22/02/2023 | 860 | A.G. ENTERPRISE | 21.49 | 10.47 | 48.7 | 40
2491 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Work Order for Construction of 600 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/8/2012) including Soil Investigation, Foundation Design & All pipe Connection For Domjur Zone-VIII, Domjur (CT) PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | 1741/HD | 25/04/2023 | 1173 | M/S ASHIRBAD (INDIA) | 174.05 | 37.81 | 21.73 | 60
2492 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Work Order for Laying Distribution Pipeline work, Providing FHTC (Functional Household Tap Connection) 2493 nos for Domjur (CT) PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte.(Part-II) For Node Section (135-136) to Node Section (800-801) | 1997/HD | 16/05/2023 | 892 | ZAKIR HOSSIN MONDAL | 212.69 | 169.7 | 79.79 | 100
2493 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Construction of 3 (Three) Nos.Pump House (5.40m x 3.60 m), Construction of Boundary Wall at Head work Site, Domjur Zone-VIII, Construction of 2(Two) nos. Boundary Wall, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work, Providing FHTC (Functional Household Tap Connection) 2494 nos for Domjur (CT) PWSS at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. (Part-I) For Node Section (R-1- 1) to Node Section (565-566) | 3041/HD | 22/08/2023 | 817 | TUSHAR KANTI GHOSH | 284.71 | 107.73 | 37.84 | 95
2494 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Supplying fabrication of 600 mm dia 10 mm thick MS casing pipe and Pushing of casing pipe by Hydraulic Jack pushing method to Cross Water carrier Pipe (Between Node Point 127 to 135 of LDS drawing) From Domjur station to Makardha station, KM/(TP/OHE) 11/03-11/04 (WL-37) of Domjur CT (Zone-8) Water Supply Scheme of Howrah Sadar Sub-Division, under Howrah Division P.H.E. Dte. | 2756/HD | 12/06/2025 | 60 | B. D. ENTERPRISE | 40.52 | 0 | 0 | 0
2495 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Laying of Rising main and road restoration at Domjur CT Zone-8 PWSS at Domjur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. | 974/HD | 19/02/2025 | 75 | KOHINOOR CONSTRUCTION CO. | 93.39 | 0 | 0 | 80
2496 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4817/HD | 19/11/2024 | 510 | TECH VISION | 8.36 | 0.09 | 5.06 | 95
2497 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah , SM/14155 | New | Supplying,fitting,fixing and erecting of Display Board at Domjur Zone -VIII PWSS [SM/14155], Rudrapur PWSS [SM/14515], Bhandardaha PWSS [SM/14197] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 224/HSSD | 27/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
2498 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 33.91 | 0 | 0 | 0
2499 | HOWRAH | Electrical | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 3592/ED | 28/08/2023 | 90 | R.N.S. TRADING | 43.65 | 0 | 0 | 0
2500 | HOWRAH | Electrical | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. III and Zone-II, T.W. No. III Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 3448/ED | 11/08/2023 | 90 | R.M.D TRADING. | 21.99 | 0 | 0 | 0
2501 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Preparation of DPR for new piped water supply scheme of Deulpur PWSS, Panchla Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 318/AE/USD | 16/08/2022 | 45 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 4.25 | 100 | 100
2502 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Continuation order for Preparation of DPR with Route Survey for new piped water supply scheme of Deulpur Gangadharpur Zone-II PWSS of Panchla Block under Howrah Division PHE Dte. | 1507/HD | 21/07/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.13 | 3.13 | 100 | 100
2503 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Material Requisition To Resource Division | 446/HD | 06/02/2023 | 0 | Resource Division | 307.95 | 0 | 0 | 0
2504 | HOWRAH | Electrical | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Quotation for new service connection charge at Gangadharpur Deulpur PWSS, Zone-II, TW - I | 529 | 15/12/2023 | 0 | WBSEDCL | 0.32 | 0 | 0 | 0
2505 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 352- 405 to Node Section 532-534 Part 8 | 875/H.D | 02/03/2023 | 120 | M/S MSS RISING ENTERPRISE | 74.39 | 19.67 | 26.45 | 30
2506 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 130-152 to Node Section 201-217 Part 6 | 876/HD | 02/03/2023 | 749 | K.B ENTERPRISE | 69.39 | 54.96 | 79.2 | 80
2507 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Work Order for Laying Distribution System for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Node Section 88-94 to Node Section 97-98 Part 3 | 855/HD | 01/03/2023 | 576 | DEBABRATA CHAKRABORTY | 16.89 | 14.16 | 83.83 | 58
2508 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) For Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P.H.E. Dte. From Node Section 255-287 to Node Section 90-91 From Node Section 287-304 to Node Section 448-450 (P-2,&4) | 1532/HD | 04/04/2023 | 1233 | N. G ENGINEERING | 91.11 | 77.74 | 85.33 | 85
2509 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Joynagar bazar to deulpur H.C Road from 2.730km to 3.00 km, Restoration work of PHE Cutting for laying pipe line under Howrah Highway Division in the District of Howrah.under deulpur gangadharpur Zone-II water supply scheme for Panchla Block. | BP-2024-25-442 | 04/10/2024 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 2.05 | 0 | 0 | 0
2510 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Deulpur Gangadharpur (Zone-II) PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H.E. Dte. | 172/HD | 13/01/2023 | 956 | PRANTIK DRILLING AGENCY | 50.26 | 16.17 | 32.17 | 35
2511 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Work Order for Laying Distribution System for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 217-230 to Node Section 352-361 Part 7 | 857/HD | 01/03/2023 | 904 | DULAL MAJUMDER | 67.69 | 48.57 | 71.76 | 75
2512 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Work Order for Construction of 700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/8/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection)For Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte. From Node Section R1-1 to Node Section 280-281, Part 1 | 1696/HD | 21/04/2023 | 916 | PRAVAT SARKAR | 351.82 | 108.89 | 30.95 | 30
2513 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection-405 NOS) For Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P.H.E. Dte. From Node Section 456-457 to Node Section 522-530 Part 9 | 1533/HD | 04/04/2023 | 906 | JHARNA ENTERPRISE | 41.43 | 29.16 | 70.37 | 100
2514 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Construction of 1 (one) no.Pump House (5.40m x 3.60m) at 4th tube well site,Construction of 1(One) no. boundary wall at 4th Tube well site, Construction of approch road and land Devlopment at 4th tubewell site and allied pipe laying work (DI) for Connecting 4th tubewell with the distribution main for Deulpur Gangadharpur Zone II PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 861/HD | 07/02/2025 | 420 | MANIRUL ISLAM | 20.91 | 0 | 0 | 0
2515 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Construction of 1(One) no. Boundary Wall at OHR site for Deulpur Gangadharpur (Zone-II) PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 3132/HD | 14/07/2025 | 360 | M/S ASHIRBAD (INDIA) | 9.06 | 0 | 0 | 0
2516 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Construction of 1 (one) no.Pump House (5.40m x 3.60m) at 3rd tube well site,Construction of 1(One) no. boundary wall at 3 rd Tube well site, Construction of land Development and approach road at 3rd tubewell site and allied pipe laying work (DI and UPVC) for connecting 3 rd tubewell with the distribution main at Deulpur Gangadharpur Zone-II PWSS under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 1070/HD | 27/02/2025 | 300 | S.S ENTERPRISE | 21.99 | 0 | 0 | 0
2517 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Work Order for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Node Section 97-127 to Node Section 423-425 Part 5 | 856/HD | 01/03/2023 | 701 | S.S ENTERPRISE | 23.46 | 8.01 | 34.45 | 100
2518 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Repair of L051-T02 Dhamalipara to Patra o Chakrabortypara L051 Road Damaged by PHE. |  | 15/12/2025 | 0 | WBSRDA-II | 5.31 | 0 | 0 | 0
2519 | HOWRAH | Electrical | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Quotation money deposition for new service connection at Deulpur-Gangadharpur w/s scheme, Zone- II, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008446417 Reference ID- 106984465 SM Code- 14154 |  | 04/07/2025 | 0 | WBSEDCL | 8.77 | 0 | 0 | 0
2520 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Repair of L033-T02 Shyamchak Purba o Paschim to Paschim Para L033 Road Damaged by PHE. |  | 15/12/2025 | 0 | WBSRDA-II | 8.64 | 0 | 0 | 0
2521 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Repair of LO52-T02 Neyogipara to Bakipara L052 Road Damaged by PHE |  | 15/12/2025 | 0 | WBSRDA-II | 3.3 | 0 | 0 | 0
2522 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Additional Laying Distribution pipeline with C.C. Road Restoration for Deulpur Gangadharpur Zone II PWSS at Panchla Block of Howrah District under Howrah Sadar Sub Division of Howrah Division, P.H.E. Dte. | 858/HD | 07/02/2025 | 525 | N. G ENGINEERING | 82.84 | 0 | 0 | 100
2523 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/14154 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Deulpur Gangadharpur (Zone-I) PWSS [SM/18560], Deulpur Gangadharpur (Zone-II) PWSS [SM/14154], Bikihakola PWSS [SM/18846] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 225-A/HSSD | 27/02/2025 | 15 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
2524 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | Work Order for Survey & Collection of house hold details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system in Bikihakola Piped Water Supply Scheme under Howrah District. | BP-2022-23-53 | 11/05/2022 | 0 | UNIVERSAL CORPORATION | 0.73 | 0 | 0 | 0
2525 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | Work Order for laying of Delivery Main proposed 700 cum reservoir for Bikihakola Water Supply scheme at Panchla Block under Howrah Division, P.H.E. Dte.( Part -II) | BP-2022-23-51 | 11/05/2022 | 0 | UNIVERSAL CORPORATION | 4.44 | 0 | 0 | 0
2526 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | Continuation order for Trial Run and Operation & maintenance of pipe lines (LDS & Risingmain) sluice valve & street stand post etc. including operation of sluice valves at Bikihakola w/s scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. (09/05/2021 to 31/08/2021)In continuation to the order under reference, and your application dated 06-05-2021, you are requested to continue the above mentioned work in consultation with the Assistant Engineer, Howrah Sadar Sub-Division, PHE Dte. | BP-2021-22-435 | 23/03/2022 | 0 | UNIVERSAL CORPORATION | 1.53 | 0 | 0 | 0
2527 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | Work Order for laying of Delivery Main proposed 700 cum reservoir for Bikihakola Water Supply scheme at Panchla Block under Howrah Division, P.H.E. Dte. | BP-2022-23-52 | 11/05/2022 | 0 | UNIVERSAL CORPORATION | 4.85 | 0 | 0 | 0
2528 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | O & M of distribution system and rising main pipe line (CI/DI/AC/UPVC) of Bikihakhola w/s scheme under Howrah Division, PHE Dte. Period for O & M (01.09.2021 to 31.12.2021) | BP-2021-22-434 | 23/03/2022 | 0 | UNIVERSAL CORPORATION | 0.99 | 0 | 0 | 0
2529 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | Work Order for Laying of Delivery Main Proposal 700 cum reservoir for BikihaKola Water Supply Scheme at Panchla Block under Howrah Division, PHE Dte. (Part-IV) | BP-2022-23-49 | 11/05/2022 | 0 | UNIVERSAL CORPORATION | 1.55 | 0 | 0 | 0
2530 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | Work Order for Laying of Delivery Main Proposal 700 cum reservoir for BikihaKola Water Supply Scheme at Panchla Block under Howrah Division, PHE Dte. (Part-III) | BP-2022-23-50 | 11/05/2022 | 0 | UNIVERSAL CORPORATION | 3.19 | 0 | 0 | 0
2531 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | Work order for Survey & Collection of house hold details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system in Bikihakola Piped Water Supply Scheme under Howrah District. (Part-B) | BP-2022-23-45 | 11/05/2022 | 0 | PRADIP KUMAR JATI | 0.73 | 0 | 0 | 0
2532 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | Work Order for Adopting Jack Pushing of 600 mm Dia M.S pipe as Casing to Cross Water carrier Pipe(Between Node Point 200-203 of LDS drawing) on Ranihati- Amta Road and adjoining work of Biki hakola Water Supply Scheme of Howrah Sadar Sub-Division, under Howrah Division P.H.E. Dte. | 377/HD | 21/02/2022 | 30 | SAMIRON GHOSH | 26.38 | 26.36 | 100 | 0
2533 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikihakola piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) Part- A | 349/HD | 17/02/2022 | 30 | UNIVERSAL CORPORATION | 4.3 | 3.98 | 100 | 0
2534 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | Work Order Retrofitting work of Laying Pipeline From Node Point 4-162, 162-220 for Bikihakola PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | 2606/HD | 07/12/2022 | 45 | UNIVERSAL CORPORATION | 11.28 | 0 | 0 | 40
2535 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) | 425/HD | 11/02/2021 | 30 | G.B. CONSTRUCTION AND CO | 92.5 | 0 | 0 | 100
2536 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) , SM/07077 | Retrofitting | Construction of Approach road 3.00 mtr wide at Pump House -I of Bikihakola PWSS at Howrah Sadar Sub- Division under Howrah Division , P.H.E Dte | 1449/HD | 13/07/2021 | 30 | S.M. CONSTRUCTION | 4.3 | 2.01 | 100 | 0
2537 | HOWRAH | Howrah Division | Ground Water Based Raspur PWSS , SM/18719 | New | Sinking of big dia Tube wells, Construction of Switch rooms(5.4x3.6) for HW site and other TW sites, Boundary walls, Land Developments, Laying distribution system (HDPE & DI) & Providing House Hold Connection(FHTC), Interconnection between tube wells and OHR and Construction of OHR 350 cum capacity (DRG. NO.- PC-I/OHR/12/2012) 20.0mtr staging height along with pipe connection, soil investigation & design etc for Raspur PWSS in Amta-I Block under Uluberia Sub Division under Howrah Division, P. H. E. Dte. | 3294/HD | 14/09/2023 | 300 | GEE BEE NIRMAN CO PVT LTD | 831.69 | 232.6 | 27.97 | 20
2538 | HOWRAH | Howrah Division | Ground Water Based Raspur PWSS , SM/18719 | New | Work Order for Preparation of DPR for new piped water supply scheme of Raspur PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 239/HD | 07/02/2022 | 15 | RADIANT | 3.87 | 3.87 | 100 | 100
2539 | HOWRAH | Howrah Division | Ground Water Based Raspur PWSS , SM/18719 | New | Material Requisition To Resource Division | 964/HD | 28/02/2024 | 0 | Resource Division | 75.31 | 0 | 0 | 0
2540 | HOWRAH | Howrah Division | Ground Water Based Raspur PWSS , SM/18719 | New | Material Requisition To Resource Division | 4864/HD | 22/11/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
2541 | HOWRAH | Electrical | Ground Water Based Raspur PWSS , SM/18719 | New | Quotation for New Service Connection at Rashpur W/S. Sch. PH-I, Amta-I | 644 | 09/01/2024 | 0 | WBSEDCL | 13.7 | 0 | 0 | 0
2542 | HOWRAH | Electrical | Ground Water Based Raspur PWSS , SM/18719 | New | Quotation for New Service Connection at Rashpur W/S. Sch. PH-II, Amta-I | 642 | 09/01/2024 | 0 | WBSEDCL | 11.6 | 0 | 0 | 0
2543 | HOWRAH | Electrical | Ground Water Based Raspur PWSS , SM/18719 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Raspur water supply scheme, T.W. No.- I & II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | 3618/ED | 29/08/2023 | 630 | SWAPAN ENTERPRISE | 20.37 | 0 | 0 | 80
2544 | HOWRAH | Howrah Division | Ground Water Based Raspur PWSS , SM/18719 | New | Sinking of 3rd T.well Size (250 X 150 mm Dia) and 250 m deep Drilling by Direct Rotary method with UPVC Pipes all complete at Raspur Piped Water Supply Scheme of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Location: Kotalpara/Putkhali) | 3165/HD | 16/07/2025 | 30 | WATER TECH | 15.58 | 0 | 0 | 0
2545 | HOWRAH | Howrah Division | Ground Water Based Raspur PWSS , SM/18719 | New | Construction of Pump House, Boundary Wall & Land development, approach road including alternative laying of DI (K-9) & DI (K-7) pipes at 3rd tube well site of Raspur Piped Water Supply Scheme at Amta-I Block in Uluberia Sub-Division of Howrah Division, P.H.E. Dte. | 3084/HD | 08/07/2025 | 60 | M/S MJA ENTERPRISE | 22.43 | 0 | 0 | 0
2546 | HOWRAH | Howrah Division | Ground Water Based Raspur PWSS , SM/18719 | New | Construction of Kiosk (2nd tube well site) at Raspur PWSS under uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Size inside 3.0 x 1.8m) | 1752/AE/USD | 04/03/2025 | 20 | J.S. CONSTRUCTION | 1.13 | 0 | 0 | 100
2547 | HOWRAH | Howrah Division | Ground Water Based Raspur PWSS , SM/18719 | New | Construction of Kiosk (Head Work site) at Raspur PWSS under uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Size inside 3.0 x 1.8m) | 1762/AE/USD | 05/03/2025 | 20 | J.S. CONSTRUCTION | 1.13 | 0 | 0 | 100
2548 | HOWRAH | Electrical | Ground Water Based Raspur PWSS , SM/18719 | New | Quotation for Shifting of energy meter by drawl of new LT-AB cable line at Someswaer PHE(Roshpur PH-II) under Amta C.C.C Application No- 10000132287 Reference ID- 860328827 SM Code- 18719 | 42151 | 30/07/2025 | 0 | WBSEDCL | 0.85 | 0 | 0 | 0
2549 | HOWRAH | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme , SM/18846 | Augmentation | Work Order Retrofitting work of Laying Pipeline From Node Point 4-162, 162-220 for Bikihakola PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | 2606/HD | 07/12/2022 | 45 | UNIVERSAL CORPORATION | 11.28 | 5.71 | 100 | 40
2550 | HOWRAH | Electrical | Source Augmentation of Bikihakola Water Supply Scheme , SM/18846 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Bikihakola Water Supply Scheme Block- Panchla District- Howrah under JJM Program under Electrical Division PHE Dte. | 4538/ED | 23/11/2023 | 90 | D. K. ELECTRIC | 10.74 | 0 | 0 | 0
2551 | HOWRAH | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme , SM/18846 | Augmentation | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) | 425/HD | 11/02/2021 | 30 | G.B. CONSTRUCTION AND CO | 92.5 | 17.93 | 100 | 100
2552 | HOWRAH | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme , SM/18846 | Augmentation | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributin system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) | 399/HD | 10/02/2021 | 30 | M/S ASHIRBAD (INDIA) | 92.07 | 33.36 | 100 | 100
2553 | HOWRAH | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme , SM/18846 | Augmentation | Work Order for Retrofitting work for Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola PWSS under Panchla Block of Howrah Sadar Sub Division under Howrah Division, PHE Dte.(Phase-II) (Part-A) No of House Hold= 100 nos. | 661/HD | 23/03/2022 | 20 | UNIQUE CONSTRUCTION | 3.82 | 3.35 | 100 | 100
2554 | HOWRAH | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme , SM/18846 | Augmentation | Work Order for Retrofitting work for Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola PWSS under Panchla Block of Howrah Sadar Sub Division under Howrah Division, PHE Dte.(Phase-II) (Part-B)No of House Hold= 100 nos. | 662/HD | 23/03/2022 | 20 | UNIQUE CONSTRUCTION | 3.67 | 2.61 | 100 | 100
2555 | HOWRAH | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme , SM/18846 | Augmentation | Work Order for Survey & Collection of house hold details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system in Bikihakola Piped Water Supply Scheme under Howrah District. (Part-C) | 508/HD | 08/03/2022 | 15 | G.B. CONSTRUCTION AND CO | 0.68 | 0.68 | 100 | 100
2556 | HOWRAH | Electrical | Source Augmentation of Bikihakola Water Supply Scheme , SM/18846 | Augmentation | Quotation money deposition for new service connection at Bikihakola w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008530674 Reference ID- 107035866 SM Code- 18846 | 42151 | 30/07/2025 | 0 | WBSEDCL | 14.53 | 0 | 0 | 0
2557 | HOWRAH | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme , SM/18846 | Augmentation | Preparation of DPR for Source Augmentation for Bikihakola PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. | 814/HSSD | 07/08/2024 | 15 | APEX ENGINEERING | 0.78 | 0 | 0 | 0
2558 | HOWRAH | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme , SM/18846 | Augmentation | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method, Construction of 1 (One) Nos.Pump House (5.40m x 3.60 m), Construction of 1(One) nos. Boundary Wall,Construction of Boundary Wall at Head work Site of Size-(50.00 m x 40.00 m), Construction of 700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/8/2012) including Soil Investigation, Foundation Design & All pipe Connection and Reconnection of FHTC & distribution pipe line and Allied Works at Bikiakhola PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. | 879/HD | 23/02/2024 | 719 | THE UNICON ENGINEERS | 289.03 | 0 | 0 | 20
2559 | HOWRAH | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme , SM/18846 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Deulpur Gangadharpur (Zone-I) PWSS [SM/18560], Deulpur Gangadharpur (Zone-II) PWSS [SM/14154], Bikihakola PWSS [SM/18846] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 225-A/HSSD | 27/02/2025 | 15 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
2560 | HOWRAH | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme , SM/18846 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Source Augmentation of Beldubi Water Supply Scheme [SM/18845], Source Augmentation of Bikihakola Water Supply Scheme [SM/18846], Source Augmentation of Sahapur Piped Water Supply Scheme [SM/18844] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 233/HSSD | 28/02/2025 | 15 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
2561 | HOWRAH | Howrah Division | Source Augmentation of Garbhabanipur Water Supply Scheme , SM/18849 | Augmentation | Sinking of additonal 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Garbhabanipur PWSS SM/18849 of Udaynarayanpur Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1306/HD | 14/03/2024 | 30 | WESTERN WATER SUPPLY AGENCY | 14.87 | 14.4 | 100 | 100
2562 | HOWRAH | Howrah Division | Source Augmentation of Garbhabanipur Water Supply Scheme , SM/18849 | Augmentation | Preparation of DPR for Source Strengthning at Garhbhabanipur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | 496/AE/USD | 29/09/2023 | 30 | APEX ENGINEERING | 0.78 | 0.22 | 22.04 | 100
2563 | HOWRAH | Electrical | Source Augmentation of Garbhabanipur Water Supply Scheme , SM/18849 | Augmentation | Additional Quotation for new service connection for source Augmentation of Garbhabanipur Water Supply Scheme, PH NO- III in the district Howrah under Electrical Division, PHE Dte. (SM/18849), Reference Id- 860319020, Application no- 100000123590 | 614 | 05/12/2024 | 0 | WBSEDCL | 0.74 | 0 | 0 | 0
2564 | HOWRAH | Electrical | Source Augmentation of Garbhabanipur Water Supply Scheme , SM/18849 | Augmentation | Quotation for new service connection for source Augmentation of Garbhabanipur Water Supply Scheme, PH NO- III in the district Howrah under Electrical Division, PHE Dte. (SM/18849), Reference Id- 106616115, Application no- 1007816541 | 212 | 11/06/2024 | 0 | WBSEDCL | 11.44 | 0 | 0 | 0
2565 | HOWRAH | Electrical | Source Augmentation of Garbhabanipur Water Supply Scheme , SM/18849 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF GARBHABANIPUR PIPED W/S SCHEME, T.W. No. III, Block: Udaynarayanpur, District - Howrah under JJM Program under Electrical Division PHE Dte. | 424/ED | 29/02/2024 | 519 | SMILE | 10.74 | 0 | 0 | 90
2566 | HOWRAH | Howrah Division | Source Augmentation of Garbhabanipur Water Supply Scheme , SM/18849 | Augmentation | Additional laying distribution pipeline with FHTC at Garbhabanipur PWSS SM/18849 of Udaynarayanpur Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 3121/HD | 09/07/2024 | 300 | TAPU SAHA | 62.11 | 0 | 0 | 70
2567 | HOWRAH | Howrah Division | Source Augmentation of Garbhabanipur Water Supply Scheme , SM/18849 | Augmentation | Land Development at 3rd Tube well Site Source Augmentation of Garbhabanipur PWSS scheme under Udaynarayanpur Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | 1699/AE/USD | 28/02/2025 | 15 | BIBHUTI SHAW | 3.52 | 0 | 0 | 100
2568 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 36.76 | 0 | 0 | 0
2569 | HOWRAH | Electrical | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 3592/ED | 28/08/2023 | 90 | R.N.S. TRADING | 43.65 | 0 | 0 | 0
2570 | HOWRAH | Electrical | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. III and Zone-II, T.W. No. III Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 3448/ED | 11/08/2023 | 90 | R.M.D TRADING. | 21.99 | 0 | 0 | 0
2571 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Material Requisition To Resource Division | 446/HD | 06/02/2023 | 0 | Resource Division | 86.28 | 0 | 0 | 0
2572 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection-1818 NOS) For Augmentation of Deulpur Gangadharpur Zone-I PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 7-34 to Node Section 74-77, From Node Section 101-248 to Node Section 356-358, From Node Section 72-84 to Node Section 241-256, From Node Section 256-257 to Node Section 449-450 (P-5,6,7 & 8) | 2956/HD | 16/08/2023 | 1080 | M/S ASHIRBAD (INDIA) | 179.05 | 159.15 | 88.89 | 85
2573 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Deulpur Gangadharpur (Zone-I) PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P.H.E. Dte. | 4597/HD | 20/12/2023 | 45 | WATER TECH | 50.26 | 48.2 | 100 | 100
2574 | HOWRAH | Electrical | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Quotation App. No.-1007748306 SM/18560 | 118 | 17/05/2024 | 0 | WBSEDCL | 6.52 | 0 | 0 | 0
2575 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Construction of 700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/8/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection)For Deulpur Gangadharpur Zone-I PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte.,Part 1 From Node Section R1-1 to Node Section 21-22 to Section 202-204 | 2838/HD | 07/08/2023 | 600 | SUJATA CONSTRUCTION | 373.91 | 99.12 | 26.51 | 24
2576 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) For Augmentation of Deulpur Gangadharpur Zone-I PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 174-242 to Node Section 411-414, Part 4 | 3279/HD | 13/09/2023 | 120 | MAA TARA CONSTRUCTION | 98.18 | 78.13 | 79.58 | 70
2577 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Special repairing work for restoration of damage pavement caused by laying of pipe line from start Node point 36 to End Node point 256 of existing LDS at Deulpur Board Girls primary School to Deulpur Bandher Bazar for the 2.0 km (PMGSY/PWD) road at Deulpur Gangadharpur Zone-I PWSS Under Panchla Block under Howrah Sadar Sub Division of Howrah Howrah Division, P.H.E. Dte. | 1313/HD | 10/03/2025 | 120 | ASSOCIATE CONSTRUCTION | 28.9 | 0 | 0 | 0
2578 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Laying of additional distribution pipe line & allied works at Deulpur Gangadharpur Zone-I PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | 859/HD | 07/02/2025 | 525 | M/S ASHIRBAD (INDIA) | 87.3 | 0 | 0 | 40
2579 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Laying Distribution Pipeline work with Providing FHTC (1300 nos) (Functional Household Tap Connection) For Augmentation of Deulpur Gangadharpur Zone-I PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P.H.E. Dte. From Node Section 55-82 to Node Section 147-148 & From Node Section 82-170 to Node Section 409-410 (P-2&3) | 3195/HD | 04/09/2023 | 516 | SANJUKTA ENGINEERS | 121.57 | 83.98 | 76.02 | 55
2580 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Laying of additional distribution pipe line and allied works in Kusadanga mouza at Deulpur Gangadharpur Zone-I PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. | 4187/HD | 26/09/2024 | 240 | MAA TARA CONSTRUCTION | 53.88 | 8.13 | 13.14 | 80
2581 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Construction of 1(One) no. Boundary Wall at OHR site for Deulpur Gangadharpur (Zone -I) PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 2838/HD | 19/06/2025 | 45 | SMK ENTERPRISE | 16.25 | 0 | 0 | 100
2582 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Construction of approach road and land Development at 3rd tubewell site, Construction of 1(One) no. boundary wall, Construction of 3rd Pump House (5.40m x 3.60m) at Deulpur Gangadharpur Zone-I PWSS under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 1015/HD | 21/02/2025 | 45 | GRAVITA ENTERPRISE | 13.04 | 0 | 0 | 100
2583 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Joynagar bazar to deulpur H.C Road from 4.340km to 5.00 km, Restoration work of PHE Cutting for laying pipe line under Howrah Highway Division in the District of Howrah.Under deulpur gangadharpur Zone-I water supply scheme of Panchla Block. |  | 21/03/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 21.24 | 0 | 0 | 0
2584 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Repair of L061-L053 Baki Daspara to Mistripara Rest L061 Road Damaged by PHE. |  | 15/12/2025 | 0 | WBSRDA-II | 4.4 | 0 | 0 | 0
2585 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Dewanghata Bowbazar Road with link to deulpur H.C from 0.00 km to 2.20 km, Restoration work of PHE cutting for laying pipe line under Howrah Highway Division in the District of Howrah. |  | 21/03/2025 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 40.44 | 0 | 0 | 0
2586 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Repair of Khusdanga - Jujarshah Bus Stand Road Damaged by PHE. |  | 15/12/2025 | 0 | WBSRDA-II | 17.49 | 0 | 0 | 0
2587 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Permanent restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road "Wadhipur - Makardaha Bazar" of Domjur Block, Howrah under W.B.S.R.D.A. Howrah Division-I. (Package No WB/09/08). |  | 19/05/2025 | 0 | WBSRDA | 21.82 | 0 | 0 | 0
2588 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4816/HD | 19/11/2024 | 510 | TECH VISION | 12.48 | 9.42 | 200 | 78
2589 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18560 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Deulpur Gangadharpur (Zone-I) PWSS [SM/18560], Deulpur Gangadharpur (Zone-II) PWSS [SM/14154], Bikihakola PWSS [SM/18846] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 225-A/HSSD | 27/02/2025 | 15 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
2590 | HOWRAH | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 38.2 | 0 | 0 | 0
2591 | HOWRAH | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Panchla PWSS (Mouza-Panchla (CT) of Panchla Block under Howrah Division PHE Dte. | 1020/HD | 05/05/2022 | 15 | ENVIROTECH SOLUTIONS | 2.53 | 2.53 | 100 | 100
2592 | HOWRAH | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Material Requisition To Resource Division | 446/HD | 06/02/2023 | 0 | Resource Division | 62.61 | 0 | 0 | 0
2593 | HOWRAH | Electrical | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Quotation money deposition for new service connection at Panchla w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1007951166 Reference ID- 106680336 SM Code- 18563 | 489 | 01/10/2024 | 0 | WBSEDCL | 3.43 | 0 | 0 | 0
2594 | HOWRAH | Electrical | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Quotation money deposition for new service connection at Panchla pwss, Dist-Howrah, under PHED. App. No.-1007554361 Ref. No.-106486310 SM/18563 | 817 | 01/03/2024 | 0 | WBSEDCL | 5.05 | 0 | 0 | 0
2595 | HOWRAH | Electrical | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Quotation money deposition for shifting of 1 mtr. pcc pole and others allied works at panchla pwss. near P.H No.-I under ED PHED. Ref. NO.-860314452 SM/18563 | BP-24-25-591 | 20/11/2024 | 0 | WBSEDCL | 0.45 | 0 | 0 | 0
2596 | HOWRAH | Electrical | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Quotation money deposition for new service connection at PANCHLA pwss, T.W No.-I , Dist-Howrah under ED PHED. App. No.-1007505290 Ref. ID.: 106463795 SM/18563 | 815 | 28/02/2024 | 0 | WBSEDCL | 4.43 | 0 | 0 | 0
2597 | HOWRAH | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Different Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, and Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Panchla Block, District:-Howrah [NEW SCHEME][Name of Schemes:-1)Paschim Panchla PWSS 2) Panchla PWSS 3) Gabberia-Mallik Bagan PWSS]. | 2866/HD | 08/08/2023 | 910 | SAMIRON GHOSH | 1986.19 | 347.51 | 34.82 | 30
2598 | HOWRAH | Electrical | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Panchla water supply scheme, T.W. No.- I, II, III & IV, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 3581/ED | 28/08/2023 | 705 | WEST BENGAL ENGINEERING CO. | 46.35 | 12.02 | 25.92 | 30
2599 | HOWRAH | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Additional Laying Distribution Pipeline & approach road with land development at OHR site & allied works of Panchla PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 2835/HD | 20/06/2024 | 600 | SAMIRON GHOSH | 66.05 | 0 | 0 | 20
2600 | HOWRAH | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Special repairing work for restoration of damage pavement caused by laying of pipe line from Start Node Section 359 to End Node section 873 of existing LDS at MEJUTI BRIDGE TO PANCHLA BAZAR for the 2.7 km (WBSRDA) road at Panchla PWSS in Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | 3144/HD | 15/07/2025 | 60 | LAKSHMI IRON | 37.39 | 0 | 0 | 0
2601 | HOWRAH | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bally Jagacha & Panchla Block) | 4118/HD | 14/10/2025 | 30 | JHARNA ENTERPRISE | 4.79 | 0 | 0 | 0
2602 | HOWRAH | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. , SM/18563 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4816/HD | 19/11/2024 | 510 | TECH VISION | 12.48 | 0 | 0 | 78
2603 | HOWRAH | Electrical | Baniban Zone-III Piped water Supply Scheme , SM/18564 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniban water supply scheme, Zone-III, T.W. No. I, II, III & IV, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | 3598/ED | 28/08/2023 | 90 | DEY ENTERPRISE | 42.99 | 0 | 0 | 0
2604 | HOWRAH | Howrah Division | Baniban Zone-III Piped water Supply Scheme , SM/18564 | New | Preparation of DPR for new piped water supply scheme of Basudebpur PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte.( Banibon, Zone-III) | 325/AE/USD | 16/08/2022 | 45 | APEX ENGINEERING | 3.76 | 3.76 | 100 | 100
2605 | HOWRAH | Howrah Division | Baniban Zone-III Piped water Supply Scheme , SM/18564 | New | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Uluberia - II block of Uluberia Sub Division under Howrah Division, P.H.E. Dte. | 1212/HD | 11/03/2024 | 15 | TRIMARV SOLUTIONS PRIVATE LIMITED | 1.85 | 1.63 | 100 | 100
2606 | HOWRAH | Howrah Division | Baniban Zone-III Piped water Supply Scheme , SM/18564 | New | Sinking of 3 (Three) Nos. 250 X 150 mm Dia tubewell Drilling by Direct Rotary method with UPVC Pipes all complete, Construction of 3no 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement, Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around head work site, Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site land development of Head work site and other Tube well sites, Laying distribution system (HDPE & DI) & Providing Household Connection (3191nos), Interconnection between Tube wells & OHR and Construction of 700 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation Baniban with foundation design Baniban Piped Water Supply Scheme (Zone-III) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | 2960/HD | 16/08/2023 | 1026 | SAMIRON GHOSH | 1022.24 | 0 | 0 | 55
2607 | HOWRAH | Howrah Division | Baniban Zone-III Piped water Supply Scheme , SM/18564 | New | Restoration of Bituminous Road along with alterntive laying of DI & HDPE (PE 100, PN6) pipes from 1) Basudebpur Lalpool to Basudebpur G.P. Office via. H/W site to Jhuri Battala(PWD), 2) Basudebpur Battala to Basudebpur Shibtala, 3) Nurullapara Battala to Katra Bazar via. Katra Auto Stand, 4) Katra Auto stand to Basudebpur Lalpool, 5) Basudebpur Bazar to Tehatta Mollickpara via. Tehatta Sishu Niketan to Tehatta Balika Vidyalaya, 6) Uttar Magurkhali to Dakshin Magurkhali, 7) Adharmanik IOCL crossing to Adharmanik Pry. School via. Adharmanik HKKS Pry. School & Pramanick para under Baniban Zone-III PWSS under Uluberia Sub-Division of Howrah Division, PHE Dte. | 3467/HD | 12/08/2025 | 60 | INDICON ENGINEERS CO-OP SOCIETY LTD | 83.93 | 0 | 0 | 0
2608 | HOWRAH | Howrah Division | Baniban Zone-III Piped water Supply Scheme , SM/18564 | New | Restoration of Black top Road along with alternative laying of DI & HDPE (PE100, PN6) pipes from Basudevpur Bazar to Nurillapara under Baniban (Zone-III) PWSS under Uluberia Sub-Division of Howrah Division, PHE Dte. (SM/18564) | 2501/HD | 26/05/2025 | 30 | SANJOY GHOSH | 9.16 | 0 | 0 | 100
2609 | HOWRAH | Howrah Division | Baniban Zone-III Piped water Supply Scheme , SM/18564 | New | Material Requisition To Resource Division | 494/HD | 24/01/2025 | 0 | Resource Division | 11.09 | 0 | 0 | 0
2610 | HOWRAH | Howrah Division | Baniban Zone-III Piped water Supply Scheme , SM/18564 | New | Material Requisition To Resource Division | 493/HD | 24/01/2025 | 0 | Resource Division | 35.82 | 0 | 0 | 0
2611 | HOWRAH | Electrical | Baniban Zone-III Piped water Supply Scheme , SM/18564 | New | Quotation money deposition for new service connection at Baniban w/s scheme, Zone- III, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008447246 Reference ID- 106985415 SM Code- 18564 |  | 20/03/2025 | 0 | WBSEDCL | 4.2 | 0 | 0 | 0
2612 | HOWRAH | Howrah Division | Baniban Zone-III Piped water Supply Scheme , SM/18564 | New | Road Restoration work due to cutting by PHE for laying water pipeline at Howrah Amta Road from 44.80 km to 47.30 km under Howrah Division, P.W.D. during the year 2025-26. |  | 10/10/2025 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 19.97 | 0 | 0 | 0
2613 | HOWRAH | Howrah Division | Baniban Zone-III Piped water Supply Scheme , SM/18564 | New | Road Restoration Work due to road cutting by PHE for laying water pipeline at Nimdighi Basudevpur Road from 2.37 kmp to 6.77 kmp in the District of Howrah during the year 2025-26. |  | 10/10/2025 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 28.53 | 0 | 0 | 0
2614 | HOWRAH | Howrah Division | Baniban Zone-III Piped water Supply Scheme , SM/18564 | New | Continuation order for Hiring of 1 (One) no. Luxury Taxi/Maxi cab/Motor cab on daily basis under monthly hiring category for the Assistant Engineer, Uluberia Sub- Division , PHE Dte of the Government of West Bengal (for Twelve months) under Howrah Division, PHE dte. (Period of 365 Days) | 1182/AE/USD | 27/11/2024 | 365 | NOBLE ENTERPRISE | 4.8 | 1.77 | 36.76 | 30
2615 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Material Requisition To Resource Division | 2839/HD | 23/12/2022 | 0 | Resource Division | 56.12 | 0 | 0 | 0
2616 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Jujarsha PWSS, Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte | BP-2021-22-405 | 14/03/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.36 | 0 | 0 | 0
2617 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Indent of Material | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
2618 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at 4th T/well site of Jujarsah PWSS at Panchla Block of Howrah District under Howrah Division, PHE Dte.. | 1760/HD | 27/04/2023 | 60 | GRAFTON TARMAC ENGINEERING AND CIVIL | 26.45 | 0 | 0 | 0
2619 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Supply, Delivery & Installation of voltage correcting device & other allied works for Jujursha W/S. Sch. PH-I Howrah | 1372/HMSD | 27/07/2022 | 7 | MAA KALI ENTERPRISE | 2.85 | 2.85 | 100 | 0
2620 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Material Requisition To Resource Division | 1624/HD | 05/08/2022 | 0 | Resource Division | 258.1 | 0 | 0 | 0
2621 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Quotation Bill for New Service Connection at Jujarsah W/S. Sch.PH-III | 348 | 11/10/2023 | 0 | WBSEDCL | 3.71 | 0 | 0 | 0
2622 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Work Order for Laying Distribution Pipeline With FHTC of Jujarsah PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Section 263-307 to Section 526-533 (Part-B) | 1827/HD | 07/09/2022 | 1370 | M/S ASHIRBAD (INDIA) | 149.32 | 77.93 | 52.19 | 40
2623 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Work Order for Laying Distribution Pipeline With FHTC of Jujarsah PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Section Node 678-679 to Section Node 804-806 (Part-E) | 1851/HD | 09/09/2022 | 931 | ADITYA HAZRA | 204.49 | 33.7 | 16.48 | 30
2624 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Work Order for Laying Distribution Pipeline With FHTC of Jujarsah PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Section Node 110-123 to Section Node 611-613 (Part-C) | 1852/HD | 09/09/2022 | 60 | UNIVERSAL CORPORATION | 158.4 | 100.9 | 63.7 | 60
2625 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Work Order for Laying Distribution Pipeline With FHTC of Jujarsah PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Section Node 248-265 to Section Node 449-453 (Part-D) | 1819/HD | 06/09/2022 | 1390 | N. G ENGINEERING | 183.13 | 102.13 | 55.77 | 30
2626 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Work Order for Construction Of 1250 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir with Rising Main Pipeline Work & Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) of Augmentation of Jujarsah PWSS Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. (Part-A) | 1842/HD | 08/09/2022 | 1021 | G.B. CONSTRUCTION AND CO | 356.33 | 189.92 | 53.3 | 30
2627 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Jujarshah PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | 310/HD | 20/01/2023 | 721 | SPG ENTERPRISES | 68.81 | 0 | 0 | 0
2628 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jujarsah water supply scheme, T.W. No.- I & II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 912/ED | 22/02/2023 | 846 | MAA KALI ENTERPRISE | 23.16 | 0 | 0 | 50
2629 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Additional distribution pipe line with Rider line and allied works at Jujarsaha PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. (SM/10146) | 3099/HD | 08/07/2024 | 480 | MA MANASA CONSTRUCTION | 176.73 | 0 | 0 | 60
2630 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Quotation money deposition for new service connection at Jujarsah w/s scheme, T.W. No.-V, Dist.-Howrah under PHE Dte. Application No- 1008476183 Reference ID- 107005259 SM Code- 10146 |  | 17/12/2025 | 0 | WBSEDCL | 4.02 | 0 | 0 | 0
2631 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Quotation money deposition for new service connection at Jujarsah w/s scheme, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1008415264 Reference ID- 106963650 SM Code- 10146 |  | 17/12/2025 | 0 | WBSEDCL | 3.68 | 0 | 0 | 0
2632 | HOWRAH | Electrical | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jujarsah water supply scheme, T.W. No. III, IV & V, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | 3439/ED | 11/08/2023 | 990 | H.K.DAS & CO. | 35.18 | 0 | 0 | 60
2633 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | 4816/HD | 19/11/2024 | 510 | TECH VISION | 12.48 | 0 | 0 | 78
2634 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah , SM/10146 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Banharishpur PWSS [SM/11723], Jujarsah PWSS [SM/10146], Samanti PWSS [SM/12562] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | 229/HSSD | 28/02/2025 | 15 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
2635 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Work Order for Operation of Laboratory activisties for Howrah District Laboratory at Domjur under Howrah Division, PHE Dte, [Period from May'2023 to October'2023] | 1903/HD | 05/05/2023 | 184 | LAB ANALYTICE | 4.3 | 4.3 | 100 | 100
2636 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Continuation order for Operation of Laboratory activities for Howrah District Laboratory at Domjur under Howrah Division, PHE Dte, [Period from 01/11/2023 to 31/12/2023] | 3920/HD | 31/10/2023 | 61 | LAB ANALYTICS | 1.37 | 1.37 | 100 | 100
2637 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Operational charge as 2nd Installment of Ranapara Gram Bikash Kendra water testing laboratory for the year 2024 | BP-2024-25-501 | 06/12/2024 | 0 | RANAPARA | 0.35 | 0 | 0 | 0
2638 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of November-2024 | BP-2024-25-508 | 10/12/2024 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2639 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Festival bonus of laboratory personnel for the year 2023-2024 | BP-2024-25-361 | 25/09/2024 | 0 | RANAPARA | 0.18 | 0 | 0 | 0
2640 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of August-2024 | BP-2024-25-311 | 06/09/2024 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2641 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of July-2024 | BP-2024-25-261 | 13/08/2024 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2642 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of September-2024 | BP-2024-25-433 | 01/10/2024 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2643 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of November-2024 | BP-2024-25-506 | 10/12/2024 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2644 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of August-2024 | BP-2024-25-312 | 06/09/2024 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2645 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of July-2024 | BP-2024-25-260 | 13/08/2024 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2646 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Operational charge as 2nd Installment of Ananda Niketan water testing laboratory for the year 2024 | BP-2024-25-502 | 06/12/2024 | 0 | ANANDA NIKETAK | 0.35 | 0 | 0 | 0
2647 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Festival bonus of laboratory personnel for the year 2023-2024 | BP-2024-25-360 | 25/09/2024 | 0 | ANANDA NIKETAK | 0.18 | 0 | 0 | 0
2648 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of October-2024 | BP-2024-25-477 | 07/11/2024 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2649 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of August-2024 | BP-2024-25-310 | 06/09/2024 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2650 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of July-2024 | BP-2024-25-259 | 13/08/2024 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2651 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of November-2024 | BP-2024-25-507 | 10/12/2024 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2652 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Festival bonus of laboratory personnel for the year 2023-2024 | BP-2024-25-359 | 25/09/2024 | 0 | GONDALPARA | 0.18 | 0 | 0 | 0
2653 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of September-2024 | BP-2024-25-432 | 01/10/2024 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2654 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of September-2024 | BP-2024-25-431 | 01/10/2024 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2655 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Operational charge as 2nd Installment of Gondalpara Nabin Pragati Seba Samity water testing laboratory for the year 2024 | BP-2024-25-500 | 06/12/2024 | 0 | GONDALPARA | 0.35 | 0 | 0 | 0
2656 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of October-2024 | BP-2024-25-476 | 07/11/2024 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2657 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of October-2024 | BP-2024-25-478 | 07/11/2024 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2658 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Yearly Maintenance of two nos Laboratories activities of Howrah District Laboratory & Sub-District Laboratory at Silampur under Howrah Division, PHE Dte. [Period from 01/07/2024 to 31/12/2024] | 2912/HD | 26/06/2024 | 183 | M/S ASHIRBAD (INDIA) | 0.93 | 0 | 0 | 100
2659 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of March-2025 | W/144 | 10/07/2025 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2660 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of December-2024 | BP-2024-25-520 | 14/01/2025 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2661 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of laboratory Personnel for the month of July,2025 |  | 11/08/2025 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2662 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of laboratory Personnel for the month of July,2025 |  | 11/08/2025 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2663 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist,Bacteriologist & Lab Assistant for the month of September,2025. |  | 25/09/2025 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2664 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of February-2025 | BP-2024-25-543 | 13/03/2025 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2665 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of January-2025 | BP-2024-25-540 | 13/02/2025 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2666 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of March-2025 | W/144 | 10/07/2025 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2667 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of December-2024 | BP-2024-25-519 | 14/01/2025 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2668 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | REMUNERATION OF CHEMIST,BACTERIOLOGIST & LAB ASSISTANT FOR THE MONTH OF AUGUST,2025. |  | 08/09/2025 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2669 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist and Lab Assistant of Ananda Niketan Laboratory for the month of October, 2025 |  | 04/11/2025 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2670 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of lab personnel for the month July 2025 |  | 11/08/2025 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2671 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | REMUNERATION OF CHEMIST,BACTERIOLOGIST & LABORATORY ASSISTANT FOR THE MONTH OF AUGUST,2025. |  | 08/09/2025 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2672 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist,Bacteriologist & Lab Assistant for the month of September,2025 |  | 25/09/2025 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2673 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of April-2025 | W/144 | 10/07/2025 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2674 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist and Lab Assistant of Gondalpara Nabin Pragati Seba Samity for the month of October, 2025 |  | 04/11/2025 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2675 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | REMUNERATION OF CHEMIST,BACTERIOLOGIST & LAB ASSISTANT FOR THE MONTH OF AUGUST,2025. |  | 08/09/2025 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2676 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of February-2025 | BP-2024-25-544 | 13/03/2025 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2677 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of May-2025 | W/144 | 10/07/2025 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2678 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of March-2025 | W/144 | 10/07/2025 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2679 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of May-2025 | W/144 | 10/07/2025 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2680 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of April-2025 | W/144 | 10/07/2025 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2681 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of February-2025 | BP-2024-25-545 | 13/03/2025 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2682 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of May-2025 | W/144 | 10/07/2025 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2683 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist and Lab Assistant of Ranapara Gram Bikash Kendra for the month of OCtober, 2025 |  | 04/11/2025 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2684 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of December-2024 | BP-2024-25-518 | 14/01/2025 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2685 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of January-2025 | BP-2024-25-538 | 13/02/2025 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2686 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of January-2025 | BP-2024-25-539 | 13/02/2025 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2687 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist and Lab Assistant for the month of September,2025 |  | 25/09/2025 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2688 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District , SM/19078 | Support-WQMSP | Remuneration of Chemist, Bacteriologist & Lab. Assistant for the Month of April-2025 | W/144 | 10/07/2025 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2689 | HOWRAH | Howrah Division | Survey & collection of data through Mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Howrah District. , SM/08990 | Support-M&E | Work Order for Survey & Collection of house hold details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system in Bikihakola Piped Water Supply Scheme under Howrah District. | 503/HD | 08/03/2022 | 15 | UNIVERSAL CORPORATION | 0.73 | 0 | 0 | 0
2690 | HOWRAH | Howrah Division | Survey & collection of data through Mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Howrah District. , SM/08990 | Support-M&E | Work order for Survey & Collection of house hold details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system in Bikihakola Piped Water Supply Scheme under Howrah District. (Part-B) | 507/HD | 08/03/2022 | 15 | PRADIP KUMAR JATI | 0.72 | 0 | 0 | 0
2691 | HOWRAH | Howrah Division | Survey & collection of data through Mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Howrah District. , SM/08990 | Support-M&E | Work Order for Conducting Training Programme under "Jal Swapno Mission" for Amta-II, Panchla, J.B.Pur, Sankrail, Domjur & Bally Jagacha Blocks of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | 331/HD | 17/02/2022 | 45 | M/S ASHIRBAD (INDIA) | 4 | 1.65 | 41.23 | 40
2692 | HOWRAH | Howrah Division | Survey & collection of data through Mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Howrah District. , SM/08990 | Support-M&E | SURVEY & COLLECTION OF DATA THROUGH MOBILE APP REGARDING AVAILABILITY OF DRINKING WATER, SANITATION FACILITIES & OTHER PARAMETERS IN PRIMARY, UPPER PRIMARY SCHOOLS AND ANGANWADI CENTERS AT THE AREA OF AMTA-I BLOCK, UDAYNARAYANPUR BLOCK, JAGATBALLVPUR BLOCK, BAGNAN-I & II BLOCK (PART-A) AND AMTA-II BLOCK (PART-B), DOMJUR BLOCK (PART-B), SANKRAIL BLOCK (PART-B) WITHIN HOWRAH DISTRICT UNDER HOWRAH DIVISION PHE DTE. (Part-I) | 1968/HD | 12/05/2023 | 15 | HUMAN RIGHTS COUNCIL OF INDIA | 0.82 | 0 | 0 | 0
2693 | HOWRAH | Howrah Division | Survey & collection of data through Mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Howrah District. , SM/08990 | Support-M&E | SURVEY & COLLECTION OF DATA THROUGH MOBILE APP REGARDING AVAILABILITY OF DRINKING WATER, SANITATION FACILITIES & OTHER PARAMETERS IN PRIMARY, UPPER PRIMARY SCHOOLS AND ANGANWADI CENTERS AT THE AREA OF AMTA-I BLOCK, UDAYNARAYANPUR BLOCK, JAGATBALLVPUR BLOCK, BAGNAN-I & II BLOCK (PART-A) AND AMTA-II BLOCK (PART-B), DOMJUR BLOCK (PART-B), SANKRAIL BLOCK (PART-B) WITHIN HOWRAH DISTRICT UNDER HOWRAH DIVISION PHE DTE. (Part-II) | 1979/HD | 12/05/2023 | 15 | HUMAN RIGHTS COUNCIL OF INDIA | 0.37 | 0 | 0 | 0
2694 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Continuation order for Remuneration of Chemist / Bacteriologist and Laboratory Assistant 02 (Two) nos. new of Silampur Sub District Laboratory & Sampling Assistant 01 (one) no. of Howrah District Laboratory under Howrah Division, PHE Dte. for 12 (twelve) months w.e.f. 01.10.2021 to 30.09.2022. | 1900/HD | 30/09/2021 | 365 | M/S ASHIRBAD (INDIA) | 4.47 | 4.47 | 100 | 100
2695 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Day to day work as 2nd Installment of Water Testing Laboratory 2023 | BP-2023-24-233 | 23/08/2023 | 0 | RANAPARA | 0.35 | 0 | 0 | 0
2696 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Payment for NGO Lab for the month of August 2023 | BP-2023-24-265 | 08/09/2023 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2697 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Payment for NGO Lab August 2023 | BP-2023-24-263 | 08/09/2023 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2698 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Festival Bonus for NGO Anandaniketan Laboratory | BP-2023-24-380 | 13/10/2023 | 0 | ANANDA NIKETAK | 0.16 | 0 | 0 | 0
2699 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary Bill of NGO Laboratory for the month of October 2023 | BP-2023-24-460 | 08/11/2023 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2700 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary Bill for the month of May 2023 for Laboratory personnel | BP-2023-24-101 | 16/06/2023 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2701 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill for the month of November 2023 for NGO Laboratory | BP-2023-24-508 | 07/12/2023 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2702 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary Bill for NG Laboratory for the month of October 2023 | BP-2023-24-459 | 08/11/2023 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2703 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Day to day work as 2nd Installment of Water Testing Laboratory 2023 | BP-2023-24-232 | 23/08/2023 | 0 | ANANDA NIKETAK | 0.35 | 0 | 0 | 0
2704 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Day to day work as 2nd Installment of Water Testing Laboratory 2023 | BP-2023-24-234 | 23/08/2023 | 0 | GONDALPARA | 0.35 | 0 | 0 | 0
2705 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill for the of September 2023 for NG Laboratory | BP-2023-24-352 | 10/10/2023 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2706 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary Bill for the month of September 2023 For NGO Laboratory | BP-2023-24-354 | 10/10/2023 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2707 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill | 23-24(23,24.25) | 12/05/2023 | 0 | DIFFERENT AGENCIES | 2.7 | 0 | 0 | 0
2708 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Payment of Chemist bacteriologist and Lab Assistant for the month of June 2023 | BP-2023-24-143 | 05/07/2023 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2709 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salaray Bill for the month of July 2023 | BP-2023-24-196 | 07/08/2023 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2710 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Payment of Chemist bacteriologist and Lab Assistant for the month of June 2023 | BP-2023-24-141 | 05/07/2023 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2711 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill of NGO Laboratory for the month of October 2023 | BP-2023-24-461 | 08/11/2023 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2712 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill for the month of November 2023 for NGO Laboratory | BP-2023-24-507 | 07/12/2023 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2713 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill for the month of July 2023 | BP-2023-24-198 | 07/08/2023 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2714 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Payment for NOG Lab for the month of August 2023 | BP-2023-24-264 | 08/09/2023 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2715 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Festival Bonus for NGO Laboratory Gondalpara | BP-2023-24-382 | 13/10/2023 | 0 | GONDALPARA | 0.16 | 0 | 0 | 0
2716 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill for the month of November 2023 for NGO Laboratory | BP-2023-24-509 | 07/12/2023 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2717 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill for NGO Laboratory personnel for the month of May 2023 | BP-2023-24-102 | 16/06/2023 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2718 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Payment of Chemist bacteriologist and Lab Assistant for the month of June 2023 | BP-2023-24-142 | 05/07/2023 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2719 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Festival Bonus for NGO Laboratory Ranapara | BP-2023-24-381 | 13/10/2023 | 0 | RANAPARA | 0.16 | 0 | 0 | 0
2720 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill for NGO Laboratory Personnel for the month of May 2023 | BP-2023-24-103 | 16/06/2023 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2721 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary Bill for the month of July 2023 | BP-2023-24-199 | 07/08/2023 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2722 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary Bill for the month of September 2023 for NGO Laboratory | BP-2023-24-353 | 10/10/2023 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2723 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary Bill of Laboratory Personnel for the month of January 2024 | BP-2023-24-628 | 07/02/2024 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2724 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill of laboratory personnel for the month of January 2024 | BP-2023-24-621 | 07/02/2024 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2725 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Remuneration for the Month of June 2024 of Chemist, Bacteriologist and Laboratory Assistant of Ananda Niketan Water Testing Laboratory. | BP-2024-25-167 | 10/07/2024 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2726 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | REMUNERATION OF CHEMIST, BACTERIOLOGIST AND LAB. ASSISTANT FOR THE MONTH MAY,2024 OF GONDALPARA NABIN PRAGATI SEBA SAMITY | BP-2024-25-119 | 11/06/2024 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2727 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | REMUNERATION OF CHEMIST, BACTERIOLOGIST AND LAB. ASSISTANT FOR THE MONTH APRIL,2024 OF GONDALPARA LABORATORY | BP-2024-25-61 | 13/05/2024 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2728 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Operational charges of water testing laboratory ( 1st instalment of FY : 2024-25) | BP-2024-25-96 | 28/05/2024 | 0 | RANAPARA | 0.4 | 0 | 0 | 0
2729 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary for Laboratory Personnel for the Month of March 2024 | BP-2024-25-6 | 05/04/2024 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2730 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Remuneration for the Month of June' 2024 of Chemist, Bacteriologist and Laboratory Assistant of Gondalpara Nabin Pragati Seba Samity Water Testing Laboratory. | BP-2024-25-169 | 10/07/2024 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2731 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Remuneration Laboratory Personnel for the month of December 2023 | BP-2023-24-554 | 08/01/2024 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2732 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill for Laboratory personnel for the month of February 2024 | BP-2023-24-678 | 07/03/2024 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2733 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | REMUNERATION OF CHEMIST, BACTERIOLOGIST AND LAB. ASSISTANT FOR THE MONTH APRIL,2024 OF RANAPARA LABORATORY | BP-2024-25-62 | 13/05/2024 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2734 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | REMUNERATION OF CHEMIST, BACTERIOLOGIST AND LAB. ASSISTANT FOR THE MONTH MAY,2024 OF ANANDA NIKETAN LABORATORY | BP-2024-25-117 | 11/06/2024 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2735 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Remuneration Laboratory Personnel for the month of December 2023 | BP-2023-24-556 | 08/01/2024 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2736 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Operational charges of water testing laboratory ( 1st instalment of FY : 2024-25) | BP-2024-25-95 | 28/05/2024 | 0 | ANANDA NIKETAK | 0.4 | 0 | 0 | 0
2737 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | REMUNERATION OF CHEMIST, BACTERIOLOGIST AND LAB. ASSISTANT FOR THE MONTH MAY,2024 OF RANAPARA GRAM BIKASH KENDRA LABORATORY | BP-2024-25-118 | 11/06/2024 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2738 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Remuneration Laboratory Personnel for the month of December 2023 | BP-2023-24-555 | 08/01/2024 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2739 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill for Laboratory personnel for the month of January 2024 | BP-2023-24-620 | 07/02/2024 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2740 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Operational charges of water testing laboratory ( 1st instalment of FY : 2024-25) | BP-2024-25-97 | 28/05/2024 | 0 | GONDALPARA | 0.4 | 0 | 0 | 0
2741 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill for Laboratory personnel for the month of February 2024 | BP-2023-24-680 | 07/03/2024 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2742 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary for Laboratory Personnel for the Month of March 2024 | BP-2024-25-5 | 05/04/2024 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2743 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Remuneration for the Month of June' 2024 of Chemist, Bacteriologist and Laboratory Assistant of Ranapara Gram Bikash Kendra Water Testing Laboratory. | BP-2024-25-168 | 10/07/2024 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2744 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary bill for Laboratory personnel for the month of February 2024 | BP-2023-24-679 | 07/03/2024 | 0 | RANAPARA | 0.45 | 0 | 0 | 0
2745 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Salary for Laboratory Personnel for the Month of March 2024 | BP-2024-25-7 | 05/04/2024 | 0 | GONDALPARA | 0.45 | 0 | 0 | 0
2746 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | REMUNERATION OF CHEMIST, BACTERIOLOGIST AND LAB. ASSISTANT FOR THE MONTH APRIL,2024 OF ANANDA NIKETAN LABORATORY | BP-2024-25-60 | 13/05/2024 | 0 | ANANDA NIKETAK | 0.45 | 0 | 0 | 0
2747 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte , SM/16933 | Support-WQMSP | Yearly Maintenance of two nos Laboratories activities of Howrah District Laboratory & Sub-District Laboratory at Silampur under Howrah Division, PHE Dte. [Period from 01/01/2024 to 30/06/2024] | 4784/HD | 29/12/2023 | 183 | M/S ASHIRBAD (INDIA) | 0.93 | 0 | 0 | 100
2748 | HOWRAH | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. , SM/06614 | Support-WQMSP | Supply of chemicals/consumables, Glasswares, Instruments & Miscellaneous related to NABL Accreditation for Chemical Testing of potable water of District level Water Quality Testing Laboratory for 11 nos mandatory parameters for Howrah District Water Testing Laboratory under Howrah Division, PHE Dte. | BP-2021-22-409 | 14/03/2022 | 0 | NATURAL RESOURCES CONSORTIUM | 8.72 | 0 | 0 | 0
2749 | HOWRAH | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. , SM/06614 | Support-WQMSP | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | 1416/HD | 08/07/2022 | 15 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 4.44 | 100 | 0
2750 | HOWRAH | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. , SM/06614 | Support-WQMSP | Supplying, fitting and fixing of ACP LED Board for Howrah District water Testing Laboratory under Howrah Division, PHE Dte. | 979/AE/USD | 24/03/2023 | 45 | ABONTICA ENTERPRISE | 0.97 | 0.97 | 100 | 100
2751 | HOWRAH | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. , SM/06614 | Support-WQMSP | Supplying, fitting and fixing of ACP LED Board for Gandalpara Nabin Pragati Seva Samity Sub-District water Testing Laboratory under Howrah Division, PHE Dte. | 978/AE/USD | 24/03/2023 | 45 | ABONTICA ENTERPRISE | 0.97 | 0.97 | 100 | 100
2752 | HOWRAH | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. , SM/06614 | Support-WQMSP | Supplying, fitting and fixing of ACP LED Board for Anandaniketan Sub-District water Testing Laboratory under Howrah Division, PHE Dte. | 976/AE/USD | 24/03/2023 | 45 | C.S CONSTRUCTION | 0.97 | 0.97 | 100 | 100
2753 | HOWRAH | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. , SM/06614 | Support-WQMSP | Supplying, fitting and fixing of water purifer machine and LED Board at different District-Laboratory under Howrah Division, PHE Dte. | 975/AE/USD | 24/03/2023 | 45 | SUSHANTA MONDAL | 0.54 | 0.54 | 100 | 100
2754 | HOWRAH | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. , SM/06614 | Support-WQMSP | Supplying, fitting and fixing of ACP LED Board for Silampur Sub- District water Testing Laboratory under Howrah Division, PHE Dte. | 980/AE/USD | 24/03/2023 | 45 | ABONTICA ENTERPRISE | 0.97 | 0.97 | 100 | 100
2755 | HOWRAH | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. , SM/06614 | Support-WQMSP | Work Order for Procurement of Chemicals required for smooth running of the laboratories under Howrah Division, PHE Dte. | 1414/HD | 08/07/2022 | 15 | M/S LAXMI ENTERPRISE | 4.17 | 4.17 | 100 | 0
2756 | HOWRAH | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. , SM/06614 | Support-WQMSP | Supplying, fitting and fixing of ACP LED Board for Ranapara Gramin Bikash Kendra Sub-District water Testing Laboratory under Howrah Division, PHE Dte. | 977/AE/USD | 24/03/2023 | 45 | ABONTICA ENTERPRISE | 0.97 | 0.97 | 100 | 100
2757 | HOWRAH | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. , SM/06614 | Support-WQMSP | Procurement of Chemicals for water testing laboratories under Howrah Division PHE Dte. | 3137/HD | 10/07/2024 | 15 | LAB ANALYTICS | 7.38 | 7.38 | 100 | 100
2758 | HOWRAH | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. , SM/06614 | Support-WQMSP | PROCUREMENT OF CHEMICALS FOR WATER TESTING LABORATORIES UNDER HOWRAH DIVISION PHE DTE. | 4415/HD | 25/11/2025 | 60 | LAB ANALYTICS | 13.58 | 0 | 0 | 0
2759 | HOWRAH | Howrah Division | Chemical Glassware and Instrument Requirement of Howrah District Laboratory for NABL Accreditation under Howrah Division PHE Dte. , SM/08684 | Support-WQMSP | Supply of chemicals /consumables and Miscellaneous items related to NABL Accreditation for Chemical Testing of potable water of District level Water Quality Testing Laboratory for 11 nos mandatory parameters for Howrah District Water Testing Laboratory under Howrah Division, PHE Dte. | BP-2021-22-382 | 08/03/2022 | 0 | NATURAL RESOURCES CONSORTIUM | 1.53 | 0 | 0 | 0
2760 | HOWRAH | Howrah Division | Chemical Glassware and Instrument Requirement of Howrah District Laboratory for NABL Accreditation under Howrah Division PHE Dte. , SM/08684 | Support-WQMSP | NABL | BP-2022-23-156 | 02/08/2022 | 0 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2761 | HOWRAH | Howrah Division | Chemical Glassware and Instrument Requirement of Howrah District Laboratory for NABL Accreditation under Howrah Division PHE Dte. , SM/08684 | Support-WQMSP | NABL Lab | BP-2022-23-93 | 28/06/2022 | 0 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2762 | HOWRAH | Howrah Division | Chemical Glassware and Instrument Requirement of Howrah District Laboratory for NABL Accreditation under Howrah Division PHE Dte. , SM/08684 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Silampur Sub-District Water Testing Laboratory under Howrah Division, PHE Dte. | W/792 | 03/03/2022 | 0 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.13 | 0 | 0 | 0
2763 | HOWRAH | Howrah Division | Chemical Glassware and Instrument Requirement of Howrah District Laboratory for NABL Accreditation under Howrah Division PHE Dte. , SM/08684 | Support-WQMSP | Work Order for Supplying of office furnitures and SS sliding main gate & SS letters for sign board required for NABL recognition for Silampur Sub-District laboratory under Uluberia Sub-Division of Howrah Division, PHE Dte. | 120/AE/USD | 15/06/2022 | 15 | ABONTICA ENTERPRISE | 3.21 | 0 | 0 | 0
2764 | HOWRAH | Howrah Division | Chemical Glassware and Instrument Requirement of Howrah District Laboratory for NABL Accreditation under Howrah Division PHE Dte. , SM/08684 | Support-WQMSP | Work Order for Supply of accessories for requirement of Audit in connection of NABL Accreditation as per ISO/IEC 17025 : 2017 Standard at Howrah District Water Testing Laboratory. | 1363/HD | 30/06/2022 | 7 | ABONTICA ENTERPRISE | 0.89 | 0 | 0 | 0
2765 | HOWRAH | Howrah Division | Chemical Glassware and Instrument Requirement of Howrah District Laboratory for NABL Accreditation under Howrah Division PHE Dte. , SM/08684 | Support-WQMSP | NABL LAB | BP-2022-23-414 | 01/02/2023 | 0 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.04 | 0 | 0 | 0
2766 | HOWRAH | Howrah Division | Chemical Glassware and Instrument Requirement of Howrah District Laboratory for NABL Accreditation under Howrah Division PHE Dte. , SM/08684 | Support-WQMSP | PROCUREMENT OF CHEMICALS FOR WATER TESTING LABORATORIES UNDER HOWRAH DIVISION PHE DTE. | 4415/HD | 25/11/2025 | 60 | LAB ANALYTICS | 13.58 | 0 | 0 | 0
2767 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte , SM/19114 | Support-MIS | Procurement of computer through GEM against order no- 511687891718750 and 511687891718755 | BP-2023-24-672 | 06/03/2024 | 0 | IONET | 12.47 | 0 | 0 | 0
2768 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte , SM/19114 | Support-MIS | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, Printer through GeM portal for the official use under office of the Executive Engineer and all sub divisional offices under Howrah Division, PHE Dte. | BP-2024-25-219 | 30/07/2024 | 0 | IONET | 0.27 | 0 | 0 | 0
2769 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte , SM/19114 | Support-MIS | Procurement of photocopier through GEM Order No- GEMC-511687891728920 | BP-2024-25-51 | 07/05/2024 | 0 | IONET | 2.49 | 0 | 0 | 0
2770 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte , SM/19114 | Support-MIS | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, Printer through GeM portal for the official use under office of the Executive Engineer and all sub divisional offices under Howrah Division, PHE Dte. | BP-2024-25-218 | 30/07/2024 | 0 | IONET | 3.36 | 0 | 0 | 0
2771 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte , SM/19114 | Support-MIS | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, Printer through GeM portal for the official use under office of the Executive Engineer and all sub divisional offices under Howrah Division, PHE Dte. | BP-2024-25-340 | 18/09/2024 | 0 | EASY DAY ENTERPRISE | 1.9 | 0 | 0 | 0
2772 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte , SM/19114 | Support-MIS | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, Printer through GeM portal for the official use under office of the Executive Engineer and all sub divisional offices under Howrah Division, PHE Dte. | BP-2024-25-221 | 30/07/2024 | 0 | IONET | 0.83 | 0 | 0 | 0
2773 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte , SM/19114 | Support-MIS | Procurement of scanner and UPS through GEM Order No- GEMC-511687891728920 | BP-2024-25-52 | 07/05/2024 | 0 | IONET | 4.62 | 0 | 0 | 0
2774 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte , SM/19114 | Support-MIS | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, Printer through GeM portal for the official use under office of the Executive Engineer and all sub divisional offices under Howrah Division, PHE Dte. | BP-2024-25-220 | 30/07/2024 | 0 | IONET | 1.49 | 0 | 0 | 0
2775 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte , SM/19114 | Support-MIS | Supply,Delivery and Installation of Desktop Computer,UPS,Scanner,Printer through GeM portal for the official use under office of the Executive Engineer and all Sub-Divisional offices under Howrah Division,P.H.E Dte. |  | 09/10/2025 | 0 | IONET | 5.38 | 0 | 0 | 0
2776 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte , SM/19114 | Support-MIS | Supply,Delivery and Installation of Desktop Computer,UPS,Scanner,Printer through GeM Portal for the official use under office of the Executive Engineer and all Sub-Divisional offices under Howrah Division,P.H.E Dte. |  | 09/10/2025 | 0 | IONET | 6.93 | 0 | 0 | 0
2777 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte , SM/19114 | Support-MIS | Supply,Delivery and Installation of Desktop Computer,UPS,Scanner,Printer through GeM Portal for the official use under office of the Executive Engineer and all Sub-Divisional offices under Howrah Division,P.H.E Dte. |  | 09/10/2025 | 0 | IONET | 0.48 | 0 | 0 | 0
2778 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte , SM/19114 | Support-MIS | Supply,Delivery and Installation of Desktop Computer,UPS,scanner,Printer through GeM Portal for the official use under office of the Executive Engineer and all Sub-Divisional offices under Howrah division,P.H.E Dte. |  | 09/10/2025 | 0 | IONET | 0.15 | 0 | 0 | 0
2779 | HOWRAH | Howrah Division | Remuneration, Festival Bonus and Maintenance of 5 nos Laboratories in Howrah District related to Water Quality Monitoring and Surveillance activities under Jal Jeevan Mission 2024-2025 , SM/19318 | Support-WQMSP | Continuation order for Remuneration of Chemist / Bacteriologist and Laboratory Assistant 02 (Two) nos. new of Silampur Sub District Laboratory & Sampling Assistant 01 (one) no. of Howrah District Laboratory under Howrah Division, PHE Dte. for 01(one) months w.e.f. 01/01/2025 to 31/01/2025. | 5426/HD | 31/12/2024 | 31 | M/S ASHIRBAD (INDIA) | 0.71 | 0 | 0 | 0
2780 | HOWRAH | Howrah Division | Remuneration, Festival Bonus and Maintenance of 5 nos Laboratories in Howrah District related to Water Quality Monitoring and Surveillance activities under Jal Jeevan Mission 2024-2025 , SM/19318 | Support-WQMSP | Continuation order for Operation of Laboratory activities for Howrah District Laboratory at Domjur under Howrah Division, PHE Dte. for 01(one) months w.e.f. 01/01/2025 to 31/01/2025. | 5427/HD | 31/12/2024 | 31 | LAB ANALYTICS | 0.84 | 0 | 0 | 0
2781 | HOWRAH | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Howrah District. , SM/08989 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | 4738/RS | 22/08/2022 | 365 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 271.44 | 271.44 | 100 | 100
2782 | HOWRAH | Howrah Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious and safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Howrah District under Howrah Division, PHE Dte , SM/19091 | Support-IEC | Conceptualization, design, implementation of community sensitization / mobilization activities using various mediums on JJM, provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water quality issues, water conservation and WASH related issues as per operational guideline of JJM and preparation of web based Digital (A/V) training material (Bengali) at Howrah District under Howrah Division, PHE Dte, Govt. of West Bengal. | 799/HD | 20/02/2024 | 602 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 57.27 | 0 | 0 | 80
2783 | HOWRAH | Howrah Division | Drinking Water sample collection and testing through field Test Kits (FTKs) and uploading charges for the same related to water quality Monitoring and surveillance programme under Jal Jeevan Mission, Howrah Division, PHE Dte , SM/18274 | Support-WQMSP | Submission of the requirement of fund for payment to Asha's under FTK Programme (Phase-II) upto September 2023 (Memo No- CMOH/DHFWS/HOW-2600/23 dated 10/11/2023 and CMOH/DHFWS/HOW-1639/23 dated 14/07/2023 | BP-2023-24-565 | 15/01/2024 | 0 | DISTRICT HEALTH FAMILY WELFARE SAMITI HOWRAH | 25.16 | 0 | 0 | 0
2784 | HOWRAH | Howrah Division | Drinking Water sample collection and testing through field Test Kits (FTKs) and uploading charges for the same related to water quality Monitoring and surveillance programme under Jal Jeevan Mission, Howrah Division, PHE Dte , SM/18274 | Support-WQMSP | Payment to ASHAs under JAL JEEVAN MISSION (FTK) Programme of September 24 to June 25 |  | 08/09/2025 | 0 | CMOH | 11.8 | 0 | 0 | 0
2785 | HOWRAH | Howrah Division | Drinking Water sample collection and testing through field Test Kits (FTKs) and uploading charges for the same related to water quality Monitoring and surveillance programme under Jal Jeevan Mission, Howrah Division, PHE Dte , SM/18274 | Support-WQMSP | Payment to ASHAs under FTK Programme (Phase-III) of April 24 to August 24 | BP-2024-25-534 | 11/02/2025 | 0 | CMOH | 19.24 | 0 | 0 | 0
2786 | HOWRAH | Howrah Division | Drinking Water sample collection and testing through field Test Kits (FTKs) and uploading charges for the same related to water quality Monitoring and surveillance programme under Jal Jeevan Mission, Howrah Division, PHE Dte , SM/18274 | Support-WQMSP | Payment to ASHAs under JAL JEEVAN MISSION (FTK) Programme of July,2025 to December,2025 |  | 30/01/2026 | 0 | CMOH | 16.9 | 0 | 0 | 0
Total | [9 empty] | 190098.25 | 38592.79 | 20.3