## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Chandkuri (Zone-II) PWSS , SM/06922 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandkuri (Zone-II) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1464/MD | 26/11/2020 | 180 | DULAL CHANDRA DAS | 80.8 | 49.63 | 61.43 | 0
2 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Panpara PWSS , SM/06924 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Panpara W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1456/MD | 26/11/2020 | 1859 | BANERJEE CONSTRUCTION | 94.34 | 48.69 | 51.61 | 5
3 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Maligram Piped Water Supply Scheme. , SM/06895 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Maligram PWSS, Block: - Pingla, in the District of Paschim Medinipur. | 844397 | 25/01/2022 | 0 | UTTAM KUMAR DAS | 17.78 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Maligram Piped Water Supply Scheme. , SM/06895 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Maligram PWSS, Block: - Pingla, in the District of Paschim Medinipur. | 844397 | 25/01/2022 | 0 | UTTAM KUMAR DAS | 14.42 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Maligram Piped Water Supply Scheme. , SM/06895 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Maligram W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1450/MD | 26/11/2020 | 180 | HARIPADA PATTANAYAK | 96.05 | 35.03 | 44.65 | 96
6 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Palashi Piped Water Supply Scheme. , SM/06930 | Retrofitting | Supply & installation of 20 KVA output diesel Generator set on monthly hire basis including day to day operation and maintenance of the same for alternative electrical arrangement in the office of Assistant Engineer, Kharagpur Sub Division and also Kharagpur WTP Water Testing Lab situated within the Inda PHE Complex etc. under Midnapore Division, PHE Dte. [Period from 03.02.2021 to 02.02.2022] | 57/AE/KSD | 02/02/2021 | 12 | PULLOCK KUMAR GHOSH | 0.86 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Palashi Piped Water Supply Scheme. , SM/06930 | Retrofitting | FHTC data entry. | 844364 | 18/01/2022 | 0 | ANIRBAN CHAKRABORTY | 0.2 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Palashi Piped Water Supply Scheme. , SM/06930 | Retrofitting | FHTC data entry. | 844364 | 18/01/2022 | 0 | SOVANDEB MANNA | 0.1 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Sabang & 1 No. PWSS within Pingla Block , SM/06932 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443458 | 26/03/2021 | 0 | SHRABONTI BERA | 0.29 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Sabang & 1 No. PWSS within Pingla Block , SM/06932 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443458 | 26/03/2021 | 0 | TANMOY BERA | 0.2 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Sabang & 1 No. PWSS within Pingla Block , SM/06932 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | `8443458 | 26/03/2021 | 0 | GANESH CH NANDY | 0.27 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Shimulia PWSS, Block - Ghatal, District - Paschim Medinipur , SM/09080 | Retrofitting | Security Deposit/Caution money for electric quotation. [MB No:- 2948/MMD] {Shimulia W/S Scheme.} |  | 05/07/2023 | 0 | EXECUTIVE ENGINEER, JHARGRAM MECHANICAL DIVISION, PHE DTE. | 0.93 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Shimulia PWSS, Block - Ghatal, District - Paschim Medinipur , SM/09080 | Retrofitting | Electric Quotation bill for the WBSEDCL. | BP-2023-24-177 | 20/07/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 0.93 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Shimulia PWSS, Block - Ghatal, District - Paschim Medinipur , SM/09080 | Retrofitting | Retrofitting of Shimulia PWSS to accommodate FHTC in Ghatal block under Midnapore Division, P.H.E. Dte. | 840/MD | 02/05/2022 | 30 | ANUSKA ENTERPRISE | 26.82 | 0 | 0 | 100
15 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Warda PWSS, Block - Kharagpur-II, District - Paschim Medinipur. , SM/09083 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Warda (Zone-II) PWSS under Kharagpur-II Block in Paschim Medinipur District. | 423/MD | 04/03/2022 | 30 | S.T. ENTERPRISE | 38.17 | 0 | 0 | 0
16 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Warda PWSS, Block - Kharagpur-II, District - Paschim Medinipur. , SM/09083 | Retrofitting | Retrofitting of Warda PWSS (Zone-II) to accommodate FHTC in Kharagpur- II block under Midnapore Division, PHE Dte. | 1134/MD | 13/06/2022 | 21 | M/S. D.K.H.CONSTRUCTION | 24.23 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Warda PWSS, Block - Kharagpur-II, District - Paschim Medinipur. , SM/09083 | Retrofitting | Material Requisition To Resource Division | 3414/MD | 25/11/2024 | 0 | Resource Division | 10.63 | 0 | 0 | 0
18 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kanchangeria PWSS, Block - Debra, District - Paschim Medinipur. , SM/09085 | Retrofitting | Retrofitting of Kanchangeria PWSS to accommodate FHTC in Debra Block under Midnapore Division, PHE Dte. | 1012/MD | 27/05/2022 | 1311 | M/S. A.R. ENTERPRISE. | 56.15 | 0 | 0 | 65
19 | PASCHIM MEDINIPUR | Midnapore Division | Rerofitting of Ground Water Based Dhengasole Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/08677 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Jharbhanga in Dhengasole PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-03) | 100/AE/MSSD | 24/02/2021 | 15 | CHANDAN YADAV | 4.82 | 0 | 0 | 0
20 | PASCHIM MEDINIPUR | Midnapore Division | Rerofitting of Ground Water Based Dhengasole Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/08677 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dhengasole, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | 60/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.08 | 1.82 | 100 | 0
21 | PASCHIM MEDINIPUR | Midnapore Division | Rerofitting of Ground Water Based Dhengasole Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/08677 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Dhengasole Dakshinpara in Dhengasole PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-02) | 99/AE/MSSD | 24/02/2021 | 15 | CHANDAN YADAV | 4.72 | 0 | 0 | 0
22 | PASCHIM MEDINIPUR | Midnapore Division | Rerofitting of Ground Water Based Dhengasole Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/08677 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Dhengasole Uttar Para in Dhengasole PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-01) | 98/AE/MSSD | 24/02/2021 | 15 | CHANDAN YADAV | 4.8 | 0 | 0 | 0
23 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Lachmi Chak water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2512/W/MMD | 30/11/2021 | 4 | DEBJYOTI BASU | 4.47 | 0 | 0 | 100
24 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Lachhmi Chak, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. (W/O-147/W/MMD, DT-31/01/2022) | BP-2021-22-120 | 17/03/2022 | 0 | P.P.CONCERN | 3.68 | 0 | 0 | 0
25 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Purchasing of materials. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.3 | 0 | 0 | 0
26 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Sinking of (1 St) mniX 100 mm.X 150rnir) RBCM by Rnla.ry method at lJaspnr writes *«mix scheme. tube we11 no. I of Sabang i3lock of Paschim Midnapur District under Midtidpur Mechanical Division P.II.E Eite. |  | 03/08/2022 | 0 | DEBJYOTI BASU | 3.95 | 0 | 0 | 0
27 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | BP-2021-22-505 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.9 | 0 | 0 | 0
28 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas. Block - Sabang, District - Paschim Medinipur |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.3 | 0 | 0 | 0
29 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Lachmi Chak water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2514/W/MMD | 30/11/2021 | 4 | DEBJYOTI BASU | 4.47 | 0 | 0 | 0
30 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Additional work in connection with sinking of (150mmX100mmX150mtr) RBTW by Rotary method at Lachmi Chak water supply scheme , tube well no. 2 of Sabang Block of Paschim Midnapur Dist. under MMD PHE Dte. | 43/MMSD-I | 19/01/2022 | 7 | DEBJYOTI BASU | 0.19 | 0 | 0 | 0
31 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Additional work in connection with sinking of (150mmX100mmX150mtr) RBTW by Rotary method at Lachmi Chak water supply scheme , tube well no. I of Sabang Block of Paschim Midnapur Dist. under MMD PHE Dte. | 44/MMSD-I | 19/01/2022 | 7 | DEBJYOTI BASU | 0.19 | 0 | 0 | 0
32 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Material Requisition To Resource Division | 2127/MD | 14/12/2021 | 0 | Resource Division | 1.3 | 0 | 0 | 0
33 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Lachhmi Chak, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 147/W/MMD | 31/01/2022 | 120 | P.P.CONCERN | 6.5 | 0 | 0 | 0
34 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -II at Lachhmi Chak, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 148/W/MMD | 31/01/2022 | 120 | SUJOY RANJAN BHOWMICK | 6.51 | 0 | 0 | 0
35 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Lachhmi Chak (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 175/MD | 01/02/2022 | 150 | BIDHAN CHANDRA PATRA | 22.21 | 0 | 0 | 80
36 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Lachhmi Chak (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 176/MD | 01/02/2022 | 150 | BIDHAN CHANDRA PATRA | 21.5 | 0 | 0 | 90
37 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09675 | New | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 0 | 100
38 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC in Bamanda PWSS within Kharagpur Sub-Division under Midnapore Division, PHE Dte. , SM/09101 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bamanda W/S Scheme, Block: - Dantan-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1320/MD | 06/11/2020 | 180 | SANKAR PRASAD MAITY | 27.77 | 0 | 0 | 0
39 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10842 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Barsahara PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1657/MD | 28/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.14 | 0 | 0 | 100
40 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10842 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0 | 0 | 25
41 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10842 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0 | 0 | 100
42 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10842 | Augmentation | Service connection charges of WBSEDCL at TW-III (Additional) of Barasahara Water Supply Scheme (Ref. ID - 20395154) | BP-2022-23-152 | 28/03/2023 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
43 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10842 | Augmentation | Electric quotation for Barsahara PWSS Tube Well-III WS Scheme (Ref. ID 203935154) |  | 25/03/2023 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
44 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10842 | Augmentation | Service connection charges of WBSEDCL at TW-IV (Additional) of Barasahara Water Supply Scheme (Ref. ID - 203934601) |  | 22/03/2023 | 0 | WBSEDCL | 2.55 | 0 | 0 | 0
45 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10842 | Augmentation | Electric quotation for Barsahara PWSS Tube Well-IV WS Scheme (Ref. ID 203934601) | BP-2002-23-153 | 28/03/2023 | 0 | WBSEDCL | 2.55 | 0 | 0 | 0
46 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10842 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | 1892/MD | 12/09/2022 | 60 | DULAL CHANDRA DAS | 50.39 | 0 | 0 | 50
47 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10842 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 2308/W/MMD | 29/12/2022 | 180 | RITESH ENTERPRISE | 10.79 | 0 | 0 | 85
48 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10842 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House for Sansahara & Manikarah villages within Barsahara PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 584/MD | 23/02/2023 | 60 | DULAL CHANDRA DAS | 17.7 | 0 | 0 | 10
49 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10842 | Augmentation | Supply and Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring at Tube Well no 4 of Barshahara Water Supply Scheme (Block- Sabang) under MMD, PHE Dte., Dist. Paschim Medinipur. | 1850/W/MMD | 22/08/2023 | 677 | MANORANJAN DEY | 12.51 | 0 | 0 | 100
50 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10842 | Augmentation | Supply and Installation of Voltage Stabilizer for Tube well No.-3 of Barshahara Water Supply Scheme [ Block-Sabang] under MMD, PHE Dte., Dist.- Paschim Medinipur. (JJM Work) | 1112/MMSD-I | 14/09/2023 | 30 | RITESH ENTERPRISE | 2.83 | 0 | 0 | 100
51 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Bajpara PWSS under Midnapore Sadar Block in Paschim Medinipur District , SM/09704 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bajpara PWSS under Midnapore Sadar Block in Paschim Medinipur District. | 2005/MD | 01/12/2021 | 30 | M/S. CARE | 64.02 | 0 | 0 | 0
52 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Balarampur PWSS under Kharagpur-II Block in Paschim Medinipur District , SM/09706 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Balarampur PWSS under Kharagpur-II Block in Paschim Medinipur District. | 2185/MD | 17/12/2021 | 30 | S.T. ENTERPRISE | 61.78 | 0 | 0 | 0
53 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Balarampur PWSS under Kharagpur-II Block in Paschim Medinipur District , SM/09706 | Retrofitting | Extension of laying of distribution uPVC Pipe line Left-out portion and all allied works at i) Balarampur village (North side), ii) Balarampur village (South side) and Madhpur, iii) Some part of Krishnapur & Ramchandrapur and iv) Some part of Gobindanagar & Kanchantala under JJM of Balarampur & its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | 2272/MD | 09/11/2022 | 30 | S.T. ENTERPRISE | 21.85 | 0 | 0 | 100
54 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Balarampur PWSS under Kharagpur-II Block in Paschim Medinipur District , SM/09706 | Retrofitting | Retrofitting to accommodate FHTC (350 Nos.) including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sche-80/20mm dia.) HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Balarampur W/S Scheme within Kharagpur-II Dev. block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | 2269/MD | 09/11/2022 | 21 | SUBRATA DAS | 13.21 | 0 | 0 | 100
55 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10685 | Augmentation | Restoration of pipe line damaged due to construction of PMGSY roads, village Roads over existing pipe line Sartla & its adjoining mouzas (Rampura, Kororda, Cheena) W/S Scheme at Sabang Block under Kharagpur Sub Division within Midnapore Division, P.H.E. Dte. | 2182/MD | 17/12/2021 | 45 | GOBINDA MAITY | 43.21 | 0 | 0 | 100
56 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10685 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Sartla PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1676/MD | 29/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.23 | 0 | 0 | 100
57 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10685 | Augmentation | Supply and delivery at site Submersible pumping machinery and other electro-mechanical equipment in connection with Rejuvenation of Ground water based piped piped water supply scheme for PH No III of Sartla Part to accommodate FHTC under Sabang Block in Paschim Medinipur District under M.M.D,.PH.E. DTE.TSM009946 | 605/MMSD-I | 06/06/2023 | 15 | EMCON | 5.76 | 0 | 0 | 100
58 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10685 | Augmentation | QUOTATION MONEY FOR ADDITIONAL TUBEWELL NO 3 OF SARTLA WATER SUPPLY SCHEME [ REFERENCE ID 860268179, APLLICATION ID 100000077609 , CHANDKURI CCC, WBSEDCL ] | BP-2023-24-44 | 19/05/2023 | 0 | WBSEDCL | 0.78 | 0 | 0 | 0
59 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10685 | Augmentation | Service Connection charges of WBSEDL at Sartla Additional TW-III W/S Scheme (Consumer No. 2004156120) | BP-2022-23-91 | 04/01/2023 | 0 | WBSEDCL | 3.81 | 0 | 0 | 0
60 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10685 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 951/W/MMD | 28/03/2023 | 180 | EMCON | 10.78 | 0 | 0 | 98
61 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10685 | Augmentation | Rejuvenation of Ground water based piped water supply scheme for Sartla (Part) to Accommodate FHTC under JJM under Sabang Block in Paschim Medinipur Districct Under Medinipur Division PHE Dte. | 1479/MD | 25/07/2022 | 45 | GOBINDA MAITY | 61.29 | 0 | 0 | 100
62 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Amlagora (Block-Garhbeta-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1624/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.01 | 0 | 0 | 0
63 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Amlagora (Block-Garhbeta-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1625/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.66 | 0 | 0 | 0
64 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Material Requisition To Resource Division | 2322/MD | 17/11/2022 | 0 | Resource Division | 32.25 | 0 | 0 | 0
65 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Amlagora, Block - Garhbeta-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-387 | 18/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.05 | 0 | 0 | 0
66 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Amlagora, Block - Garhbeta-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-383 | 18/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.11 | 0 | 0 | 0
67 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Amlagora, Jot Ghanashyam & Sonakhali in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-470 | 11/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.19 | 0 | 0 | 0
68 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | 2293/W/MMD | 29/12/2022 | 180 | DEBJYOTI BASU | 23 | 0 | 0 | 0
69 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Material Requisition To Resource Division | 244/MD | 18/01/2023 | 0 | Resource Division | 100.02 | 0 | 0 | 0
70 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Material Requisition To Resource Division | 137/MD | 11/01/2023 | 0 | Resource Division | 32.25 | 0 | 0 | 0
71 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Repair and Renovation of Switch Room cum Chlorine Room No. 1 of Amlagora Water Supply Scheme within Midnapore Sadar Sub Division under Midnapore Division, PHE Dte. | 982/AE/MSSD | 17/03/2023 | 15 | MR GOUTAM GHOSH, | 0.97 | 0 | 0 | 10
72 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Repair and Renovation of Switch Room cum Chlorine Room No. 2 of Amlagora Water Supply Scheme within Midnapore Sadar Sub Division under Midnapore Division, PHE Dte. (SL No-02) | 983/AE/MSSD | 17/03/2023 | 15 | MR GOUTAM GHOSH, | 0.97 | 0 | 0 | 10
73 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Laying distribution pipeline, Soil test and Construction of RCC Over Head Reservoir of capacity 200 CuM and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Amlagora W/S Scheme to accommodate FHTC with Garhbeta-I Dev. Block under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. Dist.- Paschim Medinipur. | 1959/MD | 20/09/2022 | 180 | BANERJEE CONSTRUCTION | 606.57 | 0 | 0 | 33
74 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. , SM/09923 | Augmentation | Construction of Boundary wall at 1st Tube well site for Augmentation of Amlagora PWSS, Block - Garhbeta-I, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Total length 120 mtr., Column size 250X250mm, 3.00M, C/C ht.- 2.300 mtr. from G.L.) | 2850/MD | 09/09/2024 | 60 | AJITESH ACHARJEE | 11.39 | 0 | 0 | 0
75 | PASCHIM MEDINIPUR | Midnapore Division | MARKUNDA AND ADJOINING MOUJAS PWSS , SM/13098 | New | Material Requisition To Resource Division | 1171/MD | 26/04/2023 | 0 | Resource Division | 32 | 0 | 0 | 0
76 | PASCHIM MEDINIPUR | Midnapore Mechanical | MARKUNDA AND ADJOINING MOUJAS PWSS , SM/13098 | New | electric quotation for T/W - II of Markunda water supply Scheme | Elce/quot/2004530133 | 14/12/2023 | 30 | WBSEDCL | 4.07 | 0 | 0 | 0
77 | PASCHIM MEDINIPUR | Midnapore Mechanical | MARKUNDA AND ADJOINING MOUJAS PWSS , SM/13098 | New | Quotation of new power connection at Markunda PWSS T/W - I | BP-2023-24-466 | 27/12/2023 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
78 | PASCHIM MEDINIPUR | Midnapore Mechanical | MARKUNDA AND ADJOINING MOUJAS PWSS , SM/13098 | New | Quotation for new power connection at Markunda PWSS T/W - II | BP-2023-24-465 | 27/12/2023 | 0 | WBSEDCL | 4.07 | 0 | 0 | 0
79 | PASCHIM MEDINIPUR | Central Drilling | MARKUNDA AND ADJOINING MOUJAS PWSS , SM/13098 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
80 | PASCHIM MEDINIPUR | Midnapore Division | MARKUNDA AND ADJOINING MOUJAS PWSS , SM/13098 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7130 Nos) including 2 years Operation & Maintenance for Kashipur, Benadiha and Markunda Pipe Water Supply Scheme within Narayangarh Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2524/MD | 18/07/2023 | 840 | NABA KUMAR BHUNIA | 1870.43 | 0 | 0 | 82
81 | PASCHIM MEDINIPUR | Midnapore Division | MARKUNDA AND ADJOINING MOUJAS PWSS , SM/13098 | New | Laying additional quantity of distribution pipeline for providing FHTC at Kashipur, Benadiha & Markunda PWSS under Narayangarh block within Midnapore Division, PHE Dte. | 3165/MD | 05/10/2024 | 255 | NABA KUMAR BHUNIA | 78.57 | 0 | 0 | 50
82 | PASCHIM MEDINIPUR | Midnapore Division | NALBONA AND ADJOINING MOUJAS PWSS , SM/13101 | New | Material Requisition To Resource Division | 1226/MD | 27/04/2023 | 0 | Resource Division | 13.53 | 0 | 0 | 0
83 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | NALBONA AND ADJOINING MOUJAS PWSS , SM/13101 | New | Quotation for new service connection atNalbona T/W-I water supply scheme. | 37/JMD | 29/04/2024 | 0 | WBSEDCL | 3.3 | 0 | 0 | 0
84 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | NALBONA AND ADJOINING MOUJAS PWSS , SM/13101 | New | Quotation for new service connection at Nalbona T/W-I water supply scheme. | 36/JMD | 29/04/2024 | 0 | WBSEDCL | 3.18 | 0 | 0 | 0
85 | PASCHIM MEDINIPUR | Central Drilling | NALBONA AND ADJOINING MOUJAS PWSS , SM/13101 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
86 | PASCHIM MEDINIPUR | Midnapore Division | NAYAPUKUR AND ADJOINING MOUJAS PWSS , SM/13102 | New | Material Requisition To Resource Division | 1177/MD | 26/04/2023 | 0 | Resource Division | 38.98 | 0 | 0 | 0
87 | PASCHIM MEDINIPUR | Central Drilling | NAYAPUKUR AND ADJOINING MOUJAS PWSS , SM/13102 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
88 | PASCHIM MEDINIPUR | Midnapore Division | NAYAPUKUR AND ADJOINING MOUJAS PWSS , SM/13102 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (5,751 Nos.) including 2 years operation & maintenance For Kunarpur, Murakata & Nayapukur Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2827/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 1515.85 | 0 | 0 | 15
89 | PASCHIM MEDINIPUR | Midnapore Division | PERUABAD AND ADJOINING MOUJAS PWSS , SM/13107 | New | Material Requisition To Resource Division | 1242/MD | 27/04/2023 | 0 | Resource Division | 24.38 | 0 | 0 | 0
90 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PERUABAD AND ADJOINING MOUJAS PWSS , SM/13107 | New | WBSEDCL new connection payment for peruabad t/w 1 | 62/JMD | 29/04/2024 | 0 | WBSEDCL | 5.52 | 0 | 0 | 0
91 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PERUABAD AND ADJOINING MOUJAS PWSS , SM/13107 | New | WBSEDCL new connection payment for Peruabad t/w 2 | 63/JMD | 29/04/2024 | 0 | WBSEDCL | 5.59 | 0 | 0 | 0
92 | PASCHIM MEDINIPUR | Central Drilling | PERUABAD AND ADJOINING MOUJAS PWSS , SM/13107 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
93 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/13111 | New | Material Requisition To Resource Division | 89/MD | 10/01/2023 | 0 | Resource Division | 6.9 | 0 | 0 | 0
94 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/13111 | New | Material Requisition To Resource Division | 3324/MD | 25/11/2024 | 0 | Resource Division | 6.78 | 0 | 0 | 0
95 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/13111 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 577/W/MMD | 20/03/2023 | 834 | R.S. ENTERPRISE | 12.62 | 0 | 0 | 60
96 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/13111 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 250 & 450 cum OHRs (Intze type) & Accommodate FHTC (4,203 Nos.) under JJM with allied work for (1) Gohaldanga & (2) Haridharpur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 3147/MD | 29/08/2023 | 718 | BANERJEE CONSTRUCTION | 1062.73 | 0 | 0 | 30
97 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/13111 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at newly proposed T/W no. II of Gohaldanga water supply scheme in the district of Paschim Medinipur under Jhargram Mechanical Division, P.H.E. Dte. | 6941/JMD | 13/09/2024 | 241 | R S ENTERPRISE | 11.26 | 0 | 0 | 60
98 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/13111 | New | Laying of rising main & interconnection for Gohaldanga & its adjoining mouzas PWSS, Block: - Chandrakona-I, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 319/MD | 29/01/2025 | 45 | ASHOK BANERJEE | 5.11 | 0 | 0 | 0
99 | PASCHIM MEDINIPUR | Midnapore Division | TRIKALPUR AND ADJOINING MOUJAS PWSS , SM/13112 | New | Material Requisition To Resource Division | 3985/MD | 06/10/2023 | 0 | Resource Division | 23.4 | 0 | 0 | 0
100 | PASCHIM MEDINIPUR | Midnapore Division | TRIKALPUR AND ADJOINING MOUJAS PWSS , SM/13112 | New | Material Requisition To Resource Division | 3443/MD | 25/11/2024 | 0 | Resource Division | 4.68 | 0 | 0 | 0
101 | PASCHIM MEDINIPUR | Midnapore Mechanical | TRIKALPUR AND ADJOINING MOUJAS PWSS , SM/13112 | New | Quotation for new power connection at Trikalpur PWSS T/W - I | BP-2023-24-602 | 07/02/2024 | 0 | WBSEDCL | 2.74 | 0 | 0 | 0
102 | PASCHIM MEDINIPUR | Midnapore Mechanical | TRIKALPUR AND ADJOINING MOUJAS PWSS , SM/13112 | New | Quotation for new power connection at Trikalpur PWSS T/W - II | BP-2023-24-601 | 07/02/2024 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
103 | PASCHIM MEDINIPUR | Central Drilling | TRIKALPUR AND ADJOINING MOUJAS PWSS , SM/13112 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
104 | PASCHIM MEDINIPUR | Midnapore Division | TRIKALPUR AND ADJOINING MOUJAS PWSS , SM/13112 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 0 | 20
105 | PASCHIM MEDINIPUR | Midnapore Division | HARINASULI & ADJOINING MOUJAS PWSS , SM/13085 | New | Material Requisition To Resource Division | 1154/MD | 25/04/2023 | 0 | Resource Division | 33.11 | 0 | 0 | 0
106 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | HARINASULI & ADJOINING MOUJAS PWSS , SM/13085 | New | New service connection charges at Harinasuli TW-II water supply scheme | 217/JMD | 21/06/2024 | 0 | WBSEDCL | 3.65 | 0 | 0 | 0
107 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | HARINASULI & ADJOINING MOUJAS PWSS , SM/13085 | New | New service connection charges at Harinasuli TW-I water supply scheme | 218/JMD | 21/06/2024 | 0 | WBSEDCL | 3.59 | 0 | 0 | 0
108 | PASCHIM MEDINIPUR | Central Drilling | HARINASULI & ADJOINING MOUJAS PWSS , SM/13085 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
109 | PASCHIM MEDINIPUR | Midnapore Division | ANTRI AND ADJOINING MOUJAS PWSS , SM/13636 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
110 | PASCHIM MEDINIPUR | Midnapore Division | ANTRI AND ADJOINING MOUJAS PWSS , SM/13636 | New | Material Requisition To Resource Division | 191/MD | 16/01/2023 | 0 | Resource Division | 20.75 | 0 | 0 | 0
111 | PASCHIM MEDINIPUR | Midnapore Division | ANTRI AND ADJOINING MOUJAS PWSS , SM/13636 | New | Material Requisition To Resource Division | 3456/MD | 25/11/2024 | 0 | Resource Division | 19.88 | 0 | 0 | 0
112 | PASCHIM MEDINIPUR | Midnapore Mechanical | ANTRI AND ADJOINING MOUJAS PWSS , SM/13636 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of ANTRI PWSS. REF CONSUMER ID-204212535, APPLICATION NO-2004593704, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2023-24-695 | 16/02/2024 | 0 | WBSEDCL | 8.6 | 0 | 0 | 0
113 | PASCHIM MEDINIPUR | Midnapore Mechanical | ANTRI AND ADJOINING MOUJAS PWSS , SM/13636 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ANTRI AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 578/W/MMD | 20/03/2023 | 834 | ALPHA ENTERPRISE | 25.24 | 0 | 0 | 20
114 | PASCHIM MEDINIPUR | Midnapore Division | BARGOPAL AND ADJOINING MOUJAS PWSS , SM/13004 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
115 | PASCHIM MEDINIPUR | Midnapore Division | BARGOPAL AND ADJOINING MOUJAS PWSS , SM/13004 | New | Material Requisition To Resource Division | 3451/MD | 25/11/2024 | 0 | Resource Division | 15.4 | 0 | 0 | 0
116 | PASCHIM MEDINIPUR | Central Drilling | BARGOPAL AND ADJOINING MOUJAS PWSS , SM/13004 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
117 | PASCHIM MEDINIPUR | Midnapore Division | BARGOPAL AND ADJOINING MOUJAS PWSS , SM/13004 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7,515 Nos.) including 2 years operation & maintenance For BARAGOPAL, DURIA, GAHIRA & RAIPUR Pipe Water Supply Scheme within NARAYANGARH Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 3048/MD | 23/08/2023 | 975 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 2197.07 | 0 | 0 | 33
118 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARGOPAL AND ADJOINING MOUJAS PWSS , SM/13004 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
119 | PASCHIM MEDINIPUR | Midnapore Division | BIKRAMPUR PWSS , SM/12203 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
120 | PASCHIM MEDINIPUR | Midnapore Division | BIKRAMPUR PWSS , SM/12203 | New | Material Requisition To Resource Division | 1144/MD | 25/04/2023 | 0 | Resource Division | 16.01 | 0 | 0 | 0
121 | PASCHIM MEDINIPUR | Midnapore Division | BIKRAMPUR PWSS , SM/12203 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (1430 Nos) including 1 years operation & maintenance For Bikrampur Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | 2820/MD | 07/08/2023 | 540 | GOBINDA MAITY | 416.11 | 0 | 0 | 55
122 | PASCHIM MEDINIPUR | Midnapore Mechanical | BIKRAMPUR PWSS , SM/12203 | New | Electrict quotation bill for TW-II of BIKRAMPUR pwss (Ref Consumar ID-204198610),Application No-2004571249,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. | BP-2023-24-605 | 07/02/2024 | 0 | WBSEDCL | 5.54 | 0 | 0 | 0
123 | PASCHIM MEDINIPUR | Midnapore Mechanical | BIKRAMPUR PWSS , SM/12203 | New | Electrict quotation bill for TW-I of Bikrampur pwss (Ref Consumar ID-204197919),Application No-2004569264,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. | BP-2023-24-611 | 07/02/2024 | 0 | WBSEDCL | 4.1 | 0 | 0 | 0
124 | PASCHIM MEDINIPUR | Midnapore Mechanical | BIKRAMPUR PWSS , SM/12203 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BIKRAMPUR PWSS Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | 2300/W/MMD | 29/12/2022 | 1037 | P.K.ENGINEERING | 22.8 | 0 | 0 | 50
125 | PASCHIM MEDINIPUR | Central Drilling | KANPUR AND ADJOINING MOUJAS PWSS , SM/13059 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 220 mtrs. Depth) by utilising Departmental machineries for Kanpur W/S Scheme (TW-I & II), Keshiary block under Paschim Midnapur District, CDD PHE Dte. | 1091/CDD | 18/08/2023 | 30 | M/S B.P.TRADING CORPORATION | 25.33 | 0 | 0 | 100
126 | PASCHIM MEDINIPUR | Midnapore Division | KANPUR AND ADJOINING MOUJAS PWSS , SM/13059 | New | Material Requisition To Resource Division | 1315/MD | 28/04/2023 | 0 | Resource Division | 27.89 | 0 | 0 | 0
127 | PASCHIM MEDINIPUR | Midnapore Mechanical | KANPUR AND ADJOINING MOUJAS PWSS , SM/13059 | New | Electric quotation bill for Tw No-II of Kanpur PWSS.(ref Consumer ID-204136082) | BP-2023-24-382 | 02/12/2023 | 0 | WBSEDCL | 3.01 | 0 | 0 | 0
128 | PASCHIM MEDINIPUR | Midnapore Mechanical | KANPUR AND ADJOINING MOUJAS PWSS , SM/13059 | New | Electric quotation bill for Tw no-I Of Kanpur PWSS.(Ref consumer ID-204136075) | BP-2023-24-380 | 02/12/2023 | 0 | WBSEDCL | 3.93 | 0 | 0 | 0
129 | PASCHIM MEDINIPUR | Midnapore Mechanical | KANPUR AND ADJOINING MOUJAS PWSS , SM/13059 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KANPUR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 56/W/MMD | 15/01/2024 | 441 | ORIENTAL ENGINEERING CO. | 22.86 | 0 | 0 | 20
130 | PASCHIM MEDINIPUR | Midnapore Division | BARABOLABANDI AND ADJOINING MOUJAS PWSS , SM/13066 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
131 | PASCHIM MEDINIPUR | Midnapore Division | BARABOLABANDI AND ADJOINING MOUJAS PWSS , SM/13066 | New | Material Requisition To Resource Division | 1234/MD | 27/04/2023 | 0 | Resource Division | 22.17 | 0 | 0 | 0
132 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BARABOLABANDI AND ADJOINING MOUJAS PWSS , SM/13066 | New | Payment for new service connection at Barabolbandi T/W-1 | 115/JMD | 13/05/2024 | 0 | WBSEDCL | 9.67 | 0 | 0 | 0
133 | PASCHIM MEDINIPUR | Central Drilling | BARABOLABANDI AND ADJOINING MOUJAS PWSS , SM/13066 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
134 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12827 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Shanrpur PWSS within Debra Block under Midnapore Division, P.H.E. Dte. | 518/MD | 17/03/2022 | 10 | SIRCON ENGINEERING SERVICES | 2.62 | 0 | 0 | 100
135 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12827 | Augmentation | Restoration of pipe line damaged due to construction of roads & Construction of Sluice Valve Chamber within Shanrpur & its adjoining mouzas (Gayeshpur, Kolkuria, Bhuiabasan, Bar Bhuiabasan, Bhainagar etc.) W/S Scheme at Debra Block under Kharagpur Sub Division within Midnapore Division, P.H.E. Dte. | 2172/MD | 17/12/2021 | 45 | UCON | 42.21 | 0 | 0 | 0
136 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12827 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 480/W/MMD | 20/03/2023 | 180 | PURUSHOTTAM ENTERPRISE | 10.98 | 0 | 0 | 0
137 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12827 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 200 Cum OHR (Intze type with Raft foundation) & under JJM with allied work for Augmentation of Shanrpur PWSS in Debra block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 3398/MD | 25/11/2024 | 180 | KISHORE GHOSH | 194.76 | 0 | 0 | 0
138 | PASCHIM MEDINIPUR | Midnapore Division | SONIAKON AND ADJOINING MOUJAS PWSS , SM/13221 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
139 | PASCHIM MEDINIPUR | Midnapore Division | SONIAKON AND ADJOINING MOUJAS PWSS , SM/13221 | New | Material Requisition To Resource Division | 1245/MD | 27/04/2023 | 0 | Resource Division | 51.32 | 0 | 0 | 0
140 | PASCHIM MEDINIPUR | Central Drilling | SONIAKON AND ADJOINING MOUJAS PWSS , SM/13221 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
141 | PASCHIM MEDINIPUR | Midnapore Division | AMSOL AND ADJOINING MOUJAS PWSS , SM/13179 | New | Material Requisition To Resource Division | 1204/MD | 26/04/2023 | 0 | Resource Division | 22.73 | 0 | 0 | 0
142 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | AMSOL AND ADJOINING MOUJAS PWSS , SM/13179 | New | Quotation for new service connection at Amsol T/W -I water supply scheme. | 45/JMD | 29/04/2024 | 0 | WBSEDCL | 4.13 | 0 | 0 | 0
143 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | AMSOL AND ADJOINING MOUJAS PWSS , SM/13179 | New | Quotation for new service connection at AMSOL T/W-II water supply scheme. | 113/JMD | 13/05/2024 | 0 | WBSEDCL | 6.12 | 0 | 0 | 0
144 | PASCHIM MEDINIPUR | Central Drilling | AMSOL AND ADJOINING MOUJAS PWSS , SM/13179 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
145 | PASCHIM MEDINIPUR | Midnapore Division | LOYADA AND ITS ADJOINING MOUJAS PWSS , SM/12992 | New | Material Requisition To Resource Division | 1515/MD | 12/05/2023 | 0 | Resource Division | 23.72 | 0 | 0 | 0
146 | PASCHIM MEDINIPUR | Midnapore Mechanical | LOYADA AND ITS ADJOINING MOUJAS PWSS , SM/12992 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for LOYADA AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 825/W/MMD | 24/03/2023 | 180 | P.K.ENGINEERING | 22.65 | 0 | 0 | 50
147 | PASCHIM MEDINIPUR | Midnapore Mechanical | LOYADA AND ITS ADJOINING MOUJAS PWSS , SM/12992 | New | Electrict quotation bill for TW-II of Lowada pwss (Ref Consumar ID-204197979),Application No-2004569198,Application Type-New Connection,Name of ccc- Lowada ccc, block-Debra. | BP-2023-24-661 | 12/02/2024 | 0 | WBSEDCL | 3.25 | 0 | 0 | 0
148 | PASCHIM MEDINIPUR | Midnapore Mechanical | LOYADA AND ITS ADJOINING MOUJAS PWSS , SM/12992 | New | Electrict quotation bill for TW-I of Lowada pwss (Ref Consumar ID-204395093),Application No-2004893015,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra | C112417246901 | 12/11/2024 | 0 | WBSEDCL | 4.82 | 0 | 0 | 0
149 | PASCHIM MEDINIPUR | Midnapore Division | LOYADA AND ITS ADJOINING MOUJAS PWSS , SM/12992 | New | Construction of 150 Cum, 200 Cum & 250 Cum Capacity R.C.C Over Head Reservoir Over (Intze type with solid raft) works with Laying of Rising Main, Distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (5061 Nos.) including 2 years Operation & Maintenance for Loyada, Madhabpur, Patna and Radhamohanpur-II Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2824/MD | 07/08/2023 | 723 | MADE AND TRADE CO. | 1346.28 | 0 | 0 | 75
150 | PASCHIM MEDINIPUR | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS , SM/14031 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
151 | PASCHIM MEDINIPUR | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS , SM/14031 | New | Material Requisition To Resource Division | 2040/MD | 18/05/2023 | 0 | Resource Division | 26.77 | 0 | 0 | 0
152 | PASCHIM MEDINIPUR | Midnapore Mechanical | BULANPUR AND ADJOINING MOUJAS PWSS , SM/14031 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BULANPUR AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. (Part-II) | 871/W/MMD | 27/03/2023 | 180 | KUSHANI ENTERPRISE | 5.98 | 0 | 0 | 0
153 | PASCHIM MEDINIPUR | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS , SM/14031 | New | Laying distribution pipe line & Accommodate FHTC (200 Nos.) under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | 5189/MD | 08/11/2023 | 45 | A.K. SIKDAR | 47.78 | 0 | 0 | 70
154 | PASCHIM MEDINIPUR | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS , SM/14031 | New | Laying of Rising main, Laying distribution pipe line, Pump House, Boundary wall & Accommodate FHTC (400 Nos.) including 2 years operation & maintenance under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 5154/MD | 07/11/2023 | 60 | SAIKAT DANDAPAT | 111.63 | 0 | 0 | 3
155 | PASCHIM MEDINIPUR | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS , SM/14031 | New | Sinking of 2 (Two) Nos. Tube well for Bulanpur & its adjoining mouzas (Zone-I) PWSS in Garhbeta-II block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | 2622/MD | 24/07/2023 | 30 | M/S BISWANATH CONSTRUCTION | 17.57 | 0 | 0 | 100
156 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BULANPUR AND ADJOINING MOUJAS PWSS , SM/14031 | New | New service connection | 72/JMD | 12/02/2024 | 0 | WBSEDCL | 4.72 | 0 | 0 | 0
157 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BULANPUR AND ADJOINING MOUJAS PWSS , SM/14031 | New | New service connection | 73/JMD | 12/02/2024 | 0 | WBSEDCL | 3.14 | 0 | 0 | 0
158 | PASCHIM MEDINIPUR | Central Drilling | BULANPUR AND ADJOINING MOUJAS PWSS , SM/14031 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
159 | PASCHIM MEDINIPUR | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS , SM/14031 | New | Laying distribution pipe line & Accommodate FHTC (202 Nos.) under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | 2676/MD | 26/07/2023 | 721 | NIMAI HAZRA | 33.52 | 0 | 0 | 70
160 | PASCHIM MEDINIPUR | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS , SM/14031 | New | Sinking of Tube well, Laying distribution pipe line, Boundary wall, Pump House alongwith 20 CuM OHR (Zone-2) under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme with Standalone in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 2677/MD | 26/07/2023 | 840 | ANNAPURNA TUBEWELL WORKS | 36.74 | 0 | 0 | 15
161 | PASCHIM MEDINIPUR | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS , SM/14031 | New | Construction of 150 CuM OHR (Torch type with Solid raft) (Zone-1) & Accommodate FHTC (300 Nos.) under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 731/MD | 18/03/2025 | 180 | DEVJYOTI BERA | 88.31 | 0 | 0 | 0
162 | PASCHIM MEDINIPUR | Midnapore Division | DUKI AND ADJOINING MOUJAS PWSS , SM/14645 | New | Material Requisition To Resource Division | 1195/MD | 26/04/2023 | 0 | Resource Division | 30.12 | 0 | 0 | 0
163 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | DUKI AND ADJOINING MOUJAS PWSS , SM/14645 | New | New service connection for Dukhi T/W - 1 water supply scheme | 44/JMD | 11/03/2024 | 0 | WBSEDCL | 5.24 | 0 | 0 | 0
164 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | DUKI AND ADJOINING MOUJAS PWSS , SM/14645 | New | New service connection for Dukhi T/W-2 water supply scheme | 45/JMD | 11/03/2024 | 0 | WBSEDCL | 4.77 | 0 | 0 | 0
165 | PASCHIM MEDINIPUR | Central Drilling | DUKI AND ADJOINING MOUJAS PWSS , SM/14645 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
166 | PASCHIM MEDINIPUR | Midnapore Division | DUKI AND ADJOINING MOUJAS PWSS , SM/14645 | New | Route survey & way leave permission along & across of National Highway in Duki PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | 376/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 10.8 | 0 | 0 | 0
167 | PASCHIM MEDINIPUR | Midnapore Division | GHRITAGRAM AND ADJOINING MOUJAS PWSS , SM/14648 | New | Material Requisition To Resource Division | 1325/MD | 28/04/2023 | 0 | Resource Division | 18.04 | 0 | 0 | 0
168 | PASCHIM MEDINIPUR | Midnapore Mechanical | GHRITAGRAM AND ADJOINING MOUJAS PWSS , SM/14648 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at GRITHAGRAM Water supply scheme, Keshiary block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 1065/W/MMD | 14/03/2024 | 360 | M/S EMMESS | 12.39 | 0 | 0 | 30
169 | PASCHIM MEDINIPUR | Central Drilling | GHRITAGRAM AND ADJOINING MOUJAS PWSS , SM/14648 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Ghritagram W/S Scheme (TW-I & II), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | 1437/CDD | 26/09/2023 | 30 | M/S B.P.TRADING CORPORATION | 25.32 | 0 | 0 | 100
170 | PASCHIM MEDINIPUR | Midnapore Division | GHRITAGRAM AND ADJOINING MOUJAS PWSS , SM/14648 | New | Material Requisition To Resource Division | 3423/MD | 25/11/2024 | 0 | Resource Division | 14.32 | 0 | 0 | 0
171 | PASCHIM MEDINIPUR | Midnapore Mechanical | GHRITAGRAM AND ADJOINING MOUJAS PWSS , SM/14648 | New | Electric quotation bill for Tw No-I of Ghritagram PWSS. Ref Consumer ID-204175253) | BP-2023-24-552 | 17/01/2024 | 0 | WBSEDCL | 3.53 | 0 | 0 | 0
172 | PASCHIM MEDINIPUR | Midnapore Mechanical | GHRITAGRAM AND ADJOINING MOUJAS PWSS , SM/14648 | New | Electric quotation bill for Tw No-II of Ghritagram PWSS .(Ref Consumer ID-204175255) | BP-2023-24-553 | 16/01/2024 | 0 | WBSEDCL | 3.05 | 0 | 0 | 0
173 | PASCHIM MEDINIPUR | Midnapore Mechanical | GHRITAGRAM AND ADJOINING MOUJAS PWSS , SM/14648 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GHRITAGRAM AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 3087/W/MMD | 29/11/2023 | 540 | PADMA ENGINEERING CO. | 10.99 | 0 | 0 | 25
174 | PASCHIM MEDINIPUR | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS , SM/14989 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
175 | PASCHIM MEDINIPUR | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS , SM/14989 | New | Material Requisition To Resource Division | 2039/MD | 18/05/2023 | 0 | Resource Division | 27.2 | 0 | 0 | 0
176 | PASCHIM MEDINIPUR | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS , SM/14989 | New | Accommodate FHTC (218 Nos.) & Construction of Boundary wall under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | 2628/MD | 24/07/2023 | 45 | M/S. BLUE BIRD | 31.54 | 0 | 0 | 25
177 | PASCHIM MEDINIPUR | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS , SM/14989 | New | Laying distribution pipe line & Accommodate FHTC (400 Nos.) under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | 2675/MD | 26/07/2023 | 45 | EVEREST CONSULTANT SERVICES | 66.12 | 0 | 0 | 80
178 | PASCHIM MEDINIPUR | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS , SM/14989 | New | Sinking of Tube well, Laying distribution pipe line, Boundary wall, Pump House alongwith 20 CuM OHR (Zone-2) under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme with Standalone in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 2636/MD | 24/07/2023 | 60 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 38.73 | 0 | 0 | 15
179 | PASCHIM MEDINIPUR | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS , SM/14989 | New | Sinking of 2 (Two) Nos. Tube well for Amlasuli & its adjoining mouzas (Zone-I) PWSS in Garhbeta-II block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | 2517/MD | 18/07/2023 | 30 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.57 | 0 | 0 | 30
180 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | AMLASULI AND ADJOINING MOUJAS PWSS , SM/14989 | New | New service connection | 71/JMD | 12/02/2024 | 0 | WBSEDCL | 3.5 | 0 | 0 | 0
181 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | AMLASULI AND ADJOINING MOUJAS PWSS , SM/14989 | New | New service connection | 70/JMD | 12/02/2024 | 0 | WBSEDCL | 4.59 | 0 | 0 | 0
182 | PASCHIM MEDINIPUR | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS , SM/14989 | New | Improvement of approach road of Bhansra PWSS Head Work Site under Kashiery Block within Midnapore Division P.H.E. Dte. | 10101/MD | 20/11/2024 | 30 | K & KABERI ENTERPRISE (PROP. GOUTAM MAITY) | 0 | 0 | 0 | 0
183 | PASCHIM MEDINIPUR | Central Drilling | AMLASULI AND ADJOINING MOUJAS PWSS , SM/14989 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
184 | PASCHIM MEDINIPUR | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS , SM/14989 | New | Construction of 250 CuM OHR (Intze type with Solid raft) (Zone-1) & Accommodate FHTC (500 Nos.) under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 199/MD | 17/01/2025 | 360 | DIPAK KUMAR BAKLY | 111.02 | 0 | 0 | 0
185 | PASCHIM MEDINIPUR | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS , SM/14989 | New | Laying of Rising main, Laying distribution pipe line, Pump House, Boundary wall & Accommodate FHTC (500 Nos.) including 2 years operation & maintenance under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 200/MD | 17/01/2025 | 360 | DIPAK KUMAR BAKLY | 117.81 | 0 | 0 | 0
186 | PASCHIM MEDINIPUR | Midnapore Division | KASHBA AND ITS ADJOINING MOUZAS PWSS , SM/14653 | New | Material Requisition To Resource Division | 195/MD | 16/01/2023 | 0 | Resource Division | 15.49 | 0 | 0 | 0
187 | PASCHIM MEDINIPUR | Midnapore Mechanical | KASHBA AND ITS ADJOINING MOUZAS PWSS , SM/14653 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KASHBA AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | 1378/W/MMD | 30/05/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 11.98 | 0 | 0 | 15
188 | PASCHIM MEDINIPUR | Midnapore Division | KASHBA AND ITS ADJOINING MOUZAS PWSS , SM/14653 | New | Material Requisition To Resource Division | 3424/MD | 25/11/2024 | 0 | Resource Division | 2.83 | 0 | 0 | 0
189 | PASCHIM MEDINIPUR | Midnapore Mechanical | KASHBA AND ITS ADJOINING MOUZAS PWSS , SM/14653 | New | Quotation for new power connection at kasba water supply scheme T/W - I | BP-2023-24-640 | 08/02/2024 | 0 | WBSEDCL | 0.51 | 0 | 0 | 0
190 | PASCHIM MEDINIPUR | Midnapore Mechanical | KASHBA AND ITS ADJOINING MOUZAS PWSS , SM/14653 | New | Quotation for new power connection at Kasba water supply scheme T/W - I | BP-2023-24-641 | 08/02/2024 | 0 | WBSEDCL | 4.6 | 0 | 0 | 0
191 | PASCHIM MEDINIPUR | Midnapore Division | KASHBA AND ITS ADJOINING MOUZAS PWSS , SM/14653 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 100 Cum OHR (Intze type with Raft foundation) & Accommodate FHTC (459 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Kashba & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 2147/MD | 08/06/2023 | 992 | A.J. ENTERPRISE | 205.4 | 0 | 0 | 65
192 | PASCHIM MEDINIPUR | Midnapore Division | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14656 | New | Preparation & Submission of 2 (Two) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Kuran & its adjoining Mouzas PWSS AND (2) Kushman & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | 1766/MD | 24/08/2022 | 30 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.92 | 0 | 0 | 0
193 | PASCHIM MEDINIPUR | Midnapore Division | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14656 | New | Material Requisition To Resource Division | 64/MD | 09/01/2023 | 0 | Resource Division | 17.03 | 0 | 0 | 0
194 | PASCHIM MEDINIPUR | Midnapore Division | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14656 | New | Material Requisition To Resource Division | 3362/MD | 25/11/2024 | 0 | Resource Division | 10.15 | 0 | 0 | 0
195 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14656 | New | QUOTATION MONEY FOR KUSHMAN WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/14656, APPLICATION NO 2004816276, REFERENCE ID 204354169, BIRSHINGHA CCC, WBSEDCL | C072445025889 | 30/07/2024 | 0 | WBSEDCL | 5.09 | 0 | 0 | 0
196 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14656 | New | QUOTATION MONEY FOR KUSHMAN WATER SUPPLY SCHEME, T W NO 2 JJM WORKS, SCHEME CODE SM/14656, APPLICATION NO 2004816294, REFERENCE ID 204354171, BIRSHINGHA CCC, WBSEDCL | C072445022964 | 30/07/2024 | 0 | WBSEDCL | 3.85 | 0 | 0 | 0
197 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14656 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 540/W/MMD | 20/03/2023 | 939 | M/S. S.R. ENTERPRISE | 22.75 | 0 | 0 | 40
198 | PASCHIM MEDINIPUR | Midnapore Division | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14656 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,647 nos.) under JJM with allied work for Kushman PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 1338/MD | 28/04/2023 | 884 | M/S. D.K.H.CONSTRUCTION | 444.51 | 0 | 0 | 8
199 | PASCHIM MEDINIPUR | Midnapore Division | BARAKADRA AND ADJOINING MOUJAS PWSS , SM/14991 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
200 | PASCHIM MEDINIPUR | Midnapore Division | BARAKADRA AND ADJOINING MOUJAS PWSS , SM/14991 | New | Material Requisition To Resource Division | 1232/MD | 27/04/2023 | 0 | Resource Division | 33.16 | 0 | 0 | 0
201 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BARAKADRA AND ADJOINING MOUJAS PWSS , SM/14991 | New | Payment for new service connection charges Barakadra T/W-2 | 61/JMD | 29/04/2024 | 0 | WBSEDCL | 4.04 | 0 | 0 | 0
202 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BARAKADRA AND ADJOINING MOUJAS PWSS , SM/14991 | New | Payment for WBSEDCL new connection at BARAKADRA 1 (SM/14991. BARAKADRA AND ADJOINING MOUJAS PWSS ) | 171/JMD | 07/06/2024 | 0 | WBSEDCL | 11.23 | 0 | 0 | 0
203 | PASCHIM MEDINIPUR | Central Drilling | BARAKADRA AND ADJOINING MOUJAS PWSS , SM/14991 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
204 | PASCHIM MEDINIPUR | Midnapore Mechanical | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14998 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 803/W/MMD | 24/03/2023 | 180 | SHREE BISHNU CONSTRUCTION | 10.79 | 0 | 0 | 0
205 | PASCHIM MEDINIPUR | Midnapore Division | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14998 | New | Laying distribution pipe line under JJM with allied work for Chaulisingpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-D] | 2428/MD | 13/07/2023 | 45 | MALLICK ENTERPRISE | 9.89 | 0 | 0 | 0
206 | PASCHIM MEDINIPUR | Midnapore Division | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14998 | New | Preparation & Submission of 6 (Six) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Shrirampur & its adjoining Mouzas PWSS, (2) Dontiara & its adjoining Mouzas PWSS, (3) Dhashachandpur Mouza Stand Alone PWSS, (4) Udayganj (P) Mouza Stand Alone PWSS, (5) Prasadchak Mouza Stand Alone PWSS AND (6) Anandapur Mouza Stand Alone PWSS, Block - Ghatal under Midnapore Division, PHE Dte. [Name of Proposed PWSS Chaulisingpur & its adjoining Mouzas PWSS & Hemantapur & its adjoining Mouzas PWSS instead of (1) Dhashachandpur Mouza Stand Alone PWSS, (2) Udayganj (P) Mouza Stand Alone PWSS, (3) Prasadchak Mouza Stand Alone PWSS AND (4) Anandapur Mouza Stand Alone PWSS] | 1767/MD | 24/08/2022 | 45 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.73 | 0 | 0 | 100
207 | PASCHIM MEDINIPUR | Midnapore Division | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14998 | New | Sinking of 250 X 150 mm dia. X 165 depth Tube well under JJM with allied work for Chaulisingpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-E] | 935/MD | 04/04/2023 | 14 | MEHER ALI KHAN. | 8.3 | 0 | 0 | 100
208 | PASCHIM MEDINIPUR | Midnapore Division | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14998 | New | Material Requisition To Resource Division | 3358/MD | 25/11/2024 | 0 | Resource Division | 2.94 | 0 | 0 | 0
209 | PASCHIM MEDINIPUR | Midnapore Mechanical | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14998 | New | QUOTATION MONEY FOR CHAULISINGPUR WATER SUPPLY SCHEME, T W NO I, [ BAHIRSINGPUR ] JJM WORKS, SCHEME CODE SM/14998, APPLICATION NO 2004995144, REFERENCE ID 204465793, GHATAL CCC, WBSEDCL |  | 18/12/2024 | 0 | WBSEDCL | 5.23 | 0 | 0 | 0
210 | PASCHIM MEDINIPUR | Midnapore Division | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14998 | New | Laying distribution pipe line, Rising main & 2 years operation & maintenance under JJM with allied work for Chaulisingpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 2427/MD | 13/07/2023 | 952 | DEVJYOTI BERA | 29.63 | 0 | 0 | 47
211 | PASCHIM MEDINIPUR | Midnapore Division | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14998 | New | Laying distribution pipe line under JJM with allied work for Chaulisingpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 934/MD | 04/04/2023 | 758 | NIMAI HAZRA | 35.97 | 0 | 0 | 100
212 | PASCHIM MEDINIPUR | Midnapore Division | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14999 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Dwandbipur & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | 1755/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.94 | 0 | 0 | 100
213 | PASCHIM MEDINIPUR | Midnapore Division | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14999 | New | Material Requisition To Resource Division | 62/MD | 09/01/2023 | 0 | Resource Division | 19.15 | 0 | 0 | 0
214 | PASCHIM MEDINIPUR | Midnapore Division | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14999 | New | Material Requisition To Resource Division | 3359/MD | 25/11/2024 | 0 | Resource Division | 13.71 | 0 | 0 | 0
215 | PASCHIM MEDINIPUR | Midnapore Mechanical | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14999 | New | DANDIPUR WATER SUPPLY SCHEME, PH - I, BLOCK - GHATAL , SCHEME - SM/14999, REF. ID - 2004496533, GHATAL CCC, | BP-2023-24-393 | 02/12/2023 | 0 | WBSEDCL | 3.86 | 0 | 0 | 0
216 | PASCHIM MEDINIPUR | Midnapore Mechanical | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14999 | New | DANDIPUR WATER SUPPLY SCHEME, PH - II, BLOCK - GHATAL , SCHEME - SM/14999, REF. ID - 2004496518, GHATAL CCC | BP-2023-24-394 | 02/12/2023 | 0 | WBSEDCL | 7.2 | 0 | 0 | 0
217 | PASCHIM MEDINIPUR | Midnapore Division | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14999 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,225 nos.) under JJM with allied work for Dwandbipur PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 1337/MD | 28/04/2023 | 884 | M/S. D.K.H.CONSTRUCTION | 460.32 | 0 | 0 | 35
218 | PASCHIM MEDINIPUR | Midnapore Mechanical | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14999 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 1684/MMSD-I | 19/12/2023 | 60 | SUBHASIS ROY | 0.29 | 0 | 0 | 40
219 | PASCHIM MEDINIPUR | Midnapore Mechanical | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14999 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
220 | PASCHIM MEDINIPUR | Midnapore Mechanical | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14999 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 494/W/MMD | 20/03/2023 | 959 | J K ENGINEERING CO | 22.96 | 0 | 0 | 100
221 | PASCHIM MEDINIPUR | Midnapore Division | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14999 | New | Laying additional distribution system pipe line for Dwandbipur W/S Scheme under JJM within Ghatal Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2848/MD | 09/09/2024 | 181 | M/S. D.K.H.CONSTRUCTION | 27.43 | 0 | 0 | 100
222 | PASCHIM MEDINIPUR | Midnapore Division | PALASIA AND ADJOINING MOUJAS PWSS , SM/13168 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
223 | PASCHIM MEDINIPUR | Midnapore Division | PALASIA AND ADJOINING MOUJAS PWSS , SM/13168 | New | Material Requisition To Resource Division | 196/MD | 16/01/2023 | 0 | Resource Division | 7.32 | 0 | 0 | 0
224 | PASCHIM MEDINIPUR | Midnapore Division | PALASIA AND ADJOINING MOUJAS PWSS , SM/13168 | New | Material Requisition To Resource Division | 3461/MD | 25/11/2024 | 0 | Resource Division | 10.39 | 0 | 0 | 0
225 | PASCHIM MEDINIPUR | Midnapore Mechanical | PALASIA AND ADJOINING MOUJAS PWSS , SM/13168 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of PALASIA PWSS. REF CONSUMER ID-204302056, APPLICATION NO-2004723600, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-227 | 31/05/2024 | 0 | WBSEDCL | 2.89 | 0 | 0 | 0
226 | PASCHIM MEDINIPUR | Midnapore Mechanical | PALASIA AND ADJOINING MOUJAS PWSS , SM/13168 | New | Electric quotation bill for Tw No-I of PALASIA PWSS. (Ref Consumer ID-204205809), APPLICATION NO-2004580481, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, BLOCK-DANTAN-I | BP-2023-24-606 | 07/02/2024 | 0 | WBSEDCL | 0.64 | 0 | 0 | 0
227 | PASCHIM MEDINIPUR | Midnapore Mechanical | PALASIA AND ADJOINING MOUJAS PWSS , SM/13168 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PALASIA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 2394/W/MMD | 31/12/2022 | 975 | DAS ENTERPRISE | 22.83 | 0 | 0 | 30
228 | PASCHIM MEDINIPUR | Midnapore Mechanical | SAORAPIR AND ADJOINING MOUJAS PWSS , SM/13172 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SAORAPIR AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 802/W/MMD | 24/03/2023 | 180 | RSA ENTERPRISE | 21.59 | 0 | 0 | 0
229 | PASCHIM MEDINIPUR | Midnapore Division | SAORAPIR AND ADJOINING MOUJAS PWSS , SM/13172 | New | Material Requisition To Resource Division | 1278/MD | 28/04/2023 | 0 | Resource Division | 21.02 | 0 | 0 | 0
230 | PASCHIM MEDINIPUR | Midnapore Mechanical | SAORAPIR AND ADJOINING MOUJAS PWSS , SM/13172 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF SAORAPIR PWSS. REF CONSUMER ID-204424028, APPLICATION NO-2004937486, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | C102455575467 | 30/10/2024 | 0 | WBSEDCL | 4.52 | 0 | 0 | 0
231 | PASCHIM MEDINIPUR | Midnapore Division | AMDA AND ADJOINING MOUJAS PWSS , SM/13177 | New | Material Requisition To Resource Division | 1306/MD | 28/04/2023 | 0 | Resource Division | 27.48 | 0 | 0 | 0
232 | PASCHIM MEDINIPUR | Midnapore Mechanical | AMDA AND ADJOINING MOUJAS PWSS , SM/13177 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF AMDA PWSS. REF CONSUMER ID-204283803, APPLICATION NO-2004695702, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2024-25-270 | 12/06/2024 | 0 | WBSEDCL | 4.88 | 0 | 0 | 0
233 | PASCHIM MEDINIPUR | Midnapore Division | AMDA AND ADJOINING MOUJAS PWSS , SM/13177 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF AMDA PWSS. REF CONSUMER ID-204283798, APPLICATION NO-2004695716, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2024-25-458 | 12/11/2024 | 0 | WBSEDCL | 13.84 | 0 | 0 | 0
234 | PASCHIM MEDINIPUR | Central Drilling | AMDA AND ADJOINING MOUJAS PWSS , SM/13177 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
235 | PASCHIM MEDINIPUR | Midnapore Division | KADRA AND ADJOINING MOUJAS PWSS , SM/13144 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
236 | PASCHIM MEDINIPUR | Midnapore Division | KADRA AND ADJOINING MOUJAS PWSS , SM/13144 | New | Material Requisition To Resource Division | 1188/MD | 26/04/2023 | 0 | Resource Division | 27.58 | 0 | 0 | 0
237 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KADRA AND ADJOINING MOUJAS PWSS , SM/13144 | New | NEW SERVICE CONNECTION CHARGES AT KADRA TW-II WATER SUPPLY SCHEME | 249/JMD | 10/07/2024 | 0 | WBSEDCL | 6.94 | 0 | 0 | 0
238 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KADRA AND ADJOINING MOUJAS PWSS , SM/13144 | New | New Service connection charges. | 59/JMD | 13/03/2024 | 0 | WBSEDCL | 6.27 | 0 | 0 | 0
239 | PASCHIM MEDINIPUR | Central Drilling | KADRA AND ADJOINING MOUJAS PWSS , SM/13144 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
240 | PASCHIM MEDINIPUR | Midnapore Division | MANSINGHA AND IT'S ADJOINING MOUJAS PWSS , SM/14002 | New | Material Requisition To Resource Division | 1193/MD | 26/04/2023 | 0 | Resource Division | 5 | 0 | 0 | 0
241 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MANSINGHA AND IT'S ADJOINING MOUJAS PWSS , SM/14002 | New | New service connection charge at Krishnasole ( Mansingha-I) water supply scheme |  | 03/09/2024 | 0 | WBSEDCL | 5.4 | 0 | 0 | 0
242 | PASCHIM MEDINIPUR | Central Drilling | MANSINGHA AND IT'S ADJOINING MOUJAS PWSS , SM/14002 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
243 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khanjapur Piped Water Supply Scheme. , SM/06902 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khanjapur W/S Scheme, Block: - Daspur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1446/MD | 26/11/2020 | 180 | MIDNAPUR PIPE CONCERN | 48.96 | 0 | 0 | 0
244 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khanjapur Piped Water Supply Scheme. , SM/06902 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khanjapur W/S Scheme District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | MIDNAPUR PIPE CONCERN | 10 | 0 | 0 | 0
245 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khanjapur Piped Water Supply Scheme. , SM/06902 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khanjapur W/S Scheme, Block: - Daspur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 8443244 | 29/03/2022 | 0 | MIDNAPUR PIPE CONCERN | 10 | 0 | 0 | 0
246 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khanjapur Piped Water Supply Scheme. , SM/06902 | Retrofitting | Continuation Work Order for the work of Retrofitting to accommodate additional FHTC under JJM in Khanjapur W/S Scheme, Block: - Daspur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 2534/MD | 12/12/2022 | 14 | MIDNAPUR PIPE CONCERN | 7 | 0 | 0 | 50
247 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/13823 | Augmentation | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Tap Connection of existing PWSS (Birsingha, Block - Ghatal) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | 1011/MD | 25/06/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 3.25 | 0 | 0 | 0
248 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/13823 | Augmentation | Special Exigent Repair of Head work site & its adjoining structures of Birsingha W/S Scheme in consultation with district administration in the model village of Birsingha (Birth place of Iswarchandra Vidyasagar) under Ghatal Sub-Division of Midnapore Division, PHE Dte. [PHASE-II] | 722/MD | 09/03/2023 | 21 | PULLOCK KUMAR GHOSH | 14.3 | 0 | 0 | 100
249 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/13823 | Augmentation | Special Exigent Repair of Head work site & its adjoining structures of Birsingha W/S Scheme in consultation with district administration in the model village of Birsingha (Birth place of Iswarchandra Vidyasagar) under Ghatal Sub-Division of Midnapore Division, PHE Dte. | 2605/MD | 20/12/2022 | 15 | HIRAK KUMAR GHOSH | 9.99 | 0 | 0 | 94
250 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/13823 | Augmentation | Material Requisition To Resource Division | 1421/MD | 04/05/2023 | 0 | Resource Division | 18.02 | 0 | 0 | 0
251 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/13823 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 475/W/MMD | 20/03/2023 | 180 | S.B.ENTERPRISE | 10.98 | 0 | 0 | 100
252 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/13823 | Augmentation | Material Requisition To Resource Division | 3366/MD | 25/11/2024 | 0 | Resource Division | 0.83 | 0 | 0 | 0
253 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/13823 | Augmentation | Laying additional pipe line, interconnection, FHTC & other allied works for continuation of laying distribution system, sinking of tube well, FHTC for Augmentation of Birsingha W/S Scheme within Ghatal block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | 138/MD | 18/01/2024 | 401 | DIPAK KUMAR BAKLY | 29.75 | 0 | 0 | 90
254 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/13823 | Augmentation | Laying distribution pipeline, providing FHTC including Sinking of 250mm X 150mm X 190 m deep tube well for Augmentation of Birsingha Water Supply Scheme within Ghatal block under Ghatal Sub-Division of Midnapore Division, PHE Dte. | 2412/MD | 25/11/2022 | 745 | DIPAK KUMAR BAKLY | 91 | 0 | 0 | 90
255 | PASCHIM MEDINIPUR | Midnapore Division | NAMJABA AND ADJOINING MOUJAS PWSS , SM/14723 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
256 | PASCHIM MEDINIPUR | Midnapore Division | NAMJABA AND ADJOINING MOUJAS PWSS , SM/14723 | New | Material Requisition To Resource Division | 1187/MD | 26/04/2023 | 0 | Resource Division | 81.82 | 0 | 0 | 0
257 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | NAMJABA AND ADJOINING MOUJAS PWSS , SM/14723 | New | New Service connection charges. | 61/JMD | 13/03/2024 | 0 | WBSEDCL | 3.3 | 0 | 0 | 0
258 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | NAMJABA AND ADJOINING MOUJAS PWSS , SM/14723 | New | New Service connection charges. | 60/JMD | 13/03/2024 | 0 | WBSEDCL | 3.48 | 0 | 0 | 0
259 | PASCHIM MEDINIPUR | Central Drilling | NAMJABA AND ADJOINING MOUJAS PWSS , SM/14723 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
260 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAITA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15574 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-I under Baita water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist.:- Paschim Medinipur. | 1864/W/MMD | 22/09/2022 | 30 | DEY ENTERPRISE | 11.17 | 0 | 0 | 0
261 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAITA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15574 | Augmentation | Continuation Work Order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Baita, Block - Mohanpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | 565/MD | 16/03/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.16 | 0 | 0 | 100
262 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAITA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15574 | Augmentation | Material Requisition To Resource Division | 538/MD | 21/02/2023 | 0 | Resource Division | 28.21 | 0 | 0 | 0
263 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAITA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15574 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAITA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 912/W/MMD | 27/03/2023 | 180 | M/S EMMESS | 11.88 | 0 | 0 | 40
264 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAITA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15574 | Augmentation | Laying of additional distribution pipe line, Rising main including interconnection of Tube well No. 2 and Construction of Sluice Valve Chamber including Supply of CIDF Sluice Valve for Augmentation of Baita PWSS within Mohanpur block under Midnapore Division, PHE Dte. | 375/MD | 12/02/2024 | 45 | A-PLUS | 22.32 | 0 | 0 | 0
265 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAITA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15574 | Augmentation | Sinking of Tube wells Laying distribution pipe line, Pump House, Soil investigation, Construction of 300 cum OHR (Pile Foundation) & Accommodate FHTC (164 Nos.) under JJM with allied work for Augmentation of Baita PWSS in Mohanpur block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 3158/MD | 04/10/2024 | 180 | SUBRATA DAS | 231.09 | 0 | 0 | 0
266 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAITA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15574 | Augmentation | Repair & renovation of switch room cum chlorine room at 1st Tube well site of Baita Pipe Water Supply Scheme at Mohanpur block under Midnapore Division, PHE Dte. | 437/AE/HQ/MD | 07/02/2025 | 30 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 1.07 | 0 | 0 | 100
267 | PASCHIM MEDINIPUR | Midnapore Division | MARKHA AND ITS ADJOINING MOUZAS PWSS , SM/15593 | New | Material Requisition To Resource Division | 1165/MD | 26/04/2023 | 0 | Resource Division | 107.5 | 0 | 0 | 0
268 | PASCHIM MEDINIPUR | Midnapore Mechanical | MARKHA AND ITS ADJOINING MOUZAS PWSS , SM/15593 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF MARKHA PWSS. REF CONSUMER ID-204383573, APPLICATION NO-2004868760, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR. | C082449441995 | 02/09/2024 | 0 | WBSEDCL | 6.9 | 0 | 0 | 0
269 | PASCHIM MEDINIPUR | Midnapore Mechanical | MARKHA AND ITS ADJOINING MOUZAS PWSS , SM/15593 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of MARKHA PWSS. REF CONSUMER ID-204291858, APPLICATION NO-2004701565, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-145 | 09/05/2024 | 0 | WBSEDCL | 3.18 | 0 | 0 | 0
270 | PASCHIM MEDINIPUR | Midnapore Mechanical | MARKHA AND ITS ADJOINING MOUZAS PWSS , SM/15593 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MARKHA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 909/W/MMD | 27/03/2023 | 919 | ORIENTAL ENGINEERING CO. | 27.37 | 0 | 0 | 30
271 | PASCHIM MEDINIPUR | Midnapore Division | MARKHA AND ITS ADJOINING MOUZAS PWSS , SM/15593 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,033 nos.) under JJM with allied work including 02 (Two) years Operation & Maintenance for Markha PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 2923/MD | 16/08/2023 | 927 | DULAL CHANDRA DAS | 812.19 | 0 | 0 | 47
272 | PASCHIM MEDINIPUR | Midnapore Division | PACHADAHARA & ADJOINING MOUJAS PWSS , SM/14732 | New | Material Requisition To Resource Division | 1178/MD | 26/04/2023 | 0 | Resource Division | 26.89 | 0 | 0 | 0
273 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PACHADAHARA & ADJOINING MOUJAS PWSS , SM/14732 | New | NEW SERVICE CONNECTION CHARGES AT POCHADOHARA TW-I WATER SUPPLY SCHEME | 247/JMD | 10/07/2024 | 0 | WBSEDCL | 7.16 | 0 | 0 | 0
274 | PASCHIM MEDINIPUR | Central Drilling | PACHADAHARA & ADJOINING MOUJAS PWSS , SM/14732 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
275 | PASCHIM MEDINIPUR | Midnapore Division | MANGAL BANDI AND ADJOINING MOUJAS PWSS , SM/15020 | New | Material Requisition To Resource Division | 1230/MD | 27/04/2023 | 0 | Resource Division | 26.85 | 0 | 0 | 0
276 | PASCHIM MEDINIPUR | Central Drilling | MANGAL BANDI AND ADJOINING MOUJAS PWSS , SM/15020 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
277 | PASCHIM MEDINIPUR | Midnapore Division | PIRRAKULI AND ADJOINING MOUJAS PWSS , SM/15028 | New | Material Requisition To Resource Division | 2225/MD | 15/06/2023 | 0 | Resource Division | 26.2 | 0 | 0 | 0
278 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PIRRAKULI AND ADJOINING MOUJAS PWSS , SM/15028 | New | New Service connection charges for Pirrakuli w/s scheme, t/w no.-II | 187/JMD | 30/03/2024 | 0 | WBSEDCL | 7.79 | 0 | 0 | 0
279 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PIRRAKULI AND ADJOINING MOUJAS PWSS , SM/15028 | New | New Service connection charges for Pirrakuli w/s scheme, t/w no.-I | 188/JMD | 30/03/2024 | 0 | WBSEDCL | 9.29 | 0 | 0 | 0
280 | PASCHIM MEDINIPUR | Central Drilling | PIRRAKULI AND ADJOINING MOUJAS PWSS , SM/15028 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
281 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/15220 | New | Preparation of D.P.Rs (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- (i) Gholshahi & (ii) Krishnaballavpur under Dewanchak-II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | 1308/MD | 12/08/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.16 | 0 | 0 | 0
282 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/15220 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-I under Gholshai water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur | 1299/W/MMD | 12/05/2023 | 120 | KAMAKSHYA ENTERPRISE | 5.93 | 0 | 0 | 80
283 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/15220 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Gholshahi (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 557/MD | 22/02/2023 | 465 | KISHORE GHOSH | 41.91 | 0 | 0 | 50
284 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/15220 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Gholshahi (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 556/MD | 22/02/2023 | 465 | KISHORE GHOSH | 45.54 | 0 | 0 | 70
285 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/15220 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Gholshai water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur | 1300/W/MMD | 12/05/2023 | 120 | SUBHRA ENTERPRISE | 5.91 | 0 | 0 | 100
286 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/15220 | New | Material Requisition To Resource Division | 3352/MD | 25/11/2024 | 0 | Resource Division | 2.41 | 0 | 0 | 0
287 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15572 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Ghatal block under Midnapore Division P.H.E. Dte. | 2683/MD | 30/12/2022 | 21 | RISHAN ENGINEERING CONSULTANCY | 7.72 | 0 | 0 | 100
288 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15572 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Daspur-I block under Midnapore Division P.H.E. Dte. | 2682/MD | 30/12/2022 | 21 | RISHAN ENGINEERING CONSULTANCY | 7.76 | 0 | 0 | 100
289 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15572 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (280 Nos.) under JJM with allied work for Augmentation of Bacchra Kundu Pipe W/S Scheme in Daspur-I Block including supply of all labour & materials within Ghtaal Sub-Division under Midnapore Division, PHE Dte. | 2620/MD | 24/07/2023 | 60 | ASHOK BANERJEE | 52.8 | 0 | 0 | 0
290 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15572 | Augmentation | Material Requisition To Resource Division | 1418/MD | 04/05/2023 | 0 | Resource Division | 2.93 | 0 | 0 | 0
291 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15572 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | 914/W/MMD | 27/03/2023 | 549 | GLACIER ENGINEERING CO. | 25.26 | 0 | 0 | 60
292 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15572 | Augmentation | Laying additional pipeline to provide balance FHTC under JJM in Bachhrakundu PWSS under Ghatal Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | 2218/MD | 19/07/2024 | 45 | ASHOK BANERJEE | 28.06 | 0 | 0 | 0
293 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15572 | Augmentation | QUOTATION MONEY FOR BACHRA KUNDU WATER SUPPLY SCHEME, T W NO4, [ AUGMENTATION ] , JJM WORKS, BLOCK- DASPUR-I, SCHEME CODE SM/15572, APPLICATION NO 2004849416, REFERENCE ID 204373204, DASPUR CCC, WBSEDCL | C082441572310 | 29/08/2024 | 0 | WBSEDCL | 3.66 | 0 | 0 | 0
294 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | 1307/W/MMD | 15/05/2023 | 90 | A.K. INDUSTRIES | 231.59 | 0 | 0 | 83
295 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp AT BASANTAPUR WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 202781424, APPLICATION NO 2004704970, DASPUR CCC [ SCHEME CODE SM/16928 ] | BP-2024-25-445 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
296 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp AT KHANJAPUR WATER SUPPLY SCHEME , P H NO II, CONSUMER ID 201201978, APPLICATION NO 2004704971, DASPUR CCC [ SCHEME CODE SM/16928 ] | BP-2024-25-444 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
297 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT BHEMWA WATER SUPPLY SCHEME , ZONE-II, P H NO 1, CONSUMER ID 200781300, APPLICATION NO 2004697971, SABANG CCC |  | 24/07/2024 | 0 | WBSEDCL | 0.18 | 0 | 0 | 0
298 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp AT SUPAPURSURI WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 201453480, APPLICATION NO 2004704898, DASPUR CCC [ SCHEME CODE SM/16928 ] | BP-2024-25-442 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
299 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FFE FOR SOLAR POWER PLANT OF 10 KWp AT BHEMWA WATER SUPPLY SCHEME , ZONE-II, P H NO 1, CONSUMER ID 200781300, APPLICATION NO 2004697971, SABANG CCC | BP-2024-25-439 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
300 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp AT NARAYANBAR WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 200452363, APPLICATION NO 2004769900, SABANG CCC | BP-2024-25-438 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
301 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT BHEMWA WATER SUPPLY SCHEME , ZONE-I, P H NO 1, CONSUMER ID 200781302, APPLICATION NO 2004697991, SABANG CCC | BP-2024-25-514 | 31/07/2024 | 0 | WBSEDCL | 0.18 | 0 | 0 | 0
302 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp FOR BURAL WATER SUPPLY SCHEME, ZONE- II , T W NO I , JJM WORKS, SCHEME CODE SM/16928, APPLICATION NO 2004697989 , CONSUMER ID 200452395, SABANG CCC, WBSEDCL | BP-2024-25-433 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
303 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT SHYASUNDARPUR WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 201045814, APPLICATION NO 2004697999, SABANG CCC |  | 24/07/2024 | 0 | WBSEDCL | 0.18 | 0 | 0 | 0
304 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FFE FOR SOLAR POWER PLANT OF 10 KWp AT BISHNUPUR WATER SUPPLY SCHEME , P H NO 1, BLOCK SABANG, CONSUMER ID 200461276, APPLICATION NO 2004769914, SABANG CCC | BP-2024-25-437 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
305 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT SABANG WATER SUPPLY SCHEME , ZONE-I, P H NO 1, CONSUMER ID 212013535, APPLICATION NO 2004697968, SABANG CCC | BP-2024-25-570 | 14/08/2024 | 0 | WBSEDCL | 0.18 | 0 | 0 | 0
306 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp FOR SHYAMSUNDARPUR WATER SUPPLY SCHEME, T W NO I , JJM WORKS, SCHEME CODE SM/16928, APPLICATION NO 2004697999 , CONSUMER ID 201045814, SABANG CCC, WBSEDCL | BP-2024-25-436 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
307 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp FOR BURAL WATER SUPPLY SCHEME, ZONE- I , T W NO I , JJM WORKS, SCHEME CODE SM/16928, APPLICATION NO 2004697958 , CONSUMER ID 200292721, SABANG CCC, WBSEDCL | BP-2024-25-432 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
308 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | QUOTATION MONEY FOR NET METERING FOR 10 KWp SOLAR POWER PLANT AT TARARUI WATER SUPPLY SCHEME , TW NO 1, SCHEME CODE SM/16928 , BLOCK DANTAN, DANTAN CCC [ APPLICATION NO 2004684098, CONSUMER ID 202834255 ] | BP-2024-24-124 | 06/05/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
309 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp AT KANJAPUR WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 201201977, APPLICATION NO 2004704974, DASPUR CCC [ SCHEME CODE SM/16928 ] | BP-2024-25-443 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
310 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FFE FOR SOLAR POWER PLANT OF 10 KWp AT KATAN WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 201975256, APPLICATION NO 2004704975, DASPUR CCC [ SCHEME CODE SM/16928 ] | BP-2024-25-440 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
311 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp FOR SABANG WATER SUPPLY SCHEME, ZONE-I, T W NO I JJM WORKS, SCHEME CODE SM/16928, APPLICATION NO 2004697968 , CONSUMER ID 212013535, SABANG CCC, WBSEDCL | BP-2024-25-435 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
312 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT KAPASDA WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 200292702, APPLICATION NO 2004697950, SABANG CCC | BP-2024-25-513 | 31/07/2024 | 0 | WBSEDCL | 0.2 | 0 | 0 | 0
313 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT BURAL WATER SUPPLY SCHEME , ZONE - I, P H NO 1, CONSUMER ID 200292721, APPLICATION NO 2004697958, SABANG CCC |  | 24/07/2024 | 0 | WBSEDCL | 0.18 | 0 | 0 | 0
314 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FFE FOR SOLAR POWER PLANT OF 10 KWp AT BACHRAKUNDU WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 201514664, APPLICATION NO 2004704979, DASPUR CCC [ SCHEME CODE SM/16928 ] | BP-2024-25-441 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
315 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | Quotation for Application Fee of Solar Power Plant 10 KW at PH-I of PURULDA PWSS . Application No-2004602453, Ref Consumer ID-202975691, Billing Type-Net Billing, Name of CCC-Khakurda CCC. | BP-2023-24-732 | 26/02/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
316 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FFE FOR SOLAR POWER PLANT OF 10 KWp AT BHEMWA WATER SUPPLY SCHEME ,ZONE- I , P H NO 1, SCHEME CODE SM/16928, CONSUMER ID 200781302, APPLICATION NO 2004697991, SABANG CCC | BP-2024-25-434 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
317 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT BURAL WATER SUPPLY SCHEME , ZONE-II, P H NO 1, CONSUMER ID 2004523395, APPLICATION NO 2004697989, SABANG CCC | BP-2024-25-515 | 31/07/2024 | 0 | WBSEDCL | 0.18 | 0 | 0 | 0
318 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp FOR KAPASDA WATER SUPPLY SCHEME, T W NO I , JJM WORKS, SCHEME CODE SM/16928, APPLICATION NO 2004697950 , CONSUMER ID 200292702, SABANG CCC, WBSEDCL | BP-2024-25-431 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
319 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16928 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 720/MMSD-I | 07/06/2024 | 15 | SUBHASIS ROY | 2.29 | 0 | 0 | 100
320 | PASCHIM MEDINIPUR | Midnapore Division | MALIHATI AND IT'S ADJOINING MOUJAS PWSS , SM/16615 | New | Material Requisition To Resource Division | 1160/MD | 25/04/2023 | 0 | Resource Division | 31.04 | 0 | 0 | 0
321 | PASCHIM MEDINIPUR | Midnapore Division | MALIHATI AND IT'S ADJOINING MOUJAS PWSS , SM/16615 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 0 | 25
322 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Lutunia PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17375 | Solarisation | Solarization of grid connected pumping installation at Lutunia PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 695/W/MMD | 23/03/2023 | 180 | NITESH MANAGEMENT | 6.25 | 0 | 0 | 0
323 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Maliara PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17376 | Solarisation | Solarization of grid connected pumping installation at Maliara PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 786/W/MMD | 24/03/2023 | 180 | M/S. JIT ENTERPRISE | 6.26 | 0 | 0 | 85
324 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Maliara PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17376 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going solarisation / rejuvenation as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 716/MMSD-I | 07/06/2024 | 15 | MUKHERJEE ART CENTRE | 1.93 | 0 | 0 | 100
325 | PASCHIM MEDINIPUR | Midnapore Division | SHASHINDA SVS PWSS , SM/18017 | New | Material Requisition To Resource Division | 1169/MD | 26/04/2023 | 0 | Resource Division | 12.88 | 0 | 0 | 0
326 | PASCHIM MEDINIPUR | Central Drilling | SHASHINDA SVS PWSS , SM/18017 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
327 | PASCHIM MEDINIPUR | Midnapore Division | SHASHINDA SVS PWSS , SM/18017 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 0 | 20
328 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Mansuka PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17799 | Solarisation | Solarization of grid connected pumping installation Mansuka PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 992/W/MMD | 29/03/2023 | 180 | ABHIJIT MUKHERJEE | 6.25 | 0 | 0 | 77
329 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18171 | New | Material Requisition To Resource Division | 4058/MD | 12/10/2023 | 0 | Resource Division | 40.25 | 0 | 0 | 0
330 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18171 | New | Material Requisition To Resource Division | 3327/MD | 25/11/2024 | 0 | Resource Division | 8.98 | 0 | 0 | 0
331 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18171 | New | New Service connection charges. | 25/JMD | 06/03/2024 | 0 | WBSEDCL | 7.47 | 0 | 0 | 0
332 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18171 | New | Quotation for Bagchori T/W - I water supply scheme. | 29/JMD | 11/03/2024 | 0 | WBSEDCL | 7.47 | 0 | 0 | 0
333 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18171 | New | Sinking of Tube wells, Construction of 450 CuM Capacity R.C.C Over Head Reservoirs (Over Pile Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (6507) for Bagchhari & Mangrul Pipe W/S Scheme including Two years O&M within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | 2825/MD | 07/08/2023 | 783 | GOBINDA MAITY | 1766.48 | 0 | 0 | 70
334 | PASCHIM MEDINIPUR | Midnapore Mechanical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18171 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at BAGCHHARI Water supply scheme, Chandrakona -I block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 2281/W/MMD | 29/08/2023 | 522 | DEBJYOTI BASU | 30.12 | 0 | 0 | 100
335 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Sutkujhuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17383 | Solarisation | Solarization of grid connected pumping installation at Sutkujhuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 712/W/MMD | 23/03/2023 | 180 | KAMAKSHYA ENTERPRISE | 6.26 | 0 | 0 | 0
336 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Panpara PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17732 | Solarisation | Solarization of grid connected pumping installation Panpara PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 981/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
337 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Chatra PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17735 | Solarisation | Solarization of grid connected pumping installation Chatra PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 983/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
338 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Hatimasan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17738 | Solarisation | Solarization of grid connected pumping installation Hatimasan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 988/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
339 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/18032 | New | Material Requisition To Resource Division | 72/MD | 09/01/2023 | 0 | Resource Division | 34.76 | 0 | 0 | 0
340 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/18032 | New | Material Requisition To Resource Division | 1508/MD | 12/05/2023 | 0 | Resource Division | 12.26 | 0 | 0 | 0
341 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/18032 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | 581/W/MMD | 20/03/2023 | 180 | B.P.TRADING CORPORATION | 25.26 | 0 | 0 | 90
342 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/18032 | New | Installation of Display Board for JJM work at different Piped Water Supply Scheme under different block within Midnapore Division, PHE Dte. [PART-A] | 506/MD | 27/02/2024 | 10 | PULLOCK KUMAR GHOSH | 0.96 | 0 | 0 | 100
343 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/18032 | New | New Service connection charges. | 49/JMD | 06/02/2024 | 0 | WBSEDCL | 4.07 | 0 | 0 | 0
344 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/18032 | New | Quotaton for new service connection charges for Maheshpur tw-II water supply scheme. | 295/JMD | 09/08/2024 | 0 | WBSEDCL | 3.48 | 0 | 0 | 0
345 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/18032 | New | Laying of Rising main & interconnection for Maheshpur & its adjoining mouzas PWSS, Block: - Chandrakona-I, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 459/MD | 11/02/2025 | 45 | DULAL CHANDRA DAS | 10.5 | 0 | 0 | 0
346 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kasanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17493 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
347 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Belda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17357 | Solarisation | Solarization of grid connected pumping installation at Belda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 680/W/MMD | 23/03/2023 | 180 | A-NIK & CO. | 6.26 | 0 | 0 | 100
348 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Belda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17357 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 720/MMSD-I | 07/06/2024 | 15 | SUBHASIS ROY | 2.29 | 0 | 0 | 100
349 | PASCHIM MEDINIPUR | Midnapore Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS , SM/18013 | New | Material Requisition To Resource Division | 1302/MD | 28/04/2023 | 0 | Resource Division | 20.4 | 0 | 0 | 0
350 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS , SM/18013 | New | New service connection charges for Saldahara pwss, t/w no. II | 50/JMD | 29/04/2024 | 0 | WBSEDCL | 7.59 | 0 | 0 | 0
351 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS , SM/18013 | New | New service connection charges for Saldahara pwss, t/w no.I | 34/JMD | 11/03/2024 | 0 | WBSEDCL | 3.32 | 0 | 0 | 0
352 | PASCHIM MEDINIPUR | Midnapore Mechanical | SHAL DAHARA AND ADJOINING MOUJAS PWWSS , SM/18013 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SHAL DAHARA AND ADJOINING MOUJAS PWWSS under JJM Program under MMD PHE Dte. | 619/W/MMD | 20/03/2023 | 531 | SUJOY RANJAN BHOWMICK | 21.58 | 0 | 0 | 56
353 | PASCHIM MEDINIPUR | Midnapore Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS , SM/18013 | New | Route survey & way leave permission along & across of National Highway in Shaldahara PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | 375/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 12.25 | 0 | 0 | 0
354 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Daspur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17373 | Solarisation | Solarization of grid connected pumping installation at Daspur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 686/W/MMD | 23/03/2023 | 900 | GOENKA ENTERPRISE | 6.26 | 0 | 0 | 80
355 | PASCHIM MEDINIPUR | Midnapore Division | NILDA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MIDNAPUR DIVISION , SM/17565 | New | Preparation & Submission of 2 (Two) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Dhuipara & its adjoining Mouzas PWSS AND (2) Nilda & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | 818/MD | 21/03/2023 | 30 | ENVIROTECH SOLUTIONS | 7.66 | 0 | 0 | 100
356 | PASCHIM MEDINIPUR | Midnapore Division | NILDA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MIDNAPUR DIVISION , SM/17565 | New | Material Requisition To Resource Division | 1452/MD | 08/05/2023 | 0 | Resource Division | 21.57 | 0 | 0 | 0
357 | PASCHIM MEDINIPUR | Midnapore Mechanical | NILDA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MIDNAPUR DIVISION , SM/17565 | New | Electrict quotation bill for TW-II of Nilda pwss (Zone-I) (Ref Consumar ID-204312269),Application No-2004743789,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | BP-2024-25-195 | 24/05/2024 | 0 | WBSEDCL | 3.66 | 0 | 0 | 0
358 | PASCHIM MEDINIPUR | Midnapore Mechanical | NILDA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MIDNAPUR DIVISION , SM/17565 | New | Electrict quotation bill for TW-I of Nilda pwss (Zone-I) (Ref Consumar ID-204312296),Application No-2004743827,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | BP-2024-25-196 | 24/05/2024 | 0 | WBSEDCL | 5.52 | 0 | 0 | 0
359 | PASCHIM MEDINIPUR | Midnapore Mechanical | NILDA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MIDNAPUR DIVISION , SM/17565 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipment¿s for NILDA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK Dist Paschim Medinipur UNDER MIDNAPUR DIVISION under JJM Program under MMD PHE Dte. | 1570/W/MMD | 13/07/2023 | 641 | DEBJYOTI BASU | 20.97 | 0 | 0 | 40
360 | PASCHIM MEDINIPUR | Midnapore Division | NILDA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MIDNAPUR DIVISION , SM/17565 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 0 | 55
361 | PASCHIM MEDINIPUR | Midnapore Division | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17566 | New | Material Requisition To Resource Division | 1453/MD | 08/05/2023 | 0 | Resource Division | 23.16 | 0 | 0 | 0
362 | PASCHIM MEDINIPUR | Midnapore Mechanical | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17566 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION under JJM Program under MMD PHE Dte. | 1195/W/MMD | 25/04/2023 | 720 | DEBJYOTI BASU | 22.64 | 0 | 0 | 40
363 | PASCHIM MEDINIPUR | Midnapore Mechanical | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17566 | New | Electrict quotation bill for TW-I of Nilda pwss (Zone-II) (Ref Consumar ID-204310685),Application No-2004741431,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | BP-2024-25-198 | 24/05/2024 | 0 | WBSEDCL | 9.92 | 0 | 0 | 0
364 | PASCHIM MEDINIPUR | Midnapore Mechanical | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17566 | New | Electrict quotation bill for TW-II of Nilda pwss (Zone-II) (Ref Consumar ID-204310727),Application No-2004741416,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | BP-2024-25-197 | 24/05/2024 | 0 | WBSEDCL | 7.26 | 0 | 0 | 0
365 | PASCHIM MEDINIPUR | Midnapore Division | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17566 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 0 | 55
366 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kashijora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17494 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
367 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Satkui PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17327 | Solarisation | Solarization of grid connected pumping installation at Satkui PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 705/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
368 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Lutunia PWSS in the District of Paschim Medinipur under JJM programme. , SM/17792 | Augmentation | Electric quotation bill for Lutunia TW-IV WS Scheme(Ref. ID 2004233628) | BP-2023-24-6 | 18/04/2023 | 0 | WBSEDCL | 0.46 | 0 | 0 | 0
369 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Amrakuchi PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17325 | Solarisation | Solarization of grid connected pumping installation at Amrakuchi PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 1052/W/MMD | 29/03/2023 | 180 | R.S. ENTERPRISE | 6.26 | 0 | 0 | 80
370 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHAMSAI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER KESHPUR BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/17395 | Augmentation | Continuation Work Order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dhamsai, Block - Keshpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | 1113/MD | 09/07/2021 | 10 | CIVIL FOUNDATION ENGINEERING | 1.29 | 0 | 0 | 100
371 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHAMSAI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER KESHPUR BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/17395 | Augmentation | Material Requisition To Resource Division | 1394/MD | 03/05/2023 | 0 | Resource Division | 16.27 | 0 | 0 | 0
372 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHAMSAI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER KESHPUR BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/17395 | Augmentation | Laying of distribution, Rising main & Accommodate balance FHTC (70 Nos.) including 2 years O & M under JJM with allied work for Augmentation of Dhamsai & its adjoining mouzas W/S scheme in Keshpur block including supply of all labour & materials within Midnapore Sadar Sub-Division under Medinipur Division, PHE Dte. | 2716/MD | 31/07/2023 | 790 | M/S. D.K.H.CONSTRUCTION | 118.46 | 0 | 0 | 0
373 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bamanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17335 | Solarisation | Solarization of grid connected pumping installation at Bamanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 678/W/MMD | 23/03/2023 | 180 | A-NIK & CO. | 6.26 | 0 | 0 | 70
374 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Pratappur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17345 | Solarisation | Solarization of grid connected pumping installation at Pratappur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 709/W/MMD | 23/03/2023 | 180 | ABHIJIT MUKHERJEE | 6.25 | 0 | 0 | 90
375 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chandrakona Road, Zone-I& Zone-II PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17463 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
376 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Chakismilepur PWSS in the District of Paschim Medinipur under JJM programme. , SM/17812 | Augmentation | Rejuvenation of Electro-Mechanical components of Chakismilepur PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | 1063/W/MMD | 29/03/2023 | 180 | M/S EMMESS | 11.01 | 0 | 0 | 55
377 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Ranapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17819 | Solarisation | Solarization of grid connected pumping installation Ranapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 970/W/MMD | 29/03/2023 | 180 | RSA ENTERPRISE | 6.25 | 0 | 0 | 0
378 | PASCHIM MEDINIPUR | Midnapore Division | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS , SM/17004 | New | Material Requisition To Resource Division | 3371/MD | 25/11/2024 | 0 | Resource Division | 11.53 | 0 | 0 | 0
379 | PASCHIM MEDINIPUR | Midnapore Mechanical | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS , SM/17004 | New | Electric quotation bill for Tw No-I of Dakshin Parshura PWSS. (Ref Consumer ID-204182272) | BP-2023-24-557 | 16/01/2024 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
380 | PASCHIM MEDINIPUR | Midnapore Mechanical | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS , SM/17004 | New | Electric quotation bill for Tw No-II of Daksin parshura PWSS. (Ref Consumer ID-204182381) | BP-2023-24-558 | 16/01/2024 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
381 | PASCHIM MEDINIPUR | Midnapore Division | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS , SM/17004 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 250 Cum OHR (Intze type with Pile Foundation) & Accommodate FHTC (1,871 Nos.) including Two years O&M under JJM with allied work for Dakshin Parshura & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | 2956/MD | 17/08/2023 | 902 | M/S. D.K.H.CONSTRUCTION | 728.65 | 0 | 0 | 15
382 | PASCHIM MEDINIPUR | Midnapore Mechanical | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS , SM/17004 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 1186/W/MMD | 25/04/2023 | 643 | RSA ENTERPRISE | 22.89 | 0 | 0 | 25
383 | PASCHIM MEDINIPUR | Midnapore Division | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS , SM/18583 | New | Material Requisition To Resource Division | 1529/MD | 12/05/2023 | 0 | Resource Division | 308.47 | 0 | 0 | 0
384 | PASCHIM MEDINIPUR | Midnapore Mechanical | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS , SM/18583 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | 1723/W/MMD | 09/08/2023 | 180 | S.K.ENTERPRISE | 25.26 | 0 | 0 | 50
385 | PASCHIM MEDINIPUR | Midnapore Mechanical | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS , SM/18583 | New | Quotation for new power connection at Jaganathchak T/W - II Within Khargpur - II Block, Application No - 2004975111 , Ref ID - 204452538 | C122403006019 | 03/12/2024 | 0 | WBSEDCL | 3.56 | 0 | 0 | 0
386 | PASCHIM MEDINIPUR | Midnapore Mechanical | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS , SM/18583 | New | Quotation for new power connection at Jaganathchak T/W - I Within Khargpur - II Block, Application No - 2004975165 , Ref ID - 204452539 | C122403005259 | 03/12/2024 | 0 | WBSEDCL | 5.31 | 0 | 0 | 0
387 | PASCHIM MEDINIPUR | Midnapore Division | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS , SM/18583 | New | Sinking of Tube wells, Construction of 400 CuM Capacity R.C.C Over Head Reservoirs (Over Raft / Pile Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (6,875 Nos.) for Jagannathchak & Barbasi Pipe W/S Scheme including 2 years O&M within Kharagpur-II Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | 3101/MD | 25/08/2023 | 772 | GOBINDA MAITY | 1932.69 | 0 | 0 | 25
388 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19049 | New | Material Requisition To Resource Division | 181/MD | 16/01/2023 | 0 | Resource Division | 48.33 | 0 | 0 | 0
389 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19049 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II and III) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 3097/W/MMD | 29/11/2023 | 906 | DEBJYOTI BASU | 43.72 | 0 | 0 | 65
390 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19049 | New | Material Requisition To Resource Division | 3441/MD | 25/11/2024 | 0 | Resource Division | 21.6 | 0 | 0 | 0
391 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19049 | New | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-III, T W NO I [ SADATPUR ] , JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2004887943, REFERENCE ID 204392629, NIMPURA CCC, WBSEDCL | C092445635685 | 30/09/2024 | 0 | WBSEDCL | 6.69 | 0 | 0 | 0
392 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19049 | New | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-I, T W NO 1, [ SUNDRABANDHA ] JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2004776663, REFERENCE ID 204331299, NIMPURA CCC, WBSEDCL | BP-2024-25-429 | 16/07/2024 | 0 | WBSEDCL | 3.37 | 0 | 0 | 0
393 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19049 | New | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-II, T W NO 2, [ SOBHAPUR ] JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2004792617, REFERENCE ID 204341188, NIMPURA CCC, WBSEDCL | BP-2024-25-428 | 16/07/2024 | 0 | WBSEDCL | 3.51 | 0 | 0 | 0
394 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19049 | New | Sinking of Tube wells, Construction of 250 CuM Capacity R.C.C Over Head Reservoirs (Over Raft Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (5415 nos.) including Two years O&M for AMBA (ZONE-I, II & III) & KASHIJORA (ZONE-I & II) Pipe W/S Scheme within Kharagpur-I Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | 2465/MD | 14/07/2023 | 808 | GOBINDA MAITY | 1571.51 | 0 | 0 | 42
395 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19049 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II and III) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. (Part-II) | 3100/W/MMD | 29/11/2023 | 540 | S.S.GHORAI | 22.81 | 0 | 0 | 100
396 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Chotokalshibhanga PWSS in the District of Paschim Medinipur under JJM programme. , SM/17796 | Augmentation | Rejuvenation of Electro-Mechanical components of Chotokalshibhanga PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | 1062/W/MMD | 29/03/2023 | 180 | THE GODFATHER TRADING COMPANY | 5.07 | 0 | 0 | 60
397 | PASCHIM MEDINIPUR | Midnapore Division | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/18585 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Shila Rajnagar & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | 1751/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.97 | 0 | 0 | 100
398 | PASCHIM MEDINIPUR | Midnapore Division | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/18585 | New | Material Requisition To Resource Division | 71/MD | 09/01/2023 | 0 | Resource Division | 15.92 | 0 | 0 | 0
399 | PASCHIM MEDINIPUR | Midnapore Division | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/18585 | New | Material Requisition To Resource Division | 3365/MD | 25/11/2024 | 0 | Resource Division | 17.22 | 0 | 0 | 0
400 | PASCHIM MEDINIPUR | Midnapore Mechanical | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/18585 | New | QUOTATION MONEY FOR SHILARAJNAGAR WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/18585, APPLICATION NO 2004628032, REFERENCE ID 204234631, GHATAL CCC, WBSEDCL | BP-2023-24-840 | 14/03/2024 | 0 | WBSEDCL | 3.29 | 0 | 0 | 0
401 | PASCHIM MEDINIPUR | Midnapore Mechanical | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/18585 | New | QUOTATION MONEY FOR SHILARAJNAGAR WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/18585, APPLICATION NO 2004627434, REFERENCE ID 204234630, GHATAL CCC, WBSEDCL | BP-2023-24-841 | 14/03/2024 | 0 | WBSEDCL | 4.46 | 0 | 0 | 0
402 | PASCHIM MEDINIPUR | Midnapore Mechanical | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/18585 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 1730/W/MMD | 09/08/2023 | 570 | ORIENTAL ENGINEERING CO. | 27.35 | 0 | 0 | 55
403 | PASCHIM MEDINIPUR | Midnapore Mechanical | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/18585 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
404 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas. , SM/18758 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas under JJM Program under MMD PHE Dte. | 2288/W/MMD | 29/08/2023 | 180 | ORIENTAL ENGINEERING CO. | 23.76 | 0 | 0 | 0
405 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas. , SM/18758 | New | Material Requisition To Resource Division | 75/MD | 09/01/2023 | 0 | Resource Division | 22.89 | 0 | 0 | 0
406 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas. , SM/18758 | New | Material Requisition To Resource Division | 3348/MD | 25/11/2024 | 0 | Resource Division | 14.24 | 0 | 0 | 0
407 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas. , SM/18758 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,311 Nos.) under JJM with allied work for Kashinathpur & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Midnapore Sub-Division under Midnapore Division, PHE Dte. | 5057/MD | 26/10/2023 | 883 | DULAL CHANDRA DAS | 602 | 0 | 0 | 25
408 | PASCHIM MEDINIPUR | Midnapore Division | BHAGABANPUR PIPED WATER SUPPLY SCHEME , SM/12202 | New | Material Requisition To Resource Division | 1412 | 04/05/2023 | 0 | Resource Division | 24.76 | 0 | 0 | 0
409 | PASCHIM MEDINIPUR | Midnapore Mechanical | BHAGABANPUR PIPED WATER SUPPLY SCHEME , SM/12202 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Bhagabanpur PWSS Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | 2298/W/MMD | 29/12/2022 | 1094 | SUBHAM ENTERPRISE | 22.79 | 0 | 0 | 40
410 | PASCHIM MEDINIPUR | Midnapore Division | BHAGABANPUR PIPED WATER SUPPLY SCHEME , SM/12202 | New | Construction of 200 Cum & 300 Cum Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,806 Nos.) including 2 years operation & maintenance For Bakalsabakram, Bhagabanpur and Chak Prayag Pipe water supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5382/MD | 04/12/2023 | 574 | M/S. KAMAK ENGINEERS AND CO. | 1277.59 | 0 | 0 | 50
411 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. , SM/18621 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas.under JJM Program under MMD PHE Dte. (Part-III) | 1734/W/MMD | 09/08/2023 | 180 | KAMAKSHYA ENTERPRISE | 11.98 | 0 | 0 | 0
412 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. , SM/18621 | New | Material Requisition To Resource Division | 109/MD | 10/01/2023 | 0 | Resource Division | 41.59 | 0 | 0 | 0
413 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. , SM/18621 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas.under JJM Program under MMD PHE Dte. | 1728/W/MMD | 09/08/2023 | 180 | SUBODH KUMAR BANIK | 27.3 | 0 | 0 | 51
414 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. , SM/18621 | New | Material Requisition To Resource Division | 3347/MD | 25/11/2024 | 0 | Resource Division | 32.92 | 0 | 0 | 0
415 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. , SM/18621 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas.under JJM Program under MMD PHE Dte. (Part-II) | 1731/W/MMD | 09/08/2023 | 180 | M/S B.M. ELECTRICAL | 22.89 | 0 | 0 | 50
416 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. , SM/18621 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 450 & 300 cum OHRs (Intze type with pile foundation) & Accommodate FHTC(5,344 Nos.) under JJM with allied work for Goura (Zone-I,II,III & IV) & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 5058/MD | 26/10/2023 | 973 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 1390.82 | 0 | 0 | 30
417 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. , SM/18621 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
418 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. , SM/18621 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
419 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KALLA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/18541 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 450 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,915) under JJM with allied work for KALLA PWSS in Chandrakona-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 3146/MD | 29/08/2023 | 180 | SATYABRATA CHAKRABORTY | 792.07 | 0 | 0 | 0
420 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KALLA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/18541 | New | Material Requisition To Resource Division | 1585/MD | 15/05/2023 | 0 | Resource Division | 85.7 | 0 | 0 | 0
421 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KALLA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/18541 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER CHANDRAKONA - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICTunder JJM Program under MMD PHE Dte. | 1693/W/MMD | 04/08/2023 | 180 | AMUSAR IMPEX PVT. LTD | 49.92 | 0 | 0 | 80
422 | PASCHIM MEDINIPUR | Midnapore Division | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME , SM/18508 | New | Material Requisition To Resource Division | 3381/MD | 25/11/2024 | 0 | Resource Division | 17 | 0 | 0 | 0
423 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME , SM/18508 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of GOPALBANDH PWSS. REF CONSUMER ID-204269029, APPLICATION NO-2004675306 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-71 | 24/04/2024 | 0 | WBSEDCL | 0.29 | 0 | 0 | 0
424 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME , SM/18508 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of GOPALBANDH PWSS. REF CONSUMER ID-204269014, APPLICATION NO-2004675316 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-72 | 24/04/2024 | 0 | WBSEDCL | 9.56 | 0 | 0 | 0
425 | PASCHIM MEDINIPUR | Midnapore Division | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME , SM/18508 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 0 | 75
426 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME , SM/18508 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | 1683/W/MMD | 04/08/2023 | 636 | ALPHA ENTERPRISE | 25.24 | 0 | 0 | 20
427 | PASCHIM MEDINIPUR | Midnapore Division | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME , SM/18508 | New | Hire charges of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 12 ( Twelve) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer, (HQ) Midnapur Division PHE Dte.for12(twelve)months.(Period From-01.01.2024 to 31.12.2024) | 925/AE/MSSD | 13/12/2023 | 366 | NAFISA ENTERPRISE | 1.73 | 0 | 0 | 0
428 | PASCHIM MEDINIPUR | Midnapore Division | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME , SM/18508 | New | Laying of rising main & interconnection for Gopal Bandh & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 435 Mtr.) | 195/MD | 17/01/2025 | 45 | M/S. S.S. ENTERPRISE | 5.73 | 0 | 0 | 0
429 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS , SM/18532 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHARI GERYA AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | 1689/W/MMD | 04/08/2023 | 180 | ORIENTAL ENGINEERING CO. | 25.25 | 0 | 0 | 0
430 | PASCHIM MEDINIPUR | Midnapore Division | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS , SM/18532 | New | Material Requisition To Resource Division | 1589/MD | 15/05/2023 | 0 | Resource Division | 34.55 | 0 | 0 | 0
431 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS , SM/18532 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of KHARIGERIA PWSS. REF CONSUMER ID-204212338, APPLICATION NO-2004593715, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-685 | 16/02/2024 | 0 | WBSEDCL | 4.92 | 0 | 0 | 0
432 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS , SM/18532 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of KHARIGERIA PWSS. REF CONSUMER ID-204211927, APPLICATION NO-2004590188 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-686 | 16/02/2024 | 0 | WBSEDCL | 3.82 | 0 | 0 | 0
433 | PASCHIM MEDINIPUR | Midnapore Division | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS , SM/18532 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 Cum (Intze type with Pile Foundation) OHR & Accommodate FHTC (2,792 Nos.) including 02(Two) years O&M under JJM with allied work for Khari Gerya & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | 5059/MD | 26/10/2023 | 700 | M/S. CARE | 871.34 | 0 | 0 | 35
434 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS , SM/18532 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0 | 0 | 50
435 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Harekrishnapur Piped Water Supply Scheme. , SM/06899 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Harekrishnapur W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | DIPAK KUMAR DOLAI | 98.16 | 0 | 0 | 0
436 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Harekrishnapur Piped Water Supply Scheme. , SM/06899 | Retrofitting | Round the Clock Guarding Arrangements to protect the Govt. properties / materials etc. at The Head work site Midnapore Divison , PHE Dte. | 8443129 | 31/03/2023 | 0 | M/S. OXFORD SECURITY SERVICE | 1.03 | 0 | 0 | 0
437 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Harekrishnapur Piped Water Supply Scheme. , SM/06899 | Retrofitting | Laying additional pipe line for retrofitting to accommodate FHTC under JJM in Harekrishnapur PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division PHE.Dte. (For the Villages- Mahabatpur, nabin Simla & Sridharpur) | 82/AE/GSD | 25/02/2021 | 20 | SUBHASIS DOLAI | 4.78 | 9.63 | 100 | 0
438 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Harekrishnapur Piped Water Supply Scheme. , SM/06899 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in HAREKRISHNAPUR PWSS in Daspur-I Block in the District of Paschim Midnapore. | 450/MD | 26/02/2021 | 30 | SUBHASIS DOLAI | 13.85 | 13.15 | 100 | 0
439 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Harekrishnapur Piped Water Supply Scheme. , SM/06899 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Harekrishnapur W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1430/MD | 26/11/2020 | 180 | DIPAK KUMAR DOLAI | 94.96 | 70.49 | 100 | 0
440 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS , SM/06909 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhemwa (Zone-II) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | HARIPADA PATTANAYAK | 30 | 0 | 0 | 0
441 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS , SM/06909 | Retrofitting | FHTC imis data entry. | 8443150 | 24/03/2022 | 0 | PARTHA PRATIM PAL | 0.09 | 0 | 0 | 0
442 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS , SM/06909 | Retrofitting | FHTC imis data entry. | 8443150 | 24/03/2022 | 0 | RINTU SAMANTA | 0.05 | 0 | 0 | 0
443 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS , SM/06909 | Retrofitting | FHTC imis data entry. | 8443150 | 24/03/2022 | 0 | TANMOY BERA | 0.14 | 0 | 0 | 0
444 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS , SM/06909 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhemwa (Zone-II) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1469/MD | 26/11/2020 | 180 | HARIPADA PATTANAYAK | 83.93 | 33.53 | 39.96 | 100
445 | PASCHIM MEDINIPUR | Midnapore Mechanical | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS , SM/06909 | Retrofitting | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Zone-II Pump House-II under Bhemwa water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist - Paschim Medinipur | 215/W/MMD | 10/02/2023 | 180 | DEBJYOTI BASU | 11.23 | 0 | 0 | 100
446 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-IV) PWSS , SM/06921 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-IV) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | M/S. CARE | 7.86 | 0 | 0 | 0
447 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-IV) PWSS , SM/06921 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-IV) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1441/MD | 26/11/2020 | 180 | M/S. CARE | 52.92 | 0 | 0 | 0
448 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Nabin Mahespur PWSS, Block - Daspur-I, District - Paschim Medinipur. , SM/09081 | Retrofitting | Laying distribution pipe line, Construction of R.C.C. Over Head Reservoir of capacity 250 Cum and staging height 20.00 mtr, FHTC with allied work for Nabin Maheshpur & its adjoining mouzas W/S Scheme in Daspur-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 608/MD | 04/04/2022 | 819 | DIPAK KUMAR DOLAI | 210.12 | 0 | 0 | 100
449 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sabang PWSS, Block - Sabang, District - Paschim Medinipur. , SM/09087 | Retrofitting | Extension of Pipeline at Mouza Gourbar Muslim Para within Sabang Augmentation Water Supply Scheme (Zone-I) at Sabang Block for FHTC Work under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | 490/AE/KSD | 01/08/2022 | 30 | PALASH KUMAR DAS | 4.7 | 0 | 0 | 0
450 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sabang PWSS, Block - Sabang, District - Paschim Medinipur. , SM/09087 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sabang (Zone-I) PWSS under Sabang Block in Paschim Medinipur District. | 2186/MD | 17/12/2021 | 1111 | MASUM ALI KHAN | 53.37 | 0 | 0 | 100
451 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Gurguripal PWSS, Block - Midnapore Sadar, District - Paschim Medinipur. , SM/09088 | Retrofitting | Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 300 Cum OHR (Intze type with solid Raft foundation) & Accommodate FHTC (1,486 nos.) under JJM with allied work for Gurguripal & its adjoining mouzas PWSS in Midnapore sadar Block including supply of all labour & materials including 02 (Two) years Operation & Maintenance under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 2657/MD | 29/08/2024 | 180 | CREATION CONSTRUCTION | 254.08 | 0 | 0 | 0
452 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas , SM/09440 | New | Service connection charge of WBSEDCL at Talda, Sabang | 2003774985/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
453 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas , SM/09440 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Talda water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2511/W/MMD | 30/11/2021 | 4 | DEBJYOTI BASU | 4.47 | 0 | 0 | 100
454 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas , SM/09440 | New | Service connection charges of WBSEDCL | BP-2021-22-57 | 22/04/2022 | 0 | WBSEDCL | 1.15 | 0 | 0 | 0
455 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas , SM/09440 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Talda, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte.(w/O No. 122/W/MMD dt. 24-01-2022) | BP-2022-23-42 | 12/08/2022 | 0 | S.S.GHORAI | 0.71 | 0 | 0 | 0
456 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas , SM/09440 | New | Providing and installation of Pumping Machinery and other electromechanical equipment at newly sunk T/W at Talda, Block- Sabang under Ground bored Mini Piped W/S Scheme Dist- Paschim Medinipur under MMD,P.H.E.Dte.(W/O No. 122/W/MMD dt. 24-01-2022)(T.No. 1206 of 21-22) | BP-2022-23-36 | 12/08/2022 | 0 | S.S.GHORAI | 0.44 | 0 | 0 | 0
457 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas , SM/09440 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Talda, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 122/W/MMD | 24/01/2022 | 120 | S.S.GHORAI | 6.55 | 0 | 0 | 0
458 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas , SM/09440 | New | onstruction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Talda, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | BP-2022-23-407 | 01/02/2023 | 0 | MIDNAPUR PIPE CONCERN | 18.52 | 0 | 0 | 0
459 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas , SM/09440 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Talda, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 2181/MD | 17/12/2021 | 150 | MIDNAPUR PIPE CONCERN | 32.63 | 0 | 0 | 10
460 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas , SM/09441 | New | Service connection charge of WBSEDCL at Dantarda, Batitaki, Chandkuri | 2003774979/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
461 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas , SM/09441 | New | Service connection charge of WBSEDCL at Nowgan, Sabang | 2003774953/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
462 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas , SM/09441 | New | Service connection charge of WBSEDCL at Now gan, Sabang | 2003774945/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
463 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas , SM/09441 | New | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for mouza (i) Dantardabatitaki, (ii) Fate Chak & (iii) Haripura of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | 1277/MD | 05/08/2021 | 10 | GOBINDA MAITY | 4.36 | 0 | 0 | 0
464 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas , SM/09441 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Dantardabatitaki, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 120/W/MMD | 24/01/2022 | 120 | ECO ENTERPRISE | 6.51 | 0 | 0 | 0
465 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas , SM/09441 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Dantardabatitaki water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2505/W/MMD | 30/11/2021 | 4 | SUJOY RANJAN BHOWMICK | 4.47 | 0 | 0 | 100
466 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas , SM/09441 | New | Quotation for service connection charges of WBSEDCL at Nilot Bhemua | 2003855203/Quot/03 | 10/03/2022 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
467 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas , SM/09441 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | BP-2021-22-505 | 22/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.82 | 0 | 0 | 0
468 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas , SM/09441 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Dantardabatitaki, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 2178/MD | 17/12/2021 | 150 | MIDNAPUR PIPE CONCERN | 26.09 | 0 | 0 | 90
469 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dhaneswarpur PWSS Block-Pingla District Paschim Medinipur , SM/08210 | Retrofitting | Trial run of distribution system & rising main (CI/DI/HDPE/UPVC) with all related structure i.e.OHR etc. Dhaneswarpur and its adjoining mouza W/S Scheme within Pingla Block under Midnapore Division P.H.E. Dte. ( for 120 days). | 112/AE/KSD | 09/03/2022 | 4 | GOBINDA MAITY | 1.14 | 0 | 0 | 0
470 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dhaneswarpur PWSS Block-Pingla District Paschim Medinipur , SM/08210 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dhaneswarpur PWSS, Block - Pingla in the district of Paschim Medinipur. | 416/MD | 26/02/2021 | 30 | GOBINDA MAITY | 71.49 | 70.09 | 98.05 | 100
471 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/08676 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Paschim Pathri PWSS to accommodate FHTC under JJM under Kharagpur-I block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 2169/MD | 17/12/2021 | 60 | MAITY ENTERPRISE | 48.5 | 0 | 0 | 0
472 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/08676 | Retrofitting | Construction of Valve Chamber and Supplying, Fitting, Fixing G.I. Pipe including allied works at Paschim Pathri PWSS within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 519/AE/KSD | 18/08/2022 | 30 | MAITY ENTERPRISE | 1.66 | 0 | 0 | 0
473 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/08676 | Retrofitting | Sinking of additional 150 X 100 mm dia. X 170 Mtr. Depth Rig bored Tube well for Paschim Pathri W/S Scheme under Kharagpur-I Dev. Block within Kharagpur Sub-Division, PHE Dte. | 2413/MD | 25/11/2022 | 7 | FIROJ KHAN | 5.47 | 0 | 0 | 100
474 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/08676 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Paschim Pathri, Block - Kharagpur-I) to be Retrofitting under Midnapore Division P.H.E. Dte. | 63/MD | 11/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.22 | 2.16 | 100 | 0
475 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Satkui PWSS , SM/08219 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Satkui PWSS, Block - Kharagpur-I in the district of Paschim Medinipur. | 415/MD | 26/02/2021 | 30 | DULAL CHANDRA DAS | 61.89 | 0 | 0 | 0
476 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Satkui PWSS , SM/08219 | Retrofitting | Restoration of distribution pipe line of Satkui and its adjoining Mouza Water Supply Scheme Kharagpur-I Block in the district of Paschim Medinipur. (PART-III) | 106/AE/KSD | 09/03/2022 | 30 | A-PLUS | 4.79 | 0 | 0 | 0
477 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Satkui PWSS , SM/08219 | Retrofitting | Restoration of distribution pipe line of Satkui and its adjoining Mouza Water Supply Scheme Kharagpur-I Block in the district of Paschim Medinipur. (PART-I) | 469/AE/KSD | 16/11/2021 | 30 | M/S. GEO | 4.81 | 0 | 0 | 100
478 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Satkui PWSS , SM/08219 | Retrofitting | Restoration of distribution pipe line of Satkui and its adjoining Mouza Water Supply Scheme Kharagpur-I Block in the district of Paschim Medinipur. (PART-II) | 470/AE/KSD | 16/11/2021 | 30 | M/S. GEO | 4.83 | 0 | 0 | 0
479 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Satkui PWSS , SM/08219 | Retrofitting | Restoration of distribution pipe line of Satkui and its adjoining Mouza Water Supply Scheme Kharagpur-I Block in the district of Paschim Medinipur. (PART-IV) | 107/AE/KSD | 09/03/2022 | 30 | M/S. GEO | 4.61 | 0 | 0 | 0
480 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Preparation of D.P.R. (Consultancy work) in connection with the Proposed Mini Pipe W/S Scheme for Chaulkuri mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | 1334/MD | 18/08/2021 | 10 | GOBINDA MAITY | 3.06 | 0 | 0 | 0
481 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Chaulkuri water supply scheme, tube well no. 3 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2508/W/MMD | 30/11/2021 | 4 | SUJOY RANJAN BHOWMICK | 4.47 | 0 | 0 | 100
482 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Chaulkuri water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2504/W/MMD | 30/11/2021 | 4 | P.K.ENGINEERING | 4.47 | 0 | 0 | 100
483 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Chaulkuri water supply scheme, tube well no. 4 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2510/W/MMD | 30/11/2021 | 4 | SUJOY RANJAN BHOWMICK | 4.47 | 0 | 0 | 100
484 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Chaulkuri water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2506/W/MMD | 30/11/2021 | 4 | P.K.ENGINEERING | 4.47 | 0 | 0 | 100
485 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | BP-2021-22-505 | 22/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 15.57 | 0 | 0 | 0
486 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Quotation bill of WBSEDCL for application no 2003798482/2003798478/2003798131/2003798158/2003798182/2003798165 | BP-2021-22-72 | 07/03/2022 | 0 | WBSEDCL | 0.76 | 0 | 0 | 0
487 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | For payment of liabilities. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.54 | 0 | 0 | 0
488 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -IV at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. (W/O-152/W/MMD, DT.-31/01/2022) | BP-2021-22-119 | 17/03/2022 | 0 | JAGANNATH ENTERPRISE | 3.87 | 0 | 0 | 0
489 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 149/W/MMD | 31/01/2022 | 120 | BUSR ENGINEERING | 6.54 | 0 | 0 | 0
490 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -III at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 151/W/MMD | 31/01/2022 | 120 | MANORANJAN DEY | 6.55 | 0 | 0 | 0
491 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -II at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 150/W/MMD | 31/01/2022 | 120 | KAMAKSHYA ENTERPRISE | 6.59 | 0 | 0 | 0
492 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -IV at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 152/W/MMD | 31/01/2022 | 120 | JAGANNATH ENTERPRISE | 6.51 | 0 | 0 | 0
493 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chaulkuri (Zone-IV), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 524/MD | 21/03/2022 | 150 | BISWAJIT BAG | 38.24 | 0 | 0 | 0
494 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Material Requisition To Resource Division | 2126/MD | 14/12/2021 | 0 | Resource Division | 5.54 | 0 | 0 | 0
495 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chaulkuri (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 521/MD | 21/03/2022 | 150 | USHA CONCERN | 44.75 | 0 | 0 | 92
496 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. |  | 31/01/2023 | 0 | BADAL CHANDRA BERA | 0.63 | 0 | 0 | 0
497 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chaulkuri (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 522/MD | 21/03/2022 | 150 | BISWAJIT BAG | 42.43 | 0 | 0 | 100
498 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chaulkuri (Zone-III), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 523/MD | 21/03/2022 | 150 | BISWAJIT BAG | 49.24 | 0 | 0 | 100
499 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur , SM/09681 | New | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 0 | 100
500 | PASCHIM MEDINIPUR | Midnapore Division | Amjor Piped Water Supply Scheme. , SM/10318 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations (250 CuM) under Amjor & its adjoining mouzas W/S scheme within Garhbeta-II block in Paschim Medinipur District through Jadavpur University. | 1285/MD | 27/06/2022 | 7 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0 | 0
501 | PASCHIM MEDINIPUR | Midnapore Division | Amjor Piped Water Supply Scheme. , SM/10318 | New | Material Requisition To Resource Division | 245/MD | 18/01/2023 | 0 | Resource Division | 17.74 | 0 | 0 | 0
502 | PASCHIM MEDINIPUR | Midnapore Division | Amjor Piped Water Supply Scheme. , SM/10318 | New | Material Requisition To Resource Division | 134/MD | 11/01/2023 | 0 | Resource Division | 8.33 | 0 | 0 | 0
503 | PASCHIM MEDINIPUR | Midnapore Mechanical | Amjor Piped Water Supply Scheme. , SM/10318 | New | Electric quotation for Amjore PWSS Tube Well-II WS Scheme (Ref. ID 203928706) | Bp-2022-23-148 | 24/03/2023 | 0 | WBSEDCL | 0.36 | 0 | 0 | 0
504 | PASCHIM MEDINIPUR | Midnapore Mechanical | Amjor Piped Water Supply Scheme. , SM/10318 | New | Electric quotation for Amjore PWSS Tube Well-I WS Scheme (Ref. ID 203928705) | BP-2022-23-149 | 24/03/2023 | 0 | WBSEDCL | 0.36 | 0 | 0 | 0
505 | PASCHIM MEDINIPUR | Midnapore Division | Amjor Piped Water Supply Scheme. , SM/10318 | New | Laying distribution pipe line, Construction of Pump House (3.6 mtr X 3.00 mtr.) & Boundary wall including Sinking of 250 X 200 mm dia. X 200 Mtr. depth deep Tube well under JJM with allied work for AMJOR and its adjoining mouzas W/S Scheme in Garhbeta -II Block including supply of all labour & materials within Midnapore Sub-Division under Midnapore Division, PHE Dte. (Part-A) | 2674/MD | 30/12/2022 | 60 | ASHIM KUMAR DEY | 169.73 | 0 | 0 | 10
506 | PASCHIM MEDINIPUR | Midnapore Division | Amjor Piped Water Supply Scheme. , SM/10318 | New | Continuation Work order for Hire charges for hiring of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 05 (Five) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer ,Midnapore Sadar Sub-Division under Midnapur Division PHE Dte.(Preferably it would be used only the 'Jal Swapna 'Program inaugurated by Honorable C.M) upto 15.07.2023 | 865/AE/MSSD | 10/02/2023 | 150 | SANJIT SINHA | 0.84 | 0 | 0 | 80
507 | PASCHIM MEDINIPUR | Midnapore Division | Amjor Piped Water Supply Scheme. , SM/10318 | New | Construction of R.C.C. Over Head Reservoir of capacity 250 Cum and staging height 20.00 mtr., Pump House (5.40 mtr X 3.60 mtr), Boundary wall including Sinking of 250 X 200 mm dia. X 200 Mtr. depth deep Tube well & FHTC under JJM with allied work for AMJOR & its adjoining mouzas W/S Scheme in Garhbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Part-B) | 1878/MD | 09/09/2022 | 180 | ASHIM KUMAR DEY | 152.15 | 0 | 0 | 30
508 | PASCHIM MEDINIPUR | Midnapore Division | Amjor Piped Water Supply Scheme. , SM/10318 | New | Laying of Rising main & interconnection pipeline for Amjor & its adjoining mouzas PWSS, Block - Garhbeta-II, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Length - 675.00 Mtr.) | 2449/MD | 08/08/2024 | 45 | ASHIM KUMAR DEY | 5.41 | 0 | 0 | 50
509 | PASCHIM MEDINIPUR | Midnapore Mechanical | Amjor Piped Water Supply Scheme. , SM/10318 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Amjor Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | 2385/W/MMD | 31/12/2022 | 180 | ABHIJIT BASU | 22.88 | 0 | 0 | 100
510 | PASCHIM MEDINIPUR | Midnapore Division | Amjor Piped Water Supply Scheme. , SM/10318 | New | Continuation work order for Hire charges for hiring of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 06 ( Six) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer ,Midnapore Sadar Sub-Division under Midnapur Division PHE Dte. (period from 01.01.2023 to 30.06.2023) | 762/AE/MSSD | 30/12/2022 | 182 | M/S. ZAMAN ENTERPRISE | 1.01 | 0 | 0 | 50
511 | PASCHIM MEDINIPUR | Midnapore Division | Amjor Piped Water Supply Scheme. , SM/10318 | New | Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre, Health Care Institution etc. under Midnapore Division PHE Dte. Period from (15.07.2023 to 14.07.2024) | 403/AE/MSSD | 14/07/2023 | 366 | PULLOCK KUMAR GHOSH | 4.65 | 0 | 0 | 60
512 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandipur PWSS under Daspur-I Block in Paschim Medinipur District , SM/09702 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandipur PWSS under Daspur-I Block in Paschim Medinipur District. | 2004/MD | 01/12/2021 | 45 | M/S. EL-CON | 79.5 | 0 | 0 | 0
513 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10778 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Kapasda PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1666/MD | 28/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.25 | 0 | 0 | 100
514 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10778 | Augmentation | Supply and delivery at site Submersible pumping machinery and other electro-mechanical equipment in connection with Rejuvenation of Ground water based piped water supply scheme for PH No III of Kapasda Part to accommodate FHTC under Sabang Block in Paschim Medinipur District under M.M.D,.PH.E. DTE. TSM009952 | 600/MMSD-I | 05/06/2023 | 15 | DEBKUMAR BASU | 5.76 | 0 | 0 | 0
515 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10778 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0 | 0 | 25
516 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10778 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0 | 0 | 100
517 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10778 | Augmentation | Quotation for New Service connection charges of Additional TW IV of Kapasda WS Scheme (Ref. ID - 203959882) | BP-2023-24-32 | 04/05/2023 | 0 | WBSEDCL | 2.08 | 0 | 0 | 0
518 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10778 | Augmentation | Quotation for New Service connection at Additional TW - III of Kapasda Water Supply Scheme (Ref. Id-203959877) | BP-2023-24-39 | 04/05/2023 | 0 | WBSEDCL | 4.45 | 0 | 0 | 0
519 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10778 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | 1733/MD | 23/08/2022 | 60 | SUNIL DULE | 71.9 | 0 | 0 | 100
520 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10778 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 2307/W/MMD | 29/12/2022 | 180 | DEBKUMAR BASU | 10.78 | 0 | 0 | 100
521 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10778 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments Rejuvenation of Ground water based piped water supply scheme for P/H-IV of Kapasda (Part) to accommodate FHTC under JJM under Sabang Block in Paschim Medinipur District under MMD PHE Dte. | 1345/W/MMD | 24/05/2023 | 180 | M/S EMMESS | 11.88 | 0 | 0 | 100
522 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Keshpur (Block-Keshpur) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1644/MD | 22/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.04 | 0 | 0 | 0
523 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Material Requisition To Resource Division | 2473/MD | 06/12/2022 | 0 | Resource Division | 41.87 | 0 | 0 | 0
524 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Material Requisition To Resource Division | 2322/MD | 17/11/2022 | 0 | Resource Division | 23.96 | 0 | 0 | 0
525 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Keshpur, Block - Keshpur) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. | BP-2021-22-397 | 22/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.65 | 0 | 0 | 0
526 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Keshpur W/S Scheme with in Keshpur Block under Midnapore Division, P.H.E. Dte. | 121/MD | 10/01/2023 | 30 | M/S. A.R. ENTERPRISE. | 41.34 | 0 | 0 | 70
527 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | PWD road challan | BP-2022-23-704 | 23/02/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 90 | 0 | 0 | 0
528 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Restoration of damage shoulder & flank etc to the different roads under Midnapore Highway Division (Damage caused during laying pipe line by public Health Engineering Department. |  | 19/02/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 138 | 0 | 0 | 0
529 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Electric quotation bill for Tw No-III of Keshpur water supply scheme.( Consumer ID-204052921.) | BP-2023-24-232 | 07/09/2023 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
530 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Electric quotation bill for Tw No- IV of Keshpur water supply scheme.(Conumer ID-204057049) | BP-2023-24-230 | 07/09/2023 | 0 | WBSEDCL | 2.76 | 0 | 0 | 0
531 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Electric quotation bill for Tw no-V of Keshpur water supply scheme.(Consumer ID-204051457) | BP-2023-24-231 | 07/09/2023 | 0 | WBSEDCL | 2.67 | 0 | 0 | 0
532 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 550 Cum and staging height 20.00 mtr. with allied work for Augmentation of Keshpur and its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 1722/MD | 22/08/2022 | 1269 | M/S. A.R. ENTERPRISE. | 605.9 | 0 | 0 | 80
533 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | 2296/W/MMD | 29/12/2022 | 180 | P.K.ENGINEERING | 22.88 | 0 | 0 | 20
534 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Additional distribution pipe line under JJM with allied works for Augmentation of Keshpur & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 5105/MD | 31/10/2023 | 60 | M/S. A.R. ENTERPRISE | 52.81 | 0 | 0 | 80
535 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 1685/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.29 | 0 | 0 | 100
536 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Fuel for Inspection Vehicle of covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission Program. [w.e.f. 01-01-2024 to 29-02-2024] | 1698/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.83 | 0 | 0 | 100
537 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Additional quotation for effective new service connection at KESHPUR(Near Auditorium) in modified route. ( Augmentation of Keshpur PWSS) | BP-2023-24-480 | 27/12/2023 | 0 | WBSEDCL | 2.96 | 0 | 0 | 0
538 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Electric Quotation Bill. |  | 15/05/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 1.84 | 0 | 0 | 0
539 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Keshpur W/S Scheme with in Keshpur Block under Midnapore Division, P.H.E. Dte. | BP-2023-24-514 | 20/12/2023 | 0 | M/S. A.R. ENTERPRISE | 1.84 | 0 | 0 | 0
540 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | ELECRTIC QUOTATION BILL FOR TW NO-IV OF KESHPUR PWSS. (Ref Consumer ID-204189500) |  | 15/01/2024 | 0 | WBSEDCL | 2.76 | 0 | 0 | 0
541 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0 | 0 | 50
542 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. , SM/09979 | Augmentation | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | 842/MMSD-I | 11/06/2025 | 243 | M/S BIKASH DE | 3.66 | 0 | 0 | 0
543 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10731 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Khasbazar PWSS within Debra Block under Midnapore Division, P.H.E. Dte. | 1667/MD | 28/09/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 2.28 | 0 | 0 | 100
544 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10731 | Augmentation | Electric quotation for KHASBAZAR Water Supply Scheme T/W-(Ref. ID - 204024556) | BP-2023-24-288 | 31/08/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 4.53 | 0 | 0 | 0
545 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10731 | Augmentation | Rejuvenation of Ground Water Based Water Supply Scheme of Khasbazar (Part) to accommodate FHTC under JJM within Debra Dev. Block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. Dist. Paschim Medinipur. | 1484/MD | 26/07/2022 | 60 | SHAKEEL KHAN | 57.44 | 0 | 0 | 100
546 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10731 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 875/W/MMD | 27/03/2023 | 180 | RADHARANI ENTERPRISE | 5.98 | 0 | 0 | 100
547 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10731 | Augmentation | Cleaning the Chokage of pipe in the existing line at Khasbazar PWSS under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | 3405/MD | 25/11/2024 | 21 | SUBRATA DAS | 4.53 | 0 | 0 | 100
548 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bural (Zone-II) PWSS , SM/06919 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bural (Zone-II) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1466/MD | 26/11/2020 | 1887 | BANERJEE CONSTRUCTION | 97 | 46.9 | 52.47 | 100
549 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Chandkuri PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1662/MD | 28/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.33 | 0 | 0 | 100
550 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | Restoration of pipe line damaged due to construction of concrete road at Kholageria village & excess length of pipe in connection with FHTC work at Chandkuri (Zone I) W/S Scheme at Sabang Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | 1067/MD | 03/06/2022 | 21 | DULAL CHANDRA DAS | 19.68 | 0 | 0 | 80
551 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | Restoration of pipe line damaged due to construction of road at Chandkuri market & excess pipeline in connection with FHTC work at Chandkuri (Zone II) W/S Scheme at Sabang Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | 1068/MD | 03/06/2022 | 21 | DULAL CHANDRA DAS | 24.23 | 0 | 0 | 80
552 | PASCHIM MEDINIPUR | Central Drilling | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 170 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHANDKURI W/S SCH (Z-II), PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | 1778/CDD | 02/01/2023 | 30 | MENAKA ENTERPRISE | 10.15 | 0 | 0 | 0
553 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0 | 0 | 25
554 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0 | 0 | 100
555 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | Replacement and upgradation work of Voltage Stabilizer for Tube well No. III of Chandkuri Zone I Water Supply Scheme Block Sabang under MMD, PHE Dte. Dist.- Paschim Medinipur. | 1226/MMSD-I | 03/10/2023 | 30 | BALAJI CONSTRUCTION | 3.6 | 0 | 0 | 100
556 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | Service Connection charges of WBSEDCL for T/W-III of Zone-I of Chandkuri W/S Scheme (Consumer No. 2004156096) | BP-2022-23-93 | 10/01/2023 | 0 | WBSEDCL | 2.2 | 0 | 0 | 0
557 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | Service Connection charges of WBSEDCL for Additional T/W-III of Zone-II of Chandkuri W/S Scheme (Consumer No. 2004156140) | BP-2022-23-92 | 04/01/2023 | 0 | WBSEDCL | 2.41 | 0 | 0 | 0
558 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Zone-I) (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | 1671/MD | 12/08/2022 | 45 | DULAL CHANDRA DAS | 44.9 | 0 | 0 | 80
559 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Zone-II) (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | 1672/MD | 12/08/2022 | 45 | DULAL CHANDRA DAS | 50.82 | 0 | 0 | 100
560 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Additional Tube Well-III, Zone-I of Chandkuri to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | 1349/W/MMD | 24/05/2023 | 180 | M/S EMMESS | 11.88 | 0 | 0 | 100
561 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10821 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 2309/W/MMD | 29/12/2022 | 180 | BALAJI CONSTRUCTION | 10.79 | 0 | 0 | 100
562 | PASCHIM MEDINIPUR | Midnapore Division | Sabra Piped Water Supply Scheme. , SM/11460 | New | Continuation Work Order for the work of Laying Balance Distribution System to accommodate FHTC of Proposed Pipe Water Supply Scheme for Sabra & its adjoining Mouzas, Block: - Dantan-II, District: - Paschim Midnapore. (Total Length = 15,893.00 Mtr.) | 676/MD | 02/03/2023 | 60 | GOBINDA MAITY | 78.34 | 0 | 0 | 0
563 | PASCHIM MEDINIPUR | Midnapore Division | Sabra Piped Water Supply Scheme. , SM/11460 | New | Material Requisition To Resource Division | 336/MD | 31/01/2023 | 0 | Resource Division | 84.48 | 0 | 0 | 0
564 | PASCHIM MEDINIPUR | Midnapore Division | Sabra Piped Water Supply Scheme. , SM/11460 | New | Material Requisition To Resource Division | 1285/MD | 28/04/2023 | 0 | Resource Division | 22.66 | 0 | 0 | 0
565 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sabra Piped Water Supply Scheme. , SM/11460 | New | Electric Quotiaton for New S.C. Sabra Water Supply Scheme PH-III (Ref. ID-203964024) | BP-2023-24-12 | 27/04/2023 | 0 | WBSEDCL | 0.58 | 0 | 0 | 0
566 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sabra Piped Water Supply Scheme. , SM/11460 | New | Electric Quotiaton for New S.C (Infra. Cost.). Sabra Water Supply Scheme PH-III (Ref. ID-860267635) | BP-2023-24-13 | 27/04/2023 | 0 | WBSEDCL | 3.51 | 0 | 0 | 0
567 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sabra Piped Water Supply Scheme. , SM/11460 | New | Extra work due to way leave at Sabra T.W.No-III | BP-2023-24-131 | 19/07/2023 | 0 | WBSEDCL | 0.95 | 0 | 0 | 0
568 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sabra Piped Water Supply Scheme. , SM/11460 | New | Electric Quotiaton for New S.C.Sabra Water Supply Scheme PH-II (Ref. ID-203964023) | BP-2023-24-10 | 27/04/2023 | 0 | WBSEDCL | 0.58 | 0 | 0 | 0
569 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sabra Piped Water Supply Scheme. , SM/11460 | New | Electric Quotiaton for New S.C. Sabra Water Supply Scheme PH-I (Ref. ID-203964025) | BP-2023-24-8 | 27/04/2023 | 0 | WBSEDCL | 0.58 | 0 | 0 | 0
570 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sabra Piped Water Supply Scheme. , SM/11460 | New | Electric Quotiaton for New S.C (Infra. Cost.). Sabra Water Supply Scheme PH-II (Ref. ID-860267634) | BP-2023-24-11 | 27/04/2023 | 0 | WBSEDCL | 2.23 | 0 | 0 | 0
571 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sabra Piped Water Supply Scheme. , SM/11460 | New | Electric Quotiaton for New S.C (Infra. Cost.). Sabra Water Supply Scheme PH-I (Ref. ID-860267633) | BP-2023-24-9 | 27/04/2023 | 0 | WBSEDCL | 2.19 | 0 | 0 | 0
572 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sabra Piped Water Supply Scheme. , SM/11460 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sabra Piped Water Supply Scheme.under JJM Program under MMD PHE Dte. | 1157/W/MMD | 17/04/2023 | 180 | PS & ASSOCIATES | 27.3 | 0 | 0 | 60
573 | PASCHIM MEDINIPUR | Midnapore Division | Sabra Piped Water Supply Scheme. , SM/11460 | New | Laying of Rising Main including interconnection for Sabra and its adjoining mouzas Water Supply Scheme within Dantan-II Block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | 139/MD | 18/01/2024 | 30 | GOBINDA MAITY | 8.07 | 0 | 0 | 0
574 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sabra Piped Water Supply Scheme. , SM/11460 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SABRA AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 1104/W/MMD | 05/04/2023 | 180 | P.K.ENGINEERING | 27.37 | 0 | 0 | 100
575 | PASCHIM MEDINIPUR | Midnapore Division | BHAUDI AND ADJOINING MOUJAS PWSS , SM/13070 | New | Material Requisition To Resource Division | 1259/MD | 28/04/2023 | 0 | Resource Division | 23.52 | 0 | 0 | 0
576 | PASCHIM MEDINIPUR | Central Drilling | BHAUDI AND ADJOINING MOUJAS PWSS , SM/13070 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
577 | PASCHIM MEDINIPUR | Midnapore Division | AMJOR AND ADJOINING MOUJAS PWSS , SM/13707 | New | Hire charges of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 12 ( Twelve) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Midnapore Sadar Sub-Division PHE Dte. (Preferably it would be used only for the JJM Programme for Period of 01 year). | 487/AE/MSSD | 08/08/2023 | 366 | SANJIT SINHA | 1.91 | 0 | 0 | 0
578 | PASCHIM MEDINIPUR | Midnapore Division | AMJOR AND ADJOINING MOUJAS PWSS , SM/13707 | New | Hire charges of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 12 ( Twelve) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Midnapore Sadar Sub-Division under Midnapur Division PHE Dte. (Period From 15.07.2023 to 14.07.2024) Note :- The vehicle will normally engaged on the all working days ,including all exigency duty and normal disaster. The working days might be enhanced as per additional portfolio entrusted to the dedicated officer . no protest by the vehicle owner will be entertained. the vehicle may be called for (24 x 7) in case of any exigency like Covid19, natural cyclone etc. Fuel-HSD=1Litre/12KM Fuel-Mobil-1Litre/500KM | 404/AE/MSSD | 14/07/2023 | 366 | M/S. ZAMAN ENTERPRISE | 1.79 | 0 | 0 | 0
579 | PASCHIM MEDINIPUR | Central Drilling | AMJOR AND ADJOINING MOUJAS PWSS , SM/13707 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
580 | PASCHIM MEDINIPUR | Midnapore Division | ANDHAR NAYAN AND ADJOINING MOUJAS PWSS , SM/13635 | New | Material Requisition To Resource Division | 1212/MD | 27/04/2023 | 0 | Resource Division | 53.41 | 0 | 0 | 0
581 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | ANDHAR NAYAN AND ADJOINING MOUJAS PWSS , SM/13635 | New | Quotation for new service connection at Andharnayan T/W-II water supply scheme. | 41/JMD | 29/04/2024 | 0 | WBSEDCL | 4.78 | 0 | 0 | 0
582 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | ANDHAR NAYAN AND ADJOINING MOUJAS PWSS , SM/13635 | New | Quotation for new service connection at Anadarnyan T/W-I water supply scheme. | 40/JMD | 29/04/2024 | 0 | WBSEDCL | 5.17 | 0 | 0 | 0
583 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | ANDHAR NAYAN AND ADJOINING MOUJAS PWSS , SM/13635 | New | Quotation for new service connection at Andharnayan T/W-III water supply scheme. | 39/JMD | 29/04/2024 | 0 | WBSEDCL | 3.22 | 0 | 0 | 0
584 | PASCHIM MEDINIPUR | Central Drilling | ANDHAR NAYAN AND ADJOINING MOUJAS PWSS , SM/13635 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
585 | PASCHIM MEDINIPUR | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS , SM/13001 | New | Material Requisition To Resource Division | 1358/MD | 02/05/2023 | 0 | Resource Division | 29.51 | 0 | 0 | 0
586 | PASCHIM MEDINIPUR | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS , SM/13001 | New | Laying distribution pipe line & Accommodate FHTC (250 Nos.) under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 2486/MD | 17/07/2023 | 659 | GOUTAM RAY | 47.26 | 0 | 0 | 70
587 | PASCHIM MEDINIPUR | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS , SM/13001 | New | Sinking of Two nos. 250 X 150 mm dia. X 160 mtr. depth deep tube well by direct rotary method under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 2512/MD | 18/07/2023 | 21 | FIROJ KHAN | 16.16 | 0 | 0 | 100
588 | PASCHIM MEDINIPUR | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS , SM/13001 | New | Laying Rising main, Laying distribution pipe line, & Accommodate FHTC (450 Nos.) including 2 years O & M under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | 3243/MD | 11/09/2023 | 60 | ASHIM KUMAR DEY | 185.94 | 0 | 0 | 10
589 | PASCHIM MEDINIPUR | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS , SM/13001 | New | Laying distribution pipe line & Accommodate FHTC (250 Nos.) under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 3097/MD | 25/08/2023 | 60 | PULLOCK KUMAR GHOSH | 46.42 | 0 | 0 | 10
590 | PASCHIM MEDINIPUR | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS , SM/13001 | New | Construction Pump House, Boundary wall & Accommodate FHTC (350 Nos.) under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | 3242/MD | 11/09/2023 | 842 | MIDNAPUR PIPE CONCERN | 53.54 | 0 | 0 | 51
591 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KARNAGAR AND ADJOINING MAOUJAS PWSS , SM/13001 | New | New service connection charges for Karnagarg, tw-I w/s scheme | 76/JMD | 12/02/2024 | 0 | WBSEDCL | 3.23 | 0 | 0 | 0
592 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KARNAGAR AND ADJOINING MAOUJAS PWSS , SM/13001 | New | New service connection charges for Karnagarh, tw-II w/s scheme | 77/JMD | 14/02/2024 | 0 | WBSEDCL | 2.99 | 0 | 0 | 0
593 | PASCHIM MEDINIPUR | Central Drilling | KARNAGAR AND ADJOINING MAOUJAS PWSS , SM/13001 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
594 | PASCHIM MEDINIPUR | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS , SM/13001 | New | Construction of 250 CuM OHR (Intez type with solid raft) & Accommodate FHTC (435 Nos.) under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-F] | 3159/MD | 04/10/2024 | 540 | D M CONSTRUCTION | 107.46 | 0 | 0 | 0
595 | PASCHIM MEDINIPUR | Midnapore Division | BAKALSABAKARAM PWSS , SM/12199 | New | Material Requisition To Resource Division | 1411 | 04/05/2023 | 0 | Resource Division | 35.33 | 0 | 0 | 0
596 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAKALSABAKARAM PWSS , SM/12199 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAKALSABAKARAM PWSS Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | 2301/W/MMD | 29/12/2022 | 972 | ECO ENTERPRISE | 23.01 | 0 | 0 | 50
597 | PASCHIM MEDINIPUR | Midnapore Division | BAKALSABAKARAM PWSS , SM/12199 | New | Construction of 200 Cum & 300 Cum Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,806 Nos.) including 2 years operation & maintenance For Bakalsabakram, Bhagabanpur and Chak Prayag Pipe water supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5382/MD | 04/12/2023 | 574 | M/S. KAMAK ENGINEERS AND CO. | 1277.59 | 0 | 0 | 50
598 | PASCHIM MEDINIPUR | Midnapore Division | BARAGARH PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR , SM/12201 | New | Material Requisition To Resource Division | 1159/MD | 25/04/2023 | 0 | Resource Division | 24.02 | 0 | 0 | 0
599 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARAGARH PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR , SM/12201 | New | Electrict quotation bill for TW-I of Baraghar pwss (Ref Consumar ID-204444966),Application No-2004963063,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | C112429694917 | 25/11/2024 | 0 | WBSEDCL | 5.52 | 0 | 0 | 0
600 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARAGARH PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR , SM/12201 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Baraghar PWSS, BLOCK - DEBRA Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | 2303/W/MMD | 29/12/2022 | 855 | DEBJYOTI BASU | 22.79 | 0 | 0 | 40
601 | PASCHIM MEDINIPUR | Midnapore Division | BARAGARH PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR , SM/12201 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 0 | 25
602 | PASCHIM MEDINIPUR | Midnapore Division | KANTAL AND ADJOINING MOUJAS PWSS , SM/13060 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
603 | PASCHIM MEDINIPUR | Midnapore Division | KANTAL AND ADJOINING MOUJAS PWSS , SM/13060 | New | Material Requisition To Resource Division | 1219/MD | 27/04/2023 | 0 | Resource Division | 26.64 | 0 | 0 | 0
604 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KANTAL AND ADJOINING MOUJAS PWSS , SM/13060 | New | New service connection for Kantal T/W- 1 water supply scheme | 51/JMD | 29/04/2024 | 0 | WBSEDCL | 12.47 | 0 | 0 | 0
605 | PASCHIM MEDINIPUR | Central Drilling | KANTAL AND ADJOINING MOUJAS PWSS , SM/13060 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
606 | PASCHIM MEDINIPUR | Midnapore Division | BANAMALIPUR AND ADJOINING MOUJAS PWSS , SM/13064 | New | Material Requisition To Resource Division | 1255/MD | 28/04/2023 | 0 | Resource Division | 20.96 | 0 | 0 | 0
607 | PASCHIM MEDINIPUR | Central Drilling | BANAMALIPUR AND ADJOINING MOUJAS PWSS , SM/13064 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
608 | PASCHIM MEDINIPUR | Midnapore Division | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS , SM/13076 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
609 | PASCHIM MEDINIPUR | Midnapore Division | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS , SM/13076 | New | Material Requisition To Resource Division | 1482 | 10/05/2023 | 0 | Resource Division | 36.86 | 0 | 0 | 0
610 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS , SM/13076 | New | Quotation for new power connection at Gobindapur PWSS TW - II Under Narayangarh Block Application No - 2004845772 , Ref ID - 204370310 | C092443180598 | 27/09/2024 | 0 | WBSEDCL | 4.92 | 0 | 0 | 0
611 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS , SM/13076 | New | Quotation for new power connection at Gobindapur PWSS TW - I Under Narayangarh Block Application No - 2004845774 , Ref ID - 204370304 | C092443178985 | 27/09/2024 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
612 | PASCHIM MEDINIPUR | Central Drilling | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS , SM/13076 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
613 | PASCHIM MEDINIPUR | Midnapore Division | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS , SM/13076 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
614 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS , SM/13076 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
615 | PASCHIM MEDINIPUR | Midnapore Division | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS , SM/13076 | New | Hiring of 1 (One) Motor Cab (Standard) commercial with Catalytic Converter attachment with Bharat Stage as per prevalent application standard compliant new/not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 06 (Six) months only having contract carriage permit for plying within West Bengal from the Regional Transport Authority for the use of the Assistant Engineer (H/Q), Midnapore Division, P.H.E. Dte. for the period of 05 (Five) months from 01.01.2025 to 31.05.2025. | 3838/AE/HQ/MD | 27/12/2024 | 151 | NAFISA ENTERPRISE | 0.72 | 0 | 0 | 0
616 | PASCHIM MEDINIPUR | Midnapore Division | GAMA AND ADJOINING MOUJAS PWSS , SM/13083 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
617 | PASCHIM MEDINIPUR | Midnapore Division | GAMA AND ADJOINING MOUJAS PWSS , SM/13083 | New | Material Requisition To Resource Division | 184/MD | 16/01/2023 | 0 | Resource Division | 14.27 | 0 | 0 | 0
618 | PASCHIM MEDINIPUR | Midnapore Division | GAMA AND ADJOINING MOUJAS PWSS , SM/13083 | New | Material Requisition To Resource Division | 3449/MD | 25/11/2024 | 0 | Resource Division | 12.04 | 0 | 0 | 0
619 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAMA AND ADJOINING MOUJAS PWSS , SM/13083 | New | Quotation for new power connection at gama PWSS T/W - I under Narayangarh block , application no - 2004739405 , ref no - 204309707 | BP-2024-25-232 | 04/06/2024 | 0 | WBSEDCL | 3.32 | 0 | 0 | 0
620 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAMA AND ADJOINING MOUJAS PWSS , SM/13083 | New | Quotation for new power connection at gama PWSS T/W - II under Narayangarh block , application no - 2004739453 , ref no - 204309708 | BP-2024-25-231 | 04/06/2024 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
621 | PASCHIM MEDINIPUR | Central Drilling | GAMA AND ADJOINING MOUJAS PWSS , SM/13083 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
622 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAMA AND ADJOINING MOUJAS PWSS , SM/13083 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
623 | PASCHIM MEDINIPUR | Midnapore Division | GAMA AND ADJOINING MOUJAS PWSS , SM/13083 | New | Continuation Work Order for "Hiring of 1 (One) Motor Cab (Standard) commercial with Catalytic Converter attachment with Bharat Stage as per prevalent application standard compliant new/not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 06 (Six) months only having contract carriage permit for plying within West Bengal from the Regional Transport Authority for the use of the Assistant Engineer (H/Q), Midnapore Division, P.H.E. Dte. for the period of 05 (Five) months from 01.06.2025 to 31.10.2025." | 1231/AE/HQ/MD | 27/05/2025 | 150 | NAFISA ENTERPRISE | 0.71 | 0 | 0 | 0
624 | PASCHIM MEDINIPUR | Midnapore Division | JALIMANDA AND IT'S ADJOINING MOUJAS PWSS , SM/13087 | New | Material Requisition To Resource Division | 1520/MD | 12/05/2023 | 0 | Resource Division | 29.35 | 0 | 0 | 0
625 | PASCHIM MEDINIPUR | Midnapore Mechanical | JALIMANDA AND IT'S ADJOINING MOUJAS PWSS , SM/13087 | New | Electrict quotation bill for TW-I of Jalimanda pwss (Ref Consumar ID-204444967),Application No-2004963152,Application Type-New Connection,Name of ccc-Balaichak ccc, block-Debra | C112429710144 | 25/11/2024 | 0 | WBSEDCL | 4.15 | 0 | 0 | 0
626 | PASCHIM MEDINIPUR | Midnapore Mechanical | JALIMANDA AND IT'S ADJOINING MOUJAS PWSS , SM/13087 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for JALIMANDA AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 576/W/MMD | 20/03/2023 | 926 | ABHIJIT MUKHERJEE | 25.24 | 0 | 0 | 46
627 | PASCHIM MEDINIPUR | Midnapore Division | JALIMANDA AND IT'S ADJOINING MOUJAS PWSS , SM/13087 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 0 | 25
628 | PASCHIM MEDINIPUR | Midnapore Division | MURAKATI AND ADJOINING MOUJAS PWSS , SM/14004 | New | Material Requisition To Resource Division | 1241/MD | 27/04/2023 | 0 | Resource Division | 24.53 | 0 | 0 | 0
629 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MURAKATI AND ADJOINING MOUJAS PWSS , SM/14004 | New | Payment for WBSEDCL new connection at MURAKATI 2 (SM/14004. MURAKATI AND ADJOINING MOUJAS PWSS ) | 170/JMD | 07/06/2024 | 0 | WBSEDCL | 4.23 | 0 | 0 | 0
630 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MURAKATI AND ADJOINING MOUJAS PWSS , SM/14004 | New | WBSEDCL new connection payment for Murakati t/w 1 | 56/JMD | 29/04/2024 | 0 | WBSEDCL | 8.25 | 0 | 0 | 0
631 | PASCHIM MEDINIPUR | Central Drilling | MURAKATI AND ADJOINING MOUJAS PWSS , SM/14004 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
632 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12825 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Gobardhanpur PWSS within Pingla Block under Midnapore Division, P.H.E. Dte. | 530/MD | 21/03/2022 | 10 | RISHAN ENGINEERING CONSULTANCY | 2.95 | 0 | 0 | 100
633 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12825 | Augmentation | Material Requisition To Resource Division | 93/MD | 10/01/2023 | 0 | Resource Division | 12.24 | 0 | 0 | 0
634 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12825 | Augmentation | Electric quotation bill for Tw no-III of Gobardhanpur water supply scheme.(Ref consumer ID-204049772) | BP-2023-24-274 | 12/10/2023 | 0 | WBSEDCL | 4.65 | 0 | 0 | 0
635 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12825 | Augmentation | Electric quotation bill for Tw No-IV of Gobardhanpur water supply scheme (Ref Consumer ID-204049773) | BP-2023-24-273 | 12/10/2023 | 0 | WBSEDCL | 2.71 | 0 | 0 | 0
636 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12825 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 478/W/MMD | 20/03/2023 | 721 | DIPALI CONSTRUCTION | 22.98 | 0 | 0 | 35
637 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12825 | Augmentation | Sinking of Tube well (2nd), Construction of Pump House & Laying rising main pipeline for Augmentation of Gobardhanpur PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 3572/MD | 06/12/2024 | 300 | ARNAB PATRA | 12.74 | 0 | 0 | 50
638 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12825 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall with allied work for Augmentation of Gobardhanpur & its adjoining mouzas W/S Scheme in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 2517/MD | 09/12/2022 | 1142 | DIPAK KUMAR BAKLY | 159.48 | 0 | 0 | 10
639 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12825 | Augmentation | Construction of 5.40 X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Augmentation of Gobardhanpur W/S Scheme in Pingla block within Kharagpur Sub-Division under Midnapore Division, PHE Dte. (Considering G.L. 1950 mm below Road Level) {Type-B}. | 706/MD | 12/03/2024 | 720 | CHANDAN YADAV | 7.21 | 0 | 0 | 50
640 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12825 | Augmentation | Construction of approach road (concrete road) for Augmentation of Gobardhanpur PWSS Head Work Site at Ratrapur in Pingla Block within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 348/MD | 30/01/2025 | 330 | M/S BAKLY CONSTRUCTION | 6.1 | 0 | 0 | 1
641 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12825 | Augmentation | Providing and installation of Submersible pumping machineries and other allied electromechanical works at Newly sunk Tube well (Relacement) at Pump House-2 under Gobardhanpur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist.:- Paschim Medinipur | 788/W/MMD | 24/02/2025 | 180 | M/S. SAJAHAN CHOWDHURY | 14.21 | 0 | 0 | 0
642 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. , SM/13046 | Augmentation | Constructing and fitting fixing MS ladder in diff. level and painting OHR of Palashi and its adjoining mouza water supply scheme within Debra Block under Midnapore Division, P.H.E. Dte. | 109/AE/KSD | 09/03/2022 | 30 | GOUTAM PARIA | 4.23 | 0 | 0 | 100
643 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. , SM/13046 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Palashi PWSS within Debra Block under Midnapore Division, P.H.E. Dte. | 517/MD | 17/03/2022 | 10 | GOBINDA MAITY | 2.81 | 0 | 0 | 100
644 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. , SM/13046 | Augmentation | Electric quotation for PALASHI Water Supply Scheme T/W-(Ref. ID - 204024556) | BP-2023-24-286 | 31/08/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.24 | 0 | 0 | 0
645 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. , SM/13046 | Augmentation | Continuation Work Order for the work of Additional Retrofitting to accommodate FHTC under JJM in Palashi Water Supply Scheme, Block: - Debra, District: - Paschim Medinipur within Midnapore Division, P.H.E. Dte. | 709/MD | 06/03/2023 | 45 | GOBINDA MAITY | 31.01 | 0 | 0 | 100
646 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. , SM/13046 | Augmentation | Continuation Work Order for Laying Balance Distribution Pipe line for Rejuvenation of Palashi and its adjoining mouzas Pipe Water Supply Scheme under Debra Block within Midnapore Division, P.H.E. Dte. (Total Length = 6,236.00 Mtr.) | 949/MD | 06/04/2023 | 45 | MASUM ALI KHAN | 28.34 | 0 | 0 | 100
647 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. , SM/13046 | Augmentation | Providing and Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring at Tube Well-III of Palashi Water Supply Scheme (Block- Debra) under MMD, PHE Dte., Dist. Paschim Medinipur. | 1851/W/MMD | 22/08/2023 | 180 | RELIABLE CONSTRUCTIONS | 12.83 | 0 | 0 | 100
648 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. , SM/13046 | Augmentation | New PHE connection at Tw No-III of Palashi PWSS. | BP-2023-24-543 | 11/01/2024 | 0 | WBSEDCL | 4.22 | 0 | 0 | 0
649 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. , SM/13046 | Augmentation | Retrofitting to accommodate FHTC under JJM in Palashi W/S Scheme, Block: - Debra, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1459/MD | 26/11/2020 | 1496 | GOBINDA MAITY | 86.73 | 0 | 0 | 100
650 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. , SM/13046 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall for Rejuvination of Palashi PWSS in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 118/MD | 10/01/2023 | 723 | MASUM ALI KHAN | 171.56 | 0 | 0 | 100
651 | PASCHIM MEDINIPUR | Midnapore Division | BELDA AND IT'S ADJOINING MOUJAS , SM/13048 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
652 | PASCHIM MEDINIPUR | Midnapore Division | BELDA AND IT'S ADJOINING MOUJAS , SM/13048 | New | Material Requisition To Resource Division | 1295/MD | 28/04/2023 | 0 | Resource Division | 26.26 | 0 | 0 | 0
653 | PASCHIM MEDINIPUR | Midnapore Mechanical | BELDA AND IT'S ADJOINING MOUJAS , SM/13048 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF BELDA PWSS. REF CONSUMER ID-204412272, APPLICATION NO-2004920291, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102455561727 | 30/10/2024 | 0 | WBSEDCL | 6.26 | 0 | 0 | 0
654 | PASCHIM MEDINIPUR | Central Drilling | BELDA AND IT'S ADJOINING MOUJAS , SM/13048 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
655 | PASCHIM MEDINIPUR | Midnapore Division | TRILOCHANPUR PWSS , SM/13049 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
656 | PASCHIM MEDINIPUR | Midnapore Division | TRILOCHANPUR PWSS , SM/13049 | New | Material Requisition To Resource Division | 537/MD | 21/02/2023 | 0 | Resource Division | 34.53 | 0 | 0 | 0
657 | PASCHIM MEDINIPUR | Midnapore Division | TRILOCHANPUR PWSS , SM/13049 | New | Sinking of Tube well, Laying of Rising main, Pump House, Boundary wall, Construction of 300 CuM OHR (Intze type with solid raft) & Accommodate FHTC (1942 Nos.) including 2 yrs. O & M under JJM with allied work for Trilochanpur PWSS in Debra block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | 824/MD | 15/03/2024 | 180 | ASHIM KUMAR DEY | 231.98 | 0 | 0 | 0
658 | PASCHIM MEDINIPUR | Midnapore Division | TRILOCHANPUR PWSS , SM/13049 | New | Laying Distribution pipe line under JJM with allied work for Trilochanpur PWSS in Debra block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | 1902/MD | 20/06/2024 | 90 | ASHIM KUMAR DEY | 308.72 | 0 | 0 | 0
659 | PASCHIM MEDINIPUR | Midnapore Mechanical | TRILOCHANPUR PWSS , SM/13049 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TRILOCHANPUR PWSS Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | 2299/W/MMD | 29/12/2022 | 180 | RITESH ENTERPRISE | 23.01 | 0 | 0 | 55
660 | PASCHIM MEDINIPUR | Midnapore Division | SHAKHA BAI AND ADJOINING MOUJAS PWSS , SM/13220 | New | Material Requisition To Resource Division | 1228/MD | 27/04/2023 | 0 | Resource Division | 26.92 | 0 | 0 | 0
661 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SHAKHA BAI AND ADJOINING MOUJAS PWSS , SM/13220 | New | Quotation for new service connection at Shakhabai T/W-II water supply scheme. | 44/JMD | 29/04/2024 | 0 | WBSEDCL | 4.18 | 0 | 0 | 0
662 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SHAKHA BAI AND ADJOINING MOUJAS PWSS , SM/13220 | New | New Service connection charges. | 196/JMD | 14/06/2024 | 0 | WBSEDCL | 10.32 | 0 | 0 | 0
663 | PASCHIM MEDINIPUR | Central Drilling | SHAKHA BAI AND ADJOINING MOUJAS PWSS , SM/13220 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
664 | PASCHIM MEDINIPUR | Midnapore Division | JHETA JAMBONI PIPED WATER SUPPLY SCHEME , SM/13806 | New | Material Requisition To Resource Division | 3367/MD | 25/11/2024 | 0 | Resource Division | 15.78 | 0 | 0 | 0
665 | PASCHIM MEDINIPUR | Midnapore Mechanical | JHETA JAMBONI PIPED WATER SUPPLY SCHEME , SM/13806 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF JHETAJAMBONI PWSS. REF CONSUMER ID-204383571, APPLICATION NO-2004868778, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | C082449438485 | 02/09/2024 | 0 | WBSEDCL | 6.32 | 0 | 0 | 0
666 | PASCHIM MEDINIPUR | Midnapore Mechanical | JHETA JAMBONI PIPED WATER SUPPLY SCHEME , SM/13806 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of JHETA JAMBONI PWSS. REF CONSUMER ID-204240654, APPLICATION NO-2004634470, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-849 | 14/03/2024 | 0 | WBSEDCL | 2.9 | 0 | 0 | 0
667 | PASCHIM MEDINIPUR | Midnapore Division | JHETA JAMBONI PIPED WATER SUPPLY SCHEME , SM/13806 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 0 | 75
668 | PASCHIM MEDINIPUR | Midnapore Division | JHETA JAMBONI PIPED WATER SUPPLY SCHEME , SM/13806 | New | Laying of rising main & interconnection for Jheta Jamboni & its adjoining mouzas PWSS, Block - Keshpur, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Length = 500 Mtr.). | 918/MD | 08/04/2025 | 45 | JULFIKAR ALI KHAN | 5.6 | 0 | 0 | 0
669 | PASCHIM MEDINIPUR | Midnapore Division | IRPALA Piped Water Supply Scheme. , SM/07386 | New | River Crossing below river bed by laying HDPE pipe with bed and bank anchoring arrangement at nodal point (NP: 63 to 64) of Irpala W/S Scheme within Ghatal Block under Ghatal Sub- Division of Midnapore Division, PHE Dte. (Length = 100.00 Mtr.) | 537/MD | 22/03/2022 | 21 | M/S. A.R. ENTERPRISE. | 11.39 | 0 | 0 | 100
670 | PASCHIM MEDINIPUR | Midnapore Mechanical | IRPALA Piped Water Supply Scheme. , SM/07386 | New | Quotation Bill of PH-II, Irhpala water supply scheme under MMD PHE Dte. | 2003978660 | 06/07/2022 | 365 | WBSEDCL | 0.46 | 0 | 0 | 0
671 | PASCHIM MEDINIPUR | Midnapore Division | IRPALA Piped Water Supply Scheme. , SM/07386 | New | Sinking of 2 (Two) Nos. 300 X 200 mm dia. X 200 Mtr. depth deep tube well by Direct Rotary Method for Head Work Site & 2nd tube well site of Irpala W/S Scheme with in Ghatal Block under Midnapore Division, P.H.E. Dte. | 297/MD | 15/02/2022 | 15 | ANNAPURNA TUBEWELL WORKS | 20.56 | 0 | 0 | 100
672 | PASCHIM MEDINIPUR | Midnapore Mechanical | IRPALA Piped Water Supply Scheme. , SM/07386 | New | Quotation Bill of PH-I, Irhpala water supply scheme under MMD PHE Dte. | 2003978653 | 06/07/2022 | 365 | WBSEDCL | 0.46 | 0 | 0 | 0
673 | PASCHIM MEDINIPUR | Midnapore Division | IRPALA Piped Water Supply Scheme. , SM/07386 | New | Material Requisition To Resource Division | 2508/MD | 09/12/2022 | 0 | Resource Division | 48.91 | 0 | 0 | 0
674 | PASCHIM MEDINIPUR | Midnapore Mechanical | IRPALA Piped Water Supply Scheme. , SM/07386 | New | Quotation Bill of PH-I, Irhpala water supply scheme under MMD PHE Dte. | BP-2022-23-24 | 08/08/2022 | 0 | WBSEDCL | 0.46 | 0 | 0 | 0
675 | PASCHIM MEDINIPUR | Midnapore Mechanical | IRPALA Piped Water Supply Scheme. , SM/07386 | New | Quotation Bill of PH-II, Irhpala water supply scheme under MMD PHE Dte. | BP-2022-23-25 | 08/08/2022 | 0 | WBSEDCL | 0.46 | 0 | 0 | 0
676 | PASCHIM MEDINIPUR | Midnapore Division | IRPALA Piped Water Supply Scheme. , SM/07386 | New | Supply of C.I.D.F Sluice Valve & C.I. Jeffy coupler for distribution pipe line and Rising main for IRPALA water Supply Scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte. | 400/AE/GSD | 11/07/2022 | 7 | M/S. GEO | 4.85 | 0 | 0 | 0
677 | PASCHIM MEDINIPUR | Midnapore Division | IRPALA Piped Water Supply Scheme. , SM/07386 | New | Construction of Retaining Wall at Head work site of IRPALA Water Supply Scheme under Ghatal Sub- Division PHE Dte. | 5384/MD | 04/12/2023 | 15 | A-PLUS | 6.31 | 0 | 0 | 0
678 | PASCHIM MEDINIPUR | Midnapore Mechanical | IRPALA Piped Water Supply Scheme. , SM/07386 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-II under Irpala water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | 1652/W/MMD | 12/08/2022 | 120 | M/S. SAJAHAN CHOWDHURY | 11.79 | 0 | 0 | 100
679 | PASCHIM MEDINIPUR | Midnapore Division | IRPALA Piped Water Supply Scheme. , SM/07386 | New | Restoration of damage shoulder & flank etc to the different roads under Midnapore Highway Division (Damage caused during laying pipe line by public Health Engineering Department. |  | 19/02/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 138 | 0 | 0 | 0
680 | PASCHIM MEDINIPUR | Midnapore Division | IRPALA Piped Water Supply Scheme. , SM/07386 | New | Laying distribution pipe line, Soil test and Construction of R.C.C. Elevated Reservoir of capacity 400 Cum and staging height 20.00 mtr. with allied works including supply of all labour & materials of IRPALA & its adjoining mouzas Water Supply Scheme within Ghatal Dev. Block under Ghatal sub-division of Midnapore Division, P.H.E. Dte. | 2167/MD | 17/12/2021 | 1617 | M/S. A.R. ENTERPRISE. | 291.14 | 0 | 0 | 70
681 | PASCHIM MEDINIPUR | Midnapore Division | IRPALA Piped Water Supply Scheme. , SM/07386 | New | Construction of swith rooms and its boundary wall, laying rising main & accommodated FHTC etc. of Irpala Water Supply Scheme within Ghatal Block under Midnapore Division PHE Dte. | 1677/MD | 12/08/2022 | 846 | DULAL CHANDRA DAS | 111.18 | 0 | 0 | 60
682 | PASCHIM MEDINIPUR | Midnapore Division | BARBHUNA BASAN STAND ALONE PWSS , SM/12841 | New | Material Requisition To Resource Division | 1357/MD | 02/05/2023 | 0 | Resource Division | 0.63 | 0 | 0 | 0
683 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARBHUNA BASAN STAND ALONE PWSS , SM/12841 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BARBHUNA BASAN STAND ALONE PWSS under JJM Program under MMD PHE Dte. | 879/W/MMD | 27/03/2023 | 180 | DEBSANKER BHATTACHARYA | 5.98 | 0 | 0 | 40
684 | PASCHIM MEDINIPUR | Midnapore Division | BARBHUNA BASAN STAND ALONE PWSS , SM/12841 | New | Construction & Installation of 10 Cum Capacity PVC Over Head Reservoir works with laying rising main, distribution system, Sinking of Tube well, Pump House & Providing FHTC (102 Nos.) with 1 year O&M for Barbhuna Basan PWSS within Debra block under Kharagpur Sub Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | 2256/MD | 23/07/2024 | 282 | BLUE BIRD | 44.33 | 0 | 0 | 50
685 | PASCHIM MEDINIPUR | Midnapore Division | AMRA TARYA AND ADJOINING MOUJAS PWSS , SM/13178 | New | Material Requisition To Resource Division | 1307/MD | 28/04/2023 | 0 | Resource Division | 23.16 | 0 | 0 | 0
686 | PASCHIM MEDINIPUR | Midnapore Mechanical | AMRA TARYA AND ADJOINING MOUJAS PWSS , SM/13178 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF AMRA TARYA PWSS. REF CONSUMER ID-204283802, APPLICATION NO-2004695729, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2024-25-271 | 12/06/2024 | 0 | WBSEDCL | 3.51 | 0 | 0 | 0
687 | PASCHIM MEDINIPUR | Midnapore Mechanical | AMRA TARYA AND ADJOINING MOUJAS PWSS , SM/13178 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF AMRA TARYA PWSS. REF CONSUMER ID-204283796, APPLICATION NO-2004695723, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2024-25-272 | 12/06/2024 | 0 | WBSEDCL | 3.24 | 0 | 0 | 0
688 | PASCHIM MEDINIPUR | Central Drilling | AMRA TARYA AND ADJOINING MOUJAS PWSS , SM/13178 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
689 | PASCHIM MEDINIPUR | Midnapore Division | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12986 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
690 | PASCHIM MEDINIPUR | Midnapore Division | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12986 | New | Construction of different capacity R.C.C. Over Head Reservoir Pile / Raft Foundation works with Laying rising main, Distribution system, Sinking of Tube well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (1,137 Nos.) including 1 year operation & maintenance for Gopinathpur Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. under Paschim Medinipur district. | 1340/MD | 28/04/2023 | 180 | SUJATA CONSTRUCTION | 367.16 | 0 | 0 | 45
691 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12986 | New | Electrict quotation bill for TW-I of Gopinathpur pwss (Ref Consumar ID-204252433),Application No-2004648562,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. | BP-2024-25-40 | 18/04/2024 | 0 | WBSEDCL | 4.27 | 0 | 0 | 0
692 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12986 | New | Electrict quotation bill for TW-II of Gopinathpur pwss (Ref Consumar ID-204251445),Application No-2004648522,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. | BP-2024-25-39 | 18/04/2024 | 0 | WBSEDCL | 3.81 | 0 | 0 | 0
693 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12986 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 1277/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 22.54 | 0 | 0 | 80
694 | PASCHIM MEDINIPUR | Midnapore Division | ANGUA AND ADJOINING MOUJAS PWSS , SM/12989 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh, Dantan-I & Dantan-II Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (A) Narayangarh block- (1) Kasba, (B) Dantan-I block - (1) Birbhadrapur, (2) Menakapur & (3) Benapura, (C) Dantan-II block - (1) Kusumda (Turkakasba)] | 707/MD | 06/03/2023 | 35 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 20
695 | PASCHIM MEDINIPUR | Midnapore Division | ANGUA AND ADJOINING MOUJAS PWSS , SM/12989 | New | Material Requisition To Resource Division | 1280/MD | 28/04/2023 | 0 | Resource Division | 28.62 | 0 | 0 | 0
696 | PASCHIM MEDINIPUR | Midnapore Mechanical | ANGUA AND ADJOINING MOUJAS PWSS , SM/12989 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of ANGUA PWSS. REF CONSUMER ID-204310356 APPLICATION NO-2004739370 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-211 | 28/05/2024 | 0 | WBSEDCL | 4.55 | 0 | 0 | 0
697 | PASCHIM MEDINIPUR | Midnapore Mechanical | ANGUA AND ADJOINING MOUJAS PWSS , SM/12989 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of ANGUA PWSS. REF CONSUMER ID-204310283 APPLICATION NO-2004740900, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-210 | 28/05/2024 | 0 | WBSEDCL | 6.04 | 0 | 0 | 0
698 | PASCHIM MEDINIPUR | Midnapore Mechanical | ANGUA AND ADJOINING MOUJAS PWSS , SM/12989 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ANGUA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 801/W/MMD | 24/03/2023 | 768 | RSA ENTERPRISE | 21.59 | 0 | 0 | 35
699 | PASCHIM MEDINIPUR | Midnapore Division | GOKULPUR AND ADJOINING MOUJAS PWSS , SM/14649 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Ganua, (2) Gokulpur & (3) Naharpur] | 834/MD | 22/03/2023 | 21 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0 | 0
700 | PASCHIM MEDINIPUR | Midnapore Division | GOKULPUR AND ADJOINING MOUJAS PWSS , SM/14649 | New | Material Requisition To Resource Division | 1483 | 10/05/2023 | 0 | Resource Division | 36.49 | 0 | 0 | 0
701 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOKULPUR AND ADJOINING MOUJAS PWSS , SM/14649 | New | Quotation for new power connection at Gokulpur PWSS T/W - I , Application no- 2004790935, Ref no : 204339890 | BP-2024-25-453 | 23/07/2024 | 0 | WBSEDCL | 3.12 | 0 | 0 | 0
702 | PASCHIM MEDINIPUR | Central Drilling | GOKULPUR AND ADJOINING MOUJAS PWSS , SM/14649 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
703 | PASCHIM MEDINIPUR | Midnapore Division | GOKULPUR AND ADJOINING MOUJAS PWSS , SM/14649 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
704 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOKULPUR AND ADJOINING MOUJAS PWSS , SM/14649 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
705 | PASCHIM MEDINIPUR | Midnapore Division | SOLEMANPUR AND IT'S ADJOINING MOJAS PWSS , SM/13139 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
706 | PASCHIM MEDINIPUR | Midnapore Division | SOLEMANPUR AND IT'S ADJOINING MOJAS PWSS , SM/13139 | New | Material Requisition To Resource Division | 1297/MD | 28/04/2023 | 0 | Resource Division | 26.1 | 0 | 0 | 0
707 | PASCHIM MEDINIPUR | Midnapore Mechanical | SOLEMANPUR AND IT'S ADJOINING MOJAS PWSS , SM/13139 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF SOLEMANPUR PWSS. REF CONSUMER ID-204393519, APPLICATION NO-2004889549, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102401981777 | 03/10/2024 | 0 | WBSEDCL | 4.34 | 0 | 0 | 0
708 | PASCHIM MEDINIPUR | Central Drilling | SOLEMANPUR AND IT'S ADJOINING MOJAS PWSS , SM/13139 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
709 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAMARIA PIPED WATER SUPPLY SCHEME , SM/13141 | New | Electric Quotation bill for Tw no-I of Gamaria PWSS. (ref Consumer ID-204109025). | BP-2023-24-326 | 03/11/2023 | 0 | WBSEDCL | 3.13 | 0 | 0 | 0
710 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAMARIA PIPED WATER SUPPLY SCHEME , SM/13141 | New | Electric quotation bill for Tw no-II of Gamaria PWSS (Ref Consumer ID-204109023) | BP-2023-24-327 | 03/11/2023 | 0 | WBSEDCL | 2.73 | 0 | 0 | 0
711 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAMARIA PIPED WATER SUPPLY SCHEME , SM/13141 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GAMARIA PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | 2391/W/MMD | 31/12/2022 | 180 | SUBHASIS ROY | 22.89 | 0 | 0 | 25
712 | PASCHIM MEDINIPUR | Midnapore Division | GAMARIA PIPED WATER SUPPLY SCHEME , SM/13141 | New | Material Requisition To Resource Division | 3373/MD | 25/11/2024 | 0 | Resource Division | 9.7 | 0 | 0 | 0
713 | PASCHIM MEDINIPUR | Midnapore Division | GAMARIA PIPED WATER SUPPLY SCHEME , SM/13141 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 0 | 75
714 | PASCHIM MEDINIPUR | Midnapore Division | GAMARIA PIPED WATER SUPPLY SCHEME , SM/13141 | New | Laying of rising main & interconnection for Gamaria & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 2,320 Mtr.) | 194/MD | 17/01/2025 | 60 | M/S. S.S. ENTERPRISE | 13.11 | 0 | 0 | 0
715 | PASCHIM MEDINIPUR | Midnapore Division | URIYASHAI AND ADJOINING MOUJAS PWSS , SM/13130 | New | Material Requisition To Resource Division | 1231/MD | 27/04/2023 | 0 | Resource Division | 27.76 | 0 | 0 | 0
716 | PASCHIM MEDINIPUR | Central Drilling | URIYASHAI AND ADJOINING MOUJAS PWSS , SM/13130 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
717 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14481 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Ragpur PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | 551/AE/KSD | 23/08/2022 | 30 | GOBINDA MAITY | 2.88 | 0 | 0 | 0
718 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14481 | Augmentation | Material Requisition To Resource Division | 96/MD | 10/01/2023 | 0 | Resource Division | 2.56 | 0 | 0 | 0
719 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14481 | Augmentation | Material Requisition To Resource Division | 3421/MD | 25/11/2024 | 0 | Resource Division | 14.91 | 0 | 0 | 0
720 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14481 | Augmentation | ELECTRIC QUOTATION BILL FOR AD TW NO-III OF RAGPUR PWSS. REF CONSUMER ID-204391667, APPLICATION NO-2004886583, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA. | BP-2024-25-680 | 27/09/2024 | 0 | WBSEDCL | 6.23 | 0 | 0 | 0
721 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14481 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 829/W/MMD | 24/03/2023 | 720 | M/S EMMESS | 11.33 | 0 | 0 | 20
722 | PASCHIM MEDINIPUR | Midnapore Division | ABHAYA AND ADJOINING MOUJAS PWSS , SM/14689 | New | Material Requisition To Resource Division | 1262/MD | 28/04/2023 | 0 | Resource Division | 17.2 | 0 | 0 | 0
723 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | ABHAYA AND ADJOINING MOUJAS PWSS , SM/14689 | New | New Service Connection Charges for Abhaya T/W - I PWSS |  | 04/10/2024 | 0 | WBSEDCL | 4.99 | 0 | 0 | 0
724 | PASCHIM MEDINIPUR | Central Drilling | ABHAYA AND ADJOINING MOUJAS PWSS , SM/14689 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
725 | PASCHIM MEDINIPUR | Midnapore Division | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS , SM/15025 | New | Material Requisition To Resource Division | 197/MD | 16/01/2023 | 0 | Resource Division | 35.4 | 0 | 0 | 0
726 | PASCHIM MEDINIPUR | Midnapore Division | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS , SM/15025 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Soil investigation , 250 Cum OHR (Intze type with Raft foundation) & Accommodate FHTC (1488 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Narasinghapur & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 2146/MD | 08/06/2023 | 180 | A.J. ENTERPRISE | 425.75 | 0 | 0 | 40
727 | PASCHIM MEDINIPUR | Midnapore Division | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS , SM/15025 | New | Material Requisition To Resource Division | 3427/MD | 25/11/2024 | 0 | Resource Division | 9.17 | 0 | 0 | 0
728 | PASCHIM MEDINIPUR | Midnapore Mechanical | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS , SM/15025 | New | Additional Quotation for LT network connection at Narasinghapur PWSS P/H- I , application no - 100000101096 , Ref id - 860293136 | BP-2023-24-781 | 06/03/2024 | 0 | WBSEDCL | 3.12 | 0 | 0 | 0
729 | PASCHIM MEDINIPUR | Midnapore Mechanical | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS , SM/15025 | New | Quotation for new power connection at Narasinghapur water supply scheme T/W - I | BP-2023-24-620 | 07/02/2024 | 0 | WBSEDCL | 0.51 | 0 | 0 | 0
730 | PASCHIM MEDINIPUR | Midnapore Mechanical | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS , SM/15025 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 616/W/MMD | 20/03/2023 | 732 | JAGANNATH ENTERPRISE | 21.58 | 0 | 0 | 40
731 | PASCHIM MEDINIPUR | Midnapore Division | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS , SM/15025 | New | Route survey & way leave permission along & across of National Highway in Narasinghapur PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | 587/MD | 03/03/2025 | 21 | DONA ASSOCIATES | 10.04 | 0 | 0 | 0
732 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Shanrpur PWSS Block - Debra District Paschim Medinipur , SM/08217 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Shanrpur PWSS, Block :- Debra in the District of Paschim Medinipur. | 305/MD | 22/02/2021 | 40 | UCON | 86.59 | 40.52 | 39.07 | 0
733 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Shanrpur PWSS Block - Debra District Paschim Medinipur , SM/08217 | Retrofitting | Preparation of DPR of Chhotokhena W/S Scheme. | BP-2021-22-280 | 16/03/2022 | 0 | SIRCON ENGINEERING SERVICES | 0.06 | 0 | 0 | 0
734 | PASCHIM MEDINIPUR | Midnapore Division | DOSATINA AND ITS ADJOINING MOUZAS PWSS , SM/15589 | New | Material Requisition To Resource Division | 1405/MD | 04/05/2023 | 0 | Resource Division | 35.42 | 0 | 0 | 0
735 | PASCHIM MEDINIPUR | Midnapore Mechanical | DOSATINA AND ITS ADJOINING MOUZAS PWSS , SM/15589 | New | Electric quotation bill for Tw No-I of Dosatina PWSS.(ref Consumer ID-204182345) | BP-2023-24-554 | 16/01/2024 | 0 | WBSEDCL | 3.93 | 0 | 0 | 0
736 | PASCHIM MEDINIPUR | Midnapore Mechanical | DOSATINA AND ITS ADJOINING MOUZAS PWSS , SM/15589 | New | Electric quotation bill for Tw No-II of Dosatina PWSS.(Ref Consumer ID-204182357) | BP-2023-24-555 | 16/01/2024 | 0 | WBSEDCL | 5.43 | 0 | 0 | 0
737 | PASCHIM MEDINIPUR | Midnapore Division | DOSATINA AND ITS ADJOINING MOUZAS PWSS , SM/15589 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 Cum (Intze type with Pile Foundation) & Accommodate FHTC (3,208 Nos.) including Two years O&M under JJM with allied work for Dosatina & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | 2954/MD | 17/08/2023 | 863 | M/S. D.K.H.CONSTRUCTION | 822.63 | 0 | 0 | 51
738 | PASCHIM MEDINIPUR | Midnapore Mechanical | DOSATINA AND ITS ADJOINING MOUZAS PWSS , SM/15589 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DOSATINA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 908/W/MMD | 27/03/2023 | 666 | SUJOY RANJAN BHOWMICK | 27.37 | 0 | 0 | 15
739 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kurul PWSS under Datan-II Block in Paschim Medinipur District , SM/09710 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kurul PWSS under Dantan-II Block in Paschim Medinipur District. | 2001/MD | 01/12/2021 | 30 | M/S. EL-CON | 59.12 | 0 | 0 | 0
740 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kurul PWSS under Datan-II Block in Paschim Medinipur District , SM/09710 | Retrofitting | Extension of Distribution pipeline at Mouza Kural(Adibasipara near Hutpara) & Satpukuria within Kurul PWSS under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | 236/AE/KSD | 12/05/2022 | 30 | RELIABLE ENTERPRISES | 3.3 | 0 | 0 | 0
741 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kurul PWSS under Datan-II Block in Paschim Medinipur District , SM/09710 | Retrofitting | Extension of Distribution pipeline at Mouza Santoshpur & Piling work near pond within Kurul PWSS under Kharagpur Sub-Division Within Midnapore Division, P.H.E. Dte. | 382/AE/KSD | 30/06/2022 | 30 | RELIABLE ENTERPRISES | 3.4 | 0 | 0 | 0
742 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Adasimla (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15217 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Adasimla PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1654/MD | 27/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.14 | 0 | 0 | 0
743 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Adasimla (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15217 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Adasimla (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 878/W/MMD | 27/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 5.99 | 0 | 0 | 0
744 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Adasimla (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15217 | Augmentation | Quotation as per WBSEDCL procedure-A (2010) electric quotation bill. | BP-2022-23-678 | 09/03/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0 | 0
745 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Adasimla (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15217 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Adasimla (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | 440/MD | 10/02/2023 | 60 | SAI TUBE CO. | 62.67 | 0 | 0 | 100
746 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Adasimla (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15217 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Augmentation of Adasimla Water Supply Scheme [ Block- Sabang ] under MMD, PHE Dte., Dist.- Paschim Medinipur. | 1352/W/MMD | 24/05/2023 | 180 | SUJOY RANJAN BHOWMICK | 14.23 | 0 | 0 | 83
747 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15570 | Augmentation | Material Requisition To Resource Division | 408/MD | 07/02/2023 | 0 | Resource Division | 2.72 | 0 | 0 | 0
748 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15570 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (317) for Augmentation of Anandapur Sundarpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2719/MD | 31/07/2023 | 60 | MIDNAPUR PIPE CONCERN | 107.87 | 0 | 0 | 10
749 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15570 | Augmentation | QUOTATION MONEY FOR ANANDAPUR- SUNDARPUR WATER SUPPLY SCHEME, T W NO IIII, [JOYNAGAR], AUGMENTATION, JJM WORKS, SCHEME CODE SM/15570, APPLICATION NO 2004815790, REFERENCE ID 204354167, GHATAL CCC, WBSEDCL | C072443785883 | 30/07/2024 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
750 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15570 | Augmentation | QUOTATION MONEY FOR ANANDAPUR WATER SUPPLY SCHEME, T W NO IV, [ AUGMENTATION ] , JJM WORKS, SCHEME CODE SM/15570, APPLICATION NO 2004815766, REFERENCE ID 204354166, GHATAL CCC, WBSEDCL | C072443787374 | 30/07/2024 | 0 | WBSEDCL | 6.86 | 0 | 0 | 0
751 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15570 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | 913/W/MMD | 27/03/2023 | 797 | GLACIER ENGINEERING CO. | 25.26 | 0 | 0 | 85
752 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-I at Mouza-Basudevpur, JL-63 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 750/MD | 13/03/2023 | 14 | DEBASIS DATTA | 9.5 | 0 | 0 | 90
753 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur -II (1 no), (i)At Mouza- Dudkorma, JL-245 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 738/MD | 10/03/2023 | 14 | A.R. CONSTRUCTION | 9.57 | 0 | 0 | 100
754 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed 26 nos. Mini Pipe W/S Scheme within Block Chandrakona-II (1 nos.), (i) at Mouza-Kharsa JL-231 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 735/MD | 10/03/2023 | 14 | TARUN MAHATA | 9.5 | 0 | 0 | 0
755 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Basanchora, JL-68 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 968/MD | 06/04/2023 | 14 | OM UDYUG | 9.54 | 0 | 0 | 90
756 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-I at Mouza-Paikpara, JL-267 in Paschim Medinipur District under Midnapore Division, PHE Dte. [PART-B] | 967/MD | 06/04/2023 | 14 | MALLIK CONSTRUCTION | 9.54 | 0 | 0 | 0
757 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Jote Ganashyam, JL-240 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 1437/MD | 04/05/2023 | 14 | M/S. BLUE BIRD | 9.58 | 0 | 0 | 98
758 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Electric quotation bill of WBSEDCL. |  | 18/07/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.13 | 0 | 0 | 0
759 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Quotation as per WBSEDCL under Banpatna, Kankuria, Dudkomra, Nabinmanua, Jateghanashyam, Nischintapur, Jagannathur, Gochhati, Arit and Bhuta Water Supply Scheme. | 23-24-78-79-84 | 12/05/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 1.29 | 0 | 0 | 0
760 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Electric quotation bill for Ghanarampur mini PWSS Tube Well in connection Chandrakona Town CCC for payment to WBSEDCL. | BP-2023-24-173 | 20/07/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 1.51 | 0 | 0 | 0
761 | PASCHIM MEDINIPUR | Midnapore Mechanical | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Electric quotation for kankuria mini w/s.(consumer ID-203877119) |  | 19/04/2023 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
762 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Electric Quotation Bill of Mararampur, Basudevpur & Dharma Mini | 23-24-128-29-30 | 19/06/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.38 | 0 | 0 | 0
763 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Ghanarmpur, Paikpara-I, Paikpara-II, Murakata, Basanchora, Peardanga, Karasia, Nischintapur, Gargarighat, Kharsa, Hematpur, Bala W/S Scheme. |  | 05/07/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 1.51 | 0 | 0 | 0
764 | PASCHIM MEDINIPUR | Midnapore Mechanical | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Electric quotation for Banpatna w/s mini scheme(Consumer ID-203877125) |  | 19/04/2023 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
765 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Electric quotation bill of WBSEDCL. | BP-2023-24-273 | 28/08/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 0.13 | 0 | 0 | 0
766 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-I at Mouza-Dharma, JL-145 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 966/MD | 06/04/2023 | 14 | OM UDYUG | 9.45 | 0 | 0 | 90
767 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Ghanarampur, JL-257 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 784/MD | 17/03/2023 | 14 | M/S. SUBHAS CHANDRA KUNDU | 9.18 | 0 | 0 | 100
768 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Gochhati, JL-161 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 1436/MD | 04/05/2023 | 14 | M/S. BLUE BIRD | 9.58 | 0 | 0 | 98
769 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Jagannathpur, JL-85 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 2473/MD | 14/07/2023 | 14 | MAHAPRABHU ENTERPRISE | 9.59 | 0 | 0 | 90
770 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Murakata, JL-49 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 653/MD | 07/03/2024 | 14 | M/S. INDRAJIT ROY | 9.53 | 0 | 0 | 0
771 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme Within Block Chandrakona-I at Mouza-Hematpur JL-209 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 734/MD | 10/03/2023 | 14 | HYDRO TECH ASSOCIATES | 9.28 | 0 | 0 | 90
772 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-I at Mouza-Paikpara, JL-267 in Paschim Medinipur District under Midnapore Division, PHE Dte. [PART-A] | 782/MD | 17/03/2023 | 14 | PRITI ENTERPRISE | 9.32 | 0 | 0 | 90
773 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Kharagpur-I at Mouza-Kankuria, JL-281 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 868/MD | 28/03/2023 | 14 | AJITESH ACHARJEE | 9.52 | 0 | 0 | 90
774 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Arit, JL-220 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 869/MD | 28/03/2023 | 14 | A R ENTERPRISE | 9.59 | 0 | 0 | 90
775 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Kharagpur-I at Mouza-Banpatna, JL-340 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 867/MD | 28/03/2023 | 14 | RITESH AGARWALL | 9.59 | 0 | 0 | 90
776 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-I at Mouza-Nischintapur, JL-264 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 870/MD | 28/03/2023 | 14 | M/S. INDRAJIT ROY | 9.54 | 0 | 0 | 90
777 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Nischintapur, JL-230 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 964/MD | 06/04/2023 | 14 | SAJAL JANA | 9.59 | 0 | 0 | 100
778 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Bhuta, JL-187 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 785/MD | 17/03/2023 | 14 | S.K. CONSTRUCTION | 9.53 | 0 | 0 | 90
779 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Karasia, JL-77 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 965/MD | 06/04/2023 | 14 | BENGAL TRADERS | 9.59 | 0 | 0 | 90
780 | PASCHIM MEDINIPUR | Midnapore Mechanical | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & Kharagpur-I (2 Nos.) in Paschim Medinipur District under Midnapore Division, PHE Dte. | 773/W/MMD | 23/03/2023 | 180 | BHABANI PRASAD MANNA | 68.08 | 0 | 0 | 97
781 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Peardanga, JL-79 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 2593/MD | 21/07/2023 | 14 | SARADA CONSTRUCTION | 9.5 | 0 | 0 | 100
782 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Material Requisition To Resource Division | 3433/MD | 25/11/2024 | 0 | Resource Division | 16.02 | 0 | 0 | 0
783 | PASCHIM MEDINIPUR | Midnapore Mechanical | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Additional Electric quotation bill of Jotekanuramgarh pwss (Ref Consumer ID-203856003),Application No-2004144274,Application Type-New Connection,Name of ccc-Daspur ccc, block-Daspur-I. |  | 12/02/2024 | 0 | WBSEDCL | 0 | 0 | 0 | 0
784 | PASCHIM MEDINIPUR | Midnapore Mechanical | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Electrict quotation bill for Jotekanuramgarh pwss (Ref Consumar ID-203856003),Application No-2004144274,Application Type-New Connection,Name of ccc-Daspur ccc, block-Daspur-II. |  | 09/02/2024 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
785 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed 26 nos. Mini Pipe W/S Scheme within Block Daspur -I (1 nos),(i) At Mouza-Makrampur JL no-125& in Paschim Medinipur District under Midnapore Division, PHE Dte. | 803/MD | 20/03/2023 | 14 | S.M. ENTERPRISE | 9.3 | 0 | 0 | 100
786 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Jotekanuramgarh, JL-212 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 742/MD | 13/03/2024 | 183 | ARNAB PATRA | 9.59 | 0 | 0 | 97
787 | PASCHIM MEDINIPUR | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & , SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Nabinmanua, JL-155 in Paschim Medinipur District under Midnapore Division, PHE Dte. | 743/MD | 13/03/2024 | 201 | S.K. CONSTRUCTION | 9.58 | 0 | 0 | 97
788 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chaita PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16983 | Solarisation | Solarization of grid connected pumping installation at Chaita PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 674/W/MMD | 23/03/2023 | 180 | M/S EMMESS | 6.26 | 0 | 0 | 50
789 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Solarization of grid connected pumping installation at Chaita PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16983 | Solarisation | Quotation bill for Providing solarization of WBSEDCL energised pumping installation at Chaita w/s scheme (t/w no.I) | 89/JMD | 12/02/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
790 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dhaneswarpur (Pingla) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17751 | Solarisation | Solarization of grid connected pumping installation at Dhaneswarpur (Pingla) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 966/W/MMD | 29/03/2023 | 180 | GOENKA ENTERPRISE | 6.26 | 0 | 0 | 0
791 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Gokulpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17752 | Solarisation | Solarization of grid connected pumping installation Gokulpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 986/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
792 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Gokulpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17752 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going solarisation / rejuvenation as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 716/MMSD-I | 07/06/2024 | 15 | MUKHERJEE ART CENTRE | 1.93 | 0 | 0 | 100
793 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Adasimla PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17759 | Solarisation | Solarization of grid connected pumping installation Adasimla PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 977/W/MMD | 29/03/2023 | 720 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 65
794 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Adasimla PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17759 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 720/MMSD-I | 07/06/2024 | 15 | SUBHASIS ROY | 2.29 | 0 | 0 | 100
795 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Jamdoba Godamouli PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17469 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
796 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Shanrpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17737 | Solarisation | Solarization of grid connected pumping installation Shanrpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 972/W/MMD | 29/03/2023 | 180 | RSA ENTERPRISE | 6.25 | 0 | 0 | 70
797 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bhimpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17451 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
798 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Ukhla PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17371 | Solarisation | Solarization of grid connected pumping installation at Ukhla PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 710/W/MMD | 23/03/2023 | 180 | ABHIJIT MUKHERJEE | 6.25 | 0 | 0 | 0
799 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Gobardhanpur PWSS in the District of Paschim Medinipur under JJM programme. , SM/17822 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Gobardhanpur PWSS in the District of Paschim Medinipur under JJM programme. under JJM Program under MMD PHE Dte. | 1069/W/MMD | 29/03/2023 | 732 | BHABANI PRASAD MANNA | 11.39 | 0 | 0 | 90
800 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Ukhla PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17479 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
801 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Jamboda Godamouli PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/18113 | Solarisation | Solarization of grid connected pumping installation Jamboda Godamouli PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1095/W/MMD | 31/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
802 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Debra PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/18120 | Solarisation | Solarization of grid connected pumping installation at Debra PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 1094/W/MMD | 31/03/2023 | 180 | GOENKA ENTERPRISE | 6.26 | 0 | 0 | 90
803 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Kasanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17733 | Solarisation | Solarization of grid connected pumping installation Kasanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 968/W/MMD | 29/03/2023 | 180 | RSA ENTERPRISE | 6.25 | 0 | 0 | 80
804 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Solarization of grid connected pumping installation Kasanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17733 | Solarisation | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
805 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Solarization of grid connected pumping installation Kasanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17733 | Solarisation | Quotation for SOLAR PANEL connection at KASANDA TW -I water supply. | 142/JMD | 24/05/2024 | 0 | WBSEDCL | 0.2 | 0 | 0 | 0
806 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Solarization of grid connected pumping installation Kasanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17733 | Solarisation | Application Fee for Solar Power Plant at Kasanda T/W - I water supply scheme. | 28/JMD | 11/03/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
807 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bajpara PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17316 | Solarisation | Solarization of grid connected pumping installation at Bajpara PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 677/W/MMD | 23/03/2023 | 180 | M/S B.M. ELECTRICAL | 6.26 | 0 | 0 | 80
808 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bajpara PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17316 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going solarisation / rejuvenation as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 716/MMSD-I | 07/06/2024 | 15 | MUKHERJEE ART CENTRE | 1.93 | 0 | 0 | 100
809 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Julkapore PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17319 | Solarisation | Solarization of grid connected pumping installation at Julkapore PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 782/W/MMD | 24/03/2023 | 180 | RSA ENTERPRISE | 6.26 | 0 | 0 | 0
810 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Julkapore PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17319 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 720/MMSD-I | 07/06/2024 | 15 | SUBHASIS ROY | 2.29 | 0 | 0 | 100
811 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Julkapore PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17319 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going solarisation / rejuvenation as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 716/MMSD-I | 07/06/2024 | 15 | MUKHERJEE ART CENTRE | 1.93 | 0 | 0 | 100
812 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kalaimuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17447 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
813 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. , SM/19101 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas.under JJM Program under MMD PHE Dte. | 3171/W/MMD | 18/12/2023 | 180 | NIRMAN | 27.34 | 0 | 0 | 0
814 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. , SM/19101 | New | Material Requisition To Resource Division | 76/MD | 09/01/2023 | 0 | Resource Division | 25.83 | 0 | 0 | 0
815 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. , SM/19101 | New | Material Requisition To Resource Division | 3349/MD | 25/11/2024 | 0 | Resource Division | 21.2 | 0 | 0 | 0
816 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. , SM/19101 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 450 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,442) under JJM with allied work for Khukur Daha & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 142/MD | 18/01/2024 | 796 | MASUM ALI KHAN | 804.29 | 0 | 0 | 30
817 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. , SM/19101 | New | Laying rising main & interconnection for Khukurdaha & its adjoining mouzas PWSS within Daspur-II block, Paschim Medinipur district under Midnapore Division, PHE Dte. | 585/MD | 03/03/2025 | 90 | GOBINDA MAITY | 9.16 | 0 | 0 | 95
818 | PASCHIM MEDINIPUR | Midnapore Division | KASBA NARAYANGARH AND ADJOINING MOUJAS PWSS , SM/19100 | New | Material Requisition To Resource Division | 1485 | 10/05/2023 | 0 | Resource Division | 39.42 | 0 | 0 | 0
819 | PASCHIM MEDINIPUR | Central Drilling | KASBA NARAYANGARH AND ADJOINING MOUJAS PWSS , SM/19100 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
820 | PASCHIM MEDINIPUR | Midnapore Division | KASBA NARAYANGARH AND ADJOINING MOUJAS PWSS , SM/19100 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
821 | PASCHIM MEDINIPUR | Midnapore Mechanical | KASBA NARAYANGARH AND ADJOINING MOUJAS PWSS , SM/19100 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
822 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09678 | New | Preparation of D.P.R. (Consultancy work) in connection with the Proposed Mini Pipe W/S Scheme for Uchitpur mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | 1331/MD | 17/08/2021 | 10 | GOBINDA MAITY | 1.94 | 0 | 0 | 0
823 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09678 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Uchitpur water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2532/W/MMD | 30/11/2021 | 4 | MENAKA ENTERPRISE | 4.48 | 0 | 0 | 100
824 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09678 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Uchitpur water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2530/W/MMD | 30/11/2021 | 4 | MENAKA ENTERPRISE | 4.47 | 0 | 0 | 100
825 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09678 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | BP-2021-22-505 | 22/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 8.13 | 0 | 0 | 0
826 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09678 | New | For payment of liabilities. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.93 | 0 | 0 | 0
827 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09678 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas. Block - Sabang. District - Paschim Medinipur. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.93 | 0 | 0 | 0
828 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09678 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -II at Uchitpur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 157/W/MMD | 31/01/2022 | 120 | P.K.ENGINEERING | 6.52 | 0 | 0 | 70
829 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09678 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Uchitpur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 156/W/MMD | 31/01/2022 | 120 | MENAKA ENTERPRISE | 6.52 | 0 | 0 | 0
830 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09678 | New | Material Requisition To Resource Division | 2118/MD | 13/12/2021 | 0 | Resource Division | 1.93 | 0 | 0 | 0
831 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09678 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Uchitpur (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 422/MD | 04/03/2022 | 150 | GOUTAM PARIA | 24.89 | 0 | 0 | 80
832 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09678 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Uchitpur (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 183/MD | 01/02/2022 | 1065 | MASUM ALI KHAN | 37.49 | 0 | 0 | 100
833 | PASCHIM MEDINIPUR | Midnapore Division | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION , SM/17005 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Dhuipara & its adjoining Mouzas PWSS & (2) Nilda & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | 1117/MD | 09/06/2022 | 30 | ENVIROTECH SOLUTIONS | 4.15 | 0 | 0 | 100
834 | PASCHIM MEDINIPUR | Midnapore Division | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION , SM/17005 | New | Material Requisition To Resource Division | 1454/MD | 08/05/2023 | 0 | Resource Division | 30.9 | 0 | 0 | 0
835 | PASCHIM MEDINIPUR | Midnapore Mechanical | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION , SM/17005 | New | Electrict quotation bill for TW-II of Dhuipara pwss (Ref Consumar ID-204310840),Application No-2004741253,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | BP-2024-25-194 | 24/05/2024 | 0 | WBSEDCL | 4.55 | 0 | 0 | 0
836 | PASCHIM MEDINIPUR | Midnapore Mechanical | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION , SM/17005 | New | Electrict quotation bill for TW-I of Dhuipara pwss (Ref Consumar ID-204310843),Application No-2004741201,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | BP-2024-25-193 | 24/05/2024 | 0 | WBSEDCL | 3.62 | 0 | 0 | 0
837 | PASCHIM MEDINIPUR | Midnapore Mechanical | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION , SM/17005 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION under JJM Program under MMD PHE Dte. | 1190/W/MMD | 25/04/2023 | 706 | RSA ENTERPRISE | 22.79 | 0 | 0 | 60
838 | PASCHIM MEDINIPUR | Midnapore Division | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION , SM/17005 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 0 | 55
839 | PASCHIM MEDINIPUR | Midnapore Division | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION , SM/17005 | New | Construction of Approach Road (3m width) of Dhuipara Piped Water Supply Scheme at Mohanpur block under Midnapore Division, PHE Dte. | 153/MD | 15/01/2025 | 30 | GOBINDA MAITY | 1.64 | 0 | 0 | 100
840 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAGUYAN AND IT'S ADJOINING MOUJAS PWSS , SM/17623 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAGUYAN AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 456/W/MMD | 20/03/2023 | 180 | BALAJI CONSTRUCTION | 22.89 | 0 | 0 | 0
841 | PASCHIM MEDINIPUR | Midnapore Division | BAGUYAN AND IT'S ADJOINING MOUJAS PWSS , SM/17623 | New | Material Requisition To Resource Division | 1413 | 04/05/2023 | 0 | Resource Division | 37.1 | 0 | 0 | 0
842 | PASCHIM MEDINIPUR | Midnapore Division | BAGUYAN AND IT'S ADJOINING MOUJAS PWSS , SM/17623 | New | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, 250 cum OHR (Intze type with solid raft) & Accommodate FHTC (1,745 Nos.) including 2 years operation & maintenance under JJM with allied work for Baguyan & its adjoining mouzas W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 3053/MD | 23/08/2023 | 857 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 452.52 | 0 | 0 | 40
843 | PASCHIM MEDINIPUR | Midnapore Division | Monoharpur Piped Water Supply Scheme. , SM/10017 | New | Sinking of 2 (Two) nos. 300 X 200 mm dia. X 200 mtr. depth deep tube well by direct rotary method for Head work site & 2nd tube well site of Monoharpur PWSS with in Dantan - I block under Midnapore Division, P.H.E. Dte. | 447/MD | 13/02/2023 | 14 | FIROJ KHAN | 23.18 | 0 | 0 | 0
844 | PASCHIM MEDINIPUR | Midnapore Division | Monoharpur Piped Water Supply Scheme. , SM/10017 | New | Material Requisition To Resource Division | 802/MD | 20/03/2023 | 0 | Resource Division | 20.04 | 0 | 0 | 0
845 | PASCHIM MEDINIPUR | Midnapore Division | Monoharpur Piped Water Supply Scheme. , SM/10017 | New | Material Requisition To Resource Division | 49/MD | 06/01/2023 | 0 | Resource Division | 25.82 | 0 | 0 | 0
846 | PASCHIM MEDINIPUR | Midnapore Division | Monoharpur Piped Water Supply Scheme. , SM/10017 | New | Material Requisition To Resource Division | 941/MD | 05/04/2023 | 0 | Resource Division | 20.04 | 0 | 0 | 0
847 | PASCHIM MEDINIPUR | Midnapore Mechanical | Monoharpur Piped Water Supply Scheme. , SM/10017 | New | Quotation for new service connection at Monoharpur T.W.no-I |  | 08/05/2023 | 0 | WBSEDCL | 0.78 | 0 | 0 | 0
848 | PASCHIM MEDINIPUR | Midnapore Mechanical | Monoharpur Piped Water Supply Scheme. , SM/10017 | New | New service connection at Monoharpur T.W.No-II |  | 08/05/2023 | 0 | WBSEDCL | 2.5 | 0 | 0 | 0
849 | PASCHIM MEDINIPUR | Midnapore Division | Monoharpur Piped Water Supply Scheme. , SM/10017 | New | Electric Quotation Bill for the West Bengal State Electricty Distribution Company LTD. | BP-2023-24-142 | 23/06/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 3.27 | 0 | 0 | 0
850 | PASCHIM MEDINIPUR | Midnapore Mechanical | Monoharpur Piped Water Supply Scheme. , SM/10017 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KAKRAJIT AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 841/W/MMD | 24/03/2023 | 180 | P.K.ENGINEERING | 54.76 | 0 | 0 | 30
851 | PASCHIM MEDINIPUR | Midnapore Division | Monoharpur Piped Water Supply Scheme. , SM/10017 | New | Laying Rising main pipe line, Construction of Pump House & Boundary wall under JJM with allied work for Monoharpur & its adjoining mouzas PWSS in Dantan-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 2817/MD | 07/08/2023 | 60 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 29.64 | 0 | 0 | 76
852 | PASCHIM MEDINIPUR | Midnapore Division | Monoharpur Piped Water Supply Scheme. , SM/10017 | New | Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 500 Cum and staging height 20.00 mtr. & FHTC under JJM with allied work for Monoharpur and its adjoining mouzas W/S Scheme in Datan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 2190/MD | 01/11/2022 | 1078 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 583.38 | 0 | 0 | 35
853 | PASCHIM MEDINIPUR | Midnapore Division | BAGRUI AND ITS ADJOINING MOUZAS PWSS , SM/19052 | New | Material Requisition To Resource Division | 1404/MD | 04/05/2023 | 0 | Resource Division | 36.78 | 0 | 0 | 0
854 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAGRUI AND ITS ADJOINING MOUZAS PWSS , SM/19052 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of BAGRUI PWSS. REF CONSUMER ID-204211962, APPLICATION NO-2004590203, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-688 | 16/02/2024 | 0 | WBSEDCL | 3.51 | 0 | 0 | 0
855 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAGRUI AND ITS ADJOINING MOUZAS PWSS , SM/19052 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of BAGRUI PWSS. REF CONSUMER ID-204211970, APPLICATION NO-2004590212, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-687 | 16/02/2024 | 0 | WBSEDCL | 3.64 | 0 | 0 | 0
856 | PASCHIM MEDINIPUR | Midnapore Division | BAGRUI AND ITS ADJOINING MOUZAS PWSS , SM/19052 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 Cum OHR (Intze type with Pile Foundation) & Accommodate FHTC (3,124 Nos.) including Two years O&M under JJM with allied work for Bagrui & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | 5479/MD | 13/12/2023 | 720 | BALAJI UDDYOG | 1062.1 | 0 | 0 | 45
857 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAGRUI AND ITS ADJOINING MOUZAS PWSS , SM/19052 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0 | 0 | 50
858 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAGRUI AND ITS ADJOINING MOUZAS PWSS , SM/19052 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAGRUI AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | 3093/W/MMD | 29/11/2023 | 475 | SUJOY RANJAN BHOWMICK | 25.26 | 0 | 0 | 15
859 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur , SM/10658 | New | Electric quotation Sabang CCC at Daspur, Bankibheri Pin-721434 | 2003870026 | 23/03/2022 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
860 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur , SM/10658 | New | Electric Quotation bill Sabang CCC at Daspur, Bankibheri, Pin-721434 |  | 17/11/2022 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
861 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur , SM/10658 | New | Sinking of (150 mmX 100 mmX 150mtr) RBTW by Rotary Method at Daspur water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur District under Midnapur Mechanical Division P.H.E Dte. | 75/W/MMD | 17/01/2022 | 5 | DEBJYOTI BASU | 4.47 | 0 | 0 | 100
862 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur , SM/10658 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at DASPUR water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 76/W/MMD | 17/01/2022 | 5 | DEBJYOTI BASU | 4.47 | 0 | 0 | 100
863 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur , SM/10658 | New | Additional work in connection with sinking of (150mmX100mmX150mtr) RBTW by Rotary method at Daspur water supply scheme, tube well no.-1 of Sabang Block of PaschimMidnapur Dist. under MMD PHE Dte. | 175/MMSD-I | 17/02/2022 | 7 | DEBJYOTI BASU | 0.35 | 0 | 0 | 80
864 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur , SM/10658 | New | QUOTATION FOR NEW POWER CONNECTION OF DASPUR MINI WATER SUPPLY ASCHEME [ APPLICATION --2004478402, REFERENCE ID ----204120945, SABONG CCC, QUOTATION NO ---2004478402/QUOT/03 DATED 26/10/2023, SCHEME NAME --- DASPUR MINI. , SCHEME CODE ---SM/10658 , MB NO--3580 ] | BP-2023-24-344 | 10/11/2023 | 0 | WBSEDCL | 3.98 | 0 | 0 | 0
865 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur , SM/10658 | New | Electric quotation Sabang CCC at Daspur, Bankibheri Pin-721434 ( 2003870026) | BP-2022-23-123 | 09/03/2023 | 0 | WBSEDCL | 0.12 | 0 | 0 | 0
866 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur , SM/10658 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Daspur (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 2184/MD | 01/11/2022 | 150 | S.N ENTERPRISE | 35.12 | 0 | 0 | 80
867 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur , SM/10658 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well-II at Daspur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 558/W/MMD | 12/04/2022 | 1032 | SUBHAM ENTERPRISE | 6.44 | 0 | 0 | 100
868 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur , SM/10658 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well-I at Daspur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 557/W/MMD | 12/04/2022 | 120 | RITESH ENTERPRISE | 6.49 | 0 | 0 | 100
869 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur , SM/10658 | New | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 0 | 100
870 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur , SM/10658 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Daspur (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 2185/MD | 01/11/2022 | 882 | S.T. ENTERPRISE | 37.32 | 0 | 0 | 80
871 | PASCHIM MEDINIPUR | Midnapore Division | TORIA PIPED WATER SUPPLY SCHEME , SM/18494 | New | Material Requisition To Resource Division | 110/MD | 10/01/2023 | 0 | Resource Division | 15.28 | 0 | 0 | 0
872 | PASCHIM MEDINIPUR | Midnapore Division | TORIA PIPED WATER SUPPLY SCHEME , SM/18494 | New | Material Requisition To Resource Division | 3368/MD | 25/11/2024 | 0 | Resource Division | 16.64 | 0 | 0 | 0
873 | PASCHIM MEDINIPUR | Midnapore Mechanical | TORIA PIPED WATER SUPPLY SCHEME , SM/18494 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of TORIA PWSS. REF CONSUMER ID-204248200, APPLICATION NO-2004645189, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-893 | 22/03/2024 | 0 | WBSEDCL | 7.19 | 0 | 0 | 0
874 | PASCHIM MEDINIPUR | Midnapore Mechanical | TORIA PIPED WATER SUPPLY SCHEME , SM/18494 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF TORIA PWSS. REF CONSUMER ID-204370272, APPLICATION NO-2004843239 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESPUR | C082421721033 | 16/08/2024 | 0 | WBSEDCL | 5.29 | 0 | 0 | 0
875 | PASCHIM MEDINIPUR | Midnapore Mechanical | TORIA PIPED WATER SUPPLY SCHEME , SM/18494 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TORIA PIPED WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | 1690/W/MMD | 04/08/2023 | 180 | UTTAM KUMAR CHATTERJEE | 25.25 | 0 | 0 | 30
876 | PASCHIM MEDINIPUR | Midnapore Division | TORIA PIPED WATER SUPPLY SCHEME , SM/18494 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,702 nos.) under JJM with allied work for Torai PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 3149/MD | 29/08/2023 | 900 | BANERJEE CONSTRUCTION | 869.66 | 0 | 0 | 35
877 | PASCHIM MEDINIPUR | Midnapore Division | TORIA PIPED WATER SUPPLY SCHEME , SM/18494 | New | Laying of rising main & interconnection for Toria & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 625 Mtr.) | 320/MD | 29/01/2025 | 45 | MAA SARADA ENTERPRISE | 6.43 | 0 | 0 | 0
878 | PASCHIM MEDINIPUR | Midnapore Division | DUBRAJI AND ITS ADJOINING MOUZAS PWSS , SM/18533 | New | Material Requisition To Resource Division | 178/MD | 16/01/2023 | 0 | Resource Division | 23.7 | 0 | 0 | 0
879 | PASCHIM MEDINIPUR | Midnapore Mechanical | DUBRAJI AND ITS ADJOINING MOUZAS PWSS , SM/18533 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DUBRAJI AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | 1692/W/MMD | 04/08/2023 | 180 | A.S.ENTERPRISE | 27.34 | 0 | 0 | 40
880 | PASCHIM MEDINIPUR | Midnapore Division | DUBRAJI AND ITS ADJOINING MOUZAS PWSS , SM/18533 | New | Material Requisition To Resource Division | 3488/MD | 25/11/2024 | 0 | Resource Division | 18.82 | 0 | 0 | 0
881 | PASCHIM MEDINIPUR | Midnapore Mechanical | DUBRAJI AND ITS ADJOINING MOUZAS PWSS , SM/18533 | New | Quotation for new power connection at Dubraji PWSS P/H- II , application no - 2004609001 , Ref id - 204222611 | BP-2023-24-778 | 06/03/2024 | 0 | WBSEDCL | 6.46 | 0 | 0 | 0
882 | PASCHIM MEDINIPUR | Midnapore Mechanical | DUBRAJI AND ITS ADJOINING MOUZAS PWSS , SM/18533 | New | Quotation for new power connection at Dubraji PWSS P/H- I , application no - 2004608941 , Ref id - 204222615 | BP-2023-24-777 | 06/03/2024 | 0 | WBSEDCL | 1.81 | 0 | 0 | 0
883 | PASCHIM MEDINIPUR | Midnapore Division | DUBRAJI AND ITS ADJOINING MOUZAS PWSS , SM/18533 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 Cum OHR (Intze type with Pile Foundation) & Accommodate FHTC (3,056 nos.) under JJM with allied work including 02 (Two ) Years Operation & Maintenance for Dubraji & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 3258/MD | 12/09/2023 | 720 | TAPAS SANTRA | 927.59 | 0 | 0 | 75
884 | PASCHIM MEDINIPUR | Midnapore Division | DUBRAJI AND ITS ADJOINING MOUZAS PWSS , SM/18533 | New | Route survey & way leave permission along & across of National Highway in Dubraji PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | 588/MD | 03/03/2025 | 21 | DONA ASSOCIATES | 10.21 | 0 | 0 | 0
885 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. , SM/06933 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sartla W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | GOBINDA MAITY | 20 | 0 | 0 | 0
886 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. , SM/06933 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443107 | 12/02/2021 | 0 | GANESH CH NANDY | 0.2 | 0 | 0 | 0
887 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. , SM/06933 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443017 | 12/02/2021 | 0 | TANMOY BERA | 0.2 | 0 | 0 | 0
888 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. , SM/06933 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443107 | 12/02/2021 | 0 | PARTHA PRATIM PAL | 0.03 | 0 | 0 | 0
889 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. , SM/06933 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443107 | 12/02/2021 | 0 | SHRABONTI BERA | 0.2 | 0 | 0 | 0
890 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. , SM/06933 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sartla W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1455/MD | 26/11/2020 | 180 | GOBINDA MAITY | 90.73 | 59.8 | 65.91 | 90
891 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. , SM/06900 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Katan W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1447/MD | 26/11/2020 | 180 | SHAKEEL KHAN | 45.04 | 16.25 | 36.07 | 0
892 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. , SM/06900 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Katan W/S Scheme, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | SHAKEEL KHAN | 30 | 0 | 0 | 0
893 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. , SM/06900 | Retrofitting | Restoration of road damaged during carrying of pipe line and allied works of KATAN water supply scheme within Ghatal Sub-Division under Midnapore Division, P.H.E. Dte. (Node- 102-105) | 806/AE/GSD | 16/12/2021 | 10 | DEVJYOTI BERA | 0.62 | 0 | 0 | 0
894 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. , SM/06900 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Katan W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | BP-2021-22-414 | 24/02/2022 | 0 | SHAKEEL KHAN | 14.25 | 0 | 0 | 0
895 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. , SM/06900 | Retrofitting | Retrofitting to accommodate Additional FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE(PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Katan Water Supply Scheme (Paschim Para) within Ghatal Dev. Block under Ghatal Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | 147/AE/GSD | 17/02/2023 | 30 | DEVJYOTI BERA | 3.57 | 0 | 0 | 0
896 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. , SM/06900 | Retrofitting | Retrofitting to accommodate Additional FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE(PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Katan Water Supply Scheme (Paschim Para) within Ghatal Dev. Block under Ghatal Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | 149/AE/GSD | 21/02/2023 | 30 | DEVJYOTI BERA | 3.57 | 0 | 0 | 10
897 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Beluria Piped Water Supply Scheme. , SM/06908 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Beluria W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | M/S. A.R. ENTERPRISE. | 35 | 0 | 0 | 0
898 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Beluria Piped Water Supply Scheme. , SM/06908 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Beluria W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1470/MD | 26/11/2020 | 180 | M/S. A.R. ENTERPRISE. | 92.63 | 69.1 | 74.59 | 100
899 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chhotokhelna Piped Water Supply Scheme. , SM/06914 | Retrofitting | Restoration of distribution pipe line damage due to construction of road by PMGSY in different mouzas required for covering FHTC works of Chhoto Khelna & its adjoining mouza Water Supply Scheme within Pingla Block under Midnapore Division, P.H.E. Dte. | BP-2021-22-373 | 17/02/2022 | 0 | WATER LINK | 15 | 0 | 0 | 0
900 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chhotokhelna Piped Water Supply Scheme. , SM/06914 | Retrofitting | Restoration of distribution pipe line damage due to construction of road by PMGSY in different mouzas required for covering FHTC works of Chhoto Khelna & its adjoining mouza Water Supply Scheme within Pingla Block under Midnapore Division, P.H.E. Dte. | 844328 | 08/03/2022 | 0 | WATER LINK | 0.41 | 0 | 0 | 0
901 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chhotokhelna Piped Water Supply Scheme. , SM/06914 | Retrofitting | Laying of additional distribution pipe line in different places and extention of pipe line for accomodation FHTC works of Chhotokhelna and its adjoining mouza Water Supply Scheme at Pingla Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | 380/AE/KSD | 30/06/2022 | 30 | ASHIM KUMAR DEY | 4.55 | 0 | 0 | 0
902 | PASCHIM MEDINIPUR | Central Drilling | Retrofitting to accommodate FHTC under JJM in Chhotokhelna Piped Water Supply Scheme. , SM/06914 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 240 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR AUGMENTATION OF MIDNAPORE MEDICAL COLLEGE & HOSPITAL W/S SCH (TW-I) UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | 1076/CDD | 28/10/2022 | 30 | PADMA ENGINEERING & CO. | 16.51 | 0 | 0 | 0
903 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chhotokhelna Piped Water Supply Scheme. , SM/06914 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chhotokhelna W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1431/MD | 26/11/2020 | 180 | ASHIM KUMAR DEY | 93.67 | 50.77 | 77.91 | 80
904 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barsahara PWSS , SM/06926 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barsahara W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1467/MD | 26/11/2020 | 180 | DULAL CHANDRA DAS | 94.66 | 65.87 | 69.58 | 0
905 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barsahara PWSS , SM/06926 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barsahara W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | DULAL CHANDRA DAS | 20 | 0 | 0 | 0
906 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barsahara PWSS , SM/06926 | Retrofitting | FHTC data entry. | 844335 | 08/12/2021 | 0 | SHRABONTI BERA | 0.16 | 0 | 0 | 0
907 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barsahara PWSS , SM/06926 | Retrofitting | FHTC data entry. | 844335 | 08/12/2021 | 0 | ANIRBAN CHAKRABORTY | 0.09 | 0 | 0 | 0
908 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barsahara PWSS , SM/06926 | Retrofitting | FHTC data entry. | 844335 | 08/12/2021 | 0 | TANMOY BERA | 0.07 | 0 | 0 | 0
909 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barsahara PWSS , SM/06926 | Retrofitting | FHTC data entry. | 844335 | 08/12/2021 | 0 | SOVANDEB MANNA | 0.06 | 0 | 0 | 0
910 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barsahara PWSS , SM/06926 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Pump House for Sansahara & Manikarah villages within Barsahara PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 584/MD | 23/02/2023 | 60 | DULAL CHANDRA DAS | 17.7 | 0 | 0 | 10
911 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kolanda Piped Water Supply Scheme. , SM/06928 | Retrofitting | Construction of Boundary wall & Land Development for Head work site of Kolanda & its adjoining mouzas Water Supply Scheme at Sabang Block under Midnapore Sadar Sub- Division within Midnapore Division, PHE. Dte. (81/EE/MD/2017-2018) | 844338 | 10/05/2023 | 0 | KAILASH KUMAR AGARWALA | 1.44 | 0 | 0 | 0
912 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kolanda Piped Water Supply Scheme. , SM/06928 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kolanda W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1452/MD | 26/11/2020 | 180 | M/S. A.R. ENTERPRISE. | 86.63 | 34.5 | 39.82 | 77
913 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Julkapur PWSS , SM/06929 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Julkapur W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1454/MD | 26/11/2020 | 180 | SUNIL DULE | 48.8 | 22.25 | 45.6 | 0
914 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Julkapur PWSS , SM/06929 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Julkapur W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 844397 | 08/03/2021 | 0 | SUNIL DULE | 25 | 0 | 0 | 0
915 | PASCHIM MEDINIPUR | Central Drilling | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. , SM/09084 | Retrofitting | RESISTIVITY SURVEY AND OTHER WORKS OF MALLARPUR W/S SCHEME (TW-II), PINGLA BLOCK, PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | 1683/CDD | 28/12/2022 | 30 | M/S PS & ASSOCIATES | 5.85 | 0 | 0 | 0
916 | PASCHIM MEDINIPUR | Central Drilling | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. , SM/09084 | Retrofitting | RESISTIVITY SURVEY AND OTHER WORKS OF MALLARPUR W/S SCHEME (TW-I), PINGLA BLOCK, UNDER PASCHIM MIDNAPOR DISTRICT, CDD, PHE DTE. | 1727/CDD | 29/12/2022 | 30 | MENAKA ENTERPRISE | 6.19 | 0 | 0 | 0
917 | PASCHIM MEDINIPUR | Central Drilling | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. , SM/09084 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN MALLARPUR TW-II, PASCHIM MEDINIPUR DISTRICT, UNDER CDD, PHE DTE. | 425/CMSD-I | 12/08/2022 | 15 | UTTAM KUMAR CHATTERJEE | 4.95 | 0 | 0 | 0
918 | PASCHIM MEDINIPUR | Central Drilling | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. , SM/09084 | Retrofitting | Hiring of Diesel driven motor cab(BS-III & Above) having contract carriage permit along with driver for the office of the Superintending Engineer, M/E PMU WBDWSIP under CMSD-I, CDD, PHE Dte. | 635/CMSD-I(D) | 26/12/2022 | 59 | SIDDHARTHA CHATTERJEE | 0.29 | 0 | 0 | 0
919 | PASCHIM MEDINIPUR | Central Drilling | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. , SM/09084 | Retrofitting | PROVIDING DRIILING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR SARBERYA W/S SCHEME (TW-I), UNDER PASCHIM MEDINIPUR DISTRICT, CDD, PHE DTE. | 1726/CDD | 29/12/2022 | 30 | MENAKA ENTERPRISE | 11.86 | 0 | 0 | 100
920 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. , SM/09084 | Retrofitting | Material Requisition To Resource Division | 3415/MD | 25/11/2024 | 0 | Resource Division | 6.02 | 0 | 0 | 0
921 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbar PWSS, Block - Ghatal, District - Paschim Medinipur. , SM/09086 | Retrofitting | Continuation Work Order for the work of Additional retrofitting to accommodate FHTC under JJM for Khasbar (Zone-II) PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division PHE Dte. | 753/MD | 13/03/2023 | 45 | S.T. ENTERPRISE | 11.47 | 0 | 0 | 0
922 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbar PWSS, Block - Ghatal, District - Paschim Medinipur. , SM/09086 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khasbar (Zone-II) PWSS under Ghatal Block in Paschim Medinipur District. | 29/MD | 07/01/2022 | 30 | S.T. ENTERPRISE | 37.86 | 0 | 0 | 100
923 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbar PWSS, Block - Ghatal, District - Paschim Medinipur. , SM/09086 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khasbar (Zone-I) PWSS under Ghatal Block in Paschim Medinipur District. | 2187/MD | 17/12/2021 | 721 | M/S. D.K.H.CONSTRUCTION | 75.89 | 0 | 0 | 50
924 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-B) | 532/AE/KSD | 17/12/2021 | 30 | ADITYA ENTERPRISE | 4.85 | 0 | 0 | 0
925 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-C) | 533/AE/KSD | 17/12/2021 | 30 | HYDRO TECH ASSOCIATES | 4.85 | 0 | 0 | 0
926 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-H) | 538/AE/KSD | 17/12/2021 | 30 | M/S. BLUE BIRD | 4.85 | 0 | 0 | 0
927 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-I) | 539/AE/KSD | 17/12/2021 | 30 | SAJAL JANA | 4.84 | 0 | 0 | 0
928 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-K) | 541/AE/KSD | 17/12/2021 | 30 | M/S. SUBHAS CHANDRA KUNDU | 4.85 | 0 | 0 | 0
929 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part- E) | 535/AE/KSD | 17/12/2021 | 30 | R. CONSTRUCTION | 4.85 | 0 | 0 | 0
930 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-F) | 536/AE/KSD | 17/12/2021 | 30 | FUTURE CONSTRUCTION | 4.85 | 0 | 0 | 0
931 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part- J) | 540/AE/KSD | 17/12/2021 | 30 | SUJOY RANJAN BHOWMICK | 4.85 | 0 | 0 | 0
932 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-G) | 537/AE/KSD | 17/12/2021 | 30 | RITESH AGARWALL | 4.85 | 0 | 0 | 0
933 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-L) | 542/AE/KSD | 17/12/2021 | 30 | M/S SARADA CONSTRUCTION | 4.85 | 0 | 0 | 0
934 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-D) | 534/AE/KSD | 17/12/2021 | 30 | OM UDYUG | 4.85 | 0 | 0 | 0
935 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-M) | 543/AE/KSD | 17/12/2021 | 30 | S.K. CONSTRUCTION | 4.85 | 0 | 0 | 0
936 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-A) | 531/AE/KSD | 17/12/2021 | 30 | BOSE & CO. | 4.84 | 0 | 0 | 0
937 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Distribution pipe line for accommodation of FHTC under JJM for the Lutunia Water Supply Scheme, Block-Sabang, District- Paschim Midnapore.(Part-I) | 66/AE/KSD | 03/02/2022 | 15 | M/S SARADA CONSTRUCTION | 4.01 | 0 | 0 | 0
938 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Distribution pipe line for accommodation of FHTC under JJM for the Lutunia Water Supply Scheme, Block-Sabang, District- Paschim Midnapore.(Part-II) | 67/AE/KSD | 03/02/2022 | 15 | SUJOY RANJAN BHOWMICK | 4 | 0 | 0 | 0
939 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Laying pipeline (Distribution System) at Mouza Lutunia (Prembazar) for Augmentation of ground water based piped water Supply Schemes to accommodate FHTC under JJM under Sabang Block under Midnapore Division, P.H.E. Dte. | 419/AE/KSD | 19/07/2022 | 30 | PALASH KUMAR DAS | 4.69 | 0 | 0 | 0
940 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Purchasing of Materials. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 7.59 | 0 | 0 | 0
941 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate PHTC. Block - Sabang. District - Paschim Medinipur. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 7.59 | 0 | 0 | 0
942 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Tap Connection of existing PWSS (Lutunia, Block - Sabang) to be Retrofitting under Midnapore Division, PHE Dte. | 1007/MD | 24/06/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.7 | 0 | 0 | 0
943 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Augmentation of Ground Water Based Piped W/S Scheme for Lutunia to Accommodate FHTC (Balance = 300 Nos.) under JJM under Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | 342/MD | 31/01/2023 | 60 | UTTAM KUMAR DAS | 67.59 | 0 | 0 | 65
944 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Tube Well-IV of Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | 1348/W/MMD | 24/05/2023 | 180 | SUJOY RANJAN BHOWMICK | 11.88 | 0 | 0 | 100
945 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Material Requisition To Resource Division | 2129/MD | 14/12/2021 | 0 | Resource Division | 7.59 | 0 | 0 | 0
946 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. , SM/09432 | Augmentation | Accommodate FHTC including supplying, laying, fitting, fixing pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Lutunia W/S Scheme under JJM within Sabang Dev. Block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | 2035/MD | 01/07/2024 | 484 | RITESH AGARWALL | 11.85 | 0 | 0 | 80
947 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Chatra in Chatra PWSS of Garhbeta-II Block in the district of Paschim Medinipur (Phase-I) | 392/MD | 25/02/2021 | 15 | SUNIL DULE | 7.93 | 6.48 | 100 | 0
948 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Sutkujuri in Sutkijhuri PWSS of Garhbeta-II Block in the district of Paschim Medinipur (Phase-I) | 393/MD | 25/02/2021 | 15 | SUNIL DULE | 7.93 | 6.83 | 100 | 0
949 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Abashgarh Paschim Para in Abashgarh PWSS of Midnapore Sadar Block in the district of Paschim Medinipur (Phase-I). | 409/MD | 26/02/2021 | 15 | WATER LINK | 7.15 | 5.46 | 45.38 | 0
950 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza ¿ Bagmari, Bhabrigeria in Chaita PWSS of Salboni Block in the district of Paschim Medinipur (Phase-I) | 391/MD | 25/02/2021 | 30 | PRADIP KUMAR SAHA | 14.17 | 13.07 | 100 | 0
951 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Amrakuchi in Amrakuchi PWSS of Keshpur Block in the district of Paschim Medinipur (Phase-I) | 406/MD | 26/02/2021 | 15 | PULLOCK KUMAR GHOSH | 7.89 | 0 | 0 | 0
952 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Sekhuasol, Bhalukasol & Dalang in Dalang PWSS of Keshpur Block in the district of Paschim Medinipur (Phase-I) | 407/MD | 26/02/2021 | 45 | M/S. D.K.H.CONSTRUCTION | 29.01 | 27.2 | 79.53 | 0
953 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Pathra in Pathra PWSS of Midnapore Sadar Block in the district of Paschim Medinipur (Phase-I) | 423/MD | 26/02/2021 | 30 | SANJIT SINHA | 14.46 | 2.19 | 13.59 | 0
954 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Jagul, Raghabchak & Belpatri in Jagul PWSS of Midnapore Sadar Block in the district of Paschim Medinipur (Phase-I) | 408/MD | 26/02/2021 | 45 | DULAL CHANDRA DAS | 29 | 28.23 | 100 | 0
955 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Benashuli, Nayagram & Bhadute in Nayagram PWSS of Midnapore Sadar Block in the district of Paschim Medinipur (Phase-I) | 422/MD | 26/02/2021 | 30 | SANJIT SINHA | 19.29 | 5.52 | 22.33 | 0
956 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Sekhuasol, Bhalukasol & Dalang in Dalang PWSS of Keshpur Block in the district of Paschim Medinipur (Phase-I) |  | 09/03/2021 | 0 | M/S. D.K.H.CONSTRUCTION | 22 | 0 | 0 | 0
957 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC (left out) at different mouzas and shifting of pipeline in connection with widenening and strengthening of road for Chaita PWSS & its adjoining mouzas W/S Scheme within Midnapore Division ,PHE Dte. (SL No-06) | 280/AE/MSSD | 15/06/2022 | 30 | AJITESH ACHARJEE | 3.98 | 0 | 0 | 0
958 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dalang W/S Scheme. | BP-2021-22-96 | 10/03/2022 | 0 | M/S. D.K.H.CONSTRUCTION | 0.49 | 0 | 0 | 0
959 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Abashgarh Purba Para in Abashgarh PWSS in Midnapore Sadar Block in the District of Paschim Medinipore.(SL No-12) | BP-2021-22-413 | 24/02/2022 | 0 | WATER LINK | 4.84 | 0 | 0 | 0
960 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dalang W/S Scheme. | BP-2021-22-96 | 10/03/2022 | 0 | M/S. D.K.H.CONSTRUCTION | 1.28 | 0 | 0 | 0
961 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Lohamelya PWSS of Jhargram Block under Jhargram Division, PHE Dte. (Phase-II) | 1059/MD | 02/07/2021 | 15 | NIMAI LAL GURIA | 7.53 | 0 | 0 | 1
962 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Dhengasole Uttar Para in Dhengasole PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-01) | 98/AE/MSSD | 24/02/2021 | 15 | CHANDAN YADAV | 4.8 | 3.66 | 100 | 0
963 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Chaita in Chaita PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-04) | 96/AE/MSSD | 23/02/2021 | 15 | AJITESH ACHARJEE | 4.81 | 3.66 | 49.44 | 0
964 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Jamdoba in Jamdoba PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-09) | 103/AE/MSSD | 24/02/2021 | 15 | A R ENTERPRISE | 1.96 | 1.15 | 100 | 0
965 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. , SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Godamouli in Jamdoba PWSS in Salboni Block in the District of Paschim Medinipore.(SLN o-08) | 102/AE/MSSD | 24/02/2021 | 15 | A R ENTERPRISE | 4.77 | 4.74 | 32.15 | 0
966 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Sutkujhuri Piped Water Supply Scheme to accommodate all FHTC. , SM/08205 | Retrofitting | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. 55/MD | 8443497 | 30/03/2021 | 0 | SIRCON ENGINEERING SERVICES | 1.5 | 0 | 0 | 0
967 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Sutkujhuri Piped Water Supply Scheme to accommodate all FHTC. , SM/08205 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Sutkijhuri, Block - Garhbeta-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | 55/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.87 | 0 | 0 | 0
968 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Sutkujhuri Piped Water Supply Scheme to accommodate all FHTC. , SM/08205 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Sutkujhuri PWSS to accommodate FHTC under JJM under Garhbeta-II block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 281/MD | 15/02/2022 | 30 | MANISHIKA CONSTRUCTION | 21.78 | 0 | 0 | 100
969 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ukhla Piped Water Supply Scheme to accommodate all FHTC. , SM/08211 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Ukhla Paschim Para in Ukhla PWSS (Part-B) in Garhbeta II Block in the District of Paschim Medinipore.(SL.NO-11) | 107/AE/MSSD | 26/02/2021 | 15 | AJIJUR RAHAMAN MALLICK | 4.83 | 3.22 | 66.69 | 0
970 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ukhla Piped Water Supply Scheme to accommodate all FHTC. , SM/08211 | Retrofitting | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. |  | 19/03/2021 | 0 | SIRCON ENGINEERING SERVICES | 2.39 | 0 | 0 | 0
971 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ukhla Piped Water Supply Scheme to accommodate all FHTC. , SM/08211 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Ukhla PWSS to accommodate FHTC under JJM under Garhbeta -II block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 282/MD | 15/02/2022 | 60 | GOUTAM RAY | 43.53 | 0 | 0 | 0
972 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ukhla Piped Water Supply Scheme to accommodate all FHTC. , SM/08211 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Ukhla, Block - Garhbeta-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | 56/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.49 | 2.39 | 100 | 0
973 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ukhla Piped Water Supply Scheme to accommodate all FHTC. , SM/08211 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Ukhla Purba Para in Ukhla PWSS in Garhbeta II Block in the District of Paschim Medinipore.(SL No-10) | 106/AE/MSSD | 26/02/2021 | 15 | AJIJUR RAHAMAN MALLICK | 4.83 | 3.94 | 84.32 | 10
974 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbazar Piped Water Supply Scheme. , SM/06925 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khasbazar W/S Scheme, Block: - Debra, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1460/MD | 26/11/2020 | 180 | SUBRATA DAS | 92.69 | 59.03 | 71.08 | 0
975 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbazar Piped Water Supply Scheme. , SM/06925 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443110 | 12/02/2021 | 0 | SIDDHESWAR BAG | 0.21 | 0 | 0 | 0
976 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbazar Piped Water Supply Scheme. , SM/06925 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443110 | 12/02/2021 | 0 | PAPPU SHAW | 0.19 | 0 | 0 | 0
977 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbazar Piped Water Supply Scheme. , SM/06925 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443110 | 12/02/2021 | 0 | SUBRATA CHAKRABORTY | 0.18 | 0 | 0 | 0
978 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. , SM/09585 | Augmentation | Continuation work order for the work of Round the Clock Guarding Arrangements to protect the Govt. properties / materials etc. at different Places of Kharagpur Sub-Division Stores / Office premises stackyard etc. under Midnapore Division, PHE Dte. [For the period 4 months i.e. from 01.04.2021 to 31.07.2021] [Considering Zone - 'A' as per Joint Labour Commissioner order vide Memo No. - 352 /Stat/2RW/76/266/LCS/JLC, Dated - 27.12.2019] | 606/MD | 30/03/2021 | 122 | M/S. OXFORD SECURITY SERVICE | 3.75 | 0 | 0 | 0
979 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. , SM/09585 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Ranirbazar (Block-Ghatal) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1647/MD | 22/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.02 | 0 | 0 | 0
980 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. , SM/09585 | Augmentation | Electric quotation Ghatal CCC at Ranisimulia, Ranirbazar Water supply scheme under MMD PHE Dte | BP-2022-23-58 | 23/11/2022 | 0 | WBSEDCL | 0.3 | 0 | 0 | 0
981 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. , SM/09585 | Augmentation | Purchasing of materials for the augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal. District - Paschim Medinipur. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 13.67 | 0 | 0 | 0
982 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. , SM/09585 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-II under Ranirbazar water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist - Paschim Medinipur. | 2114/W/MMD | 28/11/2022 | 120 | M/S EMMESS | 11.37 | 0 | 0 | 0
983 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. , SM/09585 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-III under Ranirbazar water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist - Paschim Medinipur. | 1968/W/MMD | 20/10/2022 | 120 | BUSR ENGINEERING | 10.79 | 0 | 0 | 99
984 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. , SM/09585 | Augmentation | Exigency basis laying casing pipe under Bitumineous pucca road crosssing (Near Baliaghata bus stop,Bablatola Maruti Showroom,Chanak para Soni Mandir) of Khakurda to Ghatal PWD Road of Ranapur W/S Scheme within Ghatal Sub-Division, PHE.Dte. | 171/AE/GSD | 01/04/2022 | 2 | ANNAPURNA TUBEWELL WORKS | 3.64 | 0 | 0 | 0
985 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. , SM/09585 | Augmentation | Material Requisition To Resource Division | 2278/MD | 31/12/2021 | 0 | Resource Division | 13.67 | 0 | 0 | 0
986 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. , SM/09585 | Augmentation | Material Requisition To Resource Division | 225/MD | 02/02/2023 | 0 | Resource Division | 74.42 | 0 | 0 | 0
987 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. , SM/09585 | Augmentation | Chandrakona to Ghatal Road from Chainage 36.600 Kmp to 42.00 Kmp Restoration of damages due to laying of proposed underground pipeline by PHE Deptt in the district of Paschim Medinipur. | BP-2023-24-81 | 08/05/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 80 | 0 | 0 | 0
988 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. , SM/09585 | Augmentation | Supply of C.I.D.F. Sluice valve C.I.Jeffy coupler for distribution and rising main pipe line for Augmentation of Ranirbazar water supply scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte | 108/AE/GSD | 13/02/2023 | 170 | M/S. GEO | 3.59 | 0 | 0 | 100
989 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Chatra Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09106 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Chatra, Block - Garhbeta-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | 54/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.6 | 0 | 0 | 0
990 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Paschim Beguni PWSS under Debra Block in Paschim Medinipur District , SM/09711 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Paschim Beguni PWSS under Debra Block in Paschim Medinipur District. | 2002/MD | 01/12/2021 | 21 | M/S. EL-CON | 31.78 | 0 | 0 | 0
991 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10839 | Augmentation | Conducting of Route Survey and allied works in connection with the Functional Household Tap Connection of existing PWSS (Mohanpur, Block - Mohanpur) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | 1136/MD | 16/07/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.04 | 0 | 0 | 100
992 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10839 | Augmentation | Design of Distribution Network and preparation of DPR in connection with the Functional Household Tap Connection of existing PWSS (Mohanpur, Block - Mohanpur) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | 1144/MD | 19/07/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.49 | 0 | 0 | 100
993 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10839 | Augmentation | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kashida & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | 752/MD | 22/04/2022 | 20 | ENVIROTECH SOLUTIONS | 7.87 | 0 | 0 | 0
994 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10839 | Augmentation | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Sautia & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | 754/MD | 22/04/2022 | 20 | ENVIROTECH SOLUTIONS | 6.68 | 0 | 0 | 0
995 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10839 | Augmentation | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Borai & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | 753/MD | 22/04/2022 | 20 | ENVIROTECH SOLUTIONS | 5.24 | 0 | 0 | 0
996 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10839 | Augmentation | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Jarisai & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | 755/MD | 22/04/2022 | 20 | ENVIROTECH SOLUTIONS | 6.63 | 0 | 0 | 0
997 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10839 | Augmentation | Continuation Work Order for the work of Laying Balance (Part) Distribution System to accommodate FHTC of Proposed Augmentation Pipe Water Supply Scheme for Mohanpur & its adjoining Mouzas, Block: - Mohanpur, District: - Paschim Midnapore. (Total Length = 18,000.00 Mtr.) | 382/MD | 03/02/2023 | 60 | GOBINDA MAITY | 87.47 | 0 | 0 | 79
998 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10839 | Augmentation | Sinking of 1 (One) no. 250 X 150 mm dia. X 200 mtr. Depth deep tube well by direct rotary method for Augmentation of Mohanpur W/S Scheme within Mohanpur Block under Midnapore Division, P.H.E. Dte. | 446/MD | 13/02/2023 | 10 | GOBINDA MAITY | 11.7 | 0 | 0 | 100
999 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10839 | Augmentation | Material Requisition To Resource Division | 1363/MD | 02/05/2023 | 0 | Resource Division | 61.09 | 0 | 0 | 0
1000 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10839 | Augmentation | Electrict Quotation Bill for mohanpur water supply scheme (consumer ID-203995501) | BP-2023-24-228 | 05/09/2023 | 0 | WBSEDCL | 2.3 | 0 | 0 | 0
1001 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10839 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 877/W/MMD | 27/03/2023 | 180 | JOYSHREE CONCERN | 11.85 | 0 | 0 | 51
1002 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10839 | Augmentation | Laying Distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 550 Cum (Pile foundation) and staging height 20.00 mtr. & FHTC under JJM with allied work for Augmentation of Mohanpur and its adjoining mouzas W/S scheme in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 1961/MD | 20/09/2022 | 1164 | GOBINDA MAITY | 658.99 | 0 | 0 | 95
1003 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kashijora PWSS under Salbani Block in Paschim Medinipur District , SM/09705 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza -Bara Bhursa in Kashijora PWSS in Salboni Block District :- Paschim Medinipur within Midnapore Division, PHE Dte.(SL No-02) | 649/AE/MSSD | 14/12/2021 | 15 | MAITY ENTERPRISE | 4.5 | 0 | 0 | 0
1004 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kashijora PWSS under Salbani Block in Paschim Medinipur District , SM/09705 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza-Chhoto Bhursa in Kashijora PWSS in Salboni Block District Paschim Medinipore within Midnapore Division PHE Dte.(SL No-01) | 653/AE/MSSD | 14/12/2021 | 15 | MAITY ENTERPRISE | 4.5 | 0 | 0 | 0
1005 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kashijora PWSS under Salbani Block in Paschim Medinipur District , SM/09705 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza -Deulkunda in Kashijora PWSS in Salboni Block District :- Paschim Medinipur within Midnapore Division, PHE Dte.(SL No-03) | 656/AE/MSSD | 17/12/2021 | 15 | MAITY ENTERPRISE | 3.49 | 0 | 0 | 0
1006 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kashijora PWSS under Salbani Block in Paschim Medinipur District , SM/09705 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza -Baradiha in Kashijora PWSS in Salboni Block District :- Paschim Medinipur within Midnapore Division, PHE Dte.(SL No-04) | BP-2021-22-432 | 04/03/2022 | 0 | MAITY ENTERPRISE | 4.44 | 0 | 0 | 0
1007 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kashijora PWSS under Salbani Block in Paschim Medinipur District , SM/09705 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza ¿Kashijora in Kashijora PWSS in Salboni Block District Paschim Medinipore within Midnapore Division PHE Dte.(SL No-01) | 532/AE/MSSD | 30/09/2021 | 15 | MAITY ENTERPRISE | 4.85 | 0 | 0 | 0
1008 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10717 | New | Service Connection charges of WBSEDCL at Krishnaballavpur P/H-I | BP-2022-23-95 | 11/01/2023 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
1009 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10717 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | 2315/W/MMD | 29/12/2022 | 180 | M/S EMMESS | 6.01 | 0 | 0 | 80
1010 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10717 | New | Material Requisition To Resource Division | 3354/MD | 25/11/2024 | 0 | Resource Division | 1.15 | 0 | 0 | 0
1011 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10717 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Krishnaballabhpur, Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 345/MD | 31/01/2023 | 700 | M/S. SOMNATH | 43.6 | 0 | 0 | 90
1012 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Construction of M.S. Fabricated and R.C.C Supporting Structure including aligning pipe line in connection of laying distribution main of Jote Kanuramgarh & Ranichak Water supply scheme under Midnapore Division P.H.E. Dte. | 453/MD | 13/02/2023 | 60 | GOBINDA MAITY | 50.85 | 0 | 0 | 60
1013 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Construction of Approach Road, Land development (workable to running const. work) at Head Works of Ranichak Water Supply Scheme, Block: - Daspur- I, District: - Paschim Medinipur under Midnapore Division P.H.E. Dte. | 2476/MD | 14/07/2023 | 21 | GOBINDA MAITY | 8.23 | 0 | 0 | 100
1014 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Material Requisition To Resource Division | 881/MD | 29/03/2023 | 0 | Resource Division | 37.57 | 0 | 0 | 0
1015 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Material Requisition To Resource Division | 903/MD | 31/03/2023 | 0 | Resource Division | 37.56 | 0 | 0 | 0
1016 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 22-23-707,8,9 | 13/03/2023 | 0 | GOBINDA MAITY | 61 | 0 | 0 | 0
1017 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Electric quotaion for tw-I of Ranichak w/s scheme(consumar ID-203974580) | BP-2023-24-20 | 28/04/2023 | 0 | WBSEDCL | 3 | 0 | 0 | 0
1018 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Electric quotation for tw-II of Ranichak w/s scheme(consumar ID-203974585) | BP-2023-24-19 | 28/04/2023 | 0 | WBSEDCL | 2.15 | 0 | 0 | 0
1019 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. under JJM Program under MMD PHE Dte. | 2312/W/MMD | 29/12/2022 | 180 | ECO ENTERPRISE | 25.26 | 0 | 0 | 100
1020 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Material Requisition To Resource Division | 3346/MD | 25/11/2024 | 0 | Resource Division | 17 | 0 | 0 | 0
1021 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2364/MD | 21/11/2022 | 1242 | GOBINDA MAITY | 1460.37 | 0 | 0 | 58
1022 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 1211/MMSD-I | 29/09/2023 | 92 | SUBHASIS ROY | 0.45 | 0 | 0 | 0
1023 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Laying additional distribution system pipe line & accommodate FHTC (650 Nos.) for Ranichak W/S Scheme under JJM within Daspur-II Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2789/MD | 03/09/2024 | 424 | GOBINDA MAITY | 60.71 | 0 | 0 | 30
1024 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. , SM/11624 | New | Laying of Rising main including interconnection of Ranichak & its adjoining mouzas W/S Scheme under Daspur-II block within Ghatal Sub-Division of Midnapore Division, PHE Dte. | 197/MD | 17/01/2025 | 30 | PALASH KUMAR DAS | 6.38 | 0 | 0 | 100
1025 | PASCHIM MEDINIPUR | Midnapore Division | MURAKATA AND ADJOINING MOUJAS PWSS , SM/13100 | New | Material Requisition To Resource Division | 1174/MD | 26/04/2023 | 0 | Resource Division | 30.14 | 0 | 0 | 0
1026 | PASCHIM MEDINIPUR | Midnapore Mechanical | MURAKATA AND ADJOINING MOUJAS PWSS , SM/13100 | New | Quotation for new power connection at Murakata PWSS , Application no - 2004644754 , Ref ID - 204248051 | BP-2024-25-81 | 24/04/2024 | 0 | WBSEDCL | 3.11 | 0 | 0 | 0
1027 | PASCHIM MEDINIPUR | Midnapore Mechanical | MURAKATA AND ADJOINING MOUJAS PWSS , SM/13100 | New | Quotation for new power connection at Murakata PWSS tw- II within Narayangarh block Application No- 2004844779 Ref No - 204369553 | C092443182572 | 27/09/2024 | 0 | WBSEDCL | 4.16 | 0 | 0 | 0
1028 | PASCHIM MEDINIPUR | Midnapore Mechanical | MURAKATA AND ADJOINING MOUJAS PWSS , SM/13100 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of MURAKATA PWSS. REF CONSUMER ID-204204417, APPLICATION NO-2004578935, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2023-24-637 | 08/02/2024 | 0 | WBSEDCL | 4.64 | 0 | 0 | 0
1029 | PASCHIM MEDINIPUR | Central Drilling | MURAKATA AND ADJOINING MOUJAS PWSS , SM/13100 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1030 | PASCHIM MEDINIPUR | Midnapore Division | MURAKATA AND ADJOINING MOUJAS PWSS , SM/13100 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (5,751 Nos.) including 2 years operation & maintenance For Kunarpur, Murakata & Nayapukur Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2827/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 1515.85 | 0 | 0 | 15
1031 | PASCHIM MEDINIPUR | Midnapore Division | PAKURSENI AND ADJOINING MOUJAS PWSS , SM/13104 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
1032 | PASCHIM MEDINIPUR | Midnapore Division | PAKURSENI AND ADJOINING MOUJAS PWSS , SM/13104 | New | Material Requisition To Resource Division | 1528/MD | 12/05/2023 | 0 | Resource Division | 33.2 | 0 | 0 | 0
1033 | PASCHIM MEDINIPUR | Midnapore Mechanical | PAKURSENI AND ADJOINING MOUJAS PWSS , SM/13104 | New | Quotation for new power connection at Pakurseni PWSS , Application no - 2004644720 , Ref ID - 204248038 | BP-2023-24-896 | 28/03/2024 | 0 | WBSEDCL | 3.38 | 0 | 0 | 0
1034 | PASCHIM MEDINIPUR | Midnapore Mechanical | PAKURSENI AND ADJOINING MOUJAS PWSS , SM/13104 | New | Quotation for new power connection at Pakurseni PWSS T/W - II under Narayangarh block , application no - 2004739517 , ref no - 204309706 | BP-2024-25-233 | 04/06/2024 | 0 | WBSEDCL | 4.43 | 0 | 0 | 0
1035 | PASCHIM MEDINIPUR | Central Drilling | PAKURSENI AND ADJOINING MOUJAS PWSS , SM/13104 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1036 | PASCHIM MEDINIPUR | Midnapore Division | PAKURSENI AND ADJOINING MOUJAS PWSS , SM/13104 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
1037 | PASCHIM MEDINIPUR | Midnapore Division | SINGLA AND IT'S ADJOINING MOUJAS , SM/13110 | New | Material Requisition To Resource Division | 1244/MD | 27/04/2023 | 0 | Resource Division | 20.52 | 0 | 0 | 0
1038 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SINGLA AND IT'S ADJOINING MOUJAS , SM/13110 | New | WBSEDCL new connection payment for singla t/w 1 | 52/JMD | 29/04/2024 | 0 | WBSEDCL | 3.49 | 0 | 0 | 0
1039 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SINGLA AND IT'S ADJOINING MOUJAS , SM/13110 | New | WBSEDCL new connection payment for singla t/w 2 | 53/JMD | 29/04/2024 | 0 | WBSEDCL | 3.13 | 0 | 0 | 0
1040 | PASCHIM MEDINIPUR | Central Drilling | SINGLA AND IT'S ADJOINING MOUJAS , SM/13110 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1041 | PASCHIM MEDINIPUR | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS , SM/13069 | New | Laying of Rising main, distribution pipe line & Accommodate FHTC (397 Nos.) including 2 years operation & maintenance under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 3005/MD | 21/08/2023 | 60 | SUDHAMAY MAJUMDAR | 115.72 | 0 | 0 | 0
1042 | PASCHIM MEDINIPUR | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS , SM/13069 | New | Material Requisition To Resource Division | 375/MD | 03/02/2023 | 0 | Resource Division | 26.6 | 0 | 0 | 0
1043 | PASCHIM MEDINIPUR | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS , SM/13069 | New | Construction of Pump House & Accommodate FHTC (150 Nos.) under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-F] | 1429/MD | 04/05/2023 | 60 | AJITESH ACHARJEE | 22.19 | 0 | 0 | 30
1044 | PASCHIM MEDINIPUR | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS , SM/13069 | New | Laying distribution pipe line & Accommodate FHTC (100 Nos.) under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 1430/MD | 04/05/2023 | 45 | M/S. ZAMAN ENTERPRISE | 24.56 | 0 | 0 | 10
1045 | PASCHIM MEDINIPUR | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS , SM/13069 | New | Laying distribution pipe line, Boundary wall & Accommodate FHTC (400 Nos.) under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | 2810/MD | 07/08/2023 | 60 | APURBA PATRA | 86.47 | 0 | 0 | 10
1046 | PASCHIM MEDINIPUR | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS , SM/13069 | New | Sinking of 2 nos. Tube well under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 2624/MD | 24/07/2023 | 30 | MASUM CONSTRUCTION | 16.28 | 0 | 0 | 95
1047 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BENUCHA AND ADJOINING MOUJAS PWSS , SM/13069 | New | New service connection charges for Benucha pwss, t/w no.II | 35/JMD | 11/03/2024 | 0 | WBSEDCL | 3.22 | 0 | 0 | 0
1048 | PASCHIM MEDINIPUR | Central Drilling | BENUCHA AND ADJOINING MOUJAS PWSS , SM/13069 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1049 | PASCHIM MEDINIPUR | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS , SM/13069 | New | Construction of 200 cum OHR (Intze type with solid raft) & Accommodate FHTC (400 Nos.) under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | 800/MD | 24/03/2025 | 180 | M/S BISWANATH CONSTRUCTION | 96.22 | 0 | 0 | 0
1050 | PASCHIM MEDINIPUR | Midnapore Division | BABALPUR AND ADJOINING MOUJAS PWSS , SM/13754 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
1051 | PASCHIM MEDINIPUR | Midnapore Division | BABALPUR AND ADJOINING MOUJAS PWSS , SM/13754 | New | Material Requisition To Resource Division | 189/MD | 16/01/2023 | 0 | Resource Division | 15.7 | 0 | 0 | 0
1052 | PASCHIM MEDINIPUR | Midnapore Division | BABALPUR AND ADJOINING MOUJAS PWSS , SM/13754 | New | Material Requisition To Resource Division | 3446/MD | 25/11/2024 | 0 | Resource Division | 8.57 | 0 | 0 | 0
1053 | PASCHIM MEDINIPUR | Midnapore Mechanical | BABALPUR AND ADJOINING MOUJAS PWSS , SM/13754 | New | Quotation for new power connection at Babalpur PWSS T/W - I , Application no- 2004790923, Ref no : 204339889 | C072438232052 | 23/07/2024 | 0 | WBSEDCL | 3.57 | 0 | 0 | 0
1054 | PASCHIM MEDINIPUR | Midnapore Mechanical | BABALPUR AND ADJOINING MOUJAS PWSS , SM/13754 | New | Quotation for new power connection at Babalpur PWSS T/W - II , Application no- 2004790929, Ref no : 204339891 | C072438248345 | 23/07/2024 | 0 | WBSEDCL | 2.91 | 0 | 0 | 0
1055 | PASCHIM MEDINIPUR | Central Drilling | BABALPUR AND ADJOINING MOUJAS PWSS , SM/13754 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1056 | PASCHIM MEDINIPUR | Midnapore Mechanical | BABALPUR AND ADJOINING MOUJAS PWSS , SM/13754 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
1057 | PASCHIM MEDINIPUR | Midnapore Division | BHANSRA AND ADJOINING MOUJAS PWSS , SM/13005 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | 746/MD | 13/03/2023 | 30 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 0
1058 | PASCHIM MEDINIPUR | Midnapore Division | BHANSRA AND ADJOINING MOUJAS PWSS , SM/13005 | New | Material Requisition To Resource Division | 1309/MD | 28/04/2023 | 0 | Resource Division | 33.81 | 0 | 0 | 0
1059 | PASCHIM MEDINIPUR | Midnapore Mechanical | BHANSRA AND ADJOINING MOUJAS PWSS , SM/13005 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BHANSRA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 1404/W/MMD | 02/06/2023 | 720 | DEBJYOTI BASU | 22.78 | 0 | 0 | 20
1060 | PASCHIM MEDINIPUR | Central Drilling | BHANSRA AND ADJOINING MOUJAS PWSS , SM/13005 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 220 Mtrs. Depth) by utilising Departmental Machineries for BHANSRA W/S Scheme (T/W-I & II) , Keshiery Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | 389/CDD | 18/05/2023 | 419 | PADMA ENGINEERING & CO. | 25.43 | 0 | 0 | 50
1061 | PASCHIM MEDINIPUR | Midnapore Mechanical | BHANSRA AND ADJOINING MOUJAS PWSS , SM/13005 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF BHANSRA PWSS. REF CONSUMER ID-204370484, APPLICATION NO-2004846729, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | C082448282150 | 02/09/2024 | 0 | WBSEDCL | 3.62 | 0 | 0 | 0
1062 | PASCHIM MEDINIPUR | Midnapore Division | CHHATNI AND ADJOINING MOUJAS PWSS , SM/13007 | New | Material Requisition To Resource Division | 1261/MD | 28/04/2023 | 0 | Resource Division | 19.58 | 0 | 0 | 0
1063 | PASCHIM MEDINIPUR | Central Drilling | CHHATNI AND ADJOINING MOUJAS PWSS , SM/13007 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1064 | PASCHIM MEDINIPUR | Central Drilling | KUSUMPUR AND ADJOINING MOUJAS , SM/13093 | New | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 220Mtrs. Depth) by utilising Departmental machineries for Kusumpur W/S Scheme (T/W-I & II) Keshiary Block under Paschim Medinipur District CDD PHE Dte. | 1094/CDD | 18/08/2023 | 30 | PADMA ENGINEERING & CO. | 25.33 | 0 | 0 | 100
1065 | PASCHIM MEDINIPUR | Midnapore Division | KUSUMPUR AND ADJOINING MOUJAS , SM/13093 | New | Material Requisition To Resource Division | 1319/MD | 28/04/2023 | 0 | Resource Division | 29.75 | 0 | 0 | 0
1066 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUSUMPUR AND ADJOINING MOUJAS , SM/13093 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUSUMPUR AND ADJOINING MOUJASunder JJM Program under MMD PHE Dte. | 3079/W/MMD | 29/11/2023 | 180 | BINAPANI ENTERPRISE | 23.01 | 0 | 0 | 0
1067 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUSUMPUR AND ADJOINING MOUJAS , SM/13093 | New | Electric quotation bill for Tw No-I of Kusumpur PWSS. Ref Consumer ID-204136077. | BP-2023-24-385 | 02/12/2023 | 0 | WBSEDCL | 3.66 | 0 | 0 | 0
1068 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUSUMPUR AND ADJOINING MOUJAS , SM/13093 | New | Electric quotation bill for Tw No-II of Kusumpur PWSS.(Ref Consumer ID-204136080). | BP-2023-24-386 | 02/12/2023 | 0 | WBSEDCL | 1.84 | 0 | 0 | 0
1069 | PASCHIM MEDINIPUR | Central Drilling | KUSUMPUR AND ADJOINING MOUJAS , SM/13093 | New | Hiring of Diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Superintending Engineer, M/E, PMU WBDWSIP P.H.E. Dte. under CMSD-I(D), CDD, P.H.E. Dte. | 291/CMSD-I(D) | 18/12/2023 | 182 | SIDDHARTHA CHATTERJEE | 0.89 | 0 | 0 | 0
1070 | PASCHIM MEDINIPUR | Midnapore Division | KASHBAASANDA AND ADJOINING MOUJAS PWSS at Narayangrah under Midnapore Division P.H.E.Dte. , SM/12331 | New | Material Requisition To Resource Division | 1175/MD | 26/04/2023 | 0 | Resource Division | 28.44 | 0 | 0 | 0
1071 | PASCHIM MEDINIPUR | Midnapore Mechanical | KASHBAASANDA AND ADJOINING MOUJAS PWSS at Narayangrah under Midnapore Division P.H.E.Dte. , SM/12331 | New | Quotation for new power connection at Kasba Asanda PWSS T/W - I Within Narayangarh Block Application No - 2004987922, Ref ID- 204460782 |  | 24/12/2024 | 0 | WBSEDCL | 3.7 | 0 | 0 | 0
1072 | PASCHIM MEDINIPUR | Central Drilling | KASHBAASANDA AND ADJOINING MOUJAS PWSS at Narayangrah under Midnapore Division P.H.E.Dte. , SM/12331 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1073 | PASCHIM MEDINIPUR | Midnapore Division | KASHBAASANDA AND ADJOINING MOUJAS PWSS at Narayangrah under Midnapore Division P.H.E.Dte. , SM/12331 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 0 | 20
1074 | PASCHIM MEDINIPUR | Midnapore Division | KASHBAASANDA AND ADJOINING MOUJAS PWSS at Narayangrah under Midnapore Division P.H.E.Dte. , SM/12331 | New | Improvement of approach road of Kasbasanda PWSS Head work site under Narayangarh block within Midnapore Division, PHE Dte. [Length 60.0 Mtr. X Width 2.0 Mtr. (av.) X Depth 1.50 Mtr. (av.)] | 996/AE/HQ/MD | 22/04/2025 | 30 | GOURMOHAN DAS | 2.31 | 0 | 0 | 0
1075 | PASCHIM MEDINIPUR | Midnapore Division | BAR JHIKURIA AND ITS ADJOINING MOUJAS PWSS , SM/12200 | New | Material Requisition To Resource Division | 1161/MD | 25/04/2023 | 0 | Resource Division | 21.02 | 0 | 0 | 0
1076 | PASCHIM MEDINIPUR | Midnapore Division | BAR JHIKURIA AND ITS ADJOINING MOUJAS PWSS , SM/12200 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 0 | 25
1077 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAR JHIKURIA AND ITS ADJOINING MOUJAS PWSS , SM/12200 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAR JHIKURIA AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 792/W/MMD | 24/03/2023 | 892 | M/S B.M. ELECTRICAL | 21.56 | 0 | 0 | 40
1078 | PASCHIM MEDINIPUR | Midnapore Division | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME , SM/12997 | New | Material Requisition To Resource Division | 99/MD | 10/01/2023 | 0 | Resource Division | 28.38 | 0 | 0 | 0
1079 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME , SM/12997 | New | Additional quatation for service connection charge for effecting NSC at Radhaballavpur PWSS vide Application 2004305845. | BP-2023-24-234 | 07/09/2023 | 0 | WBSEDCL | 1.91 | 0 | 0 | 0
1080 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME , SM/12997 | New | Electric quotation bill for new connection at Tw-I of Radhaballabhpur water supply scheme. Consumer ID-204030193. | BP-2023-24-127 | 13/07/2023 | 0 | WBSEDCL | 0.28 | 0 | 0 | 0
1081 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME , SM/12997 | New | Electric quotation bill for new connection at Tw No-II of Radhaballabhpur water supply scheme. Consumer ID-204018509. | BP-2023-24-126 | 13/07/2023 | 0 | WBSEDCL | 0.28 | 0 | 0 | 0
1082 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME , SM/12997 | New | Additional quotation for service connection charge for effecting NSC vide Application No-2004305839. | BP-2023-24-233 | 07/09/2023 | 0 | WBSEDCL | 2.14 | 0 | 0 | 0
1083 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME , SM/12997 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RADHABALLABHPUR PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | 833/W/MMD | 24/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 23.76 | 0 | 0 | 50
1084 | PASCHIM MEDINIPUR | Midnapore Division | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME , SM/12997 | New | Laying Rising main from 2nd tube well to 1st tube well to OHR for Radhaballavpur & its adjoining mouzas W/S Scheme within Keshpur block under Midnapore Division, PHE Dte. (Length of pipe line = 360.00 Mtr.) | 374/MD | 12/02/2024 | 30 | MAMPI ENTERPRISE | 9.73 | 0 | 0 | 0
1085 | PASCHIM MEDINIPUR | Midnapore Division | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME , SM/12997 | New | Material Requisition To Resource Division | 3383/MD | 25/11/2024 | 0 | Resource Division | 14.62 | 0 | 0 | 0
1086 | PASCHIM MEDINIPUR | Midnapore Division | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME , SM/12997 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with Pile foundation) & Accommodate FHTC (2374 Nos.) under JJM with allied work for Radhaballavpur & its adjoining mouzas W/S scheme in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 578/MD | 23/02/2023 | 1147 | DULAL CHANDRA DAS | 647.61 | 0 | 0 | 4
1087 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME , SM/12997 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | 842/MMSD-I | 11/06/2025 | 243 | M/S BIKASH DE | 3.66 | 0 | 0 | 0
1088 | PASCHIM MEDINIPUR | Midnapore Division | DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS , SM/12999 | New | Material Requisition To Resource Division | 1283/MD | 28/04/2023 | 0 | Resource Division | 29.58 | 0 | 0 | 0
1089 | PASCHIM MEDINIPUR | Midnapore Mechanical | DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS , SM/12999 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 648/W/MMD | 20/03/2023 | 180 | MANIK CHANDRA SAHA | 21.56 | 0 | 0 | 25
1090 | PASCHIM MEDINIPUR | Midnapore Mechanical | DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS , SM/12999 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of DAKSHIN AMRIA PWSS. REF CONSUMER ID-204310379 APPLICATION NO-2004739365 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-205 | 28/05/2024 | 0 | WBSEDCL | 3.79 | 0 | 0 | 0
1091 | PASCHIM MEDINIPUR | Midnapore Mechanical | DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS , SM/12999 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF DAKSHIN AMRIA PWSS. REF CONSUMER ID-204389348, APPLICATION NO-2004882536, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | C092442004530 | 27/09/2024 | 0 | WBSEDCL | 9.74 | 0 | 0 | 0
1092 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. , SM/12876 | New | Material Requisition To Resource Division | 943/MD | 05/04/2023 | 0 | Resource Division | 32.7 | 0 | 0 | 0
1093 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. , SM/12876 | New | Material Requisition To Resource Division | 3342/MD | 25/11/2024 | 0 | Resource Division | 31.37 | 0 | 0 | 0
1094 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. , SM/12876 | New | Electrict quotation bill for utta Bar water supply scheme zone-I Pump house no-I(consumar Id-204139570) | BP-2023-24-378 | 02/12/2023 | 0 | WBSEDCL | 4.3 | 0 | 0 | 0
1095 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. , SM/12876 | New | Electrict quotation bill for uttar Bar Zone-I Pump house NO-II (Consumar Id-204139580) | BP-2023-24-377 | 02/12/2023 | 0 | WBSEDCL | 2.7 | 0 | 0 | 0
1096 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. , SM/12876 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. under JJM Program under MMD PHE Dte. | 573/W/MMD | 20/03/2023 | 820 | DEY ENTERPRISE | 25.26 | 0 | 0 | 90
1097 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. , SM/12876 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. under JJM Program under MMD PHE Dte. (Part-II) | 868/W/MMD | 27/03/2023 | 889 | M/S B.M. ELECTRICAL | 23.01 | 0 | 0 | 65
1098 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. , SM/12876 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 2 nos. 400 cum OHR (Intze type with pile foundation) & 3 Nos. 300 Cum OHR & Accommodate FHTC (10,944 Nos,) under JJM with allied work for (i) Chaipat (Zone-I & Zone-II) & its adjoining mouzas W/S scheme (ii) Kelegoda & its adjoining mouzas W/S Scheme (iii) Uttarbar (Zone-I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2556/MD | 15/12/2022 | 1238 | M/S. S.S. ENTERPRISE | 2473.34 | 0 | 0 | 18
1099 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. , SM/12876 | New | Laying of Rising main pipeline for Uttarbar (Zone-II) PWSS under Daspur-II block within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2581/MD | 22/08/2024 | 45 | FIROJ KHAN | 4.91 | 0 | 0 | 0
1100 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. , SM/12876 | New | Laying of Rising main pipeline for Uttarbar (Zone-I) PWSS under Daspur-II block within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2580/MD | 22/08/2024 | 45 | FIROJ KHAN | 6.19 | 0 | 0 | 0
1101 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. , SM/12876 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
1102 | PASCHIM MEDINIPUR | Midnapore Division | KADAM BANDHI AND ADJOINING MOUJAS PWSS , SM/13058 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
1103 | PASCHIM MEDINIPUR | Midnapore Division | KADAM BANDHI AND ADJOINING MOUJAS PWSS , SM/13058 | New | Material Requisition To Resource Division | 1202/MD | 26/04/2023 | 0 | Resource Division | 22.29 | 0 | 0 | 0
1104 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KADAM BANDHI AND ADJOINING MOUJAS PWSS , SM/13058 | New | New Service connection charges. | 80/JMD | 20/03/2024 | 0 | WBSEDCL | 6.26 | 0 | 0 | 0
1105 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KADAM BANDHI AND ADJOINING MOUJAS PWSS , SM/13058 | New | New service connection for Kadambandi t/w-1 water supply scheme | 43/JMD | 11/03/2024 | 0 | WBSEDCL | 5.01 | 0 | 0 | 0
1106 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KADAM BANDHI AND ADJOINING MOUJAS PWSS , SM/13058 | New | New service connection for Nayabasat T/W-1 water supply scheme | 46/JMD | 11/03/2024 | 0 | WBSEDCL | 4.58 | 0 | 0 | 0
1107 | PASCHIM MEDINIPUR | Central Drilling | KADAM BANDHI AND ADJOINING MOUJAS PWSS , SM/13058 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1108 | PASCHIM MEDINIPUR | Midnapore Division | KARANJIMURA AND ADJOINING MOUJAS PWSS , SM/13061 | New | Material Requisition To Resource Division | 1316/MD | 28/04/2023 | 0 | Resource Division | 25.89 | 0 | 0 | 0
1109 | PASCHIM MEDINIPUR | Central Drilling | KARANJIMURA AND ADJOINING MOUJAS PWSS , SM/13061 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Karanjimura W/S Scheme (T/W-I & II), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | 1092/CDD | 18/08/2023 | 299 | PADMA ENGINEERING & CO. | 25.33 | 0 | 0 | 100
1110 | PASCHIM MEDINIPUR | Midnapore Mechanical | KARANJIMURA AND ADJOINING MOUJAS PWSS , SM/13061 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF KARANJIMURA PWSS. REF CONSUMER ID-204283800, APPLICATION NO-2004695735 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2024-25-268 | 12/06/2024 | 0 | WBSEDCL | 7.94 | 0 | 0 | 0
1111 | PASCHIM MEDINIPUR | Midnapore Mechanical | KARANJIMURA AND ADJOINING MOUJAS PWSS , SM/13061 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF KARANJIMURA PWSS. REF CONSUMER ID-204283801, APPLICATION NO-2004695741, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2024-25-269 | 12/06/2024 | 0 | WBSEDCL | 3.19 | 0 | 0 | 0
1112 | PASCHIM MEDINIPUR | Midnapore Mechanical | KARANJIMURA AND ADJOINING MOUJAS PWSS , SM/13061 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KARANJIMURA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 3084/W/MMD | 29/11/2023 | 672 | SUJOY RANJAN BHOWMICK | 21.58 | 0 | 0 | 20
1113 | PASCHIM MEDINIPUR | Midnapore Division | KHURSI AND ADJOINING MOUJAS PWSS , SM/13126 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
1114 | PASCHIM MEDINIPUR | Midnapore Division | KHURSI AND ADJOINING MOUJAS PWSS , SM/13126 | New | Material Requisition To Resource Division | 1479 | 10/05/2023 | 0 | Resource Division | 33.34 | 0 | 0 | 0
1115 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHURSI AND ADJOINING MOUJAS PWSS , SM/13126 | New | Quotation for new power connection at Khurshi PWSS P/H- I , application no - 2004609043 , Ref id - 204223722 | bp-2023-24-783 | 06/03/2024 | 0 | WBSEDCL | 3.44 | 0 | 0 | 0
1116 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHURSI AND ADJOINING MOUJAS PWSS , SM/13126 | New | Quotation for new power connection at Khurshi PWSS T/W no - II of Narayangarh block Application no - 2004754862 , Ref ID - 204323387 | BP-2024-25-343 | 25/06/2024 | 0 | WBSEDCL | 5.95 | 0 | 0 | 0
1117 | PASCHIM MEDINIPUR | Central Drilling | KHURSI AND ADJOINING MOUJAS PWSS , SM/13126 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1118 | PASCHIM MEDINIPUR | Midnapore Division | KHURSI AND ADJOINING MOUJAS PWSS , SM/13126 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
1119 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Balichak Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09420 | Retrofitting | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Tap Connection of existing PWSS (Balichak, Block - Debra) to be Retrofitting under Midnapore Division, PHE Dte. | 996/MD | 23/06/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 3.59 | 0 | 0 | 0
1120 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Balichak Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09420 | Retrofitting | Accommodate FHTC (3,350 Nos.) including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE (PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Balichak W/S Scheme within Debra Dev. block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | 2220/MD | 19/07/2024 | 60 | ASHIM KUMAR DEY | 144.99 | 0 | 0 | 0
1121 | PASCHIM MEDINIPUR | Midnapore Mechanical | MALIGHATI AND ITS ADJOINING MOUJAS PWSS , SM/13027 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MALIGHATI AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 2387/W/MMD | 31/12/2022 | 180 | BALAJI CONSTRUCTION | 22.89 | 0 | 0 | 0
1122 | PASCHIM MEDINIPUR | Midnapore Division | MALIGHATI AND ITS ADJOINING MOUJAS PWSS , SM/13027 | New | Material Requisition To Resource Division | 1509/MD | 12/05/2023 | 0 | Resource Division | 26.87 | 0 | 0 | 0
1123 | PASCHIM MEDINIPUR | Midnapore Mechanical | MALIGHATI AND ITS ADJOINING MOUJAS PWSS , SM/13027 | New | Electrict quotation bill for TW-II of Malighati pwss (Ref Consumar ID-204391665),Application No-2004886446,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | C092443140214 | 27/09/2024 | 0 | WBSEDCL | 3.8 | 0 | 0 | 0
1124 | PASCHIM MEDINIPUR | Midnapore Mechanical | MALIGHATI AND ITS ADJOINING MOUJAS PWSS , SM/13027 | New | Electrict quotation bill for TW-I of Malighati (Ref Consumar ID-204391662),Application No-2004886364, Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | C092443138989 | 27/09/2024 | 0 | WBSEDCL | 1.19 | 0 | 0 | 0
1125 | PASCHIM MEDINIPUR | Midnapore Division | MALIGHATI AND ITS ADJOINING MOUJAS PWSS , SM/13027 | New | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, 300 cum OHR (Intze type with solid raft) & Accommodate FHTC (1,763 Nos.) including 2 years operation & maintenance under JJM with allied work for Malighati & its adjoining mouzas W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 3054/MD | 23/08/2023 | 857 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 448.29 | 0 | 0 | 40
1126 | PASCHIM MEDINIPUR | Midnapore Division | RADHA KANTAPUR AND IT'S ADJOINING MOUJAS , SM/13034 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Radhakantapur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. [Name of Proposed PWSS Kalara & its adjoining Mouzas PWSS instead of Radhakantapur & its adjoining Mouzas PWSS] | 1055/MD | 02/06/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.43 | 0 | 0 | 100
1127 | PASCHIM MEDINIPUR | Midnapore Division | RADHA KANTAPUR AND IT'S ADJOINING MOUJAS , SM/13034 | New | Material Requisition To Resource Division | 1197 | 26/04/2023 | 0 | Resource Division | 22.67 | 0 | 0 | 0
1128 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHA KANTAPUR AND IT'S ADJOINING MOUJAS , SM/13034 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RADHA KANTAPUR AND IT'S ADJOINING MOUJAS under JJM Program under MMD PHE Dte. | 800/W/MMD | 24/03/2023 | 1013 | KAMAKSHYA ENTERPRISE | 21.57 | 0 | 0 | 15
1129 | PASCHIM MEDINIPUR | Midnapore Division | RADHA KANTAPUR AND IT'S ADJOINING MOUJAS , SM/13034 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 0 | 25
1130 | PASCHIM MEDINIPUR | Midnapore Division | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS , SM/13035 | New | Material Requisition To Resource Division | 2227/MD | 15/06/2023 | 0 | Resource Division | 36.62 | 0 | 0 | 0
1131 | PASCHIM MEDINIPUR | Midnapore Mechanical | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS , SM/13035 | New | Electrict quotation bill for TW-I of Ramchandrapur pwss (Ref Consumar ID-204369740),Application No-2004844151,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | C082430134176 | 20/08/2024 | 0 | WBSEDCL | 3.18 | 0 | 0 | 0
1132 | PASCHIM MEDINIPUR | Midnapore Mechanical | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS , SM/13035 | New | Electrict quotation bill for TW-II of Ramchandrapur pwss (Ref Consumar ID-204369742),Application No-2004844160,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | C082430133485 | 20/08/2024 | 0 | WBSEDCL | 3.37 | 0 | 0 | 0
1133 | PASCHIM MEDINIPUR | Midnapore Division | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS , SM/13035 | New | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, Boundary Wall, 300 cum OHR (Intze type with solid raft) & Accommodate FHTC (1,832 Nos.) including 2 years operation & maintenance under JJM with allied work for Ramchandrapur & its adjoining mouzas W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 3822/MD | 20/09/2023 | 876 | ASIS KUMAR SARANGI | 525.39 | 0 | 0 | 58
1134 | PASCHIM MEDINIPUR | Midnapore Mechanical | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS , SM/13035 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 482/W/MMD | 20/03/2023 | 873 | SAIKAT SINHA | 23.01 | 0 | 0 | 50
1135 | PASCHIM MEDINIPUR | Midnapore Division | BALADAGHATA AND ADJOINING MOUJAS PWSS , SM/12990 | New | Material Requisition To Resource Division | 1183/MD | 26/04/2023 | 0 | Resource Division | 42.44 | 0 | 0 | 0
1136 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BALADAGHATA AND ADJOINING MOUJAS PWSS , SM/12990 | New | NEW SERVICE CONNECTION CHARGES AT BALADGHATA TW-II WATER SUPPLY SCHEME | 255/JMD | 10/07/2024 | 0 | WBSEDCL | 5.07 | 0 | 0 | 0
1137 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BALADAGHATA AND ADJOINING MOUJAS PWSS , SM/12990 | New | NEW SERVICE CONNECTION CHARGES AT BALADGHATA TW-I WATER SUPPLY SCHEME | 254/JMD | 10/07/2024 | 0 | WBSEDCL | 5.02 | 0 | 0 | 0
1138 | PASCHIM MEDINIPUR | Central Drilling | BALADAGHATA AND ADJOINING MOUJAS PWSS , SM/12990 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1139 | PASCHIM MEDINIPUR | Midnapore Division | BARAMURA AND ADJOINING MOUJAS PWSS , SM/12994 | New | Material Requisition To Resource Division | 1184/MD | 26/04/2023 | 0 | Resource Division | 22.88 | 0 | 0 | 0
1140 | PASCHIM MEDINIPUR | Midnapore Division | BALIBANDH AND ADJOINING MOUJAS PWSS , SM/14990 | New | Material Requisition To Resource Division | 1254/MD | 28/04/2023 | 0 | Resource Division | 22.46 | 0 | 0 | 0
1141 | PASCHIM MEDINIPUR | Central Drilling | BALIBANDH AND ADJOINING MOUJAS PWSS , SM/14990 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1142 | PASCHIM MEDINIPUR | Midnapore Division | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS , SM/14995 | New | Material Requisition To Resource Division | 205/MD | 16/01/2023 | 0 | Resource Division | 17.35 | 0 | 0 | 0
1143 | PASCHIM MEDINIPUR | Midnapore Division | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS , SM/14995 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 300 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (1946 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Chakabdulla & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 5063/MD | 26/10/2023 | 720 | MIDNAPUR PIPE CONCERN | 522.11 | 0 | 0 | 55
1144 | PASCHIM MEDINIPUR | Midnapore Division | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS , SM/14995 | New | Material Requisition To Resource Division | 3426/MD | 25/11/2024 | 0 | Resource Division | 11.99 | 0 | 0 | 0
1145 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS , SM/14995 | New | Quotation for new power connection at Chak Abdulla PWSS P/H- I , application no - 2004608932 , Ref id - 204222608 | BP-2023-24-769 | 04/03/2024 | 0 | WBSEDCL | 2.79 | 0 | 0 | 0
1146 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS , SM/14995 | New | Quotation for new power connection at Chakabdullah PWSS t/w - II , khargpur - II block , Madpur CCC , Application No - 2004799237, Ref ID : 204344491 | BP-2024-25-482 | 30/07/2024 | 0 | WBSEDCL | 3.8 | 0 | 0 | 0
1147 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS , SM/14995 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 498/W/MMD | 20/03/2023 | 623 | GOENKA ENTERPRISE | 23.01 | 0 | 0 | 100
1148 | PASCHIM MEDINIPUR | Midnapore Division | KALAGRAM AND ITS ADJOINING MOUZAS PWSS , SM/15013 | New | Material Requisition To Resource Division | 101/MD | 10/01/2023 | 0 | Resource Division | 23.52 | 0 | 0 | 0
1149 | PASCHIM MEDINIPUR | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS , SM/15013 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 1685/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.29 | 0 | 0 | 100
1150 | PASCHIM MEDINIPUR | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS , SM/15013 | New | Fuel for Inspection Vehicle of covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission Program. [w.e.f. 01-01-2024 to 29-02-2024] | 1698/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.83 | 0 | 0 | 100
1151 | PASCHIM MEDINIPUR | Midnapore Division | KALAGRAM AND ITS ADJOINING MOUZAS PWSS , SM/15013 | New | Material Requisition To Resource Division | 3382/MD | 25/11/2024 | 0 | Resource Division | 16.98 | 0 | 0 | 0
1152 | PASCHIM MEDINIPUR | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS , SM/15013 | New | Electric Quotation bill for Tw No-II of kalagram PWSS. (ref Consumer ID-204128480) | BP-2023-24-388 | 02/12/2023 | 0 | WBSEDCL | 3.05 | 0 | 0 | 0
1153 | PASCHIM MEDINIPUR | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS , SM/15013 | New | Electric quotation bill for Tw No-I of Kalagram PWSS (Ref Consumer Id-204128489) | BP-2023-24-387 | 02/12/2023 | 0 | WBSEDCL | 3.43 | 0 | 0 | 0
1154 | PASCHIM MEDINIPUR | Midnapore Division | KALAGRAM AND ITS ADJOINING MOUZAS PWSS , SM/15013 | New | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, Construction of 400 CuM OHR (Intze type with Pile Foundation) & Accommodate FHTC (2,576 Nos.) under JJM with allied works for Kalagram PWSS in Keshpur Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Midnapur Sadar Sub-Division under Midnapore Division, PHE Dte. | 947/MD | 06/04/2023 | 1089 | DULAL CHANDRA DAS | 652.22 | 0 | 0 | 40
1155 | PASCHIM MEDINIPUR | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS , SM/15013 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0 | 0 | 50
1156 | PASCHIM MEDINIPUR | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS , SM/15013 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KALAGRAM AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 838/W/MMD | 24/03/2023 | 669 | SUJOY RANJAN BHOWMICK | 27.36 | 0 | 0 | 20
1157 | PASCHIM MEDINIPUR | Midnapore Division | KHARIKA AND ITS ADJOINING MOUZAS PWSS , SM/15015 | New | Material Requisition To Resource Division | 98/MD | 10/01/2023 | 0 | Resource Division | 18.9 | 0 | 0 | 0
1158 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHARIKA AND ITS ADJOINING MOUZAS PWSS , SM/15015 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHARIKA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 842/W/MMD | 24/03/2023 | 708 | ORIENTAL ENGINEERING CO. | 27.35 | 0 | 0 | 30
1159 | PASCHIM MEDINIPUR | Midnapore Division | KHARIKA AND ITS ADJOINING MOUZAS PWSS , SM/15015 | New | Material Requisition To Resource Division | 3384/MD | 25/11/2024 | 0 | Resource Division | 17.19 | 0 | 0 | 0
1160 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHARIKA AND ITS ADJOINING MOUZAS PWSS , SM/15015 | New | Electric quotation bill for Tw No-I of Kharika PWSS. (Ref Conumer ID-204182369) | BP-2023-24-563 | 16/01/2024 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
1161 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHARIKA AND ITS ADJOINING MOUZAS PWSS , SM/15015 | New | Electric quotation bill for Tw No-II of KHARIKA PWSS. (Ref Consumer ID-204195441), APPLICATION NO-2004564930, APPLICATION TYPE-NEW CONNECTION,NAME OF CCC-ANANDAPUR CCC, BLOCK-KESHPUR. | BP-2023-24-642 | 08/02/2024 | 0 | WBSEDCL | 4.79 | 0 | 0 | 0
1162 | PASCHIM MEDINIPUR | Midnapore Division | KHARIKA AND ITS ADJOINING MOUZAS PWSS , SM/15015 | New | Sinking Of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2790 Nos) under JJM with allied work for Kharika & its adjoining mouzas W/S scheme in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-division under Midnapore Division, PHE Dte. | 2421/MD | 13/07/2023 | 902 | BANERJEE CONSTRUCTION | 819.46 | 0 | 0 | 45
1163 | PASCHIM MEDINIPUR | Midnapore Division | KHARIKA AND ITS ADJOINING MOUZAS PWSS , SM/15015 | New | Laying of rising main & interconnection for Kharika & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 320 Mtr.) | 322/MD | 29/01/2025 | 45 | MAA SARADA ENTERPRISE | 5 | 0 | 0 | 0
1164 | PASCHIM MEDINIPUR | Midnapore Division | KUTKI AND ADJOINING MOUJAS PWSS , SM/15016 | New | Material Requisition To Resource Division | 1176/MD | 26/04/2023 | 0 | Resource Division | 27.09 | 0 | 0 | 0
1165 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUTKI AND ADJOINING MOUJAS PWSS , SM/15016 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUTKI AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. (Part-II) | 869/W/MMD | 27/03/2023 | 180 | JAL PRAVAHIKA PVT. LTD. | 11.95 | 0 | 0 | 0
1166 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUTKI AND ADJOINING MOUJAS PWSS , SM/15016 | New | Quotation for new power connection at Kutki PWSS T/W- I ,Narayangarh Block , Application no- 2004677554 , ref. Id - 204270807 | BP2024-25-152 | 09/05/2024 | 0 | WBSEDCL | 3.97 | 0 | 0 | 0
1167 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUTKI AND ADJOINING MOUJAS PWSS , SM/15016 | New | Quotation for new power connection at Kutki Pwss T/W - II within Narayangarh Block Application No- 2004857382 , Ref No - 204376545 | BP-2024-25-628 | 02/09/2024 | 0 | WBSEDCL | 3.96 | 0 | 0 | 0
1168 | PASCHIM MEDINIPUR | Central Drilling | KUTKI AND ADJOINING MOUJAS PWSS , SM/15016 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1169 | PASCHIM MEDINIPUR | Midnapore Division | KUTKI AND ADJOINING MOUJAS PWSS , SM/15016 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 0 | 20
1170 | PASCHIM MEDINIPUR | Midnapore Division | SOLPOTA AND ADJOINING MOUJAS PWSS , SM/13174 | New | Material Requisition To Resource Division | 1279/MD | 28/04/2023 | 0 | Resource Division | 40.33 | 0 | 0 | 0
1171 | PASCHIM MEDINIPUR | Midnapore Mechanical | SOLPOTA AND ADJOINING MOUJAS PWSS , SM/13174 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of SOLPOTA PWSS. REF CONSUMER ID-204310319 APPLICATION NO-2004739410, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-203 | 28/05/2024 | 0 | WBSEDCL | 6.75 | 0 | 0 | 0
1172 | PASCHIM MEDINIPUR | Midnapore Mechanical | SOLPOTA AND ADJOINING MOUJAS PWSS , SM/13174 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of SOLPOTA PWSS. REF CONSUMER ID-204310435 APPLICATION NO-2004739612, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-204 | 28/05/2024 | 0 | WBSEDCL | 6.41 | 0 | 0 | 0
1173 | PASCHIM MEDINIPUR | Midnapore Mechanical | SOLPOTA AND ADJOINING MOUJAS PWSS , SM/13174 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SOLPOTA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 647/W/MMD | 20/03/2023 | 892 | DEY ENTERPRISE | 21.57 | 0 | 0 | 20
1174 | PASCHIM MEDINIPUR | Midnapore Division | JADABBATI AND ADJOINING MOUJAS PWSS , SM/13143 | New | Material Requisition To Resource Division | 1185/MD | 26/04/2023 | 0 | Resource Division | 42.58 | 0 | 0 | 0
1175 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | JADABBATI AND ADJOINING MOUJAS PWSS , SM/13143 | New | NEW SERVICE CONNECTION CHARGES AT JADABBATI-I WATER SUPPLY SCHEME | 263/JMD | 23/07/2024 | 0 | WBSEDCL | 11.68 | 0 | 0 | 0
1176 | PASCHIM MEDINIPUR | Central Drilling | JADABBATI AND ADJOINING MOUJAS PWSS , SM/13143 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1177 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/13123 | Augmentation | Material Requisition To Resource Division | 1368/MD | 02/05/2023 | 0 | Resource Division | 38.07 | 0 | 0 | 0
1178 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/13123 | Augmentation | Quotation for Addl. TW-IV of Maligram W/S Scheme (Consumer ID 203971943) | BP-2023-24-35 | 04/05/2023 | 0 | WBSEDCL | 4.08 | 0 | 0 | 0
1179 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/13123 | Augmentation | Additional work in connection of Laying of Distribution pipe line for Augmentation of Maligram Pipe Water Supply Scheme under Pingla Block within Midnapore Division, PHE Dte. | 3404/MD | 25/11/2024 | 90 | UTTAM KUMAR DAS | 80.7 | 0 | 0 | 0
1180 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/13123 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Maligram PWSS Within Pingla Block under Midnapore Division P.H.E. Dte | 547/AE/KSD | 23/08/2022 | 30 | GOBINDA MAITY | 3.06 | 0 | 0 | 100
1181 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/13123 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 487/W/MMD | 20/03/2023 | 1032 | M/S MANABESH ROY | 22.93 | 0 | 0 | 40
1182 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/13123 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall for Augmentation of Maligram PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 297/MD | 24/01/2023 | 813 | M/S. D.K.H.CONSTRUCTION | 282.94 | 0 | 0 | 61
1183 | PASCHIM MEDINIPUR | Midnapore Division | SARANG AND ADJOINING MOUJAS PWSS , SM/13809 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
1184 | PASCHIM MEDINIPUR | Midnapore Division | SARANG AND ADJOINING MOUJAS PWSS , SM/13809 | New | Material Requisition To Resource Division | 209/MD | 16/01/2023 | 0 | Resource Division | 17 | 0 | 0 | 0
1185 | PASCHIM MEDINIPUR | Midnapore Division | SARANG AND ADJOINING MOUJAS PWSS , SM/13809 | New | Material Requisition To Resource Division | 3459/MD | 25/11/2024 | 0 | Resource Division | 13.88 | 0 | 0 | 0
1186 | PASCHIM MEDINIPUR | Midnapore Mechanical | SARANG AND ADJOINING MOUJAS PWSS , SM/13809 | New | Electric quotation bill for Tw No-I of Sarang water supply scheme.(ref consumer ID-204121968) | BP-2023-24-413 | 09/12/2023 | 0 | WBSEDCL | 4.75 | 0 | 0 | 0
1187 | PASCHIM MEDINIPUR | Midnapore Mechanical | SARANG AND ADJOINING MOUJAS PWSS , SM/13809 | New | Electric quotation bill for Tw No-II of Sarang PWSS .(Ref Conumer ID-204122250). | BP-2023-24-481 | 27/12/2023 | 0 | WBSEDCL | 5.73 | 0 | 0 | 0
1188 | PASCHIM MEDINIPUR | Midnapore Division | NAYA BASAT AND ADJOINING MOUJAS PWSS , SM/14130 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
1189 | PASCHIM MEDINIPUR | Midnapore Division | NAYA BASAT AND ADJOINING MOUJAS PWSS , SM/14130 | New | Material Requisition To Resource Division | 1203/MD | 26/04/2023 | 0 | Resource Division | 81.81 | 0 | 0 | 0
1190 | PASCHIM MEDINIPUR | Central Drilling | NAYA BASAT AND ADJOINING MOUJAS PWSS , SM/14130 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1191 | PASCHIM MEDINIPUR | Midnapore Division | KANKRISOL AND ADJOINING MOUJAS PWSS , SM/14033 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
1192 | PASCHIM MEDINIPUR | Midnapore Division | KANKRISOL AND ADJOINING MOUJAS PWSS , SM/14033 | New | Material Requisition To Resource Division | 1236/MD | 27/04/2023 | 0 | Resource Division | 19.02 | 0 | 0 | 0
1193 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KANKRISOL AND ADJOINING MOUJAS PWSS , SM/14033 | New | WBSEDCL new connection payment for Kankrisole t/w 1 | 68/JMD | 29/04/2024 | 0 | WBSEDCL | 5.11 | 0 | 0 | 0
1194 | PASCHIM MEDINIPUR | Central Drilling | KANKRISOL AND ADJOINING MOUJAS PWSS , SM/14033 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1195 | PASCHIM MEDINIPUR | Midnapore Division | KOREDAN AND ADJOINING MOUJAS PWSS , SM/14034 | New | Material Requisition To Resource Division | 1264/MD | 28/04/2023 | 0 | Resource Division | 26.72 | 0 | 0 | 0
1196 | PASCHIM MEDINIPUR | Central Drilling | KOREDAN AND ADJOINING MOUJAS PWSS , SM/14034 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1197 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/14720 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Kolanda PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1668/MD | 28/09/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 2.11 | 0 | 0 | 100
1198 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/14720 | Augmentation | Restoration of pipe line damaged due to construction of roads (Koptipur, Rautarabari, Bangaldari, Hijaltol Batitaki, Batuabazar etc.) & excess length of pipe in connection with FHTC work at Kolanda W/S Scheme at Sabang Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | 439/MD | 10/02/2023 | 45 | M/S. A.R. ENTERPRISE. | 68.31 | 0 | 0 | 100
1199 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/14720 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0 | 0 | 25
1200 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/14720 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0 | 0 | 100
1201 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/14720 | Augmentation | Electric quotation for Kolanda PWSS Tube Well-III WS Scheme (Ref. ID 203935156) | BP-2023-24-24 | 04/05/2023 | 0 | WBSEDCL | 1.78 | 0 | 0 | 0
1202 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/14720 | Augmentation | Service connection charges of WBSEDCL at TW-IV (Additional) of Kolanda Water Supply Scheme (Ref. ID - 203935153) |  | 22/03/2023 | 0 | WBSEDCL | 0.46 | 0 | 0 | 0
1203 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/14720 | Augmentation | Service connection charges of WBSEDCL at TW-III (Additional) of Kolanda Water Supply Scheme (Ref. ID - 203935156) |  | 22/03/2023 | 0 | WBSEDCL | 1.78 | 0 | 0 | 0
1204 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/14720 | Augmentation | Electric quotation for Kolanda PWSS Tube Well-IV WS Scheme (Ref. ID 203935153) |  | 25/03/2023 | 0 | WBSEDCL | 0.46 | 0 | 0 | 0
1205 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/14720 | Augmentation | Installation of Dept. Submersible Pump motor set and with other acessories and other allied works at Tubewell no 3 ( newly sunk ) of Kolanda Water Supply Scheme [ Block Sabong ] under MMD, PHE Dte. | 41/MMSD-I | 16/01/2024 | 7 | SHOVAN KUMAR DAS | 0.3 | 0 | 0 | 100
1206 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/14720 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte.under JJM Program under MMD PHE Dte. | 1426/W/MMD | 05/06/2023 | 666 | A.M.S. ENTERPRISE | 10.77 | 0 | 0 | 100
1207 | PASCHIM MEDINIPUR | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
1208 | PASCHIM MEDINIPUR | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Material Requisition To Resource Division | 3983/MD | 06/10/2023 | 0 | Resource Division | 54.29 | 0 | 0 | 0
1209 | PASCHIM MEDINIPUR | Midnapore Mechanical | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Electric quotation bill for Tw no-I of Piasala PWSS. (Ref ID- 204061141) | BP-2023-24-183 | 11/08/2023 | 0 | WBSEDCL | 2.75 | 0 | 0 | 0
1210 | PASCHIM MEDINIPUR | Midnapore Mechanical | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Electric quotation bill for Tw No-II of Piasala water supply scheme. (ref Id-204061139) | BP-2023-24-184 | 11/08/2023 | 0 | WBSEDCL | 2.82 | 0 | 0 | 0
1211 | PASCHIM MEDINIPUR | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Laying distribution pipe line, Pump House, Boundary wall & Accommodate FHTC (500 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | 1023/MD | 12/04/2023 | 60 | ASHIM KUMAR DEY | 137.59 | 0 | 0 | 0
1212 | PASCHIM MEDINIPUR | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Laying distribution pipe line & Accommodate FHTC (470 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-VI] | 937/MD | 04/04/2023 | 710 | J.K. BUILDERS | 82.89 | 0 | 0 | 100
1213 | PASCHIM MEDINIPUR | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Sinking of tube well & Accommodate FHTC (200 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-VIII] | 1385/MD | 02/05/2023 | 45 | DEBJIT PATRA | 29.29 | 0 | 0 | 50
1214 | PASCHIM MEDINIPUR | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Sinking of Tube well & Accommodate FHTC (200 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-I] | 936/MD | 04/04/2023 | 45 | ANNAPURNA TUBEWELL WORKS | 29.28 | 0 | 0 | 100
1215 | PASCHIM MEDINIPUR | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Laying distribution pipe line & Accommodate FHTC (307 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-VII] | 938/MD | 04/04/2023 | 60 | GOUTAM RAY | 52.89 | 0 | 0 | 53
1216 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | New Service connection charges. | 58/JMD | 08/02/2024 | 0 | WBSEDCL | 4.38 | 0 | 0 | 0
1217 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | New Service connection charges. | 59/JMD | 08/02/2024 | 0 | WBSEDCL | 5.04 | 0 | 0 | 0
1218 | PASCHIM MEDINIPUR | Central Drilling | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1219 | PASCHIM MEDINIPUR | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Construction Pump House, Boundary wall, Soil investigation, Construction of 450 cum OHR (Intze type with solid raft) & Accommodate FHTC (500 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-II] | 2144/MD | 11/07/2024 | 360 | KISHORE GHOSH | 179.06 | 0 | 0 | 5
1220 | PASCHIM MEDINIPUR | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Laying distribution pipe line, Rising main, Pump House, Boundary wall, Accommodate FHTC (450 nos.) & 2 years operation & maintenance under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-III] | 2145/MD | 11/07/2024 | 357 | KISHORE GHOSH | 130.76 | 0 | 0 | 30
1221 | PASCHIM MEDINIPUR | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS , SM/14628 | New | Laying of additional distribution pipeline for Piasala & its adjoining mouzas PWSS, Block - Garhbeta-II, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 699/MD | 12/03/2025 | 60 | SAFTI PRIVATE LIMITED | 11.63 | 0 | 0 | 0
1222 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15257 | New | Material Requisition To Resource Division | 190/MD | 16/01/2023 | 0 | Resource Division | 13.79 | 0 | 0 | 0
1223 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15257 | New | QUOTATION FOR NEW POWER CONNECTION OF RAGHUNATHPUR [ BONPATNA-I] WATER SUPPLY ASCHEME [ APPLICATION --2004479616, REFERENCE ID ----204122242, NIMPURA CCC, QUOTATION NO ---2004479616/QUOT/03 DATED 26/10/2023, SCHEME NAME --- RAGHUNATHPUR [ BONPATNA -I] . , SCHEME CODE ---SM/15257 , MB NO--3580 ] | BP-2023-24-349 | 10/11/2023 | 0 | WBSEDCL | 3.73 | 0 | 0 | 0
1224 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15257 | New | QUOTATION FOR NEW POWER CONNECTION OF RAGHUNATHPUR [ BONPATNA-II] WATER SUPPLY ASCHEME [ APPLICATION --2004479629, REFERENCE ID ----204122243, NIMPURA CCC, QUOTATION NO ---2004479629/QUOT/03 DATED 26/10/2023, SCHEME NAME --- RAGHUNATHPUR [ BONPATNA -II] . , SCHEME CODE ---SM/15257 , MB NO--3580 ] | BP-2023-24-348 | 10/11/2023 | 0 | WBSEDCL | 3.64 | 0 | 0 | 0
1225 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15257 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 350 Cum RCC Over Head Reservoir (Intze type with solid raft) & Accommodate FHTC (1976 Nos.) including Two years O&M under JJM with allied work for Raghunathpur & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 2526/MD | 18/07/2023 | 180 | ANIRUDDHA BAG | 582.89 | 0 | 0 | 96
1226 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15257 | New | Material Requisition To Resource Division | 3429/MD | 25/11/2024 | 0 | Resource Division | 12.17 | 0 | 0 | 0
1227 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15257 | New | Laying balance distribution system to accommodate FHTC (350 Nos.) for Raghunathpur & its adjoining mouzas W/S Scheme, Block - Kharagpur-I, District - Paschim Medinipur under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | 206/MD | 17/01/2025 | 75 | ANIRUDDHA BAG | 56.29 | 0 | 0 | 0
1228 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15257 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist-Paschim Medinipurunder JJM Program under MMD PHE Dte. | 450/W/MMD | 20/03/2023 | 959 | J K ENGINEERING CO | 22.94 | 0 | 0 | 100
1229 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14478 | Augmentation | Material Requisition To Resource Division | 92/MD | 10/01/2023 | 0 | Resource Division | 4.88 | 0 | 0 | 0
1230 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14478 | Augmentation | Electric quotation bill for Tw no-III of Chhotokhelna water supply scheme.Ref Consumer ID-204084641. | BP-2023-24-248 | 14/09/2023 | 0 | WBSEDCL | 5.48 | 0 | 0 | 0
1231 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14478 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Chhota Khelna PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | 548/AE/KSD | 23/08/2022 | 30 | GOBINDA MAITY | 3.31 | 0 | 0 | 100
1232 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14478 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 488/W/MMD | 20/03/2023 | 180 | KUSHANI ENTERPRISE | 10.98 | 0 | 0 | 50
1233 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14478 | Augmentation | Material Requisition To Resource Division | 3419/MD | 25/11/2024 | 0 | Resource Division | 23.16 | 0 | 0 | 0
1234 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14478 | Augmentation | Disinfection of different type of spot sources at flood affected area of Sultanpur GP. Of Ghatal Block within Ghatal Sub-Division, under Midnapore Division PHE. Dte. In the District of Paschim Medinipur. (Period for ¿July & August-2021) | 559/AE/GSD | 06/08/2021 | 5 | SANJIT SINHA | 2.47 | 0 | 0 | 100
1235 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14479 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Karkai PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | 549/AE/KSD | 23/08/2022 | 30 | GOBINDA MAITY | 3.06 | 0 | 0 | 0
1236 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14479 | Augmentation | Material Requisition To Resource Division | 113/MD | 10/01/2023 | 0 | Resource Division | 1.26 | 0 | 0 | 0
1237 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14479 | Augmentation | Material Requisition To Resource Division | 3420/MD | 25/11/2024 | 0 | Resource Division | 16.87 | 0 | 0 | 0
1238 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14479 | Augmentation | ELECTRIC QUOTATION BILL FOR AD TW NO-III OF KARKAI PWSS. REF CONSUMER ID-204350044, APPLICATION NO-2004810203, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA | C072443773813 | 30/07/2024 | 0 | WBSEDCL | 3.17 | 0 | 0 | 0
1239 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14479 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 534/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 11.39 | 0 | 0 | 20
1240 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14479 | Augmentation | Continuation Work Order for the work of Laying balance distribution pipe line for Augmentation of Karkai & its adjoining mouzas Pipe Water Supply Scheme under Pingla Block within Midnapore Division, P.H.E. Dte. (Total Length = 4,100.00 Mtr.) | 845/MD | 24/03/2023 | 648 | GOBINDA MAITY | 26.29 | 0 | 0 | 98
1241 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14479 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall to accommodate FHTC (327 Nos.) for Augmentation of Karkai PWSS in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 454/MD | 13/02/2023 | 831 | GOBINDA MAITY | 309.44 | 0 | 0 | 90
1242 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14479 | Augmentation | Laying balance Distribution pipeline for Augmentation of Karkai PWSS under Pingla block within Midnapore Division, PHE Dte. | 917/MD | 08/04/2025 | 75 | SUBRATA KUMAR BERA | 71.62 | 0 | 0 | 45
1243 | PASCHIM MEDINIPUR | Midnapore Division | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS , SM/14940 | New | Material Requisition To Resource Division | 1510/MD | 12/05/2023 | 0 | Resource Division | 22.87 | 0 | 0 | 0
1244 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS , SM/14940 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 827/W/MMD | 24/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 22.65 | 0 | 0 | 45
1245 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS , SM/14940 | New | Electrict quotation bill for TW-I of Radhamohanpur pwss (Ref Consumar ID-204439150),Application No-2004955822,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | C112429737180 | 25/11/2024 | 0 | WBSEDCL | 3.57 | 0 | 0 | 0
1246 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS , SM/14940 | New | Electrict quotation bill for TW-II of Radhamohanpur pwss (Ref Consumar ID-204210515),Application No-2004585811,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | BP-2023-24-704 | 16/02/2024 | 0 | WBSEDCL | 5.95 | 0 | 0 | 0
1247 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS , SM/14940 | New | Additional Electrict quotation bill for TW-II of Radhamohanpur pwss (Ref Consumar ID-860303412),Application No-100000110832,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | BP-2024-25-378 | 08/07/2024 | 0 | WBSEDCL | 0.43 | 0 | 0 | 0
1248 | PASCHIM MEDINIPUR | Midnapore Division | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS , SM/14940 | New | Construction of 150 Cum, 200 Cum & 250 Cum Capacity R.C.C Over Head Reservoir Over (Intze type with solid raft) works with Laying of Rising Main, Distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (5061 Nos.) including 2 years Operation & Maintenance for Loyada, Madhabpur, Patna and Radhamohanpur-II Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2824/MD | 07/08/2023 | 723 | MADE AND TRADE CO. | 1346.28 | 0 | 0 | 75
1249 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15072 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | 917/W/MMD | 27/03/2023 | 180 | SUBHASIS ROY | 12.62 | 0 | 0 | 0
1250 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15072 | Augmentation | Material Requisition To Resource Division | 406/MD | 07/02/2023 | 0 | Resource Division | 3.97 | 0 | 0 | 0
1251 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15072 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (502) for Augmentation of Pratappur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2672/MD | 26/07/2023 | 737 | DIPAK KUMAR DOLAI | 67.82 | 0 | 0 | 10
1252 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15072 | Augmentation | Restoration of damaged pipeline due to irrigation works of PRATAPPUR water supply scheme within Ghatal block under Ghatal Sub-Division within Midnapore Division, PHE.Dte. | 1274/AE/GSD | 28/06/2024 | 15 | SUBHASIS DOLAI | 0.48 | 0 | 0 | 100
1253 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANSUKA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15084 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 2 Nos. PWSS within Ghatal & Chandrakona-I blocks under Midnapore Division P.H.E. Dte. | 2684/MD | 30/12/2022 | 21 | SIRCON ENGINEERING SERVICES | 8.23 | 0 | 0 | 100
1254 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANSUKA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15084 | Augmentation | Laying additional pipe line to provide balance FHTC under JJM in Mansuka PWSS (Part of Kgaragpur Village) under Ghatal Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 2671/MD | 26/07/2023 | 30 | A-PLUS | 21.1 | 0 | 0 | 100
1255 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANSUKA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15084 | Augmentation | Material Requisition To Resource Division | 1419/MD | 04/05/2023 | 0 | Resource Division | 4.04 | 0 | 0 | 0
1256 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANSUKA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15084 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANSUKA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 915/W/MMD | 27/03/2023 | 180 | M/S. A.D. CONCERN | 13.68 | 0 | 0 | 80
1257 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANSUKA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15084 | Augmentation | QUOTATION MONEY FOR MANSUKA WATER SUPPLY SCHEME, T W NO 4 JJM WORKS, SCHEME CODE SM/15084, APPLICATION NO 2004759850, REFERENCE ID 204321898, BIRSINGHA CCC, WBSEDCL | BP-2024-25-295 | 18/06/2024 | 0 | WBSEDCL | 2.71 | 0 | 0 | 0
1258 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANSUKA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15084 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (522 Nos.) under JJM with allied work for Augmentation of Mansuka Pipe W/S Scheme in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2722/MD | 31/07/2023 | 732 | DIPAK KUMAR DOLAI | 111.12 | 0 | 0 | 10
1259 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 880/W/MMD | 27/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 45.55 | 0 | 0 | 0
1260 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Sinking of 1 (One) No. Tube well for Rupnarayanpur & its adjoining mouzas (Zone-II) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | 2519/MD | 18/07/2023 | 15 | THE TILES | 6.19 | 0 | 0 | 100
1261 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Material Requisition To Resource Division | 4049/MD | 12/10/2023 | 0 | Resource Division | 15.84 | 0 | 0 | 0
1262 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Laying Distribution Pipeline & Accommodate FHTC (200 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | 745/MD | 13/03/2024 | 45 | NIMAI LAL GURIA | 40.38 | 0 | 0 | 65
1263 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Laying Rising main, Distribution Pipeline & Accommodate FHTC (206 Nos.) including 2 yrs. O&M under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | 834/MD | 15/03/2024 | 45 | SAI TUBE CO. | 51.27 | 0 | 0 | 65
1264 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Construction of Pump House & Accommodate FHTC (240 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | 835/MD | 15/03/2024 | 60 | HYDROTECH ASSOCIATES | 20.6 | 0 | 0 | 60
1265 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Laying Rising main, Distribution Pipeline & Accommodate FHTC (200 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | 828/MD | 15/03/2024 | 45 | PULLOCK KUMAR GHOSH | 42.81 | 0 | 0 | 0
1266 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Construction of 150 CuM OHR (Torch type with Solid raft) & Boundary wall under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | 833/MD | 15/03/2024 | 180 | SUBRATA KUMAR BERA | 89.95 | 0 | 0 | 0
1267 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Laying Distribution Pipeline under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | 836/MD | 15/03/2024 | 45 | S.B. ENTERPRISE | 25.73 | 0 | 0 | 88
1268 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Laying Distribution Pipeline & Accommodate FHTC (241 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | 1838/MD | 12/06/2024 | 45 | DEBASISH DOGRA | 40.29 | 0 | 0 | 60
1269 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Construction of 150 CuM OHR (Torch type with Solid raft), Pump House, Boundary wall & Accommodate FHTC (200 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | 3550/MD | 04/12/2024 | 180 | BIDYUT KUMAR SANTRA | 108.07 | 0 | 0 | 0
1270 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Sinking of 3 (Three) Nos. Tube well for Rupnarayanpur & its adjoining mouzas (Zone-I) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | 2518/MD | 18/07/2023 | 40 | DEBASISH DOGRA | 18.02 | 0 | 0 | 90
1271 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Sinking of 3 (Three) Nos. Tube well for Rupnarayanpur & its adjoining mouzas (Zone-III) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | 2520/MD | 18/07/2023 | 40 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.74 | 0 | 0 | 100
1272 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | QUOTATION MONEY FOR RUPNARAYANPUR WATER SUPPLY SCHEME [ JINSAR ] , ZONE-III/I, T W NO I, JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004582814, REFERENCE ID 204206254, NIMPURA CCC, WBSEDCL | BP-2023-24-714 | 20/02/2024 | 0 | WBSEDCL | 0.12 | 0 | 0 | 0
1273 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | QUOTATION MONEY FOR RUPNARAYANPUR WATER SUPPLY SCHEME ( SOVANIPUR ), ZONE-III JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004582809, REFERENCE ID 204206252, NIMPURA CCC, WBSEDCL | BP-2023-24-703 | 16/02/2024 | 0 | WBSEDCL | 0.12 | 0 | 0 | 0
1274 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | RUPNARAYANPUR WATER SUPPLY SCHEME,ZONE-III, T W - I , JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004606325, REFERENCE ID 204221223, KHARAGPUR CCC, WBSEDCL | BP-2023-24-780 | 06/03/2024 | 0 | WBSEDCL | 0.54 | 0 | 0 | 0
1275 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | QUOTATION MONEY FOR KASHIJORA WATER SUPPLY SCHEME ( JINSAR ), MINI, ZONE-III JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004582814, REFERENCE ID 204206254, NIMPURA CCC, WBSEDCL |  | 24/04/2024 | 0 | WBSEDCL | 0.12 | 0 | 0 | 0
1276 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | RUPNARAYANPUR WATER SUPPLY SCHEME, MINI , ZONE - I , T W NO 1 , JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004614456, REFERENCE ID 204224878, NIMPURA CCC, WBSEDCL | BP-2023-24-779 | 06/03/2024 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
1277 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | QUOTATION MONEY FOR RUPNARAYANPUR [ ZONE-III/ T W NO I ] WATER SUPPLY SCHEME, MINI- JINSAHAR , JJM WORKS, SCHEME CODE 16262, APPLICATION NO 2004652971, REFERENCE ID 204253744, NIMPURA CCC, WBSEDCL | BP-2024-25-80 | 24/04/2024 | 0 | WBSEDCL | 1.47 | 0 | 0 | 0
1278 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte.(Part-II) | 881/W/MMD | 27/03/2023 | 889 | M/S B ENTERPRISE | 17.88 | 0 | 0 | 80
1279 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
1280 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/16262 | New | Laying Pipeline (Distribution system & Rising main), Switch Room, Land development & Accommodate FHTC (164 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | 1839/MD | 12/06/2024 | 420 | A R ENTERPRISE | 48.59 | 0 | 0 | 86
1281 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/15569 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 2 Nos. PWSS within Ghatal & Chandrakona-I blocks under Midnapore Division P.H.E. Dte. | 2684/MD | 30/12/2022 | 21 | SIRCON ENGINEERING SERVICES | 8.23 | 0 | 0 | 100
1282 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/15569 | Augmentation | Material Requisition To Resource Division | 1420/MD | 04/05/2023 | 0 | Resource Division | 18.38 | 0 | 0 | 0
1283 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/15569 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (2835 Nos.) under JJM with allied work for Augmentation of Srinagar Pipe W/S Scheme in Chandrakona-I Block including supply of all labour & materials within Ghtaal Sub-Division under Midnapore Division, PHE Dte. | 2721/MD | 31/07/2023 | 1059 | M/S. D.K.H.CONSTRUCTION | 239.56 | 0 | 0 | 11
1284 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/15569 | Augmentation | New Service connection charges. | 52/JMD | 06/02/2024 | 0 | WBSEDCL | 3.22 | 0 | 0 | 0
1285 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/15569 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | 919/W/MMD | 27/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 25.26 | 0 | 0 | 100
1286 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/15569 | Augmentation | Damaged UPVC pipeline & withdrawing of CI PIPE and replace with DI pipe & allied works in Srinagar W/S Scheme under Ghatal Sub-Division PHE Dte. | 4041/MD | 11/10/2023 | 15 | SAYEEDI CONSTRUCTION | 2.12 | 0 | 0 | 100
1287 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/16252 | New | Material Requisition To Resource Division | 1162/MD | 25/04/2023 | 0 | Resource Division | 52.06 | 0 | 0 | 0
1288 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/16252 | New | New service connection for Pursuri T/W-2 water supply scheme | 99/JMD | 23/02/2024 | 0 | WBSEDCL | 4.69 | 0 | 0 | 0
1289 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/16252 | New | New service connection for Pursuri T/W -1 water supply scheme. | 98/JMD | 23/02/2024 | 0 | WBSEDCL | 7.84 | 0 | 0 | 0
1290 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/16252 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 1231/W/MMD | 25/04/2023 | 676 | PRADIP KUMAR DHABAL | 25.24 | 0 | 0 | 80
1291 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/16252 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 450 cum OHR each (Intze type with pile foundation) & Accommodate FHTC (6283 Nos.) under JJM with allied work for Purshuri & Ramkrishnapur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2422/MD | 13/07/2023 | 808 | GOBINDA MAITY | 1504.9 | 0 | 0 | 60
1292 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/16252 | New | Laying of rising main & additional distribution pipe line due to re-design of mouzas Pipe W/S Schemes [Mangrul / Ramkrishnapur / Bagchhari / Purshuri] at Chandrakona-I block under Ghatal Sub-Division, PHE Dte. | 55/MD | 07/01/2025 | 266 | GOBINDA MAITY | 79.62 | 0 | 0 | 60
1293 | PASCHIM MEDINIPUR | Midnapore Division | THAUR AND ITS ADJOINING MOUZAS PWSS , SM/15906 | New | Material Requisition To Resource Division | 1163/MD | 26/04/2023 | 0 | Resource Division | 33.8 | 0 | 0 | 0
1294 | PASCHIM MEDINIPUR | Midnapore Mechanical | THAUR AND ITS ADJOINING MOUZAS PWSS , SM/15906 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF THAUR PWSS. REF CONSUMER ID-204342953, APPLICATION NO-2004797675, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESPUR | BP-2024-25-415 | 15/07/2024 | 0 | WBSEDCL | 3.08 | 0 | 0 | 0
1295 | PASCHIM MEDINIPUR | Midnapore Mechanical | THAUR AND ITS ADJOINING MOUZAS PWSS , SM/15906 | New | Electric quotation bill for Tw No-II of Thaur PWSS. (Ref Consumer ID-204182374) | BP-2023-24-561 | 16/01/2024 | 0 | WBSEDCL | 3.12 | 0 | 0 | 0
1296 | PASCHIM MEDINIPUR | Midnapore Mechanical | THAUR AND ITS ADJOINING MOUZAS PWSS , SM/15906 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THAUR AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 905/W/MMD | 27/03/2023 | 950 | SUJOY RANJAN BHOWMICK | 27.37 | 0 | 0 | 25
1297 | PASCHIM MEDINIPUR | Midnapore Division | THAUR AND ITS ADJOINING MOUZAS PWSS , SM/15906 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 300 Cum & 400 Cum RCC Over Head Reservoir (Intze type with Pile Foundation) & Accommodate FHTC (4,797 Nos.) including Two years O&M under JJM with allied work for Teghari & Thaur & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | 2924/MD | 16/08/2023 | 927 | M/S. A.R. ENTERPRISE. | 1490.96 | 0 | 0 | 49
1298 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Ukhla PWSS in the District of Paschim Medinipur under JJM programme. , SM/17755 | Augmentation | Electric quotation bill for load enhacement at Tw no-I of Ukhla water supply scheme. Consumer ID-200331903. |  | 22/05/2023 | 0 | WBSEDCL | 0.36 | 0 | 0 | 0
1299 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Ukhla PWSS in the District of Paschim Medinipur under JJM programme. , SM/17755 | Augmentation | Rejuvenation of Electro-Mechanical components of Ukhla PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | 1061/W/MMD | 29/03/2023 | 180 | ABHIJIT MUKHERJEE | 21.09 | 0 | 0 | 55
1300 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Rejuvenation of Electro-Mechanical components of Ukhla PWSS in the District of Paschim Medinipur under JJM programme. , SM/17755 | Augmentation | Repairing & rejuvenation of electro-mechanical accessories for Ukhla W/S scheme Pump house no -2 in Garbeta II block under Jhargram Mechanical Division, PHE. Dte. | 7246/JMD | 05/11/2024 | 188 | ABHIJIT MUKHERJEE | 4.43 | 0 | 0 | 100
1301 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18172 | New | Material Requisition To Resource Division | 4061/MD | 12/10/2023 | 0 | Resource Division | 47.34 | 0 | 0 | 0
1302 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18172 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Basanchhara & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | 1018/MD | 27/05/2022 | 20 | SIRCON ENGINEERING SERVICES | 6 | 0 | 0 | 100
1303 | PASCHIM MEDINIPUR | Midnapore Mechanical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18172 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at BASANCHHARA Water supply scheme, Chandrakona -II block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 2284/W/MMD | 29/08/2023 | 180 | RSA ENTERPRISE | 30.18 | 0 | 0 | 100
1304 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18172 | New | Material Requisition To Resource Division | 3334/MD | 25/11/2024 | 0 | Resource Division | 10.6 | 0 | 0 | 0
1305 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18172 | New | New Service connection charges. | 53/JMD | 06/02/2024 | 0 | WBSEDCL | 3.82 | 0 | 0 | 0
1306 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18172 | New | New Service connection charges. | 23/JMD | 04/03/2024 | 0 | WBSEDCL | 9.72 | 0 | 0 | 0
1307 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18172 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 450 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,044 Nos.) under JJM including Two years O&M with allied work for Basanchhara PWSS in Chandrakona-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 3260/MD | 12/09/2023 | 907 | M/S. D.K.H.CONSTRUCTION | 776.36 | 0 | 0 | 70
1308 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18028 | New | Material Requisition To Resource Division | 111/MD | 10/01/2023 | 0 | Resource Division | 32.36 | 0 | 0 | 0
1309 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18028 | New | Material Requisition To Resource Division | 1456/MD | 08/05/2023 | 0 | Resource Division | 10.16 | 0 | 0 | 0
1310 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18028 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 587/W/MMD | 20/03/2023 | 180 | M/S NABIN GOPAL SENGUPTA | 25.24 | 0 | 0 | 100
1311 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18028 | New | New Service connection charges. | 69/JMD | 13/03/2024 | 0 | WBSEDCL | 5.25 | 0 | 0 | 0
1312 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18028 | New | New Service connection charges. | 54/JMD | 07/02/2024 | 0 | WBSEDCL | 4.29 | 0 | 0 | 0
1313 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Keshpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17382 | Solarisation | Solarization of grid connected pumping installation at Keshpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 692/W/MMD | 23/03/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 6.26 | 0 | 0 | 70
1314 | PASCHIM MEDINIPUR | Midnapore Division | SAIYADPUR AND ADJOINING MOUJAS PWSS , SM/17996 | New | Material Requisition To Resource Division | 1271/MD | 28/04/2023 | 0 | Resource Division | 21.29 | 0 | 0 | 0
1315 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SAIYADPUR AND ADJOINING MOUJAS PWSS , SM/17996 | New | New service connection charges for Saiyadpur pwss, t/w no. II | 48/JMD | 29/04/2024 | 0 | WBSEDCL | 7.54 | 0 | 0 | 0
1316 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SAIYADPUR AND ADJOINING MOUJAS PWSS , SM/17996 | New | New service connection charges for Saiyadpur pwss, t/w no.I | 49/JMD | 29/04/2024 | 0 | WBSEDCL | 8.15 | 0 | 0 | 0
1317 | PASCHIM MEDINIPUR | Central Drilling | SAIYADPUR AND ADJOINING MOUJAS PWSS , SM/17996 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1318 | PASCHIM MEDINIPUR | Midnapore Division | SAIYADPUR AND ADJOINING MOUJAS PWSS , SM/17996 | New | Route survey & way leave permission along & across of National Highway under Saiyadpur PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | 373/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 11.88 | 0 | 0 | 0
1319 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Madpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17354 | Solarisation | Solarization of grid connected pumping installation at Madpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 785/W/MMD | 24/03/2023 | 180 | M/S. JIT ENTERPRISE | 6.26 | 0 | 0 | 85
1320 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Madpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17354 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going solarisation / rejuvenation as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 716/MMSD-I | 07/06/2024 | 15 | MUKHERJEE ART CENTRE | 1.93 | 0 | 0 | 100
1321 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Hatimasan PWSS in the District of Paschim Medinipur under JJM programme. , SM/17750 | Augmentation | Rejuvenation of Electro-Mechanical components of Hatimasan PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | 1059/W/MMD | 29/03/2023 | 180 | THE GODFATHER TRADING COMPANY | 5.07 | 0 | 0 | 60
1322 | PASCHIM MEDINIPUR | Midnapore Division | SAMSARA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17569 | New | Material Requisition To Resource Division | 1451/MD | 08/05/2023 | 0 | Resource Division | 29.23 | 0 | 0 | 0
1323 | PASCHIM MEDINIPUR | Midnapore Mechanical | SAMSARA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17569 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SAMSARA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION under JJM Program under MMD PHE Dte. | 1197/W/MMD | 25/04/2023 | 720 | DEBJYOTI BASU | 22.64 | 0 | 0 | 40
1324 | PASCHIM MEDINIPUR | Midnapore Division | SAMSARA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17569 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 0 | 55
1325 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Anandapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17727 | Solarisation | Solarization of grid connected pumping installation Anandapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 987/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 30
1326 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dhamsai PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17320 | Solarisation | Solarization of grid connected pumping installation at Dhamsai PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 708/W/MMD | 23/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
1327 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dharmma PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17346 | Solarisation | Solarization of grid connected pumping installation at Dharmma PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 688/W/MMD | 23/03/2023 | 180 | GOENKA ENTERPRISE | 6.26 | 0 | 0 | 90
1328 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Sarta PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17312 | Solarisation | Solarization of grid connected pumping installation at Sarta PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 698/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
1329 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dhengasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17457 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
1330 | PASCHIM MEDINIPUR | Midnapore Division | NANASOL AND ADJOINING MOUJAS PWSS , SM/13808 | New | Material Requisition To Resource Division | 2224/MD | 15/06/2023 | 0 | Resource Division | 20.41 | 0 | 0 | 0
1331 | PASCHIM MEDINIPUR | Midnapore Division | NANASOL AND ADJOINING MOUJAS PWSS , SM/13808 | New | Sinking of Tube Well ,Laying of Rising Main ,Laying distribution pipe line, Pump House , Boundary Wall , soil investigation , 100 cum OHR( Torch type with solid raft ) & Accommodate FHTC (529 Nos.) including 2 years operation & maintenance under JJM with allied work for Nanasol & its adjoining mouzas W/S scheme in Salbani Block including supply of all labour & materials within Medinipur Sadar Sub-division under Midnapore Division, PHE Dte. | 5064/MD | 26/10/2023 | 180 | ASHIM KUMAR DEY | 218.49 | 0 | 0 | 15
1332 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | NANASOL AND ADJOINING MOUJAS PWSS , SM/13808 | New | New service connection charges for Nonasol w/s scheme, t/w no.II | 39/JMD | 11/03/2024 | 0 | WBSEDCL | 2.29 | 0 | 0 | 0
1333 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | NANASOL AND ADJOINING MOUJAS PWSS , SM/13808 | New | New service connection charges for Nonasole w/s scheme, t/w no.I | 38/JMD | 11/03/2024 | 0 | WBSEDCL | 5.62 | 0 | 0 | 0
1334 | PASCHIM MEDINIPUR | Central Drilling | NANASOL AND ADJOINING MOUJAS PWSS , SM/13808 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1335 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF SALBANI AND IT'S ADJOINING MOUJAS PWSS, BLOCK - SALBONI, DIST.- PASCHIM MEDINIPUR. , SM/17000 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF SALBANI AND IT'S ADJOINING MOUJAS PWSS, BLOCK - SALBONI, DIST.- PASCHIM MEDINIPUR. under JJM Program under MMD PHE Dte. | 1200/W/MMD | 25/04/2023 | 180 | MANORANJAN DEY | 25.26 | 0 | 0 | 0
1336 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF SALBANI AND IT'S ADJOINING MOUJAS PWSS, BLOCK - SALBONI, DIST.- PASCHIM MEDINIPUR. , SM/17000 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Soil investigation, 450 cum OHR (Intze type with solid Raft) & Accommodate FHTC (3,272 Nos.) under JJM with allied work for Augmentation of Salboni Pipe Water Supply Scheme under Salbani Block including supply of all labour & materials within Medinipur Sadar Sub-Division under Medinipur Division, PHE Dte. under Paschim Medinipur District. | 5069/MD | 26/10/2023 | 752 | IJABUL SEKH | 552.44 | 0 | 0 | 70
1337 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF SALBANI AND IT'S ADJOINING MOUJAS PWSS, BLOCK - SALBONI, DIST.- PASCHIM MEDINIPUR. , SM/17000 | Augmentation | Route survey & way leave permission along & across of National Highway in Augmentation of Salboni PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | 1630/MD | 06/08/2025 | 21 | PIONEER SURVEYORS | 10.84 | 0 | 0 | 0
1338 | PASCHIM MEDINIPUR | Midnapore Division | SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17624 | New | Material Requisition To Resource Division | 1513/MD | 12/05/2023 | 0 | Resource Division | 28.97 | 0 | 0 | 0
1339 | PASCHIM MEDINIPUR | Midnapore Mechanical | SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17624 | New | Electrict quotation bill for TW-I of Shyampur pwss (Ref Consumar ID-204391666),Application No-2004886437,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | BP-2024-25-682 | 27/09/2024 | 0 | WBSEDCL | 5.56 | 0 | 0 | 0
1340 | PASCHIM MEDINIPUR | Midnapore Mechanical | SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17624 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 793/W/MMD | 24/03/2023 | 903 | M/S B.M. ELECTRICAL | 21.56 | 0 | 0 | 40
1341 | PASCHIM MEDINIPUR | Midnapore Division | SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17624 | New | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, 150 cum OHR (Intze type with solid raft) & Accommodate FHTC (1014 Nos) including 2 years operation & maintenance under JJM with allied work for Shyampur & its adjoining mouzas W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-division under Midnapore Division, PHE Dte. | 3039/MD | 22/08/2023 | 720 | CREATION CONSTRUCTION | 272.66 | 0 | 0 | 70
1342 | PASCHIM MEDINIPUR | Midnapore Division | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18502 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kalara & its adjoining Mouzas PWSS instead Radhakantapur its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | 1263/MD | 23/06/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.73 | 0 | 0 | 100
1343 | PASCHIM MEDINIPUR | Midnapore Division | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18502 | New | Material Requisition To Resource Division | 95/MD | 10/01/2023 | 0 | Resource Division | 192.26 | 0 | 0 | 0
1344 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18502 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 1684/W/MMD | 04/08/2023 | 905 | ALPHA ENTERPRISE | 37.86 | 0 | 0 | 60
1345 | PASCHIM MEDINIPUR | Midnapore Division | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18502 | New | Material Requisition To Resource Division | 3336/MD | 25/11/2024 | 0 | Resource Division | 17.48 | 0 | 0 | 0
1346 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18502 | New | QUOTATION MONEY FOR KALARA WATER SUPPLY SCHEME, T W NO I , JJM WORKS, SCHEME CODE SM/18502, APPLICATION NO 2004809520, REFERENCE ID 204352787, DASPUR CCC, WBSEDCL. | BP-2024-25-487 | 30/07/2024 | 0 | WBSEDCL | 6.53 | 0 | 0 | 0
1347 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18502 | New | QUOTATION MONEY FOR KALARA WATER SUPPLY SCHEME, T W NO II, JJM WORKS, SCHEME CODE SM/18502, APPLICATION NO 2004829551, REFERENCE ID 204362487,BLOCK- DASPUR-I, DASPUR CCC, WBSEDCL | BP-2024-25-543 | 07/08/2024 | 0 | WBSEDCL | 3.01 | 0 | 0 | 0
1348 | PASCHIM MEDINIPUR | Midnapore Division | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18502 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 500 & 600 cum OHR (Intze type with pile foundation) & Accommodate FHTC (5,406 nos.) under JJM with allied work for Gopalnagar & Kalara PWSS in Daspur-I Block including supply of all labour & materials including Two (02) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2953/MD | 17/08/2023 | 772 | GOBINDA MAITY | 1693.15 | 0 | 0 | 20
1349 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18502 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
1350 | PASCHIM MEDINIPUR | Midnapore Division | KUILABAD AND ADJOINING MOUJAS PWSS at Garbeta-I Block. , SM/12335 | New | Material Requisition To Resource Division | 1156/MD | 25/04/2023 | 0 | Resource Division | 33.76 | 0 | 0 | 0
1351 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KUILABAD AND ADJOINING MOUJAS PWSS at Garbeta-I Block. , SM/12335 | New | new service connection charges at Kuilabad T/W-II | 426/JMD | 28/11/2024 | 0 | WBSEDCL | 5.59 | 0 | 0 | 0
1352 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KUILABAD AND ADJOINING MOUJAS PWSS at Garbeta-I Block. , SM/12335 | New | new service connection charges at Kuilabad TW-I water supply scheme | 338/JMD | 05/09/2024 | 0 | WBSEDCL | 12.35 | 0 | 0 | 0
1353 | PASCHIM MEDINIPUR | Central Drilling | KUILABAD AND ADJOINING MOUJAS PWSS at Garbeta-I Block. , SM/12335 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1354 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HARIDHARPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/18249 | New | Material Requisition To Resource Division | 91/MD | 10/01/2023 | 0 | Resource Division | 31.55 | 0 | 0 | 0
1355 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HARIDHARPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/18249 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HARIDHARPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTEunder JJM Program under MMD PHE Dte. | 1629/W/MMD | 25/07/2023 | 180 | BHABANI PRASAD MANNA | 27.39 | 0 | 0 | 60
1356 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HARIDHARPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/18249 | New | Material Requisition To Resource Division | 3325/MD | 25/11/2024 | 0 | Resource Division | 19.11 | 0 | 0 | 0
1357 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HARIDHARPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE , SM/18249 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 250 & 450 cum OHRs (Intze type) & Accommodate FHTC (4,203 Nos.) under JJM with allied work for (1) Gohaldanga & (2) Haridharpur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 3147/MD | 29/08/2023 | 718 | BANERJEE CONSTRUCTION | 1062.73 | 0 | 0 | 30
1358 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19053 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, and IV) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. .(Part-II) | 3099/W/MMD | 29/11/2023 | 180 | SUBHASIS ROY | 11.97 | 0 | 0 | 0
1359 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19053 | New | Material Requisition To Resource Division | 1164/MD | 26/04/2023 | 0 | Resource Division | 72.2 | 0 | 0 | 0
1360 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19053 | New | QUOTATION MONEY FOR BHETIA WATER SUPPLY SCHEME, ZONE-I, T W NO II, [ PURBA BHURKUNDI ], KGP-I, JJM WORKS, SCHEME CODE SM/19053, , APPLICATION NO 2004890152, REFERENCE ID 204393530, NIMPURA CCC, WBSEDCL | C112417250894 | 12/11/2024 | 0 | WBSEDCL | 3.7 | 0 | 0 | 0
1361 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19053 | New | QUOTATION MONEY FOR BHETIA WATER SUPPLY SCHEME, ZONE-II, T W NO 1, JJM WORKS, SCHEME CODE SM/19053, APPLICATION NO 2004776674, REFERENCE ID 204331298, NIMPURA CCC, WBSEDCL | BP-2024-25-419 | 15/07/2024 | 0 | WBSEDCL | 3.1 | 0 | 0 | 0
1362 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19053 | New | QUOTATION MONEY FOR BHETIA WATER SUPPLY SCHEME, ZONE-I, T W NO 1, JJM WORKS, SCHEME CODE SM/19053, APPLICATION NO 2004796950, REFERENCE ID 204343402, NIMPURA CCC, WBSEDCL | BP-2024-25-420 | 15/07/2024 | 0 | WBSEDCL | 4.86 | 0 | 0 | 0
1363 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19053 | New | Sinking of Tube Wells, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 cum & 150 cum OHRs & Accommodate FHTC (3,462 Nos.) including Two years O&M under JJM with allied work for Bhetia (Zone-I, II, III & IV) & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 216/MD | 31/01/2024 | 786 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 1062.32 | 0 | 0 | 70
1364 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19053 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, and IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 3094/W/MMD | 29/11/2023 | 906 | DEBJYOTI BASU | 43.97 | 0 | 0 | 95
1365 | PASCHIM MEDINIPUR | Midnapore Division | KANAKPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12988 | New | Material Requisition To Resource Division | 1516/MD | 12/05/2023 | 0 | Resource Division | 34.57 | 0 | 0 | 0
1366 | PASCHIM MEDINIPUR | Midnapore Mechanical | KANAKPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12988 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KANAKPUR AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 476/W/MMD | 20/03/2023 | 180 | M/S. SAJAHAN CHOWDHURY | 23 | 0 | 0 | 60
1367 | PASCHIM MEDINIPUR | Midnapore Division | KANAKPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12988 | New | Construction of 350 Cum & 300 Cum Capacity R.C.C Over Head Reservoir (Intze type with solid raft) works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,209 Nos) including 2 years operation & maintenance For Golegram and Kanakpur Pipe water supply Scheme within Debra Block under Kharagpur Sub Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5060/MD | 26/10/2023 | 613 | IJABUL SEKH | 992.27 | 0 | 0 | 45
1368 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/18539 | New | Material Requisition To Resource Division | 1523/MD | 12/05/2023 | 0 | Resource Division | 59.93 | 0 | 0 | 0
1369 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/18539 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I and II) and its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 1695/W/MMD | 04/08/2023 | 180 | AMUSAR IMPEX PVT. LTD | 45.31 | 0 | 0 | 50
1370 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/18539 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Bhutna & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | 673/MD | 11/04/2022 | 20 | GOBINDA MAITY | 8.37 | 0 | 0 | 100
1371 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/18539 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, 350 Cum & 250 cum OHR (Zone- I & II) (Intze type with pile foundation) & Accommodate FHTC (3,339 Nos.) including Two years O&M under JJM with allied work for Bhuta (Zone- I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 5066/MD | 26/10/2023 | 898 | M/S. SOURABH KUMAR ROY | 838.26 | 0 | 0 | 0
1372 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/18539 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
1373 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/18539 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
1374 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Ranapur PWSS , SM/06934 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Ranapur W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1429/MD | 26/11/2020 | 180 | KISHORE GHOSH | 92.88 | 73.29 | 78.91 | 0
1375 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Ranapur PWSS , SM/06934 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Ranapur W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | KISHORE GHOSH | 90 | 0 | 0 | 0
1376 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Ranapur PWSS , SM/06934 | Retrofitting | Exingeny basis laying casing pipe under Bitumineous pucca road crosssing near Oil Meal,Mondal Hard Works of Khakurda to Ghatal PWD Road of Ranapur W/S Scheme within Ghatal Sub-Division, PHE.Dte. | 172/AE/GSD | 01/04/2022 | 2 | WATER LINK | 2.22 | 0 | 0 | 0
1377 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Ranapur PWSS , SM/06934 | Retrofitting | Hire bill of vehicle No. WB 25L3164 for the month of March 2023 Under the O/O the SE/WC, PHE Dte. | 8443133 | 26/06/2023 | 0 | BISWADIP SIKDAR | 0.4 | 0 | 0 | 0
1378 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Adasimla Piped Water Supply Scheme. , SM/06897 | Retrofitting | FHTC imis data entry. | 8443147 | 24/03/2022 | 0 | SIDDHESWAR BAG | 0.16 | 0 | 0 | 0
1379 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Adasimla Piped Water Supply Scheme. , SM/06897 | Retrofitting | FHTC imis data entry. | 8443147 | 24/03/2022 | 0 | SUBRATA CHAKRABORTY | 0.09 | 0 | 0 | 0
1380 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Adasimla Piped Water Supply Scheme. , SM/06897 | Retrofitting | FHTC imis data entry. | 8443147 | 24/03/2022 | 0 | PAPPU SHAW | 0.15 | 0 | 0 | 0
1381 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Adasimla Piped Water Supply Scheme. , SM/06897 | Retrofitting | Extension of pipe line From Adasimla G.P. office to Harijan Pally under Adasimla & its adjoining mouzas water supply Scheme at Sabang Block under Kharagpur Sub Division within Midnapore Division, P.H.E.Dte. | 311/AE/KSD | 16/07/2021 | 30 | SAI TUBE CO. | 4.78 | 0 | 0 | 0
1382 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Adasimla Piped Water Supply Scheme. , SM/06897 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Adasimla Piped Water Supply Scheme | 844397 | 30/11/2022 | 0 | SAI TUBE CO. | 4.64 | 0 | 0 | 0
1383 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Adasimla Piped Water Supply Scheme. , SM/06897 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Adasimla W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1462/MD | 26/11/2020 | 1643 | SAI TUBE CO. | 94.76 | 49.55 | 52.29 | 100
1384 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-II) PWSS , SM/06906 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barisha (Zone-II) W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1434/MD | 26/11/2020 | 180 | UTTAM KUMAR DAS | 97.01 | 44.07 | 45.43 | 0
1385 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-II) PWSS , SM/06906 | Retrofitting | Construction of SSP & Soak Pit at different places laying of pipe line of Barisha Zone -II . | BP-2022-23-34 | 29/04/2022 | 0 | BIDHAN CHANDRA PATRA | 2.82 | 0 | 0 | 0
1386 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-II) PWSS , SM/06906 | Retrofitting | Material Requisition To Resource Division | 3408/MD | 25/11/2024 | 0 | Resource Division | 12.42 | 0 | 0 | 0
1387 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhemwa (Zone-I) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | MASUM ALI KHAN | 20 | 0 | 0 | 0
1388 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443461 | 26/03/2021 | 0 | ARUP KR ADAK | 0.07 | 0 | 0 | 0
1389 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443461 | 26/03/2021 | 0 | PRATHA PRATIM PAL | 0.2 | 0 | 0 | 0
1390 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443461 | 26/03/2021 | 0 | ANIRBAN CHAKRABORTY | 0.17 | 0 | 0 | 0
1391 | PASCHIM MEDINIPUR | Central Drilling | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER MATERIALS & ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL AT (ZONE-II) TW-II (REPLACEMENT) OF BHEMWA W/S SCHEME IN SABANG BLOCK UNDER CDD, PHE DTE. | 244/CMSD-I (D) | 20/06/2022 | 15 | MENAKA ENTERPRISE | 1.98 | 0 | 0 | 0
1392 | PASCHIM MEDINIPUR | Central Drilling | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | PROVIDING HOUSING PIPE CONFORMING TO IS 12818:2010 WITH OTHER MATERIALS & ALLIED WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT (ZONE-II) TW-II (REPLACEMENT) OF BHEMWA W/S SCHEME IN SABANG BLOCK UNDER CDD, PHE DTE. | 242/CMSD-I (D) | 20/06/2022 | 15 | MENAKA ENTERPRISE | 3.76 | 0 | 0 | 0
1393 | PASCHIM MEDINIPUR | Central Drilling | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & ALLIED WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT (ZONE-II) TW-II (REPLACEMENT) OF BHEMWA W/S SCHEME IN SABANG BLOCK UNDER CDD, PHE DTE. | 243/CMSD-I (D) | 20/06/2022 | 15 | MENAKA ENTERPRISE | 1.98 | 0 | 0 | 0
1394 | PASCHIM MEDINIPUR | Central Drilling | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT (ZONE-II) TW-II (REPLACEMENT) OF BHEMWA W/S SCHEME IN SABANG BLOCK UNDER CMSD-I (D), CDD, PHE DTE. | 241/CMSD-I (D) | 20/06/2022 | 15 | MENAKA ENTERPRISE | 2.64 | 0 | 0 | 0
1395 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | FHTC imis data entry. | 8443148 | 24/03/2022 | 0 | MANABENDRA DAS | 0.15 | 0 | 0 | 0
1396 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | FHTC imis data entry. | 8443148 | 24/03/2022 | 0 | NABOGOPAL ADHIKARI | 0.08 | 0 | 0 | 0
1397 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | FHTC imis data entry. | 8443148 | 24/03/2022 | 0 | SANDIP MANNA | 0.09 | 0 | 0 | 0
1398 | PASCHIM MEDINIPUR | Central Drilling | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | REPAIRING OF WATER SWIVEL AND OTHER WORKS FOR RIG NO. SUPER RR UNDER CMSD-II (D), CDD, PHE DTE. | 564/CMSD-II (D) | 26/11/2021 | 30 | PADMA ENGINEERING & CO. | 4.08 | 0 | 0 | 0
1399 | PASCHIM MEDINIPUR | Central Drilling | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | REPAIRING OF DAMAGE TRUCK DRIVER CABIN, STEEL BODY, CHEQUER PLATE, CHASSIS AND TRUCK BODY PAINTING OF GOVT VEHICLE NO. WMK 6422 (TATA) UNDER CMSD-I (D), CDD, PHE DTE. | 77/CMSD-I | 01/04/2022 | 15 | M/S B.P.TRADING CORPORATION | 2.36 | 0 | 0 | 0
1400 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS , SM/06907 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhemwa (Zone-I) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1468/MD | 26/11/2020 | 180 | MASUM ALI KHAN | 86.17 | 35.71 | 41.44 | 100
1401 | PASCHIM MEDINIPUR | Midnapore Division | Gopinathpur Piped Water Supply Scheme. , SM/07964 | New | Material Requisition To Resource Division | 1146/MD | 25/04/2023 | 0 | Resource Division | 16.15 | 0 | 0 | 0
1402 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gopinathpur Piped Water Supply Scheme. , SM/07964 | New | Electric quotation for Gopinathpur PWSS Tube Well-II WS Scheme (Ref. ID 203917725) | BP-2022-23-144 | 24/03/2023 | 0 | WBSEDCL | 0.49 | 0 | 0 | 0
1403 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gopinathpur Piped Water Supply Scheme. , SM/07964 | New | Electric quotation for Gopinathpur PWSS Tube Well-I WS Scheme (Ref. ID 203917726) | BP-2022-23-143 | 24/03/2023 | 0 | WBSEDCL | 0.49 | 0 | 0 | 0
1404 | PASCHIM MEDINIPUR | Midnapore Division | Gopinathpur Piped Water Supply Scheme. , SM/07964 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for Gopinathpur W/S Scheme in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 2189/MD | 01/11/2022 | 180 | BANERJEE CONSTRUCTION | 410.37 | 0 | 0 | 56
1405 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gopinathpur Piped Water Supply Scheme. , SM/07964 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gopinathpur Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | 530/W/MMD | 20/03/2023 | 180 | P.K.ENGINEERING | 22.78 | 0 | 0 | 50
1406 | PASCHIM MEDINIPUR | Midnapore Division | Gopinathpur Piped Water Supply Scheme. , SM/07964 | New | Laying of Rising main including interconnection pipeline for Gopinathpur W/S Scheme within Pingla block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. (Length - 350.00 Mtr.) | 3406/MD | 25/11/2024 | 45 | MAA SARADA ENTERPRISE | 3.62 | 0 | 0 | 0
1407 | PASCHIM MEDINIPUR | Midnapore Division | Gopinathpur Piped Water Supply Scheme. , SM/07964 | New | Laying additional distribution pipeline to accommodate FHTC & allied work for Gopinathpur PWSS under Pingla block within Midnapore Division, PHE Dte. | 3570/MD | 06/12/2024 | 75 | ASHOK BANERJEE | 82.67 | 0 | 0 | 0
1408 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas , SM/09439 | New | Service connection charge of WBSEDCL at Dantarda, Chandkuri | 2003775012/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
1409 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas , SM/09439 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Dontarda, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 119/W/MMD | 24/01/2022 | 120 | DEBKUMAR BASU | 6.52 | 0 | 0 | 0
1410 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas , SM/09439 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Dontarda water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2507/W/MMD | 30/11/2021 | 4 | DEBJYOTI BASU | 4.47 | 0 | 0 | 100
1411 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas , SM/09439 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | BP-2021-22-505 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 4.08 | 0 | 0 | 0
1412 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas , SM/09439 | New | Sinking of different Tube-well. | BP-2021-22-523 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.66 | 0 | 0 | 0
1413 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas , SM/09439 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Dontarda, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 2179/MD | 17/12/2021 | 150 | MIDNAPUR PIPE CONCERN | 31.32 | 0 | 0 | 100
1414 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Sitanathpur Piped Water Supply Scheme to accommodate all FHTC. , SM/08208 | Retrofitting | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte.61/MD |  | 19/03/2021 | 0 | SIRCON ENGINEERING SERVICES | 1.49 | 0 | 0 | 0
1415 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Sitanathpur Piped Water Supply Scheme to accommodate all FHTC. , SM/08208 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Sitanathpur, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | 61/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.57 | 1.44 | 100 | 0
1416 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Sitanathpur Piped Water Supply Scheme to accommodate all FHTC. , SM/08208 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Sitanathpur PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. (2nd Call) | 184/MD | 01/02/2022 | 1155 | DEBJIT PATRA | 25.18 | 0 | 0 | 75
1417 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Bhimpur Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/08675 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Bhimpur PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 234/MD | 08/02/2022 | 45 | DIPAK KUMAR BAKLY | 36.72 | 0 | 0 | 0
1418 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Bhimpur Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/08675 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Bhimpur, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | 348/MD | 25/02/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.99 | 1.97 | 100 | 0
1419 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Kalaimuri Piped Water Supply Scheme to accommodate all FHTC. , SM/08215 | Retrofitting | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. |  | 19/03/2021 | 0 | SIRCON ENGINEERING SERVICES | 1.57 | 0 | 0 | 0
1420 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Kalaimuri Piped Water Supply Scheme to accommodate all FHTC. , SM/08215 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kalaimuri, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | 64/MD | 11/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.14 | 1.57 | 100 | 0
1421 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Kalaimuri Piped Water Supply Scheme to accommodate all FHTC. , SM/08215 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Kalaimuri PWSS to accommodate FHTC under JJM under Salboni Block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 2248/MD | 28/12/2021 | 45 | NIMAI HAZRA | 25.66 | 0 | 0 | 0
1422 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC 4 Nos. PWSS (Phase-II) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08696 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Daulatchak PWSS (2nd Phase), Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1464/MD | 07/09/2021 | 45 | M/S. D.K.H.CONSTRUCTION | 73.12 | 35.9 | 49.09 | 0
1423 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC 4 Nos. PWSS (Phase-II) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08696 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (2nd Phase), Block: - Chandrakona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1469/MD | 07/09/2021 | 10 | M/S ZAMAN ENTERPRISE | 10.84 | 0 | 0 | 0
1424 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC 4 Nos. PWSS (Phase-II) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08696 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhabanipur PWSS (2nd Phase), Block: - Chandrakona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1443/MD | 03/09/2021 | 15 | SAMIT PAL | 23.91 | 8.18 | 34.23 | 0
1425 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC 4 Nos. PWSS (Phase-II) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08696 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pratappur PWSS (2nd Phase) in Ghatal Block in the district of Paschim Medinipur. | 1445/MD | 03/09/2021 | 60 | DIPAK KUMAR DOLAI | 135.13 | 18.3 | 13.69 | 0
1426 | PASCHIM MEDINIPUR | Central Drilling | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 190 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR KRISHNAPRIYA W/S SCH (TW-II), PINGLA BLOCK UNDER PASCHIM MEDINIPUR DISTRICT, CDD, PHE DTE. | 16/CDD | 04/04/2022 | 30 | MENAKA ENTERPRISE | 9.32 | 0 | 0 | 0
1427 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | Preparation of D.P.R (Consultancy work) in connection with the Proposed Pipe Water Supply Scheme for Dashagram & its adjoining mouza within Sabang Block under Midnapore Division, P.H.E. Dte. | 1691/MD | 30/09/2021 | 10 | GOBINDA MAITY | 2.74 | 0 | 0 | 0
1428 | PASCHIM MEDINIPUR | Central Drilling | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (2522MM X 150MM X 190 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DASHAGRAM W/S SCH (TW-II), PINGLA BLOCK UNDER PASCHIM MEDINIPUR DISTRICT, CDD, PHE DTE. | 16/ CDD | 04/04/2022 | 30 | MENAKA ENTERPRISE | 9.32 | 0 | 0 | 0
1429 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. under JJM Program under MMD PHE Dte. | 2311/W/MMD | 29/12/2022 | 180 | KAMAKSHYA ENTERPRISE | 25.14 | 0 | 0 | 0
1430 | PASCHIM MEDINIPUR | Central Drilling | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | Providing TW materials conforming to IS: 12818:2010 with other works at site for construction of TW in Dasha Gram PWSS under CDD, PHE Dte. | 579/CMSD-I | 30/11/2022 | 7 | MENAKA ENTERPRISE | 0.98 | 0 | 0 | 0
1431 | PASCHIM MEDINIPUR | Central Drilling | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 160 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DASAGRAM W/S SCH (TW-II), PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | 1455/CDD | 30/11/2022 | 30 | MENAKA ENTERPRISE | 9.3 | 0 | 0 | 0
1432 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | Material Requisition To Resource Division | 137/MD | 11/01/2023 | 0 | Resource Division | 15.83 | 0 | 0 | 0
1433 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | Material Requisition To Resource Division | 514/MD | 20/02/2023 | 0 | Resource Division | 28.24 | 0 | 0 | 0
1434 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | Material Requisition To Resource Division | 940/MD | 05/04/2023 | 0 | Resource Division | 28.23 | 0 | 0 | 0
1435 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | Electric quotation for Dasagram PWSS Tube Well-II in connection Chandkuri CCC ( Consumer No. 2004164613) | BP-2022-23-101 | 18/01/2023 | 0 | WBSEDCL | 2.47 | 0 | 0 | 0
1436 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | Electric quotation for Dasagram PWSS Tube Well-I near Hospital in connection Chandkuri CCC (Consumer No. 2004164602) | BP-2022-23-102 | 30/01/2023 | 0 | WBSEDCL | 2.41 | 0 | 0 | 0
1437 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 400 Cum (Intze type with Pile Foundation) and staging height 20.00 mtr. & FHTC under JJM with allied work for Dasha Gram and its adjoining mouzas W/S Scheme in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 1956/MD | 20/09/2022 | 1271 | M/S. A.R. ENTERPRISE. | 512.44 | 0 | 0 | 60
1438 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. , SM/10649 | New | Laying of Rising Main including Interconnection, Construction of Pump House & Boundary wall for Dasha Gram & its adjoining mouzas W/S Scheme in Sabang block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 441/MD | 10/02/2023 | 963 | M/S. A.R. ENTERPRISE. | 44.01 | 0 | 0 | 20
1439 | PASCHIM MEDINIPUR | Midnapore Division | Panna Piped Water Supply Scheme. , SM/10065 | New | Material Requisition To Resource Division | 135/MD | 11/01/2023 | 0 | Resource Division | 4.73 | 0 | 0 | 0
1440 | PASCHIM MEDINIPUR | Midnapore Division | Panna Piped Water Supply Scheme. , SM/10065 | New | Material Requisition To Resource Division | 888/MD | 30/03/2023 | 0 | Resource Division | 21.77 | 0 | 0 | 0
1441 | PASCHIM MEDINIPUR | Midnapore Division | Panna Piped Water Supply Scheme. , SM/10065 | New | Material Requisition To Resource Division | 1134/MD | 24/04/2023 | 0 | Resource Division | 21.77 | 0 | 0 | 0
1442 | PASCHIM MEDINIPUR | Midnapore Division | Panna Piped Water Supply Scheme. , SM/10065 | New | Electric Quotation. {Enter in MB No:- 3068, Page No:- 165} | BP-2022-23-468 | 27/12/2022 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.46 | 0 | 0 | 0
1443 | PASCHIM MEDINIPUR | Midnapore Mechanical | Panna Piped Water Supply Scheme. , SM/10065 | New | Installation of Dept. Submersible Pump motor set and with other supplied items and other allied works at Tubewell no 1 of Panna Water Supply Scheme Block Ghatal under MMD, PHE Dte. | 1546/MMSD-I | 12/12/2023 | 15 | SHOVAN KUMAR DAS | 1.29 | 0 | 0 | 100
1444 | PASCHIM MEDINIPUR | Midnapore Division | Panna Piped Water Supply Scheme. , SM/10065 | New | QUOTATION MONEY FOR PANNA WATER SUPPLY SCHEME, T W NO 2, [ BLOCK GHATAL ] JJM WORKS, SCHEME CODE SM/110065, APPLICATION NO 2004843733, REFERENCE ID 204368914, GHATAL CCC, WBSEDCL | BP-2024-25-458 | 12/11/2024 | 0 | WBSEDCL | 5.57 | 0 | 0 | 0
1445 | PASCHIM MEDINIPUR | Midnapore Division | Panna Piped Water Supply Scheme. , SM/10065 | New | Sinking of 200 mm x 100 mm dia. X 156 Mtr. Depth Rig bored Tube wells at 2nd Tube well site with Laying of uPVC (Class-III) & DI pipeline with FHTC works, Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room & Boundary wall, Laying of Rising main at 2nd T/W site for Panna W/S Scheme within Ghatal Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. (PART- B) | 2186/MD | 01/11/2022 | 878 | S.N ENTERPRISE | 67.2 | 0 | 0 | 5
1446 | PASCHIM MEDINIPUR | Midnapore Division | Panna Piped Water Supply Scheme. , SM/10065 | New | Soil investigation work in connection with Construction of RCC OHR, Construction & Commissioning of 150 CuM RCC OHR with FHTC works for Panna W/S Scheme within Ghatal Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. (PART- C) | 2673/MD | 30/12/2022 | 880 | CHAKRABORTTI ENTERPRISE | 86.3 | 0 | 0 | 12
1447 | PASCHIM MEDINIPUR | Midnapore Mechanical | Panna Piped Water Supply Scheme. , SM/10065 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Panna Piped Water Supply Scheme under JJM Program under MMD PHE Dte. | 789/W/MMD | 24/03/2023 | 923 | A G ENTERPRISE | 22.77 | 0 | 0 | 80
1448 | PASCHIM MEDINIPUR | Midnapore Division | Panna Piped Water Supply Scheme. , SM/10065 | New | Sinking of 200 mm x 100 mm dia. X 156 Mtr. Depth Rig bored Tube wells at Head Works cum 1st Tube well site with Laying of uPVC (Class-III) & DI pipeline, Construction of 5.40 Mtr. X 3.60 Mtr. Switch Room & Boundary wall for Panna W/S Scheme within Ghatal Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. (PART- A) | 1673/MD | 12/08/2022 | 872 | M/S. D.K.H.CONSTRUCTION | 65.06 | 0 | 0 | 100
1449 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10686 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Bhikni Nischintapur PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1660/MD | 28/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.12 | 0 | 0 | 100
1450 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10686 | Augmentation | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Bhikini Nischintapur water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | 1336/MMSD-I | 26/12/2022 | 15 | DEBJYOTI BASU | 4.37 | 0 | 0 | 50
1451 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10686 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0 | 0 | 25
1452 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10686 | Augmentation | Supply and delivery at site Submersible pumping machinery and other electro-mechanical equipment in connection with Rejuvenation of Ground water based piped piped water supply scheme for PH No III of Bhikini Nischintapur Part to accommodate FHTC under Sabang Block in Paschim Medinipur District under M.M.D,.PH.E. DTE.TSM009947 | 602/MMSD-I | 05/06/2023 | 15 | SRI KRISHNA NIRMAN | 5.76 | 0 | 0 | 100
1453 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10686 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0 | 0 | 100
1454 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10686 | Augmentation | Continuation work order for hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 922/MMSD-I | 08/08/2023 | 30 | M/S BIKASH DE | 0.15 | 0 | 0 | 100
1455 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10686 | Augmentation | Service connection charges of WBSEDCL for Bikini Nischintapur, Badalpur, Sabang additional T/W-III of Bikini Nischintapur W/S Scheme(Consumer No. 2004156126) | BP-2022-23-90 | 04/01/2023 | 0 | WBSEDCL | 2.2 | 0 | 0 | 0
1456 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10686 | Augmentation | Rejuvenation of Ground water based piped water supply scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under JJM under Sabang Block in Paschim Medinipur District Under Midnapur Division PHE Dte. | 1420/MD | 15/07/2022 | 45 | WATER LINK | 50.72 | 0 | 0 | 80
1457 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10686 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 610/W/MMD | 20/03/2023 | 180 | SRI KRISHNA NIRMAN | 10.79 | 0 | 0 | 48
1458 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10686 | Augmentation | Continuation work order for hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 894/MMSD-I | 04/08/2023 | 30 | SUBHASIS ROY | 0.15 | 0 | 0 | 0
1459 | PASCHIM MEDINIPUR | Midnapore Division | Kutulpur Piped Water Supply Scheme. , SM/09988 | New | Sinking of (Two) nos. 250 X 150 mm dia. X 120 mtr. Depth deep tube well by direct rotary method for Kutulpur & adjoining mouzas W/S Scheme within Ghatal Block under Midnapore Division, P.H.E. Dte. | 2491/MD | 17/07/2023 | 14 | MIDNAPUR PIPE CONCERN | 13.37 | 0 | 0 | 100
1460 | PASCHIM MEDINIPUR | Midnapore Division | Kutulpur Piped Water Supply Scheme. , SM/09988 | New | Material Requisition To Resource Division | 337/MD | 31/01/2023 | 0 | Resource Division | 18.14 | 0 | 0 | 0
1461 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kutulpur Piped Water Supply Scheme. , SM/09988 | New | KOTULPUR WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/09988, APPLICATION NO 2004606465, REFERENCE ID 204221239, BIRSINGHA CCC, WBSEDCL | BP-2023-24-768 | 04/03/2024 | 0 | WBSEDCL | 2.67 | 0 | 0 | 0
1462 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kutulpur Piped Water Supply Scheme. , SM/09988 | New | KOTULPUR WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/09988, APPLICATION NO 2004606516, REFERENCE ID 204221238, BIRSINGHA CCC, WBSEDCL | BP-2023-24-767 | 04/03/2024 | 0 | WBSEDCL | 4.14 | 0 | 0 | 0
1463 | PASCHIM MEDINIPUR | Midnapore Division | Kutulpur Piped Water Supply Scheme. , SM/09988 | New | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 250 Cum ( Pile Foundation) and staging height 20.00 mtr. & FHTC under JJM with allied work for Kotulpur and its adjoining mouzas W/S scheme in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 1957/MD | 20/09/2022 | 1271 | DIPAK KUMAR DOLAI | 306.49 | 0 | 0 | 72
1464 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kutulpur Piped Water Supply Scheme. , SM/09988 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Kutulpur Water supply scheme,Ghatal block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 2007/W/MMD | 30/08/2024 | 180 | M/S S M ELECTRICAL | 27 | 0 | 0 | 80
1465 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kutulpur Piped Water Supply Scheme. , SM/09988 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
1466 | PASCHIM MEDINIPUR | Midnapore Division | Kutulpur Piped Water Supply Scheme. , SM/09988 | New | Laying of rising main & inter connection for Kutulpur & its adjoining mouzas PWSS within block - Ghatal, Dist.- Paschim Medinipur under Midnapore Division, PHE Dte. | 621/MD | 05/03/2025 | 45 | SUBHASIS DOLAI | 5.67 | 0 | 0 | 0
1467 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Sinking of 2 (Two) Nos. 300 X 200 mm dia. X 220 Mtr. Depth deep tube well by Direct Rotary Method for Head Work site & 2nd Tube well site of Antla W/S Scheme with in Mohanpur block under Midnapore Division, PHE Dte. | 289/MD | 15/02/2022 | 15 | KISHORE GHOSH | 21.82 | 0 | 0 | 100
1468 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Supply & delivery of different dia. C.I.D.F. Sluice Valves for laying of Distribution main pipeline for Antla Piped water Supply Scheme within Mohanpur Block under Kharagpur Sub-division of Midnapore Division, PHE Dte. In Paschim Medinipur District (Part -II) | 312/AE/KSD | 10/06/2022 | 15 | GOBINDA MAITY | 3.51 | 0 | 0 | 0
1469 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Laying of distribution HDPE pipe line of Left-out portion and all allied works at Antla and its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. (Phase-II) | 537/AE/KSD | 23/08/2022 | 30 | PALASH KUMAR DAS | 4.78 | 0 | 0 | 0
1470 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Laying of distribution HDPE Pipe line of Left-Out portion and all allied works at Antla and its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division of Midnapore Division, PHE Dte. (Phase-I) | 536/AE/KSD | 23/08/2022 | 30 | PALASH KUMAR DAS | 4.81 | 0 | 0 | 0
1471 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Laying of distribution HDPE pipe line of Left-out portion and all allied works at Antla and its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. (Phase-III) Location Mathuribar ICDS & Kharpara | 538/AE/KSD | 23/08/2022 | 30 | PALASH KUMAR DAS | 4.85 | 0 | 0 | 0
1472 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room with out W.C. & Bath for Second Tube Well Site under Antla W/S Scheme within Midnapore Division, PHE Dte. (Considering G.L. 300 mm below road level) (Type -A) | 544/AE/KSD | 23/08/2022 | 30 | PRITI ENTERPRISE | 2.79 | 0 | 0 | 0
1473 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Continuation Work Order for the work of Laying Balance Distribution System to accommodate FHTC of Proposed Pipe Water Supply Scheme for Antla & its adjoining Mouzas, Block: - Mohanpur, District: - Paschim Midnapore. (Total Length = 11,200.00 Mtr.) | 383/MD | 03/02/2023 | 60 | MASUM ALI KHAN | 53.34 | 0 | 0 | 0
1474 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Construction of 5.40 Mtr. X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Head Works Site under Antla W/S Scheme within Midnapore Division, PHE Dte. (Considering G.L. 300 mm below road level) (Type - A) | 444/MD | 13/02/2023 | 60 | MASUM ALI KHAN | 5.21 | 0 | 0 | 0
1475 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Material Requisition To Resource Division | 148/MD | 28/01/2022 | 0 | Resource Division | 10.97 | 0 | 0 | 0
1476 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Material Requisition To Resource Division | `2430/MD | 29/11/2022 | 0 | Resource Division | 82.33 | 0 | 0 | 0
1477 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Material Requisition To Resource Division | 932/MD | 04/04/2023 | 0 | Resource Division | 57.12 | 0 | 0 | 0
1478 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Electric Quotation for Antla PWSS Tube well-II in connection Mohanpur CCC. | BP-2023-24-30 | 01/05/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 2.99 | 0 | 0 | 0
1479 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Electric Quotation for Antla PWSS Tube well-I in connection Mohanpur CCC. | BP-2023-24-31 | 01/05/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 2.72 | 0 | 0 | 0
1480 | PASCHIM MEDINIPUR | Midnapore Mechanical | Antla Piped Water Supply Scheme. , SM/09991 | New | Eletrict quotation bill for Atla water supply scheme at PH-II(Consumar Id-860286126) |  | 28/11/2023 | 0 | WBSEDCL | 2.88 | 0 | 0 | 0
1481 | PASCHIM MEDINIPUR | Midnapore Mechanical | Antla Piped Water Supply Scheme. , SM/09991 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Antla Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | 1103/W/MMD | 05/04/2023 | 180 | WEST BENGAL ENGINEERING CO. | 23.74 | 0 | 0 | 87
1482 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Electric quotation bill for Atla Water supply Scheme at PH-II (Consumar Id-860286126) [MB-No- 3179/MMD] | BP-2023-24-509 | 15/12/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 2.88 | 0 | 0 | 0
1483 | PASCHIM MEDINIPUR | Midnapore Division | Antla Piped Water Supply Scheme. , SM/09991 | New | Soil Investigation, Construction of R.C.C. Elevated Reservoir of Capacity 400 cum and staging height 20.00 mtr. (Pile Foundation) with allied works, Laying Distribution System of HDPE (PE-100) and Providing of FHTC for Antla and its adjoining mouzas Water Supply Scheme within Mohanpur Block in the district of Paschim Medinipur under Midnapore Division, P.H.E. Dte. | 2255/MD | 28/12/2021 | 1250 | MASUM ALI KHAN | 332.28 | 0 | 0 | 99
1484 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Belda, Block - Narayangarh) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | 1008/MD | 24/06/2021 | 10 | SIRCON ENGINEERING SERVICES | 4.22 | 0 | 0 | 100
1485 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Belda, Block ¿ Narayangarh) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | 965/MD | 18/06/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.9 | 0 | 0 | 100
1486 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Preparation of DPR with allied works in connection with the Functional Household Tap Connection of existing PWSS (Belda, Block - Narayangarh) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | 1009/MD | 24/06/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.19 | 0 | 0 | 100
1487 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Repairing of Damage pipe line (AC) at Mouza Deuli, Kusmuri, Sarisha of Belda Zone II W/S Scheme within Narayangarh Block under Kharagpur Sub-Division under Midnapore Division P.H.E. Dte. | 496/AE/KSD | 30/11/2021 | 30 | NIMAI LAL GURIA | 0.52 | 0 | 0 | 100
1488 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Sinking of (Two) nos. 300 X 200 mm dia. X 200mtr. depth deep tube well by direct rotary method for Augmentation of Belda PWSS (Zone-I & II) with in Narayangarh Block under Midnapore Division, P.H.E. Dte. | 583/MD | 23/02/2023 | 14 | M/S. A.R. ENTERPRISE. | 23.69 | 0 | 0 | 80
1489 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Continuation Work Order for the work of Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Belda, Block - Narayangarh) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | 1108/MD | 09/07/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.74 | 0 | 0 | 100
1490 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Material Requisition To Resource Division | 132/MD | 11/01/2023 | 0 | Resource Division | 38.43 | 0 | 0 | 0
1491 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Material Requisition To Resource Division | 1364/MD | 02/05/2023 | 0 | Resource Division | 49.19 | 0 | 0 | 0
1492 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 531/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 22.79 | 0 | 0 | 80
1493 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Material Requisition To Resource Division | 3466/MD | 25/11/2024 | 0 | Resource Division | 1.63 | 0 | 0 | 0
1494 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Laying distribution pipe line, Soil test and Construction of R.C.C. Over Head Reservoir of capacity 200 Cum and staging height 20.00 mtr. with allied work under Augmentation of Belda Zone-II & its adjoining moujas Water Supply Scheme within Narayangarh Dev. Block including supply of all labour & materials under Midnapore Division, P.H.E. Dte. Dist. Paschim Medinipur. | 2188/MD | 01/11/2022 | 180 | BANERJEE CONSTRUCTION | 558.93 | 0 | 0 | 50
1495 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Continuation Work order For "Casual hiring of Inspection vehicle for Jal Jeevan Mission on an ¿as and when required¿ basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of (01.08.2024 to 31.01.2025) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use under Midnapore Division, PHE Dte." | 2338/MD | 30/07/2024 | 183 | PULLOCK KUMAR GHOSH | 0.87 | 0 | 0 | 0
1496 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Construction of Boundary wall at Head work site for Augmentation of Belda (Zone-I) W/S Scheme within Narayangarh Block under Midnapore Division, PHE Dte. | 57/MD | 07/01/2025 | 360 | K & KABERI ENTERPRISE (PROP. GOUTAM MAITY) | 13.65 | 0 | 0 | 75
1497 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11898 | Augmentation | Continuation Work order For "Casual hiring of Inspection vehicle for Jal Jeevan Mission as and when required basis Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure from 01.02.2025 to 31.07.2025 only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use under Midnapore Division, PHE Dte." | 308/MD | 28/01/2025 | 180 | PULLOCK KUMAR GHOSH | 0.86 | 0 | 0 | 0
1498 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. , SM/11879 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kelegoda & its adjoining Mouzas PWSS Block - Ghatal under Midnapore Division, PHE Dte. | 529/MD | 21/03/2022 | 20 | GOBINDA MAITY | 4.86 | 0 | 0 | 0
1499 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. , SM/11879 | New | Material Requisition To Resource Division | 944/MD | 05/04/2023 | 0 | Resource Division | 26.63 | 0 | 0 | 0
1500 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. , SM/11879 | New | Electric quotation bill for Tw no-I of Kelegoda water supply scheme. Ref Consumer ID-204087644. | BP-2023-24-264 | 26/09/2023 | 0 | WBSEDCL | 3.99 | 0 | 0 | 0
1501 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. , SM/11879 | New | Electric Quotation bill for Tw No-II of Kelegoda water supply scheme. Ref Consumer ID-204087648. | BP-2023-24-263 | 26/09/2023 | 0 | WBSEDCL | 2.87 | 0 | 0 | 0
1502 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. , SM/11879 | New | Material Requisition To Resource Division | 3343/MD | 25/11/2024 | 0 | Resource Division | 10.47 | 0 | 0 | 0
1503 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. , SM/11879 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 2 nos. 400 cum OHR (Intze type with pile foundation) & 3 Nos. 300 Cum OHR & Accommodate FHTC (10,944 Nos,) under JJM with allied work for (i) Chaipat (Zone-I & Zone-II) & its adjoining mouzas W/S scheme (ii) Kelegoda & its adjoining mouzas W/S Scheme (iii) Uttarbar (Zone-I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2556/MD | 15/12/2022 | 1238 | M/S. S.S. ENTERPRISE | 2473.34 | 0 | 0 | 18
1504 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. , SM/11879 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based PWSS for Kelegoda & its adjoining mouzas Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | 2302/W/MMD | 29/12/2022 | 720 | DEBJYOTI BASU | 22.87 | 0 | 0 | 50
1505 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. , SM/11879 | New | Laying of Rising main pipeline for Kelegoda PWSS under Daspur-II block within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2651/MD | 28/08/2024 | 180 | SAMIR PATRA | 5.12 | 0 | 0 | 100
1506 | PASCHIM MEDINIPUR | Midnapore Division | MAHISAMURA PWSS , SM/13095 | New | Material Requisition To Resource Division | 1321/MD | 28/04/2023 | 0 | Resource Division | 25.15 | 0 | 0 | 0
1507 | PASCHIM MEDINIPUR | Central Drilling | MAHISAMURA PWSS , SM/13095 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Mahisamura WS Scheme (T/W-l & ll), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | 1095/CDD | 18/08/2023 | 30 | UNIVERSAL ENTERPRISES | 25.31 | 0 | 0 | 100
1508 | PASCHIM MEDINIPUR | Midnapore Mechanical | MAHISAMURA PWSS , SM/13095 | New | ADDITIONAL ELECTRIC QUOTATION BILL FOR TW NO-I OF MAHISHAMURA PWSS DUE TO WAY LEAVE DISPUTE. REF ID-860310382, APPLICATION NO-2004543905, APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION., NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2024-25-624 | 02/09/2024 | 0 | WBSEDCL | 3.89 | 0 | 0 | 0
1509 | PASCHIM MEDINIPUR | Midnapore Mechanical | MAHISAMURA PWSS , SM/13095 | New | ADDITIONAL ELECTRIC QUOTATION BILL FOR TW NO-II OF MAHISHAMURA PWSS DUE TO WAY LEAVE PROBLEM I.R.O APPLICATION NO-2004578943, APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, REFERENCE ID-860304242, APPLICATION ID-100000111812, NAME OF CCC- KESHIARY CCC, BLOCK-KESHIARY. | BP-2024-25-544 | 07/08/2024 | 0 | WBSEDCL | 0.81 | 0 | 0 | 0
1510 | PASCHIM MEDINIPUR | Midnapore Mechanical | MAHISAMURA PWSS , SM/13095 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of MAHISHAMURAPWSS. REF CONSUMER ID-204204415, APPLICATION NO-2004578943, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2023-24-634 | 08/02/2024 | 0 | WBSEDCL | 3.05 | 0 | 0 | 0
1511 | PASCHIM MEDINIPUR | Midnapore Mechanical | MAHISAMURA PWSS , SM/13095 | New | Electric quotation bill for Tw No-I of Mahisamura PWSS.(Ref Consumer ID-204175254) | BP-2023-24-556 | 16/01/2024 | 0 | WBSEDCL | 4.22 | 0 | 0 | 0
1512 | PASCHIM MEDINIPUR | Midnapore Mechanical | MAHISAMURA PWSS , SM/13095 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MAHISAMURA PWSSunder JJM Program under MMD PHE Dte. | 3077/W/MMD | 29/11/2023 | 489 | DAS ENTERPRISE | 22.6 | 0 | 0 | 20
1513 | PASCHIM MEDINIPUR | Midnapore Division | KONTORE AND ADJOINING MOUJAS PWSS , SM/13113 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
1514 | PASCHIM MEDINIPUR | Midnapore Division | KONTORE AND ADJOINING MOUJAS PWSS , SM/13113 | New | Material Requisition To Resource Division | 1238/MD | 27/04/2023 | 0 | Resource Division | 23.72 | 0 | 0 | 0
1515 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KONTORE AND ADJOINING MOUJAS PWSS , SM/13113 | New | Payment for new connection at Kantore t/w-1 | 59/JMD | 29/04/2024 | 0 | WBSEDCL | 4.07 | 0 | 0 | 0
1516 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KONTORE AND ADJOINING MOUJAS PWSS , SM/13113 | New | Payment for new service connection charges Kantore T/W-2 | 58/JMD | 29/04/2024 | 0 | WBSEDCL | 8.63 | 0 | 0 | 0
1517 | PASCHIM MEDINIPUR | Central Drilling | KONTORE AND ADJOINING MOUJAS PWSS , SM/13113 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1518 | PASCHIM MEDINIPUR | Central Drilling | DUDHE BUDE AND ADJOINING MOUJAS PWSS , SM/13080 | New | Providing drilling crew and other works for construction of Tube Well (250 mm X 150 mm x 220 Mtrs. Depth) by utilising Departmental Machineries for Dudhe Bude W/S Scheme (T/W-I & II), Keshiery Block under Paschim Medinipur Distrct, CDD PHE Dte. | 392/CDD | 18/05/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 25.42 | 0 | 0 | 100
1519 | PASCHIM MEDINIPUR | Midnapore Division | DUDHE BUDE AND ADJOINING MOUJAS PWSS , SM/13080 | New | Material Requisition To Resource Division | 1311/MD | 28/04/2023 | 0 | Resource Division | 30.52 | 0 | 0 | 0
1520 | PASCHIM MEDINIPUR | Midnapore Mechanical | DUDHE BUDE AND ADJOINING MOUJAS PWSS , SM/13080 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DUDHE BUDE AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 3081/W/MMD | 29/11/2023 | 180 | SANKAR PRASAD DUTTA AND CO | 22.99 | 0 | 0 | 30
1521 | PASCHIM MEDINIPUR | Midnapore Mechanical | DUDHE BUDE AND ADJOINING MOUJAS PWSS , SM/13080 | New | Electric quotation bill for Tw No-I of Dudhebudhe PWSS. (Ref Consumer ID-204136081) | BP-2023-24-384 | 02/12/2023 | 0 | WBSEDCL | 4.06 | 0 | 0 | 0
1522 | PASCHIM MEDINIPUR | Midnapore Mechanical | DUDHE BUDE AND ADJOINING MOUJAS PWSS , SM/13080 | New | Electric quotation bill for Tw No-II of Dudhebudhe PWSS. (Ref Consumer ID-204136079) | BP-2023-24-383 | 02/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0 | 0
1523 | PASCHIM MEDINIPUR | Midnapore Division | BAHURUPA AND ADJOINING MOUJAS PWSS , SM/13755 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
1524 | PASCHIM MEDINIPUR | Midnapore Division | BAHURUPA AND ADJOINING MOUJAS PWSS , SM/13755 | New | Material Requisition To Resource Division | 185/MD | 16/01/2023 | 0 | Resource Division | 15.33 | 0 | 0 | 0
1525 | PASCHIM MEDINIPUR | Midnapore Division | BAHURUPA AND ADJOINING MOUJAS PWSS , SM/13755 | New | Material Requisition To Resource Division | 3447/MD | 25/11/2024 | 0 | Resource Division | 14.89 | 0 | 0 | 0
1526 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAHURUPA AND ADJOINING MOUJAS PWSS , SM/13755 | New | Quotation for new power connection at Bahurupa PWSS tw- II within Narayangarh block Application No- 2004845777 Ref No - 204370313 | C092443173799 | 27/09/2024 | 0 | WBSEDCL | 4.41 | 0 | 0 | 0
1527 | PASCHIM MEDINIPUR | Central Drilling | BAHURUPA AND ADJOINING MOUJAS PWSS , SM/13755 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1528 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAHURUPA AND ADJOINING MOUJAS PWSS , SM/13755 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
1529 | PASCHIM MEDINIPUR | Midnapore Division | BISHNUPUR AND ADJOINING MOUJAS PWSS , SM/13006 | New | Material Requisition To Resource Division | 1260/MD | 28/04/2023 | 0 | Resource Division | 22.87 | 0 | 0 | 0
1530 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BISHNUPUR AND ADJOINING MOUJAS PWSS , SM/13006 | New | New service connection charges for Bishnupur pwss, t/w no. I | 47/JMD | 29/04/2024 | 0 | WBSEDCL | 3.92 | 0 | 0 | 0
1531 | PASCHIM MEDINIPUR | Central Drilling | BISHNUPUR AND ADJOINING MOUJAS PWSS , SM/13006 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1532 | PASCHIM MEDINIPUR | Midnapore Division | DAMODARPUR AND ADJOINING MOUJAS PWSS , SM/13008 | New | Material Requisition To Resource Division | 1201/MD | 26/04/2023 | 0 | Resource Division | 26.92 | 0 | 0 | 0
1533 | PASCHIM MEDINIPUR | Central Drilling | DAMODARPUR AND ADJOINING MOUJAS PWSS , SM/13008 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1534 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | DAMODARPUR AND ADJOINING MOUJAS PWSS , SM/13008 | New | Supply, delivery & fitting fixing of wooden board & Porcelain fuse unit for receiving power from WBSEDCL at Damodarpur & adjacent water supply schemes of Garhbeta-III block under JJM progamme under Jhargram Mechanical Division, P.H.E Dte. in the district of Paschim Medinipur. | 3784/JMD | 12/07/2024 | 30 | MONORANJAN DEY | 2.83 | 0 | 0 | 30
1535 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/11858 | New | Preparation of D.P.Rs (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- (i) Jamira & (ii) Bhagirathpur under Dewanchak-II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | 1312/MD | 16/08/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.75 | 0 | 0 | 0
1536 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/11858 | New | Service connection charge of WBSEDCL at Bhagirathpur Zone-I | BP-2022-23-96 | 11/01/2023 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
1537 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/11858 | New | Service Connection charges of WBSEDCL at Bhagirathpur TW -II Water Supply Scheme Chowka | BP-2022-23-97 | 11/01/2023 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
1538 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/11858 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Bhagirathpur (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 1729/MD | 23/08/2022 | 150 | PULLOCK KUMAR GHOSH | 43.24 | 0 | 0 | 75
1539 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/11858 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Bhagirathpur (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 1730/MD | 23/08/2022 | 150 | PULLOCK KUMAR GHOSH | 50.14 | 0 | 0 | 70
1540 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/11858 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | 2317/W/MMD | 29/12/2022 | 180 | M/S EMMESS | 6.01 | 0 | 0 | 90
1541 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/11858 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Zone-II) | 883/W/MMD | 27/03/2023 | 180 | RISHAV ENTERPRISE | 6 | 0 | 0 | 100
1542 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/11858 | New | Material Requisition To Resource Division | 3350/MD | 25/11/2024 | 0 | Resource Division | 2.87 | 0 | 0 | 0
1543 | PASCHIM MEDINIPUR | Midnapore Division | BARANGI AND ADJOINING MOUJAS PWSS , SM/12996 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh, Dantan-I & Dantan-II Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (A) Narayangarh block- (1) Kasba, (B) Dantan-I block - (1) Birbhadrapur, (2) Menakapur & (3) Benapura, (C) Dantan-II block - (1) Kusumda (Turkakasba)] | 707/MD | 06/03/2023 | 35 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 20
1544 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARANGI AND ADJOINING MOUJAS PWSS , SM/12996 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BARANGI AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 834/W/MMD | 24/03/2023 | 180 | BHAGIRATHI JUTH AND HOLDINGS PVT LTD | 23.76 | 0 | 0 | 0
1545 | PASCHIM MEDINIPUR | Midnapore Division | BARANGI AND ADJOINING MOUJAS PWSS , SM/12996 | New | Material Requisition To Resource Division | 1281/MD | 28/04/2023 | 0 | Resource Division | 29.36 | 0 | 0 | 0
1546 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARANGI AND ADJOINING MOUJAS PWSS , SM/12996 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of BARANGI PWSS. REF CONSUMER ID-204310410 APPLICATION NO-2004739361 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-213 | 28/05/2024 | 0 | WBSEDCL | 4.88 | 0 | 0 | 0
1547 | PASCHIM MEDINIPUR | Midnapore Division | SOHAGPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13057 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
1548 | PASCHIM MEDINIPUR | Midnapore Division | SOHAGPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13057 | New | Material Requisition To Resource Division | 1292/MD | 28/04/2023 | 0 | Resource Division | 31.46 | 0 | 0 | 0
1549 | PASCHIM MEDINIPUR | Midnapore Mechanical | SOHAGPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13057 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF SOHAGPUR PWSS. REF CONSUMER ID-204373750, APPLICATION NO-2004853006, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | BP-2024-25-583 | 20/08/2024 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
1550 | PASCHIM MEDINIPUR | Midnapore Mechanical | SOHAGPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13057 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF SOHAGPUR PWSS. REF CONSUMER ID-204373749, APPLICATION NO-2004852981, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | BP-2024-25-582 | 20/08/2024 | 0 | WBSEDCL | 3.21 | 0 | 0 | 0
1551 | PASCHIM MEDINIPUR | Central Drilling | SOHAGPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13057 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1552 | PASCHIM MEDINIPUR | Midnapore Division | PATHRI AND AJOINING MOUJAS , SM/13807 | New | Material Requisition To Resource Division | 536/MD | 21/02/2023 | 0 | Resource Division | 9.38 | 0 | 0 | 0
1553 | PASCHIM MEDINIPUR | Midnapore Division | PATHRI AND AJOINING MOUJAS , SM/13807 | New | Sinking of 2 Nos. Tube well & Accommodate FHTC (100 Nos.) under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 2511/MD | 18/07/2023 | 45 | DEBASISH DOGRA | 21.94 | 0 | 0 | 70
1554 | PASCHIM MEDINIPUR | Midnapore Division | PATHRI AND AJOINING MOUJAS , SM/13807 | New | Laying distribution pipe line under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | 2485/MD | 17/07/2023 | 521 | A R ENTERPRISE | 18.49 | 0 | 0 | 70
1555 | PASCHIM MEDINIPUR | Midnapore Division | PATHRI AND AJOINING MOUJAS , SM/13807 | New | Laying distribution pipe line & Accommodate FHTC (200 Nos.) under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | 5500/MD | 14/12/2023 | 45 | MAHARAJA CONSTRUCTION CO. | 43.39 | 0 | 0 | 40
1556 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PATHRI AND AJOINING MOUJAS , SM/13807 | New | New Service connection charges for Pathri w/s scheme, t/w no.-II | 184/JMD | 30/03/2024 | 0 | WBSEDCL | 8.52 | 0 | 0 | 0
1557 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PATHRI AND AJOINING MOUJAS , SM/13807 | New | New Service connection charges for Pathri w/s scheme, t/w no.-I | 185/JMD | 30/03/2024 | 0 | WBSEDCL | 3.3 | 0 | 0 | 0
1558 | PASCHIM MEDINIPUR | Central Drilling | PATHRI AND AJOINING MOUJAS , SM/13807 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1559 | PASCHIM MEDINIPUR | Midnapore Division | PATHRI AND AJOINING MOUJAS , SM/13807 | New | Laying distribution pipe line, Rising main & Accommodate FHTC (400 Nos.) including 2 yrs. O & M under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 2639/MD | 24/07/2023 | 723 | GOUTAM RAY | 138.15 | 0 | 0 | 70
1560 | PASCHIM MEDINIPUR | Midnapore Division | PATHRI AND AJOINING MOUJAS , SM/13807 | New | Construction of Pump House, Boundary wall & Accommodate FHTC (216 Nos.) under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-F] | 5152/MD | 07/11/2023 | 663 | BISWAS CONSTRUCTION | 45.23 | 0 | 0 | 81
1561 | PASCHIM MEDINIPUR | Midnapore Division | PATHRI AND AJOINING MOUJAS , SM/13807 | New | Construction of RCC OHR (150 CuM) & Accommodate FHTC (200 Nos.) under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 738/MD | 19/03/2025 | 180 | SAMIT PAL | 83.17 | 0 | 0 | 0
1562 | PASCHIM MEDINIPUR | Midnapore Mechanical | UTTAR PIASHALA PIPED WATER SUPPLY SCHEME , SM/13810 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for UTTAR PIASHALA PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | 794/W/MMD | 24/03/2023 | 180 | PADMA ENGINEERING CO. | 21.55 | 0 | 0 | 20
1563 | PASCHIM MEDINIPUR | Midnapore Division | UTTAR PIASHALA PIPED WATER SUPPLY SCHEME , SM/13810 | New | Material Requisition To Resource Division | 3372/MD | 25/11/2024 | 0 | Resource Division | 14.24 | 0 | 0 | 0
1564 | PASCHIM MEDINIPUR | Midnapore Mechanical | UTTAR PIASHALA PIPED WATER SUPPLY SCHEME , SM/13810 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of UTTAR PIASALA PWSS. REF CONSUMER ID-204188705, APPLICATION NO-2004550684, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-693 | 16/02/2024 | 0 | WBSEDCL | 2.92 | 0 | 0 | 0
1565 | PASCHIM MEDINIPUR | Midnapore Mechanical | UTTAR PIASHALA PIPED WATER SUPPLY SCHEME , SM/13810 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of UTTAR PIASALA PWSS. REF CONSUMER ID-204200349, APPLICATION NO-2004571244 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-694 | 16/02/2024 | 0 | WBSEDCL | 4.26 | 0 | 0 | 0
1566 | PASCHIM MEDINIPUR | Midnapore Division | UTTAR PIASHALA PIPED WATER SUPPLY SCHEME , SM/13810 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 0 | 75
1567 | PASCHIM MEDINIPUR | Midnapore Mechanical | UTTAR PIASHALA PIPED WATER SUPPLY SCHEME , SM/13810 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | 842/MMSD-I | 11/06/2025 | 243 | M/S BIKASH DE | 3.66 | 0 | 0 | 0
1568 | PASCHIM MEDINIPUR | Midnapore Division | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur , SM/13026 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
1569 | PASCHIM MEDINIPUR | Midnapore Division | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur , SM/13026 | New | Material Requisition To Resource Division | 1145/MD | 25/04/2023 | 0 | Resource Division | 22.96 | 0 | 0 | 0
1570 | PASCHIM MEDINIPUR | Midnapore Mechanical | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur , SM/13026 | New | Electric quotation bill for khamra pwss at TW-I (Ref Id-204169703) | BP-2023-24-490 | 29/12/2023 | 0 | WBSEDCL | 6.37 | 0 | 0 | 0
1571 | PASCHIM MEDINIPUR | Midnapore Mechanical | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur , SM/13026 | New | lectrict quotation bill for TW-II of KHAMRA pwss (Ref Consumar ID-204235950),Application No-2004627275,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | BP-2023-24-814 | 13/03/2024 | 0 | WBSEDCL | 3.17 | 0 | 0 | 0
1572 | PASCHIM MEDINIPUR | Midnapore Division | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur , SM/13026 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | 2145/MD | 08/06/2023 | 846 | GOBINDA MAITY | 1960.6 | 0 | 0 | 65
1573 | PASCHIM MEDINIPUR | Midnapore Mechanical | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur , SM/13026 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Khamra PWSS, Block-Debra, Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | 2297/W/MMD | 29/12/2022 | 914 | ABHIJIT BASU | 22.87 | 0 | 0 | 45
1574 | PASCHIM MEDINIPUR | Midnapore Division | PANCHYAR AND ADJOINING MOUJAS PWSS , SM/13216 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | 746/MD | 13/03/2023 | 30 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 0
1575 | PASCHIM MEDINIPUR | Midnapore Division | PANCHYAR AND ADJOINING MOUJAS PWSS , SM/13216 | New | Material Requisition To Resource Division | 1322/MD | 28/04/2023 | 0 | Resource Division | 28.03 | 0 | 0 | 0
1576 | PASCHIM MEDINIPUR | Midnapore Mechanical | PANCHYAR AND ADJOINING MOUJAS PWSS , SM/13216 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PANCHYAR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 3073/W/MMD | 29/11/2023 | 180 | CONCORD ENGINEERING | 21.56 | 0 | 0 | 0
1577 | PASCHIM MEDINIPUR | Central Drilling | PANCHYAR AND ADJOINING MOUJAS PWSS , SM/13216 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 220 mtrs. Depth) by utilising Departmental machineries for Panchyar W/S Scheme (TW-I & II), keshiary block under Paschim Midnapur District, CDD PHE Dte. | 1435/CDD | 26/09/2023 | 180 | SUNRISE ENGINEERING CORPORATION | 25.25 | 0 | 0 | 100
1578 | PASCHIM MEDINIPUR | Midnapore Mechanical | PANCHYAR AND ADJOINING MOUJAS PWSS , SM/13216 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of PANCHYAR PWSS. REF CONSUMER ID-204234628, APPLICATION NO-2004627380 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2023-24-891 | 22/03/2024 | 0 | WBSEDCL | 3.1 | 0 | 0 | 0
1579 | PASCHIM MEDINIPUR | Midnapore Mechanical | PANCHYAR AND ADJOINING MOUJAS PWSS , SM/13216 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of PANCHYAR PWSS. REF CONSUMER ID-204234627, APPLICATION NO-2004627392, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2023-24-892 | 21/03/2024 | 0 | WBSEDCL | 3.1 | 0 | 0 | 0
1580 | PASCHIM MEDINIPUR | Midnapore Division | BAMANBIRUA AND ADJOINING MOUJAS PWSS , SM/12991 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
1581 | PASCHIM MEDINIPUR | Midnapore Division | BAMANBIRUA AND ADJOINING MOUJAS PWSS , SM/12991 | New | Material Requisition To Resource Division | 217/MD | 16/01/2023 | 0 | Resource Division | 14.02 | 0 | 0 | 0
1582 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAMANBIRUA AND ADJOINING MOUJAS PWSS , SM/12991 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAMANBIRUA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 2396/W/MMD | 31/12/2022 | 899 | M/S EMMESS | 22.89 | 0 | 0 | 20
1583 | PASCHIM MEDINIPUR | Midnapore Division | BAMANBIRUA AND ADJOINING MOUJAS PWSS , SM/12991 | New | Material Requisition To Resource Division | 3457/MD | 25/11/2024 | 0 | Resource Division | 11.03 | 0 | 0 | 0
1584 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAMANBIRUA AND ADJOINING MOUJAS PWSS , SM/12991 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of BAMANBIRUAN PWSS. REF CONSUMER ID-204183585, APPLICATION NO-2004552319, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2023-24-747 | 27/02/2024 | 0 | WBSEDCL | 4.81 | 0 | 0 | 0
1585 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAMANBIRUA AND ADJOINING MOUJAS PWSS , SM/12991 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of BAMANBIRUAN PWSS. REF CONSUMER ID-204244321, APPLICATION NO-2004640141, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | C092403245767 | 04/09/2024 | 0 | WBSEDCL | 6.16 | 0 | 0 | 0
1586 | PASCHIM MEDINIPUR | Midnapore Division | BAMANDA AND ADJOINING MOUJAS PWSS , SM/12993 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
1587 | PASCHIM MEDINIPUR | Midnapore Division | BAMANDA AND ADJOINING MOUJAS PWSS , SM/12993 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh, Dantan-I & Dantan-II Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (A) Narayangarh block- (1) Kasba, (B) Dantan-I block - (1) Birbhadrapur, (2) Menakapur & (3) Benapura, (C) Dantan-II block - (1) Kusumda (Turkakasba)] | 707/MD | 06/03/2023 | 35 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 20
1588 | PASCHIM MEDINIPUR | Midnapore Division | BAMANDA AND ADJOINING MOUJAS PWSS , SM/12993 | New | Material Requisition To Resource Division | 192/MD | 16/01/2023 | 0 | Resource Division | 17.1 | 0 | 0 | 0
1589 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAMANDA AND ADJOINING MOUJAS PWSS , SM/12993 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAMANDA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 486/W/MMD | 20/03/2023 | 652 | DIPALI CONSTRUCTION | 22.98 | 0 | 0 | 20
1590 | PASCHIM MEDINIPUR | Midnapore Division | BAMANDA AND ADJOINING MOUJAS PWSS , SM/12993 | New | Material Requisition To Resource Division | 3458/MD | 25/11/2024 | 0 | Resource Division | 14.16 | 0 | 0 | 0
1591 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAMANDA AND ADJOINING MOUJAS PWSS , SM/12993 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of BAMANDA PWSS. REF CONSUMER ID-204212537, APPLICATION NO-2004593868, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2023-24-691 | 16/02/2024 | 0 | WBSEDCL | 4.5 | 0 | 0 | 0
1592 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAMANDA AND ADJOINING MOUJAS PWSS , SM/12993 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of BAMANDA PWSS. REF CONSUMER ID-204302072, APPLICATION NO-2004723744, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-212 | 28/05/2024 | 0 | WBSEDCL | 2.35 | 0 | 0 | 0
1593 | PASCHIM MEDINIPUR | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS , SM/14036 | New | Construction of Boundary wall & Accommodate FHTC (200 Nos.) under JJM with allied work for Mahasol & its adjoining mouzas W/S Scheme in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | 2872/MD | 10/08/2023 | 45 | DEBJIT PATRA | 16.83 | 0 | 0 | 0
1594 | PASCHIM MEDINIPUR | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS , SM/14036 | New | Construction of 250 cum OHR (Intze type with solid raft) & Accommodate FHTC (526 Nos.) under JJM with allied work for Mahasol & its adjoining mouzas W/S Scheme in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 3578/MD | 06/12/2024 | 180 | A R CONSTRUCTION | 111.83 | 0 | 0 | 0
1595 | PASCHIM MEDINIPUR | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS , SM/14036 | New | Sinking of 1 (One) Nos. Tube well for Mahasol & its adjoining mouzas PWSS in Salboni block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. (Part-II) | 2514/MD | 18/07/2023 | 15 | BADAL CHANDRA MAIKAP | 8.13 | 0 | 0 | 100
1596 | PASCHIM MEDINIPUR | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS , SM/14036 | New | Sinking of 2 (Two) Nos. Tube well for Mahasol & its adjoining mouzas PWSS in Salboni block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. (Part-I) | 2873/MD | 10/08/2023 | 30 | DEBJIT PATRA | 16.28 | 0 | 0 | 100
1597 | PASCHIM MEDINIPUR | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS , SM/14036 | New | Material Requisition To Resource Division | 3388/MD | 25/11/2024 | 0 | Resource Division | 9.4 | 0 | 0 | 0
1598 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MAHASOL AND ADJOINING MOUJAS PWSS , SM/14036 | New | New service connection charges for Mahasol, t/w-II w/s scheme | 78/JMD | 12/02/2024 | 0 | WBSEDCL | 4.38 | 0 | 0 | 0
1599 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MAHASOL AND ADJOINING MOUJAS PWSS , SM/14036 | New | New service connection charges for Mahasol, t/w-I w/s scheme | 80/JMD | 12/02/2024 | 0 | WBSEDCL | 3.03 | 0 | 0 | 0
1600 | PASCHIM MEDINIPUR | Central Drilling | MAHASOL AND ADJOINING MOUJAS PWSS , SM/14036 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1601 | PASCHIM MEDINIPUR | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS , SM/14036 | New | Laying Rising main, distribution pipe line, 2 nos. Pump House, Boundary wall & Accommodate FHTC (800 Nos.) including 2 years operation & maintenance under JJM with allied work for Mahasol & its adjoining mouzas W/S Scheme in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 2717/MD | 31/07/2023 | 754 | M/S. D.K.H.CONSTRUCTION | 241.48 | 0 | 0 | 40
1602 | PASCHIM MEDINIPUR | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS , SM/14036 | New | Construction of Pump House under JJM with allied work for Mahasol & its adjoining mouzas W/S Scheme in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 2467/MD | 14/07/2023 | 658 | ARNAB PATRA | 7.17 | 0 | 0 | 60
1603 | PASCHIM MEDINIPUR | Midnapore Division | KULDIHA AND ITS ADJOINING MOUZAS PWSS , SM/14655 | New | Material Requisition To Resource Division | 1362/MD | 02/05/2023 | 0 | Resource Division | 29.38 | 0 | 0 | 0
1604 | PASCHIM MEDINIPUR | Midnapore Mechanical | KULDIHA AND ITS ADJOINING MOUZAS PWSS , SM/14655 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KULDIHA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 460/W/MMD | 20/03/2023 | 180 | BALAJI CONSTRUCTION | 22.89 | 0 | 0 | 50
1605 | PASCHIM MEDINIPUR | Midnapore Division | KULDIHA AND ITS ADJOINING MOUZAS PWSS , SM/14655 | New | Laying distribution pipe line, Pump House, Boundary Wall, soil investigation, 250 Cum OHR ((Intze type with solid raft ) & Accommodate FHTC (2,237 nos.) under JJM with allied work for Kuldiha & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials including 02(Two) Years Operation & Maintanance under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 1964/MD | 26/06/2024 | 360 | ANIRUDDHA BAG | 517.34 | 0 | 0 | 25
1606 | PASCHIM MEDINIPUR | Midnapore Mechanical | KULDIHA AND ITS ADJOINING MOUZAS PWSS , SM/14655 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
1607 | PASCHIM MEDINIPUR | Midnapore Division | KULDIHA AND ITS ADJOINING MOUZAS PWSS , SM/14655 | New | Sinking of 2 (Two) Nos. Tube well for Kuldiha & its adjoining mouzas PWSS in Kharagpur-II block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | 2621/MD | 24/07/2023 | 623 | R. CONSTRUCTION | 16.52 | 0 | 0 | 50
1608 | PASCHIM MEDINIPUR | Midnapore Division | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15017 | New | Preparation & Submission of 2 (Two) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Kuran & its adjoining Mouzas PWSS AND (2) Kushman & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | 1766/MD | 24/08/2022 | 30 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.92 | 0 | 0 | 0
1609 | PASCHIM MEDINIPUR | Midnapore Division | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15017 | New | Material Requisition To Resource Division | 68/MD | 09/01/2023 | 0 | Resource Division | 15.87 | 0 | 0 | 0
1610 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15017 | New | QUOTATION MONEY FOR KURAN WATER SCHEME , T W NO NO 2 , APLLICATION 2004345710, REFERENCE ID 204027343, BIRSINGHA CCCC WBSEDCL | BP-2023-24-125 | 13/07/2023 | 0 | WBSEDCL | 0.51 | 0 | 0 | 0
1611 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15017 | New | QUOTATION MONEY FOR KURAN WATER SCHEME , T W NO NO 1 , APLLICATION 2004345690, REFERENCE ID 204027368, BIRSINGHA CCCC WBSEDCL | BP-2023-24-124 | 13/07/2023 | 0 | WBSEDCL | 0.51 | 0 | 0 | 0
1612 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15017 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 831/W/MMD | 24/03/2023 | 895 | WEST BENGAL ENGINEERING CO. | 22.63 | 0 | 0 | 80
1613 | PASCHIM MEDINIPUR | Midnapore Division | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15017 | New | Material Requisition To Resource Division | 3361/MD | 25/11/2024 | 0 | Resource Division | 8.6 | 0 | 0 | 0
1614 | PASCHIM MEDINIPUR | Midnapore Division | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15017 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 200 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1396 Nos.) under JJM with allied work for Kuran PWSS in Ghatal Block including supply of all labour & materials including 2 (Two) years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 577/MD | 23/02/2023 | 1133 | SUJATA CONSTRUCTION | 385.35 | 0 | 0 | 32
1615 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15017 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 1684/MMSD-I | 19/12/2023 | 60 | SUBHASIS ROY | 0.29 | 0 | 0 | 40
1616 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15017 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
1617 | PASCHIM MEDINIPUR | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15120 | New | Preparation & Submission of 6 (Six) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Shrirampur & its adjoining Mouzas PWSS, (2) Dontiara & its adjoining Mouzas PWSS, (3) Dhashachandpur Mouza Stand Alone PWSS, (4) Udayganj (P) Mouza Stand Alone PWSS, (5) Prasadchak Mouza Stand Alone PWSS AND (6) Anandapur Mouza Stand Alone PWSS, Block - Ghatal under Midnapore Division, PHE Dte. [Name of Proposed PWSS Chaulisingpur & its adjoining Mouzas PWSS & Hemantapur & its adjoining Mouzas PWSS instead of (1) Dhashachandpur Mouza Stand Alone PWSS, (2) Udayganj (P) Mouza Stand Alone PWSS, (3) Prasadchak Mouza Stand Alone PWSS AND (4) Anandapur Mouza Stand Alone PWSS] | 1767/MD | 24/08/2022 | 45 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.73 | 0 | 0 | 100
1618 | PASCHIM MEDINIPUR | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15120 | New | Material Requisition To Resource Division | 409/MD | 07/02/2023 | 0 | Resource Division | 7.09 | 0 | 0 | 0
1619 | PASCHIM MEDINIPUR | Midnapore Mechanical | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15120 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 651/W/MMD | 20/03/2023 | 180 | KAMAKSHYA ENTERPRISE | 10.77 | 0 | 0 | 80
1620 | PASCHIM MEDINIPUR | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15120 | New | Sinking of Tube well, Laying distribution pipe line, Rising main, Pump House, Operation & maintenance of 2 years under JJM with allied work for Shrirampur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 2493/MD | 17/07/2023 | 60 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.45 | 0 | 0 | 60
1621 | PASCHIM MEDINIPUR | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15120 | New | Construction of Boundary wall, Soil investigation, 100 cum OHR (Torch type with solid raft) & Accommodate FHTC (667 nos.) under JJM with allied work for Shrirampur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 807/MD | 15/03/2024 | 180 | M/S. SOURAV MAHAPATRA | 103.06 | 0 | 0 | 30
1622 | PASCHIM MEDINIPUR | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15120 | New | Laying Distribution system pipe line for Shrirampur W/S Scheme under JJM within Ghatal Block under Ghatal Sub-Division under Midnapore Division, PHE Dte. (PART - 'E') | 2262/MD | 23/07/2024 | 45 | BHOWMIK CONSTRUCTION | 14.53 | 0 | 0 | 0
1623 | PASCHIM MEDINIPUR | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15120 | New | Laying distribution pipe line under JJM with allied work for Shrirampur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 1432/MD | 04/05/2023 | 608 | AJITESH ACHARJEE | 14.56 | 0 | 0 | 40
1624 | PASCHIM MEDINIPUR | Midnapore Mechanical | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15120 | New | QUOTATION MONEY FOR SHRIRAMPUR WATER SUPPLY SCHEME, T W NO I JJM WORKS, SCHEME CODE SM/15120, APPLICATION NO 2004760170, REFERENCE ID 204322019, GHATAL CCC, WBSEDCL | BP-2024-25-294 | 18/06/2024 | 0 | WBSEDCL | 3.63 | 0 | 0 | 0
1625 | PASCHIM MEDINIPUR | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15120 | New | Laying distribution pipe line under JJM with allied work for Shrirampur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-D] | 2637/MD | 24/07/2023 | 313 | HYDRO TECH ASSOCIATES | 9.71 | 0 | 0 | 90
1626 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIRCHAK TO ACCOMMODATEFHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/15122 | New | Material Requisition To Resource Division | 74/MD | 09/01/2023 | 0 | Resource Division | 34.58 | 0 | 0 | 0
1627 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIRCHAK TO ACCOMMODATEFHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/15122 | New | Material Requisition To Resource Division | 1455/MD | 08/05/2023 | 0 | Resource Division | 11.14 | 0 | 0 | 0
1628 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIRCHAK TO ACCOMMODATEFHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/15122 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIRCHAK TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 586/W/MMD | 20/03/2023 | 717 | M.DHARA & BROTHERS | 25.14 | 0 | 0 | 90
1629 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIRCHAK TO ACCOMMODATEFHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/15122 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House , Boundary Wall soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1809 Nos) under JJM with allied work for Pirachak PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2419/MD | 13/07/2023 | 718 | BANERJEE CONSTRUCTION | 484.55 | 0 | 0 | 30
1630 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIRCHAK TO ACCOMMODATEFHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/15122 | New | New Service connection charges. | 20/JMD | 04/03/2024 | 0 | WBSEDCL | 4.23 | 0 | 0 | 0
1631 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIRCHAK TO ACCOMMODATEFHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/15122 | New | New Service connection charges. | 19/JMD | 04/03/2024 | 0 | WBSEDCL | 5.33 | 0 | 0 | 0
1632 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIRCHAK TO ACCOMMODATEFHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/15122 | New | Laying of rising main & interconnection for Pirchak & its adjoining mouzas PWSS, Block: - Chandrakona-I, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 318/MD | 29/01/2025 | 45 | MAA SARADA ENTERPRISE | 7.33 | 0 | 0 | 0
1633 | PASCHIM MEDINIPUR | Midnapore Division | TARUA AND ADJOINING MOUJAS PWSS , SM/13166 | New | Material Requisition To Resource Division | 1170/MD | 26/04/2023 | 0 | Resource Division | 33.08 | 0 | 0 | 0
1634 | PASCHIM MEDINIPUR | Central Drilling | TARUA AND ADJOINING MOUJAS PWSS , SM/13166 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1635 | PASCHIM MEDINIPUR | Midnapore Division | TARUA AND ADJOINING MOUJAS PWSS , SM/13166 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 0 | 20
1636 | PASCHIM MEDINIPUR | Midnapore Division | ELUNI PIPED WATER SUPPLY SCHEME , SM/13081 | New | Material Requisition To Resource Division | 3369/MD | 25/11/2024 | 0 | Resource Division | 10.82 | 0 | 0 | 0
1637 | PASCHIM MEDINIPUR | Midnapore Mechanical | ELUNI PIPED WATER SUPPLY SCHEME , SM/13081 | New | Electric quotation bill for Tw No-I of ELUNI PWSS. (Ref Consumer ID-204188708), APPLICATION NO-2004550744, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC | BP-2023-24-616 | 07/02/2024 | 0 | WBSEDCL | 2.88 | 0 | 0 | 0
1638 | PASCHIM MEDINIPUR | Midnapore Mechanical | ELUNI PIPED WATER SUPPLY SCHEME , SM/13081 | New | Electric quotation bill for Tw No-II of ELUNI PWSS. (Ref Consumer ID-204200310), Application No-2004571268, Application Type-New Connection, Name of CCC-Upperkuai. Block-Keshpur | BP-2023-24-617 | 07/02/2024 | 0 | WBSEDCL | 3.19 | 0 | 0 | 0
1639 | PASCHIM MEDINIPUR | Midnapore Mechanical | ELUNI PIPED WATER SUPPLY SCHEME , SM/13081 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ELUNI PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | 535/W/MMD | 20/03/2023 | 803 | DEBJYOTI BASU | 22.78 | 0 | 0 | 25
1640 | PASCHIM MEDINIPUR | Midnapore Division | ELUNI PIPED WATER SUPPLY SCHEME , SM/13081 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 0 | 75
1641 | PASCHIM MEDINIPUR | Midnapore Division | ELUNI PIPED WATER SUPPLY SCHEME , SM/13081 | New | Laying of rising main & interconnection for Eluni & its adjoining mouzas PWSS, Block ¿ Keshpur, District ¿ Paschim Medinipur under Midnapore Division, PHE Dte. (Length = 1,040 Mtr.). | 51/MD | 07/01/2025 | 45 | SAYEEDI CONSTRUCTION | 6.84 | 0 | 0 | 0
1642 | PASCHIM MEDINIPUR | Midnapore Mechanical | ELUNI PIPED WATER SUPPLY SCHEME , SM/13081 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | 842/MMSD-I | 11/06/2025 | 243 | M/S BIKASH DE | 3.66 | 0 | 0 | 0
1643 | PASCHIM MEDINIPUR | Midnapore Division | GARMAL AND ADJOINING MOUJAS PWSS , SM/14090 | New | Material Requisition To Resource Division | 539/MD | 21/02/2023 | 0 | Resource Division | 14 | 0 | 0 | 0
1644 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GARMAL AND ADJOINING MOUJAS PWSS , SM/14090 | New | New Service Connection Charges for Garmal T/W - I PWSS | 359/JMD | 20/09/2024 | 0 | WBSEDCL | 8.11 | 0 | 0 | 0
1645 | PASCHIM MEDINIPUR | Central Drilling | GARMAL AND ADJOINING MOUJAS PWSS , SM/14090 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1646 | PASCHIM MEDINIPUR | Midnapore Division | GARMAL AND ADJOINING MOUJAS PWSS , SM/14090 | New | Laying distribution pipe line, Rising main & Accommodate FHTC (250 Nos.) including 2 yrs. O & M under JJM with allied work for Garmal PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 1837/MD | 12/06/2024 | 541 | S.T. ENTERPRISE | 141.14 | 0 | 0 | 0
1647 | PASCHIM MEDINIPUR | Midnapore Division | GARMAL AND ADJOINING MOUJAS PWSS , SM/14090 | New | Sinking of Tube well, Laying distribution pipe line, Pump House & Accommodate FHTC (300 Nos.) under JJM with allied work for Garmal PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 827/MD | 15/03/2024 | 660 | MIDNAPUR PIPE CONCERN | 75.01 | 0 | 0 | 40
1648 | PASCHIM MEDINIPUR | Midnapore Division | GARMAL AND ADJOINING MOUJAS PWSS , SM/14090 | New | Construction of RCC OHR (150 CuM), Boundary wall & Accommodate FHTC (400 Nos.) under JJM with allied work for Garmal PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 3402/MD | 25/11/2024 | 360 | S.T. ENTERPRISE | 113.63 | 0 | 0 | 0
1649 | PASCHIM MEDINIPUR | Midnapore Division | PATHRAJURI AND ADJOINING MOUJAS PWSS , SM/15535 | New | Material Requisition To Resource Division | 1263/MD | 28/04/2023 | 0 | Resource Division | 16.49 | 0 | 0 | 0
1650 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PATHRAJURI AND ADJOINING MOUJAS PWSS , SM/15535 | New | New Service Connection Charges for Pathrajuri-I PWSS |  | 12/12/2024 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
1651 | PASCHIM MEDINIPUR | Central Drilling | PATHRAJURI AND ADJOINING MOUJAS PWSS , SM/15535 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1652 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14480 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Raghunath chak PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | 552/AE/KSD | 23/08/2022 | 30 | GOBINDA MAITY | 2.36 | 0 | 0 | 0
1653 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14480 | Augmentation | Material Requisition To Resource Division | 1371/MD | 02/05/2023 | 0 | Resource Division | 6.5 | 0 | 0 | 0
1654 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14480 | Augmentation | Electric Quotation for ADD Tw No-III of Raghunathchak w/s scheme.(Consumer ID-203972934) | BP-2023-24-27 | 04/05/2023 | 0 | WBSEDCL | 2.53 | 0 | 0 | 0
1655 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14480 | Augmentation | Laying additional distribution pipeline to accommodate FHTC & allied work for Raghunath Chak PWSS under Pingla block within Midnapore Division, PHE Dte. | 3571/MD | 06/12/2024 | 60 | SANJIT SINHA | 34.47 | 0 | 0 | 0
1656 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14480 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 615/W/MMD | 20/03/2023 | 180 | CHAKRABORTY MINING & ENGINEERING | 10.78 | 0 | 0 | 80
1657 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/14480 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Balance FHTC (109) & Repair of Pump House & for Augmentation of Raghunathchak PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 451/MD | 13/02/2023 | 689 | MASUM ALI KHAN | 95 | 0 | 0 | 82
1658 | PASCHIM MEDINIPUR | Midnapore Division | NAHARPUR AND ADJOINING MOUJAS PWSS , SM/15024 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Ganua, (2) Gokulpur & (3) Naharpur] | 834/MD | 22/03/2023 | 21 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0 | 0
1659 | PASCHIM MEDINIPUR | Midnapore Division | NAHARPUR AND ADJOINING MOUJAS PWSS , SM/15024 | New | Material Requisition To Resource Division | 1478 | 10/05/2023 | 0 | Resource Division | 43.26 | 0 | 0 | 0
1660 | PASCHIM MEDINIPUR | Midnapore Mechanical | NAHARPUR AND ADJOINING MOUJAS PWSS , SM/15024 | New | Quotation for new power connection at Nahapar PWSS T/W- I , Application no- 2004677546 , ref. Id - 204270806 | BP-2024-25-141 | 09/05/2024 | 0 | WBSEDCL | 2.96 | 0 | 0 | 0
1661 | PASCHIM MEDINIPUR | Central Drilling | NAHARPUR AND ADJOINING MOUJAS PWSS , SM/15024 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1662 | PASCHIM MEDINIPUR | Midnapore Division | NAHARPUR AND ADJOINING MOUJAS PWSS , SM/15024 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
1663 | PASCHIM MEDINIPUR | Midnapore Mechanical | NAHARPUR AND ADJOINING MOUJAS PWSS , SM/15024 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
1664 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15218 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Beluria PWSS within Pingla Block under Midnapore Division, P.H.E. Dte. | 1658/MD | 28/09/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 2.18 | 0 | 0 | 0
1665 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15218 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0 | 0 | 25
1666 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15218 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0 | 0 | 100
1667 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15218 | Augmentation | Electric quotation for Add Tw no-III of Beluria w/s scheme. (Consumer ID-203972911) | BP-2023-24-28 | 04/05/2023 | 0 | WBSEDCL | 2.31 | 0 | 0 | 0
1668 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15218 | Augmentation | Electric Quotation for Add Tw no-IV of Beluria w/s scheme. (Consumer ID-203972925) | BP-2023-24-29 | 04/05/2023 | 0 | WBSEDCL | 2.32 | 0 | 0 | 0
1669 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15218 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall for Rejuvenation of Beluria PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 448/MD | 13/02/2023 | 45 | BABUSONA CONSTRUCTION | 75.12 | 0 | 0 | 80
1670 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15218 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 611/W/MMD | 20/03/2023 | 180 | MAA TARA ENTERPRISE | 10.76 | 0 | 0 | 25
1671 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15218 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Additional Tube Well-IV of Beluria to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | 1415/W/MMD | 02/06/2023 | 180 | AMIT DAS | 11.85 | 0 | 0 | 10
1672 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15218 | Augmentation | Material Requisition To Resource Division | 3428/MD | 25/11/2024 | 0 | Resource Division | 6.27 | 0 | 0 | 0
1673 | PASCHIM MEDINIPUR | Central Drilling | LENGA MARA AND IT'S ADJOINING MOUJAS , SM/13094 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm x 150mm x 220 Mtrs.) by utilising departmental rig machine for Langamara PWSS (T/W-I, II & III) Keshiary Block under Pachim Medinipur District, Central Drilling Division PHE Dte. | 1097/CDD | 18/08/2023 | 30 | UNIVERSAL ENTERPRISES | 36.91 | 0 | 0 | 55
1674 | PASCHIM MEDINIPUR | Midnapore Division | LENGA MARA AND IT'S ADJOINING MOUJAS , SM/13094 | New | Material Requisition To Resource Division | 1320/MD | 28/04/2023 | 0 | Resource Division | 45.8 | 0 | 0 | 0
1675 | PASCHIM MEDINIPUR | Midnapore Mechanical | LENGA MARA AND IT'S ADJOINING MOUJAS , SM/13094 | New | Electric quotation bill for Tw No-II of Lengamara PWSS.(Ref Conumer ID-204136078) | BP-2023-24-379 | 02/12/2023 | 0 | WBSEDCL | 4.36 | 0 | 0 | 0
1676 | PASCHIM MEDINIPUR | Midnapore Mechanical | LENGA MARA AND IT'S ADJOINING MOUJAS , SM/13094 | New | Electric quotation bill for Tw no-I of Langamara PWSS.(Ref Consumer ID-204136076 | BP-2023-24-381 | 02/12/2023 | 0 | WBSEDCL | 6.74 | 0 | 0 | 0
1677 | PASCHIM MEDINIPUR | Midnapore Mechanical | LENGA MARA AND IT'S ADJOINING MOUJAS , SM/13094 | New | ADDITIONAL QUOTATION FOR NEW SERVICE CONNECTION IRO APPLICATION NO-2004495588, FOR TW NO-II of LANGAMARA PWSS. REF ID-860293842 , APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION., NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY. | BP-2023-24-810 | 11/03/2024 | 0 | WBSEDCL | 1.44 | 0 | 0 | 0
1678 | PASCHIM MEDINIPUR | Midnapore Mechanical | LENGA MARA AND IT'S ADJOINING MOUJAS , SM/13094 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for LENGA MARA AND IT'S ADJOINING MOUJASunder JJM Program under MMD PHE Dte. | 3078/W/MMD | 29/11/2023 | 672 | S.P. ENTERPRISE | 22.65 | 0 | 0 | 20
1679 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Shyamsundarpur PWSS , SM/08695 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Shyamsundarpur PWSS (2nd Phase) in Sabang block in the district of Paschim Medinipur. | 1449/MD | 03/09/2021 | 60 | M/S. A.R. ENTERPRISE. | 122.79 | 60.6 | 49.35 | 75
1680 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Hatimasan Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/08678 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Hatimasan PWSS to accommodate FHTC under JJM under Garhbeta-II block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 2247/MD | 28/12/2021 | 15 | NIMAI HAZRA | 17.04 | 0 | 0 | 0
1681 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Hatimasan Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/08678 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Hatimasan, Block - Garhbeta-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | 65/MD | 11/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.91 | 1.74 | 100 | 0
1682 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING OF GROUND WATER BASED BHIMPUR PWSS TO ACCOMMODATE FHTC INCLUDING ALLIED WORKS UNDER JJM UNDER SALBONI BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MIDNAPORE DIVISION,P.H.E. Dte. , SM/16949 | Retrofitting | Accommodate balance FHTC (150 Nos.) and others allied works for Ground Water Based Bhimpur PWSS under JJM of Salboni Block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 2489/MD | 17/07/2023 | 30 | DIPAK KUMAR BAKLY | 13.72 | 0 | 0 | 95
1683 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING OF GROUND WATER BASED BHIMPUR PWSS TO ACCOMMODATE FHTC INCLUDING ALLIED WORKS UNDER JJM UNDER SALBONI BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MIDNAPORE DIVISION,P.H.E. Dte. , SM/16949 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Bhimpur, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | 348/MD | 25/02/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.99 | 0 | 0 | 0
1684 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KENCHKAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/15595 | New | Material Requisition To Resource Division | 1581/MD | 15/05/2023 | 0 | Resource Division | 51.23 | 0 | 0 | 0
1685 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KENCHKAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/15595 | New | New Service connection charges. | 199/JMD | 14/06/2024 | 0 | WBSEDCL | 4.72 | 0 | 0 | 0
1686 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KENCHKAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/15595 | New | Quotation for new service connection at Kenchkapur T/W-II water supply scheme. | 377/JMD | 30/09/2024 | 0 | WBSEDCL | 5.3 | 0 | 0 | 0
1687 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KENCHKAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/15595 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KENCHKAPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 911/W/MMD | 27/03/2023 | 886 | JAL PRAVAHIKA PVT. LTD. | 25.24 | 0 | 0 | 95
1688 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18027 | New | Sinking of 2 (Two) nos. 250 X 200 mm dia. X 190 mtr. depth deep tube well by direct rotary method for Head work site & 2nd tube well site of Dhanyagachhi PWSS with in Chandrakona- II block under Midnapore Division, P.H.E Dte. [PART-F] | 973/MD | 10/04/2023 | 21 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.67 | 0 | 0 | 100
1689 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18027 | New | Laying of Distribution pipe line for Dhanyagachhi & its adjoing mouza Water Supply Scheme under Chandrakona-II block within Midnapore Division, PHE Dte. [PART-D] | 1024/MD | 12/04/2023 | 30 | R. CONSTRUCTION | 31.96 | 0 | 0 | 100
1690 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18027 | New | Material Requisition To Resource Division | 203/MD | 16/01/2023 | 0 | Resource Division | 32.91 | 0 | 0 | 0
1691 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18027 | New | New service connection | 9/JMD | 11/10/2023 | 0 | WBSEDCL | 7.31 | 0 | 0 | 0
1692 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18027 | New | New service connection | 8/JMD | 11/10/2023 | 0 | WBSEDCL | 11.96 | 0 | 0 | 0
1693 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18027 | New | Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for Dhanyagachhi PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE. Dte. [PART-A] | 1142/MD | 25/04/2023 | 180 | SUJATA CONSTRUCTION | 262.98 | 0 | 0 | 30
1694 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18027 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 944/W/MMD | 28/03/2023 | 180 | DEBJYOTI BASU | 25.25 | 0 | 0 | 100
1695 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18027 | New | Material Requisition To Resource Division | 3332/MD | 25/11/2024 | 0 | Resource Division | 10.85 | 0 | 0 | 0
1696 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Abashgarh PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17380 | Solarisation | Solarization of grid connected pumping installation at Abashgarh PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 711/W/MMD | 23/03/2023 | 180 | M/S EMMESS | 6.26 | 0 | 0 | 0
1697 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Mohanpur (Ghatal) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17744 | Solarisation | Solarization of grid connected pumping installation at Mohanpur (Ghatal) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 984/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
1698 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Sonakhali PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17370 | Solarisation | Solarization of grid connected pumping installation at Sonakhali PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 702/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
1699 | PASCHIM MEDINIPUR | Midnapore Division | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS , SM/17619 | New | Material Requisition To Resource Division | 1584/MD | 15/05/2023 | 0 | Resource Division | 22.79 | 0 | 0 | 0
1700 | PASCHIM MEDINIPUR | Midnapore Mechanical | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS , SM/17619 | New | Electrict quotation bill for TW-I of Nijpapan pwss (Ref Consumar ID-204439149),Application No-2004955912,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | C112429784294 | 25/11/2024 | 0 | WBSEDCL | 7.13 | 0 | 0 | 0
1701 | PASCHIM MEDINIPUR | Midnapore Mechanical | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS , SM/17619 | New | Electrict quotation bill for TW-II of Nijpapan pwss (Ref Consumar ID-204439153),Application No-2004955897,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | C112429781413 | 25/11/2024 | 0 | WBSEDCL | 8.48 | 0 | 0 | 0
1702 | PASCHIM MEDINIPUR | Midnapore Division | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS , SM/17619 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 0 | 25
1703 | PASCHIM MEDINIPUR | Midnapore Mechanical | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS , SM/17619 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NIJPAPAN AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 824/W/MMD | 24/03/2023 | 952 | P.K.ENGINEERING | 22.65 | 0 | 0 | 45
1704 | PASCHIM MEDINIPUR | Midnapore Mechanical | MADHABPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17622 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MADHABPUR AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 799/W/MMD | 24/03/2023 | 180 | BHABANI PRASAD MANNA | 21.62 | 0 | 0 | 0
1705 | PASCHIM MEDINIPUR | Midnapore Division | MADHABPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17622 | New | Material Requisition To Resource Division | 1511/MD | 12/05/2023 | 0 | Resource Division | 26.72 | 0 | 0 | 0
1706 | PASCHIM MEDINIPUR | Midnapore Division | MADHABPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17622 | New | Construction of 150 Cum, 200 Cum & 250 Cum Capacity R.C.C Over Head Reservoir Over (Intze type with solid raft) works with Laying of Rising Main, Distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (5061 Nos.) including 2 years Operation & Maintenance for Loyada, Madhabpur, Patna and Radhamohanpur-II Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2824/MD | 07/08/2023 | 723 | MADE AND TRADE CO. | 1346.28 | 0 | 0 | 75
1707 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Keshiary PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17342 | Solarisation | Solarization of grid connected pumping installation at Keshiary PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 691/W/MMD | 23/03/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 6.26 | 0 | 0 | 70
1708 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Barisha, Zone-I & Zone-II PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17343 | Solarisation | Solarization of grid connected pumping installation at Barisha, Zone-I & Zone-II PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 679/W/MMD | 23/03/2023 | 180 | A-NIK & CO. | 12.52 | 0 | 0 | 35
1709 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Bhikni Nischintapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17734 | Solarisation | Solarization of grid connected pumping installation Bhikni Nischintapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 978/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 77
1710 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Bhikni Nischintapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17734 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 720/MMSD-I | 07/06/2024 | 15 | SUBHASIS ROY | 2.29 | 0 | 0 | 100
1711 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Khasbazar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17328 | Solarisation | Solarization of grid connected pumping installation at Khasbazar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 783/W/MMD | 24/03/2023 | 180 | A.S.ENGINEERING | 6.25 | 0 | 0 | 60
1712 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18192 | New | Sinking of 1 (One) No. 200 X 100 mm dia. X 150 Mtr. depth deep tube wells drilling by direct rotary method for Keshuria & its adjoining mouzas PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. [Part-II] | 2627/MD | 24/07/2023 | 10 | GOPAL RANA | 6.01 | 0 | 0 | 0
1713 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18192 | New | Sinking of 2 (Two) Nos. 150 X 100 mm dia. X 150 Mtr. depth deep tube wells drilling by direct rotary method for Keshuria & its adjoining mouzas PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | 2626/MD | 24/07/2023 | 21 | MIDNAPUR PIPE CONCERN | 11.81 | 0 | 0 | 100
1714 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18192 | New | Material Requisition To Resource Division | 1366/MD | 02/05/2023 | 0 | Resource Division | 22.98 | 0 | 0 | 0
1715 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18192 | New | QUOTATION FOR NEW POWER CONNECTION OF KESHURIA [ ZONE-II/ T W -I] WATER SUPPLY ASCHEME [ APPLICATION --2004479640, REFERENCE ID ----204122245, NIMPURA CCC, QUOTATION NO ---2004479640/QUOT/03 DATED 26/10/2023, SCHEME NAME --- KESHURIA [ ZONE-II/ TW -I] . , SCHEME CODE ---SM/18192 , MB NO--3580 ] | BP-2023-24-345 | 10/11/2023 | 0 | WBSEDCL | 0.51 | 0 | 0 | 0
1716 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18192 | New | QUOTATION FOR NEW POWER CONNECTION OF KESHURIA [ ZONE-II/ T W -II] WATER SUPPLY ASCHEME [ APPLICATION --2004479660, REFERENCE ID ----204122246, NIMPURA CCC, QUOTATION NO ---2004479660/QUOT/03 DATED 26/10/2023, SCHEME NAME --- KESHURIA [ ZONE-II/ TW -II] . , SCHEME CODE ---SM/18192 , MB NO--3580 ] | BP-2023-24-346 | 10/11/2023 | 0 | WBSEDCL | 4.04 | 0 | 0 | 0
1717 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18192 | New | Sinking of 1 (One) No. 200 X 100 mm dia. X 150 Mtr. depth deep tube wells drilling by direct rotary method for Keshuria & its adjoining mouzas PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. [Part-I] | 2488/MD | 17/07/2023 | 10 | MAHALAKSHMI ENTERPRISE | 5.88 | 0 | 0 | 100
1718 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18192 | New | QUOTATION MONEY FOR KESHURIA WATER SUPPLY SCHEME, ZONE- I , T W NO I , [ DARKHOLA ] , JJM WORKS, SCHEME CODE SM/18192, APPLICATION NO 2004890131, REFERENCE ID 204393531, NIMPURA CCC, WBSEDCL | C112417260038 | 12/11/2024 | 0 | WBSEDCL | 5.17 | 0 | 0 | 0
1719 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18192 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER Kharagpur - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | 1187/W/MMD | 25/04/2023 | 180 | A G ENTERPRISE | 40.67 | 0 | 0 | 40
1720 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18192 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
1721 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18192 | New | Construction of 250 Cum capacity R.C.C. Over Head Reservoirs including Sub-Soil Investigation work with Laying of distribution system, Pump Houses, Boundary Walls & providing Functional Household Tap Connection (1258 Nos.) including 02 (Two) years O & M for KESHURIA (ZONE-I,II) Pipe W/S Scheme within Kharagpur-I Block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in Paschim Medinipur District. | 1778/MD | 08/09/2025 | 180 | CHAKRBORTTI ENTERPRISE | 334.01 | 0 | 0 | 0
1722 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Jote Ghanashyam PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17407 | Solarisation | Solarization of grid connected pumping installation at Jote Ghanashyam PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 781/W/MMD | 24/03/2023 | 180 | RSA ENTERPRISE | 6.26 | 0 | 0 | 0
1723 | PASCHIM MEDINIPUR | Midnapore Division | Jarisai (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17560 | New | Material Requisition To Resource Division | 2006/MD | 16/05/2023 | 0 | Resource Division | 40.53 | 0 | 0 | 0
1724 | PASCHIM MEDINIPUR | Midnapore Division | Jarisai (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17560 | New | Material Requisition To Resource Division | 1464 | 08/05/2023 | 0 | Resource Division | 36.82 | 0 | 0 | 0
1725 | PASCHIM MEDINIPUR | Midnapore Mechanical | Jarisai (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17560 | New | Electrict quotation bill for TW-I of Jarisai pwss (Zone-II) (Ref Consumar ID-204310810),Application No-2004741371,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | BP-2024-25-199 | 24/05/2024 | 0 | WBSEDCL | 4.68 | 0 | 0 | 0
1726 | PASCHIM MEDINIPUR | Midnapore Mechanical | Jarisai (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17560 | New | Electrict quotation bill for TW-II of Jarisai pwss (Zone-II) (Ref Consumar ID-204310795),Application No-2004741390,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | BP-2024-25-200 | 24/05/2024 | 0 | WBSEDCL | 5.43 | 0 | 0 | 0
1727 | PASCHIM MEDINIPUR | Midnapore Mechanical | Jarisai (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17560 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Jarisai (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 1192/W/MMD | 25/04/2023 | 712 | GOENKA ENTERPRISE | 22.76 | 0 | 0 | 50
1728 | PASCHIM MEDINIPUR | Midnapore Division | Jarisai (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17560 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 200 Cum & 300 Cum OHR (Intze type with Solid raft/ Pile Foundation) & Accommodate FHTC (6,605 Nos.) including Two years O&M under JJM with allied work for Jarisai PWSS (Zone-I & Zone-II) & Kashida (Zone-I & Zone-II) with in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5360/MD | 30/11/2023 | 673 | GOBINDA MAITY | 2125.38 | 0 | 0 | 46
1729 | PASCHIM MEDINIPUR | Midnapore Division | Jarisai (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17560 | New | Construction of Approach Road (3m width) of Jarisai (Zone-II) Piped Water Supply Scheme at Mohanpur block under Midnapore Division, PHE Dte. | 157/MD | 15/01/2025 | 30 | GOBINDA MAITY | 1.31 | 0 | 0 | 100
1730 | PASCHIM MEDINIPUR | Midnapore Division | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17561 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kashida & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | 1113/MD | 09/06/2022 | 20 | ENVIROTECH SOLUTIONS | 1.69 | 0 | 0 | 100
1731 | PASCHIM MEDINIPUR | Midnapore Division | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17561 | New | Material Requisition To Resource Division | 2010/MD | 16/05/2023 | 0 | Resource Division | 24.75 | 0 | 0 | 0
1732 | PASCHIM MEDINIPUR | Midnapore Division | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17561 | New | Material Requisition To Resource Division | 000209 | 08/05/2023 | 0 | Resource Division | 24.75 | 0 | 0 | 0
1733 | PASCHIM MEDINIPUR | Midnapore Division | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17561 | New | Material Requisition To Resource Division | 1532/MD | 12/05/2023 | 0 | Resource Division | 0.67 | 0 | 0 | 0
1734 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17561 | New | Electrict quotation bill for TW-II of Kashida pwss (Zone-II) (Ref Consumar ID-204434298),Application No-2004944507,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | C112429747814 | 25/11/2024 | 0 | WBSEDCL | 3.97 | 0 | 0 | 0
1735 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17561 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 1193/W/MMD | 25/04/2023 | 716 | GOENKA ENTERPRISE | 22.63 | 0 | 0 | 50
1736 | PASCHIM MEDINIPUR | Midnapore Division | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17561 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 200 Cum & 300 Cum OHR (Intze type with Solid raft/ Pile Foundation) & Accommodate FHTC (6,605 Nos.) including Two years O&M under JJM with allied work for Jarisai PWSS (Zone-I & Zone-II) & Kashida (Zone-I & Zone-II) with in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5360/MD | 30/11/2023 | 673 | GOBINDA MAITY | 2125.38 | 0 | 0 | 46
1737 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Maligram PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17333 | Solarisation | Solarization of grid connected pumping installation at Maligram PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 696/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
1738 | PASCHIM MEDINIPUR | Midnapore Division | DHENGADAHA AND ADJOINING MOUJAS PWSS , SM/13000 | New | Material Requisition To Resource Division | 1180/MD | 26/04/2023 | 0 | Resource Division | 28.14 | 0 | 0 | 0
1739 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | DHENGADAHA AND ADJOINING MOUJAS PWSS , SM/13000 | New | NEW SERVICE CONNECTION CHARGES AT DHENGADAHA TW-II WATER SUPPLY SCHEME | 251/JMD | 10/07/2024 | 0 | WBSEDCL | 5.83 | 0 | 0 | 0
1740 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | DHENGADAHA AND ADJOINING MOUJAS PWSS , SM/13000 | New | NEW SERVICE CONNECTION CHARGES AT DHENGADAHA TW-I WATER SUPPLY SCHEME | 250/JMD | 10/07/2024 | 0 | WBSEDCL | 5.32 | 0 | 0 | 0
1741 | PASCHIM MEDINIPUR | Central Drilling | DHENGADAHA AND ADJOINING MOUJAS PWSS , SM/13000 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1742 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11895 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Julkapur PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1665/MD | 28/09/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 2.02 | 0 | 0 | 100
1743 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11895 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Additional Tube Well-IV of Julkapur to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | 1350/W/MMD | 24/05/2023 | 180 | SUBHASIS ROY | 11.88 | 0 | 0 | 93
1744 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11895 | Augmentation | Supply and delivery at site Submersible pumping machinery and other electro-mechanical equipment in connection with Rejuvenation of Ground water based piped piped water supply scheme for PH NoIII of Julkapur Part to accommodate FHTC under Sabang Block in Paschim Medinipur District under M.M.D,.PH.E. DTE.TSM009944 | 606/MMSD-I | 06/06/2023 | 15 | EMCON | 5.76 | 0 | 0 | 100
1745 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11895 | Augmentation | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Julkapur water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | 1335/MMSD-I | 26/12/2022 | 15 | DEBJYOTI BASU | 4.37 | 0 | 0 | 50
1746 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11895 | Augmentation | Service Connection charges of WBSEDCL for Additional T/W-III of Julkapur W/S Scheme (Consumer No. 2004156146) | BP-2022-23-89 | 04/01/2023 | 0 | WBSEDCL | 2.41 | 0 | 0 | 0
1747 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11895 | Augmentation | Electric quotation for Julkapur PWSS Tube Well-IV WS Scheme (Ref. ID 203938905) | BP-2022-23-154 | 29/03/2023 | 0 | WBSEDCL | 1.85 | 0 | 0 | 0
1748 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11895 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 950/W/MMD | 28/03/2023 | 180 | EMCON | 10.78 | 0 | 0 | 90
1749 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11895 | Augmentation | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. |  | 31/01/2023 | 0 | BADAL CHANDRA BERA | 0.63 | 0 | 0 | 0
1750 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11895 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | 371/MD | 02/02/2023 | 60 | DEBASISH DOGRA | 27.86 | 0 | 0 | 100
1751 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Construction of 250 (Intze type Raft Foundation) & Accommodate FHTC (2,237 Nos.) including Two years O&M under JJM with allied work for Panchkuri & adjoining Mouza W/S Scheme in Midnapur Sadar Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | 2926/MD | 16/08/2023 | 180 | M/S. CARE | 462.61 | 0 | 0 | 10
1752 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Sinking of Tube Well, Pump House, Boundary Wall & Accommodate FHTC (354 Nos.) under JJM with allied work for Barua & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | 3098/MD | 25/08/2023 | 45 | PULLOCK KUMAR GHOSH | 36.04 | 0 | 0 | 5
1753 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 100 (Intze type Raft Foundation) & Accommodate FHTC (709 Nos.) including 2 years O&M under JJM with allied work for Chandipur (Zone-I) & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | 3904/MD | 27/09/2023 | 180 | KISHORE GHOSH | 219.55 | 0 | 0 | 15
1754 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 Cum OHR (Intze type Pile Foundation) & Accommodate FHTC (3,719 Nos.) including Two years O&M under JJM with allied work for Juarhati & adjoining Mouza W/S Scheme in Midnapur Sadar Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | 438/MD | 20/02/2024 | 720 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 575.05 | 0 | 0 | 0
1755 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Construction of Boundary Wall, Construction & Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 cum and staging height 20 mtr. & Accommodate FHTC (691 Nos.) including 2 years O&M under JJM with allied work for Bishra & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | 3580/MD | 06/12/2024 | 180 | DEBASISH DOGRA | 134.93 | 0 | 0 | 0
1756 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Construction of Boundary wall, Soil investigation, Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 200 cum and staging height 20 mtr & Accommodate FHTC (800 Nos.) under JJM with allied work for Pachra & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | 2219/MD | 19/07/2024 | 180 | ASHIM KUMAR DEY | 126.93 | 0 | 0 | 0
1757 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 100 (Intze type Raft Foundation) & Accommodate FHTC (473 Nos.) including 2 years O&M under JJM with allied work for Chandipur (Zone-II) & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | 3160/MD | 04/10/2024 | 180 | ASHIM KUMAR DEY | 191.82 | 0 | 0 | 0
1758 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising main, Pump House, Boundary wall & Accommodate FHTC (500 Nos.) including 2 years O&M under JJM with allied work for Sholkamari & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | 2870/MD | 10/08/2023 | 897 | MIDNAPUR PIPE CONCERN | 213.41 | 0 | 0 | 60
1759 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House, Boundary wall & Accommodate FHTC (576 Nos.) including 2 years O&M under JJM with allied work for Mahadevchak & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | 2871/MD | 10/08/2023 | 884 | MIDNAPUR PIPE CONCERN | 131.19 | 0 | 0 | 35
1760 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House & Accommodate FHTC (304 Nos.) under JJM with allied work for Khangardihi & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | 3099/MD | 25/08/2023 | 705 | PULLOCK KUMAR GHOSH | 83.11 | 0 | 0 | 25
1761 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Construction of 300 Cum OHR (Intze type Raft Foundation) & Accommodate FHTC (2,400 Nos.) including Two years O&M under JJM with allied work for Pathra & adjoining Mouza W/S Scheme in Midnapur Sadar Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | 3239/MD | 11/09/2023 | 530 | M/S. CARE | 492.38 | 0 | 0 | 10
1762 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House, Boundary wall, & Accommodate FHTC (659 Nos.) including 2 years O&M under JJM with allied work for Pachra & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | 3100/MD | 25/08/2023 | 714 | M/S. D.K.H.CONSTRUCTION | 280.51 | 0 | 0 | 60
1763 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Laying rising main, Pump House & Accommodate FHTC (1,212 Nos.) including 2 yrs. O & M under JJM with allied work for Gurehara & adjoining Mouza W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | 5258/MD | 21/11/2023 | 857 | SUNIL DULE | 119.03 | 0 | 0 | 60
1764 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Laying rising main, Pump House & Accommodate FHTC (1,039 Nos.) including 2 yrs. O & M under JJM with allied work for Garhberia & adjoining Mouza W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | 5257/MD | 21/11/2023 | 421 | CREATION CONSTRUCTION | 94.26 | 0 | 0 | 40
1765 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Laying rising main, Pump House & Accommodate FHTC (1,164 Nos.) including 2 yrs. O & M under JJM with allied work for Banpura & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | 141/MD | 18/01/2024 | 753 | MIDNAPUR PIPE CONCERN | 96.72 | 0 | 0 | 10
1766 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipeline, Rising main, Pump House, Boundary Wall & Accommodate FHTC (546 Nos.) including 2 yrs. O & M under JJM with allied work for Shiromani & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | 140/MD | 18/01/2024 | 752 | MIDNAPUR PIPE CONCERN | 186.66 | 0 | 0 | 20
1767 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Laying rising main, Pump House & Accommodate FHTC (1,257 Nos.) including 2 yrs. O & M under JJM with allied work for Pathaisol & adjoining Mouza W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | 218/MD | 31/01/2024 | 587 | ASIS KUMAR SARANGI | 104.62 | 0 | 0 | 95
1768 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Construction of Boundary wall, Soil investigation, Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 cum and staging height 20 mtr. & Accommodate FHTC (1,000 Nos.) including 2 years O&M under JJM with allied work for Khangardihi & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | 3044/MD | 25/09/2024 | 540 | WATER LINK | 139.11 | 0 | 0 | 0
1769 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Laying additional distribution pipeline, Land development at 1st Tube well cum Head work site & Accommodate FHTC (1,797 Nos.) including all allied works for Hatihalka PWSS within Midnapore Sadar block under Midnapore Division, PHE Dte. [Mid-Term Plan under Master Plan] | 3403/MD | 25/11/2024 | 450 | UTTAM KUMAR DAS | 84.05 | 0 | 0 | 0
1770 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Construction of Boundary wall, Soil investigation, Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 250 cum and staging height 20 mtr. & Accommodate FHTC (1,423 Nos.) under JJM with allied work for Sholkamari & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | 2146/MD | 11/07/2024 | 540 | DIPAK KUMAR BAKLY | 175.22 | 0 | 0 | 5
1771 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Construction and commissioning of RCC Over Head Reservoir (Intez type with solid raft) of capacity 200 cum and staging height 20 mtr., Boundary wall & Accommodate FHTC (500 Nos.) under JJM with allied work for Shiromani & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | 2052/MD | 02/07/2024 | 360 | ADITYA MALLIK | 108.95 | 0 | 0 | 15
1772 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 cum and staging height 20 mtr. as per approved drawing (No:- PC-I/OHR /10/15/2012) with allied works for Barua & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-C] | 3579/MD | 06/12/2024 | 360 | GOUTAM PARIA | 71.28 | 0 | 0 | 0
1773 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Accommodate FHTC (801 Nos.) including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM for Banpura PWSS within Midnapore Sadar Dev. Block under Midnapore Division in Paschim Medinipur district. [Mid-Term Plan under Master Plan] | 1067/MD | 02/05/2025 | 298 | MIDNAPUR PIPE CONCERN | 30.79 | 0 | 0 | 0
1774 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Construction and commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 250 CuM & staging height 20 mtr. as per approved drawing (No:- PC-I/OHR/10/2012) with allied works for Banpura & its adjoining mouzas water supply scheme within Midnapore Sadar Block including supply of all labour & materials under Midnapore Division, PHE Dte. (Mid- Term Plan under Master Plan) | 1777/MD | 08/09/2025 | 180 | M/S RAJKUMAR KHAN | 81.1 | 0 | 0 | 0
1775 | PASCHIM MEDINIPUR | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. , SM/18486 | Retrofitting | Sinking of Tube well, Rising Main & Accommodate FHTC (618 Nos.) including 2 years O&M under JJM with allied work for Hatihalka & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | 3905/MD | 27/09/2023 | 766 | DIPAK KUMAR BAKLY | 61.27 | 0 | 0 | 60
1776 | PASCHIM MEDINIPUR | Midnapore Division | Jankapur Piped Water Supply Scheme. , SM/18786 | New | Material Requisition To Resource Division | 3987/MD | 06/10/2023 | 0 | Resource Division | 37.09 | 0 | 0 | 0
1777 | PASCHIM MEDINIPUR | Midnapore Division | Jankapur Piped Water Supply Scheme. , SM/18786 | New | Material Requisition To Resource Division | 3464/MD | 25/11/2024 | 0 | Resource Division | 7.77 | 0 | 0 | 0
1778 | PASCHIM MEDINIPUR | Midnapore Mechanical | Jankapur Piped Water Supply Scheme. , SM/18786 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of JANKAPUR PWSS. REF CONSUMER ID-204298988, APPLICATION NO-2004720671, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | BP-2024-25-180 | 20/05/2024 | 0 | WBSEDCL | 2.99 | 0 | 0 | 0
1779 | PASCHIM MEDINIPUR | Midnapore Mechanical | Jankapur Piped Water Supply Scheme. , SM/18786 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of JANKAPUR PWSS. REF CONSUMER ID-204298990, APPLICATION NO-2004720643, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | BP-2024-25-181 | 20/05/2024 | 0 | WBSEDCL | 3.52 | 0 | 0 | 0
1780 | PASCHIM MEDINIPUR | Central Drilling | Jankapur Piped Water Supply Scheme. , SM/18786 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1781 | PASCHIM MEDINIPUR | Midnapore Division | Jankapur Piped Water Supply Scheme. , SM/18786 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 (Intze type with Pile) & Accommodate FHTC (2,381 Nos.) including Two years O&M under JJM with allied work for Jankapur & its adjoining mouzas W/S Scheme in Datan-II Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5067/MD | 26/10/2023 | 900 | DIPAK KUMAR BAKLY | 624.05 | 0 | 0 | 10
1782 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Supapursuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17811 | Solarisation | Solarization of grid connected pumping installation Supapursuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 971/W/MMD | 29/03/2023 | 180 | RSA ENTERPRISE | 6.25 | 0 | 0 | 65
1783 | PASCHIM MEDINIPUR | Midnapore Division | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/18535 | New | Material Requisition To Resource Division | 79/MD | 09/01/2023 | 0 | Resource Division | 16.2 | 0 | 0 | 0
1784 | PASCHIM MEDINIPUR | Midnapore Division | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/18535 | New | Material Requisition To Resource Division | 3386/MD | 25/11/2024 | 0 | Resource Division | 20.73 | 0 | 0 | 0
1785 | PASCHIM MEDINIPUR | Midnapore Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/18535 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF GHOSHPUR PWSS. REF CONSUMER ID-204294953, APPLICATION NO-2004713752, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | C072449541730 | 02/08/2024 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
1786 | PASCHIM MEDINIPUR | Midnapore Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/18535 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of GHOSHPUR PWSS. REF CONSUMER ID-204218492, APPLICATION NO-2004603166, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-713 | 20/02/2024 | 0 | WBSEDCL | 4.85 | 0 | 0 | 0
1787 | PASCHIM MEDINIPUR | Midnapore Division | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/18535 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,366 nos.) under JJM with allied work for Ghoshpur PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 3842/MD | 21/09/2023 | 905 | M/S. A.R. ENTERPRISE. | 917.44 | 0 | 0 | 35
1788 | PASCHIM MEDINIPUR | Midnapore Division | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/18535 | New | Laying of rising main & interconnection for Ghoshpur & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 650 Mtr.) | 60/MD | 07/01/2025 | 45 | A-PLUS | 6.5 | 0 | 0 | 0
1789 | PASCHIM MEDINIPUR | Midnapore Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/18535 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | 842/MMSD-I | 11/06/2025 | 243 | M/S BIKASH DE | 3.66 | 0 | 0 | 0
1790 | PASCHIM MEDINIPUR | Midnapore Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/18535 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GHOSHPUR PIPED WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | 1686/W/MMD | 04/08/2023 | 678 | SHOVAN KUMAR DAS | 27.39 | 0 | 0 | 20
1791 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Beluria PWSS in Pingla Block in the District of Paschim Medinipur. | 376/MD | 25/02/2021 | 30 | M/S. A.R. ENTERPRISE. | 21.79 | 0 | 0 | 0
1792 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Barsahara PWSS in Sabang Block in the District of Paschim Medinipur. | 374/MD | 25/02/2021 | 15 | MAMPI ENTERPRISE | 4.32 | 0 | 0 | 0
1793 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Adasimla PWSS in Sabang Block in the District of Paschim Medinipur. | 686/MD | 03/05/2021 | 45 | SAI TUBE CO. | 34.29 | 0 | 0 | 0
1794 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhikni Nischintapur W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | BP-2022-23-33 | 29/04/2022 | 0 | SAI TUBE CO. | 12.05 | 0 | 0 | 0
1795 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Maligram W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | BP-2021-22-475 | 16/03/2022 | 0 | HARIPADA PATTANAYAK | 14.63 | 0 | 0 | 0
1796 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chhotokhelna W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | BP-2021-22-524 | 25/03/2022 | 0 | ASHIM KUMAR DEY | 15.66 | 0 | 0 | 0
1797 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Maligram W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1450/MD | 26/11/2020 | 180 | HARIPADA PATTANAYAK | 96.05 | 0 | 0 | 96
1798 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Construction of Boundary wall & land development with approach road for 2nd T.W. Site of Maligram & its adjoining mouzas W/S Scheme at Pingla Block within Kharagpur Sub-Division under Midnapore Division, PHE Dte. (Total Length of the Boundary wall = 56.00 Mtr. & C/C distance of 250 X 250 mm size Column = 3.00 Mtr. & Height =2.45 Mtr. above GL) | 261/MD | 12/02/2021 | 45 | SAKTI PADA BERA | 5.05 | 0 | 0 | 0
1799 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Bhikni Nischintapur PWSS, Block: - Sabang, in the District of Paschim Medinipur. | 685/MD | 03/05/2021 | 25 | SAI TUBE CO. | 45.46 | 0 | 0 | 30
1800 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Khasbazar PWSS in Debra Block in the District of Paschim Medinipur. | 420/MD | 26/02/2021 | 45 | SUBRATA DAS | 31.59 | 0 | 0 | 67
1801 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Restoration of laying of distribution pipe line damage due to construction of road by PMGSY in different mouzas required for covering FHTC works of Maligram & its adjoining mouza Water Supply Scheme within Pingla Block under Midnapore Division, P.H.E. Dte. | 30/MD | 07/01/2022 | 30 | HARIPADA PATTANAYAK | 18.99 | 0 | 0 | 95
1802 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chhotokhelna W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1431/MD | 26/11/2020 | 180 | ASHIM KUMAR DEY | 93.67 | 0 | 0 | 80
1803 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Chhotokhelna PWSS, Block :- Pingla in the District of Paschim Medinipur. | 339/MD | 24/02/2021 | 40 | ASHIM KUMAR DEY | 64.56 | 0 | 0 | 15
1804 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Material Requisition To Resource Division | 3412/MD | 25/11/2024 | 0 | Resource Division | 82.38 | 0 | 0 | 0
1805 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Panpara PWSS in Sabang Block in the District of Paschim Medinipur. | 338/MD | 24/02/2021 | 1588 | BANERJEE CONSTRUCTION | 11.02 | 0 | 0 | 5
1806 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Bural (Zone-I) PWSS, Block :- Sabang in the District of Paschim Medinipur. | 308/MD | 22/02/2021 | 1859 | ASHOK BANERJEE | 93.36 | 0 | 0 | 70
1807 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Bural (Zone-II) PWSS, Block :- Sabang in the District of Paschim Medinipur. | 307/MD | 22/02/2021 | 1772 | ASHOK BANERJEE | 53.72 | 0 | 0 | 45
1808 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Ragpur PWSS in Pingla Block in the District of Paschim Medinipur. | 378/MD | 25/02/2021 | 1406 | GOBINDA MAITY | 9.25 | 0 | 0 | 100
1809 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Chandkuri (Zone-I) PWSS in Sabang Block in the District of Paschim Medinipur. | 373/MD | 25/02/2021 | 30 | DULAL CHANDRA DAS | 16.68 | 0 | 0 | 75
1810 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Sartla PWSS in Sabang Block in the District of Paschim Medinipur. | 375/MD | 25/02/2021 | 30 | GOBINDA MAITY | 26.59 | 0 | 0 | 100
1811 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Maligram PWSS, Block: - Pingla, in the District of Paschim Medinipur. | 684/MD | 03/05/2021 | 1423 | UTTAM KUMAR DAS | 94.86 | 0 | 0 | 76
1812 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Narayanbar PWSS, Block: - Sabang, in the District of Paschim Medinipur. | 266/MD | 12/02/2021 | 25 | BANERJEE CONSTRUCTION | 49.06 | 0 | 0 | 5
1813 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Gobardhanpur PWSS in Pingla Block in the District of Paschim Medinipur. | 313/MD | 22/02/2021 | 1400 | DIPAK KUMAR BAKLY | 22.23 | 0 | 0 | 70
1814 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. , SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Karkai PWSS in Pingla Block in the District of Paschim Medinipur. | 377/MD | 25/02/2021 | 1404 | GOBINDA MAITY | 22.16 | 0 | 0 | 100
1815 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. , SM/06905 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Mohanpur W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1445/MD | 26/11/2020 | 180 | M/S. D.K.H.CONSTRUCTION | 67.23 | 64.32 | 63.34 | 0
1816 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. , SM/06905 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Mohanpur W/S Scheme District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | M/S. D.K.H.CONSTRUCTION | 30 | 0 | 0 | 0
1817 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. , SM/06905 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Mohanpur W/S Scheme. |  | 05/02/2021 | 0 | PULLOCK KUMAR GHOSH | 5 | 0 | 0 | 0
1818 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. , SM/06905 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443459 | 26/03/2021 | 0 | MANABENDRA DAS | 0.16 | 0 | 0 | 0
1819 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. , SM/06905 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443459 | 26/03/2021 | 0 | SUBRATA CHAKRABORTY | 0.17 | 0 | 0 | 0
1820 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. , SM/06905 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443459 | 26/03/2021 | 0 | RINTU SAMANTA | 0.17 | 0 | 0 | 0
1821 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. , SM/06905 | Retrofitting | FHTC data entry. | 844363 | 18/01/2022 | 0 | SANDIP MANNA | 0.12 | 0 | 0 | 0
1822 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. , SM/06905 | Retrofitting | FHTC data entry. | 844363 | 18/01/2022 | 0 | TANMOY BERA | 0.21 | 0 | 0 | 0
1823 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. , SM/06905 | Retrofitting | Laying of Rising Main including interconnection for Augmentation of Mohanpur and its adjoining mouzas Water Supply Scheme within Mohanpur Block under Kharagpur Sub Division of Midnapore Division, P.H.E. Dte. | 5568/MD | 26/12/2023 | 30 | GOBINDA MAITY | 6.55 | 0 | 0 | 0
1824 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chaupanya Piped Water Supply Scheme. , SM/06913 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chaupanya W/S Scheme, Block: - Kharagpur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | M/S. A.R. ENTERPRISE. | 25 | 0 | 0 | 0
1825 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chaupanya Piped Water Supply Scheme. , SM/06913 | Retrofitting | Material Requisition To Resource Division | 3410/MD | 25/11/2024 | 0 | Resource Division | 12.21 | 0 | 0 | 0
1826 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chaupanya Piped Water Supply Scheme. , SM/06913 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chaupanya w/s Scheme. | 84434 | 03/05/2024 | 0 | M/S. A.R. ENTERPRISE | 33.39 | 0 | 0 | 0
1827 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chaupanya Piped Water Supply Scheme. , SM/06913 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chaupanya W/S Scheme, Block: - Kharagpur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1451/MD | 26/11/2020 | 1823 | M/S. A.R. ENTERPRISE. | 94.15 | 28.6 | 30.38 | 100
1828 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chaupanya Piped Water Supply Scheme. , SM/06913 | Retrofitting | Restoration of pipe line From Ramnagar to Mominpur SSK for Covering FHTC Work & Development of Land at H.W Site of Chaupanya PWSS within Kharagpur-II Block under Kharagpur Sub Division within Midnapore Division, P.H.E. Dte. | 2246/MD | 28/12/2021 | 21 | MAMPI ENTERPRISE | 9.04 | 0 | 0 | 100
1829 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Gobardhanpur Piped Water Supply Scheme. , SM/06916 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Gobardhanpur W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1432/MD | 26/11/2020 | 180 | DIPAK KUMAR BAKLY | 88.12 | 55.92 | 63.46 | 0
1830 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Malara PWSS , SM/08221 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Malara W/S Scheme, Block: - Garhbeta-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 383/MD | 25/02/2021 | 30 | PULLOCK KUMAR GHOSH | 22.4 | 0 | 0 | 0
1831 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Dhaneswarpur PWSS to accommodate FHTC under JJM under Dantan-II block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09722 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dhaneswarpur, Block - Dantan-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | BP-2021-22-456 | 11/03/2022 | 0 | SIRCON ENGINEERING SERVICES | 2.54 | 0 | 0 | 0
1832 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Dhaneswarpur PWSS to accommodate FHTC under JJM under Dantan-II block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09722 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dhaneswarpur, Block - Dantan-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | 296/MD | 19/02/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.15 | 0 | 0 | 0
1833 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Dhaneswarpur PWSS to accommodate FHTC under JJM under Dantan-II block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09722 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Dhaneswarpur PWSS to accommodate FHTC under JJM under Dantan-II block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 2170/MD | 17/12/2021 | 35 | UTTAM KUMAR DAS | 89.26 | 0 | 0 | 0
1834 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Keot Khalisha PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09723 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Keot Khalisha PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 28/MD | 07/01/2022 | 21 | SUNIL DULE | 48.62 | 0 | 0 | 0
1835 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Keot Khalisha PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09723 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Keot Khalisha, Block - Mohanpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | BP-2021-22-416 | 24/02/2022 | 0 | RISHAN ENGINEERING CONSULTANCY | 1.94 | 0 | 0 | 0
1836 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Keot Khalisha PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09723 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Keot Khalisha, Block - Mohanpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | 298/MD | 19/02/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 1.94 | 0 | 0 | 0
1837 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Sonakania PWSS to accommodate FHTC under JJM under Dantan-I block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09725 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Sonakania PWSS to accommodate FHTC under JJM under Dantan-I block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 2003/MD | 01/12/2021 | 15 | M/S. EL-CON | 36.71 | 0 | 0 | 0
1838 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Sonakania PWSS to accommodate FHTC under JJM under Dantan-I block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09725 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Sonakania, Block - Dantan-I) to be Retrofitting under Midnapore Division P.H.E. Dte. | BP-2021-22-417 | 24/02/2022 | 0 | SIRCON ENGINEERING SERVICES | 1.69 | 0 | 0 | 0
1839 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Sonakania PWSS to accommodate FHTC under JJM under Dantan-I block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09725 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Sonakania, Block - Dantan-I) to be Retrofitting under Midnapore Division P.H.E. Dte. | 52/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.3 | 0 | 0 | 0
1840 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. , SM/09726 | Retrofitting | Supply of C.I.D.F Sluice Valve & C.I. Jeffy coupler for distribution and Rising main pipe line for Retrofitting of JOTGHANASHYAM water Supply Scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte. | 402/AE/GSD | 11/07/2022 | 7 | GOBINDA MAITY | 4.5 | 0 | 0 | 0
1841 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. , SM/09726 | Retrofitting | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Jot Ghanashyam (Block-Daspur-II) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1653/MD | 23/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.38 | 0 | 0 | 0
1842 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. , SM/09726 | Retrofitting | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Amlagora, Jot Ghanashyam & Sonakhali in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-470 | 11/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.19 | 0 | 0 | 0
1843 | PASCHIM MEDINIPUR | Midnapore Mechanical | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. , SM/09726 | Retrofitting | Laying of 25sq.mm armoured cable and electromechanical equipment at pump house no II of Jotghanashyam water supply scheme under Panschim Medinipur District under Midnapore Mechanical Division, P.H.E. Dte. | 196/MMSD-I | 28/02/2023 | 7 | DIPALI CONSTRUCTION | 4.42 | 0 | 0 | 0
1844 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. , SM/09726 | Retrofitting | Retrofitting of Jot Ghanashyam Piped Water Supply Scheme to accommodate FHTC under Jal Swapna including Sinking of 1 nos. Tube Well and other allied Works in Daspur-II Block of Paschim Medinipur District under Midnapore Division, PHE Dte. | 2015/MD | 03/12/2021 | 90 | GOBINDA MAITY | 297.42 | 0 | 0 | 100
1845 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. , SM/09726 | Retrofitting | Continuation Work Order for the work of "Retrofitting of Jot Ghanashyam Piped Water Supply Scheme to accommodate FHTC under Jal Swapna including Sinking of 1 nos. Tube Well and other allied Works in Daspur-II Block of Paschim Medinipur District under Midnapore Division, PHE Dte." | 1242/MD | 20/06/2022 | 1239 | GOBINDA MAITY | 90.19 | 0 | 0 | 100
1846 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/09455 | Augmentation | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC. Block - Dantan-I. District - Paschim Medinipur. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 2.64 | 0 | 0 | 0
1847 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/09455 | Augmentation | Material Requisition To Resource Division | 2276/MD | 31/12/2021 | 0 | Resource Division | 2.64 | 0 | 0 | 0
1848 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/09455 | Augmentation | Material Requisition To Resource Division | 1369/MD | 02/05/2023 | 0 | Resource Division | 12.34 | 0 | 0 | 0
1849 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/09455 | Augmentation | Electric quatation for New service connection at Sijua T.W.No-II (Ref Id-203987545) | BP-2023-24-40 | 15/05/2023 | 0 | WBSEDCL | 4.17 | 0 | 0 | 0
1850 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/09455 | Augmentation | Laying balance quantity of pipe line & accommodate FHTC (21 Nos.) with allied works for Augmentation of Sarta-Sijua W/S Scheme under Dantan-I block within Midnapore Division, PHE Dte. | 2849/MD | 09/09/2024 | 45 | PROVAT KUMAR DE | 11.96 | 0 | 0 | 85
1851 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/09455 | Augmentation | Laying of (Left out & Damaged) Distribution pipe line including Supply of Valves for Augmentation Sarta-Sijua Pipe Water Supply Scheme in Dantan-I Block under Khargapur Sub-Division within Midnapore Division, PHE Dte. | 3906/MD | 27/09/2023 | 45 | PROVAT KUMAR DE | 10.22 | 0 | 0 | 95
1852 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/09455 | Augmentation | Laying Rising Main system including inter-connection and By-Pass arrangement for Augmentation Sarta-Sijua PWSS in Dantan-I Block under Khargapur Sub-Division of Midnapur Division PHE Dte. | 4042/MD | 11/10/2023 | 30 | PROVAT KUMAR DE | 3.27 | 0 | 0 | 95
1853 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/09455 | Augmentation | Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 100 Cum and staging height 20.00 mtr. with allied work including Sinking of 250mm x 150mm x 190m deep tube well for Augmentation of Sarta-Sijua W/S Scheme in Datan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 1958/MD | 20/09/2022 | 180 | PROVAT KUMAR DE | 111.93 | 0 | 0 | 99
1854 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/09455 | Augmentation | Cleaning the Chokage of pipe in the existing line at Sarta-Sijua PWSS under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | 2246/AE/HQ/MD | 22/07/2024 | 10 | PULLOCK KUMAR GHOSH | 0.9 | 0 | 0 | 100
1855 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/09455 | Augmentation | Repairing of 2nd Pump House & Boundary wall for Sarta-Sijua PWSS within Dantan-I block under Midnapore Division, PHE Dte. | 570/AE/HQ/MD | 28/02/2025 | 60 | PROVAT KUMAR DE | 3.65 | 0 | 0 | 100
1856 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/09455 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | 2294/W/MMD | 29/12/2022 | 520 | P.K.ENGINEERING | 11.44 | 0 | 0 | 20
1857 | PASCHIM MEDINIPUR | Midnapore Division | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Sinking of 2 (Two) Nos. 200 X 100 mm dia. X 180 Mtr. depth Rig bored tube wells at Head Works cum 1st Tube well & 2nd tube well sites of Gobindanagar W/S Scheme within Daspur-I Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | 1312/MD | 30/06/2022 | 15 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12.8 | 0 | 0 | 100
1858 | PASCHIM MEDINIPUR | Midnapore Division | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Supply of C.I.D.F Sluice Valve & C.I. Jeffy coupler for distribution and Rising main pipe line for GOBINDANAGAR water Supply Scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte. | 401/AE/GSD | 11/07/2022 | 7 | SUBHASIS DOLAI | 3.22 | 0 | 0 | 0
1859 | PASCHIM MEDINIPUR | Midnapore Division | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Exigency basis laying casing pipe under Bitumineous pucca road crosssing near Goura Bridge,Sarala Ciname of Khakurda to Ghatal PWD Road of Gobindanagar W/S Scheme within Ghatal Sub-Division, PHE.Dte. | 165/AE/GSD | 01/04/2022 | 2 | SUBHASIS DOLAI | 3.64 | 0 | 0 | 0
1860 | PASCHIM MEDINIPUR | Midnapore Division | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Exigency basis laying casing pipe under Bitumineous pucca road crosssing Near Anapurna Nursing Home,Panchberia Bus Stop, Nirmal Paludhi house of Khakurda to Ghatal PWD Road of Gobindanagar W/S Scheme within Ghatal Sub-Division, PHE.Dte. | 166/AE/GSD | 01/04/2022 | 2 | SUBHASIS DOLAI | 3.64 | 0 | 0 | 0
1861 | PASCHIM MEDINIPUR | Central Drilling | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (200 MM X 100 MM) WITH IN gHATAL BLOCK (PASCHIM MEDINIPUR) UNDER CENTRAL DRILLING DIVISION, PHE DTE. | 387/CDD | 23/08/2021 | 15 | MENAKA ENTERPRISE | 8.73 | 0 | 0 | 0
1862 | PASCHIM MEDINIPUR | Midnapore Division | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Construction of RCC Pile for Over Head Reservoir (in place of Intze type with solid raft) of capacity 300 CuM and Staging height 20 mtr. as per approved drawing (No:- PC-I/OHR/07/2012) with allied works for Gobindanagar & its adjoining Mouzas W/S Scheme within Daspur-I block including supply of all labour & materials under Midnapore Division, PHE Dte. | 2270/MD | 09/11/2022 | 30 | DIPAK KUMAR DOLAI | 36.58 | 0 | 0 | 100
1863 | PASCHIM MEDINIPUR | Midnapore Division | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Continuation Work Order for the work of Laying additional distribution pipe line for Gobindanagar Water Supply Scheme under Daspur-I block within Midnapore Division PHE Dte. | 219/MD | 16/01/2023 | 30 | DIPAK KUMAR DOLAI | 13.3 | 0 | 0 | 100
1864 | PASCHIM MEDINIPUR | Midnapore Division | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Material Requisition To Resource Division | 378/MD | 03/02/2023 | 0 | Resource Division | 25.32 | 0 | 0 | 0
1865 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Electric quotation for Gobindanagar PWSS Tube Well-II at under Daspur Customer Care Centre | BP-2022-23-83 | 27/12/2022 | 0 | WBSEDCL | 0.46 | 0 | 0 | 0
1866 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Electric quotation for Gobindanagar PWSS Tube Well-III (Ref. ID-203924590) | BP-2022-23-130 | 14/03/2023 | 0 | WBSEDCL | 0.47 | 0 | 0 | 0
1867 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Electric quotation for Gobindanagar PWSS T/W-I at under Daspur CCC | BP-2022-23-82 | 27/12/2022 | 0 | WBSEDCL | 0.46 | 0 | 0 | 0
1868 | PASCHIM MEDINIPUR | Midnapore Division | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Flank restoration of Panskura Ghatal Road from 15.00 kmp to 17.00 kmp under Midnapore Highway Division in the District of Paschim Medinipur. | BP-2023-24-80 | 08/05/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 20 | 0 | 0 | 0
1869 | PASCHIM MEDINIPUR | Midnapore Division | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Construction of RCC Pile for Over Head Reservoir (in place of Intze type with solid raft) of capacity 300 CuM and Staging height 20 mtr. as per approved drawing (No:- PC-I/OHR/07/2012) with allied works for Gobindanagar & its adjoining Mouzas W/S Scheme within Daspur-I block including supply of all labour & materials under Midnapore Division, PHE Dte. | BP-2022-23-665 | 04/03/2023 | 0 | DIPAK KUMAR DOLAI | 24 | 0 | 0 | 0
1870 | PASCHIM MEDINIPUR | Midnapore Division | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Laying rising main, Pump houses (5.40 X 3.60 Mtr.) & (3.60 X 3.00 Mtr.), Boundary wall, Approach road for Gobindanagar Piped Water Supply Scheme within Daspur-I Block under Ghatal Sub-Division of Midnapore Division PHE Dte. | 1964/MD | 20/09/2022 | 60 | DEBASISH DOGRA | 34.31 | 0 | 0 | 65
1871 | PASCHIM MEDINIPUR | Midnapore Division | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Continuation Work Order for the work of Laying additional pipeline for Gobindanagar W/S Scheme in Daspur-I block within Ghatal Sub-Division under Midnapore Division PHE Dte. | 962/MD | 06/04/2023 | 60 | DIPAK KUMAR DOLAI | 52.61 | 0 | 0 | 95
1872 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Supply and installation of chlorination and fenching and civil works for protection of pumping machinaries at Tube Well no III of Gobindanagar Water Supply Scheme [ Block- Daspur-I] under MMD, PHE Dte., Dist.- Paschim Medinipur. | 318/MMSD-I | 04/03/2024 | 10 | S.S.GHORAI | 1.72 | 0 | 0 | 0
1873 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gobindanagar(Add. Tube Well No.-III) Piped Water Supply Scheme under JJM Program under MMD PHE Dte. | 778/W/MMD | 24/03/2023 | 180 | S.S.GHORAI | 8.17 | 0 | 0 | 100
1874 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Replacement and upgradation work of Voltage Stabilizer for Tube well No. 1 and 2 of Gobindanagar Water Supply Scheme Block Daspur I under MMD, PHE Dte., Dist. Paschim Medinipur. | 1227/MMSD-I | 03/10/2023 | 30 | BALAJI CONSTRUCTION | 5.17 | 0 | 0 | 100
1875 | PASCHIM MEDINIPUR | Midnapore Division | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Laying distribution pipe line, soil test, FHTC & construction of R.C.C. Over Head Reservoir of capacity 300 Cum and staging height 20.00 mtr. with allied work for Gobindanagar W/S Scheme in Daspur-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 838/MD | 02/05/2022 | 1425 | DIPAK KUMAR DOLAI | 238.12 | 0 | 0 | 81
1876 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme , SM/10066 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gobindanagar Piped Water Supply Scheme under JJM Program under MMD PHE Dte. | 2386/W/MMD | 31/12/2022 | 852 | BALAJI CONSTRUCTION | 22.89 | 0 | 0 | 100
1877 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10779 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Narayanbar PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1674/MD | 29/09/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 2.11 | 0 | 0 | 100
1878 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10779 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0 | 0 | 25
1879 | PASCHIM MEDINIPUR | Central Drilling | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10779 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250mm x 150mm x 200mtrs. Depth) by utilising Departmental Machineries for Narayanbar W/S Scheme ,TW-II, Block- Sabang under Paschim Midnapore District, CDD, PHE Dte. | 1725/CDD | 29/12/2022 | 30 | MENAKA ENTERPRISE | 11.86 | 0 | 0 | 100
1880 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10779 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0 | 0 | 100
1881 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10779 | Augmentation | QUOTATION FOR NEW POWER CONNECTION OF NARAYANBARH [AUG.] WATER SUPPLY ASCHEME [ APPLICATION --2004480446, REFERENCE ID ----204122723, SABONG CCC, QUOTATION NO ---2004480446/QUOT/03 DATED 26/10/2023, SCHEME NAME --- NARAYANBARH AUG. , SCHEME CODE ---SM/10779 , MB NO--3580 ] | BP-2023-24-342 | 10/11/2023 | 0 | WBSEDCL | 7.58 | 0 | 0 | 0
1882 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10779 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 2306/W/MMD | 29/12/2022 | 180 | DEBKUMAR BASU | 10.79 | 0 | 0 | 70
1883 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10779 | Augmentation | Laying pipeline at command area of Pump House No. 3 of Narayanbar PWSS to accommodate FHTC under JJM at Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. | 124/MD | 10/01/2023 | 21 | A-PLUS | 10.56 | 0 | 0 | 100
1884 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10779 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | 1728/A/MD | 23/08/2022 | 1088 | BANERJEE CONSTRUCTION | 36.87 | 0 | 0 | 25
1885 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Bashuli) | 515/AE/GSD | 07/09/2022 | 20 | PRITI ENTERPRISE | 4.33 | 0 | 0 | 100
1886 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.(Srinagar) | 521/AE/GSD | 07/09/2022 | 20 | A.R. CONSTRUCTION | 4.33 | 0 | 0 | 0
1887 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.( Srinagar Madhya para) | 522/AE/GSD | 07/09/2022 | 20 | PULLOCK KUMAR GHOSH | 4.33 | 0 | 0 | 100
1888 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. ( Kochgeria) | 516/AE/GSD | 07/09/2022 | 20 | PULLOCK KUMAR GHOSH | 4.33 | 0 | 0 | 100
1889 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Rejna) | 518/AE/GSD | 07/09/2022 | 20 | INDRAJIT ROY | 4.33 | 0 | 0 | 100
1890 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Jara Uttar Para) | 513/AE/GSD | 07/09/2022 | 20 | TARUN MAHATA | 4.33 | 0 | 0 | 0
1891 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.(Narayanpur) | 517/AE/GSD | 07/09/2022 | 20 | BUNBA CONSTRUCTION | 4.33 | 0 | 0 | 100
1892 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accomodate FHTC under JJM ar Srinagar water supply scheme Block-Candrakona-I and II District Paschim Medinipur within Midnapore Division P.H.E.Dte. (Rejna) | 336/AE/GSD | 16/05/2023 | 20 | INDRAJIT ROY | 1.45 | 0 | 0 | 0
1893 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.( Maide) | 524/AE/GSD | 07/09/2022 | 20 | M/S. ZAMAN ENTERPRISE | 3.31 | 0 | 0 | 0
1894 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Jara Purba Para.) | 511/AE/GSD | 07/09/2022 | 20 | M/S JITEN BANARJEE | 4.33 | 0 | 0 | 100
1895 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Jara Paschim Para) | 512/AE/GSD | 07/09/2022 | 20 | M/S JITEN BANARJEE | 4.33 | 0 | 0 | 20
1896 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.(Jara Dakshin Para) | 514/AE/GSD | 07/09/2022 | 20 | KAMAKHYA ENTERPRISE | 4.33 | 0 | 0 | 100
1897 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. ( Sanpur) | 519/AE/GSD | 07/09/2022 | 20 | SURAJIT GHOSH | 4.33 | 0 | 0 | 100
1898 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Srinagar Purba Para) | 520/AE/GSD | 07/09/2022 | 20 | MAHAPRABHU ENTERPRISE | 4.33 | 0 | 0 | 100
1899 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.( Mahabala) | 523/AE/GSD | 07/09/2022 | 20 | M/S. ZAMAN ENTERPRISE | 4.33 | 0 | 0 | 100
1900 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Rejna) | 337/AE/GSD | 16/05/2023 | 20 | INDRAJIT ROY | 1.45 | 0 | 0 | 100
1901 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. ( Kochgeri | BP-2022-23-608 | 01/09/2023 | 0 | PULLOCK KUMAR GHOSH | 4.25 | 0 | 0 | 0
1902 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. ( Kochgeria) | 107/AE.GSD | 13/02/2023 | 20 | PULLOCK KUMAR GHOSH | 0.85 | 0 | 0 | 100
1903 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.( Srinagar Madhya para) | 109/AE/GSD | 13/02/2023 | 20 | PULLOCK KUMAR GHOSH | 0.4 | 0 | 0 | 100
1904 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur , SM/12117 | Retrofitting | Laying additional pipelines regarding Balance work of Retrofitting to accommodate FHTC under JJM at SRINAGAR water supply scheme Block-Chandrakona-I & 2 District- Paschim Medinipur within Midnapore Division, PHE.Dte. (Muide, Jara Purba & Mahabala) | 1494/AE/GSD | 24/09/2024 | 15 | M/S JITEN BANARJEE | 3.48 | 0 | 0 | 100
1905 | PASCHIM MEDINIPUR | Midnapore Division | RUPARGHAGRA AND ADJOINING MOUJAS PWSS , SM/13108 | New | Material Requisition To Resource Division | 1243/MD | 27/04/2023 | 0 | Resource Division | 19.22 | 0 | 0 | 0
1906 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | RUPARGHAGRA AND ADJOINING MOUJAS PWSS , SM/13108 | New | Payment for new service connection charges Ruparghagra T/W-2 | 65/JMD | 29/04/2024 | 0 | WBSEDCL | 7.43 | 0 | 0 | 0
1907 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | RUPARGHAGRA AND ADJOINING MOUJAS PWSS , SM/13108 | New | Payment for new service connection charges Ruparghagra T/W-1 | 64/JMD | 29/04/2024 | 0 | WBSEDCL | 8.29 | 0 | 0 | 0
1908 | PASCHIM MEDINIPUR | Central Drilling | RUPARGHAGRA AND ADJOINING MOUJAS PWSS , SM/13108 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1909 | PASCHIM MEDINIPUR | Midnapore Division | KUNARPUR AND ADJOINING MOUJAS PWSS , SM/13122 | New | Material Requisition To Resource Division | 1172/MD | 26/04/2023 | 0 | Resource Division | 29.08 | 0 | 0 | 0
1910 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUNARPUR AND ADJOINING MOUJAS PWSS , SM/13122 | New | Quotation for new power connection at Kunarpur PWSS PH - I within Narayangarh Block Application No - 2004909181, Ref ID - 204404487 | C102455616858 | 30/10/2024 | 0 | WBSEDCL | 3.69 | 0 | 0 | 0
1911 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUNARPUR AND ADJOINING MOUJAS PWSS , SM/13122 | New | Quotation for new power connection at Kunarpur PWSS PH - II within Narayangarh Block Application No - 2004909199, Ref ID - 204404484 | C102455618296 | 30/10/2024 | 0 | WBSEDCL | 4.96 | 0 | 0 | 0
1912 | PASCHIM MEDINIPUR | Central Drilling | KUNARPUR AND ADJOINING MOUJAS PWSS , SM/13122 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1913 | PASCHIM MEDINIPUR | Midnapore Division | KUNARPUR AND ADJOINING MOUJAS PWSS , SM/13122 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (5,751 Nos.) including 2 years operation & maintenance For Kunarpur, Murakata & Nayapukur Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2827/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 1515.85 | 0 | 0 | 15
1914 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUNARPUR AND ADJOINING MOUJAS PWSS , SM/13122 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
1915 | PASCHIM MEDINIPUR | Central Drilling | KUNARPUR AND ADJOINING MOUJAS PWSS , SM/13122 | New | Hiring of Diesel driven motor cab (BS-III & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub-Divn-I(D), C.D.D., P.H.E. Dte. | 129/CMSD-I | 25/04/2025 | 184 | RUPAM GHOSH | 0.87 | 0 | 0 | 0
1916 | PASCHIM MEDINIPUR | Midnapore Division | DINGAL AND ITS ADJOINING MOUJAS PWSS , SM/12828 | New | Material Requisition To Resource Division | 1410 | 04/05/2023 | 0 | Resource Division | 36.06 | 0 | 0 | 0
1917 | PASCHIM MEDINIPUR | Midnapore Mechanical | DINGAL AND ITS ADJOINING MOUJAS PWSS , SM/12828 | New | Electrict quotation bill for TW-II of Dingal pwss (Ref Consumar ID-204198617),Application No-2004571068,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. | BP-2023-24-600 | 07/02/2024 | 0 | WBSEDCL | 0.51 | 0 | 0 | 0
1918 | PASCHIM MEDINIPUR | Midnapore Mechanical | DINGAL AND ITS ADJOINING MOUJAS PWSS , SM/12828 | New | Electrict quotation bill for TW-I of Dingal pwss (Ref Consumar ID-204199250),Application No-2004571039,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. | BP-2023-24-599 | 07/02/2024 | 0 | WBSEDCL | 6.95 | 0 | 0 | 0
1919 | PASCHIM MEDINIPUR | Midnapore Division | DINGAL AND ITS ADJOINING MOUJAS PWSS , SM/12828 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House, Boundary Wall, laying of Rising Main & Providing Functional Household Tap Connection (4740 Nos) including 2 years Operation & Maintenance For Dingal, Duan and Gobindapur Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | 2826/MD | 07/08/2023 | 785 | GOBINDA MAITY | 1375.06 | 0 | 0 | 74
1920 | PASCHIM MEDINIPUR | Midnapore Mechanical | DINGAL AND ITS ADJOINING MOUJAS PWSS , SM/12828 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DINGAL AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 826/W/MMD | 24/03/2023 | 952 | P.K.ENGINEERING | 22.65 | 0 | 0 | 50
1921 | PASCHIM MEDINIPUR | Midnapore Division | BARAKURYA AND ADJOINING MOUJAS PWSS , SM/13068 | New | Material Requisition To Resource Division | 1214/MD | 27/04/2023 | 0 | Resource Division | 19.59 | 0 | 0 | 0
1922 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BARAKURYA AND ADJOINING MOUJAS PWSS , SM/13068 | New | Quotation for new service connection at BARAKURA T/W -I water supply scheme. | 112/JMD | 13/05/2024 | 0 | WBSEDCL | 12.13 | 0 | 0 | 0
1923 | PASCHIM MEDINIPUR | Central Drilling | BARAKURYA AND ADJOINING MOUJAS PWSS , SM/13068 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1924 | PASCHIM MEDINIPUR | Central Drilling | CHANDANA AND ADJOINING MOUJAS PWSS , SM/13074 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm x 150mm x 220 Mtrs. Depth) by utilising Departmental machineries for Chandana W/S Scheme (T/W-I & II), Keshierya Block under PaschimeMedinipur District, CDD, PHE Dte. | 390/CDD | 18/05/2023 | 30 | S.G. ENTERPRISE | 25.39 | 0 | 0 | 100
1925 | PASCHIM MEDINIPUR | Midnapore Division | CHANDANA AND ADJOINING MOUJAS PWSS , SM/13074 | New | Material Requisition To Resource Division | 1310/MD | 28/04/2023 | 0 | Resource Division | 21.97 | 0 | 0 | 0
1926 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHANDANA AND ADJOINING MOUJAS PWSS , SM/13074 | New | ADDITIONAL QUOTATION FOR TW NO-I OF CHANDANA PWSS DUE TO SITE CHANGE. APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION. NAME OF CCC- KESHIARY CCC, NAME OF BLOCK- KESHIARY, REFERENCE ID-860308277, APPLICATION ID-100000116147. | BP-2024-25-606 | 29/08/2024 | 0 | WBSEDCL | 3.62 | 0 | 0 | 0
1927 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHANDANA AND ADJOINING MOUJAS PWSS , SM/13074 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of CHANDANA PWSS. (Ref Consumer ID-204175251) | BP-2023-24-585 | 25/01/2024 | 0 | WBSEDCL | 3.37 | 0 | 0 | 0
1928 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHANDANA AND ADJOINING MOUJAS PWSS , SM/13074 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF CHANDANA PWSS. (Ref Consumer ID-204175252) | BP-2023-24-584 | 25/01/2024 | 0 | WBSEDCL | 4.03 | 0 | 0 | 0
1929 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHANDANA AND ADJOINING MOUJAS PWSS , SM/13074 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHANDANA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 3083/W/MMD | 29/11/2023 | 641 | DIPALI CONSTRUCTION | 21.53 | 0 | 0 | 20
1930 | PASCHIM MEDINIPUR | Midnapore Division | GAZIPUR PATNA AND ADJOINING MOUJAS PWSS , SM/13084 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
1931 | PASCHIM MEDINIPUR | Midnapore Division | GAZIPUR PATNA AND ADJOINING MOUJAS PWSS , SM/13084 | New | Material Requisition To Resource Division | 211/MD | 16/01/2023 | 0 | Resource Division | 17 | 0 | 0 | 0
1932 | PASCHIM MEDINIPUR | Midnapore Division | GAZIPUR PATNA AND ADJOINING MOUJAS PWSS , SM/13084 | New | Material Requisition To Resource Division | 3460/MD | 25/11/2024 | 0 | Resource Division | 14.78 | 0 | 0 | 0
1933 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAZIPUR PATNA AND ADJOINING MOUJAS PWSS , SM/13084 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF GAZIPUR PATNA PWSS. REF CONSUMER ID-204362824, APPLICATION NO-2004829676, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-498 | 30/07/2024 | 0 | WBSEDCL | 2.98 | 0 | 0 | 0
1934 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAZIPUR PATNA AND ADJOINING MOUJAS PWSS , SM/13084 | New | Electric quotation bill for Tw No-II of GAZIPUR PATNA PWSS (REf CONSUMER ID-204183572) | BP-2023-24-583 | 25/01/2024 | 0 | WBSEDCL | 0.72 | 0 | 0 | 0
1935 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAZIPUR PATNA AND ADJOINING MOUJAS PWSS , SM/13084 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GAZIPUR PATNA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 835/W/MMD | 24/03/2023 | 737 | BHAGIRATHI JUTH AND HOLDINGS PVT LTD | 23.74 | 0 | 0 | 5
1936 | PASCHIM MEDINIPUR | Midnapore Division | BARAKEUNDI AND ADJOINING MOUJAS PWSS , SM/13002 | New | Material Requisition To Resource Division | 1257/MD | 28/04/2023 | 0 | Resource Division | 25.04 | 0 | 0 | 0
1937 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BARAKEUNDI AND ADJOINING MOUJAS PWSS , SM/13002 | New | New service connection charges for Barakeundi w/s scheme, t/w no.II | 37/JMD | 11/03/2024 | 0 | WBSEDCL | 3.45 | 0 | 0 | 0
1938 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BARAKEUNDI AND ADJOINING MOUJAS PWSS , SM/13002 | New | New service connection charges for Barakeundi w/s scheme, t/w no.I | 36/JMD | 11/03/2024 | 0 | WBSEDCL | 3.51 | 0 | 0 | 0
1939 | PASCHIM MEDINIPUR | Central Drilling | BARAKEUNDI AND ADJOINING MOUJAS PWSS , SM/13002 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1940 | PASCHIM MEDINIPUR | Midnapore Division | BARANAGARA AND ADJOINING MOUJAS PWSS , SM/13003 | New | Material Requisition To Resource Division | 1233/MD | 27/04/2023 | 0 | Resource Division | 25.56 | 0 | 0 | 0
1941 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BARANAGARA AND ADJOINING MOUJAS PWSS , SM/13003 | New | WBSEDCL new connection payment for Baranagora t/w 2 | 55/JMD | 29/04/2024 | 0 | WBSEDCL | 10.04 | 0 | 0 | 0
1942 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BARANAGARA AND ADJOINING MOUJAS PWSS , SM/13003 | New | WBSEDCL new connection payment for Baranagora t/w 1 | 54/JMD | 29/04/2024 | 0 | WBSEDCL | 6.85 | 0 | 0 | 0
1943 | PASCHIM MEDINIPUR | Central Drilling | BARANAGARA AND ADJOINING MOUJAS PWSS , SM/13003 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1944 | PASCHIM MEDINIPUR | Midnapore Division | KARSA AND ADJOINING MOUJAS PWSS , SM/13090 | New | Material Requisition To Resource Division | 1220/MD | 27/04/2023 | 0 | Resource Division | 21.92 | 0 | 0 | 0
1945 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KARSA AND ADJOINING MOUJAS PWSS , SM/13090 | New | New Service connection charges. | 198/JMD | 14/06/2024 | 0 | WBSEDCL | 6.87 | 0 | 0 | 0
1946 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KARSA AND ADJOINING MOUJAS PWSS , SM/13090 | New | Quotation for new service connection at Karsa T/W-II water supply scheme. | 42/JMD | 29/04/2024 | 0 | WBSEDCL | 3.15 | 0 | 0 | 0
1947 | PASCHIM MEDINIPUR | Central Drilling | KARSA AND ADJOINING MOUJAS PWSS , SM/13090 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1948 | PASCHIM MEDINIPUR | Midnapore Division | ASHARI AND IT'S ADJOINING MOUJAS PWSS , SM/12198 | New | Material Requisition To Resource Division | 4053/MD | 12/10/2023 | 0 | Resource Division | 20.09 | 0 | 0 | 0
1949 | PASCHIM MEDINIPUR | Midnapore Mechanical | ASHARI AND IT'S ADJOINING MOUJAS PWSS , SM/12198 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ASHARI AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 798/W/MMD | 24/03/2023 | 1013 | BHABANI PRASAD MANNA | 21.62 | 0 | 0 | 80
1950 | PASCHIM MEDINIPUR | Midnapore Division | ASHARI AND IT'S ADJOINING MOUJAS PWSS , SM/12198 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 0 | 25
1951 | PASCHIM MEDINIPUR | Midnapore Division | HARI PURA AND ADJOINING MOUJAS PWSS , SM/13053 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | 746/MD | 13/03/2023 | 30 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 0
1952 | PASCHIM MEDINIPUR | Midnapore Division | HARI PURA AND ADJOINING MOUJAS PWSS , SM/13053 | New | Material Requisition To Resource Division | 1314/MD | 28/04/2023 | 0 | Resource Division | 27.15 | 0 | 0 | 0
1953 | PASCHIM MEDINIPUR | Midnapore Mechanical | HARI PURA AND ADJOINING MOUJAS PWSS , SM/13053 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for HARI PURA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 3085/W/MMD | 29/11/2023 | 180 | M/S EMMESS | 22.79 | 0 | 0 | 20
1954 | PASCHIM MEDINIPUR | Central Drilling | HARI PURA AND ADJOINING MOUJAS PWSS , SM/13053 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Hari Pura W/S Scheme (TW-I & II), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | 1090/CDD | 18/08/2023 | 714 | PADMA ENGINEERING & CO. | 25.33 | 0 | 0 | 100
1955 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12826 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Satkui PWSS within Kharagpur-I Block under Midnapore Division, P.H.E. Dte. | 519/MD | 17/03/2022 | 10 | SIRCON ENGINEERING SERVICES | 2.24 | 0 | 0 | 100
1956 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12826 | Augmentation | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations under (1) Augmentation of Keshiary & its adjoining mouzas W/S Scheme within Keshiary block & (2) Augmentation of Satkui & its adjoining mouzas W/S Scheme within Kharagpur-I block in Paschim Medinipur District through Jadavpur University. | 471/MD | 15/02/2023 | 14 | JADAVPUR UNIVERSITY | 9.56 | 0 | 0 | 100
1957 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12826 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 533/W/MMD | 20/03/2023 | 180 | P.K.ENGINEERING | 22.78 | 0 | 0 | 45
1958 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12826 | Augmentation | Material Requisition To Resource Division | 182/MD | 16/01/2023 | 0 | Resource Division | 15.15 | 0 | 0 | 0
1959 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12826 | Augmentation | QUOTATION FOR NEW POWER SUPPLY FOR SAKUI W/S SCHEME , T W NO 02, CONSUMER ID 204030395, SCHEME CODE SM/12826 , NIMPURA CCC WBSEDCL | BP-2023-24-130 | 19/07/2023 | 0 | WBSEDCL | 0.56 | 0 | 0 | 0
1960 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12826 | Augmentation | Laying of pipeline supportive to retrofitting to accommodate FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM for Augmentation of Satkui & its adjoining mouza W/S Scheme within Kharagpur-I Dev. block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | 2475/MD | 14/07/2023 | 14 | ARNAB PATRA | 7.07 | 0 | 0 | 100
1961 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12826 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall & Construction of 200 CuM Capacity OHR with 20 m Staging height for Augmentation of Satkui PWSS in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 2572/MD | 16/12/2022 | 1159 | DULAL CHANDRA DAS | 196.05 | 0 | 0 | 42
1962 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12826 | Augmentation | Sinking of 250 X 150 mm dia. X 215 Mtr. Depth deep tube well, Construction of Pump House & Boundary wall of 3rd tube well site and interconnection of 3rd tube well with distribution line and repair of OHR & Pump House-I for Augmentation of Satkui W/S Scheme within Kharagpur-I block under Midnapore Division, PHE Dte. | 669/MD | 10/03/2025 | 75 | M/S CHOWDHURY CONSTRUCTION (NEW) | 21.62 | 0 | 0 | 0
1963 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/12826 | Augmentation | Route survey & way leave permission along & across of National Highway under Augmentation of Satkui PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | 523/MD | 19/02/2025 | 21 | PIONEER SURVEYORS | 9.11 | 0 | 0 | 0
1964 | PASCHIM MEDINIPUR | Midnapore Division | AGRA & ADJOINING MOUJAS PWSS , SM/13052 | New | Material Requisition To Resource Division | 1151/MD | 25/04/2023 | 0 | Resource Division | 23.1 | 0 | 0 | 0
1965 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | AGRA & ADJOINING MOUJAS PWSS , SM/13052 | New | New Service connection charges. | 62/JMD | 13/03/2024 | 0 | WBSEDCL | 5.26 | 0 | 0 | 0
1966 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | AGRA & ADJOINING MOUJAS PWSS , SM/13052 | New | New service connection charges at Agra-II water supply scheme | 183/JMD | 11/06/2024 | 0 | WBSEDCL | 3.34 | 0 | 0 | 0
1967 | PASCHIM MEDINIPUR | Central Drilling | AGRA & ADJOINING MOUJAS PWSS , SM/13052 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1968 | PASCHIM MEDINIPUR | Midnapore Division | KHANDRUI AND IT'S ADJOINING MOUJAS PWSS. , SM/13025 | New | Material Requisition To Resource Division | 1293/MD | 28/04/2023 | 0 | Resource Division | 28.04 | 0 | 0 | 0
1969 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHANDRUI AND IT'S ADJOINING MOUJAS PWSS. , SM/13025 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF KHANDRUI PWSS. REF CONSUMER ID-204393520, APPLICATION NO-2004889527, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102401983645 | 03/10/2024 | 0 | WBSEDCL | 6.62 | 0 | 0 | 0
1970 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHANDRUI AND IT'S ADJOINING MOUJAS PWSS. , SM/13025 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF KHANDRUI PWSS. REF CONSUMER ID-204393518, APPLICATION NO-2004889496, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102401983017 | 03/10/2024 | 0 | WBSEDCL | 5.19 | 0 | 0 | 0
1971 | PASCHIM MEDINIPUR | Central Drilling | KHANDRUI AND IT'S ADJOINING MOUJAS PWSS. , SM/13025 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1972 | PASCHIM MEDINIPUR | Midnapore Division | PATHARISOL AND ADJOINING MOUJAS PWSS , SM/13030 | New | Material Requisition To Resource Division | 1179/MD | 26/04/2023 | 0 | Resource Division | 28.94 | 0 | 0 | 0
1973 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PATHARISOL AND ADJOINING MOUJAS PWSS , SM/13030 | New | NEW SERVICE CONNECTION CHARGES AT PATHRISOLE TW-I WATER SUPPLY SCHEME | 244/JMD | 10/07/2024 | 0 | WBSEDCL | 7.8 | 0 | 0 | 0
1974 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PATHARISOL AND ADJOINING MOUJAS PWSS , SM/13030 | New | NEW SERVICE CONNECTION CHARGES AT PATHRISOLE TW-II WATER SUPPLY SCHEME | 245/JMD | 10/07/2024 | 0 | WBSEDCL | 3.93 | 0 | 0 | 0
1975 | PASCHIM MEDINIPUR | Central Drilling | PATHARISOL AND ADJOINING MOUJAS PWSS , SM/13030 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1976 | PASCHIM MEDINIPUR | Midnapore Division | PATHARISOL AND ADJOINING MOUJAS PWSS , SM/13030 | New | Route survey & way leave permission along & across of National Highway in Patharisol PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | 1628/MD | 06/08/2025 | 21 | PIONEER SURVEYORS | 9.55 | 0 | 0 | 0
1977 | PASCHIM MEDINIPUR | Midnapore Division | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR , SM/13031 | New | Material Requisition To Resource Division | 1517/MD | 12/05/2023 | 0 | Resource Division | 11.96 | 0 | 0 | 0
1978 | PASCHIM MEDINIPUR | Midnapore Mechanical | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR , SM/13031 | New | Electrict quotation bill for TW-II of Patna pwss (Ref Consumar ID-204252309),Application No-2004648500,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. | BP-2024-25-41 | 18/04/2024 | 0 | WBSEDCL | 5.21 | 0 | 0 | 0
1979 | PASCHIM MEDINIPUR | Midnapore Mechanical | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR , SM/13031 | New | Electrict quotation bill for TW-I of Patna pwss (Ref Consumar ID-204251327),Application No-2004648431,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. | BP-2024-25-42 | 18/04/2024 | 0 | WBSEDCL | 3.6 | 0 | 0 | 0
1980 | PASCHIM MEDINIPUR | Midnapore Division | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR , SM/13031 | New | Construction of 150 Cum, 200 Cum & 250 Cum Capacity R.C.C Over Head Reservoir Over (Intze type with solid raft) works with Laying of Rising Main, Distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (5061 Nos.) including 2 years Operation & Maintenance for Loyada, Madhabpur, Patna and Radhamohanpur-II Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2824/MD | 07/08/2023 | 723 | MADE AND TRADE CO. | 1346.28 | 0 | 0 | 75
1981 | PASCHIM MEDINIPUR | Midnapore Mechanical | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR , SM/13031 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Patna PWSS, BLOCK - DEBRA Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | 2304/W/MMD | 29/12/2022 | 1274 | DEBJYOTI BASU | 22.87 | 0 | 0 | 50
1982 | PASCHIM MEDINIPUR | Midnapore Division | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS , SM/13032 | New | Material Requisition To Resource Division | 97/MD | 10/01/2023 | 0 | Resource Division | 15.44 | 0 | 0 | 0
1983 | PASCHIM MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS , SM/13032 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZASunder JJM Program under MMD PHE Dte. | 3086/W/MMD | 29/11/2023 | 457 | M/S BARMAN ROY TRADERS | 25.52 | 0 | 0 | 20
1984 | PASCHIM MEDINIPUR | Midnapore Division | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS , SM/13032 | New | Material Requisition To Resource Division | 3379/MD | 25/11/2024 | 0 | Resource Division | 16.42 | 0 | 0 | 0
1985 | PASCHIM MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS , SM/13032 | New | Electric quotation bill for Tw No-II of RANIOR PWSS.(Ref Consumer ID-204200319), APPLICATION NO-2004571260, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC- UPPERKUAI CCC, BLOCK-KESHPUR | BP-2023-24-615 | 07/02/2024 | 0 | WBSEDCL | 4.85 | 0 | 0 | 0
1986 | PASCHIM MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS , SM/13032 | New | Electric quotation bill for Tw No-I of RANIOR PWSS.(Ref Consumer ID-204200356), APPLICATION NO-2004571235, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC- UPPERKUAI CCC. | BP-2023-24-614 | 07/02/2024 | 0 | WBSEDCL | 4.15 | 0 | 0 | 0
1987 | PASCHIM MEDINIPUR | Midnapore Division | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS , SM/13032 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2725 nos) under JJM with allied work for Raniar PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 2420/MD | 13/07/2023 | 839 | BANERJEE CONSTRUCTION | 800.44 | 0 | 0 | 66
1988 | PASCHIM MEDINIPUR | Midnapore Division | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS , SM/13032 | New | Laying of rising main & interconnection for Raniar & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 730 Mtr.) | 321/MD | 29/01/2025 | 45 | ASHOK BANERJEE | 6.81 | 0 | 0 | 0
1989 | PASCHIM MEDINIPUR | Midnapore Division | DUMURIA AND ADJOINING MOUJAS PWSS , SM/14032 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
1990 | PASCHIM MEDINIPUR | Midnapore Division | DUMURIA AND ADJOINING MOUJAS PWSS , SM/14032 | New | Material Requisition To Resource Division | 1525/MD | 12/05/2023 | 0 | Resource Division | 15.49 | 0 | 0 | 0
1991 | PASCHIM MEDINIPUR | Midnapore Division | DUMURIA AND ADJOINING MOUJAS PWSS , SM/14032 | New | Construction of 250 Cum Capacity R.C.C Over Head Reservoir Over Raft Foundation works with laying rising main, distribution system, Sinking of Tube Well, Pump House, Soil Investigation, Boundary Wall & Providing Functional Household Tap Connection (1968 Nos.) including Two Years Operation & maintenance For Dumuria Pipe Water Supply Scheme within Garbeta-II Block Under Medinipur Sadar Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | 5068/MD | 26/10/2023 | 463 | TITAS COSTRUCTION | 540.55 | 0 | 0 | 3
1992 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | DUMURIA AND ADJOINING MOUJAS PWSS , SM/14032 | New | Payment for new service connection at Dumuria T/W-2 | 116/JMD | 13/05/2024 | 0 | WBSEDCL | 4.95 | 0 | 0 | 0
1993 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | DUMURIA AND ADJOINING MOUJAS PWSS , SM/14032 | New | Payment for new service connection charges Dumuria T/W-1 | 60/JMD | 29/04/2024 | 0 | WBSEDCL | 3.59 | 0 | 0 | 0
1994 | PASCHIM MEDINIPUR | Central Drilling | DUMURIA AND ADJOINING MOUJAS PWSS , SM/14032 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1995 | PASCHIM MEDINIPUR | Midnapore Division | KUKRADA AND ITS ADJOINING MOUZAS PWSS , SM/14654 | New | Material Requisition To Resource Division | 212/MD | 16/01/2023 | 0 | Resource Division | 42.05 | 0 | 0 | 0
1996 | PASCHIM MEDINIPUR | Midnapore Division | KUKRADA AND ITS ADJOINING MOUZAS PWSS , SM/14654 | New | Material Requisition To Resource Division | 3425/MD | 25/11/2024 | 0 | Resource Division | 13.45 | 0 | 0 | 0
1997 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUKRADA AND ITS ADJOINING MOUZAS PWSS , SM/14654 | New | Quotation for new power connection at Kukrada PWSS TW - II with in Narayangarh Block Application No - 2005005228 Ref ID - 204471132 |  | 18/12/2024 | 0 | WBSEDCL | 6.21 | 0 | 0 | 0
1998 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUKRADA AND ITS ADJOINING MOUZAS PWSS , SM/14654 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUKRADA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 500/W/MMD | 20/03/2023 | 819 | PADMA ENGINEERING CO. | 23 | 0 | 0 | 80
1999 | PASCHIM MEDINIPUR | Midnapore Division | KUKRADA AND ITS ADJOINING MOUZAS PWSS , SM/14654 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 300 Cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,184 nos.) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Kukrada & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 5283/MD | 23/11/2023 | 720 | CREATION CONSTRUCTION | 530.64 | 0 | 0 | 60
2000 | PASCHIM MEDINIPUR | Midnapore Division | KUKRADA AND ITS ADJOINING MOUZAS PWSS , SM/14654 | New | Route survey & way leave permission along & across of National Highway in Kukrada PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | 522/MD | 19/02/2025 | 21 | PIONEER SURVEYORS | 9.44 | 0 | 0 | 0
2001 | PASCHIM MEDINIPUR | Midnapore Division | GANUA AND ADJOINING MOUJAS PWSS , SM/15000 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Ganua, (2) Gokulpur & (3) Naharpur] | 834/MD | 22/03/2023 | 21 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0 | 0
2002 | PASCHIM MEDINIPUR | Midnapore Division | GANUA AND ADJOINING MOUJAS PWSS , SM/15000 | New | Material Requisition To Resource Division | 183/MD | 16/01/2023 | 0 | Resource Division | 17.04 | 0 | 0 | 0
2003 | PASCHIM MEDINIPUR | Midnapore Division | GANUA AND ADJOINING MOUJAS PWSS , SM/15000 | New | Material Requisition To Resource Division | 3450/MD | 25/11/2024 | 0 | Resource Division | 16.08 | 0 | 0 | 0
2004 | PASCHIM MEDINIPUR | Central Drilling | GANUA AND ADJOINING MOUJAS PWSS , SM/15000 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2005 | PASCHIM MEDINIPUR | Midnapore Mechanical | GANUA AND ADJOINING MOUJAS PWSS , SM/15000 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
2006 | PASCHIM MEDINIPUR | Midnapore Division | KADAM DIHA AND ADJOINING MOUJAS PWSS , SM/15012 | New | Material Requisition To Resource Division | 1229/MD | 27/04/2023 | 0 | Resource Division | 30.35 | 0 | 0 | 0
2007 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KADAM DIHA AND ADJOINING MOUJAS PWSS , SM/15012 | New | WBSEDCL new connection payment for Kadamdiha t/w 2 | 228/JMD | 28/06/2024 | 0 | WBSEDCL | 7.12 | 0 | 0 | 0
2008 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KADAM DIHA AND ADJOINING MOUJAS PWSS , SM/15012 | New | Payment for WBSEDCL new connection at KADAMDIHA 1 (SM/15012. KADAMDIHA AND ADJOINING MOUJAS PWSS ) | 174/JMD | 07/06/2024 | 0 | WBSEDCL | 5.17 | 0 | 0 | 0
2009 | PASCHIM MEDINIPUR | Central Drilling | KADAM DIHA AND ADJOINING MOUJAS PWSS , SM/15012 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2010 | PASCHIM MEDINIPUR | Midnapore Division | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15118 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Ranjapur & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | 1754/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.93 | 0 | 0 | 100
2011 | PASCHIM MEDINIPUR | Midnapore Division | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15118 | New | Material Requisition To Resource Division | 1276/MD | 28/04/2023 | 0 | Resource Division | 33.3 | 0 | 0 | 0
2012 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15118 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 1461/W/MMD | 13/06/2023 | 180 | TAPAN KUMAR SARKAR | 22.99 | 0 | 0 | 40
2013 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15118 | New | QUOTATION MONEY FOR RANJAPUR WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/15118, APPLICATION NO 2004816291, REFERENCE ID 204354170, BIRSHINGHA CCC, WBSEDCL | BP-2024-25-505 | 30/07/2024 | 0 | WBSEDCL | 6.72 | 0 | 0 | 0
2014 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15118 | New | QUOTATION MONEY FOR RANJAPUR WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/15118, APPLICATION NO 2004816268, REFERENCE ID 204354168, BIRSHINGHA CCC, WBSEDCL | BP-2024-25-500 | 30/07/2024 | 0 | WBSEDCL | 3.09 | 0 | 0 | 0
2015 | PASCHIM MEDINIPUR | Midnapore Division | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/15119 | New | Material Requisition To Resource Division | 107/MD | 10/01/2023 | 0 | Resource Division | 44.15 | 0 | 0 | 0
2016 | PASCHIM MEDINIPUR | Midnapore Division | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/15119 | New | Material Requisition To Resource Division | 3355/MD | 25/11/2024 | 0 | Resource Division | 10.98 | 0 | 0 | 0
2017 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/15119 | New | QUOTATION MONEY FOR SAGARPUR WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/15119, [ NABODAY SANGHA ] APPLICATION NO 2004809587, REFERENCE ID 204352800, DASPUR CCC, WBSEDCL | C072443762107 | 29/07/2024 | 0 | WBSEDCL | 9.98 | 0 | 0 | 0
2018 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/15119 | New | QUOTATION MONEY FOR SAGARPUR WATER SUPPLY SCHEME, T W NO I, JJM WORKS, SCHEME CODE SM/15591, APPLICATION NO 2004809605, REFERENCE ID 204352801, DASPUR CCC, WBSEDCL | C072443748308 | 29/07/2024 | 0 | WBSEDCL | 10.81 | 0 | 0 | 0
2019 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/15119 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 491/W/MMD | 20/03/2023 | 845 | INDTECH ASSOCIATES | 23 | 0 | 0 | 85
2020 | PASCHIM MEDINIPUR | Midnapore Division | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/15119 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,783 nos.) under JJM with allied work for Sagarpur PWSS in Daspur- I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 3821/MD | 20/09/2023 | 540 | KISHORE GHOSH | 559.14 | 0 | 0 | 10
2021 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15121 | New | Material Requisition To Resource Division | 102/MD | 10/01/2023 | 0 | Resource Division | 32.36 | 0 | 0 | 0
2022 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15121 | New | Material Requisition To Resource Division | 1373/MD | 02/05/2023 | 0 | Resource Division | 10.87 | 0 | 0 | 0
2023 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15121 | New | New service connection | 7/JMD | 11/10/2023 | 0 | WBSEDCL | 6.36 | 0 | 0 | 0
2024 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15121 | New | New service connection | 6/JMD | 11/10/2023 | 0 | WBSEDCL | 5.63 | 0 | 0 | 0
2025 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15121 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 945/W/MMD | 28/03/2023 | 180 | DEBJYOTI BASU | 25.25 | 0 | 0 | 5
2026 | PASCHIM MEDINIPUR | Midnapore Division | TELIJANT AND IT'S ADJOINING MOUJAS PWSS , SM/13175 | New | Material Requisition To Resource Division | 1186/MD | 26/04/2023 | 0 | Resource Division | 31.65 | 0 | 0 | 0
2027 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | TELIJANT AND IT'S ADJOINING MOUJAS PWSS , SM/13175 | New | New service connection charges at Telijhant TW-II water supply scheme | 219/JMD | 21/06/2024 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
2028 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | TELIJANT AND IT'S ADJOINING MOUJAS PWSS , SM/13175 | New | New service connection charges at Telijhant TW-I water supply scheme | 220/JMD | 21/06/2024 | 0 | WBSEDCL | 3.67 | 0 | 0 | 0
2029 | PASCHIM MEDINIPUR | Central Drilling | TELIJANT AND IT'S ADJOINING MOUJAS PWSS , SM/13175 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2030 | PASCHIM MEDINIPUR | Midnapore Division | DHOBABARIA AND ADJOINIONG MOUJAS PWSS , SM/13140 | New | Material Requisition To Resource Division | 1181/MD | 26/04/2023 | 0 | Resource Division | 37.9 | 0 | 0 | 0
2031 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | DHOBABARIA AND ADJOINIONG MOUJAS PWSS , SM/13140 | New | NEW SERVICE CONNECTION CHARGES AT Dhobaberia TW-II WATER SUPPLY SCHEME | 253/JMD | 10/07/2024 | 0 | WBSEDCL | 3.76 | 0 | 0 | 0
2032 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | DHOBABARIA AND ADJOINIONG MOUJAS PWSS , SM/13140 | New | NEW SERVICE CONNECTION CHARGES AT Dhobaberia TW-I WATER SUPPLY SCHEME | 252/JMD | 10/07/2024 | 0 | WBSEDCL | 4.02 | 0 | 0 | 0
2033 | PASCHIM MEDINIPUR | Central Drilling | DHOBABARIA AND ADJOINIONG MOUJAS PWSS , SM/13140 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2034 | PASCHIM MEDINIPUR | Midnapore Division | DHOBABARIA AND ADJOINIONG MOUJAS PWSS , SM/13140 | New | Route survey & way leave permission along & across of National Highway in Dhobaberiya PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | 379/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 10.59 | 0 | 0 | 0
2035 | PASCHIM MEDINIPUR | Midnapore Division | GAGANESHWAR AND ADJOINING MOUJAS PWSS , SM/13082 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | 746/MD | 13/03/2023 | 30 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 0
2036 | PASCHIM MEDINIPUR | Midnapore Division | GAGANESHWAR AND ADJOINING MOUJAS PWSS , SM/13082 | New | Material Requisition To Resource Division | 1313/MD | 28/04/2023 | 0 | Resource Division | 46.06 | 0 | 0 | 0
2037 | PASCHIM MEDINIPUR | Central Drilling | GAGANESHWAR AND ADJOINING MOUJAS PWSS , SM/13082 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 220 Mtrs. Depth) by utilising Departmental Machineries for GAGANESHWAR W/S Scheme (T/W-I & II) , Keshiery Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | 393/CDD | 18/05/2023 | 30 | PADMA ENGINEERING & CO. | 25.43 | 0 | 0 | 100
2038 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAGANESHWAR AND ADJOINING MOUJAS PWSS , SM/13082 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of GAGANESHWAR PWSS. REF CONSUMER ID-204208789, APPLICATION NO-2004586829, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2023-24-636 | 08/02/2024 | 0 | WBSEDCL | 4.03 | 0 | 0 | 0
2039 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAGANESHWAR AND ADJOINING MOUJAS PWSS , SM/13082 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of GAGANESHWAR PWSS. REF CONSUMER ID-204204420, APPLICATION NO-2004578826, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2023-24-635 | 08/02/2024 | 0 | WBSEDCL | 7.11 | 0 | 0 | 0
2040 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAGANESHWAR AND ADJOINING MOUJAS PWSS , SM/13082 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GAGANESHWAR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 2120/W/MMD | 01/10/2024 | 180 | ORIENTAL ENGINEERING CO. | 32.75 | 0 | 0 | 20
2041 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/13826 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR location for Augmentation of Chak Ismailpur W/S Scheme under Dantan-I Block of Paschim Medinipur District through Jadavpur University. | 706/MD | 06/03/2023 | 7 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0 | 0
2042 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/13826 | Augmentation | Laying Rising main pipe line, Construction of Pump House & Boundary wall under JJM with allied work for Augmentation Chak Ismailpur PWSS in Dantan-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 4023/MD | 10/10/2023 | 60 | TARUN MAHATA | 24.51 | 0 | 0 | 0
2043 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/13826 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Chak Ismailpur, Block - Dantan-I) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. | 246/DP/MD | 10/02/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.77 | 0 | 0 | 100
2044 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/13826 | Augmentation | Material Requisition To Resource Division | 94/MD | 10/01/2023 | 0 | Resource Division | 16.53 | 0 | 0 | 0
2045 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/13826 | Augmentation | Quatation for New service connection at Chakismilpur(Ref no-203987606) | BP-2023-24-65 | 06/06/2023 | 0 | WBSEDCL | 5.42 | 0 | 0 | 0
2046 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/13826 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | 355/W/MMD | 09/03/2023 | 180 | MANORANJAN DEY | 11.44 | 0 | 0 | 20
2047 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/13826 | Augmentation | Sinking of 250 X 150 mm dia. X 200 Mtr. Depth tube well, Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 100 Cum and staging height 20.00 mtr. & FHTC (853 Nos.) under JJM with allied work for Augmentation of Chak Ismailpur and its adjoining mouzas W/S scheme in Datan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 455/MD | 13/02/2023 | 1005 | M/S. D.K.H.CONSTRUCTION | 200.6 | 0 | 0 | 82
2048 | PASCHIM MEDINIPUR | Midnapore Division | BENYA AND IT'S ADJOINING MOUJAS PWSS. , SM/14721 | New | Material Requisition To Resource Division | 1582/MD | 15/05/2023 | 0 | Resource Division | 26.86 | 0 | 0 | 0
2049 | PASCHIM MEDINIPUR | Midnapore Mechanical | BENYA AND IT'S ADJOINING MOUJAS PWSS. , SM/14721 | New | Electrict quotation bill for TW-II of Benia pwss (Ref Consumar ID-204439151),Application No-2004955856,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | C112429735070 | 25/11/2024 | 0 | WBSEDCL | 3.64 | 0 | 0 | 0
2050 | PASCHIM MEDINIPUR | Midnapore Mechanical | BENYA AND IT'S ADJOINING MOUJAS PWSS. , SM/14721 | New | Electrict quotation bill for TW-I of Benia pwss (Ref Consumar ID-204439152),Application No-2004955874,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | C112429730333 | 25/11/2024 | 0 | WBSEDCL | 4.68 | 0 | 0 | 0
2051 | PASCHIM MEDINIPUR | Midnapore Division | BENYA AND IT'S ADJOINING MOUJAS PWSS. , SM/14721 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 0 | 25
2052 | PASCHIM MEDINIPUR | Midnapore Mechanical | BENYA AND IT'S ADJOINING MOUJAS PWSS. , SM/14721 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BENYA AND IT'S ADJOINING MOUJAS PWSS. under JJM Program under MMD PHE Dte. | 484/W/MMD | 20/03/2023 | 1290 | SHOVAN KUMAR DAS | 23.01 | 0 | 0 | 65
2053 | PASCHIM MEDINIPUR | Midnapore Division | HATKATA AND ITS ADJOINING MOUZAS PWSS , SM/15592 | New | Material Requisition To Resource Division | 1407/MD | 04/05/2023 | 0 | Resource Division | 68.4 | 0 | 0 | 0
2054 | PASCHIM MEDINIPUR | Midnapore Mechanical | HATKATA AND ITS ADJOINING MOUZAS PWSS , SM/15592 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for HATKATA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 906/W/MMD | 27/03/2023 | 719 | JYOTY SOLAR POWER | 27.36 | 0 | 0 | 30
2055 | PASCHIM MEDINIPUR | Midnapore Mechanical | HATKATA AND ITS ADJOINING MOUZAS PWSS , SM/15592 | New | ADDITIONAL QUOTATION FEE FOR EFFECTING NSC AT HATKATA PWSS. REF ID-860299035, APPLICATION ID-100000106465, APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-127 | 06/05/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2056 | PASCHIM MEDINIPUR | Midnapore Mechanical | HATKATA AND ITS ADJOINING MOUZAS PWSS , SM/15592 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF HATKATA PWSS. REF CONSUMER ID-204325523, APPLICATION NO-2004767096, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-293 | 18/06/2024 | 0 | WBSEDCL | 5.49 | 0 | 0 | 0
2057 | PASCHIM MEDINIPUR | Midnapore Mechanical | HATKATA AND ITS ADJOINING MOUZAS PWSS , SM/15592 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of HATKATA PWSS. REF CONSUMER ID-204210559, APPLICATION NO-2004589087, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-699 | 16/02/2024 | 0 | WBSEDCL | 6.35 | 0 | 0 | 0
2058 | PASCHIM MEDINIPUR | Midnapore Mechanical | HATKATA AND ITS ADJOINING MOUZAS PWSS , SM/15592 | New | ADDITIONAL QUOTATION FOR EFFECTING NSC IRO ASSISTANT ENGINEER PHE DTE FOR EFFECTING NSC IN REVISED ROUTE AT TW-I OF HATKATA PWSS, REFERENCE ID-860305080, APPLICATION ID-100000112900. APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION. | C072445050786 | 30/07/2024 | 0 | WBSEDCL | 2.46 | 0 | 0 | 0
2059 | PASCHIM MEDINIPUR | Midnapore Division | HATKATA AND ITS ADJOINING MOUZAS PWSS , SM/15592 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 Cum OHR (Intze type with Pile Foundation) & Accommodate FHTC (2,882 Nos.) including Two years O&M under JJM with allied work for Hatkata & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | 2955/MD | 17/08/2023 | 903 | M/S. D.K.H.CONSTRUCTION | 719.89 | 0 | 0 | 25
2060 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 650/W/MMD | 20/03/2023 | 180 | M/S. SAJAHAN CHOWDHURY | 43.15 | 0 | 0 | 63
2061 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Installation of 250mm X 150mm X 150 Mtr. Depth Rig bore Tube well (2 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VI] | 2425/MD | 13/07/2023 | 21 | MIDNAPUR PIPE CONCERN | 15.62 | 0 | 0 | 100
2062 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Installation of 250mm X 150mm X 150 Mtr. Depth Rig bore Tube well (2 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VI] | 2640/MD | 24/07/2023 | 21 | MIDNAPUR PIPE CONCERN | 15.62 | 0 | 0 | 100
2063 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Material Requisition To Resource Division | 1365/MD | 02/05/2023 | 0 | Resource Division | 36.92 | 0 | 0 | 0
2064 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | QUOTATION FOR NEW POWER CONNECTION OF HARIATARA [ GERIASULI-II] WATER SUPPLY ASCHEME [ APPLICATION --2004479502, REFERENCE ID ----204122241, NIMPURA CCC, QUOTATION NO ---2004479502/QUOT/03 DATED 26/10/2023, SCHEME NAME --- HARIATARA [ GERIASULI-II ] . , SCHEME CODE ---SM/14483 , MB NO--3580 ] | BP-2023-24-354 | 13/11/2023 | 0 | WBSEDCL | 0.51 | 0 | 0 | 0
2065 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | QUOTATION FOR NEW POWER CONNECTION OF HARIATARA [ GURIAMARI] WATER SUPPLY ASCHEME [ APPLICATION --2004479524, REFERENCE ID ----204122240, NIMPURA CCC, QUOTATION NO ---2004479524/QUOT/03 DATED 26/10/2023, SCHEME NAME --- HARIATARA [ GURIAMARI ] . , SCHEME CODE ---SM/14483 , MB NO--3580 ], | BP-2023-24-353 | 13/11/2023 | 0 | WBSEDCL | 3.5 | 0 | 0 | 0
2066 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | QUOTATION FOR NEW POWER CONNECTION OF HARIATARA [ GERIASULI-I] WATER SUPPLY ASCHEME [ APPLICATION --2004479494, REFERENCE ID ----204122247, NIMPURA CCC, QUOTATION NO ---2004479494/QUOT/03 DATED 26/10/2023, SCHEME NAME --- HARIATARA [ GERIASULI-I] . , SCHEME CODE ---SM/14483 , MB NO--3580 ] | BP-2023-24-350 | 10/11/2023 | 0 | WBSEDCL | 4.75 | 0 | 0 | 0
2067 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | QUOTATION FOR NEW POWER CONNECTION OF HARIATARA [ MULBANDH] WATER SUPPLY ASCHEME [ APPLICATION --2004479472, REFERENCE ID ----204122244, NIMPURA CCC, QUOTATION NO ---2004479472/QUOT/03 DATED 26/10/2023, SCHEME NAME --- HARIATARA [ MULBANDH ] . , SCHEME CODE ---SM/14483 , MB NO--3580 ] | BP-2023-24-347 | 10/11/2023 | 0 | WBSEDCL | 0.51 | 0 | 0 | 0
2068 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Construction of Pump House, Laying Rising main, Boundary wall, Laying distribution system pipe line, Accommodate FHTC (252 Nos.) including 2 yrs. O&M under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | 1408/MD | 04/05/2023 | 749 | R. CONSTRUCTION | 88.64 | 0 | 0 | 65
2069 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Laying distribution system pipe line & Accommodate FHTC (252 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | 2468/MD | 14/07/2023 | 600 | WATER LINK | 69.34 | 0 | 0 | 70
2070 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Laying distribution system pipe line & Accommodate FHTC (100 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | 2469/MD | 14/07/2023 | 879 | GOUTAM PARIA | 44.55 | 0 | 0 | 75
2071 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Laying distribution system pipe line & Accommodate FHTC (152 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-V] | 2470/MD | 14/07/2023 | 60 | BUNBA CONSTRUCTION | 34.51 | 0 | 0 | 68
2072 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Laying distribution system pipe line & Accommodate FHTC (269 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | 2471/MD | 14/07/2023 | 989 | MIDNAPUR PIPE CONCERN | 80.7 | 0 | 0 | 70
2073 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Laying distribution system pipe line & Accommodate FHTC (100 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | 2472/MD | 14/07/2023 | 60 | DEBASISH DOGRA | 47.36 | 0 | 0 | 95
2074 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Laying distribution system pipe line & Accommodate FHTC (152 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-V] | 2673/MD | 26/07/2023 | 45 | AJIJUR RAHAMAN MALLICK | 26.72 | 0 | 0 | 80
2075 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Construction of Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, FHTC (100 Nos.) under JJM with allied work for Hariatara PWSS (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | 2638/MD | 24/07/2023 | 60 | HYDRO TECH ASSOCIATES | 15.63 | 0 | 0 | 75
2076 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Laying distribution pipe line with Rising Main, Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, Development H/W site FHTC (117 Nos.) & 2 yrs. O&M under JJM with allied work for Hariatara PWSS (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | 805/MD | 15/03/2024 | 60 | AJIJUR RAHAMAN MALLICK | 42.9 | 0 | 0 | 92
2077 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Construction of Pump House, Laying Rising main, Boundary wall, Laying distribution system pipe line, Accommodate FHTC (252 Nos.) including 2 yrs. O&M under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | 1965/MD | 26/06/2024 | 300 | DEBASISH DOGRA | 97.72 | 0 | 0 | 55
2078 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Sinking of 2 Nos. Tube well under JJM with allied work for Hariatara PWSS (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | 2669/MD | 26/07/2023 | 21 | DEBASISH DOGRA | 12.01 | 0 | 0 | 100
2079 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | QUOTATION MONEY FOR HARIATARA WATER SUPPLY SCHEME (PORADIHA), JJM WORKS, SCHEME CODE SM/14483, APPLICATION NO 2004576970, REFERENCE ID 204203221, NIMPURA CCC, WBSEDCL | BP-2023-24-701 | 16/02/2024 | 0 | WBSEDCL | 3.26 | 0 | 0 | 0
2080 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | QUOTATION MONEY FOR HARIATARA WATER SUPPLY SCHEME, ZONE-I, T W NO II, JJM WORKS, SCHEME CODE SM/14483, APPLICATION NO 2004576786, REFERENCE ID 204203220, NIMPURA CCC, WBSEDCL | BP-2023-24-917 | 28/03/2024 | 0 | WBSEDCL | 3.29 | 0 | 0 | 0
2081 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, and III) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte.(Part-II) | 934/W/MMD | 28/03/2023 | 180 | SUBHASIS ROY | 11.97 | 0 | 0 | 90
2082 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Construction of RCC OHR (150 CuM), Pump House, Boundary wall & Accommodate FHTC (335 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | 3399/MD | 25/11/2024 | 180 | A K SIKDAR | 110.39 | 0 | 0 | 15
2083 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14483 | New | Construction of RCC OHR (150 CuM), Pump House, Boundary wall & Accommodate FHTC (324 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | 3479/MD | 26/11/2024 | 360 | DEBASISH DOGRA | 109.07 | 0 | 0 | 20
2084 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT DEBHOG AND OTHER 26 PWSS IN PASCHIM MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. , SM/14485 | Augmentation | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT DEBHOG AND OTHER 26 PWSS IN PASCHIM MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. | 364/W/MMD | 09/03/2023 | 180 | P.K.ENGINEERING | 53.06 | 0 | 0 | 0
2085 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | Material Requisition To Resource Division | 208/MD | 16/01/2023 | 0 | Resource Division | 30.42 | 0 | 0 | 0
2086 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | Material Requisition To Resource Division | 3422/MD | 25/11/2024 | 0 | Resource Division | 11.76 | 0 | 0 | 0
2087 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | QUOTATION MONEY FOR KASHIJORA WATER SUPPLY SCHEME,ZONE-II/I, T W - I ,[ RAMNAGAR ] JJM WORKS, SCHEME CODE SM/14492, KGP-I, APPLICATION NO 2004696766, REFERENCE ID 204284088, NIMPURA CCC, WBSEDCL | BP-2024-25-120 | 06/05/2024 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
2088 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | CERTIFIED THAT IT IS QUOTATION MONEY FOR KASHIJORA WATER SUPPLY SCHEME (SANKARACHAK) , MINI, ZONE-I , JJM WORKS, SCHEME CODE SM/14492, , APPLICATION NO 2004582819, REFERENCE ID 204206253, NIMPURA CCC, WBSEDCL | BP-2023-24-702 | 16/02/2024 | 0 | WBSEDCL | 0.12 | 0 | 0 | 0
2089 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | QUOTATION MONEY FOR KASHIJORA, ZONE-II/I, T W NO II [ BENAPURUR CHAITA ] WATER SUPPLY SCHEME, JJM WORKS, SCHEME CODE SM/14492, APPLICATION NO 2004890141, REFERENCE ID 204393532, NIMPURA CCC, WBSEDCL | C112429713000 | 25/11/2024 | 0 | WBSEDCL | 4.28 | 0 | 0 | 0
2090 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | QUOTATION MONEY FOR KASHIJORA WATER SUPPLY SCHEME ( SANKARCHAK ), MINI, ZONE-I JJM WORKS, SCHEME CODE SM/14492, APPLICATION NO 2004582819, REFERENCE ID 204206253, NIMPURA CCC, WBSEDCL |  | 24/04/2024 | 0 | WBSEDCL | 0.12 | 0 | 0 | 0
2091 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | KASHIJORA WATER SUPPLY SCHEME, ZONE I , T W NO 2 , JJM WORKS, SCHEME CODE SM/14492, APPLICATION NO 2004582759, REFERENCE ID 204223621, NIMPURA CCC, WBSEDCL | BP-2023-24-771 | 05/03/2024 | 0 | WBSEDCL | 3.29 | 0 | 0 | 0
2092 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | KASHIJORA WATER SUPPLY SCHEME, ZONE I , T W NO 1 , JJM WORKS, SCHEME CODE SM/14492, APPLICATION NO 2004582753, REFERENCE ID 204224605, NIMPURA CCC, WBSEDCL | BP-2023-24-770 | 04/03/2024 | 0 | WBSEDCL | 3.25 | 0 | 0 | 0
2093 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | Sinking of Tube wells, Construction of 250 CuM Capacity R.C.C Over Head Reservoirs (Over Raft Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (5415 nos.) including Two years O&M for AMBA (ZONE-I, II & III) & KASHIJORA (ZONE-I & II) Pipe W/S Scheme within Kharagpur-I Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | 2465/MD | 14/07/2023 | 808 | GOBINDA MAITY | 1571.51 | 0 | 0 | 42
2094 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | Supply and Installation of ( Dept. ) Submersible Pumping Machinery, Voltage Stabilizer ( Dept. ) , Chlorination System ( Dept. ) and Internal House Wiring and other allied works at Tube Well no 2 of Kashijora Mini Water Supply Scheme , Zone -II [ Block- Kharagpur-I ] under MMD, PHE Dte., Dist.- Paschim Medinipur. | 730/MMSD-I | 07/06/2024 | 365 | PURUSHOTTAM ENTERPRISE | 2.86 | 0 | 0 | 87
2095 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I and II) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. .(Part-II) | 935/W/MMD | 28/03/2023 | 900 | RISHAV ENTERPRISE | 5.98 | 0 | 0 | 80
2096 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 538/W/MMD | 20/03/2023 | 710 | SOUMEN ELECTRIC | 34.15 | 0 | 0 | 55
2097 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/14492 | New | Supply and Installation of ( Dept. ) Submersible Pumping Machinery, Voltage Stabilizer ( Dept. ) , Chlorination System ( Dept. ) and Internal House Wiring and other allied works at Tube Well no 1 of Kashijora Mini Water Supply Scheme , Zone -II [ Block- Kharagpur-I ] under MMD, PHE Dte., Dist.- Paschim Medinipur. | 732/MMSD-I | 07/06/2024 | 318 | M/S SREEJIT ENTERPRISE | 2.87 | 0 | 0 | 100
2098 | PASCHIM MEDINIPUR | Midnapore Division | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/16374 | New | Material Requisition To Resource Division | 194/MD | 16/01/2023 | 0 | Resource Division | 21.9 | 0 | 0 | 0
2099 | PASCHIM MEDINIPUR | Midnapore Mechanical | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/16374 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DHITPUR AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 837/W/MMD | 24/03/2023 | 180 | HARA PROSAD DAS | 23.73 | 0 | 0 | 70
2100 | PASCHIM MEDINIPUR | Midnapore Mechanical | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/16374 | New | Quotation for new power connection at Dhitpur water supply scheme T/W - I | BP-2023-24-623 | 07/02/2024 | 0 | WBSEDCL | 1.28 | 0 | 0 | 0
2101 | PASCHIM MEDINIPUR | Midnapore Mechanical | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/16374 | New | Quotation for new power connection at Dhitpur PWSS P/H- II , application no - 2004609048 , Ref id - 204222614 | BP-2023-24-776 | 06/03/2024 | 0 | WBSEDCL | 4.62 | 0 | 0 | 0
2102 | PASCHIM MEDINIPUR | Midnapore Division | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/16374 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, soil investigation, 300 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (2432 nos.) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Dhitpur & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 2144/MD | 08/06/2023 | 840 | M/S. EL-CON | 649.48 | 0 | 0 | 60
2103 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. , SM/16296 | Augmentation | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well for boosting purpose including FHTC, Valve chamber and other ancillary works of under Augmentation of Abasgarh W/S Scheme under Midnapore Division, PHE Dte. | 723/MD | 09/03/2023 | 35 | WATER LINK | 11.31 | 0 | 0 | 50
2104 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. , SM/16296 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Abasgarh PWSS within Midnapore Saar Block under Midnapore Division, P.H.E. Dte. | 531/MD | 21/03/2022 | 10 | GOBINDA MAITY | 2.26 | 0 | 0 | 100
2105 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. , SM/16296 | Augmentation | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Abasgarh water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | 428/MMSD-I | 24/04/2023 | 15 | SUJOY RANJAN BHOWMICK | 4.37 | 0 | 0 | 100
2106 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. , SM/16296 | Augmentation | Material Requisition To Resource Division | 1422/MD | 04/05/2023 | 0 | Resource Division | 18.38 | 0 | 0 | 0
2107 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. , SM/16296 | Augmentation | QUOTATION MONEY FOR T W NO 3 OF ABASHGARH WATER SUPPLY SCHEME [ REF- CONSUMER ID 203990474, UNDER RAJABAZAR CCC, WBSEDCL ] | BP-2023-24-43 | 19/05/2023 | 0 | WBSEDCL | 0.31 | 0 | 0 | 0
2108 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. , SM/16296 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. under JJM Program under MMD PHE Dte. | 904/W/MMD | 27/03/2023 | 900 | ECO ENTERPRISE | 10.78 | 0 | 0 | 40
2109 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Chaupenia PWSS in the District of Paschim Medinipur under JJM programme. , SM/17779 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Chaupenia PWSS in the District of Paschim Medinipur under JJM programme. under JJM Program under MMD PHE Dte. | 1057/W/MMD | 29/03/2023 | 180 | M/S EMMESS | 11.28 | 0 | 0 | 100
2110 | PASCHIM MEDINIPUR | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | Material Requisition To Resource Division | 1299/MD | 28/04/2023 | 0 | Resource Division | 72.43 | 0 | 0 | 0
2111 | PASCHIM MEDINIPUR | Midnapore Mechanical | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | Electric quotation bill for tw no-I of Sashabedia PWSS . (Ref ID-204061143). | BP-2023-24-182 | 11/08/2023 | 0 | WBSEDCL | 3.09 | 0 | 0 | 0
2112 | PASCHIM MEDINIPUR | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | Sinking of 4 (four) nos. 250 X 150 mm dia. X 180 mtr. Depth deep tube well by direct rotary method for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-VII] | 2426/MD | 13/07/2023 | 45 | MIDNAPUR PIPE CONCERN | 34.6 | 0 | 0 | 80
2113 | PASCHIM MEDINIPUR | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | Laying distribution of Pipe line, Construction of Pump House, Boundary wall and FHTC work (440 Nos.) for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-III] | 2484/MD | 17/07/2023 | 60 | MIDNAPUR PIPE CONCERN | 96.29 | 0 | 0 | 70
2114 | PASCHIM MEDINIPUR | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | Laying distribution of Pipe line and Accommodate FHTC (459 Nos.) work for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-V] | 975/MD | 10/04/2023 | 60 | J.K. BUILDERS | 77.87 | 0 | 0 | 100
2115 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | New Service connection charges. | 55/JMD | 08/02/2024 | 0 | WBSEDCL | 5.67 | 0 | 0 | 0
2116 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | New Service connection charges. | 56/JMD | 08/02/2024 | 0 | WBSEDCL | 5.67 | 0 | 0 | 0
2117 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | New Service connection charges. | 57/JMD | 08/02/2024 | 0 | WBSEDCL | 3.49 | 0 | 0 | 0
2118 | PASCHIM MEDINIPUR | Central Drilling | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2119 | PASCHIM MEDINIPUR | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | Laying distribution of Pipe line and Accommodate FHTC (440 Nos.) work for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-IV] | 2522/MD | 18/07/2023 | 590 | S.N ENTERPRISE | 66.39 | 0 | 0 | 80
2120 | PASCHIM MEDINIPUR | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | Laying distribution of Pipe line, Rising main, Construction of Pump House, Boundary wall, FHTC work (360 Nos.) with 2 years operation & maintenance for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-II] | 2808/MD | 07/08/2023 | 637 | CHANDAN ROY | 157.84 | 0 | 0 | 2
2121 | PASCHIM MEDINIPUR | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | Laying distribution of Pipe line, Construction of Pump House, Boundary wall and FHTC work (300 Nos.) for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-VI] | 3004/MD | 21/08/2023 | 838 | A.K. SIKDAR | 118.98 | 0 | 0 | 70
2122 | PASCHIM MEDINIPUR | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS , SM/18001 | New | Construction and Commissioning of 450 Cum Capacity (Intze type with Pile) Over Headed Reservoir, Soil Investigation, Construction of Pump House, Boundary wall & accommodate FHTC (600 Nos.) for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-I] | 831/MD | 15/03/2024 | 721 | SUNIL DULE | 183.79 | 0 | 0 | 30
2123 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18236 | New | Material Requisition To Resource Division | 202/MD | 16/01/2023 | 0 | Resource Division | 37.26 | 0 | 0 | 0
2124 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18236 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | 1495/W/MMD | 22/06/2023 | 180 | DEBJYOTI BASU | 25.25 | 0 | 0 | 80
2125 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18236 | New | Material Requisition To Resource Division | 3331/MD | 25/11/2024 | 0 | Resource Division | 15.69 | 0 | 0 | 0
2126 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18236 | New | New service connection for Bandipur W/S Scheme | 379/JMD | 30/09/2024 | 0 | WBSEDCL | 6.77 | 0 | 0 | 0
2127 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18236 | New | Laying distribution pipe line, Accommodate FHTC, Laying Rising main, Operation & Maintenance under JJM with allied work for Bandipur PWSS in Chandrakona-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 3902/MD | 27/09/2023 | 762 | M/S. D.K.H.CONSTRUCTION | 327.58 | 0 | 0 | 30
2128 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18236 | New | Sinking of 2 (Two) nos. 250 X 200 mm dia. X 190 mtr. depth deep tube well by direct rotary method for Head work site & 2nd tube well site of Bandipur PWSS with in Chandrakona- II block under Midnapore Division, P.H.E Dte. [PART-D] | 2424/MD | 13/07/2023 | 517 | MR GOUTAM GHOSH, | 20.39 | 0 | 0 | 100
2129 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kalaimuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17362 | Solarisation | Solarization of grid connected pumping installation at Kalaimuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 689/W/MMD | 23/03/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 6.26 | 0 | 0 | 0
2130 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Salbani PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17365 | Solarisation | Solarization of grid connected pumping installation at Salbani PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 697/W/MMD | 23/03/2023 | 180 | M/S EMMESS | 6.26 | 0 | 0 | 0
2131 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Kalshibhanga PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17749 | Solarisation | Solarization of grid connected pumping installation Kalshibhanga PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1051/W/MMD | 29/03/2023 | 180 | DIPALI CONSTRUCTION | 6.26 | 0 | 0 | 0
2132 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Nona Ragpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17368 | Solarisation | Solarization of grid connected pumping installation at Ragpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 701/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
2133 | PASCHIM MEDINIPUR | Midnapore Division | GOLEGRAM AND ITS ADJOINING MOUJAS PWSS , SM/17617 | New | Material Requisition To Resource Division | 1583/MD | 15/05/2023 | 0 | Resource Division | 27.82 | 0 | 0 | 0
2134 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOLEGRAM AND ITS ADJOINING MOUJAS PWSS , SM/17617 | New | Electrict quotation bill for TW-I of Golegram pwss (Ref Consumar ID-204391663),Application No-2004886425,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | C092442840754 | 27/09/2024 | 0 | WBSEDCL | 3.7 | 0 | 0 | 0
2135 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOLEGRAM AND ITS ADJOINING MOUJAS PWSS , SM/17617 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GOLEGRAM AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 1130/W/MMD | 12/04/2023 | 720 | P.K.ENGINEERING | 25.25 | 0 | 0 | 50
2136 | PASCHIM MEDINIPUR | Midnapore Division | GOLEGRAM AND ITS ADJOINING MOUJAS PWSS , SM/17617 | New | Construction of 350 Cum & 300 Cum Capacity R.C.C Over Head Reservoir (Intze type with solid raft) works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,209 Nos) including 2 years operation & maintenance For Golegram and Kanakpur Pipe water supply Scheme within Debra Block under Kharagpur Sub Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5060/MD | 26/10/2023 | 613 | IJABUL SEKH | 992.27 | 0 | 0 | 45
2137 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Nona Madhabchak PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17338 | Solarisation | Solarization of grid connected pumping installation at Nona Madhabchak PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 699/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
2138 | PASCHIM MEDINIPUR | Midnapore Division | SAMSARA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17568 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Samsara & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | 819/MD | 21/03/2023 | 20 | ENVIROTECH SOLUTIONS | 5.39 | 0 | 0 | 100
2139 | PASCHIM MEDINIPUR | Midnapore Division | SAMSARA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17568 | New | Continuation Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Samsara & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | 1116/MD | 09/06/2022 | 20 | ENVIROTECH SOLUTIONS | 2.4 | 0 | 0 | 100
2140 | PASCHIM MEDINIPUR | Midnapore Division | SAMSARA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17568 | New | Material Requisition To Resource Division | 1373/MD | 02/05/2023 | 0 | Resource Division | 27.23 | 0 | 0 | 0
2141 | PASCHIM MEDINIPUR | Midnapore Mechanical | SAMSARA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17568 | New | Electrict quotation bill for TW-I of Samsara pwss (Ref Consumar ID-204434263),Application No-2004944497,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | C112423562182 | 19/11/2024 | 0 | WBSEDCL | 3.42 | 0 | 0 | 0
2142 | PASCHIM MEDINIPUR | Midnapore Mechanical | SAMSARA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17568 | New | Electrict quotation bill for TW-II of Samsara pwss (Ref Consumar ID-204431250),Application No-2004944502,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | C112423562756 | 19/11/2024 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
2143 | PASCHIM MEDINIPUR | Midnapore Mechanical | SAMSARA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17568 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SAMSARA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION under JJM Program under MMD PHE Dte. | 1196/W/MMD | 25/04/2023 | 720 | DEBJYOTI BASU | 22.64 | 0 | 0 | 40
2144 | PASCHIM MEDINIPUR | Midnapore Division | SAMSARA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION , SM/17568 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 0 | 55
2145 | PASCHIM MEDINIPUR | Midnapore Division | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17572 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Sautia & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | 1112/MD | 09/06/2022 | 20 | ENVIROTECH SOLUTIONS | 1.49 | 0 | 0 | 100
2146 | PASCHIM MEDINIPUR | Midnapore Division | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17572 | New | Material Requisition To Resource Division | 2008/MD | 16/05/2023 | 0 | Resource Division | 27.68 | 0 | 0 | 0
2147 | PASCHIM MEDINIPUR | Midnapore Division | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17572 | New | Material Requisition To Resource Division | 1460 | 08/05/2023 | 0 | Resource Division | 10.52 | 0 | 0 | 0
2148 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17572 | New | Electrict quotation bill for TW-I of Sautia pwss (Zone-I) (Ref Consumar ID-204310821),Application No-2004741353,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | BP-2024-25-202 | 24/05/2024 | 0 | WBSEDCL | 4.52 | 0 | 0 | 0
2149 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17572 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 1198/W/MMD | 25/04/2023 | 720 | DEBJYOTI BASU | 22.77 | 0 | 0 | 40
2150 | PASCHIM MEDINIPUR | Midnapore Division | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17572 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 0 | 55
2151 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Khanjapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17307 | Solarisation | Solarization of grid connected pumping installation at Khanjapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 693/W/MMD | 23/03/2023 | 180 | A.K. INDUSTRIES | 12.52 | 0 | 0 | 75
2152 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/18191 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 617/W/MMD | 20/03/2023 | 180 | JAGANNATH ENTERPRISE | 21.58 | 0 | 0 | 0
2153 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/18191 | Augmentation | Laying distribution pipe under JJM with allied work for Augmentation of Amrakuchi & its adjoining mouzas W/S Scheme in Keshpur block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 2623/MD | 24/07/2023 | 45 | M/S. BLUE BIRD | 21.94 | 0 | 0 | 71
2154 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/18191 | Augmentation | Preparation of D.P.R {Consultancy work} in connection with the Functional House Hold Tap connection for Rejuvenation /Augmentation of existing AMRAKUCHI PWSS within Keshpur Block under Midnapore Division PHE Dte. (SL No-01) | 461/AE/MSSD | 05/08/2022 | 15 | ROY DESIGN & INFRASTRUCTURE | 2.15 | 0 | 0 | 100
2155 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/18191 | Augmentation | Material Requisition To Resource Division | 377/MD | 03/02/2023 | 0 | Resource Division | 27.13 | 0 | 0 | 0
2156 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/18191 | Augmentation | Sinking of Tube well, Laying distribution pipe line & accommodate FHTC (118 Nos.) including 2 years O&M under JJM with allied work for Augmentation of Amrakuchi & its adjoining mouzas W/S Scheme in Keshpur block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 1356/MD | 02/05/2023 | 60 | PULLOCK KUMAR GHOSH | 54.56 | 0 | 0 | 85
2157 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/18191 | Augmentation | ELECTRIC QUOTATION BILL FOR ADDITIONAL TW NO-III of AMRAKUCHI PWSS. REF CONSUMER ID-204269829, APPLICATION NO-2004675304, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-73 | 24/04/2024 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
2158 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/18191 | Augmentation | Sinking of Tube well, Rising main, Pump House, Boundary wall, Soil investigation, Construction of 100 CuM OHR (Torch type with solid raft) & Accommodate FHTC (250 Nos.) under JJM with allied work for Augmentation of Amrakuchi & its adjoining mouzas W/S Scheme in Keshpur block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 3043/MD | 25/09/2024 | 540 | WATER LINK | 114.3 | 0 | 0 | 30
2159 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/18191 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-II) | 1121/W/MMD | 12/04/2023 | 696 | S.S.GHORAI | 22.89 | 0 | 0 | 20
2160 | PASCHIM MEDINIPUR | Midnapore Division | Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17398 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Borai & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | 1114/MD | 09/06/2022 | 20 | ENVIROTECH SOLUTIONS | 0.57 | 0 | 0 | 100
2161 | PASCHIM MEDINIPUR | Midnapore Division | Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17398 | New | Material Requisition To Resource Division | 2007/MD | 16/05/2023 | 0 | Resource Division | 55.28 | 0 | 0 | 0
2162 | PASCHIM MEDINIPUR | Midnapore Division | Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17398 | New | Material Requisition To Resource Division | 1465 | 08/05/2023 | 0 | Resource Division | 37.96 | 0 | 0 | 0
2163 | PASCHIM MEDINIPUR | Midnapore Mechanical | Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17398 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 1189/W/MMD | 25/04/2023 | 180 | RSA ENTERPRISE | 23.01 | 0 | 0 | 0
2164 | PASCHIM MEDINIPUR | Midnapore Division | Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17398 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 0 | 55
2165 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chandrakona Road, Zone-I& Zone-II PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17330 | Solarisation | Solarization of grid connected pumping installation at Chandrakona Road, Zone-I& Zone-II PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 683/W/MMD | 23/03/2023 | 180 | M/S EMMESS | 12.52 | 0 | 0 | 0
2166 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Khagragerya PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17414 | Solarisation | Solarization of grid connected pumping installation at Khagragerya PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 675/W/MMD | 23/03/2023 | 180 | M/S B.M. ELECTRICAL | 6.26 | 0 | 0 | 90
2167 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Khagragerya PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17414 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going solarisation / rejuvenation as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 716/MMSD-I | 07/06/2024 | 15 | MUKHERJEE ART CENTRE | 1.93 | 0 | 0 | 100
2168 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Chakmakrampur PWSS in the District of Paschim Medinipur under JJM programme. , SM/17818 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Chakmakrampur PWSS in the District of Paschim Medinipur under JJM programme. under JJM Program under MMD PHE Dte. | 1068/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 11.02 | 0 | 0 | 70
2169 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Chakmakrampur PWSS in the District of Paschim Medinipur under JJM programme. , SM/17818 | Augmentation | Supply and installation of sign board for depicting the scheme details of different on-going solarisation / rejuvenation as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 716/MMSD-I | 07/06/2024 | 15 | MUKHERJEE ART CENTRE | 1.93 | 0 | 0 | 100
2170 | PASCHIM MEDINIPUR | Midnapore Division | GANGANI AND ADJOINING MOUJAS PWSS , SM/19099 | New | Material Requisition To Resource Division | 1194/MD | 26/04/2023 | 0 | Resource Division | 115 | 0 | 0 | 0
2171 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GANGANI AND ADJOINING MOUJAS PWSS , SM/19099 | New | New service connection charges at Gangani TW-II | 222/JMD | 21/06/2024 | 0 | WBSEDCL | 3.22 | 0 | 0 | 0
2172 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GANGANI AND ADJOINING MOUJAS PWSS , SM/19099 | New | New service connection charges at Gangani TW-I | 221/JMD | 21/06/2024 | 0 | WBSEDCL | 4.57 | 0 | 0 | 0
2173 | PASCHIM MEDINIPUR | Central Drilling | GANGANI AND ADJOINING MOUJAS PWSS , SM/19099 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2174 | PASCHIM MEDINIPUR | Midnapore Division | AKRA MARKANDAPUR PWSS , SM/17003 | New | Material Requisition To Resource Division | 1372/MD | 02/05/2023 | 0 | Resource Division | 1.57 | 0 | 0 | 0
2175 | PASCHIM MEDINIPUR | Midnapore Mechanical | AKRA MARKANDAPUR PWSS , SM/17003 | New | Quotation for new power connection at Akramarkandapur PWSS P/H- I , application no - 2004609042 , Ref id - 204222613 | BP-2023-24-775 | 06/03/2024 | 0 | WBSEDCL | 4.16 | 0 | 0 | 0
2176 | PASCHIM MEDINIPUR | Midnapore Mechanical | AKRA MARKANDAPUR PWSS , SM/17003 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER Kharagpur - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | 1187/W/MMD | 25/04/2023 | 180 | A G ENTERPRISE | 40.67 | 0 | 0 | 40
2177 | PASCHIM MEDINIPUR | Midnapore Division | AKRA MARKANDAPUR PWSS , SM/17003 | New | Laying of uPVC distribution system, Rising Main, Construction of supporting structure of 10 Cum Water Tank, Switch Room cum Chlorine Room & Accommodate FHTC (124 Nos.) under JJM with allied work & 1 year O&M for Arka Markandapur Mini Water Supply Scheme in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 2487/MD | 17/07/2023 | 992 | A R ENTERPRISE | 36.71 | 0 | 0 | 60
2178 | PASCHIM MEDINIPUR | Midnapore Division | CHAK PRAYAG AND ITS ADJOINING MOUJAS PWSS , SM/17615 | New | Material Requisition To Resource Division | 1409 | 04/05/2023 | 0 | Resource Division | 24.77 | 0 | 0 | 0
2179 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAK PRAYAG AND ITS ADJOINING MOUJAS PWSS , SM/17615 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAK PRAYAG AND ITS ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 532/W/MMD | 20/03/2023 | 180 | P.K.ENGINEERING | 22.78 | 0 | 0 | 40
2180 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAK PRAYAG AND ITS ADJOINING MOUJAS PWSS , SM/17615 | New | Electrict quotation bill for TW-I of Chak Prayag pwss (Ref Consumar ID-204391664),Application No-2004886442,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | C092443136780 | 27/09/2024 | 0 | WBSEDCL | 3.14 | 0 | 0 | 0
2181 | PASCHIM MEDINIPUR | Midnapore Division | CHAK PRAYAG AND ITS ADJOINING MOUJAS PWSS , SM/17615 | New | Construction of 200 Cum & 300 Cum Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,806 Nos.) including 2 years operation & maintenance For Bakalsabakram, Bhagabanpur and Chak Prayag Pipe water supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5382/MD | 04/12/2023 | 574 | M/S. KAMAK ENGINEERS AND CO. | 1277.59 | 0 | 0 | 50
2182 | PASCHIM MEDINIPUR | Midnapore Division | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17620 | New | Material Requisition To Resource Division | 4060/MD | 12/10/2023 | 0 | Resource Division | 29.73 | 0 | 0 | 0
2183 | PASCHIM MEDINIPUR | Midnapore Division | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17620 | New | Material Requisition To Resource Division | 2108/MD | 08/07/2024 | 0 | Resource Division | 6.49 | 0 | 0 | 0
2184 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17620 | New | Electric quotation bill for Gobindapur pwss at pump house no-II (Consumar Id-204182972) | BP-2023-24-537 | 11/01/2024 | 0 | WBSEDCL | 3 | 0 | 0 | 0
2185 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17620 | New | Electrict quation bill for gobindapur pwss at pump house no-I (Consumar Id-204182978) | BP-2023-24-536 | 11/01/2024 | 0 | WBSEDCL | 3.28 | 0 | 0 | 0
2186 | PASCHIM MEDINIPUR | Midnapore Division | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17620 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House, Boundary Wall, laying of Rising Main & Providing Functional Household Tap Connection (4740 Nos) including 2 years Operation & Maintenance For Dingal, Duan and Gobindapur Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | 2826/MD | 07/08/2023 | 785 | GOBINDA MAITY | 1375.06 | 0 | 0 | 74
2187 | PASCHIM MEDINIPUR | Midnapore Mechanical | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/17620 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 483/W/MMD | 20/03/2023 | 864 | M/S. P.P.ELECTRICALS | 22.95 | 0 | 0 | 90
2188 | PASCHIM MEDINIPUR | Midnapore Division | SINNIBAR PIPED WATER SUPPLY SCHEME , SM/18527 | New | Material Requisition To Resource Division | 104/MD | 10/01/2023 | 0 | Resource Division | 22.51 | 0 | 0 | 0
2189 | PASCHIM MEDINIPUR | Midnapore Division | SINNIBAR PIPED WATER SUPPLY SCHEME , SM/18527 | New | Material Requisition To Resource Division | 3377/MD | 25/11/2024 | 0 | Resource Division | 21.04 | 0 | 0 | 0
2190 | PASCHIM MEDINIPUR | Midnapore Mechanical | SINNIBAR PIPED WATER SUPPLY SCHEME , SM/18527 | New | Electric quotation bill for TW No-I of SINNIBAR PWSS (Ref Consumer ID-204182338) | BP-2023-24-562 | 16/01/2024 | 0 | WBSEDCL | 3.23 | 0 | 0 | 0
2191 | PASCHIM MEDINIPUR | Midnapore Mechanical | SINNIBAR PIPED WATER SUPPLY SCHEME , SM/18527 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF SINNIBAR PWSS. REF CONSUMER ID-204211984, APPLICATION NO-2004590238, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-418 | 15/07/2024 | 0 | WBSEDCL | 4.67 | 0 | 0 | 0
2192 | PASCHIM MEDINIPUR | Midnapore Mechanical | SINNIBAR PIPED WATER SUPPLY SCHEME , SM/18527 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SINNIBAR PIPED WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | 1688/W/MMD | 04/08/2023 | 804 | SOUMEN ELECTRIC | 27.37 | 0 | 0 | 20
2193 | PASCHIM MEDINIPUR | Midnapore Division | SINNIBAR PIPED WATER SUPPLY SCHEME , SM/18527 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,416 nos.) under JJM with allied work for Sinnibar PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 3232/MD | 11/09/2023 | 848 | M/S. A.R. ENTERPRISE. | 917.01 | 0 | 0 | 40
2194 | PASCHIM MEDINIPUR | Midnapore Division | SINNIBAR PIPED WATER SUPPLY SCHEME , SM/18527 | New | Laying of rising main & interconnection for Sinnibar & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 675 Mtr.) | 61/MD | 07/01/2025 | 45 | A-PLUS | 6.58 | 0 | 0 | 0
2195 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19046 | New | Material Requisition To Resource Division | 532/MD | 21/02/2023 | 0 | Resource Division | 52.71 | 0 | 0 | 0
2196 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19046 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | 3096/W/MMD | 29/11/2023 | 180 | SHREE BISHNU CONSTRUCTION | 25.25 | 0 | 0 | 80
2197 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19046 | New | New Service connection charges. | 88/JMD | 22/03/2024 | 0 | WBSEDCL | 7.03 | 0 | 0 | 0
2198 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19046 | New | Quotation for new service connection at Jhakra T/W-II water supply scheme. | 305/JMD | 14/08/2024 | 0 | WBSEDCL | 8.95 | 0 | 0 | 0
2199 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19046 | New | Laying distribution pipeline, Rising main, Accommodate FHTC (1140 Nos.) including 2yrs. O & M under JJM with allied work for Jhakra PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 5562/MD | 26/12/2023 | 756 | M/S. D.K.H.CONSTRUCTION | 388.07 | 0 | 0 | 5
2200 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19046 | New | Construction of RCC OHR (400 CuM), Soil investigation, Boundary wall & Accommodate FHTC (1431 Nos.) under JJM with allied work for Jhakra PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 826/MD | 15/03/2024 | 720 | M/S R.N. ENTERPRISE | 233.69 | 0 | 0 | 30
2201 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19046 | New | Laying additional pipeline regarding balance work of distribution network for Jhakra & its adjoining mouza W/S Scheme under Chandrakona-II block within Midnapore Division, PHE Dte. | 481/MD | 13/02/2025 | 150 | NIMAI HAZRA | 37.52 | 0 | 0 | 0
2202 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19046 | New | Sinking of Tube well & Construction of Pump House under JJM with allied work for Jhakra PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 5345/MD | 29/11/2023 | 300 | ANNAPURNA TUBEWELL WORKS | 31.46 | 0 | 0 | 10
2203 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19047 | New | Material Requisition To Resource Division | 1457/MD | 08/05/2023 | 0 | Resource Division | 16.87 | 0 | 0 | 0
2204 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19047 | New | Material Requisition To Resource Division | 533/MD | 21/02/2023 | 0 | Resource Division | 57.85 | 0 | 0 | 0
2205 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19047 | New | Sinking of Tube well, Construction of Pump House & Accommodate FHTC (910 Nos.) under JJM with allied work for Kuapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 5326/MD | 28/11/2023 | 60 | PULLOCK KUMAR GHOSH | 83.89 | 0 | 0 | 30
2206 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19047 | New | Construction of RCC OHR (450 CuM), Soil investigation, Boundary wall & Accommodate FHTC (919 Nos.) under JJM with allied work for Kuapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 1836/MD | 12/06/2024 | 180 | S.N ENTERPRISE | 216.01 | 0 | 0 | 0
2207 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19047 | New | New service connection for Kuapur W/S Scheme. | 380/JMD | 30/09/2024 | 0 | WBSEDCL | 3.81 | 0 | 0 | 0
2208 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19047 | New | Laying distribution pipeline, Rising main, Accommodate FHTC (910 Nos.) including 2yrs. O & M under JJM with allied work for Kuapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 5327/MD | 28/11/2023 | 759 | M/S. D.K.H.CONSTRUCTION | 367.84 | 0 | 0 | 40
2209 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19047 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | 3095/W/MMD | 29/11/2023 | 550 | JAL PRAVAHIKA PVT. LTD. | 25.24 | 0 | 0 | 90
2210 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19047 | New | Hiring of Inspection vehicle for Jal Jeevan Mission on an ¿as and when required¿ basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of 06 (Six months) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Ghatal Sub-Division, P.H.E Dte. | 1687/AE/GSD | 09/12/2024 | 182 | HIRAK KUMAR GHOSH | 0.85 | 0 | 0 | 0
2211 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19047 | New | Hiring of Inspection vehicle for Jal Jeevan Mission on an ¿as and when required¿ basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of 06 (Six months) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Ghatal Sub-Division, P.H.E Dte. | 1220/AE/GSD | 10/06/2024 | 183 | HIRAK KUMAR GHOSH | 0.76 | 0 | 0 | 0
2212 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. , SM/19047 | New | Continuation work order for Hiring of Inspection vehicle for Jal Jeevan Mission on an ¿as and when required¿ basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of 06 (Six months) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Ghatal Sub-Division, P.H.E Dte. | 962/AE/GSD | 09/12/2025 | 159 | HIRAK KUMAR GHOSH | 0.9 | 0 | 0 | 0
2213 | PASCHIM MEDINIPUR | Midnapore Division | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18586 | New | Material Requisition To Resource Division | 108/MD | 10/01/2023 | 0 | Resource Division | 103.9 | 0 | 0 | 0
2214 | PASCHIM MEDINIPUR | Midnapore Division | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18586 | New | Material Requisition To Resource Division | 3337/MD | 25/11/2024 | 0 | Resource Division | 14.38 | 0 | 0 | 0
2215 | PASCHIM MEDINIPUR | Midnapore Mechanical | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18586 | New | QUOTATION MONEY FOR MAKARAMPUR WATER SUPPLY SCHEME , T W - II , JJM WORKS, SCHEME CODE SM/18586, APPLICATION NO 2004696147, REFERENCE ID 204284316, DASPUR CCC, WBSEDCL | BP-2024-25-118 | 06/05/2024 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
2216 | PASCHIM MEDINIPUR | Midnapore Mechanical | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18586 | New | QUOTATION MONEY FOR MAKARAMPUR WATER SUPPLY SCHEME , T W - I , JJM WORKS, SCHEME CODE SM/18586, APPLICATION NO 2004696153, REFERENCE ID 204284318, DASPUR CCC, WBSEDCL | BP-2024-25-119 | 06/05/2024 | 0 | WBSEDCL | 5.84 | 0 | 0 | 0
2217 | PASCHIM MEDINIPUR | Midnapore Mechanical | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18586 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 1721/W/MMD | 09/08/2023 | 754 | S.G.TECHNICAL SERVICE | 23 | 0 | 0 | 85
2218 | PASCHIM MEDINIPUR | Midnapore Division | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18586 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 450 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,335 nos.) under JJM with allied work for Makarampur PWSS in Daspur- I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 5090/MD | 30/10/2023 | 875 | SWACH ENVIRONMENT PRIVATE LIMITED | 733.83 | 0 | 0 | 55
2219 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Tararui PWSS , SM/08220 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Tararui W/S Scheme in the District of Paschim Medinipore. | BP-2022-23-345 | 01/02/2023 | 0 | DIPAK KUMAR BAKLY | 1.54 | 0 | 0 | 0
2220 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Tararui PWSS , SM/08220 | Retrofitting | Laying of pipe line at Tararui East (Nimapada), Tararui Paschim (Ghosh Para) for supporting FHTC works of Tararui and its adjoining mouza W/S Scheme within Kharagpur Sub Division under Midnapore Division, PHE Dte. | 455/RWS/MID | 10/08/2023 | 30 | ASMA CONSTRUCTION | 1.22 | 0 | 0 | 100
2221 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Tararui PWSS , SM/08220 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Trarui PWSS, Block :- Dantan-I in the District of Paschim Medinipur. | 309/MD | 22/02/2021 | 35 | DIPAK KUMAR BAKLY | 74.94 | 25.66 | 37.25 | 98
2222 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Tararui PWSS , SM/08220 | Retrofitting | Sinking of 150 X 100 mm dia. X 150 mtr. Depth Rig bored Tube wells for proposed additionally (boosting) to existing Tararui W/S Scheme, Dantan-I Block under Midnapore Division, P.H.E. Dte. | 2490/MD | 17/07/2023 | 15 | M/S BAKLY CONSTRUCTION | 5.91 | 0 | 0 | 80
2223 | PASCHIM MEDINIPUR | Midnapore Division | CHOTA TARA AND ADJOINING MOUJAS PWSS , SM/18619 | New | Material Requisition To Resource Division | 1218/MD | 27/04/2023 | 0 | Resource Division | 76.55 | 0 | 0 | 0
2224 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | CHOTA TARA AND ADJOINING MOUJAS PWSS , SM/18619 | New | New Service connection charges. | 197/JMD | 14/06/2024 | 0 | WBSEDCL | 10.09 | 0 | 0 | 0
2225 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | CHOTA TARA AND ADJOINING MOUJAS PWSS , SM/18619 | New | New Service connection charges. | 194/JMD | 14/06/2024 | 0 | WBSEDCL | 5.62 | 0 | 0 | 0
2226 | PASCHIM MEDINIPUR | Central Drilling | CHOTA TARA AND ADJOINING MOUJAS PWSS , SM/18619 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2227 | PASCHIM MEDINIPUR | Central Drilling | CHOTA TARA AND ADJOINING MOUJAS PWSS , SM/18619 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2228 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME , SM/14506 | New | Electric Quotation bill for Tw No-I of Khasjangal water supply scheme. (ref Consumer ID-204109026) | BP-2023-24-330 | 03/11/2023 | 0 | WBSEDCL | 2.83 | 0 | 0 | 0
2229 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME , SM/14506 | New | Electric Quotation bill for Tw no-II of Khasjangal water supply scheme.(Ref Consumer ID-204109024) | BP-2023-24-331 | 03/11/2023 | 0 | WBSEDCL | 3.58 | 0 | 0 | 0
2230 | PASCHIM MEDINIPUR | Midnapore Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME , SM/14506 | New | Material Requisition To Resource Division | 3378/MD | 25/11/2024 | 0 | Resource Division | 12.14 | 0 | 0 | 0
2231 | PASCHIM MEDINIPUR | Midnapore Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME , SM/14506 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 0 | 75
2232 | PASCHIM MEDINIPUR | Midnapore Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME , SM/14506 | New | Laying of rising main & interconnection for Khas Jangal & its adjoining mouzas PWSS, Block - Keshpur, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Length = 420 Mtr.) | 730/MD | 18/03/2025 | 45 | MALLICK ENTERPRISE | 5.4 | 0 | 0 | 0
2233 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME , SM/14506 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHAS JANGAL PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | 495/W/MMD | 20/03/2023 | 1019 | M/S MANABESH ROY | 22.91 | 0 | 0 | 25
2234 | PASCHIM MEDINIPUR | Midnapore Division | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18540 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Tatarpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | 1269/MD | 23/06/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.39 | 0 | 0 | 100
2235 | PASCHIM MEDINIPUR | Midnapore Division | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18540 | New | Material Requisition To Resource Division | 534/MD | 21/02/2023 | 0 | Resource Division | 239.55 | 0 | 0 | 0
2236 | PASCHIM MEDINIPUR | Midnapore Division | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18540 | New | Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 700 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,529 nos.) under JJM with allied work for Tatarpur PWSS in Daspur -I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 741/MD | 13/03/2024 | 361 | KHAN ENTERPRISE | 820.87 | 0 | 0 | 35
2237 | PASCHIM MEDINIPUR | Midnapore Division | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18540 | New | Sinking of Three nos. 250 X 150 mm dia. X 200 mtr. Depth deep tube well by direct rotary method under JJM with allied work for Tatarpur PWSS in Daspur-I block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 2737/MD | 01/08/2023 | 30 | SAJAL JANA | 35.06 | 0 | 0 | 100
2238 | PASCHIM MEDINIPUR | Midnapore Mechanical | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18540 | New | QUOTATION MONEY FOR TATARPUR WATER SUPPLY SCHEME, T W - II, JJM WORKS, SCHEME CODE SM/18540, APPLICATION NO 2004696073, REFERENCE ID 204284332, DASPUR CCC, WBSEDCL | BP-2024-25-122 | 06/05/2024 | 0 | WBSEDCL | 3.49 | 0 | 0 | 0
2239 | PASCHIM MEDINIPUR | Midnapore Mechanical | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18540 | New | QUOTATION MONEY FOR TATARPUR WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/18540, APPLICATION NO 2004696081, REFERENCE ID 2204284306, DASPUR CCC, WBSEDCL | BP-2024-25-121 | 06/05/2024 | 0 | WBSEDCL | 4.33 | 0 | 0 | 0
2240 | PASCHIM MEDINIPUR | Midnapore Mechanical | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18540 | New | QUOTATION MONEY FOR TATARPUR WATER SUPPLY SCHEME, T W - I, JJM WORKS, SCHEME CODE SM/18540, APPLICATION NO 2004700117, REFERENCE ID 204286354, DASPUR CCC, WBSEDCL | BP-2024-25-159 | 13/05/2024 | 0 | WBSEDCL | 7.37 | 0 | 0 | 0
2241 | PASCHIM MEDINIPUR | Midnapore Mechanical | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18540 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER DASPUR - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTEunder JJM Program under MMD PHE Dte. | 1694/W/MMD | 04/08/2023 | 759 | A G ENTERPRISE | 78.38 | 0 | 0 | 20
2242 | PASCHIM MEDINIPUR | Midnapore Mechanical | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18540 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
2243 | PASCHIM MEDINIPUR | Midnapore Mechanical | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS , SM/18524 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DHARMA PUR AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | 1680/W/MMD | 04/08/2023 | 180 | SUBHASIS ROY | 27.34 | 0 | 0 | 0
2244 | PASCHIM MEDINIPUR | Midnapore Division | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS , SM/18524 | New | Material Requisition To Resource Division | 100/MD | 10/01/2023 | 0 | Resource Division | 19.61 | 0 | 0 | 0
2245 | PASCHIM MEDINIPUR | Midnapore Division | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS , SM/18524 | New | Material Requisition To Resource Division | 3374/MD | 25/11/2024 | 0 | Resource Division | 17.55 | 0 | 0 | 0
2246 | PASCHIM MEDINIPUR | Midnapore Mechanical | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS , SM/18524 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of DHARMAPUR PWSS. REF CONSUMER ID-204188704, APPLICATION NO-2004559827, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-700 | 16/02/2024 | 0 | WBSEDCL | 3.6 | 0 | 0 | 0
2247 | PASCHIM MEDINIPUR | Midnapore Mechanical | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS , SM/18524 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of DHARMAPUR PWSS. REF CONSUMER ID-204240653, APPLICATION NO-2004634438, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPEERKUAI CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-847 | 14/03/2024 | 0 | WBSEDCL | 7.59 | 0 | 0 | 0
2248 | PASCHIM MEDINIPUR | Midnapore Division | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS , SM/18524 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,760 nos.) under JJM with allied work for Dharmmapur PWSS in Keshpur Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 3040/MD | 22/08/2023 | 900 | BANERJEE CONSTRUCTION | 939.5 | 0 | 0 | 28
2249 | PASCHIM MEDINIPUR | Midnapore Mechanical | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS , SM/18524 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0 | 0 | 50
2250 | PASCHIM MEDINIPUR | Midnapore Division | RERIPUR AND ADJ0INING MOUJAS PWSS , SM/18530 | New | Material Requisition To Resource Division | 1480 | 10/05/2023 | 0 | Resource Division | 54.64 | 0 | 0 | 0
2251 | PASCHIM MEDINIPUR | Midnapore Mechanical | RERIPUR AND ADJ0INING MOUJAS PWSS , SM/18530 | New | Quotation for new power connection at Reripur PWSS P/H- II , application no - 2004590055 , Ref id - 204211393 | BP-2023-24-785 | 06/03/2024 | 0 | WBSEDCL | 3.81 | 0 | 0 | 0
2252 | PASCHIM MEDINIPUR | Midnapore Mechanical | RERIPUR AND ADJ0INING MOUJAS PWSS , SM/18530 | New | Quotation for new power connection at Reripur PWSS P/H- I , application no - 2004590029 , Ref id - 204211394 | BP-2023-24-784 | 06/03/2024 | 0 | WBSEDCL | 2.61 | 0 | 0 | 0
2253 | PASCHIM MEDINIPUR | Central Drilling | RERIPUR AND ADJ0INING MOUJAS PWSS , SM/18530 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2254 | PASCHIM MEDINIPUR | Midnapore Division | RERIPUR AND ADJ0INING MOUJAS PWSS , SM/18530 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
2255 | PASCHIM MEDINIPUR | Midnapore Division | KUSUMDAHARI PIPED WATER SUPPLY SCHEME , SM/18531 | New | Material Requisition To Resource Division | 3375/MD | 25/11/2024 | 0 | Resource Division | 11.51 | 0 | 0 | 0
2256 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUSUMDAHARI PIPED WATER SUPPLY SCHEME , SM/18531 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of KUSUMDAHARI PWSS. REF CONSUMER ID-204269085, APPLICATION NO-2004675279, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-77 | 24/04/2024 | 0 | WBSEDCL | 4.8 | 0 | 0 | 0
2257 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUSUMDAHARI PIPED WATER SUPPLY SCHEME , SM/18531 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of KUSUMDAHARI PWSS. REF CONSUMER ID-204269092, APPLICATION NO-2004675269, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-76 | 24/04/2024 | 0 | WBSEDCL | 3.88 | 0 | 0 | 0
2258 | PASCHIM MEDINIPUR | Midnapore Division | KUSUMDAHARI PIPED WATER SUPPLY SCHEME , SM/18531 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 0 | 75
2259 | PASCHIM MEDINIPUR | Midnapore Division | KUSUMDAHARI PIPED WATER SUPPLY SCHEME , SM/18531 | New | Laying of rising main & interconnection for Kusumdahari & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 560 Mtr.) | 196/MD | 17/01/2025 | 45 | M/S. S.S. ENTERPRISE | 6.2 | 0 | 0 | 0
2260 | PASCHIM MEDINIPUR | Midnapore Division | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/18507 | New | Material Requisition To Resource Division | 1587/MD | 15/05/2023 | 0 | Resource Division | 70.34 | 0 | 0 | 0
2261 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/18507 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME.under JJM Program under MMD PHE Dte. | 1685/W/MMD | 04/08/2023 | 180 | S.K.ENTERPRISE | 25.26 | 0 | 0 | 50
2262 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/18507 | New | Quotation for new power connection at Barbasi T/W - I Within Khargpur - II Block, Application No - 2004975141 , Ref ID - 204452540 | C122403004364 | 04/12/2024 | 0 | WBSEDCL | 3.36 | 0 | 0 | 0
2263 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/18507 | New | Quotation for new power connection at Barbasi T/W - II Within Khargpur - II Block, Application No - 2004970379 , Ref ID - 204449425 | C122403004056 | 04/12/2024 | 0 | WBSEDCL | 3.06 | 0 | 0 | 0
2264 | PASCHIM MEDINIPUR | Midnapore Division | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/18507 | New | Sinking of Tube wells, Construction of 400 CuM Capacity R.C.C Over Head Reservoirs (Over Raft / Pile Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (6,875 Nos.) for Jagannathchak & Barbasi Pipe W/S Scheme including 2 years O&M within Kharagpur-II Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | 3101/MD | 25/08/2023 | 772 | GOBINDA MAITY | 1932.69 | 0 | 0 | 25
2265 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Salboni & 1 No. PWSS within Garhbeta-III Block , SM/06935 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443116 | 31/05/2021 | 0 | SUBRATA CHAKRABORTY | 0.05 | 0 | 0 | 0
2266 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Salboni & 1 No. PWSS within Garhbeta-III Block , SM/06935 | Retrofitting | FHTC Data entry | 8443122 | 23/08/2021 | 0 | SANDIP MANNA | 0.02 | 0 | 0 | 0
2267 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Salboni & 1 No. PWSS within Garhbeta-III Block , SM/06935 | Retrofitting | FHTC Data entry | 8443122 | 23/08/2021 | 0 | ANIRBAN CHAKRABORTY | 0.03 | 0 | 0 | 0
2268 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Salboni & 1 No. PWSS within Garhbeta-III Block , SM/06935 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443116 | 31/05/2021 | 0 | SIDDHESWAR BAG | 0.12 | 0 | 0 | 0
2269 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Salboni & 1 No. PWSS within Garhbeta-III Block , SM/06935 | Retrofitting | FHTC Data entry | 8443122 | 23/08/2021 | 0 | TANMOY BERA | 0.04 | 0 | 0 | 0
2270 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Salboni & 1 No. PWSS within Garhbeta-III Block , SM/06935 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443116 | 31/05/2021 | 0 | MANABENDAN DAS | 0.08 | 0 | 0 | 0
2271 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Salboni & 1 No. PWSS within Garhbeta-III Block , SM/06935 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443116 | 31/05/2021 | 0 | PAPPU SHAW | 0.09 | 0 | 0 | 0
2272 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Salboni & 1 No. PWSS within Garhbeta-III Block , SM/06935 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Tilabani W/S Scheme, Block: - Salboni, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1428/MD | 26/11/2020 | 180 | M/S. CARE | 30.62 | 17.61 | 57.5 | 0
2273 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Salboni & 1 No. PWSS within Garhbeta-III Block , SM/06935 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Raskundu W/S Scheme, Block: - Garhbeta-III, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1427/MD | 26/11/2020 | 180 | M/S. EL-CON | 40.7 | 36.19 | 100 | 0
2274 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS , SM/06898 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Maliara W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | M/S. EL-CON | 27.28 | 0 | 0 | 0
2275 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS , SM/06898 | Retrofitting | Sinking of One no Additional Rig bored Tube Well 150 X 100 mm dia. X 120 Mtr. Depth for Maliara Pipe W/S Scheme under Midnapur Sadar Sub Division Within Midnapore Division, PHE Dte. (SL No-01) | 464./AE/MSSD | 08/08/2022 | 10 | HIRAK KUMAR GHOSH | 4.74 | 0 | 0 | 0
2276 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS , SM/06898 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Maliara W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1426/MD | 26/11/2020 | 180 | M/S. EL-CON | 40.92 | 25.45 | 62.19 | 0
2277 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS , SM/06898 | Retrofitting | Additional Laying of Distribution pipe line at (Kalgunj ,Madhypara, Gourangapally & other different left out area) within Maliara Pipe Water Supply Scheme under Medinipore Sadar Block within Midnapore Division ,PHE Dte. (SL No-01) | 481/AE/MSSD | 08/08/2023 | 10 | HIRAK KUMAR GHOSH | 4.18 | 0 | 0 | 100
2278 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS , SM/06898 | Retrofitting | Continuation for the work of "Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre , Health Care Institution etc" under Midnapur Division,PHE Dte. for the period of 03 months (from 01.04.2022 to 30.06.2022) | 147/AE/MSSD | 28/03/2022 | 3 | PULLOCK KUMAR GHOSH | 1.52 | 0 | 0 | 0
2279 | PASCHIM MEDINIPUR | Midnapore Mechanical | Retrofitting to accomodate FHTC under JJM in Maliara PWSS , SM/06898 | Retrofitting | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Maliara water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | 1345/MMSD-I | 30/12/2022 | 15 | P.K.ENGINEERING | 4.37 | 0 | 0 | 100
2280 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS , SM/06898 | Retrofitting | Electric Bill of WBSEDCL. | BP-2022-23-683 | 09/03/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.19 | 0 | 0 | 0
2281 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS , SM/06898 | Retrofitting | Quotation as per WBSEDCL procedure-A (2010) electric quotation bill. | BP-2022-23-683 | 09/03/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.19 | 0 | 0 | 0
2282 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS , SM/06898 | Retrofitting | Accommodate FHTC( 70 ) including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE(PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Maliara Water Supply Scheme within Medinipur Sadar Dev. Block under Midnapur Sadar Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. (SL No-02) | 482/AEMSSD | 08/08/2023 | 10 | HIRAK KUMAR GHOSH | 4.44 | 0 | 0 | 100
2283 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS , SM/06898 | Retrofitting | Accommodate FHTC( 70 ) including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE(PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Maliara Water Supply Scheme within Medinipur Sadar Dev. Block under Midnapur Sadar Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. (SL No-02) | BP-2023-24-601 | 02/02/2024 | 0 | HIRAK KUMAR GHOSH | 0.23 | 0 | 0 | 0
2284 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS , SM/06918 | Retrofitting | For FHTC Data Entry. | 844386 | 13/09/2021 | 0 | SUBRATA CHAKRABORTY | 0.02 | 0 | 0 | 0
2285 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS , SM/06918 | Retrofitting | For FHTC Data Entry. | 844386 | 13/09/2021 | 0 | SIDDHESWAR BAG | 0.1 | 0 | 0 | 0
2286 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS , SM/06918 | Retrofitting | FHTC Data entry | 8443121 | 23/08/2021 | 0 | PARTHA PRATIM PAL | 0.01 | 0 | 0 | 0
2287 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS , SM/06918 | Retrofitting | Data Entry of FHTC. | 844386 | 13/09/2021 | 0 | PAPPU SHAW | 0.05 | 0 | 0 | 0
2288 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS , SM/06918 | Retrofitting | FHTC Data entry | 8443121 | 23/08/2021 | 0 | SHRABONTI BERA | 0.1 | 0 | 0 | 0
2289 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS , SM/06918 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-III) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1440/MD | 26/11/2020 | 180 | M/S. EL-CON | 70.72 | 27.4 | 38.75 | 100
2290 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS , SM/06918 | Retrofitting | Continuation work order ¿ Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre ,Health Care Institution etc¿. under Midnapore Division PHE Dte.for the period of 06 (months), from (01.01.2023 to 30.06.2023) | 764/MSSD | 31/12/2022 | 181 | PULLOCK KUMAR GHOSH | 2.04 | 0 | 0 | 0
2291 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS , SM/06918 | Retrofitting | Functional Household Tap Connection data uploading charges in JJM_IMIS portal in Paschim Medinipur & Jhargram District under Jal Jeevan Mission | 844336 | 12/09/2023 | 0 | PULLOCK KUMAR GHOSH | 2.04 | 0 | 0 | 0
2292 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS , SM/06918 | Retrofitting | Hire charges of Car No WB 33 D 6299 including supply of fuel and lubricants for the office of the Dy. SE, WC, PHE Dte. for the month of August. (MB No 3634/MD) | 84439 | 02/02/2024 | 0 | PULLOCK KUMAR GHOSH | 1.69 | 0 | 0 | 0
2293 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS , SM/06918 | Retrofitting | Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre, Health Care Institution etc. under Midnapore Division PHE Dte. Period from (15.07.2023 to 14.07.2024) | 844369 | 22/02/2024 | 0 | PULLOCK KUMAR GHOSH | 2.33 | 0 | 0 | 0
2294 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS , SM/06918 | Retrofitting | Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre, Health Care Institution etc. under Midnapore Division PHE Dte. Period from (15.07.2023 to 14.07.2024) |  | 20/02/2024 | 0 | PULLOCK KUMAR GHOSH | 2.33 | 0 | 0 | 0
2295 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Chandkuri (Zone-I) PWSS , SM/06920 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandkuri (Zone-I) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1463/MD | 26/11/2020 | 180 | DULAL CHANDRA DAS | 87.43 | 37.47 | 42.85 | 0
2296 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Chandkuri (Zone-I) PWSS , SM/06920 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandkuri (Zone-I) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | DULAL CHANDRA DAS | 20 | 0 | 0 | 0
2297 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in KASANDA W/S Scheme, Block: - Chandrokona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. , SM/09082 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kasanda W/S Scheme, Block: - Chandrakona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1585/MD | 11/12/2020 | 180 | DEVJYOTI BERA | 24.31 | 0 | 0 | 0
2298 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in KASANDA W/S Scheme, Block: - Chandrokona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. , SM/09082 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kasanda PWSS under Chandrakona-I block in Paschim Medinipur district (Phase-II). | 611/MD | 04/04/2022 | 15 | DEVJYOTI BERA | 7.67 | 0 | 0 | 0
2299 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in KASANDA W/S Scheme, Block: - Chandrokona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. , SM/09082 | Retrofitting | Laying interconnection in between Rising main pipe line and distribution pipe line with OHR and allied works of KASANDA W/S Scheme within Candrakona-I Block, under Midnapore Division, PHE Dte. | BP-2023-24-16 | 28/04/2023 | 0 | M/S. A.R. ENTERPRISE. | 0.55 | 0 | 0 | 0
2300 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Keudi Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09417 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Keudi PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 2174/MD | 17/12/2021 | 21 | DEBJIT PATRA | 8.45 | 0 | 0 | 0
2301 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Keudi Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09417 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Chhoto Keundi, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | 343/MD | 24/02/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.4 | 0 | 0 | 0
2302 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. , SM/09431 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Khairullachak (Block-Midnapore Sadar) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1645/MD | 22/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.56 | 0 | 0 | 0
2303 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. , SM/09431 | Augmentation | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC. Block - Midnapore. District - Paschim Medinipur. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 12.33 | 0 | 0 | 0
2304 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. , SM/09431 | Augmentation | Laying distribution pipe line, soil test, FHTC & construction of R.C.C. Over Head Reservoir of capacity 150 Cum and staging height 20.00 mtr. with allied work including Sinking of Deep Tube Well of 250 mm x 150 mm x250 m for Augmentation of Khairullachak W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 605/MD | 04/04/2022 | 180 | BANERJEE CONSTRUCTION | 411.2 | 0 | 0 | 21
2305 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. , SM/09431 | Augmentation | Material Requisition To Resource Division | 2275/MD | 31/12/2021 | 0 | Resource Division | 12.33 | 0 | 0 | 0
2306 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. , SM/09431 | Augmentation | Material Requisition To Resource Division | 2474/MD | 06/12/2022 | 0 | Resource Division | 13.36 | 0 | 0 | 0
2307 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. , SM/09431 | Augmentation | Material Requisition To Resource Division | 218/MD | 16/01/2023 | 0 | Resource Division | 9.39 | 0 | 0 | 0
2308 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. , SM/09431 | Augmentation | Restoration of road shoulder flank etc. after laying pipeline by PHE Deptt. At NL Khan Link Road from 3.10 km to 4.20 km under PWD, Midnapur Division, in the district of Paschim Medinipur during the year 2022-23 | BP-2022-23-631 | 23/02/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 10 | 0 | 0 | 0
2309 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. , SM/09431 | Augmentation | Electric Quation for Khairullachaki PWSS Tube well-II in connection Mohanpur CCC. | BP-2023-24-12 | 24/04/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.27 | 0 | 0 | 0
2310 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. , SM/09431 | Augmentation | Construction of Chlorine storage room for Midnapore Sadar Sub-Division Store at Narampur P.H.E. Complex under Midnapore Division, PHE Dte. | 2661/MD | 29/08/2024 | 60 | PULLOCK KUMAR GHOSH | 5 | 0 | 0 | 60
2311 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. , SM/09431 | Augmentation | Construction of 1 (One) No. 5.40 X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Augmentation of Khairullachak & its adjoining mouzas PWSS in block - Midnapore Sadar, District - Paschim Medinipur (Type-B). | 806/MD | 15/03/2024 | 60 | BENGAL TRADERS | 7.12 | 0 | 0 | 91
2312 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. , SM/09431 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | 1135/W/MMD | 12/04/2023 | 180 | SUBHASIS ROY | 11.32 | 0 | 0 | 100
2313 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Jatra & Banshiraisol Piped Water Supply Scheme to accommodate all FHTC. , SM/08206 | Retrofitting | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. | 8443498 | 30/03/2021 | 0 | SIRCON ENGINEERING SERVICES | 2.05 | 0 | 0 | 0
2314 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Jatra & Banshiraisol Piped Water Supply Scheme to accommodate all FHTC. , SM/08206 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Jatra & Banshirasol, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | 59/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.06 | 0 | 0 | 0
2315 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Jatra & Banshiraisol Piped Water Supply Scheme to accommodate all FHTC. , SM/08206 | Retrofitting | Continuation Work Order for the work of Retrofitting to accommodate FHTC (additional quantity) under JJM in Jatra Bansiraisol PWSS in Salboni block within Midnapore Division, PHE Dte. | 2382/MD | 23/11/2022 | 10 | PULLOCK KUMAR GHOSH | 1.82 | 0 | 0 | 0
2316 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur , SM/08214 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur. | BP-2021-22-410 | 23/02/2022 | 0 | BANERJEE CONSTRUCTION | 15 | 0 | 0 | 0
2317 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur , SM/08214 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur. | BP-2021-22-410 | 23/02/2022 | 0 | BANERJEE CONSTRUCTION | 0.21 | 0 | 0 | 0
2318 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Sauri Kotbar PWSS Block - Dantan-II District Paschim Medinipur , SM/08216 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sauri Kotbar PWSS, Block :- Dantan-II in the District of Paschim Medinipur. | 425/MD | 26/02/2021 | 40 | TARUN KUMAR BHATTACHARYA | 89.08 | 0 | 0 | 0
2319 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Sauri Kotbar PWSS Block - Dantan-II District Paschim Medinipur , SM/08216 | Retrofitting | Retrofitting to accommodate FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Sauri Kotbar & its adjoining mouzas W/S Scheme within Dantan-II Dev. Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | 581/MD | 23/02/2023 | 30 | DIPAK KUMAR BAKLY | 22.43 | 0 | 0 | 100
2320 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Baita PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09724 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Baita, Block - Mohanpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | BP-2021-22-416 | 24/02/2022 | 0 | SIRCON ENGINEERING SERVICES | 2.47 | 0 | 0 | 0
2321 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Baita PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09724 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Baita PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 2018/MD | 03/12/2021 | 60 | M/S. A.R. ENTERPRISE. | 100.97 | 0 | 0 | 80
2322 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09676 | New | Preparation of D.P.Rs. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for mouza (i) Nilhat, (ii) Mirjapur & (iii) Lachhmi Chak & its adj. Mouzas of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | 1337/MD | 18/08/2021 | 10 | GOBINDA MAITY | 4.39 | 0 | 0 | 0
2323 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09676 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Nilhat, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 155/W/MMD | 31/01/2022 | 120 | DEY ENTERPRISE | 6.81 | 0 | 0 | 0
2324 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09676 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Nilhat water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2524/W/MMD | 30/11/2021 | 4 | MENAKA ENTERPRISE | 4.48 | 0 | 0 | 100
2325 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09676 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | BP-2021-22-505 | 22/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 4.19 | 0 | 0 | 0
2326 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09676 | New | For payment of liabilities. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.39 | 0 | 0 | 0
2327 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09676 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.39 | 0 | 0 | 0
2328 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09676 | New | Material Requisition To Resource Division | 2115/MD | 13/12/2021 | 0 | Resource Division | 1.39 | 0 | 0 | 0
2329 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09676 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Nilhat, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 180/MD | 01/02/2022 | 1065 | MASUM ALI KHAN | 36.44 | 0 | 0 | 100
2330 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. , SM/09677 | New | Quotation for service connection charges of WBSEDCL at Neziveri | 2003855194/Quot/03 | 10/03/2022 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
2331 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. , SM/09677 | New | Purchasing of Materials. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.58 | 0 | 0 | 0
2332 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. , SM/09677 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.58 | 0 | 0 | 0
2333 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. , SM/09677 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Lejibheri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 153/W/MMD | 31/01/2022 | 120 | DEBJYOTI BASU | 6.51 | 0 | 0 | 0
2334 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. , SM/09677 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at LEJIBHERI water supply scheme, of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2516/W/MMD | 30/11/2021 | 4 | OSMAN SEKH | 4.47 | 0 | 0 | 0
2335 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. , SM/09677 | New | Preparation of D.P.Rs. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for mouza (i) Mangrajpur & (ii) Lejibheri of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | 1336/MD | 18/08/2021 | 10 | GOBINDA MAITY | 2.79 | 0 | 0 | 10
2336 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. , SM/09677 | New | Material Requisition To Resource Division | 2116/MD | 13/12/2021 | 0 | Resource Division | 0.58 | 0 | 0 | 0
2337 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. , SM/09677 | New | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 0 | 100
2338 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. , SM/09677 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Lejibheri, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 181/MD | 01/02/2022 | 1065 | MASUM ALI KHAN | 23.48 | 0 | 0 | 100
2339 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for Naoyagan & its adjoining mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | 1276/MD | 05/08/2021 | 10 | GOBINDA MAITY | 2.11 | 0 | 0 | 0
2340 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Naoyagan water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2528/W/MMD | 30/11/2021 | 4 | MENAKA ENTERPRISE | 4.47 | 0 | 0 | 100
2341 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Naoyagan water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2526/W/MMD | 30/11/2021 | 4 | MENAKA ENTERPRISE | 4.47 | 0 | 0 | 100
2342 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Naoyagan, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. (W/O-145/W/MMD, DT.-31/01/2022) | BP-2021-22-118 | 17/03/2022 | 0 | PRANAB KUMAR DAS | 4.13 | 0 | 0 | 0
2343 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Purchasing of materials for the Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.06 | 0 | 0 | 0
2344 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for Naoyagan & its adjoining mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | BP-2021-22-388 | 18/02/2022 | 0 | GOBINDA MAITY | 0.32 | 0 | 0 | 0
2345 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | BP-2021-22-505 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 8.11 | 0 | 0 | 0
2346 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | For payment of liabilities. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 2.92 | 0 | 0 | 0
2347 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Naoyagan, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 145/W/MMD | 31/01/2022 | 120 | PRANAB KUMAR DAS | 6.51 | 0 | 0 | 0
2348 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -II at Naoyagan, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 146/W/MMD | 31/01/2022 | 120 | BHABANI PRASAD MANNA | 6.56 | 0 | 0 | 0
2349 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Material Requisition To Resource Division | 2125/MD | 14/12/2021 | 0 | Resource Division | 2.92 | 0 | 0 | 0
2350 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Naoyagan (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 344/MD | 21/02/2022 | 150 | SANKAR PRASAD MAITY | 41.8 | 0 | 0 | 70
2351 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Naoyagan (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 343/MD | 21/02/2022 | 150 | SANKAR PRASAD MAITY | 43.79 | 0 | 0 | 100
2352 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09683 | New | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 0 | 100
2353 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Panpara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10841 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Panpara PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1675/MD | 29/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.16 | 0 | 0 | 100
2354 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Panpara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10841 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0 | 0 | 25
2355 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Panpara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10841 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0 | 0 | 100
2356 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Panpara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10841 | Augmentation | Quotation for New Service Connection charges of Additional TW-III of Panapara WS Scheme (Ref. Id-203959888) | BP-2023-24-31 | 04/05/2023 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
2357 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Panpara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10841 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Panpara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 609/W/MMD | 20/03/2023 | 180 | M/S EMMESS | 10.79 | 0 | 0 | 85
2358 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Panpara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10841 | Augmentation | Rejuvenation of Ground water based piped water supply scheme for Panpara (Part) to Accommodate FHTC under JJM under Sabang Block in Paschim Medinipur Districct Under Medinipur Division PHE Dte. | 1674/MD | 12/08/2022 | 1234 | BANERJEE CONSTRUCTION | 55.48 | 0 | 0 | 30
2359 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10655 | New | Electric quotation BIRSINGHA CCC at Masharpur, chowka, Ghatal, T/W-I P/H-II Pin-721232 |  | 17/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
2360 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10655 | New | Electric quotation BIRSINGHA CCC at Jamira, chowka, Ghatal, T/W-I P/H-II Pin-721232 |  | 17/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
2361 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10655 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Jamira (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 1731/MD | 23/08/2022 | 150 | MIDNAPUR PIPE CONCERN | 45.86 | 0 | 0 | 80
2362 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10655 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Jamira (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 1732/MD | 23/08/2022 | 150 | MIDNAPUR PIPE CONCERN | 39.37 | 0 | 0 | 100
2363 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10655 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Zone-II) | 229/W/MMD | 13/02/2023 | 180 | RISHAV ENTERPRISE | 6 | 0 | 0 | 100
2364 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10655 | New | Electric quotation BIRSINGHA CCC at Jamira, chowka, Ghatal, T/W-I Pin-721232 | BP-2022-23-70 | 14/12/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
2365 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10655 | New | Electric quotation BIRSINGHA CCC at Masharpur, chowka, Ghatal, P/H-II Pin-721232 | BP-2022-23-71 | 14/12/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
2366 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10655 | New | Service Connection charges of WBSEDCL at P/H-II of Jamira W/S Scheme | BP-2022-23-99 | 11/01/2023 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
2367 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10655 | New | Material Requisition To Resource Division | 3353/MD | 25/11/2024 | 0 | Resource Division | 2.34 | 0 | 0 | 0
2368 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10655 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | 2316/W/MMD | 29/12/2022 | 180 | M/S EMMESS | 6.01 | 0 | 0 | 100
2369 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10657 | New | Preparation of D.P.R (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- Raghunathpur under Dewanchak¿II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | 1328/MD | 17/08/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.18 | 0 | 0 | 0
2370 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10657 | New | Electric quotation BIRSINGHA CCC at Raghunathpur, monoharpur, Ghatal, T/W-II Pin-721232 | BP-2022-23-62 | 23/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
2371 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10657 | New | Electric quotation BIRSINGHA CCC at Raghunathpur, monoharpur, Ghatal, T/W-III P/H-II Pin-721232 | BP-2022-23-63 | 23/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
2372 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10657 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Raghunathpur (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 1418/MD | 15/07/2022 | 150 | ASHIM KUMAR DEY | 41.83 | 0 | 0 | 0
2373 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10657 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Raghunathpur water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | 2175/W/MMD | 12/12/2022 | 120 | A.S.ENTERPRISE | 5.92 | 0 | 0 | 0
2374 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10657 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-III under Raghunathpur water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | 2176/W/MMD | 12/12/2022 | 120 | M.D.ENTERPRISE | 5.97 | 0 | 0 | 100
2375 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10657 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Raghunathpur (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 1363/MD | 08/07/2022 | 150 | GOUTAM RAY | 43.98 | 0 | 0 | 100
2376 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10657 | New | Service Connection Charges of WBSEDCL at T/W-I of Raghunathpur W/S Scheme | BP-2022-23-98 | 11/01/2023 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
2377 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10657 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | 608/W/MMD | 20/03/2023 | 180 | M/S S M ELECTRICAL | 6 | 0 | 0 | 0
2378 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10657 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Raghunathpur (Zone-III), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 1419/MD | 15/07/2022 | 150 | WATER LINK | 43.03 | 0 | 0 | 100
2379 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10657 | New | Material Requisition To Resource Division | 3356/MD | 25/11/2024 | 0 | Resource Division | 3.17 | 0 | 0 | 0
2380 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bishnupur (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10840 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Bishnupur PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1661/MD | 28/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.16 | 0 | 0 | 100
2381 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bishnupur (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10840 | Augmentation | Electric quotation for WBSEDCL at TW-III of Bishnupur Water Supply Scheme (Ref. ID-203959904) | BP-2023-24-42 | 19/05/2023 | 0 | WBSEDCL | 2.18 | 0 | 0 | 0
2382 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bishnupur (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10840 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bishnupur (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | 1962/MD | 20/09/2022 | 45 | KISHORE GHOSH | 49.7 | 0 | 0 | 60
2383 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bishnupur (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/10840 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bishnupur (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 876/W/MMD | 27/03/2023 | 180 | RADHARANI ENTERPRISE | 5.98 | 0 | 0 | 100
2384 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Bhabaninagar PWSS under Midnapore Sadar Block in Paschim Medinipur District , SM/09701 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhabaninagar PWSS Block-Midnapore Sadar in the District of Paschim Medinipur. | 2017/MD | 03/12/2021 | 60 | MASUM ALI KHAN | 113.43 | 0 | 0 | 80
2385 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Krishnapriya PWSS under Pingla Block in Paschim Medinipur District , SM/09707 | Retrofitting | Retrofitting of Krishnapriya PWSS to accommodate FHTC in Pingla block under Midnapore Division, P.H.E. Dte. | 839/MD | 02/05/2022 | 30 | ANUSKA ENTERPRISE | 36.17 | 0 | 0 | 99
2386 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Krishnapriya PWSS under Pingla Block in Paschim Medinipur District , SM/09707 | Retrofitting | Material Requisition To Resource Division | 3416/MD | 25/11/2024 | 0 | Resource Division | 5.4 | 0 | 0 | 0
2387 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10002 | New | Quotation Bill of Mosharpur water supply scheme under MMD PHE Dte. | 2003978639 | 28/06/2022 | 365 | WBSEDCL | 0.11 | 0 | 0 | 0
2388 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10002 | New | Quotation Bill of Mosharpur water supply scheme under MMD PHE Dte. | BP-2022-23-45 | 23/08/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
2389 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10002 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal. GP - Dewanchak-11, PS - Ghatal, Dist.- Paschim Medinipur. |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.64 | 0 | 0 | 0
2390 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10002 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Masharpur water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | 2174/W/MMD | 12/12/2022 | 120 | SUBHASIS ROY | 5.92 | 0 | 0 | 91
2391 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10002 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-I under Masharpur water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | 1653/W/MMD | 12/08/2022 | 120 | BHABANI PRASAD MANNA | 5.64 | 0 | 0 | 100
2392 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10002 | New | Material Requisition To Resource Division | 2273/MD | 31/12/2021 | 0 | Resource Division | 1.64 | 0 | 0 | 0
2393 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10002 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Masharpur (Zone-I), Block - Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 319/MD | 17/02/2022 | 150 | PULLOCK KUMAR GHOSH | 39.42 | 0 | 0 | 100
2394 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10002 | New | Continuation Work Order for Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Masharpur (Zone-I), Block ¿ Ghatal, District ¿ Paschim Medinipur under Midnapore Division, PHE Dte. | 433/MD | 10/02/2023 | 15 | PULLOCK KUMAR GHOSH | 0.84 | 0 | 0 | 100
2395 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10002 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Masharpur (Zone-II), Block - Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 618/MD | 04/04/2022 | 637 | DEVJYOTI BERA | 36.33 | 0 | 0 | 90
2396 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. , SM/11622 | New | Construction of M.S. Fabricated and R.C.C Supporting Structure including aligning pipe line in connection of laying distribution main of Jote Kanuramgarh & Ranichak Water supply scheme under Midnapore Division P.H.E. Dte. | 453/MD | 13/02/2023 | 60 | GOBINDA MAITY | 50.85 | 0 | 0 | 60
2397 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. , SM/11622 | New | Material Requisition To Resource Division | 904/MD | 31/03/2023 | 0 | Resource Division | 40.66 | 0 | 0 | 0
2398 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. , SM/11622 | New | Material Requisition To Resource Division | 516/MD | 20/02/2023 | 0 | Resource Division | 40.67 | 0 | 0 | 0
2399 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. , SM/11622 | New | Electric quotation for tw-II of Jote kanuramgarh w/s scheme(consumar ID-203974597) | BP-2023-24-17 | 28/04/2023 | 0 | WBSEDCL | 4.14 | 0 | 0 | 0
2400 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. , SM/11622 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2022-23-780-781 | 29/03/2023 | 0 | GOBINDA MAITY | 28.72 | 0 | 0 | 0
2401 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. , SM/11622 | New | Electric quotation for tw-I of Jotekanuramgarh w/s scheme (consumar ID-203974593) | BP-2023-24-18 | 28/04/2023 | 0 | WBSEDCL | 7.05 | 0 | 0 | 0
2402 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. , SM/11622 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 22-23-707,8,9 | 13/03/2023 | 0 | GOBINDA MAITY | 61 | 0 | 0 | 0
2403 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. , SM/11622 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2022-23-723,24 | 20/03/2023 | 0 | GOBINDA MAITY | 4.92 | 0 | 0 | 0
2404 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. , SM/11622 | New | Preliminarily ground protection works (i.e. Driving Eucalyptus Bullah Piles, Land Development etc.) in connection with Construction of R.C.C. OHR at Head Works site of Jote Kanuramgar W/S Scheme under Midnapore Division, PHE Dte. (Total Length of Double row piling works @ 500 C/C = 100.00 Mtr.) | 2662/MD | 29/08/2024 | 30 | GOBINDA MAITY | 18.98 | 0 | 0 | 0
2405 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. , SM/11622 | New | Material Requisition To Resource Division | 3344/MD | 25/11/2024 | 0 | Resource Division | 18.02 | 0 | 0 | 0
2406 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. , SM/11622 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2364/MD | 21/11/2022 | 1242 | GOBINDA MAITY | 1460.37 | 0 | 0 | 58
2407 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. , SM/11622 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. under JJM Program under MMD PHE Dte. | 2313/W/MMD | 29/12/2022 | 720 | DEBJYOTI BASU | 25.25 | 0 | 0 | 100
2408 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Material Requisition To Resource Division | 517/MD | 20/02/2023 | 0 | Resource Division | 16.87 | 0 | 0 | 0
2409 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 22-23-707,8,9 | 13/03/2023 | 0 | GOBINDA MAITY | 61 | 0 | 0 | 0
2410 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2022-23-780-781 | 29/03/2023 | 0 | GOBINDA MAITY | 28.72 | 0 | 0 | 0
2411 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Electric Quotation for TW-II of Ramkrishnapur W/S Scheme (ID-203974545) | BP-2023-24-21 | 28/04/2023 | 0 | WBSEDCL | 3.11 | 0 | 0 | 0
2412 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Electric Quotation for TW-I of Ramkrishapur W/S Scheme (ID-203973517) | BP-2023-24-22 | 28/04/2023 | 0 | WBSEDCL | 5.24 | 0 | 0 | 0
2413 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2022-23-723,24 | 20/03/2023 | 0 | GOBINDA MAITY | 4.92 | 0 | 0 | 0
2414 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. under JJM Program under MMD PHE Dte. | 2314/W/MMD | 29/12/2022 | 180 | SUJOY RANJAN BHOWMICK | 27.35 | 0 | 0 | 80
2415 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Additional work for increasing of hight of tube well and other allied work ar tube well no. I & II of Ramkrishnapur and Kanchangeria (Tube well no. I) water supply scheme [Block-Daspur-II and Debra] under MMD, PHE Dte., Dist.- Paschim Medinipur. | 338/MMSD-I | 05/03/2024 | 10 | SUJOY RANJAN BHOWMICK | 1.33 | 0 | 0 | 100
2416 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Material Requisition To Resource Division | 3345/MD | 25/11/2024 | 0 | Resource Division | 10.33 | 0 | 0 | 0
2417 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Supply & Delivery of DI Specials for laying of Rising Main & distribution system including interconnection for Ramkrishnapur and its adjoining mouzas Water Supply Scheme within Daspur-II Block under Ghatal Sub Division of Midnapore Division, P.H.E.Dte. | 799/AE/GSD | 10/11/2023 | 7 | GOBINDA MAITY | 1.26 | 0 | 0 | 100
2418 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2364/MD | 21/11/2022 | 1242 | GOBINDA MAITY | 1460.37 | 0 | 0 | 58
2419 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 1211/MMSD-I | 29/09/2023 | 92 | SUBHASIS ROY | 0.45 | 0 | 0 | 0
2420 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Laying of Rising main including interconnection of Ramkrishnapur and its adjoining mouzas Water Supply Scheme under Daspur-II Block under Ghatal Sub-Division within Midnapore Division, PHE Dte. | 143/MD | 18/01/2024 | 20 | GOBINDA MAITY | 6.05 | 0 | 0 | 100
2421 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. , SM/11623 | New | Laying additional distribution system pipe line & accommodate FHTC (350 Nos.) for Ramkrishnapur W/S Scheme under JJM within Daspur-II Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2788/MD | 03/09/2024 | 75 | GOBINDA MAITY | 44.45 | 0 | 0 | 0
2422 | PASCHIM MEDINIPUR | Midnapore Division | BRINDABANPUR AND ITS ADJOINING MOJAS PWSS , SM/12384 | New | Material Requisition To Resource Division | 1196 | 26/04/2023 | 0 | Resource Division | 31.5 | 0 | 0 | 0
2423 | PASCHIM MEDINIPUR | Midnapore Mechanical | BRINDABANPUR AND ITS ADJOINING MOJAS PWSS , SM/12384 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BRINDABANPUR AND ITS ADJOINING MOJAS PWSS under JJM Program under MMD PHE Dte. | 1125/W/MMD | 12/04/2023 | 180 | S.P. ENTERPRISE | 22.65 | 0 | 0 | 50
2424 | PASCHIM MEDINIPUR | Midnapore Division | BRINDABANPUR AND ITS ADJOINING MOJAS PWSS , SM/12384 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 0 | 25
2425 | PASCHIM MEDINIPUR | Midnapore Division | MIRGA AND ADJOINING MOUJAS PWSS , SM/13099 | New | Material Requisition To Resource Division | 1266/MD | 28/04/2023 | 0 | Resource Division | 22.99 | 0 | 0 | 0
2426 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MIRGA AND ADJOINING MOUJAS PWSS , SM/13099 | New | New service connection charges for Mirga w/s scheme, t/w no.I | 40/JMD | 11/03/2024 | 0 | WBSEDCL | 5.86 | 0 | 0 | 0
2427 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MIRGA AND ADJOINING MOUJAS PWSS , SM/13099 | New | New service connection charges for Mirga w/s scheme, t/w no.II | 41/JMD | 11/03/2024 | 0 | WBSEDCL | 5.09 | 0 | 0 | 0
2428 | PASCHIM MEDINIPUR | Central Drilling | MIRGA AND ADJOINING MOUJAS PWSS , SM/13099 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2429 | PASCHIM MEDINIPUR | Midnapore Division | PATHARTERIA AND ADJOINING MOUJAS PWSS , SM/13106 | New | Material Requisition To Resource Division | 1190/MD | 26/04/2023 | 0 | Resource Division | 23.87 | 0 | 0 | 0
2430 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PATHARTERIA AND ADJOINING MOUJAS PWSS , SM/13106 | New | NEW SERVICE CONNECTION CHARGES AT PATHARTORIA TW-I WATER SUPPLY SCHEME | 246/JMD | 10/07/2024 | 0 | WBSEDCL | 3.53 | 0 | 0 | 0
2431 | PASCHIM MEDINIPUR | Central Drilling | PATHARTERIA AND ADJOINING MOUJAS PWSS , SM/13106 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2432 | PASCHIM MEDINIPUR | Midnapore Division | KESHIA AND ADJOINING MOUJAS PWSS , SM/13124 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
2433 | PASCHIM MEDINIPUR | Midnapore Division | KESHIA AND ADJOINING MOUJAS PWSS , SM/13124 | New | Material Requisition To Resource Division | 1237/MD | 27/04/2023 | 0 | Resource Division | 26.22 | 0 | 0 | 0
2434 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KESHIA AND ADJOINING MOUJAS PWSS , SM/13124 | New | Payment for WBSEDCL new connection at KESIA 2 (SM/13124. KESIA AND ADJOINING MOUJAS PWSS ) | 173/JMD | 07/06/2024 | 0 | WBSEDCL | 7.69 | 0 | 0 | 0
2435 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KESHIA AND ADJOINING MOUJAS PWSS , SM/13124 | New | Payment for new service connection at Keshia T/W-1 | 57/JMD | 29/04/2024 | 0 | WBSEDCL | 3.45 | 0 | 0 | 0
2436 | PASCHIM MEDINIPUR | Central Drilling | KESHIA AND ADJOINING MOUJAS PWSS , SM/13124 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2437 | PASCHIM MEDINIPUR | Midnapore Division | BHIKUBAR AND ADJOINING MOUJAS PWSS , SM/13071 | New | Material Requisition To Resource Division | 1284/MD | 28/04/2023 | 0 | Resource Division | 39.41 | 0 | 0 | 0
2438 | PASCHIM MEDINIPUR | Midnapore Division | BHIKUBAR AND ADJOINING MOUJAS PWSS , SM/13071 | New | Installation of Display Board for JJM work at different Piped Water Supply Scheme under different block within Midnapore Division, PHE Dte. [PART-B] | 507/MD | 27/02/2024 | 10 | HIRAK KUMAR GHOSH | 0.96 | 0 | 0 | 100
2439 | PASCHIM MEDINIPUR | Midnapore Mechanical | BHIKUBAR AND ADJOINING MOUJAS PWSS , SM/13071 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of BHIKUBAR PWSS. REF CONSUMER ID-204310423 APPLICATION NO-2004739593 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-206 | 28/05/2024 | 0 | WBSEDCL | 0.84 | 0 | 0 | 0
2440 | PASCHIM MEDINIPUR | Midnapore Mechanical | BHIKUBAR AND ADJOINING MOUJAS PWSS , SM/13071 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of BHIKUBAR PWSS. REF CONSUMER ID-204310348 APPLICATION NO-2004739394 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-207 | 28/05/2024 | 0 | WBSEDCL | 1.23 | 0 | 0 | 0
2441 | PASCHIM MEDINIPUR | Midnapore Mechanical | BHIKUBAR AND ADJOINING MOUJAS PWSS , SM/13071 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BHIKUBAR AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 649/W/MMD | 20/03/2023 | 744 | M/S. S.R. ENTERPRISE | 32.33 | 0 | 0 | 30
2442 | PASCHIM MEDINIPUR | Midnapore Division | DURIA AND ADJOINING MOUJAS PWSS , SM/13009 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
2443 | PASCHIM MEDINIPUR | Midnapore Division | DURIA AND ADJOINING MOUJAS PWSS , SM/13009 | New | Material Requisition To Resource Division | 3452/MD | 25/11/2024 | 0 | Resource Division | 8 | 0 | 0 | 0
2444 | PASCHIM MEDINIPUR | Midnapore Mechanical | DURIA AND ADJOINING MOUJAS PWSS , SM/13009 | New | Quotation for new power connection at Duria PWSS P/H- I , application no - 2004609049 , Ref id - 204223727 | BP-2023-24-786 | 06/03/2024 | 0 | WBSEDCL | 3.45 | 0 | 0 | 0
2445 | PASCHIM MEDINIPUR | Central Drilling | DURIA AND ADJOINING MOUJAS PWSS , SM/13009 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2446 | PASCHIM MEDINIPUR | Midnapore Division | DURIA AND ADJOINING MOUJAS PWSS , SM/13009 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7,515 Nos.) including 2 years operation & maintenance For BARAGOPAL, DURIA, GAHIRA & RAIPUR Pipe Water Supply Scheme within NARAYANGARH Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 3048/MD | 23/08/2023 | 975 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 2197.07 | 0 | 0 | 33
2447 | PASCHIM MEDINIPUR | Midnapore Division | ASTI AND ADJOINING MOUJAS PWSS , SM/13655 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
2448 | PASCHIM MEDINIPUR | Midnapore Division | ASTI AND ADJOINING MOUJAS PWSS , SM/13655 | New | Material Requisition To Resource Division | 1481 | 10/05/2023 | 0 | Resource Division | 37.4 | 0 | 0 | 0
2449 | PASCHIM MEDINIPUR | Midnapore Mechanical | ASTI AND ADJOINING MOUJAS PWSS , SM/13655 | New | Quotation for new power connection at Asti PWSS T/W - I Within Narayangarh Block Application No - 2004987846, Ref ID- 204460783 |  | 24/12/2024 | 0 | WBSEDCL | 4.13 | 0 | 0 | 0
2450 | PASCHIM MEDINIPUR | Midnapore Mechanical | ASTI AND ADJOINING MOUJAS PWSS , SM/13655 | New | Quotation for new power connection at Asti PWSS T/W - II Within Narayangarh Block Application No - 2004987869, Ref ID- 204460781 |  | 24/12/2024 | 0 | WBSEDCL | 3.11 | 0 | 0 | 0
2451 | PASCHIM MEDINIPUR | Central Drilling | ASTI AND ADJOINING MOUJAS PWSS , SM/13655 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2452 | PASCHIM MEDINIPUR | Midnapore Division | ASTI AND ADJOINING MOUJAS PWSS , SM/13655 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
2453 | PASCHIM MEDINIPUR | Midnapore Mechanical | ASTI AND ADJOINING MOUJAS PWSS , SM/13655 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
2454 | PASCHIM MEDINIPUR | Midnapore Mechanical | BHETIAMLA AND ADJOINING MOUJAS PWSS , SM/12998 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BHETIAMLA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 485/W/MMD | 20/03/2023 | 180 | DIAMOND ELECTRICAL WORKS | 22.95 | 0 | 0 | 10
2455 | PASCHIM MEDINIPUR | Midnapore Division | BHETIAMLA AND ADJOINING MOUJAS PWSS , SM/12998 | New | Material Requisition To Resource Division | 1277/MD | 28/04/2023 | 0 | Resource Division | 27.29 | 0 | 0 | 0
2456 | PASCHIM MEDINIPUR | Midnapore Mechanical | BHETIAMLA AND ADJOINING MOUJAS PWSS , SM/12998 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of BHETIA MALA PWSS. REF CONSUMER ID-204310299 APPLICATION NO-2004739419, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-209 | 28/05/2024 | 0 | WBSEDCL | 6.22 | 0 | 0 | 0
2457 | PASCHIM MEDINIPUR | Midnapore Division | BHETIAMLA AND ADJOINING MOUJAS PWSS , SM/12998 | New | Joint inspection regarding laying of water supply pipe line of under ground Railway track crossing of 600mm dia M.S. carrier pipe by jack pushing method by PHE at Km 171/06/08-171/05-07 between DNT-AGV under the jurisdiction of ADEN/South/KGP. [Application ID - SER-KGP-2024-WL-181] | BP-2024-25-444 | 07/10/2024 | 0 | SOUTH EASTERN RAILWAY | 6.32 | 0 | 0 | 0
2458 | PASCHIM MEDINIPUR | Midnapore Division | BHETIAMLA AND ADJOINING MOUJAS PWSS , SM/12998 | New | Joint inspection regarding laying of water supply pipe line of under ground Railway track crossing of 600mm dia M.S. carrier pipe by jack pushing method by PHE at Km 171/06/08-171/05-07 between DNT-AGV under the jurisdiction of ADEN/South/KGP. [Application ID - SER-KGP-2024-WL-182] | BP-2024-25-444 | 07/10/2024 | 0 | SOUTH EASTERN RAILWAY | 5.93 | 0 | 0 | 0
2459 | PASCHIM MEDINIPUR | Midnapore Mechanical | BHETIAMLA AND ADJOINING MOUJAS PWSS , SM/12998 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of BHETIA MALA PWSS. REF CONSUMER ID-204310335, APPLICATION NO-2004739400, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-208 | 28/05/2024 | 0 | WBSEDCL | 5.73 | 0 | 0 | 0
2460 | PASCHIM MEDINIPUR | Midnapore Division | BHETIAMLA AND ADJOINING MOUJAS PWSS , SM/12998 | New | Joint inspection regarding laying of water supply pipe line of under ground Railway track crossing of 600mm dia M.S. carrier pipe by jack pushing method by PHE at Km 171/06/08-171/05-07 between DNT-AGV under the jurisdiction of ADEN/South/KGP. [Application ID - SER-KGP-2024-WL-182] | BP-2024-25-444 | 07/10/2024 | 0 | SOUTH EASTERN RAILWAY | 6.24 | 0 | 0 | 0
2461 | PASCHIM MEDINIPUR | Midnapore Division | FATEHSINGPUR AND ADJOINING MOUJAS PWSS , SM/13062 | New | Material Requisition To Resource Division | 1153/MD | 25/04/2023 | 0 | Resource Division | 23.29 | 0 | 0 | 0
2462 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | FATEHSINGPUR AND ADJOINING MOUJAS PWSS , SM/13062 | New | New service connection charges at Fatesingpur TW-I water supply scheme | 216/JMD | 21/06/2024 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
2463 | PASCHIM MEDINIPUR | Central Drilling | FATEHSINGPUR AND ADJOINING MOUJAS PWSS , SM/13062 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2464 | PASCHIM MEDINIPUR | Midnapore Division | BARAKALANKI AND ADJOINING MOUJAS PWSS , SM/13067 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
2465 | PASCHIM MEDINIPUR | Midnapore Division | BARAKALANKI AND ADJOINING MOUJAS PWSS , SM/13067 | New | Material Requisition To Resource Division | 188/MD | 16/01/2023 | 0 | Resource Division | 16.01 | 0 | 0 | 0
2466 | PASCHIM MEDINIPUR | Midnapore Division | BARAKALANKI AND ADJOINING MOUJAS PWSS , SM/13067 | New | Material Requisition To Resource Division | 3448/MD | 25/11/2024 | 0 | Resource Division | 12.2 | 0 | 0 | 0
2467 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARAKALANKI AND ADJOINING MOUJAS PWSS , SM/13067 | New | Quotation for new power connection at Barakalankai PWSS T/W no - II of Narayangarh block Applocation no - 2004754804 , Ref ID - 204323283 | BP-2024-25-342 | 25/06/2024 | 0 | WBSEDCL | 4.75 | 0 | 0 | 0
2468 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARAKALANKI AND ADJOINING MOUJAS PWSS , SM/13067 | New | Quotation for new power connection at Barakalankai PWSS T/W no - I of Narayangarh block Applocation no - 2004752560 , Ref ID - 204317453 | BP-2024-25-341 | 25/06/2024 | 0 | WBSEDCL | 6.29 | 0 | 0 | 0
2469 | PASCHIM MEDINIPUR | Central Drilling | BARAKALANKI AND ADJOINING MOUJAS PWSS , SM/13067 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2470 | PASCHIM MEDINIPUR | Midnapore Division | SATYAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13038 | New | Material Requisition To Resource Division | 1199 | 26/04/2023 | 0 | Resource Division | 13.34 | 0 | 0 | 0
2471 | PASCHIM MEDINIPUR | Midnapore Mechanical | SATYAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13038 | New | Electrict quotation bill for TW-II of Satyapur pwss (Ref Consumar ID-204369741),Application No-2004844164,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | BP-2024-25-579 | 20/08/2024 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
2472 | PASCHIM MEDINIPUR | Midnapore Mechanical | SATYAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13038 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SATYAPUR AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 481/W/MMD | 20/03/2023 | 897 | SAIKAT SINHA | 23.01 | 0 | 0 | 52
2473 | PASCHIM MEDINIPUR | Midnapore Division | SATYAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13038 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 0 | 25
2474 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. , SM/12875 | New | Electric quotation for TW-I,ZONE-I for chaipat water supply scheme.Ref consumer Id-204087542 | BP-2023-24-262 | 26/09/2023 | 0 | WBSEDCL | 4.7 | 0 | 0 | 0
2475 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. , SM/12875 | New | Laying of Rising main pipeline for Chaipat (Zone-II) PWSS under Daspur-II block within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 3788/MD | 24/12/2024 | 45 | ENVIROEXCELSIOR SOLUTIONS PRIVATE LIMITED | 5.32 | 0 | 0 | 0
2476 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. , SM/12875 | New | Laying of Rising main pipeline for Chaipat (Zone-I) PWSS under Daspur-II block within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 3787/MD | 24/12/2024 | 45 | ENVIROEXCELSIOR SOLUTIONS PRIVATE LIMITED | 6.2 | 0 | 0 | 0
2477 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. , SM/12875 | New | Material Requisition To Resource Division | 3341/MD | 25/11/2024 | 0 | Resource Division | 25.58 | 0 | 0 | 0
2478 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. , SM/12875 | New | Electrict quotation bill for TW-I of Chaipat(Zone-II)(Nischintapur) pwss ,(Ref Consumar ID-204219008),Application No-2004604095,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II. |  | 24/04/2024 | 0 | WBSEDCL | 3.9 | 0 | 0 | 0
2479 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. , SM/12875 | New | Electrict quotation bill for TW-II of CHAIPAT,ZONE-II pwss (Ref Consumar ID-204239049),Application No-2004633954,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II. | BP-2023-24-817 | 13/03/2024 | 0 | WBSEDCL | 13.12 | 0 | 0 | 0
2480 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. , SM/12875 | New | Electrict quotation bill for TW-I of chaipat , Zone-II pwss (Ref Consumar ID-204219008),Application No-2004604095,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II. | BP-2023-24-726 | 23/02/2024 | 0 | WBSEDCL | 3.9 | 0 | 0 | 0
2481 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. , SM/12875 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 2 nos. 400 cum OHR (Intze type with pile foundation) & 3 Nos. 300 Cum OHR & Accommodate FHTC (10,944 Nos,) under JJM with allied work for (i) Chaipat (Zone-I & Zone-II) & its adjoining mouzas W/S scheme (ii) Kelegoda & its adjoining mouzas W/S Scheme (iii) Uttarbar (Zone-I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2556/MD | 15/12/2022 | 1238 | M/S. S.S. ENTERPRISE | 2473.34 | 0 | 0 | 18
2482 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. , SM/12875 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
2483 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. , SM/12875 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. under JJM Program under MMD PHE Dte. | 823/W/MMD | 24/03/2023 | 892 | M/S. SAJAHAN CHOWDHURY | 47.51 | 0 | 0 | 80
2484 | PASCHIM MEDINIPUR | Midnapore Division | BRAHMAN KHALISA & ADJOINING MOUZAS , SM/13051 | New | Material Requisition To Resource Division | 1296/MD | 28/04/2023 | 0 | Resource Division | 23.21 | 0 | 0 | 0
2485 | PASCHIM MEDINIPUR | Midnapore Mechanical | BRAHMAN KHALISA & ADJOINING MOUZAS , SM/13051 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF BRAHMAN KHALISA PWSS. REF CONSUMER ID-204373748, APPLICATION NO-2004853061, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C082430150750 | 20/08/2024 | 0 | WBSEDCL | 3.48 | 0 | 0 | 0
2486 | PASCHIM MEDINIPUR | Midnapore Mechanical | BRAHMAN KHALISA & ADJOINING MOUZAS , SM/13051 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF BRAHMAN KHALISA PWSS. REF CONSUMER ID-204373752, APPLICATION NO-2004853092, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C082430136142 | 20/08/2024 | 0 | WBSEDCL | 3.87 | 0 | 0 | 0
2487 | PASCHIM MEDINIPUR | Central Drilling | BRAHMAN KHALISA & ADJOINING MOUZAS , SM/13051 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2488 | PASCHIM MEDINIPUR | Midnapore Division | ANAR AND ADJOINING MOUJAS PWSS , SM/13180 | New | Material Requisition To Resource Division | 1308/MD | 28/04/2023 | 0 | Resource Division | 32.28 | 0 | 0 | 0
2489 | PASCHIM MEDINIPUR | Midnapore Mechanical | ANAR AND ADJOINING MOUJAS PWSS , SM/13180 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ANAR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 3074/W/MMD | 29/11/2023 | 180 | SANKAR PRASAD DUTTA AND CO | 22.99 | 0 | 0 | 60
2490 | PASCHIM MEDINIPUR | Central Drilling | ANAR AND ADJOINING MOUJAS PWSS , SM/13180 | New | Hiring of Diesel Driven Motor cab (BS-III & Above) having contract carriage permit along with driver for the office of The Executive Engineer, Central Drilling Division, P.H.E. Dte. | 165/S&WSD | 19/12/2023 | 183 | ASHUTOSH DAS & CO | 0.86 | 0 | 0 | 50
2491 | PASCHIM MEDINIPUR | Central Drilling | ANAR AND ADJOINING MOUJAS PWSS , SM/13180 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 220 Mtrs. Depth) by utilising Departmental Machineries for ANAR W/S Scheme (T/W-I & II) , Keshiery Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | 388/CDD | 18/05/2023 | 30 | KARTICK BAL | 25.4 | 0 | 0 | 100
2492 | PASCHIM MEDINIPUR | Midnapore Mechanical | ANAR AND ADJOINING MOUJAS PWSS , SM/13180 | New | ELECTRIC QUOTATION BILL TW NO-II of ANAR PWSS. REF CONSUMER ID-204204416, APPLICATION NO-2004578958, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2023-24-639 | 08/02/2024 | 0 | WBSEDCL | 4.1 | 0 | 0 | 0
2493 | PASCHIM MEDINIPUR | Midnapore Mechanical | ANAR AND ADJOINING MOUJAS PWSS , SM/13180 | New | ELECTRIC QUOTATION BILL TW NO-I of ANAR PWSS. REF CONSUMER ID-204204419, APPLICATION NO-2004578966, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2023-24-638 | 07/02/2024 | 0 | WBSEDCL | 3.13 | 0 | 0 | 0
2494 | PASCHIM MEDINIPUR | Midnapore Division | KESHARAMBHA AND IT'S ADJOINING MOUJAS PWSS , SM/13023 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
2495 | PASCHIM MEDINIPUR | Midnapore Division | KESHARAMBHA AND IT'S ADJOINING MOUJAS PWSS , SM/13023 | New | Material Requisition To Resource Division | 1288/MD | 28/04/2023 | 0 | Resource Division | 34.59 | 0 | 0 | 0
2496 | PASCHIM MEDINIPUR | Midnapore Mechanical | KESHARAMBHA AND IT'S ADJOINING MOUJAS PWSS , SM/13023 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF KESHARAMBHA PWSS. REF CONSUMER ID-204391649, APPLICATION NO-2004886653, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102401979918 | 03/10/2024 | 0 | WBSEDCL | 3.59 | 0 | 0 | 0
2497 | PASCHIM MEDINIPUR | Midnapore Mechanical | KESHARAMBHA AND IT'S ADJOINING MOUJAS PWSS , SM/13023 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF KESHARAMBHA PWSS. REF CONSUMER ID-204391647, APPLICATION NO-2004886652, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102401980457 | 03/10/2024 | 0 | WBSEDCL | 3.23 | 0 | 0 | 0
2498 | PASCHIM MEDINIPUR | Central Drilling | KESHARAMBHA AND IT'S ADJOINING MOUJAS PWSS , SM/13023 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2499 | PASCHIM MEDINIPUR | Midnapore Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/13217 | New | Material Requisition To Resource Division | 213/MD | 16/01/2023 | 0 | Resource Division | 18.54 | 0 | 0 | 0
2500 | PASCHIM MEDINIPUR | Midnapore Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/13217 | New | Material Requisition To Resource Division | 1168/MD | 26/04/2023 | 0 | Resource Division | 28.05 | 0 | 0 | 0
2501 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/13217 | New | Quotation for new power connection at Radhanagar PWSS T/W- I ,Narayangarh Block , Application no- 2004680777 , ref. Id - 204273485 | BP-2024-25-148 | 09/05/2024 | 0 | WBSEDCL | 4.23 | 0 | 0 | 0
2502 | PASCHIM MEDINIPUR | Central Drilling | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/13217 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2503 | PASCHIM MEDINIPUR | Midnapore Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/13217 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 0 | 20
2504 | PASCHIM MEDINIPUR | Midnapore Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/13217 | New | Construction of approach road for Head work site of Radhanagar Piped Water Supply Scheme within Narayangarh Block under Midnapore Division, PHE Dte. [200 Mtr. Long X 3 Mtr. Width] | 995/AE/HQ/MD | 22/04/2025 | 30 | GOURMOHAN DAS | 2.28 | 0 | 0 | 0
2505 | PASCHIM MEDINIPUR | Midnapore Division | RAUTARA AND ADJOINING MOUJAS PWSS , SM/13218 | New | Material Requisition To Resource Division | 1270/MD | 28/04/2023 | 0 | Resource Division | 24.42 | 0 | 0 | 0
2506 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | RAUTARA AND ADJOINING MOUJAS PWSS , SM/13218 | New | New Service Connection Charges for Rautara T/W - I PWSS | 358/JMD | 20/09/2024 | 0 | WBSEDCL | 5.17 | 0 | 0 | 0
2507 | PASCHIM MEDINIPUR | Central Drilling | RAUTARA AND ADJOINING MOUJAS PWSS , SM/13218 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2508 | PASCHIM MEDINIPUR | Midnapore Division | MADHUPUR AND ADJOINING MOUJAS PWSS , SM/14035 | New | Material Requisition To Resource Division | 1265/MD | 28/04/2023 | 0 | Resource Division | 24.15 | 0 | 0 | 0
2509 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MADHUPUR AND ADJOINING MOUJAS PWSS , SM/14035 | New | New service connection charges for Madhupur w/s scheme, t/w no.I | 156/JMD | 31/05/2024 | 0 | WBSEDCL | 6.6 | 0 | 0 | 0
2510 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MADHUPUR AND ADJOINING MOUJAS PWSS , SM/14035 | New | New service charges for Madhupur w/s scheme, t/w no.II | 157/JMD | 31/05/2024 | 0 | WBSEDCL | 5.91 | 0 | 0 | 0
2511 | PASCHIM MEDINIPUR | Central Drilling | MADHUPUR AND ADJOINING MOUJAS PWSS , SM/14035 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2512 | PASCHIM MEDINIPUR | Midnapore Mechanical | Dontiara & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14646 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Dontiara and its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 1232/W/MMD | 25/04/2023 | 180 | PRADIP KUMAR DHABAL | 21.56 | 0 | 0 | 0
2513 | PASCHIM MEDINIPUR | Midnapore Division | Dontiara & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14646 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 200 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1188 nos) under JJM with allied work for Dontiara PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2523/MD | 18/07/2023 | 180 | SUJATA CONSTRUCTION | 350.99 | 0 | 0 | 0
2514 | PASCHIM MEDINIPUR | Midnapore Division | Dontiara & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14646 | New | Preparation & Submission of 6 (Six) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Shrirampur & its adjoining Mouzas PWSS, (2) Dontiara & its adjoining Mouzas PWSS, (3) Dhashachandpur Mouza Stand Alone PWSS, (4) Udayganj (P) Mouza Stand Alone PWSS, (5) Prasadchak Mouza Stand Alone PWSS AND (6) Anandapur Mouza Stand Alone PWSS, Block - Ghatal under Midnapore Division, PHE Dte. [Name of Proposed PWSS Chaulisingpur & its adjoining Mouzas PWSS & Hemantapur & its adjoining Mouzas PWSS instead of (1) Dhashachandpur Mouza Stand Alone PWSS, (2) Udayganj (P) Mouza Stand Alone PWSS, (3) Prasadchak Mouza Stand Alone PWSS AND (4) Anandapur Mouza Stand Alone PWSS] | 1767/MD | 24/08/2022 | 45 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.73 | 0 | 0 | 100
2515 | PASCHIM MEDINIPUR | Midnapore Division | Dontiara & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14646 | New | Material Requisition To Resource Division | 70/MD | 09/01/2023 | 0 | Resource Division | 15.8 | 0 | 0 | 0
2516 | PASCHIM MEDINIPUR | Midnapore Division | BENADIHA AND ADJOINING MOUJAS PWSS , SM/14993 | New | Material Requisition To Resource Division | 3454/MD | 25/11/2024 | 0 | Resource Division | 19.82 | 0 | 0 | 0
2517 | PASCHIM MEDINIPUR | Midnapore Mechanical | BENADIHA AND ADJOINING MOUJAS PWSS , SM/14993 | New | Quotation for new power connection at Benadiha water supply scheme T/W no I | BP-2023-24-500 | 05/01/2024 | 0 | WBSEDCL | 4.63 | 0 | 0 | 0
2518 | PASCHIM MEDINIPUR | Midnapore Mechanical | BENADIHA AND ADJOINING MOUJAS PWSS , SM/14993 | New | Quotation for New power connection at Benadiha water supply Scheme T/W no - II | BP-2023-24-499 | 05/01/2024 | 0 | WBSEDCL | 3.08 | 0 | 0 | 0
2519 | PASCHIM MEDINIPUR | Central Drilling | BENADIHA AND ADJOINING MOUJAS PWSS , SM/14993 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2520 | PASCHIM MEDINIPUR | Midnapore Division | BENADIHA AND ADJOINING MOUJAS PWSS , SM/14993 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7130 Nos) including 2 years Operation & Maintenance for Kashipur, Benadiha and Markunda Pipe Water Supply Scheme within Narayangarh Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2524/MD | 18/07/2023 | 840 | NABA KUMAR BHUNIA | 1870.43 | 0 | 0 | 82
2521 | PASCHIM MEDINIPUR | Midnapore Mechanical | BENADIHA AND ADJOINING MOUJAS PWSS , SM/14993 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
2522 | PASCHIM MEDINIPUR | Midnapore Division | BENADIHA AND ADJOINING MOUJAS PWSS , SM/14993 | New | Laying additional quantity of distribution pipeline for providing FHTC at Kashipur, Benadiha & Markunda PWSS under Narayangarh block within Midnapore Division, PHE Dte. | 3165/MD | 05/10/2024 | 255 | NABA KUMAR BHUNIA | 78.57 | 0 | 0 | 50
2523 | PASCHIM MEDINIPUR | Midnapore Division | KASHIPUR AND ADJOINING MOUJAS PWSS , SM/15014 | New | Material Requisition To Resource Division | 3455/MD | 25/11/2024 | 0 | Resource Division | 16.23 | 0 | 0 | 0
2524 | PASCHIM MEDINIPUR | Midnapore Mechanical | KASHIPUR AND ADJOINING MOUJAS PWSS , SM/15014 | New | Electric quotation for TW-I of Kashipur Water Supply Scheme | BP-2023-24-534 | 11/01/2024 | 0 | WBSEDCL | 4.56 | 0 | 0 | 0
2525 | PASCHIM MEDINIPUR | Midnapore Mechanical | KASHIPUR AND ADJOINING MOUJAS PWSS , SM/15014 | New | Electric quotation for TW-II of Kashipur Water Supply Scheme | BP-2023-24-535 | 11/01/2024 | 0 | WBSEDCL | 7.91 | 0 | 0 | 0
2526 | PASCHIM MEDINIPUR | Central Drilling | KASHIPUR AND ADJOINING MOUJAS PWSS , SM/15014 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2527 | PASCHIM MEDINIPUR | Midnapore Division | KASHIPUR AND ADJOINING MOUJAS PWSS , SM/15014 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7130 Nos) including 2 years Operation & Maintenance for Kashipur, Benadiha and Markunda Pipe Water Supply Scheme within Narayangarh Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2524/MD | 18/07/2023 | 840 | NABA KUMAR BHUNIA | 1870.43 | 0 | 0 | 82
2528 | PASCHIM MEDINIPUR | Midnapore Division | KASHIPUR AND ADJOINING MOUJAS PWSS , SM/15014 | New | Laying additional quantity of distribution pipeline for providing FHTC at Kashipur, Benadiha & Markunda PWSS under Narayangarh block within Midnapore Division, PHE Dte. | 3165/MD | 05/10/2024 | 255 | NABA KUMAR BHUNIA | 78.57 | 0 | 0 | 50
2529 | PASCHIM MEDINIPUR | Midnapore Division | SALIKOTHA AND ADJOINING MOUJAS PWSS , SM/13171 | New | Material Requisition To Resource Division | 206/MD | 16/01/2023 | 0 | Resource Division | 22.06 | 0 | 0 | 0
2530 | PASCHIM MEDINIPUR | Midnapore Division | SALIKOTHA AND ADJOINING MOUJAS PWSS , SM/13171 | New | Material Requisition To Resource Division | 3463/MD | 25/11/2024 | 0 | Resource Division | 21.44 | 0 | 0 | 0
2531 | PASCHIM MEDINIPUR | Midnapore Mechanical | SALIKOTHA AND ADJOINING MOUJAS PWSS , SM/13171 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF SALIKOTHA PWSS. REF CONSUMER ID-204355062, APPLICATION NO-2004817398, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2024-25-480 | 30/07/2024 | 0 | WBSEDCL | 0.82 | 0 | 0 | 0
2532 | PASCHIM MEDINIPUR | Midnapore Mechanical | SALIKOTHA AND ADJOINING MOUJAS PWSS , SM/13171 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of SALIKOTHA PWSS. REF CONSUMER ID-204212538, APPLICATION NO-2004593803, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | BP-2023-24-692 | 16/02/2024 | 0 | WBSEDCL | 7.51 | 0 | 0 | 0
2533 | PASCHIM MEDINIPUR | Midnapore Mechanical | SALIKOTHA AND ADJOINING MOUJAS PWSS , SM/13171 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SALIKOTHA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 843/W/MMD | 24/03/2023 | 861 | SOUMEN ELECTRIC | 27.37 | 0 | 0 | 20
2534 | PASCHIM MEDINIPUR | Midnapore Division | AKANDA AND ADJOINING MOUJAS PWSS , SM/13176 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh, Dantan-I & Dantan-II Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (A) Narayangarh block- (1) Kasba, (B) Dantan-I block - (1) Birbhadrapur, (2) Menakapur & (3) Benapura, (C) Dantan-II block - (1) Kusumda (Turkakasba)] | 707/MD | 06/03/2023 | 35 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 20
2535 | PASCHIM MEDINIPUR | Midnapore Division | AKANDA AND ADJOINING MOUJAS PWSS , SM/13176 | New | Material Requisition To Resource Division | 1173/MD | 26/04/2023 | 0 | Resource Division | 26.77 | 0 | 0 | 0
2536 | PASCHIM MEDINIPUR | Central Drilling | AKANDA AND ADJOINING MOUJAS PWSS , SM/13176 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2537 | PASCHIM MEDINIPUR | Midnapore Division | AKANDA AND ADJOINING MOUJAS PWSS , SM/13176 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 0 | 20
2538 | PASCHIM MEDINIPUR | Midnapore Mechanical | AKANDA AND ADJOINING MOUJAS PWSS , SM/13176 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
2539 | PASCHIM MEDINIPUR | Midnapore Division | GODAPIASOL AND ADJOINING MOUJAS PWSS , SM/13077 | New | Material Requisition To Resource Division | 374/MD | 03/02/2023 | 0 | Resource Division | 24.83 | 0 | 0 | 0
2540 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GODAPIASOL AND ADJOINING MOUJAS PWSS , SM/13077 | New | New service connection charges for Godapiasal, tw-I w/s scheme | 81/JMD | 12/02/2024 | 0 | WBSEDCL | 3.18 | 0 | 0 | 0
2541 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GODAPIASOL AND ADJOINING MOUJAS PWSS , SM/13077 | New | New service connection charges for Godapiasal, tw-II w/s scheme | 75/JMD | 12/02/2024 | 0 | WBSEDCL | 3.58 | 0 | 0 | 0
2542 | PASCHIM MEDINIPUR | Central Drilling | GODAPIASOL AND ADJOINING MOUJAS PWSS , SM/13077 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2543 | PASCHIM MEDINIPUR | Midnapore Division | GODAPIASOL AND ADJOINING MOUJAS PWSS , SM/13077 | New | Sinking of Tube well, Laying of Rising Main, Laying distribution pipe line, Pump House & Accommodate FHTC (437 Nos.) including 2 years operation & maintenance under JJM with allied work for Godapiyasol & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. in Paschim Medinipur District. [PART-A] | 2492/MD | 17/07/2023 | 841 | MIDNAPUR PIPE CONCERN | 154.62 | 0 | 0 | 40
2544 | PASCHIM MEDINIPUR | Midnapore Division | GODAPIASOL AND ADJOINING MOUJAS PWSS , SM/13077 | New | Construction of Boundary wall, 150 cum OHR (Torch type with solid raft) & Accommodate FHTC (400 Nos.) under JJM with allied work for Godapiyasol & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. in Paschim Medinipur District. [PART-B] | 3577/MD | 06/12/2024 | 540 | MIDNAPUR PIPE CONCERN | 115.89 | 0 | 0 | 0
2545 | PASCHIM MEDINIPUR | Midnapore Division | KHARIPARA AND IT'S ADJOINING MOUJAS , SM/13125 | New | Material Requisition To Resource Division | 1317/MD | 28/04/2023 | 0 | Resource Division | 25.94 | 0 | 0 | 0
2546 | PASCHIM MEDINIPUR | Central Drilling | KHARIPARA AND IT'S ADJOINING MOUJAS , SM/13125 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Kharipara W/S Scheme (T/W-I & II), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | 1093/CDD | 18/08/2023 | 30 | M/S B.P.TRADING CORPORATION | 25.33 | 0 | 0 | 100
2547 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHARIPARA AND IT'S ADJOINING MOUJAS , SM/13125 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF KHARIPARA PWSS. REFERENCE CONSUMER ID NO-204408594, APPLICATION NO-2004913789, APPLICATION TYPE- NEW CONNECTION, NAME OF CCC- KESHIARY CCC, NAME OF BLOCK- KESHIARY. | C112417261030 | 12/11/2024 | 0 | WBSEDCL | 4.59 | 0 | 0 | 0
2548 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHARIPARA AND IT'S ADJOINING MOUJAS , SM/13125 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF KHARIPARA PWSS. REFERENCE CONSUMER ID NO-204408593, APPLICATION NO-2004913778, APPLICATION TYPE- NEW CONNECTION, NAME OF CCC- KESHIARY CCC, NAME OF BLOCK- KESHIARY. | C112417261960 | 12/11/2024 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
2549 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHARIPARA AND IT'S ADJOINING MOUJAS , SM/13125 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHARIPARA AND IT'S ADJOINING MOUJASunder JJM Program under MMD PHE Dte. | 3075/W/MMD | 29/11/2023 | 489 | DAS ENTERPRISE | 22.6 | 0 | 0 | 25
2550 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kapasda Piped Water Supply Scheme. , SM/06923 | Retrofitting | Extension of pipe line in connection with of FHTC Work at Mouza Kapasda, Uttar Bansboni, Rambar, Khepal at Kapasda PWSS within Sabang Block under Kharagpur Sub-Division Within Midnapore Division, Phe.Dte. District- Paschim Midnapore. | 68/AE/KSD | 03/02/2022 | 15 | KRISHNENDU SEKHAR DAS | 4.83 | 0 | 0 | 0
2551 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kapasda Piped Water Supply Scheme. , SM/06923 | Retrofitting | Continuation Work for Hiring of Bharat Stage-II/III/diesel motor cab(Lusury Taxi)(Standard Non-AC) having contract carriage permit from the reginal transport authority for the office of the Assistant Engineer, Kharagpur Sub-Division, P.H.E. Dte.(For 3 Months) | 116/AE/KSD | 30/01/2023 | 90 | GOBINDA MAITY | 0.48 | 0 | 0 | 100
2552 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARMMA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15576 | Augmentation | Material Requisition To Resource Division | 1417/MD | 04/05/2023 | 0 | Resource Division | 29.1 | 0 | 0 | 0
2553 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARMMA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/15576 | Augmentation | Laying distribution pipe line, Rising Main, Boundary wall, Soil investigation, 350 CuM OHR (Intze type with pile foundation) & Accommodate FHTC (264 Nos.) under JJM with allied work for Augmentation of Dharma Pipe W/S Scheme in Daspur-I Block including supply of all labour & materials within Ghtaal Sub-Division under Midnapore Division, PHE Dte. | 734/MD | 18/03/2025 | 180 | KHAN ENTERPRISE (PARTNER - MD. BABAR ALI KHAN & MD. SHAIN KHAN) | 324.3 | 0 | 0 | 0
2554 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MULGRAM TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15578 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MULGRAM TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | 916/W/MMD | 27/03/2023 | 180 | BALAJI CONSTRUCTION | 12.63 | 0 | 0 | 0
2555 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MULGRAM TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15578 | Augmentation | Material Requisition To Resource Division | 405/MD | 07/02/2023 | 0 | Resource Division | 3.21 | 0 | 0 | 0
2556 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MULGRAM TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15578 | Augmentation | QUOTATION MONEY FOR MULGRAM WATER SUPPLY SCHEME, T W NO 3 JJM WORKS, SCHEME CODE SM/15578, APPLICATION NO 2004759871, REFERENCE ID 204321899, BIRSINGHA CCC, WBSEDCL | C082421719721 | 16/08/2024 | 0 | WBSEDCL | 3.14 | 0 | 0 | 0
2557 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MULGRAM TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15578 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (342) for Augmentation of Mulgram PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2811/MD | 07/08/2023 | 753 | SAMIT PAL | 47.99 | 0 | 0 | 12
2558 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MULGRAM TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15578 | Augmentation | Balance allied works for construction of OHR at Head Works Site of Mulgram water supply Scheme within Ghatal Sub-Division under Midnapore Division PHE.Dte. | 733/AE/GSD | 12/10/2023 | 10 | SUBHASIS DOLAI | 1.84 | 0 | 0 | 100
2559 | PASCHIM MEDINIPUR | Midnapore Mechanical | BHATUIGERYA PIPED WATER SUPPLY SCHEME , SM/15509 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BHATUIGERYA PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | 574/W/MMD | 20/03/2023 | 180 | DEY ENTERPRISE | 25.26 | 0 | 0 | 0
2560 | PASCHIM MEDINIPUR | Midnapore Division | BHATUIGERYA PIPED WATER SUPPLY SCHEME , SM/15509 | New | Material Requisition To Resource Division | 1406/MD | 04/05/2023 | 0 | Resource Division | 57.13 | 0 | 0 | 0
2561 | PASCHIM MEDINIPUR | Midnapore Mechanical | BHATUIGERYA PIPED WATER SUPPLY SCHEME , SM/15509 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of BHATUIGERIA PWSS. REF CONSUMER ID-204269804, APPLICATION NO-2004675318, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-78 | 24/04/2024 | 0 | WBSEDCL | 4.27 | 0 | 0 | 0
2562 | PASCHIM MEDINIPUR | Midnapore Mechanical | BHATUIGERYA PIPED WATER SUPPLY SCHEME , SM/15509 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of BHATUIGERIA PWSS. REF CONSUMER ID-204269077, APPLICATION NO-2004675295, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-79 | 24/04/2024 | 0 | WBSEDCL | 3.82 | 0 | 0 | 0
2563 | PASCHIM MEDINIPUR | Midnapore Division | BHATUIGERYA PIPED WATER SUPPLY SCHEME , SM/15509 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 (Intze type with Pile Foundation) & Accommodate FHTC (2,554 Nos.) including Two years O&M under JJM with allied work for Bhatuigerya & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | 3237/MD | 11/09/2023 | 924 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 837.38 | 0 | 0 | 37
2564 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15533 | New | Material Requisition To Resource Division | 180/MD | 16/01/2023 | 0 | Resource Division | 36.49 | 0 | 0 | 0
2565 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15533 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 536/W/MMD | 20/03/2023 | 180 | AHALYA ENGINEERING WORKS | 45.54 | 0 | 0 | 60
2566 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15533 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-II) | 870/W/MMD | 27/03/2023 | 180 | AHALYA ENGINEERING WORKS | 35.94 | 0 | 0 | 35
2567 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15533 | New | Material Requisition To Resource Division | 3430/MD | 25/11/2024 | 0 | Resource Division | 29.45 | 0 | 0 | 0
2568 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15533 | New | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, ZONE-I, T W NO I , [ RADHANAGAR ] , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004722207, REFERENCE ID 204303570, NIMPURA CCC, WBSEDCL | BP-2024-25-426 | 16/07/2024 | 0 | WBSEDCL | 3.24 | 0 | 0 | 0
2569 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15533 | New | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, ZONE-II, T W NO I, [ BALARAMPUR ] , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004734869, REFERENCE ID 204308441, NIMPURA CCC, WBSEDCL | BP-2024-25-503 | 30/07/2024 | 0 | WBSEDCL | 7.56 | 0 | 0 | 0
2570 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15533 | New | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, ZONE IV , T W NO I , MINI , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004601377, REFERENCE ID 204217215, MANIKPARA CCC, WBSEDCL | BP-2023-24-789 | 06/03/2024 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
2571 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15533 | New | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, ZONE-II, T W NO 2, [PATHRI ], JJM WORKS, BLOCK- KHARAGPUR-I, SCHEME CODE SM/15533, APPLICATION NO 2004834083, REFERENCE ID 204364748, NIMPURA CCC, WBSEDCL | BP-2024-25-602 | 29/08/2024 | 0 | WBSEDCL | 4.53 | 0 | 0 | 0
2572 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15533 | New | ARJUNI WATER SUPPLY SCHEME, ZONE- III, T W - I ,[ SHUSHNIA ] , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004614503, REFERENCE ID 204224894, NIMPURA CCC, WBSEDCL | BP-2023-24-788 | 06/03/2024 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
2573 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15533 | New | QUOTATION MONEY FOR ARJUNI , ZONE-III, TW-I, WATER SUPPLY SCHEME, T W NO I , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004793768, REFERENCE ID 204340976, NIMPURA CCC, WBSEDCL | BP-2024-25-425 | 16/07/2024 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
2574 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15533 | New | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, Z-V, T W NO I , [ HARIHARPUR ] , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004800012, REFERENCE ID 204344344, NIMPURA CCC, WBSEDCL | C092403086596 | 04/09/2024 | 0 | WBSEDCL | 1.52 | 0 | 0 | 0
2575 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15533 | New | Hiring of Bharat Stage IV/V diesel Motor Cabs usury AC), having contract Carriage permit from the Regional Transport Authority for the offies of the Assistant Engineer, Kharagpur Sub-Division, PILE. Die. (For 06 months). period for 23.03.2024 to 22.09.2024 | 1598/AE/KSD | 22/03/2024 | 180 | M/S. SOMNATH | 1.01 | 0 | 0 | 0
2576 | PASCHIM MEDINIPUR | Midnapore Division | TEGHARI AND ITS ADJOINING MOUZAS PWSS , SM/15594 | New | Material Requisition To Resource Division | 1167/MD | 26/04/2023 | 0 | Resource Division | 6.66 | 0 | 0 | 0
2577 | PASCHIM MEDINIPUR | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS , SM/15594 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TEGHARI AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 907/W/MMD | 27/03/2023 | 180 | JYOTY SOLAR POWER | 21.98 | 0 | 0 | 30
2578 | PASCHIM MEDINIPUR | Midnapore Division | TEGHARI AND ITS ADJOINING MOUZAS PWSS , SM/15594 | New | Material Requisition To Resource Division | 3385/MD | 25/11/2024 | 0 | Resource Division | 12.62 | 0 | 0 | 0
2579 | PASCHIM MEDINIPUR | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS , SM/15594 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of TAGHORI PWSS. REF CONSUMER ID-204212284, APPLICATION NO-2004590144, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-689 | 16/02/2024 | 0 | WBSEDCL | 0.29 | 0 | 0 | 0
2580 | PASCHIM MEDINIPUR | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS , SM/15594 | New | ADDITIONAL QUOTATION FEE FOR EFFECTING NSC AT TW-I & II of TEGHORI PWSS. REF ID-860299039, APPLICATION ID-100000106469, APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-126 | 06/05/2024 | 0 | WBSEDCL | 0.24 | 0 | 0 | 0
2581 | PASCHIM MEDINIPUR | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS , SM/15594 | New | ADDITIONAL QUOTATION (2) FEE FOR EFFECTING NSC AT TW-I & II of TEGHORI PWSS. REF ID-860298907, APPLICATION ID-100000106407, APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-125 | 06/05/2024 | 0 | WBSEDCL | 1.49 | 0 | 0 | 0
2582 | PASCHIM MEDINIPUR | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS , SM/15594 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of TAGHORI PWSS. REF CONSUMER ID-204211957, APPLICATION NO-2004590158, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-690 | 16/02/2024 | 0 | WBSEDCL | 8.97 | 0 | 0 | 0
2583 | PASCHIM MEDINIPUR | Midnapore Division | TEGHARI AND ITS ADJOINING MOUZAS PWSS , SM/15594 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 300 Cum & 400 Cum RCC Over Head Reservoir (Intze type with Pile Foundation) & Accommodate FHTC (4,797 Nos.) including Two years O&M under JJM with allied work for Teghari & Thaur & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | 2924/MD | 16/08/2023 | 927 | M/S. A.R. ENTERPRISE. | 1490.96 | 0 | 0 | 49
2584 | PASCHIM MEDINIPUR | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS , SM/15594 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0 | 0 | 50
2585 | PASCHIM MEDINIPUR | Midnapore Division | BAGDOBA AND ADJOINING MOUJAS PWSS , SM/14690 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
2586 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAGDOBA AND ADJOINING MOUJAS PWSS , SM/14690 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAGDOBA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. (Part-II) | 872/W/MMD | 27/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 5.99 | 0 | 0 | 0
2587 | PASCHIM MEDINIPUR | Midnapore Division | BAGDOBA AND ADJOINING MOUJAS PWSS , SM/14690 | New | Material Requisition To Resource Division | 1191/MD | 26/04/2023 | 0 | Resource Division | 20.91 | 0 | 0 | 0
2588 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BAGDOBA AND ADJOINING MOUJAS PWSS , SM/14690 | New | NEW SERVICE CONNECTION CHARGES AT BAGDOBA-I WATER SUPPLY SCHEME | 261/JMD | 23/07/2024 | 0 | WBSEDCL | 4.53 | 0 | 0 | 0
2589 | PASCHIM MEDINIPUR | Central Drilling | BAGDOBA AND ADJOINING MOUJAS PWSS , SM/14690 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2590 | PASCHIM MEDINIPUR | Midnapore Division | BAGDOBA AND ADJOINING MOUJAS PWSS , SM/14690 | New | Route survey & way leave permission along & across of National Highway in Bagdoba PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | 378/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 9.39 | 0 | 0 | 0
2591 | PASCHIM MEDINIPUR | Midnapore Division | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/14493 | New | Material Requisition To Resource Division | 1461/MD | 08/05/2023 | 0 | Resource Division | 62.18 | 0 | 0 | 0
2592 | PASCHIM MEDINIPUR | Midnapore Mechanical | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/14493 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. under JJM Program under MMD PHE Dte. | 459/W/MMD | 20/03/2023 | 180 | BALAJI CONSTRUCTION | 22.89 | 0 | 0 | 60
2593 | PASCHIM MEDINIPUR | Midnapore Division | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/14493 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 300 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (1844 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Manibpur & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 2538/MD | 19/07/2023 | 1031 | SUJATA CONSTRUCTION | 435.01 | 0 | 0 | 25
2594 | PASCHIM MEDINIPUR | Midnapore Mechanical | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/14493 | New | Quotation for new power connection at Manibpur water supply scheme T/W - I | BP-2023-24-619 | 07/02/2024 | 0 | WBSEDCL | 4.3 | 0 | 0 | 0
2595 | PASCHIM MEDINIPUR | Midnapore Mechanical | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/14493 | New | Quotation for new power connection at Manibpur PWSS , T/W - II , Application no - 2004582208 , Ref ID - 204206278 , Madpur CCC | BP-2023-24-708 | 16/02/2024 | 0 | WBSEDCL | 4.14 | 0 | 0 | 0
2596 | PASCHIM MEDINIPUR | Midnapore Division | MURARI AND ADJOINING MOUJAS PWSS , SM/15021 | New | Material Requisition To Resource Division | 1267/MD | 28/04/2023 | 0 | Resource Division | 61.53 | 0 | 0 | 0
2597 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MURARI AND ADJOINING MOUJAS PWSS , SM/15021 | New | New service connection charges for Murari w/s scheme, t/w no.-II | 161/JMD | 31/05/2024 | 0 | WBSEDCL | 4.17 | 0 | 0 | 0
2598 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MURARI AND ADJOINING MOUJAS PWSS , SM/15021 | New | New service connection charges for Murari w/s scheme, t/w no.-I | 160/JMD | 31/05/2024 | 0 | WBSEDCL | 3.76 | 0 | 0 | 0
2599 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MURARI AND ADJOINING MOUJAS PWSS , SM/15021 | New | New Service Connection Charges for Murari T/W - III PWSS | 350/JMD | 13/09/2024 | 0 | WBSEDCL | 3.48 | 0 | 0 | 0
2600 | PASCHIM MEDINIPUR | Central Drilling | MURARI AND ADJOINING MOUJAS PWSS , SM/15021 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2601 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15590 | New | KHEMASOLI WATER SUPPLY SCHEME , TUBE WELL NO II, SCHEME CODE - SM/15590, BLOCK KHARAGPUR - I, MB NO 3580, PAGE 30-31, and ORIGINAL QUOTATION | BP-2023-24-261 | 26/09/2023 | 0 | WBSEDCL | 0.54 | 0 | 0 | 0
2602 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15590 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II and III) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 920/W/MMD | 27/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 31.54 | 0 | 0 | 43
2603 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15590 | New | Sinking of Tube well, Laying distribution pipe line with Rising main, Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20.00 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, FHTC (261 Nos.) & Two years O & M under JJM with allied work for Khemasoli & its adjoining mouzas W/S Scheme (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 946/MD | 05/04/2023 | 1000 | GOUTAM PARIA | 55.7 | 0 | 0 | 95
2604 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15590 | New | Sinking of Tube well, Laying distribution pipe line with Rising main, Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20.00 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, FHTC (121 Nos.) & Two years O & M under JJM with allied work for Khemasoli & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 832/MD | 15/03/2024 | 60 | RITESH AGARWALL | 41.32 | 0 | 0 | 0
2605 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15590 | New | Material Requisition To Resource Division | 3431/MD | 25/11/2024 | 0 | Resource Division | 4.18 | 0 | 0 | 0
2606 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15590 | New | QUOTATION MONEY FOR KHEMASOLI WATER SUPPLY SCHEME, ZONE-I, T W NO I, [ KEMASOLI], JJM WORKS, SCHEME CODE SM/15590, APPLICATION NO 2004825735, REFERENCE ID 204360220, NIMPURA CCC, WBSEDCL | BP-2024-25-294 | 27/08/2024 | 0 | WBSEDCL | 3.1 | 0 | 0 | 0
2607 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15590 | New | Sinking of Tube well, Laying distribution pipe line with Rising main, Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20.00 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, FHTC (281 Nos.) & Two years O & M under JJM with allied work for Khemasoli & its adjoining mouzas W/S Scheme (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 1797/MD | 07/06/2024 | 301 | A K SIKDAR | 60.48 | 0 | 0 | 57
2608 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhemwa (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15219 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Bhemwa PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1659/MD | 27/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.31 | 0 | 0 | 0
2609 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhemwa (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15219 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0 | 0 | 25
2610 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhemwa (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15219 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0 | 0 | 100
2611 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhemwa (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15219 | Augmentation | Sinking of Tube well, Laying distribution pipeline & Construction of Pump House for Rejuvenation of Ground Water Based PWSS for Bhemwa (Part) under JJM of Sabang block in Paschim Medinipur District under Midnapore Division, PHE Dte. | 2430/MD | 13/07/2023 | 597 | SANKAR PRASAD MAITY | 94.81 | 0 | 0 | 85
2612 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhemwa (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15219 | Augmentation | QUOTATION MONEY FOR BHEWMA WATER SUPPLY SCHEME,ZONE-II, T W - III , JJM WORKS, SCHEME CODE SM/15219, PARENT CODE SM/03856 , APPLICATION NO 2004571035, REFERENCE ID 204198622, SABONG CCC, WBSEDCL | BP-2023-24-607 | 07/02/2024 | 0 | WBSEDCL | 4 | 0 | 0 | 0
2613 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhemwa (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/15219 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhemwa (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 612/W/MMD | 20/03/2023 | 854 | A.K.SIKDAR | 10.79 | 0 | 0 | 100
2614 | PASCHIM MEDINIPUR | Midnapore Division | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS , SM/16259 | New | Material Requisition To Resource Division | 198/MD | 16/01/2023 | 0 | Resource Division | 26.69 | 0 | 0 | 0
2615 | PASCHIM MEDINIPUR | Midnapore Division | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS , SM/16259 | New | Material Requisition To Resource Division | 3434/MD | 25/11/2024 | 0 | Resource Division | 11.38 | 0 | 0 | 0
2616 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS , SM/16259 | New | Quotation for new power connection at Chak keshi PWSS P/H- II , application no - 2004609056 , Ref id - 204222612 | BP-2023-24-772 | 06/03/2024 | 0 | WBSEDCL | 3.37 | 0 | 0 | 0
2617 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS , SM/16259 | New | Quotation for new power connection at ckakkesi PWSS , T/W - I , Application no - 2004582548 , Ref ID - 204206277 , Madpur CCC | BP-2023-24-707 | 16/02/2024 | 0 | WBSEDCL | 3.51 | 0 | 0 | 0
2618 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS , SM/16259 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAKKESHI AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 830/W/MMD | 24/03/2023 | 739 | WEST BENGAL ENGINEERING CO. | 22.63 | 0 | 0 | 80
2619 | PASCHIM MEDINIPUR | Midnapore Division | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS , SM/16259 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 200 Cum OHR (Intze type with Raft foundation) & Accommodate FHTC (1847 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Chakkeshi & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 2525/MD | 18/07/2023 | 983 | SUJATA CONSTRUCTION | 482.35 | 0 | 0 | 75
2620 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Jatra Bansiriasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17377 | Solarisation | Solarization of grid connected pumping installation at Jatra Bansiriasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 780/W/MMD | 24/03/2023 | 180 | MANORANJAN DEY | 6.26 | 0 | 0 | 0
2621 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Solarization of grid connected pumping installation at Jatra Bansiriasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17377 | Solarisation | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
2622 | PASCHIM MEDINIPUR | Midnapore Division | SHUKHNATOR AND ADJOINING MOUJAS PWSS , SM/18020 | New | Material Requisition To Resource Division | 1227/MD | 27/04/2023 | 0 | Resource Division | 38.62 | 0 | 0 | 0
2623 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SHUKHNATOR AND ADJOINING MOUJAS PWSS , SM/18020 | New | Quotation for new service connection at Sukhnator T/W-I water supply scheme. | 43/JMD | 29/04/2024 | 0 | WBSEDCL | 14.15 | 0 | 0 | 0
2624 | PASCHIM MEDINIPUR | Central Drilling | SHUKHNATOR AND ADJOINING MOUJAS PWSS , SM/18020 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2625 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. , SM/17949 | Augmentation | Material Requisition To Resource Division | 200/MD | 16/01/2023 | 0 | Resource Division | 1.26 | 0 | 0 | 0
2626 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. , SM/17949 | Augmentation | QUOTATION FOR NEW POWER CONNECTION OF SHYAMSUNDAR [AUG.] WATER SUPPLY ASCHEME [ APPLICATION --2004480397 REFERENCE ID ----204122721 SABONG CCC, QUOTATION NO ---2004480397/QUOT/03 DATED 26/10/2023, SCHEME NAME --- SHYAMSUNDAR AUG. , SCHEME CODE ---SM/17949 , MB NO--3580 ] | BP-2023-24-343 | 10/11/2023 | 0 | WBSEDCL | 3.49 | 0 | 0 | 0
2627 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. , SM/17949 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall for Augmentation of Shyamsundarpur Water Supply Scheme within Sabang Block under Midnapore Division, PHE Dte. | 953/MD | 06/04/2023 | 825 | CREATION CONSTRUCTION | 222.15 | 0 | 0 | 90
2628 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. , SM/17949 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 458/W/MMD | 20/03/2023 | 180 | S.B.ENTERPRISE | 10.91 | 0 | 0 | 100
2629 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Keshpur PWSS in the District of Paschim Medinipur under JJM programme. , SM/17776 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Keshpur PWSS in the District of Paschim Medinipur under JJM programme. under JJM Program under MMD PHE Dte. | 1067/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 11.39 | 0 | 0 | 0
2630 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Kolanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17778 | Solarisation | Solarization of grid connected pumping installation Kolanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 980/W/MMD | 29/03/2023 | 805 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 90
2631 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Solarization of grid connected pumping installation Kashijora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17798 | Solarisation | Quotation bill for Providing solarization of WBSEDCL energised pumping installation at Kashijora w/s scheme (T/W No. I) | 257/JMD | 10/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2632 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Solarization of grid connected pumping installation Kashijora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17798 | Solarisation | Quation bill for Kashijora T/W -I PWSS | 425/JMD | 27/11/2024 | 0 | WBSEDCL | 0.23 | 0 | 0 | 0
2633 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Kashijora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17798 | Solarisation | Solarization of grid connected pumping installation Kashijora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 967/W/MMD | 29/03/2023 | 720 | RSA ENTERPRISE | 6.25 | 0 | 0 | 100
2634 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Balarampur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17810 | Solarisation | Solarization of grid connected pumping installation Balarampur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 976/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
2635 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Mohanpur (Mohanpur) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17381 | Solarisation | Solarization of grid connected pumping installation at Mohanpur (Mohanpur) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 707/W/MMD | 23/03/2023 | 180 | R.S. ENTERPRISE | 6.26 | 0 | 0 | 0
2636 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Mohanpur (Mohanpur) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17381 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 720/MMSD-I | 07/06/2024 | 15 | SUBHASIS ROY | 2.29 | 0 | 0 | 100
2637 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Mohanpur (Mohanpur) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17381 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going solarisation / rejuvenation as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 716/MMSD-I | 07/06/2024 | 15 | MUKHERJEE ART CENTRE | 1.93 | 0 | 0 | 100
2638 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Dhaneswarpur (Block Dantan-II) PWSS in the District of Paschim Medinipur under JJM programme. , SM/17728 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Dhaneswarpur (Block Dantan-II) PWSS in the District of Paschim Medinipur under JJM programme. under JJM Program under MMD PHE Dte. | 1066/W/MMD | 29/03/2023 | 308 | BHABANI PRASAD MANNA | 11.39 | 0 | 0 | 100
2639 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18235 | New | Material Requisition To Resource Division | 78/MD | 09/01/2023 | 0 | Resource Division | 32.78 | 0 | 0 | 0
2640 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18235 | New | Material Requisition To Resource Division | 3329/MD | 25/11/2024 | 0 | Resource Division | 21.66 | 0 | 0 | 0
2641 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18235 | New | New Service connection charges. | 83/JMD | 21/03/2024 | 0 | WBSEDCL | 3.28 | 0 | 0 | 0
2642 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18235 | New | Quotation for new service connection at RAMKRISHNAPUR T/W-II water supply scheme. | 124/JMD | 20/05/2024 | 0 | WBSEDCL | 3.17 | 0 | 0 | 0
2643 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18235 | New | SHIFTING OF 11 KV HTOH LINE HATPUKUR FEEDER FOR CONSTRUCTION OF RAMKRISHNAPUR T/W-I P.H. | 234/JMD | 09/07/2024 | 0 | WBSEDCL | 2.52 | 0 | 0 | 0
2644 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18235 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 450 cum OHR each (Intze type with pile foundation) & Accommodate FHTC (6283 Nos.) under JJM with allied work for Purshuri & Ramkrishnapur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2422/MD | 13/07/2023 | 808 | GOBINDA MAITY | 1504.9 | 0 | 0 | 60
2645 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18235 | New | Laying of rising main & additional distribution pipe line due to re-design of mouzas Pipe W/S Schemes [Mangrul / Ramkrishnapur / Bagchhari / Purshuri] at Chandrakona-I block under Ghatal Sub-Division, PHE Dte. | 55/MD | 07/01/2025 | 266 | GOBINDA MAITY | 79.62 | 0 | 0 | 60
2646 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18235 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | 1491/W/MMD | 22/06/2023 | 715 | SUJOY RANJAN BHOWMICK | 23.69 | 0 | 0 | 100
2647 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANIKKUNDA TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18237 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANIKKUNDA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | 1492/W/MMD | 22/06/2023 | 180 | S.K.ENTERPRISE | 25.26 | 0 | 0 | 0
2648 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANIKKUNDA TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18237 | New | Material Requisition To Resource Division | 73/MD | 09/01/2023 | 0 | Resource Division | 56.53 | 0 | 0 | 0
2649 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANIKKUNDA TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18237 | New | Material Requisition To Resource Division | 1507/MD | 12/05/2023 | 0 | Resource Division | 15.91 | 0 | 0 | 0
2650 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANIKKUNDA TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18237 | New | New Service connection charges. | 22/JMD | 04/03/2024 | 0 | WBSEDCL | 6.8 | 0 | 0 | 0
2651 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANIKKUNDA TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18237 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,583 Nos.) under JJM with allied work for Manikkunda PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 3233/MD | 11/09/2023 | 898 | M/S. A.R. ENTERPRISE. | 959.94 | 0 | 0 | 0
2652 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Amlagora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17739 | Solarisation | Solarization of grid connected pumping installation Amlagora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 973/W/MMD | 29/03/2023 | 180 | RSA ENTERPRISE | 6.25 | 0 | 0 | 100
2653 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Solarization of grid connected pumping installation Amlagora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17739 | Solarisation | New Service connection charges. | 66/JMD | 13/03/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2654 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Solarization of grid connected pumping installation Amlagora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17739 | Solarisation | solar quotation charges at Amlagora water supply scheme | 20/JMD | 15/04/2024 | 0 | WBSEDCL | 0.31 | 0 | 0 | 0
2655 | PASCHIM MEDINIPUR | Midnapore Division | DUAN-II AND ITS ADJOINING MOUJAS PWSS , SM/17616 | New | Material Requisition To Resource Division | 1519/MD | 12/05/2023 | 0 | Resource Division | 24.68 | 0 | 0 | 0
2656 | PASCHIM MEDINIPUR | Midnapore Mechanical | DUAN-II AND ITS ADJOINING MOUJAS PWSS , SM/17616 | New | Electrict quotation bill for TW-I of DUAN-II pwss (Ref Consumar ID-204235948),Application No-2004627235,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. | BP-2023-24-815 | 13/03/2024 | 0 | WBSEDCL | 3.36 | 0 | 0 | 0
2657 | PASCHIM MEDINIPUR | Midnapore Mechanical | DUAN-II AND ITS ADJOINING MOUJAS PWSS , SM/17616 | New | Electrict quotation bill for TW-II of DUAN-II pwss (Ref Consumar ID-204235945),Application No-2004627252,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. | BP-2023-24-816 | 13/03/2024 | 0 | WBSEDCL | 3.26 | 0 | 0 | 0
2658 | PASCHIM MEDINIPUR | Midnapore Division | DUAN-II AND ITS ADJOINING MOUJAS PWSS , SM/17616 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House, Boundary Wall, laying of Rising Main & Providing Functional Household Tap Connection (4740 Nos) including 2 years Operation & Maintenance For Dingal, Duan and Gobindapur Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | 2826/MD | 07/08/2023 | 785 | GOBINDA MAITY | 1375.06 | 0 | 0 | 74
2659 | PASCHIM MEDINIPUR | Midnapore Mechanical | DUAN-II AND ITS ADJOINING MOUJAS PWSS , SM/17616 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DUAN-II AND ITS ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 477/W/MMD | 20/03/2023 | 716 | M/S. SAJAHAN CHOWDHURY | 23 | 0 | 0 | 60
2660 | PASCHIM MEDINIPUR | Midnapore Division | KHASKENDU BAGICHA AND IT'S ADJOINING MOUJAS PWSS , SM/17618 | New | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, 350 cum OHR (Intze type with solid raft) & Accommodate FHTC (2,170 Nos.) including 2 years operation & maintenance under JJM with allied work for Khaskendu Bagicha & its adjoining mouzas W/S scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5062/MD | 26/10/2023 | 180 | CIVCON CONSTRUCTION PVT. LTD. | 548.71 | 0 | 0 | 0
2661 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHASKENDU BAGICHA AND IT'S ADJOINING MOUJAS PWSS , SM/17618 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHASKENDU BAGICHA AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 832/W/MMD | 24/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 23.76 | 0 | 0 | 0
2662 | PASCHIM MEDINIPUR | Midnapore Division | KHASKENDU BAGICHA AND IT'S ADJOINING MOUJAS PWSS , SM/17618 | New | Material Requisition To Resource Division | 1580/MD | 15/05/2023 | 0 | Resource Division | 25.74 | 0 | 0 | 0
2663 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Ranibazar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17821 | Solarisation | Solarization of grid connected pumping installation Ranibazar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 975/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
2664 | PASCHIM MEDINIPUR | Midnapore Division | Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17573 | New | Material Requisition To Resource Division | 2009/MD | 16/05/2023 | 0 | Resource Division | 24.11 | 0 | 0 | 0
2665 | PASCHIM MEDINIPUR | Midnapore Division | Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17573 | New | Material Requisition To Resource Division | 1459 | 08/05/2023 | 0 | Resource Division | 7.86 | 0 | 0 | 0
2666 | PASCHIM MEDINIPUR | Midnapore Mechanical | Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17573 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 1199/W/MMD | 25/04/2023 | 180 | TAPAN KUMAR SARKAR | 22.62 | 0 | 0 | 50
2667 | PASCHIM MEDINIPUR | Midnapore Division | Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17573 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 0 | 55
2668 | PASCHIM MEDINIPUR | Midnapore Division | KADABANI AND ADJOINING MOUJAS PWSS , SM/18188 | New | Material Requisition To Resource Division | 1155/MD | 25/04/2023 | 0 | Resource Division | 18.05 | 0 | 0 | 0
2669 | PASCHIM MEDINIPUR | Midnapore Mechanical | KADABANI AND ADJOINING MOUJAS PWSS , SM/18188 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KADABANI AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 1122/W/MMD | 12/04/2023 | 180 | ABHIJIT MUKHERJEE | 21.56 | 0 | 0 | 40
2670 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | KADABANI AND ADJOINING MOUJAS PWSS , SM/18188 | New | NEW SERVICE CONNECTION CHARGES AT KADABONI TW-I WATER SUPPLY SCHEME | 248/JMD | 10/07/2024 | 0 | WBSEDCL | 7.78 | 0 | 0 | 0
2671 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | Laying distribution system & Accommodate FHTC (300 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-D] | 2433/MD | 13/07/2023 | 60 | DEV KUMAR ADAK | 44.86 | 0 | 0 | 0
2672 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | Laying distribution system & Accommodate FHTC (200 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-E] | 2434/MD | 13/07/2023 | 60 | M/S JITEN BANARJEE | 37.78 | 0 | 0 | 0
2673 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | Laying distribution system & Accommodate FHTC (200 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-F] | 2435/MD | 13/07/2023 | 45 | SUBHASIS DOLAI | 28.79 | 0 | 0 | 0
2674 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | Laying distribution system with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-G] | 2592/MD | 21/07/2023 | 30 | LOWADA HI-TECHTONIC ENGINEER,S CO. OP. SOCIETY LTD. | 18.92 | 0 | 0 | 0
2675 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | Material Requisition To Resource Division | 77/MD | 09/01/2023 | 0 | Resource Division | 38.5 | 0 | 0 | 0
2676 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | 1494/W/MMD | 22/06/2023 | 180 | DEBJYOTI BASU | 27.38 | 0 | 0 | 80
2677 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | Laying distribution system & Accommodate FHTC (500 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 2594/MD | 21/07/2023 | 60 | R. CONSTRUCTION | 92.24 | 0 | 0 | 40
2678 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | Sinking of 2 (Two) Nos. 300 X 200 mm dia. X 190 mtr. depth deep tube well by direct rotary method for Head work site & 2nd tube well site of Krishnapur PWSS within Chandrakona-II block under Midnapore Division, P.H.E Dte. [PART-I] | 2423/MD | 13/07/2023 | 21 | SAJAL JANA | 22.7 | 0 | 0 | 50
2679 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | Material Requisition To Resource Division | 3333/MD | 25/11/2024 | 0 | Resource Division | 21.7 | 0 | 0 | 0
2680 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | Quotation for new service connection at Krishnapur T/W-II water supply scheme. | 308/JMD | 14/08/2024 | 0 | WBSEDCL | 3.11 | 0 | 0 | 0
2681 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | New Service connection charges. | 26/JMD | 06/03/2024 | 0 | WBSEDCL | 3.38 | 0 | 0 | 0
2682 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | Quotation for Krishnapur T/W - I water supply scheme. | 30/JMD | 11/03/2024 | 0 | WBSEDCL | 3.38 | 0 | 0 | 0
2683 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. , SM/18233 | New | Laying distribution pipe line, Rising main & Accommodate FHTC (500 Nos.) including 2 years operation & maintenance with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 2809/MD | 07/08/2023 | 812 | M/S. D.K.H.CONSTRUCTION | 149.24 | 0 | 0 | 35
2684 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chotkhelna PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17306 | Solarisation | Solarization of grid connected pumping installation at Chotkhelna PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 684/W/MMD | 23/03/2023 | 180 | NITESH MANAGEMENT | 6.25 | 0 | 0 | 60
2685 | PASCHIM MEDINIPUR | Midnapore Division | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17562 | New | Material Requisition To Resource Division | 2011/MD | 16/05/2023 | 0 | Resource Division | 37.87 | 0 | 0 | 0
2686 | PASCHIM MEDINIPUR | Midnapore Division | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17562 | New | Material Requisition To Resource Division | 1462 | 08/05/2023 | 0 | Resource Division | 13.6 | 0 | 0 | 0
2687 | PASCHIM MEDINIPUR | Midnapore Division | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17562 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 200 Cum & 300 Cum OHR (Intze type with Solid raft/ Pile Foundation) & Accommodate FHTC (6,605 Nos.) including Two years O&M under JJM with allied work for Jarisai PWSS (Zone-I & Zone-II) & Kashida (Zone-I & Zone-II) with in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5360/MD | 30/11/2023 | 673 | GOBINDA MAITY | 2125.38 | 0 | 0 | 46
2688 | PASCHIM MEDINIPUR | Midnapore Mechanical | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17562 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 1194/W/MMD | 25/04/2023 | 885 | RISHAV ENTERPRISE | 22.95 | 0 | 0 | 80
2689 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18615 | New | Material Requisition To Resource Division | 4056/MD | 12/10/2023 | 0 | Resource Division | 46.13 | 0 | 0 | 0
2690 | PASCHIM MEDINIPUR | Midnapore Mechanical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18615 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at MANGRUL Water supply scheme, Chandrakona -I block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 2283/W/MMD | 29/08/2023 | 180 | S.B.ENTERPRISE | 30.52 | 0 | 0 | 90
2691 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18615 | New | Quotation for Mangrul T/W - 2 water supply scheme. | 67/JMD | 13/03/2024 | 0 | WBSEDCL | 2.79 | 0 | 0 | 0
2692 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18615 | New | Aditional quotation of new service connection at Mangrul T/W-I due to way leave problem under Ramjibanpur C.C.C. | 296/JMD | 09/08/2024 | 0 | WBSEDCL | 0.49 | 0 | 0 | 0
2693 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18615 | New | New Service connection charges. | 79/JMD | 20/03/2024 | 0 | WBSEDCL | 3.69 | 0 | 0 | 0
2694 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18615 | New | Sinking of Tube wells, Construction of 450 CuM Capacity R.C.C Over Head Reservoirs (Over Pile Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (6507) for Bagchhari & Mangrul Pipe W/S Scheme including Two years O&M within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | 2825/MD | 07/08/2023 | 783 | GOBINDA MAITY | 1766.48 | 0 | 0 | 70
2695 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18615 | New | Laying of rising main & additional distribution pipe line due to re-design of mouzas Pipe W/S Schemes [Mangrul / Ramkrishnapur / Bagchhari / Purshuri] at Chandrakona-I block under Ghatal Sub-Division, PHE Dte. | 55/MD | 07/01/2025 | 266 | GOBINDA MAITY | 79.62 | 0 | 0 | 60
2696 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/16999 | Augmentation | Material Requisition To Resource Division | 421/MD | 08/02/2023 | 0 | Resource Division | 3.52 | 0 | 0 | 0
2697 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/16999 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 1184/W/MMD | 25/04/2023 | 180 | AMUSAR IMPEX PVT. LTD | 23.77 | 0 | 0 | 15
2698 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/16999 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Soil investigation, Construction of 200 cum OHR & Accommodate FHTC (125 Nos.) under JJM with allied work for Augmentation of Sonakania Pipe W/S Scheme in Dantan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 3143/MD | 04/10/2024 | 360 | SAI TUBE CO. | 156.46 | 0 | 0 | 18
2699 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/16999 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Additional Tw No-II (Boosting) of SONAKANIA water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist.:- Paschim Medinipur | 1066/W/MMD | 14/03/2024 | 180 | MANORANJAN DEY | 6.72 | 0 | 0 | 0
2700 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/16999 | Augmentation | Repairing of 2nd Pump House & Boundary wall for Sonakania PWSS within Dantan-I block under Midnapore Division, PHE Dte. | 569/AE/HQ/MD | 28/02/2025 | 45 | PROVAT KUMAR DE | 1.86 | 0 | 0 | 100
2701 | PASCHIM MEDINIPUR | Midnapore Division | GROUND BASED MINI PIPED WATER SUPPLY SCHEME FOR DEULBERE MOUZA, BLOCK CHANDRAKONA-II, DISTRICT-PASCHIM MEDINIPUR , SM/17008 | New | Sinking of 150 X 100 mm dia. X 165 mtr. depth deep boosting tube well by direct rotary method for Deulbere PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 2521/MD | 18/07/2023 | 10 | ANNAPURNA TUBEWELL WORKS | 6.18 | 0 | 0 | 100
2702 | PASCHIM MEDINIPUR | Midnapore Division | GROUND BASED MINI PIPED WATER SUPPLY SCHEME FOR DEULBERE MOUZA, BLOCK CHANDRAKONA-II, DISTRICT-PASCHIM MEDINIPUR , SM/17008 | New | Material Requisition To Resource Division | 1360/MD | 02/05/2023 | 0 | Resource Division | 0.83 | 0 | 0 | 0
2703 | PASCHIM MEDINIPUR | Midnapore Division | GROUND BASED MINI PIPED WATER SUPPLY SCHEME FOR DEULBERE MOUZA, BLOCK CHANDRAKONA-II, DISTRICT-PASCHIM MEDINIPUR , SM/17008 | New | Laying distribution pipe line, Accommodate FHTC (135 Nos.) under JJM with allied work including 1 year O & M for Deulbere PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 2674/MD | 26/07/2023 | 45 | SUBHASIS DOLAI | 27.2 | 0 | 0 | 90
2704 | PASCHIM MEDINIPUR | Midnapore Mechanical | GROUND BASED MINI PIPED WATER SUPPLY SCHEME FOR DEULBERE MOUZA, BLOCK CHANDRAKONA-II, DISTRICT-PASCHIM MEDINIPUR , SM/17008 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER CHANDRAKONA - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICTunder JJM Program under MMD PHE Dte. | 1693/W/MMD | 04/08/2023 | 180 | AMUSAR IMPEX PVT. LTD | 49.92 | 0 | 0 | 80
2705 | PASCHIM MEDINIPUR | Midnapore Division | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19044 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Dadpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. [Name of Proposed PWSS Gopalnagar & its adjoining Mouzas PWSS instead of Dadpur & its adjoining Mouzas PWSS] | 1065/MD | 02/06/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5.24 | 0 | 0 | 100
2706 | PASCHIM MEDINIPUR | Midnapore Division | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19044 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Gopalnagar & its adjoining Mouzas PWSS instead Dadpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | 1266/MD | 23/06/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.16 | 0 | 0 | 100
2707 | PASCHIM MEDINIPUR | Midnapore Division | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19044 | New | Material Requisition To Resource Division | 63/MD | 09/01/2023 | 0 | Resource Division | 104.79 | 0 | 0 | 0
2708 | PASCHIM MEDINIPUR | Midnapore Division | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19044 | New | Material Requisition To Resource Division | 3335/MD | 25/11/2024 | 0 | Resource Division | 15.82 | 0 | 0 | 0
2709 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19044 | New | QUOTATION MONEY FOR GOPALNAGAR WATER SUPPLY SCHEME, T W - II , JJM WORKS, SCHEME CODE SM/19044, APPLICATION NO 2004702574, REFERENCE ID 204287860, DASPUR CCC, WBSEDCL | BP-2024-25-160 | 13/05/2024 | 0 | WBSEDCL | 7.03 | 0 | 0 | 0
2710 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19044 | New | QUOTATION MONEY FOR GOPALNAGAR WATER SUPPLY SCHEME, T W - I , JJM WORKS, SCHEME CODE SM/19044, APPLICATION NO 2004696196, REFERENCE ID 204284323, DASPUR CCC, WBSEDCL | BP-2024-25-113 | 06/05/2024 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
2711 | PASCHIM MEDINIPUR | Midnapore Division | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19044 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 500 & 600 cum OHR (Intze type with pile foundation) & Accommodate FHTC (5,406 nos.) under JJM with allied work for Gopalnagar & Kalara PWSS in Daspur-I Block including supply of all labour & materials including Two (02) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2953/MD | 17/08/2023 | 772 | GOBINDA MAITY | 1693.15 | 0 | 0 | 20
2712 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19044 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 3088/W/MMD | 29/11/2023 | 495 | S.P. ENTERPRISE | 22.95 | 0 | 0 | 80
2713 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Mangrajpur mouzas, Block - Sabang, District - Paschim Medinipur , SM/18785 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Magrajpur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 559/W/MMD | 12/04/2022 | 120 | M/S NABIN GOPAL SENGUPTA | 6.46 | 0 | 0 | 100
2714 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Mangrajpur mouzas, Block - Sabang, District - Paschim Medinipur , SM/18785 | New | Electric Quotation for MAGRAJPUR (MINIPIPED) Water Supply Scheme, (Ref. ID-203942445) | BP-2023-24-237 | 12/09/2023 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
2715 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mangrajpur mouzas, Block - Sabang, District - Paschim Medinipur , SM/18785 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Mangrajpur, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 3165/MD | 31/08/2023 | 547 | SANKAR PRASAD MAITY | 29.51 | 0 | 0 | 100
2716 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/19050 | Augmentation | Material Requisition To Resource Division | 1166/MD | 26/04/2023 | 0 | Resource Division | 14.14 | 0 | 0 | 0
2717 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/19050 | Augmentation | Sinking of Tube Well, Construction of 250 Cum OHR including Soil Investigation, Laying distribution pipe line, Pump House, Boundary wall for Augmentation of Barisha (Zone-II) PWSS in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5513/MD | 15/12/2023 | 180 | NIRMAL UDYOG | 366.33 | 0 | 0 | 5
2718 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/19050 | Augmentation | ELECTRIC QUOTATION BILL FOR TW NO-III, Zone -I OF BARISHA PWSS (NARANGADIHI). REF CONSUMER ID-204376280, APPLICATION NO-2004857600, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA | BP-2024-25-650 | 06/09/2024 | 0 | WBSEDCL | 3.6 | 0 | 0 | 0
2719 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/19050 | Augmentation | ELECTRIC QUOTATION BILL FOR ZONE-I , TW NO-III OF BARISHA PWSS. REF CONSUMER ID-204351761, APPLICATION NO-2004812598, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA | BP-2024-25-459 | 23/07/2024 | 0 | WBSEDCL | 3.6 | 0 | 0 | 0
2720 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/19050 | Augmentation | ELECTRIC QUOTATION BILL FOR ZONE-II, TW NO-III OF BARISHA PWSS. REF CONSUMER ID-204391668, APPLICATION NO-2004886574, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA | C102415730586 | 05/10/2024 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
2721 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/19050 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I and II/II)} and its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 3098/W/MMD | 29/11/2023 | 540 | DEBJYOTI BASU | 34.18 | 0 | 0 | 25
2722 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/19050 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall for Augmentation of Barisha (Zone-I) PWSS in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5512/MD | 15/12/2023 | 726 | KRISHNENDU SEKHAR DAS | 221.3 | 0 | 0 | 35
2723 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/19050 | Augmentation | Laying of Distribution pipe line (extension) for Barisha (Zone-1) PWSS under Pingla Block within Midnapore Division, PHE Dte. | 59/MD | 07/01/2025 | 375 | KRISHNENDU SEKHAR DAS | 48.99 | 0 | 0 | 10
2724 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Birsingha PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17797 | Solarisation | Solarization of grid connected pumping installation Birsingha PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 991/W/MMD | 29/03/2023 | 180 | ABHIJIT MUKHERJEE | 6.25 | 0 | 0 | 77
2725 | PASCHIM MEDINIPUR | Midnapore Division | MELERACHAK AND ITS ADJOINING MOUZAS PWSS , SM/18587 | New | Material Requisition To Resource Division | 179/MD | 16/01/2023 | 0 | Resource Division | 16.2 | 0 | 0 | 0
2726 | PASCHIM MEDINIPUR | Midnapore Mechanical | MELERACHAK AND ITS ADJOINING MOUZAS PWSS , SM/18587 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MELERACHAK AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | 1729/W/MMD | 09/08/2023 | 180 | SUJOY RANJAN BHOWMICK | 27.36 | 0 | 0 | 60
2727 | PASCHIM MEDINIPUR | Midnapore Division | MELERACHAK AND ITS ADJOINING MOUZAS PWSS , SM/18587 | New | Material Requisition To Resource Division | 3439/MD | 25/11/2024 | 0 | Resource Division | 21.97 | 0 | 0 | 0
2728 | PASCHIM MEDINIPUR | Midnapore Mechanical | MELERACHAK AND ITS ADJOINING MOUZAS PWSS , SM/18587 | New | Quotation for new power connection at Melerachak water supply scheme T/W - I | BP-2023-24-630 | 08/02/2024 | 0 | WBSEDCL | 4.37 | 0 | 0 | 0
2729 | PASCHIM MEDINIPUR | Midnapore Mechanical | MELERACHAK AND ITS ADJOINING MOUZAS PWSS , SM/18587 | New | Quotation for new power connection at Melerachak PWSS , T/W - I , Application no - 2004582161 , Ref ID - 204206275 , Madpur CCC | BP-2023-24-706 | 16/02/2024 | 0 | WBSEDCL | 4.25 | 0 | 0 | 0
2730 | PASCHIM MEDINIPUR | Midnapore Division | MELERACHAK AND ITS ADJOINING MOUZAS PWSS , SM/18587 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (3,567 nos.) under JJM with allied work including 02 (Tow) Years Operation & Maintenance for Melerchak PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 3275/MD | 13/09/2023 | 720 | TAPAS SANTRA | 973.12 | 0 | 0 | 73
2731 | PASCHIM MEDINIPUR | Central Drilling | DAKSHINDIHA AND ADJOINING MOUJAS PWSS , SM/13079 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm x 150mm x 220Mtrs. Depth) by utilising Departmental for Dakshindiha W/S Scheme (T/W- I & II) , Keshiarya block under Paschim Medinipur District, CDD PHE Dte | 391/CDD | 18/05/2023 | 30 | PADMA ENGINEERING & CO. | 25.43 | 0 | 0 | 100
2732 | PASCHIM MEDINIPUR | Midnapore Division | DAKSHINDIHA AND ADJOINING MOUJAS PWSS , SM/13079 | New | Material Requisition To Resource Division | 1312/MD | 28/04/2023 | 0 | Resource Division | 25.9 | 0 | 0 | 0
2733 | PASCHIM MEDINIPUR | Midnapore Mechanical | DAKSHINDIHA AND ADJOINING MOUJAS PWSS , SM/13079 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DAKSHINDIHA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 3082/W/MMD | 29/11/2023 | 180 | CONCORD ENGINEERING | 21.56 | 0 | 0 | 30
2734 | PASCHIM MEDINIPUR | Midnapore Mechanical | DAKSHINDIHA AND ADJOINING MOUJAS PWSS , SM/13079 | New | ELECTRIC QUOTATION BILL TW NO-I of DAKHINDIHA PWSS. REF CONSUMER ID-204204413, APPLICATION NO-2004578886, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2023-24-633 | 08/02/2024 | 0 | WBSEDCL | 2.9 | 0 | 0 | 0
2735 | PASCHIM MEDINIPUR | Midnapore Mechanical | DAKSHINDIHA AND ADJOINING MOUJAS PWSS , SM/13079 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of DAKHINDIHA PWSS. REF CONSUMER ID-204204414, APPLICATION NO-2004578903, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2023-24-632 | 08/02/2024 | 0 | WBSEDCL | 3.04 | 0 | 0 | 0
2736 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pratappur PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | 371/MD | 25/02/2021 | 15 | DIPAK KUMAR DOLAI | 18.46 | 15.43 | 83.55 | 0
2737 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Madhya Para in Pratappur PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | 372/MD | 25/02/2021 | 15 | SUBHASIS DOLAI | 9.63 | 7.98 | 82.86 | 0
2738 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in RAJNAGAR (PASCHIM) PWSS in Daspur-I Block in the District of Paschim Midnapore. | 311/MD | 22/02/2021 | 30 | ASHOK BANERJEE | 11.93 | 0 | 0 | 0
2739 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Manikkundu in Bhabanipur PWSS within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | 370/MD | 25/02/2021 | 15 | SAMIT PAL | 12.53 | 11.23 | 100 | 0
2740 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Birsingha PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | 410/MD | 26/02/2021 | 15 | SAMIT PAL | 6.95 | 6.7 | 100 | 0
2741 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Daulatchak PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | 413/MD | 26/02/2021 | 15 | DEV KUMAR ADAK | 11.41 | 0 | 0 | 0
2742 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in HAREKRISHNAPUR PWSS in Daspur-I Block in the District of Paschim Midnapore. | 450/MD | 26/02/2021 | 30 | SUBHASIS DOLAI | 13.85 | 0 | 0 | 0
2743 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhabanipur PWSS within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | 411/MD | 26/02/2021 | 15 | JIT ENTERPRISE | 15.04 | 13.63 | 100 | 0
2744 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | 412/MD | 26/02/2021 | 15 | M/S JITEN BANARJEE | 11.44 | 0 | 0 | 0
2745 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Electrical maintenance instrument for the O/F of the EE/MD, PHE Dte. | BP-2021-22-86 | 16/07/2021 | 0 | PULLOCK KUMAR GHOSH | 0.14 | 0 | 0 | 0
2746 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Continuation Work Order for the work of Retrofitting to accommodate additional FHTC under JJM including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Bhabanipur W/S Scheme within Chandrakona-I Dev. Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | 2169/MD | 21/10/2022 | 30 | SAMIT PAL | 17.77 | 0 | 0 | 100
2747 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Continuation Work Order for the work of Retrofitting to accommodate additional FHTC under JJM including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Bhabanipur W/S Scheme within Chandrakona-I Dev. Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | BP-2023-24-246 | 23/08/2023 | 0 | SAMIT PAL | 5.25 | 0 | 0 | 0
2748 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Daulatchak PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | 97/AE/GSD | 25/02/2021 | 7 | DEV KUMAR ADAK | 4.84 | 0 | 0 | 0
2749 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Dolai Para in Dharma PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | 99/AE/GSD | 25/02/2021 | 7 | PBA INFRASTRUCTURE | 4.72 | 4.26 | 100 | 0
2750 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. , SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nandanpur-II in Dharma PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | 100/AE/GSD | 25/02/2021 | 7 | PBA INFRASTRUCTURE | 4.76 | 4.24 | 100 | 0
2751 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Material Requisition To Resource Division | 1367/MD | 02/05/2023 | 0 | Resource Division | 69.43 | 0 | 0 | 0
2752 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. (Part-II) | 1733/W/MMD | 09/08/2023 | 180 | ORIENTAL ENGINEERING CO. | 21.57 | 0 | 0 | 45
2753 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 1727/W/MMD | 09/08/2023 | 180 | HARA PROSAD DAS | 23.73 | 0 | 0 | 40
2754 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Laying Distribution pipeline, Switch Room, Land development & Accommodate FHTC (75 Nos.) under JJM with allied work for Tangasol (Zone-II) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | 5155/MD | 07/11/2023 | 440 | RITESH AGARWALL | 25.25 | 0 | 0 | 62
2755 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Laying Distribution pipeline & Accommodate FHTC (300 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VIII] | 5157/MD | 07/11/2023 | 60 | R. CONSTRUCTION | 71.32 | 0 | 0 | 55
2756 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Laying Rising main pipeline & Accommodate FHTC (100 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | 5104/MD | 31/10/2023 | 30 | CHANDAN DAS | 15.96 | 0 | 0 | 68
2757 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Laying Distribution pipeline & Accommodate FHTC (300 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-V] | 5358/MD | 30/11/2023 | 45 | S.N.A. CONSTRUCTION | 63.8 | 0 | 0 | 72
2758 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Sinking of 2 (Two) Nos. Tube well for Tangasol & its adjoining mouzas (Zone-II i.e. II/I & II/II) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | 2816/MD | 07/08/2023 | 30 | MANNA COMPUTER | 11.83 | 0 | 0 | 100
2759 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Sinking of 2 (Two) Nos. Tube well for Tangasol & its adjoining mouzas (Zone-I) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | 2815/MD | 07/08/2023 | 30 | ANNAPURNA TUBEWELL WORKS | 19.43 | 0 | 0 | 100
2760 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | QUOTATION MONEY FOR TUNGASOLE WATER SUPPLY SCHEME, ZONE-I , T W NO II [ NEAR AMGACHIYA ] , KGP-I , JJM WORKS, SCHEME CODE SM/18696, APPLICATION NO 2004580997, REFERENCE ID 204205374, NIMPURA CCC, WBSEDCL | BP-2023-24-790 | 06/03/2024 | 0 | WBSEDCL | 5.81 | 0 | 0 | 0
2761 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | QUOTATION MONEY FOR TANGASOL WATER SUPPLY SCHEME ( NEAR ICDS ) , JJM WORKS, SCHEME CODE SM/18696, APPLICATION NO 2004580955, REFERENCE ID 204205371, NIMPURA CCC, WBSEDCL | BP-2023-24-698 | 16/02/2024 | 0 | WBSEDCL | 4.09 | 0 | 0 | 0
2762 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | QUOTATION MONEY FOR TUNGASOLE WATER SUPPLY SCHEME, ZONE-II , T W NO I ,MINI [ NEAR PRIMARY SCHOOL ] , KGP-I , JJM WORKS, SCHEME CODE SM/18696, APPLICATION NO 2004580975, REFERENCE ID 204205372, NIMPURA CCC, WBSEDCL | BP-2023-24-791 | 06/03/2024 | 0 | WBSEDCL | 4.12 | 0 | 0 | 0
2763 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | QUOTATION MONEY FOR TANGASOL WATER SUPPLY SCHEME ( GALUKSAL ) JJM WORKS, SCHEME CODE SM/18696, APPLICATION NO 2004581010, REFERENCE ID 204205373, NIMPURA CCC, WBSEDCL | BP-2023-24-697 | 16/02/2024 | 0 | WBSEDCL | 3.99 | 0 | 0 | 0
2764 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Laying Distribution pipeline & Accommodate FHTC (346 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VII] | 5156/MD | 07/11/2023 | 798 | GOUTAM PARIA | 53.34 | 0 | 0 | 80
2765 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Laying Distribution pipeline & Accommodate FHTC (330 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VI] | 5502/MD | 14/12/2023 | 482 | SK. SANAMAJ | 85.43 | 0 | 0 | 65
2766 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Laying Distribution pipeline & Accommodate FHTC (260 Nos.) including 2 yrs. O&M under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | 5501/MD | 14/12/2023 | 514 | EVEREST CONSULTANT SERVICES | 143.94 | 0 | 0 | 30
2767 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Laying Distribution pipeline & Accommodate FHTC (260 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | 2079/MD | 04/07/2024 | 242 | A R CONSTRUCTION | 84.14 | 0 | 0 | 68
2768 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/18696 | New | Construction of 400 CuM OHR, Pump House & Boundary wall under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | 1237/MD | 28/05/2025 | 180 | M/S P.B. ENTERPRISE | 141.67 | 0 | 0 | 0
2769 | PASCHIM MEDINIPUR | Midnapore Division | RAUTMANI AND ITS ADJOINING MOUZAS PWSS , SM/18523 | New | Material Requisition To Resource Division | 1506/MD | 12/05/2023 | 0 | Resource Division | 39.69 | 0 | 0 | 0
2770 | PASCHIM MEDINIPUR | Midnapore Mechanical | RAUTMANI AND ITS ADJOINING MOUZAS PWSS , SM/18523 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RAUTMANI AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | 3090/W/MMD | 29/11/2023 | 180 | AMITAVA CHAKRABORTY | 25.24 | 0 | 0 | 0
2771 | PASCHIM MEDINIPUR | Midnapore Mechanical | RAUTMANI AND ITS ADJOINING MOUZAS PWSS , SM/18523 | New | Quotation for new power connection at Routhmoni PWSS T/W - I , Application no- 2004812911, Ref no : 204353062 | BP-2024-25-458 | 23/07/2024 | 0 | WBSEDCL | 5.12 | 0 | 0 | 0
2772 | PASCHIM MEDINIPUR | Midnapore Mechanical | RAUTMANI AND ITS ADJOINING MOUZAS PWSS , SM/18523 | New | Quotation for new power connection at Routhmoni PWSS T/W - II Khargpur - II Block, Application No - 2004799376 , Ref ID : 204344493 | C082430203830 | 20/08/2024 | 0 | WBSEDCL | 4.72 | 0 | 0 | 0
2773 | PASCHIM MEDINIPUR | Midnapore Division | RAUTMANI AND ITS ADJOINING MOUZAS PWSS , SM/18523 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 Cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,186 Nos.) under JJM with allied work including 02 (Two) years Operation & Maintenance for Rautmani & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the distrist of Paschim Medinipur. | 3049/MD | 23/08/2023 | 927 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 876.48 | 0 | 0 | 15
2774 | PASCHIM MEDINIPUR | Midnapore Division | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS , SM/18526 | New | Material Requisition To Resource Division | 207/MD | 16/01/2023 | 0 | Resource Division | 76.02 | 0 | 0 | 0
2775 | PASCHIM MEDINIPUR | Midnapore Division | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS , SM/18526 | New | Material Requisition To Resource Division | 3437/MD | 25/11/2024 | 0 | Resource Division | 21.41 | 0 | 0 | 0
2776 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS , SM/18526 | New | Quotation for new power connection at Radhakishore PWSS T/W - II under KGP - II block , Application No- 2004799279, Ref No- 204344494 | BP-2024-25-525 | 06/08/2024 | 0 | WBSEDCL | 6.95 | 0 | 0 | 0
2777 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS , SM/18526 | New | Quotation for new power connection at Radhakishore PWSS T/W - I Khargpur - II Block, Application No - 2004799343 , Ref ID : 204344492 | BP-2024-25-585 | 20/08/2024 | 0 | WBSEDCL | 4.95 | 0 | 0 | 0
2778 | PASCHIM MEDINIPUR | Midnapore Mechanical | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS , SM/18526 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RADHAKISHOR AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | 1687/W/MMD | 04/08/2023 | 696 | ORIENTAL ENGINEERING CO. | 27.35 | 0 | 0 | 80
2779 | PASCHIM MEDINIPUR | Midnapore Division | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS , SM/18526 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (3,476 nos.) under JJM with allied work including 02 (Two ) Years Operation & Maintenance for Radhakishor & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 4000/MD | 06/10/2023 | 904 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 1051.83 | 0 | 0 | 70
2780 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Palashpai (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/18538 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main Pump House, Boundary Wall, Soil investigation, 300 cum OHR (Zone- I & II) ( Intze type with pile foundation) & Accommodate FHTC (4,261 Nos.) including Two years O&M under JJM with allied work for Palashpai (Zone- I & Zone-II) & its adjoining mouzas W/S scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 3234/MD | 11/09/2023 | 180 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 938.92 | 0 | 0 | 0
2781 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Palashpai (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/18538 | New | Material Requisition To Resource Division | 1521/MD | 12/05/2023 | 0 | Resource Division | 74.13 | 0 | 0 | 0
2782 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Palashpai (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/18538 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Palashpai (Zone-I and II) and its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 1696/W/MMD | 04/08/2023 | 180 | AMUSAR IMPEX PVT. LTD | 46.02 | 0 | 0 | 50
2783 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Palashpai (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/18538 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Palashpai & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | 689/MD | 13/04/2022 | 20 | GOBINDA MAITY | 12.29 | 0 | 0 | 100
2784 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Palashpai (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/18538 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 1684/MMSD-I | 19/12/2023 | 60 | SUBHASIS ROY | 0.29 | 0 | 0 | 40
2785 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Palashpai (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/18538 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
2786 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS , SM/06903 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barisha (Zone-I) W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1471/MD | 26/11/2020 | 180 | SK. SALIM | 96.82 | 34.85 | 100 | 0
2787 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS , SM/06903 | Retrofitting | FHTC DATA ENTRY | 8443208 | 27/09/2021 | 0 | SUBRATA CHAKRABORTY | 0.12 | 0 | 0 | 0
2788 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS , SM/06903 | Retrofitting | FHTC DATA ENTRY | 8443208 | 27/09/2021 | 0 | PAPPU SHAW | 0.2 | 0 | 0 | 0
2789 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS , SM/06903 | Retrofitting | Retrofitting to accomdate 80(Eighty) nos FHTC under JJM at different places for Barisha (Zone -I) and its adjoining Mouzas Water Supply Scheme Within Pingla Block under Midnapore Division, P.H.E. Dte. | 213/AE/KSD | 29/04/2022 | 15 | SK. TASLIM | 4.82 | 0 | 0 | 0
2790 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS , SM/06903 | Retrofitting | FHTC data entry. | 844337 | 08/12/2021 | 0 | GANESH CH NANDY | 0.11 | 0 | 0 | 0
2791 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS , SM/06903 | Retrofitting | FHTC data entry. | 844337 | 08/12/2021 | 0 | PAPPU SHAW | 0.12 | 0 | 0 | 0
2792 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS , SM/06903 | Retrofitting | FHTC Data Entry. | 844360 | 18/01/2022 | 0 | SIDDHESWAR BAG | 0.21 | 0 | 0 | 0
2793 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS , SM/06903 | Retrofitting | FHTC Data Entry. | 844360 | 18/01/2022 | 0 | PAPPU SHAW | 0.17 | 0 | 0 | 0
2794 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS , SM/06903 | Retrofitting | FHTC data entry. | 844337 | 08/12/2021 | 0 | SUBRATA CHAKRABORTY | 0.07 | 0 | 0 | 0
2795 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS , SM/06903 | Retrofitting | Laying of UPVC (Class-III) pipe line supportive to retrofitting to accommodate FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM at Barisha (Zone-I) and its adjoining mouza Water Supply Scheme within Pingla Dev. Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | 2278/MD | 09/11/2022 | 21 | AJIJUR RAHAMAN MALLICK | 10.96 | 0 | 0 | 0
2796 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS , SM/06903 | Retrofitting | Material Requisition To Resource Division | 3407/MD | 25/11/2024 | 0 | Resource Division | 12.53 | 0 | 0 | 0
2797 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS , SM/06903 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM at different places for Barisha (Zone-I) & its adj. mouzas W/S Scheme within Pingla block under Midnapore Division, PHE Dte. | 617/MD | 04/04/2022 | 1003 | NUTAN BAZAR ENGINEER,S CO-OPERATIVE SOCIETY LTD. | 39.19 | 0 | 0 | 100
2798 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Debhog W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | MIDNAPUR PIPE CONCERN | 30 | 0 | 0 | 0
2799 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | For FHTC Data Entry. | 844375 | 10/09/2021 | 0 | SHRABONTI BERA | 0.17 | 0 | 0 | 0
2800 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | For FHTC Data Entry. | 844375 | 08/09/2021 | 0 | SUBHAJIT GANGULY | 0.01 | 0 | 0 | 0
2801 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | FHTC DATA ENTRY | 8443211 | 27/09/2021 | 0 | SHRABONTI BERA | 0.2 | 0 | 0 | 0
2802 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | FHTC DATA ENTRY | 8443211 | 27/09/2021 | 0 | TANMOY BERA | 0.17 | 0 | 0 | 0
2803 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | FHTC data entry. | 844336 | 03/12/2021 | 0 | NABOGOPAL ADHIKARI | 0.06 | 0 | 0 | 0
2804 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | FHTC data entry. | 844336 | 08/12/2021 | 0 | PRATHA PRATIM PAL | 0.07 | 0 | 0 | 0
2805 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | FHTC data entry. | 844336 | 08/12/2021 | 0 | RINTU SAMANTA | 0.07 | 0 | 0 | 0
2806 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | FHTC data entry. | 844362 | 18/01/2022 | 0 | SHRABONTI BERA | 0.2 | 0 | 0 | 0
2807 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | FHTC data entry. | 844336 | 08/12/2021 | 0 | SANDIP MANNA | 0.06 | 0 | 0 | 0
2808 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | FHTC data entry. | 844362 | 18/01/2022 | 0 | MANABENDAN DAS | 0.2 | 0 | 0 | 0
2809 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | Continuation Work Order for the work of Retrofitting to accommodate additional FHTC under JJM in Debhog W/S Scheme, Block :- Sabang, District :- Paschim Medinipur within Midnapore Division, PHE Dte. | 2533/MD | 12/12/2022 | 14 | MIDNAPUR PIPE CONCERN | 13.69 | 0 | 0 | 50
2810 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. , SM/06915 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Debhog W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1461/MD | 26/11/2020 | 180 | MIDNAPUR PIPE CONCERN | 67.06 | 58.97 | 87.93 | 100
2811 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bural (Zone-I) PWSS , SM/06917 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bural (Zone-I) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1465/MD | 26/11/2020 | 1887 | BANERJEE CONSTRUCTION | 96.92 | 24.87 | 25.99 | 80
2812 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS , SM/06931 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Rajnagar (Paschim) W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1444/MD | 26/11/2020 | 180 | BANERJEE CONSTRUCTION | 96.09 | 21.36 | 22.23 | 0
2813 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS , SM/06931 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Rajnagar W/S Scheme District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | BANERJEE CONSTRUCTION | 30 | 0 | 0 | 0
2814 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS , SM/06931 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443118 | 31/05/2021 | 0 | SOVANDEB MANNA | 0.05 | 0 | 0 | 0
2815 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS , SM/06931 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443118 | 28/05/2021 | 0 | SHRABONTI BERA | 0.17 | 0 | 0 | 0
2816 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS , SM/06931 | Retrofitting | FHTC DATA ENTRY | 8443210 | 27/09/2021 | 0 | PARTHA PRATIM PAL | 0.11 | 0 | 0 | 0
2817 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS , SM/06931 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443118 | 31/05/2021 | 0 | ANIRBAN CHAKRABORTY | 0.05 | 0 | 0 | 0
2818 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS , SM/06931 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443118 | 31/05/2021 | 0 | TANMOY BERA | 0.11 | 0 | 0 | 0
2819 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS , SM/06931 | Retrofitting | FHTC DATA ENTRY | 8443210 | 27/09/2021 | 0 | NABOGOPAL ADHIKARI | 0.1 | 0 | 0 | 0
2820 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS , SM/06931 | Retrofitting | FHTC DATA ENTRY | 8443210 | 27/09/2021 | 0 | SANDIP MANNA | 0.1 | 0 | 0 | 0
2821 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS , SM/06931 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443118 | 31/05/2021 | 0 | ARUP KR ADAK | 0 | 0 | 0 | 0
2822 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & its adjoining mouzas within Midnapore Division, PHE Dte. (Phase-F) | 1069/MD | 03/06/2022 | 21 | MAITY ENTERPRISE | 22.04 | 0 | 0 | 0
2823 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09421 | Retrofitting | Construction of R.C.C. Over Head Reservoir (Raft Foundation) of capacity 600 CuM and staging height 20.00 mtr. as per approved drawing (PC-I/OHR/13/2012) with allied works under Goaltore Augmentation W/S Scheme within Garhbeta-II Block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. | BP-2021-22-544 | 29/03/2022 | 0 | ASHIM KUMAR DEY | 20 | 0 | 0 | 0
2824 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-D) (SL No-04) | 799/AE/MSSD | 10/01/2023 | 15 | RUPKUMAR KARMAKAR | 4.67 | 0 | 0 | 0
2825 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-C) (SL No-03) | 798/AE/MSSD | 10/01/2023 | 15 | CHANDAN YADAV | 4.67 | 0 | 0 | 0
2826 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-B) (SL No-02) | 797/AE/MSSD | 10/01/2023 | 15 | ARNAB PATRA | 4.67 | 0 | 0 | 0
2827 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-A) (SL No-01) | 794/AE/MSSD | 10/01/2023 | 15 | A R ENTERPRISE | 4.66 | 0 | 0 | 0
2828 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09421 | Retrofitting | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Tap Connection of existing PWSS (Goaltore, Block - Garhbeta-II) to be Retrofitting under Midnapore Division, PHE Dte. | 994/MD | 23/06/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.8 | 0 | 0 | 0
2829 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-E) (SL No-05) | 804/AE/MSSD | 11/01/2023 | 15 | JIT ENTERPRISE | 4.62 | 0 | 0 | 100
2830 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09421 | Retrofitting | Laying of Rising main & interconnection pipeline for Augmentation of Goaltore & its adjoining mouzas PWSS, Block - Garhbeta-II, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Length - 950.00 Mtr.) | 2448/MD | 08/08/2024 | 45 | ARNAB PATRA | 7.64 | 0 | 0 | 50
2831 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & its adjoining mouzas within Midnapore Division, PHE Dte. (Phase-G) | 1070/MD | 03/06/2022 | 1120 | MAITY ENTERPRISE | 72.11 | 0 | 0 | 20
2832 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Nankarnila Mouzas , SM/09442 | New | Service connection charge of WBSEDCL at Nankar Nila, Chandkuri | 2003774962/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
2833 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Nankarnila Mouzas , SM/09442 | New | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for mouza (i) Nankarnila, (ii) Dontarda & (iii) Talda of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | 1278/MD | 05/08/2021 | 10 | GOBINDA MAITY | 4.46 | 0 | 0 | 0
2834 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Nankarnila Mouzas , SM/09442 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Nankarnila water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2509/W/MMD | 30/11/2021 | 4 | SUJOY RANJAN BHOWMICK | 4.47 | 0 | 0 | 100
2835 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Nankarnila Mouzas , SM/09442 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | BP-2021-22-505 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.87 | 0 | 0 | 0
2836 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Nankarnila Mouzas , SM/09442 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Nankarnila, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 2180/MD | 17/12/2021 | 150 | MIDNAPUR PIPE CONCERN | 29.46 | 0 | 0 | 90
2837 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Nankarnila Mouzas , SM/09442 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Nankarnila, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 121/W/MMD | 24/01/2022 | 120 | SHOVAN KUMAR DAS | 6.51 | 0 | 0 | 0
2838 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Basantapur PWSS Block Daspur-I District Paschim Medinipur , SM/08207 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Basantapur PWSS, Block ¿ Daspur-I in the district of Paschim Medinipur. | 417/MD | 26/02/2021 | 40 | MASUM ALI KHAN | 95.51 | 53.11 | 53.34 | 0
2839 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Basantapur PWSS Block Daspur-I District Paschim Medinipur , SM/08207 | Retrofitting | Continuation Work Order for the work of ?Retrofitting to accommodate FHTC under JJM for Basantapur PWSS, Block- Daspur-I in the district of Paschim Medinipur.? | 1241/MD | 20/06/2022 | 21 | MASUM ALI KHAN | 30.95 | 0 | 0 | 0
2840 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Jamna PWSS Block-Pingla District Paschim Medinipur , SM/08212 | Retrofitting | Material Requisition To Resource Division | 3413/MD | 25/11/2024 | 0 | Resource Division | 5.17 | 0 | 0 | 0
2841 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Jamna PWSS Block-Pingla District Paschim Medinipur , SM/08212 | Retrofitting | Accomdation of FHTC under JJM for the leftout Portion of Jamna Water Supply Scheme catchment area as per site reconnaissance, Block: - Pingla , within Midnapore Division, P.H.E. Dte. District: - Paschim Midnapore. | 217/AE/KSD | 29/04/2022 | 30 | GOBINDA MAITY | 4.57 | 0 | 0 | 100
2842 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Jamna PWSS Block-Pingla District Paschim Medinipur , SM/08212 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Jamna PWSS, Block - Pingla in the district of Paschim Medinipur. | 445/MD | 26/02/2021 | 1405 | GOBINDA MAITY | 41.65 | 25.06 | 48.53 | 100
2843 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Jamdoba & Godamauli Piped Water Supply Scheme to accommodate all FHTC. , SM/08213 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Jamdoba in Jamdoba PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-09) | 103/AE/MSSD | 24/02/2021 | 15 | A R ENTERPRISE | 1.96 | 0.45 | 100 | 0
2844 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Jamdoba & Godamauli Piped Water Supply Scheme to accommodate all FHTC. , SM/08213 | Retrofitting | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. | 8443496 | 30/03/2021 | 0 | SIRCON ENGINEERING SERVICES | 1.49 | 0 | 0 | 0
2845 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Jamdoba & Godamauli Piped Water Supply Scheme to accommodate all FHTC. , SM/08213 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Jamdoba & Godamauli, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | 57/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.79 | 0 | 0 | 0
2846 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Mugbasan PWSS , SM/08218 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Mugbasan PWSS, Block - Keshpur in the district of Paschim Medinipur. | 1065/MD | 02/07/2021 | 30 | MIDNAPUR PIPE CONCERN | 68.71 | 37.42 | 54.88 | 0
2847 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09721 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dharma, Block - Ghatal) to be Retrofitting under Midnapore Division P.H.E. Dte. | BP-2021-22-380 | 17/02/2022 | 0 | SIRCON ENGINEERING SERVICES | 3.09 | 0 | 0 | 0
2848 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09721 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Dolai Para in Dharma PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | 99/AE/GSD | 25/02/2021 | 7 | PBA INFRASTRUCTURE | 4.72 | 0 | 0 | 0
2849 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09721 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nandanpur-II in Dharma PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | 100/AE/GSD | 25/02/2021 | 7 | PBA INFRASTRUCTURE | 4.76 | 0 | 0 | 0
2850 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09721 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 2188/MD | 17/12/2021 | 60 | M/S. D.K.H.CONSTRUCTION | 85.4 | 0 | 0 | 100
2851 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. , SM/09721 | Retrofitting | Laying pipe line to provide balance FHTC under JJM in DHARMA PWSS under Ghatal Sub-Division in the District of Paschim Medinipur | 5359/MD | 30/11/2023 | 25 | SK REAJUL HOSSAIN | 6.49 | 0 | 0 | 100
2852 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Karkai Piped Water Supply Scheme. , SM/06901 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443105 | 12/02/2021 | 0 | KOUSHIK PAL | 0.15 | 0 | 0 | 0
2853 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Karkai Piped Water Supply Scheme. , SM/06901 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443105 | 12/02/2021 | 0 | MANABENDAN DAS | 0.19 | 0 | 0 | 0
2854 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Karkai Piped Water Supply Scheme. , SM/06901 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443105 | 09/02/2021 | 0 | RINTU SAMANTA | 0.19 | 0 | 0 | 0
2855 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Karkai Piped Water Supply Scheme. , SM/06901 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443105 | 12/02/2021 | 0 | NABOGOPAL ADHIKARI | 0.16 | 0 | 0 | 0
2856 | PASCHIM MEDINIPUR | Midnapore Division | Rerofitting of Ground Water Based Pirakata Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09107 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Khandibundh & Pathra in Pirakata PWSS in Salboni Block District :-Paschim Medinipore within Midnapore Division PHE Dte. | 675/AE/MSSD | 24/12/2021 | 15 | DEBJIT PATRA | 4.48 | 0 | 0 | 0
2857 | PASCHIM MEDINIPUR | Midnapore Division | Rerofitting of Ground Water Based Pirakata Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09107 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Khadibandh in Pirakata PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-06) | BP-2021-22-516 | 25/03/2022 | 0 | DEBJIT PATRA | 1.02 | 0 | 0 | 0
2858 | PASCHIM MEDINIPUR | Midnapore Division | Rerofitting of Ground Water Based Pirakata Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09107 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Pirakata, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | 58/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.68 | 0 | 0 | 0
2859 | PASCHIM MEDINIPUR | Midnapore Division | Rerofitting of Ground Water Based Pirakata Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09107 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Pirakata PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 2175/MD | 17/12/2021 | 45 | SANJIT SINHA | 52.54 | 0 | 0 | 0
2860 | PASCHIM MEDINIPUR | Midnapore Division | Rerofitting of Ground Water Based Pirakata Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09107 | Retrofitting | Sinking of Rig bored Tube well of 150 X 100 mm dia. X 200 Mtr. Depth for boosting perpose of Pirakata Water supply Scheme under Midnapore Division, PHE Dte. | 700/AE/MSSD | 06/10/2023 | 15 | SANJIT SINHA | 7.01 | 0 | 0 | 100
2861 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Sinking of 125 mm X 80 mm.dia. & 138 Mtr. Depth, Tubewell Including installation of pumping machinery and accessories etc at Chandrakona Road Headwork site in the district of Pashcim Medinipur under Midnapore Division, P.H.E. Dte. (SL No-05) | 223/AE/MSSD | 13/05/2022 | 20 | CHANDAN YADAV | 3.03 | 0 | 0 | 90
2862 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Chandrakona (Block-Garhbeta-III) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1622/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.06 | 0 | 0 | 100
2863 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Chandrakona (Block-Garhbeta-III) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1623/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.9 | 0 | 0 | 100
2864 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Block - Garhbeta-III) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-468 | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.28 | 0 | 0 | 0
2865 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Hire and labour charges for staging and scaffolding, bamboo barricading and removal of rubbish for dismantling of existing OHR (Capacity 2,27,000 Ltr.) at Head work Site of Chandrakona Road Railway Station Water Supply Scheme (Zone-I) within Garhbeta-III Block under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. | BP-2021-22-424 | 02/03/2022 | 0 | BISWAJIT BAG | 4.72 | 0 | 0 | 0
2866 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Block - Garhbeta-III) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-469 | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.21 | 0 | 0 | 0
2867 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Amlagora, Jot Ghanashyam & Sonakhali in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-470 | 11/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.19 | 0 | 0 | 0
2868 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Hiring of 01 (one) no, Motor Cab(standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older then 30 (thirty) months from the date of 1st registration on daily hire basis for 12 (twelve) months only having contract carriage permit for plying within west Bengal from Regional Transport Authority for the use of the Executive Engineer,Midnapore Division PHE Dte. | 474/AE/MSSD | 30/08/2021 | 365 | SUKUMAR SANTRA | 1.7 | 0 | 0 | 100
2869 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Continuation Work Order for the work of Hiring of 01 (one) no. Motor Cab (standard) commercial with catalytic converter attachment with Bharat Stage as perprevalent applicable standard compliant new/not older then 30 (thirty) months from the date of 1st registration on daily hire basis for 6 (six) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Executive Engineer, Midnapore Division, PHE Dte. w.e.f. 01.09.2022 to 28.02.2023. | 503/AE/MSSD | 29/08/2022 | 160 | SUKUMAR SANTRA | 0.9 | 0 | 0 | 100
2870 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Continuation Work order for Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 06 (Six) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, (HQ) under Midnapore Division PHE Dte. for the Period of 6 ( Six ) months. | 680/AE/MSSD | 30/11/2022 | 182 | PULLOCK KUMAR GHOSH | 1.01 | 0 | 0 | 0
2871 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Material Requisition To Resource Division | 1121/MD | 20/04/2023 | 0 | Resource Division | 111.82 | 0 | 0 | 0
2872 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Car Bill | BP-2023-24-001 | 01/04/2023 | 0 | SUKUMAR SANTRA | 0.8 | 0 | 0 | 0
2873 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Laying distribution pipeline, Providing FHTC, Soil test and Construction of RCC Over Head Reservoir of capacity 550 CuM (Intez type with solid raft) and staging height 20.00 mtr. with allied work including Sinking of Rig bored tube well for Augmentation of Chandrakona Road Rly. Station (Zone-I) Water Supply Scheme in Garhbeta-III block including supply of all labour & materials within Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | 1960/MD | 20/09/2022 | 180 | BANERJEE CONSTRUCTION | 588.73 | 0 | 0 | 25
2874 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | 874/W/MMD | 27/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 23.76 | 0 | 0 | 95
2875 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Repair and Rennovation of Switch Room cum Chlorine Room ( No. 2 ) of Chandrakona Road Water Supply Scheme ( Zone-II ) within Midnapore Sadar Sub Division under Midnapore Division, PHE Dte. (SL No-03) | 984/AE/MSSD | 17/03/2023 | 15 | NAYAN CONSTRUCTION | 0.97 | 0 | 0 | 100
2876 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Material Requisition To Resource Division | 3387/MD | 25/11/2024 | 0 | Resource Division | 58.96 | 0 | 0 | 0
2877 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Quotation for Dedicated Transformer for C.K Road Z - I P.H - III water supply scheme. | 331/JMD | 29/08/2024 | 0 | WBSEDCL | 4.42 | 0 | 0 | 0
2878 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Laying distribution pipe line, Providing FHTC and Sinking of Rig Bored Tube well for Augmentation of Chandrakona Road Rly. Station (Zone-II) W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 526/MD | 21/03/2022 | 1361 | GOBINDA MAITY | 459.24 | 0 | 0 | 75
2879 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Route survey & way leave permission along & across of National Highway in Augmentation of Chandrakona Road Railway Station (Zone-I) PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | 372/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 11.47 | 0 | 0 | 0
2880 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. , SM/10091 | Augmentation | Laying Rising main from Common manifold to OHR for Augmentation of Chandrakona Road ( Zone-II ) W/S scheme within Garhbeta-III Block under Midnapur Division P.H.E. Dte. | 853/AE/MSSD | 03/02/2023 | 879 | GOBINDA MAITY | 3.33 | 0 | 0 | 70
2881 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Sonakhali (Block-Daspur-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1642/MD | 22/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.78 | 0 | 0 | 0
2882 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Sonakhali (Block-Daspur-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1643/MD | 22/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.41 | 0 | 0 | 0
2883 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Sonakhali, Block ¿ Daspur-II) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-386 | 23/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.87 | 0 | 0 | 0
2884 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Sonakhali, Block - Daspur-II) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-385 | 18/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.4 | 0 | 0 | 0
2885 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Amlagora, Jot Ghanashyam & Sonakhali in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-470 | 11/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.19 | 0 | 0 | 0
2886 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Preliminarily Ground Protection works (i,e, Construction R.C.C. Retaining wall, Land development) And Rising main in connection with Construction of Boundary wall, OHR, Switch Room etc. at Head Works site of Augmentation of Sonakhali W/S Scheme under Midnapore Division P.H.E. Dte. | 452/MD | 13/02/2023 | 30 | GOBINDA MAITY | 25.92 | 0 | 0 | 25
2887 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Sinking of 3 (Three) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Sonakhali W/S Scheme with in Daspur-II Block under Midnapore Division, P.H.E. Dte. | 120/MD | 10/01/2023 | 21 | PRANTIK DRILLING AGENCY | 29.59 | 0 | 0 | 100
2888 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Material Requisition To Resource Division | 901/MD | 31/03/2023 | 0 | Resource Division | 75.94 | 0 | 0 | 0
2889 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Material Requisition To Resource Division | 133/MD | 11/01/2023 | 0 | Resource Division | 28.24 | 0 | 0 | 0
2890 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Material Requisition To Resource Division | 531/MD | 21/02/2023 | 0 | Resource Division | 75.94 | 0 | 0 | 0
2891 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Electric Quotation for SONAKHALI Water Supply Scheme T/W-II (Ref. ID-204046818 ) | BP-2023-24-133 | 20/07/2023 | 0 | WBSEDCL | 5.24 | 0 | 0 | 0
2892 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Electric Quotation ID No. 204047232 | BP-2023-24-132 | 20/07/2023 | 0 | WBSEDCL | 3.07 | 0 | 0 | 0
2893 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Day to day operation & maintenance of distribution system & Rising main (CI/DI/HDPE/UPVC) with all related structure i.e. OHR etc. of Sonakhali W/S Scheme under Midnapore Division P.H.E. Dte. (Period from 01/11/2021 to 31/12/2021) | 743/A/AE/GSD | 26/10/2021 | 61 | SUBHASIS DOLAI | 0.88 | 0 | 0 | 100
2894 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Laying distribution pipe line, Pump House, FHTC & Construction of R.C.C. Over Head Reservoir of capacity 600 Cum (including Pile) and staging height 20.00 mtr. with allied work for Augmentation of Sonakhali W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 1688/MD | 16/08/2022 | 1320 | GOBINDA MAITY | 757.01 | 0 | 0 | 60
2895 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | 452/W/MMD | 20/03/2023 | 864 | SAIKAT SINHA | 27.36 | 0 | 0 | 71
2896 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-II) | 865/W/MMD | 27/03/2023 | 857 | S.S.GHORAI | 13.68 | 0 | 0 | 95
2897 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. , SM/09980 | Augmentation | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room with out W.C. & Bath for 2nd. Tube Well site of Augmentation of Sonakhali water supply scheme within Ghatal Sub-Division under Midnapore Division, PHE Dte. (Considering G.L. 1950 mm below Road Level) {TYPE - B} | 1495/AE/GSD | 24/09/2024 | 169 | SK REAJUL HOSSAIN | 3.64 | 0 | 0 | 100
2898 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Sinking of 125mm X 80mm dia. & 150 Mtr.Depth, Deep Tubewell by Water Jet System at Garhbeta Water Testing Lab Premises in the district of Paschim Medinipore under Midnapore Division PHE Dte.(SL No-01) | 438/AE/MSSD | 10/08/2021 | 15 | S.T. ENTERPRISE | 2.87 | 0 | 0 | 0
2899 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Repairing of damaged (due to flood) Rising main from river bank Tube Well to CWR of Garhbeta & its adjoining Mouzas W/S Scheme within Garhbeta Block under Midnapore Division PHE Dte. (SL No-02) | 467/AE/MSSD | 08/08/2022 | 45 | CHANDAN YADAV | 0.81 | 0 | 0 | 0
2900 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Continuation Work Order for the work of Conducting of Route survey & Design with allied works in connection with the FHTC of existing PWSS Garhbeta (Block-Garhbeta-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1652/MD | 23/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.69 | 0 | 0 | 0
2901 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Garhbeta, Block - Garhbeta-I) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. | BP-2021-22-398 | 08/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.67 | 0 | 0 | 0
2902 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Hire and labour charges for staging and scaffolding, bamboo barricading and removal of rubbish for dismantling of existing OHR (Capacity 2,27,000 Ltr.) at Head work Site of Garhbeta Water Supply Scheme within Garhbeta-I Block under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. | BP-2021-22-421 | 02/03/2022 | 0 | BISWAJIT BAG | 4.7 | 0 | 0 | 0
2903 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I. District - Paschim Medinipur. |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 25.21 | 0 | 0 | 0
2904 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Hiring of 1 (one) no, Motor Cab(standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older then 30 (thirty) months from the date of 1st registration on daily hire basis for 12 (twelve) months only having contract carriage permit for plying within west Bengal from Regional Transport Authority for the use of the Assistant Engineer, Midnapore Sadar Sub- Division PHE Dte. (It would be used only the 'JAL SWAPNA" Schematic Programme, inaugurated by Honorable C.M ) for the period of 06 (Six) months. | 470/AE/MSSD | 10/08/2022 | 184 | SANJIT SINHA | 0.85 | 0 | 0 | 0
2905 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well at Mouza Pochadohora, J.L No.618, G.P - Shyamnagar within Garhbeta -I Block under Midnapore Division, PHE Dte. | 2587/MD | 21/07/2023 | 15 | RUPKUMAR KARMAKAR | 5.91 | 0 | 0 | 100
2906 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well at Saradapara Manasatala, Mouza - Mohanpur, J.L. No. 838, G.P. - Kadra Uttarbil within Garhbeta-I Block under Midnapore Division PHE Dte. | 2586/MD | 21/07/2023 | 15 | MANNA COMPUTER | 5.91 | 0 | 0 | 100
2907 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Material Requisition To Resource Division | 150/MD | 28/01/2022 | 0 | Resource Division | 25.21 | 0 | 0 | 0
2908 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Material Requisition To Resource Division | 518/MD | 20/02/2023 | 0 | Resource Division | 90.05 | 0 | 0 | 0
2909 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Garbeta to Hoomgarh Road from chainage 0.00 Km- Restoration of damages due to laying of proposed underground pipeline by PHE in the district of Paschim Medinipur under Midnapore Division, P.W.D during the year 2022-23 | BP-2023-24-82 | 11/05/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 5 | 0 | 0 | 0
2910 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | 1134/W/MMD | 12/04/2023 | 180 | ORIENTAL ENGINEERING CO. | 89.14 | 0 | 0 | 20
2911 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well at Kadra Nimnapalli, Pratiharpara, Mouza Kadra , J.L. No. 867, G.P - Kadra Uttarbil within Garhbeta-I Block under Midnapore Division PHE Dte. | 2585/MD | 21/07/2023 | 15 | M/S. ZAMAN ENTERPRISE | 5.91 | 0 | 0 | 100
2912 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Laying distribution pipe line, Providing FHTC, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 500 Cum (Intze type with solid raft) and staging height 20.00 mtr. with allied work including Construction of 150 Cum capacity CWR for Augmentation of Garhbeta W/S Scheme in Garhbeta-I Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 837/MD | 02/05/2022 | 180 | BANERJEE CONSTRUCTION | 580.16 | 0 | 0 | 72
2913 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. , SM/09933 | Augmentation | Laying additional distribution pipeline for Augmentation of Garhbeta PWSS, Block - Garhbeta-I, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 811/MD | 25/03/2025 | 60 | KISHORE GHOSH | 51.54 | 0 | 0 | 10
2914 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Pingla (Block-Pingla) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1646/MD | 22/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0 | 0 | 0
2915 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Pingla, Block - Pingla) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. | BP-2021-22-396 | 22/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.62 | 0 | 0 | 0
2916 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Continuation Work Order for the work of Laying Balance Distribution System to accommodate FHTC of Proposed Augmentation Pipe Water Supply Scheme for Pingla & its adjoining Mouzas, Block: - Pingla, District: - Paschim Midnapore. Total Length = 12,600.00 Mtr. | 2467/MD | 05/12/2022 | 60 | GOBINDA MAITY | 68.72 | 0 | 0 | 0
2917 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | 2310/W/MMD | 29/12/2022 | 180 | SHOVAN KUMAR DAS | 25.52 | 0 | 0 | 0
2918 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Sinking of 2 (Two) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Pingla W/S Scheme with in Pingla Block under Midnapore Division, P.H.E. Dte. | 229/MD | 17/01/2023 | 14 | GOBINDA MAITY | 20.68 | 0 | 0 | 0
2919 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Material Requisition To Resource Division | 335/MD | 31/01/2023 | 0 | Resource Division | 20.85 | 0 | 0 | 0
2920 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Material Requisition To Resource Division | 139/MD | 11/01/2023 | 0 | Resource Division | 21.67 | 0 | 0 | 0
2921 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Electric quotation for Pingla PWSS Tube Well-III WS Scheme (Ref. ID 203917728) | BP-2022-23-146 | 27/03/2023 | 0 | WBSEDCL | 0.49 | 0 | 0 | 0
2922 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Electric Quotation for Add tw no- IV of Pingla w/s scheme.(Consumer ID-203970943) | BP-2023-24-23 | 28/04/2023 | 0 | WBSEDCL | 2.83 | 0 | 0 | 0
2923 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. |  | 31/01/2023 | 0 | BADAL CHANDRA BERA | 0.63 | 0 | 0 | 0
2924 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Laying distribution pipe line, Soil test and Construction of R.C.C. Over Head Reservoir of capacity 400 CuM and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Pingla & its adjoining mouzas Water Supply Scheme within Pingla Dev. Block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. Dist. Paschim Medinipur. | 1311/MD | 30/06/2022 | 1245 | GOBINDA MAITY | 668 | 0 | 0 | 100
2925 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur.under JJM Program under MMD PHE Dte. | 1375/W/MMD | 30/05/2023 | 680 | SHOVAN KUMAR DAS | 25.24 | 0 | 0 | 20
2926 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. , SM/09999 | Augmentation | Balance work to accommodate FHTC of Augmentation Pipe Water Supply Scheme for Pingla & its adjoining mouzas, Block - Pingla, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 52/MD | 07/01/2025 | 75 | GOBINDA MAITY | 62.68 | 0 | 0 | 100
2927 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11811 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Debhog PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | 1664/MD | 28/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.19 | 0 | 0 | 100
2928 | PASCHIM MEDINIPUR | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11811 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to accommodate FHTC under JJM of Sabang Block in Paschim Medinipur District under Medinipur Division, PHE Dte. | 2271/MD | 09/11/2022 | 45 | S.T. ENTERPRISE | 46.36 | 0 | 0 | 77
2929 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11811 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | 2305/W/MMD | 29/12/2022 | 180 | SUBHASIS ROY | 10.78 | 0 | 0 | 0
2930 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11811 | Augmentation | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW IV of Debhog water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | 1333/MMSD-I | 26/12/2022 | 15 | DEBJYOTI BASU | 4.37 | 0 | 0 | 50
2931 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11811 | Augmentation | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Debhog water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | 1334/MMSD-I | 26/12/2022 | 15 | DEBJYOTI BASU | 4.37 | 0 | 0 | 50
2932 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11811 | Augmentation | Supply and delivery at site Submersible pumping machinery and other electro-mechanical equipment in connection with Rejuvenation of Ground water based piped piped water supply scheme for PH No IV of Debhog Part to accommodate FHTC under Sabang Block in Paschim Medinipur District under M.M.D,.PH.E. DTE. TSM009949 | 601/MMSD-I | 05/06/2023 | 15 | SUBHASIS ROY | 5.76 | 0 | 0 | 0
2933 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11811 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0 | 0 | 25
2934 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11811 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0 | 0 | 100
2935 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11811 | Augmentation | Service Connection charges of WBSEDCL for Additional T/W-III of Debhog Water Supply Scheme (Consumer No. 2004156111) | BP-2022-23-88 | 04/01/2023 | 0 | WBSEDCL | 2.2 | 0 | 0 | 0
2936 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11811 | Augmentation | Service Connection charges of WBSEDCL for Additional T/W-IV of Debhog Water Supply Scheme (Consumer No. 2004156795) | Bp-2022-23-87 | 10/01/2023 | 0 | WBSEDCL | 0.19 | 0 | 0 | 0
2937 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11811 | Augmentation | SUPPLY AND DELIVERY OF FUEL FOR INSPECTION VEHICAL FOR INSPECTION OF JJM WORK AT OFFICE OF THE ASSISTANT ENGINEER MMSD1 | 186./MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 3 | 0 | 0 | 100
2938 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/11811 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments 250 X 150 mm dia. Deep tube well with (A.S.T.M.D. Schedule-80) Medium Duty P.V.C. Pipe and 150 mm dia. Fiberglass strainer sunk AS ADDITIONAL T.W. (T/W No.- III) of Debhog W/S Scheme Within Sabang Block Under Midnapore Division PHE Dte. | 1346/W/MMD | 24/05/2023 | 180 | S.S.GHORAI | 11.88 | 0 | 0 | 100
2939 | PASCHIM MEDINIPUR | Midnapore Division | CHAK BAJIT AND IT'S ADJOINING MOUJAS PWSS , SM/12410 | New | Material Requisition To Resource Division | 1512/MD | 12/05/2023 | 0 | Resource Division | 27.4 | 0 | 0 | 0
2940 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAK BAJIT AND IT'S ADJOINING MOUJAS PWSS , SM/12410 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAK BAJIT AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 796/W/MMD | 24/03/2023 | 180 | CHAKRABORTY MINING & ENGINEERING | 21.58 | 0 | 0 | 38
2941 | PASCHIM MEDINIPUR | Midnapore Division | CHAK BAJIT AND IT'S ADJOINING MOUJAS PWSS , SM/12410 | New | Construction of 150 Cum & 100 Cum Capacity R.C.C Over Head Reservoir (Intze type with solid raft) with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (1904 Nos) including 2 years operation & maintenance For Chak Bajit and Kankara Shibram Pipe Water Supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5061/MD | 26/10/2023 | 638 | ANIRUDDHA BAG | 561.96 | 0 | 0 | 75
2942 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bishnupur PWSS Block Sabang District Paschim Medinipur , SM/08209 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bishnupur PWSS, Block :- Sabang in the District of Paschim Medinipur. | 310/MD | 22/02/2021 | 1114 | KISHORE GHOSH | 90.52 | 31.27 | 34.55 | 80
2943 | PASCHIM MEDINIPUR | Midnapore Division | PARBATIPUR AND ADJOINING MOUJAS PWSS , SM/13105 | New | Material Requisition To Resource Division | 1189/MD | 26/04/2023 | 0 | Resource Division | 76.51 | 0 | 0 | 0
2944 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PARBATIPUR AND ADJOINING MOUJAS PWSS , SM/13105 | New | New service connection charges at Parbatipur TW-I | 226/JMD | 21/06/2024 | 0 | WBSEDCL | 3.52 | 0 | 0 | 0
2945 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PARBATIPUR AND ADJOINING MOUJAS PWSS , SM/13105 | New | New service connection charges at Parbatipur TW-II | 225/JMD | 21/06/2024 | 0 | WBSEDCL | 3.67 | 0 | 0 | 0
2946 | PASCHIM MEDINIPUR | Central Drilling | PARBATIPUR AND ADJOINING MOUJAS PWSS , SM/13105 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2947 | PASCHIM MEDINIPUR | Midnapore Division | SHUJA AND ADJOINING MOUJAS PWSS , SM/13109 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
2948 | PASCHIM MEDINIPUR | Midnapore Division | SHUJA AND ADJOINING MOUJAS PWSS , SM/13109 | New | Material Requisition To Resource Division | 4051/MD | 12/10/2023 | 0 | Resource Division | 23.01 | 0 | 0 | 0
2949 | PASCHIM MEDINIPUR | Midnapore Division | SHUJA AND ADJOINING MOUJAS PWSS , SM/13109 | New | Material Requisition To Resource Division | 3445/MD | 25/11/2024 | 0 | Resource Division | 4.39 | 0 | 0 | 0
2950 | PASCHIM MEDINIPUR | Midnapore Mechanical | SHUJA AND ADJOINING MOUJAS PWSS , SM/13109 | New | Quotation for new power connection at Shuja Pwss T/W - II within Narayangarh Block Application No- 2004857400 , Ref No - 204376544 | BP-2024-25-626 | 02/09/2024 | 0 | WBSEDCL | 3.74 | 0 | 0 | 0
2951 | PASCHIM MEDINIPUR | Midnapore Mechanical | SHUJA AND ADJOINING MOUJAS PWSS , SM/13109 | New | Quotation for new power connection at Shuja Pwss T/W - I within Narayangarh Block Application No- 2004857391 , Ref No - 204376543 | BP-2024-25-625 | 02/09/2024 | 0 | WBSEDCL | 3.15 | 0 | 0 | 0
2952 | PASCHIM MEDINIPUR | Central Drilling | SHUJA AND ADJOINING MOUJAS PWSS , SM/13109 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2953 | PASCHIM MEDINIPUR | Midnapore Division | SHUJA AND ADJOINING MOUJAS PWSS , SM/13109 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
2954 | PASCHIM MEDINIPUR | Midnapore Division | TUTRANGA AND ADJOINING MOUJAS PWSS , SM/13131 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
2955 | PASCHIM MEDINIPUR | Midnapore Division | TUTRANGA AND ADJOINING MOUJAS PWSS , SM/13131 | New | Material Requisition To Resource Division | 1588/MD | 15/05/2023 | 0 | Resource Division | 25.71 | 0 | 0 | 0
2956 | PASCHIM MEDINIPUR | Midnapore Mechanical | TUTRANGA AND ADJOINING MOUJAS PWSS , SM/13131 | New | Quotation for new power connection at Tutranga PWSS T/W- I ,Narayangarh Block , Application no- 2004680694 , ref. Id - 204273484 | BP-2024-25-149 | 09/05/2024 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
2957 | PASCHIM MEDINIPUR | Midnapore Mechanical | TUTRANGA AND ADJOINING MOUJAS PWSS , SM/13131 | New | Quotation for new power connection at Tutranga PWSS T/W- II ,Narayangarh Block , Application no- 2004680728 , ref. Id - 204273486 | BP-2024-25-150 | 09/05/2024 | 0 | WBSEDCL | 2.84 | 0 | 0 | 0
2958 | PASCHIM MEDINIPUR | Central Drilling | TUTRANGA AND ADJOINING MOUJAS PWSS , SM/13131 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2959 | PASCHIM MEDINIPUR | Midnapore Division | TUTRANGA AND ADJOINING MOUJAS PWSS , SM/13131 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
2960 | PASCHIM MEDINIPUR | Midnapore Division | JAHALDA AND IT'S ADJOINING MOUJAS PWSS , SM/13086 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
2961 | PASCHIM MEDINIPUR | Midnapore Division | JAHALDA AND IT'S ADJOINING MOUJAS PWSS , SM/13086 | New | Material Requisition To Resource Division | 1287/MD | 28/04/2023 | 0 | Resource Division | 24.63 | 0 | 0 | 0
2962 | PASCHIM MEDINIPUR | Midnapore Division | JAHALDA AND IT'S ADJOINING MOUJAS PWSS , SM/13086 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF JAHALDA PWSS. REF CONSUMER ID-204373753, APPLICATION NO-2004852919, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | BP-2024-25-294 | 27/08/2024 | 0 | WBSEDCL | 13.22 | 0 | 0 | 0
2963 | PASCHIM MEDINIPUR | Midnapore Division | JAHALDA AND IT'S ADJOINING MOUJAS PWSS , SM/13086 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF JAHALDA PWSS. REF CONSUMER ID-204373747, APPLICATION NO-2004852930, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | BP-2024-25-294 | 27/08/2024 | 0 | WBSEDCL | 9.12 | 0 | 0 | 0
2964 | PASCHIM MEDINIPUR | Central Drilling | JAHALDA AND IT'S ADJOINING MOUJAS PWSS , SM/13086 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2965 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/13709 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Belun PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | 550/AE/KSD | 23/08/2022 | 30 | GOBINDA MAITY | 2.26 | 0 | 0 | 0
2966 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/13709 | Augmentation | Material Requisition To Resource Division | 1370/MD | 02/05/2023 | 0 | Resource Division | 5.84 | 0 | 0 | 0
2967 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/13709 | Augmentation | Electric quotation for Belun PWSS Tube Well-III WS Scheme (Ref. ID 203917727) | BP-2022-23-147 | 27/03/2023 | 0 | WBSEDCL | 0.5 | 0 | 0 | 0
2968 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/13709 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Balance FHTC (127) & Repair of Pump House & or Augmentation of Belun PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 450/MD | 13/02/2023 | 689 | MASUM ALI KHAN | 55.11 | 0 | 0 | 100
2969 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/13709 | Augmentation | Laying additional distribution pipe line to accommodate FHTC (200 Nos.) of Belun Pipe Water Supply Scheme within Pingla Block under Midnapore Division, P.H.E. Dte. | 482/MD | 13/02/2025 | 60 | NIMAI HAZRA | 17.07 | 0 | 0 | 0
2970 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. , SM/13709 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 614/W/MMD | 20/03/2023 | 531 | A.K.SIKDAR | 10.79 | 0 | 0 | 70
2971 | PASCHIM MEDINIPUR | Midnapore Division | JAGARDANGA AND ADJOINING MOUJAS PWSS , SM/13055 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
2972 | PASCHIM MEDINIPUR | Midnapore Division | JAGARDANGA AND ADJOINING MOUJAS PWSS , SM/13055 | New | Material Requisition To Resource Division | 1235/MD | 27/04/2023 | 0 | Resource Division | 37.87 | 0 | 0 | 0
2973 | PASCHIM MEDINIPUR | Central Drilling | JAGARDANGA AND ADJOINING MOUJAS PWSS , SM/13055 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2974 | PASCHIM MEDINIPUR | Midnapore Division | JAMUNA AND ADJOINING MOUJAS PWSS , SM/13056 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
2975 | PASCHIM MEDINIPUR | Midnapore Division | JAMUNA AND ADJOINING MOUJAS PWSS , SM/13056 | New | Material Requisition To Resource Division | 1526/MD | 12/05/2023 | 0 | Resource Division | 29.35 | 0 | 0 | 0
2976 | PASCHIM MEDINIPUR | Central Drilling | JAMUNA AND ADJOINING MOUJAS PWSS , SM/13056 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2977 | PASCHIM MEDINIPUR | Midnapore Division | JAMUNA AND ADJOINING MOUJAS PWSS , SM/13056 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
2978 | PASCHIM MEDINIPUR | Midnapore Division | KATAI AND IT'S ADJOINING MOUJAS PWSS , SM/13088 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
2979 | PASCHIM MEDINIPUR | Midnapore Division | KATAI AND IT'S ADJOINING MOUJAS PWSS , SM/13088 | New | Material Requisition To Resource Division | 1148/MD | 25/04/2023 | 0 | Resource Division | 14.87 | 0 | 0 | 0
2980 | PASCHIM MEDINIPUR | Midnapore Mechanical | KATAI AND IT'S ADJOINING MOUJAS PWSS , SM/13088 | New | Electrict quotation bill for TW-II of KATAI pwss (Ref Consumar ID-204251279),Application No-2004649169,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. | BP-2023-24-916 | 28/03/2024 | 0 | WBSEDCL | 3.51 | 0 | 0 | 0
2981 | PASCHIM MEDINIPUR | Midnapore Division | KATAI AND IT'S ADJOINING MOUJAS PWSS , SM/13088 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | 2145/MD | 08/06/2023 | 846 | GOBINDA MAITY | 1960.6 | 0 | 0 | 65
2982 | PASCHIM MEDINIPUR | Midnapore Mechanical | KATAI AND IT'S ADJOINING MOUJAS PWSS , SM/13088 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KATAI AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 646/W/MMD | 20/03/2023 | 1018 | PINTU DEY | 21.56 | 0 | 0 | 90
2983 | PASCHIM MEDINIPUR | Midnapore Division | SANTRAPUR AND ADJOINING MOUJAS PWSS , SM/13219 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | 746/MD | 13/03/2023 | 30 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 0
2984 | PASCHIM MEDINIPUR | Midnapore Division | SANTRAPUR AND ADJOINING MOUJAS PWSS , SM/13219 | New | Material Requisition To Resource Division | 1323/MD | 28/04/2023 | 0 | Resource Division | 23.2 | 0 | 0 | 0
2985 | PASCHIM MEDINIPUR | Central Drilling | SANTRAPUR AND ADJOINING MOUJAS PWSS , SM/13219 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Santrapur W/S Scheme (TW-I & II), Keshiary Block under PaschimMedinipur District, Central Drilling Division, P.H.E. Dte. | 1436/CDD | 26/09/2023 | 240 | MENAKA ENTERPRISE | 25.33 | 0 | 0 | 100
2986 | PASCHIM MEDINIPUR | Midnapore Division | SANTRAPUR AND ADJOINING MOUJAS PWSS , SM/13219 | New | Material Requisition To Resource Division | 3417/MD | 25/11/2024 | 0 | Resource Division | 12.22 | 0 | 0 | 0
2987 | PASCHIM MEDINIPUR | Midnapore Mechanical | SANTRAPUR AND ADJOINING MOUJAS PWSS , SM/13219 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF SANTRAPUR PWSS. REF CONSUMER ID-204283799, APPLICATION NO-2004695693, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2024-25-274 | 12/06/2024 | 0 | WBSEDCL | 9.04 | 0 | 0 | 0
2988 | PASCHIM MEDINIPUR | Midnapore Mechanical | SANTRAPUR AND ADJOINING MOUJAS PWSS , SM/13219 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF SANTRAPUR PWSS. REF CONSUMER ID-204283797, APPLICATION NO-2004695677, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2024-25-273 | 12/06/2024 | 0 | WBSEDCL | 9.04 | 0 | 0 | 0
2989 | PASCHIM MEDINIPUR | Midnapore Mechanical | SANTRAPUR AND ADJOINING MOUJAS PWSS , SM/13219 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SANTRAPUR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 3072/W/MMD | 29/11/2023 | 520 | SANKAR PRASAD DUTTA AND CO | 22.99 | 0 | 0 | 25
2990 | PASCHIM MEDINIPUR | Midnapore Division | NAHANJARA AND IT'S ADJOINING MOUJAS PWSS , SM/13029 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
2991 | PASCHIM MEDINIPUR | Midnapore Division | NAHANJARA AND IT'S ADJOINING MOUJAS PWSS , SM/13029 | New | Material Requisition To Resource Division | 1289/MD | 28/04/2023 | 0 | Resource Division | 22.38 | 0 | 0 | 0
2992 | PASCHIM MEDINIPUR | Central Drilling | NAHANJARA AND IT'S ADJOINING MOUJAS PWSS , SM/13029 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2993 | PASCHIM MEDINIPUR | Midnapore Division | PUNYA AND IT'S ADJOINING MOUJAS PWSS , SM/13033 | New | Material Requisition To Resource Division | 1290/MD | 28/04/2023 | 0 | Resource Division | 20.99 | 0 | 0 | 0
2994 | PASCHIM MEDINIPUR | Midnapore Mechanical | PUNYA AND IT'S ADJOINING MOUJAS PWSS , SM/13033 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF PUNYA PWSS. REF CONSUMER ID-204412273, APPLICATION NO-2004920306, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102455560774 | 30/10/2024 | 0 | WBSEDCL | 8.8 | 0 | 0 | 0
2995 | PASCHIM MEDINIPUR | Central Drilling | PUNYA AND IT'S ADJOINING MOUJAS PWSS , SM/13033 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2996 | PASCHIM MEDINIPUR | Midnapore Division | BHATMARA AND ADJOINING MOUJAS PWSS , SM/14644 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
2997 | PASCHIM MEDINIPUR | Midnapore Division | BHATMARA AND ADJOINING MOUJAS PWSS , SM/14644 | New | Material Requisition To Resource Division | 1192/MD | 26/04/2023 | 0 | Resource Division | 13.69 | 0 | 0 | 0
2998 | PASCHIM MEDINIPUR | Central Drilling | BHATMARA AND ADJOINING MOUJAS PWSS , SM/14644 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2999 | PASCHIM MEDINIPUR | Midnapore Division | GHAGRASOL AND ADJOINING MOUJAS PWSS , SM/14647 | New | Material Requisition To Resource Division | 1304/MD | 28/04/2023 | 0 | Resource Division | 2.79 | 0 | 0 | 0
3000 | PASCHIM MEDINIPUR | Central Drilling | GHAGRASOL AND ADJOINING MOUJAS PWSS , SM/14647 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3001 | PASCHIM MEDINIPUR | Midnapore Division | BENACHAPRA AND ADJOINING MOUJAS PWSS , SM/14992 | New | Material Requisition To Resource Division | 1258/MD | 28/04/2023 | 0 | Resource Division | 26.15 | 0 | 0 | 0
3002 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BENACHAPRA AND ADJOINING MOUJAS PWSS , SM/14992 | New | New service connection charges for Benachapra pwss, t/w no. II | 46/JMD | 29/04/2024 | 0 | WBSEDCL | 3.44 | 0 | 0 | 0
3003 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BENACHAPRA AND ADJOINING MOUJAS PWSS , SM/14992 | New | New service connection charges for Benachapra pwss, t/w no.I | 33/JMD | 11/03/2024 | 0 | WBSEDCL | 5.66 | 0 | 0 | 0
3004 | PASCHIM MEDINIPUR | Central Drilling | BENACHAPRA AND ADJOINING MOUJAS PWSS , SM/14992 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3005 | PASCHIM MEDINIPUR | Midnapore Division | BENACHAPRA AND ADJOINING MOUJAS PWSS , SM/14992 | New | Route survey & way leave permission along & across of National Highway in Benachapra PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | 374/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 11.64 | 0 | 0 | 0
3006 | PASCHIM MEDINIPUR | Midnapore Division | GOTSHINGLA AND ADJOINING MOUJAS PWSS , SM/15010 | New | Material Requisition To Resource Division | 3390/MD | 25/11/2024 | 0 | Resource Division | 3.79 | 0 | 0 | 0
3007 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GOTSHINGLA AND ADJOINING MOUJAS PWSS , SM/15010 | New | WBSEDCL new connection payment for Goatsingla t/w 1 | 67/JMD | 29/04/2024 | 0 | WBSEDCL | 3.68 | 0 | 0 | 0
3008 | PASCHIM MEDINIPUR | Central Drilling | GOTSHINGLA AND ADJOINING MOUJAS PWSS , SM/15010 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3009 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/13167 | New | Material Requisition To Resource Division | 103/MD | 10/01/2023 | 0 | Resource Division | 34.55 | 0 | 0 | 0
3010 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/13167 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 839/W/MMD | 24/03/2023 | 180 | SHOVAN KUMAR DAS | 27.39 | 0 | 0 | 90
3011 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/13167 | New | Material Requisition To Resource Division | 3330/MD | 25/11/2024 | 0 | Resource Division | 23.3 | 0 | 0 | 0
3012 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/13167 | New | Quotation for new service connection at Khandanga T/W-II water supply scheme. | 307/JMD | 14/08/2024 | 0 | WBSEDCL | 5.56 | 0 | 0 | 0
3013 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/13167 | New | Quotation for new service connection at Khandanga TW-I water supply scheme. | 306/JMD | 14/08/2024 | 0 | WBSEDCL | 6.54 | 0 | 0 | 0
3014 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/13167 | New | Laying of rising main & interconnection for Khandanga & its adjoining mouzas PWSS, Block: - Chandrakona-II, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 317/MD | 29/01/2025 | 45 | AMAL DUTTA ROY | 16.19 | 0 | 0 | 0
3015 | PASCHIM MEDINIPUR | Midnapore Division | SHYAMNAGAR AND ADJOINING MOUJAS PWSS , SM/13173 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
3016 | PASCHIM MEDINIPUR | Midnapore Division | SHYAMNAGAR AND ADJOINING MOUJAS PWSS , SM/13173 | New | Material Requisition To Resource Division | 1150/MD | 25/04/2023 | 0 | Resource Division | 54.02 | 0 | 0 | 0
3017 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SHYAMNAGAR AND ADJOINING MOUJAS PWSS , SM/13173 | New | New Service connection charges. | 58/JMD | 13/03/2024 | 0 | WBSEDCL | 7.09 | 0 | 0 | 0
3018 | PASCHIM MEDINIPUR | Central Drilling | SHYAMNAGAR AND ADJOINING MOUJAS PWSS , SM/13173 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3019 | PASCHIM MEDINIPUR | Midnapore Division | SHYAMNAGAR AND ADJOINING MOUJAS PWSS , SM/13173 | New | Route survey & way leave permission along & across of National Highway in Shyamnagar PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | 1629/MD | 06/08/2025 | 21 | PIONEER SURVEYORS | 8.64 | 0 | 0 | 0
3020 | PASCHIM MEDINIPUR | Midnapore Division | GILABANI AND ADJOINING MOUJAS PWSS , SM/13142 | New | Material Requisition To Resource Division | 1182/MD | 26/04/2023 | 0 | Resource Division | 31.67 | 0 | 0 | 0
3021 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GILABANI AND ADJOINING MOUJAS PWSS , SM/13142 | New | New service connection charges at Gilabani TW-II | 223/JMD | 21/06/2024 | 0 | WBSEDCL | 3.22 | 0 | 0 | 0
3022 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GILABANI AND ADJOINING MOUJAS PWSS , SM/13142 | New | New service connection charges at Gilabani TW-I | 224/JMD | 21/06/2024 | 0 | WBSEDCL | 5.08 | 0 | 0 | 0
3023 | PASCHIM MEDINIPUR | Central Drilling | GILABANI AND ADJOINING MOUJAS PWSS , SM/13142 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3024 | PASCHIM MEDINIPUR | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS , SM/13078 | New | Sinking of 2 (Two) Nos. 250 X 150 mm dia. X 180 mtr. Depth deep tube well by direct rotary method Proposed Pipe Water Supply Scheme for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-VI] | 974/MD | 10/04/2023 | 21 | ANNAPURNA TUBEWELL WORKS | 17.57 | 0 | 0 | 100
3025 | PASCHIM MEDINIPUR | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS , SM/13078 | New | Material Requisition To Resource Division | 1300/MD | 28/04/2023 | 0 | Resource Division | 27.76 | 0 | 0 | 0
3026 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS , SM/13078 | New | Electric quotation bill for Tw No-I of Chotanakdana water supply scheme.(Ref Id-204061140) | BP-2023-24-185 | 11/08/2023 | 0 | WBSEDCL | 3.42 | 0 | 0 | 0
3027 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS , SM/13078 | New | Electric quotation bill for Tw No-II of Chhotanakdana water supply scheme.(Ref Id-204061142). | BP-2023-24-186 | 11/08/2023 | 0 | WBSEDCL | 5.41 | 0 | 0 | 0
3028 | PASCHIM MEDINIPUR | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS , SM/13078 | New | Laying distribution of Pipe line and accommodate FHTC work (320 Nos.) for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-V] | 977/MD | 10/04/2023 | 709 | S.T. ENTERPRISE | 95.59 | 0 | 0 | 70
3029 | PASCHIM MEDINIPUR | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS , SM/13078 | New | Laying distribution pipe line and Accommodate FHTC (316 Nos.) under JJM with allied work for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-III] | 976/MD | 10/04/2023 | 60 | SANJIT SINHA | 49.38 | 0 | 0 | 70
3030 | PASCHIM MEDINIPUR | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS , SM/13078 | New | Laying distribution pipe line and Accommodate FHTC (320 Nos.) under JJM with allied work for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-II] | 1386/MD | 02/05/2023 | 60 | S.N. ENTERPRISE (PROP. DIBYENDU GUHA) | 76.5 | 0 | 0 | 66
3031 | PASCHIM MEDINIPUR | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS , SM/13078 | New | Construction and Commissioning of 250 Cum Capacity (Intze Type with Pile) Over Headed Reservoir, Soil Investigation, Construction of Pump House, Boundary wall, Laying of Rising main, accommodate FHTC (320 Nos.) with 2 years operation & maintenance for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-I] | 2257/MD | 23/07/2024 | 180 | M/S R.N. ENTERPRISE | 136.16 | 0 | 0 | 0
3032 | PASCHIM MEDINIPUR | Central Drilling | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS , SM/13078 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3033 | PASCHIM MEDINIPUR | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS , SM/13078 | New | Laying distribution of Pipe line, Construction of Pump House, Boundary wall and Accommodate FHTC work (360 Nos.) for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-IV] | 2578/MD | 22/08/2024 | 120 | S.N ENTERPRISE | 95.96 | 0 | 0 | 0
3034 | PASCHIM MEDINIPUR | Midnapore Division | UTATR KARKARA AND ADJOINING MOUJAS PWSS , SM/13129 | New | Material Requisition To Resource Division | 4052/MD | 12/10/2023 | 0 | Resource Division | 25.14 | 0 | 0 | 0
3035 | PASCHIM MEDINIPUR | Midnapore Division | UTATR KARKARA AND ADJOINING MOUJAS PWSS , SM/13129 | New | Material Requisition To Resource Division | 3444/MD | 25/11/2024 | 0 | Resource Division | 5.12 | 0 | 0 | 0
3036 | PASCHIM MEDINIPUR | Midnapore Mechanical | UTATR KARKARA AND ADJOINING MOUJAS PWSS , SM/13129 | New | Quotation for new power connection at Uttar Karkara PWSS T/W- I ,Narayangarh Block , Application no- 2004683009 , ref. Id - 204276095 | BP-2024-25-151 | 09/05/2024 | 0 | WBSEDCL | 7.19 | 0 | 0 | 0
3037 | PASCHIM MEDINIPUR | Central Drilling | UTATR KARKARA AND ADJOINING MOUJAS PWSS , SM/13129 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3038 | PASCHIM MEDINIPUR | Midnapore Division | UTATR KARKARA AND ADJOINING MOUJAS PWSS , SM/13129 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 0 | 20
3039 | PASCHIM MEDINIPUR | Midnapore Division | UTATR KARKARA AND ADJOINING MOUJAS PWSS , SM/13129 | New | Construction of approach road for 2nd work site of Uttar Karkara Piped Water Supply Scheme within Narayangarh Block under Midnapore Division, PHE Dte. [100 Mtr. Long X 3 Mtr. Width] | 997/AE/HQ/MD | 22/04/2025 | 30 | GOURMOHAN DAS | 1.14 | 0 | 0 | 0
3040 | PASCHIM MEDINIPUR | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS , SM/13805 | New | Material Requisition To Resource Division | 1359/MD | 02/05/2023 | 0 | Resource Division | 55.34 | 0 | 0 | 0
3041 | PASCHIM MEDINIPUR | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS , SM/13805 | New | Laying distribution pipeline & Accommodate FHTC (555 Nos.) under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | 2474/MD | 14/07/2023 | 961 | WATER LINK | 81.95 | 0 | 0 | 50
3042 | PASCHIM MEDINIPUR | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS , SM/13805 | New | Laying distribution pipeline & Accommodate FHTC (400 Nos.) under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-F] | 4002/MD | 06/10/2023 | 60 | SK. MAIDUL ISLAM | 50.44 | 0 | 0 | 50
3043 | PASCHIM MEDINIPUR | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS , SM/13805 | New | Sinking of 2 (Two) Nos. Tube well for Bag Basa & its adjoining mouzas PWSS in Salboni block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | 2515/MD | 18/07/2023 | 30 | ANNAPURNA TUBEWELL WORKS | 15.96 | 0 | 0 | 100
3044 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BAGBASA AND ADJOINING MOUJAS PWSS , SM/13805 | New | New service connection charges for Bagbasa tw-II | 82/JMD | 12/02/2024 | 0 | WBSEDCL | 6.09 | 0 | 0 | 0
3045 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BAGBASA AND ADJOINING MOUJAS PWSS , SM/13805 | New | New service connection charges for Bagbasa tw-I | 74/JMD | 12/02/2024 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
3046 | PASCHIM MEDINIPUR | Central Drilling | BAGBASA AND ADJOINING MOUJAS PWSS , SM/13805 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3047 | PASCHIM MEDINIPUR | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS , SM/13805 | New | Laying Rising main, Distribution pipeline & Accommodate FHTC (400 Nos.) including 2 years O & M under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | 3241/MD | 11/09/2023 | 961 | MIDNAPUR PIPE CONCERN | 132.56 | 0 | 0 | 20
3048 | PASCHIM MEDINIPUR | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS , SM/13805 | New | Construction of Pump House & Boundary wall under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 2037/MD | 01/07/2024 | 420 | M/S. INDRAJIT ROY | 26.6 | 0 | 0 | 10
3049 | PASCHIM MEDINIPUR | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS , SM/13805 | New | Construction of 200 cum OHR (Intze type with solid raft) & Accommodate FHTC (400 Nos.) under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 608/MD | 04/03/2025 | 360 | KRISHNENDU SEKHAR DAS | 88.98 | 0 | 0 | 0
3050 | PASCHIM MEDINIPUR | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS , SM/13805 | New | Construction of Pump House under JJM for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 3164/MD | 05/10/2024 | 120 | A R ENTERPRISE | 7.17 | 0 | 0 | 80
3051 | PASCHIM MEDINIPUR | Midnapore Division | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14131 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Radhanagr & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | 1756/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.12 | 0 | 0 | 0
3052 | PASCHIM MEDINIPUR | Midnapore Division | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14131 | New | Material Requisition To Resource Division | 3364/MD | 25/11/2024 | 0 | Resource Division | 16.7 | 0 | 0 | 0
3053 | PASCHIM MEDINIPUR | Midnapore Mechanical | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14131 | New | QUOTATION MONEY FOR RADHANAGAR WATER SUPPLY SCHEME, T W NO 2 JJM WORKS, SCHEME CODE SM/14131, APPLICATION NO 2004759835, REFERENCE ID 204321895, BIRSINGHA CCC, WBSEDCL | BP-2024-25-302 | 18/06/2024 | 0 | WBSEDCL | 6.7 | 0 | 0 | 0
3054 | PASCHIM MEDINIPUR | Midnapore Mechanical | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14131 | New | QUOTATION MONEY FOR RADHANAGAR WATER SUPPLY SCHEME, T W NO I JJM WORKS, SCHEME CODE SM/14131, APPLICATION NO 2004759827, REFERENCE ID 204321839, BIRSINGHA CCC, WBSEDCL | BP-2024-25-303 | 18/06/2024 | 0 | WBSEDCL | 5.19 | 0 | 0 | 0
3055 | PASCHIM MEDINIPUR | Midnapore Mechanical | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14131 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 589/W/MMD | 20/03/2023 | 748 | K.S.P. ENTERPRISE | 25.24 | 0 | 0 | 80
3056 | PASCHIM MEDINIPUR | Midnapore Mechanical | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14131 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
3057 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. , SM/13822 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kalaikunda, Block - Kharagpur-I) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. | 67/MD | 11/01/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.52 | 0 | 0 | 100
3058 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. , SM/13822 | Augmentation | Electric Quotation for KALAIKUNDA Water Supply Scheme T/W-I (Ref. ID-212248275) | BP-2023-24-174 | 04/08/2023 | 0 | WBSEDCL | 0.95 | 0 | 0 | 0
3059 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. , SM/13822 | Augmentation | Laying distribution pipe line, Soil test, FHTC & Construction of R.C.C. Over Head Reservoir of capacity 300 Cum and staging height 20.00 mtr. with allied work for Augmentation of Kalaikunda W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 2411/MD | 25/11/2022 | 917 | ASHIM KUMAR DEY | 226.86 | 0 | 0 | 69
3060 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. , SM/13822 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | 1129/W/MMD | 12/04/2023 | 180 | P.K.ENGINEERING | 23.75 | 0 | 0 | 70
3061 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. , SM/13822 | Augmentation | Material Requisition To Resource Division | 3418/MD | 25/11/2024 | 0 | Resource Division | 14.5 | 0 | 0 | 0
3062 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. , SM/13822 | Augmentation | Cleaning the chokage of pipe in the existing line at Kalaikunda PWSS under Kharagpur Sub-Division of Midnapur Division, P.H.E Dte. | 3582/MD | 06/12/2024 | 30 | M/S. GEO | 4.56 | 0 | 0 | 100
3063 | PASCHIM MEDINIPUR | Midnapore Division | KUBIR CHAK PIPED WATER SUPPLY SCHEME , SM/14484 | New | Material Requisition To Resource Division | 3370/MD | 25/11/2024 | 0 | Resource Division | 9.42 | 0 | 0 | 0
3064 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUBIR CHAK PIPED WATER SUPPLY SCHEME , SM/14484 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of KUBIR CHAK PWSS. REF CONSUMER ID-204240650, APPLICATION NO-2004634372, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | BP-2023-24-848 | 14/03/2024 | 0 | WBSEDCL | 4.34 | 0 | 0 | 0
3065 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUBIR CHAK PIPED WATER SUPPLY SCHEME , SM/14484 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of KUBIR CHAK PWSS. REF CONSUMER ID-204266459, APPLICATION NO-2004670480, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-46 | 18/04/2024 | 0 | WBSEDCL | 4.92 | 0 | 0 | 0
3066 | PASCHIM MEDINIPUR | Midnapore Division | KUBIR CHAK PIPED WATER SUPPLY SCHEME , SM/14484 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 0 | 75
3067 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUBIR CHAK PIPED WATER SUPPLY SCHEME , SM/14484 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUBIR CHAK PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | 457/W/MMD | 20/03/2023 | 805 | KAMAKSHYA ENTERPRISE | 22.77 | 0 | 0 | 25
3068 | PASCHIM MEDINIPUR | Midnapore Division | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS , SM/14939 | New | Material Requisition To Resource Division | 1143/MD | 25/04/2023 | 0 | Resource Division | 16.01 | 0 | 0 | 0
3069 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS , SM/14939 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUMARSANDA AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 1276/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 22.54 | 0 | 0 | 90
3070 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS , SM/14939 | New | Electric quotation bill for kumarsanda pwss at pump house NO-I (Ref Id-204159129) | BP-2023-24-458 | 21/12/2023 | 0 | WBSEDCL | 5.97 | 0 | 0 | 0
3071 | PASCHIM MEDINIPUR | Midnapore Mechanical | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS , SM/14939 | New | Electric quotation bill for KUMARSANDA pwss at TW-II (Ref Id-204158498) | BP-2023-24-491 | 29/12/2023 | 0 | WBSEDCL | 3.17 | 0 | 0 | 0
3072 | PASCHIM MEDINIPUR | Midnapore Division | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS , SM/14939 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | 2145/MD | 08/06/2023 | 846 | GOBINDA MAITY | 1960.6 | 0 | 0 | 65
3073 | PASCHIM MEDINIPUR | Midnapore Division | PALAIBANI AND ADJOINING MOUJAS PWSS , SM/15026 | New | Material Requisition To Resource Division | 1268/MD | 28/04/2023 | 0 | Resource Division | 22.39 | 0 | 0 | 0
3074 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PALAIBANI AND ADJOINING MOUJAS PWSS , SM/15026 | New | New Service Connection Charges for Palaiboni T/W -I PWSS | 351/JMD | 13/09/2024 | 0 | WBSEDCL | 8.03 | 0 | 0 | 0
3075 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PALAIBANI AND ADJOINING MOUJAS PWSS , SM/15026 | New | New Service Connection Charges for Palaiboni-II PWSS | 352/JMD | 13/09/2024 | 0 | WBSEDCL | 7.97 | 0 | 0 | 0
3076 | PASCHIM MEDINIPUR | Central Drilling | PALAIBANI AND ADJOINING MOUJAS PWSS , SM/15026 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3077 | PASCHIM MEDINIPUR | Midnapore Division | PUKHARIA SOL AND ADJOINING MOUJAS PWSS , SM/15029 | New | Material Requisition To Resource Division | 2226/MD | 15/06/2023 | 0 | Resource Division | 32.3 | 0 | 0 | 0
3078 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PUKHARIA SOL AND ADJOINING MOUJAS PWSS , SM/15029 | New | New service connection charges for Pukuriasole w/s scheme, t/w no.I | 42/JMD | 11/03/2024 | 0 | WBSEDCL | 8.33 | 0 | 0 | 0
3079 | PASCHIM MEDINIPUR | Central Drilling | PUKHARIA SOL AND ADJOINING MOUJAS PWSS , SM/15029 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3080 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Quotation Bill of PH-I, Dewanchak water supply scheme under MMD PHE Dte. | 2003978666 | 28/06/2022 | 365 | WBSEDCL | 0.11 | 0 | 0 | 0
3081 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Electric quotation BIRSINGHA CCC at Chowka, chowka, Ghatal, T/W-I Pin-721232 |  | 17/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3082 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Electric quotation BIRSINGHA CCC at Gholsai, Chowka, a, Ghatal, T/W-II Pin-721232 |  | 17/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3083 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Electric quotation BIRSINGHA CCC at Gholsai, Chowka, a, Ghatal, T/W-I Pin-721232 |  | 17/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3084 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Electric quotation BIRSINGHA CCC at Chowka, chowka, Ghatal, T/W-II Pin-721232 |  | 17/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3085 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Preparation of D.P.Rs (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- (i) Chauka & (ii) Masarpur under Dewanchak-II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | 1330/MD | 17/08/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 3.46 | 0 | 0 | 0
3086 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Chowka water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | 2171/W/MMD | 12/12/2022 | 120 | M/S BARMAN ROY TRADERS | 5.93 | 0 | 0 | 0
3087 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-I under Chowka water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | 2170/W/MMD | 12/12/2022 | 120 | BHABANI PRASAD MANNA | 5.93 | 0 | 0 | 0
3088 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Electric quotation BIRSINGHA CCC at Chowka, chowka, Ghatal, T/W-I Pin-721232 | BP-2022-23-72 | 14/12/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3089 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Electric quotation BIRSINGHA CCC at Gholsai, Chowka, a, Ghatal, T/W-I Pin-721232 | BP-2022-23-74 | 14/12/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3090 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Electric quotation BIRSINGHA CCC at Gholsai, Chowka, a, Ghatal, T/W-II Pin-721232 | BP-2022-23-75 | 14/12/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3091 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Electric quotation BIRSINGHA CCC at Chowka, chowka, Ghatal, T/W-II Pin-721232 | BP-2022-23-73 | 14/12/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3092 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chauka (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | BP-2022-23-661 | 29/03/2023 | 0 | M/S. D.K.H.CONSTRUCTION | 3.05 | 0 | 0 | 0
3093 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chauka (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 1675/MD | 12/08/2022 | 150 | M/S. D.K.H.CONSTRUCTION | 39.56 | 0 | 0 | 91
3094 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Material Requisition To Resource Division | 3351/MD | 25/11/2024 | 0 | Resource Division | 2.67 | 0 | 0 | 0
3095 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. , SM/10648 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chauka (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | 1676/MD | 12/08/2022 | 872 | M/S. D.K.H.CONSTRUCTION | 45.86 | 0 | 0 | 91
3096 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. , SM/15567 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Ghatal block under Midnapore Division P.H.E. Dte. | 2683/MD | 30/12/2022 | 21 | RISHAN ENGINEERING CONSULTANCY | 7.72 | 0 | 0 | 100
3097 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. , SM/15567 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Daspur-I block under Midnapore Division P.H.E. Dte. | 2682/MD | 30/12/2022 | 21 | RISHAN ENGINEERING CONSULTANCY | 7.76 | 0 | 0 | 100
3098 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. , SM/15567 | Augmentation | Material Requisition To Resource Division | 407/MD | 07/02/2023 | 0 | Resource Division | 3.42 | 0 | 0 | 0
3099 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. , SM/15567 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 918/W/MMD | 27/03/2023 | 180 | MAA TARA ENTERPRISE | 25.2 | 0 | 0 | 85
3100 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. , SM/15567 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (325) for Augmentation of Ranapur PWSS in Daspur-I block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2812/MD | 07/08/2023 | 383 | KISHORE GHOSH | 82.99 | 0 | 0 | 70
3101 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. , SM/15567 | Augmentation | QUOTATION MONEY FOR RANAPUR WATER SUPPLY SCHEME, T W NO III [ BAIDYAPUR ] , JJM WORKS, SCHEME CODE SM/15567, [ PARENT CODE - SM/04578 ] APPLICATION NO 2004648343, REFERENCE ID 204250593, DASPUR CCC, WBSEDCL | BP-2024-25-70 | 24/04/2024 | 0 | WBSEDCL | 10.58 | 0 | 0 | 0
3102 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. , SM/15567 | Augmentation | QUOTATION MONEY FOR RANAPUR WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/15567, APPLICATION NO 2004697947, REFERENCE ID 204284912, DASPUR CCC, WBSEDCL |  | 29/04/2024 | 0 | WBSEDCL | 3.09 | 0 | 0 | 0
3103 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. , SM/15567 | Augmentation | QUOTATION MONEY FOR RANAPUR WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/15567, APPLICATION NO 2004697947, REFERENCE ID 204284912, DASPUR CCC, WBSEDCL | BP-2024-25-117 | 06/05/2024 | 0 | WBSEDCL | 3.09 | 0 | 0 | 0
3104 | PASCHIM MEDINIPUR | Midnapore Division | PELAGERYA & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/16378 | New | Material Requisition To Resource Division | 193/MD | 16/01/2023 | 0 | Resource Division | 44.34 | 0 | 0 | 0
3105 | PASCHIM MEDINIPUR | Midnapore Mechanical | PELAGERYA & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/16378 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PELAGERYA & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. under JJM Program under MMD PHE Dte. | 836/W/MMD | 24/03/2023 | 180 | HARA PROSAD DAS | 23.73 | 0 | 0 | 20
3106 | PASCHIM MEDINIPUR | Midnapore Division | PELAGERYA & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/16378 | New | Material Requisition To Resource Division | 3435/MD | 25/11/2024 | 0 | Resource Division | 16.31 | 0 | 0 | 0
3107 | PASCHIM MEDINIPUR | Midnapore Mechanical | PELAGERYA & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/16378 | New | Quotation for new power connection at Pelageriya PWSS P/H- II , application no - 2004608985 , Ref id - 204222610 | BP-2023-24-774 | 06/03/2024 | 0 | WBSEDCL | 3.33 | 0 | 0 | 0
3108 | PASCHIM MEDINIPUR | Midnapore Mechanical | PELAGERYA & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/16378 | New | Quotation for new power connection at Pelageriya PWSS P/H- I , application no - 2004609021 , Ref id - 204222609 | BP-2023-24-773 | 06/03/2024 | 0 | WBSEDCL | 5.26 | 0 | 0 | 0
3109 | PASCHIM MEDINIPUR | Midnapore Division | PELAGERYA & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. , SM/16378 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 350 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (2,648 nos.) under JJM with allied work including 02 (Two ) Years Operation & Maintenance for Pelagerya & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 2952/MD | 17/08/2023 | 997 | A.J. ENTERPRISE | 605.48 | 0 | 0 | 61
3110 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15905 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Ghatal block under Midnapore Division P.H.E. Dte. | 2683/MD | 30/12/2022 | 21 | RISHAN ENGINEERING CONSULTANCY | 7.72 | 0 | 0 | 100
3111 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15905 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Daspur-I block under Midnapore Division P.H.E. Dte. | 2682/MD | 30/12/2022 | 21 | RISHAN ENGINEERING CONSULTANCY | 7.76 | 0 | 0 | 100
3112 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15905 | Augmentation | Material Requisition To Resource Division | 413/MD | 07/02/2023 | 0 | Resource Division | 6.69 | 0 | 0 | 0
3113 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15905 | Augmentation | SUPAPURSURI WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/15905, APPLICATION NO 2004588382, REFERENCE ID 204209925, DASPUR CCC, WBSEDCL | BP-2023-24-787 | 06/03/2024 | 0 | WBSEDCL | 3.08 | 0 | 0 | 0
3114 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15905 | Augmentation | QUOTATION MONEY FOR SUPAPURSURI WATER SUPPLY SCHEME, T W NO 2 , [ AUGMENTATION ] , JJM WORKS, SCHEME CODE SM/15905, APPLICATION NO 2004809558, REFERENCE ID 204352004, DASPUR CCC, WBSEDCL. | C072443865657 | 29/07/2024 | 0 | WBSEDCL | 4.59 | 0 | 0 | 0
3115 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15905 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (998) for Augmentation of Supapursuri PWSS in Daspur-I block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2720/MD | 31/07/2023 | 819 | M/S. D.K.H.CONSTRUCTION | 127.08 | 0 | 0 | 15
3116 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15905 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | 1133/W/MMD | 12/04/2023 | 540 | BUSR ENGINEERING | 25.25 | 0 | 0 | 100
3117 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/15905 | Augmentation | Laying additional distribution system pipe line to provide balance FHTC for Augmentation of Supapursuri W/S Scheme, Block - Daspur-I, Dist.- Paschim Medinipur under Midnapore Division, PHE Dte. (PART-B) | 2847/MD | 09/09/2024 | 204 | SK REAJUL HOSSAIN | 15.33 | 0 | 0 | 100
3118 | PASCHIM MEDINIPUR | Midnapore Division | KADAMDIHA AND IT'S ADJOINING MOUJAS PWSS , SM/16620 | New | Material Requisition To Resource Division | 3391/MD | 25/11/2024 | 0 | Resource Division | 11.09 | 0 | 0 | 0
3119 | PASCHIM MEDINIPUR | Central Drilling | KADAMDIHA AND IT'S ADJOINING MOUJAS PWSS , SM/16620 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3120 | PASCHIM MEDINIPUR | Midnapore Division | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/16632 | New | Material Requisition To Resource Division | 106/MD | 10/01/2023 | 0 | Resource Division | 43.22 | 0 | 0 | 0
3121 | PASCHIM MEDINIPUR | Midnapore Division | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/16632 | New | Material Requisition To Resource Division | 3338/MD | 25/11/2024 | 0 | Resource Division | 4.95 | 0 | 0 | 0
3122 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/16632 | New | QUOTATION MONEY FOR RAMCHANDRAPUR WATER SUPPLY SCHEME, T W - II , JJM WORKS, SCHEME CODE SM/16632, APPLICATION NO 2004696180, REFERENCE ID 204284327, DASPUR CCC, WBSEDCL | BP-2024-25-116 | 06/05/2024 | 0 | WBSEDCL | 3.18 | 0 | 0 | 0
3123 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/16632 | New | QUOTATION MONEY FOR RAMCHANDRAPUR WATER SUPPLY SCHEME, T W - I , JJM WORKS, SCHEME CODE SM/16632, APPLICATION NO 2004696177, REFERENCE ID 204284325, DASPUR CCC, WBSEDCL | BP-2024-25-115 | 06/05/2024 | 0 | WBSEDCL | 3.19 | 0 | 0 | 0
3124 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/16632 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 537/W/MMD | 20/03/2023 | 1108 | BALAJI CONSTRUCTION | 22.79 | 0 | 0 | 80
3125 | PASCHIM MEDINIPUR | Midnapore Division | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/16632 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 150 cum OHR (Intze type with pile foundation) & Accommodate FHTC (803 nos) under JJM with allied work for Ramchandrapur PWSS in Daspur- I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2416/MD | 13/07/2023 | 897 | SAI TUBE CO. | 284.53 | 0 | 0 | 80
3126 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/18184 | New | Material Requisition To Resource Division | 1524/MD | 12/05/2023 | 0 | Resource Division | 53.67 | 0 | 0 | 0
3127 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/18184 | New | New Service connection charges. | 81/JMD | 20/03/2024 | 0 | WBSEDCL | 6.88 | 0 | 0 | 0
3128 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/18184 | New | New Service connection charges. | 97/JMD | 22/02/2024 | 0 | WBSEDCL | 4.13 | 0 | 0 | 0
3129 | PASCHIM MEDINIPUR | Midnapore Mechanical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. , SM/18184 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 1123/W/MMD | 12/04/2023 | 811 | R.S. ENTERPRISE | 25.24 | 0 | 0 | 60
3130 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Dhamsai PWSS in the District of Paschim Medinipur under JJM programme. , SM/17754 | Augmentation | Rejuvenation of Electro-Mechanical components of Dhamsai PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | 1060/W/MMD | 29/03/2023 | 180 | PADMA ENGINEERING CO. | 11.37 | 0 | 0 | 40
3131 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. , SM/17946 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing (i) Chakmakrampur PWSS within Kharagpur-II block & (ii) Shyamsundarpur PWSS within Sabang Block under Midnapore Division P.H.E. Dte. | 2063/MD | 30/09/2022 | 15 | GOBINDA MAITY | 5.83 | 0 | 0 | 0
3132 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. , SM/17946 | Augmentation | Material Requisition To Resource Division | 204/MD | 16/01/2023 | 0 | Resource Division | 6.8 | 0 | 0 | 0
3133 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. , SM/17946 | Augmentation | Material Requisition To Resource Division | 3436/MD | 25/11/2024 | 0 | Resource Division | 18.82 | 0 | 0 | 0
3134 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. , SM/17946 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur.under JJM Program under MMD. PHE Dte. | 539/W/MMD | 20/03/2023 | 900 | M/S. S.R. ENTERPRISE | 22.75 | 0 | 0 | 65
3135 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. , SM/17946 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall for Augmentation of Chakmakrampur PWSS in Kharagpur-II Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 948/MD | 06/04/2023 | 722 | ASIS KUMAR SARANGI | 292.42 | 0 | 0 | 45
3136 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chandpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17360 | Solarisation | Solarization of grid connected pumping installation at Chandpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 682/W/MMD | 23/03/2023 | 180 | A-NIK & CO. | 6.26 | 0 | 0 | 65
3137 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Nona Pingla PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17363 | Solarisation | Solarization of grid connected pumping installation at Pingla PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 700/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
3138 | PASCHIM MEDINIPUR | Midnapore Division | Rabidaspur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/17567 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Rabidaspur, Tiorberya & Ramchandrapur & its adjoining Mouzas PWSS instead Rabidaspur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | 1267/MD | 23/06/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.37 | 0 | 0 | 100
3139 | PASCHIM MEDINIPUR | Midnapore Division | Rabidaspur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/17567 | New | Material Requisition To Resource Division | 1586/MD | 15/05/2023 | 0 | Resource Division | 43.26 | 0 | 0 | 0
3140 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rabidaspur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/17567 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER DASPUR - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTEunder JJM Program under MMD PHE Dte. | 1694/W/MMD | 04/08/2023 | 759 | A G ENTERPRISE | 78.38 | 0 | 0 | 20
3141 | PASCHIM MEDINIPUR | Midnapore Division | Rabidaspur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/17567 | New | Sinking of Tube Well, Rising main, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 150 cum OHR (Intze type with pile foundation) & Accommodate FHTC (863 nos.) including 2 years of Operation & Maintenance under JJM with allied work for Rabidaspur PWSS in Daspur- I Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 5065/MD | 26/10/2023 | 717 | ZENITH CONSTRUCTION | 310.14 | 0 | 0 | 10
3142 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DWARKHOLA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/17574 | New | Material Requisition To Resource Division | 535/MD | 21/02/2023 | 0 | Resource Division | 7.23 | 0 | 0 | 0
3143 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DWARKHOLA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/17574 | New | Sinking of Tube well, Laying distribution pipe line, Rising main, Pump House, Boundary wall & Accommodate FHTC (105 Nos.) including 2 yrs. O & M under JJM with allied work for Dwarkhola PWSS in Chandrakona-I block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2431/MD | 13/07/2023 | 60 | WATER LINK | 53.82 | 0 | 0 | 35
3144 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DWARKHOLA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/17574 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER CHANDRAKONA - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICTunder JJM Program under MMD PHE Dte. | 1693/W/MMD | 04/08/2023 | 180 | AMUSAR IMPEX PVT. LTD | 49.92 | 0 | 0 | 80
3145 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DWARKHOLA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE , SM/17574 | New | New Service connection charges. | 31/JMD | 01/02/2024 | 0 | WBSEDCL | 4.69 | 0 | 0 | 0
3146 | PASCHIM MEDINIPUR | Midnapore Division | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/17575 | New | Material Requisition To Resource Division | 4054/MD | 12/10/2023 | 0 | Resource Division | 32.99 | 0 | 0 | 0
3147 | PASCHIM MEDINIPUR | Midnapore Division | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/17575 | New | Material Requisition To Resource Division | 3389/MD | 25/11/2024 | 0 | Resource Division | 7.18 | 0 | 0 | 0
3148 | PASCHIM MEDINIPUR | Midnapore Mechanical | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/17575 | New | QUOTATION MONEY FOR TIORBERYA WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, BLOCK- DASPUR-I, SCHEME CODE SM/17575, APPLICATION NO 2004826966, REFERENCE ID 204360838, DASPUR CCC, WBSEDCL | C082441589956 | 29/08/2024 | 0 | WBSEDCL | 6.75 | 0 | 0 | 0
3149 | PASCHIM MEDINIPUR | Midnapore Mechanical | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/17575 | New | QUOTATION MONEY FOR TIORBERYA WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/17575, APPLICATION NO 2004723249, REFERENCE ID 204300057, SONAKHALI CCC, WBSEDCL | BP-2024-25-182 | 20/05/2024 | 0 | WBSEDCL | 5.68 | 0 | 0 | 0
3150 | PASCHIM MEDINIPUR | Midnapore Mechanical | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/17575 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER DASPUR - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTEunder JJM Program under MMD PHE Dte. | 1694/W/MMD | 04/08/2023 | 759 | A G ENTERPRISE | 78.38 | 0 | 0 | 20
3151 | PASCHIM MEDINIPUR | Midnapore Division | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/17575 | New | Sinking of Tube Well ,Laying Rising Main,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 100 cum OHR (Intze type foundation) & Accommodate FHTC (490nos) Including 2 years of Operation & Maintenance under JJM with allied work for Tiorberya PWSS in Daspur- I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2822/MD | 07/08/2023 | 902 | ZENITH CONSTRUCTION | 222.1 | 0 | 0 | 20
3152 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Gobardhanpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17310 | Solarisation | Solarization of grid connected pumping installation at Gobardhanpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 779/W/MMD | 24/03/2023 | 180 | RSA ENTERPRISE | 6.26 | 0 | 0 | 30
3153 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Karkai PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17311 | Solarisation | Solarization of grid connected pumping installation at Karkai PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 690/W/MMD | 23/03/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 6.26 | 0 | 0 | 80
3154 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Khasbar, Zone-I & Zone-II PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17326 | Solarisation | Solarization of grid connected pumping installation at Khasbar, Zone-I & Zone-II PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 694/W/MMD | 23/03/2023 | 180 | A.K. INDUSTRIES | 12.52 | 0 | 0 | 80
3155 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18234 | New | Material Requisition To Resource Division | 59/MD | 09/01/2023 | 0 | Resource Division | 68.66 | 0 | 0 | 0
3156 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18234 | New | Material Requisition To Resource Division | 4057/MD | 12/10/2023 | 0 | Resource Division | 56.31 | 0 | 0 | 0
3157 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18234 | New | Material Requisition To Resource Division | 3326/MD | 25/11/2024 | 0 | Resource Division | 16.21 | 0 | 0 | 0
3158 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18234 | New | Quotation for new service connection at Jadavpur T/W-I water supply scheme. | 304/JMD | 14/08/2024 | 0 | WBSEDCL | 7.79 | 0 | 0 | 0
3159 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18234 | New | Quotation for new service connection at Jadavpur T/W-III water supply scheme. | 294/JMD | 09/08/2024 | 0 | WBSEDCL | 6.84 | 0 | 0 | 0
3160 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18234 | New | New Service connection charges. | 68/JMD | 13/03/2024 | 0 | WBSEDCL | 3.67 | 0 | 0 | 0
3161 | PASCHIM MEDINIPUR | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18234 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 550 cum OHR (Intze type with pile foundation) & Accommodate FHTC (4,219 Nos.) under JJM with allied work for Jadabpur PWSS in Chandrakona-I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 2951/MD | 17/08/2023 | 773 | GOBINDA MAITY | 1057.25 | 0 | 0 | 65
3162 | PASCHIM MEDINIPUR | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. , SM/18234 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | 1493/W/MMD | 22/06/2023 | 694 | SUJOY RANJAN BHOWMICK | 37.89 | 0 | 0 | 100
3163 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Sauri Kotbar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17300 | Solarisation | Solarization of grid connected pumping installation Sauri Kotbar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 676/W/MMD | 23/03/2023 | 180 | M/S B.M. ELECTRICAL | 6.26 | 0 | 0 | 70
3164 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/17558 | New | Material Requisition To Resource Division | 1530/MD | 12/05/2023 | 0 | Resource Division | 36.37 | 0 | 0 | 0
3165 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/17558 | New | Electrict quotation bill for TW-I of Dubrajpur pwss (Ref Consumar ID-204373188),Application No-2004849368,Application Type-New Connection,Name of ccc-Daspur ccc, block-Daspue-II | C082430177901 | 20/08/2024 | 0 | WBSEDCL | 15.54 | 0 | 0 | 0
3166 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/17558 | New | Electrict quotation bill for TW-II of Dubrajpur pwss (Ref Consumar ID-204362492),Application No-2004829564,Application Type-New Connection,Name of ccc-Daspur ccc, block-Daspur-II. | BP-2024-25-527 | 06/08/2024 | 0 | WBSEDCL | 4.42 | 0 | 0 | 0
3167 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/17558 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Dubrajpur and its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 1202/W/MMD | 25/04/2023 | 1075 | TAPAN KUMAR SARKAR | 23.77 | 0 | 0 | 45
3168 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/17558 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,304 Nos.) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Dubrajpur & its adjoining mouzas W/S scheme in Daspur- II Block including supply of all labour & materials within Midnapore Sub-Division under Midnapore Division, PHE Dte. | 3235/MD | 11/09/2023 | 1045 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 399.53 | 0 | 0 | 10
3169 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. , SM/17558 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
3170 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Kalshibhanga Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09419 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Kalshibhanga PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | 420/MD | 04/03/2022 | 21 | CHANDAN YADAV | 9.91 | 0 | 0 | 0
3171 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Kalshibhanga Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09419 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Chotto Kalsibhanga, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | 299/MD | 19/02/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.4 | 0 | 0 | 0
3172 | PASCHIM MEDINIPUR | Midnapore Division | Islampur Piped Water Supply Scheme. , SM/18782 | New | Material Requisition To Resource Division | 3984/MD | 06/10/2023 | 0 | Resource Division | 34.8 | 0 | 0 | 0
3173 | PASCHIM MEDINIPUR | Midnapore Mechanical | Islampur Piped Water Supply Scheme. , SM/18782 | New | Electrict quotation bill for TW-I of Islampur pwss (Ref Consumar ID-204444968),Application No-2004963184,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | C112429789179 | 25/11/2024 | 0 | WBSEDCL | 6.34 | 0 | 0 | 0
3174 | PASCHIM MEDINIPUR | Midnapore Mechanical | Islampur Piped Water Supply Scheme. , SM/18782 | New | Electrict quotation bill for TW-II of Islampur pwss (Ref Consumar ID-204444970),Application No-2004963217,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | C112429786723 | 25/11/2024 | 0 | WBSEDCL | 6.59 | 0 | 0 | 0
3175 | PASCHIM MEDINIPUR | Midnapore Mechanical | Islampur Piped Water Supply Scheme. , SM/18782 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ISLAMPUR AND IT'S ADJOINING MOUJAS under JJM Program under MMD PHE Dte. | 795/W/MMD | 24/03/2023 | 799 | CHAKRABORTY MINING & ENGINEERING | 21.58 | 0 | 0 | 38
3176 | PASCHIM MEDINIPUR | Midnapore Division | Islampur Piped Water Supply Scheme. , SM/18782 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 Cum OHR (Intze type with Pile) & Accommodate FHTC (2,431 Nos.) including Two years O&M under JJM with allied work for Islampur W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 3965/MD | 05/10/2023 | 540 | M/S. MALLIK CONSTRUCTION | 607.53 | 0 | 0 | 53
3177 | PASCHIM MEDINIPUR | Midnapore Division | TALBANDI AND ITS ADJOINING MOUJAS PWSS , SM/17614 | New | Material Requisition To Resource Division | 1518/MD | 12/05/2023 | 0 | Resource Division | 20.4 | 0 | 0 | 0
3178 | PASCHIM MEDINIPUR | Midnapore Division | TALBANDI AND ITS ADJOINING MOUJAS PWSS , SM/17614 | New | Sinking of Tube Well ,Laying of Rising Main ,Laying distribution pipe line, Pump House, 100 cum OHR( Intze type with solid raft ) & Accommodate FHTC (712 Nos) including 2 years operation & maintenance under JJM with allied work for Talbandi & its adjoining mouzas W/S scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-division under Midnapore Division, PHE Dte. | 2148/MD | 08/06/2023 | 180 | M/S. RAJ KUMAR KHAN | 239.9 | 0 | 0 | 45
3179 | PASCHIM MEDINIPUR | Midnapore Mechanical | TALBANDI AND ITS ADJOINING MOUJAS PWSS , SM/17614 | New | Electrict quotation bill for TW-I of Talbandi pwss (Ref Consumar ID-204314575),Application No-2004747841,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra | BP-2024-25-234 | 04/06/2024 | 0 | WBSEDCL | 3.85 | 0 | 0 | 0
3180 | PASCHIM MEDINIPUR | Midnapore Mechanical | TALBANDI AND ITS ADJOINING MOUJAS PWSS , SM/17614 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TALBANDI AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 952/W/MMD | 28/03/2023 | 180 | MASSK ENGINEERING WORKS | 21.58 | 0 | 0 | 0
3181 | PASCHIM MEDINIPUR | Midnapore Division | KEDAR AND ITS ADJOINING MOUJAS PWSS , SM/17621 | New | Material Requisition To Resource Division | 1286/MD | 28/04/2023 | 0 | Resource Division | 45.86 | 0 | 0 | 0
3182 | PASCHIM MEDINIPUR | Midnapore Mechanical | KEDAR AND ITS ADJOINING MOUJAS PWSS , SM/17621 | New | ADDITIONAL QUOTATION FOR SHIFTING OF 11 KV LINE & DTR AT TW NO-I OF KEDAR PWSS.(APPLICATION NO-2004886654), REFERENCE ID-860319778, APPLICATION ID-100000125268, APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC- KHAKURDA CCC, NAME OF BLOCK-DANTAN-II. |  | 18/12/2024 | 0 | WBSEDCL | 2.05 | 0 | 0 | 0
3183 | PASCHIM MEDINIPUR | Midnapore Mechanical | KEDAR AND ITS ADJOINING MOUJAS PWSS , SM/17621 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF KEDAR PWSS. REF CONSUMER ID-204393521, APPLICATION NO-2004889559, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102401978777 | 03/10/2024 | 0 | WBSEDCL | 6.65 | 0 | 0 | 0
3184 | PASCHIM MEDINIPUR | Midnapore Mechanical | KEDAR AND ITS ADJOINING MOUJAS PWSS , SM/17621 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF KEDAR PWSS. REF CONSUMER ID-204391651, APPLICATION NO-2004886654, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102401977236 | 03/10/2024 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
3185 | PASCHIM MEDINIPUR | Central Drilling | KEDAR AND ITS ADJOINING MOUJAS PWSS , SM/17621 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3186 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19048 | New | Material Requisition To Resource Division | 187/MD | 16/01/2023 | 0 | Resource Division | 35.98 | 0 | 0 | 0
3187 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19048 | New | Material Requisition To Resource Division | 3440/MD | 25/11/2024 | 0 | Resource Division | 18.75 | 0 | 0 | 0
3188 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19048 | New | THE QUOTATION MONEY FOR GOPALI WATER SUPPLY SCHEME, ZONE-II, T W NO I, [ GHOLGHARIA FREE PRIMARY SCHOOL ] , JJM WORKS, SCHEME CODE SM/19048, APPLICATION NO 2004726901, REFERENCE ID 204303571, NIMPURA CCC, WBSEDCL | C072445369106 | 30/07/2024 | 0 | WBSEDCL | 2.98 | 0 | 0 | 0
3189 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19048 | New | THE QUOTATION MONEY FOR GOPALI WATER SUPPLY SCHEME, ZONE-II, T W NO I, [ GHOLGHARIA ] , JJM WORKS, SCHEME CODE SM/19048, APPLICATION NO 2004726863, REFERENCE ID 204303571, NIMPURA CCC, WBSEDCL | C072445370570 | 30/07/2024 | 0 | WBSEDCL | 3.36 | 0 | 0 | 0
3190 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19048 | New | QUOTATION MONEY FOR GOPALI WATER SUPPLY SCHEME, ZONE- I ,T W NO I [ RANGAMATIA ] , JJM WORKS, SCHEME CODE SM/19048, APPLICATION NO 20047411952, REFERENCE ID 204310973, NIMPURA CCC, WBSEDCL | BP-2024-25-424 | 15/07/2024 | 0 | WBSEDCL | 5.89 | 0 | 0 | 0
3191 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19048 | New | QUOTATION MONEY FOR GOPALI WATER SUPPLY SCHEME, ZONE- I, T W NO II, [ GOPALI ] JJM WORKS, SCHEME CODE SM/19048, APPLICATION NO 2004741941, REFERENCE ID 204310971, NIMPURA CCC, WBSEDCL | BP-2024-25-423 | 15/07/2024 | 0 | WBSEDCL | 4.31 | 0 | 0 | 0
3192 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19048 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Gopali (Zone-I and II) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 3092/W/MMD | 29/11/2023 | 540 | M.S.ENTERPRISE | 47.53 | 0 | 0 | 85
3193 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19048 | New | Sinking of Tube Wells, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Two nos. 150 cum & 450 cum OHRs & Accommodate FHTC (3,044 Nos.) including Two years O&M under JJM with allied work for Gopali (Zone-I,II) & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5480/MD | 13/12/2023 | 720 | SUJOY KUMAR MANDAL | 831.24 | 0 | 0 | 66
3194 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/19048 | New | Construction of boundary wall of Kharagpur Sub-Divisional Store cum Stack yard and Guard Room at Gopali, Mouza ¿ Rangametya, vide J.L. No. - 255, Plot No. - 75/570 under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | 53/MD | 07/01/2025 | 75 | GOBINDA MAITY | 64.56 | 0 | 0 | 0
3195 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Ragpur PWSS , SM/06927 | Retrofitting | Material Requisition To Resource Division | 3411/MD | 25/11/2024 | 0 | Resource Division | 12.39 | 0 | 0 | 0
3196 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Ragpur PWSS , SM/06927 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Ragpur W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1449/MD | 26/11/2020 | 1496 | GOBINDA MAITY | 94.99 | 27.37 | 28.81 | 100
3197 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. , SM/18622 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas.under JJM Program under MMD PHE Dte. | 1722/W/MMD | 09/08/2023 | 180 | DEY ENTERPRISE | 25.26 | 0 | 0 | 0
3198 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. , SM/18622 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas.under JJM Program under MMD PHE Dte. (Part-II) | 1732/W/MMD | 09/08/2023 | 180 | M/S. JIT ENTERPRISE | 22.78 | 0 | 0 | 0
3199 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. , SM/18622 | New | Material Requisition To Resource Division | 112/MD | 10/01/2023 | 0 | Resource Division | 65.54 | 0 | 0 | 0
3200 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. , SM/18622 | New | Laying Rising main pipe line for "Benai Zone-II" PWSS under Daspur-II Block within Ghatal Sub-Division under Midnapore Division, P.H.E.Dte | 1493/AE/GSD | 24/09/2024 | 30 | M/S. A.R. ENTERPRISE | 3.17 | 0 | 0 | 0
3201 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. , SM/18622 | New | Material Requisition To Resource Division | 3340/MD | 25/11/2024 | 0 | Resource Division | 25.95 | 0 | 0 | 0
3202 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. , SM/18622 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR & 250 Cum OHR (Intze type with pile foundation) & Accommodate FHTC (4,213 Nos.) under JJM with allied work for Benai (Zone- I & Zone-II) & its adjoining mouzas W/S scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 3231/MD | 11/09/2023 | 900 | M/S. A.R. ENTERPRISE. | 983.46 | 0 | 0 | 15
3203 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. , SM/18622 | New | Laying rising main pipeline for Benai (Zone-I) PWSS under Daspur-II block within Ghatal sub-Division under Midnapore Division, PHE Dte. | 3575/MD | 06/12/2024 | 405 | M/S. A.R. ENTERPRISE | 5.52 | 0 | 0 | 0
3204 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. , SM/18622 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
3205 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. , SM/18622 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
3206 | PASCHIM MEDINIPUR | Midnapore Division | BIRSINGPUR AND ADJOINING MOUJAS PWSS , SM/14994 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
3207 | PASCHIM MEDINIPUR | Midnapore Division | BIRSINGPUR AND ADJOINING MOUJAS PWSS , SM/14994 | New | Material Requisition To Resource Division | 1217/MD | 27/04/2023 | 0 | Resource Division | 28.24 | 0 | 0 | 0
3208 | PASCHIM MEDINIPUR | Central Drilling | BIRSINGPUR AND ADJOINING MOUJAS PWSS , SM/14994 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3209 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Bhikni Nischintapur Piped Water Supply Scheme. , SM/06911 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhikni Nischintapur W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | SAI TUBE CO. | 20 | 0 | 0 | 0
3210 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Bhikni Nischintapur Piped Water Supply Scheme. , SM/06911 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Jamna W/S Scheme. EE/MD/595/20-21 | BP-2021-22-140 | 10/03/2022 | 0 | GOBINDA MAITY | 12.45 | 0 | 0 | 0
3211 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Bhikni Nischintapur Piped Water Supply Scheme. , SM/06911 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhikni Nischintapur W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1458/MD | 26/11/2020 | 1643 | SAI TUBE CO. | 91.84 | 75.6 | 82.32 | 100
3212 | PASCHIM MEDINIPUR | Midnapore Division | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS , SM/18525 | New | Material Requisition To Resource Division | 65/MD | 09/01/2023 | 0 | Resource Division | 17.57 | 0 | 0 | 0
3213 | PASCHIM MEDINIPUR | Midnapore Division | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS , SM/18525 | New | Material Requisition To Resource Division | 3380/MD | 25/11/2024 | 0 | Resource Division | 12.06 | 0 | 0 | 0
3214 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS , SM/18525 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of KHIRISHMUL PWSS. REF CONSUMER ID-204269069, APPLICATION NO-2004675308 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-75 | 24/04/2024 | 0 | WBSEDCL | 3.36 | 0 | 0 | 0
3215 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS , SM/18525 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of KHIRISHMUL PWSS. REF CONSUMER ID-204269078, APPLICATION NO-2004675326, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-74 | 24/04/2024 | 0 | WBSEDCL | 6.61 | 0 | 0 | 0
3216 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS , SM/18525 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHIRISH MUL AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | 1682/W/MMD | 04/08/2023 | 678 | PADMA ENGINEERING CO. | 23 | 0 | 0 | 30
3217 | PASCHIM MEDINIPUR | Midnapore Division | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS , SM/18525 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,958 nos.) under JJM with allied work for Khirishmul PWSS in Keshpur Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 3148/MD | 29/08/2023 | 870 | BANERJEE CONSTRUCTION | 1014.08 | 0 | 0 | 35
3218 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS , SM/18525 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0 | 0 | 50
3219 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS , SM/18525 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | 842/MMSD-I | 11/06/2025 | 243 | M/S BIKASH DE | 3.66 | 0 | 0 | 0
3220 | PASCHIM MEDINIPUR | Midnapore Division | RAIPUR AND ITS ADJOINING MOUJAS PWSS , SM/13170 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
3221 | PASCHIM MEDINIPUR | Midnapore Division | RAIPUR AND ITS ADJOINING MOUJAS PWSS , SM/13170 | New | Material Requisition To Resource Division | 1527/MD | 12/05/2023 | 0 | Resource Division | 26.82 | 0 | 0 | 0
3222 | PASCHIM MEDINIPUR | Central Drilling | RAIPUR AND ITS ADJOINING MOUJAS PWSS , SM/13170 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3223 | PASCHIM MEDINIPUR | Midnapore Division | RAIPUR AND ITS ADJOINING MOUJAS PWSS , SM/13170 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7,515 Nos.) including 2 years operation & maintenance For BARAGOPAL, DURIA, GAHIRA & RAIPUR Pipe Water Supply Scheme within NARAYANGARH Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 3048/MD | 23/08/2023 | 975 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 2197.07 | 0 | 0 | 33
3224 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18506 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Daspur, Block - Daspur-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | 930/MD | 14/06/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.07 | 0 | 0 | 100
3225 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18506 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Daspur, Block - Daspur-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | 914/MD | 10/06/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.88 | 0 | 0 | 100
3226 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18506 | Augmentation | Material Requisition To Resource Division | 3339/MD | 25/11/2024 | 0 | Resource Division | 117.64 | 0 | 0 | 0
3227 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18506 | Augmentation | QUOTATION MONEY FOR DASPUR AUGMENTATION, DIHIBALIHARPUR WATER SUPPLY SCHEME, T W NO IV , JJM WORKS, SCHEME CODE SM/18506, APPLICATION NO 2004809572, REFERENCE ID 204352799, DASPUR CCC, WBSEDCL | BP-2024-25-488 | 30/07/2024 | 0 | WBSEDCL | 6.23 | 0 | 0 | 0
3228 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18506 | Augmentation | QUOTATION MONEY FOR DASPUR WATER SUPPLY SCHEME, T W NO 3, [ AUGMENTATION ] , JJM WORKS, BLOCK- DASPUR-I, SCHEME CODE SM/18506, APPLICATION NO 2004849405, REFERENCE ID 204373191, DASPUR CCC, WBSEDCL | C082441593739 | 29/08/2024 | 0 | WBSEDCL | 5.2 | 0 | 0 | 0
3229 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18506 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 1691/W/MMD | 04/08/2023 | 702 | P.K.ENGINEERING | 37.87 | 0 | 0 | 100
3230 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18506 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (5,245 Nos.) under JJM with allied work for Augmentation of Daspur (Zone-I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 3145/MD | 29/08/2023 | 761 | GOBINDA MAITY | 1112.86 | 0 | 0 | 20
3231 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/18506 | Augmentation | Laying of rising main pipeline for Augmentation of Daspur (Zone-I & II) & its adj. mouzas Pipe W/S Scheme within block - Daspur-I, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 54/MD | 07/01/2025 | 60 | GOBINDA MAITY | 20.06 | 0 | 0 | 80
3232 | PASCHIM MEDINIPUR | Midnapore Mechanical | Khirinda Piped Water Supply Scheme. , SM/07393 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Khirinda Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | 572/W/MMD | 20/03/2023 | 180 | DEY ENTERPRISE | 25.26 | 0 | 0 | 0
3233 | PASCHIM MEDINIPUR | Central Drilling | Khirinda Piped Water Supply Scheme. , SM/07393 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KHIRINDA W/S SCHEME (TW-I), PINGLA BLOCK UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | 1720/CDD | 29/12/2022 | 30 | UNIVERSAL ENTERPRISES | 5.62 | 0 | 0 | 0
3234 | PASCHIM MEDINIPUR | Central Drilling | Khirinda Piped Water Supply Scheme. , SM/07393 | New | Hiring of Diesel driven motor cab(BS-III & Above) having contract carriage permit along with driver for the office of the Executive Engineer, CDD, PHE Dte. Car No. WB-04H-5846. | 33/S&WSD | 23/03/2023 | 30 | ASHUTOSH DAS & CO | 0.14 | 0 | 0 | 100
3235 | PASCHIM MEDINIPUR | Central Drilling | Khirinda Piped Water Supply Scheme. , SM/07393 | New | Water sample testing and other works for construction of tube well (300mm x 200mm x 200 mtrs depth) by utilising departmental machineries for khirinda w/s scheme (TW-II), Pingla block under Paschim Midnapore Distrrict, CDD, PHE Dte. | 1723/CDD | 29/12/2022 | 30 | SANKAR PRASAD DUTTA & CO. | 10.21 | 0 | 0 | 0
3236 | PASCHIM MEDINIPUR | Central Drilling | Khirinda Piped Water Supply Scheme. , SM/07393 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KHIRINDA W/S SCHEME (TW-II), PINGLA BLOCK, UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | 1722/CDD | 29/12/2022 | 30 | SANKAR PRASAD DUTTA & CO. | 5.6 | 0 | 0 | 0
3237 | PASCHIM MEDINIPUR | Central Drilling | Khirinda Piped Water Supply Scheme. , SM/07393 | New | WATER SAMPLE TESTING AND OTHER WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KHIRINDA W/S SCHEME (TW-I), PINGLA BLOCK UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | 1721/CDD | 29/12/2022 | 30 | UNIVERSAL ENTERPRISES | 10.23 | 0 | 0 | 0
3238 | PASCHIM MEDINIPUR | Midnapore Mechanical | Khirinda Piped Water Supply Scheme. , SM/07393 | New | Electric Quotation for TW-II of Khirinda W/S Scheme (Consumer ID 203971015) | BP-2023-24-33 | 04/05/2023 | 0 | WBSEDCL | 2.69 | 0 | 0 | 0
3239 | PASCHIM MEDINIPUR | Midnapore Mechanical | Khirinda Piped Water Supply Scheme. , SM/07393 | New | Electric quotation for Tw no-I of Khirinda w/s scheme ( Consumer ID-203972928) | BP-2023-24-34 | 04/05/2023 | 0 | WBSEDCL | 2.63 | 0 | 0 | 0
3240 | PASCHIM MEDINIPUR | Midnapore Mechanical | Khirinda Piped Water Supply Scheme. , SM/07393 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
3241 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate balance FHTC in 5 Nos. PWSS within Ghatal Sub-Division , SM/07876 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in RANAPUR PWSS in Daspur-I Block in the District of Paschim Midnapore. | 263/MD | 12/02/2021 | 30 | KISHORE GHOSH | 9.49 | 0 | 0 | 0
3242 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate balance FHTC in 5 Nos. PWSS within Ghatal Sub-Division , SM/07876 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Harekrishnapur W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1430/MD | 26/11/2020 | 180 | DIPAK KUMAR DOLAI | 94.96 | 0 | 0 | 0
3243 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Narayanbar Piped Water Supply Scheme. , SM/06896 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Narayanbar W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1457/MD | 26/11/2020 | 1859 | BANERJEE CONSTRUCTION | 93.13 | 22.32 | 23.97 | 90
3244 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | FHTC Data entry | 8443119 | 23/08/2021 | 0 | SIDDHESWAR BAG | 0.05 | 0 | 0 | 0
3245 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | Electric bill for the office of the Executive Engineer Mid. Mech. Divn. PHE Dte. | 844382 | 25/11/2021 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.11 | 0 | 0 | 0
3246 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | DATA ENTRY FOR FHTC | 844387 | 13/09/2021 | 0 | MANABENDRA DAS | 0.08 | 0 | 0 | 0
3247 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | FHTC Data entry | 8443119 | 23/08/2021 | 0 | PAPPU SHAW | 0.04 | 0 | 0 | 0
3248 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | DATA ENTRY FOR FHTC | 844387 | 13/09/2021 | 0 | KOUSHIK PAL | 0.01 | 0 | 0 | 0
3249 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | DATA ENTRY FOR FHTC | 844387 | 13/09/2021 | 0 | BIPLAB SHIT | 0.01 | 0 | 0 | 0
3250 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | Electric bill for the office of the Executive Engineer Mid. Mech. Divn. PHE Dte. | 844383 | 25/11/2021 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.11 | 0 | 0 | 0
3251 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | FHTC Data entry | 8443119 | 23/08/2021 | 0 | SUBRATA CHAKRABORTY | 0.03 | 0 | 0 | 0
3252 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | Electric bill for the office of the Executive Engineer Mid. Mech. Divn. PHE Dte. | 844381 | 25/11/2021 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.11 | 0 | 0 | 0
3253 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | Milan Jana | 844387 | 19/09/2021 | 0 | MILAN JANA | 0.01 | 0 | 0 | 0
3254 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | DATA ENTRY FOR FHTC | 844387 | 13/09/2021 | 0 | ANKITA HAZRA | 0.01 | 0 | 0 | 0
3255 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | DATA ENTRY FOR FHTC | 844387 | 13/09/2021 | 0 | SANJOY DAS | 0.02 | 0 | 0 | 0
3256 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | FHTC imis data entry. | 8443146 | 24/03/2022 | 0 | SOVANDEB MANNA | 0.09 | 0 | 0 | 0
3257 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | FHTC imis data entry. | 8443146 | 24/03/2022 | 0 | GANESH CH NANDY | 0.14 | 0 | 0 | 0
3258 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | FHTC imis data entry. | 8443146 | 24/03/2022 | 0 | RAJIB DEY | 0.15 | 0 | 0 | 0
3259 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-I) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1438/MD | 26/11/2020 | 180 | M/S. EL-CON | 91.85 | 24.91 | 27.12 | 100
3260 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | Damage of existing pipeline lies under the existing carriageway of the road at Chuasol (Zone ¿V) & Boylasole ,Siarboni (zone) under Dherua and its adjoining mouzas water supply scheme within Midnapore Sadar Sub-Division under Midnapore Division PHE Dte. | 785/AE/MSSD | 06/01/2023 | 30 | SANJIT SINHA | 1.78 | 0 | 0 | 0
3261 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | Round the Clock Guarding Arrangements to protect the Govt. properties / materials etc. at The Head work site Midnapore Divison , PHE Dte. | 8443125 | 29/03/2023 | 0 | M/S. OXFORD SECURITY SERVICE | 3.28 | 0 | 0 | 0
3262 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre ,Health Care Institution etc. under Midnapore Division PHE Dte.(SL No-02) | 13/AE/MSSD | 06/01/2021 | 3 | PULLOCK KUMAR GHOSH | 1.48 | 1.47 | 100 | 0
3263 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | Laying Distribution system connected with newly sunk tube well from Debra to Chuasole pipe line at Dherua Zone - IV piped water supply scheme with in Midnapore Sadar Block( Within MSSD) under Midnapore Division PHE Dte.(SL No-03) | 844357 | 24/10/2024 | 0 | SANJIT SINHA | 1.48 | 0 | 0 | 0
3264 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | Laying Distribution system connected with newly sunk tube well from Chaipur Sitala Mandir to Kundalboni pipe line at Dherua Zone -I piped water supply scheme with in Midnapore Sadar Block ( Within MSSD) under Midnapore Division PHE Dte.(SL No-01) | 844334 | 09/05/2024 | 0 | SANJIT SINHA | 2.7 | 0 | 0 | 0
3265 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS , SM/06904 | Retrofitting | Laying Distribution system connected with newly sunk tube well from Mohulboni to Chaipur Sitala Mandir pipe line at Dherua Zone -I piped water supply scheme with in Midnapore Sadar Block( Within MSSD) under Midnapore Division PHE Dte.(SL No-02) | 844376 | 24/06/2024 | 0 | SANJIT SINHA | 3.47 | 0 | 0 | 0
3266 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | FHTC Data entry | 8443119 | 23/08/2021 | 0 | RINTU SAMANTA | 0.04 | 0 | 0 | 0
3267 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | DATA ENTRY FOR FHTC | 844388 | 13/09/2021 | 0 | NABOGOPAL ADHIKARI | 0.05 | 0 | 0 | 0
3268 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | FHTC Data entry | 8443119 | 23/08/2021 | 0 | MANABENDRA DAS | 0.03 | 0 | 0 | 0
3269 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | DATA ENTRY FOR FHTC | 844388 | 13/09/2021 | 0 | ANIRBAN CHAKRABORTY | 0.02 | 0 | 0 | 0
3270 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | FHTC Data entry | 8443119 | 23/08/2021 | 0 | NABOGOPAL ADHIKARI | 0.04 | 0 | 0 | 0
3271 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | DATA ENTRY FOR FHTC | 844388 | 13/09/2021 | 0 | RINTU SAMANTA | 0.08 | 0 | 0 | 0
3272 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | DATA ENTRY FOR FHTC | 844388 | 13/09/2021 | 0 | SANDIP MANNA | 0.05 | 0 | 0 | 0
3273 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-II) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1439/MD | 26/11/2020 | 180 | M/S. CARE | 91.69 | 62.56 | 68.23 | 100
3274 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-III) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 844335 | 19/04/2023 | 0 | M/S. EL-CON | 15 | 0 | 0 | 0
3275 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-III) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 8443137 | 28/08/2023 | 0 | M/S. EL-CON | 2.48 | 0 | 0 | 0
3276 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-II) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 844380 | 15/05/2023 | 0 | M/S. EL-CON | 7.51 | 0 | 0 | 0
3277 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | Supply and delivery of Sluice Valve for Dherua W/S Scheme (Zone-II & III) of Midnapore Sadar Block within Midnapore Divison PHE Dte.(SL No-02) | 443/AE/MSSD | 12/08/2021 | 15 | DIPAK KUMAR BAKLY | 2.33 | 2.33 | 100 | 0
3278 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS , SM/06910 | Retrofitting | Hiring of vehicle for the SE, WC PHE Dte. [01/11/2023 to 31/03/2024] | 844332 | 14/05/2024 | 0 | BISWADIP SIKDAR | 0.99 | 0 | 0 | 0
3279 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. , SM/06894 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandpur W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1443/MD | 26/11/2020 | 180 | MASUM ALI KHAN | 76.1 | 66.12 | 86.88 | 0
3280 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. , SM/06894 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandpur W/S Scheme District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  | 15/12/2020 | 0 | MASUM ALI KHAN | 30 | 0 | 0 | 0
3281 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. , SM/06894 | Retrofitting | FHTC DATA ENTRY | 8443212 | 27/09/2021 | 0 | SIDDHESWAR BAG | 0.17 | 0 | 0 | 0
3282 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. , SM/06894 | Retrofitting | FHTC DATA ENTRY | 8443212 | 27/09/2021 | 0 | MANABENDRA DAS | 0.14 | 0 | 0 | 0
3283 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. , SM/06894 | Retrofitting | FHTC DATA ENTRY | 8443212 | 27/09/2021 | 0 | RINTU SAMANTA | 0.12 | 0 | 0 | 0
3284 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. , SM/06894 | Retrofitting | FHTC data entry. | 844334 | 08/12/2021 | 0 | SIDDHESWAR BAG | 0.14 | 0 | 0 | 0
3285 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. , SM/06894 | Retrofitting | FHTC data entry. | 844334 | 08/12/2021 | 0 | MANABENDRA DAS | 0.14 | 0 | 0 | 0
3286 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. , SM/06894 | Retrofitting | FHTC Data Entry. | 844361 | 18/01/2022 | 0 | GANESH CH NANDY | 0.2 | 0 | 0 | 0
3287 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. , SM/06894 | Retrofitting | FHTC data Entry. | 844361 | 18/01/2022 | 0 | SUBRATA CHAKRABORTY | 0.12 | 0 | 0 | 0
3288 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. , SM/06894 | Retrofitting | Engagement of 1(one) no Contractual Clerical staff cum office assistant for different official purpose for office of the Assistant Engineer, Ghatal Sub-Division, P.H.E. dte. (1st year) | 844356 | 09/09/2022 | 0 | DEVJYOTI BERA | 0.18 | 0 | 0 | 0
3289 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. , SM/06894 | Retrofitting | Engagement of 1 (One) No. Orderly Peon,Contractrual Group-D, through Agency for different official purpose for office of the office of the Assistant Engineer, Ghatal Sub-Division, P.H.E. Dte. (For 12 months) | 8443171 | 26/09/2022 | 0 | SUBHASIS DOLAI | 0.16 | 0 | 0 | 0
3290 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Dhamsai Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09418 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dhamsai PWSS, Block - Keshpur in the district of Paschim Medinipur. | 2176/MD | 17/12/2021 | 30 | PRADIP KUMAR SAHA | 20.61 | 0 | 0 | 0
3291 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting of Ground Water Based Dhamsai Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. , SM/09418 | Retrofitting | Laying of distribution system of uPVC pipeline due to damage portion road along the pipeline and including shifting under Dhamsai W/S Scheme in Keshpur Block under Midnapore Division, PHE Dte. | BP-2021-22-356 | 08/02/2022 | 0 | M/S. D.K.H.CONSTRUCTION | 6 | 0 | 0 | 0
3292 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Supply of CIDF valves and Jeffy Coupler for Augumentation of Debra and its adjoining Mouzas W/S Scheme under Debra Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte.(Sl.No. -01) | 256/AE/KSD | 20/05/2022 | 15 | GOBINDA MAITY | 4.64 | 0 | 0 | 0
3293 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Debra (Block- Debra) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1616/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.48 | 0 | 0 | 0
3294 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Debra (Block- Debra) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1617/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.16 | 0 | 0 | 0
3295 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra. District - Paschim Medinipur. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 17.82 | 0 | 0 | 0
3296 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of ground based piped water Supply scheme for DEBRA to accommodate FHTC under JJM Program under MMD PHE Dte. | 94/W/MMD | 17/01/2023 | 180 | M/S. S.R. ENTERPRISE | 25.23 | 0 | 0 | 80
3297 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Construction of 1 No. 5.40 Mtr. X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Head Works Site, 1 No. 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room without W.C. & Bath for 2nd Tube Well site and Laying of rising main & interconnection including supply of CIDF valves for Augmentation of Debra & its adjoining mouzas W/S Scheme of Debra Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | 1963/MD | 20/09/2022 | 60 | DEBASISH DOGRA | 15.62 | 0 | 0 | 100
3298 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Material Requisition To Resource Division | 2432/MD | 29/11/2022 | 0 | Resource Division | 60.26 | 0 | 0 | 0
3299 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Material Requisition To Resource Division | 2277/MD | 31/12/2021 | 0 | Resource Division | 18.73 | 0 | 0 | 0
3300 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Supply of different material for Debra W/S Scheme. | BP-2022-23-359 | 01/02/2023 | 0 | GOBINDA MAITY | 4.64 | 0 | 0 | 0
3301 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | wbsedcl Quotation bill of Debra water supply scheme at pump house no-III |  | 23/06/2023 | 0 | WBSEDCL | 2.87 | 0 | 0 | 0
3302 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Electric quotation for Debra Water Supply Scheme T/W-(Ref. ID - 204024559) | BP-2023-24-287 | 31/08/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 2.87 | 0 | 0 | 0
3303 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Laying Distribution pipe line under JJM with allied work for Trilochanpur PWSS in Debra block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | 1902/MD | 20/06/2024 | 90 | ASHIM KUMAR DEY | 308.72 | 0 | 0 | 0
3304 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of ground based piped water Supply scheme for DEBRA to accommodate FHTC under JJM Program under MMD PHE Dte. (Part-II) | 873/W/MMD | 27/03/2023 | 180 | MASSK ENGINEERING WORKS | 8.35 | 0 | 0 | 0
3305 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. , SM/09430 | Augmentation | Construction of boundary wall & allied works for Head Work site, 2nd Tube well site & 3rd Tube well site and Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room including W.C. for 3rd Tube well site for Augmentation of Debra PWSS within Debra Block under Midnapore Division, PHE Dte. | 312/MD | 29/01/2025 | 240 | R. CONSTRUCTION | 24.48 | 0 | 0 | 60
3306 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Madpur PWSS , SM/08694 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Madpur PWSS, Block: - Kharagpur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1465/MD | 07/09/2021 | 1393 | DULAL CHANDRA DAS | 96.74 | 0 | 0 | 0
3307 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Purulda PWSS, Block - Dantan-II in the district of Paschim Medinipur. , SM/08697 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Purulda PWSS, Block: - Dantan-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1466/MD | 07/09/2021 | 1474 | BANERJEE CONSTRUCTION | 90.08 | 0 | 0 | 15
3308 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09679 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Mirjapur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 154/W/MMD | 31/01/2022 | 120 | DIPALI CONSTRUCTION | 6.49 | 0 | 0 | 0
3309 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09679 | New | Quotation for service connection charges of WBSEDCL at Lakshmichak,Andulia T/W-I | 2003855188/Quot/03 | 10/03/2022 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
3310 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09679 | New | Purchasing of materials for the Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas. Block - Sabang. District - Paschim Medinipur. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.31 | 0 | 0 | 0
3311 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09679 | New | For payment of liabilities. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.31 | 0 | 0 | 0
3312 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09679 | New | Electric quotation Sabang CCC at Mirjapur Mini piped Water supply scheme under MMD PHE Dte | BP-2022-23-59 | 23/11/2022 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
3313 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09679 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Mirjapur water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2518/W/MMD | 30/11/2021 | 4 | OSMAN SEKH | 4.47 | 0 | 0 | 60
3314 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09679 | New | Material Requisition To Resource Division | 2119/MD | 13/12/2021 | 0 | Resource Division | 0.31 | 0 | 0 | 0
3315 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09679 | New | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. |  | 01/02/2023 | 0 | BADAL CHANDRA BERA | 0.07 | 0 | 0 | 0
3316 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09679 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Mirjapur, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 421/MD | 04/03/2022 | 150 | A R ENTERPRISE | 17.21 | 0 | 0 | 90
3317 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09679 | New | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. |  | 31/01/2023 | 0 | BADAL CHANDRA BERA | 0.63 | 0 | 0 | 0
3318 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09679 | New | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 0 | 100
3319 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Haripura mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09680 | New | Service connection charge of WBSEDCL at Haripura, Bonai | 2003774906/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
3320 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Haripura mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09680 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Haripura water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2522/W/MMD | 30/11/2021 | 4 | P.K.ENGINEERING | 4.47 | 0 | 0 | 100
3321 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Haripura mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09680 | New | Quotation for service connection charges of WBSEDCL at Lakshmichak,Andulia T/W-II | 2003855176/Quot/03 | 10/03/2022 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
3322 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Haripura mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09680 | New | For payment of liabilities. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.04 | 0 | 0 | 0
3323 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Haripura mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09680 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | BP-2021-22-505 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 4.1 | 0 | 0 | 0
3324 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Haripura mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09680 | New | Purchasing of materials for the Ground Based Mini Piped Water Supply Scheme for Haripura mouzas. Block - Sabang. District - Paschim Medinipur. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.04 | 0 | 0 | 0
3325 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Haripura mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09680 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Haripura, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 124/W/MMD | 24/01/2022 | 120 | M/S B.M. ELECTRICAL | 6.54 | 0 | 0 | 0
3326 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Haripura mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09680 | New | Material Requisition To Resource Division | 2113/MD | 13/12/2021 | 0 | Resource Division | 1.04 | 0 | 0 | 0
3327 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Haripura mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09680 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza ¿ Haripura, Block ¿ Sabang, District ¿ Paschim Medinipur under Midnapore Division, PHE Dte. | 286/MD | 15/02/2022 | 150 | SAI TUBE CO. | 34.13 | 0 | 0 | 100
3328 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. , SM/09682 | New | Service connection charge of WBSEDCL at Fatechak, Sabang | 2003774921/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
3329 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. , SM/09682 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Fate Chak water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2520/W/MMD | 30/11/2021 | 4 | P.K.ENGINEERING | 4.47 | 0 | 0 | 100
3330 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. , SM/09682 | New | For purchasing of liabilities. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.67 | 0 | 0 | 0
3331 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. , SM/09682 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | BP-2021-22-505 | 22/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.87 | 0 | 0 | 0
3332 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. , SM/09682 | New | Purchasing of materials for the Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.67 | 0 | 0 | 0
3333 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. , SM/09682 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Fate Chak, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 123/W/MMD | 24/01/2022 | 120 | SOUMEN ELECTRIC | 6.55 | 0 | 0 | 0
3334 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. , SM/09682 | New | Material Requisition To Resource Division | 2117/MD | 13/12/2021 | 0 | Resource Division | 0.67 | 0 | 0 | 0
3335 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. , SM/09682 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Fate Chak, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 182/MD | 01/02/2022 | 1065 | MASUM ALI KHAN | 21.15 | 0 | 0 | 100
3336 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09684 | New | Service connection charge of WBSEDCL at Khunkhunia, Sabang | 2003774931/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0 | 0 | 0
3337 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09684 | New | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for Khunkhunya & its adjoining mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | 1275/MD | 05/08/2021 | 10 | GOBINDA MAITY | 1.67 | 0 | 0 | 0
3338 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09684 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Khunkhunya water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | 2534/W/MMD | 30/11/2021 | 4 | MENAKA ENTERPRISE | 4.47 | 0 | 0 | 100
3339 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09684 | New | For payment of liabilities. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.27 | 0 | 0 | 0
3340 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09684 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | BP-2021-22-505 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.66 | 0 | 0 | 0
3341 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09684 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Khunkhunya, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 125/W/MMD | 24/01/2022 | 120 | M.S.ENTERPRISE | 6.52 | 0 | 0 | 0
3342 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09684 | New | Material Requisition To Resource Division | 2114/MD | 13/12/2021 | 0 | Resource Division | 1.27 | 0 | 0 | 0
3343 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09684 | New | LOAD ENHANCEMENT OF KHUNKHUNYA MINI WATER SUPPLY SCHEME , SCHEME CODE SM/09684, COSUMER ID 20350372, CHANDKURI CCC [ ENTERED MB NO 3580, PAGE 13-14 ] | BP-2023-24-128 | 13/07/2023 | 0 | WBSEDCL | 0.37 | 0 | 0 | 0
3344 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. , SM/09684 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza ¿ Khunkhunya, Block ¿ Sabang, District ¿ Paschim Medinipur under Midnapore Division, PHE Dte. | 287/MD | 15/02/2022 | 150 | SAI TUBE CO. | 42.01 | 0 | 0 | 100
3345 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for Uttar Eral mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | 1332/MD | 17/08/2021 | 10 | GOBINDA MAITY | 2.17 | 0 | 0 | 0
3346 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Uttar Eral water supply scheme, Tube Well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte.. | 73/W/MMD | 17/01/2022 | 5 | SUJOY RANJAN BHOWMICK | 4.48 | 0 | 0 | 100
3347 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Uttar Eral water supply scheme, Tube Well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte.. | 74/W/MMD | 17/01/2022 | 5 | SUJOY RANJAN BHOWMICK | 4.48 | 0 | 0 | 100
3348 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | BP-2021-22-505 | 22/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 7.98 | 0 | 0 | 0
3349 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Electric quotation Chandkuri CCC? at L ttar Eral W/S Scheme i¿ui-721144 |  | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.13 | 0 | 0 | 0
3350 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Electric quotation Chandkuri CCC at Uttar Eral W/S Scheme Pin:- 721144 |  | 03/08/2022 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.13 | 0 | 0 | 0
3351 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Jhargram Mechanical Electrical Bill. | 2022-23-210 | 18/08/2022 | 0 | EXECUTIVE ENGINEER, JHARGRAM MECHANICAL DIVISION, PHE DTE. | 0.25 | 0 | 0 | 0
3352 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | For payment of liabilities. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 2.28 | 0 | 0 | 0
3353 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well-I at Uttar Eral, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 158/W/MMD | 31/01/2022 | 120 | TAPAN KUMAR SARKAR | 6.47 | 0 | 0 | 0
3354 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well-II at Uttar Eral, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | 159/W/MMD | 31/01/2022 | 120 | RAJIB COMPANY | 6.46 | 0 | 0 | 0
3355 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Uttar Eral (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 469/MD | 09/03/2022 | 150 | SUJATA CONSTRUCTION | 46.64 | 0 | 0 | 0
3356 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Uttar Eral (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 470/MD | 09/03/2022 | 150 | SUJATA CONSTRUCTION | 37.67 | 0 | 0 | 0
3357 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Material Requisition To Resource Division | 2128/MD | 14/12/2021 | 0 | Resource Division | 2.28 | 0 | 0 | 0
3358 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur , SM/09795 | New | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 0 | 100
3359 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Nona Madhabchak PWSS under Sabang Block in Paschim Medinipur District , SM/09708 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Nona Madhabchak PWSS Block-Sabang in the District of Paschim Medinipur. | 2016/MD | 03/12/2021 | 60 | DULAL CHANDRA DAS | 101.79 | 0 | 0 | 0
3360 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Nona Madhabchak PWSS under Sabang Block in Paschim Medinipur District , SM/09708 | Retrofitting | Construction of Sluice Valve/Air Valve/wash out valve Chamber Over the distribution pipe line at within Nonamadhachak & its adjoining mouzas water Supply Scheme at Sabang Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte.(Part -I). | 487/AE/KSD | 01/08/2022 | 30 | BADAL CHANDRA MAIKAP | 4.82 | 0 | 0 | 0
3361 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chakmakrampur Piped Water Supply Scheme. , SM/06912 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chakmakrampur W/S Scheme, Block: - Kharagpur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | 1442/MD | 26/11/2020 | 180 | M/S. CARE | 89.58 | 50.8 | 56.72 | 0
3362 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chakmakrampur Piped Water Supply Scheme. , SM/06912 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Chakmakrampur PWSS in Kharagpur-II Block in the District of Paschim Medinipur. | 306/MD | 22/02/2021 | 45 | M/S. EL-CON | 32.11 | 0 | 0 | 0
3363 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chakmakrampur Piped Water Supply Scheme. , SM/06912 | Retrofitting | Material Requisition To Resource Division | 3409/MD | 25/11/2024 | 0 | Resource Division | 12.07 | 0 | 0 | 0
3364 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Preparation of D.P.R (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- Dewanchak under Dewanchak¿II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | 1329/MD | 17/08/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.34 | 0 | 0 | 0
3365 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Quotation Bill of PH-II, Dewanchak water supply scheme under MMD PHE Dte. | 2003978672 | 28/06/2022 | 365 | WBSEDCL | 0.11 | 0 | 0 | 0
3366 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Service Connection charges of WBSEDCL at Dewanchak, Chowka, Dewanchak P/H-I | 2003978666 | 28/06/2022 | 365 | WBSEDCL | 0.11 | 0 | 0 | 0
3367 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 4.04 | 0 | 0 | 0
3368 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Quotation Bill of PH-I, Dewanchak water supply scheme under MMD PHE Dte. | BP-2022-23-23 | 08/08/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3369 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Electric quotation for Birsingha CCC, Zone-II, Dewanchak water supply scheme under MMD PHE Dte, Pin no.-14/10/2022 | 2004068300 | 17/10/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3370 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY. Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 4.04 | 0 | 0 | 0
3371 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Submission of bill for cleaning head work site, supplying, fitting, fixing RCC demarcation pillers etc. of Mini pipe water supply schemes under SAGY. | BP-2022-23-01 | 18/04/2022 | 0 | SUBHASIS DOLAI | 0.25 | 0 | 0 | 0
3372 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Quotation Bill of PH-II, Dewanchak water supply scheme under MMD PHE Dte. | BP-2022-23-46 | 23/08/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3373 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | electric quotation for Birsingha CCC, Zone-I Dewanchak water supply scheme undre MMD PHE Dte. Pin No.-721232 | 2004068257 | 17/10/2022 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3374 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Submission of bill for cleaning head work site, supplying, fitting, fixing RCC demarcation pillers etc. of Mini pipe water supply schemes under SAGY. | BP-2022-23-02 | 18/04/2022 | 0 | SUBHASIS DOLAI | 0.42 | 0 | 0 | 0
3375 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Electric quotation for Birsingha CCC, Dewanchak water supply scheme Zone-II, Pin no-721232 | 2003788821../Quot/03 | 06/08/2022 | 365 | WBSEDCL | 0.11 | 0 | 0 | 0
3376 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Dewanchak water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | 2173/W/MMD | 12/12/2022 | 120 | PADMA ENGINEERING CO. | 5.93 | 0 | 0 | 0
3377 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-III under Dewanchak water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | 1649/W/MMD | 12/08/2022 | 120 | KAMAKSHYA ENTERPRISE | 5.6 | 0 | 0 | 98
3378 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-IV under Dewanchak water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | 1650/W/MMD | 12/08/2022 | 120 | SHOVAN KUMAR DAS | 5.75 | 0 | 0 | 100
3379 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Material Requisition To Resource Division | 2274/MD | 31/12/2021 | 0 | Resource Division | 4.04 | 0 | 0 | 0
3380 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Dewanchak (Zone-I), Block-Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 293/MD | 15/02/2022 | 150 | DIPAK KUMAR DOLAI | 42.69 | 0 | 0 | 100
3381 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Dewanchak (Zone-IV), Block-Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 294/MD | 15/02/2022 | 150 | SAMIT PAL | 39.22 | 0 | 0 | 100
3382 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Dewanchak (Zone-II), Block - Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 539/MD | 22/03/2022 | 150 | M/S. ZAMAN ENTERPRISE | 36.07 | 0 | 0 | 100
3383 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Dewanchak (Zone-III), Block-Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | 525/MD | 21/03/2022 | 150 | WATER LINK | 41.84 | 0 | 0 | 100
3384 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. , SM/10003 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-I under Dewanchak water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | 2172/W/MMD | 12/12/2022 | 880 | P.K.ENGINEERING | 5.91 | 0 | 0 | 100
3385 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Dantan (Block- Dantan-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1614/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3 | 0 | 0 | 0
3386 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Dantan (Block- Dantan-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1615/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.97 | 0 | 0 | 0
3387 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Hire and labour charges for staging and scaffolding, bamboo barricading and removal of rubbish for dismantling of existing OHR (Capacity 1,00,000 Gallon) at Head work Site of Dantan Water Supply Scheme within Dantan-I Block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | BP-2021-22-477 | 16/03/2022 | 0 | BISWAJIT BAG | 8.57 | 0 | 0 | 0
3388 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Dantan, Block - Dantan-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-384 | 18/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.45 | 0 | 0 | 0
3389 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Dantan, Block - Dantan-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-382 | 18/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.87 | 0 | 0 | 0
3390 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Hiring charges of Bharat Stage ¿ III Diesel Indigo ECS Car / Motor Cabs (Luxury Taxi) having contract Carriage permit from the Regional Transport Authority valid for the State of West Bengal not older than 5 years from the date of 1st Registration on monthly hire rate basis for the period from 15.02.2022 to 14.02.2023(12 months) for the office of the Assistant Engineer, RWS Midnapore Sub-Division, P.H.E. Dte. The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, fees etc. | 28/RWS/MID | 11/02/2022 | 12 | S.K. CONSTRUCTION | 1.52 | 0 | 0 | 0
3391 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Round the Clock Guarding Arrangements to protect the Govt. properties/materials etc. at Dantan Store within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [ for the period 01.02.2022 to30.11.2022] | 48./AE/KSD | 31/01/2022 | 303 | M/S. OXFORD SECURITY SERVICE | 4.58 | 0 | 0 | 0
3392 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur.under JJM Program under MMD PHE Dte. | 1414/W/MMD | 02/06/2023 | 180 | DEY ENTERPRISE | 54.73 | 0 | 0 | 0
3393 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Daspur, Keshiary, Debra & Dantan in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | 951/MD | 17/06/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.77 | 0 | 0 | 100
3394 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Sinking of 125mm X 80 mm. dia. & 138 Mtr. Depth, Tubewell including installation of pumping machinery and accessories etc at Datan Headwork site in the district of Paschim Medinipur under Midnapore Division, P.H.E. Dte. | 488/AE/KSD | 01/08/2022 | 30 | K & KABERI ENTERPRISE (PROP. GOUTAM MAITY) | 2.5 | 0 | 0 | 0
3395 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Dantan W/S Scheme with in Datan-I Block under Midnapore Division, P.H.E. Dte. [Allotted for Sinking of 2 (Nos.) of Tube wells i.e. 50% of the total works] (Part-1/2) | 231/MD | 17/01/2023 | 30 | ANNAPURNA TUBEWELL WORKS | 20.67 | 0 | 0 | 100
3396 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Material Requisition To Resource Division | 395/MD | 06/02/2023 | 0 | Resource Division | 16.56 | 0 | 0 | 0
3397 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Material Requisition To Resource Division | 48/MD | 06/01/2023 | 0 | Resource Division | 48.12 | 0 | 0 | 0
3398 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Material Requisition To Resource Division | 515/MD | 20/02/2023 | 0 | Resource Division | 48.12 | 0 | 0 | 0
3399 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Material Requisition To Resource Division | 5251/MD | 21/11/2023 | 0 | Resource Division | 95.87 | 0 | 0 | 0
3400 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Electric quotation bill for Ad Tw no -III of Dantan PWSS (Ref Consumer ID-204122249) | BP-2023-24-325 | 03/11/2023 | 0 | WBSEDCL | 3.33 | 0 | 0 | 0
3401 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Dantan W/S Scheme with in Datan-I Block under Midnapore Division, P.H.E. Dte. [Allotted for Sinking of 2 (Nos.) of Tube wells i.e. 50% of the total works] (Part-2/2) | 119/MD | 10/01/2023 | 30 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.67 | 0 | 0 | 100
3402 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Electric quotation bill for Tw No-V of Dantan PWSS .(Krishnapur), Ref Consumer ID-204205815, APPLICATION NO-2004580504, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, BLOCK-DANTAN-I | BP-2023-24-604 | 07/02/2024 | 0 | WBSEDCL | 3.78 | 0 | 0 | 0
3403 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Electric quotation bill for Tw No-IV of Dantan PWSS (UTTAR RAY BAR).(Ref Consumer ID-204205780), APPLICATION NO-2004580499, APPLICATION TYPE-NEW CONNECTION, BLOCK-DANTAN-I, NAME OF CCC-DANTAN CCC. | BP-2023-24-603 | 07/02/2024 | 0 | WBSEDCL | 9.63 | 0 | 0 | 0
3404 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. , SM/10000 | Augmentation | Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 900 Cum and staging height 20.00 mtr. & FHTC under JJM with allied work for Augmentation of Datan and its adjoining mouzas W/S Scheme in Datan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 1364/MD | 08/07/2022 | 180 | CONCORD ENGINEERING | 1162.81 | 0 | 0 | 60
3405 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/11880 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Chaupanya PWSS within Kharagpur-II Block under Midnapore Division, P.H.E. Dte. | 520/MD | 17/03/2022 | 10 | SIRCON ENGINEERING SERVICES | 2.7 | 0 | 0 | 100
3406 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/11880 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. (Phase-II) | 1571/W/MMD | 13/07/2023 | 180 | M/S EMMESS | 11.81 | 0 | 0 | 90
3407 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/11880 | Augmentation | Material Requisition To Resource Division | 90/MD | 10/01/2023 | 0 | Resource Division | 21.98 | 0 | 0 | 0
3408 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/11880 | Augmentation | New service connection charges for the pump house at Maheshpur under Choupenia W/S Scheme, ID-2004294624 | BP-2023-24-68 | 07/06/2023 | 0 | WBSEDCL | 3.42 | 0 | 0 | 0
3409 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/11880 | Augmentation | New Service connection charge at Kuliara under Choupenia W/S scheme, ID-2004294643 | BP-2023-24-69 | 07/06/2023 | 0 | WBSEDCL | 3.05 | 0 | 0 | 0
3410 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/11880 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 479/W/MMD | 20/03/2023 | 180 | PURUSHOTTAM ENTERPRISE | 10.98 | 0 | 0 | 100
3411 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/11880 | Augmentation | Augmentation of Ground water based piped water supply scheme for Chaupanya to Accommodate FHTC under JJM under Kharagpur-II Block in Paschim Medinipur Districct under Medinipur Division, PHE Dte. | 2575/MD | 16/12/2022 | 966 | M/S. A.R. ENTERPRISE. | 116.89 | 0 | 0 | 100
3412 | PASCHIM MEDINIPUR | Midnapore Division | CHAK NARSINGHA AND IT'S ADJOINING MOUJAS PWSS , SM/12411 | New | Material Requisition To Resource Division | 1198 | 26/04/2023 | 0 | Resource Division | 25.26 | 0 | 0 | 0
3413 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAK NARSINGHA AND IT'S ADJOINING MOUJAS PWSS , SM/12411 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAK NARSINGHA AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 613/W/MMD | 20/03/2023 | 1095 | BHABANI PRASAD MANNA | 21.58 | 0 | 0 | 85
3414 | PASCHIM MEDINIPUR | Midnapore Division | CHAK NARSINGHA AND IT'S ADJOINING MOUJAS PWSS , SM/12411 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 0 | 25
3415 | PASCHIM MEDINIPUR | Midnapore Division | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS , SM/12412 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
3416 | PASCHIM MEDINIPUR | Midnapore Division | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS , SM/12412 | New | Material Requisition To Resource Division | 1149/MD | 25/04/2023 | 0 | Resource Division | 16.14 | 0 | 0 | 0
3417 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS , SM/12412 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 828/W/MMD | 24/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 22.65 | 0 | 0 | 50
3418 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS , SM/12412 | New | Electrict quotation bill for Chaksulpan water supply scheme pump house NO-I(Consumar Id-204134472) | BP-2023-24-362 | 24/11/2023 | 0 | WBSEDCL | 4.7 | 0 | 0 | 0
3419 | PASCHIM MEDINIPUR | Midnapore Division | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS , SM/12412 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | 2145/MD | 08/06/2023 | 846 | GOBINDA MAITY | 1960.6 | 0 | 0 | 65
3420 | PASCHIM MEDINIPUR | Midnapore Division | MAKLI AND ADJOINING MOUJAS PWSS , SM/13096 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
3421 | PASCHIM MEDINIPUR | Midnapore Division | MAKLI AND ADJOINING MOUJAS PWSS , SM/13096 | New | Material Requisition To Resource Division | 1239/MD | 27/04/2023 | 0 | Resource Division | 20.36 | 0 | 0 | 0
3422 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MAKLI AND ADJOINING MOUJAS PWSS , SM/13096 | New | Payment for WBSEDCL new connection at MAKLI 2 (SM/13096. MAKLI AND ADJOINING MOUJAS PWSS ) | 172/JMD | 07/06/2024 | 0 | WBSEDCL | 10.13 | 0 | 0 | 0
3423 | PASCHIM MEDINIPUR | Central Drilling | MAKLI AND ADJOINING MOUJAS PWSS , SM/13096 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3424 | PASCHIM MEDINIPUR | Midnapore Division | MANIKDIPABARA AND AJOINING MOUJAS PWSS , SM/13097 | New | Material Requisition To Resource Division | 1240/MD | 27/04/2023 | 0 | Resource Division | 27.19 | 0 | 0 | 0
3425 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MANIKDIPABARA AND AJOINING MOUJAS PWSS , SM/13097 | New | Payment for WBSEDCL new connection at Manikdipa 2 (SM/13097. MANIKDIPABARA AND ADJOINING MOUJAS PWSS ) | 169/JMD | 07/06/2024 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
3426 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MANIKDIPABARA AND AJOINING MOUJAS PWSS , SM/13097 | New | WBSEDCL new connection payment for Manikdipa t/w 1 | 66/JMD | 29/04/2024 | 0 | WBSEDCL | 3.39 | 0 | 0 | 0
3427 | PASCHIM MEDINIPUR | Central Drilling | MANIKDIPABARA AND AJOINING MOUJAS PWSS , SM/13097 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3428 | PASCHIM MEDINIPUR | Midnapore Division | GAHIRA AND ADJOINING MOUJAS PWSS , SM/13010 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 0 | 94
3429 | PASCHIM MEDINIPUR | Midnapore Division | GAHIRA AND ADJOINING MOUJAS PWSS , SM/13010 | New | Material Requisition To Resource Division | 3453/MD | 25/11/2024 | 0 | Resource Division | 9.23 | 0 | 0 | 0
3430 | PASCHIM MEDINIPUR | Central Drilling | GAHIRA AND ADJOINING MOUJAS PWSS , SM/13010 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3431 | PASCHIM MEDINIPUR | Midnapore Division | GAHIRA AND ADJOINING MOUJAS PWSS , SM/13010 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7,515 Nos.) including 2 years operation & maintenance For BARAGOPAL, DURIA, GAHIRA & RAIPUR Pipe Water Supply Scheme within NARAYANGARH Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 3048/MD | 23/08/2023 | 975 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 2197.07 | 0 | 0 | 33
3432 | PASCHIM MEDINIPUR | Midnapore Mechanical | GAHIRA AND ADJOINING MOUJAS PWSS , SM/13010 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
3433 | PASCHIM MEDINIPUR | Midnapore Division | BABAIBASA AND ADJOINING MOUJAS PWSS , SM/13753 | New | Material Requisition To Resource Division | 1253/MD | 28/04/2023 | 0 | Resource Division | 19.95 | 0 | 0 | 0
3434 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BABAIBASA AND ADJOINING MOUJAS PWSS , SM/13753 | New | Supply, delivery & fitting fixing of wooden board & Porcelain fuse unit for receiving power from WBSEDCL at Babaibasa & adjacent water supply schemes of Salboni block under JJM progamme under Jhargram Mechanical Division, P.H.E Dte. in the district of Paschim Medinipur. | 3783/JMD | 12/07/2024 | 30 | MONORANJAN DEY | 3.85 | 0 | 0 | 0
3435 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BABAIBASA AND ADJOINING MOUJAS PWSS , SM/13753 | New | New service connection charges for Babuibasa w/s scheme, t/w no.I | 158/JMD | 31/05/2024 | 0 | WBSEDCL | 6.05 | 0 | 0 | 0
3436 | PASCHIM MEDINIPUR | Central Drilling | BABAIBASA AND ADJOINING MOUJAS PWSS , SM/13753 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3437 | PASCHIM MEDINIPUR | Midnapore Division | CHANDABILA & ADJOINING MOUJAS PWSS , SM/13054 | New | Material Requisition To Resource Division | 1152/MD | 25/04/2023 | 0 | Resource Division | 18.15 | 0 | 0 | 0
3438 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | CHANDABILA & ADJOINING MOUJAS PWSS , SM/13054 | New | new service connection charges at Chandabila-II water supply scheme | 258/JMD | 15/07/2024 | 0 | WBSEDCL | 3.61 | 0 | 0 | 0
3439 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | CHANDABILA & ADJOINING MOUJAS PWSS , SM/13054 | New | New Service connection charges. | 63/JMD | 13/03/2024 | 0 | WBSEDCL | 6.83 | 0 | 0 | 0
3440 | PASCHIM MEDINIPUR | Central Drilling | CHANDABILA & ADJOINING MOUJAS PWSS , SM/13054 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3441 | PASCHIM MEDINIPUR | Midnapore Division | BALARAMPUR AND ADJOINING MOUJAS PWSS , SM/13063 | New | Material Requisition To Resource Division | 1213/MD | 27/04/2023 | 0 | Resource Division | 22.26 | 0 | 0 | 0
3442 | PASCHIM MEDINIPUR | Central Drilling | BALARAMPUR AND ADJOINING MOUJAS PWSS , SM/13063 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3443 | PASCHIM MEDINIPUR | Midnapore Division | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS , SM/13089 | New | Material Requisition To Resource Division | 1514/MD | 12/05/2023 | 0 | Resource Division | 21.12 | 0 | 0 | 0
3444 | PASCHIM MEDINIPUR | Midnapore Division | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS , SM/13089 | New | Construction of 150 Cum & 100 Cum Capacity R.C.C Over Head Reservoir (Intze type with solid raft) with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (1904 Nos) including 2 years operation & maintenance For Chak Bajit and Kankara Shibram Pipe Water Supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5061/MD | 26/10/2023 | 638 | ANIRUDDHA BAG | 561.96 | 0 | 0 | 75
3445 | PASCHIM MEDINIPUR | Midnapore Mechanical | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS , SM/13089 | New | Electrict quotation bill for TW-I of Kanakpur pwss (Ref Consumar ID-204314629),Application No-2004748015,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra | BP-2024-25-278 | 12/06/2024 | 0 | WBSEDCL | 4.62 | 0 | 0 | 0
3446 | PASCHIM MEDINIPUR | Midnapore Mechanical | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS , SM/13089 | New | Electrict quotation bill for TW-II of Kanakpur pwss (Ref Consumar ID-204314650),Application No-2004748062,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra | BP-2024-25-279 | 12/06/2024 | 0 | WBSEDCL | 3.21 | 0 | 0 | 0
3447 | PASCHIM MEDINIPUR | Midnapore Mechanical | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS , SM/13089 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 953/W/MMD | 28/03/2023 | 180 | MASSK ENGINEERING WORKS | 21.58 | 0 | 0 | 0
3448 | PASCHIM MEDINIPUR | Midnapore Division | BAMANSAI AND IT'S ADJOINING MOUJAS PWSS , SM/13047 | New | Material Requisition To Resource Division | 1294/MD | 28/04/2023 | 0 | Resource Division | 25.64 | 0 | 0 | 0
3449 | PASCHIM MEDINIPUR | Central Drilling | BAMANSAI AND IT'S ADJOINING MOUJAS PWSS , SM/13047 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3450 | PASCHIM MEDINIPUR | Midnapore Division | TURKA KASHBA AND IT'S ADJOINING MOUJAS PWSS , SM/13050 | New | Material Requisition To Resource Division | 1291/MD | 28/04/2023 | 0 | Resource Division | 29.16 | 0 | 0 | 0
3451 | PASCHIM MEDINIPUR | Midnapore Mechanical | TURKA KASHBA AND IT'S ADJOINING MOUJAS PWSS , SM/13050 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF TURKA KASHBA PWSS. REF CONSUMER ID-204391652, APPLICATION NO-2004886649, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102401985532 | 03/10/2024 | 0 | WBSEDCL | 7.1 | 0 | 0 | 0
3452 | PASCHIM MEDINIPUR | Midnapore Mechanical | TURKA KASHBA AND IT'S ADJOINING MOUJAS PWSS , SM/13050 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF TURKA KASHBA PWSS. REF CONSUMER ID-204391650, APPLICATION NO-2004886647, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102401986837 | 03/10/2024 | 0 | WBSEDCL | 3.46 | 0 | 0 | 0
3453 | PASCHIM MEDINIPUR | Central Drilling | TURKA KASHBA AND IT'S ADJOINING MOUJAS PWSS , SM/13050 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3454 | PASCHIM MEDINIPUR | Midnapore Division | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/13024 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
3455 | PASCHIM MEDINIPUR | Midnapore Division | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/13024 | New | Material Requisition To Resource Division | 1147/MD | 25/04/2023 | 0 | Resource Division | 14.87 | 0 | 0 | 0
3456 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/13024 | New | Electric qutation bill for khanamohan water supply scheme at pump house NO-I | BP-2023-24-341 | 10/11/2023 | 0 | WBSEDCL | 3.06 | 0 | 0 | 0
3457 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/13024 | New | Electric quotation bill for khanamohan water supply scheme at pump house N0-II | BP-2023-24-340 | 10/11/2023 | 0 | WBSEDCL | 3.61 | 0 | 0 | 0
3458 | PASCHIM MEDINIPUR | Midnapore Division | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/13024 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | 2145/MD | 08/06/2023 | 846 | GOBINDA MAITY | 1960.6 | 0 | 0 | 65
3459 | PASCHIM MEDINIPUR | Midnapore Mechanical | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/13024 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 797/W/MMD | 24/03/2023 | 860 | BHABANI PRASAD MANNA | 21.62 | 0 | 0 | 80
3460 | PASCHIM MEDINIPUR | Midnapore Division | MOHANPUR & ADJOINING MOUJAS PWSS , SM/13028 | New | Material Requisition To Resource Division | 1157/MD | 25/04/2023 | 0 | Resource Division | 25.71 | 0 | 0 | 0
3461 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MOHANPUR & ADJOINING MOUJAS PWSS , SM/13028 | New | New Service connection charges. | 64/JMD | 13/03/2024 | 0 | WBSEDCL | 6.33 | 0 | 0 | 0
3462 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | MOHANPUR & ADJOINING MOUJAS PWSS , SM/13028 | New | New Service connection charges. | 65/JMD | 13/03/2024 | 0 | WBSEDCL | 3.09 | 0 | 0 | 0
3463 | PASCHIM MEDINIPUR | Central Drilling | MOHANPUR & ADJOINING MOUJAS PWSS , SM/13028 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3464 | PASCHIM MEDINIPUR | Midnapore Division | RELA AND IT'S ADJOINING MOUJAS PWSS , SM/13036 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
3465 | PASCHIM MEDINIPUR | Midnapore Division | RELA AND IT'S ADJOINING MOUJAS PWSS , SM/13036 | New | Material Requisition To Resource Division | 1298/MD | 28/04/2023 | 0 | Resource Division | 23.27 | 0 | 0 | 0
3466 | PASCHIM MEDINIPUR | Midnapore Mechanical | RELA AND IT'S ADJOINING MOUJAS PWSS , SM/13036 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF RELA PWSS. REF CONSUMER ID-204391648, APPLICATION NO-2004886689, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102401976404 | 03/10/2024 | 0 | WBSEDCL | 5.33 | 0 | 0 | 0
3467 | PASCHIM MEDINIPUR | Midnapore Mechanical | RELA AND IT'S ADJOINING MOUJAS PWSS , SM/13036 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF RELA PWSS. REF CONSUMER ID-204391646, APPLICATION NO-2004886695, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | C102401976054 | 03/10/2024 | 0 | WBSEDCL | 3.68 | 0 | 0 | 0
3468 | PASCHIM MEDINIPUR | Central Drilling | RELA AND IT'S ADJOINING MOUJAS PWSS , SM/13036 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3469 | PASCHIM MEDINIPUR | Midnapore Division | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14651 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Gopmahal urf Monaharpur & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | 1765/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.05 | 0 | 0 | 100
3470 | PASCHIM MEDINIPUR | Midnapore Division | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14651 | New | Material Requisition To Resource Division | 4059/MD | 12/10/2023 | 0 | Resource Division | 23.42 | 0 | 0 | 0
3471 | PASCHIM MEDINIPUR | Midnapore Division | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14651 | New | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,690 Nos.) under JJM with allied work for Gopmahal PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 555/MD | 22/02/2023 | 180 | ASHIM KUMAR DEY | 353.2 | 0 | 0 | 15
3472 | PASCHIM MEDINIPUR | Midnapore Division | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14651 | New | Material Requisition To Resource Division | 3360/MD | 25/11/2024 | 0 | Resource Division | 4.77 | 0 | 0 | 0
3473 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14651 | New | GOPMAHAL WATER SUPPLY SCHEME, PH - I, BLOCK - GHATAL , SCHEME - SM/14651, REF. ID - 204135807, GHATAL CCC, | BP-2023-24-391 | 02/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0 | 0
3474 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14651 | New | QUOTATION MONEY FOR SHIFTING OF HT LINE ALONG WITH DTR OF GOPMAHAL URF MONAHARPUR WATER SUPPLY SCHEME, T W - I , JJM WORKS, SCHEME CODE SM/14651, APPLICATION NO 100000109467, REFERENCE ID 860301697, GHATAL CCC, WBSEDCL | BP-2024-25-357 | 01/07/2024 | 0 | WBSEDCL | 2.02 | 0 | 0 | 0
3475 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14651 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 461/W/MMD | 20/03/2023 | 180 | M/S B.M. ELECTRICAL | 22.89 | 0 | 0 | 40
3476 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14651 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 1684/MMSD-I | 19/12/2023 | 60 | SUBHASIS ROY | 0.29 | 0 | 0 | 40
3477 | PASCHIM MEDINIPUR | Midnapore Mechanical | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14651 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
3478 | PASCHIM MEDINIPUR | Midnapore Division | BHATURBANDI AND ADJOINING MOUJAS PWSS , SM/14825 | New | Material Requisition To Resource Division | 1216/MD | 27/04/2023 | 0 | Resource Division | 21.29 | 0 | 0 | 0
3479 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BHATURBANDI AND ADJOINING MOUJAS PWSS , SM/14825 | New | Quotation for new service connection at Bhaturbandi T/W-I water supply scheme. | 38/JMD | 29/04/2024 | 0 | WBSEDCL | 4.02 | 0 | 0 | 0
3480 | PASCHIM MEDINIPUR | Central Drilling | BHATURBANDI AND ADJOINING MOUJAS PWSS , SM/14825 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3481 | PASCHIM MEDINIPUR | Midnapore Division | JHARBHANGA AND ADJOINING MOUJAS PWSS , SM/14652 | New | Material Requisition To Resource Division | 1303/MD | 28/04/2023 | 0 | Resource Division | 32.22 | 0 | 0 | 0
3482 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | JHARBHANGA AND ADJOINING MOUJAS PWSS , SM/14652 | New | New service connection charges for Jharbhanga, t/w-II w/s scheme | 88/JMD | 12/02/2024 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
3483 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | JHARBHANGA AND ADJOINING MOUJAS PWSS , SM/14652 | New | New service connection charges for Jharbhanga, t/w-I w/s scheme | 79/JMD | 12/02/2024 | 0 | WBSEDCL | 3.39 | 0 | 0 | 0
3484 | PASCHIM MEDINIPUR | Central Drilling | JHARBHANGA AND ADJOINING MOUJAS PWSS , SM/14652 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3485 | PASCHIM MEDINIPUR | Midnapore Division | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS , SM/14996 | New | Sinking of 2 (Two) Nos. Tube well for Chakmaoa & its adjoining mouzas PWSS in Kharagpur-II block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | 2513/MD | 18/07/2023 | 30 | FIROJ KHAN | 16.41 | 0 | 0 | 100
3486 | PASCHIM MEDINIPUR | Midnapore Division | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS , SM/14996 | New | Material Requisition To Resource Division | 1361/MD | 02/05/2023 | 0 | Resource Division | 20.15 | 0 | 0 | 0
3487 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS , SM/14996 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAKMAOA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | 618/W/MMD | 20/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 21.58 | 0 | 0 | 50
3488 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS , SM/14996 | New | Quotation for new power connection at Chakmaoa water supply scheme T/W - II | BP-2023-24-618 | 07/02/2024 | 0 | WBSEDCL | 1.99 | 0 | 0 | 0
3489 | PASCHIM MEDINIPUR | Midnapore Mechanical | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS , SM/14996 | New | Quotation for new power connection at Chakmawa PWSS , T/W - I , Application no - 2004582518 , Ref ID - 204206276 , Madpur CCC | BP-2023-24-705 | 16/02/2024 | 0 | WBSEDCL | 3.78 | 0 | 0 | 0
3490 | PASCHIM MEDINIPUR | Midnapore Division | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS , SM/14996 | New | Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 200 Cum OHR (Intze type with Raft foundation) & Accommodate FHTC (837 nos.) under JJM with allied work including supply of all labour & materials for Chakmaoa & its adjoining mouzas PWSS within Kharagpur-II Block including 02 (Two) Years Operation & Maintenance under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | 1848/MD | 13/06/2024 | 540 | DIPAK KUMAR BAKLY | 264.73 | 0 | 0 | 15
3491 | PASCHIM MEDINIPUR | Midnapore Division | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14997 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Chaksadi & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | 1753/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.35 | 0 | 0 | 100
3492 | PASCHIM MEDINIPUR | Midnapore Division | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14997 | New | Material Requisition To Resource Division | 69/MD | 09/01/2023 | 0 | Resource Division | 22.68 | 0 | 0 | 0
3493 | PASCHIM MEDINIPUR | Midnapore Division | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14997 | New | Material Requisition To Resource Division | 3357/MD | 25/11/2024 | 0 | Resource Division | 10.72 | 0 | 0 | 0
3494 | PASCHIM MEDINIPUR | Midnapore Mechanical | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14997 | New | QUOTATION MONEY FOR CHAKSADI WATER SUPPLY SCHEME, T W NO 1 JJM WORKS, SCHEME CODE SM/14997, APPLICATION NO 2004759795, REFERENCE ID 204321902, BIRSINGHA CCC, WBSEDCL | BP-2024-25-297 | 18/06/2024 | 0 | WBSEDCL | 4.43 | 0 | 0 | 0
3495 | PASCHIM MEDINIPUR | Midnapore Mechanical | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14997 | New | QUOTATION MONEY FOR CHAKSADI WATER SUPPLY SCHEME, T W NO 2 JJM WORKS, SCHEME CODE SM/14997, APPLICATION NO 2004759781, REFERENCE ID 204321817, BIRSINGHA CCC, WBSEDCL | BP-2024-25-298 | 18/06/2024 | 0 | WBSEDCL | 5.1 | 0 | 0 | 0
3496 | PASCHIM MEDINIPUR | Midnapore Mechanical | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/14997 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 840/W/MMD | 24/03/2023 | 180 | RITESH ENTERPRISE | 27.39 | 0 | 0 | 40
3497 | PASCHIM MEDINIPUR | Midnapore Division | GOHALDANGA AND ADJOINING MOUJAS PWSS , SM/15004 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
3498 | PASCHIM MEDINIPUR | Midnapore Division | GOHALDANGA AND ADJOINING MOUJAS PWSS , SM/15004 | New | Material Requisition To Resource Division | 1522/MD | 12/05/2023 | 0 | Resource Division | 10.33 | 0 | 0 | 0
3499 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GOHALDANGA AND ADJOINING MOUJAS PWSS , SM/15004 | New | New service connection at Gohaldanga T/W-II water supply scheme. | 327/JMD | 29/08/2024 | 0 | WBSEDCL | 3.37 | 0 | 0 | 0
3500 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GOHALDANGA AND ADJOINING MOUJAS PWSS , SM/15004 | New | New Service connection charges. | 21/JMD | 04/03/2024 | 0 | WBSEDCL | 4.68 | 0 | 0 | 0
3501 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GOHALDANGA AND ADJOINING MOUJAS PWSS , SM/15004 | New | New service connection | 69/JMD | 12/02/2024 | 0 | WBSEDCL | 4.49 | 0 | 0 | 0
3502 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GOHALDANGA AND ADJOINING MOUJAS PWSS , SM/15004 | New | New Service connection charges. | 86/JMD | 21/03/2024 | 0 | WBSEDCL | 11.56 | 0 | 0 | 0
3503 | PASCHIM MEDINIPUR | Midnapore Division | GOHALDANGA AND ADJOINING MOUJAS PWSS , SM/15004 | New | Construction of 200 Cum capacity R.C.C. Over Head Reservoir over Raft Foundation works with Laying rising main, Distribution system, Sinking of Tube Well, Pump House, Soil investigation, Boundary Wall & Providing Functional Household Tap Connection (1538 Nos.) including Two years operation & maintenance for Gohaldanga Pipe Water Supply Scheme within Garbeta-II Block under Medinipur Sadar Sub-Division of Midnapore Division, PHE Dte. under Paschim Medinipur District. | 2152/MD | 08/06/2023 | 910 | M/S. D.C.M. CONSTRUCTION | 454.46 | 0 | 0 | 40
3504 | PASCHIM MEDINIPUR | Central Drilling | GOHALDANGA AND ADJOINING MOUJAS PWSS , SM/15004 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3505 | PASCHIM MEDINIPUR | Midnapore Division | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15011 | New | Preparation & Submission of 6 (Six) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Shrirampur & its adjoining Mouzas PWSS, (2) Dontiara & its adjoining Mouzas PWSS, (3) Dhashachandpur Mouza Stand Alone PWSS, (4) Udayganj (P) Mouza Stand Alone PWSS, (5) Prasadchak Mouza Stand Alone PWSS AND (6) Anandapur Mouza Stand Alone PWSS, Block - Ghatal under Midnapore Division, PHE Dte. [Name of Proposed PWSS Chaulisingpur & its adjoining Mouzas PWSS & Hemantapur & its adjoining Mouzas PWSS instead of (1) Dhashachandpur Mouza Stand Alone PWSS, (2) Udayganj (P) Mouza Stand Alone PWSS, (3) Prasadchak Mouza Stand Alone PWSS AND (4) Anandapur Mouza Stand Alone PWSS] | 1767/MD | 24/08/2022 | 45 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.73 | 0 | 0 | 100
3506 | PASCHIM MEDINIPUR | Midnapore Division | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15011 | New | Material Requisition To Resource Division | 410/MD | 07/02/2023 | 0 | Resource Division | 7.2 | 0 | 0 | 0
3507 | PASCHIM MEDINIPUR | Midnapore Division | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15011 | New | Material Requisition To Resource Division | 410/MD | 07/02/2023 | 0 | Resource Division | 7.2 | 0 | 0 | 0
3508 | PASCHIM MEDINIPUR | Midnapore Mechanical | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15011 | New | CERTIFIED THAT IT IS THE QUOTATION MONEY FOR HEMANTAPUR WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/15011, APPLICATION NO 2004627986, REFERENCE ID 204234632, GHATAL CCC, WBSEDCL | BP-2023-24-842 | 14/03/2024 | 0 | WBSEDCL | 3.35 | 0 | 0 | 0
3509 | PASCHIM MEDINIPUR | Midnapore Mechanical | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15011 | New | ADDITIONAL QUOTATION MONEY FOR HEMANTAPUR WATER SUPPLY SCHEME, T W NO I, ADDITIONAL QUOTATION, JJM WORKS, SCHEME CODE SM/15011, APPLICATION NO 100000114253, REFERENCE ID 860308903, GHATAL CCC, WBSEDCL | BP-2024-25-545 | 07/08/2024 | 0 | WBSEDCL | 0.73 | 0 | 0 | 0
3510 | PASCHIM MEDINIPUR | Midnapore Mechanical | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15011 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 804/W/MMD | 24/03/2023 | 180 | SHREE BISHNU CONSTRUCTION | 10.79 | 0 | 0 | 80
3511 | PASCHIM MEDINIPUR | Midnapore Mechanical | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15011 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 1684/MMSD-I | 19/12/2023 | 60 | SUBHASIS ROY | 0.29 | 0 | 0 | 40
3512 | PASCHIM MEDINIPUR | Midnapore Mechanical | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15011 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
3513 | PASCHIM MEDINIPUR | Midnapore Division | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15011 | New | Laying distribution pipe line & Pump House under JJM with allied work for Hemantapur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 2429/MD | 13/07/2023 | 538 | JIT ENTERPRISE | 31.13 | 0 | 0 | 100
3514 | PASCHIM MEDINIPUR | Midnapore Division | PUNDRA AND ADJOINING MOUJAS PWSS , SM/13169 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
3515 | PASCHIM MEDINIPUR | Midnapore Division | PUNDRA AND ADJOINING MOUJAS PWSS , SM/13169 | New | Material Requisition To Resource Division | 210/MD | 16/01/2023 | 0 | Resource Division | 18.39 | 0 | 0 | 0
3516 | PASCHIM MEDINIPUR | Midnapore Division | PUNDRA AND ADJOINING MOUJAS PWSS , SM/13169 | New | Material Requisition To Resource Division | 3462/MD | 25/11/2024 | 0 | Resource Division | 11.14 | 0 | 0 | 0
3517 | PASCHIM MEDINIPUR | Midnapore Mechanical | PUNDRA AND ADJOINING MOUJAS PWSS , SM/13169 | New | Electric quotation bill for Tw No-I of Pundra PWSS (ref Consumer ID-204121973) | BP-2023-24-412 | 09/12/2023 | 0 | WBSEDCL | 5.37 | 0 | 0 | 0
3518 | PASCHIM MEDINIPUR | Midnapore Mechanical | PUNDRA AND ADJOINING MOUJAS PWSS , SM/13169 | New | Electric quotation bill for Tw no-II of PUNDRA PWSS.(Ref Consumer ID-204183610) | BP-2023-24-564 | 16/01/2024 | 0 | WBSEDCL | 4.78 | 0 | 0 | 0
3519 | PASCHIM MEDINIPUR | Midnapore Mechanical | PUNDRA AND ADJOINING MOUJAS PWSS , SM/13169 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PUNDRA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | 2395/W/MMD | 31/12/2022 | 819 | DAS ENTERPRISE | 22.83 | 0 | 0 | 30
3520 | PASCHIM MEDINIPUR | Midnapore Division | KULBANI AND ADJOINING MOUJAS PWSS , SM/13121 | New | Material Requisition To Resource Division | 1318/MD | 28/04/2023 | 0 | Resource Division | 43.67 | 0 | 0 | 0
3521 | PASCHIM MEDINIPUR | Midnapore Mechanical | KULBANI AND ADJOINING MOUJAS PWSS , SM/13121 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KULBANI AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 3076/W/MMD | 29/11/2023 | 180 | M/S EMMESS | 34.18 | 0 | 0 | 20
3522 | PASCHIM MEDINIPUR | Central Drilling | KULBANI AND ADJOINING MOUJAS PWSS , SM/13121 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Kulbani W/S Scheme (T/W-I, II & III), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | 1096/CDD | 18/08/2023 | 30 | PADMA ENGINEERING & CO. | 36.93 | 0 | 0 | 60
3523 | PASCHIM MEDINIPUR | Midnapore Mechanical | KULBANI AND ADJOINING MOUJAS PWSS , SM/13121 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of KULBONI PWSS. REF CONSUMER ID-204226373, APPLICATION NO-2004615869, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2023-24-805 | 11/03/2024 | 0 | WBSEDCL | 6.65 | 0 | 0 | 0
3524 | PASCHIM MEDINIPUR | Midnapore Mechanical | KULBANI AND ADJOINING MOUJAS PWSS , SM/13121 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of KULBONI PWSS. REF CONSUMER ID-204226372, APPLICATION NO-2004615833, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | BP-2023-24-806 | 11/03/2024 | 0 | WBSEDCL | 6.53 | 0 | 0 | 0
3525 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing (i) Barisha PWSS within Pingla block & (ii) Nayagram PWSS within Midnapore Sadar Block under Midnapore Division P.H.E. Dte. | 2064/MD | 30/09/2022 | 15 | GOBINDA MAITY | 7.34 | 0 | 0 | 0
3526 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Nayagram water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | 423/MMSD-I | 20/04/2023 | 15 | DEBJYOTI BASU | 4.37 | 0 | 0 | 100
3527 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW IV of Nayagram water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | 424/MMSD-I | 20/04/2023 | 15 | SUJOY RANJAN BHOWMICK | 4.37 | 0 | 0 | 60
3528 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Material Requisition To Resource Division | 1395/MD | 03/05/2023 | 0 | Resource Division | 15.86 | 0 | 0 | 0
3529 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Electric quotation for Nayagram PWSS Tube Well- IV in connection Barua CCC (2004189731) |  | 21/02/2023 | 0 | WBSEDCL | 0.19 | 0 | 0 | 0
3530 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Electric quotation for Nayagram PWSS Tube Well- III in connection Barua CCC | BP-2022-23-159 | 31/03/2023 | 0 | WBSEDCL | 0.19 | 0 | 0 | 0
3531 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Electric quotation for Nayagram PWSS Tube Well- IV in connection Barua CCC (2004189731) | BP-2022-23-160 | 31/03/2023 | 0 | WBSEDCL | 0.19 | 0 | 0 | 0
3532 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Electric quotation for Nayagram PWSS Tube Well- III in connection Barua CCC ( |  | 21/02/2023 | 0 | WBSEDCL | 0.19 | 0 | 0 | 0
3533 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram and its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 791/W/MMD | 24/03/2023 | 180 | SHOVAN KUMAR DAS | 22.79 | 0 | 0 | 68
3534 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Laying distribution pipe line, Rising main, Boundary wall & Accommodate FHTC (200 Nos.) under JJM with allied work for Augmentation of Nayagram & its adjoining mouzas W/S Scheme in Midnapore Sadar block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 2718/MD | 31/07/2023 | 179 | MIDNAPUR PIPE CONCERN | 112.05 | 0 | 0 | 40
3535 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Laying distribution pipeline under JJM with allied work for Augmentation of Nayagram & its adjoining mouzas W/S Scheme in Midnapore Sadar block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | 3966/MD | 05/10/2023 | 45 | AJIJUR RAHAMAN MALLICK | 24.77 | 0 | 0 | 60
3536 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Accommodate FHTC (126 Nos.), Construction of Boundary wall, Switch Room under JJM with allied work for Augmentation of Nayagram & its adjoining mouzas W/S Scheme in Midnapore Sadar block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 5563/MD | 26/12/2023 | 60 | MODERN CONSTRUCTION | 18.35 | 0 | 0 | 0
3537 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Construction of OHR (250 cum) & Accommodate FHTC (200 Nos.) under JJM with allied work for Augmentation of Nayagram & its adjoining mouzas W/S Scheme in Midnapore Sadar block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 3163/MD | 05/10/2024 | 180 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 91.94 | 0 | 0 | 0
3538 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/15092 | Augmentation | Sinking of 2 (Two) Nos. Tube well for Augmentation of Nayagram & its adjoining mouzas PWSS in Midnapore Sadar block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | 2516/MD | 18/07/2023 | 30 | MIDNAPUR PIPE CONCERN | 23.44 | 0 | 0 | 55
3539 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15591 | New | Material Requisition To Resource Division | 67/MD | 09/01/2023 | 0 | Resource Division | 36.02 | 0 | 0 | 0
3540 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15591 | New | Material Requisition To Resource Division | 3432/MD | 25/11/2024 | 0 | Resource Division | 13.47 | 0 | 0 | 0
3541 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15591 | New | QUOTATION MONEY FOR RISA WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/15591, APPLICATION NO 2004636219, REFERENCE ID 204240939, NIMPURA CCC, WBSEDCL | BP-2024-25-427 | 16/07/2024 | 0 | WBSEDCL | 4.64 | 0 | 0 | 0
3542 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15591 | New | QUOTATION MONEY FOR RISA WATER SUPPLY SCHEME, T W NO I JJM WORKS, SCHEME CODE SM/15591, APPLICATION NO 2004582784, REFERENCE ID 204211198, NIMPURA CCC, WBSEDCL | BP-2023-24-696 | 16/02/2024 | 0 | WBSEDCL | 3.29 | 0 | 0 | 0
3543 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15591 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 910/W/MMD | 27/03/2023 | 894 | JAL PRAVAHIKA PVT. LTD. | 25.24 | 0 | 0 | 95
3544 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. , SM/15591 | New | Sinking of Tube Well, Laying distribution pipe line, Rising main, Pump House, Boundary wall, Soil investigation, Construction of 450 (Intze type with pile foundation) & 250 & 400 cum OHRs (Intze type with solid raft) & Accommodate FHTC (6,370 Nos.) including Two years O&M under JJM with allied work for (1) Gokulpur (Zone-I,II & III ) and (2) Risa & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 2466/MD | 14/07/2023 | 1009 | GOBINDA MAITY | 1715.83 | 0 | 0 | 30
3545 | PASCHIM MEDINIPUR | Midnapore Division | UMRAPATA AND ADJOINING MOUJAS PWSS , SM/15123 | New | Material Requisition To Resource Division | 1246 | 27/04/2023 | 0 | Resource Division | 4.78 | 0 | 0 | 0
3546 | PASCHIM MEDINIPUR | Central Drilling | UMRAPATA AND ADJOINING MOUJAS PWSS , SM/15123 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3547 | PASCHIM MEDINIPUR | Midnapore Division | BARDIHA AND ADJOINING MOUJAS PWSS , SM/14692 | New | Material Requisition To Resource Division | 1215/MD | 27/04/2023 | 0 | Resource Division | 18.54 | 0 | 0 | 0
3548 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BARDIHA AND ADJOINING MOUJAS PWSS , SM/14692 | New | Quotation for new service connection at BARDIHA T/W-II water supply scheme. | 370/JMD | 25/09/2024 | 0 | WBSEDCL | 7.27 | 0 | 0 | 0
3549 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | BARDIHA AND ADJOINING MOUJAS PWSS , SM/14692 | New | Quotation for new service connection at BARDIHA T/W-I water supply scheme. | 371/JMD | 25/09/2024 | 0 | WBSEDCL | 5.38 | 0 | 0 | 0
3550 | PASCHIM MEDINIPUR | Central Drilling | BARDIHA AND ADJOINING MOUJAS PWSS , SM/14692 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3551 | PASCHIM MEDINIPUR | Midnapore Division | BARA MAHANPUR AND ADJOINING MOUJAS PWSS , SM/14941 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation at 3 Nos. of locations adjacent to the Bara Mahanpur of Narayangarh block in Paschim Medinipur district under Midnapore Division, PHE Dte. | 708/MD | 06/03/2023 | 21 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0 | 0
3552 | PASCHIM MEDINIPUR | Midnapore Division | BARA MAHANPUR AND ADJOINING MOUJAS PWSS , SM/14941 | New | Material Requisition To Resource Division | 1484 | 10/05/2023 | 0 | Resource Division | 24.73 | 0 | 0 | 0
3553 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARA MAHANPUR AND ADJOINING MOUJAS PWSS , SM/14941 | New | Quotation for new power connection at Bara Mohanpur PWSS T/W- I ,Narayangarh Block , Application no- 2004641957 , ref. Id - 404244873 | BP-2024-25-153 | 09/05/2024 | 0 | WBSEDCL | 5.26 | 0 | 0 | 0
3554 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARA MAHANPUR AND ADJOINING MOUJAS PWSS , SM/14941 | New | Quotation for new power connection at Baramohanpur PWSS T/W - II under Narayangarh Block , Application no - 2004852851 , Ref No - 204373751. | C092402013162 | 04/09/2024 | 0 | WBSEDCL | 4.02 | 0 | 0 | 0
3555 | PASCHIM MEDINIPUR | Central Drilling | BARA MAHANPUR AND ADJOINING MOUJAS PWSS , SM/14941 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3556 | PASCHIM MEDINIPUR | Midnapore Division | BARA MAHANPUR AND ADJOINING MOUJAS PWSS , SM/14941 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
3557 | PASCHIM MEDINIPUR | Midnapore Mechanical | BARA MAHANPUR AND ADJOINING MOUJAS PWSS , SM/14941 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
3558 | PASCHIM MEDINIPUR | Midnapore Division | PATAJHARIA AND ADJOINING MOUJAS PWSS , SM/15027 | New | Material Requisition To Resource Division | 1269/MD | 28/04/2023 | 0 | Resource Division | 20.93 | 0 | 0 | 0
3559 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | PATAJHARIA AND ADJOINING MOUJAS PWSS , SM/15027 | New | New service connection charges for Patajhariya w/s scheme, t/w no.-II | 159/JMD | 31/05/2024 | 0 | WBSEDCL | 8.54 | 0 | 0 | 0
3560 | PASCHIM MEDINIPUR | Central Drilling | PATAJHARIA AND ADJOINING MOUJAS PWSS , SM/15027 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3561 | PASCHIM MEDINIPUR | Midnapore Division | METELDEBIGHATA AND ADJOINING MOUJAS PWSS , SM/14624 | New | Material Requisition To Resource Division | 1305/MD | 28/04/2023 | 0 | Resource Division | 1.8 | 0 | 0 | 0
3562 | PASCHIM MEDINIPUR | Central Drilling | METELDEBIGHATA AND ADJOINING MOUJAS PWSS , SM/14624 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3563 | PASCHIM MEDINIPUR | Midnapore Mechanical | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15325 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 493/W/MMD | 20/03/2023 | 180 | S.P. ENTERPRISE | 22.95 | 0 | 0 | 0
3564 | PASCHIM MEDINIPUR | Midnapore Division | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15325 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Maharajpur & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | 1752/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.95 | 0 | 0 | 100
3565 | PASCHIM MEDINIPUR | Midnapore Division | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15325 | New | Material Requisition To Resource Division | 60/MD | 09/01/2023 | 0 | Resource Division | 36.92 | 0 | 0 | 0
3566 | PASCHIM MEDINIPUR | Midnapore Division | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15325 | New | Material Requisition To Resource Division | 3363/MD | 25/11/2024 | 0 | Resource Division | 13.44 | 0 | 0 | 0
3567 | PASCHIM MEDINIPUR | Midnapore Mechanical | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. , SM/15325 | New | QUOTATION MONEY FOR MAHARJPUR WATER SUPPLY SCHEME, T W NO I, JJM WORKS, SCHEME CODE SM/15325, APPLICATION NO 2004857637, REFERENCE ID 204376542, BIRSINGHA CCC, WBSEDCL | C112429741036 | 25/11/2024 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
3568 | PASCHIM MEDINIPUR | Midnapore Division | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Sinking of 2 (Two) Nos. 300 X 200 mm dia. X 220 Mtr. Depth deep tube well by Direct Rotary Method for Head Work site & 2nd Tube well site of Tanuya W/S Scheme with in Mohanpur block under Midnapore Division, PHE Dte. | 609/MD | 04/04/2022 | 15 | TAPAS KUMAR GIRI | 21.93 | 0 | 0 | 100
3569 | PASCHIM MEDINIPUR | Midnapore Division | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room with out W.C. & Bath for Second Tube Well Site under Tanuya W/S Scheme within Midnapore Division, PHE Dte. (Considering G.L. 300 mm below road level) (Type -A) | 543/AE/KSD | 23/08/2022 | 30 | PRITI ENTERPRISE | 2.8 | 0 | 0 | 0
3570 | PASCHIM MEDINIPUR | Midnapore Division | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Purchasing of materials for the Tanuya Piped Water Supply Scheme. |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 13.62 | 0 | 0 | 0
3571 | PASCHIM MEDINIPUR | Midnapore Division | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Supply & delivery of different dia. C.I.D. F. Sluice Valves for laying of Distribution main pipeline for Tanuya Piped Water Supply Scheme within Mohanpur Block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. In Paschim Medinipur District. (Sl.No.-03) | 313/AE/KSD | 10/06/2022 | 15 | ASHOK BANERJEE | 3.24 | 0 | 0 | 0
3572 | PASCHIM MEDINIPUR | Midnapore Division | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Material Requisition To Resource Division | 149/MD | 28/01/2022 | 0 | Resource Division | 13.62 | 0 | 0 | 0
3573 | PASCHIM MEDINIPUR | Midnapore Division | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Material Requisition To Resource Division | `2430/MD | 29/11/2022 | 0 | Resource Division | 58.77 | 0 | 0 | 0
3574 | PASCHIM MEDINIPUR | Midnapore Division | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Electric Quation for Tanua Bandh mini PWSS Tube well-I in connection Mohanpur CCC. | BP-2023-24-14 | 24/04/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 1.98 | 0 | 0 | 0
3575 | PASCHIM MEDINIPUR | Midnapore Division | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Electric Quation for Tanua Bandh PWSS Tube well-II in connection Mohanpur CCC. | BP-2023-24-13 | 24/04/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 1.9 | 0 | 0 | 0
3576 | PASCHIM MEDINIPUR | Midnapore Division | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Laying distribution pipe line, Soil test and Construction of R.C.C. Elevated Reservoir of capacity 400 Cum and staging height 20.00 mtr. with allied works (Pile Foundation) including Providing FHTC of TANUYA & its adjoining mouzas Water Supply Scheme within Mohanpur Dev. Block in the district of Paschim Medinipur under Midnapore Division, P.H.E. Dte. | 33/MD | 07/01/2022 | 180 | BANERJEE CONSTRUCTION | 473.08 | 0 | 0 | 95
3577 | PASCHIM MEDINIPUR | Midnapore Division | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Construction of 5.40 Mtr. X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Head Works Site under Tanuya W/S Scheme within Midnapore Division, PHE Dte. (Considering G.L. 300 mm below road level) (Type - A) | 981/MD | 10/04/2023 | 60 | BANERJEE CONSTRUCTION | 5.22 | 0 | 0 | 90
3578 | PASCHIM MEDINIPUR | Midnapore Mechanical | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Tanuya Piped Water Supply Scheme.under JJM Program under MMD PHE Dte. | 1358/W/MMD | 24/05/2023 | 180 | PS & ASSOCIATES | 27.3 | 0 | 0 | 60
3579 | PASCHIM MEDINIPUR | Midnapore Division | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Material Requisition To Resource Division | 3465/MD | 25/11/2024 | 0 | Resource Division | 15.27 | 0 | 0 | 0
3580 | PASCHIM MEDINIPUR | Midnapore Mechanical | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Additional quatation bill for application no-2004172244 for Tw No-II of Tanuya PWSS. | BP-2023-24-464 | 27/12/2023 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
3581 | PASCHIM MEDINIPUR | Midnapore Division | Tanuya Piped Water Supply Scheme. , SM/09992 | New | Laying of rising main including interconnection for Tanuya & its adjoining mouzas W/S Scheme within Mohanpur block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | 48/MD | 07/01/2025 | 45 | AJITESH ACHARJEE | 6.8 | 0 | 0 | 0
3582 | PASCHIM MEDINIPUR | Midnapore Division | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16542 | New | Material Requisition To Resource Division | 1324/MD | 28/04/2023 | 0 | Resource Division | 30.06 | 0 | 0 | 0
3583 | PASCHIM MEDINIPUR | Central Drilling | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16542 | New | Hiring of Diesel Driven Motor Cab (BS-IV & Above) hiving contract carriage permit along with driver for office of the Store & Workshop Sub Division, Central Drilling Division, PHE Dte. | 12/S&WSD | 15/01/2024 | 198 | SULEKHA GHOSH | 0.94 | 0 | 0 | 15
3584 | PASCHIM MEDINIPUR | Midnapore Mechanical | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16542 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MURAKATA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | 499/W/MMD | 20/03/2023 | 804 | PADMA ENGINEERING CO. | 32.97 | 0 | 0 | 25
3585 | PASCHIM MEDINIPUR | Central Drilling | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16542 | New | Continuation for Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for office of the Store & Workshop Sub Division, Central Drilling Division, PHE Dte. | 157/S&WSD | 26/07/2024 | 184 | SULEKHA GHOSH | 0.87 | 0 | 0 | 0
3586 | PASCHIM MEDINIPUR | Midnapore Division | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16542 | New | Route survey & way leave permission along & across of National Highway in Murakata PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | 586/MD | 03/03/2025 | 21 | DONA ASSOCIATES | 8.74 | 0 | 0 | 0
3587 | PASCHIM MEDINIPUR | Central Drilling | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16542 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Murakata W/S Scheme (T/W-I, II & III), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | 1438/CDD | 26/09/2023 | 463 | PADMA ENGINEERING & CO. | 36.93 | 0 | 0 | 35
3588 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Chatra PWSS in the District of Paschim Medinipur under JJM programme. , SM/17758 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Chatra PWSS in the District of Paschim Medinipur under JJM programme. under JJM Program under MMD PHE Dte. | 1058/W/MMD | 29/03/2023 | 180 | S.S.GHORAI | 5.07 | 0 | 0 | 95
3589 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Mulgram PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17760 | Solarisation | Solarization of grid connected pumping installation Mulgram PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 989/W/MMD | 29/03/2023 | 180 | ABHIJIT MUKHERJEE | 6.25 | 0 | 0 | 90
3590 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Chakismilepur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17763 | Solarisation | Solarization of grid connected pumping installation Chakismilepur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 990/W/MMD | 29/03/2023 | 180 | ABHIJIT MUKHERJEE | 6.25 | 0 | 0 | 0
3591 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Dhaneswarpur (Dantan-II) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17765 | Solarisation | Solarization of grid connected pumping installation Dhaneswarpur (Dantan-II) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 982/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 80
3592 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Dhaneswarpur (Dantan-II) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17765 | Solarisation | Quotation for Application fee of Solar Power Plant 10 KW at PH-I of Dhaneshwarpur PWSS .Application No-2004583657, Ref Consumer ID-212392694,Biiling Type-NET BILLING, NAME OF CCC-KHAKURDA CCC, SCHEME CODE-SM/17765, BLOCK-DANTAN-II | BP-2023-24-650 | 09/02/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
3593 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Rajnagar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17766 | Solarisation | Solarization of grid connected pumping installation Rajnagar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 985/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
3594 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Satkui PWSS in the District of Paschim Medinipur under JJM programme. , SM/17785 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Satkui PWSS in the District of Paschim Medinipur under JJM programme.under JJM Program under MMD PHE Dte. | 1065/W/MMD | 29/03/2023 | 720 | BHABANI PRASAD MANNA | 11.02 | 0 | 0 | 55
3595 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Debhog PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17806 | Solarisation | Solarization of grid connected pumping installation Debhog PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 979/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
3596 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Debhog PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17806 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 720/MMSD-I | 07/06/2024 | 15 | SUBHASIS ROY | 2.29 | 0 | 0 | 100
3597 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18173 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Lakshipur & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | 665/MD | 08/04/2022 | 20 | SIRCON ENGINEERING SERVICES | 4.89 | 0 | 0 | 100
3598 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18173 | New | Material Requisition To Resource Division | 4055/MD | 12/10/2023 | 0 | Resource Division | 42.67 | 0 | 0 | 0
3599 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18173 | New | Material Requisition To Resource Division | 3328/MD | 25/11/2024 | 0 | Resource Division | 9.41 | 0 | 0 | 0
3600 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18173 | New | New service connection | 83/JMD | 12/02/2024 | 0 | WBSEDCL | 4.17 | 0 | 0 | 0
3601 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18173 | New | New Service connection charges. | 22/JMD | 11/01/2024 | 0 | WBSEDCL | 2.79 | 0 | 0 | 0
3602 | PASCHIM MEDINIPUR | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18173 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,522 Nos.) under JJM including Two years O&M with allied work for Lakshipur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 3238/MD | 11/09/2023 | 928 | UNIQUE AGENCY | 619.92 | 0 | 0 | 72
3603 | PASCHIM MEDINIPUR | Midnapore Mechanical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. , SM/18173 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at LAKSHIPUR Water supply scheme, Chandrakona -I block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 2282/W/MMD | 29/08/2023 | 306 | SUJOY RANJAN BHOWMICK | 30.18 | 0 | 0 | 95
3604 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dhengasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17384 | Solarisation | Solarization of grid connected pumping installation at Dhengasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 687/W/MMD | 23/03/2023 | 180 | GOENKA ENTERPRISE | 6.26 | 0 | 0 | 0
3605 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Palashi (Debra)PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17356 | Solarisation | Solarization of grid connected pumping installation at Palashi (Debra)PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 703/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 75
3606 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kurul PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17358 | Solarisation | Solarization of grid connected pumping installation at Kurul PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 784/W/MMD | 24/03/2023 | 180 | A.S.ENGINEERING | 6.25 | 0 | 0 | 40
3607 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kurul PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17358 | Solarisation | Quotation for Application Fee of Solar Power Plant 10 KW at PH-I of KURUL PWSS . Application No-2004602435, Ref Consumer ID-203432661, Billing Type-Net Billing, Name of CCC-Khakurda CCC. | BP-2023-24-731 | 26/02/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
3608 | PASCHIM MEDINIPUR | Midnapore Division | SATPATI AND ADJOINING MOUJAS PWSS , SM/18009 | New | Material Requisition To Resource Division | 1301/MD | 28/04/2023 | 0 | Resource Division | 34.69 | 0 | 0 | 0
3609 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SATPATI AND ADJOINING MOUJAS PWSS , SM/18009 | New | New service connection charges for Satpati w/s scheme, t/w no.II | 163/JMD | 31/05/2024 | 0 | WBSEDCL | 3.95 | 0 | 0 | 0
3610 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | SATPATI AND ADJOINING MOUJAS PWSS , SM/18009 | New | New service connection charges for Satpati w/s scheme, t/w no.-I | 162/JMD | 31/05/2024 | 0 | WBSEDCL | 3.36 | 0 | 0 | 0
3611 | PASCHIM MEDINIPUR | Central Drilling | SATPATI AND ADJOINING MOUJAS PWSS , SM/18009 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3612 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Goaltore PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17745 | Solarisation | Solarization of grid connected pumping installation Goaltore PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 974/W/MMD | 29/03/2023 | 180 | M/S EMMESS | 6.26 | 0 | 0 | 0
3613 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Paschim Pathari PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17369 | Solarisation | Solarization of grid connected pumping installation at Paschim Pathari PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 704/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
3614 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bhabaninagar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17374 | Solarisation | Solarization of grid connected pumping installation at Bhabaninagar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 681/W/MMD | 23/03/2023 | 180 | A-NIK & CO. | 6.26 | 0 | 0 | 0
3615 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bhabaninagar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17374 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 720/MMSD-I | 07/06/2024 | 15 | SUBHASIS ROY | 2.29 | 0 | 0 | 100
3616 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bhabaninagar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17374 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going solarisation / rejuvenation as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 716/MMSD-I | 07/06/2024 | 15 | MUKHERJEE ART CENTRE | 1.93 | 0 | 0 | 100
3617 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chaita PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17492 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
3618 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Goaltore PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17501 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
3619 | PASCHIM MEDINIPUR | Midnapore Division | NARMA AND ADJOINING MOUJAS PWSS , SM/18229 | New | Material Requisition To Resource Division | 1531/MD | 12/05/2023 | 0 | Resource Division | 73.62 | 0 | 0 | 0
3620 | PASCHIM MEDINIPUR | Midnapore Mechanical | NARMA AND ADJOINING MOUJAS PWSS , SM/18229 | New | Quotation for new power connection at Narma PWSS T/W no - II of Narayangarh block Application no - 2004754830 , Ref ID - 204323480 | BP-2024-25-338 | 25/06/2024 | 0 | WBSEDCL | 8.18 | 0 | 0 | 0
3621 | PASCHIM MEDINIPUR | Midnapore Mechanical | NARMA AND ADJOINING MOUJAS PWSS , SM/18229 | New | Quotation for new power connection at Narma PWSS P/H- I , application no - 2004609088 , Ref id - 204223723 | BP-2023-24-782 | 06/03/2024 | 0 | WBSEDCL | 3.45 | 0 | 0 | 0
3622 | PASCHIM MEDINIPUR | Central Drilling | NARMA AND ADJOINING MOUJAS PWSS , SM/18229 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3623 | PASCHIM MEDINIPUR | Midnapore Division | NARMA AND ADJOINING MOUJAS PWSS , SM/18229 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
3624 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Salboni PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17589 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
3625 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Amlagora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17520 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
3626 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Jatra Bansiriasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17525 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
3627 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Sutkujhuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17532 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
3628 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KEOT KHALISA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/17396 | Augmentation | Continuation Work Order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Keot Khalisha, Block - Mohanpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | 520/MD | 08/03/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 0.82 | 0 | 0 | 100
3629 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KEOT KHALISA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/17396 | Augmentation | Material Requisition To Resource Division | 1424/MD | 04/05/2023 | 0 | Resource Division | 8.94 | 0 | 0 | 0
3630 | PASCHIM MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KEOT KHALISA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/17396 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KEOT KHALISA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 1188/W/MMD | 25/04/2023 | 180 | M/S EMMESS | 23.77 | 0 | 0 | 52
3631 | PASCHIM MEDINIPUR | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KEOT KHALISA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. , SM/17396 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Soil investigation, Construction of 250 CuM OHR (Pile Foundation) & Accommodate FHTC (33 Nos.) under JJM with allied work for Augmentation Keot Khalisa PWSS in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 46/MD | 07/01/2025 | 180 | SAI TUBE CO. | 177.4 | 0 | 0 | 0
3632 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Nayagram PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17344 | Solarisation | Solarization of grid connected pumping installation at Nayagram PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 706/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
3633 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Nayagram PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17344 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 720/MMSD-I | 07/06/2024 | 15 | SUBHASIS ROY | 2.29 | 0 | 0 | 100
3634 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Nayagram PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17344 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going solarisation / rejuvenation as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | 716/MMSD-I | 07/06/2024 | 15 | MUKHERJEE ART CENTRE | 1.93 | 0 | 0 | 100
3635 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dantan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17321 | Solarisation | Solarization of grid connected pumping installation at Dantan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 685/W/MMD | 23/03/2023 | 180 | SUBHRA ENTERPRISE | 6.26 | 0 | 0 | 80
3636 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dantan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17321 | Solarisation | Quotation for Application fee of Solar Power Plant 10 KW at PH-II of Dantan PWSS. Application No-2004558445. Ref Consumer ID-212061369.Billing Type-NET BILLING. Name of CCC-Dantan CCC. SCHEME CODE-SM/17321 | BP-2023-24-631 | 08/02/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
3637 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system at Pirakata PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17452 | IOT | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | 6881/JMD | 05/09/2024 | 30 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
3638 | PASCHIM MEDINIPUR | Midnapore Division | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17559 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Jarisai & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | 1115/MD | 09/06/2022 | 20 | ENVIROTECH SOLUTIONS | 1.61 | 0 | 0 | 100
3639 | PASCHIM MEDINIPUR | Midnapore Division | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17559 | New | Material Requisition To Resource Division | 2005/MD | 16/05/2023 | 0 | Resource Division | 34.25 | 0 | 0 | 0
3640 | PASCHIM MEDINIPUR | Midnapore Division | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17559 | New | Material Requisition To Resource Division | 1463 | 08/05/2023 | 0 | Resource Division | 9.68 | 0 | 0 | 0
3641 | PASCHIM MEDINIPUR | Midnapore Mechanical | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17559 | New | Electrict quotation bill for TW-I of Jarisai pwss (Zone-I) (Ref Consumar ID-204310834),Application No-2004741317,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur. | BP-2024-25-201 | 24/05/2024 | 0 | WBSEDCL | 4.08 | 0 | 0 | 0
3642 | PASCHIM MEDINIPUR | Midnapore Mechanical | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17559 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | 1191/W/MMD | 25/04/2023 | 712 | GOENKA ENTERPRISE | 22.63 | 0 | 0 | 50
3643 | PASCHIM MEDINIPUR | Midnapore Division | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. , SM/17559 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 200 Cum & 300 Cum OHR (Intze type with Solid raft/ Pile Foundation) & Accommodate FHTC (6,605 Nos.) including Two years O&M under JJM with allied work for Jarisai PWSS (Zone-I & Zone-II) & Kashida (Zone-I & Zone-II) with in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 5360/MD | 30/11/2023 | 673 | GOBINDA MAITY | 2125.38 | 0 | 0 | 46
3644 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Suktajuri PWSS in the District of Paschim Medinipur under JJM programme. , SM/17820 | Augmentation | Electric quotation for Load enhancement at Tw no-I of Suktajuri water supply scheme. Consumer ID-200331905. |  | 22/05/2023 | 0 | WBSEDCL | 0.36 | 0 | 0 | 0
3645 | PASCHIM MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Suktajuri PWSS in the District of Paschim Medinipur under JJM programme. , SM/17820 | Augmentation | Rejuvenation of Electro-Mechanical components of Suktajuri PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | 1064/W/MMD | 29/03/2023 | 180 | TAPAN KUMAR SARKAR | 21.01 | 0 | 0 | 52
3646 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | Rejuvenation of Electro-Mechanical components of Suktajuri PWSS in the District of Paschim Medinipur under JJM programme. , SM/17820 | Augmentation | Repairing & rejuvenation of electro-mechanical accessories for Suktajuri W/S scheme Pump house no -2 in Garbeta II block under Jhargram Mechanical Division, PHE. Dte. | 7332/JMD | 19/11/2024 | 102 | TAPAN KUMAR SARKAR | 4.86 | 0 | 0 | 100
3647 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Manidaha PWSS under Midnapore Sadar Block in Paschim Medinipur District , SM/09703 | Retrofitting | Laying distribution pipe line, soil test and Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 350 CuM and staging height 20 mtr. as per approved drawing (No:- PC-I /OHR /12/2012 ) with allied works for Manidaha Water Supply Scheme within Medinipur Sadar Block including supply of all labour & materials under Midnapore Division, PHE Dte. | 2245/MD | 28/12/2021 | 180 | DIPAK KUMAR BAKLY | 230.53 | 0 | 0 | 70
3648 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Manidaha PWSS under Midnapore Sadar Block in Paschim Medinipur District , SM/09703 | Retrofitting | Retrofitting of Manidaha PWSS to accommodate FHTC in Midnapore Sadar block under Midnapore Division, P.H.E. Dte. | 873/MD | 10/05/2022 | 1146 | DIPAK KUMAR BAKLY | 46.8 | 0 | 0 | 60
3649 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I , SM/19102 | New | Material Requisition To Resource Division | 66/MD | 09/01/2023 | 0 | Resource Division | 54.01 | 0 | 0 | 0
3650 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I , SM/19102 | New | Material Requisition To Resource Division | 3442/MD | 25/11/2024 | 0 | Resource Division | 25.77 | 0 | 0 | 0
3651 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I , SM/19102 | New | QUOTATION MONEY FOR GOKULPUR MINI WATER SUPPLY SCHEME,ZONE-III, T W NO I [ LELUAKOLA ] ,JJM WORKS, SCHEME CODE SM/19102, APPLICATION NO 2004793778, REFERENCE ID 204340985, NIMPURA CCC, WBSEDCL | BP-2024-25-430 | 16/07/2024 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
3652 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I , SM/19102 | New | QUOTATION MONEY FOR GOKULPUR WATER SUPPLY SCHEME, ZONE-II, T W NO I [ KESHPAL] , JJM WORKS, SCHEME CODE SM/19102, APPLICATION NO 2004825721, REFERENCE ID 204360221, NIMPURA CCC, WBSEDCL | C082408994649 | 07/08/2024 | 0 | WBSEDCL | 4.01 | 0 | 0 | 0
3653 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I , SM/19102 | New | QUOTATION MONEY FOR GOKULPUR WATER SUPPLY SCHEME, ZONE-III, T W NO II [ WALIPUR] , JJM WORKS, SCHEME CODE SM/19102, BLOCK- KHARAGPUR-I, APPLICATION NO 2004831803, REFERENCE ID 204363828, NIMPURA CCC, WBSEDCL | C082408995334 | 07/08/2024 | 0 | WBSEDCL | 3.81 | 0 | 0 | 0
3654 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I , SM/19102 | New | Sinking of Tube Well, Laying distribution pipe line, Rising main, Pump House, Boundary wall, Soil investigation, Construction of 450 (Intze type with pile foundation) & 250 & 400 cum OHRs (Intze type with solid raft) & Accommodate FHTC (6,370 Nos.) including Two years O&M under JJM with allied work for (1) Gokulpur (Zone-I,II & III ) and (2) Risa & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | 2466/MD | 14/07/2023 | 1009 | GOBINDA MAITY | 1715.83 | 0 | 0 | 30
3655 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I , SM/19102 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, and III) and its adjoining mouzas, Block - Kharagpur-Iunder JJM Program under MMD PHE Dte. (Zone-III) | 3173/W/MMD | 18/12/2023 | 836 | RISHAV ENTERPRISE | 5.98 | 0 | 0 | 85
3656 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I , SM/19102 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-Iunder JJM Program under MMD PHE Dte. | 54/W/MMD | 15/01/2024 | 807 | M/S BARMAN ROY TRADERS | 25.52 | 0 | 0 | 75
3657 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I , SM/19102 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, and III) and its adjoining mouzas, Block - Kharagpur-Iunder JJM Program under MMD PHE Dte.(Zone-II) | 3172/W/MMD | 18/12/2023 | 540 | S.S.GHORAI | 22.89 | 0 | 0 | 100
3658 | PASCHIM MEDINIPUR | Midnapore Division | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19043 | New | Material Requisition To Resource Division | 1282/MD | 28/04/2023 | 0 | Resource Division | 190.54 | 0 | 0 | 0
3659 | PASCHIM MEDINIPUR | Midnapore Mechanical | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19043 | New | QUOTATION MONEY FOR SURATPUR WATER SUPPLY SCHEME, T W NO I JJM WORKS, SCHEME CODE SM/19043, APPLICATION NO 2004809647, REFERENCE ID 20352804, DASPUR CCC, WBSEDCL | BP-2024-25-490 | 30/07/2024 | 0 | WBSEDCL | 11.24 | 0 | 0 | 0
3660 | PASCHIM MEDINIPUR | Midnapore Mechanical | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19043 | New | QUOTATION MONEY FOR SURATPUR WATER SUPPLY SCHEME, T W NO II, JJM WORKS, SCHEME CODE SM/19043, APPLICATION NO 2004809619, REFERENCE ID 204352803, DASPUR CCC, WBSEDCL. | BP-2024-25-489 | 30/07/2024 | 0 | WBSEDCL | 4.78 | 0 | 0 | 0
3661 | PASCHIM MEDINIPUR | Midnapore Mechanical | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19043 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 3089/W/MMD | 29/11/2023 | 525 | GOENKA ENTERPRISE | 23.01 | 0 | 0 | 100
3662 | PASCHIM MEDINIPUR | Midnapore Division | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. , SM/19043 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,144 nos.) under JJM with allied work for Suratpur PWSS in Daspur- I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | 5514/MD | 15/12/2023 | 652 | MASUM ALI KHAN | 694.39 | 0 | 0 | 30
3663 | PASCHIM MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation Gobardhanpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17795 | Solarisation | Solarization of grid connected pumping installation Gobardhanpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 969/W/MMD | 29/03/2023 | 180 | RSA ENTERPRISE | 6.25 | 0 | 0 | 0
3664 | PASCHIM MEDINIPUR | Midnapore Division | AMLA BANI AND ITS ADJOINING MOUZAS PWSS , SM/18584 | New | Material Requisition To Resource Division | 61/MD | 09/01/2023 | 0 | Resource Division | 16.89 | 0 | 0 | 0
3665 | PASCHIM MEDINIPUR | Midnapore Mechanical | AMLA BANI AND ITS ADJOINING MOUZAS PWSS , SM/18584 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 1685/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.29 | 0 | 0 | 100
3666 | PASCHIM MEDINIPUR | Midnapore Mechanical | AMLA BANI AND ITS ADJOINING MOUZAS PWSS , SM/18584 | New | Fuel for Inspection Vehicle of covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission Program. [w.e.f. 01-01-2024 to 29-02-2024] | 1698/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.83 | 0 | 0 | 100
3667 | PASCHIM MEDINIPUR | Midnapore Division | AMLA BANI AND ITS ADJOINING MOUZAS PWSS , SM/18584 | New | Material Requisition To Resource Division | 3376/MD | 25/11/2024 | 0 | Resource Division | 14.49 | 0 | 0 | 0
3668 | PASCHIM MEDINIPUR | Midnapore Mechanical | AMLA BANI AND ITS ADJOINING MOUZAS PWSS , SM/18584 | New | Electric quotation bill for Tw No-II of Amla Bani PWSS. (Ref Consumer ID-204182328) | BP-2023-24-559 | 16/01/2024 | 0 | WBSEDCL | 2.93 | 0 | 0 | 0
3669 | PASCHIM MEDINIPUR | Midnapore Mechanical | AMLA BANI AND ITS ADJOINING MOUZAS PWSS , SM/18584 | New | Electric quotation bill for Tw No-I of Amla Bani PWSS (Ref Consumer ID-204182336) | BP-2023-24-560 | 16/01/2024 | 0 | WBSEDCL | 5.76 | 0 | 0 | 0
3670 | PASCHIM MEDINIPUR | Midnapore Mechanical | AMLA BANI AND ITS ADJOINING MOUZAS PWSS , SM/18584 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AMLA BANI AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | 1724/W/MMD | 09/08/2023 | 600 | K.S.P. ENTERPRISE | 25.24 | 0 | 0 | 20
3671 | PASCHIM MEDINIPUR | Midnapore Division | AMLA BANI AND ITS ADJOINING MOUZAS PWSS , SM/18584 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 350 cum OHR (Intze type with raft foundation) & Accommodate FHTC (2,353 nos.) under JJM with allied work for Amlabani PWSS in Keshpur Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | 3843/MD | 21/09/2023 | 905 | M/S. A.R. ENTERPRISE. | 1033.27 | 0 | 0 | 43
3672 | PASCHIM MEDINIPUR | Midnapore Mechanical | AMLA BANI AND ITS ADJOINING MOUZAS PWSS , SM/18584 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0 | 0 | 50
3673 | PASCHIM MEDINIPUR | Midnapore Division | BANKIBANDH AND ADJOINING MOUJAS PWSS , SM/13065 | New | Material Requisition To Resource Division | 1256/MD | 28/04/2023 | 0 | Resource Division | 23.45 | 0 | 0 | 0
3674 | PASCHIM MEDINIPUR | Central Drilling | BANKIBANDH AND ADJOINING MOUJAS PWSS , SM/13065 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3675 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Extension of laying of distribution UPVC pipe line in Gopalpur village Basti of Keshiary GP Within Keshiry W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | 114/AE/KSD | 09/03/2022 | 30 | NIMAI LAL GURIA | 2.55 | 0 | 0 | 100
3676 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Keshiary (Block- Keshiary) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1620/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.41 | 0 | 0 | 100
3677 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Keshiary (Block- Keshiary) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | 1621/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.87 | 0 | 0 | 100
3678 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Keshiary, Block - Keshiary) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-467 | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.24 | 0 | 0 | 0
3679 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Keshiary, Block - Keshiary) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | BP-2021-22-466 | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.76 | 0 | 0 | 0
3680 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Continuation Work order for the work Hiring of Bharat Stage- II/III / diesel motor cab (Luxury Taxi) / Maruti Omni (Standard Non-AC) having contract carriage permit from the regional transport authority for the Office of the Assistant Engineer, Kharagpur Sub- Division, P.H.E. Dte. [Period for 04.02.2022 to 20.03.2022] | 59/AE/KSD | 03/02/2022 | 45 | SANJIT SINHA | 0.25 | 0 | 0 | 0
3681 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Sinking of 1(one) No. 125mm X 80mm dia. & 150 Mtr. Depth Deep Tube well including construction of Community Storage Tank (2000 Ltr. Capacity) and Installation of Submersible pumping machineries etc. for Creation of drinking water source at Chandana village, vide J.L.No. -47, Plot No.-1530(near house of Dhananjoy Mandi), GP- Khajra, Block- Keshiary under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in Paschim Medinipur District. | 486/AE/KSD | 01/08/2022 | 30 | ASSOCIATED ENGINEERS & TRADERS | 4.41 | 0 | 0 | 0
3682 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Keshiary W/S Scheme with in Keshiary block under Midnapore Division, P.H.E. Dte. | 445/MD | 13/02/2023 | 30 | KISHORE GHOSH | 41.07 | 0 | 0 | 100
3683 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations under (1) Augmentation of Keshiary & its adjoining mouzas W/S Scheme within Keshiary block & (2) Augmentation of Satkui & its adjoining mouzas W/S Scheme within Kharagpur-I block in Paschim Medinipur District through Jadavpur University. | 471/MD | 15/02/2023 | 14 | JADAVPUR UNIVERSITY | 9.56 | 0 | 0 | 100
3684 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-III) | 936/W/MMD | 28/03/2023 | 180 | EMCON | 11.49 | 0 | 0 | 0
3685 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Material Requisition To Resource Division | 138/MD | 11/01/2023 | 0 | Resource Division | 29.36 | 0 | 0 | 0
3686 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Material Requisition To Resource Division | 3988/MD | 06/10/2023 | 0 | Resource Division | 29.18 | 0 | 0 | 0
3687 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Electric quotation bill for Ad Tw no-IV of Keshiary PWSS. (Ref Consumer ID-204117417) | BP-2023-24-329 | 03/11/2023 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
3688 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Electric quotation bill for Ad Tw no-III of Keshaiary PWSS . Ref Consumer ID-204117416) | BP-2023-24-328 | 03/11/2023 | 0 | WBSEDCL | 4.24 | 0 | 0 | 0
3689 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-II) | 866/W/MMD | 27/03/2023 | 180 | S.S.GHORAI | 23.01 | 0 | 0 | 20
3690 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | ADDITIONAL QUOTATION FOR SHIFTING OF LTOH AT CENTRAL BUS STAND PH NO-III OF KESHIARY PWSS, REFERENCE ID-860319179,APPLICATION ID-100000125209, APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC-KESHAIRY CCC, NAME OF BLOCK- KESHIARY. |  | 18/12/2024 | 0 | WBSEDCL | 0.92 | 0 | 0 | 0
3691 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Laying distribution pipe line, Soil test and Construction of R.C.C. Over Head Reservoir of capacity 200 Cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Keshiary & its adjoining mouzas Water Supply Scheme to accomodate FHTC within Keshiary Block under Kharagpur Sub-Division of Midnapore Division, P.H.E.Dte. Dist. Paschim Medinipur. | 1734/MD | 23/08/2022 | 1292 | M/S. A.R. ENTERPRISE. | 601.47 | 0 | 0 | 80
3692 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | 2295/W/MMD | 29/12/2022 | 883 | BUSR ENGINEERING | 22.99 | 0 | 0 | 20
3693 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Laying of Rising Main pipe line and construction 2 (two) nos. Pump house for Augmentation of Keshiary & its adjoining mouzas W/S Scheme under JJM within Keshiary block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. within the District of Paschim Medinipur. | 449/MD | 13/02/2023 | 878 | M/S. A.R. ENTERPRISE. | 13.49 | 0 | 0 | 0
3694 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Hiring of Bharat Stage- IV/V diesel motor cab (Luxury Taxi) (Standard Non-AC) having contract carriage permit from the regional transport authority for the Office of the Assistant Engineer, Kharagpur Sub- Division, P.H.E. Dte. ( For 12 MONTH )[ Perion fro 23.03.2023 to 22.03.2024] | 342/1/AE/KSD | 23/03/2023 | 366 | M/S. SOMNATH | 1.35 | 0 | 0 | 100
3695 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Laying of distribution pipeline for left out node and to provide FHTC for Augmentation of Keshiary Piped Water Supply Scheme under Keshiary block within Midnapore Division, PHE Dte. | 2844/MD | 09/09/2024 | 420 | A-PLUS | 59.9 | 0 | 0 | 50
3696 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Continuation Work order Hiring of Bharat Stage - IV/VI Diesel Motor Cabs (Standard), having contract Carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Kharagpur Sub-Division, P.H.E. Dte. for the period (23.09.2024 to 31.12.2024) Vehicle No-WB 05 9394 | 519/AE/KSD | 23/09/2024 | 100 | M/S. SOMNATH | 0.56 | 0 | 0 | 0
3697 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. , SM/10124 | Augmentation | Cleaning the Chokage of pipe in the existing line at Keshiary PWSS under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | 3581/MD | 06/12/2024 | 30 | MAMPI ENTERPRISE | 4.59 | 0 | 0 | 100
3698 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/19051 | Augmentation | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | 1685/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.29 | 0 | 0 | 100
3699 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/19051 | Augmentation | Fuel for Inspection Vehicle of covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission Program. [w.e.f. 01-01-2024 to 29-02-2024] | 1698/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.83 | 0 | 0 | 100
3700 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/19051 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing Dherua PWSS within Midnapore Sadar Block under Midnapore Division P.H.E. Dte. | 2191/MD | 01/11/2022 | 21 | UMWELT ENGINEER PVT. LTD. | 16.52 | 0 | 0 | 100
3701 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/19051 | Augmentation | Quotation for service connection(Ref ID: 204307608, Application No: 2004733766) for Dherua Augmentation Zone-ii(BHatpara SSK) (SM/19051) under Pirakata CCC,WBSEDCL | BP-2024-25-280 | 14/06/2024 | 0 | WBSEDCL | 0.54 | 0 | 0 | 0
3702 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/19051 | Augmentation | Providing and Installation of pumping machineries and other electromechanical equipments for Augmentation of Dherua and its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | 3101/W/MMD | 29/11/2023 | 540 | DEBJYOTI BASU | 90.58 | 0 | 0 | 30
3703 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/19051 | Augmentation | Sinking of Tube Well, Construction of RCC OHR (250 Cum & 100 Cum Capacity), Boundary Wall, Pump House and GLR (35 Cum & 75 Cum Capacity) to accommodate FHTC (1,140 Nos) under JJM for Piped Water Supply Scheme under JJM with allied work for Augmentation of Dherua W/S Scheme in Medinipur Sadar Block under Midnapore Sadar Sub Division under Midnapore Division, PHE Dte. | 2034/MD | 01/07/2024 | 360 | M/S. MALLIK CONSTRUCTION | 964.38 | 0 | 0 | 30
3704 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. , SM/19051 | Augmentation | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0 | 0 | 50
3705 | PASCHIM MEDINIPUR | Midnapore Division | BAJGERYA AND ITS ADJOINING MOUZAS PWSS , SM/18658 | New | Material Requisition To Resource Division | 3986/MD | 06/10/2023 | 0 | Resource Division | 33.31 | 0 | 0 | 0
3706 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAJGERYA AND ITS ADJOINING MOUZAS PWSS , SM/18658 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAJGERYA AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | 1725/W/MMD | 09/08/2023 | 180 | B.P.TRADING CORPORATION | 25.26 | 0 | 0 | 20
3707 | PASCHIM MEDINIPUR | Midnapore Division | BAJGERYA AND ITS ADJOINING MOUZAS PWSS , SM/18658 | New | Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 350 Cum (Intze type with Pile Foundation) & Accommodate FHTC (2904 Nos.) including Two years O&M under JJM with allied work for Bajgerya & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials including 02(Two) Years Operation & Mainatanance within Midnapur Sadar Sub-Division under Midnapore Division, PHE Dte. | 2008/MD | 28/06/2024 | 180 | M/S. EL-CON | 971.71 | 0 | 0 | 0
3708 | PASCHIM MEDINIPUR | Midnapore Division | BAJGERYA AND ITS ADJOINING MOUZAS PWSS , SM/18658 | New | Sinking of 1 (One) No. Tube well for Bajgerya & its adjoining mouzas PWSS in Keshpur block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. [Part-II] | 2579/MD | 22/08/2024 | 15 | MANNA COMPUTER | 8.3 | 0 | 0 | 0
3709 | PASCHIM MEDINIPUR | Midnapore Division | BAJGERYA AND ITS ADJOINING MOUZAS PWSS , SM/18658 | New | Sinking of 1 (One) No. Tube well for Bajgerya & its adjoining mouzas PWSS in Keshpur block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. [Part-I] | 2814/MD | 07/08/2023 | 15 | RUPKUMAR KARMAKAR | 8.3 | 0 | 0 | 100
3710 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAJGERYA AND ITS ADJOINING MOUZAS PWSS , SM/18658 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF BAJGERYA PWSS. REF CONSUMER ID-204325522, APPLICATION NO-2004767121, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | BP-2024-25-291 | 18/06/2024 | 0 | WBSEDCL | 5.83 | 0 | 0 | 0
3711 | PASCHIM MEDINIPUR | Midnapore Mechanical | BAJGERYA AND ITS ADJOINING MOUZAS PWSS , SM/18658 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
3712 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. , SM/19037 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at BURAL Water supply scheme, Sabang block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 59/W/MMD | 15/01/2024 | 180 | M/S. SAJAHAN CHOWDHURY | 47.41 | 0 | 0 | 40
3713 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. , SM/19037 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing Bural PWSS within Sabang Block under Midnapore Division P.H.E. Dte. | 2048/MD | 28/09/2022 | 21 | GOBINDA MAITY | 10.93 | 0 | 0 | 100
3714 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. , SM/19037 | Augmentation | QUOTATION MONEY FOR BURAL WATER SUPPLY SCHEME, T W NO 4 / ZONE-I [ KERUR ] , JJM WORKS, SCHEME CODE SM/19037, APPLICATION NO 2004884722, REFERENCE ID 204391136, SABANG CCC, WBSEDCL | BP-2024-25-696 | 27/09/2024 | 0 | WBSEDCL | 5.62 | 0 | 0 | 0
3715 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. , SM/19037 | Augmentation | QUOTATION MONEY FOR BURAL WATER SUPPLY SCHEME, ZONE-I, T W -III, [ GUNDUT ] JJM WORKS, SCHEME CODE SM/19037, APPLICATION NO 2004884758, REFERENCE ID 204391138, SABANG CCC, WBSEDCL | C112422745630 | 18/11/2024 | 0 | WBSEDCL | 6.87 | 0 | 0 | 0
3716 | PASCHIM MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. , SM/19037 | Augmentation | QUOTATION MONEY FOR BURAL WATER SUPPLY SCHEME, AUGMENTATION , ZONE-II, T W 4, JJM WORKS, SCHEME CODE SM/19037, APPLICATION NO 2004923771, REFERENCE ID 204414194, SABANG CCC, WBSEDCL | BP-2024-25-784 | 12/11/2024 | 0 | WBSEDCL | 7.05 | 0 | 0 | 0
3717 | PASCHIM MEDINIPUR | Midnapore Division | NERASOL AND ADJOINING MOUJAS PWSS , SM/13103 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
3718 | PASCHIM MEDINIPUR | Midnapore Division | NERASOL AND ADJOINING MOUJAS PWSS , SM/13103 | New | Material Requisition To Resource Division | 1158/MD | 25/04/2023 | 0 | Resource Division | 64.6 | 0 | 0 | 0
3719 | PASCHIM MEDINIPUR | Jhargram Mechanical Division | NERASOL AND ADJOINING MOUJAS PWSS , SM/13103 | New | NEW SERVICE CONNECTION CHARGES AT NERASOLE-II WATER SUPPLY SCHEME | 262/JMD | 23/07/2024 | 0 | WBSEDCL | 5.29 | 0 | 0 | 0
3720 | PASCHIM MEDINIPUR | Central Drilling | NERASOL AND ADJOINING MOUJAS PWSS , SM/13103 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3721 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Construction of Pump House, Boundary wall & Accommodate FHTC (842 nos.) under JJM in (Zone-I) for Proposed Mohar-Katina (Zone-I & II) PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-E] | 2803/MD | 07/08/2023 | 60 | SHAKEEL KHAN | 64.42 | 0 | 0 | 0
3722 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Construction of Pump House, Boundary wall & Accommodate FHTC (568 nos.) under JJM with allied work for Mohar-Katina (Zone-II) PWSS in Sabang block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-F] | 2806/MD | 07/08/2023 | 60 | NUTAN BAZAR ENGINEER,S CO-OPERATIVE SOCIETY LTD. | 48.67 | 0 | 0 | 0
3723 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Laying distribution pipe line & Accommodate FHTC (200 nos.) under JJM with allied work for Proposed Mohar-Katina (Zone-II) PWSS in Sabang. Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-C] | 3051/MD | 23/08/2023 | 30 | JOY GURU TRADING | 33.64 | 0 | 0 | 0
3724 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Material Requisition To Resource Division | 199/MD | 16/01/2023 | 0 | Resource Division | 45.97 | 0 | 0 | 0
3725 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Laying distribution pipe line & Accommodate FHTC (400 nos.) under JJM with allied work for Proposed Mohar-Katina (Zone-II) PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-A] | 2804/MD | 07/08/2023 | 844 | SANKAR PRASAD MAITY | 64.97 | 0 | 0 | 40
3726 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang.under JJM Program under MMD PHE Dte. | 1726/W/MMD | 09/08/2023 | 180 | DAS ENTERPRISE | 47.42 | 0 | 0 | 30
3727 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Laying of Distribution Pipe Line and FHTC (1182 nos.) work including 2 (Two) years O&M for Proposed Mohar-Katina & its adjoining Mouzas (Zone-I) PWSS, Block- Sabong, Dist: - Paschim Medinipur under Midnapore Division, PHE Dte. [PART-D] | 2119/MD | 09/07/2024 | 60 | BHUWALKA DEVELOPMENTS PRIVATE LIMITED | 228.56 | 0 | 0 | 0
3728 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Sinking of 2 (Two) nos. 250 X 150 X 170 mtr. depth deep Tube well (Zone-I) for Proposed Mohar- Katina & its adjoining mouzas PWSS, Block- Sabong, Dist:- Paschim Medinipur under Midnapur Division, PHE Dte. [PART-A] | 2802/MD | 07/08/2023 | 21 | MANISHIKA CONSTRUCTION | 16.89 | 0 | 0 | 50
3729 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Sinking of 2 (Two) Nos. 200 X 100 X 170 mtr. depth deep Tube well (Zone-II) for Proposed Mohar-Katina & its adjoining mouzas (Zone-I & II) PWSS, Block- Sabong Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-E] | 2801/MD | 07/08/2023 | 21 | MANNA COMPUTER | 13.54 | 0 | 0 | 100
3730 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | QUOTATION MONEY FOR MOHAR-KATINA WATER SUPPLY SCHEME, T W NO I, [ KATINA] , JJM WORKS, SCHEME CODE SM/18620, APPLICATION NO 2004806819, REFERENCE ID 204348010, SABANG CCC, WBSEDCL | BP-2024-25-422 | 15/07/2024 | 0 | WBSEDCL | 6.29 | 0 | 0 | 0
3731 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | QUOTATION MONEY FOR MOHAR-KATINA WATER SUPPLY SCHEME, T W NO I, [ MOHAR ] , JJM WORKS, SCHEME CODE SM/18620, APPLICATION NO 2004806860, REFERENCE ID 204348023, SABANG CCC, WBSEDCL | BP-2024-25-421 | 15/07/2024 | 0 | WBSEDCL | 5.53 | 0 | 0 | 0
3732 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Laying distribution pipe line & Accommodate FHTC (300 nos.) under JJM with allied work for Proposed Mohar-Katina (Zone-II) PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-B] | 2805/MD | 07/08/2023 | 726 | SANKAR PRASAD MAITY | 73.64 | 0 | 0 | 50
3733 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Laying Rising Main & distribution of Pipe line, Construction of Pump House and Boundary wall and FHTC (786 nos.) work for Proposed Mohar-Katina & its adjoining Mouzas (Zone-I) PWSS, Block- Sabong, Dist: - Paschim Medinipur under Midnapore Division, PHE Dte. [PART-C] | 3903/MD | 27/09/2023 | 724 | M/S. D.K.H.CONSTRUCTION | 241.34 | 0 | 0 | 75
3734 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Laying distribution pipe line, Pump House, Boundary wall & Accommodate FHTC (430 nos.) including 2 (Two) years O&M under JJM with allied work for Proposed Mohar-Katina (Zone-II) PWSS in Sabang. Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-D] | 5098/MD | 30/10/2023 | 548 | SAI TUBE CO. | 170.59 | 0 | 0 | 40
3735 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Construction and Commissioning of 2 Nos. O.H.R [400 CuM capacity & 300 CuM Capacity (Both Intze type with pile)] & LDS (Zone-II) for Proposed Mohar-Katina & its adjoining Mouzas (Zone-I & II) PWSS, Block- Sabong, Dist: - Paschim Medinipur under Midnapur Division, PHE Dte. [PART-B] | 2118/MD | 09/07/2024 | 480 | JAY MATA DI ENTERPRISE | 244.46 | 0 | 0 | 0
3736 | PASCHIM MEDINIPUR | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. , SM/18620 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
3737 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Bar Kashimpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. [Name of Proposed PWSS Makarampur & its adjoining Mouzas PWSS instead of Bar Kashimpur & its adjoining Mouzas PWSS] | 1061/MD | 02/06/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.26 | 0 | 0 | 0
3738 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Rabidaspur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. [Name of proposed PWSS - (1) Rabidaspur & its adjoining Mouzas PWSS, (2) Tiorberya & its adjoining Mouzas PWSS & (3) Ramchandrapur & its adjoining Mouzas PWSS instead of Rabidaspur & its adjoining Mouzas PWSS]. | 1066/MD | 02/06/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.72 | 0 | 0 | 0
3739 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 108; 110; 111; 116; 118; 119; 120; 121; 122; 123; 124; 125; 197; 198; 199; 200; 201; 202; 206; 207 ;208 ;209] (Population as per 2011 Census: 18,226) [PART-II] | 1601/MD | 02/08/2022 | 20 | GOBINDA MAITY | 10.54 | 0 | 0 | 0
3740 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 12; 13; 14; 15; 16; 17; 18; 19; 20; 21; 22; 23; 24; 25; 26; 27; 28; 29; 30; 31; 32; 33; 34; 35; 36; 37; 38; 39; 40; 41; 42; 45 (50%); 46; 47; 48; 49; 50; 51; 52; 53; 54; 56; 65; 67] (Population as per 2011 Census : 18,719) [PART-III] | 1602/MD | 02/08/2022 | 20 | GOBINDA MAITY | 10.82 | 0 | 0 | 0
3741 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 184; 246; 247; 254; 255; 256; 257; 258; 259; 260; 261; 262; 263] (Population as per 2011 Census: 14,366) [PART-V] | 1604/MD | 02/08/2022 | 20 | GOBINDA MAITY | 8.31 | 0 | 0 | 0
3742 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 1; 2; 3; 4; 5; 6; 7; 8; 9; 10; 11; 55; 57; 58; 59; 60; 61; 62; 63; 89; 90; 91; 92; 93; 94; 95; 96; 97; 98; 99; 100; 101; 102; 103; 104; 105; 106; 107; 108; 109; 110; 111; 112; 113; 114; 115; 117; 126; 127; 128; 129; 130; 134; 136; 137; 138 & 139] (Population as per 2011 Census : 30,848) | 2062/MD | 30/09/2022 | 15 | GOBINDA MAITY | 17.83 | 0 | 0 | 0
3743 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 45(50%), 43, 44, 87, 149, 66; 85; 86; 145; 146; 147; 148; 150; 152; 153; 185; 187] (Population as per 2011 Census : 13,852) [PART-VIII] | 1693/MD | 16/08/2022 | 45 | GOBINDA MAITY | 7.52 | 0 | 0 | 0
3744 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Ranichak & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | 497/MD | 15/03/2022 | 20 | GOBINDA MAITY | 6.21 | 0 | 0 | 0
3745 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Ramkrishnapur & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | 510/MD | 16/03/2022 | 20 | SIRCON ENGINEERING SERVICES | 6.64 | 0 | 0 | 0
3746 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Jot Kanuramgar & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | 511/MD | 16/03/2022 | 20 | SIRCON ENGINEERING SERVICES | 7.13 | 0 | 0 | 0
3747 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Ramkrishnapur & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | 666/MD | 08/04/2022 | 20 | SIRCON ENGINEERING SERVICES | 7.11 | 0 | 0 | 0
3748 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Purshuri & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | 668/MD | 08/04/2022 | 20 | SIRCON ENGINEERING SERVICES | 6.25 | 0 | 0 | 0
3749 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Krishnapur & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | 1007/MD | 27/05/2022 | 20 | SIRCON ENGINEERING SERVICES | 7.38 | 0 | 0 | 0
3750 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kalla & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | 1016/MD | 27/05/2022 | 20 | SIRCON ENGINEERING SERVICES | 6.87 | 0 | 0 | 0
3751 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Khandanga & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | 1017/MD | 27/05/2022 | 20 | SIRCON ENGINEERING SERVICES | 7.91 | 0 | 0 | 0
3752 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Benai & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | 686/MD | 12/04/2022 | 20 | GOBINDA MAITY | 10.01 | 0 | 0 | 0
3753 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Garurna & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | 690/MD | 13/04/2022 | 20 | GOBINDA MAITY | 9.65 | 0 | 0 | 0
3754 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kashinathpur & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | 691/MD | 13/04/2022 | 20 | GOBINDA MAITY | 5.48 | 0 | 0 | 0
3755 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Khukudaha & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | 692/MD | 13/04/2022 | 20 | GOBINDA MAITY | 7.69 | 0 | 0 | 0
3756 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Katina & its adjoining Mouzas PWSS, Block - Sabang under Midnapore Division, PHE Dte. | 693/MD | 13/04/2022 | 20 | GOBINDA MAITY | 10.1 | 0 | 0 | 0
3757 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Mahespur & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | 1022/MD | 30/05/2022 | 20 | SIRCON ENGINEERING SERVICES | 5.27 | 0 | 0 | 0
3758 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Piardanga & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | 1019/MD | 27/05/2022 | 20 | SIRCON ENGINEERING SERVICES | 5.88 | 0 | 0 | 0
3759 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Chanipat & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | 674/MD | 11/04/2022 | 20 | GOBINDA MAITY | 9.45 | 0 | 0 | 0
3760 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Sagarpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | 1054/MD | 02/06/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.35 | 0 | 0 | 0
3761 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Tatarpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | 1062/MD | 02/06/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 7.2 | 0 | 0 | 0
3762 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Suratpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | 1063/MD | 02/06/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.99 | 0 | 0 | 0
3763 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Haridharpur & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | 1023/MD | 30/05/2022 | 20 | SIRCON ENGINEERING SERVICES | 6.92 | 0 | 0 | 0
3764 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Jadabpur & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | 685/MD | 12/04/2022 | 20 | GOBINDA MAITY | 10.25 | 0 | 0 | 0
3765 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Uttar Bar & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | 688/MD | 13/04/2022 | 20 | GOBINDA MAITY | 11.78 | 0 | 0 | 0
3766 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 211; 212; 213; 214; 215; 228; 229; 230; 231] (Population as per 2011 Census: 8,961) [PART-I] | 1600/MD | 02/08/2022 | 20 | GOBINDA MAITY | 5.18 | 0 | 0 | 0
3767 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 156; 157; 158; 159; 160; 161; 162; 163; 164; 165; 166; 167; 168; 169; 170; 171; 172; 174; 177; 178; 179; 180; 181; 182; 183] (Population as per 2011 Census : 16,311) [PART-IV] | 1603/MD | 02/08/2022 | 20 | GOBINDA MAITY | 9.43 | 0 | 0 | 0
3768 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 337; 338; 339; 340; 341; 342; 343; 344; 273; 274; 275 & 248; 249; 250; 251; 252; 253; 290; 291; 292; 293; 294; 295; 296; 297; 298; 299; 300; 301; 333; 334; 335; 336] (Population as per 2011 Census 15,869) [PART-VI] | 1605/MD | 02/08/2022 | 30 | GOBINDA MAITY | 9.17 | 0 | 0 | 0
3769 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kenchkapur & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | 2679/MD | 30/12/2022 | 20 | SIRCON ENGINEERING SERVICES | 6.25 | 0 | 0 | 0
3770 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of 2 (Two) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Bandipur & its adjoining Mouzas PWSS AND (2) Dhanyagachhi & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | 2680/MD | 30/12/2022 | 30 | SIRCON ENGINEERING SERVICES | 9.89 | 0 | 0 | 0
3771 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of 3 (Three) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Gohaldanga & its adjoining Mouzas PWSS (2) Pirchak & its adjoining Mouzas PWSS & (3) Dwarkhola Mouza Stand Alone PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | 2675/MD | 30/12/2022 | 45 | SIRCON ENGINEERING SERVICES | 6.19 | 0 | 0 | 0
3772 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of 2 (Two) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Hrisingpur & its adjoining Mouzas PWSS AND (2) Dhunrabila & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | 2676/MD | 30/12/2022 | 30 | SIRCON ENGINEERING SERVICES | 7.92 | 0 | 0 | 0
3773 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kuapur & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | 2677/MD | 30/12/2022 | 20 | SIRCON ENGINEERING SERVICES | 6.18 | 0 | 0 | 0
3774 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Jhakra & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | 2678/MD | 30/12/2022 | 20 | SIRCON ENGINEERING SERVICES | 5.8 | 0 | 0 | 0
3775 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 69; 70; 71; 72; 73; 74; 75; 76; 77; 78; 79; 80; 81; 82; 83; 84; 154; 155; 173; 175; 176 & 264; 265; 266; 267; 268; 269; 270; 271; 272; 276; 277; 278; 279; 280; 281; 282; 283; 284; 285; 286; 287; 288; 289] (Population as per 2011 Census: 16,781) [PART-VII] | 1692/MD | 16/08/2022 | 30 | GOBINDA MAITY | 9.7 | 0 | 0 | 0
3776 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Manikkundu & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | 684/MD | 12/04/2022 | 20 | GOBINDA MAITY | 6.02 | 0 | 0 | 0
3777 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Preparation of D.P.R (Consultancy work) in connection with the functional house hold connection Proposed Dadpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. [Name of Proposed PWSS Gopalnagar & its adjoining Mouzas PWSS instead of Dadpur & its adjoining Mouzas PWSS] | BP-2023-24-376 | 10/10/2023 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.01 | 0 | 0 | 0
3778 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Suratpur & its adjoining Mouzas PWSS Block - Daspur-I under Midnapore Division, PHE Dte. | 1264/MD | 23/06/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.35 | 0 | 0 | 100
3779 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Sagarpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | 1268/MD | 23/06/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.48 | 0 | 0 | 100
3780 | PASCHIM MEDINIPUR | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL , SM/14107 | Support-M&E | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for proposed Makrampur & its adjoining Mouzas PWSS instead Kashimpur & its adjoining Mouzas PWSS, Block ¿ Daspur-I under Midnapore Division, PHE Dte. | 1261/MD | 23/06/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.34 | 0 | 0 | 100
3781 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 2 (Two) Nos Laboratory Personnel ( One Chemist / Bacteriologist & One Laboratory Assistant ) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for 01 (One)No. Bikini Nischintapur Sub - District Laboratary within Kharagpur Sub-Division under Midnapore Division, P.H.E. Dte. (For the period 01.10.2021 to 30.09.2022 ) | 433/AE/KSD | 30/09/2021 | 12 | ARUNALOY SCIENTIFIC HOUSE | 3.62 | 0 | 0 | 0
3782 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 2 (two) nos. Laboratory personal (one Chemist/Bacteriologist & One Laboratory Assistant) for regular analysis , testing and monitoring of water samples and others allied minor Mtc. works for Chandrakona Sub-District Laboratory within MidnaporeSadar Sub-Division under Midnapore Division PHE Dte. .(For the period of 12 (twelve) months starting from October-2021) (SL No-02) | 534/1/AE/MSSD | 30/09/2021 | 365 | UTSAV AGENCY | 3.62 | 0 | 0 | 0
3783 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 2 (Two) Nos Laboratory Personnel ( One Chemist / Bacteriologist & One Laboratory Assistant ) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for 01 (One)No. Belda Sub - District Laboratary within Kharagpur Sub-Division under Midnapore Division, P.H.E. Dte. (For the period 01.10.2021 to 30.09.2022 ) | 431/AE/KSD | 30/09/2021 | 12 | MASUM ALI KHAN | 3.62 | 0 | 0 | 0
3784 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 2 (Two) Nos Laboratory Personnel ( One Chemist / Bacteriologist & One Laboratory Assistant ) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for 01 (One)No. DATAN Sub - District Laboratary within Kharagpur Sub-Division under Midnapore Division, P.H.E. Dte. (For the period 01.10.2021 to 30.09.2022 ) | 432/AE/KSD | 30/09/2021 | 12 | GOBINDA MAITY | 3.62 | 0 | 0 | 0
3785 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 2 (two) nos. Laboratory personal (one Chemist/Bacteriologist & One Laboratory Assistant) for regular analysis , testing and monitoring of water samples and others allied minor Mtc. works for Garhbeta Sub-District Laboratory within Midnapore Sadar Sub-Division ,under Midnapore Division PHE Dte.(For the period of 12 (twelve) months starting from October-2021) (SL No-01) | 536/AE/MSSD | 30/09/2021 | 12 | UTSAV AGENCY | 3.62 | 0 | 0 | 0
3786 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 2 (Two) Nos Laboratory Personnel ( One Chemist / Bacteriologist & One Laboratory Assistant ) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for 01 (One)No. Keshiary Sub - District Laboratary within Kharagpur Sub-Division under Midnapore Division, P.H.E. Dte. (For the period 01.10.2021 to 30.09.2022 ) | 430/AE/KSD | 30/09/2021 | 12 | GOBINDA MAITY | 3.62 | 0 | 0 | 0
3787 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 2 (Two) Nos Laboratory Personnel ( One Chemist / Bacteriologist & One Laboratory Assistant ) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for 01 (One)No. Balichak Sub - District Laboratary within Kharagpur Sub-Division under Midnapore Division, P.H.E. Dte. (For the period 01.10.2021 to 30.09.2022 ) | 429/AE/KSD | 30/09/2021 | 12 | GOBINDA MAITY | 3.62 | 0 | 0 | 0
3788 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 3 (Three) Nos. Laboratory Personnel (One Chemist, One Bacteriologist & One Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Kharagpur Sub-District Laboratory within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [For the period of 12 (Twelve) months i.e. from 01.10.2021 to 30.09.2022] | 1689/MD | 30/09/2021 | 365 | CANVAS | 5.15 | 0 | 0 | 0
3789 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 01 no. Sampling Assistant each at 1) Chondrakona Road Sub-District Lab, 2) Chondrakona Town Sub-District Lab & 3) Gidni Sub-District Lab for collecting the water sample from different sources and other allied works under Midnapore Division, P.H.E. Dte. [For the period 12 Months i.e. from 01/10/2021 to 30/09/2022] | 360/RWS/MID | 30/09/2021 | 12 | GOBINDA MAITY | 4.2 | 0 | 0 | 0
3790 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 01 no. Sampling Assistant each at 1) Belda Sub-District Lab, 2) Keshiary Sub-District Lab for collecting the water sample from different sources and other allied works for & 01 no. Lab Attendent at 3) Balichak Sub-District Lab under Midnapore Division, P.H.E. Dte. [For the period 12 Months i.e. from 01/10/2021 to 30/09/2022] | 361/RWS/MID | 30/09/2021 | 12 | GOBINDA MAITY | 4.12 | 0 | 0 | 0
3791 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 2 (Two) Nos Laboratory Personnel ( One Chemist / Bacteriologist & One Laboratory Assistant ) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for 1 (One) No. Ghatal Sub- District Laboratary within Ghatal Sub-Division under Midnapore Division, P.H.E. Dte.[For the period of 12 (Twelve) months starting from 01/10/2021 to 30/09/2022] | 705./AE/GSD | 30/09/2021 | 365 | UTSAV AGENCY | 3.62 | 0 | 0 | 0
3792 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 2 (Two) Nos Laboratory Personnel ( One Chemist / Bacteriologist & One Laboratory Assistant ) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for 1 (One) No. Ghatal Sub- District Laboratary within Ghatal Sub-Division under Midnapore Division, P.H.E. Dte.[For the period of 12 (Twelve) months starting from 01/10/2021 to 30/09/2022] | 705/AE/GSD | 30/09/2021 | 365 | UTSAV AGENCY | 3.62 | 0 | 0 | 0
3793 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Engagement of 2 (Two) Nos Laboratory Personnel ( One Chemist / Bacteriologist & One Laboratory Assistant ) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for 1 (One) No. Chandrakona Sub-District Laboratary within Ghatal Sub-Division under Midnapore Division, P.H.E. Dte. .[For the period of 12 (Twelve) months starting from 01/10/2021 to 30/09/2022] | 706./AE/GSD | 30/09/2021 | 365 | UTSAV AGENCY | 3.62 | 0 | 0 | 0
3794 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill for the month of June to December 2022. |  | 03/02/2023 | 0 | SARBIK GRAM BIKASH KENDRA | 2.31 | 0 | 0 | 0
3795 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Laboratory Maintenance Bill for Abash Saradamoyee Unnayn Parishad. | BP-2023-24-162 | 19/07/2023 | 0 | ABASH SARADAMOY UNNAYN PARISHAD | 0.75 | 0 | 0 | 0
3796 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Laboratory Maintenance KANGSABATI GUCHHA SAMITY | BP-2023-24-165 | 19/07/2023 | 0 | SARBIK GRAM BIKASH KENDRA | 0.75 | 0 | 0 | 0
3797 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Maintenance bill of NGO manage laboratory. | BP-2023-24-327 | 21/09/2023 | 0 | PALLIMANGAL GUCHHA SAMITY | 1.35 | 0 | 0 | 0
3798 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Maintenance bill of NGO manage laboratory. | BP-2023-24-329 | 21/09/2023 | 0 | KANGSABATI GUCHHA SAMITY | 1.35 | 0 | 0 | 0
3799 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill for the month of June to December 2022. | BP-2022-23-585 | 08/02/2023 | 0 | KANGSABATI GUCHHA SAMITY | 2.31 | 0 | 0 | 0
3800 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill for the month of June to December 2022. | BP-2022-23-587 | 08/02/2023 | 0 | PALLIMANGAL GUCHHA SAMITY | 2.31 | 0 | 0 | 0
3801 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill of Lab personnel under Keshpur Shahid Kshudiram Seva Samity NGO Manage Laboratory for the month of January 2023 to March 2023 | BP-2023-24-68 | 04/05/2023 | 0 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 1.35 | 0 | 0 | 0
3802 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Maintenance bill of NGO manage laboratory. | BP-2023-24-327 | 21/09/2023 | 0 | SARBIK GRAM BIKASH KENDRA | 1.35 | 0 | 0 | 0
3803 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill for the month of June to December 2022. |  | 03/02/2023 | 0 | ABASH SARADAMOY UNNAYN PARISHAD | 2.31 | 0 | 0 | 0
3804 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Laboratory Maintenance PALLIMANGAL GUCHHA SAMITY | BP-2023-24-164 | 12/07/2023 | 0 | PALLIMANGAL GUCHHA SAMITY | 0.75 | 0 | 0 | 0
3805 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Laboratory Maintanance KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | BP-2023-24-166 | 12/07/2023 | 0 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 0.75 | 0 | 0 | 0
3806 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | laboratory maintenance JHARGRAM MAHAKUMAR JANASIKSHA PRASAD SAMITY. | BP-2023-24-168 | 19/07/2023 | 0 | JHARGRAM MAHAKUMAR JANASIKSHA PRASAD SAMITY | 0.38 | 0 | 0 | 0
3807 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Maintenance bill of NGO manage laboratory. | BP-2023-24-330 | 21/09/2023 | 0 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 1.35 | 0 | 0 | 0
3808 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill for the month of June to December 2022. |  | 03/02/2023 | 0 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 2.31 | 0 | 0 | 0
3809 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Maintenance bill of NGO manage laboratory. | BP-2023-24-325 | 21/09/2023 | 0 | BELDA SAURYA PRABHA GUCHHA SAMITI | 1.35 | 0 | 0 | 0
3810 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Maintenance bill of NGO manage laboratory. | BP-2023-24-328 | 21/09/2023 | 0 | ABASH SARADAMOY UNNAYN PARISHAD | 1.35 | 0 | 0 | 0
3811 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill for the month of June to December 2022. | BP-2022-23-584 | 08/02/2023 | 0 | ABASH SARADAMOY UNNAYN PARISHAD | 2.31 | 0 | 0 | 0
3812 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill for the month of June to December 2022. | BP-2022-23-585 | 02/02/2023 | 0 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 2.31 | 0 | 0 | 0
3813 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill for the month of June to December 2022. |  | 03/02/2023 | 0 | KANGSABATI GUCHHA SAMITY | 2.31 | 0 | 0 | 0
3814 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill of Lab personnel under Kangsabati Guchha Samity NGO Manage Laboratory for the month of January 2023 to March 2023 | BP-2023-24-67 | 04/05/2023 | 0 | KANGSABATI GUCHHA SAMITY | 1.35 | 0 | 0 | 0
3815 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill for the month of June to December 2022. | BP-2022-23-586 | 08/02/2023 | 0 | BELDA SAURYA PRABHA GUCHHA SAMITI | 2.31 | 0 | 0 | 0
3816 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill of Lab personnel under Abash Saradamoy Unnayn Parishad NGO Manage Laboratory for the month of January 2023 to March 2023 | BP-2023-24-71 | 04/05/2023 | 0 | ABASH SARADAMOY UNNAYN PARISHAD | 1.35 | 0 | 0 | 0
3817 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Laboratory Maintenance Bill for BELDA SAURYA PRABHA GUCHHA SAMITI | BP-2023-24-163 | 12/07/2023 | 0 | BELDA SAURYA PRABHA GUCHHA SAMITI | 0.75 | 0 | 0 | 0
3818 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill for the month of June to December 2022. |  | 03/02/2023 | 0 | BELDA SAURYA PRABHA GUCHHA SAMITI | 2.31 | 0 | 0 | 0
3819 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill for the month of June to December 2022. |  | 03/02/2023 | 0 | PALLIMANGAL GUCHHA SAMITY | 2.31 | 0 | 0 | 0
3820 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill of Lab personnel under Belda Saurya Prabha Guchha Samiti NGO Manage Laboratory for the month of January 2023 to March 2023 | BP-2023-24-69 | 04/05/2023 | 0 | BELDA SAURYA PRABHA GUCHHA SAMITI | 1.35 | 0 | 0 | 0
3821 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill of Lab personnel under Sarbik Gram Bikash Kendra NGO Manage Laboratory for the month of January 2023 to March 2023 | BP-2023-24-72 | 04/05/2023 | 0 | SARBIK GRAM BIKASH KENDRA | 1.35 | 0 | 0 | 0
3822 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill for the month of June to December 2022. | BP-2022-23-589 | 08/02/2023 | 0 | SARBIK GRAM BIKASH KENDRA | 2.31 | 0 | 0 | 0
3823 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration bill of Lab personnel under Pallimangal Guchha Samity NGO Manage Laboratory for the month of January 2023 to March 2023 | BP-2023-24-70 | 04/05/2023 | 0 | PALLIMANGAL GUCHHA SAMITY | 1.35 | 0 | 0 | 0
3824 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Laboratory Maintenance KANGSABATI GUCHHA SAMITY | BP-2023-24-165 | 19/07/2023 | 0 | KANGSABATI GUCHHA SAMITY | 0.75 | 0 | 0 | 0
3825 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration for the month of October 2023. | BP-2023-24-709 | 11/03/2024 | 0 | ABASH SARADAMOY UNNAYN PARISHAD | 0.14 | 0 | 0 | 0
3826 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration for the month of October 2023. | BP-2023-24-708 | 11/03/2024 | 0 | PALLIMANGAL GUCHHA SAMITY | 0.14 | 0 | 0 | 0
3827 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration for the month of October 2023. | BP-2023-24-710 | 11/03/2024 | 0 | SARBIK GRAM BIKASH KENDRA | 0.14 | 0 | 0 | 0
3828 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration for the month of October 2023. | BP-2023-24-707 | 11/03/2024 | 0 | BELDA SAURYA PRABHA GUCHHA SAMITI | 0.14 | 0 | 0 | 0
3829 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration for the month of October 2023. | BP-2023-24-705 | 11/03/2024 | 0 | KANGSABATI GUCHHA SAMITY | 0.14 | 0 | 0 | 0
3830 | PASCHIM MEDINIPUR | Midnapore Division | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. , SM/14086 | Support-WQMSP | Remuneration for the month of October 2023. | BP-2023-24-706 | 11/03/2024 | 0 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 0.14 | 0 | 0 | 0
3831 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | Supply of 5nos. LLOYD 2 TON 3 Star A/C. [3924/MD] | BP-2023-24-218 | 03/08/2023 | 0 | NEXUS ENTERPRISE | 2.46 | 0 | 0 | 0
3832 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | Supply of 15 nos. laser jet printer [MB No. 3924/MD] | BP-2023-24-161 | 12/07/2023 | 0 | IONET | 3.78 | 0 | 0 | 0
3833 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | SUPPLY OF KINGS NON REVOLVING AND NON TILTING CHAIR WITH ARMREST. | BP-2023-24-219 | 03/08/2023 | 0 | GLOBAL MARKETING | 0.15 | 0 | 0 | 0
3834 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | PURCHES OF CANON MILTIFUNCTION MACHINES MFM, ON SITE OEM WARRANTY 1 YEAR. | BP-2023-24-217 | 03/08/2023 | 0 | IONET | 2.5 | 0 | 0 | 0
3835 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. | BP-2022-23-667 | 08/03/2023 | 0 | IONET | 21.98 | 0 | 0 | 0
3836 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | SUPPLY OF HP MULTIFUNCTIONAL MACHINES MFM, ON SITE OEM WARRANTY 5 YEAR | BP-2023-24-216 | 03/08/2023 | 0 | IONET | 0.93 | 0 | 0 | 0
3837 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | supply & delivery of people link PTZ video conferencing Camera 1080p, 30fps Resolution-1 pieces. Mricrotek line Interactive UPS with AVR of Rating 0.65 KVA of Rating 0.65 KVA with warranty of 2 years 20 pieces. |  | 30/03/2024 | 0 | CITY ENTERPRISE | 1.11 | 0 | 0 | 0
3838 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | Supply & delivery of Microtek line interactive UPS with AVR of Rating 0.65 KVA with Warranty of 2 Years-20 Pieces and People link PTZ video conferencing Camera 1080p, 30fps Resolution-1 Pieces. | BP-24-25-131-32 | 06/06/2024 | 0 | COMPUTER CITY | 5.4 | 0 | 0 | 0
3839 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | Supply & delivery of hp Intel Core i5 14 inch Laptops Nine pieces, Epson Multi functional Machines 6 pieces, and HP intel core i3 12100 8GB/0 GB HDD/Windows | BP-2023-24-133 | 06/06/2024 | 0 | CITY ENTERPRISE | 0.56 | 0 | 0 | 0
3840 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | Supply & delivery of Microtek line interactive UPS with AVR of Rating 0.65 KVA with Warranty of 2 Years-20 Pieces and People link PTZ video conferencing Camera 1080p, 30fps Resolution-1 Pieces. | BP-2024-25-106 | 30/05/2024 | 0 | CITY ENTERPRISE | 0.55 | 0 | 0 | 0
3841 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | Supply & delivery of hp Intel Core i5 14 inch Laptops Nine pieces, Epson Multi functional Machines 6 pieces, and HP intel core i3 12100 8GB/0 GB HDD/Windows | BP-2024-25-107 | 30/05/2024 | 0 | COMPUTER CITY | 6.52 | 0 | 0 | 0
3842 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | supply & delivery of akg form factor lavalier HSN code Measurem ent unit GST UQ Name Mircrophones and LED indicator, dispaly and headphone. |  | 30/03/2024 | 0 | M/S EAGLE TRADERS | 0.16 | 0 | 0 | 0
3843 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | Supply & delivery of JBL Water Proof and Splash Proof and LED indicator and LED Display and Headphone jack and Mic and MP3 and FM and Memory Slot Woofer Bluetooth Speakers 1 Year Warranty - 1 Piece, HSN Code Measurem ent Unit GST UQ Name Mircrophones (Lapel Microphones) Minimum Free | BP-2023-24-138 | 07/06/2024 | 0 | M/S EAGLE TRADERS | 0.16 | 0 | 0 | 0
3844 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | Supply & delivery of hp Intel core i5 14 inch Laptop (Windows 11 Home)6 pieces , Epson multi functional mechanics 4 pieces, Hp 50, 5-61.5 CM liquid Crystal display LCD Panel 1 pieces, 3 Pieces Laptop, |  | 30/03/2024 | 0 | COMPUTER CITY | 11.92 | 0 | 0 | 0
3845 | PASCHIM MEDINIPUR | Midnapore Division | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. , SM/12378 | Support-MIS | Supply & delivery of hp Intel Core i5 14 inch Laptops Nine pieces, Epson Multi functional Machines 6 pieces, and HP intel core i3 12100 8GB/0 GB HDD/Windows |  | 20/05/2024 | 0 | COMPUTER CITY | 11.92 | 0 | 0 | 0
3846 | PASCHIM MEDINIPUR | Midnapore Division | Collection,Testing & Uploading charges of Drinking Water Samples through Field Test Kits(FTKs) in Paschim Medinipur District(Phase-II) related to Water Quality Monitoring & Surveillance Program Under Jal Jeevan Mission. , SM/19089 | Support-WQMSP | Water Sample Collection and Testing Charges through FTK Kit. | BP-2023-24-626 | 15/02/2024 | 0 | CMOH PASCHIM MEDINIPUR. | 20.9 | 0 | 0 | 0
3847 | PASCHIM MEDINIPUR | Midnapore Division | Collection,Testing & Uploading charges of Drinking Water Samples through Field Test Kits(FTKs) in Paschim Medinipur District(Phase-II) related to Water Quality Monitoring & Surveillance Program Under Jal Jeevan Mission. , SM/19089 | Support-WQMSP | Data uploading charges of FTK test results into State Water Quality Dashboard tested by ASHA workers using Field Test Kit (FTKs) related with Water Quality Monitoring & Surveillance under JJM. | 620/MD | 05/03/2025 | 180 | UTSAV AGENCY | 6.09 | 0 | 0 | 0
3848 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Garhbeta Sub-District Laboratory & (B) Chandrakona Road Sub-District Laboratory within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [For the period of 12 (Twelve) months staring from 01.10.2022 to 30.09.2023] | 2066/MD | 30/09/2022 | 365 | UTSAV AGENCY | 7.32 | 0 | 0 | 60
3849 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Regular analysis, Testing and Monitoring of water samples by experienced & trained personnel for District Water Testing Laboratory activities of Midnapore District Water Testing Laboratory of PHE Dte. at Narampur PHE Complex under Midnapore Sadar Sub-Division, PHE Dte. [Period from 01.01.2022 to 31.12.2022] | 2258/MD | 29/12/2021 | 365 | MASUM ALI KHAN | 3.41 | 0 | 0 | 100
3850 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Chandrakona Municipality Sub-District Laboratory & (B) Ghatal Sub-District Laboratory within Ghatal Sub-Division under Midnapore Division, PHE Dte. [For the period of 12 (Twelve) months staring from 01.10.2022 to 30.09.2023] | 2065/MD | 30/09/2022 | 365 | UTSAV AGENCY | 7.32 | 0 | 0 | 100
3851 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Continuation Work Order for Engagement of 3 (Three) Nos. Laboratory Personnel (One Chemist, One Bacteriologist & One Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Kharagpur Sub-District Laboratory within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [For the period of 04 (Four) months staring from 01.10.2023 to 31.01.2024] | 3889/MD | 27/09/2023 | 122 | GOBINDA MAITY | 1.19 | 0 | 0 | 0
3852 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Engagement of 3 (Three) Nos. Laboratory Personnel (One Chemist, One Bacteriologist & One Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Kharagpur Sub-District Laboratory within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [For the period of 12 (Twelve) months staring from 01.10.2022 to 30.09.2023] | 2054/MD | 29/09/2022 | 365 | GOBINDA MAITY | 3.83 | 0 | 0 | 10
3853 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Continuation Work Order for Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Chandrakona Municipality Sub-District Laboratory & (B) Ghatal Sub-District Laboratory within Ghatal Sub-Division under Midnapore Division, PHE Dte. [For the period of 04 (Four) months staring from 01.10.2023 to 31.01.2024] | 3887/MD | 27/09/2023 | 122 | UTSAV AGENCY | 2.19 | 0 | 0 | 100
3854 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration bill for the NGO Managed Laboratory Personnel from Nov. 2023 to Jan. 2024. | BP-2023-24-739 | 19/03/2024 | 0 | ABASH SARADAMOY UNNAYN PARISHAD | 1.35 | 0 | 0 | 0
3855 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration bill of NGO Managed Laboratory for the month of April 2024 to June 2024. | BP-2024-25-250 | 05/08/2024 | 0 | SARBIK GRAM BIKASH KENDRA | 1.35 | 0 | 0 | 0
3856 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration of 6 nos NGO - Kangsabati, Keshpur, Belda, Sabang, Abash, Sarbik. | 24-25-423-428 | 04/10/2024 | 0 | SIX NOS OF NGO MANAGED LABORATORIES | 0.95 | 0 | 0 | 0
3857 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration bill of NGO Managed Laboratory for the month of April 2024 to June 2024. | BP-2024-25-247 | 05/08/2024 | 0 | BELDA SAURYA PRABHA GUCHHA SAMITI | 1.35 | 0 | 0 | 0
3858 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration bill of NGO Managed Laboratory for the month of April 2024 to June 2024. | BP-2024-25-248 | 05/08/2024 | 0 | PALLIMANGAL GUCHHA SAMITY | 1.35 | 0 | 0 | 0
3859 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration of the Lab personnel of the NGO managed Laboratory under Midnapore Division, PHE Dte. | BP-2023-24-543 | 17/01/2024 | 0 | PALLIMANGAL GUCHHA SAMITY | 1.8 | 0 | 0 | 0
3860 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration bill for the NGO Managed Laboratory Personnel from Nov. 2023 to Jan. 2024. | BP-2023-24-740 | 19/03/2024 | 0 | SARBIK GRAM BIKASH KENDRA | 1.35 | 0 | 0 | 0
3861 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Laboratory Maintenance bill from October 2022 to September 2023. | BP-2024-25-353 | 13/09/2024 | 0 | BELDA SAURYA PRABHA GUCHHA SAMITI | 0.75 | 0 | 0 | 0
3862 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration of the Lab personnel of the NGO managed Laboratory under Midnapore Division, PHE Dte. | BP-2023-24-546 | 19/01/2024 | 0 | ABASH SARADAMOY UNNAYN PARISHAD | 1.8 | 0 | 0 | 0
3863 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration of the Lab personnel of the NGO managed Laboratory under Midnapore Division, PHE Dte. | BP-2023-24-545 | 19/01/2024 | 0 | KANGSABATI GUCHHA SAMITY | 1.8 | 0 | 0 | 0
3864 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Mobile data recharge of 10 nos. of sub-district laboratories under Midnapore Division, PHE Dte. |  | 21/05/2024 | 0 | SUB DISTRICT WATER TESTING LABORATORY | 0.35 | 0 | 0 | 0
3865 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Laboratory Maintenance bill from October 2022 to September 2023. | BP-2024-25-352 | 13/09/2024 | 0 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 0.75 | 0 | 0 | 0
3866 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration of the Lab personnel of the NGO managed Laboratory under Midnapore Division, PHE Dte. | BP-2023-24-547 | 17/01/2024 | 0 | SARBIK GRAM BIKASH KENDRA | 1.8 | 0 | 0 | 0
3867 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration bill for the NGO Managed Laboratory Personnel from Nov. 2023 to Jan. 2024. | BP-2023-24-736 | 19/03/2024 | 0 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 1.35 | 0 | 0 | 0
3868 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration of Six Nos. Laboratory Personnel's of NGO Managed Laboratories from February 2024 to March 2024 | BP24-25-100-105 | 28/05/2024 | 0 | SIX NOS OF NGO MANAGED LABORATORIES | 5.4 | 0 | 0 | 0
3869 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration bill for the NGO Managed Laboratory Personnel from Nov. 2023 to Jan. 2024. | BP-2023-24-738 | 19/03/2024 | 0 | PALLIMANGAL GUCHHA SAMITY | 1.35 | 0 | 0 | 0
3870 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration bill for the NGO Managed Laboratory Personnel from Nov. 2023 to Jan. 2024. | BP-2023-24-735 | 19/03/2024 | 0 | KANGSABATI GUCHHA SAMITY | 1.35 | 0 | 0 | 0
3871 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Laboratory Maintenance bill from October 2022 to September 2023. | BP-2023-24-351 | 13/09/2024 | 0 | KANGSABATI GUCHHA SAMITY | 0.75 | 0 | 0 | 0
3872 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration bill of NGO Managed Laboratory for the month of April 2024 to June 2024. | BP-2024-25-245 | 05/08/2024 | 0 | KANGSABATI GUCHHA SAMITY | 1.35 | 0 | 0 | 0
3873 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration bill of NGO Managed Laboratory for the month of April 2024 to June 2024. | BP-2024-25-249 | 05/08/2024 | 0 | ABASH SARADAMOY UNNAYN PARISHAD | 1.35 | 0 | 0 | 0
3874 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration of Laboratory Personnel's i.e Chemist, Bacteriologist and Lab-assistant of 6 nos. NGO managed laboratories under Midnapore Division PHE Dte. for the period from July 2024 to September 2024. | BP-24-25-465-70 | 23/12/2024 | 0 | SIX NOS OF NGO MANAGED LABORATORIES | 8.1 | 0 | 0 | 0
3875 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration of the Lab personnel of the NGO managed Laboratory under Midnapore Division, PHE Dte. | BP-2023-24-542 | 17/01/2024 | 0 | BELDA SAURYA PRABHA GUCHHA SAMITI | 1.8 | 0 | 0 | 0
3876 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration bill for the NGO Managed Laboratory Personnel from Nov. 2023 to Jan. 2024. | BP-2023-24-737 | 19/03/2024 | 0 | BELDA SAURYA PRABHA GUCHHA SAMITI | 1.35 | 0 | 0 | 0
3877 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Laboratory Maintenance bill from October 2022 to September 2023. | BP-2024-25-356 | 13/09/2024 | 0 | PALLIMANGAL GUCHHA SAMITY | 0.75 | 0 | 0 | 0
3878 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Laboratory Maintenance bill from October 2022 to September 2023. | BP-2024-25-354 | 13/09/2024 | 0 | ABASH SARADAMOY UNNAYN PARISHAD | 0.75 | 0 | 0 | 0
3879 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration of the Lab personnel of the NGO managed Laboratory under Midnapore Division, PHE Dte. | BP-2023-24-544 | 17/01/2024 | 0 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 1.8 | 0 | 0 | 0
3880 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Laboratory Maintenance bill from October 2022 to September 2023. | BP-2024-25-355 | 13/09/2024 | 0 | SARBIK GRAM BIKASH KENDRA | 0.75 | 0 | 0 | 0
3881 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Remuneration bill of NGO Managed Laboratory for the month of April 2024 to June 2024. | BP-2024-25-246 | 05/08/2024 | 0 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 1.35 | 0 | 0 | 0
3882 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. , SM/19061 | Support-WQMSP | Engagement of Laboratory Personnel (One Chemist, One Bacteriologist, One Laboratory Assistant & One Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor mtc. works of 10 Nos. Water Testing Laboratory under Midnapore Division, PHE Dte. [For the period of 12 (Twelve) months starting from 01.02.2024 to 31.01.2025] | 240/MD | 01/02/2024 | 366 | UTSAV AGENCY | 82.82 | 0 | 0 | 100
3883 | PASCHIM MEDINIPUR | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Paschim Medinipur District. , SM/08999 | Support-M&E | Engagement of Implementation Support Agency (ISA) for Implementation of commudity mobilization & capacity building activities related to House Hold tap connection (FHTC) in Paschim Midnapur district Under Jal Jeevan Mission (JJM) Support Activities. | 5772/RS | 09/11/2022 | 365 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 454.73 | 0 | 0 | 100
3884 | PASCHIM MEDINIPUR | Midnapore Division | Regular Upkeep of Drinking Water Testing Laboratory in Paschim Medinipur Under Midnapore Division, PHE dte. Related to Water Quality Monitoring and Surveillance Support Activities under Jal Jeevan Mission. , SM/18277 | Support-WQMSP | Repairing and Renovation work of an existing damaged PHE Dte. Laboratories building in connection with different 08 (Eight) Nos. Sub-District Water Testing Laboratories under Midnapore Division, PHE Dte. of Paschim Medinipur District. | 3576/MD | 06/12/2024 | 480 | D M CONSTRUCTION | 69.35 | 0 | 0 | 75
3885 | PASCHIM MEDINIPUR | Midnapore Division | Estimate for procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Laboratories for the year 2024- 2025 in the District of Paschim Medinipur Under Midnapore Division P.H.E. Dte. , SM/19270 | Support-WQMSP | Continuation Work Order for "Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Laboratories for the year 2024 in the district of Paschim Medinipur under Midnapore Division, PHE Dte. (Total Nos. of Laboratories = 17 Nos. including 6 Nos. NGO managed Laboratories)" | 869/MD | 28/03/2025 | 217 | UTSAV AGENCY | 52.03 | 0 | 0 | 87
3886 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. , SM/14687 | Support-MIS | HP 59/5-61.5 CM Liquid Crystal Display LCD Panel or Monitors | BP-2023-24-102 | 11/07/2023 | 0 | IONET | 0.22 | 0 | 0 | 0
3887 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. , SM/14687 | Support-MIS | HP 59.5-61.5 CM Liquid Crystal Display LCD Panel or Monitors | BP-2023-24-207 | 24/08/2023 | 0 | IONET | 0.22 | 0 | 0 | 0
3888 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. , SM/14687 | Support-MIS | HP 59.5-61.5 CM Liquid Crystal Display LCD Panel or Monitors | BP-2023-24-103 | 11/07/2023 | 0 | IONET | 0.22 | 0 | 0 | 0
3889 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. , SM/14687 | Support-MIS | HP 59.5-61.5 CM Liquid Crystal Display LCD Panel or Monitors | BP-2023-24-102 | 11/07/2023 | 0 | IONET | 0.22 | 0 | 0 | 0
3890 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. , SM/14687 | Support-MIS | LLOYD 2.0 TR 3 STAR INVERTER GLS2413 | BP-2023-24-323 | 01/11/2023 | 0 | M/S NEXUS ENTERPISE | 0.5 | 0 | 0 | 0
3891 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. , SM/14687 | Support-MIS | Supply of 12A toner cartridge, PC, 88A toner cartridge, UPS, Mouse, Quick heal, 2365 toner cartridge , under MMD | BP-2022-23-115 | 06/03/2023 | 0 | IONET | 8.64 | 0 | 0 | 0
3892 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. , SM/14687 | Support-MIS | Copper pipe with insulation(RFT), Electrical Cable 2.5 sq. mm 4 core, Drain Pipe (RFT), White Roll, 3 Pin Top, Outdoor stand for Split AC for Office of the Assistant Engineer, Haldia Electrical Sub-Division, P.H.E.Dte. | BP-2023-24-324 | 01/11/2023 | 0 | M/S NEXUS ENTERPISE | 0.08 | 0 | 0 | 0
3893 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. , SM/14687 | Support-MIS | Cannon Multifunction Machines Mfm. on site OEM Warranty 3 year | BP-2023-24-105 | 11/07/2023 | 0 | IONET | 3.9 | 0 | 0 | 0
3894 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. , SM/14687 | Support-MIS | HP 53.5-55.5 CM Liquid Crystal Display LCD Panel or Monitors - 2 unit | BP-2023-24-101 | 11/07/2023 | 0 | IONET | 0.22 | 0 | 0 | 0
3895 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. , SM/14687 | Support-MIS | HP INTELCORE i5 12100 8GB/WINDOWS 11 | BP-2023-24-351 | 10/11/2023 | 0 | IONET | 3.77 | 0 | 0 | 0
3896 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. , SM/14687 | Support-MIS | LLOYD 2.0 TR 3 STAR INVERTER GLS2413 | BP-2023-24-352 | 10/11/2023 | 0 | M/S NEXUS ENTERPISE | 0.5 | 0 | 0 | 0
3897 | PASCHIM MEDINIPUR | Midnapore Mechanical | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. , SM/14687 | Support-MIS | Supply and delivery of HP Intel core i5 12400 8GB HDD / Windows 11 Professional computer. | C072449548031 | 02/08/2024 | 0 | IONET | 1.89 | 0 | 0 | 0
3898 | PASCHIM MEDINIPUR | Midnapore Division | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission under Midnapore Division, PHE Dte. , SM/12633 | Support-WQMSP | Procurement of 1 no. of Mobile Laboratory Van (MLV) complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with OMAS instruments, devices, consumables, reagents, smart phone with preloaded water quality app synchronized with PHED water quality dashboard and safety gear for resource personnel for water quality testing in remote areas including external designing and painting for IEC propaganda complete with IEC audio visual aids as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. | 751/MD | 13/03/2023 | 366 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 75.86 | 0 | 0 | 66
3899 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) , SM/19285 | Support-WQMSP | Engagement of Laboratory Personnel (One Chemist, One Bacteriologist, One Laboratory Assistant & One Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor mtc. works of 11 Nos. Water Testing Laboratory under Midnapore Division, PHE Dte. [For the period of 12 (Twelve) months i.e. from 01.02.2025 to 31.01.2026] | 371/MD | 31/01/2025 | 365 | CFS MANAGEMENT PVT. LTD. | 92.03 | 0 | 0 | 75
3900 | PASCHIM MEDINIPUR | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) , SM/19285 | Support-WQMSP | Regular analysis, Testing and Monitoring of water samples by experienced & trained personnel for District Water Testing Laboratory activities of Midnapore District Water Testing Laboratory of PHE Dte. at Narampur PHE Complex under Midnapore Sadar Sub-Division, PHE Dte. [For the period of 03 (Three) months starting from 15.06.2024 to 14.09.2024] | 1863/MD | 14/06/2024 | 92 | GOBINDA MAITY | 1.63 | 0 | 0 | 100
3901 | PASCHIM MEDINIPUR | Midnapore Division | Drinking Water sample collection and testing through Field Test Kit(FTKs) and uploading charges for the same related to water quality monitoring and surveillance programme under Jal Jeevan Mission. , SM/19214 | Support-WQMSP | Remunation of Asha Kormi for the period of May 2023 to June 2024 | BP-2024-25-350 | 13/09/2024 | 0 | CMOH PASCHIM MEDINIPUR. (ASHA KORMI) | 42.43 | 0 | 0 | 0
3902 | PASCHIM MEDINIPUR | Midnapore Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues and WASH issues under Jal Jeevan Mission (JJM) Support Activities at Paschim Medinipur District. , SM/19172 | Support-IEC | Organize one day Sub Division level orientation programme on JJM involving PRI Functionaries & VWSC members at Paschim Medinipur district and conceptualization, design, implementation of community sensitization / mobilization activities using various mediums on JJM, provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water quality issues, water conservation and WASH related issues as per operational guideline of JJM and preparation of web based Digital (A/V) training material (Bengali) at Paschim Medinipur District under Midnapore Division, PHE Dte, Govt. of West Bengal. | 139/MD | 14/01/2025 | 180 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 120.34 | 0 | 0 | 0
3903 | PASCHIM MEDINIPUR | Midnapore Division | Regular Upkeepment of Mobile Laboratory Van (MLV) complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents. accessories and safety , SM/19282 | Support-WQMSP | Regular Up-keepment of Mobile Laboratory Van (MLV) complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents, accessories and safety gear for resource personnel for water quality testing in remote areas including external designing and painting for IEC propaganda complete with IEC audio visual aids as directed by EIC under Midnapore Division PHE Dte. [For the Period of 12 (Twelve) Months i.e. from 01.01.2025 to 31.12.2025] | 3810/MD | 26/12/2024 | 365 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 35.7 | 0 | 0 | 50
Total | [9 empty] | 3804045.83 | 2252.17 | 0.06