## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accommodate FHTC [181 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-B) Dakshin Choumukh(209, part), Gagana(211, part), Paik Bar(212, part), Dhalgoda (Part, 231) [ PART - 1B ]. | 2925/TD | 22/02/2021 | 20 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 8.77 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accommodate FHTC [206 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-C),Bamaniabar(228), Narubhunya Chak(229). | 2716/TD | 21/01/2021 | 20 | DHANANJOY DAS | 9.99 | 0 | 0 | 100
3 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accommodate FHTC [740 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.( Part-A), Nalbar(227),Dhalgoda (231) part, .Uttar Padma(233), Kashmali(234), .Kumbha Dharbar(235), | 2717/TD | 21/01/2021 | 35 | LOKENATH ENTERPRISES | 35.86 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accommodate FHTC [206 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-D) Jagannath Karbar(213)(Part) | 2715/TD | 21/01/2021 | 20 | ANUPAM CONSTRUCTION | 9.99 | 0 | 0 | 40
5 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accomodate FHTC 536 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. | 982/W | 25/03/2021 | 0 | PALCON | 10.68 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accomodate for 206 Nos. FHTC connection under JJM in Astichak W/S Scheme within Egra - II Dev. Block Block under Tamluk Division, PHE Dte. | 209/W | 18/08/2021 | 0 | DHANANJOY DAS | 5.2 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accomodate for 206 Nos. FHTC connection under JJM in Astichak W/S Scheme within Egra - II Dev. Block Block under Tamluk Division, PHE Dte. | 97/W | 07/07/2021 | 0 | DHANANJOY DAS | 4.68 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accomodate FHTC (206 Nos.) under JJM of Astichak W/S Scheme within Egra-II Block under Tamluk Division, PHE Dte. (Part-D) | 397/W | 25/11/2021 | 0 | ANUPAM CONSTRUCTION | 2.65 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accomodate FHTC 740 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. | 233/W | 07/09/2021 | 0 | LOKENATH ENTERPRISES | 25.14 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accomodate FHTC 536 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. | 160/W | 30/07/2021 | 0 | PALCON | 4.33 | 0 | 0 | 0
11 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accomodate FHTC 740 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. | 971/W | 25/03/2021 | 0 | LOKENATH ENTERPRISES | 10.64 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accommodate FHTC [126 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-B) Dakshin Choumukh(209, part), Gagana(211, part), Paik Bar(212, part), Dhalgoda (Part, 231) [ PART - 2B ]. | 2924/TD | 22/02/2021 | 20 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.1 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Retrofitting to accommodate FHTC [536 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-E) Jagannath Karbar(213)(Part) | 2714/TD | 21/01/2021 | 30 | PALCON | 25.95 | 0.39 | 100 | 70
14 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme , SM/07098 | Retrofitting | Laying 150mm. dia. D.I. (K-9) Rising main pipe line in between 1st Tube Well to pump house & O.H.R. to Distribution Main including construction of masonry pillar and Thrust concrete block for Astichak Water supply Scheme under Digha Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. | 834/TD | 18/07/2022 | 7 | ANUPAM CONSTRUCTION | 3.14 | 0 | 0 | 100
15 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme , SM/06884 | Retrofitting | Functional Household Tap Connection to the 275 nos. Household of Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Damudarpur (357) ii) Hamirpur (545). | 2454/TD | 18/12/2020 | 20 | ABHIJIT BERA | 13.49 | 0 | 0 | 100
16 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme , SM/06884 | Retrofitting | Functional Household Tap Connection to the 237 nos. Household of Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Chandanpur (422) ii) Dakshin Rampur ( 539). | 2455/TD | 18/12/2020 | 20 | PARIA ENTERPRISE | 11.6 | 0 | 0 | 100
17 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme , SM/06884 | Retrofitting | Functional Household Tap Connection to the 233 nos. Household of Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Baliapur (358) ii) Jamna Madhusudhanbar (365). | 2456/TD | 18/12/2020 | 20 | BADAL CHANDRA GOLE | 11.46 | 0 | 0 | 100
18 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme , SM/06884 | Retrofitting | Retrofitting to accomodate for 233 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. | 956/W | 19/03/2021 | 0 | BADAL CHANDRA GOLE | 10.24 | 0 | 0 | 0
19 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme , SM/06884 | Retrofitting | Retrofitting to accomodate for 233 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. | 325/W | 08/10/2021 | 0 | BADAL CHANDRA GOLE | 0.81 | 0 | 0 | 0
20 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme , SM/06884 | Retrofitting | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. | 224/W | 01/09/2021 | 0 | ABHIJIT BERA | 1.3 | 0 | 0 | 0
21 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme , SM/06884 | Retrofitting | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. | 728/W | 18/02/2021 | 0 | ABHIJIT BERA | 11.81 | 0 | 0 | 0
22 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme , SM/06884 | Retrofitting | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. | 801/W | 24/02/2021 | 0 | PARIA ENTERPRISE | 11.27 | 0 | 0 | 0
23 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme , SM/06886 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Kanaidighi PWSS Block Contai-III in the District of Purba Medinipur. | 2109/TD | 05/11/2020 | 180 | DAS ENTERPRISE | 96.3 | 26.7 | 100 | 100
24 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme , SM/06886 | Retrofitting | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme within Contai - III Block under Tamluk Division, PHE Dte. | 640/W | 13/01/2021 | 0 | DAS ENTERPRISE | 52.63 | 0 | 0 | 0
25 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme , SM/06886 | Retrofitting | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme within Contai - III Block under Tamluk Division, PHE Dte. | 935/W | 18/03/2021 | 0 | DAS ENTERPRISE | 16.93 | 0 | 0 | 0
26 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XIII , SM/07118 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -XIII(Balance Work) Block Panskura-II in the District of Purba Medinipur. | 2632/TD | 05/01/2021 | 60 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 96.92 | 195.77 | 202 | 100
27 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) in the District of Purba Medinipur , SM/07661 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XI (Balance Work) Block ¿ Panskura-II in the District of Purba Medinipur. | 2820/TD | 05/02/2021 | 70 | TAPAS SANTRA | 196.75 | 6.19 | 100 | 100
28 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) in the District of Purba Medinipur , SM/07661 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) under Tamluk Division, PHE Dte. |  | 09/09/2021 | 0 | TAPAS SANTRA | 134 | 0 | 0 | 0
29 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) in the District of Purba Medinipur , SM/07661 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) under Tamluk Division, PHE Dte. | BP-2021-22-78 | 17/09/2021 | 0 | TAPAS SANTRA | 134 | 0 | 0 | 0
30 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) in the District of Purba Medinipur , SM/07661 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Zone ¿ XI (Balance Work) Piped Water Supply Scheme | 1081/W | 30/03/2021 | 0 | TAPAS SANTRA | 56.32 | 0 | 0 | 0
31 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS , SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village-Hariharpur,J.L. No-43 and Village-Uttar Rautori,J.L No-40 under JJM in Dakshin Dhalhara PWSS Block - Nandakumar in the District of Purba Medinipur. | 2459/TD | 18/12/2020 | 30 | ARABINDA GHOSH | 38.54 | 0.88 | 100 | 100
32 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS , SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village-Alisuli,J.L. No-42 under JJM in Dakshin Dhalhara PWSS Block - Nandakumar in the District of Purba Medinipur. | 2457/TD | 18/12/2020 | 20 | KRISHNENDU SEKHAR DAS | 16.12 | 0.59 | 100 | 100
33 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS , SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village-Bet Kalla,J.L. No-41 and Village-Dakshin Dhalhara,J.L No-39 under JJM in Dakshin Dhalhara PWSS Block - Nandakumar in the District of Purba Medinipur. | 2458/TD | 18/12/2020 | 30 | ARABINDA GHOSH | 33.51 | 1.43 | 100 | 100
34 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS , SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village - Hariharpur under JJM Dakshin Dhalhara W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. | 1033/W | 30/03/2021 | 0 | ARABINDA GHOSH | 14.42 | 0 | 0 | 0
35 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS , SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village - Hariharpur under JJM Dakshin Dhalhara W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. | 641/W | 13/01/2021 | 0 | ARABINDA GHOSH | 23.24 | 0 | 0 | 0
36 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS , SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village - Betkalla under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. | 642/W | 13/01/2021 | 0 | ARABINDA GHOSH | 21.06 | 0 | 0 | 0
37 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS , SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village - Alisuli under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. | 1032/W | 27/03/2021 | 0 | KRISHNENDU SEKHAR DAS | 3.44 | 0 | 0 | 0
38 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS , SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village - Alisuli under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. | 647/W | 25/01/2021 | 0 | KRISHNENDU SEKHAR DAS | 12.09 | 0 | 0 | 0
39 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS , SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village - Betkalla under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. | 1034/W | 30/03/2021 | 0 | ARABINDA GHOSH | 11.02 | 0 | 0 | 0
40 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Uttar Charaikhia W/S Scheme Under Contai-I Block , SM/07478 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Uttar Charaikhia PWSS Block -Contai-l in the District of Purba Medinipur. | 2804/TD | 04/02/2021 | 25 | M/S SREE DURGA ENTERPRISE | 45.73 | 0 | 0 | 100
41 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Uttar Charaikhia W/S Scheme Under Contai-I Block , SM/07478 | Retrofitting | Retrofitting to accomodate FHTC under JJM Uttar Charaikhia W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. | 1088/W | 30/03/2021 | 0 | M/S SREE DURGA ENTERPRISE | 44.55 | 0 | 0 | 0
42 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Uttar Charaikhia W/S Scheme Under Contai-I Block , SM/07478 | Retrofitting | Retrofitting to accomodate FHTC under JJM Uttar Charaikhia W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-73 | 04/09/2021 | 0 | M/S SREE DURGA ENTERPRISE | 0.69 | 0 | 0 | 0
43 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Uttar Charaikhia W/S Scheme Under Contai-I Block , SM/07478 | Retrofitting | Functional Household Tap Connection for Uttar Charaikhia W/S Scheme within Contai - I Block Tamluk Division, PHE Dte. |  | 08/03/2021 | 0 | M/S SREE DURGA ENTERPRISE | 44.55 | 0 | 0 | 0
44 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Sinking of 300 mm. x 200 mm. dia. x 230 mtr. deep tube well by direct rotary rig method using UPVC pipe and UPVC Deep Well Screen (RDS) at Kasbagola PWSS, Block- EGRA-I under Digha Sub-Division of Tamluk Division Dist- Purba Medinipur. | 2048/TD | 14/03/2022 | 21 | KISHORE GHOSH | 13.75 | 10.69 | 100 | 100
45 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kasbagola Water Supply Scheme under Tamluk Division, PHE Dte. | 1200/TD | 02/12/2021 | 20 | RADIANT | 3.78 | 3.78 | 100 | 100
46 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Material Requisition To Resource Division | 1955/TD | 04/03/2022 | 0 | Resource Division | 11.7 | 0 | 0 | 0
47 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Material Requisition To Resource Division | 2189/TD | 21/03/2022 | 0 | Resource Division | 14.39 | 0 | 0 | 0
48 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Electric Quotiaton for Kasbagola Water Supply Scheme T/W-III (Ref. ID-204005246) | BP-2023-24-66 | 06/06/2023 | 0 | WBSEDCL | 0.61 | 0 | 0 | 0
49 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Augmentation of ground water based Kasbagola Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 300 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Egra-I Dev. Block under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1910/TD | 23/02/2022 | 180 | KISHORE GHOSH | 287.79 | 156.81 | 54.49 | 70
50 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Construction of Pump House, Boundary Wall, of 3rd Tube Well site with allied works of Kasbagola & its adjoining mouzas W/S Scheme within Egra -I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 594/TD | 17/05/2023 | 60 | CHAKRABORTY CONSTRUCTION | 13.42 | 5.07 | 37.75 | 90
51 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Requirement of additional pipeline to accommodate FHTC under JJM for Augmentation of Kasbagola PWSS under Egra-I Block within Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 3191/TD | 11/12/2023 | 25 | KISHORE GHOSH | 31.07 | 29.75 | 95.75 | 95
52 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Supply of CIDF sluice valve for Augmentation of Kasbagola PWSS within Egra-I Block under Digha Sub Division of Tamluk division PHE Dte. | 2334/TD | 08/09/2023 | 10 | KISHORE GHOSH | 3.38 | 3.38 | 100 | 100
53 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Kasbagola W/S Scheme (T/W-I) , Egra-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 859/CDD | 10/07/2023 | 287 | PADMA ENGINEERING & CO. | 18.23 | 15.33 | 100 | 100
54 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Quotation for new service connection at TW-4 of Kasbagola ws scheme under MMD, PHE Dte, Block-Egra-1, Chorpalia CCC Application no-2004773721 Con ID-204332518 | BP-2024-25-359 | 01/07/2024 | 0 | WBSEDCL | 4.68 | 0 | 0 | 0
55 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Bill for damage of Road flank / hard shoulder due to cutting of hard shoulder and road flank on Alamgiri Birbara Khosbagola Road from 5.80 Km. to 6.20 Km., 6.40 Km. to 6.50 Km. & 6.80 Km. to 7.00 Km. for laying water pipe line of Kasbagola PWSS. | BP-2024-25-493 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.24 | 0 | 0 | 0
56 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | 844/W/MMD | 24/03/2023 | 840 | ECO ENTERPRISE | 35.55 | 13.97 | 39.3 | 25
57 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Repairing of Pump house, Construction of Boundary Wall, Laying Rising main pipe line & Supply under JJM with allied work for Kasbagola PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 401/TD | 27/04/2023 | 789 | ANUSKA ENTERPRISE | 26.15 | 14.62 | 55.89 | 95
58 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09402 | Augmentation | Construction of Pump House (3.6mx 3.0m), Boundary Wall, Proposed Rising & Interconnection, Supply and delivery of different dia D.I. specials & fittings with allied works under JJM at 4th TW site for Augmentation of Kasbagola Water Supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 490/TD | 06/02/2025 | 40 | AYSAN KHAN | 15.06 | 0 | 0 | 0
59 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under RAMNAGAR Water Supply Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 647/TD | 08/09/2021 | 20 | SNEHESH SEN | 3.8 | 3.8 | 100 | 0
60 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under HALDIA Water Supply Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 648/TD | 08/09/2021 | 20 | LOKENATH ENTERPRISES | 3.97 | 3.97 | 100 | 0
61 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under RANISAI Water Supply Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 649/TD | 08/09/2021 | 20 | LOKENATH ENTERPRISES | 3.9 | 3.89 | 100 | 0
62 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under TAMALDA Water Supply Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 643/TD | 08/09/2021 | 20 | SOM CONSTRUCTION | 3.94 | 3.83 | 100 | 0
63 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under BADHIA Water Supply Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 646/TD | 08/09/2021 | 20 | SOM CONSTRUCTION | 3.2 | 3.2 | 100 | 0
64 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Chirulia Chatla Water Supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 644/TD | 08/09/2021 | 20 | SOM CONSTRUCTION | 3.87 | 3.87 | 100 | 0
65 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Kasbagola W/S Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 320/A/DSD | 28/12/2020 | 20 | DHANANJOY DAS | 2.89 | 2.89 | 100 | 0
66 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under NARANDIHA W/S Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 319/A/DSD | 28/12/2020 | 20 | CHARUBALA ENTERPRISE | 2.92 | 2.91 | 100 | 0
67 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Repairing of existing Boundary Wall & Door,Window,Ventilator of Digha S.G. Hospital due to combats Super Cyclonic Storm "AMPHAN" within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 322/DSD | 28/12/2020 | 20 | LOKENATH ENTERPRISES | 1.95 | 1.91 | 100 | 0
68 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Kudi W/S Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 315/DSD | 24/12/2020 | 20 | AJIT KUMAR SOM | 2.92 | 2.92 | 100 | 0
69 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Paniparul W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 320/C/DSD | 28/12/2020 | 20 | AJIT KUMAR SOM | 2.65 | 2.65 | 100 | 0
70 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under SANKARPUR W/S Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 315/A/DSD | 24/12/2020 | 20 | MAITY CONSTRUCTION | 2.7 | 2.68 | 100 | 0
71 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under KANPUR W/S Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 324/A/DSD | 28/12/2020 | 20 | MAITY CONSTRUCTION | 2.99 | 2.91 | 100 | 0
72 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Madhabpur W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 320/B/DSD | 28/12/2020 | 20 | S.D. CONSTRUCTION | 2.87 | 2.87 | 100 | 0
73 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Astichak W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 314/DSD | 24/12/2020 | 20 | ANUPAM CONSTRUCTION | 2.87 | 2.87 | 100 | 0
74 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under BAGMARI W/S Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 318/A/DSD | 28/12/2020 | 20 | LAKSHMI NARAYAN ENTERPRISE | 2.89 | 2.89 | 100 | 0
75 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under CHANDANPUR W/S Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 324/DSD | 28/12/2020 | 20 | BASANTA KUMAR MAITY | 2.61 | 2.59 | 100 | 0
76 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Bathuary. W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 314/A/DSD | 24/12/2020 | 20 | BHOWMIK & SONS | 2.11 | 2.1 | 100 | 0
77 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under DIGHA AUGMENTATION(E.Z.) Water Supply Scheme under Digha Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 370/TD | 19/07/2021 | 20 | CHARUBALA ENTERPRISE | 3.86 | 3.85 | 100 | 0
78 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di , SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Mandarmoni Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 645/TD | 08/09/2021 | 20 | KAMAL KUMAR ROY | 3.02 | 3.02 | 100 | 0
79 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDHUI PWSS UNDER RAMNAGAR - II BLOCK , SM/08746 | Retrofitting | Retrofitting to accomodate FHTC (1575 nos.) under JJM in Palduhi PWSS Block - RAMNAGAR-II under Digha Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Phase- I) | 685/TD | 10/09/2021 | 45 | BASANTA KUMAR MAITY | 95.95 | 61.88 | 100 | 100
80 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDHUI PWSS UNDER RAMNAGAR - II BLOCK , SM/08746 | Retrofitting | Retrofitting to accommodate FHTC 1575 Nos. under JJM in Palduhi PWSS Block Ramnagar - II in the district of Purba Medinipur under Tamluk Division, PHE Dte. | BP-2021-22-135 | 18/10/2021 | 0 | BASANTA KUMAR MAITY | 34.05 | 0 | 0 | 0
81 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN HABICHAK PWSS BALANCE WORK BLOCK CHANDIPUR IN THE DISTRICT OF PURBA MEDINIPUR. , SM/08757 | Retrofitting | Retrofitting to accomodate FHTC (548 nos.) under JJM in Habichak PWSS(Balance Work) Block - Chandipur in the District of Purba Medinipur. (Phase- II) | 681/TD | 10/09/2021 | 50 | S.D. CONSTRUCTION | 24.29 | 0 | 0 | 100
82 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN HABICHAK PWSS BALANCE WORK BLOCK CHANDIPUR IN THE DISTRICT OF PURBA MEDINIPUR. , SM/08757 | Retrofitting | Retrofitting to accomodate FHTC (548 Nos.) under JJM in Habichak PWSS (Balance Work) Block-Chandipur under Tamluk Division, PHE Dte. (Phase-II) | BP-2021-22-87 | 05/10/2021 | 0 | S.D. CONSTRUCTION | 24 | 0 | 0 | 0
83 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN DAMUDARPUR PWSS UNDER CONTAI - I BLOCK PHASE II , SM/08758 | Retrofitting | Retrofitting to accomodate FHTC (220 nos.) under JJM IN Damudarpur PWSS under Contai-I Block of Contai Sub-Division under Tamluk Division, PHE Dte. (PHASE-II) | 687/TD | 10/09/2021 | 20 | MAA ANANDAMAYEE | 16.62 | 15.68 | 94.31 | 96
84 | PURBA MEDINIPUR | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Chirulia PWSS under Egra II Block (Phase-II) , SM/09054 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Chirulia PWSS Block - Egra-II in the District of Purba Medinipur. (PHASE- II) | 1014/TD | 02/11/2021 | 30 | FIROZ KHAN | 44.75 | 43.55 | 97.31 | 100
85 | PURBA MEDINIPUR | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Chirulia PWSS under Egra II Block (Phase-II) , SM/09054 | Retrofitting | Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | 2209/TD | 01/09/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 3 | 100 | 100
86 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Jinandapur AWC (19345250319), G.P- Badalpur, (ii) Balarampur AWC (19345250323), G.P- Maitana, (iii) Uttar Kalindi AWC (19345250401), G.P- Kalindi, (iv) Kalindi Basti AWC (19345250405), G.P- Kalindi, (v) Purbabarh Manodamoyee AWC (19345250406), G.P- Kalindi, (vi) Teghari ICDS Centre (19345250409), G.P- Kalindi, (vii) Demuria Paikbar AWC (19345250510), G.P- Maitana, (viii) Mandarpur Pry. School(OWN) (19345250516), G.P- Maitana. | 1398/TD | 28/12/2021 | 45 | MAITY CONSTRUCTION | 23.94 | 22.03 | 100 | 100
87 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Patashpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Kaijuddin para-06 (19345220406), G.P- Amarshi 7/1, (ii) Amarshi Kasba-08 (19345220408), G.P- Amarshi 7/1, (iii) Amarshi(e)muslimpara-12 (19345220412), G.P- Amarshi 7/1, (iv) Barsankar-01 (19345220501), (v) Sanamginga-03 (19345220503), G.P- Amarshi 7/2, (vi) Bantitaka-06 (19345220506), (vii) Gumraveri-07 (19345220507), G.P- Amarshi 7/2, (viii) Taladiha-2-08 (19345220508), G.P- Amarshi 7/2. | 1403/TD | 28/12/2021 | 45 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.23 | 21 | 100 | 100
88 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakkhin Amtalia Anathbandhu A.W.C. (19345050907), G.P- Amtalia, (ii) Kasafalia A.W.C. (19345050105), G.P- Amtalia, (iii) Aurai Kacharibari A.W.C. (19345050301), G.P- Aurai, (iv) Chhanberya A.W.C. (19345050121), G.P- Aurai, (v) Uttar Basudebberya Bramhanarayan A.W.C. (19345050307), G.P- Aurai, (vi) Namaldiha Mother Teresa A.W.C. (19345050302), G.P- Aurai, (vii) Uttar Karpura Keshabchandra A.W.C. (19345050315), G.P- Aurai, (viii) Sarsa A.W.C. (19345050610), G.P- Bamunia. | 1360/TD | 24/12/2021 | 45 | PARIA ENTERPRISE | 24.53 | 23.27 | 100 | 100
89 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 250 mt.) along with stand post at different Sourceless AWC under Contai-III Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Khalsiberia AWC (19345060125), (ii) Marishda AWC (19345060524), G.P- Marishda, (iii) Dakhsin Sukunia (19345060310), (iv) Sukunia Uttar (19345060312), (v) Jagudasbar AWC (19345060413). | 1361/TD | 24/12/2021 | 35 | JASODA ENTERPRISE | 16.04 | 14.11 | 100 | 100
90 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Tamluk Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) HOUSE OF SADHAN KUILA,JASADUMBUR (19345281114). G.P- Bishnubarh-I, (ii) MAISALI MAHILA SAMITY HOUSE (19345281118), G.P- Bishnubarh-I, (iii) GHOLECHAK VIJOY PRY. SCH. (19345281119),G.P- Bishnubarh-I, (iv) AMGECHHIA SITALA AWC (19345280915),G.P- Bishnubarh-I, (v) BAHICHARD DAKSHIN PALLI AWC (19345280917),G.P- Bishnubarh-I. | 1357/TD | 24/12/2021 | 35 | BHOLANATH DEY | 14.22 | 14.09 | 100 | 100
91 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakshin Veribaranga AWC (19345250122), G.P- Paldhui, (ii) Uttar Kanpur Awc (19345250206), G.P- Depal, (iii) Tajpur AWC (19345250307), G.P- Badalpur, (iv) Badalpur Tarun Sangha Awc (19345250313), G.P- Badalpur. | 1505/TD | 06/01/2022 | 30 | TAPAN BERA | 11.98 | 11.5 | 100 | 100
92 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Block: (i) Sukrasoni (19345240211), G.P- Haldia-I, (ii) Dikshal (19345240216), G.P- Haldia-I, (iii) Khairanda-3 (19345240218), G.P- Haldia-I, (iv) Bandhmuri (19345240219), G.P- Haldia-I, (v) Gangra-1 (19345240312), G.P-Haldia-II, (vi) Gangra-2 (19345240315), G.P- Haldia-II, (vii) Ranisai-2 (19345240322), G.P- Haldia-II, (viii) Koniora-3 (19345240323), G.P- Haldia-II. | 1396/TD | 28/12/2021 | 45 | PALCON | 24.7 | 21.07 | 100 | 100
93 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 03 (Three) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Gopalpur (19345240720), G.P- Talgachari-II, (ii) Nariha-2 (19345240802), G.P- Talgachari-I, (iii) Jamra (19345240819), G.P- Talgachari-II. | 1397/TD | 28/12/2021 | 25 | SAYAN MAITY | 9.31 | 8.34 | 100 | 100
94 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 39,Rasan Chakbandi FpSchool 23 (19345070323), G.P- Chhatri, (ii) 40,Rasan Own AWC 25 (19345070325), G.P-G.P- Chhatri. | 1400/TD | 28/12/2021 | 20 | GRAND CONSTRUCTION | 5.55 | 5.53 | 100 | 100
95 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 28,Baranihari Ramkrishna Seba Sangha 05 (19345070305), G.P- Chhatri, (ii) 30,Ramkrishnapur AWC 03 (19345070303), G.P- Chhatri, (iii) 31, Sannihari Own AWC 14 (19345070314), G.P- Chhatri, (iv) 133, Arjuni ICJCK 21 (19345070821), G.P- Jumki, (v) 134, Hansaria AWC (19345070725), G.P- Jumki, (vi) 136, Chaulda AWC (19345070727), G.P- Jumki,, (vii) 137, Nischinta AWC 27 (19345070827), G.P- Jumki, (viii) 62, Benachakri Mandalpara 24 (19345070424), G.P- Jerthan. | 1399/TD | 28/12/2021 | 45 | AJIT KUMAR SOM | 22.24 | 22.15 | 100 | 100
96 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Benagolisa Tapas Mandal House (19345200609), G.P- Gobindanagar, (ii) Ratulia Jr. Basic School (19345200501), G.P- Gobindanagar, (iii) Paschim Arjunda Pry. (19345200502), G.P- Gobindanagar,, (iv) Paschim Nekra Pry. School (19345200505), G.P- Gobindanagar, (v) Joykrishnapur I.C.J.C.K. (19345200507),G.P- Gobindanagar, (vi) Dharmapore Asharam (19345200508), G.P- Gobindanagar, (vii) Manur Pry. School (19345200611), (viii) Golghat Pry. School (19345200613), G.P- Gobindanagar. | 1356/TD | 24/12/2021 | 45 | MADAN MOHAN MAITY | 22.79 | 22.56 | 100 | 100
97 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Moyna Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakshin Moyna Badurtala (19345140202), G.P- Moyna-II,(ii) Dakshin Moyna Dangisai (19345140215), G.P- Moyna-II, (iii) P D Moyna (19345140216), G.P- Moyna-II, (iv) Radhaballabh Chak (19345140509), G.P- Gokulnagar. | 1358/TD | 24/12/2021 | 30 | JAGANNATH MAKAR | 12.4 | 12.4 | 100 | 100
98 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Mahapur Pry. School G.P. Gobindanagar. (ii) Bijaharpur Nabarun Sangha ( 19345200604), G.P- Gobindanagar, (iii) Rajnagar Pry. School (19345200605), G.P- Gobindanagar, (iv) Anupganj Pry. School (19345200606), G.P- Gobindanagar, (v) Gobindanagar Pry. School(19345200607), G.P- Gobindanagar. | 1502/TD | 06/01/2022 | 35 | BARH CONSTRUCTION | 14.25 | 13.5 | 100 | 100
99 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Purba Gurgram-2 No. ICDS (19345010314), G.P- Gurgram, (ii) Amratala AWC (19345010213), G.P- Gurgram. | 1407/TD | 28/12/2021 | 20 | BADAL CHANDRA GOLE | 6.06 | 5.99 | 100 | 100
100 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dhelua AWC (19345020309), G.P- Jukhia, (ii) Bani Mandir AWC (19345020312), G.P- Jukhia. | 1363/TD | 24/12/2021 | 20 | DHANANJOY DAS | 6.05 | 5.61 | 100 | 100
101 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 64,Kiya Nonformal School 22 (19345070422), G.P- Jerthan, (ii) 66, Ashada 19 (19345070419), G.P- Jerthan, (iii) 59, Satkhanda FP School 02 (19345070402), G.P- Jerthan, (iv) 38,Chhatri Bhatgeria 06 (19345070306), G.P- Chhatri. | 1365/TD | 24/12/2021 | 30 | M/S. S. A. CONSTRUCTION | 11.1 | 11.07 | 100 | 100
102 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 240 mt.) along with stand post at different Sourceless AWC under Patashpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Muradpur AWC (19345230101), G.P- Khar, (ii) Manpur AWC (19345230102), G.P- Khar, (iii) Girisha AWC (19345230104), G.P- Khar, (iv) Gangasagar AWC (19345230105), G.P- Khar, (v) Mustafapur Dakshin AWC (19345230107), G.P- Khar, (vi) Bar Mustafapur AWC (19345230108), G.P- Khar, (vii) Panchet Uttar AWC (19345230206), G.P- Panchet-04, (viii) Panchet Daksin AWC (19345230207) | 1404/TD | 28/12/2021 | 45 | GIRI CONSTRUCTION | 25.08 | 24 | 100 | 100
103 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Paschimbarh-2 No. ICDS (19345010102), G.P- Mahammadpur-I, (ii) Paschimbarh-3 No. ICDS (19345010103), G.P- Mahammadpur-I, (iii) Uttarbarh-1 No ICDS (19345010104), G.P- Mahammadpur-I, (iv) Sekbarh ICDS (19345010105), G.P- Mahammadpur-I, (v) Mahammadpur-2 No. ICDS (19345010107), G.P- Mahammadpur-I, (vi) Sribachhipur-1 No. ICDS (19345010108), G.P- Mahammadpur-I, (vii) Nimakbarh-2 No. ICDS (19345010113),G.P- Mahammadpur-I, (viii) Uttarbarh-3 No. ICDS (19345010114), G.P- Mahammadpur-I. | 1506/TD | 06/01/2022 | 45 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.25 | 23.52 | 100 | 100
104 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 240 mt.) along with stand post at different Sourceless AWC under Patashpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Nimja AWC (19345230213), G.P- Panchet-04, (ii) Bamunda-II AWC (19345230307), G.P- Panchet-04, (iii) Etachana AWC (19345230309), G.P- Panchet-04, (iv) Motirampur AWC (19345230310), G.P- Patashpur-05. | 1405/TD | 28/12/2021 | 30 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12.55 | 11.45 | 100 | 100
105 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Rasulpur A.W.C. (19345050911), G.P- Basantia, (ii) Tengorerya Ma Ballavi A.W.C. (19345051007), G.P- Basantia, (iii) Kultalia Paschimpara A.W.C. (19345050915), G.P- Basantia, (iv) Dakkhin Deulpota Subhashchandra A.W.C. (19345051009), G.P- Basantia, (v) Gokulnagar A.W.C. ( 19345050916), G.P- Basantia, (vi) Kalikakumari Vivekananda A.W.C. (19345051010), G.P- Basantia, (vii) Purba Mahammadpur Jana Para A.W.C. (19345051005), G.P- Basantia, (viii) Kultalia Purba Para A.W.C. (19345050914), G.P- Basantia. | 1394/TD | 28/12/2021 | 45 | M/S SREE DURGA ENTERPRISE | 24.51 | 24.23 | 100 | 100
106 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakshin Veribaranga AWC (19345250102), G.P- Paldhui, (ii) Kanwa ICDS (19345250105), G.P- Paldhui, (iii) Purba Paldhui AWC (19345250108), G.P- Paldhui, (iv) Uttar Sabitrapur AWC (19345250116), G.P- Paldhui. | 1504/TD | 06/01/2022 | 30 | SUDIP MANNA | 11.98 | 11.05 | 100 | 100
107 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Bikra Khan Para (19345200216), G.P- Mysora, (ii) Sahalajpur (Chotto Bhim Para) (19345200218), G.P- Mysora, (iii) Mysora Paschim Muslim Para (19345200124), G.P- Mysora, (iv) Gobindanagar Kali Mandir (19345200603), G.P- Gobindanagar. | 1896/TD | 23/02/2022 | 30 | TARUN KHATUA | 11.39 | 11.29 | 100 | 100
108 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Sikarput A.W.C. (19345050705), G.P- Bamunia, (ii) Choudhuribar A.W.C. (19345051011), G.P- Basantia, (iii) Mukundapur Paschim Para A.W.C. (19345051018), G.P- Basantia, (iv) Basantia Mago Mandir A.W.C. (19345051012), G.P- Basantia. | 1897/TD | 23/02/2022 | 30 | FARID UDDIN AHMED | 12.26 | 12.16 | 100 | 100
109 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Patashpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Panchuria-2-12 (19345220512), G.P- Amarshi-7/2, (ii) Taladiha-3-13 (19345220513), G.P- Amarshi-7/2. | 1848/TD | 16/02/2022 | 20 | SK. SAHALAM | 5.55 | 5.19 | 100 | 100
110 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 240 mt.) along with stand post at different Sourceless AWC under Patashpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Kamalpur AWC (19345230311), G.P- Patashpur-05, (ii) Shikhoda AWC (19345230319), G.P- Patashpur-05, (iii) Morirampur Uttar Awc (19345230322), G.P- Patashpur-05, (iv) Tupchibarh- III AWC (19345230327), G.P- G.P- Patashpur-05. | 1849/TD | 16/02/2022 | 30 | ELECTIVA ENTERPRISE | 12.43 | 11.24 | 100 | 100
111 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Porachingra AWC (19345020102), G.P- Garbari-I, (ii) Jhinuk-khali Madhyapally AWC (19345020117), G.P- Garbari-I, (iii) Paschim Garbari AWC (19345020216), G.P- Garbari-II, (iv) Kutubuddinpur AWC (19345020302), G.P- Jukhia, (v) Madhakhali Primary School (19345020303), G.P- Jukhia, (vi) Sitadighi Primary School (19345020305), G.P- Jukhia, (vii) Jukhia AWC (19345020307), G.P- Jukhia, (viii) Jukhia Sitadhighi Primary School (19345020308), G.P- Jukhia. | 1939/TD | 02/03/2022 | 45 | DAS ENTERPRISE | 24.24 | 23.02 | 100 | 100
112 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 17,Batashpur FP School 15 (19345070115), G.P- Barida, (ii) 10, Barida Banikishor Sangha 11, (19345070111), G.P- Barida, (iii) 11, Khalina ICJCK 17 (19345070117), G.P- Barida, (iv) 12,Khalina Own Awc 13 (19345070113), G.P- Barida, (v) 13, Madhabpur FP School 16 (19345070116), G.P- Barida, (vi) 194,Sekhpara,Jerthan 08 (19345070408), G.P- Jerthan, (vii) 2, Swarrang Narayan Das'House 06 (19345070106), G.P- Barida, (viii) 190,Sannihari Dhananjoy Patra 15 (19345070315). G.P- Chhatri. | 1364/TD | 24/12/2021 | 45 | S.D. CONSTRUCTION | 22.23 | 22.14 | 100 | 100
113 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 270 mt.) along with stand post at different Sourceless AWC under Nandigram-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Amdabad Uttar AWC (19345160504), G.P- Amdabad-I, (ii) Amdabad Purba chara AWC (19345160618), G.P- Amdabad-I, (iii) Amdabad Madhya AWC (19345160502), G.P- Amdabad-I, (iv) Subdi N. State Plan AWC (19345160514), G.P- Amdabad-I, (v) Amdabad 2 N0.AWC (19345160516), G.P- Amdabad-I, (vi) Hanubhuiya Uttar AWC (19345160420),G.P- Birulia, (vii) Sibrampur AWC (19345160422), G.P- Birulia, (viii) Gholpukur Dakshin AWC (19345160409), G.P- Birulia. | 1359/TD | 24/12/2021 | 45 | NARAYAN CHANDRA DAS | 26.82 | 25.2 | 100 | 100
114 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Chandanpur-1 (19345240116), G.P- Badhia, (ii) South Badhia-3 (19345240121), G.P- Badhia, (iii) Dangri Patna (19345240125), G.P- Badhia, (iv) Damodarpur Paschim (19345240203), G.P- Badhia, (v) Sadi (19345240207), G.P- Haldia-I, (vi) Kholaberia (19345240208), G.P- Haldia-I, (vii) Nilkanthapur (19345240209), G.P- Haldia-I, (viii) Rania (19345240210), G.P- Haldia-I. | 1938/TD | 02/03/2022 | 45 | AYSAN KHAN | 24.8 | 21.96 | 100 | 100
115 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 1.0 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at Sourceless School under Ramnagar-I Dev. Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: Ghersai SSK, G.P- Padima-II, Mouza - Ghersai, J.L. No.- 88 | 138/RWS/TSD | 14/06/2022 | 7 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 2.97 | 2.62 | 100 | 100
116 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 1.0 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at Sourceless AWC under Ramnagar-I Dev. Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: Dakshin Badhia AWC, G.P- Badhia, Mouza - Badhia, J.L. No.- 06 | 135/RWS/TSD | 14/06/2022 | 7 | GRAND CONSTRUCTION | 2.98 | 2.59 | 100 | 100
117 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 210 mt.) along with stand post at different Sourceless AWC under Egra-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Narubhuiachak ICDS (19345080410), G.P- Bathuary, (ii) Jaganathkarbar Sunrise ICDS ( 193450805414), G.P- Bathuary, (iii) Bhatda Haripur Youth Club (19345080101), G.P- Manjushree, (iv) Bhatda Palli Mongal ICDS (19345080102), G.P- Manjushree. | 1402/TD | 28/12/2021 | 30 | DEBABRATA DAS | 11.69 | 11.63 | 100 | 100
118 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 210 mt.) along with stand post at different Sourceless AWC under Egra-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Rukminipur ICDS Centre (19345080302), G.P- Deshbandhu, (ii) Eranda Binapani Club (19345080306), G.P- Deshbandhu, (iii) Kirtipur Bhai Bhai Sangha (19345080307), G.P- Deshbandhu, (iv) Rajendrachak Matsya Jibi Yuva Kalyan Sangha (19345080501), G.P- Deshbandhu, (v) Urijalkar Martri Sakti Sangha (19345080310), G.P- Deshbandhu, (vi) Sarisa Jagrata Yuva Sangha (19345080203), G.P- Deshbandhu, (vii) Hurkuchia Sourav Club (19345080503), G.P- Deshbandhu, (viii) Eranda Haripriya Seba Sangha (19345080309), G.P- Deshbandhu. | 1401/TD | 28/12/2021 | 45 | ABHIJIT BERA | 23.38 | 23.29 | 100 | 100
119 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Uttar Tiraipur AWC (19345010201), G.P- Mahammadpur-II, (ii) Benauda 1 No. ICDS (19345010203), G.P- Mahammadpur-II, (iii) Goalapukur AWC (19345010208), G.P- Mahammadpur-II, (iv) Garbhera South ICDS (19345010214), G.P- Gurgram (v) Purba Gurgram-1 No. ICDS (19345010302), G.P- Gurgram, (vi) Dakshin Gurgram ICDS (19345010304), G.P- Gurgram, (vii) Fatepur ICDS (19345010312), G.P- Gurgram, (viii) Buraburi-2 No.ICDS (19345010313), G.P- Gurgram. | 1406/TD | 28/12/2021 | 45 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.23 | 23.51 | 100 | 100
120 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Saiadpur (19345240701), G.P- Talgachari-I, (ii) Uttar Bagpura (19345240712), G.P- Talgachari-I, (iii) Bagpura-2 (19345240714), G.P- Talgachari-I, (iv) Ramnagar (19345240718), G.P- Talgachari-I. | 1503/TD | 06/01/2022 | 30 | SWADHIN KUMAR CHAKRABORTY | 12.43 | 11.57 | 100 | 100
121 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 07 (Seven) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Bakshishpur AWC (19345250519), G.P- Maitana, (ii) Dakshin Tentultala AWC (19345250522), G.P- Maitana, (iii) Dakshin Maitana AWC (19345250525), G.P- Maitana, (iv) Satilapur AWC (19345250604), G.P- Sitalapur, (v) Purba Satilapur AWC (19345250605), G.P- Sitalapur, (vi) Purba Ghole AWC (19345250622), G.P- Sitalapur, (vii) Bararankua Harijan AWC (19345250716), G.P- Balisai. | 1362/TD | 24/12/2021 | 45 | MRINAL KANTI PRADHAN | 20.96 | 19.36 | 100 | 100
122 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 07 (Seven) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Purba Kusbani A.W.C. (19345050919), G.P- Basantia, (ii) Baghaghole Vivekananda A.W.C. (19345050620), G.P- Chalti, (iii) Dakkhin Kalikapur A.W.C. (19345050619), G.P- Chalti, (iv) Nanker Gopinathpur A.W.C. ( 19345050804) G.P- Dariapur, (v) Chitanyapur A.W.C. (19345050818), G.P- Dariapur, (vi) Haripur A.W.C. (19345050812), G.P- Dariapur, (vii) Uttar Deulpota Padmabati A.W.C. (19345050202), G.P- Dhobaberya. | 1395/TD | 28/12/2021 | 45 | SUBRATA KUMAR BERA | 21.46 | 21.14 | 100 | 100
123 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Charaput A.W.C. (19345050612), G.P- Bamunia, (ii) Murabenia Maktab A.W.C. (19345050617), G.P- Bamunia, (iii) Dakshin Kadua A.W.C. (19345050706), G.P- Bamunia (iv) Uttar Kadua Vivekananda A.W.C. (19345050708), G.P- Bamunia. | 1898/TD | 23/02/2022 | 30 | SUBHRANGSHU SEKHAR GIRI | 12.25 | 11.62 | 94.88 | 100
124 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Paschim Bakulda Dashibard AWC (19345200204), G.P- Mysora, (ii) Radhaballavpur P.L.C. (19345200208), G.P- Mysora, (iii) Bikra Pry. School (19345200209), G.P- Mysora, (iv) Rajshar AWC (19345200113), G.P- Mysora, (v) Paschim Shyampur (19345200115), G.P- Mysora, (vi) Purba Mysora Club (19345200117), G.P- Mysora, (vii) Balarampur S.S.K. (19345200211), G.P- Mysora, (viii) Gopal Hazra SSK (19345200213),G.P- Mysora. | 1937/TD | 02/03/2022 | 45 | BIDHAN MONDAL | 22.81 | 21.39 | 100 | 100
125 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 210 mt.) along with stand post at different Sourceless AWC under Egra-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Shilampur Swamiji Seba Sangha ( 19345080519), G.P- Vivekananda, (ii) Uttar Eranda Tapsili Sangha (19345080315), G.P- Deshbandhu, (iii) Nijdant Tarun Sangha (19345080316), G.P- Bathuary, (iv) Dakshin Chowmukh ICDS ( 19345080507), G.P- Bathuary, (v) Gangadharbar ICDS Center (19345080508), G.P- Bathuary. | 1366/TD | 24/12/2021 | 35 | ANUPAM CONSTRUCTION | 14.59 | 14.3 | 100 | 100
126 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Sinking of 1(One) nos. 100 mm X 50 mm dia. X 220.0 m(av.) depth Indian Mark-II tube well with PVC pipes including cost of all materials and construction of Platform (as per Departtl. approved drawing) at ''Tamralipta Mahavidyalaya'' due to scarcity of drinking water in a newly constructed three- storied building under Tamluk Sub Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 626/TD | 17/05/2023 | 15 | GLOBAL TRADE | 2.29 | 2.16 | 100 | 100
127 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Diesel Motor Cab/Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage IV) on daily rate basis for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, PHE Dte. from 01.07.2023 to 31.12.2023 (Six) Months. | 1299/TD | 30/06/2023 | 184 | JOY MAA TARA TRAVELS & TRANSPORT | 0.87 | 1.91 | 100 | 100
128 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Continuation work order for hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily rate basis (as and when required including Govt. Holiday) for the period from 01.06.2023 to 30.06.2023 i.e. 01 (one) month only, having contract carriage permit from Regional Transport Authority for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. (Ref:- Memo No.- 375/RWS/TSD Dated, 30/11/2022 | 54/RWS/TSD | 19/05/2023 | 30 | SRIMANTA PANJA | 0.14 | 0.38 | 100 | 100
129 | PURBA MEDINIPUR | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. , SM/08698 | New | Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.07.2024 to 31.12.2024 i.e. 06 (Six) Months for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. | 104/RWS/TSD | 28/06/2024 | 184 | HALADHAR SAMANTA | 0.87 | 2.03 | 232.16 | 50
130 | PURBA MEDINIPUR | Tamluk Division | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Sinking of 300 mm. x 200 mm. dia. x 240 mtr. deep tube well by direct rotary rig method at of 1st Tubewell Site of Shyampur Water Supply Scheme within under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 1995/TD | 07/03/2022 | 21 | AQUATECH ENGINEERS | 15.11 | 14.07 | 100 | 100
131 | PURBA MEDINIPUR | Tamluk Division | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Construction of M.S. Structure over drainage canal to support different dia DI(K-7) distribution pipe & 150 mm dia. DI(K-9) rising main pipe under Shyampur Water Supply Scheme at different Nodal Point within Moyna Block under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte. | 271/TD | 02/05/2022 | 30 | RAJ KUMAR SINGHA | 17.62 | 15.54 | 100 | 100
132 | PURBA MEDINIPUR | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Electic quotation bill at Moyna CCC for T/W -I Shyampur Water supply scheme under MMD PHE Dte. | 2003984006/QUOT/1017 | 05/07/2022 | 365 | WBSEDCL | 0.56 | 0 | 0 | 0
133 | PURBA MEDINIPUR | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Electic quotation bill at Moyna CCC for T/W -II Shyampur Water supply scheme under MMD PHE Dte. | 2003984015/QUOT/1016 | 05/07/2022 | 365 | WBSEDCL | 0.56 | 0 | 0 | 0
134 | PURBA MEDINIPUR | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. , SM/08878 | New | New Service Connection Full Deposit Scheme, T/W-I of Shyampur Water supply scheme under MMD PHE Dte. | MNA/QUT/22-23/NSC/PHE/201 | 08/07/2022 | 365 | WBSEDCL | 1.86 | 0 | 0 | 0
135 | PURBA MEDINIPUR | Central Drilling | Shyampur Piped Water Supply Scheme. , SM/08878 | New | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE FOR CONSTRUCTION OF TUBE WELL IN PURBA MEDINIPUR DIST. UNDER CDD, PHE DTE. | 241/CMSD-II (D) | 20/05/2022 | 15 | MENAKA ENTERPRISE | 2.42 | 1.74 | 100 | 100
136 | PURBA MEDINIPUR | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. , SM/08878 | New | New service connection PHE Full deposite scheme for T/W -II of Shyampur Water supply scheme under MMD PHE Dte. | MNA/QUT/22-23/NSC/PHE/101 | 08/07/2022 | 365 | WBSEDCL | 1.42 | 0 | 0 | 0
137 | PURBA MEDINIPUR | Central Drilling | Shyampur Piped Water Supply Scheme. , SM/08878 | New | PROVIDING TUBE WELL MATERIALS OF 200 MM NOMINAL DIA, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | 244/CMSD-II (D) | 20/05/2022 | 15 | MENAKA ENTERPRISE | 3.85 | 2.77 | 100 | 100
138 | PURBA MEDINIPUR | Central Drilling | Shyampur Piped Water Supply Scheme. , SM/08878 | New | SINKING OF 300 MM X 200 MM DIA X 240 MTRS DEPTH TUBE WELL IN PURBA MEDINPUR DISTRICT UNDER CDD, PHE DTE. | 242/CMSD-II (D) | 20/05/2022 | 15 | MENAKA ENTERPRISE | 3.18 | 3.05 | 100 | 100
139 | PURBA MEDINIPUR | Central Drilling | Shyampur Piped Water Supply Scheme. , SM/08878 | New | PROVIDING TUBE WELL MATERIALS OF 300 MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | 243/ CMSD-II (D) | 20/05/2022 | 15 | MENAKA ENTERPRISE | 4.9 | 4.9 | 100 | 100
140 | PURBA MEDINIPUR | Central Drilling | Shyampur Piped Water Supply Scheme. , SM/08878 | New | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | 214/CMSD-I(D) | 09/11/2021 | 15 | PADMA ENGINEERING & CO. | 4.52 | 0.55 | 100 | 0
141 | PURBA MEDINIPUR | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. , SM/08878 | New | New Servic Connection Full Deposit Scheme, T/W-I of Shyampur Water supply scheme under MMD PHE Dte. | BP-2022-23-29 | 10/08/2022 | 0 | WBSEDCL | 1.86 | 0 | 0 | 0
142 | PURBA MEDINIPUR | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Electic quotation bill at Moyna CCC for T/W -II Shyampur Water supply scheme under MMD PHE Dte. | BP-2022-23-30 | 10/08/2022 | 0 | WBSEDCL | 0.56 | 0 | 0 | 0
143 | PURBA MEDINIPUR | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Electic quotation bill at Moyna CCC for Shyampur Water supply scheme under MMD PHE Dte. | BP-2022-23-32 | 11/08/2022 | 0 | WBSEDCL | 1.42 | 0 | 0 | 0
144 | PURBA MEDINIPUR | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Electic quotation bill at Moyna CCC for T/W -I Shyampur Water supply scheme under MMD PHE Dte. | BP-2022-23-28 | 10/08/2022 | 0 | WBSEDCL | 0.56 | 0 | 0 | 0
145 | PURBA MEDINIPUR | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-I under Shyampur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | 1863/W/MMD | 22/09/2022 | 120 | PRANAB KUMAR DAS | 12.66 | 11.9 | 93.96 | 100
146 | PURBA MEDINIPUR | Tamluk Division | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Material Requisition To Resource Division | 1284/TD | 15/12/2021 | 0 | Resource Division | 33.3 | 0 | 0 | 0
147 | PURBA MEDINIPUR | Tamluk Division | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Material Requisition To Resource Division | 1474/TD | 03/01/2022 | 0 | Resource Division | 14.11 | 0 | 0 | 0
148 | PURBA MEDINIPUR | Tamluk Division | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Material Requisition To Resource Division | 1680/TD | 28/01/2022 | 0 | Resource Division | 3.98 | 0 | 0 | 0
149 | PURBA MEDINIPUR | Tamluk Division | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 500 Cum and staging height 20.00 mtr. with allied work under Shyampur & its adjoining mouzas Water Supply Scheme within Moyna Dev. Block including supply of all labour & materials under Tamluk sub-division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | 1092/TD | 17/11/2021 | 210 | RAJ KUMAR SINGHA | 521.85 | 484.18 | 100 | 100
150 | PURBA MEDINIPUR | Tamluk Division | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Interconnection with laying of 150 mm dia DI (K-9) Rising main From 1st & 2nd Tube Well Site to O.H.R. and other allied works at Shyampur PWSS Water Supply Scheme within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1425/TD | 26/09/2022 | 15 | MAHAMAYA TIMBER AND CONSTRUCTION | 3.91 | 3.04 | 100 | 100
151 | PURBA MEDINIPUR | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. , SM/08878 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-II under Shyampur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | 2111/W/MMD | 28/11/2022 | 120 | ECO ENTERPRISE | 12.68 | 12.42 | 100 | 100
152 | PURBA MEDINIPUR | Central Drilling | Baharampur Piped Water Supply Scheme. , SM/08879 | New | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BAHARAMPUR PWSS, BLOCK- BHAGAWANPUR-II UNDER CDD, PHE DTE. | 305/CMSD-I | 08/07/2022 | 15 | MENAKA ENTERPRISE | 4.89 | 4.18 | 85.44 | 100
153 | PURBA MEDINIPUR | Tamluk Division | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Laying of Distribution pipe line , Construction of Pump House & Boundary Wall, Construction of RCC Over Head Reservoir of Capacity 450 Cum, Sub -Soil Investigation with allied works of Baharampur & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 1091/TD | 17/11/2021 | 210 | TAPAS SANTRA | 526.12 | 429.67 | 81.67 | 95
154 | PURBA MEDINIPUR | Tamluk Division | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Supply & Delivery of 80 mm dia Sluice Valve for Baharampur piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 1687/TD | 31/01/2022 | 15 | SANTRA ENTERPRISE. | 4.01 | 4.01 | 100 | 100
155 | PURBA MEDINIPUR | Tamluk Division | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Supply & Delivery of 125 mm, 150 mm,200 mm & 250 mm dia Sluice Valve for Baharampur piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 1688/TD | 31/01/2022 | 15 | SANTRA ENTERPRISE. | 3.81 | 3.81 | 100 | 100
156 | PURBA MEDINIPUR | Tamluk Division | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Construction of Culvert with Wing-wall & Toe wall for Approach Road at 1st TW / Head Work Site ( Mouza- Kalmichhabar ,J.L. No-317, Plot No- 599), for Baharampur Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur,PHE Dte. | 1682/TD | 28/01/2022 | 45 | BIBEKANANDA DAS | 6.41 | 6.4 | 100 | 100
157 | PURBA MEDINIPUR | Tamluk Division | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Construction of Culvert with Wing-wall & Toe wall for Approach Road at 2nd TW Site ( Mouza- Jethaibari ,J.L. No-307, Plot No- 106), for Baharampur Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur, PHE Dte. | 1683/TD | 28/01/2022 | 45 | BIBEKANANDA DAS | 6.41 | 6.4 | 100 | 100
158 | PURBA MEDINIPUR | Tamluk Division | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at of 2nd Tubewell Site of Baharampur Water Supply Scheme within under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 1994/TD | 07/03/2022 | 21 | AQUATECH ENGINEERS | 14.76 | 10.39 | 100 | 100
159 | PURBA MEDINIPUR | Central Drilling | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Providing Tube Well Materials conforming to IS : 12818:2010 with other works at site for construction of tube well at Baharampur PWSS, Block - Bhagawanpur-II under CDD, PHE Dte. | 305/CMSD-I(D) | 08/07/2022 | 15 | MENAKA ENTERPRISE | 4.89 | 0.08 | 100 | 100
160 | PURBA MEDINIPUR | Central Drilling | Baharampur Piped Water Supply Scheme. , SM/08879 | New | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL & OTHER MATERIALS AT BAHARAMPUR PWSS, BLOCK-BHAGAWANPUR-II BY UTILIZING DEPARTMENTAL MACHINERIES UNDER CDD, PHE DTE. | 303/CMSD-I | 08/07/2022 | 15 | MENAKA ENTERPRISE | 3.76 | 1.51 | 100 | 100
161 | PURBA MEDINIPUR | Central Drilling | Baharampur Piped Water Supply Scheme. , SM/08879 | New | SUPPLY AND DELIVERY OF BRICKS BATS WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BAHARAMPUR PWSS, BLOCK- BHAGAWANPUR-II UNDER CDD, PHE DTE. | 246/CMSD-II | 23/05/2022 | 10 | MENAKA ENTERPRISE | 0.57 | 0.57 | 100 | 100
162 | PURBA MEDINIPUR | Central Drilling | Baharampur Piped Water Supply Scheme. , SM/08879 | New | ADDITIONAL WORKS FOR CONSTRUCTION OF TUBE WELL & OTHER MATERIALS AT SITE FOR BAHARAMPUR PWSS, BLOCK BHAGAWANPUR-II BY UTILIZING SKILLED DRILLING CREW & DEPARTMENTAL MACHINERIES UNDER CDD, PHE DTE. | 304/CMSD-I | 08/07/2022 | 15 | MENAKA ENTERPRISE | 4.9 | 3.68 | 100 | 100
163 | PURBA MEDINIPUR | Central Drilling | Baharampur Piped Water Supply Scheme. , SM/08879 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAHARAMPUR W/S SCH (TW-I), BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 380/CDD | 17/05/2022 | 30 | MENAKA ENTERPRISE | 14.69 | 5.64 | 100 | 100
164 | PURBA MEDINIPUR | Midnapore Mechanical | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Electric quotation MADHAKHALI CCC at Baharampur T/W-II Pin-721444 | BP-2022-23-60 | 23/11/2022 | 0 | WBSEDCL | 0.61 | 0 | 0 | 0
165 | PURBA MEDINIPUR | Midnapore Mechanical | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-2 under Baharampur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | 2112/W/MMD | 28/11/2022 | 120 | ALPHA ENTERPRISE | 10.92 | 8.34 | 100 | 100
166 | PURBA MEDINIPUR | Tamluk Division | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Laying of 150 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials in between 1st Tube well to 2nd Tube Well of Baharampur & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 295/TD | 20/04/2023 | 30 | SUBHENDU HAZRA | 3.71 | 2.91 | 100 | 100
167 | PURBA MEDINIPUR | Midnapore Mechanical | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Supply delivery of Voltage Stabilizer and submersible pump motor set at PH No. II of Baharampur Water Supply Scheme under H.E.S.D. under Midnapore Mechanical Division, P.H.E. Dte. | 291/MMSD-I | 23/03/2023 | 10 | ALPHA ENTERPRISE | 3.06 | 3.06 | 100 | 100
168 | PURBA MEDINIPUR | Tamluk Division | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Material Requisition To Resource Division | 1283/TD | 15/12/2021 | 0 | Resource Division | 3.37 | 0 | 0 | 0
169 | PURBA MEDINIPUR | Tamluk Division | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Material Requisition To Resource Division | 1475/TD | 03/01/2022 | 0 | Resource Division | 12.61 | 0 | 0 | 0
170 | PURBA MEDINIPUR | Tamluk Division | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Material Requisition To Resource Division | 81/TD | 08/04/2022 | 0 | Resource Division | 21.16 | 0 | 0 | 0
171 | PURBA MEDINIPUR | Midnapore Mechanical | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Electric quotation for Baharampur PWSS Tube Well- I in connection Madhakhali CCC (2004185409) | BP-2022-23-105 | 27/02/2023 | 0 | WBSEDCL | 0.47 | 0 | 0 | 0
172 | PURBA MEDINIPUR | Tamluk Division | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Retrofitting to accommodate FHTC under JJM in Baharampur PWSS Block - Bhagwanpur-II in the District of Purba Medinipur. | 2959/TD | 24/11/2023 | 25 | S.D. CONSTRUCTION | 51.79 | 37.96 | 73.3 | 85
173 | PURBA MEDINIPUR | Midnapore Mechanical | Baharampur Piped Water Supply Scheme. , SM/08879 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Baharampur Piped Water Supply Scheme., Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 35/W/MMD | 04/01/2023 | 180 | SUJOY RANJAN BHOWMICK | 13.58 | 11.58 | 87.48 | 100
174 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Basudebberya Water Supply Scheme under Tamluk Division, PHE Dte. | 1185/TD | 02/12/2021 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 12.84 | 9.56 | 100 | 100
175 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Supply & Delivery of different dia. Sluice Valve for Augmentation of Basudebberia Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | 630/TD | 23/06/2022 | 15 | BIBEKANANDA DAS | 4.82 | 4.82 | 100 | 100
176 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 260MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR Basudebberya W/S SCH (TW-I), DESHPRAN BLOCK UNDER PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | 1344/CDD | 24/11/2022 | 30 | MENAKA ENTERPRISE | 19.77 | 17.25 | 100 | 100
177 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Basudebbrya, JL No. 428 Plot No. 2879) of Basudebberya Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 477/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.91 | 0 | 0 | 0
178 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya in Block - Deshopran under JJM Program under MMD PHE Dte. | 159/W/MMD | 02/02/2023 | 180 | MUKHERJEE ART CENTRE | 25.26 | 12.02 | 47.59 | 54
179 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Supply and Delivery of Different dia Sluice Valves for Basudebberiya Water Supply Scheme in the District of Purba Medinipur. | 440 / CSD | 20/03/2023 | 15 | GIRI ENTERPRISE | 0.91 | 0.91 | 100 | 0
180 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Material Requisition To Resource Division | 1252/TD | 13/12/2021 | 0 | Resource Division | 19.67 | 0 | 0 | 0
181 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Material Requisition To Resource Division | 1953/TD | 04/03/2022 | 0 | Resource Division | 16.73 | 0 | 0 | 0
182 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Laying distribution pipe line and providing of FHTC for Augmentation of Basudebberiya Water Supply Scheme In Deshpran Block in the District of Purba Medinipur. | 1946/TD | 03/03/2022 | 180 | M/S A.R. ENTERPRISE | 490.93 | 393.51 | 80.16 | 90
183 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Laying distribution pipe line & Accommodate FHTC (60 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - E) | 541/TD | 12/05/2023 | 508 | GRAND CONSTRUCTION | 9.36 | 4.6 | 49.17 | 60
184 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Relaying of Existing Damaged Distribution Pipe Line With allied Works for Augmentation Of Basudebberiya Water Supply Scheme in Deshpran Block Of Purba Medinipur District. | 807/TD | 30/05/2023 | 30 | A-PLUS | 20.92 | 20.92 | 100 | 100
185 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Basudebbrya, JL No. 428 Plot No. 2879) of Basudebberya Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tubewell Site (Mouza- Uttar Ektarpur, JL No. - 136, Plot No. 38) of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 2048/TD | 25/08/2023 | 40 | KALPANA BUILDERS | 34.03 | 30.04 | 100 | 40
186 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Quotation for new service connection at TW-III of Basudebberia ws scheme under MMD,PHE Dte, Block-Contai-III, Marishda CCC Application no-2004765941 Con ID-204324592 | BP-2024-25-290 | 29/07/2024 | 0 | WBSEDCL | 6.15 | 0 | 0 | 0
187 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Laying of Washout pipeline, Repairing of OHR, Pump House no 1, Pump House No. 2 and Head Works Boundary Wall under JJM with allied work of Basudebberiya PWSS within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 3057/TD | 19/09/2024 | 400 | ABHIJIT BERA | 19.56 | 0 | 0 | 100
188 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya , SM/09034 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Basudebberiya Water Supply Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | 849/TD | 19/03/2025 | 60 | SMMD | 3.59 | 0 | 0 | 0
189 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Near house of Mohitosh Maity, J.L. No.-98, Plot No.-790, Mouza- Thanaberia , G.P.-Nijkasba b) Near house of Pabitra Pramanik, J.L. No.-98, Plot No.-103, Mouza- Thanaberia , G.P.-Nijkasba | 1962/TD | 04/03/2022 | 21 | KAMAL KUMAR BERA | 3.79 | 3.78 | 100 | 0
190 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)At Shilaberia, J.L. No.-83, Plot No.-38, Mouza- Shilaberia , G.P.-Nijkasba b)At Shilaberia, J.L. No.-83, Plot No.-98, Mouza- Shilaberia , G.P.-Nijkasba | 1965/TD | 04/03/2022 | 21 | M/S. NEW DINDA ENTERPRISE | 3.79 | 3.71 | 100 | 0
191 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Subhasis Das, J.L. No.-120, Plot No.-391, Mouza-Kadirabadchar, G.P.-Khejuri b)Near house of Bhagirath Mandal, J.L. No.-120, Plot No.-379, Mouza- Kadirabadchar , G.P.-Khejuri | 1974/TD | 04/03/2022 | 21 | GIRI CONSTRUCTION | 3.79 | 3.78 | 100 | 0
192 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Pradip Mandal, J.L. No.-59, Plot No.-471, Mouza-Kasaria, G.P.-Khejuri b)Near house of Amitabh Mandal, J.L. No.-59, Plot No.-1149, Mouza- Kasaria , G.P.-Khejuri | 1975/TD | 04/03/2022 | 21 | ABHIJIT BERA | 3.79 | 3.78 | 100 | 0
193 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Booth no 141, Plot No.-744, Mouza- Keshabchak,J.L. No.-21, G.P.-Haludbari b) Booth no 146, JL No.-35,Plot No.-184, Mouza- Katickhali , G.P.-Haludbari | 1981/TD | 04/03/2022 | 21 | BISWA NIRMAN ENTERPRISE. | 3.79 | 3.72 | 100 | 0
194 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)JL No.-21,Plot No.-1461, Mouza-Halutbari, G.P.-Haludbari b) JL No.-23,Plot No.-190, Mouza-Narsulachak, G.P.-Haludbari | 1985/TD | 04/03/2022 | 21 | M/S SREE DURGA ENTERPRISE | 3.79 | 3.79 | 100 | 0
195 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Near house of Subhash Guria, J.L. No.-96, Plot No.-90, Mouza-Matilal Chak, G.P.-Nijkasba b)At Das Para, J.L. No.-95, Plot No.-347, Mouza- Lakshan chak, G.P.-Nijkasba | 1968/TD | 04/03/2022 | 21 | JASODA ENTERPRISE | 3.79 | 3.78 | 100 | 0
196 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)JL No.-21,Plot No.-409, Mouza-Halutbari, G.P.-Haludbari b)JL No.-21,Plot No.-344, Mouza-Halutbari, G.P.-Haludbari | 1986/TD | 04/03/2022 | 21 | M/S SREE DURGA ENTERPRISE | 3.79 | 3.73 | 100 | 0
197 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Malay Kumar Aari, J.L. No.-46, Plot No.-651, Mouza-Bar Kasaria, G.P.-Khejuri b)Near house of Asutosh Mahakal, J.L. No.-37, Plot No.-1291, Mouza- Kastala , G.P.-Khejuri | 1973/TD | 04/03/2022 | 21 | GIRI ENTERPRISE | 3.79 | 3.78 | 100 | 0
198 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Schedule for Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Parimal Kanti Das, J.L. No.-43, Plot No.-189, Mouza-Mansinghabar, , G.P.-Khejuri b)Near house of Nilmani Dhali, J.L. No.-55, Plot No.-116, Mouza-Satsimali , G.P.-Khejuri | 1976/TD | 04/03/2022 | 21 | PARTHA CONSTRUCTION | 3.79 | 3.78 | 100 | 0
199 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Basudev Das, J.L. No.-47, Plot No.-443, Mouza-Sathkhanda, , G.P.-Khejuri b)Near house of Prajapati Mandal, J.L. No.-77, Plot No.-156, Mouza-Dhobaghata Bamanchak , G.P.-Khejuri | 1977/TD | 04/03/2022 | 21 | SWARUPANANDA DAS | 3.79 | 3.78 | 100 | 0
200 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Alakranjan Paria, J.L. No.-39, Plot No.-395, Mouza-Kunjapur, , G.P.-Khejuri b)Near house of Sisir karan, J.L. No.-41, Plot No.-300, Mouza-Satkumari , G.P.-Khejuri | 1978/TD | 04/03/2022 | 21 | BIBEKANANDA DAS | 3.79 | 3.78 | 100 | 0
201 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Booth no 160, Plot No.-3128, Mouza- Dekhali,J.L. No.-20, G.P.-Haludbari b) Near Natun Bazar Kali Mandir, Booth no 161, JL No.-20,Plot No.-1040, Mouza- Dekhali , G.P.-Haludbari. | 1979/TD | 04/03/2022 | 21 | GITA ENTERPRISE | 3.79 | 3.75 | 100 | 0
202 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)At SSK School, J.L. No.-96, Mouza-Matilal Chak, G.P.-Nijkasba b)At Barik Pally, J.L. No.-96, Plot No.-133, Mouza- Matilal Chak, G.P.-Nijkasba | 1969/TD | 04/03/2022 | 21 | JASODA ENTERPRISE | 3.79 | 3.78 | 100 | 0
203 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) At Anchal Para, J.L. No.-106, Mouza- Dakshin Kalagechia, G.P.-Nijkasba b)At Dakshin Matilal Chak, J.L. No.-96, Plot No.-665, Mouza- Matilal Chak , G.P.-Nijkasba | 1966/TD | 04/03/2022 | 21 | M/S. NEW DINDA ENTERPRISE | 3.79 | 3.76 | 100 | 0
204 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) At Das Para, J.L. No.-95, Plot No.-751, Mouza- Lakshan chak, G.P.-Nijkasba b)At Sen Pally, J.L. No.-95, Plot No.-63, Mouza- Lakshan chak, G.P.-Nijkasba | 1967/TD | 04/03/2022 | 21 | BADAL CHANDRA GOLE | 3.79 | 3.79 | 100 | 0
205 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)At Khatua Para, J.L. No.-58, Mouza-Paschim Bhanganmari, G.P.-Janka b)At Jhati Hari, J.L. No.-101, Plot No.-155, Mouza-Oashil Chak, G.P.-Janka | 1970/TD | 04/03/2022 | 21 | PARIA ENTERPRISE | 3.79 | 3.78 | 100 | 0
206 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Srikanta Bera, J.L. No.-49, Plot No.-712, Mouza-Khejuri, G.P.-Khejuri b)Near house of Bhakti Nayak, J.L. No.-49, Plot No.-2453, Mouza-Khejuri, G.P.-Khejuri | 1972/TD | 04/03/2022 | 21 | SACHINDRA NATH GIRI | 3.79 | 3.78 | 100 | 0
207 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Near house of Sudarshan Singha, J.L. No.-98, Plot No.-527, Mouza- Thanaberia , G.P.-Nijkasba b) Near house of Anukul Das, J.L. No.-98, Plot No.-15, Mouza- Thanaberia , G.P.-Nijkasba | 1961/TD | 04/03/2022 | 21 | M/S. NEW DINDA ENTERPRISE | 3.79 | 3.78 | 100 | 0
208 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near Sudam Bera House, Mouza -Meheshpur, JL.No- 264 Plot No.-1699 & Basudevpur Hat, Mouza - Basudevpur, JL. No- 259, Plot No.- 5100 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2169/TD | 17/03/2022 | 15 | SAURAV HAZRA | 3.57 | 3.54 | 100 | 0
209 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 1 no. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Radhakrishna Das, J.L. No.-56, Plot No.-26, Mouza-Chak Arabari, G.P.-Khejuri | 241 / CSD | 27/05/2022 | 14 | GIRI CONSTRUCTION | 1.9 | 1.89 | 100 | 0
210 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Dakshin Shyamharibar, Mouza -Shyamharibar, JL.No- 266 Plot No.-3611 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 724/DSD | 17/03/2022 | 15 | SANTANU PATTANAYAK | 1.78 | 1.77 | 100 | 0
211 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Mrityunjay Pradhan, Booth no 146, Plot No.-1033, Mouza-Katickhali,J.L. No.-35, G.P.-Haludbari b) Booth no 147, JL No.-32,Plot No.-525, Mouza-Gharrang, G.P.-Haludbari | 1983/TD | 04/03/2022 | 21 | AHINDRA BARIK | 3.79 | 0 | 0 | 0
212 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Deuli, Plot No. 220, J.L.No. 49 & Mouza - Padubar, Plot No. 3301, J.L.No. 6 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2106/TD | 17/03/2022 | 15 | MAHAPRABHU ENTERPRISE | 3.57 | 0 | 0 | 0
213 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Barida, Plot No. 2164/3203, J.L.No.6 & Mouza -Tentulia, Plot No. 48, J.L.No.3 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District | 2143/TD | 17/03/2022 | 15 | SOURAV DAS | 3.57 | 0 | 0 | 0
214 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Basanti Mayer Mandir Mouza -Jagannathkarbar, JL.No- 213, Plot No.- 12 & Bathuary fourth star Club ICDS Mouza - Bathuary, JL. No- 244, Plot No.- 863 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2157/TD | 17/03/2022 | 15 | FIROZ KHAN | 3.57 | 3.34 | 93.57 | 0
215 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Barabhagia Paschim SSK Mouza -Barabhagia, JL.No- 236, Plot No.- 358 & Pirijkhanbar Mouza - Pirijkhanbar, JL. No- 225, Plot No.- 658 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2158/TD | 17/03/2022 | 15 | FIROZ KHAN | 3.57 | 3.39 | 94.98 | 0
216 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near House of Kalipada Manna Mouza -Uttar Tajpur, JL.No- 250, Plot No.- 455 & Palpara Sammilita Mouza - Uttar Tajpur, JL. No- 250, Plot No.- 2816 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2159/TD | 17/03/2022 | 15 | FIROZ KHAN | 3.57 | 3.42 | 95.76 | 0
217 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Maity Para Mouza -Daudpur, JL.No- 217, Plot No.-1060 & Balighai Hat Samity Mouza - Mallikpur, JL. No- 176, Plot No.- 04/05 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2160/TD | 17/03/2022 | 15 | FIROZ KHAN | 3.57 | 3.34 | 93.73 | 0
218 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Giri O Maity Para Mouza -Bhatda, JL.No- 180, Plot No.-2465 & Jana Para Mouza - Bhatda, JL. No- 180, Plot No.- 1115 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2161/TD | 17/03/2022 | 15 | FIROZ KHAN | 3.57 | 3.23 | 90.61 | 0
219 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Chandanpur Patna, Plot No. 480, J.L.No. 13 & Mouza - Bagbrajakishor, Plot No. 8, J.L.No. 7 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2108/TD | 17/03/2022 | 15 | MAHAPRABHU ENTERPRISE | 3.57 | 0 | 0 | 0
220 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Champabani, Plot No. 137, J.L.No. 80 & Mouza - Mirzapur, Plot No. 197, J.L.No. 74 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2112/TD | 17/03/2022 | 15 | DIPANKAR MAITY | 3.57 | 3.48 | 97.55 | 0
221 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza-Bodhra, Plot No. 233, J.L.No. 228 & Mouza-Jhaugeriya, Plot No. 377, J.L.No. 207 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2088/TD | 17/03/2022 | 15 | DEBABRATA DAS | 3.57 | 3.31 | 92.64 | 0
222 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near Srinibas Das's House Mouza - Erenda, JL.No- 155, Plot No.- 900 & Beltalia Maa Chandi SSK Mouza - Erenda, JL. No- 155, Plot No.- 690 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2156/TD | 17/03/2022 | 15 | FIROZ KHAN | 3.57 | 3.36 | 94.2 | 0
223 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near Gurupada Das House, Mouza -Shyambaribar, JL.No- 266 Plot No.-1207 & Maity Para near Ajit Maity House, Mouza - Dulalpur, JL. No- 256, Plot No.- 908 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2170/TD | 17/03/2022 | 15 | S.A. ENTERPRISE | 3.57 | 0 | 0 | 0
224 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Near house of Jaydev Jana, Booth no 140, Plot No.-1644, Mouza-Katickhali,J.L. No.-35, G.P.-Haludbari b) Booth no 141, JL No.-18,Plot No.-540, Mouza-Keshabchak, G.P.-Haludbari | 1982/TD | 04/03/2022 | 21 | AHINDRA BARIK | 3.79 | 0 | 0 | 0
225 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Uttam Purakait, J.L. No.-64, Plot No.-379, Mouza-Kadirpur, G.P.-Janka b)Near house of Sunil Das, J.L. No.-69, Plot No.-1453, Mouza-Paschim Panikhya, G.P.-Janka | 1971/TD | 04/03/2022 | 21 | S. A. ENTERPRISE | 3.79 | 0 | 0 | 0
226 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Gopalpur, Plot No. 20, J.L.No. 210 & Mouza-Jamra Shyampur,Plot No. 205, J.L.No. 218 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2090/TD | 17/03/2022 | 15 | DEBABRATA DAS | 3.57 | 3.39 | 95.13 | 0
227 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Uttar Gobra, Plot No. 65, J.L.No. 526 & Mouza - Akna, Plot No. 101, J.L.No. 302 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2114/TD | 17/03/2022 | 15 | AHINDRA BARIK | 3.57 | 0 | 0 | 0
228 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Dublabari, Plot No. 491, J.L.No. 240 & Mouza - Chandpur, Plot No. 289, J.L.No. 237 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2099/TD | 17/03/2022 | 15 | PRALAY RANJAN PATRA | 3.57 | 3.21 | 89.83 | 0
229 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Purusottampur, Plot No. 902, J.L.No. 11 & Mouza - Mukundapur Uttar, Plot No. 98, J.L.No. 19 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2107/TD | 17/03/2022 | 15 | MAHAPRABHU ENTERPRISE | 3.57 | 0 | 0 | 0
230 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Sanbalisai, Plot No. 107, J.L.No. 150 & Mouza - Hirapur, Plot No. 60, J.L.No. 48 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2115/TD | 17/03/2022 | 15 | AHINDRA BARIK | 3.57 | 0 | 0 | 0
231 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Foolbari Gram near Nayek & Bar Para, J.L. No. 249, Dag No. 812 & near Kandarpur Masasa Mandir in front of Sukumar Bhunia's house, J.L. No. 252 Dag No. 758 under Satilapur G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2127/TD | 17/03/2022 | 15 | PULAK KUMAR SAMANTA | 3.57 | 3.33 | 93.34 | 0
232 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)At Shilaberia, J.L. No.-83, Plot No.-415, Mouza- Shilaberia , G.P.-Nijkasba b)At Shilaberia, J.L. No.-83, Plot No.-770, Mouza- Shilaberia , G.P.-Nijkasba | 1964/TD | 04/03/2022 | 21 | SUBHRANGSHU SEKHAR GIRI | 3.79 | 3.73 | 100 | 0
233 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Near house of Sisir Maity, J.L. No.-98, Plot No.-55, Mouza- Thanaberia , G.P.-Nijkasba b) Near house of Nijkasba Purba Shoni Mondir, J.L. No.-119, Plot No.-628, Mouza- Nijkasba , G.P.-Nijkasba | 1963/TD | 04/03/2022 | 21 | SUBHRANGSHU SEKHAR GIRI | 3.79 | 3.74 | 100 | 0
234 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Dendari, Plot No. 16, J.L.No. 38 & Mouza - Purba Mukundapur, Plot No. 749, J.L.No. 211 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2118/TD | 17/03/2022 | 15 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.57 | 3.4 | 100 | 0
235 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Ullaspur, Plot No. 587, J.L.No. 71 & Mouza - Jasteghari, Plot No. 262/1087, J.L.No. 44 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2105/TD | 17/03/2022 | 15 | SUBRATA KUMAR BERA | 3.57 | 3.05 | 100 | 0
236 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Dahadaya, Plot No. 804, J.L.No. 98 & Mouza - Haropur, Plot No. 527, J.L.No. 96 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2119/TD | 17/03/2022 | 15 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.57 | 3.42 | 100 | 0
237 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Alankarpur, Plot No. 124, J.L.No. 97 & Mouza - Ghersai, Plot No. 408, J.L.No. 88 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2120/TD | 17/03/2022 | 15 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.57 | 3.36 | 100 | 0
238 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Uttar Bagpura, Plot No. 135, J.L.No. 202 & Mouza - Biswanathpur, Plot No. 962, J.L.No. 233 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2125/TD | 17/03/2022 | 15 | MAITY CONSTRUCTION | 3.57 | 3.32 | 100 | 0
239 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza- Biswanathpur, Plot No. 574, J.L.No. 233 & Mouza - Talgachhari, Plot No. 332/151, J.L.No. 108 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2126/TD | 17/03/2022 | 15 | KOUSHIK MALLICK | 3.57 | 3.34 | 100 | 0
240 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Bansbani, Plot No. 8, J.L.No. 70 & Mouza - Kantabani, Plot No. 63, J.L.No. 35 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2113/TD | 17/03/2022 | 15 | PARIA ENTERPRISE | 3.57 | 3.28 | 100 | 0
241 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at infront of Kalikapur Masjit, J.L. No. 250, Dag No. 669 & in Keshobpur Gram in front of Badal Shamal's house, J.L. No. 254 Dag No. 814 under Satilapur G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2128/TD | 17/03/2022 | 15 | PULAK KUMAR SAMANTA | 3.57 | 3.41 | 100 | 0
242 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Amadpur, Plot No. 59, J.L.No. 189 & Mouza - Kourpur, Plot No. 191, J.L.No. 187 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2137/TD | 17/03/2022 | 15 | DHANANJOY DAS | 3.57 | 3.57 | 100 | 0
243 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Amdai, Plot No. 120, J.L.No.55 & Mouza - Bindhya, Plot No. 91, J.L.No. 124 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2138/TD | 17/03/2022 | 15 | DHANANJOY DAS | 3.57 | 3.48 | 100 | 0
244 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Simulia, Plot No. 128, J.L.No.103 & Mouza -Chatla, Plot No. 2384, J.L.No. 93 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2140/TD | 17/03/2022 | 15 | DHANANJOY DAS | 3.57 | 3.48 | 100 | 0
245 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Bolkushda, Plot No. 734, J.L.No.90 & Mouza -Erendabar, Plot No. 184, J.L.No. 147 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2141/TD | 17/03/2022 | 15 | DHANANJOY DAS | 3.57 | 3.55 | 100 | 0
246 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Bahiya, Plot No. 128, J.L.No.51 & Mouza -Ghabi, Plot No. 82/6, J.L.No.66 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2145/TD | 17/03/2022 | 15 | AJIT KUMAR SOM | 3.57 | 3.43 | 100 | 0
247 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Chhatri, Plot No. 2481, J.L.No.184 & Mouza -Boyespur, Plot No. 297, J.L.No.10 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2146/TD | 17/03/2022 | 15 | AJIT KUMAR SOM | 3.57 | 3.43 | 100 | 0
248 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza Tajpur, Plot No. 171, J.L.No. 244 & Mouza-Jaldha, Plot No. 631, J.L.No. 242 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2087/TD | 17/03/2022 | 15 | BASANTA KUMAR MAITY | 3.57 | 3.16 | 100 | 0
249 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Shipur, Plot No. 607, J.L.No.96 & Mouza - Barandia, Plot No. 84, J.L.No.84 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2154/TD | 17/03/2022 | 15 | SAI TUBE CO. | 3.57 | 3.2 | 100 | 0
250 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Satkania, Plot No. 183, J.L.No.95 & Mouza - Vetia, Plot No. 51, J.L.No.77 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur D | 2155/TD | 17/03/2022 | 15 | SAI TUBE CO. | 3.57 | 3.16 | 100 | 0
251 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza-Chandpur, Plot No. 156, J.L.No. 237 & MOuza-Kshirpal, Plot No. 521, J.L.No. 238 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2089/TD | 17/03/2022 | 15 | BASANTA KUMAR MAITY | 3.57 | 3.3 | 100 | 0
252 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Booth no 145, Plot No.-1868, Mouza- Katickhali,J.L. No.-35, G.P.-Haludbari b) Booth no 145, JL No.-35,Plot No.-1486, Mouza- Katickhali , G.P.-Haludbari. | 1980/TD | 04/03/2022 | 21 | SUBHENDU HAZRA | 3.79 | 3.77 | 100 | 0
253 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Gholai, Plot No. 7, J.L.No.111 & Mouza - Bahalia, Plot No. 427, J.L.No. 91 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2139/TD | 17/03/2022 | 15 | AJIT KUMAR SOM | 3.57 | 3.31 | 100 | 0
254 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Kasbagola, Plot No. 2176, J.L.No.62 & Mouza -Kalyanpur, Plot No. 582/713, J.L.No.54 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2144/TD | 17/03/2022 | 15 | AJIT KUMAR SOM | 3.57 | 3.44 | 100 | 0
255 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Alangiri, Plot No. 3959, J.L.No.48 & Mouza - Satkhanda, Plot No. 201, J.L.No.43 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2150/TD | 17/03/2022 | 15 | SAI TUBE CO. | 3.57 | 3.48 | 100 | 0
256 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Kudi, Plot No. 817, J.L.No.39 & Mouza - Chhatri, Plot No. 1475, J.L.No.184 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2151/TD | 17/03/2022 | 15 | SOM CONSTRUCTION | 3.57 | 3.37 | 100 | 0
257 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Sannihari, Plot No. 714, J.L.No.32 & Mouza - Chhatri, Plot No. 2925, J.L.No.184 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2152/TD | 17/03/2022 | 15 | SOM CONSTRUCTION | 3.57 | 3.3 | 100 | 0
258 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Alipur Sukanta SSK, Mouza -Alipur, JL.No- 183, Plot No.-406 & Bhatda Sahoo Para, Mouza - Bhatda, JL. No- 180, Plot No.- 2315 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2162/TD | 17/03/2022 | 15 | SAI TUBE CO. | 3.57 | 3.24 | 100 | 0
259 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Bakharpur, Plot No. 140, J.L.No. 4 & Mouza - Kandagram, Plot No. 343, J.L.No. 1 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2109/TD | 17/03/2022 | 15 | SUBRATA KUMAR BERA | 3.57 | 2.96 | 100 | 0
260 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Dakshin Badhia, Plot No. 3584, J.L.No. 6 & Mouza - Paschim Santesswarpur, Plot No. 1072, J.L.No. 8 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2110/TD | 17/03/2022 | 15 | SUBRATA KUMAR BERA | 3.57 | 3.22 | 100 | 0
261 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Medinipur, Plot No. 720, J.L.No. 66 & Mouza - Dakshin Simulia, Plot No. 650, J.L.No. 84 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2111/TD | 17/03/2022 | 15 | SUBRATA KUMAR BERA | 3.57 | 3.28 | 100 | 0
262 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Bararankua (Maktab) Gram near Sk. Atauddin's house, J.L. No. 200, Dag No. 701 & Bararankua (Maktab) Gram near Sk. Nawas Ali's house, J.L. No. 200 Dag No. 562 under Balisai G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2130/TD | 17/03/2022 | 15 | LAKSHMI NARAYAN ENTERPRISE | 3.57 | 3.15 | 100 | 0
263 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Bararankua Gram near Swapan Bar's house, J.L. No. 200, Dag No. 792 & Bararankua Gram near Joydeb Mondal's house, J.L. No. 200 Dag No. 1048 under Balisai G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2131/TD | 17/03/2022 | 15 | LAKSHMI NARAYAN ENTERPRISE | 3.57 | 3.18 | 100 | 0
264 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Bodhra, Plot No. 1098, J.L.No. 234 & Mouza - Lachhimpur, Plot No. 523, J.L.No. 219 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2091/TD | 17/03/2022 | 15 | BASANTA KUMAR MAITY | 3.57 | 3.39 | 100 | 0
265 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Jhamra Shyampur, Plot No. 352, J.L.No. 218 & Mouza - Tajpur, Plot No. 325, J.L.No. 244 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2092/TD | 17/03/2022 | 15 | BASANTA KUMAR MAITY | 3.57 | 3.19 | 100 | 0
266 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Tajpur, Plot No. 420, J.L.No. 244 & Mouza - Kshirpal, Plot No. 304, J.L.No. 238 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2093/TD | 17/03/2022 | 15 | ABHIJIT BERA | 3.57 | 3.46 | 100 | 0
267 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Chandpur, Plot No. 513, J.L.No. 237 & Mouza - Chandpur, Plot No. 107, J.L.No. 237 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2100/TD | 17/03/2022 | 15 | CHARUBALA ENTERPRISE | 3.57 | 3.5 | 100 | 0
268 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Bahadurpur, Plot No. 81, J.L.No. 209 & Mouza - Jhaugeria, Plot No. 173, J.L.No. 207 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2095/TD | 17/03/2022 | 15 | KAMAL KUMAR BERA | 3.57 | 3.42 | 100 | 0
269 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Verichawli, Plot No. 47, J.L.No. 239 & Mouza - Panchadaria, Plot No. 277, J.L.No. 221 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2094/TD | 17/03/2022 | 15 | KAMAL KUMAR BERA | 3.57 | 3.38 | 100 | 0
270 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Somaibasan, Plot No. 10, J.L.No. 89 & Mouza - Jagadispur, Plot No. 398, J.L.No. 87 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2121/TD | 17/03/2022 | 15 | KOUSHIK MALLICK | 3.57 | 3.51 | 100 | 0
271 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Jaldha, Plot No. 298, J.L.No. 242 & Mouza - Jaldha, Plot No. 773, J.L.No. 242 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2098/TD | 17/03/2022 | 15 | DAS ENTERPRISE. | 3.57 | 3.37 | 100 | 0
272 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Kshirpal, Plot No. 336, J.L.No. 238 & Mouza - Kshirpal, Plot No. 885, J.L.No. 238 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2103/TD | 17/03/2022 | 15 | GITA ENTERPRISE | 3.57 | 3.21 | 100 | 0
273 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at near Susanta Mondal's house, mouza - Dadanpatrabarh, J.L. No. 284, Dag No. 1141 & near SK Asef' House, mouza - Dakshin Purosottompur Arkboniya, J.L. No. 286, Dag No.1691 under Kalindi G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2136/TD | 17/03/2022 | 15 | MRINAL KANTI PRADHAN | 3.57 | 3.29 | 100 | 0
274 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Sahadeb Manna Booth no 159, Plot No.-3899, G.P.-Haludbari b) Near house of Basudev Mandal Booth no 146, JL No.-35,Plot No.-342, Mouza-Katickhali, G.P.-Haludbari | 1984/TD | 04/03/2022 | 21 | MRINAL KANTI PRADHAN | 3.79 | 3.79 | 100 | 0
275 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Kultikri Sub-Centre, Mouza -Kultikri, JL.No- 197, Plot No.-1471 & Aranga Hat near GP office, Mouza - Paniparul, JL. No- 203, Plot No.- 3700 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2163/TD | 17/03/2022 | 15 | SOM CONSTRUCTION | 3.57 | 3.37 | 100 | 0
276 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near Giri Para Sunil Giri House, Mouza -Debidaspur, JL.No- 207, Plot No.-678 & Paniparul SSK, Mouza - Paniparul, JL. No- 203, Plot No.- 3910 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2164/TD | 17/03/2022 | 15 | SOM CONSTRUCTION | 3.57 | 3.43 | 100 | 0
277 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Madhupur, Plot No. 240, J.L.No. 52 & Mouza - Dihibirkul, Plot No. 565, J.L.No. 51 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2116/TD | 17/03/2022 | 15 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.57 | 3.35 | 100 | 0
278 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near Barendranath Das House, Mouza -Kultikri, JL.No- 197, Plot No.-1718 & Near Kultikri Samsan math Parikshit Mandal House, Mouza - Kultikri, JL. No- 197, Plot No.- 614 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2165/TD | 17/03/2022 | 15 | SOM CONSTRUCTION | 3.57 | 3.42 | 100 | 0
279 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Paniparul Pry.Health Centre, Mouza -Paniparul, JL.No- 203, Plot No.-2476 & Paniparul Hat, Mouza - Paniparul, JL. No- 203, Plot No.- 2021 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2166/TD | 17/03/2022 | 15 | SOM CONSTRUCTION | 3.57 | 3.4 | 100 | 0
280 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Bararankua Gram near Amalendu Maity's house, J.L. No. 200, Dag No. 975 under Balisai G.P & near Abdul Rasid' House mouza - Sonamui, J.L. No. 282, Dag No. 325 under Kalindi G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2132/TD | 17/03/2022 | 15 | MRINAL KANTI PRADHAN | 3.57 | 3.39 | 100 | 0
281 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at near Nejam's house, mouza - Sonamui, J.L. No. 282, Dag No. 114 & near Batul Das' Shop mouza - Silampur, J.L. No. 246, Dag No. 614 under Kalindi G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2133/TD | 17/03/2022 | 15 | M/S SREE DURGA ENTERPRISE | 3.57 | 3.55 | 100 | 0
282 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Ramnagar, Plot No. 17, J.L.No. 205 & Mouza - Ghritapura, Plot No. 304, J.L.No. 107 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2122/TD | 17/03/2022 | 15 | KOUSHIK MALLICK | 3.57 | 3.19 | 100 | 0
283 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Dakshin Basulipat, Plot No. 238, J.L.No. 203 & Mouza - Barsolemanpur, Plot No. 230, J.L.No. 146 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2123/TD | 17/03/2022 | 15 | MAITY CONSTRUCTION | 3.57 | 3.29 | 100 | 0
284 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at near Bishnu Pada Shyamal's house, mouza - Dadanpatrabarh, J.L. No. 284, Dag No. 1293 & near Parul Santra' House, mouza - Dadanpatrabarh, J.L. No. 284, Dag No.663 under Kalindi G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2135/TD | 17/03/2022 | 15 | MRINAL KANTI PRADHAN | 3.57 | 3.32 | 100 | 0
285 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Bodhra, Plot No. 1069, J.L.No. 228 & Mouza - Jashipur, Plot No. 998, J.L.No. 235 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2096/TD | 17/03/2022 | 15 | DAS ENTERPRISE. | 3.57 | 3.17 | 100 | 0
286 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Tengramari, Plot No. 988, J.L.No. 235 & Mouza - Tengramari, Plot No. 116, J.L.No. 242 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2097/TD | 17/03/2022 | 15 | DAS ENTERPRISE. | 3.57 | 3.09 | 100 | 0
287 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Bodhra, Plot No. 375, J.L.No. 234 & Mouza - Jaldha, Plot No. 551, J.L.No. 238 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2102/TD | 17/03/2022 | 15 | CHARUBALA ENTERPRISE | 3.57 | 3.41 | 100 | 0
288 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Durgapur, Plot No. 1446, J.L.No. 48 & Mouza - Dakshin Mukundapur, Plot No. 1473, J.L.No. 42 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2104/TD | 17/03/2022 | 15 | SUBRATA KUMAR BERA | 3.57 | 3.06 | 100 | 0
289 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Arjuni, Plot No. 173, J.L.No. 35 & Mouza - Koniara, Plot No. 101, J.L.No. 37 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2117/TD | 17/03/2022 | 15 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.57 | 3.31 | 100 | 0
290 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 1 no. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Tapan Ari, Booth no 161, Plot No.-1086, Mouza-Dekhali,J.L. No.-20, G.P.-Haludbari | 209/CSD | 19/05/2022 | 14 | MRINAL KANTI PRADHAN | 1.9 | 1.89 | 100 | 0
291 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Deuli Gram near Sudhangshu Patra & Tapan Bar's Salt factory, J.L. No. 248, Dag No. 212 under Satilapur GP & in Narandia Gram near Kamal Maity house,, J.L. No. 198 Dag No. 634 under Balisai G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2129/TD | 17/03/2022 | 15 | JASODA ENTERPRISE | 3.57 | 3.11 | 100 | 0
292 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at near SK Kasim's house, mouza - Mandarmoni, J.L. No. 245, Dag No. 102 & near S.T Para Pond mouza - Dadanpatrabarh, J.L. No. 284, Dag No.127 under Kalindi G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2134/TD | 17/03/2022 | 15 | M/S SREE DURGA ENTERPRISE | 3.57 | 3.54 | 100 | 0
293 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Chandpur, Plot No. 226, J.L.No. 237 & Mouza - Lachhimpur, Plot No. 275, J.L.No. 219 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2101/TD | 17/03/2022 | 15 | CHARUBALA ENTERPRISE | 3.57 | 3.41 | 100 | 0
294 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Kainthore, Plot No. 244, J.L.No.144 & Mouza -Bartana, Plot No. 3897, J.L.No. 12 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2142/TD | 17/03/2022 | 15 | DHANANJOY DAS | 3.57 | 3.33 | 100 | 0
295 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Ramnagar Purba, Plot No.354 , J.L.No. 205 & Mouza - Uttar Bagpura, Plot No. 20, J.L.No. 202 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2124/TD | 17/03/2022 | 15 | MAITY CONSTRUCTION | 3.57 | 3.32 | 100 | 0
296 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Material Requisition To Resource Division | 316/TD | 11/05/2022 | 0 | Resource Division | 26.83 | 0 | 0 | 0
297 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Material Requisition To Resource Division | 811/TD | 13/07/2022 | 0 | Resource Division | 8.84 | 0 | 0 | 0
298 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Material Requisition To Resource Division | 810/TD | 13/07/2022 | 0 | Resource Division | 26.83 | 0 | 0 | 0
299 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Kalyanpur, Plot No. 498, J.L.No.54 & Mouza -Kiya, Plot No. 511, J.L.No.15 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2149/TD | 17/03/2022 | 15 | KAMAL KUMAR ROY | 3.57 | 3.47 | 100 | 100
300 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Mahabishra, Plot No. 1547, J.L.No.145 & Mouza -Bahalia, Plot No. 885, J.L.No.92 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2147/TD | 17/03/2022 | 15 | KAMAL KUMAR ROY | 3.57 | 3.44 | 100 | 100
301 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Chirulia, Plot No. 526, J.L.No.102 & Mouza -Negua, Plot No. 115, J.L.No.119 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2148\TD | 17/03/2022 | 15 | KAMAL KUMAR ROY | 3.57 | 3.44 | 100 | 100
302 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near Gayendranath Garu House, Mouza -Dubda, JL.No- 191, Plot No.-6574 & Near Prasanta Sahoo Hazra House, Mouza - Dubda, JL. No- 191, Plot No.- 2092 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2167/TD | 17/03/2022 | 15 | ANUPAM CONSTRUCTION | 3.57 | 3.44 | 100 | 100
303 | PURBA MEDINIPUR | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) , SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Purba Asti SSK, Mouza -Asti, JL.No- 195 Plot No.-496/497 & Bankim Pukur Par, Mouza - Dubda, JL. No- 191, Plot No.- 4222 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2168/TD | 17/03/2022 | 21 | ANUPAM CONSTRUCTION | 3.57 | 3.44 | 100 | 100
304 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Land filling with earth at H/W site at Narikeldaha Water Supply scheme of Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division. PHE Dte. | 860/TD | 21/07/2022 | 7 | GHOSH ENTERPRISE | 4.79 | 4.79 | 100 | 100
305 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Sinking of 300 mm. x 200 mm. dia. x 240 mtr. deep tube well by direct rotary rig method at of 1st Tubewell Site of Narkeldaha Water Supply Scheme within under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 2049/TD | 14/03/2022 | 21 | AQUATECH ENGINEERS | 15.11 | 14.32 | 100 | 100
306 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Sinking of 300 mm. x 200 mm. dia. x 240 mtr. deep tube well by direct rotary rig method at of 2nd Tubewell Site of Narkeldaha Water Supply Scheme within under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 2050/TD | 14/03/2022 | 21 | AQUATECH ENGINEERS | 15.11 | 14.1 | 100 | 100
307 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Land filling with earth at 2nd. T/W site at Narikeldaha W/S scheme of Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | 712/TSD | 16/06/2022 | 7 | GHOSH ENTERPRISE | 1.43 | 1.43 | 100 | 100
308 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Bill for WBSEDCL for Quotation charges of Narikeldaha PWSS under Moyna Block under Tamluk Division, PHE Dte. | BP-2022-23-272 | 29/08/2022 | 0 | WBSEDCL | 9.17 | 0 | 0 | 0
309 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 400 Cum and staging height 20.00 mtr. with allied work under Narikeldaha & its adjoining moujas Water Supply Scheme within Moyna Dev. Block including supply of all labour & materials under Tamluk sub-division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | 1154/TD | 30/11/2021 | 210 | ARABINDA GHOSH | 523.45 | 518.48 | 99.05 | 100
310 | PURBA MEDINIPUR | Midnapore Mechanical | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-II under Narikelda water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2189/W/MMD | 12/12/2022 | 120 | MENAKA ENTERPRISE | 13.09 | 12.32 | 94.1 | 100
311 | PURBA MEDINIPUR | Midnapore Mechanical | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-I under Narikelda water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2188/W/MMD | 12/12/2022 | 120 | S.S.GHORAI | 13.09 | 12.3 | 93.95 | 75
312 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Additional work of Plinth protection, surface drain, septic tank, soak well, plumbing work, brick work,water arrangement of Toilet at 2nd T/W site for Narikeldaha Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1172/TSD | 07/09/2022 | 25 | GHOSH ENTERPRISE | 2.27 | 2.27 | 100 | 100
313 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Construction of M.S. Structure over irrigation canal to support 200 mm dia. DI (K-7) distribution pipe under Narikeldaha Water Supply Scheme at different Nodal Point under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte (L=40.00 Mtr ) | 1429/TD | 26/09/2022 | 25 | KRISHNENDU SEKHAR DAS | 4.48 | 4.48 | 100 | 100
314 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Material Requisition To Resource Division | 1685/TD | 31/01/2022 | 0 | Resource Division | 12.47 | 0 | 0 | 0
315 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Material Requisition To Resource Division | 1832/TD | 15/02/2022 | 0 | Resource Division | 36.27 | 0 | 0 | 0
316 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Material Requisition To Resource Division | 1681/TD | 28/01/2022 | 0 | Resource Division | 3.98 | 0 | 0 | 0
317 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Interconnection with laying of 150 mm dia DI (K-9) rising main from H/W site tube well to 2nd T/W site at Narikeldaha PWSS under Tamluk Sub-Division of Tamluk Division PHE Dte. | 972/TD | 03/08/2022 | 15 | GHOSH ENTERPRISE | 5.7 | 3.7 | 100 | 100
318 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Functional Household Tap Connection (FHTC=798 nos)at Narikeldaha water supply scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 1447/TD | 13/07/2023 | 30 | GHOSH ENTERPRISE | 31.51 | 31.45 | 100 | 100
319 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Laying Distribution system of Left-out portion of pipe line at Narikeldaha Water Supply Scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 2046/TD | 25/08/2023 | 30 | GHOSH ENTERPRISE | 88.3 | 88.28 | 100 | 100
320 | PURBA MEDINIPUR | Tamluk Division | Narikeldaha Piped Water Supply Scheme. , SM/09342 | New | Installation of display Board (80 nos.) at different work site for PHE Dept. Land under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 3544/TD | 14/11/2024 | 25 | MISHRA ENTERPRISE | 13.33 | 5.91 | 30.73 | 100
321 | PURBA MEDINIPUR | Tamluk Division | Balance Work for Retrofitting to Accommodate FHTC (152 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of different nodal point of Dona Zone-II and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk , SM/09443 | Retrofitting | Retrofitting to accommodate .FHTC (152 nos.)(Balance work) and laying of left-out portion with uPVC pipeline due to uncovered area of Dona Zone-II Water Supply Scheme and its adjoining mouzas Water Supply Scheme at different nodal point under JJM within Moyna Block under Tamluk Sub-Division of Tamluk Division in the District of Purba Medinipur. (Phase-II) | 1267/TD | 13/12/2021 | 25 | TARUN KOLEY | 46.72 | 45.8 | 100 | 100
322 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Shankarpur Water Supply Scheme under Tamluk Division, PHE Dte. | 1609/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.36 | 3.54 | 100 | 100
323 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Supply & Delivery of different dia Sluice Valve for Augmentation of Sankarpur Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | 628/TD | 23/06/2022 | 15 | BIBEKANANDA DAS | 4.21 | 4.21 | 100 | 100
324 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Additional 3rd Tubewell of Augmentation of Shankarpur Water Supply Scheme (Mouza - Kukraul, JL No. - 468, Plot No. - 66) within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 980/TD | 03/08/2022 | 15 | PRANTIK DRILLING AGENCY | 12.15 | 11.67 | 100 | 100
325 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Renovation work of spiral staircase and related works for R.C.C. Over Head Reservoir of capacity 250 Cum for Augmentation of Sankarpur Water Supply Scheme within Block Contai- III under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | 392 / CSD | 12/07/2022 | 30 | LAKSHMI NARAYAN ENTERPRISE | 2.43 | 2.34 | 100 | 100
326 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary and water supply arrangements including Plinth Protection at 3rd TW site for Shankarpur Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | 717/TD | 24/05/2023 | 60 | JASODA ENTERPRISE | 3.73 | 3.67 | 100 | 100
327 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Material Requisition To Resource Division | 411/TD | 25/05/2022 | 0 | Resource Division | 18.52 | 0 | 0 | 0
328 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Material Requisition To Resource Division | 1265/TD | 12/09/2022 | 0 | Resource Division | 13.3 | 0 | 0 | 0
329 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Electric Quotation for SHANKARPUR Water Supply Scheme T/W-III, (Ref. ID-204049544) | BP-2023-24-168 | 04/08/2023 | 0 | WBSEDCL | 4.93 | 0 | 0 | 0
330 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Laying of Distribution pipeline to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Shankarpur Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division,P.H.E. Dte., Purba Medinipur. | 1226/TD | 07/09/2022 | 45 | PATHIK PABAN NANDI | 359.47 | 356.17 | 99.08 | 99
331 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Continuation work order for Hiring of one no. Diesel Motor cabs (Luxury Taxi Standered non air conditioned) Bharat Stage -IV , on daily rate basis (including Govt. Holidays as and when required ) Having contract carraige permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. For the Period from 01/07/2022 to 30/06/2023. (12 Months) Vehicle No-WB-31/6974 | 357/CSD | 30/06/2022 | 365 | SABITA PRADHA | 1.49 | 4.57 | 100 | 100
332 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Rising main and other allied works Augmentation of Shankarpur W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1092/CSD | 06/06/2023 | 30 | LAKSHMI NARAYAN ENTERPRISE | 2.58 | 0.68 | 100 | 100
333 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1223/W/MMD | 25/04/2023 | 180 | THE GODFATHER TRADING COMPANY | 11.96 | 11.75 | 100 | 100
334 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Quotation for new service connection at Zone-1, TW-1 of Shankarpur (Ramnagar)ws scheme under MMD,PHE Dte Ref. Application no.-2004577423, Con ID-204203250 | BP-2023-24-675 | 15/02/2024 | 0 | WBSEDCL | 7.83 | 0 | 0 | 0
335 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur , SM/10342 | Augmentation | Laying of Left out Distribution pipe line by HDPE pipes with allied works for Augmentation of Shankarpur & adjoining mouzas Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3476/TD | 06/11/2024 | 20 | KOUSHIK MALLICK | 7.56 | 0 | 0 | 100
336 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC (Balance Work) (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-V, Bloc , SM/10437 | Retrofitting | Retrofitting of FHTC (200 nos.) and Laying of Left-Out portion HDPE Pipe line under Surface Water Based Water Supply Scheme at Zone-V due to uncovered area of this Zone and damaged pipe line at different Nodal Point under Tamluk Sub-Division of Tamluk Division, PHE Dte.in the District of Purba Medinipur. | 61/TD | 05/04/2022 | 20 | MRITYUNJOY PARIA | 17.51 | 16.09 | 91.9 | 100
337 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Gobra PWSS under Ramnagar-I Block. , SM/09800 | Retrofitting | Providing FHTC under JJM in Gobra PWSS within Ramnagar-II Dev. Block under Digha Sub-Division of Tamluk Division PHE Dte.in the District of Purba Medinipur. | 1640/TD | 19/01/2022 | 100 | M/S CARE | 122.42 | 92.17 | 75.29 | 80
338 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Gobra PWSS under Ramnagar-I Block. , SM/09800 | Retrofitting | Material Requisition To Resource Division | 1749/TD | 08/02/2022 | 0 | Resource Division | 14.03 | 0 | 0 | 0
339 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block. , SM/09801 | Retrofitting | Providing 1450 Nos FHTC with allied works of Arjunnagar & its adjoining mouzas Water Supply Scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 2203/TD | 21/03/2022 | 35 | TAPAS SANTRA | 78.78 | 78.78 | 100 | 100
340 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block. , SM/09801 | Retrofitting | Providing 1412 Nos FHTC with allied works of Arjunnagar & its adjoining mouzas Water Supply Scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 719/TD | 29/06/2022 | 40 | S.D. CONSTRUCTION | 64.5 | 64.48 | 100 | 100
341 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block. , SM/09801 | Retrofitting | Instalation of display Board at different work site of Paschimbetiya Retrofitting PWSS in Contai - III Block, Mahammadpur Retrofitting PWSS in Bhagwanpur - I Block, Baharampur, Arjunnagar Retrofitting PWSS in Bhagwanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2335/CSD | 29/12/2023 | 15 | SAURAV HAZRA | 0.83 | 0.83 | 100 | 100
342 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC (2753) Nos. and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different nodal point under JJM in Uttar Dhalhara Zone-II of Sahid Matangini Block in this district of Purba Medinipur. , SM/09802 | Retrofitting | Retrofitting to accommodate FHTC (2753 nos) and laying of left-out uPVC pipeline due to uncovered area of this zone at different nodal point under JJM in Uttar Dhalhara Zone-II Water Supply Scheme for Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division in the District of Purba medinipur. | 1634/TD | 19/01/2022 | 120 | M/S CARE | 135.49 | 63.79 | 47.08 | 80
343 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC (2753) Nos. and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different nodal point under JJM in Uttar Dhalhara Zone-II of Sahid Matangini Block in this district of Purba Medinipur. , SM/09802 | Retrofitting | Material Requisition To Resource Division | 2349/TD | 31/03/2022 | 0 | Resource Division | 15.14 | 0 | 0 | 0
344 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC (2753) Nos. and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different nodal point under JJM in Uttar Dhalhara Zone-II of Sahid Matangini Block in this district of Purba Medinipur. , SM/09802 | Retrofitting | Material Requisition To Resource Division | 1116/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
345 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC (2633) Nos. of Chandibenia Zone-I and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division, PHE Dte. in the district of Purba Medinipur. , SM/09803 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandibeniya Zone-I PWSS within Moyna Dev. Block .in the District of Purba Medinipur. | 1633/TD | 19/01/2022 | 90 | ARABINDA GHOSH | 105.61 | 104.47 | 100 | 100
346 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC (2633) Nos. of Chandibenia Zone-I and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division, PHE Dte. in the district of Purba Medinipur. , SM/09803 | Retrofitting | Material Requisition To Resource Division | 1100/TD | 19/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
347 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09272 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Mechogram Water Supply Scheme under Tamluk Division, PHE Dte. | 1190/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 5.28 | 5.28 | 100 | 100
348 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09272 | Augmentation | Supply of sluice valve & delivery at Chapbasan Store for Dakshin Mechogram PWSS within Panskura-I Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte. | 442/TD | 31/05/2022 | 15 | SWADHIN KUMAR CHAKRABORTY | 3.34 | 3.34 | 100 | 100
349 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09272 | Augmentation | Laying distribution system of pipe line and its allied works for Dakshin Mechogram & its adjoining mouzas Water Supply Scheme at Panskura-I Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. Purba Medinipur. | 1146/TD | 31/08/2022 | 20 | M/S. CHANDI CHARAN MISHRA & CO. | 14.56 | 14.4 | 100 | 100
350 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09272 | Augmentation | Material Requisition To Resource Division | 1256/TD | 13/12/2021 | 0 | Resource Division | 0.59 | 0 | 0 | 0
351 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09272 | Augmentation | Material Requisition To Resource Division | 1730/TD | 02/02/2022 | 0 | Resource Division | 12.11 | 0 | 0 | 0
352 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09272 | Augmentation | Material Requisition To Resource Division | 419/TD | 25/05/2022 | 0 | Resource Division | 1.16 | 0 | 0 | 0
353 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09272 | Augmentation | 1(One) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room, Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Dakshin Mechogram Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 267/TD | 20/04/2023 | 45 | TARUN KHATUA | 13.06 | 12.52 | 95.89 | 96
354 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09272 | Augmentation | Rejuvenation of Dakshin Mechogram Water Supply Scheme by Providing Laying Distribution System and FHTC in Panskura Block in the District of Purba Medinipur. (PART-A) | 1668/TD | 25/01/2022 | 120 | M/S. CHANDI CHARAN MISHRA & CO. | 134.86 | 123.22 | 100 | 100
355 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09272 | Augmentation | Augmentation Of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura-I Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | 2552/TD | 24/01/2023 | 60 | FARID UDDIN AHMED | 43.27 | 25.35 | 100 | 100
356 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09272 | Augmentation | Rejuvenation of Dakshin Mechogram Water Supply Scheme by Providing Laying Distribution System and FHTC in Panskura Block in the District of Purba Medinipur. (PART-B) | 1667/TD | 25/01/2022 | 120 | SWADHIN KUMAR CHAKRABORTY | 135.54 | 135.32 | 100 | 100
357 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 533 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Bhandarberya) (PART-E) | 1775/TD | 08/02/2022 | 30 | S.D. CONSTRUCTION | 58 | 32.49 | 56.01 | 100
358 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 586 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Ganapatinagar) (PART-K) | 1779/TD | 08/02/2022 | 40 | BHOLANATH DEY | 57.93 | 47 | 81.12 | 95
359 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 388 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-II) (PART-D) | 1774/TD | 08/02/2022 | 30 | ADHIKARY CONSTRUCTION | 42.02 | 31.98 | 76.11 | 95
360 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 204 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Nimtouri,P-II) (PART-G) | 2061/TD | 15/03/2022 | 30 | J.M. CONSTRUCTION | 29.04 | 24.61 | 84.74 | 95
361 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme under Tamluk Division, PHE Dte. | 1162/TD | 01/12/2021 | 7 | HORIZEN | 7.18 | 7.16 | 100 | 100
362 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Left-out portion of uncovered area with uPVC pipe line and its allied works for Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-I) within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(PART-A) | 970/TD | 03/08/2022 | 15 | NARAYAN MANDAL | 10.6 | 10.59 | 100 | 100
363 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Left-out portion of uncovered area with uPVC pipe line and its allied works for Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-II) within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(PART-B) | 971/TD | 03/08/2022 | 15 | KRISHNENDU SEKHAR DAS | 8.3 | 8.29 | 100 | 100
364 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 2nd Tube well Site of Uttar Sonamui Water Supply Scheme within Tamluk Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 905/TD | 27/07/2022 | 21 | AQUATECH ENGINEER | 17.25 | 15.53 | 100 | 100
365 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Supply & Delivery of different dia DI Specials for Laying of Distribution Main (K-7) of Different works for providing functional house hold tap connection(FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | 1175/TSD | 09/09/2022 | 15 | SK. NUR ISLAM | 1.92 | 1.77 | 100 | 100
366 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 510 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Nimtouri,P-I) (PART-F) | 1776/TD | 08/02/2022 | 40 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 76.98 | 67.75 | 88.01 | 95
367 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 858 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Chak Srikrishnapur &Uttar Narikelda) (PART-H) | 1777/TD | 08/02/2022 | 40 | NARAYAN CHANDRA DAS | 86.75 | 81.26 | 93.68 | 100
368 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 484 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme''(Mouza-Payrachali) (PART-J) | 1778/TD | 08/02/2022 | 30 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 43.68 | 39.07 | 89.45 | 100
369 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Uttar Sonamui Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 2215/TD | 22/12/2022 | 25 | ADHIKARY CONSTRUCTION | 4.46 | 3.93 | 87.98 | 0
370 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Uttar Sonamui Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2214/TD | 22/12/2022 | 25 | KRISHNENDU SEKHAR DAS | 4.56 | 0 | 0 | 0
371 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Uttar Sonamui Water Supply Scheme within Tamluk Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 904/TD | 27/07/2022 | 21 | AQUATECH ENGINEER | 17.25 | 15.84 | 100 | 100
372 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 374 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Kulberya) (PART-I) | 2062/TD | 15/03/2022 | 30 | SK. NUR ISLAM | 51.1 | 48.35 | 100 | 100
373 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Material Requisition To Resource Division | 1833/TD | 15/02/2022 | 0 | Resource Division | 26.06 | 0 | 0 | 0
374 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Material Requisition To Resource Division | 2191/TD | 21/03/2022 | 0 | Resource Division | 30.92 | 0 | 0 | 0
375 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Payment to WBSEDCL for Quotation Money of Uttar Sonamui PWSS under Tamluk Division, PHE Dte. | BP-2023-24-1 | 13/04/2023 | 0 | WBSEDCL | 0.5 | 0 | 0 | 0
376 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Payment to WBSEDCL for Quotation Money for Uttar Sonamui PWSS under Tamluk Division, PHE Dte. | BP-2022-23-934 | 30/03/2023 | 0 | WBSEDCL | 4.34 | 0 | 0 | 0
377 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Interconnection with laying of 150 mm dia DI(K-9) Rising main From 3 rd Tube Well & 2 nd Tube Well Site to O.H.R. Site and other allied works at Uttar Sonamui Water Supply Scheme within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3196/TD | 14/03/2023 | 15 | MAHAMAYA TIMBER AND CONSTRUCTION | 5.48 | 0 | 0 | 0
378 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Sutahata and Tamluk in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1218/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 40.43 | 23.84 | 88.44 | 60
379 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room for Water Supply (as per Deptt. drawing) at 2nd. Tube well site. of Uttar Sonamui Pipe Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte.in the District of Purba Medinipur . | 2982/TD | 29/11/2023 | 45 | KRISHNENDU SEKHAR DAS | 7.81 | 4.3 | 100 | 100
380 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Leftout FHTC- 15 Nos. including supplying, laying, fitting, fixing of Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials and labour for Uttar Sonamui Water Supply Scheme under Uttar Sonamui Gram Panchayat Area within Tamluk-II Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. in the District of Purba Medinipur . | 1061/TSD | 19/07/2024 | 84 | DIPANKAR MALAKAR | 0.97 | 0.72 | 100 | 100
381 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Material Requisition To Resource Division | 1121/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
382 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 810 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-I) (PART-C) | 1773/TD | 08/02/2022 | 1336 | NARAYAN MANDAL | 74.62 | 68.32 | 91.56 | 95
383 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. , SM/09282 | Augmentation | Construction of R.C.C. Elevated Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Uttar Sonamui & its adjoining moujas Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District . (PART-A) | 2550/TD | 24/01/2023 | 738 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 149.76 | 120.36 | 80.67 | 80
384 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sapai Water Supply Scheme under Tamluk Division, PHE Dte. | 1187/TD | 02/12/2021 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.13 | 4.11 | 100 | 100
385 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional Tubewell Site (JL no. 171, Plot no. 65/215, Mouza-Chandrikalapunja) of Sapai Water Supply Scheme under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | 1993/TD | 07/03/2022 | 21 | PRANTIK DRILLING AGENCY | 12.08 | 8.76 | 100 | 100
386 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Supply & Delivery of CIDF Sluice Valve for laying of distribution pipe line by UPVC pipes with allied works for Augmentation of Sapai Water Supply Scheme within Contai-III Block under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. | 2224/TD | 24/03/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.31 | 4.31 | 100 | 100
387 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including land development for Additional Tube Well at J.L. No.-171, PLot no.-65/215, Mouza-Chandrikalapunja under Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1294/TD | 13/09/2022 | 60 | GITA ENTERPRISE | 4.85 | 3.81 | 78.39 | 100
388 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well I under Sapai water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2124/W/MMD | 28/11/2022 | 120 | DEBKUMAR BASU | 11.15 | 10.8 | 96.87 | 0
389 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Repairing of 100 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir for Augmentation of Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 2347/TD | 10/01/2023 | 60 | BARH CONSTRUCTION | 14.41 | 8.54 | 59.29 | 0
390 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Augmentation of Sapai Water Supply Scheme by Providing Laying Distribution System and FHTC in Conati-III Block of Purba Medinipur District | 1653/TD | 21/01/2022 | 90 | ARUP KUMAR DEY | 223.76 | 205.92 | 100 | 100
391 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Reservoir (OHR)Site, Mouza -Sapai, J.L no - 176, under Augmentation of Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. Length 76.00 mtr. | 2346/TD | 10/01/2023 | 30 | JASODA ENTERPRISE | 10.32 | 8.76 | 100 | 100
392 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Material Requisition To Resource Division | 1251/TD | 13/12/2021 | 0 | Resource Division | 0.35 | 0 | 0 | 0
393 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Material Requisition To Resource Division | 1866/TD | 17/02/2022 | 0 | Resource Division | 5.42 | 0 | 0 | 0
394 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Electric Quotation bill of Sapai T/W-III ,P.O.-Bahitrakunda under Marishda CCC (Memo No. 2004155106) | BP-2022-23-100 | 10/01/2023 | 0 | WBSEDCL | 0.47 | 0 | 0 | 0
395 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Payment to WBSEDCL for Quotation Money of Ramchak PWSS from Sapai PWSS under Tamluk Division, PHE Dte. | BP-2023-24-2 | 13/04/2023 | 0 | WBSEDCL | 0.28 | 0 | 0 | 0
396 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Providing FHTC( Functional Household tap connection )For implementation of Har Ghar Jhal Gram / Sajal Gram under Augmentation of Sapai Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | 133/TD | 10/04/2023 | 20 | MRINAL KANTI PRADHAN | 10.72 | 8.12 | 75.75 | 60
397 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1394/W/MMD | 01/06/2023 | 180 | BHABANI PRASAD MANNA | 11.59 | 0 | 0 | 80
398 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Rising main and other allied works for connecting Additional Tube well of Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1295/TD | 13/09/2022 | 30 | AMIT PAYRA | 4.57 | 3.48 | 100 | 100
399 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Repairing Of Pump House and Boundary Wall of Pump House No-I & II under Augmentation of Sapai Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | 486/TD | 10/05/2023 | 30 | SADDAM DIN | 4.19 | 1.94 | 100 | 100
400 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai , SM/09287 | Augmentation | Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method with 150 dia. uPVC Steiner of 30 m length for replacement of 1st Tube Well for Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 455/TD | 04/02/2025 | 40 | PRANTIK DRILLING AGENCY | 13.3 | 0 | 0 | 0
401 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS , SM/06889 | Retrofitting | Retrofitting to accomodate FHTC of Village- Saripur,J.L. No-92 under JJM in Saripur PWSS Block - Chandipur in the District of Purba Medinipur. | 2466/TD | 18/12/2020 | 25 | NARAYAN MANDAL | 27.85 | 0 | 0 | 100
402 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS , SM/06889 | Retrofitting | Retrofitting to accomodate FHTC of Village- Damodarpur,J.L. No-93 under JJM in Saripur PWSS Block - Chandipur in the District of Purba Medinipur. | 2467/TD | 18/12/2020 | 25 | NARAYAN MANDAL | 27.46 | 0 | 0 | 100
403 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS , SM/06889 | Retrofitting | Retrofitting to accommodate FHTC (53 nos) under JJM within Saripur PWSS(Balance Work), Block- Chandipur in the District of Purba Medinipur | 639/TSD | 26/10/2021 | 20 | NARAYAN MANDAL | 2.52 | 1.69 | 100 | 100
404 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS , SM/06889 | Retrofitting | Retrofitting to accomodate FHTC of Village - Saripur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 123/W | 07/07/2021 | 0 | NARAYAN MANDAL | 1.54 | 0 | 0 | 0
405 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS , SM/06889 | Retrofitting | Retrofitting to accomodate FHTC of Village - Damudarpur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 648/W | 25/01/2021 | 0 | NARAYAN MANDAL | 25.46 | 0 | 0 | 0
406 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS , SM/06889 | Retrofitting | Retrofitting to accomodate FHTC of Village - Damudarpur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 124/W | 07/07/2021 | 0 | NARAYAN MANDAL | 2 | 0 | 0 | 0
407 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS , SM/06889 | Retrofitting | Retrofitting to accomodate FHTC of Village - Saripur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 644/W | 13/01/2021 | 0 | NARAYAN MANDAL | 26.31 | 0 | 0 | 0
408 | PURBA MEDINIPUR | Tamluk Division | CHALTI AND ADJOINING MOUJAS PWSS , SM/12505 | New | Material Requisition To Resource Division | 2404/TD | 16/01/2023 | 0 | Resource Division | 49.91 | 0 | 0 | 0
409 | PURBA MEDINIPUR | Tamluk Division | CHALTI AND ADJOINING MOUJAS PWSS , SM/12505 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Chalti PWSS at Deshpran Block under Tamluk Division, PHE Dte. | 1052/TD | 15/03/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 0
410 | PURBA MEDINIPUR | Tamluk Division | CHALTI AND ADJOINING MOUJAS PWSS , SM/12505 | New | Material Requisition To Resource Division | 2952/TD | 12/09/2024 | 0 | Resource Division | 6.76 | 0 | 0 | 0
411 | PURBA MEDINIPUR | Midnapore Mechanical | CHALTI AND ADJOINING MOUJAS PWSS , SM/12505 | New | Quotation Bill for New Service connection at T/W NO-II Of CHALTI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004945784/QUOT/03 DT. 05-11-2024 Application NO- 2004767136 Application type-New connection Consumer Id- 204429932 | C112423558564 | 19/11/2024 | 0 | WBSEDCL | 3.85 | 0 | 0 | 0
412 | PURBA MEDINIPUR | Tamluk Division | CHALTI AND ADJOINING MOUJAS PWSS , SM/12505 | New | Quotation Bill for New Service connection at T/W NO-I Of CHALTI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004767136/QUOT/03 DT. 07-06-2024 Application NO- 2004767136 Application type-New connection Consumer Id- 204325528 | BP-2024-25-291 | 29/07/2024 | 0 | WBSEDCL | 21.24 | 0 | 0 | 0
413 | PURBA MEDINIPUR | Midnapore Mechanical | CHALTI AND ADJOINING MOUJAS PWSS , SM/12505 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHALTI and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2422/W/MMD | 31/12/2022 | 882 | P.K.ENGINEERING | 22.8 | 17.61 | 77.22 | 90
414 | PURBA MEDINIPUR | Tamluk Division | CHALTI AND ADJOINING MOUJAS PWSS , SM/12505 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 26.98 | 6.17 | 51
415 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12570 | Augmentation | Material Requisition To Resource Division | 1662/TD | 03/11/2022 | 0 | Resource Division | 263.84 | 0 | 0 | 0
416 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12570 | Augmentation | Material Requisition To Resource Division | 613/TD | 17/05/2023 | 0 | Resource Division | 45.22 | 0 | 0 | 0
417 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12570 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I and III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | 810/W/MMD | 24/03/2023 | 180 | SUBHAM ENTERPRISE | 13.59 | 6.32 | 46.46 | 47
418 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12570 | Augmentation | Laying of 90 mm dia HDPE Pipe Lines With allied works to accommodate Total 7341 nos FHTC of Augmentation of Contai Saline Area Zone -III (Phase-A) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 00/TD | 09/01/2024 | 40 | TAPAS SANTRA | 0 | 0 | 0 | 0
419 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12570 | Augmentation | Replacement of Damaged Existing DI/CI pipe line with HPPE Pipe line With allied works to accommodate Total 7341 nos FHTC of Augementation of Contai Saline Area Zone -III (Phase-A) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 849/TD | 06/03/2024 | 30 | TAPAS SANTRA | 52.89 | 37.93 | 71.71 | 100
420 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12570 | Augmentation | Ancillary Work of Reinforcement for reinforced cement concrete work for Constrution of R.C.C Elevated Reservoir of Capacity 900 cum and staging height 20.00mtr. With allied work including supply of all labour & material of Augmentation of Contai Saline Area Zone-III (PHASE-A) & its adjoining maujas water supply scheme within Contai-I Block under Contai sub- Division of Tamluk Division, P.H.E.Dte. Dist.- Purba Medinipur. | 393/TD | 27/04/2023 | 40 | TAPAS SANTRA | 48.63 | 47.68 | 100 | 60
421 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12570 | Augmentation | Laying of 90 mm dia HDPE Pipe Lines With allied works to accommodate Total 7341 nos FHTC of Augementation of Contai Saline Area Zone -III (Phase-A) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 3115/TD | 05/12/2023 | 40 | TAPAS SANTRA | 115.73 | 115.64 | 100 | 100
422 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12570 | Augmentation | Quotation Bill for New Service connection at CONTAI SALINE AREA ZONE-III, T/W NO-I, PHASE-B W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004696671/QUOT/03 DT. 24-04-2024 Application NO- 2004696671 Application type-New connection Consumer Id- 204284086 | BP-2024-25-146 | 09/05/2024 | 0 | WBSEDCL | 3.26 | 0 | 0 | 0
423 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12570 | Augmentation | Laying of distribution pipe line to accommodate FHTC (7341 Nos) with construction of R.C.C. Elevated Reservoir of capacity 900cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Contai Saline Area Zone-III (Phase-A) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 2062/TD | 09/12/2022 | 935 | TAPAS SANTRA | 1130.28 | 941.81 | 83.33 | 80
424 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12570 | Augmentation | Boundary Wall, Raising Main, and Pump House, under JJM with allied work for Augmentation of Contai Saline area Zone-III( Phase-B) in Contai-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 561/TD | 15/02/2024 | 481 | PULAK KUMAR SAMANTA | 46.1 | 3.51 | 7.61 | 25
425 | PURBA MEDINIPUR | Central Drilling | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/11612 | Augmentation | additional compressor development of the newly construction tube well at argoal w/s scheme 2nd tw site, block-pataspur -ii under CMSD-I (D), CDD, PHE DTE. | 63/CMSD-I | 18/03/2021 | 3 | ASHUTOSH DAS & CO | 0.49 | 0 | 0 | 100
426 | PURBA MEDINIPUR | Tamluk Division | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/11612 | Augmentation | Material Requisition To Resource Division | 357/TD | 26/04/2023 | 0 | Resource Division | 17.67 | 0 | 0 | 0
427 | PURBA MEDINIPUR | Midnapore Mechanical | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/11612 | Augmentation | Electric quotation bill for WBSEDCL at TW III of Argoal WS Scheme (Ref. ID - 203932077) | BP-2023-24-7 | 18/04/2023 | 0 | WBSEDCL | 0.74 | 0 | 0 | 0
428 | PURBA MEDINIPUR | Tamluk Division | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/11612 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 14.62 | 80.25 | 100
429 | PURBA MEDINIPUR | Midnapore Mechanical | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/11612 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. Block ¿ Potashpur II within the Purba Medinipur District, under JJM Program under MMD PHE Dte. | 640/W/MMD | 20/03/2023 | 180 | PURUSHOTTAM ENTERPRISE | 13.57 | 13.27 | 100 | 100
430 | PURBA MEDINIPUR | Tamluk Division | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/11612 | Augmentation | Laying Rising Main DI(K-9) pipe line with interconnection, Construction of 3.60 mtr. X 3.00 mtr. Size Switch Room cum Chlorine Room & Boundary Wall at 3rd Boosting TW site (Mouza-Jabda, J.L No-225, Plot No-887) of Argoal PWSS in Patashpur-II within Contai Sub-Division of Tamluk Division,PHE Dte.(Length-50.00 mtr.) (for Low Land) | 1521/TD | 18/07/2023 | 30 | SK. SARFARAJ | 33.57 | 9.68 | 28.81 | 90
431 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II , SM/12490 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | 1803/TD | 08/02/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.79 | 3.32 | 100 | 100
432 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II , SM/12490 | Augmentation | Material Requisition To Resource Division | 1671/TD | 03/11/2022 | 0 | Resource Division | 39.54 | 0 | 0 | 0
433 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II , SM/12490 | Augmentation | Material Requisition To Resource Division | 608/TD | 17/05/2023 | 0 | Resource Division | 13.82 | 0 | 0 | 0
434 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II , SM/12490 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Pora Chingra, JL No. 155) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for Additional Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 2244/TD | 29/12/2022 | 40 | PRANTIK DRILLING AGENCY | 61.68 | 23.98 | 90.4 | 90
435 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II , SM/12490 | Augmentation | Electric Quotation for BAJKUL Water Supply Scheme T/W-I, Zone- II, (Ref. ID-204114262) | BP-2023-24-374 | 01/12/2023 | 0 | WBSEDCL | 3.48 | 0 | 0 | 0
436 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II , SM/12490 | Augmentation | Electric Quotation for BAJKUL Water Supply Scheme T/W-II, Zone- II, (Ref. ID-204114267) | BP-2023-24-375 | 02/12/2023 | 0 | WBSEDCL | 4.77 | 0 | 0 | 0
437 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II , SM/12490 | Augmentation | Additional Quotation Bill for the Service connection at T/W NO-I , ZONE-II Of BAJKUL W/S Scheme Under Jal Jeevan Mission under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: KHEJURI C.C.C. Ref. Memo No-KJR/QTN/200 DT. 25-06-2024 Application NO- 100000111551 DT. 25-06-2024 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860303091 | BP-2024-25-379 | 08/07/2024 | 0 | WBSEDCL | 0.53 | 0 | 0 | 0
438 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II , SM/12490 | Augmentation | Laying of Distribution pipe line to accommodate FHTC (2244 Nos) with construction of R.C.C. Elevated Reservoir of capacity 300 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Bajkul Zone - II Water Supply Scheme within Bhagabanpur- II Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | 1891/TD | 24/11/2022 | 1103 | MAA ANANDAMAYEE | 407.46 | 227.81 | 55.91 | 50
439 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II , SM/12490 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II, Block Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 819/W/MMD | 24/03/2023 | 180 | S.K.ENTERPRISE | 23.7 | 21.81 | 92.05 | 85
440 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II , SM/12490 | Augmentation | Laying of Left-Out portion uPVC Pipe line, Construction of New Pump House, Boundary Wall and others allied works for 3rd Tube well site and Repair & renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site and 2nd Tube well site at mouza- Kismat Bajkul,J.L- No -156, under Bajkul Zone-II Water Supply scheme. ( Augmentation) in Bhagabanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 2185/TD | 01/09/2023 | 770 | MAA ANANDAMAYEE | 84.88 | 37.42 | 44.09 | 60
441 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II , SM/12490 | Augmentation | Brick bats road due to smoothly carring Rig Machine and soil testing equipment for Head Works site at Mouza-Pora Chingra, J.L. NO.-155, under Bajkul Zone-II W/S Scheme (Augmentation) within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1705/CSD | 31/08/2023 | 15 | M/S MONDAL CONSTRUCTION & CO. | 0.8 | 0 | 0 | 0
442 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bhajachauli Water Supply Scheme under Tamluk Division, PHE Dte. | 1186/TD | 02/12/2021 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 12.34 | 9.91 | 100 | 100
443 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Supply & Delivery of different dia Sluice Valve for Augmentation of Bhajachauli Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | 629/TD | 23/06/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.44 | 4.44 | 100 | 100
444 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Augmentation of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART- D [Bamania Jangal(62) part, Chhota Sijua(64) part, Parihara(65), Panchberya(67) part, Dhandali Bar(139) part, Bhaja Chauli(140)]. | 322/TD | 11/05/2022 | 45 | SRIMANTA KUMAR MAITY | 287.16 | 264.06 | 91.96 | 92
445 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Augmentation of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART - A [ Bamania(74), Ugalpur(73), Kajli(70), Katmuri(69), Amratalia(68), Panchberya(67) part]. | 395/TD | 23/05/2022 | 30 | PRANAB KUMAR DAS | 118.3 | 93.84 | 79.33 | 65
446 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Augmentation of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART- B [Dhandi Bar (139) part]. | 385/TD | 20/05/2022 | 30 | SWARUPANANDA DAS | 120.93 | 117.93 | 97.52 | 100
447 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional(4th) Tubewell of Augmentation of Bhagwanpur Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia. x 250 mtr. deep tube well by direct rotary rig method at Additonal 3rd Tubewell of Augmentation of Bhajachauli Water Supply Scheme (Mouza - Khalsiberia, JL No. - 138, Plot No. - 162/387) within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 1224/TD | 07/09/2022 | 21 | B. K. ENTERPRISE | 34.31 | 16.53 | 96.36 | 0
448 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Construction of TW (300mm x 200mm x Depth 250 Mtr.) for Bhajachauli WS Scheme (TW-II), Contai-III block within Purba Midnapur District by utilising Skilled Departmental crew & machineries of CDD, PHE Dte. | 414/CDD | 20/05/2022 | 30 | M/S B.P.TRADING CORPORATION | 14.69 | 5.48 | 100 | 45
449 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Resistivity Survey & other works of Bhajachauli WS Scheme (TW-III), Contai-III Block under Purba Midnapur District, CDD, PHE Dte. | 1640/CDD | 20/12/2022 | 30 | M/S B.P.TRADING CORPORATION | 12.62 | 10.21 | 100 | 100
450 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Material Requisition To Resource Division | 644/TD | 27/06/2022 | 0 | Resource Division | 23.79 | 0 | 0 | 0
451 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Material Requisition To Resource Division | 101/TD | 11/04/2022 | 0 | Resource Division | 21.75 | 0 | 0 | 0
452 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Electric Quotation for BHAJACHAULI Water Supply Scheme T/W-III, (Ref. ID-204050249) | BP-2023-24-167 | 04/08/2023 | 0 | WBSEDCL | 1.74 | 0 | 0 | 0
453 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Rising main and other allied works of 3rd Tube Well for Augmentation of BHAJACHAULI W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 930/TD | 01/06/2023 | 25 | DEBABRATA DAS | 4.31 | 2.81 | 100 | 100
454 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for BHAJACHAULI PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-160.00 mtr.) | 931/TD | 01/06/2023 | 40 | DEBABRATA DAS | 22.69 | 21.07 | 100 | 100
455 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Construction of 3.60 mtr. x 3.00 mtr. size switch Room cum chlorine room without sanitary & water supply arrangements including plinth protection at 3rd TW site for Bhajachauli Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 929/TD | 01/06/2023 | 25 | DEBABRATA DAS | 3.53 | 3.53 | 100 | 100
456 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Laying Distribution Pipe Line & Accommodate FHTC (146 nos) under JJM with allied work for Left out Areas of BHAJACHAULI- PWSS in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 2198/TD | 01/09/2023 | 30 | SUBHENDU HAZRA | 19.54 | 18.3 | 100 | 100
457 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Repairing of Switch Room cum Chlorin Room at 2nd TW site at Bhajachauli Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Low Land) | 2971/TD | 28/11/2023 | 45 | SUBHENDU HAZRA | 3.53 | 3.34 | 100 | 100
458 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Augmentation of Bhajachauli Water Supply Scheme for Supply and Delivery of Different dia Sluice Valves under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2128/CSD | 24/11/2023 | 20 | SAURAV HAZRA | 1.22 | 1.22 | 100 | 100
459 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Washout pipeline, Repairing of OHR, Pump House no 1 under JJM with allied work of Bhajachauli PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 3056/TD | 19/09/2024 | 186 | SUBHENDU HAZRA | 31.12 | 0 | 0 | 50
460 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Augmentation Of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART-C [Bamania Jangal (62) part, Sijua (63), Chhota Sijua (64) part.] | 433/TD | 27/05/2022 | 981 | SNEHESH SEN | 113.07 | 89.13 | 93.03 | 100
461 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli , SM/09912 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 806/W/MMD | 24/03/2023 | 536 | DEBKUMAR BASU | 13.58 | 12.76 | 95.59 | 100
462 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Suadighi (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | 1694/TD | 31/01/2022 | 20 | CONCORD ENGINEERING | 4.2 | 4.02 | 100 | 100
463 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Suadighi (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | 1695/TD | 31/01/2022 | 20 | CONCORD ENGINEERING | 4.47 | 4.47 | 100 | 100
464 | PURBA MEDINIPUR | Central Drilling | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUADIGHI PWSS, ZONE-II, TW-II, BHAGAWANPUR -II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 375/CDD | 13/05/2022 | 30 | MENAKA ENTERPRISE | 14.69 | 5.66 | 100 | 100
465 | PURBA MEDINIPUR | Central Drilling | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUADIGHI PWSS, ZONE-I, TW-I, BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 430/CDD | 23/05/2022 | 30 | MENAKA ENTERPRISE | 14.69 | 5.65 | 100 | 100
466 | PURBA MEDINIPUR | Central Drilling | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN SUADIGHI PWSS, BLOCK BHAGAWANPUR-II, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. | 151/S&WSD | 12/08/2022 | 15 | MENAKA ENTERPRISE | 4.99 | 4.97 | 100 | 100
467 | PURBA MEDINIPUR | Central Drilling | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 260 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUADIGHI W/S SCH (TW-II), BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 1349/CDD | 24/11/2022 | 30 | PADMA ENGINEERING & CO. | 19.77 | 16.95 | 100 | 100
468 | PURBA MEDINIPUR | Central Drilling | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN SUADIGHI PWSS, ZONE-I, TW-I, BLOCK - KHEJURI, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. | 152/S&WSD | 12/08/2022 | 15 | MENAKA ENTERPRISE | 4.99 | 4.97 | 100 | 100
469 | PURBA MEDINIPUR | Central Drilling | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN SUADIGHI PWSS, ZONE-II, TW-II, BLOCK-KHEJURI, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. | 150/S&WSD | 12/08/2022 | 15 | MENAKA ENTERPRISE | 4.91 | 4.88 | 100 | 100
470 | PURBA MEDINIPUR | Central Drilling | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL INSUADIGHI PWSS, ZONE-II, TW-II, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. | 149/S&WSD | 12/08/2022 | 15 | MENAKA ENTERPRISE | 4.98 | 4.95 | 100 | 100
471 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1498) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 476/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.91 | 0 | 0 | 0
472 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 1st Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1228) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 481/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.91 | 0 | 0 | 0
473 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Suadighi Zone-II Water Supply Scheme in Bhagabanpur II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | 2266/TD | 30/12/2022 | 20 | MAKALI ENGINEERING CORPORATION | 1.01 | 0 | 0 | 0
474 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements at 1st TW (Head Work) site at Suadighi Zone-II Water Supply Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Low Land) | 1594/TD | 18/10/2022 | 60 | M/S. NEW DINDA ENTERPRISE | 6.94 | 6.32 | 100 | 100
475 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Suadighi Zone-II Water Supply Scheme in Bhagabanpur II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | 2261/TD | 30/12/2022 | 20 | SWASTIK ENTERPRISE | 6.18 | 6.18 | 100 | 100
476 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Suadighi Zone-I Water Supply Scheme in Bhagabanpur II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | 1435/TD | 27/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.34 | 7.34 | 100 | 100
477 | PURBA MEDINIPUR | Central Drilling | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Providing drilling crew and other allied works for construction of TW (300mm x 200mm x 260mtrs. depth) by utilising Departmental Machineries for Suadighi WS Scheme (TW-I) Bhagwanpur-II block under Purba midnapore Dist., CDD,PHE Dte. | 1348/CDD | 24/11/2022 | 30 | MENAKA ENTERPRISE | 19.77 | 17.03 | 100 | 100
478 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements at for 3rd Tube well J.L no. -257,Plot no. -240, Mouza -Kasba under Suadighi Zone-I Water Supply Scheme within Bhawanpur-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 2097/TD | 13/12/2022 | 60 | SMMD | 3.4 | 3.16 | 100 | 100
479 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including land development at for 2nd Tube well site J.L no. -262,Plot no. -272, Mouza -Keshaidighi under Suadighi Zone-II Water Supply Scheme within Bhawanpur-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 2098/TD | 13/12/2022 | 60 | SMMD | 3.46 | 3.45 | 100 | 100
480 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Material Requisition To Resource Division | 649/TD | 27/06/2022 | 0 | Resource Division | 21.19 | 0 | 0 | 0
481 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Material Requisition To Resource Division | 95/TD | 11/04/2022 | 0 | Resource Division | 58.97 | 0 | 0 | 0
482 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Material Requisition To Resource Division | 648/TD | 27/06/2022 | 0 | Resource Division | 21.41 | 0 | 0 | 0
483 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Electric Quotation for SUADIGHI Water Supply Scheme T/W-II, Zone-II (Ref. ID-204020001) | BP-2023-24-201 | 24/08/2023 | 0 | WBSEDCL | 0.56 | 0 | 0 | 0
484 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Electric Quotation for Suadighi Water Supply Scheme Zone-I, TW-III (Ref. Id-203950247) | BP-2023-24-38 | 04/05/2023 | 0 | WBSEDCL | 0.56 | 0 | 0 | 0
485 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Electric Quotation for Suadighi Water Supply Scheme TW-I , zone-II (Ref. ID -203932077) | BP-2023-24-26 | 04/05/2023 | 0 | WBSEDCL | 0.56 | 0 | 0 | 0
486 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Restoration of Hard shoulder at Heria-Mugberia and Itaberia-Mugberia Road after laying pipe line by PHE under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 | BP-2023-24-121 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 5.16 | 0 | 0 | 0
487 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Suadighi piped water supply scheme (Zone II), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 205/W/MMD | 10/02/2023 | 180 | BALAJI CONSTRUCTION | 40.78 | 34.24 | 83.94 | 70
488 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 101/HESD | 27/02/2023 | 184 | S.S.GHORAI | 0.9 | 0 | 0 | 53
489 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Dhalua, JL No. 243 Plot No. 152) of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1498) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 2047/TD | 25/08/2023 | 40 | PADMA ENGINEERING CO. | 38.21 | 0 | 0 | 44
490 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Suadighi piped water supply scheme (Zone I), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 208/W/MMD | 10/02/2023 | 180 | NIRMAN | 27.16 | 25.53 | 93.98 | 75
491 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Left out Portion of uncovered area with upvc pipes with allied works of Suadighi Zone-I PWSS in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 1038/TD | 15/03/2024 | 350 | S.D. CONSTRUCTION | 43.4 | 9.08 | 20.93 | 50
492 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Rising main, Boundary Wall under JJM with allied work at 3rd TW site for Augmentation of SUADIGHI ZONE-I PWSS in Bhagwanpur-II Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 2598/TD | 10/10/2023 | 40 | A. R. CONSTRUCTION | 14.76 | 9.66 | 100 | 100
493 | PURBA MEDINIPUR | Central Drilling | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Suadighi W/S Scheme( TW-III) , Bhagawanpur-II Block under Purba Midnapore District, Central Drilling Division, P.H.E. Dte. | 1453/CDD | 30/11/2023 | 120 | MENAKA ENTERPRISE | 18.35 | 15.83 | 100 | 100
494 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Electric Quotation for Suadighi Water Supply Scheme TW-I , zone-II (Ref. ID -203932077) |  | 28/04/2023 | 0 | WBSEDCL | 0.56 | 0 | 0 | 0
495 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | quotation for new power connection at newly sunk t/w at Madhakhali w/s scheme zone -II , T/W - I |  | 23/05/2023 | 0 | WBSEDCL | 0.59 | 0 | 0 | 0
496 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Suadighi W/S scheme TW no.-III, Z-I Ref.-860286948 ID-100000094898 | BP-2023-24-449 | 19/12/2023 | 0 | WBSEDCL | 3.64 | 0 | 0 | 0
497 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE-II Of SUADIGHI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2004740459/QUOT/03 DT. 17-05-2024 Application NO- 2004740459 Application type-New connection Consumer Id- 204309985 | BP-2024-25-246 | 06/06/2024 | 0 | WBSEDCL | 7.11 | 0 | 0 | 0
498 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Suadighi Zone-II Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 814/TD | 12/07/2022 | 963 | JAYANTA KUMAR MONDAL | 584.44 | 426.54 | 72.98 | 80
499 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Suadighi Zone-I Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 815/TD | 12/07/2022 | 1085 | JAYANTA KUMAR MONDAL | 565.34 | 490.77 | 86.81 | 88
500 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including land development at for 3rd Tube well site J.L no. -253,Plot no. -1498, Mouza -Bhupatinagar under Suadighi Zone-II Water Supply Scheme within Bhawanpur-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 2099/TD | 13/12/2022 | 712 | SMMD | 3.4 | 0 | 0 | 0
501 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Laying Rising Main, Earth work filling & Construction of Boundary wall at OHR (1st), 2nd & 3rd Tube Well Site Mouza- Bhupatinagar & Keshaidighi, J.L No.-253,262 for Augmentation of Suadighi Zone-II PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division,PHE Dte. | 1599/TD | 24/07/2023 | 540 | JAYANTA KUMAR MONDAL | 45.98 | 0 | 0 | 0
502 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Left-out portion of uncovered area of different dia. uPVC pipeline within Suadighi Zone-II Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 1910/TD | 07/06/2024 | 267 | SETH ENTERPRISE | 48.35 | 0 | 0 | 0
503 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Suadighi piped water supply scheme. , SM/09919 | Augmentation | Boundary Wall Repair at 2nd TW Site and Construction of Toilet at 1st TW site of Suadighi Zone-I PWSS in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 3339/TD | 22/10/2024 | 40 | BIBEKANANDA DAS | 7.03 | 0 | 0 | 0
504 | PURBA MEDINIPUR | Tamluk Division | BIRAMPUT AND ADJOINING MOUJAS PWSS , SM/12497 | New | Material Requisition To Resource Division | 2390/TD | 16/01/2023 | 0 | Resource Division | 43.89 | 0 | 0 | 0
505 | PURBA MEDINIPUR | Tamluk Division | BIRAMPUT AND ADJOINING MOUJAS PWSS , SM/12497 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Biramput PWSS at Contai-I Block under Tamluk Division, PHE Dte. | 2067/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
506 | PURBA MEDINIPUR | Tamluk Division | BIRAMPUT AND ADJOINING MOUJAS PWSS , SM/12497 | New | Material Requisition To Resource Division | 2951/TD | 12/09/2024 | 0 | Resource Division | 5.79 | 0 | 0 | 0
507 | PURBA MEDINIPUR | Midnapore Mechanical | BIRAMPUT AND ADJOINING MOUJAS PWSS , SM/12497 | New | Quotation Bill for New Service connection at T/W NO-I Of BIRAMPUT W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, CONTAI C.C.C. Ref. Memo No-2004614786/QUOT/03 DT. 23-02-2024 Application NO- 2004614786 Application type-New connection Reference Id- 204225082 | BP-2023-24-792 | 06/03/2024 | 0 | WBSEDCL | 3.83 | 0 | 0 | 0
508 | PURBA MEDINIPUR | Tamluk Division | NARAYAN DANRI AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12401 | New | Material Requisition To Resource Division | 2723/TD | 06/02/2023 | 0 | Resource Division | 15.86 | 0 | 0 | 0
509 | PURBA MEDINIPUR | Midnapore Mechanical | NARAYAN DANRI AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12401 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NARAYAN DANRI and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 468/W/MMD | 20/03/2023 | 180 | SOUMEN ELECTRIC | 23.68 | 16.85 | 71.14 | 30
510 | PURBA MEDINIPUR | Tamluk Division | NARAYAN DANRI AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12401 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2046 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of NARAYAN DANRI PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 72/TD | 05/01/2024 | 540 | SRIMANTA KUMAR MAITY | 519.29 | 23.48 | 4.66 | 25
511 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Material Requisition To Resource Division | 2987/TD | 27/02/2023 | 0 | Resource Division | 29.7 | 0 | 0 | 0
512 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(ii)) | 3239/TD | 15/03/2023 | 45 | MAHAPRABHU ENTERPRISE | 9.86 | 2.02 | 20.46 | 21
513 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | 3216/TD | 14/03/2023 | 60 | THREE MAA ENTERPRISE | 64.69 | 39.91 | 61.69 | 50
514 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (100 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(iii)) | 3240/TD | 15/03/2023 | 996 | MODERN CONSTRUCTION | 9.69 | 4.86 | 50.16 | 43
515 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (200 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | 3214/TD | 14/03/2023 | 30 | G. S. CONSTRUCTION | 34.87 | 26.93 | 77.22 | 79
516 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (100 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(iv)) | 521/TD | 11/05/2023 | 849 | PRASANTA MONDAL | 8.09 | 3.41 | 42.16 | 35
517 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (100 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C(ii)) | 877/TD | 01/06/2023 | 30 | TARUN KHATUA | 28.18 | 27.54 | 97.73 | 85
518 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (115 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(i)) | 3238/TD | 15/03/2023 | 45 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 9.62 | 9.32 | 100 | 100
519 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C(i)) | 876/TD | 01/06/2023 | 45 | TARUN KHATUA | 11.03 | 10.07 | 100 | 100
520 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | "G.I pipe column with M.S. Structure for laying of HDPE pipe line with Casing at Kanchanpur Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. " (Total Length= 60.00 mtr, {i) NP-21 to 27= 30.00 mtr + ii) NP-44 to 50= 30.00 mtr .} | 727/TD | 28/02/2024 | 30 | TARUN KHATUA | 8.88 | 8.71 | 100 | 100
521 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Material Requisition To Resource Division | 115/TD | 05/01/2024 | 0 | Resource Division | 10.5 | 0 | 0 | 0
522 | PURBA MEDINIPUR | Midnapore Mechanical | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Quotation for Kanchanpur w/s scheme PH I in the Purba Medinipur under MMD PHE Dte.(Ref ID 204216166, App No 2004599555) | BP-2023-24-755 | 01/03/2024 | 0 | WBSEDCL | 5.06 | 0 | 0 | 0
523 | PURBA MEDINIPUR | Midnapore Mechanical | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Quotation for Kanchanpur w/s scheme PH II in the Purba Medinipur under MMD PHE Dte.(Ref ID 204216165, App No 2004599558) | BP-2023-24-756 | 01/03/2024 | 0 | WBSEDCL | 3.82 | 0 | 0 | 0
524 | PURBA MEDINIPUR | Midnapore Mechanical | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KANCHANPUR and ADJOINING MOUJAS, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 466/W/MMD | 20/03/2023 | 914 | DEY ENTERPRISE | 23.7 | 11.15 | 47.04 | 45
525 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 300 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | 1099/TD | 08/06/2023 | 877 | MAA ANANDAMAYEE | 139.46 | 0 | 0 | 2
526 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Construction of Retaining wall, Approach road & Earth filling Work in Head work site of Kanchanpur Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(length of Retaining wall-120mtr) & (length of Approach road- 60 mtr). | 3705/TD | 03/12/2024 | 200 | TARUN KHATUA | 17.55 | 0 | 0 | 90
527 | PURBA MEDINIPUR | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS , SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (280 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-F) | 3213/TD | 14/03/2023 | 654 | SK MAIDUL ISLAM | 39.57 | 25.63 | 64.79 | 60
528 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS , SM/12405 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN KADUA and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 941/W/MMD | 28/03/2023 | 180 | S.G.ENTERPRISE | 21.6 | 0 | 0 | 0
529 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS , SM/12405 | New | Material Requisition To Resource Division | 2406/TD | 16/01/2023 | 0 | Resource Division | 18.29 | 0 | 0 | 0
530 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS , SM/12405 | New | Material Requisition To Resource Division | 2954/TD | 12/09/2024 | 0 | Resource Division | 5.5 | 0 | 0 | 0
531 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS , SM/12405 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House ,Boundary Wall & Providing Functional Household Tap Connection (3734 Nos), including 2 years Operation & Maintenance For Purba Mukundapur, Dakshin Kadua, Purba Mahammadpur Pipe water supply Scheme within Deshapran Block Under Tamluk Division PHE Dte. | 1593/TD | 21/07/2023 | 711 | JAYANTA KUMAR MONDAL | 1264.74 | 0 | 0 | 30
532 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Material Requisition To Resource Division | 2968TD | 27/02/2023 | 0 | Resource Division | 21.55 | 0 | 0 | 0
533 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Laying distribution pipe line, & Accommodate FHTC (325 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-D) | 376/TD | 27/04/2023 | 60 | A. K. SIKDAR | 73.19 | 35.95 | 49.12 | 52
534 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Laying distribution pipe line, & Accommodate FHTC (322 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-E) | 377/TD | 27/04/2023 | 668 | SWARUPANANDA DAS | 73.44 | 36.55 | 49.77 | 50
535 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Laying distribution pipe line, Boundary Wall & Accommodate FHTC (160 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-B) | 516/TD | 11/05/2023 | 60 | NEW STAR CONSTRUCTION | 84.23 | 60.35 | 71.65 | 73
536 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Tube well, Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert, CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (195 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-A) | 1016/TD | 06/06/2023 | 900 | DAS ENTERPRISE | 189.43 | 0 | 0 | 10
537 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Panushi PWSS at Bhagwanpur-II Block under Tamluk Division,PHE Dte. | 381/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
538 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Instalation of display Board at different work site of Pachahari, Basudevberya,Panusi & Adjoining Moujas New PWSS in Bhagawanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2329/CSD | 29/12/2023 | 10 | KAMAL KUMAR BERA | 0.62 | 0.62 | 100 | 100
539 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Material Requisition To Resource Division | 635/W | 20/02/2024 | 0 | Resource Division | 12.55 | 0 | 0 | 0
540 | PURBA MEDINIPUR | Midnapore Mechanical | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Quotation Bill for New Service connection at T/W NO-II Of PANUSI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2004615668/QUOT/03 DT. 23-02-2024 Application NO- 2004615668 Application type-New connection Consumer Id- 204225684 | C102412615985 | 04/10/2024 | 0 | WBSEDCL | 11.08 | 0 | 0 | 0
541 | PURBA MEDINIPUR | Midnapore Mechanical | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Quotation Bill for New Service connection at T/W NO-I Of PANSUI W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004601802/QUOT/03 DT. 15-02-2024 Application NO- 2004601802 Application type-New connection Reference Id- 204217830 | BP-2023-24-811 | 11/03/2024 | 0 | WBSEDCL | 6.85 | 0 | 0 | 0
542 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Laying distribution pipe line, & Accommodate FHTC (200 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte.(Part-G) | 379/TD | 27/04/2023 | 30 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 38.51 | 22.02 | 57.16 | 60
543 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Laying distribution pipe line, & Accommodate FHTC (150 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-H) | 380/TD | 27/04/2023 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 26.52 | 14.8 | 55.8 | 58
544 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Laying distribution pipe line, & Accommodate FHTC (170 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte.(Part-I) | 381/TD | 27/04/2023 | 25 | M/S. NEW DINDA ENTERPRISE | 19.14 | 7.88 | 41.18 | 45
545 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Laying distribution pipe line, & Accommodate FHTC (140 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-F) | 378/TD | 27/04/2023 | 30 | M/S. NEW DINDA ENTERPRISE | 38.62 | 22.81 | 59.07 | 65
546 | PURBA MEDINIPUR | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Laying distribution pipe line, Pump House & Accommodate FHTC (375 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-C) | 517/TD | 11/05/2023 | 818 | S.S.T ENGINEERING | 77.56 | 47.05 | 60.66 | 65
547 | PURBA MEDINIPUR | Central Drilling | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 75.69 | 148.35 | 11
548 | PURBA MEDINIPUR | Central Drilling | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Hiring of Diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Superintending Engineer, M/E, PMU WBDWSIP P.H.E. Dte. under CMSD-I(D), CDD, P.H.E. Dte. | 254/CMSD-I | 26/06/2024 | 182 | SIDDHARTHA CHATTERJEE | 0.89 | 0.97 | 108.55 | 0
549 | PURBA MEDINIPUR | Midnapore Mechanical | PANUSI AND ADJOINING MOUJAS PWSS , SM/12506 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
550 | PURBA MEDINIPUR | Tamluk Division | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS , SM/12433 | New | Material Requisition To Resource Division | 2991/TD | 27/02/2023 | 0 | Resource Division | 14.06 | 0 | 0 | 0
551 | PURBA MEDINIPUR | Midnapore Mechanical | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS , SM/12433 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TALCHITKINI and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 520/W/MMD | 20/03/2023 | 180 | BIJAN ENTERPRISE | 22.72 | 0 | 0 | 0
552 | PURBA MEDINIPUR | Tamluk Division | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS , SM/12433 | New | Sinking of Tube well,Pump House ,Construction of 200 cum & 250 Cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3146 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Dhankar & Talchitkini its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1671/TD | 25/07/2023 | 860 | HALDIA DEVELOPMENT CONSTRUCTION | 895.07 | 0 | 0 | 20
553 | PURBA MEDINIPUR | Midnapore Mechanical | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11859 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 808/W/MMD | 24/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 13.58 | 8.29 | 61.02 | 60
554 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11859 | Augmentation | Material Requisition To Resource Division | 347/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0 | 0
555 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11859 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 0 | 0 | 100
556 | PURBA MEDINIPUR | Midnapore Mechanical | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11859 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 0 | 50
557 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11859 | Augmentation | Dismantling & Re-Construction of Boundary Wall and Land Filling at 2nd TW site for Site Preparation for Lowering of Replacement Tube Well at Paschimbetya PWSS for within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1495/TD | 17/07/2023 | 15 | PULAK KUMAR SAMANTA | 4.84 | 0 | 0 | 30
558 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS , SM/12485 | Augmentation | Laying of Distribution System to accomodate FHTC (3086 Nos) for Augmentation of Ramnagar Water Supply Scheme (Zone-I) within Ramnagar-I Block under Tamluk Division in the district of Purba Medinipur. | 2533/TD | 19/01/2023 | 90 | BASANTA KUMAR MAITY | 287.99 | 125.94 | 43.73 | 45
559 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS , SM/12485 | Augmentation | Material Requisition To Resource Division | 2613/TD | 02/02/2023 | 0 | Resource Division | 75.91 | 0 | 0 | 0
560 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS , SM/12485 | Augmentation | Material Requisition To Resource Division | 2639/TD | 02/02/2023 | 0 | Resource Division | 19.01 | 0 | 0 | 0
561 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS , SM/12485 | Augmentation | Laying of Distribution Pipe Line for Balance 180 mm dia HDPE pipe( N.P-72-74(P)=18.0M, 53-72=298.0M, 34-53(P)=53.0M) within Ramnagar Zone-I & Its Adjoining Mouzas Water Supply Scheme of Ramnagar-I Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. (Part-A) | 1032/TD | 15/03/2024 | 45 | APARNA CONSTRUCTION | 4.72 | 4.72 | 100 | 100
562 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS , SM/12485 | Augmentation | Laying of Distribution Pipe Line for Balance 180 mm dia HDPE pipe( N.P- 34-53(P)=233.0M, 26-34=136.0M) within Ramnagar Zone-I & Its Adjoining Mouzas Water Supply Scheme of Ramnagar-I Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. (Part-B) | 1033/TD | 15/03/2024 | 45 | BASANTI ENTERPRISE | 4.69 | 4.67 | 100 | 100
563 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ramnagar (Zone-I) PWSS , SM/12485 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE-I Of RAMNAGAR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004957544/QUOT/03 DT. 06-11-2024 Application NO- 2004957544 Application type-New connection Consumer Id- 204440003 | C112423558120 | 19/11/2024 | 0 | WBSEDCL | 2.66 | 0 | 0 | 0
564 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ramnagar (Zone-I) PWSS , SM/12485 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ramnagar (Zone-I) PWSS, Block Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 820/W/MMD | 24/03/2023 | 860 | M/S SWAPAN BANERJEE | 27.17 | 0 | 0 | 52
565 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS , SM/12485 | Augmentation | Construction of Pump House, Boundary Wall, Laying of Rising main with distribution pipe line & Accommodate FHTC ( 500 Nos) under JJM with allied work for Ramnagar Zone-I & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 169/TD | 09/01/2024 | 45 | BASANTA KUMAR MAITY | 104.58 | 38.48 | 36.8 | 41
566 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS , SM/12485 | Augmentation | Renovation & Repairing of existing pump house - II at 2nd tube well site of Ramnagar Zone-I W/S Scheme within Ramnagar-I Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 1316/DSD | 13/01/2025 | 7 | PURNENDU MAITY | 0.94 | 0 | 0 | 0
567 | PURBA MEDINIPUR | Tamluk Division | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS , SM/12129 | New | Material Requisition To Resource Division | 2676/TD | 06/02/2023 | 0 | Resource Division | 35.6 | 0 | 0 | 0
568 | PURBA MEDINIPUR | Midnapore Mechanical | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS , SM/12129 | New | Chawrakalganda W/S scheme T/W-I Application No.-2004520328 Ref:-204154822 | BP-2023-24-438 | 18/12/2023 | 0 | WBSEDCL | 8.99 | 0 | 0 | 0
569 | PURBA MEDINIPUR | Midnapore Mechanical | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS , SM/12129 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 627/W/MMD | 20/03/2023 | 957 | P.K.ENGINEERING | 23.7 | 18.1 | 76.38 | 35
570 | PURBA MEDINIPUR | Tamluk Division | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS , SM/12129 | New | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(5198nos), Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of different capacity as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Chawrakalganda PWSS & Mirikpur PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 433/TD | 03/05/2023 | 820 | ARABINDA GHOSH | 1233.42 | 423.27 | 89.89 | 65
571 | PURBA MEDINIPUR | Tamluk Division | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS , SM/12134 | New | Material Requisition To Resource Division | 2726/TD | 06/02/2023 | 0 | Resource Division | 59.37 | 0 | 0 | 0
572 | PURBA MEDINIPUR | Midnapore Mechanical | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS , SM/12134 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BETULYA CHAKLALPUR and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2325/W/MMD | 29/12/2022 | 180 | S.S.GHORAI | 23.7 | 14.81 | 62.47 | 55
573 | PURBA MEDINIPUR | Tamluk Division | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS , SM/12134 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Betula Chaklalpur Water Supply Scheme at Bhagwanpur-I Block under Tamluk Division, PHE Dte. | 1050/TD | 15/03/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
574 | PURBA MEDINIPUR | Tamluk Division | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS , SM/12134 | New | Material Requisition To Resource Division | 94/TD | 05/01/2024 | 0 | Resource Division | 12.25 | 0 | 0 | 0
575 | PURBA MEDINIPUR | Midnapore Mechanical | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS , SM/12134 | New | Quotation Bill for New Service connection at T/W NO-I Of BETULIACHAKLALPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818516/QUOT/03 DT. 12-07-2024 Application NO- 2004818516 Application type-New connection Consumer Id- 204355509 | C082410083941 | 08/08/2024 | 0 | WBSEDCL | 13.02 | 0 | 0 | 0
576 | PURBA MEDINIPUR | Tamluk Division | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS , SM/12134 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1988 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of BETULYA CHAKLAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 413/TD | 02/05/2023 | 728 | DAS CONSTRUCTION | 517.7 | 0 | 0 | 7
577 | PURBA MEDINIPUR | Tamluk Division | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. , SM/12318 | New | Material Requisition To Resource Division | 2434/TD | 16/01/2023 | 0 | Resource Division | 39.7 | 0 | 0 | 0
578 | PURBA MEDINIPUR | Tamluk Division | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. , SM/12318 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Chongra PWSS at Moyna Block under Tamluk Division,PHE Dte. | 202/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
579 | PURBA MEDINIPUR | Tamluk Division | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. , SM/12318 | New | Material Requisition To Resource Division | 1561/TD | 23/04/2024 | 0 | Resource Division | 11.88 | 0 | 0 | 0
580 | PURBA MEDINIPUR | Midnapore Mechanical | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. , SM/12318 | New | Quotation of New service connection at Chongra w/s scheme PH I at Moyna Block in the District of Purba Medinipur under MMD PHE Dte. (App ID 2004653990 Con ID 204255037) | BP-2024-25-32 | 15/04/2024 | 0 | WBSEDCL | 15.26 | 0 | 0 | 0
581 | PURBA MEDINIPUR | Midnapore Mechanical | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. , SM/12318 | New | Quotation of New service connection at Chongra w/s scheme PH II at Moyna Block in the District of Purba Medinipur under MMD PHE Dte. (App ID 2004653966 Con ID 204255035) | BP-2024-25-33 | 15/04/2024 | 0 | WBSEDCL | 8.93 | 0 | 0 | 0
582 | PURBA MEDINIPUR | Tamluk Division | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. , SM/12318 | New | Instalation of display Board at 5 nos { 1. CHONGRA PWSS( PUMP HOUSE -1) , 2. BASANTA CHAK PWSS( PUMP HOUSE 1 & 2), 3. GOKUL NAGAR PWSS( PUMP HOUSE 1 & 2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 57/RWS/TSD | 06/05/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
583 | PURBA MEDINIPUR | Midnapore Mechanical | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. , SM/12318 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHONGRA and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2373/W/MMD | 31/12/2022 | 720 | DIPALI CONSTRUCTION | 23.68 | 13.53 | 36.89 | 50
584 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District , SM/09273 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chatra Water Supply Scheme under Tamluk Division, PHE Dte. | 1189/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 3.53 | 3.53 | 100 | 100
585 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District , SM/09273 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Rejuvenation of Chatra Water Supply Scheme in Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District | 1836/TD | 08/08/2023 | 20 | RAMESH & SHANTI ENGINEERING WORKS | 3.13 | 3.13 | 100 | 100
586 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District , SM/09273 | Augmentation | Material Requisition To Resource Division | 1731/TD | 02/02/2022 | 0 | Resource Division | 8.76 | 0 | 0 | 0
587 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District , SM/09273 | Augmentation | Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division ,PHE Dte. Under Tamluk Division for the period from 12 (Twelve) Months. | 1345/TSD | 28/10/2022 | 239 | TAPAS SANTRA | 1.14 | 2.39 | 100 | 100
588 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District , SM/09273 | Augmentation | Material Requisition To Resource Division | 1112/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
589 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District , SM/09273 | Augmentation | Rejuvenation of Ground Water Based Chatra PWSS by Providing Laying Distribution System and FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in the District of Purba Medinipur. | 1648/TD | 20/01/2022 | 90 | MAITY ENTERPRISE | 165.08 | 51.25 | 31.05 | 35
590 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District , SM/09273 | Augmentation | Repairing and Renovation of the Elevated Water Reservoir, Renovation of Switch Room cum Chlorine Room with water supply & sanitary arrangement at 2nd. T/W Site Along with Renovation of Existing Boundary Wall and Renovation of Switch Room cum Chlorine Room with sanitary arrangement at 1st. Tube well site i.c.w Rejuvenation of Ground Water Based Chatra PWSS by Providing Laying Distribution System and FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in the District of Purba Medinipur. | 3335/TD | 22/10/2024 | 436 | TAPAS SANTRA | 14.99 | 0 | 0 | 100
591 | PURBA MEDINIPUR | Midnapore Mechanical | SOYA DIGHI AND IT'S ADJOINING MOUJAS , SM/12809 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SOYA DIGHI and ADJOINING MOUJAS, Block - Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 943/W/MMD | 28/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 22.79 | 0 | 0 | 0
592 | PURBA MEDINIPUR | Tamluk Division | SOYA DIGHI AND IT'S ADJOINING MOUJAS , SM/12809 | New | Material Requisition To Resource Division | 2680/TD | 06/02/2023 | 0 | Resource Division | 20.04 | 0 | 0 | 0
593 | PURBA MEDINIPUR | Tamluk Division | SOYA DIGHI AND IT'S ADJOINING MOUJAS , SM/12809 | New | Material Requisition To Resource Division | 110/TD | 05/01/2024 | 0 | Resource Division | 11.79 | 0 | 0 | 0
594 | PURBA MEDINIPUR | Midnapore Mechanical | SOYA DIGHI AND IT'S ADJOINING MOUJAS , SM/12809 | New | Quatation bill for Swadighi H/W Site W/S SCHEME under MMD,PHE,Dte. BLOCK- Sahid Matangini WBSEDCL SUPPLY OFFICE: Matangini C.C.C Ref. Memo No- 2004992438/Quot/03/1203 DT. 05-12-2024 APPLICATION NO: 2004992438 Consumer Id- 204463808 |  | 18/12/2024 | 0 | WBSEDCL | 8.06 | 0 | 0 | 0
595 | PURBA MEDINIPUR | Tamluk Division | SOYA DIGHI AND IT'S ADJOINING MOUJAS , SM/12809 | New | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1914 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SOYA DIGHI PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 412/TD | 02/05/2023 | 821 | JAYANTA KUMAR MONDAL | 418.27 | 73.15 | 17.49 | 40
596 | PURBA MEDINIPUR | Tamluk Division | GULURI AND IT'S ADJOING MOUJAS , SM/13888 | New | Material Requisition To Resource Division | 2470/TD | 16/01/2023 | 0 | Resource Division | 25.32 | 0 | 0 | 0
597 | PURBA MEDINIPUR | Tamluk Division | GULURI AND IT'S ADJOING MOUJAS , SM/13888 | New | Crossing permission of laying HDPE pipeline along and across of NH-116B of Guluri PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 742/TD | 28/02/2024 | 20 | DONA ASSOCIATES | 9.53 | 0 | 0 | 0
598 | PURBA MEDINIPUR | Tamluk Division | GULURI AND IT'S ADJOING MOUJAS , SM/13888 | New | Land Development work at Headwork Site of Guluria Water Supply Scheme within Sahid Matangini Development Block under Tamluk Sadar Sub-Division of Tamluk Division, PHE Dte. | 3050/TD | 19/09/2024 | 15 | S.D. CONSTRUCTION | 5.82 | 5.82 | 100 | 100
599 | PURBA MEDINIPUR | Tamluk Division | GULURI AND IT'S ADJOING MOUJAS , SM/13888 | New | Material Requisition To Resource Division | 131/TD | 05/01/2024 | 0 | Resource Division | 8.48 | 0 | 0 | 0
600 | PURBA MEDINIPUR | Midnapore Mechanical | GULURI AND IT'S ADJOING MOUJAS , SM/13888 | New | New electric Quotation as per bill for Guluri water supply scheme, T/W-II Matangini CCC Block- Sahid Matangini Application No.-2004770105 Consumer ID.-204328454 Date.-12/06/2024 | BP-2024-25-340 | 25/06/2024 | 0 | WBSEDCL | 3.61 | 0 | 0 | 0
601 | PURBA MEDINIPUR | Midnapore Mechanical | GULURI AND IT'S ADJOING MOUJAS , SM/13888 | New | Quotation Bill for New connection GULARI water supply scheme Head Work Site. Quotation Bill Date.-01/04/2024 Block-Kolaghat. Kolaghat CCC Application No.-2004662586 Ref no.-204260849 | BP-2024-25-28 | 15/04/2024 | 0 | WBSEDCL | 4.85 | 0 | 0 | 0
602 | PURBA MEDINIPUR | Midnapore Mechanical | GULURI AND IT'S ADJOING MOUJAS , SM/13888 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GULURI and ADJOINING MOUJAS, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 557/W/MMD | 20/03/2023 | 720 | SHIVAM ENTERPRISE | 22.78 | 10.61 | 46.57 | 75
603 | PURBA MEDINIPUR | Tamluk Division | GULURI AND IT'S ADJOING MOUJAS , SM/13888 | New | Sinking of Tube Well ,Construction of Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1376 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of GULURI PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 219/TD | 17/04/2023 | 900 | TAPAS SANTRA | 384.71 | 87.95 | 22.86 | 60
604 | PURBA MEDINIPUR | Tamluk Division | KIA AND IT'S ADJOINING MOUJAS , SM/12814 | New | Material Requisition To Resource Division | 2412/TD | 16/01/2023 | 0 | Resource Division | 35.2 | 0 | 0 | 0
605 | PURBA MEDINIPUR | Midnapore Mechanical | KIA AND IT'S ADJOINING MOUJAS , SM/12814 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KIA and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 942/W/MMD | 28/03/2023 | 709 | ORIENTAL ENGINEERING CO. | 22.79 | 7.34 | 32.2 | 90
606 | PURBA MEDINIPUR | Tamluk Division | KIA AND IT'S ADJOINING MOUJAS , SM/12814 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kia PWSS at Egra-I Block under Tamluk Division, PHE Dte. | 2083/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
607 | PURBA MEDINIPUR | Midnapore Mechanical | KIA AND IT'S ADJOINING MOUJAS , SM/12814 | New | Quotation for new service connection at TW-1 of KIA ws scheme under MMD, PHE DTE, Block-Egra-1, under EGRA CCC. Application no-2004607227, CON ID-204221794. | BP-2023-24-758 | 01/03/2024 | 0 | WBSEDCL | 4.72 | 0 | 0 | 0
608 | PURBA MEDINIPUR | Midnapore Mechanical | KIA AND IT'S ADJOINING MOUJAS , SM/12814 | New | Quotation Bill for New Service connection at T/W NO-II of KIA W/S Scheme under MMD, PHE, Dte. Block- Egra-I, Egra CCC Ref. Memo no- 2004607232/QUOT/03/3197 Dt. 20-Feb-2024 Application NO- 2004607232 Application type-New connection Reference Id- 204221796 | bp-2023-24-759 | 01/03/2024 | 0 | WBSEDCL | 3.79 | 0 | 0 | 0
609 | PURBA MEDINIPUR | Tamluk Division | KIA AND IT'S ADJOINING MOUJAS , SM/12814 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 261.62 | 49.47 | 51
610 | PURBA MEDINIPUR | Tamluk Division | BASANTIA AND IT'S ADJOINING MOUJAS PWSS , SM/14451 | New | Material Requisition To Resource Division | 2970/TD | 27/02/2023 | 0 | Resource Division | 21.24 | 0 | 0 | 0
611 | PURBA MEDINIPUR | Midnapore Mechanical | BASANTIA AND IT'S ADJOINING MOUJAS PWSS , SM/14451 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BASANTIA AND IT'S ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 597/W/MMD | 20/03/2023 | 180 | M/S. JIT ENTERPRISE | 22.8 | 0 | 0 | 0
612 | PURBA MEDINIPUR | Tamluk Division | BASANTIA AND IT'S ADJOINING MOUJAS PWSS , SM/14451 | New | Sinking of Tube well, Pump House, 300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Soil investigation & Accommodate FHTC (1581 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Basantia and Adjoining Moujas PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1412/TD | 12/07/2023 | 180 | JAYANTA KUMAR MONDAL | 413.14 | 102.11 | 24.72 | 85
613 | PURBA MEDINIPUR | Tamluk Division | BASANTIA AND IT'S ADJOINING MOUJAS PWSS , SM/14451 | New | Material Requisition To Resource Division | 2949/TD | 12/09/2024 | 0 | Resource Division | 9.74 | 0 | 0 | 0
614 | PURBA MEDINIPUR | Midnapore Mechanical | BASANTIA AND IT'S ADJOINING MOUJAS PWSS , SM/14451 | New | Quotation Bill for New Service connection at T/W NO-I Of BASANTIA W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004877659/QUOT/03 DT. 12-09-2024 Application NO- 2004877659 Application type-New connection Consumer Id- 204397982 | C092445108283 | 30/09/2024 | 0 | WBSEDCL | 7.85 | 0 | 0 | 0
615 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. , SM/14837 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Central Zone) under Tamluk Division, PHE Dte. | 1665/TD | 24/01/2022 | 20 | HORIZEN | 3.52 | 3.46 | 100 | 100
616 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. , SM/14837 | Augmentation | Material Requisition To Resource Division | 2077/TD | 28/08/2023 | 0 | Resource Division | 38.59 | 0 | 0 | 0
617 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. , SM/14837 | Augmentation | Material Requisition To Resource Division | 2642/TD | 13/10/2023 | 0 | Resource Division | 12.75 | 0 | 0 | 0
618 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. , SM/14837 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 101/HESD | 27/02/2023 | 184 | S.S.GHORAI | 0.9 | 0 | 0 | 53
619 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. , SM/14837 | Augmentation | Providing and Installation of electromechanical equipments for Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme in Block Ramnagar I under JJM Program under MMD PHE Dte. | 1241/W/MMD | 28/04/2023 | 180 | SOUMEN ELECTRIC | 33.56 | 33.15 | 100 | 100
620 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. , SM/14837 | Augmentation | Quotation for new service connection at TW-II of Digha Central zone under MMD, PHE Dte, Block-Ramnagar-I, DIGHA CCC Application no-2004812648 CON ID-204351925 | C072438486724 | 23/07/2024 | 0 | WBSEDCL | 0.71 | 0 | 0 | 0
621 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. , SM/14837 | Augmentation | Quotation for new service connection at T/W-III of Digha Central zone under MMD,PHE DTE, Block-Ramnagar-I, DIGHA CCC Application no-2004812635 CON ID-204351924 | C072438487551 | 23/07/2024 | 0 | WBSEDCL | 0.43 | 0 | 0 | 0
622 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. , SM/14837 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2069 nos) under JJM with allied work for Digha Augmentation (Central Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 2271/TD | 05/09/2023 | 808 | ORIENT CONSTRUCTION | 477.25 | 166.99 | 34.99 | 22
623 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. , SM/14838 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Eastern Zone) under Tamluk Division, PHE Dte. | .1651/TD | 20/01/2022 | 20 | HORIZEN | 4.21 | 4.15 | 100 | 100
624 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. , SM/14838 | Augmentation | Material Requisition To Resource Division | 2640/TD | 13/10/2023 | 0 | Resource Division | 13.39 | 0 | 0 | 0
625 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. , SM/14838 | Augmentation | Material Requisition To Resource Division | 2066/TD | 28/08/2023 | 0 | Resource Division | 106.76 | 0 | 0 | 0
626 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. , SM/14838 | Augmentation | Quotation for new service connection at T/W-III of Digha Eastern zone under MMD, PHE Dte, Block-Ramnagar-I,DIGHA CCC Application no-2004812582 CON ID-204351921 | C072438488216 | 23/07/2024 | 0 | WBSEDCL | 0.88 | 0 | 0 | 0
627 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. , SM/14838 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2052 nos) under JJM with allied work for Digha Augmentation (Eastern Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 1591/TD | 21/07/2023 | 864 | ATCO ENTERPRISE | 642.85 | 185.21 | 28.81 | 40
628 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. , SM/14838 | Augmentation | Repairing & renovation of Switch Room , existing boundary wall, Store Room, OHR 250 cum. capacity 20 m height, & Accommodate FHTC (125 Nos) under JJM with allied work for Digha Augmentation (Eastern Zone ) Water Supply Scheme under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 3219/TD | 01/10/2024 | 426 | M/S. NEW DINDA ENTERPRISE | 28.09 | 0 | 0 | 65
629 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. , SM/14838 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme within Purba Medinipur District under JJM Program under MMD PHE Dte. | 900/W/MMD | 27/03/2023 | 765 | S.S.GHORAI | 25.26 | 14.86 | 61.5 | 100
630 | PURBA MEDINIPUR | Tamluk Division | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS , SM/14673 | New | Material Requisition To Resource Division | 2398/TD | 16/01/2023 | 0 | Resource Division | 34.37 | 0 | 0 | 0
631 | PURBA MEDINIPUR | Midnapore Mechanical | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS , SM/14673 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 591/W/MMD | 20/03/2023 | 180 | S.S.GHORAI | 21.58 | 13.15 | 60.92 | 62
632 | PURBA MEDINIPUR | Tamluk Division | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS , SM/14673 | New | Material Requisition To Resource Division | 2964/TD | 12/09/2024 | 0 | Resource Division | 3.78 | 0 | 0 | 0
633 | PURBA MEDINIPUR | Midnapore Mechanical | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS , SM/14673 | New | Quotation Bill for New Service connection at T/W NO-I Of KASHI BHUINABAR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2004804684/QUOT/03 DT. 03-07-2024 Application NO- 2004804684 Application type-New connection Consumer Id- 204347452 | BP-2024-25-417 | 15/07/2024 | 0 | WBSEDCL | 0.51 | 0 | 0 | 0
634 | PURBA MEDINIPUR | Tamluk Division | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS , SM/14673 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at KASHIBHUIAN BAR PWSS at Contai-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 189/CSD | 27/01/2025 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 0
635 | PURBA MEDINIPUR | Central Drilling | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. , SM/13851 | New | Providing drilling crew and other allied works for construction of Tube Well ( 150mm X150mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Bakshi Chak W/S Scheme (T/W-I) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 1396/CDD | 19/09/2023 | 30 | DEV AND COMPANY | 13.38 | 0 | 0 | 0
636 | PURBA MEDINIPUR | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. , SM/13851 | New | Material Requisition To Resource Division | 2988/TD | 27/02/2023 | 0 | Resource Division | 4.55 | 0 | 0 | 0
637 | PURBA MEDINIPUR | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. , SM/13851 | New | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-II) [Bakshichak PWSS, Bamanpur PWSS, Kanchanpur PWSS & Madhyahingli PWSS] | 618/HSD | 21/12/2023 | 7 | SNEHASIS BERA | 0.83 | 0.83 | 100 | 100
638 | PURBA MEDINIPUR | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. , SM/13851 | New | Material Requisition To Resource Division | 80/TD | 05/01/2024 | 0 | Resource Division | 1.53 | 0 | 0 | 0
639 | PURBA MEDINIPUR | Midnapore Mechanical | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. , SM/13851 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAKSHI CHAK, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 571/W/MMD | 20/03/2023 | 895 | DEY ENTERPRISE | 5.99 | 0 | 0 | 95
640 | PURBA MEDINIPUR | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. , SM/13851 | New | Ground water based Bakshichak Water Supply Scheme by providing Sinking of Tube Well, Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-A) | 276/TD | 20/04/2023 | 806 | NARAYAN CHANDRA DAS | 84.8 | 52.91 | 62.4 | 39
641 | PURBA MEDINIPUR | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. , SM/13851 | New | Ground water based Bakshichak Water Supply Scheme by Sub-Soil investigation, Construction of OHR - 50 Cum, within Mahishadal Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | 1008/TD | 05/06/2023 | 900 | ZENITH CONSTRUCTION | 45.79 | 0 | 0 | 5
642 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III , SM/15841 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | 1856/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.22 | 100 | 100
643 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III , SM/15841 | Augmentation | Material Requisition To Resource Division | 3010/TD | 29/11/2023 | 0 | Resource Division | 0.61 | 0 | 0 | 0
644 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III , SM/15841 | Augmentation | Material Requisition To Resource Division | 2083/TD | 28/08/2023 | 0 | Resource Division | 13.95 | 0 | 0 | 0
645 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III , SM/15841 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 99 Nos) under JJM with allied work for KANPUR (Zone-III) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 2820/TD | 08/11/2023 | 510 | BASANTA KUMAR MAITY | 282.99 | 0 | 0 | 55
646 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III , SM/15841 | Augmentation | Drum Sheet walling, road restoration for distribution pipe line ( for FHTC) & Accommodate FHTC (172 Nos) under JJM with allied work for KANPUR (Zone-III) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | 3182/TD | 30/09/2024 | 40 | MAITY CONSTRUCTION | 91.37 | 0 | 0 | 0
647 | PURBA MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III , SM/15841 | Augmentation | Quotation Bill for New Service connection at T/W NO-II , zone-III Of KANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004927974/QUOT/03 DT. 04-10-2024 Application NO- 2004927974 Application type-New connection Consumer Id- 204417444 | BP-2024-25-779 | 05/11/2024 | 0 | WBSEDCL | 4.94 | 0 | 0 | 0
648 | PURBA MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III , SM/15841 | Augmentation | Quotation Bill for New Service connection at T/W NO-I, ZONE-III Of KANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004927967/QUOT/03 DT. 04-10-2024 Application NO- 2004927967 Application type-New connection Consumer Id- 204417441 | C112422744521 | 18/11/2024 | 0 | WBSEDCL | 4.99 | 0 | 0 | 0
649 | PURBA MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III , SM/15841 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 0 | 34
650 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 60 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-K) | 791/TD | 12/07/2022 | 15 | M/S BLUE BIRD | 10.57 | 7.28 | 68.89 | 80
651 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 200 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-L) | 792/TD | 12/07/2022 | 20 | AHINDRA BARIK | 44.27 | 0 | 0 | 0
652 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 85 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-J) | 790/TD | 12/07/2022 | 15 | GIRI ENTERPRISE | 20.05 | 16.08 | 80.21 | 70
653 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 69 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-N) | 793/TD | 12/07/2022 | 15 | GITA ENTERPRISE | 8.33 | 4.78 | 57.41 | 75
654 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Khejuri Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | 1519/TD | 07/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.96 | 4.92 | 100 | 100
655 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Supply & Delivery 125 mm dia Sluice Valve for Augmentation of Khejuri Zone-I & Zone-II Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-A) (Supply at Mukutshila Store) | 597 / CSD | 06/09/2022 | 15 | ABHIJIT BERA | 2.46 | 2.46 | 100 | 100
656 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 67 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-E) | 786/TD | 12/07/2022 | 15 | KAMAL KUMAR BERA | 9.5 | 9.49 | 99.88 | 100
657 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 1410 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-B) | 1078/TD | 23/08/2022 | 45 | SWADHIN KUMAR CHAKRABORTY | 241.76 | 67.26 | 81.93 | 95
658 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 80 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-M) | 1082/TD | 24/08/2022 | 15 | MUKHERJEE ENTERPRISE | 18.87 | 15.4 | 81.62 | 80
659 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 70 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-T) | 1083/TD | 24/08/2022 | 15 | GITA ENTERPRISE | 8.99 | 4.96 | 55.21 | 80
660 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 99 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-U) | 1084/TD | 24/08/2022 | 15 | SUBHRANGSHU SEKHAR GIRI | 7.86 | 2.73 | 34.66 | 70
661 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 112 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-G) | 788/TD | 12/07/2022 | 15 | LAKSHMI NARAYAN ENTERPRISE | 19.61 | 19.61 | 100 | 100
662 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 300 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-C) | 784/TD | 12/07/2022 | 25 | JASODA ENTERPRISE | 63.98 | 63.98 | 100 | 100
663 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 81 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-I) | 861/TD | 21/07/2022 | 15 | R K CONSTRUCTION | 11.52 | 6.6 | 57.26 | 75
664 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Supply & Delivery 150mm, 200mm & 250mm dia Sluice Valve for Augmentation of Khejuri Zone-I Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-B) (Supply at Mukutshila Store) | 1285/TD | 12/09/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.37 | 4.37 | 100 | 100
665 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Supply & Delivery 80 mm dia Sluice Valve for Augmentation of Khejuri Zone-I Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-C) (Supply at Mukutshila Store) | 1286/TD | 12/09/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.79 | 3.79 | 100 | 100
666 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Supply & Delivery 100 mm dia Sluice Valve for Augmentation of Khejuri Zone-I & Zone-II Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-B) (Supply at Mukutshila Store) | 1296/TD | 13/09/2022 | 15 | NANDY UDYOG | 3.62 | 3.62 | 100 | 100
667 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Material Requisition To Resource Division | 827/TD | 15/07/2022 | 0 | Resource Division | 210.14 | 0 | 0 | 0
668 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Material Requisition To Resource Division | 1258/TD | 12/09/2022 | 0 | Resource Division | 31.77 | 0 | 0 | 0
669 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 68 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-O) | 794/TD | 12/07/2022 | 15 | S.A. ENTERPRISE | 9.73 | 0 | 0 | 0
670 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 217 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-F) | 787/TD | 12/07/2022 | 1071 | PARIA ENTERPRISE | 42.11 | 34.27 | 81.39 | 100
671 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) under JJM Program under MMD PHE Dte. | 861/W/MMD | 27/03/2023 | 180 | DIAMOND ELECTRICAL WORKS | 13.43 | 0 | 0 | 95
672 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 220 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-D) | 785/TD | 12/07/2022 | 1171 | ABHIJIT BERA | 45.02 | 41.98 | 93.25 | 100
673 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 65 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-P) | 795/TD | 12/07/2022 | 998 | HYDROTECH ASSOCIATES | 9.05 | 4.57 | 50.45 | 98
674 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 65 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-R) | 797/TD | 12/07/2022 | 1034 | DEBABRATA DAS | 9.59 | 6.14 | 64.04 | 100
675 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 198 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-H) | 789/TD | 12/07/2022 | 1104 | SUBHENDU HAZRA | 39.49 | 29.43 | 74.52 | 75
676 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10647 | Augmentation | Retrofitting to accommodate of 66 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-Q) | 796/TD | 12/07/2022 | 969 | SUSANTA KUMAR KAR | 9.24 | 6.88 | 100 | 99
677 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) , SM/16458 | Augmentation | Laying of Distribution pipe line,Rising main pipe line, Pump House, Boundary Wall, with allied works of MANDARMANI & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Phase-III) | 842/TD | 31/05/2023 | 40 | DILIP KUMAR GHOSH | 94.7 | 0 | 0 | 0
678 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) , SM/16458 | Augmentation | Pipe crossing for laying Distribution pipe line to provide FHTC (9 nos.) of Mondarmoni W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (NP- 8 - 6, NP- 48 - 50, NP-50 - 52) | 1010/TD | 05/06/2023 | 20 | UNIQUE AGENCY | 7.52 | 7.52 | 100 | 100
679 | PURBA MEDINIPUR | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) , SM/16458 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) within Purba Medinipur District under JJM Program under MMD PHE Dte. | 901/W/MMD | 27/03/2023 | 1336 | S.S.GHORAI | 12.63 | 0 | 0 | 100
680 | PURBA MEDINIPUR | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDUHI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) , SM/16461 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDUHI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) within Purba Medinipur District under JJM Program under MMD PHE Dte. | 898/W/MMD | 27/03/2023 | 180 | A.S.ENTERPRISE | 12.62 | 0 | 0 | 0
681 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDUHI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) , SM/16461 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (176 nos) under JJM with allied work for Palduhi PWSS within Ramnagar -II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 599/TD | 17/05/2023 | 45 | BASANTA KUMAR MAITY | 61.68 | 27.05 | 43.86 | 45
682 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. , SM/16463 | Augmentation | Laying of Distribution pipe line for FHTC (920 nos), Rising main pipe line, Pump House, Boundary Wall, Sinking of 3rd Tube Well with allied works of Lakshya & its adjoining mouzas Water Supply Scheme within Mahisadal Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 254/TD | 19/04/2023 | 30 | HARIPADA PATTANAYAK | 64.14 | 0 | 0 | 0
683 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. , SM/16463 | Augmentation | Way Leave permission from South Eastern Railway for Lakshya PWSS for Application ID-SER-KGP-2023-WL-66 | BP-2023-24-821 | 22/01/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.52 | 0 | 0 | 0
684 | PURBA MEDINIPUR | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. , SM/16463 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | 903/W/MMD | 27/03/2023 | 180 | RITESH ENTERPRISE | 13.59 | 0 | 0 | 0
685 | PURBA MEDINIPUR | Tamluk Division | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (545 NOS) UNDER JJM SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE VII,BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA MEDINIPUR. (PHASE-III) , SM/16468 | Retrofitting | Balance work for retrofitting to accommodate FHTC (545 Nos) under JJM in Surface water Based Water Supply Scheme for Zone-VII Block - Kolaghat in the District of Purba Medinipur.(Phase-III) | 251/TD | 19/04/2023 | 25 | MRITYUNJOY PARIA | 32.97 | 30.37 | 100 | 100
686 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-V , SM/15847 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone-V) under Tamluk Division, PHE Dte. | 1934/TD | 28/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.3 | 100 | 100
687 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-V , SM/15847 | Augmentation | Material Requisition To Resource Division | 2069/TD | 28/08/2023 | 0 | Resource Division | 14.56 | 0 | 0 | 0
688 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-V , SM/15847 | Augmentation | Material Requisition To Resource Division | 3000/TD | 29/11/2023 | 0 | Resource Division | 1.98 | 0 | 0 | 0
689 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-V , SM/15847 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Zone-V PWSS at Ramnagar - I Block under Tamluk Division,PHE Dte. | 189/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
690 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-V , SM/15847 | Augmentation | Sankarpur W/S scheme TW no.-I, Z-V Ref.-204156069 Application ID-2004521724 | BP-2023-24-443 | 19/12/2023 | 0 | WBSEDCL | 3.08 | 0 | 0 | 0
691 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-V , SM/15847 | Augmentation | Sankarpur W/S scheme T/W-II, Z-V Application-no.-2004522973 Ref.-204157003 | BP-2023-24-444 | 19/12/2023 | 0 | WBSEDCL | 3 | 0 | 0 | 0
692 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-V , SM/15847 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-V in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1213/W/MMD | 25/04/2023 | 180 | SUBHASIS ROY | 21.6 | 19.98 | 92.49 | 90
693 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-V , SM/15847 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 321 Nos) under JJM with allied work for SANKARPUR (Zone-V) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 1729/TD | 31/07/2023 | 756 | ONKAR ENTERPRISE | 194.4 | 62.64 | 32.22 | 55
694 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-II , SM/15853 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | 1860./TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 3.1 | 100 | 100
695 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-II , SM/15853 | Augmentation | Material Requisition To Resource Division | 2071/TD | 28/08/2023 | 0 | Resource Division | 15.21 | 0 | 0 | 0
696 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-II , SM/15853 | Augmentation | Material Requisition To Resource Division | 3004/TD | 29/11/2023 | 0 | Resource Division | 0.07 | 0 | 0 | 0
697 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-II , SM/15853 | Augmentation | Quotation Bill for New Service connection at T/W NO-I, Zone-II Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004732398/QUOT/03/213 DT. 15-05-2024 Application NO- 2004732398 Application type-New connection Consumer Id- 204305458 | BP-2024-25-247 | 06/06/2024 | 0 | WBSEDCL | 6.88 | 0 | 0 | 0
698 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-II , SM/15853 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1242/W/MMD | 28/04/2023 | 764 | BHABANI PRASAD MANNA | 84.29 | 0 | 0 | 70
699 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-II , SM/15853 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (24 nos) under JJM with allied work for Bathuari (Zone-II) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 1760/TD | 01/08/2023 | 853 | ARABINDA GHOSH | 294.32 | 102.26 | 34.74 | 50
700 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. , SM/16288 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Western Zone) under Tamluk Division, PHE Dte. | .1652/TD | 20/01/2022 | 20 | HORIZEN | 3.2 | 3.15 | 100 | 100
701 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. , SM/16288 | Augmentation | Material Requisition To Resource Division | 2639/TD | 13/10/2023 | 0 | Resource Division | 4.82 | 0 | 0 | 0
702 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. , SM/16288 | Augmentation | Material Requisition To Resource Division | 2065/TD | 28/08/2023 | 0 | Resource Division | 29.47 | 0 | 0 | 0
703 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. , SM/16288 | Augmentation | Quotation for new service connection at T/W-IV of Digha western zone under MMD,PHE DTE, Block-Ramnagar-I, DIGHA CCC Application no-2004812623 CON ID-204351922 | BP-2024-25-457 | 23/07/2024 | 0 | WBSEDCL | 0.92 | 0 | 0 | 0
704 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. , SM/16288 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (782 nos) under JJM with allied work for Digha Augmentation (Western Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 1569/TD | 19/07/2023 | 713 | GUHA CONSTRUCTION | 355.55 | 143.04 | 40.23 | 16
705 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme , SM/16194 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. [PART-III] | 1855./TD | 21/11/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.23 | 100 | 100
706 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme , SM/16194 | Augmentation | Material Requisition To Resource Division | 2637/TD | 13/10/2023 | 0 | Resource Division | 8.79 | 0 | 0 | 0
707 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme , SM/16194 | Augmentation | Material Requisition To Resource Division | 2095/TD | 29/08/2023 | 0 | Resource Division | 156.45 | 0 | 0 | 0
708 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme , SM/16194 | Augmentation | Withdrawing and Relaying of different dia D.I pipe line at Contai Saline Area Zone-IV PART-III Water Supply Scheme due to Widening and Strengthening along existing alignment of Contai-Rasulpur Road under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 1907/TD | 07/06/2024 | 25 | TARUN KHATUA | 43.11 | 0 | 0 | 0
709 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme , SM/16194 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Contai - I and III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1205/W/MMD | 25/04/2023 | 859 | BHABANI PRASAD MANNA | 57.85 | 0 | 0 | 60
710 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme , SM/16194 | Augmentation | Laying distribution pipe line, & Accommodate FHTC (1427 nos) under JJM with allied work for Augmentation of Contai Saline Area Zone-IV PART-III PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1091/TD | 08/06/2023 | 840 | SUJATA CONSTRUCTION | 214.81 | 84.58 | 39.38 | 50
711 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme , SM/16194 | Augmentation | Repairing of Switch Room cum Chlorin Room at 2nd TW site for Augmentation of Contai Saline Area Zoner-IV Part-III Water Supply Scheme within Deshpran Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 3399/TD | 28/10/2024 | 30 | SUBRATA KUMAR BERA | 1.8 | 0 | 0 | 0
712 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme , SM/16194 | Augmentation | Repairing of OHR, Pump House no 1 and Head Works Boundary Wall under JJM with allied work of Contai Saline Area Zone-IV Part-III PWSS within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 3058/TD | 19/09/2024 | 40 | SOUMEN KUMAR GHOSH | 29.17 | 0 | 0 | 100
713 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bagmari (Egra-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16857 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
714 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme , SM/16711 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bagmari Water Supply Scheme under Tamluk Division, PHE Dte. | 1741/TD | 03/02/2022 | 20 | HORIZEN | 3.67 | 3.14 | 85.45 | 0
715 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme , SM/16711 | Augmentation | Material Requisition To Resource Division | 3008/TD | 29/11/2023 | 0 | Resource Division | 5.72 | 0 | 0 | 0
716 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme , SM/16711 | Augmentation | Material Requisition To Resource Division | 2635/TD | 13/10/2023 | 0 | Resource Division | 5.72 | 0 | 0 | 0
717 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme , SM/16711 | Augmentation | Payment of WBSEDCL for Quotation of Shifting of 11 KV line of Bagmari Water Supply Scheme within Egra-II Block | BP-2023-24-664 | 15/12/2023 | 0 | WBSEDCL | 4.64 | 0 | 0 | 0
718 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Bagmari Water Supply Scheme , SM/16711 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Bagmari Water Supply Scheme, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 632/W/MMD | 20/03/2023 | 180 | JOYSHREE CONCERN | 13.56 | 0.64 | 4.78 | 90
719 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme , SM/16711 | Augmentation | Instalation of display Board at different work site of Kanakpur Retrofitting PWSS in Potashpur - I Block, Argoal, Bagmari, Pratapdighi Retrofitting PWSS in Potashpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2336/CSD | 29/12/2023 | 15 | THE GODFATHER TRADING COMPANY | 0.83 | 0.83 | 100 | 100
720 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme , SM/16711 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 100cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bagmari Water Supply Scheme within Egra-I Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 459/TD | 04/05/2023 | 881 | AJIT KUMAR SOM | 241.82 | 161.5 | 66.78 | 70
721 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme , SM/16711 | Augmentation | Renovation & Repairing of existing pump house H/W site and 2nd TW Site of Bagmari Water Supply Scheme within Egra-I Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 3616/TD | 27/11/2024 | 240 | SOM CONSTRUCTION | 11.36 | 0 | 0 | 0
722 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagmari Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. , SM/16712 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site(Boosting T/W) of Bagmari Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1094/TD | 25/08/2022 | 40 | AQUATECH ENGINEERS | 70.49 | 15.62 | 100 | 100
723 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagmari Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. , SM/16712 | Augmentation | Electric Quotation for BAGMARI Water Supply Scheme T/W-III, (Ref. ID-204067663) | W/23-24/223 | 01/09/2023 | 0 | WBSEDCL | 3.34 | 0 | 0 | 0
724 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagmari Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. , SM/16712 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bagmari Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1221/W/MMD | 25/04/2023 | 180 | RISHAV ENTERPRISE | 11.94 | 11.49 | 95.14 | 100
725 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagmari Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. , SM/16712 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site( Mouza- Bagmari ,J.L. No-116, Plot No- 189), for Bagmari Water Supply Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur | 138/TD | 10/04/2023 | 60 | GRAND CONSTRUCTION | 3.99 | 3.58 | 100 | 100
726 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagmari Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. , SM/16712 | Augmentation | Laying of Distribution pipe line, Rising main pipe line with allied works of Bagmari & its adjoining mouzas Water Supply Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(PHASE-III) | 1825/TD | 07/08/2023 | 576 | DAS ENTERPRISE | 63.16 | 35.49 | 56.18 | 100
727 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Alinan, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16876 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
728 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Basudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16877 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
729 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Basudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16877 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
730 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Kasbagola PWSS in the District of Purba Medinipur under JJM programme. , SM/16671 | Augmentation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0.18 | 100 | 100
731 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Kasbagola PWSS in the District of Purba Medinipur under JJM programme. , SM/16671 | Augmentation | Rejuvenation of Electro-Mechanical components of Kasbagola PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 756/W/MMD | 23/03/2023 | 720 | UNITED TRADERS | 11.34 | 6.7 | 51.48 | 100
732 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Barchunfali PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16894 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
733 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Barchunfali PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16894 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
734 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chandibeniya, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16878 | IOT | Supply and installation of Sign Board for depicting the scheme details of different on going Design development works for the purpose of Geotagging at different PWSS under Moyna block under MMD, P.H.E. Dte.in the Dist. of Purba Medinipur. | 625/HESD | 08/07/2024 | 7 | S.S.GHORAI | 0.9 | 0 | 0 | 0
735 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chandibeniya, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16878 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
736 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Argoal PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16872 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
737 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Argoal PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16872 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
738 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Muradpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17753 | Solarisation | Solarization of grid connected pumping installation at Muradpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 998/W/MMD | 29/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 4.88 | 78.03 | 80
739 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bathuari PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17888 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
740 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bathuari PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17888 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
741 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Aladarput PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17918 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
742 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Aladarput PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17918 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
743 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Madhabpur (Balighai) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17767 | Solarisation | Solarization of grid connected pumping installation at Madhabpur (Balighai) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1009/W/MMD | 29/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
744 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Madhabpur (Balighai) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17767 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0.18 | 100 | 50
745 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Jagatpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17805 | Solarisation | Solarization of grid connected pumping installation at Jagatpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1030/W/MMD | 29/03/2023 | 180 | KAMAKSHYA ENTERPRISE | 6.26 | 0 | 0 | 0
746 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Mandarmani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17808 | Solarisation | Solarization of grid connected pumping installation at Mandarmani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 1037/W/MMD | 29/03/2023 | 180 | S.S.GHORAI | 6.25 | 4.85 | 77.48 | 60
747 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Mandarmani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17808 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0.18 | 94.81 | 100
748 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kanaidighi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17736 | Solarisation | Solarization of grid connected pumping installation at Kanaidighi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1005/W/MMD | 29/03/2023 | 180 | AMITAVA CHAKRABORTY | 6.26 | 3.91 | 62.42 | 25
749 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Gogras keshab bar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17913 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
750 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dakhsin Mechogram PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17367 | Solarisation | Solarization of grid connected pumping installation at Dakhsin Mechogram PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 738/W/MMD | 23/03/2023 | 180 | SUBHASIS ROY | 6.26 | 0 | 0 | 0
751 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Ramnagar Zone I & II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17828 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
752 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Ramnagar Zone I & II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17828 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
753 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dariapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17340 | Solarisation | Solarization of grid connected pumping installation at Dariapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 723/W/MMD | 23/03/2023 | 180 | AMITAVA CHAKRABORTY | 6.26 | 4.85 | 77.48 | 85
754 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dakshin Dalhara PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17314 | Solarisation | Solarization of grid connected pumping installation at Dakshin Dalhara PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 734/W/MMD | 23/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
755 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Sankarpur (Ramnagar) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17922 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
756 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Sankarpur (Ramnagar) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17922 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
757 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Guria PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17294 | Solarisation | Solarization of grid connected pumping installation at Guria PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 733/W/MMD | 23/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 4.85 | 77.48 | 65
758 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Guria PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17294 | Solarisation | Quotation bill for application fees of NET METERING for solar power plant at Guria w/s scheme,Block-Nandakumar in the Dist. of Purba Medinipur under MMD PHE Dte. Name of C.C.C.-Nandakumar Application No.-2004846736 Consumer ID-202863806 Issuance Date-01/08/2024 | C092443146203 | 27/09/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
759 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Shankarpur (Contai) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17856 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
760 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Shankarpur (Contai) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17856 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
761 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bamunia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17324 | Solarisation | Solarization of grid connected pumping installation at Bamunia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 718/W/MMD | 23/03/2023 | 180 | S.S.GHORAI | 6.25 | 0 | 0 | 0
762 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Lakshya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17837 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
763 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Lakshya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17837 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
764 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Junbani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17838 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
765 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Junbani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17838 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
766 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Suadighi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17867 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at MAHAMMADPUR and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 649/HESD | 08/07/2024 | 15 | SOUMEN ELECTRIC | 1.94 | 0 | 0 | 100
767 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Suadighi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17867 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
768 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Tajpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17415 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
769 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Tajpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17415 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
770 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Argoal PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17332 | Solarisation | Solarization of grid connected pumping installation at Argoal PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 739/W/MMD | 23/03/2023 | 180 | PRANAB KUMAR DAS | 6.26 | 4.85 | 77.48 | 80
771 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Barsundra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17296 | Solarisation | Quotation Bill for new service connection at TW-III of Barsundra w/s scheme,under MMD,PHE,Dte.,Purba Medinipur Block-Haldia, C.C.C.-Brajalalchak Application no.-2004651015 Application Type-New connection Quotation Date-22/03/2024 Quotation Due Date-24/03/2025 Contract Demand-10209 W | BP-2024-25-17 | 08/04/2024 | 0 | WBSEDCL | 4.22 | 0 | 0 | 0
772 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Barsundra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17296 | Solarisation | Solarization of grid connected pumping installation at Barsundra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 730/W/MMD | 23/03/2023 | 681 | MEGA SOLAR ENERGY | 6.26 | 1.23 | 19.72 | 60
773 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kulbari PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17815 | Solarisation | Solarization of grid connected pumping installation at Kulbari PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 997/W/MMD | 29/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 4.88 | 78.03 | 60
774 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kulbari PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17815 | Solarisation | Processing fees for solar metering application for KULBARI w/s scheme in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004649808, C ID 200121558) | BP-2024-25-51 | 18/04/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
775 | PURBA MEDINIPUR | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS , SM/12512 | New | Material Requisition To Resource Division | 2436/TD | 16/01/2023 | 0 | Resource Division | 23.09 | 0 | 0 | 0
776 | PURBA MEDINIPUR | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS , SM/12512 | New | Material Requisition To Resource Division | 1571/TD | 23/04/2024 | 0 | Resource Division | 15.86 | 0 | 0 | 0
777 | PURBA MEDINIPUR | Midnapore Mechanical | SRIKANTHA AND ADJOINING MOUJAS PWSS , SM/12512 | New | Quotation for new service connection at Srikanta w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004707397, Ref ID 204292174) | BP-2024-25-192 | 24/05/2024 | 0 | WBSEDCL | 8.38 | 0 | 0 | 0
778 | PURBA MEDINIPUR | Midnapore Mechanical | SRIKANTHA AND ADJOINING MOUJAS PWSS , SM/12512 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SRIKANTHA and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 471/W/MMD | 20/03/2023 | 955 | SOUMEN ELECTRIC | 25.24 | 19.29 | 76.41 | 60
779 | PURBA MEDINIPUR | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS , SM/12512 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at SRIKANTHA PWSS at MOYNA Block under Tamluk Division, PHE Dte. Purba Medinipur District. | 07/RWS/TSD | 04/04/2025 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
780 | PURBA MEDINIPUR | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS , SM/12512 | New | Installation of display Board at 4 nos {1. SRIKHANTA PWSS,( PUMP HOUSE 1 & 2) 2. KIYARANA PWSS ( PUMP HOUSE -1 &2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 62/RWS/TSD | 06/05/2025 | 7 | SUDIP MANNA | 0.69 | 0 | 0 | 100
781 | PURBA MEDINIPUR | Tamluk Division | DEULI & IT'S ADJOINING MOUJAS PWSS , SM/13744 | New | Material Requisition To Resource Division | 2689/TD | 06/02/2023 | 0 | Resource Division | 43.3 | 0 | 0 | 0
782 | PURBA MEDINIPUR | Tamluk Division | DEULI & IT'S ADJOINING MOUJAS PWSS , SM/13744 | New | Material Requisition To Resource Division | 84/TD | 05/01/2024 | 0 | Resource Division | 9.77 | 0 | 0 | 0
783 | PURBA MEDINIPUR | Midnapore Mechanical | DEULI & IT'S ADJOINING MOUJAS PWSS , SM/13744 | New | Quotation Bill for New Service connection at T/W NO-I Of DEULI W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, PICHABANI C.C.C. Ref. Memo No- 2004641295/QUOT/03 DT. 12-03-2024 Application NO- 2004641295 Application type-New connection Consumer Id- 204244736 | BP-2023-24-863 | 16/03/2024 | 0 | WBSEDCL | 3.7 | 0 | 0 | 0
784 | PURBA MEDINIPUR | Midnapore Mechanical | DEULI & IT'S ADJOINING MOUJAS PWSS , SM/13744 | New | ADDITIONAL Quotation Bill for DEULI W/S SCHEME T/W NO- I , RAMNAGRA -II BLOCK . Ref. MEMO No- PBN/NS/36 Dt. 25.04.2024 Application NO- 100000106413 Dt. 25.04.2024 Reference Id- 860299003 REF CONSUMER ID: 204244736 WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. | BP-2024-25-147 | 09/05/2024 | 0 | WBSEDCL | 0.84 | 0 | 0 | 0
785 | PURBA MEDINIPUR | Midnapore Mechanical | DEULI & IT'S ADJOINING MOUJAS PWSS , SM/13744 | New | Quotation Bill for New Service connection at T/W NO-II Of DEULI W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670691/QUOT/03 DT. 05-04-2024 Application NO- 2004670691 Application type-New connection Consumer Id- 204266384 | BP-2024-25-44 | 18/04/2024 | 0 | WBSEDCL | 3.7 | 0 | 0 | 0
786 | PURBA MEDINIPUR | Tamluk Division | DEULI & IT'S ADJOINING MOUJAS PWSS , SM/13744 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3103 Nos) For 2 nos Pipe Water Supply Scheme including two years Operation & Maintainance for BHUINAJIBAR and DEULI within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 1068/TD | 08/06/2023 | 934 | TAPAS SANTRA | 1110.29 | 405.43 | 73.51 | 85
787 | PURBA MEDINIPUR | Midnapore Mechanical | DEULI & IT'S ADJOINING MOUJAS PWSS , SM/13744 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DEULI and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 564/W/MMD | 20/03/2023 | 1487 | DEY ENTERPRISE | 22.8 | 10.63 | 47.45 | 85
788 | PURBA MEDINIPUR | Tamluk Division | UTTAR CHANDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12160 | New | Material Requisition To Resource Division | 2427/TD | 16/01/2023 | 0 | Resource Division | 41.87 | 0 | 0 | 0
789 | PURBA MEDINIPUR | Tamluk Division | UTTAR CHANDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12160 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Uttar Chandra Chak PWSS at Moyna Block under Tamluk Division,PHE Dte. | 194/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
790 | PURBA MEDINIPUR | Tamluk Division | UTTAR CHANDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12160 | New | Material Requisition To Resource Division | 1573/TD | 23/04/2024 | 0 | Resource Division | 12.71 | 0 | 0 | 0
791 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR CHANDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12160 | New | Quotation for new service connection at Uttar Chandrachak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004707437, Ref ID 204292173) | BP-2024-25-190 | 24/05/2024 | 0 | WBSEDCL | 4.89 | 0 | 0 | 0
792 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR CHANDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12160 | New | Quotation for new service connection at Uttar chandrachak w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App No 2004756265, Ref ID 204319510) | BP-2024-25-485 | 30/07/2024 | 0 | WBSEDCL | 4.37 | 0 | 0 | 0
793 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR CHANDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12160 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR CHANDRA CHAK and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2342/W/MMD | 29/12/2022 | 823 | SOUMEN ELECTRIC | 23.68 | 18.26 | 78.84 | 60
794 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme , SM/07096 | Retrofitting | Functional Household Tap Connection to the 190 nos. Household of Paschimbetya W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-A [(Balagerya(77 ) ,Aluan(78) ,Part)] | 2720/TD | 21/01/2021 | 20 | SUBRATA KUMAR BERA | 9 | 1.52 | 100 | 100
795 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme , SM/07096 | Retrofitting | Functional Household Tap Connection to the 172 nos. Household of Paschimbetya W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-C [(Bara Rasulpur(635)] | 2718/TD | 21/01/2021 | 20 | SUKOMAL BERA | 8.15 | 1.3 | 100 | 100
796 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme , SM/07096 | Retrofitting | Functional Household Tap Connection to the 355 nos. Household of Paschimbetya W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-B [(Aluan(78 ) part,Paschimbatya(79)] | 2719/TD | 21/01/2021 | 25 | MRINAL KANTI PRADHAN | 16.73 | 0.64 | 100 | 100
797 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme , SM/07096 | Retrofitting | Functional Household Tap Connection to the 190 Nos. Household of Paschimbetya W/S Scheme within Contai - III Block Tamluk Division, PHE Dte. (PART-A) | 843/W | 08/03/2021 | 0 | SUBRATA KUMAR BERA | 7.26 | 0 | 0 | 0
798 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme , SM/07096 | Retrofitting | Retrofitting to accomodate FHTC 355 Nos. connection under JJM Paschim Betya W/S Scheme within Contai - III Dev. Block under Tamluk Division, PHE Dte. | 329/W | 08/10/2021 | 0 | MRINAL KANTI PRADHAN | 2.08 | 0 | 0 | 0
799 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme , SM/07096 | Retrofitting | Retrofitting to accomodate FHTC 355 Nos. connection under JJM Paschim Betya W/S Scheme within Contai - III Dev. Block under Tamluk Division, PHE Dte. | 967/W | 22/03/2021 | 0 | MRINAL KANTI PRADHAN | 14.01 | 0 | 0 | 0
800 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme , SM/07096 | Retrofitting | Retrofitting to accomodate FHTC 172 Nos. connection under JJM Paschim Betya W/S Scheme within Contai - III Dev. Block under Tamluk Division, PHE Dte. | 823/W | 26/02/2021 | 0 | SUKOMAL BERA | 6.61 | 0 | 0 | 0
801 | PURBA MEDINIPUR | Tamluk Division | BATIPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16257 | New | Material Requisition To Resource Division | 2717/TD | 06/02/2023 | 0 | Resource Division | 42.25 | 0 | 0 | 0
802 | PURBA MEDINIPUR | Midnapore Mechanical | BATIPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16257 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BATIPUR AND ITS ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 947/W/MMD | 28/03/2023 | 180 | A.S.ENTERPRISE | 21.57 | 0 | 0 | 0
803 | PURBA MEDINIPUR | Tamluk Division | BATIPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16257 | New | Material Requisition To Resource Division | 2950/TD | 12/09/2024 | 0 | Resource Division | 5.9 | 0 | 0 | 0
804 | PURBA MEDINIPUR | Tamluk Division | BATIPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16257 | New | Sinking Tube well ,Construction of Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (958 nos), Including 2 years of Operation maintance under JJM with allied work of BATIPUR PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 1092/TD | 08/06/2023 | 840 | SUJATA CONSTRUCTION | 368.76 | 47.72 | 12.94 | 30
805 | PURBA MEDINIPUR | Tamluk Division | ERENDA AND ADJOINING MOUJAS PWSS , SM/12298 | New | Material Requisition To Resource Division | 2713/TD | 06/02/2023 | 0 | Resource Division | 29.89 | 0 | 0 | 0
806 | PURBA MEDINIPUR | Midnapore Mechanical | ERENDA AND ADJOINING MOUJAS PWSS , SM/12298 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ERENDA and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2367/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 10.96 | 46.25 | 45
807 | PURBA MEDINIPUR | Midnapore Mechanical | ERENDA AND ADJOINING MOUJAS PWSS , SM/12298 | New | Quotation Bill for New Service connection at T/W NO-II Of ERENDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004792956/QUOT/03/379 DT. 02-07-2024 Application NO- 2004792956 Application type-New connection Consumer Id- 204345868 | BP-2024-25-494 | 29/07/2024 | 0 | WBSEDCL | 3.96 | 0 | 0 | 0
808 | PURBA MEDINIPUR | Midnapore Mechanical | ERENDA AND ADJOINING MOUJAS PWSS , SM/12298 | New | Erenda W/S scheme PH-I Application no.-2004523042 ref.-204156895 | BP-2023-24-482 | 27/12/2023 | 0 | WBSEDCL | 4.3 | 0 | 0 | 0
809 | PURBA MEDINIPUR | Tamluk Division | ERENDA AND ADJOINING MOUJAS PWSS , SM/12298 | New | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1648 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Erenda PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | 1592/TD | 21/07/2023 | 856 | MUKHERJEE CONSTRUCTION | 504.12 | 221.63 | 43.96 | 62
810 | PURBA MEDINIPUR | Tamluk Division | TAJPUR AND ADJOINING MOUJAS PWSS , SM/12284 | New | Material Requisition To Resource Division | 2715/TD | 06/02/2023 | 0 | Resource Division | 32.5 | 0 | 0 | 0
811 | PURBA MEDINIPUR | Tamluk Division | TAJPUR AND ADJOINING MOUJAS PWSS , SM/12284 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 400 cum RCC OHR at Tajpur PWSS at Egra-II Block under Tamluk Division, PHE Dte. | 2072/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
812 | PURBA MEDINIPUR | Midnapore Mechanical | TAJPUR AND ADJOINING MOUJAS PWSS , SM/12284 | New | Quotation Bill for New Service connection at T/W NO-I Of TAJPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, BALIGHAI C.C.C. Ref. Memo No- 2004626691/QUOT/03/1613 DT. 01/03/2024 Application NO- 2004626691 Application type-New connection Consumer Id- 204233925 | BP-2023-24-857 | 16/03/2024 | 0 | WBSEDCL | 4.05 | 0 | 0 | 0
813 | PURBA MEDINIPUR | Midnapore Mechanical | TAJPUR AND ADJOINING MOUJAS PWSS , SM/12284 | New | Quotation Bill for New Service connection at T/W NO-II Of TAJPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, BALIGHAI C.C.C. Ref. Memo No- 2004626737/QUOT/03/1611 DT. 01-03-2024 Application NO- 2004626737 Application type-New connection Consumer Id- 204233924 | BP-2023-24-856 | 16/03/2024 | 0 | WBSEDCL | 4.66 | 0 | 0 | 0
814 | PURBA MEDINIPUR | Tamluk Division | TAJPUR AND ADJOINING MOUJAS PWSS , SM/12284 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2785 nos) under JJM with allied work for Tajpur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 1415/TD | 12/07/2023 | 873 | FIROZ KHAN | 607.63 | 296.14 | 48.74 | 70
815 | PURBA MEDINIPUR | Tamluk Division | TAJPUR AND ADJOINING MOUJAS PWSS , SM/12284 | New | Leftout pipeline & Drum Sheet Walling to accommodate FHTC under JJM of Tajpur Water Supply Scheme within Egra II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1167/TD | 22/04/2025 | 40 | R CONSTRUCTION | 103.69 | 0 | 0 | 0
816 | PURBA MEDINIPUR | Midnapore Mechanical | TAJPUR AND ADJOINING MOUJAS PWSS , SM/12284 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TAJPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 470/W/MMD | 20/03/2023 | 744 | SOUMEN ELECTRIC | 25.24 | 23.66 | 80.69 | 100
817 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS , SM/11947 | New | Material Requisition To Resource Division | 3007/TD | 27/02/2023 | 0 | Resource Division | 18.84 | 0 | 0 | 0
818 | PURBA MEDINIPUR | Midnapore Mechanical | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS , SM/11947 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 621/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 22.81 | 21.15 | 92.73 | 35
819 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS , SM/11947 | New | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(1435 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of capacity 200 cum and staging height20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall ,Instalation of display Board and 2 yeras Operation & Maintenance under JJM with allied work for Harashankar Khamarchak PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 907/TD | 01/06/2023 | 610 | HARIPADA PATTANAYAK | 371.31 | 201.64 | 54.31 | 50
820 | PURBA MEDINIPUR | Midnapore Mechanical | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS , SM/11947 | New | Harasankarpur Khamarchak W/S scheme T/W-II Application No.-2004586186, Ref ID.-204209423 Date of quotation .-06/02/2024 New connection. | BP-2023-24-683 | 15/02/2024 | 0 | WBSEDCL | 4.35 | 0 | 0 | 0
821 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS , SM/11947 | New | payment for Wayleave plan & survey charges SER-KGP-2024-WL-95 | BP-2024-25-188 | 14/06/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0 | 0
822 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS , SM/11947 | New | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-95) | BP-2024-25-298 | 30/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.08 | 0 | 0 | 0
823 | PURBA MEDINIPUR | Midnapore Mechanical | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS , SM/11947 | New | Quotation Bill for Harasankar Khamarchak H/W Site Block=Sahid Matangini Application No=2004626478 Reference ID=204233282 | BP-2023-24-803 | 11/03/2024 | 0 | WBSEDCL | 4.36 | 0 | 0 | 0
824 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS , SM/11947 | New | M.S. Structure for canel crossing for laying 90 mm dia pipe of Harasankar Khamarchak PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Nodal Point 242-243, 314-315,356-343 & 88A-128 ) Canal Length- = 14.00 mtr. Number of crossing -4 | 3290/TD | 05/10/2024 | 30 | BAGLAMUKHI SECURITY SERVICE | 9.39 | 0 | 0 | 100
825 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS , SM/11947 | New | Canal crossing, land development, dismentling concrete and restoration work,dram sheet walling of Harasankar Khamarchak PWSS of Tamluk Block under Tamluk Sub- Division of Tamluk division PHE Dte. | 3140/TD | 26/09/2024 | 30 | BAGLAMUKHI SECURITY SERVICE | 17.81 | 0 | 0 | 100
826 | PURBA MEDINIPUR | Tamluk Division | KIARANA AND ADJOINING MOUJAS PWSS , SM/12628 | New | Material Requisition To Resource Division | 2433/TD | 16/01/2023 | 0 | Resource Division | 36.03 | 0 | 0 | 0
827 | PURBA MEDINIPUR | Tamluk Division | KIARANA AND ADJOINING MOUJAS PWSS , SM/12628 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Kiarana PWSS at Moyna Block under Tamluk Division,PHE Dte. | 192/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
828 | PURBA MEDINIPUR | Tamluk Division | KIARANA AND ADJOINING MOUJAS PWSS , SM/12628 | New | Material Requisition To Resource Division | 1567/TD | 23/04/2024 | 0 | Resource Division | 8.77 | 0 | 0 | 0
829 | PURBA MEDINIPUR | Midnapore Mechanical | KIARANA AND ADJOINING MOUJAS PWSS , SM/12628 | New | Quotation for new service connection at Kiarana w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App ID 2004686357, Con ID 204277586) | BP-2024-25-110 | 06/05/2024 | 0 | WBSEDCL | 13.89 | 0 | 0 | 0
830 | PURBA MEDINIPUR | Midnapore Mechanical | KIARANA AND ADJOINING MOUJAS PWSS , SM/12628 | New | Quotation for Kiarana w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.(App No.- 2004620100, Ref ID 204229479) | BP-2023-24-860 | 16/03/2024 | 0 | WBSEDCL | 4.37 | 0 | 0 | 0
831 | PURBA MEDINIPUR | Midnapore Mechanical | KIARANA AND ADJOINING MOUJAS PWSS , SM/12628 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KIARANA and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2426/W/MMD | 31/12/2022 | 670 | DEY ENTERPRISE | 23.7 | 19.45 | 82.08 | 100
832 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII , SM/07116 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -XII Block Panskura-II in the District of Purba Medinipur. | 2769/TD | 28/01/2021 | 60 | UMWELT ENGINEER PVT. LTD. | 96.7 | 0 | 0 | 100
833 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII , SM/07116 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII within Panskura - II Block under Tamluk Division, PHE Dte. | 133/W | 15/07/2021 | 0 | UMWELT ENGINEER PVT. LTD. | 4.15 | 0 | 0 | 0
834 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII , SM/07116 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII within Panskura - II Block under Tamluk Division, PHE Dte. | BP-2021-22-51 | 29/07/2021 | 0 | UMWELT ENGINEER PVT. LTD. | 0.73 | 0 | 0 | 0
835 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII , SM/07116 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII within Panskura - II Block under Tamluk Division, PHE Dte. | 943/W | 19/03/2021 | 0 | UMWELT ENGINEER PVT. LTD. | 91.85 | 0 | 0 | 0
836 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur , SM/07660 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block -Nandigram-I & Nandigram-II in the District of Purba Medinipur. | 2974/TD | 25/02/2021 | 70 | SANKHA ENTERPRISE | 164.85 | 0 | 0 | 100
837 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur , SM/07660 | Retrofitting | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-66 | 18/08/2021 | 0 | SANKHA ENTERPRISE | 70.63 | 0 | 0 | 0
838 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur , SM/07660 | Retrofitting | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-298 | 10/03/2022 | 0 | SANKHA ENTERPRISE | 14.19 | 0 | 0 | 0
839 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur , SM/07660 | Retrofitting | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-297 | 10/03/2022 | 0 | SANKHA ENTERPRISE | 80 | 0 | 0 | 0
840 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme , SM/06891 | Retrofitting | Retrofitting to accomodate FHTC of Village-Gogras Keshab bar,J.L. No-328 and Village-Gogras Kottaluk,J.L. No-329 under JJM in Gogras Keshab Bar PWSS Block - Panskura - I in the District of Purba Medinipur. | 2460/TD | 18/12/2020 | 30 | TARUN KOLEY | 37.07 | 0 | 0 | 100
841 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme , SM/06891 | Retrofitting | Retrofitting to accomodate FHTC of Village-Beraberia,J.L. No-330 under JJM in Gogras Keshab Bar PWSS Block - Panskura - I in the District of Purba Medinipur. | 2461/TD | 18/12/2020 | 20 | TARUN KOLEY | 17.22 | 0 | 0 | 100
842 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme , SM/06891 | Retrofitting | Retrofitting to accomodate FHTC of Village-Purushottampur,J.L. No-331 under JJM in Gogras Keshab Bar PWSS Block - Panskura - I in the District of Purba Medinipur. | 2462/TD | 18/12/2020 | 25 | TARUN KOLEY | 26.29 | 0 | 0 | 100
843 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme , SM/06891 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gogras Keshab Bar W/S Scheme within village Gogas Keshab Bar and Gogras Kottaluk Mouza under Tamluk Division, PHE Dte. | 700/W | 02/02/2021 | 0 | TARUN KOLEY | 36.85 | 0 | 0 | 0
844 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme , SM/06891 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gogras Keshab Bar W/S Scheme within village Purushottampur Mouza under Tamluk Division, PHE Dte. | 702/W | 02/02/2021 | 0 | TARUN KOLEY | 25.18 | 0 | 0 | 0
845 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme , SM/06891 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gogras Keshab Bar W/S Scheme within village Beraberia Mouza under Tamluk Division, PHE Dte. | 701/W | 02/02/2021 | 0 | TARUN KOLEY | 17.09 | 0 | 0 | 0
846 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme , SM/06891 | Retrofitting | Survey and data collection through mobile application regarding availability of drinking water, Sanitation facility, Rain water harvesting, greywater management and others parameters in High School, upper Primary School, Primary School, Sisu Siksha Kendra of 25 blocks areas under Tamluk Division PHE Dte within Purba Medinipur District. | 1618/TD | 20/10/2022 | 20 | SUDIP MANNA | 3.67 | 3.52 | 100 | 100
847 | PURBA MEDINIPUR | Tamluk Division | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. , SM/06651 | New | Different work under Tamluk Division, PHE Dte. | 05 | 16/04/2020 | 0 | DIFFERENT CONTRACTOR OF TAMLUK DIVISION, PHE DTE. | 9.82 | 0 | 0 | 0
848 | PURBA MEDINIPUR | Tamluk Division | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. , SM/06651 | New | Different work under Tamluk Division, PHE Dte. | 06 | 16/04/2020 | 0 | DIFFERENT CONTRACTOR OF TAMLUK DIVISION, PHE DTE. | 8.25 | 0 | 0 | 0
849 | PURBA MEDINIPUR | Tamluk Division | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. , SM/06651 | New | Annual Maintenance of Computer and Peripherals for different laboratories in Purba Medinipur District under Tamluk Division, PHE Dte. (Period from 01/11/20 to 28/02/2021) | 08/W | 05/05/2021 | 0 | MISHRA ENTERPRISE | 0.78 | 0 | 0 | 0
850 | PURBA MEDINIPUR | Tamluk Division | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. , SM/06651 | New | Contigency Bill of NGO managed laboratory for the period from October, 2020 to March, 2021. under Tamluk Division, PHE Dte. | 161/W | 30/07/2021 | 0 | TAMRALIPTA GUCHHA SAMITY AND OTHERS | 2.45 | 0 | 0 | 0
851 | PURBA MEDINIPUR | Tamluk Division | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. , SM/06651 | New | Instrument / Equipment for Digha Sub-Divisional Water Testing Laboratory under Digha Sub-Division of Tamluk Division, PHE Dte. | 1115/W | 30/03/2021 | 0 | LABARD INSTRUCHEM PVT. LTD. | 8.06 | 0 | 0 | 0
852 | PURBA MEDINIPUR | Tamluk Division | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. , SM/06651 | New | THIS BILL HAS BEEN RAISED FOR SURRENDER OF UNSPENT FUND TO THE SINGLE NODAL ACCOUNT AS PER CLAUSE 2(III) OF D.O. NO. F.1(13)PFMS/FCD/2020, DTD. 12TH APRIL, 2021 BY SECRETARY, EXPENDITURE, GOVT. OF INDIA, MINISTRY OF FINANCE, DEPARTMENT OF EXPENDITURE AND CLAUSE 13 OF OFFICE MEMORANDUM. NO. F.I. (13) PFMS FCD / 2020 DTD. 23/03/2021 BY THE DIRECTOR (FCD), GOVT. OF INDIA, MINISTRY OF FINANCE, DEPARTMENT OF EXPENDITURE, PFMS DIVISION, AND VIDE MEMO NO. 2724/PHE-13011/7/2021-BUDGET CELL-DEPT. OF PHE Dte. | 452/W | 22/12/2021 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW ACCOUNT | 7.13 | 0 | 0 | 0
853 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. , SM/07477 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Tamalda PWSS Block -Egra-I in the District of Purba Medinipur. | 2866/TD | 10/02/2021 | 25 | AJIT KUMAR SOM | 44.61 | 0 | 0 | 100
854 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. , SM/07477 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Tamalda Piped Water Supply Scheme |  | 15/03/2021 | 0 | AJIT KUMAR SOM | 29.34 | 0 | 0 | 0
855 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. , SM/07477 | Retrofitting | Retrofitting to accomodate FHTC under JJM Tamalda W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-149 | 09/11/2021 | 0 | AJIT KUMAR SOM | 8.58 | 0 | 0 | 0
856 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. , SM/07477 | Retrofitting | Retrofitting to accomodate FHTC under JJM Tamalda W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. | 1089/W | 30/03/2021 | 0 | AJIT KUMAR SOM | 29.34 | 0 | 0 | 0
857 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. , SM/07477 | Retrofitting | Laying distribution system of Tamalda & its adjoining moujas Water Supply Scheme to support the ongoing FHTC Connection within Egra-I Dev. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | 1930/TD | 28/02/2022 | 15 | SOM CONSTRUCTION | 4.84 | 4.84 | 100 | 100
858 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. , SM/07477 | Retrofitting | Preparation and submission of Revised Detailed Project Report for Retrofitting to accommodate FHTC under JJM in TAMALDA piped water supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur District. | 145/DSD | 14/05/2025 | 7 | ASTER CONSULTANCY | 2.66 | 0 | 0 | 0
859 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accommodate FHTC (121 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Gholepukuria JL-134(P) - (Gholepukuria Dakshin Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-E | 2752/TD | 27/01/2021 | 20 | PULAK KUMAR SAMANTA | 6.33 | 0 | 0 | 100
860 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accommodate FHTC (387 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II )_within Rankinipur JL-135(P) - (Rankinipur Uttar) &Gholepukuria JL-134(P) - (Madhya Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. PART-A | 2748/TD | 27/01/2021 | 20 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.48 | 0 | 0 | 100
861 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accommodate FHTC (397 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Rankinipur - (Rankinipur Purba) JL-135(P) &Gholepukuria - (Gholepukuria Purba Uttar Para) JL-134(P) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-B | 2749/TD | 27/01/2021 | 20 | ADHIKARY CONSTRUCTION | 20.1 | 0 | 0 | 100
862 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accommodate FHTC (395 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Rankinipur JL-135(P) - (Rankinipur Dakshin) & Gholepukuria JL-134(P) - (Gholepukuria Uttar Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-D | 2751/TD | 27/01/2021 | 20 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 20.37 | 11.38 | 100 | 100
863 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accommodate FHTC (424 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Rankinipur JL-135(P) - (Rankinipur Paschim) & GholepukuriaJL-134(P) - (Gholepukuria Dakshin Paschim Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. PART-C | 2750/TD | 27/01/2021 | 20 | FARID UDDIN AHMED | 21.27 | 4.5 | 100 | 100
864 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gholpukuria - I W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) | 1101/W | 30/03/2021 | 0 | ADHIKARY CONSTRUCTION | 10.54 | 0 | 0 | 0
865 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accomodate FHTC 387 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-A) | BP-2021-22-56 | 13/08/2021 | 0 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 8.11 | 0 | 0 | 0
866 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gholpukuria - I W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) | 1114/W | 30/03/2021 | 0 | PULAK KUMAR SAMANTA | 5.34 | 0 | 0 | 0
867 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - I W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Phase-II) | 1100/W | 30/03/2021 | 0 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 8.89 | 0 | 0 | 0
868 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accomodate FHTC 121 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-E) | BP-2021-22-49 | 29/07/2021 | 0 | PULAK KUMAR SAMANTA | 0.97 | 0 | 0 | 0
869 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accomodate FHTC 397 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-B) | BP-2021-22-116 | 05/10/2021 | 0 | ADHIKARY CONSTRUCTION | 9.55 | 0 | 0 | 0
870 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gholpukuria - I W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) | 1094/W | 30/03/2021 | 0 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 11.1 | 0 | 0 | 0
871 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) , SM/07480 | Retrofitting | Retrofitting to accomodate FHTC 424 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-C) | BP-2021-22-146 | 03/11/2021 | 0 | FARID UDDIN AHMED | 16.5 | 0 | 0 | 0
872 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Functional Household Tap connection to the 200 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- B (Mouza-GuriaJL-45). | 2743/TD | 27/01/2021 | 20 | G. S. CONSTRUCTION | 9.5 | 0 | 0 | 100
873 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Functional Household Tap connection to the 200 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- A (Mouza-Guria JL-45.) | 2742/TD | 27/01/2021 | 20 | MADAN MOHAN MAITY | 9.51 | 4.07 | 200 | 100
874 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Functional Household Tap connection to the 200 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- C (Mouza-Guria JL-45). | 2744/TD | 27/01/2021 | 20 | SUDIP MANNA | 9.5 | 1.78 | 200 | 100
875 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Functional Household Tap connection to the 531 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- D (Mouza-Betalbasan & Ghatual (282+249= 531 nos), JL-47 & 50. | 2745/TD | 27/01/2021 | 25 | BHOLANATH DEY | 25.08 | 4.72 | 200 | 100
876 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Functional Household Tap connection to the 300 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- F (Mouza-Narayanpur,JL-46). | 2747/TD | 27/01/2021 | 20 | MAA KALI CONSTRUCTION | 14.3 | 2.16 | 100 | 100
877 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Retrofitting to accomodate FHTC under JJM Guria W/S Scheme under Tamluk Division, PHE Dte. | 1108/W | 30/03/2021 | 0 | SK. NUR ISLAM | 6.01 | 0 | 0 | 0
878 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Retrofitting to accomodate FHTC under JJM Guria W/S Scheme under Tamluk Division, PHE Dte. | 1098/W | 30/03/2021 | 0 | MAA KALI CONSTRUCTION | 12.11 | 0 | 0 | 0
879 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Functional Household Tap Connection for Guria W/S Scheme within Nandakumar Block Tamluk Division, PHE Dte. | 1106/W | 30/03/2021 | 0 | G. S. CONSTRUCTION | 9.28 | 0 | 0 | 0
880 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Retrofitting to accomodate FHTC under JJM Guria W/S Scheme under Tamluk Division, PHE Dte. | 1112/W | 30/03/2021 | 0 | SUDIP MANNA | 8.61 | 0 | 0 | 0
881 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Guria W/S Scheme within Nandakumar Dev. Block under Tamluk Division, PHE Dte. |  | 17/03/2021 | 0 | MADAN MOHAN MAITY | 7.46 | 0 | 0 | 0
882 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Retrofitting to accomodate FHTC 200 Nos. connection under JJM Guria W/S Scheme within Nandakumar Dev. Block under Tamluk Division, PHE Dte. (Part-A) | 1105/W | 30/03/2021 | 0 | MADAN MOHAN MAITY | 7.46 | 0 | 0 | 0
883 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Guria W/S Scheme within Nandakumar Dev. Block under Tamluk Division, PHE Dte. | 1096/W | 30/03/2021 | 0 | BHOLANATH DEY | 22.75 | 0 | 0 | 0
884 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Functional Household Tap connection to the 140 nos. Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- E (Mouza-Narayanpur,JL-46). | 2746/TD | 27/01/2021 | 20 | SK. NUR ISLAM | 6.64 | 0.34 | 100 | 100
885 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. , SM/07483 | Retrofitting | Material Requisition To Resource Division | 1107/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
886 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paya(Mahaprabhu) W/S Scheme , SM/08232 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Paya(Mahaprabhu) PWSS Block- Ramnagar-I in the District of Purba Medinipur.(Phase-II) | 2996/TD | 25/02/2021 | 30 | MAITY CONSTRUCTION | 99.11 | 72.39 | 100 | 100
887 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paya(Mahaprabhu) W/S Scheme , SM/08232 | Retrofitting | Retrofitting to accomodate FHTC under JJM Paya (Mahaprabhu) W/S Scheme under Tamluk Division, PHE Dte. | 1087/W | 30/03/2021 | 0 | MAITY CONSTRUCTION | 24.87 | 0 | 0 | 0
888 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paya(Mahaprabhu) W/S Scheme , SM/08232 | Retrofitting | valve operator (one no) in head work site at Paya(Mahaprabhu) & its adjoining mouzas water supply scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division PHE Dte. (For 12 months or 365 days) w.e.f from 01.09.2024 | 873/DSD | 27/08/2024 | 365 | MAITY CONSTRUCTION | 2.14 | 0 | 0 | 0
889 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR - II BLOCK , SM/08753 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bheribharanga PWSS Block Ramnagar - II in the district of Purba Medinipur under Tamluk Division, PHE Dte. | BP-2021-22-144 | 03/11/2021 | 0 | DAS CONSTRUCTION | 37.37 | 0 | 0 | 0
890 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR - II BLOCK , SM/08753 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bheribaranga PWSS Block- Ramnagar-II in the District of Purba Medinipur.(Phase-II) | 694/TD | 10/09/2021 | 60 | DAS CONSTRUCTION | 97.49 | 60.11 | 100 | 80
891 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Alinan Zone-I and II PWSS Balance Part Block Sahid Matangini under Tamluk Sub Division of Tamluk Division PHE Dte. Purba Medinipur. , SM/08754 | Retrofitting | Retrofitting to accomodate FHTC (1100 nos.) under JJM in Alinan -I & II PWSS(Balance Work) Block- Sahid Matangini under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District . (Phase- II). | 692/TD | 10/09/2021 | 45 | TAPAS SANTRA | 58.58 | 0 | 0 | 100
892 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Alinan Zone-I and II PWSS Balance Part Block Sahid Matangini under Tamluk Sub Division of Tamluk Division PHE Dte. Purba Medinipur. , SM/08754 | Retrofitting | Retrofitting to accomodate FHTC (1100 Nos.) under JJM in Alinan Zone - I & II PWSS (Balance Work) Block - Sahid Matangini under Tamluk Division, PHE Dte. (Phase-II) | BP-2021-22-107 | 05/10/2021 | 0 | TAPAS SANTRA | 56.73 | 0 | 0 | 0
893 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Uttar Khasda W/S Scheme under Contai-I Block (PHASE-II) , SM/08225 | Retrofitting | Retrofitting to accomodate for 300 Nos. FHTC connection under JJM in Uttar Khasda W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. (Phase-II) |  | 24/08/2021 | 0 | SRIMANTA KUMAR MAITY | 23.49 | 0 | 0 | 0
894 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Uttar Khasda W/S Scheme under Contai-I Block (PHASE-II) , SM/08225 | Retrofitting | Retrofitting to accomodate for 300 Nos. FHTC connection under JJM in Uttar Khasda W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. (Phase-II) | BP-2021-22-71 | 04/09/2021 | 0 | SRIMANTA KUMAR MAITY | 23.49 | 0 | 0 | 0
895 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Uttar Khasda W/S Scheme under Contai-I Block (PHASE-II) , SM/08225 | Retrofitting | Retrofitting to accommodate FHTC [ 300 nos] under JJM in Uttar Khasda PWSS [Kulbaria(119,part),DakshinKhasda(120,part), Harichak(121,part),Akgerya(123,part), Palta Beria(128,part), Paschim Teghari(129,part), Tedubi(184,part), Uttar Khasda(185,part), Ulu Bere(186,part), Naraharichak(187,part), Dhangan(188,part),Paschim Jagannathchak(189,part), Rautara(193,part)] within Contai-I Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) | 2923/TD | 22/02/2021 | 20 | SRIMANTA KUMAR MAITY | 26.25 | 0 | 0 | 100
896 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) , SM/10433 | Retrofitting | Repairing of staircase and related works for R.C.C. Over Head Reservoir of capacity 350 Cum at Contai-II Block within Baharchandberya W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | 516 / CSD | 29/11/2021 | 21 | LAKSHMI NARAYAN ENTERPRISE | 0.55 | 0 | 0 | 0
897 | PURBA MEDINIPUR | Midnapore Mechanical | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) , SM/10433 | Retrofitting | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) under JJM Program under MMD PHE Dte. | 884/W/MMD | 27/03/2023 | 180 | UTTAM KUMAR CHATTERJEE | 12.39 | 0 | 0 | 0
898 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) , SM/10433 | Retrofitting | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 0.5 | 100 | 100
899 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) , SM/10433 | Retrofitting | Repairing of OHR, Pump House no 1, Pump House No. 2 under JJM with allied work of Baharchandberya PWSS within Deshpran Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 3328/TD | 22/10/2024 | 40 | S R TRADING CORPORATION | 12.55 | 0 | 0 | 0
900 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) , SM/10433 | Retrofitting | Land Development for approach road for entry of Rig Machine for Replacement of 2nd Tube Well of Baharchandberya W/S Scheme within Desopran Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1583/CSD | 16/08/2023 | 15 | ABHIJIT BERA | 0.49 | 0.48 | 100 | 100
901 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) , SM/10433 | Retrofitting | Laying Distribution pipe line to accommodate FHTC with allied works for Retrofitting in Baharchandberya Water Supply Scheme within Deshpran Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte., Purba Medinipur. (PHASE-II) | 969/TD | 03/08/2022 | 786 | DIPAK KUMAR BAKLY | 92.52 | 71.22 | 76.97 | 70
902 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS and Jalpai Part-II PWSS under Nandigram-I and II Dev. Block. , SM/09074 | Retrofitting | Retrofitting to accommodate FHTC (335 Nos.) under JJM in Manikpur PWSS & Jalpai Part-II PWSS (Balance Part) Block -Nandigram-I & Nandigram-II in the District of Purba Medinipur. | 1124/TD | 22/11/2021 | 20 | SANKHA ENTERPRISE | 36.47 | 26.1 | 71.58 | 100
903 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS and Jalpai Part-II PWSS under Nandigram-I and II Dev. Block. , SM/09074 | Retrofitting | Work order for laying of left out HDPE pipe line at Manikpur & Champainagar mouja for Manikpur & its Adjoining Mouzas W/S Scheme within Nandigram - I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 599/HSD | 30/08/2022 | 10 | SANKHA ENTERPRISE | 2.46 | 2.46 | 100 | 100
904 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bainchberia Water Supply Scheme under Tamluk Division, PHE Dte. | 1163/TD | 01/12/2021 | 7 | HORIZEN | 9.35 | 9.23 | 100 | 100
905 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Supply of sluice valve & delivery at Chapbasan Store for Bahichberia PWSS within Nandakumar Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-B) | 1232/TD | 07/09/2022 | 15 | J.S. CONSTRUCTION | 3.61 | 3.61 | 100 | 100
906 | PURBA MEDINIPUR | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | 214/CMSD-I(D) | 09/11/2021 | 15 | PADMA ENGINEERING & CO. | 4.52 | 0.72 | 100 | 0
907 | PURBA MEDINIPUR | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAICHBERYA W/S SCH (REPLACEMENT TW-II) NANDAKUMAR BLOCK PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 433/CDD | 23/05/2022 | 30 | PADMA ENGINEERING & CO. | 13.86 | 12.78 | 100 | 100
908 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Supply of sluice valve & delivery at Chapbasan Store for Bahichberia PWSS within Nandakumar Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-A) | 1231/TD | 07/09/2022 | 15 | J.S. CONSTRUCTION | 3.14 | 3.14 | 100 | 100
909 | PURBA MEDINIPUR | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAICHBERIA W/S SCH (TW-III), NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 1231/CDD | 16/11/2022 | 30 | PADMA ENGINEERING & CO. | 18.95 | 16.13 | 100 | 100
910 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Baichberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 480/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.39 | 0 | 0 | 0
911 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Bahichberia Water Supply Scheme under Tamluk Sub Division, PHE Dte. Purba Medinipur. | 2482/TD | 16/01/2023 | 30 | SK. NUR ISLAM | 4.85 | 4.85 | 100 | 25
912 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 2nd tube well site of Bahichberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 2483/TD | 16/01/2023 | 30 | S.K. MONDAL | 3.53 | 3.52 | 99.74 | 0
913 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Land filling work for entrance approach & 3rd tube well site of Bahichberia Water Supply Scheme for augmentation of Bahichberia pwss under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1086/TSD | 22/08/2022 | 15 | J.S. CONSTRUCTION | 1.72 | 1.54 | 100 | 100
914 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Material Requisition To Resource Division | 84/TD | 08/04/2022 | 0 | Resource Division | 53.93 | 0 | 0 | 0
915 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Material Requisition To Resource Division | 650/TD | 27/06/2022 | 0 | Resource Division | 39.34 | 0 | 0 | 0
916 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Electric quotation for Baichberya PWSS Tube Well- III (Ref. ID - 203911567) | BP-2022-23-129 | 13/03/2023 | 0 | WBSEDCL | 8.28 | 0 | 0 | 0
917 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Bahichberia PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 270/TD | 20/04/2023 | 630 | S.K. MONDAL | 29.92 | 4.51 | 15.09 | 80
918 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Laying left out portion of 90 mm dia UPVC pipe line ( 3991.00 mtr ) with allied works to facilitating the FHTC connection for Bainchberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. ( Part-A) | 3054/TD | 19/09/2024 | 25 | HYDROTECH ASSOCIATES | 17.58 | 0 | 0 | 0
919 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well - II of Baichberiya water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2118/W/MMD | 28/11/2022 | 458 | RITESH ENTERPRISE | 12.17 | 11.3 | 100 | 90
920 | PURBA MEDINIPUR | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries at Baichberia , Nandakumar Block under Purba Midnapore District, Central Drilling Division, P.H.E. Dte. | 1229/CDD | 16/11/2022 | 390 | MENAKA ENTERPRISE | 18.61 | 15.55 | 100 | 100
921 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Material Requisition To Resource Division | 1103/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
922 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Material Requisition To Resource Division | 2002/TD | 14/06/2024 | 0 | Resource Division | 2.64 | 0 | 0 | 0
923 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Qoutation bill for T/W -IV of Baichberia water supply scheme | BP-2023-24-608 | 07/02/2024 | 0 | WBSEDCL | 3.8 | 0 | 0 | 0
924 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Augmentation of ground water based Bahichberia Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of RCC Over Head Reservoir 900 cum and staging height 20.00 mtr. With allied work including Sub Soil Investigation within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 56/TD | 05/04/2022 | 922 | JAYANTA KUMAR MONDAL | 952.26 | 917.45 | 96.34 | 99
925 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well site of Bahichberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 79/TSD | 13/01/2023 | 690 | J.S. CONSTRUCTION | 2.61 | 0 | 0 | 0
926 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1219/W/MMD | 25/04/2023 | 860 | BHABANI PRASAD MANNA | 27.19 | 12.79 | 47.04 | 50
927 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Dismentling of existing damaged godown at Bainchberia and its adj mouzas Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | 195/TSD | 22/01/2025 | 30 | SUDIP MANNA | 2.12 | 0 | 0 | 0
928 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division ,PHE Dte. Under Tamluk Division for the period from 01.11.2024 upto 31.10.2025 i.e 12 (Twelve) Months. | 1636/TSD | 30/10/2024 | 239 | TAPAS SANTRA | 1.14 | 0.8 | 70.47 | 0
929 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme , SM/10122 | Augmentation | Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, bearing Vehicle No-WB-29F-4919 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 07.08.2025 to 06.02.2026.(06 Months) | 2671/TSD | 06/08/2025 | 184 | KHOKAN SAMANTA | 0.87 | 0 | 0 | 10
930 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | Laying distribution pipe line, and providing of FHTC for Rejuvenation of GOBINDANAGAR & its adjoining moujas Water Supply Scheme within Panskura Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | 1899/TD | 23/02/2022 | 180 | TARUN KOLEY | 554.16 | 519.2 | 93.69 | 100
931 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Gobindanagar (Zone-I & Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | 1192/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 9.26 | 9.26 | 100 | 100
932 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | Charges for entry of Household data in J.J.M. website along with House hold Addhar detai1s and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. The work should be taken up as per direction of Engineer-In-Charge. N.B. This item should be exclusively used for IMIS entry through J.J.M. | 90/TD | 11/04/2022 | 30 | MISHRA ENTERPRISE | 4.85 | 4.85 | 100 | 100
933 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | Supply of sluice valve & delivery at Chapbasan Store for Gobindanagar Zone-I & II PWSS within Panskura-I Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-A) | 424/TD | 27/05/2022 | 15 | TARUN KOLEY | 4.32 | 4.32 | 100 | 100
934 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | Supply of sluice valve & delivery at Chapbasan Store for Gobindanagar Zone-I & II PWSS within Panskura-I Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-B) | 425/TD | 27/05/2022 | 15 | TARUN KOLEY | 3.65 | 3.65 | 100 | 100
935 | PURBA MEDINIPUR | Central Drilling | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 230 mtrs. depth) by utilising Departmental machineries for Gobindanagar W/S Scheme (Z-II) panskura block under purba medinipur district, CDD, PHE Dte. | 2112/CDD | 02/03/2023 | 30 | PADMA ENGINEERING & CO. | 17.76 | 13.68 | 77.04 | 0
936 | PURBA MEDINIPUR | Central Drilling | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR GOBINDANAGAR W/S SCH (ZONE-I, TW-III), PANSKURA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 2119/CDD | 02/03/2023 | 30 | PADMA ENGINEERING & CO. | 17.76 | 15.08 | 84.94 | 0
937 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | Land development and making approach road of 3 (three) nos. Boosting Tube Well site at Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | 2980/TD | 29/11/2023 | 20 | M/S. S. A. CONSTRUCTION | 5.11 | 0 | 0 | 0
938 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | Augmentation of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura-I Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | 2558/TD | 24/01/2023 | 60 | TARUN KOLEY | 73.36 | 62.84 | 100 | 100
939 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | Material Requisition To Resource Division | 1259/TD | 13/12/2021 | 0 | Resource Division | 4.42 | 0 | 0 | 0
940 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | Material Requisition To Resource Division | 417/TD | 25/05/2022 | 0 | Resource Division | 2.19 | 0 | 0 | 0
941 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | Material Requisition To Resource Division | 1954/TD | 04/03/2022 | 0 | Resource Division | 23.84 | 0 | 0 | 0
942 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) , SM/09286 | Augmentation | Quotation money payment to WBSEDCL for GobindanagarZone-II Water Supply Scheme of Tube Well No. - IV | BP-2023-24-324 | 29/08/2023 | 0 | WBSEDCL | 4.39 | 0 | 0 | 0
943 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-X , SM/07117 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -X(Balance Work) Block Panskura-II in the District of Purba Medinipur. | 2504/TD | 23/12/2020 | 60 | JAYANTA KUMAR MONDAL | 96.37 | 192.59 | 199.85 | 100
944 | PURBA MEDINIPUR | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR BHAGWANPUR-I & BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. , SM/10689 | New | Material Requisition To Resource Division | 2901/TD | 21/11/2023 | 0 | Resource Division | 13.69 | 0 | 0 | 0
945 | PURBA MEDINIPUR | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR BHAGWANPUR-I & BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. , SM/10689 | New | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0 | 0
946 | PURBA MEDINIPUR | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR BHAGWANPUR-I & BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. , SM/10689 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 825.55 | 84.46 | 48
947 | PURBA MEDINIPUR | Central Drilling | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | CONTINUATION OF MAXI CAB (BS-III & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE SEMC-II, PHE DTE. | 26/ S&WSD | 18/03/2020 | 15 | MITALI DAS | 0.29 | 0.84 | 290.39 | 100
948 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme under Tamluk Division, PHE Dte. | 1161/TD | 01/12/2021 | 7 | HORIZEN | 9.49 | 9.05 | 100 | 100
949 | PURBA MEDINIPUR | Central Drilling | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE JOHN/1000 UNDER CDD, PHE DTE. | 1016/CDD | 15/12/2021 | 30 | MENAKA ENTERPRISE | 13.81 | 12.72 | 100 | 100
950 | PURBA MEDINIPUR | Central Drilling | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHAPBASAN BLOCK TAMLUK UNDER CMSD-I (D), CDD, PHE DTE. | 66/CMSD-I (D) | 22/03/2022 | 7 | MENAKA ENTERPRISE | 0.84 | 0.84 | 100 | 100
951 | PURBA MEDINIPUR | Central Drilling | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 240 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHAPBASAN W/S SCHEME (TW-IV), TAMLUK BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 386/ CDD | 18/05/2022 | 30 | PADMA ENGINEERING & CO. | 14.26 | 13.31 | 100 | 100
952 | PURBA MEDINIPUR | Central Drilling | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | ADDITIONAL WORK FOR CONSTRUCTION OF TUBE WELL AT CHAPBASAN, BLOCK - TAMLUK BY UTILIZING SKILLED DRILLING CREW & DEPRTMENTAL MACHINERIES UNDER CMSD-I (D), CDD, PHE DTE. | 69/CMSD-I (D) | 29/03/2022 | 7 | MENAKA ENTERPRISE | 0.4 | 0.4 | 100 | 100
953 | PURBA MEDINIPUR | Central Drilling | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHAPBASAN PWSS (TW-IV) BLOCK- TAMLUK UNDER CDD, PHE DTE. | 125/CMSD-I | 17/05/2022 | 7 | PADMA ENGINEERING & CO. | 0.53 | 0.15 | 100 | 100
954 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Chapbasan Water Supply Scheme within Tamluk Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 692/TD | 27/06/2022 | 180 | TARUN KOLEY | 724.76 | 531.29 | 73.31 | 75
955 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Continuation work order for Hiring of one no Diesel Motor Cabs & Maxi cab with Engine Capacity More than 2000 C.C. with (Air Condition) on monthly haring (per day) (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Engineering Chief Govt of West Bengal PHE Deptt. for the period from 01.07.2022 to 31.12.2022. | 783/TSD | 29/06/2022 | 183 | KRISHNA MONDAL | 1.09 | 1.97 | 100 | 100
956 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division ,PHE Dte. under Tamluk Division for the period from 01.10.2022 to 30.09.2023. | 1297/TSD | 29/09/2022 | 239 | DEBNATH MAITY | 1.14 | 4.69 | 100 | 100
957 | PURBA MEDINIPUR | Central Drilling | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 240 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR AUGMENTATION OF MIDNAPORE MEDICAL COLLEGE & HOSPITAL W/S SCH (TW-I) UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | 1076/CDD | 28/10/2022 | 30 | PADMA ENGINEERING & CO. | 16.51 | 0.72 | 15.98 | 0
958 | PURBA MEDINIPUR | Central Drilling | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELLS AT HARIPAL (Z-I) PWSS, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. | 574/CMSD-I (D) (P-II) | 30/11/2022 | 7 | C.M. ENTERPRISE | 0.7 | 0.64 | 100 | 0
959 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) (Bharat stage-IV) bearing vehicle no- WB-29B-2278 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division, PHE Dte. under Tamluk Division for the period from 01.08.2022 to30.09.2022. | 991/TSD | 27/07/2022 | 62 | DEBNATH MAITY | 0.19 | 0.4 | 100 | 100
960 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th Tube Well site of Chapbasan Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 1340/TD | 16/09/2022 | 25 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 4.46 | 3.98 | 100 | 100
961 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Chapbasan Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 1341/TD | 16/09/2022 | 25 | SWAPAN KUMAR MAITY | 4.55 | 1.93 | 100 | 100
962 | PURBA MEDINIPUR | Central Drilling | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | CONSTRUCTION OF TUBE WELL (250MM X 150MM X DEPTH 220 MTRS) FOR IIEST (TW-I), MELLOK, HOWRAH DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | 400/CDD | 20/05/2022 | 30 | ASHUTOSH DAS & CO | 10.05 | 0 | 0 | 0
963 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Chapbasan Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 1339/TD | 16/09/2022 | 25 | MOYNA TECHNOLINK ENGINEER'S CO-OP SOCIETY LTD. | 4.46 | 3.77 | 100 | 100
964 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Hiring of one no Diesel Motor Cabs & Maxi cab with Engine Capacity More than 2000 C.C. with (Air Condition) on monthly haring (per day) (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Engineering Chief Govt of West Bengal PHE Deptt. for the period from 01.01.2023 to 30.06.2023. | 1675/TSD | 30/12/2022 | 182 | KRISHNA MONDAL | 1.09 | 2.39 | 100 | 100
965 | PURBA MEDINIPUR | Central Drilling | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | CONSTRUCTION OF TUBE WELL (250MM X 150MM X DEPTH 220 MTR) FOR IIEST (TW-I), SHIBPUR, HOWRAH DISTRICT BY UTILISING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | 400/CDD (P-II) | 20/05/2022 | 30 | ASHUTOSH DAS & CO | 10.05 | 5.2 | 100 | 0
966 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Material Requisition To Resource Division | 643/TD | 27/06/2022 | 0 | Resource Division | 44.53 | 0 | 0 | 0
967 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Material Requisition To Resource Division | 100/TD | 11/04/2022 | 0 | Resource Division | 56.47 | 0 | 0 | 0
968 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Electric quotation for Gourangapur/Chapbasan PWSS Tube Well-I in connection Tamluk CCC (2004170186) |  | 09/02/2023 | 0 | WBSEDCL | 4.58 | 0 | 0 | 0
969 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Way leave charges of Souther Eastern Railway Track for Application ID SER-KGP-2021-WL-01 under Tamluk Division, PHE Dte. | BP-2023-24-567 | 07/11/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.22 | 0 | 0 | 0
970 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Payment to WBSEDCL for Quotation Money of Chapbasan W/S Scheme for Tube Well No. - 2 | BP-2022-23-715 | 24/02/2023 | 0 | WBSEDCL | 4.16 | 0 | 0 | 0
971 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Electric quotation for Chapbasan PWSS Tube Well-II in connection Tamluk CCC (2004150121) |  | 09/02/2023 | 0 | WBSEDCL | 4.16 | 0 | 0 | 0
972 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Payment to WBSEDCL for Quotation Money at 3rd Pump House of Chapbasan Water Supply Scheme under Tamluk Division, PHE Dte. | BP-2023-24-95 | 07/06/2023 | 0 | WBSEDCL | 1.74 | 0 | 0 | 0
973 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Payment to WBSEDCL for Quotation Money of Chapbasan W/S Scheme for Tube Well No. ¿ 1 | BP-2022-23-715 | 24/02/2023 | 0 | WBSEDCL | 4.58 | 0 | 0 | 0
974 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Restoration estimate with sand filling and jhama -metal consolidation of link road to NH-41 along the bank of Sankarara Khal Road due to cutting of hard shoulder for laying water pipeliones by PHE Dte. within Tamluk Highway Sub-Division in the district of Purba Medinipur during the year 2022-23 | BP-2023-24-115 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.05 | 0 | 0 | 0
975 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Continuation work order for Hiring of one Diesel motor cabs & Maxi cab with Engine capacity more than 2000 C.C. with (Air Condition) on monthly hiring (Per day) (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Engineering Chief Govt of West Bengal PHE Deptt. for the period from 01.07.2023 to 31.12.2023 | 913/TSD | 30/06/2023 | 184 | KRISHNA MONDAL | 1.09 | 2.4 | 150 | 100
976 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Continuation work order for Hiring of one no Diesel Motor Cabs (Luxury Taxi) (Standard non air conditioned) Bharat stage-IV, (Vehicle No. WB-29B-2278) on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub-Division, PHE Dte under Tamluk Division for the period from 01.04.2024 to 30.06.2024. | 551/TSD | 28/03/2024 | 50 | DEBNATH MAITY | 0.24 | 1.13 | 477.07 | 100
977 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme Block - Tamluk under JJM Program under MMD PHE Dte. | 206/W/MMD | 10/02/2023 | 180 | UNITED TRADERS | 27.3 | 26.8 | 100 | 60
978 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Material Requisition To Resource Division | 1120/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
979 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Interconnection with laying of 150 mm dia & 200 mm dia DI(K-9) Rising main From 3rd Tube Well & 4 th Tube Well Site to O.H.R. Site and other allied works at Chapbasan Water Supply Scheme within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2351/TD | 10/01/2023 | 330 | PULAK KUMAR SAMANTA | 9.84 | 0 | 0 | 100
980 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, bearing vehicle no-WB 29C 2453 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 01.07.2024 to 31.12.2024.(06 Months) | 949/TSD | 28/06/2024 | 183 | DEBNATH MAITY | 0.87 | 2.31 | 263.85 | 0
981 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Construction of 1(one) nos M.S. Structure over irrigation canal to support 200 mm dia. DI K9 Rising Main under Chapbasan Water Supply Scheme at Pipulberia under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte. | 38/TSD | 08/01/2025 | 20 | PULAK KUMAR SAMANTA | 1.58 | 0 | 0 | 100
982 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | New construction of Boundaty wall at Chapbasan Water Supply Scheme 3rd (52 mtr) & 4th(47 mtr) T/W site under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E.Dte. | 674/TD | 03/03/2025 | 40 | SUDIP MANNA | 9.68 | 0 | 0 | 0
983 | PURBA MEDINIPUR | Tamluk Division | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. , SM/09977 | Augmentation | Repairing & Renovation work of Boundary wall, Staff Quarter, Godown & approach Road at Chapbassan Store of Tamluk Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | 1725/TD | 30/06/2025 | 45 | GOUTAM DEY | 44.99 | 0 | 0 | 0
984 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I , SM/10725 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 400cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhabpur Zone-I Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 2183/TD | 20/12/2022 | 180 | GUPTA ENTERPRISE. | 638.56 | 82.65 | 12.94 | 15
985 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I , SM/10725 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I, Block Egra II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1279/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 25.14 | 0 | 0 | 0
986 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I , SM/10725 | Augmentation | Material Requisition To Resource Division | 1665/TD | 03/11/2022 | 0 | Resource Division | 141.02 | 0 | 0 | 0
987 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I , SM/10725 | Augmentation | Material Requisition To Resource Division | 2636/TD | 02/02/2023 | 0 | Resource Division | 18.68 | 0 | 0 | 0
988 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I , SM/10725 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-I Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1909/TD | 25/11/2022 | 912 | OSMAN SEKH | 69.99 | 0 | 0 | 100
989 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I , SM/10725 | Augmentation | Laying of Balance portion for Distribution pipe line by UPVC pipes with allied works for Madhakhali Zone-I & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 2189/TD | 01/09/2023 | 45 | SWARUPANANDA DAS | 95.53 | 93.29 | 97.66 | 98
990 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I , SM/10725 | Augmentation | Requirement of additional pipeline to accommodate FHTC for Augmentation of Madhabpur Zone-I Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 2197/TD | 01/09/2023 | 25 | DEBABRATA DAS | 16.53 | 0 | 0 | 0
991 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I , SM/10725 | Augmentation | Repaire of Pump House , Boundary Wall construction of boundary wall & Land development approch road under JJM with allied work for Madhabpur (Z-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 1023/TD | 07/06/2023 | 40 | KAMAL KUMAR ROY | 41.68 | 0 | 0 | 0
992 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. , SM/10682 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme under Tamluk Division, PHE Dte. | 1160/TD | 01/12/2021 | 7 | HORIZEN | 8.24 | 8.12 | 100 | 100
993 | PURBA MEDINIPUR | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. , SM/10682 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBEWELL (300MM X 200MM X 240 MTRS DEPTH) BY UTILISING DEPARTMENTALMACHINERIES FOR DAKSHIN GUMAI W/S SCHEME (TW-III), NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 2118/CDD | 02/03/2023 | 30 | PADMA ENGINEERING & CO. | 18.26 | 15.62 | 85.52 | 0
994 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. , SM/10682 | Augmentation | Material Requisition To Resource Division | 1257/TD | 12/09/2022 | 0 | Resource Division | 34.11 | 0 | 0 | 0
995 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. , SM/10682 | Augmentation | Material Requisition To Resource Division | 1016/TD | 08/08/2022 | 0 | Resource Division | 232.04 | 0 | 0 | 0
996 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. , SM/10682 | Augmentation | Payment to WBSEDCL for Electric Quotation money of Dakshin Gumai Water Supply Scheme for Tube Well No.- III | BP-2023-24-218 | 02/08/2023 | 0 | WBSEDCL | 3.12 | 0 | 0 | 0
997 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. , SM/10682 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme Block - Nandakumar under JJM Program under MMD PHE Dte. | 863/W/MMD | 27/03/2023 | 180 | PRANAB KUMAR DAS | 13.47 | 0 | 0 | 70
998 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. , SM/10682 | Augmentation | Continuation work order for Hiring of one no Diesel Motor Cabs (Luxary Taxi) (standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Executive Engineer, Tamluk Division, PHE Dte. under Tamluk Division for the period from 12 (twelve) months, w.e.f. 01/11/2022 to 31/10/2023. | 1344/TSD | 28/10/2022 | 239 | TAPAS SANTRA | 1.14 | 2.4 | 150 | 75
999 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. , SM/10682 | Augmentation | Construction of 3.6 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room for water supply scheme with Boundary Wall (as per Deptt. drawing) at 3rd Tube well site of Dakshin Gumai Pipe Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte.in the District of Purba Medinipur . | 2983/TD | 29/11/2023 | 45 | BHOWMIK & SONS | 11.41 | 8.07 | 70.79 | 72
1000 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. , SM/10682 | Augmentation | Dismantling of existing OHR (Capacity 61550 Gallons or 341000 Ltr.) at Head work site of Dakshin Gumai Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte. | 1029/TD | 07/06/2023 | 45 | BISWAJIT BAG | 9.42 | 9.42 | 100 | 100
1001 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. , SM/10682 | Augmentation | Material Requisition To Resource Division | 1108/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
1002 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. , SM/10682 | Augmentation | Laying of Distribution pipe line to accommodate FHTC (5547 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Dakshin Gumai Water Supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1420/TD | 26/09/2022 | 979 | ARABINDA GHOSH | 944.7 | 805.94 | 85.31 | 85
1003 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. , SM/10682 | Augmentation | Left out FHTC 402 Nos. including supplying, laying, fitting, fixing of Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials and labour for Dakshin Gumai Water Supply Scheme within Nandakumar Dev. Block under Tamluk SubDivision of Tamluk Division PHE Dte. in the District of Purba Medinipur . | 2895/TD | 10/09/2024 | 360 | ARABINDA GHOSH | 91.84 | 0 | 0 | 56
1004 | PURBA MEDINIPUR | Tamluk Division | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS , SM/12434 | New | Material Requisition To Resource Division | 2699/TD | 06/02/2023 | 0 | Resource Division | 20.82 | 0 | 0 | 0
1005 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS , SM/12434 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA MUKUNDAPUR and ADJOINING MOUJAS, Block - Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 518/W/MMD | 20/03/2023 | 180 | RMD TRADING | 22.76 | 8.42 | 36.98 | 85
1006 | PURBA MEDINIPUR | Tamluk Division | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS , SM/12434 | New | Material Requisition To Resource Division | 118/TD | 05/01/2024 | 0 | Resource Division | 7.8 | 0 | 0 | 0
1007 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS , SM/12434 | New | Quotation Bill for New Service connection at T/W NO-I Of PURBA MUKUNDAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004738920/QUOT/03 DT. 17-05-2024 Application NO- LY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004738920 Application type-New connection Consumer Id- 204309716 | BP-2024-25-225 | 31/05/2024 | 0 | WBSEDCL | 4.96 | 0 | 0 | 0
1008 | PURBA MEDINIPUR | Tamluk Division | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS , SM/12434 | New | Quotation Bill for New Service connection at T/W NO-II Of PURBA MUKUNDAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004720948/QUOT/03 DT. 07-05-2024 Application NO- 2004720948 Application type-New connection Consumer Id- 204298864 | BP-2024-25-171 | 07/06/2024 | 0 | WBSEDCL | 36.92 | 0 | 0 | 0
1009 | PURBA MEDINIPUR | Tamluk Division | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS , SM/12434 | New | Sinking of Tube Well ,Construction of 250 Cu.m. Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2852 Nos) For 2 nos Pipe Water Supply Scheme including (Santra & Purba Mukundapur) including two years Operation & Maintainance within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 2711/TD | 30/10/2023 | 790 | TAPAS SANTRA | 938.36 | 294.07 | 59.55 | 40
1010 | PURBA MEDINIPUR | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Jaynagar Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Jaynagar Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 3345/TD | 22/03/2023 | 25 | M R ENTERPRISE | 30.84 | 0 | 0 | 0
1011 | PURBA MEDINIPUR | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Material Requisition To Resource Division | 2473/TD | 16/01/2023 | 0 | Resource Division | 30.03 | 0 | 0 | 0
1012 | PURBA MEDINIPUR | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Ground water based Jaynagar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (700 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | 3042/TD | 27/02/2023 | 35 | RELIABLE CONSTRUCTIONS | 90.11 | 51.54 | 57.19 | 68
1013 | PURBA MEDINIPUR | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Ground water based Jaynagar Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work (400nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | 524/TD | 11/05/2023 | 864 | ZENITH CONSTRUCTION | 141.93 | 45.73 | 32.22 | 30
1014 | PURBA MEDINIPUR | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-I) [Jaynagar PWSS, Mohanpur PWSS, Erekhali PWSS & Hariballavpur PWSS] | 617/HSD, | 21/12/2023 | 7 | SNEHASIS BERA | 0.83 | 0.83 | 100 | 100
1015 | PURBA MEDINIPUR | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Jaynagar PWSS at Mahisadal Block under Tamluk Division,PHE Dte. | 376/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
1016 | PURBA MEDINIPUR | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Material Requisition To Resource Division | 639/W | 20/02/2024 | 0 | Resource Division | 13.39 | 0 | 0 | 0
1017 | PURBA MEDINIPUR | Midnapore Mechanical | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Quotation bill for new service connection at TW-I of Joynagar w/s scheme Block-sutahata in the Dist. of Purba Medinipur under MMD ,PHE Dte. Name of C.C.C.-Chaitanyapur Application no.-2004839280 Application type-new connection Reference ID-204366525 Quotation Date-26/07/2024 Quotation due Date-28/07/2025 Contract Demand-8344W | C082408702219 | 07/08/2024 | 0 | WBSEDCL | 7.89 | 0 | 0 | 0
1018 | PURBA MEDINIPUR | Midnapore Mechanical | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Quotation bill for new service connection at TW-II of Joynagar w/s scheme,Block-Sutahata under MMD PHE Dte. Name of C.C.C.-Chaitanyapur Application No.-2004818887 Application type-new connection Reference ID-204355766 Quotation Date-12/7/2024 Quotation Due Date-14/7/2025 Contract Demand-8344 W | BP-2024-25-495 | 29/07/2024 | 0 | WBSEDCL | 4.61 | 0 | 0 | 0
1019 | PURBA MEDINIPUR | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Ground water based Jaynagar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (774 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | 3043/TD | 27/02/2023 | 951 | ZENITH CONSTRUCTION | 89.68 | 45.99 | 51.29 | 55
1020 | PURBA MEDINIPUR | Midnapore Mechanical | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JAYNAGAR and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 469/W/MMD | 20/03/2023 | 742 | BHABANI PRASAD MANNA | 23.7 | 0 | 0 | 0
1021 | PURBA MEDINIPUR | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Ground water based Jaynagar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | 686/TD | 23/05/2023 | 950 | RELIABLE CONSTRUCTIONS | 172.01 | 21.99 | 12.78 | 20
1022 | PURBA MEDINIPUR | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS , SM/12502 | New | Land Development work at Head work site of Jaynagar Water supply Scheme within Sutahata Develompent Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 1082/TD | 07/04/2025 | 240 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 3.29 | 0 | 0 | 0
1023 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). , SM/11615 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1361/TD | 22/09/2022 | 40 | B. K. ENTERPRISE | 72.46 | 15.29 | 100 | 63
1024 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). , SM/11615 | Augmentation | Material Requisition To Resource Division | 1660/TD | 03/11/2022 | 0 | Resource Division | 143.41 | 0 | 0 | 0
1025 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). , SM/11615 | Augmentation | Material Requisition To Resource Division | 610/TD | 17/05/2023 | 0 | Resource Division | 23.76 | 0 | 0 | 0
1026 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). , SM/11615 | Augmentation | Electric Quotation for CONTAI S.A.Rej. Water Supply Scheme T/W-I, Part-A, Zone-I (Ref. ID-204050258) | BP-2023-24-164 | 04/08/2023 | 0 | WBSEDCL | 2.34 | 0 | 0 | 0
1027 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). , SM/11615 | Augmentation | Electric Quotation for CONTAI S.A.Rej. Water Supply Scheme T/W-II, Part-A, Zone-I (Ref. ID-204050190) | BP-2023-24-163 | 04/08/2023 | 0 | WBSEDCL | 2.48 | 0 | 0 | 0
1028 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). , SM/11615 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A),under JJM Program under MMD PHE Dte. | 1393/W/MMD | 01/06/2023 | 180 | P.K.ENGINEERING | 27.18 | 10.43 | 38.36 | 30
1029 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). , SM/11615 | Augmentation | Payment of wayleave facility charges (SER-KGP-2024-WL-47) | BP-2024-25-78 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.38 | 0 | 0 | 0
1030 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). , SM/11615 | Augmentation | Payment of wayleave facility(SER-KGP-2024-WL-48) | BP-2024-25-79 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.25 | 0 | 0 | 0
1031 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). , SM/11615 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 400 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Contai Saline Area Zone-I (Phase - A) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-I) | 2314/TD | 05/01/2023 | 995 | DAS CONSTRUCTION | 456.2 | 0 | 0 | 0
1032 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). , SM/11615 | Augmentation | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Contai Saline Area Zone-I ( Phase - A) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-II) | 2311/TD | 05/01/2023 | 983 | DAS CONSTRUCTION | 230.47 | 0 | 0 | 0
1033 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madakhali (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | 1696/TD | 31/01/2022 | 20 | CONCORD ENGINEERING | 4.15 | 4.15 | 100 | 100
1034 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madakhali (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | 1697/TD | 31/01/2022 | 20 | CONCORD ENGINEERING | 3.42 | 3.27 | 100 | 100
1035 | PURBA MEDINIPUR | Central Drilling | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MADHAKHALI W/S SCHEME (REPLACEMENT TW, ZONE-I, TW-I), BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 385/CDD | 18/05/2022 | 30 | MENAKA ENTERPRISE | 14.69 | 12.58 | 100 | 100
1036 | PURBA MEDINIPUR | Central Drilling | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MADHAKHALI W/S SCH (REPLACEMENT TW, ZONE-I, TW-II) BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHD DTE. | 432/CDD | 23/05/2022 | 30 | MENAKA ENTERPRISE | 14.69 | 12.83 | 100 | 100
1037 | PURBA MEDINIPUR | Central Drilling | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | PROVIDING ADDITIONAL TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT MADHAKHALI PWSS, TW-II, BLOCK-BHAGAWANPUR-II UNDER CDD, PHE DTE. | 269/CMSD-II (D) | 31/05/2022 | 10 | MENAKA ENTERPRISE | 0.69 | 0.69 | 100 | 100
1038 | PURBA MEDINIPUR | Central Drilling | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | PROVIDING ADDITIONAL TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL UNDER CDD, PHE DTE. | 171/CMSD-I (D) | 06/06/2022 | 7 | MENAKA ENTERPRISE | 0.49 | 0.49 | 100 | 100
1039 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Dhalua, JL No. 243 Plot No. 152) of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 475/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.91 | 0 | 0 | 0
1040 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-I of Zone - I Madhakhali water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | 1862/W/MMD | 22/09/2022 | 120 | M/S B.M. ELECTRICAL | 11.68 | 10.76 | 92.07 | 70
1041 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1st Tubewell of Head Works site (Mouza - Baghadanri, JL No. - 246, Plot No. - 1029) of Madhakhali Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 136/TD | 19/04/2022 | 21 | MENAKA ENTERPRISE | 13.26 | 11.76 | 100 | 100
1042 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District | 1929/TD | 28/11/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.64 | 7.64 | 100 | 100
1043 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Madhakhali Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District | 1930/TD | 28/11/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 5.42 | 5.42 | 100 | 100
1044 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Land Development at Head Work Site of Madhakhali Zone-II PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Part-A) | 1097/CSD | 07/06/2023 | 15 | BIBEKANANDA DAS | 0.97 | 0.97 | 100 | 100
1045 | PURBA MEDINIPUR | Central Drilling | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 20mm x 250 mtrs depth) by utilising Departmental Machineries for Madhakhali W/S scheme(TW-III) ,Bhagawanpur- II Block under Purba Midnapore Dristict ,CDD,P.H.E. Dte. | 1232/CDD | 16/11/2022 | 30 | MENAKA ENTERPRISE | 19.35 | 15.45 | 100 | 100
1046 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Material Requisition To Resource Division | 646/TD | 27/06/2022 | 0 | Resource Division | 23.67 | 0 | 0 | 0
1047 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Material Requisition To Resource Division | 647/TD | 27/06/2022 | 0 | Resource Division | 20.06 | 0 | 0 | 0
1048 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Material Requisition To Resource Division | 99/TD | 11/04/2022 | 0 | Resource Division | 53.75 | 0 | 0 | 0
1049 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Electric Quotiaton for Madhakhali Water Supply Scheme Zone-II, T/W-I (Ref. ID-204004293) | BP-2023-24-67 | 06/06/2023 | 0 | WBSEDCL | 0.59 | 0 | 0 | 0
1050 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Electric Quotation for MADHAKHALI Water Supply Scheme Z-II, T/W-II (Ref. ID-204049127 ) | BP-2023-24-138 | 27/07/2023 | 0 | WBSEDCL | 2.39 | 0 | 0 | 0
1051 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Laying of distribution pipe line to accommodate 1900 nos FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhakhali Zone-I Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.(Part-A). | 817/TD | 12/07/2022 | 180 | DAS ENTERPRISE | 477.83 | 472.5 | 98.88 | 98
1052 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Laying of distribution pipe line to accommodate 1933 nos FHTC with allied works including supply of all labour & materials for Augmentation of Madhakhali Zone-I Water Supply Scheme within Bhagwanpur-II Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-B) | 384/TD | 20/05/2022 | 45 | DAS ENTERPRISE | 223.21 | 223.66 | 100.2 | 98
1053 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Madhakhali piped water supply scheme, (Zone I), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 359/W/MMD | 09/03/2023 | 180 | AHALYA ENGINEERING WORKS | 27.16 | 25.59 | 94.23 | 20
1054 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 101/HESD | 27/02/2023 | 184 | S.S.GHORAI | 0.9 | 0 | 0 | 53
1055 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Dhalua, JL No. 243 Plot No. 152) of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1498) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 2047/TD | 25/08/2023 | 40 | PADMA ENGINEERING CO. | 38.21 | 16.19 | 84.75 | 44
1056 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Laying of Left-Out portion uPVC pipes with allied works due to uncovered area under of Madhakhali Zone-II & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part - A + B + C + D). | 965/TD | 12/03/2024 | 40 | DAS ENTERPRISE | 100.28 | 82.34 | 82.11 | 90
1057 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | M.S. Structures and allied works under Madhakhali Zone-I Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 722/TD | 28/02/2024 | 30 | DAS ENTERPRISE | 17.77 | 0 | 0 | 0
1058 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell (Mouza - Baghadanri, JL No. - 246, Plot No. -495/1489) of Madhakhali Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 135/TD | 19/04/2022 | 21 | MENAKA ENTERPRISE | 13.26 | 11.83 | 100 | 100
1059 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Madhakhali Zone-I W/S Scheme within Bhagwanpur- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Normal Land) | 1179/TD | 05/09/2022 | 60 | M/S. NEW DINDA ENTERPRISE | 3.53 | 3.25 | 100 | 100
1060 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Madhakhali Zone-II W/S Scheme within Bhagwanpur- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | 1177/TD | 05/09/2022 | 60 | PARTHA CONSTRUCTION | 3.81 | 3.13 | 100 | 100
1061 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Madhakhali Zone-I PWSS within Bhagwanpur -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) Laying Rising main and other allied works Augmentation of Madhakhali Zone-I W/S Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3393/TD | 24/03/2023 | 532 | SWARUPANANDA DAS | 19.31 | 0 | 0 | 100
1062 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Land Development at HeadWorks site of Madhakhali Zone-II W/S Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur. (Part-B) | 375/CSD | 23/02/2024 | 15 | PARTHA CONSTRUCTION | 0.97 | 0.96 | 100 | 100
1063 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Madhakhali W/S scheme PH-III, Zone-I Application no-2004427213 Ref.-204078346 | BP-2023-24-501 | 05/01/2024 | 0 | WBSEDCL | 5.26 | 0 | 0 | 0
1064 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE-II Of MADHAKHALI W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No- 2004826940/QUOT/03 DT. 25-07-2024 Application NO- 2004826940 Application type-New connection Consumer Id- 204360840 | BP-2024-25-551 | 08/08/2024 | 0 | WBSEDCL | 3.35 | 0 | 0 | 0
1065 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhakhali Zone-II Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 1003/TD | 08/08/2022 | 180 | DAS ENTERPRISE | 512.49 | 431.94 | 84.28 | 90
1066 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | i) Laying Rising main and other allied works Augmentation of Madhakhali Zone-II W/S Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. Ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Augmentation of Madhakhali Zone-II PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-136.00 mtr.) iii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 2nd TW site for Augmentation of Madhakhali Zone-II PWSS within Bhagwanpur -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iv) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Madhakhali Zone-II PWSS within Bhagwanpur -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | 878/TD | 01/06/2023 | 880 | M/S. PRADIP PRADHAN | 49.33 | 0 | 0 | 70
1067 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW(Head Work) site at Madhakhali Zone-I Water Supply Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. (For Normal Land) | 1092/TD | 25/08/2022 | 60 | SWARUPANANDA DAS | 6.34 | 0 | 0 | 100
1068 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW (Head Work) site at Madhakhali Zone-II Water Supply Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. (For Low Land) | 1093/TD | 25/08/2022 | 60 | BIBEKANANDA DAS | 6.63 | 0 | 0 | 100
1069 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. , SM/09920 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 2nd Tube Well site for Madhakhali Zone-II W/S Scheme within Bhagwanpur- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | 1178/TD | 05/09/2022 | 840 | SWARUPANANDA DAS | 3.81 | 0 | 0 | 100
1070 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VIA , SM/07111 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -VIA Block Panskura-II in the District of Purba Medinipur. | 81/TD | 11/05/2021 | 60 | TITAS CONSTRUCTION | 53.3 | 51.1 | 100 | 100
1071 | PURBA MEDINIPUR | Tamluk Division | JAMITTA & ADJOINING MOUZAS , SM/12137 | New | Material Requisition To Resource Division | 3002/TD | 27/02/2023 | 0 | Resource Division | 19.42 | 0 | 0 | 0
1072 | PURBA MEDINIPUR | Tamluk Division | JAMITTA & ADJOINING MOUZAS , SM/12137 | New | Laying distribution pipe line, Pump House , Boundary Wall, Rising Main & Accommodate FHTC (400 nos) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-B) | 3242/TD | 15/03/2023 | 992 | S.D. CONSTRUCTION | 70.03 | 20.77 | 29.65 | 70
1073 | PURBA MEDINIPUR | Tamluk Division | JAMITTA & ADJOINING MOUZAS , SM/12137 | New | Land filling with silver sand and land development of approach road and other side at 1st. & 2nd. T/W site at Jamitta Water Supply scheme of Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | 829/TD | 05/03/2024 | 24 | S.D. CONSTRUCTION | 4.77 | 4.77 | 100 | 100
1074 | PURBA MEDINIPUR | Tamluk Division | JAMITTA & ADJOINING MOUZAS , SM/12137 | New | Material Requisition To Resource Division | 123/TD | 05/01/2024 | 0 | Resource Division | 7.16 | 0 | 0 | 0
1075 | PURBA MEDINIPUR | Midnapore Mechanical | JAMITTA & ADJOINING MOUZAS , SM/12137 | New | Quotation Bill for New connection Jamitya water supply scheme Tube Well-II. Quotation Bill Date.-01/04/2024 Block-Kolaghat. Kolaghat CCC Application No.-2004662461 Ref no.-204260852 | BP-2024-25-27 | 15/04/2024 | 0 | WBSEDCL | 10.19 | 0 | 0 | 0
1076 | PURBA MEDINIPUR | Midnapore Mechanical | JAMITTA & ADJOINING MOUZAS , SM/12137 | New | New service connection at Jamitya water supply scheme H/W site Kolaghat CCC Block- Kolaghat Application No.-2004803550 Consumer ID.-204346513 Date.-02-07-2024 | BP-2024-25-416 | 15/07/2024 | 0 | WBSEDCL | 3.77 | 0 | 0 | 0
1077 | PURBA MEDINIPUR | Tamluk Division | JAMITTA & ADJOINING MOUZAS , SM/12137 | New | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC (653 nos) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (PART-A) | 3241/TD | 15/03/2023 | 992 | S.D. CONSTRUCTION | 70.26 | 31.59 | 44.97 | 80
1078 | PURBA MEDINIPUR | Tamluk Division | JAMITTA & ADJOINING MOUZAS , SM/12137 | New | Soil investigation & construction of 200 cum OHR (Intze type with pile foundation) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-E) | 3394/TD | 24/03/2023 | 1013 | TAPAS SANTRA | 99.27 | 0 | 0 | 70
1079 | PURBA MEDINIPUR | Tamluk Division | JAMITTA & ADJOINING MOUZAS , SM/12137 | New | Laying distribution pipe line & Accommodate FHTC (110 nos) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-C) | 3243/TD | 15/03/2023 | 992 | MISHRA ENTERPRISE | 9.53 | 3.16 | 33.21 | 100
1080 | PURBA MEDINIPUR | Central Drilling | JAMITTA & ADJOINING MOUZAS , SM/12137 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 59.71 | 118.46 | 11
1081 | PURBA MEDINIPUR | Central Drilling | JAMITTA & ADJOINING MOUZAS , SM/12137 | New | Hiring of Diesel Driven Motor cab (BS-III & Above) having contract carriage permit along with driver for the office of The Executive Engineer, Central Drilling Division, P.H.E. Dte. | 139/S&WSD | 26/06/2024 | 182 | ASHUTOSH DAS & CO | 0.86 | 0.91 | 105.77 | 0
1082 | PURBA MEDINIPUR | Tamluk Division | JERTHAN AND ADJOINING MOUJAS PWSS , SM/12308 | New | Material Requisition To Resource Division | 2420/TD | 16/01/2023 | 0 | Resource Division | 34.51 | 0 | 0 | 0
1083 | PURBA MEDINIPUR | Midnapore Mechanical | JERTHAN AND ADJOINING MOUJAS PWSS , SM/12308 | New | Quotation Bill for New Service connection at T/W NO-I Of JERTHAN W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004847107/QUOT/03/1183 DT. 13-08-2024 Application NO- 2004847107 Application type-New connection Consumer Id- 204372867 | C082448274884 | 02/09/2024 | 0 | WBSEDCL | 10.86 | 0 | 0 | 0
1084 | PURBA MEDINIPUR | Midnapore Mechanical | JERTHAN AND ADJOINING MOUJAS PWSS , SM/12308 | New | Quotation Bill for New Service connection at T/W NO-II Of JERTHAN W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004812325/QUOT/03/814 DT. 09-07-2024 Application NO- 2004812325 Application type-New connection Consumer Id- 204352202 | BP-2024-25-450 | 23/07/2024 | 0 | WBSEDCL | 6.77 | 0 | 0 | 0
1085 | PURBA MEDINIPUR | Midnapore Mechanical | JERTHAN AND ADJOINING MOUJAS PWSS , SM/12308 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JERTHAN and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2382/W/MMD | 31/12/2022 | 180 | ECO ENTERPRISE | 25.26 | 13.35 | 52.87 | 40
1086 | PURBA MEDINIPUR | Tamluk Division | JERTHAN AND ADJOINING MOUJAS PWSS , SM/12308 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 406.93 | 78.8 | 51
1087 | PURBA MEDINIPUR | Midnapore Mechanical | MALIKPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12141 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MALIKPUR and ADJOINING MOUJAS, Block Potashpur II District Purba Medinipur under JJM Program under MMD PHE Dte. | 2329/W/MMD | 29/12/2022 | 180 | DAS ENTERPRISE | 23.64 | 0 | 0 | 0
1088 | PURBA MEDINIPUR | Tamluk Division | MALIKPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12141 | New | Material Requisition To Resource Division | 2454/TD | 16/01/2023 | 0 | Resource Division | 39.75 | 0 | 0 | 0
1089 | PURBA MEDINIPUR | Tamluk Division | MALIKPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12141 | New | Material Requisition To Resource Division | 1658/TD | 29/04/2024 | 0 | Resource Division | 14.83 | 0 | 0 | 0
1090 | PURBA MEDINIPUR | Tamluk Division | MALIKPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12141 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 2703/TD | 20/10/2023 | 620 | S & P ENTERPRISE | 1928.99 | 212.88 | 28.78 | 30
1091 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work(50 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-H) | 3105/TD | 02/03/2023 | 15 | DEBDUT CONSTRUCTION | 16.69 | 11.31 | 67.75 | 68
1092 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (50 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | 3120/TD | 02/03/2023 | 20 | TAPAN BERA | 20.42 | 0 | 0 | 0
1093 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Material Requisition To Resource Division | 2471/TD | 16/01/2023 | 0 | Resource Division | 18.07 | 0 | 0 | 0
1094 | PURBA MEDINIPUR | Midnapore Mechanical | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARIBALLABHPUR and ADJOINING MOUJAS, Block Sutahata District Purba Medinipur under JJM Program under MMD PHE Dte. | 2330/W/MMD | 29/12/2022 | 180 | MAHADEV ENTERPRISE | 23.65 | 0 | 0 | 80
1095 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (25 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | 3104/TD | 02/03/2023 | 1008 | MODERN CONSTRUCTION | 10.75 | 3.17 | 29.49 | 36
1096 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (300 nos) and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | 566/TD | 12/05/2023 | 718 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 167.34 | 65.25 | 38.99 | 70
1097 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Construction of R.C.C. approach road at Head work site of Hariballabhpur & its adjoining mouzas Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E.Dte.(Length of Approach Road-45mtr) | 240/TD | 11/01/2024 | 20 | G. S. CONSTRUCTION | 4.78 | 0 | 0 | 0
1098 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Hariballabhpur Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Hariballabhpur Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 3346/TD | 22/03/2023 | 25 | PRANTIK DRILLING AGENCY | 30.88 | 30.47 | 100 | 100
1099 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work(50nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | 504/TD | 11/05/2023 | 594 | TAPAN BERA | 20.43 | 17.71 | 87.64 | 100
1100 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Material Requisition To Resource Division | 637/W | 20/02/2024 | 0 | Resource Division | 10.66 | 0 | 0 | 0
1101 | PURBA MEDINIPUR | Midnapore Mechanical | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Quotation Bill for New Service Connection at PH-II of Hariballavpur pwss,Block-Sutahata, under MMD,PHE Dte. Name of C.C.C.- Chaitanyapur Application no.-2004644794 Application Type-New Connection Quotation Date-15/03/2024 Quotation Due Date-17/03/2025 | BP-2023-24-920 | 28/03/2024 | 0 | WBSEDCL | 0.28 | 0 | 0 | 0
1102 | PURBA MEDINIPUR | Midnapore Mechanical | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Quotation Bill for new service connection at TW-I & II of Hariballavpur w/s scheme under MMD,PHE, Dte. Block-Sutahata,Chaitanyapur C.C.C Memo No.-2004632082/Quot/03 Date-05/03/2024 Application No.-2004632082 Application Type-New Connection Reference ID-204237950 | BP-2023-24-826 | 13/03/2024 | 0 | WBSEDCL | 13.11 | 0 | 0 | 0
1103 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (50 nos)within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | 3103/TD | 02/03/2023 | 604 | MUKHERJEE ENTERPRISE | 19.22 | 14.6 | 76 | 26
1104 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (725nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-J) | 139/TD | 10/04/2023 | 720 | S. B. ASSOCIATES | 83.67 | 30.56 | 36.53 | 55
1105 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work (400nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | 499/TD | 11/05/2023 | 844 | BARH CONSTRUCTION | 131.4 | 68.59 | 52.2 | 70
1106 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work(50 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-I) | 3106/TD | 02/03/2023 | 665 | TAPAN BERA | 21.6 | 21.23 | 100 | 90
1107 | PURBA MEDINIPUR | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS , SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (30 nos)within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-K) | 3107/TD | 02/03/2023 | 662 | ELECTIVA ENTERPRISE | 4.53 | 4.14 | 100 | 50
1108 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA RADHAPUR & ADJOINING MOUZAS , SM/12154 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA RADHAPUR and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2339/W/MMD | 29/12/2022 | 180 | MAHADEV ENTERPRISE | 23.63 | 0 | 0 | 0
1109 | PURBA MEDINIPUR | Tamluk Division | PURBA RADHAPUR & ADJOINING MOUZAS , SM/12154 | New | Material Requisition To Resource Division | 2383/TD | 16/01/2023 | 0 | Resource Division | 47.81 | 0 | 0 | 0
1110 | PURBA MEDINIPUR | Tamluk Division | PURBA RADHAPUR & ADJOINING MOUZAS , SM/12154 | New | Wideing of approach road of Head work Site of Purba Radhapur PWSS under Bhagabanpur-I. Block under Contai Sub-Division of Tamluk Division , P.H.E. Dte Dist- Purba Medinipur | 3066/TD | 30/11/2023 | 20 | PARTHA CONSTRUCTION | 3.89 | 3.64 | 100 | 100
1111 | PURBA MEDINIPUR | Tamluk Division | PURBA RADHAPUR & ADJOINING MOUZAS , SM/12154 | New | Material Requisition To Resource Division | 86/TD | 05/01/2024 | 0 | Resource Division | 11.52 | 0 | 0 | 0
1112 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA RADHAPUR & ADJOINING MOUZAS , SM/12154 | New | Quotation Bill for New Service connection at T/W NO-II Of PURBA RADHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Application NO- 2004835536 Application type-New connection Consumer Id- 204365524 | C082448207124 | 02/09/2024 | 0 | WBSEDCL | 4.22 | 0 | 0 | 0
1113 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA RADHAPUR & ADJOINING MOUZAS , SM/12154 | New | Quotation Bill for New Service connection at T/W NO-I Of PURBA RADHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Application NO- 2004835493 Application type-New connection Consumer Id- 204365530 | C082448216760 | 02/09/2024 | 0 | WBSEDCL | 7.35 | 0 | 0 | 0
1114 | PURBA MEDINIPUR | Tamluk Division | PURBA RADHAPUR & ADJOINING MOUZAS , SM/12154 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1870 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of PURBA RADHAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 1090/TD | 08/06/2023 | 754 | DAS ENTERPRISE | 595.42 | 251.29 | 42.2 | 65
1115 | PURBA MEDINIPUR | Tamluk Division | PURBA RADHAPUR & ADJOINING MOUZAS , SM/12154 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Purba Radhapur at Bhagwanpur - I Block under Tamluk Division, PHE Dte. | 461/TD | 04/02/2025 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
1116 | PURBA MEDINIPUR | Tamluk Division | GOYALDA & ADJOINING MOUZAS PWSS , SM/12155 | New | Material Requisition To Resource Division | 2438/TD | 16/01/2023 | 0 | Resource Division | 19.42 | 0 | 0 | 0
1117 | PURBA MEDINIPUR | Midnapore Mechanical | GOYALDA & ADJOINING MOUZAS PWSS , SM/12155 | New | Goyalda W/S scheme, TW-I, site tarat(near swasan) application no-2004515964 id-204153046 | BP-2023-24-457 | 21/12/2023 | 0 | WBSEDCL | 3.74 | 0 | 0 | 0
1118 | PURBA MEDINIPUR | Midnapore Mechanical | GOYALDA & ADJOINING MOUZAS PWSS , SM/12155 | New | Goyalda W/S scheme, TW-II, site tarat(near Tower) application no-2004515995 id-204153075 | BP-2023-24-456 | 21/12/2023 | 0 | WBSEDCL | 3.23 | 0 | 0 | 0
1119 | PURBA MEDINIPUR | Tamluk Division | GOYALDA & ADJOINING MOUZAS PWSS , SM/12155 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (4443 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance work for Goyalda PWSS, Palpara PWSS within Patashpur-I Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 879/TD | 01/06/2023 | 761 | SANKHA ENTERPRISE | 1144 | 201.16 | 42.46 | 30
1120 | PURBA MEDINIPUR | Midnapore Mechanical | GOYALDA & ADJOINING MOUZAS PWSS , SM/12155 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOYALDA and ADJOINING MOUJAS, Block Potashpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2321/W/MMD | 29/12/2022 | 824 | S.S.GHORAI | 22.81 | 17.99 | 75.34 | 100
1121 | PURBA MEDINIPUR | Tamluk Division | ABAS BERYA & ADJOINING MOUZAS , SM/12162 | New | Material Requisition To Resource Division | 2729/TD | 06/02/2023 | 0 | Resource Division | 19.06 | 0 | 0 | 0
1122 | PURBA MEDINIPUR | Midnapore Mechanical | ABAS BERYA & ADJOINING MOUZAS , SM/12162 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ABAS BERYA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2346/W/MMD | 29/12/2022 | 180 | EASTERN INDIA SALES & SERVICE | 25.25 | 0 | 0 | 0
1123 | PURBA MEDINIPUR | Tamluk Division | ABAS BERYA & ADJOINING MOUZAS , SM/12162 | New | Material Requisition To Resource Division | 75/TD | 05/01/2024 | 0 | Resource Division | 9.71 | 0 | 0 | 0
1124 | PURBA MEDINIPUR | Midnapore Mechanical | ABAS BERYA & ADJOINING MOUZAS , SM/12162 | New | Quotation Bill for New Service connection at T/W NO-II Of ABASBERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE : BHAGWANPUR C.C.C. Ref. Memo No- 2004940081/QUOT/03 DT. 24-10-2024 Application NO- 2004940081 Application type-New connection CONSUMER ID: 204426079 | C112423541900 | 19/11/2024 | 0 | WBSEDCL | 14.89 | 0 | 0 | 0
1125 | PURBA MEDINIPUR | Midnapore Mechanical | ABAS BERYA & ADJOINING MOUZAS , SM/12162 | New | Quotation Bill for New Service connection at T/W NO-I Of ABASBERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818449/QUOT/03 DT. 12-07-2024 Application NO- 2004818449 Application type-New connection Consumer Id- 204355505 | BP-2024-25-552 | 08/08/2024 | 0 | WBSEDCL | 3.11 | 0 | 0 | 0
1126 | PURBA MEDINIPUR | Tamluk Division | ABAS BERYA & ADJOINING MOUZAS , SM/12162 | New | Sinking tube well ,Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert,CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (1418 nos), Including 2 years of Operation & Maintenance under JJM with allied work of Abas Berya PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 1414/TD | 12/07/2023 | 180 | SUDHAMAY MAJUMDAR | 462.29 | 101.03 | 21.85 | 45
1127 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 3rt Tube Well site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1878/TD | 22/11/2022 | 60 | M/S SOURAV MAHAPATRA | 5.03 | 4.99 | 100 | 100
1128 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube well site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1877/TD | 22/11/2022 | 30 | MODERN CONSTRUCTION | 4.06 | 4.01 | 100 | 100
1129 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Material Requisition To Resource Division | 1013/TD | 08/08/2022 | 0 | Resource Division | 106.84 | 0 | 0 | 0
1130 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Electric quotation for Natshallakhya PWSS Tube Well- III, Zone-I in connection Mukundapur CCC (2004197468) | BP-2022-23-128 | 13/03/2023 | 0 | WBSEDCL | 0.59 | 0 | 0 | 0
1131 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Supply and delivery of CIDF sluice valve,construction of sluice valve chamber ,Canal crossing & pilling work of ground water based Natshal Lakshya (Zone-I) Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(for Part-B) | 803/TD | 30/05/2023 | 30 | BARH CONSTRUCTION | 25.52 | 12.05 | 47.21 | 40
1132 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 2nd Tubewell Site of Natshal Lakshya Zone - I W/S Scheme within Mahishadal Block under Haldia Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 5th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 4th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | 1905/TD | 10/08/2023 | 40 | AQUATECH ENGINEER | 58.34 | 20.45 | 96.25 | 45
1133 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 4th & 5th Tube well of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Development Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 2321/TD | 23/07/2024 | 40 | MANNA COMPUTER | 39.77 | 0 | 0 | 0
1134 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | 211/W/MMD | 10/02/2023 | 180 | S.B.ENTERPRISE | 13.65 | 13.41 | 100 | 75
1135 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Construction of boundary wall in OHR site of Natshal Lakshya (Zone-I) Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-155mtr) | 2254/TD | 05/09/2023 | 45 | PRAMANIK AND ROY CONSTRUCTION | 13.18 | 11 | 100 | 100
1136 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Replacement of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-I Tube Well-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur Districtunder JJM Program under MMD PHE Dte. | 1072/W/MMD | 14/03/2024 | 180 | ECO ENTERPRISE | 10.85 | 10.61 | 100 | 90
1137 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Natshal Lakshya W/S Scheme (Z-I, T/W-I) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 1391/CDD | 19/09/2023 | 204 | DEV AND COMPANY | 21.16 | 19.89 | 100 | 100
1138 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (3772 Nos) work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | 3459/TD | 27/03/2023 | 1007 | SANKHA ENTERPRISE | 609.47 | 0 | 0 | 25
1139 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Construction of boundary wall in 3rd tubewell site of Natshal Lakshya (Zone-I) W/S scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) | 804/TD | 30/05/2023 | 660 | TAPAN BERA | 5.92 | 0 | 0 | 60
1140 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Construction of (5.40 Mtr. X 3.60 Mtr.) Chlorine Room including Plinth Protection at Natshal Lakshya Store within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 204/TD | 15/01/2025 | 160 | BHOWMIK & SONS | 6.18 | 0 | 0 | 80
1141 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11473 | Augmentation | Construction of 2 nos (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 4th Tube Well site & 5th Tube well site, Laying of Rising main with interconnection, and Supplying of D.I. Specials for Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1924/TD | 07/06/2024 | 319 | TAPAN BERA | 22.25 | 0 | 0 | 50
1142 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme , SM/11206 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bethkundu Water Supply Scheme under Tamluk Division, PHE Dte. | 1543/TD | 11/01/2022 | 20 | HORIZEN | 4.88 | 4.88 | 100 | 100
1143 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme , SM/11206 | Augmentation | Material Requisition To Resource Division | 1673/TD | 03/11/2022 | 0 | Resource Division | 48.38 | 0 | 0 | 0
1144 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme , SM/11206 | Augmentation | Culvert, Approach Road and Guard wall cum Boundery wall including land development at Headwork site of Betkundu Pwss under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | 2367/TD | 12/09/2023 | 60 | BABUL DAS | 55.26 | 22.24 | 40.24 | 41
1145 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme , SM/11206 | Augmentation | Laying of Leftout Pipeline, Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement at 4th Tube Well site, Construction new Boundary Wall at 4th Tube well site and Laying of proposed Rising main line and inter connection at Betkundu Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 979/TD | 13/03/2024 | 45 | RAJ KUMAR SINGHA | 111.15 | 98.53 | 88.65 | 10
1146 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme , SM/11206 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 900 cum RCC OHR at Betkundu PWSS at Mahishadal Block under Tamluk Division, PHE Dte. | 2087/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 0
1147 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme , SM/11206 | Augmentation | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 4th Tube well Site of Betkundu Water Supply Scheme within mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 2051/TD | 25/08/2023 | 25 | DEV & COMPANY | 20.17 | 18.97 | 100 | 100
1148 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground water Based Betkundu Water Supply Scheme , SM/11206 | Augmentation | Quotation for net billing meter at Betkundu w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (Con ID - 222016853 & Application No.- 2004450537) | BP-2023-24-674 | 15/02/2024 | 0 | WBSEDCL | 0.42 | 0 | 0 | 0
1149 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground water Based Betkundu Water Supply Scheme , SM/11206 | Augmentation | QUATATION BILL FOR BETKUNDU Water Supply scheme Tube Well no.-III Mahishadal CCC Application No.-2004625358 Ref ID.-204232822 Block-Mahishadal | BP-2023-24-889 | 22/03/2024 | 0 | WBSEDCL | 4.84 | 0 | 0 | 0
1150 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme , SM/11206 | Augmentation | Augmentation of ground water based Betkundu Water Supply Scheme by providing Laying of Distribution pipe line, FHTC work, Construction of R.C.C. Over Head Reservoir of capacity 900 cum and staging height 20.00 mtr. and Sub-Soil Investigation within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1577/TD | 14/10/2022 | 930 | RAJ KUMAR SINGHA | 1014.31 | 744.56 | 73.41 | 68
1151 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground water Based Betkundu Water Supply Scheme , SM/11206 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground water Based Betkundu Water Supply Scheme, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 847/W/MMD | 24/03/2023 | 896 | MAA BHABOTARINE ENTERPRISE | 27.18 | 0 | 0 | 60
1152 | PURBA MEDINIPUR | Tamluk Division | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12399 | New | Material Requisition To Resource Division | 2993/TD | 27/02/2023 | 0 | Resource Division | 2.69 | 0 | 0 | 0
1153 | PURBA MEDINIPUR | Midnapore Mechanical | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12399 | New | Quotation Bill for New Service connection at T/W NO-I Of BARAHAT W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004769741/QUOT/03 DT. 10-06-2024 MEMO NO: AMR/PHE/171 DT. 10-06-2024 Application NO- 2004769741 Application type-New connection Consumer Id- 204327215 | BP-2024-25-336 | 25/06/2024 | 0 | WBSEDCL | 5 | 0 | 0 | 0
1154 | PURBA MEDINIPUR | Midnapore Mechanical | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12399 | New | Quotation Bill for New Service connection at T/W NO-II Of BARAHAT W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004769769/QUOT/03 DT. 10-06-2024 MEMO NO: AMR/PHE/170 DT. 10-06-2024 Application NO- 2004769769 Application type-New connection Consumer Id- 204327222 | BP-2024-25-335 | 25/06/2024 | 0 | WBSEDCL | 1.2 | 0 | 0 | 0
1155 | PURBA MEDINIPUR | Tamluk Division | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12399 | New | Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert, CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (1808 nos) under JJM with allied work for Barahat & its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 2481/TD | 26/09/2023 | 797 | MAA ANANDAMAYEE | 547.32 | 149.65 | 27.34 | 35
1156 | PURBA MEDINIPUR | Midnapore Mechanical | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12399 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARAHAT and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2425/W/MMD | 31/12/2022 | 882 | DEY ENTERPRISE | 22.8 | 0 | 0 | 85
1157 | PURBA MEDINIPUR | Tamluk Division | PADIMA AND ADJOINING MOUJAS PWSS , SM/12430 | New | Material Requisition To Resource Division | 2998/TD | 27/02/2023 | 0 | Resource Division | 23.63 | 0 | 0 | 0
1158 | PURBA MEDINIPUR | Tamluk Division | PADIMA AND ADJOINING MOUJAS PWSS , SM/12430 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Padima PWSS at Ramnagar - I Block under Tamluk Division,PHE Dte. | 205/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
1159 | PURBA MEDINIPUR | Tamluk Division | PADIMA AND ADJOINING MOUJAS PWSS , SM/12430 | New | Material Requisition To Resource Division | 99/TD | 05/01/2024 | 0 | Resource Division | 5.91 | 0 | 0 | 0
1160 | PURBA MEDINIPUR | Midnapore Mechanical | PADIMA AND ADJOINING MOUJAS PWSS , SM/12430 | New | PADIMA W/S SCHEME T/W-I Application No.-2004566513 Ref.-204194520 | BP-2023-24-613 | 07/02/2024 | 0 | WBSEDCL | 6.31 | 0 | 0 | 0
1161 | PURBA MEDINIPUR | Midnapore Mechanical | PADIMA AND ADJOINING MOUJAS PWSS , SM/12430 | New | Quotation Bill for New Service connection at T/W NO-II Of PADIMA W/S Scheme under MMD, PHE, Dte. Block- Ramnagar-I, DIGHA C.C.C. Ref. Memo No- 2004626606/QUOT/03 DT. 04-03-2024 Application NO- 2004626606 Application type-New connection CONSUMMER ID- 204233354 | BP-2023-24-804 | 11/03/2024 | 0 | WBSEDCL | 7.74 | 0 | 0 | 0
1162 | PURBA MEDINIPUR | Tamluk Division | PADIMA AND ADJOINING MOUJAS PWSS , SM/12430 | New | Sinking of Tube Well, Rising main ,Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 150Cum OHR ( Intze type with pile foundatio ) Pipe Carrying canal crossing Structure & Accommodate FHTC ( 960 Nos) Including 2 years of Operation & Maintenance under JJM with allied work for Padima & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 1987/TD | 21/08/2023 | 864 | ONKAR ENTERPRISE | 339.12 | 210.05 | 61.94 | 50
1163 | PURBA MEDINIPUR | Midnapore Mechanical | PADIMA AND ADJOINING MOUJAS PWSS , SM/12430 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PADIMA and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 548/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 21.62 | 19.87 | 93.08 | 100
1164 | PURBA MEDINIPUR | Tamluk Division | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS , SM/12293 | New | Material Requisition To Resource Division | 2967/TD | 27/02/2023 | 0 | Resource Division | 35.37 | 0 | 0 | 0
1165 | PURBA MEDINIPUR | Tamluk Division | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS , SM/12293 | New | Material Requisition To Resource Division | 633/W | 20/02/2024 | 0 | Resource Division | 8.46 | 0 | 0 | 0
1166 | PURBA MEDINIPUR | Tamluk Division | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS , SM/12293 | New | Bill for damage of Road flank / hard shoulder due to cutting of hard shoulder and road flank on Itaberia Mugberia Road from 1.25 Km. To 3.10 Km. for laying water pipe line of Dakshin Patherbaria PWSS. | BP-2024-25-494 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.12 | 0 | 0 | 0
1167 | PURBA MEDINIPUR | Tamluk Division | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS , SM/12293 | New | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1373 nos) under JJM with allied work of DAKSHIN PATHAR BERYA AND IT'S ADJOINING MOUJAS PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 555/TD | 12/05/2023 | 180 | PATHIK PABAN NANDI | 460.76 | 167.47 | 36.35 | 50
1168 | PURBA MEDINIPUR | Central Drilling | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS , SM/12293 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1169 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS , SM/12293 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
1170 | PURBA MEDINIPUR | Tamluk Division | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS , SM/12293 | New | Sinking of (2 nos.) 250 x 150mm Dia and 230mtr deep tubewell Drilling by Direct Rotary method with 150mm dia. uPVC Strainer of 30mtr length all complete including cost of materials for 1st & 2nd Tubewell of Dakshin Patharberya PWSS under Bhagwanpur-II Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, Purba Medinipur PHE Dte | 457/TD | 04/02/2025 | 40 | B. K. ENTERPRISE | 26.35 | 0 | 0 | 0
1171 | PURBA MEDINIPUR | Tamluk Division | GATHRA AND ADJOINING MOUJAS PWSS , SM/12299 | New | Material Requisition To Resource Division | 2468/TD | 16/01/2023 | 0 | Resource Division | 17.41 | 0 | 0 | 0
1172 | PURBA MEDINIPUR | Midnapore Mechanical | GATHRA AND ADJOINING MOUJAS PWSS , SM/12299 | New | Electric Quotation for GOTHRA Water Supply Scheme , (Ref. ID-204075850) | BP-2023-24-238 | 12/09/2023 | 0 | WBSEDCL | 3.98 | 0 | 0 | 0
1173 | PURBA MEDINIPUR | Midnapore Mechanical | GATHRA AND ADJOINING MOUJAS PWSS , SM/12299 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GATHRA and ADJOINING MOUJAS, Block Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2366/W/MMD | 31/12/2022 | 180 | ABHIJIT BASU | 23.69 | 11.08 | 46.75 | 35
1174 | PURBA MEDINIPUR | Tamluk Division | GATHRA AND ADJOINING MOUJAS PWSS , SM/12299 | New | Work order for installation of 18 nos Dispaly Board at different PWSS works site under Tamluk Sub-Division of Tamluk Division PHE Dte. | 2279/TD | 18/07/2024 | 7 | GLOBAL TRADE | 3.95 | 3.78 | 100 | 100
1175 | PURBA MEDINIPUR | Tamluk Division | GATHRA AND ADJOINING MOUJAS PWSS , SM/12299 | New | Land development work at Headwork Site of Gathra Water Supply Scheme within Sahid Matangini Development Block under Tamluk Sadar Sub-Division of Tamluk Division, PHE Dte. | 1925/TD | 07/06/2024 | 14 | S. P. ENTERPRISE (GSTIN- 19FLFPR7861R1ZS) | 4.23 | 4.18 | 100 | 100
1176 | PURBA MEDINIPUR | Tamluk Division | GATHRA AND ADJOINING MOUJAS PWSS , SM/12299 | New | Material Requisition To Resource Division | 129/TD | 05/01/2024 | 0 | Resource Division | 11.19 | 0 | 0 | 0
1177 | PURBA MEDINIPUR | Midnapore Mechanical | GATHRA AND ADJOINING MOUJAS PWSS , SM/12299 | New | Quotation Bill for Gathra W/S Scheme T/W-II Application No=2005003708 Reference ID=204470377 |  | 18/12/2024 | 0 | WBSEDCL | 3.06 | 0 | 0 | 0
1178 | PURBA MEDINIPUR | Midnapore Mechanical | GATHRA AND ADJOINING MOUJAS PWSS , SM/12299 | New | Gathra W/S scheme H/W site. Application No.-100000094421 Ref.-860286461 | BP-2023-24-544 | 15/01/2024 | 0 | WBSEDCL | 0.34 | 0 | 0 | 0
1179 | PURBA MEDINIPUR | Tamluk Division | GATHRA AND ADJOINING MOUJAS PWSS , SM/12299 | New | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1816 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of GATHRA PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 218/TD | 17/04/2023 | 900 | TAPAS SANTRA | 495.61 | 270.77 | 56.23 | 75
1180 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I , SM/12489 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | 1802/TD | 08/02/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.79 | 3.3 | 100 | 100
1181 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I , SM/12489 | Augmentation | Material Requisition To Resource Division | 1670/TD | 03/11/2022 | 0 | Resource Division | 95.79 | 0 | 0 | 0
1182 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I , SM/12489 | Augmentation | Material Requisition To Resource Division | 607/TD | 17/05/2023 | 0 | Resource Division | 15.99 | 0 | 0 | 0
1183 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I , SM/12489 | Augmentation | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-I Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-I Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-I Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 2243/TD | 29/12/2022 | 40 | R K CONSTRUCTION | 39.67 | 12.07 | 30.42 | 0
1184 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I , SM/12489 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 0 | 50
1185 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I , SM/12489 | Augmentation | Laying of Left-Out portion uPVC Pipe line, Construction of New Pump House, Boundary Wall and others allied works for 3rd Tube well site and Repair & renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site and 2nd Tube well site at mouza- Kismat Bajkul,J.L- No -156, under Bajkul Zone-I Water Supply Scheme. ( Augmentation) in Bhagabanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 2184/TD | 01/09/2023 | 636 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 65.41 | 0 | 0 | 70
1186 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I , SM/12489 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk and replacement Tube well at BAJKUL zone I Water supply scheme, BHAGWANPUR - II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 1077/W/MMD | 15/03/2024 | 180 | SOUMEN ELECTRIC | 24.86 | 8.41 | 33.82 | 35
1187 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I , SM/12489 | Augmentation | Quotation money for shifting of 11 KV OH Henria Feeder at Bajkul for Bajukl Zone-I PWSS under Tamluk Division, PHE Dte. | BP-2023-24-744 | 04/01/2024 | 0 | WBSEDCL | 2.08 | 0 | 0 | 0
1188 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I , SM/12489 | Augmentation | Laying of Distribution pipe line to accommodate FHTC(2596 Nos) with construction of R.C.C. Elevated Reservoir of capacity 400 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Bajkul Zone - I Water Supply Scheme within Bhagabanpur- II Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | 1892/TD | 24/11/2022 | 1103 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 440.22 | 264.92 | 60.18 | 78
1189 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I , SM/12489 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I, Block Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 818/W/MMD | 24/03/2023 | 180 | EMCON | 11.83 | 11 | 92.95 | 100
1190 | PURBA MEDINIPUR | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Material Requisition To Resource Division | 2464/TD | 16/01/2023 | 0 | Resource Division | 24.12 | 0 | 0 | 0
1191 | PURBA MEDINIPUR | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Laying distribution pipe line, & Accommodate FHTC (124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-E ) | 3180/TD | 10/03/2023 | 15 | ANUPAM CONSTRUCTION | 19.85 | 12.06 | 60.78 | 62
1192 | PURBA MEDINIPUR | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Laying distribution pipe line, & Accommodate FHTC ( 538 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C) | 3179/TD | 10/03/2023 | 1117 | LOKENATH ENTERPRISES | 84.26 | 54.11 | 64.21 | 65
1193 | PURBA MEDINIPUR | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Laying distribution pipe line, & Accommodate FHTC (124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-F ) | 3181/TD | 10/03/2023 | 15 | ANUPAM CONSTRUCTION | 19.87 | 12.08 | 60.82 | 60
1194 | PURBA MEDINIPUR | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Laying distribution pipe line, & Accommodate FHTC ( 124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-H ) | 3182/TD | 10/03/2023 | 15 | MAHAMAYA TIMBER AND CONSTRUCTION | 6.81 | 5.92 | 87 | 95
1195 | PURBA MEDINIPUR | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Laying distribution pipe line, & Accommodate FHTC ( 538 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-D) | 1839/TD | 08/08/2023 | 40 | MRINAL KANTI PRADHAN | 84.49 | 52.16 | 61.74 | 65
1196 | PURBA MEDINIPUR | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Laying of Balance Distribution HDPE Pipe Line(225 mm dia) for Islampur Piped Water Supply Scheme due to Revised drawing within Ramnagar-II Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. | 2872/TD | 17/11/2023 | 20 | A. K. SIKDAR | 9.42 | 9.36 | 99.43 | 99
1197 | PURBA MEDINIPUR | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Material Requisition To Resource Division | 103/TD | 05/01/2024 | 0 | Resource Division | 13 | 0 | 0 | 0
1198 | PURBA MEDINIPUR | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Laying distribution pipe line, & Accommodate FHTC ( 124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-G ) | 173/TD | 11/04/2023 | 870 | AYSAN KHAN | 19.97 | 0 | 0 | 60
1199 | PURBA MEDINIPUR | Central Drilling | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 50.75 | 94.03 | 11
1200 | PURBA MEDINIPUR | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( with pile foundatio ) & Accommodate FHTC ( 414 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-A) | 1098/TD | 08/06/2023 | 812 | FIROZ KHAN | 199.26 | 0 | 0 | 30
1201 | PURBA MEDINIPUR | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 238 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-B) | 563/TD | 12/05/2023 | 839 | LOKENATH ENTERPRISES | 119.04 | 87.21 | 73.26 | 60
1202 | PURBA MEDINIPUR | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS , SM/13683 | New | Canal crossing Structure for laying of Distribution line from Sapua Bridge towards Chaulkhola parallel of NH-116B for Islampur & Its Adjoining Mouzas water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | 3538/TD | 13/11/2024 | 270 | AYSAN KHAN | 21.61 | 0 | 0 | 100
1203 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Material Requisition To Resource Division | 2475/TD | 16/01/2023 | 0 | Resource Division | 17 | 0 | 0 | 0
1204 | PURBA MEDINIPUR | Midnapore Mechanical | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Electric Quotation for URDHABMAL Water Supply Scheme T/W-I, (Ref. ID-204076039) | BP-2023-24-244 | 12/09/2023 | 0 | WBSEDCL | 15.45 | 0 | 0 | 0
1205 | PURBA MEDINIPUR | Midnapore Mechanical | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Electric Quotation for URDHABMAL Water Supply Scheme T/W-II, (Ref. ID-204076027) | BP-2023-24-243 | 12/09/2023 | 0 | WBSEDCL | 3.36 | 0 | 0 | 0
1206 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (260 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | 3035/TD | 27/02/2023 | 60 | R K CONSTRUCTION | 97.19 | 26.22 | 26.98 | 30
1207 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (140 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | 3036/TD | 27/02/2023 | 30 | CEM ENGINEERS CO-OPERATIVE SOCIETY LTD. | 39 | 22.77 | 58.4 | 65
1208 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(137 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-H) | 3037/TD | 27/02/2023 | 20 | M/S BLUE BIRD | 15.92 | 0 | 0 | 0
1209 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(50 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-I) | 3038/TD | 27/02/2023 | 20 | SAYAN MAITY | 20.13 | 17.36 | 86.25 | 87
1210 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-J) | 3039/TD | 27/02/2023 | 20 | M/S BLUE BIRD | 15.99 | 13.44 | 84.05 | 85
1211 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (120nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-K) | 3040/TD | 27/02/2023 | 20 | SUDIP MANNA | 15.47 | 9.32 | 60.27 | 65
1212 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(130nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-L) | 3041/TD | 27/02/2023 | 20 | SAYAN MAITY | 19.92 | 14.14 | 71 | 72
1213 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(140 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-F) | 3559/TD | 29/03/2023 | 632 | S. B. ASSOCIATES | 57.43 | 46.53 | 81.02 | 85
1214 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (140 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | 170/TD | 10/04/2023 | 30 | SK MAIDUL ISLAM | 40.83 | 32.18 | 78.81 | 78
1215 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (450 nos) work and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | 526/TD | 11/05/2023 | 180 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 172.54 | 37 | 21.44 | 22
1216 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (230nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | 3560/TD | 29/03/2023 | 632 | S. B. ASSOCIATES | 67.13 | 40.57 | 60.43 | 65
1217 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Material Requisition To Resource Division | 641/W | 20/02/2024 | 0 | Resource Division | 11.07 | 0 | 0 | 0
1218 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Urddhabmal Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Urddhabmal Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 3344/TD | 22/03/2023 | 25 | M R ENTERPRISE | 30.86 | 0 | 0 | 50
1219 | PURBA MEDINIPUR | Midnapore Mechanical | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for URDDHABMAL and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 562/W/MMD | 20/03/2023 | 895 | M/S B.M. ELECTRICAL | 22.81 | 16.19 | 71.01 | 70
1220 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Urddhabmal Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 2061/TD | 24/06/2024 | 20 | KISHORE GHOSH | 14.87 | 0 | 0 | 0
1221 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Land Development work at Head work site & 2nd Tube well site of Urddhabmal Water supply Scheme within Sutahata Develompent Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 1008/HSD, | 04/10/2024 | 220 | TARUN KHATUA | 4.85 | 0 | 0 | 50
1222 | PURBA MEDINIPUR | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS , SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (260 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) (Balance Part) | 2902/TD | 10/09/2024 | 240 | TARUN KHATUA | 68.16 | 0 | 0 | 50
1223 | PURBA MEDINIPUR | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS , SM/12171 | New | Material Requisition To Resource Division | 2961/TD | 27/02/2023 | 0 | Resource Division | 33.37 | 0 | 0 | 0
1224 | PURBA MEDINIPUR | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS , SM/12171 | New | Laying Distribution pipe line & Accommodate FHTC (330 nos) under JJM with allied work of MANIKJOR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-C) | 3465/TD | 27/03/2023 | 45 | SUBHENDU HAZRA | 76.59 | 47.28 | 61.73 | 60
1225 | PURBA MEDINIPUR | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS , SM/12171 | New | Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (511 nos) under JJM with allied work of Manikjor PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-A) | 1050/TD | 07/06/2023 | 180 | TARUN KOLEY | 222.99 | 45.72 | 20.5 | 22
1226 | PURBA MEDINIPUR | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS , SM/12171 | New | Material Requisition To Resource Division | 625/W | 20/02/2024 | 0 | Resource Division | 12.23 | 0 | 0 | 0
1227 | PURBA MEDINIPUR | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS , SM/12171 | New | Laying distribution pipe line & Accommodate FHTC ( 180nos) under JJM with allied work of MANIKJOR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - D) | 3466/TD | 27/03/2023 | 302 | SUBRATA KUMAR BERA | 28.31 | 16.28 | 57.52 | 60
1228 | PURBA MEDINIPUR | Central Drilling | MANIKJOR AND ADJOINING MOUJAS PWSS , SM/12171 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1229 | PURBA MEDINIPUR | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS , SM/12171 | New | Pump House, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (850 nos) under JJM with allied work of Manikjor PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | 536/TD | 12/05/2023 | 568 | GIRI CONSTRUCTION | 191.14 | 78.24 | 40.93 | 42
1230 | PURBA MEDINIPUR | Midnapore Mechanical | MANIKJOR AND ADJOINING MOUJAS PWSS , SM/12171 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
1231 | PURBA MEDINIPUR | Midnapore Mechanical | MANIKJOR AND ADJOINING MOUJAS PWSS , SM/12171 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
1232 | PURBA MEDINIPUR | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS , SM/12171 | New | Sinking of (2 nos.) 250 x 150mm Dia and 230mtr deep tubewell Drilling by Direct Rotary method with 150mm dia. uPVC Strainer of 30mtr length all complete including cost of materials for 1st & 2nd Tubewell of Manikjore PWSS under Bhagwanpur-II Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, Purba Medinipur PHE Dte | 458/TD | 04/02/2025 | 40 | B. K. ENTERPRISE | 26.18 | 0 | 0 | 0
1233 | PURBA MEDINIPUR | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS , SM/12173 | New | Material Requisition To Resource Division | 2960/TD | 27/02/2023 | 0 | Resource Division | 33.17 | 0 | 0 | 0
1234 | PURBA MEDINIPUR | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS , SM/12173 | New | Laying distribution pipe line, Pump House & Accommodate FHTC (315 nos), Boundary Wall under JJM with allied work for PANCH BAJARI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-C) | 135/TD | 10/04/2023 | 45 | SOUMYA ENTERPRISE | 53.18 | 34.5 | 64.89 | 67
1235 | PURBA MEDINIPUR | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS , SM/12173 | New | Instalation of display Board at different work site of Panch Bajari, Manikjor, Bahadurpur, Kayemgerya, & Adjoining Moujas New PWSS in Bhagawanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2327/CSD | 29/12/2023 | 15 | M/S. NEW DINDA ENTERPRISE | 0.83 | 0.83 | 100 | 100
1236 | PURBA MEDINIPUR | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS , SM/12173 | New | Material Requisition To Resource Division | 624/W | 20/02/2024 | 0 | Resource Division | 6.25 | 0 | 0 | 0
1237 | PURBA MEDINIPUR | Midnapore Mechanical | PANCH BAJARI & ADJOINING MOUJAS PWSS , SM/12173 | New | Quotation Bill for New Service connection at T/W NO-I Of Panchbajari W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004601878/QUOT/03 DT. 15-02-2024 Quotation due date-14.02.2025 Application NO- 2004601878 Application type-New connection Reference Id- 204217833 | BP-2023-24-793 | 06/03/2024 | 0 | WBSEDCL | 4.1 | 0 | 0 | 0
1238 | PURBA MEDINIPUR | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS , SM/12173 | New | Laying distribution pipe line,Pump House, Accommodate FHTC & Boundary Wall (400 nos) under JJM with allied work for PANCH BAJARI PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-B) | 134/TD | 10/04/2023 | 719 | JAI BHARAT COMMERCIAL CORPORATION | 78.91 | 0 | 0 | 65
1239 | PURBA MEDINIPUR | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS , SM/12173 | New | Laying distribution pipe line & Accommodate FHTC (100 nos) under JJM with allied work for PANCH BAJARI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-D) | 136/TD | 10/04/2023 | 765 | SUDIP MANNA | 19.43 | 10.36 | 53.34 | 60
1240 | PURBA MEDINIPUR | Central Drilling | PANCH BAJARI & ADJOINING MOUJAS PWSS , SM/12173 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 50.2 | 92.93 | 11
1241 | PURBA MEDINIPUR | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS , SM/12173 | New | Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (200 nos) under JJM with allied work for PANCH BAJARI PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-A) | 1755/TD | 01/08/2023 | 784 | DIPAK ROY | 159.88 | 49.25 | 30.81 | 50
1242 | PURBA MEDINIPUR | Midnapore Mechanical | PANCH BAJARI & ADJOINING MOUJAS PWSS , SM/12173 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
1243 | PURBA MEDINIPUR | Tamluk Division | Tilkhoja & Adjoining mouzas , SM/12133 | New | Material Requisition To Resource Division | 2432/TD | 16/01/2023 | 0 | Resource Division | 27.95 | 0 | 0 | 0
1244 | PURBA MEDINIPUR | Midnapore Mechanical | Tilkhoja & Adjoining mouzas , SM/12133 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Tilkhoja and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2324/W/MMD | 29/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 0 | 0 | 60
1245 | PURBA MEDINIPUR | Tamluk Division | Tilkhoja & Adjoining mouzas , SM/12133 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Tilkhoja PWSS at Moyna Block under Tamluk Division,PHE Dte. | 198/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
1246 | PURBA MEDINIPUR | Tamluk Division | Tilkhoja & Adjoining mouzas , SM/12133 | New | Material Requisition To Resource Division | 1570/TD | 23/04/2024 | 0 | Resource Division | 14.36 | 0 | 0 | 0
1247 | PURBA MEDINIPUR | Midnapore Mechanical | Tilkhoja & Adjoining mouzas , SM/12133 | New | Quotation for Tilkhoja w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608980, Ref ID-204222618) | BP-2023-24-852 | 16/03/2024 | 0 | WBSEDCL | 2.97 | 0 | 0 | 0
1248 | PURBA MEDINIPUR | Midnapore Mechanical | Tilkhoja & Adjoining mouzas , SM/12133 | New | Quotation for new service connection at Tlkhoja w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. ( App ID 2004685657, Con ID 204277587) | BP-2024-25-123 | 05/05/2024 | 0 | WBSEDCL | 9.91 | 0 | 0 | 0
1249 | PURBA MEDINIPUR | Tamluk Division | Tilkhoja & Adjoining mouzas , SM/12133 | New | Installation of display Board at 5 nos {1. TILKHOJA PWSS,( PUMP HOUSE -1 &2) 2. RADHABALLAVCHAK PWSS ( PUMP HOUSE -1 &2), 3. GOBARDHAN PWSS( PUMP HOUSE -1), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 61/RWS/TSD | 06/05/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
1250 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11472 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Natshal Lakshya Water Supply Scheme (Zone- I) under Tamluk Division, PHE Dte. | 49/TD | 05/04/2022 | 20 | RADIANT | 5.76 | 5.75 | 100 | 100
1251 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11472 | Augmentation | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part -C) | 1278/TD | 12/09/2022 | 90 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 416.22 | 307.87 | 73.97 | 80
1252 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11472 | Augmentation | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part -B) | 1288/TD | 13/09/2022 | 60 | BARH CONSTRUCTION | 205.99 | 124.95 | 60.66 | 65
1253 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11472 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | 854/W/MMD | 24/03/2023 | 180 | SUBHASIS ROY | 27.33 | 0 | 0 | 0
1254 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11472 | Augmentation | Material Requisition To Resource Division | 1014/TD | 08/08/2022 | 0 | Resource Division | 15.11 | 0 | 0 | 0
1255 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11472 | Augmentation | Material Requisition To Resource Division | 1255/TD | 12/09/2022 | 0 | Resource Division | 50.47 | 0 | 0 | 0
1256 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11472 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 1st Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1249/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 83.68 | 19.25 | 100 | 75
1257 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11472 | Augmentation | Quotation for new application at Natshallakhya Zone I PH IV in the district of Purba Medinipur under MMD PHE Dte. ( App No. 20046922155, Ref ID 204281189) | BP-2024-25-191 | 24/05/2024 | 0 | WBSEDCL | 4.12 | 0 | 0 | 0
1258 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11472 | Augmentation | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (3772 Nos) work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | 3459/TD | 27/03/2023 | 1007 | SANKHA ENTERPRISE | 609.47 | 117.91 | 31.01 | 25
1259 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Asadtalia Water Supply Scheme under Tamluk Division, PHE Dte. | 1197/TD | 02/12/2021 | 20 | RADIANT | 3.95 | 3.82 | 100 | 100
1260 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Providing Drilling crew and other allied works for construction of TW (300mm x 200mm x280mtrs) by utilising Departmental machinery for Sutahata Block under Purba Midnapur, CDD,PHE Dte. | 106/CDD | 12/04/2022 | 30 | MENAKA ENTERPRISE | 18.7 | 18.33 | 100 | 100
1261 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 270 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR ASADTALIA W/S SCHEME (TW-I), SUTAHATA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 15/CDD | 04/04/2022 | 30 | MENAKA ENTERPRISE | 18.53 | 17.39 | 100 | 100
1262 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT ASADTALIA PWSS, SUTAHATA BLOCK UNDER CDD, PHE DTE. | 225/CMSD-I | 20/06/2022 | 15 | MENAKA ENTERPRISE | 5 | 5 | 100 | 100
1263 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | PROVIDING TUBE WELL MATERIALS WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT ASADTALIA W/S SCH (TW-II) UNDER CDD, PHE DTE. | 254/CMSD-I | 23/06/2022 | 10 | MENAKA ENTERPRISE | 0.93 | 0.3 | 100 | 100
1264 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT ASADTALIA PWSS, SUTAHATA BLOCK UNDER CDD, HE DTE. | 224/CMSD-I (D) | 20/06/2022 | 15 | MENAKA ENTERPRISE | 4.96 | 4.63 | 100 | 100
1265 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER MATERIALS & WORKS FOR CONSTRUCTION OF TUBE WELL AT ASADTALIA PWSS, SUTAHATA BLOCK UNDER CDD, PHE DTE. | 226/CMSD-I | 20/06/2022 | 15 | MENAKA ENTERPRISE | 4.98 | 4.44 | 100 | 100
1266 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well I under Asadtaliya water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2116/W/MMD | 28/11/2022 | 120 | BALAJI CONSTRUCTION | 11.24 | 10.54 | 93.72 | 100
1267 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well II under Asadtaliya water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2117/W/MMD | 28/11/2022 | 120 | SHOVAN KUMAR DAS | 11.37 | 10.65 | 93.67 | 100
1268 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments at newly sunk replacement tube well-II under Asadtaliya w/s scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | 578/HESD | 04/08/2023 | 7 | SHOVAN KUMAR DAS | 0.13 | 0 | 0 | 0
1269 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments at newly sunk replacement tube well-I under Asadtaliya w/s scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | 579/HESD | 04/08/2023 | 7 | BALAJI CONSTRUCTION | 0.19 | 0 | 0 | 0
1270 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Supply & delivery of different dia CIDF Sluice Valve for Asadtalia Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. | 2186/TD | 17/03/2022 | 20 | BAGLAMUKHI SECURITY SERVICE | 3.61 | 3.61 | 100 | 100
1271 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2nd tube well site of Asadtalia Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1068/TD | 22/08/2022 | 45 | BUNBA CONSTRUCTION | 3.95 | 3.51 | 100 | 100
1272 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | PROVIDING TUBEWELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMODGHATA W/S SCH TW-II, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 378/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 5 | 2.23 | 100 | 0
1273 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0.01 | 100 | 0
1274 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Material Requisition To Resource Division | 1263/TD | 13/12/2021 | 0 | Resource Division | 11.63 | 0 | 0 | 0
1275 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Material Requisition To Resource Division | 1868/TD | 17/02/2022 | 0 | Resource Division | 10.22 | 0 | 0 | 0
1276 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Quotation payment for shifting of 11 KV line at Gobindapur on Full deposit of scheme of Asadtalia PWSS of Sutathat Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | BP-2023-24-282 | 17/08/2023 | 0 | WBSEDCL | 2.92 | 0 | 0 | 0
1277 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Augmentation of ground water based Asadtalia Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1815/TD | 11/02/2022 | 1145 | HARIPADA PATTANAYAK | 303.25 | 242.47 | 79.96 | 85
1278 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09337 | Augmentation | Laying Rising main, laying left out pipe line, canal crossing and supporting work with Drum Sheet walling and Earth filling in Asadtalia Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | 2168/TD | 19/12/2022 | 30 | HARIPADA PATTANAYAK | 64.43 | 54.65 | 84.83 | 100
1279 | PURBA MEDINIPUR | Tamluk Division | FATEPUR AND ADJOINING MOUJAS PWSS , SM/13687 | New | Material Requisition To Resource Division | 2697/TD | 06/02/2023 | 0 | Resource Division | 4.51 | 0 | 0 | 0
1280 | PURBA MEDINIPUR | Tamluk Division | FATEPUR AND ADJOINING MOUJAS PWSS , SM/13687 | New | Drum Sheet walling, road restoration for distribution pipe line( for FHTC) & Accommodate FHTC (82 Nos) under JJM with allied work for FATEPUR PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 3722/TD | 04/12/2024 | 30 | MAITY CONSTRUCTION | 14.16 | 0 | 0 | 0
1281 | PURBA MEDINIPUR | Tamluk Division | FATEPUR AND ADJOINING MOUJAS PWSS , SM/13687 | New | Material Requisition To Resource Division | 107/TD | 05/01/2024 | 0 | Resource Division | 2.32 | 0 | 0 | 0
1282 | PURBA MEDINIPUR | Midnapore Mechanical | FATEPUR AND ADJOINING MOUJAS PWSS , SM/13687 | New | Fatepur W/S scheme TW-II Application No.-2004521 Ref.-204156067 | BP-2023-24-574 | 18/01/2024 | 0 | WBSEDCL | 0.26 | 0 | 0 | 0
1283 | PURBA MEDINIPUR | Midnapore Mechanical | FATEPUR AND ADJOINING MOUJAS PWSS , SM/13687 | New | Fatepur W/S scheme PH-I Application no.-2004511512 ref.-204147631 | BP-2023-24-468 | 27/12/2023 | 0 | WBSEDCL | 0.86 | 0 | 0 | 0
1284 | PURBA MEDINIPUR | Midnapore Mechanical | FATEPUR AND ADJOINING MOUJAS PWSS , SM/13687 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for FATEPUR and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 570/W/MMD | 20/03/2023 | 539 | DEY ENTERPRISE | 11.98 | 10.88 | 90.85 | 100
1285 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 , SM/14836 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | 1931./TD | 28/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.46 | 100 | 100
1286 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 , SM/14836 | Augmentation | Material Requisition To Resource Division | 2994/TD | 29/11/2023 | 0 | Resource Division | 1.29 | 0 | 0 | 0
1287 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 , SM/14836 | Augmentation | Material Requisition To Resource Division | 2063/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0 | 0
1288 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 , SM/14836 | Augmentation | Quotation for new service connection at Zone-III,TW-II of Chirulia Chatla ws scheme under MMD, PHE Dte. Block-Egra-I, Chopalia CCC. App. no-2004635402, Con ID-204242995 | Bp-2023-24-915 | 28/03/2024 | 0 | WBSEDCL | 3.69 | 0 | 0 | 0
1289 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 , SM/14836 | Augmentation | Chirulia Chatla W/S scheme Zone-III, T/W-I Application.-2004553660 Ref.-204183515 | BP-2023-24-575 | 18/01/2024 | 0 | WBSEDCL | 4.96 | 0 | 0 | 0
1290 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 , SM/14836 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Piped Water Supply Scheme for Chirulia-Chatla Zone-3 Egra I Block under JJM Program under MMD PHE Dte. | 892/W/MMD | 27/03/2023 | 888 | SHREE BISHNU CONSTRUCTION | 23.68 | 0 | 0 | 52
1291 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 , SM/14836 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 210 Nos) under JJM with allied work for Chirulia-Chatla (Zone-III) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | 1089/TD | 08/06/2023 | 753 | AJIT KUMAR SOM | 233.68 | 78.46 | 33.57 | 85
1292 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/14845 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at 4th TW site for Augmentation of Mukutshila Zone-II PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.)For Low Land. | 1421/TD | 12/07/2023 | 30 | M/S. NEW DINDA ENTERPRISE | 6.93 | 0 | 0 | 0
1293 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/14845 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | 474/TD | 10/05/2023 | 60 | GIRI ENTERPRISE | 3.71 | 3.67 | 100 | 100
1294 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/14845 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting TW site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | 476/TD | 10/05/2023 | 60 | GIRI CONSTRUCTION | 3.71 | 3.7 | 100 | 100
1295 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/14845 | Augmentation | Electric quotation for Mukutshila PWSS Zone-II, Tube Well-II WS Scheme (Ref. ID 203933340) |  | 25/03/2023 | 0 | WBSEDCL | 0.37 | 0 | 0 | 0
1296 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/14845 | Augmentation | Electric quotation for Mukutshila PWSS Zone-II, Tube Well-II WS Scheme (Ref. ID 203933340) | BP-2023-24-25 | 04/05/2023 | 0 | WBSEDCL | 0.37 | 0 | 0 | 0
1297 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/14845 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II water supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -N) | 1501/TD | 17/07/2023 | 20 | THE GODFATHER TRADING COMPANY | 5.24 | 3.2 | 61.03 | 65
1298 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/14845 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | 475/TD | 10/05/2023 | 60 | GIRI ENTERPRISE | 3.71 | 3.69 | 100 | 100
1299 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/14845 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting TW site for Augmentation of Mukutshila Zone-II PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.)For Low Land | 663/TD | 19/05/2023 | 30 | GIRI CONSTRUCTION | 6.94 | 5.89 | 100 | 100
1300 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/14845 | Augmentation | Rising main 200mm dia DI(K9) Rising main pipeline with specials and other allied works at 3rd Tube Well Site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1083/TD | 08/06/2023 | 20 | M/S. NEW DINDA ENTERPRISE | 5.07 | 3.28 | 100 | 100
1301 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/14845 | Augmentation | Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Mukutshila Zone-II PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.)For Low Land | 664/TD | 19/05/2023 | 30 | DAS ENTERPRISE | 6.91 | 5.07 | 100 | 100
1302 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/14845 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. under JJM Program under MMD PHE Dte. | 209/W/MMD | 10/02/2023 | 180 | SUBHASIS ROY | 11.84 | 9.44 | 79.77 | 70
1303 | PURBA MEDINIPUR | Tamluk Division | BISWANATHPUR PIPED WATER SUPPLY SCHEME. , SM/13850 | New | Material Requisition To Resource Division | 2695/TD | 06/02/2023 | 0 | Resource Division | 4.13 | 0 | 0 | 0
1304 | PURBA MEDINIPUR | Tamluk Division | BISWANATHPUR PIPED WATER SUPPLY SCHEME. , SM/13850 | New | Material Requisition To Resource Division | 106/TD | 05/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
1305 | PURBA MEDINIPUR | Midnapore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. , SM/13850 | New | Biswanathpur W/S scheme TW-I Application no.-2004496775 Ref no.-204135775 | BP-2023-24-469 | 27/12/2023 | 0 | WBSEDCL | 1.54 | 0 | 0 | 0
1306 | PURBA MEDINIPUR | Midnapore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. , SM/13850 | New | Biswanathpur W/S scheme PH no.-II Application No.-2004521756 Ref.-204156072 | BP-2023-24-498 | 05/01/2024 | 0 | WBSEDCL | 2.56 | 0 | 0 | 0
1307 | PURBA MEDINIPUR | Midnapore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. , SM/13850 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BISWANATHPUR PWSS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 600/W/MMD | 20/03/2023 | 499 | M/S S M ELECTRICAL | 5.98 | 5.42 | 90.63 | 100
1308 | PURBA MEDINIPUR | Tamluk Division | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS , SM/13853 | New | Material Requisition To Resource Division | 2395/TD | 16/01/2023 | 0 | Resource Division | 25.23 | 0 | 0 | 0
1309 | PURBA MEDINIPUR | Midnapore Mechanical | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS , SM/13853 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 594/W/MMD | 20/03/2023 | 180 | INDIA ENTERPRISE | 21.62 | 0 | 0 | 0
1310 | PURBA MEDINIPUR | Tamluk Division | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS , SM/13853 | New | Material Requisition To Resource Division | 2970/TD | 12/09/2024 | 0 | Resource Division | 6.11 | 0 | 0 | 0
1311 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Astichak (Zone-I) PWSS , SM/15462 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Astichak Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | 1472/TD | 03/01/2022 | 20 | APEX ENGINEERING | 3.99 | 3.99 | 100 | 100
1312 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Astichak (Zone-I) PWSS , SM/15462 | Augmentation | Material Requisition To Resource Division | 2078/TD | 28/08/2023 | 0 | Resource Division | 24.42 | 0 | 0 | 0
1313 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Astichak (Zone-I) PWSS , SM/15462 | Augmentation | Material Requisition To Resource Division | 3009/TD | 29/11/2023 | 0 | Resource Division | 7.95 | 0 | 0 | 0
1314 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Astichak (Zone-I) PWSS , SM/15462 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Astichak (Zone-I) PWSS Egra II Block under JJM Program under MMD PHE Dte. | 889/W/MMD | 27/03/2023 | 180 | M.D.ENTERPRISE | 23.65 | 0 | 0 | 0
1315 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Astichak (Zone-I) PWSS , SM/15462 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Astichak Zone-I PWSS at Egra-II Block under Tamluk Division,PHE Dte. | 378/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
1316 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Astichak (Zone-I) PWSS , SM/15462 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, ZONE-I Of ASTICHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671988/QUOT/03/47 DT. 05-04-2024 Application NO- 2004671988 Application type-New connection Consumer Id- 204266732 | BP-2024-25-91 | 24/04/2024 | 0 | WBSEDCL | 7.72 | 0 | 0 | 0
1317 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Astichak (Zone-I) PWSS , SM/15462 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (291 nos) under JJM with allied work for ASTICHAK (ZONE-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 2444/TD | 19/09/2023 | 804 | HALDIA DEVELOPMENT CONSTRUCTION | 446.88 | 0 | 0 | 55
1318 | PURBA MEDINIPUR | Midnapore Mechanical | MURARI KALUA PWSS , SM/14693 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAHISHAGOT AND IT'S ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 602/W/MMD | 20/03/2023 | 712 | BHABANI PRASAD MANNA | 11.98 | 0 | 0 | 40
1319 | PURBA MEDINIPUR | Midnapore Mechanical | MURARI KALUA PWSS , SM/14693 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
1320 | PURBA MEDINIPUR | Midnapore Mechanical | DUBDA IT'S ADJOINING MOUJAS PWSS , SM/15513 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DUBDA and ADJOINING MOUJAS, Block Egra II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1269/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 27.04 | 0 | 0 | 0
1321 | PURBA MEDINIPUR | Tamluk Division | DUBDA IT'S ADJOINING MOUJAS PWSS , SM/15513 | New | Material Requisition To Resource Division | 2974/TD | 27/02/2023 | 0 | Resource Division | 49.63 | 0 | 0 | 0
1322 | PURBA MEDINIPUR | Central Drilling | DUBDA IT'S ADJOINING MOUJAS PWSS , SM/15513 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1323 | PURBA MEDINIPUR | Tamluk Division | DUBDA IT'S ADJOINING MOUJAS PWSS , SM/15513 | New | Sinking of Tube Well ,Rising main ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , OHR (Intze type with pile foundation) & Accommodate FHTC (5135 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dubda & Khagda PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 1733/TD | 31/07/2023 | 819 | MAHAVIR PUMPS MFG. PVT. LTD. | 1235.52 | 236.48 | 26.17 | 48
1324 | PURBA MEDINIPUR | Midnapore Mechanical | DUBDA IT'S ADJOINING MOUJAS PWSS , SM/15513 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
1325 | PURBA MEDINIPUR | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme under Tamluk Division, PHE Dte. | 1631/TD | 18/01/2022 | 20 | HORIZEN | 5.27 | 5.25 | 100 | 100
1326 | PURBA MEDINIPUR | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Kanktia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2342/TD | 10/01/2023 | 40 | TARUN KHATUA | 5.11 | 5.1 | 99.84 | 0
1327 | PURBA MEDINIPUR | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site(Boosting T/W) of Bagmari Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1094/TD | 25/08/2022 | 40 | AQUATECH ENGINEERS | 70.49 | 16.11 | 100 | 100
1328 | PURBA MEDINIPUR | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1428/TD | 26/09/2022 | 27 | PRANTIK DRILLING AGENCY | 49.66 | 15 | 100 | 80
1329 | PURBA MEDINIPUR | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well sites of Kanktia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2343/TD | 10/01/2023 | 40 | SUDIP MANNA | 5.11 | 5.11 | 100 | 100
1330 | PURBA MEDINIPUR | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Material Requisition To Resource Division | 1260/TD | 12/09/2022 | 0 | Resource Division | 44.52 | 0 | 0 | 0
1331 | PURBA MEDINIPUR | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Material Requisition To Resource Division | 653/TD | 27/06/2022 | 0 | Resource Division | 26.13 | 0 | 0 | 0
1332 | PURBA MEDINIPUR | Midnapore Mechanical | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Additional Electric Quotiaton for KAKTIA Water Supply Scheme T/W-III (Ref. ID-860272167) | BP-2023-24-134 | 27/07/2023 | 0 | WBSEDCL | 0.28 | 0 | 0 | 0
1333 | PURBA MEDINIPUR | Midnapore Mechanical | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Electric quotation for Kaktia PWSS Tube Well--IV WS Scheme (Ref. ID - 203931902) | BP-2022-23-139 | 20/03/2023 | 0 | WBSEDCL | 2.94 | 0 | 0 | 0
1334 | PURBA MEDINIPUR | Midnapore Mechanical | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Electric quotation for Kaktia PWSS Tube Well--III WS Scheme (Ref. ID - 203931856) | BP-2022-23-138 | 20/03/2023 | 0 | WBSEDCL | 2.96 | 0 | 0 | 0
1335 | PURBA MEDINIPUR | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 1000 cum and staging height 20.00 mtr. and repairing as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Kaktiya Water Supply Scheme within Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 690/TD | 27/06/2022 | 1188 | TAPAS SANTRA | 965.88 | 929.87 | 96.27 | 86
1336 | PURBA MEDINIPUR | Midnapore Mechanical | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 212/W/MMD | 10/02/2023 | 180 | WEST BENGAL ENGINEERING CO. | 40.35 | 25.37 | 62.88 | 35
1337 | PURBA MEDINIPUR | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Laying of rising main, Left out pipe line with FHTC (200 nos.) work for Kanktia PWSS in Sahid Matangini Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 3208/TD | 14/03/2023 | 1024 | TAPAS SANTRA | 68.55 | 46.63 | 68.01 | 72
1338 | PURBA MEDINIPUR | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Construction of boundary wall (Length-50 m) with R.C.C structures including provision of M.S. gate at 2nd. tube well site under Kanktiya Water Supply Scheme within Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. in the District of Purba Medinipur . | 945/TD | 27/03/2025 | 40 | MRITYUNJOY PARIA | 5.31 | 0 | 0 | 90
1339 | PURBA MEDINIPUR | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Construction of boundary wall (Length-150 m With Double Tie Beam at 01 Longer & 01 Shorter Side) with R.C.C structures including provision of M.S. gate at H/W site under Kanktiya Water Supply Scheme within Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. in the District of Purba Medinipur . | 696/TD | 05/03/2025 | 100 | A. R. CONSTRUCTION | 21.69 | 0 | 0 | 100
1340 | PURBA MEDINIPUR | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. , SM/10120 | Augmentation | Continuation work order for Additional Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 01.08.2025 to 31.01.2026.(06 Months) | 2632/TSD | 30/07/2025 | 181 | KISHORE KUMAR SEN | 0.86 | 0 | 0 | 0
1341 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV , SM/16286 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. | 1857/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.38 | 100 | 100
1342 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV , SM/16286 | Augmentation | Material Requisition To Resource Division | 2068/TD | 28/08/2023 | 0 | Resource Division | 13.67 | 0 | 0 | 0
1343 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV , SM/16286 | Augmentation | Material Requisition To Resource Division | 3005/TD | 29/11/2023 | 0 | Resource Division | 1.29 | 0 | 0 | 0
1344 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV , SM/16286 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kanpur Zone- IV PWSS at Ramnagar - II Block under Tamluk Division,PHE Dte. | 191/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
1345 | PURBA MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV , SM/16286 | Augmentation | Kanpur W/S scheme T/W-I, Zone-IV Application No.-2004536085 Ref.-204168169 | BP-2023-24-542 | 11/01/2024 | 0 | WBSEDCL | 3.6 | 0 | 0 | 0
1346 | PURBA MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV , SM/16286 | Augmentation | Kanpur W/S scheme PH-II, Zone-IV Application No.-2004565701 Ref no.-204193734 | BP-2023-24-587 | 02/02/2024 | 0 | WBSEDCL | 4.96 | 0 | 0 | 0
1347 | PURBA MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV , SM/16286 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 0 | 34
1348 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV , SM/16286 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 209 Nos) under JJM with allied work for KANPUR (Zone-IV) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | 1730/TD | 31/07/2023 | 790 | ONKAR ENTERPRISE | 308.34 | 222.32 | 72.1 | 40
1349 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV , SM/16286 | Augmentation | Drum Sheet walling, road restoration for distribution pipe line ( for FHTC) & Accommodate FHTC (130Nos) under JJM with allied work for KANPUR (Zone -IV) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 3183/TD | 30/09/2024 | 240 | GHOSH CONSTRUCTION | 95.27 | 0 | 0 | 85
1350 | PURBA MEDINIPUR | Tamluk Division | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16390 | Augmentation | Material Requisition To Resource Division | 352/TD | 26/04/2023 | 0 | Resource Division | 8.83 | 0 | 0 | 0
1351 | PURBA MEDINIPUR | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16390 | Augmentation | Electric Quotation for HABICHAK Water Supply SchemeT/W-IV (Ref. ID-204049766) | BP-2023-24-141 | 27/07/2023 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
1352 | PURBA MEDINIPUR | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16390 | Augmentation | Electric Quotation for HABICHAK Water Supply SchemeT/W-III (Ref. ID-204049767) | BP-2023-24-142 | 27/07/2023 | 0 | WBSEDCL | 3.76 | 0 | 0 | 0
1353 | PURBA MEDINIPUR | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16390 | Augmentation | Additional Electric Quotiaton for HABICHAK Water Supply Scheme, T/W- II, (Ref. ID-860281634) | BP-2023-24-322 | 01/11/2023 | 0 | WBSEDCL | 2.27 | 0 | 0 | 0
1354 | PURBA MEDINIPUR | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16390 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1204/W/MMD | 25/04/2023 | 740 | BHABANI PRASAD MANNA | 77.91 | 25.33 | 93.97 | 55
1355 | PURBA MEDINIPUR | Tamluk Division | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16390 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 116/TD | 06/04/2023 | 40 | AQUATECH ENGINEERS | 74.22 | 34.96 | 100 | 100
1356 | PURBA MEDINIPUR | Tamluk Division | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16390 | Augmentation | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room,Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Habichak Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 602/TD | 17/05/2023 | 45 | SOUMEN KUMAR GHOSH | 25.91 | 25.89 | 100 | 100
1357 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chapbasan PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16895 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1358 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Betkundu PWSS in the District of Purba Medinipur under JJM programme. , SM/16655 | Augmentation | Rejuvenation of Electro-Mechanical components of Betkundu PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 766/W/MMD | 23/03/2023 | 180 | MENAKA ENTERPRISE | 12.24 | 0 | 0 | 0
1359 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Betkundu PWSS in the District of Purba Medinipur under JJM programme. , SM/16655 | Augmentation | Electric Quotation for MAHISHADAL BETKUNDU Water Supply Scheme T/W-, (Ref. ID-222016853) | BP-2023-24-268 | 10/10/2023 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
1360 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chandiveti PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16880 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
1361 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chandiveti PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16880 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1362 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvination of Electro-Mechanical components of Pratapdighi PWSS in the District of Purba Medinipur under JJM programme , SM/16658 | Augmentation | Rejuvination of Electro-Mechanical components of Pratapdighi PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 768/W/MMD | 23/03/2023 | 180 | SOUMEN ELECTRIC | 12.65 | 10.44 | 82.51 | 75
1363 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Betkundu PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16896 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
1364 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Betkundu PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16896 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1365 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Muradpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17874 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
1366 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Muradpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17874 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1367 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Natshallakhya, Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17876 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
1368 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Natshallakhya, Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17876 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1369 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mukutshila Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17887 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
1370 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mukutshila Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17887 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1371 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Habichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17781 | Solarisation | Solarization of grid connected pumping installation at Habichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 995/W/MMD | 29/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 4.88 | 78.03 | 80
1372 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Amtalia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17366 | Solarisation | Solarization of grid connected pumping installation at Amtalia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 717/W/MMD | 23/03/2023 | 180 | AMITAVA CHAKRABORTY | 6.26 | 4.85 | 77.48 | 85
1373 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Golaranji PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17823 | Solarisation | Solarization of grid connected pumping installation at Golaranji PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1032/W/MMD | 29/03/2023 | 180 | PRANAB KUMAR DAS | 6.26 | 0 | 0 | 0
1374 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Damudarpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17341 | Solarisation | Solarization of grid connected pumping installation at Damudarpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 716/W/MMD | 23/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 0 | 0 | 0
1375 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Baharampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17906 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at MAHAMMADPUR and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 649/HESD | 08/07/2024 | 15 | SOUMEN ELECTRIC | 1.94 | 0 | 0 | 100
1376 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Baharampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17906 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1377 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Golaranji PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17917 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
1378 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Golaranji PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17917 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1379 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Haldia (Ramnagar) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17923 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
1380 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Haldia (Ramnagar) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17923 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1381 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Simulia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17859 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1382 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Madhabpur (Balighai) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17831 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
1383 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Madhabpur (Balighai) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17831 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1384 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Gogras keshab bar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17723 | Solarisation | Solarization of grid connected pumping installation at Gogras keshab bar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1028/W/MMD | 29/03/2023 | 180 | KAMAKSHYA ENTERPRISE | 6.26 | 0 | 0 | 0
1385 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Erasal PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17724 | Solarisation | Solarization of grid connected pumping installation at Erasal PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 994/W/MMD | 29/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 0 | 0 | 0
1386 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Mahammadpur (Bhagwanpur-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17790 | Solarisation | Solarization of grid connected pumping installation at Mahammadpur (Bhagwanpur-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 993/W/MMD | 29/03/2023 | 180 | S.S.GHORAI | 6.25 | 4.85 | 77.48 | 80
1387 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Khejurberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17793 | Solarisation | Solarization of grid connected pumping installation at Khejurberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1021/W/MMD | 29/03/2023 | 733 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
1388 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Damudarpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17841 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
1389 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Damudarpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17841 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1390 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bagmari (Potashpur - II) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17350 | Solarisation | Solarization of grid connected pumping installation at Bagmari (Potashpur - II) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 740/W/MMD | 23/03/2023 | 180 | PRANAB KUMAR DAS | 6.26 | 0 | 0 | 0
1391 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bagmari (Egra-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17351 | Solarisation | Solarization of grid connected pumping installation at Bagmari (EGRA - I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 725/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
1392 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bagmari (Egra-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17351 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0.18 | 96.99 | 100
1393 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Badhia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17309 | Solarisation | Solarization of grid connected pumping installation at Badhia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 741/W/MMD | 23/03/2023 | 707 | PRANAB KUMAR DAS | 6.26 | 4.85 | 77.48 | 65
1394 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Badhia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17309 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0.18 | 94.81 | 100
1395 | PURBA MEDINIPUR | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/18303 | New | Material Requisition To Resource Division | 2959/TD | 27/02/2023 | 0 | Resource Division | 54.95 | 0 | 0 | 0
1396 | PURBA MEDINIPUR | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/18303 | New | Laying distribution System & Accommodate FHTC (1250 nos) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) | 1408/TD | 12/07/2023 | 80 | UCON | 204.9 | 82.81 | 40.42 | 25
1397 | PURBA MEDINIPUR | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/18303 | New | Laying distribution System, Construction of Pump House, Construction of Boundary Wall & Accommodate FHTC (1250 nos) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (Part-C) | 1410/TD | 12/07/2023 | 716 | NARAYAN CHANDRA DAS | 200.01 | 74.62 | 37.31 | 45
1398 | PURBA MEDINIPUR | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/18303 | New | Laying distribution System, Construction of Pump House Accommodate FHTC (1100 nos) & Rising Main including interconnection for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(Part-D) | 1407/TD | 12/07/2023 | 80 | BARH CONSTRUCTION | 205.81 | 99.87 | 48.53 | 50
1399 | PURBA MEDINIPUR | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/18303 | New | Material Requisition To Resource Division | 133/TD | 05/01/2024 | 0 | Resource Division | 27.7 | 0 | 0 | 0
1400 | PURBA MEDINIPUR | Midnapore Mechanical | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/18303 | New | Quotation Bill for New Service connection at T/W NO-I Of NUNHANDA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, BHAGWANPUR C.C.C. Ref. Memo No- 2004638854/QUOT/03 DT. 13-03-2024 Application NO- 2004638854 Application type-New connection CONSUMER ID: 204243849 | BP-2023-24-911 | 28/03/2024 | 0 | WBSEDCL | 2.77 | 0 | 0 | 0
1401 | PURBA MEDINIPUR | Midnapore Mechanical | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/18303 | New | Quotation Bill for New Service connection at T/W NO-III Of NUNHANDA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, BHAGWANPUR C.C.C. Ref. Memo No- 2004638811/QUOT/03 DT. 13-03-2024 Application NO- 2004638811 Application type-New connection CONSUMER ID: 204243848 | BP-2023-24-912 | 28/03/2024 | 0 | WBSEDCL | 3.13 | 0 | 0 | 0
1402 | PURBA MEDINIPUR | Midnapore Mechanical | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/18303 | New | Quotation Bill for New Service connection at T/W NO-II Of NUNHANDA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004698092/QUOT/03 DT. 23-04-2024 Application NO- 2004698092 Application type-New connection Consumer Id- 204285056 | BP-2024-25-139 | 09/05/2024 | 0 | WBSEDCL | 10.71 | 0 | 0 | 0
1403 | PURBA MEDINIPUR | Central Drilling | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/18303 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 81.51 | 105.49 | 11
1404 | PURBA MEDINIPUR | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/18303 | New | Laying distribution System & Accommodate FHTC (897 nos) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(Part-B) | 1409/TD | 12/07/2023 | 786 | SWADHIN KUMAR CHAKRABORTY | 211.86 | 70.39 | 33.22 | 40
1405 | PURBA MEDINIPUR | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/18303 | New | Soil investigation, R.C.C. Elevated Reservoir of capacity 550cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (Part-F) | 2441/TD | 19/09/2023 | 529 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 178.22 | 0 | 0 | 0
1406 | PURBA MEDINIPUR | Midnapore Mechanical | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/18303 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
1407 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bankiput PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17353 | Solarisation | Solarization of grid connected pumping installation at Bankiput PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 719/W/MMD | 23/03/2023 | 180 | AMITAVA CHAKRABORTY | 6.26 | 0 | 0 | 0
1408 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bhajachauli PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17869 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
1409 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bhajachauli PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17869 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1410 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Paramanandapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17794 | Solarisation | Solarization of grid connected pumping installation at Paramanandapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1020/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 4.89 | 78.03 | 80
1411 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Paramanandapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17794 | Solarisation | Application fee for net metering at Paramanandapur w/s scheme PH I Solar power plant in the district of Purba MEdinipur under MMD PHE Dte. (App No 2004980276, Con ID 222197563) |  | 18/12/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
1412 | PURBA MEDINIPUR | Tamluk Division | AJANGECHHYA PIPED WATER SUPPLY SCHEME. , SM/13852 | New | Material Requisition To Resource Division | 2675/TD | 06/02/2023 | 0 | Resource Division | 4.96 | 0 | 0 | 0
1413 | PURBA MEDINIPUR | Midnapore Mechanical | AJANGECHHYA PIPED WATER SUPPLY SCHEME. , SM/13852 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AJANGECHHYA, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 545/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 21.58 | 9.75 | 45.16 | 45
1414 | PURBA MEDINIPUR | Midnapore Mechanical | AJANGECHHYA PIPED WATER SUPPLY SCHEME. , SM/13852 | New | AJANGECHIA w/s SCHEME Application No.-2004568912 Ref.-204196601 | BP-2023-24-586 | 02/02/2024 | 0 | WBSEDCL | 5.6 | 0 | 0 | 0
1415 | PURBA MEDINIPUR | Tamluk Division | AJANGECHHYA PIPED WATER SUPPLY SCHEME. , SM/13852 | New | Sinking of Tube Well, Construction of Pump House, 50 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (314 nos.), Installation of display Board, under JJM with allied work including 02 (two) Years Operation & Maintenance of Ajangechhya PWSS within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 208/TD | 13/04/2023 | 719 | RELIABLE CONSTRUCTIONS | 135.23 | 26.21 | 19.38 | 45
1416 | PURBA MEDINIPUR | Tamluk Division | PUTPUTIA PWSS , SM/11886 | New | Material Requisition To Resource Division | 2677/TD | 06/02/2023 | 0 | Resource Division | 23.37 | 0 | 0 | 0
1417 | PURBA MEDINIPUR | Midnapore Mechanical | PUTPUTIA PWSS , SM/11886 | New | Electric Quotation for PUTPUTIA Head Work Water Supply Scheme T/W-I, (Ref. ID-204094476) | BP-2023-24-270 | 10/10/2023 | 0 | WBSEDCL | 5.52 | 0 | 0 | 0
1418 | PURBA MEDINIPUR | Midnapore Mechanical | PUTPUTIA PWSS , SM/11886 | New | Electric Quotation for PUTPUTIA Water Supply Scheme , T/W-II (Ref. ID-204075888) | BP-2023-24-240 | 12/09/2023 | 0 | WBSEDCL | 4.59 | 0 | 0 | 0
1419 | PURBA MEDINIPUR | Tamluk Division | PUTPUTIA PWSS , SM/11886 | New | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(1670 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of capacity 250 cum and staging height20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Putputia PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 130/TD | 10/04/2023 | 691 | TARUN KOLEY | 483.49 | 237.21 | 49.06 | 70
1420 | PURBA MEDINIPUR | Midnapore Mechanical | PUTPUTIA PWSS , SM/11886 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PUTPUTIA PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 620/W/MMD | 20/03/2023 | 896 | M/S B.M. ELECTRICAL | 22.81 | 19.81 | 86.85 | 35
1421 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme , SM/07094 | Retrofitting | Functional Household Tap Connection to the 1174 nos. Household of Bagmari W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-A [Srirampur(118) Bagmari(116)] | 2864/TD | 09/02/2021 | 30 | SWARUPANANDA DAS | 57.51 | 0 | 0 | 100
1422 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme , SM/07094 | Retrofitting | Functional Household Tap Connection to the 836 nos. Household of Bagmari W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-B [Dwarakapur(115) Rannagarpur(119) Dhusurda(239) Kashimpur(240) Joykrishnapur(114)PART] | 2865/TD | 09/02/2021 | 30 | S.K. MONDAL | 38.92 | 25.89 | 200 | 100
1423 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme , SM/07094 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme within Potashpur - II Dev. Block under Tamluk Division, PHE Dte. | 965/W | 22/03/2021 | 0 | SWARUPANANDA DAS | 47.13 | 0 | 0 | 0
1424 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme , SM/07094 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme under Tamluk Division, PHE Dte. | 1118/W | 30/03/2021 | 0 | S.K. MONDAL | 25.94 | 0 | 0 | 0
1425 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme , SM/07094 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme within Potashpur - II Dev. Block under Tamluk Division, PHE Dte. | 302/W | 05/10/2021 | 0 | SWARUPANANDA DAS | 2.87 | 0 | 0 | 0
1426 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme , SM/07094 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme within Potashpur - II Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-114 | 05/10/2021 | 0 | SWARUPANANDA DAS | 7.5 | 0 | 0 | 0
1427 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Basudevpur Piped Water Supply Scheme , SM/07100 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Basudevpur PWSS Block Egra-II in the District of Purba Medinipur. | 2629/TD | 05/01/2021 | 60 | SNEHESH SEN | 87.4 | 87.39 | 100 | 100
1428 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Basudevpur Piped Water Supply Scheme , SM/07100 | Retrofitting | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | 895/TD | 07/03/2024 | 300 | MISHRA ENTERPRISE | 9.53 | 0.8 | 59.57 | 65
1429 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme , SM/06878 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Bamunia PWSS Block Contai-II in the District of Purba Medinipur. | 2106/TD | 05/11/2020 | 180 | JAYANTA KR. MONDAL | 74.72 | 0 | 0 | 100
1430 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme , SM/06878 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. | 639/W | 13/01/2021 | 0 | JAYANTA KUMAR MONDAL | 54.64 | 0 | 0 | 0
1431 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme , SM/06878 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. | 995/W | 26/03/2021 | 0 | JAYANTA KUMAR MONDAL | 10.33 | 0 | 0 | 0
1432 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme , SM/06878 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. | 303/W | 05/10/2021 | 0 | JAYANTA KUMAR MONDAL | 5 | 0 | 0 | 0
1433 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme , SM/06878 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. | BP-2021-22-121 | 05/10/2021 | 0 | JAYANTA KUMAR MONDAL | 3.99 | 0 | 0 | 0
1434 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-II , SM/07114 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -II(Balance Work) Block Panskura-II in the District of Purba Medinipur. | 2631/TD | 05/01/2021 | 60 | MAA ANANDAMAYEE | 96.97 | 192 | 200 | 100
1435 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 1 Water Supply Scheme , SM/07119 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Gholepukuria PWSS (Zone-I)Block -Nandigram-II in the District of Purba Medinipur. | 2503/TD | 23/12/2020 | 60 | M/S. CHANDI CHARAN MISHRA & CO. | 76.13 | 31.88 | 100 | 100
1436 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 1 Water Supply Scheme , SM/07119 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - I W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. | 936/W | 18/03/2021 | 0 | M/S. CHANDI CHARAN MISHRA & CO. | 22.35 | 0 | 0 | 0
1437 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 1 Water Supply Scheme , SM/07119 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - I W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. | 296/W | 07/10/2021 | 0 | M/S. CHANDI CHARAN MISHRA & CO. | 21.89 | 0 | 0 | 0
1438 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 1 Water Supply Scheme , SM/07119 | Retrofitting | Continuation Work Order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Augmentation Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | 2566/TD | 06/10/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 1.64 | 100 | 100
1439 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (673 nos) under JJM in Mahammadpur PWSS within Mahammadpur JL No.-185 (Dakshin Mahammadpur) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-C) [2nd Call] | 2926/TD | 22/02/2021 | 25 | TARUN KOLEY | 31.71 | 0 | 0 | 100
1440 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (100 nos) under JJM in Mahammadpur PWSS within Khariberia JL No.-183 (Khariberia) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-A) | 2877/TD | 11/02/2021 | 20 | TAPAN BERA | 4.84 | 0 | 0 | 100
1441 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (102 nos) under JJM in Tajpur PWSS within Tajpur (P) J.L.- 210 (Tajpur Dakshin Pally) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-H) | 2878/TD | 11/02/2021 | 20 | BUNBA CONSTRUCTION | 4.85 | 0 | 0 | 100
1442 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (590 nos) under JJM in Tajpur PWSS within Bartalya - JL No.-209 (Bartalya) & Chargalya (P) - J.L. - 150 (Chargalya) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-F) | 2825/TD | 05/02/2021 | 25 | KRISHNENDU SEKHAR DAS | 27.98 | 0 | 0 | 100
1443 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (590 nos) under JJM in Tajpur PWSS within Chargalya (P) - J.L. - 150 (Chargalya) & Tajpur (P) - J.L. - 210 (Tajpur & Tajpur Paschim Pally) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-G) | 2826/TD | 05/02/2021 | 25 | DEBASIS DAS | 27.75 | 0 | 0 | 100
1444 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (409 nos) under JJM in Tajpur PWSS within Dijam Talya - JL No.-149 (Dijam Talya) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-D) | 2823/TD | 05/02/2021 | 20 | MRITYUNJOY PARIA | 19.4 | 12.43 | 100 | 100
1445 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (429 nos) under JJM in Tajpur PWSS within Bar Jamtalya - JL No.-148 (Bar Jamtalya) & Nandanayak Bar - J.L. - 179 (Nandanayak Bar) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-E) | 2824/TD | 05/02/2021 | 20 | SK. NUR ISLAM | 20.36 | 8.35 | 100 | 100
1446 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accomodate FHTC under JJM Tajpur W/S Scheme under Tamluk Division, PHE Dte. | 1102/W | 30/03/2021 | 0 | SK. NUR ISLAM | 12 | 0 | 0 | 0
1447 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accomodate FHTC (673 Nos.) under JJM in Mahammadpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-88 | 05/10/2021 | 0 | TARUN KOLEY | 32.35 | 0 | 0 | 0
1448 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accomodate FHTC under JJM Mahammadpur W/S Scheme under Tamluk Division, PHE Dte. | 1093/W | 30/03/2021 | 0 | NARAYAN CHANDRA DAS | 19.15 | 0 | 0 | 0
1449 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accomodate FHTC 590 Nos. connection under JJM Tajpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. (Part-F) | BP-2021-22-118 | 05/10/2021 | 0 | KRISHNENDU SEKHAR DAS | 13.48 | 0 | 0 | 0
1450 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accomodate FHTC under JJM Tajpur W/S Scheme under Tamluk Division, PHE Dte. | 1095/W | 30/03/2021 | 0 | KRISHNENDU SEKHAR DAS | 14.5 | 0 | 0 | 0
1451 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Tajpur W/S Scheme within Nandigram ¿ I Dev. Block under Tamluk Division, PHE Dte. | 1097/W | 30/03/2021 | 0 | DEBASIS DAS | 13.78 | 0 | 0 | 0
1452 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accomodate FHTC 741 Nos. connection under JJM in Mahammadpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. (Part-B) | BP-2021-22-72 | 04/09/2021 | 0 | NARAYAN CHANDRA DAS | 16.12 | 0 | 0 | 0
1453 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accomodate for 409 Nos. FHTC connection under JJM in Tajpur W/S Scheme within Nandigram - I Dev. Block Block under Tamluk Division, PHE Dte. (Part-D) | BP-2021-22-69 | 04/09/2021 | 0 | MRITYUNJOY PARIA | 6.98 | 0 | 0 | 0
1454 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting to accomodate FHTC for Tajpur W/S Scheme | BP-2021-22-62 | 13/08/2021 | 0 | BUMBA CONSTRUCTION | 4.84 | 0 | 0 | 0
1455 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Retrofitting of accommodate FHTC 100 Nos. under JJM in Mahammadpur W/S Scheme within Nandigram - I Block. | BP-2021-22-60 | 13/08/2021 | 0 | TAPAN BERA | 4.84 | 0 | 0 | 0
1456 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Laying Left Out UPVC pipe line of Mouza- Di-jamtalya for Tajpur & its adjoinin Mouzas Water Supply Scheme within Nandigram - I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1944/TD | 03/03/2022 | 15 | MRITYUNJOY PARIA | 4.85 | 4.64 | 100 | 100
1457 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur , SM/07657 | Retrofitting | Construction of Approach Road for Mahammadpur PWSS RCC Elevated Reservoir of Capacity 350 Cum. Within Nandigram-I Block under Haldia Sub-Division of Tamluk Division., P.H.E. Dte.Length = 150.00 Mtr Width = 3.0 Mtr. Thickness = 150 mm | 983/TD | 13/03/2024 | 40 | SATYABRATA BHAUMIK | 5.74 | 5.74 | 100 | 100
1458 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. , SM/07659 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. | 2843/TD | 08/02/2021 | 70 | RAJ KUMAR SINGHA | 222.76 | 0 | 0 | 100
1459 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. , SM/07659 | Retrofitting | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  | 23/06/2021 | 0 | RAJ KUMAR SINGHA | 116.52 | 0 | 0 | 0
1460 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. , SM/07659 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. | 1090/W | 30/03/2021 | 0 | RAJ KUMAR SINGHA | 28.06 | 0 | 0 | 0
1461 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. , SM/07659 | Retrofitting | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-34 | 23/07/2021 | 0 | RAJ KUMAR SINGHA | 116.52 | 0 | 0 | 0
1462 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. , SM/07659 | Retrofitting | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  | 16/09/2021 | 0 | RAJ KUMAR SINGHA | 78.17 | 0 | 0 | 0
1463 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. , SM/07659 | Retrofitting | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-105 | 05/10/2021 | 0 | RAJ KUMAR SINGHA | 78.17 | 0 | 0 | 0
1464 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Sankarpur Piped Water Supply Scheme , SM/07108 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sankarpur PWSS Block - Ramnagar-I in the District of Purba Medinipur. | 2637/TD | 05/01/2021 | 60 | MAITY CONSTRUCTION | 94.92 | 186.18 | 196.15 | 100
1465 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Sankarpur Piped Water Supply Scheme , SM/07108 | Retrofitting | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | 895/TD | 07/03/2024 | 300 | MISHRA ENTERPRISE | 9.53 | 0 | 0 | 65
1466 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme , SM/07109 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kanpur PWSS Block-Ramnagar-II in the District of Purba Medinipur. | 2634/TD | 05/01/2021 | 60 | BASANTA KUMAR MAITY | 96.58 | 3.47 | 100 | 100
1467 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme , SM/07109 | Retrofitting | Retrofitting to accomodate FHTC under JJM Kanpur W/S Scheme within Ramnagar - II Dev. Block under Tamluk Division, PHE Dte. | 715/W | 09/02/2021 | 0 | BASANTA KUMAR MAITY | 59.24 | 0 | 0 | 0
1468 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme , SM/07109 | Retrofitting | Retrofitting to accomodate FHTC under JJM Kanpur W/S Scheme within Ramnagar - II Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-29 | 19/07/2021 | 0 | BASANTA KUMAR MAITY | 13.32 | 0 | 0 | 0
1469 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme , SM/07109 | Retrofitting | Retrofitting to accomodate FHTC under JJM Kanpur W/S Scheme within Ramnagar - II Dev. Block under Tamluk Division, PHE Dte. | 991/W | 26/03/2021 | 0 | BASANTA KUMAR MAITY | 20.5 | 0 | 0 | 0
1470 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme , SM/07109 | Retrofitting | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | 895/TD | 07/03/2024 | 300 | MISHRA ENTERPRISE | 9.53 | 2.67 | 100 | 65
1471 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Protection arrangement of damaged boundary wall at Chapbasan store due to Amphan of Chapbasan W/S Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | 03/Camp/TSD | 22/05/2020 | 0 | MAA ANANDAMAYEE | 0.66 | 0.66 | 100 | 0
1472 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-Laying Distribution system of pipe line and its allied works for Bahichberia water supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | 3357/TD | 26/03/2021 | 25 | TARUN KOLEY | 4.85 | 4.85 | 100 | 0
1473 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Repairing, renovation & construction of Boundary wall at Gobindanagar Zone-II Water Supply Scheme & its adjoining Mouzas Water Supply Scheme within Panskura-I Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. | 3359/TD | 26/03/2021 | 25 | MADAN MOHAN MAITY | 4.76 | 4.71 | 100 | 0
1474 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-Laying of UPVC Pipe line under Gogras Keshabbarh Water Supply Scheme & its adjoining mouzas W/S Scheme within Panskura Block under Tamluk Sub- Division of Tamluk Division, PHE Dte.(PART-B). | 3367/TD | 26/03/2021 | 25 | TARUN KOLEY | 3.19 | 3.04 | 100 | 0
1475 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-laying Distribution system of pipe line and its allied works for Simulia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3368/TD | 26/03/2021 | 25 | GHOSH ENTERPRISE | 4.82 | 4.8 | 100 | 0
1476 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-Laying Distribution system of pipe line and its allied works for Thekuachak Zone- I Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3369/TD | 26/03/2021 | 25 | GHOSH ENTERPRISE | 4.85 | 4.85 | 100 | 0
1477 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | New construction of part Boundary wall & repairing & renovation of old wall at Erasal H/W site under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E. Dte. | 3358/TD | 26/03/2021 | 25 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.8 | 4.68 | 100 | 0
1478 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | New construction of Boundary wall and repairing & Renovation of old wall at Chapbasan Store of Chapbasan water supply scheme within Tamluk Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte. (Part-II) . | 3366/TD | 26/03/2021 | 25 | M/S MONDAL CONSTRUCTION & CO. | 4.63 | 4.46 | 100 | 0
1479 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | New construction of Boundary wall and Lantern net of OHR at H/W site and Earth filling at 2nd T/W Site and damage portion of pipe line of Muradpur Water Supply Scheme under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E. Dte. | 3360/TD | 26/03/2021 | 25 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.83 | 4.81 | 100 | 0
1480 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Construction of guard wall for protection of rising main line & additional work of septic tank, plinth protection work at 2nd T/W site for Alinan Zone -I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3362/TD | 26/03/2021 | 25 | TAPAS SANTRA | 4.79 | 4.75 | 100 | 0
1481 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 3363/TD | 26/03/2021 | 25 | J.M. CONSTRUCTION | 3.93 | 2.96 | 100 | 0
1482 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-Laying distribution system of UPVC Pipe line by different dia. UPVC pipes for Nodal point (3-21,21-23,23-63) damaged of Dakshin Mechogram Water Supply Scheme at H/W site within Panskura Block under Tamluk Sub- Division of Tamluk Division, PHE Dte. | 3377/TD | 26/03/2021 | 25 | PURNA CHANDRA BARH | 4.85 | 4.8 | 100 | 0
1483 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | 125mm. dia. Eucalyptus bullah pilling for protecting the pipe line at pond side and damage portion of pipe line at Rashikachak & its adjoining mouzas Water Supply Scheme at Chandipur Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. Purba Medinipur. | 3371/TD | 26/03/2021 | 25 | BAGLAMUKHI SECURITY SERVICE | 4.84 | 4.82 | 100 | 0
1484 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | New construction of part Boundary wall & repairing & renovation of old wall at Khejurberia H/W site under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E.Dte. (Rate as per PWD 2nd Corrigendum , w.e.f. 04.06.2018) | 3379/TD | 26/03/2021 | 25 | J.S. CONSTRUCTION | 4.82 | 4.78 | 100 | 0
1485 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-Laying Distribution system of pipe line and its allied works for Thekuachak Zone- II Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3373/TD | 26/03/2021 | 25 | SWAPAN KUMAR MAITY | 4.84 | 4.69 | 100 | 0
1486 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-Laying Distribution system of pipe line and its allied works for Jalpai Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3374/TD | 26/03/2021 | 25 | J.M. CONSTRUCTION | 4.85 | 4.62 | 100 | 0
1487 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Bargodagodar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 3375/TD | 26/03/2021 | 25 | S.K. MONDAL | 3.93 | 2.84 | 100 | 0
1488 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-Laying of 90mm dia. UPVC Pipe line under Gogras Keshabbarh W/S Scheme & its adjoining mouzas Water Supply Scheme within Panskura Block under Tamluk Sub- Division of Tamluk Division, PHE Dte.(PART-A). | 3376/TD | 26/03/2021 | 25 | TARUN KOLEY | 4.76 | 4.76 | 100 | 0
1489 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-laying Distribution system of pipe line and its allied works for Dakshin Dhalhara Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3378/TD | 26/03/2021 | 25 | BAGLAMUKHI SECURITY SERVICE | 4.85 | 4.61 | 100 | 0
1490 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | New construction of part Boundary wall & repairing & renovation of old wall at Dakshin Gumai H/W site under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E.Dte. (Rate as per PWD 2nd Corrigemdum , w.e.f. 04.06.2018) | 611/TSD | 12/11/2020 | 25 | M/S MONDAL CONSTRUCTION & CO. | 1.92 | 1.88 | 100 | 0
1491 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Relaying of pipe line of Erasal & its adjoining mouzas W/S Scheme at Chandipur Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. purba Medinipur. | 610/TSD | 12/11/2020 | 25 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 2.72 | 2.71 | 100 | 0
1492 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-Laying Distribution system of pipe line and its allied works for Alinan zone - I water supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 614/TSD | 12/11/2020 | 25 | TAPAS SANTRA | 2.91 | 2.89 | 100 | 0
1493 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Acceptance-cum-work order for New construction of part Boundary wall & repairing & renovation of old wall at Khejurberia 2nd T/W site under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E. Dte. | 619/TSD | 13/11/2020 | 25 | RAI CONSTRUCTION | 1.6 | 1.6 | 100 | 0
1494 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-Laying Distribution system of pipe line and its allied works for Dakshin Gumai Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3361/TD | 26/03/2021 | 25 | M/S MONDAL CONSTRUCTION & CO. | 4.85 | 4.73 | 100 | 0
1495 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-laying Distribution system of pipe line and its allied works for Gobindanagar Zone-I water supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3364/TD | 26/03/2021 | 25 | MRITYUNJOY PARIA | 4.84 | 4.84 | 100 | 0
1496 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Relaying of pipe line of Chatra & its adjoining mouzas W/S Scheme at Sahid Matangani Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. purba Medinipur. | 3365/TD | 26/03/2021 | 25 | BAGLAMUKHI SECURITY SERVICE | 4.85 | 4.85 | 100 | 0
1497 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-laying Distribution system of pipe line and its allied works for Bargodagodar water supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3356/TD | 26/03/2021 | 25 | S.K. MONDAL | 4.84 | 4.84 | 100 | 0
1498 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Protection arrangement at h/w site of Erashal W/S Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | 04/Camp/TSD | 22/05/2020 | 3 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 0.22 | 0.22 | 100 | 0
1499 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Renovation & repairing of Guard Room, Gunman Room, Godown & 2nd T/W pump house of Chapbasan Water Supply Scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | 3372/TD | 26/03/2021 | 25 | S.D. CONSTRUCTION | 4.05 | 4 | 100 | 0
1500 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | New construction of part Boundaty wall & repairing & renovation of old wall (H/W & 2nd)site at Bahichberia pwss under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E.Dte. | 620/TSD | 13/11/2020 | 25 | S.D. CONSTRUCTION | 2.9 | 2.17 | 100 | 0
1501 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | 125mm. dia.Eucalyptus bullah pilling for protecting the pipe line at pond side of Habichak & its adjoining mouzas W/S Scheme at Chandipur Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. Purba Medinipur. | 621/TSD | 13/11/2020 | 25 | SWADHIN KUMAR CHAKRABORTY | 2.91 | 2.91 | 100 | 0
1502 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. , SM/09354 | Disaster | Re-Laying Distribution system of pipe line damaged due to AMPHAN and its allied works for Alinan zone - II water supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 615/TSD | 12/11/2020 | 25 | TARUN KOLEY | 2.92 | 2.9 | 100 | 0
1503 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BADHIA PWSS UNDER RAMNAGAR - I BLOCK PHASE II , SM/08745 | Retrofitting | Supply of C.I D.F sluice valve to accommodate FHTC under JJM in BADHYA PWSS Block-Ramnagar-I in the district of Purba Medinipur ( phase -II ) | 617/DSD | 31/01/2022 | 15 | AJIT KUMAR SOM | 1.03 | 1.03 | 100 | 100
1504 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BADHIA PWSS UNDER RAMNAGAR - I BLOCK PHASE II , SM/08745 | Retrofitting | Rejuvenation to accommodate FHTC (670 nos.) under JJM in BADHIA PWSS Block-Ramnagar-I in the district of Purba Medinipur ( Phase -II ) | 691/TD | 10/09/2021 | 20 | AJIT KUMAR SOM | 94.24 | 89.52 | 94.99 | 100
1505 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BADHIA PWSS UNDER RAMNAGAR - I BLOCK PHASE II , SM/08745 | Retrofitting | Laying ( Left Out ) UPVC pipe line to accommodate FHTC under JJM in Badhya PWSS within Ramnagar-I Block ( To support Phase-I FHTC) under Digha Sub-Division of Tamluk Division, PHE Dte. ( Mouza- Kachum, Bakharpur, Khandagram, Badhya) | 2003/TD | 08/03/2022 | 25 | R CONSTRUCTION | 10.79 | 10.79 | 100 | 100
1506 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BADHIA PWSS UNDER RAMNAGAR - I BLOCK PHASE II , SM/08745 | Retrofitting | Material Requisition To Resource Division | 1234/TD | 09/12/2021 | 0 | Resource Division | 0.08 | 0 | 0 | 0
1507 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PASCHIM KAMARDA PWSS UNDER CONTAI - III BLOCK , SM/08750 | Retrofitting | Retrofitting to accomodate FHTC (1487 nos.) under JJM in Paschim Kamarda PWSS Block - Contai-III under Contai Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Phase- I) | 688/TD | 10/09/2021 | 50 | RAJ KUMAR SINGHA | 96.99 | 170.64 | 175.94 | 100
1508 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PASCHIM KAMARDA PWSS UNDER CONTAI - III BLOCK , SM/08750 | Retrofitting | Sinking of 2 (two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Tubewell Site (Mouza- Panbhuni, JL No. - 163, Plot No. 551) of Paschim Kamarda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Replacement of 2nd Tube Tubewell Site (Mouza- Nilpur, JL No. - 160, Plot No. 318) of Paschim Kamarda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 1095/TD | 25/08/2022 | 21 | M/S SYCHROTECH INDUSTRY | 26.31 | 0 | 0 | 0
1509 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS under Contai II (Deshapran) Block (Phase-II). , SM/09048 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS Block - Contai-II in the District of Purba Medinipur. Mouza- Sofiabad(497),Dholmari(498),Kultalia(500),(Phase-II) | 1009/TD | 02/11/2021 | 30 | RELIABLE CONSTRUCTIONS | 35.54 | 35.66 | 100 | 100
1510 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS under Contai II (Deshapran) Block (Phase-II). , SM/09048 | Retrofitting | Material Requisition To Resource Division | 2162/TD | 05/07/2024 | 0 | Resource Division | 0.81 | 0 | 0 | 0
1511 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) , SM/09339 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Haipur PWSS Block-Contai-I in the district of Purba Medinipur.(Phase-II) | 1637/TD | 19/01/2022 | 60 | SRIMANTA KUMAR MAITY | 118.38 | 105.84 | 89.4 | 100
1512 | PURBA MEDINIPUR | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) , SM/09339 | Retrofitting | SUPPLY & DELIVERY OF BENTONITE POWDER SODIUM BASED (RAJASTHAN VARIETY) FOR CONSTRUCTION OF TUBE WELLS AT HAZIPUR PWSS TW-I, GOGHAT-II, BLOCK HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 429/CMSD-II (D) | 30/09/2021 | 15 | S B S ENTERPRISE | 0.41 | 0.41 | 100 | 100
1513 | PURBA MEDINIPUR | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) , SM/09339 | Retrofitting | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HAZIPUR PWSS TW-I, GOGHAT-II, BLOCK HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 428/CMSD-II (D) | 30/09/2021 | 15 | S B S ENTERPRISE | 0.96 | 0.79 | 100 | 100
1514 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) , SM/09339 | Retrofitting | Supply & Delivery of different dia C.I.D.F. Sluice Valve for Retrofitting to accommodate FHTC under JJM in Haipur PWSS Block- Contai-I in the district of Purba Medinipur (Phase-II) under Contai Sub- Division, of Tamluk Division, PHE Dte. | 12/A/CSD | 05/04/2022 | 15 | SRIMANTA KUMAR MAITY | 1.89 | 1.89 | 100 | 100
1515 | PURBA MEDINIPUR | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) , SM/09339 | Retrofitting | SEALING BORE- HOLE ANNULAR SPACE AND OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HAIPUR PWSS UNDER CMSD-I (D), CDD, PHE DTE. | 188/CMSD-I (D) | 30/09/2021 | 7 | MENAKA ENTERPRISE | 0.6 | 0.6 | 100 | 100
1516 | PURBA MEDINIPUR | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) , SM/09339 | Retrofitting | Supply & Delivery of 12 1/4" dia RR Bit for Drilling work at haipur PWSS, Dist. Purba Midnapore under CDD,PHE Dte. | 253/CMSD-I(D) | 23/06/2022 | 15 | DAS ENTERPRISE | 4.65 | 4.65 | 100 | 100
1517 | PURBA MEDINIPUR | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) , SM/09339 | Retrofitting | SUPPLY & DELIBVERY OF 9 7/8'' DIA RR BIT FOR DRILLING WORK AT HAIPUR PWSS, DISTRICT PURBA MEDINIPUR AND OTHER PWSS UNDER CDD, PHE DTE. | 249/CMSD-I | 22/06/2022 | 15 | M.S. ENTERPRISE | 4.21 | 4.21 | 100 | 100
1518 | PURBA MEDINIPUR | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) , SM/09339 | Retrofitting | REPAIRING OF DAMAGE TRUCK DRIVER CABIN, STEEL BODY, CHEQUER PLATE, CHASSIS AND TRUCK BODY PAINTING OF GOVT VEHICLE NO. WMK 6422 (TATA) UNDER CMSD-I (D), CDD, PHE DTE. | 77/CMSD-I | 01/04/2022 | 15 | M/S B.P.TRADING CORPORATION | 2.36 | 0.79 | 100 | 0
1519 | PURBA MEDINIPUR | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) , SM/09339 | Retrofitting | SUPPLY & DELIVERY OF COMPRESSOR PIPE AND HOSE AT SITE FOR COMPRESSOR UNIT ATTACHED WITH RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | 65/CMSD-I (D) | 22/03/2022 | 7 | PADMA ENGINEERING & CO. | 0.98 | 0.98 | 100 | 100
1520 | PURBA MEDINIPUR | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) , SM/09339 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0.35 | 100 | 0
1521 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme under Tamluk Division, PHE Dte. | 1632/TD | 18/01/2022 | 20 | HORIZEN | 3.35 | 3.35 | 100 | 100
1522 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Bishnubar Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-B-B) | 2195/TD | 21/03/2022 | 30 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 39.96 | 39.89 | 100 | 100
1523 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-1) | 455/TD | 01/06/2022 | 15 | GRAND CONSTRUCTION | 4.84 | 4.78 | 100 | 100
1524 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Land filling with earth of approach road and other side of 3rd T/W site at Bishnubar Water Supply scheme of Tamluk Dev. Block under Tamluk Sub-Division of Tamlul Division PHE Dte. | 857/TD | 21/07/2022 | 7 | KRISHNENDU SEKHAR DAS | 4.82 | 4.8 | 100 | 100
1525 | PURBA MEDINIPUR | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BISHNUBAR, NANDAKUMAR BLOCK, DIST : PURBA MEDINIPUR UNDER CDD, PHE DTE. | 145/S&WSD | 12/08/2022 | 15 | PADMA ENGINEERING & CO. | 5 | 4.97 | 100 | 90
1526 | PURBA MEDINIPUR | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | ADDITIONAL DEVELOPMENT OF TUBE WELL BY AIR COMPRESSOR WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BISHNUBAR SCHEME (TW-III) UNDER CDD, PHE DTE. | 360/CMSD-II | 15/07/2022 | 10 | PADMA ENGINEERING & CO. | 0.99 | 0.97 | 100 | 0
1527 | PURBA MEDINIPUR | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BISHNUBAR W/S SCH, NANDAKUMAR BLOCK, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. | 144/S&WSD | 12/08/2022 | 15 | PADMA ENGINEERING & CO. | 5 | 4.98 | 100 | 100
1528 | PURBA MEDINIPUR | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 240 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BISHNUBAR W/S SCH (TW-III), TAMLIK BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 431/CDD | 23/05/2022 | 30 | PADMA ENGINEERING & CO. | 14.26 | 5.58 | 100 | 100
1529 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Purbakola Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- G ) | 1364/TD | 22/09/2022 | 25 | SOUMYA ENTERPRISE | 30.53 | 30.43 | 99.66 | 30
1530 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC (245 nos.) at Jashdumbur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-C-B) | 64/TD | 05/04/2022 | 20 | PULAK KUMAR SAMANTA | 28.02 | 23.63 | 100 | 100
1531 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Bishnubar Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-B-C) | 2196/TD | 21/03/2022 | 20 | CEM ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.98 | 20.77 | 100 | 100
1532 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Jashdumber Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-C-A) | 2197/TD | 21/03/2022 | 30 | GHOSH ENTERPRISE | 45.02 | 44.98 | 100 | 85
1533 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Melahait & Jotankur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- E & I) | 2199/TD | 21/03/2022 | 35 | KRISHNENDU SEKHAR DAS | 74.87 | 74.82 | 100 | 85
1534 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Naikuri Jagannath Chak-I & Khas Panchpukhuria Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- F & J) | 2200/TD | 21/03/2022 | 35 | S.K. MONDAL | 77.9 | 77.77 | 100 | 100
1535 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Jotankur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- H-B ) | 2202/TD | 21/03/2022 | 20 | DEBDUT CONSTRUCTION | 20.89 | 20.57 | 100 | 100
1536 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-2) | 456/TD | 01/06/2022 | 15 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.84 | 4.82 | 100 | 100
1537 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-3) | 457/TD | 01/06/2022 | 15 | MISHRA ENTERPRISE | 4.84 | 4.83 | 100 | 100
1538 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-4) | 458/TD | 01/06/2022 | 15 | SANTRA ENTERPRISE. | 4.85 | 4.85 | 100 | 100
1539 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Bishnubar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 2164/TD | 19/12/2022 | 60 | SK. SAHALAM | 5.11 | 5.1 | 100 | 100
1540 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | New Construction of boundary wall (Length-50 m) with R.C.C structures including provision of M.S. gate at 3nd tube well site under Bishnubar Water Supply Scheme. | 2165/TD | 19/12/2022 | 45 | SK. SAHALAM | 5.83 | 5.81 | 100 | 0
1541 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Bishnubar Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-B-A-5) | 2194/TD | 21/03/2022 | 20 | MADAN MOHAN MAITY | 23.06 | 22.96 | 100 | 100
1542 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Material Requisition To Resource Division | 2350/TD | 31/03/2022 | 0 | Resource Division | 23.8 | 0 | 0 | 0
1543 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Material Requisition To Resource Division | 80/TD | 08/04/2022 | 0 | Resource Division | 38.98 | 0 | 0 | 0
1544 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Electric quotation for Bishnubar PWSS Tube Well-III WS Scheme Additional TW (Ref. ID - 203930212) | BP-2022-23-140 | 20/03/2023 | 0 | WBSEDCL | 3.23 | 0 | 0 | 0
1545 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Hirapur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- H-A ) | 2201/TD | 21/03/2022 | 20 | G. S. CONSTRUCTION | 20.87 | 11.62 | 55.66 | 100
1546 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 405/W/MMD | 16/03/2023 | 180 | DAS ENTERPRISE | 35.46 | 11.06 | 31.19 | 61
1547 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Laying Distribution system of Left-out portion of pipe line and its allied works to accommodate FHTC at Bishnubar water supply scheme in Tamluk Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.PART-C-B(PHASE-II) | 335/TD | 25/04/2023 | 20 | PULAK KUMAR SAMANTA | 6.91 | 5.83 | 84.34 | 100
1548 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Repair & renovation of exisiting pump house and boundary wall at OHR site & 2nd tube well site of Bishnubar PWSS Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. | 934/TD | 01/06/2023 | 30 | MOYNA TECHNOLINK ENGINEER'S CO-OP SOCIETY LTD. | 18.32 | 0 | 0 | 100
1549 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Laying Distribution system of Left-out portion of pipe line and its allied works to accommodate FHTC at Bishnubar water supply scheme in Tamluk Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.PART-A(PHASE-II) | 334/TD | 25/04/2023 | 30 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 58.58 | 54.39 | 92.85 | 100
1550 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Maishali Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-D) | 2198/TD | 21/03/2022 | 35 | BIDHAN MONDAL | 74.98 | 60.06 | 100 | 100
1551 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Material Requisition To Resource Division | 1117/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
1552 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme , SM/09448 | Augmentation | Construction of R.C.C. Elevated Reservoir of capacity 600 cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Bishnubar & its adjoining moujas Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District . (PART-A) | 1820/TD | 14/11/2022 | 870 | HARIPADA PATTANAYAK | 163.96 | 116.5 | 71.05 | 100
1553 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in MUKUNDAPUR PWSS under Ramnagar-I Block , SM/10432 | Retrofitting | Retrofitting to accommodate FHTC (2488 nos.) under JJM in MUKUNDAPUR PWSS Block- Ramnagar-I in the District of Purba Medinipur. | 172/TD | 25/04/2022 | 30 | M/S EL-CON | 90.6 | 0 | 0 | 60
1554 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in MUKUNDAPUR PWSS under Ramnagar-I Block , SM/10432 | Retrofitting | Laying distribution pipe line due to damaged by the construction of connecting Road & to Accommodate balance FHTC (290 Nos) with allied work for Mukundapur Piped Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 3065/TD | 19/09/2024 | 30 | BASANTA KUMAR MAITY | 35.18 | 0 | 0 | 0
1555 | PURBA MEDINIPUR | Tamluk Division | Balance Work for Retrofitting to Accommodate FHTC (300 nos) and Laying of Left-Out Portion UPVC Pipeline due to uncovered area of different Nodal point of Srirampur and its Adjoining Mouzas Water Supply Scheme under JJM within Tamluk Block under Tamluk S , SM/09073 | Retrofitting | Retrofitting to accommodate FHTC (300 Nos.) under JJM in Srirampur PWSS (PART-I) Block - Tamluk in the District of Purba Medinipur. | 1125/TD | 22/11/2021 | 40 | GHOSH ENTERPRISE | 19.58 | 18.98 | 96.9 | 100
1556 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Supply & Delivery of 125 mm dia & 80 mm dia Sluice Valve for Bhagwanpur Zone-I Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-B) (Supply at Mukutshila Store) | 893/TD | 25/07/2022 | 15 | SRIMANTA KUMAR MAITY | 4.8 | 4.8 | 100 | 100
1557 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bhagawanpur Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | 1676/TD | 27/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.46 | 4.46 | 100 | 100
1558 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bhagawanpur Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | 1677/TD | 27/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.19 | 4.19 | 100 | 100
1559 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 200cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bhagwanpur Zone-I Water Supply Scheme within Bhagwanpur-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 691/TD | 27/06/2022 | 180 | TAPAS SANTRA | 597.73 | 567.16 | 94.88 | 82
1560 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional(4th) Tubewell of Augmentation of Bhagwanpur Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia. x 250 mtr. deep tube well by direct rotary rig method at Additonal 3rd Tubewell of Augmentation of Bhajachauli Water Supply Scheme (Mouza - Khalsiberia, JL No. - 138, Plot No. - 162/387) within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 1224/TD | 07/09/2022 | 21 | B. K. ENTERPRISE | 34.31 | 0 | 0 | 0
1561 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (4th) Tube Well site for Augmentation of Bhagwanpur Zone-I Water Supply Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Normal Land). | 1344/TD | 19/09/2022 | 60 | M/S SOURAV MAHAPATRA | 3.82 | 0 | 0 | 0
1562 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION F TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BHAGWANPUR W/S SCHEME, TW-III, Z-I, BLOCK BHAGAWANPUR-I, UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 2115/CDD | 02/03/2023 | 30 | PADMA ENGINEERING & CO. | 17.76 | 16.63 | 93.63 | 0
1563 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (3rd) Tube Well site for Augmentation of Bhagwanpur Zone-II W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Normal Land) | 1281/TD | 12/09/2022 | 60 | BISWA NIRMAN ENTERPRISE. | 3.82 | 3.73 | 100 | 100
1564 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Supply & Delivery of 125 mm dia & 80 mm dia Sluice Valve for Bhagwanpur Zone-II Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-B) (Supply at Mukutshila Store) 2nd Call. | 1299/TD | 13/09/2022 | 15 | NANDY UDYOG | 4.83 | 4.83 | 100 | 100
1565 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Supply & Delivery of 100mm,150mm,200mm,250mm & 300mm dia Sluice Valve for Bhagwanpur Zone-I piped Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) (Supply at Mukutshila Store). 2nd Call | 1297/TD | 13/09/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.41 | 3.41 | 100 | 100
1566 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (3rd) Tube Well site for Augmentation of Bhagwanpur Zone-I W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Normal Land) | 1345/TD | 19/09/2022 | 60 | GIRI CONSTRUCTION | 3.82 | 3.68 | 100 | 100
1567 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Supply & Delivery of 100mm,150mm,200mm,250mm & 300mm dia Sluice Valve for Bhagwanpur Zone-II piped Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) (Supply at Mukutshila Store). 2nd Call. | 1300/TD | 13/09/2022 | 15 | PARTHA CONSTRUCTION | 3.23 | 3.23 | 100 | 100
1568 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 260 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BHAGWANPUR W/S SCH (TW-III), BHAGAWANPUR-II BLOCK UNDER PURBA MEDNAIPORE DISTRICT, CDD, PHE DTE. | 1347/CDD | 24/11/2022 | 30 | PADMA ENGINEERING & CO. | 19.77 | 17.45 | 100 | 100
1569 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Construction and Commissioning of R.C.C. Over Head Reservoir of capacity 500 cum and staging height 20.00 mtr, as per Departmental Drawing no-PC-1/O.H.R./5/2012 for Rejuvination of Bhagwanpur Zone-I Water Supply Scheme under Bhagwanpur-I Block of Contai sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | 2839/TD | 05/02/2021 | 200 | DAS CONSTRUCTION | 118.1 | 15.5 | 100 | 90
1570 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | ADDITIONAL WORKS FOR CONSTRUCTION OF TUBE WELL FOR BHAGAWANPUR W/S SCHEME TW-III, ZONE-I, PURBA MEDINIPU DISTRICT BY UTILISING SKILLED CREW & DEPARTMENTAL MACHINERRIES OF CDD, PHE DTE. | 92/CMSD-II | 17/04/2023 | 15 | PADMA ENGINEERING & CO. | 1 | 0.32 | 100 | 100
1571 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Material Requisition To Resource Division | 403/TD | 25/05/2022 | 0 | Resource Division | 102.66 | 0 | 0 | 0
1572 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Material Requisition To Resource Division | 404/TD | 25/05/2022 | 0 | Resource Division | 28.11 | 0 | 0 | 0
1573 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Material Requisition To Resource Division | 1272/TD | 12/09/2022 | 0 | Resource Division | 59.54 | 0 | 0 | 0
1574 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Electric Quotation for Bhagwanpur Zone-II, TW - III (Ref. ID - 203964030) | BP-2023-24-30 | 04/05/2023 | 0 | WBSEDCL | 0.56 | 0 | 0 | 0
1575 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Electric Quotation for BHAGWANPUR Water Supply Scheme Z-I, T/W-III (Ref. ID-204049532 ) | BP-2023-24-137 | 27/07/2023 | 0 | WBSEDCL | 3.34 | 0 | 0 | 0
1576 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bhagwanpur Zone-II Water Supply Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 726/TD | 04/07/2022 | 180 | TARUN KOLEY | 595.09 | 532.66 | 89.51 | 83
1577 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) under JJM Program under MMD PHE Dte. | 848/W/MMD | 24/03/2023 | 180 | BHABANI PRASAD MANNA | 59.25 | 18.74 | 31.63 | 35
1578 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Laying of 90 mm dia UPVC pipe lines with allied works to accommodate Total 5666 nos FHTC of Augmentation of Bhagwanpur Zone-I & its adjoining mouzas W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 623/TD | 17/05/2023 | 30 | TAPAS SANTRA | 67.97 | 55.64 | 81.86 | 85
1579 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Laying of Rising Main DI(K9) pipe line with CIDF Pipe & Speacials for interconnection in between 3rd TW & OHR of Augmentation of Bhagabanpur Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. | 2597/TD | 10/10/2023 | 20 | TAPAS SANTRA | 9.63 | 0 | 0 | 0
1580 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Bhagabanpur Zone-II PWSS in Bhagwanpur-I Dev. Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-50.00 mtr.)For Low Land. | 2696/TD | 17/10/2023 | 30 | BHOWMIK & SONS | 8.66 | 6.39 | 73.81 | 100
1581 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Boundary Wall, Raising Main, Approch Road , Repairing work of Boundary wall and Pump House, under JJM with allied work for Augmentation of Bhagabanpur Zone -I PWSS in Bhagwanpur-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 725/TD | 28/02/2024 | 40 | M/S. PRADIP PRADHAN | 32.11 | 0 | 0 | 0
1582 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Laying of 200 mm dia & 150 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials in between 1st Tube well to 2nd Tube Well & 2nd Tube well to 3rd Tube Well (Additional) of Augmentation of Bhagwanpur Zone II & its adjoining mouzas Water Supply Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 297/TD | 20/04/2023 | 30 | BARH CONSTRUCTION | 11.04 | 8.14 | 100 | 100
1583 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Laying of 90 mm dia UPVC Pipe Lines With allied works to accommodate Total 4010 nos FHTC of Augementation of Bhagabanpur Zone -II Water Supply Scheme within Bhagabanpur -I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 2874/TD | 17/11/2023 | 30 | TARUN KOLEY | 79.77 | 78.53 | 100 | 100
1584 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Boundary Wall, Raising Main, Approach Road , Repairing work of Boundary wall and Pump House, under JJM with allied work for Augmentation of Bhagabanpur Zone -I PWSS in Bhagwanpur-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 3293/TD | 05/10/2024 | 120 | SAMIT KUMAR MONDAL | 31.76 | 0 | 0 | 60
1585 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Repairing of Boundary Wall, and Pump House (1st & 2nd) under JJM with allied work for Augmentation of Bhagabanpur Zone -II PWSS in Bhagwanpur-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 3216/TD | 01/10/2024 | 120 | SAMIT KUMAR MONDAL | 8.34 | 0 | 0 | 100
1586 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Construction of Approach Road at 4th TW site for Augmentation of Bhagabanpur Zone-I PWSS in Bhagwanpur-I Dev. Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur.(Length-58 mtr.) | 570/TD | 17/02/2025 | 25 | CHANDA AGENCIES | 4.92 | 0 | 0 | 0
1587 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Renovation and new Construction of Boundary Wall (as per Departmental Design & Drawing) at OHR site for Augmentation of Bhagabanpur Zone-II Water Supply Scheme in Bhagabanpur-I Dev. Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1077/TD | 07/04/2025 | 40 | RAI CONSTRUCTION | 18.27 | 0 | 0 | 0
1588 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) , SM/10125 | Augmentation | Interconection work Between 2nd pump and 3rd pump , of Augementation of Bhagabanpur Zone-II water supply scheme under Contai Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. | 2445/CSD | 22/10/2024 | 21 | BARH CONSTRUCTION | 0.52 | 0 | 0 | 0
1589 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme , SM/09276 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kapasberia Water Supply Scheme under Tamluk Division, PHE Dte. | 1167/TD | 01/12/2021 | 7 | HORIZEN | 3.42 | 3.31 | 100 | 100
1590 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme , SM/09276 | Augmentation | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Kapaseria W/S Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head work Site of Rajarampur W/S Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Tabakhali W/S Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 976/TD | 03/08/2022 | 21 | SIMPLEX DRILLING COMPANY | 58.06 | 19.52 | 100 | 100
1591 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme , SM/09276 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Kapaseria Water Supply Scheme under Haldia Sub-Division of Tamluk Division in Purba Medinipur District | 1051/TD | 07/06/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.73 | 3.73 | 100 | 100
1592 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme , SM/09276 | Augmentation | Material Requisition To Resource Division | 1254/TD | 13/12/2021 | 0 | Resource Division | 10.46 | 0 | 0 | 0
1593 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme , SM/09276 | Augmentation | Material Requisition To Resource Division | 639/TD | 27/06/2022 | 0 | Resource Division | 5.6 | 0 | 0 | 0
1594 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme , SM/09276 | Augmentation | Crossing permission of laying HDPE pipeline along and across of NH-116 of Kapaseria Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3286/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 9.41 | 1.04 | 11.01 | 30
1595 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme , SM/09276 | Augmentation | Laying of proposed Rising main line and inter connection including repairing & renovation of switch room cum chlorine room at Head work site of Kapasaria Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2737/TD | 01/11/2023 | 20 | R CONSTRUCTION | 8.2 | 6.06 | 100 | 10
1596 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme , SM/09276 | Augmentation | Construction Temporary Approach road by Brick Bats & Carried Earth over Nayanjuli of PWD Roads for H/W Site of Kapasaria W/S Scheme for accessibility of Rig Machine and removal of road materials from Nayanjuli of PWD Roads under Haldia Sub-Division of Tamluk Division, PHE Dte., Purba Medinipur District. | 576/HSD, | 08/12/2023 | 7 | SNEHASIS BERA | 0.8 | 0.8 | 100 | 100
1597 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme , SM/09276 | Augmentation | Augmentation of ground water based Kapaseria Water Supply Scheme by Providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 100 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 269/TD | 02/05/2022 | 1340 | MONDAL PRECISION PRIVATE LIMITED | 222.44 | 119.87 | 53.89 | 60
1598 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme , SM/09276 | Augmentation | Construction of New Boundary Wall at H/W site & 2nd TW Site of Kapasaria Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall- 80mtr at H/W Site & 50mtr at 2nd TW Site) | 3948/TD | 23/12/2024 | 190 | ANIRBAN BHOWMIK | 15.18 | 0 | 0 | 0
1599 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme , SM/09276 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme, Block Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 809/W/MMD | 24/03/2023 | 180 | RITESH ENTERPRISE | 13.59 | 12.86 | 100 | 90
1600 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme under Tamluk Division, PHE Dte. | 1181/TD | 02/12/2021 | 20 | HORIZEN | 6.91 | 5.92 | 100 | 100
1601 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Supply of 80 mm.dia C.I D.F sluice valve for laying distribution & rising main pipe line of Kalindi W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1049/TD | 17/08/2022 | 7 | BASANTA KUMAR MAITY | 4.72 | 4.72 | 100 | 100
1602 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Supply & delevary of 100 mm,200mm,150mm & 250mm dia C.I D.F sluice valve for laying distribution & rising main pipe line of Kalindi W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1155/TD | 31/08/2022 | 7 | BASANTA KUMAR MAITY | 4.28 | 4.28 | 100 | 100
1603 | PURBA MEDINIPUR | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 240 mtrs. Depth) by utilising Departmental machineries for Kalindi W/S Scheme(TW-I), Ramnagar-II block under Purba medinipur District, CDD PHE Dte. | 857/CDD | 10/07/2023 | 30 | MENAKA ENTERPRISE | 18.74 | 14.63 | 100 | 100
1604 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Supply of 125 mm.dia C.I D.F sluice valve for laying distribution & rising main pipe line of Kalindi W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 323/DSD | 15/07/2022 | 7 | BASANTA KUMAR MAITY | 1.32 | 1.32 | 100 | 100
1605 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Material Requisition To Resource Division | 1260/TD | 13/12/2021 | 0 | Resource Division | 21.19 | 0 | 0 | 0
1606 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Material Requisition To Resource Division | 2348/TD | 31/03/2022 | 0 | Resource Division | 16.82 | 0 | 0 | 0
1607 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Laying Rising Main Pipe Line With allied Works For Augmentation Of KALINDI Water Supply Scheme In Ramnagar-II Block Of Purba Medinipur District | 3223/TD | 14/03/2023 | 20 | ABHIJIT BERA | 6.86 | 6.34 | 100 | 100
1608 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Laying of Distribution pipe line by UPVC pipes with allied works for complete balance FHTC under Kalindi & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 1449/TD | 13/07/2023 | 30 | BASANTA KUMAR MAITY | 24.44 | 23.58 | 100 | 100
1609 | PURBA MEDINIPUR | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Providing drilling crews Including Allied Materials for construction of Tube Well at Kalindi within Ramnagar-II Block, District Purba Medinipur under Central Drilling Division, P.H.E. Dte. | 1536/CDD | 06/10/2023 | 180 | MENAKA ENTERPRISE | 8.73 | 5.11 | 100 | 100
1610 | PURBA MEDINIPUR | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Resistivity Survey and other works of Kalindi WS Scheme (TW-Il) , Ramnagar-ll Block under Purba Midnapore District, Central Drilling Division, P.H.E. Dte. | 1540/CDD | 08/12/2022 | 480 | MENAKA ENTERPRISE | 12.67 | 9.92 | 100 | 100
1611 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Augmentation of ground water based Kalindi Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Ramnagar-II Dev. Block under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2185/TD | 17/03/2022 | 180 | BASANTA KUMAR MAITY | 533.41 | 376.04 | 70.5 | 50
1612 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. , SM/09278 | Augmentation | Renovation & Repairing of existing pump house I & II, Boundary Wall at head works & 2nd tube well site of Kalindi Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 3401/TD | 28/10/2024 | 40 | DAS ENTERPRISE. | 9.65 | 0 | 0 | 0
1613 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. , SM/09280 | Augmentation | Rejuvenation & Retrofitting of ground water based Haur PWSS & its adjoining moujas within Panskura Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. (Part-A) | 137/TD | 19/04/2022 | 90 | ASIS KUMAR SARANGI | 192.27 | 114.53 | 59.57 | 90
1614 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. , SM/09280 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Haur Water Supply Scheme under Tamluk Division, PHE Dte. | 1191/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 5.95 | 5.95 | 100 | 100
1615 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. , SM/09280 | Augmentation | Material Requisition To Resource Division | 2343/TD | 31/03/2022 | 0 | Resource Division | 11.07 | 0 | 0 | 0
1616 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. , SM/09280 | Augmentation | Material Requisition To Resource Division | 1111/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
1617 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. , SM/09280 | Augmentation | Rejuvenation & Retrofitting of ground water based Haur PWSS & its adjoining moujas within Panskura Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. (Part-B) | 53/TD | 05/04/2022 | 60 | MUNNA AGROTECH ENTERPRISE | 150.85 | 99.71 | 66.1 | 90
1618 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. , SM/09280 | Augmentation | Proposed Left out portion of pipe line Rejuvenation & Retrofitting of of HAUR PWSS under Tamluk Sub Division, PHE Dte. (PART- B) | 3064/TD | 19/09/2024 | 25 | KAMALA ENTERPRISE | 14.42 | 0 | 0 | 0
1619 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. , SM/09280 | Augmentation | Construction of Boundary Wall ( 1mtr height) & Painting Pump House and Boundary wall & other allied works at 1 st TW site, Dismantling of Existing B/W & Construction of Boundary Wall with Gate and along PCC road & other allied works at 2nd TW site of Haur Pipe Water Supply Scheme, within Panskura-I Block under Tamluk Sadar Sub-Division of Tamluk Division, PHE Dte. | 736/TD | 07/03/2025 | 40 | SINHA BUILDERS | 9.71 | 0 | 0 | 0
1620 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -B). | 1039/TD | 16/08/2022 | 45 | I. S. ENTERPRISE. | 154.56 | 102.85 | 66.54 | 70
1621 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -J) | 1333/TD | 16/09/2022 | 20 | SUBRATA KUMAR BERA | 35.6 | 23.71 | 66.6 | 70
1622 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -F) | 2241/TD | 29/12/2022 | 20 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LIMITED | 32.16 | 19.73 | 61.33 | 65
1623 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -E) | 1338/TD | 16/09/2022 | 30 | A. K. SIKDAR | 69.34 | 36.22 | 52.24 | 60
1624 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Material Requisition To Resource Division | 1195/TD | 06/09/2022 | 0 | Resource Division | 186.74 | 0 | 0 | 0
1625 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Material Requisition To Resource Division | 1197/TD | 06/09/2022 | 0 | Resource Division | 47.95 | 0 | 0 | 0
1626 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Electric Quotation for Chargeable Head, MUKUTSHILA, Water Supply Scheme T/W-IV, Zone-II (Ref. ID-204049562) | BP-2023-24-160 | 04/08/2023 | 0 | WBSEDCL | 1.51 | 0 | 0 | 0
1627 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Electric Quotation for MUKUTSHILA, Water Supply Scheme T/W-V, Zone-II (Ref. ID-204049558) | BP-2023-24-162 | 04/08/2023 | 0 | WBSEDCL | 2.26 | 0 | 0 | 0
1628 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 1000 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II water supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -A) | 1112/TD | 29/08/2022 | 180 | M/S. CARE | 361.65 | 60.86 | 44.46 | 18
1629 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -K) | 2100/TD | 13/12/2022 | 722 | M/S. NEW DINDA ENTERPRISE | 41.85 | 39.6 | 94.62 | 85
1630 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -G) | 1387/TD | 23/09/2022 | 25 | NEW STAR CONSTRUCTION | 76.73 | 68.22 | 88.91 | 85
1631 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -L) | 1334/TD | 16/09/2022 | 25 | THREE MAA ENTERPRISE | 41.22 | 29.45 | 71.46 | 85
1632 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -M) | 1335/TD | 16/09/2022 | 25 | ANUSKA ENTERPRISE | 51.96 | 38.82 | 74.71 | 75
1633 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -I) | 2341/TD | 10/01/2023 | 25 | MRINAL KANTI PRADHAN | 44.01 | 32.43 | 73.69 | 0
1634 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2)under JJM Program under MMD PHE Dte. | 1377/W/MMD | 30/05/2023 | 180 | MENAKA ENTERPRISE | 35.5 | 31.24 | 88.01 | 75
1635 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Land Filling & allied works for Boosting Tube Well (5Th TW) site of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1488/A/CSD | 03/08/2023 | 15 | KAMAL KUMAR BERA | 0.72 | 0.71 | 100 | 100
1636 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Bill for Restoration of damage of Heria Mugberia Road at 1.80 KM caused due to lying of PHE water pipe line across the road under Tamluk Highway Division of Mukutshilla Zone-II PWSS | BP-2024-25-495 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.19 | 0 | 0 | 0
1637 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -D) | 1002/TD | 08/08/2022 | 897 | GIRI CONSTRUCTION | 106.79 | 92.03 | 86.17 | 88
1638 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -C) | 1079/TD | 23/08/2022 | 867 | RELIABLE CONSTRUCTIONS | 130.52 | 103.15 | 79.03 | 80
1639 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) , SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -H) | 1332/TD | 16/09/2022 | 20 | PULAK KUMAR SAMANTA | 28 | 23.39 | 83.54 | 85
1640 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Replacement of Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 2nd Tube well Site of Sherkhanchak Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at Replacement of 1st Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 4th Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1223/TD | 07/09/2022 | 40 | KALPANA BUILDERS | 71.97 | 49.28 | 91.3 | 48
1641 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Repairing of Switch Room cum Chlorin Room and Interconnection work of Rising Main at 1st TW site for Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 0 | 28/11/2023 | 45 | GIRI CONSTRUCTION | 0 | 0 | 0 | 0
1642 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Material Requisition To Resource Division | 1193/TD | 06/09/2022 | 0 | Resource Division | 97.03 | 0 | 0 | 0
1643 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Way Leave permission from South Eastern Railway for Mukutshilla Zone-II PWSS for Application ID ¿ SER-KGP-2023-WL-33 | BP-2023-24-204 | 25/07/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0 | 0
1644 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Way Leave permission from South Eastern Railway for Mukutshilla Zone-II PWSS for Application ID-SER-KGP-2023-WL-34 | BP-2023-24-256 | 10/08/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.27 | 0 | 0 | 0
1645 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Way Leave permission from South Eastern Railway for Mukutshilla Zone- II PWSS for Application ID ¿ SER-KGP-2023-WL-32 | BP-2023-24-203 | 25/07/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0 | 0
1646 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Way Leave permission from South Eastern Railway for Mukutshilla Zone- II PWSS for Application ID ¿ SER-KGP-2023-WL-30 | BP-2023-24-201 | 25/07/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0 | 0
1647 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Way Leave permission from South Eastern Railway for Mukutshilla Zone- II PWSS for Application ID ¿ SER-KGP-2023-WL-31 | BP-2023-24-202 | 25/07/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0 | 0
1648 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 1000 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II water supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -A) | 1112/TD | 29/08/2022 | 180 | M/S. CARE | 361.65 | 0 | 0 | 18
1649 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART Work Order- B) | 59/TD | 05/01/2024 | 20 | MAJI ENGINEERING WORKS | 0.96 | 0 | 0 | 0
1650 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-B for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | 1911/TD | 07/06/2024 | 25 | DEBABRATA DAS | 14.72 | 14.31 | 97.24 | 90
1651 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Land Filling & allied works for 3rd TW site of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1490/CSD | 04/08/2023 | 15 | GIRI ENTERPRISE | 0.96 | 0.96 | 100 | 100
1652 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 250 mm Dia HDPE (PE-100) Carrier Pipe in between OHE MAST NO 32/4 & 32/5 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =46 Mtr) Nodal Point 18 to 19. | 2945/TD | 23/11/2023 | 25 | ROY CONSTRUCTION | 64.87 | 59.78 | 100 | 100
1653 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 33/1 & 33/2 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =61 Mtr) Nodal Point 5 to 109. | 2947/TD | 23/11/2023 | 25 | BISWAJIT BAG | 71.16 | 71.07 | 100 | 100
1654 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 33/17 & 33/18 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =61 Mtr) Nodal Point 55 to 58. | 2948/TD | 23/11/2023 | 25 | ROY CONSTRUCTION | 68.36 | 67.46 | 100 | 100
1655 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 34/2 & 34/3 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =54 Mtr) Nodal Point 253 to 182. | 2949/TD | 23/11/2023 | 25 | ZENITH CONSTRUCTION | 69.67 | 64.84 | 100 | 100
1656 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 31/13 & 31/14 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =38 Mtr) Nodal Point 64 to 68. | 2946/TD | 23/11/2023 | 25 | JOY GURU TRADING | 65.18 | 62.73 | 100 | 100
1657 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District.(PART Work Order - A) | 58/TD | 05/01/2024 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 8.43 | 8.43 | 100 | 100
1658 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Repairing of Switch Room cum Chlorin Room and Interconnection work of Rising Main at 1st TW site for Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 2157/CSD | 04/12/2023 | 136 | GIRI CONSTRUCTION | 2.26 | 0 | 0 | 100
1659 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-G for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | 569/TD | 15/02/2024 | 20 | NEW STAR CONSTRUCTION | 9.63 | 9.52 | 100 | 100
1660 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 1000 cum RCC OHR at Mukutshila Z-II Water Supply Scheme at Khejuri-I Block under Tamluk Division, PHE Dte. | 1048/TD | 15/03/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
1661 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mukutshila Water Supply Scheme (Zone- II) under Tamluk Division, PHE Dte. | 46/TD | 05/04/2022 | 20 | INDRANIL DUTTA & ASSOCIATES | 5.82 | 0 | 0 | 0
1662 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-H for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | 570/TD | 15/02/2024 | 20 | PULAK KUMAR SAMANTA | 6.98 | 0 | 0 | 80
1663 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-C for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | 577/TD | 15/02/2024 | 20 | RELIABLE CONSTRUCTIONS | 13.64 | 9.1 | 66.67 | 100
1664 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-L for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 726/TD | 28/02/2024 | 30 | ROY BISWAS CONSTRUCTION | 4.8 | 0 | 0 | 0
1665 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-D for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | 1948/TD | 10/06/2024 | 244 | DEBABRATA DAS | 10.35 | 2.68 | 25.87 | 80
1666 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-J for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | 2184/CSD | 05/09/2024 | 150 | GIRI ENTERPRISE | 1.85 | 0 | 0 | 0
1667 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Laying Distribution pipe line by HDPE pipes with allied works for Left Out Area of PART-K for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Phase-II) | 3051/TD | 19/09/2024 | 150 | M/S. NEW DINDA ENTERPRISE | 49.94 | 0 | 0 | 0
1668 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of (PART M) for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri I Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE II) | 3036/TD | 18/09/2024 | 150 | M/S. NEW DINDA ENTERPRISE | 4.18 | 0 | 0 | 0
1669 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10589 | Augmentation | Rising main 200mm dia DI(K9) Rising main pipeline with specials and other allied works at 4th Tube Well Site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 590/TD | 19/02/2025 | 30 | M/S. NEW DINDA ENTERPRISE | 4.09 | 0 | 0 | 0
1670 | PURBA MEDINIPUR | Tamluk Division | Sinking of Boosting Tube Well and Allied Works to Accommodate FHTC under JJM in Kanaidighi PWSS under Contai-III Block. , SM/11613 | Augmentation | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube well of 1st Tubewell at Mouza- Baliarpur, JL. No. -358 for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method of Boosting Tube well of 3rd Tubewell at Mouza- Madhusudhanbar, JL. No. 365, Plot No. 237 - for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Mouza -Bhaitghar, JL No. - 415, Plot No. -287, Contai- III Block of Kanaidighi Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1051/TD | 18/08/2022 | 40 | AQUATECH ENGINEER | 54.66 | 0 | 0 | 32
1671 | PURBA MEDINIPUR | Midnapore Mechanical | Sinking of Boosting Tube Well and Allied Works to Accommodate FHTC under JJM in Kanaidighi PWSS under Contai-III Block. , SM/11613 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sinking of Boosting Tube Well and Allied Works to Accommodate FHTC under JJM in Kanaidighi PWSS under Contai-III Block, under JJM Program under MMD PHE Dte. | 639/W/MMD | 20/03/2023 | 180 | A.M.S. ENTERPRISE | 13.59 | 0 | 0 | 0
1672 | PURBA MEDINIPUR | Tamluk Division | Sinking of Boosting Tube Well and Allied Works to Accommodate FHTC under JJM in Kanaidighi PWSS under Contai-III Block. , SM/11613 | Augmentation | Material Requisition To Resource Division | 358/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0 | 0
1673 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12279 | Augmentation | Material Requisition To Resource Division | 614/TD | 17/05/2023 | 0 | Resource Division | 30.14 | 0 | 0 | 0
1674 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12279 | Augmentation | Material Requisition To Resource Division | 1664/TD | 03/11/2022 | 0 | Resource Division | 325.57 | 0 | 0 | 0
1675 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12279 | Augmentation | Contai S.A Zone -III W/S scheme PH-II Application no.-2004474775 ref.-204117777 |  | 15/12/2023 | 0 | WBSEDCL | 4.72 | 0 | 0 | 0
1676 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12279 | Augmentation | Laying of distribution pipe line to accommodate FHTC (4893 Nos) with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 2063/TD | 09/12/2022 | 841 | TARUN KOLEY | 1059.62 | 828.04 | 78.15 | 80
1677 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12279 | Augmentation | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 2340/TD | 10/01/2023 | 40 | M/S SYCHROTECH INDUSTRY | 57.41 | 30.27 | 52.73 | 60
1678 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12279 | Augmentation | Pump House and Rising main, under Augmentation of Contai Saline Area Zone-III (Phase-B) PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 2199/TD | 01/09/2023 | 40 | S B ENTERPRISE | 25.16 | 19.96 | 100 | 100
1679 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12279 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone- I) under Tamluk Division, PHE Dte. | 47/TD | 05/04/2022 | 20 | INDRANIL DUTTA & ASSOCIATES | 5.82 | 0 | 0 | 0
1680 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12279 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone- III) under Tamluk Division, PHE Dte. | 48/TD | 05/04/2022 | 20 | INDRANIL DUTTA & ASSOCIATES | 8.67 | 0 | 0 | 0
1681 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12279 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I and III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | 822/W/MMD | 24/03/2023 | 720 | P.K.ENGINEERING | 40.78 | 28.91 | 70.91 | 80
1682 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12279 | Augmentation | Supply of documents for way leave permission of Railway Track Between NACHINDA-KANTHI Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I (Phase-A) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (TD-46/09-10) | 141/CSD | 16/01/2025 | 20 | SUBHENDU HAZRA | 1.16 | 0 | 0 | 0
1683 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/12279 | Augmentation | Laying of Damaged HDPE Pipe line of 180 mm dia with allied works under Augmentation of Contai Saline area Zone-III( Phase-B) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(N.P.-1074 -1084 Part) | 1342/CSD | 02/06/2025 | 21 | JASODA ENTERPRISE | 0.88 | 0 | 0 | 100
1684 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) , SM/11617 | Augmentation | Instalation of display Board at different work site of Augmentation of Shilaberia Zone-I-1 no, Shilaberia Zone-II-1 no, Durmuth-1 no, Amarshikasba Zone-I-1 no, Amarshikasba Zone-II-1 no, Golaranij-1 no & Mukutshila Zone-I-1 no PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 809 / CSD | 21/10/2022 | 15 | THE GODFATHER TRADING COMPANY | 0.81 | 0.81 | 100 | 100
1685 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) , SM/11617 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-B) | 397/TD | 27/04/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 2.02 | 2.02 | 100 | 100
1686 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) , SM/11617 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-A) | 396/TD | 27/04/2023 | 20 | MA SARADA ENTERPRISE | 8.14 | 8.14 | 100 | 100
1687 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) , SM/11617 | Augmentation | Material Requisition To Resource Division | 1657/TD | 03/11/2022 | 0 | Resource Division | 106.02 | 0 | 0 | 0
1688 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) , SM/11617 | Augmentation | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-III, Zone-I (Ref. ID-204049557) | BP-2023-24-154 | 04/08/2023 | 0 | WBSEDCL | 2.55 | 0 | 0 | 0
1689 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) , SM/11617 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) under JJM Program under MMD PHE Dte. | 812/W/MMD | 24/03/2023 | 714 | DEBJYOTI BASU | 54.33 | 28.88 | 53.16 | 25
1690 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) , SM/11617 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1653/TD | 02/11/2022 | 1032 | TAPAS SANTRA | 997.19 | 251.77 | 65.1 | 70
1691 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) , SM/11617 | Augmentation | Repair and renovation of of Boundary Wall (as per Departmental Design & Drawing) at OHR site for Augmentation of Shillaberia Jhanka Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Length-78.00 mtr.) | 2324/TD | 23/07/2024 | 40 | S.D. CONSTRUCTION | 10.42 | 0 | 0 | 0
1692 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) , SM/11617 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Shillaberia Jhanka Zone-I PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. ii) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 4th Tube Well Site for Shillaberia Jhanka Zone-I PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | 3144/TD | 09/03/2023 | 40 | B. K. ENTERPRISE | 35.19 | 33.45 | 100 | 100
1693 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) , SM/11617 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Shilaberia Janka Water Supply Scheme (Zone- I) under Tamluk Division, PHE Dte. | 45/TD | 05/04/2022 | 20 | INDRANIL DUTTA & ASSOCIATES | 5.26 | 0 | 0 | 0
1694 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) , SM/11617 | Augmentation | Name of Work: i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 4th TW site for Augmentation of Shillaberia Jhanka Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Shillaberia Jhanka Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iii) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Augmentation of Shillaberia Jhanka Zone-I & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) iv) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Shillaberia Jhanka Zone-I & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) v) Rising main and other allied works Augmentation of Shillaberia Jhanka Zone-I W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3218/TD | 14/03/2023 | 843 | BARH CONSTRUCTION | 46.11 | 7.76 | 16.82 | 80
1695 | PURBA MEDINIPUR | Central Drilling | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 280 mtrs. Depth) by utilising Departmental machineries for Tikashi W/S Scheme (TW-III), Khejuri-I block under Purba Midnapore District, CDD PHE Dte. | 21/CDD | 04/04/2023 | 30 | MENAKA ENTERPRISE | 15.48 | 12.17 | 100 | 100
1696 | PURBA MEDINIPUR | Central Drilling | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Providing drilling crew and other allied works for construction of Tube Well (250 mm X 150mm X 280mm Depth) by utilising Departmental Machineries for Tikashi W/S Scheme(TW-I), Khejuri-I Block under Purba Medinipur District, CDD,P.H.E.Dte. | 850/CDD | 10/07/2023 | 30 | UNIVERSAL ENTERPRISES | 15.71 | 12.88 | 100 | 100
1697 | PURBA MEDINIPUR | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Material Requisition To Resource Division | 2978/TD | 27/02/2023 | 0 | Resource Division | 42.38 | 0 | 0 | 0
1698 | PURBA MEDINIPUR | Midnapore Mechanical | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Electric Quotation for TIKASHI, Water Supply Scheme T/W-II, (Ref. ID-204049560) | BP-2023-24-161 | 04/08/2023 | 0 | WBSEDCL | 2.41 | 0 | 0 | 0
1699 | PURBA MEDINIPUR | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Instalation of display Board at different work site of Tikashi & Adjoining Moujas New PWSS in Khejuri-I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2330/CSD | 29/12/2023 | 7 | M/S. NEW DINDA ENTERPRISE | 0.21 | 0.21 | 100 | 100
1700 | PURBA MEDINIPUR | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Material Requisition To Resource Division | 2979/TD | 12/09/2024 | 0 | Resource Division | 15.26 | 0 | 0 | 0
1701 | PURBA MEDINIPUR | Midnapore Mechanical | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Electric Quotation for TIKASHI Water Supply Scheme T/W-I, (Ref. ID-204134790) | BP-2023-24-440 | 19/12/2023 | 0 | WBSEDCL | 5.13 | 0 | 0 | 0
1702 | PURBA MEDINIPUR | Midnapore Mechanical | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Additional quotation for Tkashi w/s swcheme PH I at Khejuri I Block in the District of Purba Medinipur under MMD PHE Dte. (Application ID 100000100192 Dated 12.02.2024 Ref ID 860292212) | BP-2023-24-715 | 20/02/2024 | 0 | WBSEDCL | 0.84 | 0 | 0 | 0
1703 | PURBA MEDINIPUR | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Laying distribution pipe line, Boundary Wall, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-V) | 272/TD | 20/04/2023 | 60 | MRINAL KANTI PRADHAN | 61.5 | 41.07 | 66.77 | 60
1704 | PURBA MEDINIPUR | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VI) | 273/TD | 20/04/2023 | 737 | PARIA ENTERPRISE | 38.1 | 23.31 | 61.2 | 65
1705 | PURBA MEDINIPUR | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VII) | 274/TD | 20/04/2023 | 25 | DEBABRATA DAS | 10.89 | 7.92 | 72.78 | 74
1706 | PURBA MEDINIPUR | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VIII) | 275/TD | 20/04/2023 | 737 | PARIA ENTERPRISE | 46.77 | 39.65 | 84.78 | 85
1707 | PURBA MEDINIPUR | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Laying distribution pipe line & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-III) | 271/TD | 20/04/2023 | 786 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 97.2 | 56.76 | 58.4 | 60
1708 | PURBA MEDINIPUR | Midnapore Mechanical | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TIKASHI and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1266/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 25.14 | 22.33 | 88.82 | 88
1709 | PURBA MEDINIPUR | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-IX) | 1007/TD | 05/06/2023 | 25 | DEBABRATA DAS | 14.02 | 9.94 | 70.87 | 73
1710 | PURBA MEDINIPUR | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Pump House,350 cum OHR (Intze type with pile foundation), Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-I) | 1043/TD | 07/06/2023 | 755 | TAPAS SANTRA | 245.15 | 134.79 | 54.98 | 85
1711 | PURBA MEDINIPUR | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Pump House , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-II) | 537/TD | 12/05/2023 | 566 | GIRI CONSTRUCTION | 139.39 | 111.43 | 79.94 | 80
1712 | PURBA MEDINIPUR | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. , SM/12482 | New | Laying distribution pipe line & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-IV) | 509/TD | 11/05/2023 | 45 | B M ENTERPRISE | 81.75 | 40.93 | 50.07 | 60
1713 | PURBA MEDINIPUR | Tamluk Division | SIMULYA & IT'S ADJOINING MOUJAS PWSS , SM/12492 | New | Material Requisition To Resource Division | 2725/TD | 06/02/2023 | 0 | Resource Division | 58.93 | 0 | 0 | 0
1714 | PURBA MEDINIPUR | Tamluk Division | SIMULYA & IT'S ADJOINING MOUJAS PWSS , SM/12492 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Simulya PWSS at Bhagwanpur-I Block under Tamluk Division, PHE Dte. | 2203/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
1715 | PURBA MEDINIPUR | Midnapore Mechanical | SIMULYA & IT'S ADJOINING MOUJAS PWSS , SM/12492 | New | Quotation Bill for New Service connection at T/W NO-II Of SIMULIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No-2004691120/QUOT/03 DT. 19-04-2024 Application NO- 2004691120 Application type-New connection Consumer Id- 204280540 | BP-2024-25-142 | 09/05/2024 | 0 | WBSEDCL | 11.94 | 0 | 0 | 0
1716 | PURBA MEDINIPUR | Midnapore Mechanical | SIMULYA & IT'S ADJOINING MOUJAS PWSS , SM/12492 | New | Quotation Bill for New Service connection at T/W NO-I Of SIMULIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No-2004686956/QUOT/03 DT. 19-04-2024 Application NO- 2004686956 Application type-New connection Consumer Id- 204277583 | BP-2024-25-143 | 09/05/2024 | 0 | WBSEDCL | 2.78 | 0 | 0 | 0
1717 | PURBA MEDINIPUR | Midnapore Mechanical | SIMULYA & IT'S ADJOINING MOUJAS PWSS , SM/12492 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SIMULYA and ADJOINING MOUJAS, Block - Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 525/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 19.94 | 84.12 | 80
1718 | PURBA MEDINIPUR | Tamluk Division | SIMULYA & IT'S ADJOINING MOUJAS PWSS , SM/12492 | New | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2740 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SIMULYA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 451/TD | 04/05/2023 | 876 | TARUN KOLEY | 663.05 | 209.12 | 31.54 | 35
1719 | PURBA MEDINIPUR | Central Drilling | RAMCHANDRAPUR AND ADJOINING MOUJAS , SM/12147 | New | Providing drilling crew and other works for construction of Tube Well (300 mm X 200 mm x 230 Mtrs. Depth) by utilising Departmental Machineries for Ramchandrapur W/S Scheme (T/W-III), Moyna Block under Purba Medinipur Distrct, CDD PHE Dte. | 543/CDD | 02/06/2023 | 30 | WIZARDTECH SOLUTION | 17.72 | 15.95 | 100 | 100
1720 | PURBA MEDINIPUR | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS , SM/12147 | New | Material Requisition To Resource Division | 2429/TD | 16/01/2023 | 0 | Resource Division | 23.04 | 0 | 0 | 0
1721 | PURBA MEDINIPUR | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS , SM/12147 | New | Laying distribution System & Accommodate FHTC (520 nos) with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-C,MOUZA-SHRI BRINDABAN CHAK) | 3215/TD | 14/03/2023 | 993 | MAA KALI CONSTRUCTION | 71.8 | 40.8 | 56.82 | 55
1722 | PURBA MEDINIPUR | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS , SM/12147 | New | Laying distribution System, Accommodate FHTC (700 Nos) & Construction of Boundary Wall with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-B,MOUZA-UTTAMPUR) | 523/TD | 11/05/2023 | 911 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 136.15 | 90.38 | 66.39 | 65
1723 | PURBA MEDINIPUR | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS , SM/12147 | New | Soil investigation & R.C.C. Elevated Reservoir of capacity 350cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 170/TD | 09/01/2024 | 180 | SATYABRATA BHAUMIK | 133.51 | 45.78 | 34.29 | 10
1724 | PURBA MEDINIPUR | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS , SM/12147 | New | Earth work in filling by carried earth and Construction of link Road for Ramchandrapur and its adjoining mouzas new Piped Water Supply Scheme at Head Work Site within Moyna Block, under Tamluk Sub-Divn. of Tamluk Division. P.H.E.Dte. Purba Medinipur. | 563/TD | 15/02/2024 | 20 | KIRON CONSTRUCTION | 5.66 | 0 | 0 | 11
1725 | PURBA MEDINIPUR | Central Drilling | RAMCHANDRAPUR AND ADJOINING MOUJAS , SM/12147 | New | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Ramchandrapur W/S Scheme (T/W -II ) , Moyna Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 542/CDD | 02/06/2023 | 374 | UNIVERSAL ENTERPRISES | 17.74 | 14.87 | 100 | 100
1726 | PURBA MEDINIPUR | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS , SM/12147 | New | Material Requisition To Resource Division | 1570/TD | 23/04/2024 | 0 | Resource Division | 13.75 | 0 | 0 | 0
1727 | PURBA MEDINIPUR | Midnapore Mechanical | RAMCHANDRAPUR AND ADJOINING MOUJAS , SM/12147 | New | Ramchandrapur W/S scheme PH No.-I Application No.-2004543119 Ref.-204175235 | BP-2023-24-512 | 09/01/2024 | 0 | WBSEDCL | 2.95 | 0 | 0 | 0
1728 | PURBA MEDINIPUR | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS , SM/12147 | New | Laying distribution System, Accommodate FHTC (1012 nos) Construction of Switch Room cum Chlorine Room I & II and Interconnection of Risisng main with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-A,MOUZA-RAMCHANDRAPUR) | 498/TD | 11/05/2023 | 837 | S.K. MONDAL | 138.29 | 78.3 | 56.62 | 80
1729 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. , SM/11552 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Solat Water Supply Scheme under Tamluk Division, PHE Dte. | 1723/TD | 01/02/2022 | 20 | RADIANT | 3.65 | 3.58 | 100 | 100
1730 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. , SM/11552 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 361/W/MMD | 09/03/2023 | 180 | AMIT DAS | 13.56 | 12.85 | 94.73 | 0
1731 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. , SM/11552 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1361/TD | 22/09/2022 | 40 | B. K. ENTERPRISE | 72.46 | 19.05 | 100 | 63
1732 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. , SM/11552 | Augmentation | Installation of display Board of 8 nos work site within different PWSS under Haldia Sub-Division of Tamluk Division, PHE Dte. District Purba Medinipur. (Phase -1) Name of Work site :- 1) Asadtalia PWSS, 2) Rangibasan PWSS, 3) Kapaseria PWSS, 4) Rajarampur PWSS, 5) Begunberia PWSS, 6) Dhenkua PWSS, 7) Solat PWSS & 8) Gopalpur PWSS. | 721/HSD | 28/10/2022 | 3 | TAPAN BERA | 0.93 | 0.93 | 100 | 100
1733 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. , SM/11552 | Augmentation | Material Requisition To Resource Division | 1019/TD | 08/08/2022 | 0 | Resource Division | 12.18 | 0 | 0 | 0
1734 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. , SM/11552 | Augmentation | Material Requisition To Resource Division | 1201/TD | 06/09/2022 | 0 | Resource Division | 16.27 | 0 | 0 | 0
1735 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. , SM/11552 | Augmentation | Additional drilling works & other materials at site for construction of Tube Well at Solat W/S Scheme, Haldia Block, Purba MedinipurDist. under CDD, P.H.E. Dte. | 146/CMSD-II | 22/07/2024 | 10 | PADMA ENGINEERING & CO. | 0.99 | 0.79 | 100 | 100
1736 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. , SM/11552 | Augmentation | Providing Tube Well materials Conforming to IS: 12818:2010 at site for construction of Tube Well at Solat PWSS, Purba Medinipur district under CDD, P.H.E. Dte. | 145/CMSD-II | 22/07/2024 | 7 | PADMA ENGINEERING & CO. | 0.97 | 0.97 | 100 | 100
1737 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. , SM/11552 | Augmentation | Quotation bill for new service connection at TW-III of solat w/s scheme under Haldia block in the Dist. of purba medinipur under MMD,PHE Dte. Name of C.C.C.-Brajalalchak Application no.-2004898781 Reference ID-204397568 Contract Demand-12074watt Quotation Date-12/09/2024 Quotation Due Date-12/09/2025 | BP-2024-25-632 | 26/11/2024 | 0 | WBSEDCL | 10.59 | 0 | 0 | 0
1738 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. , SM/11552 | Augmentation | Augmentation of ground water based Solat Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1113/TD | 29/08/2022 | 1190 | ARUP KUMAR DEY | 454.08 | 289.11 | 63.67 | 83
1739 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. , SM/11552 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipment¿s at TW II for Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1243/W/MMD | 28/04/2023 | 644 | M/S EMMESS | 13.59 | 6.63 | 48.79 | 60
1740 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. , SM/11552 | Augmentation | Additional Laying of Distribution pipeline,Drum Sheet Walling,G.I. Casing & Laying Rising Main of Solat Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 932/TD | 01/06/2023 | 824 | SANKHA ENTERPRISE | 68.51 | 0 | 0 | 40
1741 | PURBA MEDINIPUR | Tamluk Division | SELMABAD AND ADJOINING MOUJAS PWSS , SM/12518 | New | Material Requisition To Resource Division | 2443/TD | 16/01/2023 | 0 | Resource Division | 14.54 | 0 | 0 | 0
1742 | PURBA MEDINIPUR | Midnapore Mechanical | SELMABAD AND ADJOINING MOUJAS PWSS , SM/12518 | New | Quotation Bill for New Service connection at T/W NO-I Of SELMABAD W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-20048335913/QUOT/03 DT. 26-07-2024 Application NO- 20048335913 MEMO NO: AMR/PHE/282 DT.26/7/2024 Application type-New connection Consumer Id- 204365755 | BP-2024-25-539 | 07/08/2024 | 0 | WBSEDCL | 4.45 | 0 | 0 | 0
1743 | PURBA MEDINIPUR | Midnapore Mechanical | SELMABAD AND ADJOINING MOUJAS PWSS , SM/12518 | New | Quotation Bill for New Service connection at T/W NO-II Of SELMABAD W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835826/QUOT/03 DT. 26-07-2024 Application NO- 2004835826 MEMO NO: AMR/PHE/288 DT.26/7/2024 Application type-New connection Consumer Id- 204365757 | BP-2024-25-538 | 07/08/2024 | 0 | WBSEDCL | 4.24 | 0 | 0 | 0
1744 | PURBA MEDINIPUR | Midnapore Mechanical | SELMABAD AND ADJOINING MOUJAS PWSS , SM/12518 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SELMABAD and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 522/W/MMD | 20/03/2023 | 1317 | S.S.ENTERPRISES | 23.7 | 2.91 | 12.3 | 51
1745 | PURBA MEDINIPUR | Tamluk Division | SELMABAD AND ADJOINING MOUJAS PWSS , SM/12518 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 143.9 | 22.43 | 51
1746 | PURBA MEDINIPUR | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS , SM/12286 | New | Material Requisition To Resource Division | 2693/TD | 06/02/2023 | 0 | Resource Division | 54.53 | 0 | 0 | 0
1747 | PURBA MEDINIPUR | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS , SM/12286 | New | Canal crossing structure for Distribution pipe line with allied works of Nijmaitana & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. N.P-From 1193 towards Kathmundi 45.0M & N.P 1190 to N.P 1191 15.0 M. | 1926/TD | 07/06/2024 | 15 | SNEHESH SEN | 4.87 | 4.03 | 100 | 100
1748 | PURBA MEDINIPUR | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS , SM/12286 | New | Material Requisition To Resource Division | 134/TD | 05/01/2024 | 0 | Resource Division | 12.26 | 0 | 0 | 0
1749 | PURBA MEDINIPUR | Midnapore Mechanical | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS , SM/12286 | New | Quotation for new service connection at TW-II of Nijmaitana ws scheme under MMD,PHE, Dte. Ref. Application no-2004579831. Con ID-204204430. PICHABONI CCC, BLOCK-RAMNAGAR-II | BP-2023-24-680 | 15/02/2024 | 0 | WBSEDCL | 3.07 | 0 | 0 | 0
1750 | PURBA MEDINIPUR | Midnapore Mechanical | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS , SM/12286 | New | Nij-Maitana W/S scheme T/W-I Application No.-2004550686 Ref.-204181243 | BP-2023-24-540 | 11/01/2024 | 0 | WBSEDCL | 2.76 | 0 | 0 | 0
1751 | PURBA MEDINIPUR | Central Drilling | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS , SM/12286 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 48.99 | 79.54 | 11
1752 | PURBA MEDINIPUR | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS , SM/12286 | New | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( with pile foundation ) & Accommodate FHTC ( 1050 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHED , Purba Medinipur ( Part - A) | 1753/TD | 01/08/2023 | 853 | SUSIL KUMAR HAZRA | 254.73 | 77.56 | 30.45 | 32
1753 | PURBA MEDINIPUR | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS , SM/12286 | New | Laying Balance distribution pipe line,with balance FHTC and allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 569/TD | 17/02/2025 | 25 | R CONSTRUCTION | 36.35 | 0 | 0 | 0
1754 | PURBA MEDINIPUR | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS , SM/12286 | New | Laying distribution pipe line, & Accommodate FHTC (19 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHED, Purba Medinipur (Part-F) | 3556/TD | 29/03/2023 | 799 | DEBABRATA DAS | 11.2 | 9.64 | 86.14 | 100
1755 | PURBA MEDINIPUR | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS , SM/12286 | New | Laying distribution pipe line, & Accommodate FHTC (123 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C) | 3554/TD | 29/03/2023 | 876 | SUBRATA KUMAR BERA | 39.9 | 31.5 | 80.39 | 100
1756 | PURBA MEDINIPUR | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS , SM/12286 | New | Laying distribution pipe line, & Accommodate FHTC (42 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHED, Purba Medinipur (Part-D) | 3555/TD | 29/03/2023 | 889 | DEBABRATA DAS | 9.94 | 6.57 | 66.13 | 100
1757 | PURBA MEDINIPUR | Tamluk Division | PALPARA AND ADJOINING MOUJAS PWSS , SM/12508 | New | Material Requisition To Resource Division | 2446/TD | 16/01/2023 | 0 | Resource Division | 19.77 | 0 | 0 | 0
1758 | PURBA MEDINIPUR | Midnapore Mechanical | PALPARA AND ADJOINING MOUJAS PWSS , SM/12508 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PALPARA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 472/W/MMD | 20/03/2023 | 180 | SOUMEN ELECTRIC | 25.24 | 17.6 | 69.73 | 53
1759 | PURBA MEDINIPUR | Midnapore Mechanical | PALPARA AND ADJOINING MOUJAS PWSS , SM/12508 | New | Quotation Bill for New Service connection at T/W NO-II Of PALPARA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835399/QUOT/03 DT. 26-07-2024 Application NO- 2004835399 MEMO NO: AMR/PHE/281 DT.26/7/2024 Application type-New connection Consumer Id- 204365758 | BP-2024-25-541 | 07/08/2024 | 0 | WBSEDCL | 4.98 | 0 | 0 | 0
1760 | PURBA MEDINIPUR | Midnapore Mechanical | PALPARA AND ADJOINING MOUJAS PWSS , SM/12508 | New | Quotation Bill for New Service connection at T/W NO-I Of PALPARA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004895165/QUOT/03 DT. 10-09-2024 MEMO NO: AMR/PHE/377 DT. 10-09-2024 Application NO- 2004895165 Application type-New connection Consumer Id- 204395918 | BP-2024-25-718 | 30/09/2024 | 0 | WBSEDCL | 3.34 | 0 | 0 | 0
1761 | PURBA MEDINIPUR | Tamluk Division | PALPARA AND ADJOINING MOUJAS PWSS , SM/12508 | New | Shifting of HTOH line at Palpara PWSS, OHR Site under Patashpur-I Dev. Block. Memo No: AMR/SHIFTING/HTOH/.....Date: 05.04.2024 Reference ID: 860297135 Application ID: 100000104915 Application Date: 05.04.2024 | BP-2024-25-66 | 26/04/2024 | 0 | WBSEDCL | 5.23 | 0 | 0 | 0
1762 | PURBA MEDINIPUR | Tamluk Division | PALPARA AND ADJOINING MOUJAS PWSS , SM/12508 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (4443 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance work for Goyalda PWSS, Palpara PWSS within Patashpur-I Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 879/TD | 01/06/2023 | 761 | SANKHA ENTERPRISE | 1144 | 121.46 | 18.12 | 30
1763 | PURBA MEDINIPUR | Tamluk Division | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS , SM/12510 | New | Material Requisition To Resource Division | 2417/TD | 16/01/2023 | 0 | Resource Division | 24.12 | 0 | 0 | 0
1764 | PURBA MEDINIPUR | Tamluk Division | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS , SM/12510 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Mahabisra PWSS at Egra-I Block under Tamluk Division, PHE Dte. | 2081/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
1765 | PURBA MEDINIPUR | Tamluk Division | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS , SM/12510 | New | Quotation for new service connection at TW-II of Mahabishra ws scheme under MMD,PHE Dte, Block-Egra-I, EGRA CCC Application no-2004823398 Consumer ID-204358386 | BP-2024-25-380 | 29/08/2024 | 0 | WBSEDCL | 17.31 | 0 | 0 | 0
1766 | PURBA MEDINIPUR | Midnapore Mechanical | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS , SM/12510 | New | Quotation Bill for New Service connection at T/W NO-I Of MAHABISHRA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004667051/QUOT/03 DT. 15-04-2024 Application NO- 2004667051 Application type-New connection Consumer Id- 204275715 | BP-2024-25-101 | 26/04/2024 | 0 | WBSEDCL | 6.36 | 0 | 0 | 0
1767 | PURBA MEDINIPUR | Midnapore Mechanical | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS , SM/12510 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAHABISHRA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 465/W/MMD | 20/03/2023 | 803 | DEY ENTERPRISE | 23.7 | 0 | 0 | 90
1768 | PURBA MEDINIPUR | Tamluk Division | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS , SM/12510 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 199.43 | 37.99 | 51
1769 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the district of Purba Medinipur. , SM/12301 | Retrofitting | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the District of Purba Medinipur | 1423/TD | 26/09/2022 | 30 | SANKHA ENTERPRISE | 86.77 | 68.76 | 79.24 | 100
1770 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the district of Purba Medinipur. , SM/12301 | Retrofitting | Material Requisition To Resource Division | 1115/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
1771 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Baranalgeria (Zone-I) PWSS under Egra-II Block. , SM/12303 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Baranalgeria Zone-I PWSS under Egra-II Block within Digha Sub-Division of Tamluk Division. | 2859/TD | 17/02/2023 | 45 | DAS CONSTRUCTION | 80.73 | 54.34 | 67.31 | 70
1772 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Baranalgeria (Zone-I) PWSS under Egra-II Block. , SM/12303 | Retrofitting | Material Requisition To Resource Division | 2646/TD | 02/02/2023 | 0 | Resource Division | 14.41 | 0 | 0 | 0
1773 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Baranalgeria (Zone-I) PWSS under Egra-II Block. , SM/12303 | Retrofitting | Requirement of additional pipeline for Retrofitting to accommodate FHTC under JJM in Baranalgeria Zone-I PWSS under Egra-II Block within Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 2672/TD | 16/10/2023 | 602 | M/S. CHANDI CHARAN MISHRA & CO. | 51.03 | 0 | 0 | 1
1774 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11861 | Augmentation | Material Requisition To Resource Division | 361/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0 | 0
1775 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11861 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 11.46 | 87.17 | 100
1776 | PURBA MEDINIPUR | Midnapore Mechanical | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11861 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District, Block ¿ Deshopran under JJM Program under MMD PHE Dte. | 643/W/MMD | 20/03/2023 | 180 | K.S.P. ENTERPRISE | 13.57 | 11.31 | 83.35 | 85
1777 | PURBA MEDINIPUR | Midnapore Mechanical | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11861 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 0 | 50
1778 | PURBA MEDINIPUR | Midnapore Mechanical | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11861 | Augmentation | Quotation for new service connection at TW-III of Baharchandberia ws scheme under MMD, PHE Dte, Block-Conai-II, MARISHDA CCC Application no-2004763702 Con ID-204323627 | BP-2024-25-286 | 18/06/2024 | 0 | WBSEDCL | 5.48 | 0 | 0 | 0
1779 | PURBA MEDINIPUR | Tamluk Division | KHAGDA PWSS at Egra-II Block in Tamluk Division P.H.E. Dte. , SM/12483 | New | Material Requisition To Resource Division | 2972/TD | 27/02/2023 | 0 | Resource Division | 65.15 | 0 | 0 | 0
1780 | PURBA MEDINIPUR | Midnapore Mechanical | KHAGDA PWSS at Egra-II Block in Tamluk Division P.H.E. Dte. , SM/12483 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHAGDA and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2409/W/MMD | 31/12/2022 | 180 | SUJOY RANJAN BHOWMICK | 21.62 | 13.57 | 62.77 | 45
1781 | PURBA MEDINIPUR | Midnapore Mechanical | KHAGDA PWSS at Egra-II Block in Tamluk Division P.H.E. Dte. , SM/12483 | New | Quotation Bill for New Service connection at T/W NO-I Of KHAGDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004852019/QUOT/03/563 DT. 07-08-2024 Application NO- 2004852019 Application type-New connection Consumer Id- 204373372 | C082449401206 | 02/09/2024 | 0 | WBSEDCL | 5.03 | 0 | 0 | 0
1782 | PURBA MEDINIPUR | Tamluk Division | KHAGDA PWSS at Egra-II Block in Tamluk Division P.H.E. Dte. , SM/12483 | New | Sinking of Tube Well ,Rising main ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , OHR (Intze type with pile foundation) & Accommodate FHTC (5135 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dubda & Khagda PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 1733/TD | 31/07/2023 | 819 | MAHAVIR PUMPS MFG. PVT. LTD. | 1235.52 | 97.49 | 29.37 | 48
1783 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11984 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sherkhanchak Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | 1477/TD | 03/01/2022 | 20 | SANTRA ENTERPRISE. | 4.97 | 4.97 | 100 | 100
1784 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11984 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Replacement of Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 2nd Tube well Site of Sherkhanchak Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at Replacement of 1st Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 4th Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1223/TD | 07/09/2022 | 40 | KALPANA BUILDERS | 71.97 | 17.72 | 98.47 | 48
1785 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11984 | Augmentation | Material Requisition To Resource Division | 1200/TD | 06/09/2022 | 0 | Resource Division | 292.79 | 0 | 0 | 0
1786 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11984 | Augmentation | Material Requisition To Resource Division | 1199/TD | 06/09/2022 | 0 | Resource Division | 44.01 | 0 | 0 | 0
1787 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11984 | Augmentation | Electric Quotation for SHERKHANCHAK Water Supply Scheme Z-I, T/W-III (Ref. ID-204040417 ) | BP-2023-24-139 | 27/07/2023 | 0 | WBSEDCL | 0.56 | 0 | 0 | 0
1788 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11984 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Sherkhanchak Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1447/TD | 27/09/2022 | 1068 | TAPAS SANTRA | 896.61 | 774.33 | 86.36 | 70
1789 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11984 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 358/W/MMD | 09/03/2023 | 180 | S.K.ENTERPRISE | 35.55 | 29.45 | 82.85 | 70
1790 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11984 | Augmentation | Laying of Balance portion for Distribution pipe line by UPVC pipes with allied works for Sherkhanchak Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (PART-A) | 924/TD | 01/06/2023 | 40 | S.D. CONSTRUCTION | 98.88 | 94.52 | 95.59 | 95
1791 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11984 | Augmentation | i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Sherkhanchak Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) construction of Boundary Wall (as per Departmental Design & Drawing) at 4th TW site for Augmentation of Sherkhanchak Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iii) construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Sherkhanchak Zone-I W/S Scheme within Khejuri - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) ( Location:-Mouza-Baratala, J.L No-29, Plot No-342) iv) construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Sherkhanchak Zone-I W/S Scheme within Khejuri - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) ( Location:-Mouza-Baratala, J.L No-29, Plot No-2543) v) Laying Rising main and other allied works Augmentation of Sherkhanchak Zone-I W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1422/TD | 12/07/2023 | 622 | M/S. NEW DINDA ENTERPRISE | 41.06 | 13.22 | 32.19 | 75
1792 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11984 | Augmentation | Replacement of Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well site of Sherkhanchak Zone-I Water Supply Scheme within Khejuri - II Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | 977/TD | 13/03/2024 | 25 | B. K. ENTERPRISE | 19.16 | 0 | 0 | 100
1793 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11984 | Augmentation | Quotation for new service connection at Serkhanchak Zone I w/s scheme PH IV Additional TW in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004675042, Ref ID 204268872) | BP-2024-25-50 | 18/04/2024 | 0 | WBSEDCL | 8.33 | 0 | 0 | 0
1794 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11984 | Augmentation | Rising main (Balance Portion) with laying of 200mm dia & 150 mm dia DI (K-9) From 2nd Tube Well & 4th Tube Well Site to O.H.R. Site and other allied works for Sherkhanchak Zone-I Water Supply Scheme in Khejuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 978/TD | 13/03/2024 | 329 | M/S. NEW DINDA ENTERPRISE | 7.34 | 0 | 0 | 0
1795 | PURBA MEDINIPUR | Tamluk Division | KEKAI & ADJOINING MOUJAS PWSS , SM/12168 | New | Material Requisition To Resource Division | 2453/TD | 16/01/2023 | 0 | Resource Division | 37.57 | 0 | 0 | 0
1796 | PURBA MEDINIPUR | Tamluk Division | KEKAI & ADJOINING MOUJAS PWSS , SM/12168 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kekai PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | 2069/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
1797 | PURBA MEDINIPUR | Tamluk Division | KEKAI & ADJOINING MOUJAS PWSS , SM/12168 | New | Material Requisition To Resource Division | 1654/TD | 29/04/2024 | 0 | Resource Division | 11.04 | 0 | 0 | 0
1798 | PURBA MEDINIPUR | Midnapore Mechanical | KEKAI & ADJOINING MOUJAS PWSS , SM/12168 | New | Quotation Bill for New Service connection at T/W NO-II Of KEKAI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004657831/QUOT/03/1513 DT. 28-03-2024 Application NO- 2004657831 Application type-New connection Consumer Id- 204257680 | BP-2024-25-30 | 15/04/2024 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
1799 | PURBA MEDINIPUR | Tamluk Division | KEKAI & ADJOINING MOUJAS PWSS , SM/12168 | New | Bill or Damage of road flank / hard shoulder due to cutting of hard shoulder and road flank on Egra-Bajkul Road from 5.30 Km. To 7.00 Km. For laying water pipe line of Kekai PWSS. | BP-2024-25-492 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.03 | 0 | 0 | 0
1800 | PURBA MEDINIPUR | Tamluk Division | KEKAI & ADJOINING MOUJAS PWSS , SM/12168 | New | Charges for WBSEDCL for Shifting of Rail Pole of 33 KV OH Line at Kekai, Junpukur under Tamluk Division, PHE Dte. | BP-2024-25-633 | 30/11/2024 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1801 | PURBA MEDINIPUR | Midnapore Mechanical | KEKAI & ADJOINING MOUJAS PWSS , SM/12168 | New | Quotation Bill for New Service connection at T/W NO-I Of KEKAI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760163/QUOT/03 DT. 04-06-2024 Application NO- 2004760163 Application type-New connection Consumer Id- 204322029 | BP-2024-25-287 | 18/06/2024 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
1802 | PURBA MEDINIPUR | Tamluk Division | KEKAI & ADJOINING MOUJAS PWSS , SM/12168 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 136.54 | 23.88 | 51
1803 | PURBA MEDINIPUR | Midnapore Mechanical | KEKAI & ADJOINING MOUJAS PWSS , SM/12168 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KEKAI and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2377/W/MMD | 31/12/2022 | 900 | GHOSH ENGINEERING SYNDICATE | 25.24 | 5.85 | 23.17 | 51
1804 | PURBA MEDINIPUR | Tamluk Division | RUKMINIPUR AND ADJOINING MOUJAS PWSS , SM/12176 | New | Material Requisition To Resource Division | 2716/TD | 06/02/2023 | 0 | Resource Division | 34.45 | 0 | 0 | 0
1805 | PURBA MEDINIPUR | Midnapore Mechanical | RUKMINIPUR AND ADJOINING MOUJAS PWSS , SM/12176 | New | Quotation Bill for New Service connection at T/W NO-II Of RUKMINIPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004792717/QUOT/03/381 DT. 02/07/2024 Application NO- 2004792717 Application type-New connection Consumer Id- 204345882 | BP-2024-25-493 | 29/07/2024 | 0 | WBSEDCL | 4.04 | 0 | 0 | 0
1806 | PURBA MEDINIPUR | Midnapore Mechanical | RUKMINIPUR AND ADJOINING MOUJAS PWSS , SM/12176 | New | Quotation Bill for New Service connection at T/W NO-I Of RUKMINIPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004701293/QUOT/03/98 DT. 25-04-2024 Application NO- 2004701293 Application type-New connection Consumer Id- 204287569 | BP-2024-25-162 | 15/05/2024 | 0 | WBSEDCL | 3.52 | 0 | 0 | 0
1807 | PURBA MEDINIPUR | Midnapore Mechanical | RUKMINIPUR AND ADJOINING MOUJAS PWSS , SM/12176 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RUKMINIPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2365/W/MMD | 31/12/2022 | 974 | ABHIJIT BASU | 23.69 | 14.81 | 62.5 | 80
1808 | PURBA MEDINIPUR | Tamluk Division | RUKMINIPUR AND ADJOINING MOUJAS PWSS , SM/12176 | New | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1588 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Rukminipur PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | 460/TD | 04/05/2023 | 942 | FIROZ KHAN | 483.49 | 204.95 | 42.39 | 70
1809 | PURBA MEDINIPUR | Tamluk Division | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/13742 | New | Material Requisition To Resource Division | 2688/TD | 06/02/2023 | 0 | Resource Division | 24.43 | 0 | 0 | 0
1810 | PURBA MEDINIPUR | Tamluk Division | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/13742 | New | Material Requisition To Resource Division | 83/TD | 05/01/2024 | 0 | Resource Division | 9.34 | 0 | 0 | 0
1811 | PURBA MEDINIPUR | Midnapore Mechanical | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/13742 | New | Quotation Bill for New Service connection at T/W NO-I Of BHUNIAJIBAR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, PICHABANI C.C.C. Ref. Memo No- 2004620665/QUOT/03 DT. 27-02-2024 Application NO- 2004620665 Application type-New connection Reference Id- 204229268 | BP-2023-24-807 | 11/03/2024 | 0 | WBSEDCL | 3.18 | 0 | 0 | 0
1812 | PURBA MEDINIPUR | Midnapore Mechanical | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/13742 | New | Quotation Bill for New Service connection at T/W NO-II Of BHUIAJIBAR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004950601/QUOT/03 DT. 30-10-2024 Application NO- 2004950601 Application type-New connection Consumer Id- 204434656 | C112423559210 | 20/11/2024 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
1813 | PURBA MEDINIPUR | Midnapore Mechanical | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/13742 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BHUIANJIBAR and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 563/W/MMD | 20/03/2023 | 803 | SUBHRA ENTERPRISE | 22.78 | 16.52 | 72.5 | 100
1814 | PURBA MEDINIPUR | Tamluk Division | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/13742 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3103 Nos) For 2 nos Pipe Water Supply Scheme including two years Operation & Maintainance for BHUINAJIBAR and DEULI within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 1068/TD | 08/06/2023 | 934 | TAPAS SANTRA | 1110.29 | 444.54 | 79.56 | 85
1815 | PURBA MEDINIPUR | Tamluk Division | GOJINA AND IT'S ADJOINING MOUJAS PWSS , SM/12812 | New | Material Requisition To Resource Division | 2435/TD | 16/01/2023 | 0 | Resource Division | 46.71 | 0 | 0 | 0
1816 | PURBA MEDINIPUR | Midnapore Mechanical | GOJINA AND IT'S ADJOINING MOUJAS PWSS , SM/12812 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOJINA and ADJOINING MOUJAS, Block - Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 526/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 5.65 | 23.85 | 60
1817 | PURBA MEDINIPUR | Tamluk Division | GOJINA AND IT'S ADJOINING MOUJAS PWSS , SM/12812 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Gojina PWSS at Moyna Block under Tamluk Division,PHE Dte. | 200/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
1818 | PURBA MEDINIPUR | Tamluk Division | GOJINA AND IT'S ADJOINING MOUJAS PWSS , SM/12812 | New | Material Requisition To Resource Division | 1564/TD | 23/04/2024 | 0 | Resource Division | 15.01 | 0 | 0 | 0
1819 | PURBA MEDINIPUR | Midnapore Mechanical | GOJINA AND IT'S ADJOINING MOUJAS PWSS , SM/12812 | New | Quotation for Gojina w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004619919, Ref ID-204229478) | BP-2023-24-861 | 16/03/2024 | 0 | WBSEDCL | 2.78 | 0 | 0 | 0
1820 | PURBA MEDINIPUR | Midnapore Mechanical | GOJINA AND IT'S ADJOINING MOUJAS PWSS , SM/12812 | New | Quotation for Gojina w/s scheme PH-II in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004619845, Ref ID-204229480) | BP-2023-24-862 | 16/03/2024 | 0 | WBSEDCL | 5.65 | 0 | 0 | 0
1821 | PURBA MEDINIPUR | Tamluk Division | GOJINA AND IT'S ADJOINING MOUJAS PWSS , SM/12812 | New | Continuation for Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.07.2025 to 31.12.2025 i.e. 06 (Six) months for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. | 169/RWS/TSD | 26/06/2025 | 184 | SADHAN CHANDRA SAMANTA | 0.87 | 0 | 0 | 0
1822 | PURBA MEDINIPUR | Central Drilling | KATARI AND ADJOINING MOUJAS PWSS , SM/12815 | New | Providing drliing crew and other allied works for construction of Tube Well (250 mm x 150mm x 280 Mtrs Depth) by utilising Departmental Machineries for katari W/S Scheme (T/W-III), khejuri-I Block under Purba Mednipur District, CDD PHE Dte. | 59/CDD | 06/04/2023 | 30 | PADMA ENGINEERING & CO. | 15.48 | 12.9 | 100 | 100
1823 | PURBA MEDINIPUR | Central Drilling | KATARI AND ADJOINING MOUJAS PWSS , SM/12815 | New | Provicjing drilling crew and other allied works for construction of Tube Well (250mm Xi50mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Katari W/S Scheme (T/W-l) , Khejuri-l Block under Purba IVedinipur District, CentralDrilling Division, P.H.E. Dte. | 853/CDD | 10/07/2023 | 30 | C.M. ENTERPRISE | 15.47 | 12.9 | 100 | 100
1824 | PURBA MEDINIPUR | Tamluk Division | KATARI AND ADJOINING MOUJAS PWSS , SM/12815 | New | Material Requisition To Resource Division | 2980/TD | 27/02/2023 | 0 | Resource Division | 17.68 | 0 | 0 | 0
1825 | PURBA MEDINIPUR | Midnapore Mechanical | KATARI AND ADJOINING MOUJAS PWSS , SM/12815 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KATARI and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 505/W/MMD | 20/03/2023 | 180 | AMIT DAS | 21.57 | 20.26 | 100 | 50
1826 | PURBA MEDINIPUR | Tamluk Division | KATARI AND ADJOINING MOUJAS PWSS , SM/12815 | New | Material Requisition To Resource Division | 2965/TD | 12/09/2024 | 0 | Resource Division | 4.72 | 0 | 0 | 0
1827 | PURBA MEDINIPUR | Midnapore Mechanical | KATARI AND ADJOINING MOUJAS PWSS , SM/12815 | New | Katari W/S scheme PH.-I Application No.-2004565589 Ref No.-204193626 | BP-2023-24-590 | 02/02/2024 | 0 | WBSEDCL | 5.84 | 0 | 0 | 0
1828 | PURBA MEDINIPUR | Midnapore Mechanical | KATARI AND ADJOINING MOUJAS PWSS , SM/12815 | New | Katari W/S scheme PH.-II Application No.-2004565602 Ref No.-204193624 | BP-2023-24-591 | 02/02/2024 | 0 | WBSEDCL | 5.2 | 0 | 0 | 0
1829 | PURBA MEDINIPUR | Tamluk Division | KATARI AND ADJOINING MOUJAS PWSS , SM/12815 | New | Sinking of Tube well, Pump House , OHR (Intze type with pile foundation), Rising main, Head work site pipe connection, Laying distribution pipe line,Rigid Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (2953 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dakshin Kalamdan, Katari, and its adjoing Mouzas- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1417/TD | 12/07/2023 | 812 | TAPAS SANTRA | 1109.38 | 124.19 | 51.96 | 75
1830 | PURBA MEDINIPUR | Central Drilling | KATARI AND ADJOINING MOUJAS PWSS , SM/12815 | New | Hiring of diesel driven Motor Cab (BS-III & Above) having contract carriage permit along with driver for the office of The Executive Engineer, Central Drilling Division, P.H.E. Dte. | 11/S&WSD | 15/01/2025 | 197 | SULEKHA PAUL | 0.94 | 1.9 | 203.55 | 0
1831 | PURBA MEDINIPUR | Tamluk Division | POTA PAKURIA AND IT'S ADJOINING MOUJAS , SM/13886 | New | Material Requisition To Resource Division | 2397/TD | 16/01/2023 | 0 | Resource Division | 22.13 | 0 | 0 | 0
1832 | PURBA MEDINIPUR | Midnapore Mechanical | POTA PAKURIA AND IT'S ADJOINING MOUJAS , SM/13886 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for POTA PAKURIA and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 551/W/MMD | 20/03/2023 | 712 | DEBJYOTI BASU | 21.62 | 9.99 | 46.23 | 80
1833 | PURBA MEDINIPUR | Tamluk Division | POTA PAKURIA AND IT'S ADJOINING MOUJAS , SM/13886 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Potapukuria PWSS at Contai-I Block under Tamluk Division, PHE Dte. | 2066/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
1834 | PURBA MEDINIPUR | Tamluk Division | POTA PAKURIA AND IT'S ADJOINING MOUJAS , SM/13886 | New | Material Requisition To Resource Division | 2972/TD | 12/09/2024 | 0 | Resource Division | 6.04 | 0 | 0 | 0
1835 | PURBA MEDINIPUR | Midnapore Mechanical | POTA PAKURIA AND IT'S ADJOINING MOUJAS , SM/13886 | New | Quotation Bill for New Service connection at T/W NO-I Of POTA PUKURIA W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670768/QUOT/03 DT. 05-04-2024 Application NO- 2004670768 Application type-New connection Consumer Id- 204266388 | BP-2024-25-45 | 18/04/2024 | 0 | WBSEDCL | 3.45 | 0 | 0 | 0
1836 | PURBA MEDINIPUR | Tamluk Division | BADALPUR AND IT'S ADJOINING MOUJAS , SM/13887 | New | Material Requisition To Resource Division | 2686/TD | 06/02/2023 | 0 | Resource Division | 8.88 | 0 | 0 | 0
1837 | PURBA MEDINIPUR | Tamluk Division | BADALPUR AND IT'S ADJOINING MOUJAS , SM/13887 | New | Material Requisition To Resource Division | 78/TD | 05/01/2024 | 0 | Resource Division | 3.91 | 0 | 0 | 0
1838 | PURBA MEDINIPUR | Midnapore Mechanical | BADALPUR AND IT'S ADJOINING MOUJAS , SM/13887 | New | Electric Quotation for BADALPUR Water Supply Scheme T/W-I, (Ref. ID-204134593) | BP-2023-24-360 | 24/11/2023 | 0 | WBSEDCL | 3.28 | 0 | 0 | 0
1839 | PURBA MEDINIPUR | Midnapore Mechanical | BADALPUR AND IT'S ADJOINING MOUJAS , SM/13887 | New | Badalpur W/S scheme PH-II Application no.-2004522472 ref.-204156771 | BP-2023-24-470 | 27/12/2023 | 0 | WBSEDCL | 4.53 | 0 | 0 | 0
1840 | PURBA MEDINIPUR | Tamluk Division | BADALPUR AND IT'S ADJOINING MOUJAS , SM/13887 | New | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (635 nos) including 02(two) Years Operation & Maintenance under JJM with allied work of Badalpur PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | 853/TD | 31/05/2023 | 851 | GHOSH CONSTRUCTION | 320.45 | 214.44 | 66.92 | 52
1841 | PURBA MEDINIPUR | Tamluk Division | BADALPUR AND IT'S ADJOINING MOUJAS , SM/13887 | New | Pump House ,Rising main, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (248nos) under JJM with allied work of BADALPUR PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 603/TD | 17/05/2023 | 685 | AYSAN KHAN | 63.14 | 26.03 | 41.22 | 60
1842 | PURBA MEDINIPUR | Midnapore Mechanical | BADALPUR AND IT'S ADJOINING MOUJAS , SM/13887 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BADALPUR and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 546/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 21.58 | 19.98 | 94.44 | 100
1843 | PURBA MEDINIPUR | Tamluk Division | Providing FHTC (Functional Household Tap Connection) with Augmentation of Murisai Water Supply Scheme , SM/13889 | Augmentation | Construction of R.C.C. Elevated Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied works under Murisai & its adjoining moujas Water Supply Scheme within Contai-III Block including supply of all labour & materials under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1741/TD | 01/08/2023 | 180 | ANUSKA ENTERPRISE | 130.06 | 0 | 0 | 0
1844 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme , SM/15034 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme Deshopran Block under JJM Program under MMD PHE Dte. | 891/W/MMD | 27/03/2023 | 180 | GANGULY ENGINEERING CO. | 23.69 | 0 | 0 | 0
1845 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme , SM/15034 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. [PART-I] | .1853/TD | 21/11/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.2 | 100 | 100
1846 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme , SM/15034 | Augmentation | Material Requisition To Resource Division | 2093/TD | 29/08/2023 | 0 | Resource Division | 69.1 | 0 | 0 | 0
1847 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme , SM/15034 | Augmentation | Sinking of Tubewell, 250 cum OHR (Intze type with pile foundation), Laying distribution pipe line, Soil investigation, Pump House, Boundary wall, Rising Main & Accommodate FHTC (1807 nos) under JJM with allied work for Augmentation of Contai Saline Area Zone-IV PART-I PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 897/TD | 11/03/2024 | 180 | SRIMANTA KUMAR MAITY | 428.55 | 0 | 0 | 0
1848 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM un Baranalgeria (Zone-II) PWSS under Egra-II Block. , SM/10431 | Retrofitting | Land development at 1st tube well site of Baranalgeria ( Zone-II ) Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1595/TD | 18/10/2022 | 20 | PULAK KUMAR SAMANTA | 3.51 | 3.5 | 100 | 100
1849 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM un Baranalgeria (Zone-II) PWSS under Egra-II Block. , SM/10431 | Retrofitting | Retrofitting to accommodate FHTC (1718 nos.) under JJM in Baranalgeria Zone -II PWSS Block - EGRA -II in the District of Purba Medinipur. | 173/TD | 25/04/2022 | 30 | FIROZ KHAN | 82.65 | 82.65 | 100 | 100
1850 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM un Baranalgeria (Zone-II) PWSS under Egra-II Block. , SM/10431 | Retrofitting | Laying ( Left out ) HDPE pipe lineto accommodated FHTC under JJM in Baranalgeria (Zone-II) PWSS within Egra-II Block( to Support Phase -I FHTC ( part -B ) under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 402/TD | 27/04/2023 | 30 | DEBDUT CONSTRUCTION | 32.43 | 35.41 | 100 | 100
1851 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM un Baranalgeria (Zone-II) PWSS under Egra-II Block. , SM/10431 | Retrofitting | TRIAL RUN work of distribution system and rising main pipe line etc. of Baranalgeriya (Zone - II) W/S Scheme within Egra - II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. For the period of 90 (Ninety) Days. (01/04/2022 to 29/06/2022 | 778/DSD | 31/03/2022 | 90 | BIBEKANANDA DAS | 0.72 | 0 | 0 | 100
1852 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme under block Paskura-II in the district of Purba Medinipur Zone-VIII , SM/08790 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -VIII (Balance Work) Block Panskura-II in the District of Purba Medinipur. | 729/TD | 15/09/2021 | 180 | ARABINDA GHOSH | 342.78 | 471.5 | 199.55 | 100
1853 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme under block Paskura-II in the district of Purba Medinipur Zone-VIII , SM/08790 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Surface Water Based W/S Scheme for Zone - VIII under Tamluk Division, PHE Dte. in the district of Purba Medinipur. | BP-2021-22-125 | 07/10/2021 | 0 | ARABINDA GHOSH | 106.46 | 0 | 0 | 0
1854 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-II Piped Water Supply Scheme , SM/16464 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte.[PART-II] | .1854/TD | 21/11/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.09 | 3.49 | 100 | 100
1855 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-II Piped Water Supply Scheme , SM/16464 | Augmentation | Material Requisition To Resource Division | 2094/TD | 29/08/2023 | 0 | Resource Division | 15.65 | 0 | 0 | 0
1856 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-II Piped Water Supply Scheme , SM/16464 | Augmentation | Material Requisition To Resource Division | 3006/TD | 29/11/2023 | 0 | Resource Division | 10.08 | 0 | 0 | 0
1857 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-II Piped Water Supply Scheme , SM/16464 | Augmentation | Sinking of Tubewell, 250 cum OHR (Intze type with pile foundation), Laying distribution pipe line, Soil investigation, Pump House, Boundary wall, Rising Main & Accommodate FHTC (1636 nos) under JJM with allied work for Augmentation of Contai Saline Area Zone-IV PART-II PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 2709/TD | 30/10/2023 | 180 | TAPAS SANTRA | 480.26 | 0 | 0 | 0
1858 | PURBA MEDINIPUR | Tamluk Division | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (851 NOS.) AND LAYING OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XII, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA , SM/16470 | Retrofitting | Supply of DI Specials for Zone-XII under Surface Water based Water Supply Scheme of Panskura-II Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. Purba Medinipur. | 1528/TSD | 10/11/2023 | 10 | KRISHNENDU SEKHAR DAS | 0.73 | 0.73 | 100 | 100
1859 | PURBA MEDINIPUR | Central Drilling | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS , SM/15848 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 230 mtrs. Depth) by utilising Departmental machineries for Purba Teghari W/S Scheme(TW-III), Deshpran block under Purba Medinipur District, CDD PHE Dte. | 12/CDD | 04/04/2023 | 30 | MENAKA ENTERPRISE | 13.29 | 12.08 | 100 | 100
1860 | PURBA MEDINIPUR | Central Drilling | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS , SM/15848 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 230 mtrs. Depth) by utilising Departmental machineries for Purba Teghari W/S Scheme(TW-II), Deshpran block under Purba Medinipur District, CDD PHE Dte. | 19/CDD | 04/04/2023 | 30 | MENAKA ENTERPRISE | 13.29 | 12.01 | 100 | 100
1861 | PURBA MEDINIPUR | Tamluk Division | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS , SM/15848 | New | Material Requisition To Resource Division | 3013/TD | 27/02/2023 | 0 | Resource Division | 14.09 | 0 | 0 | 0
1862 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS , SM/15848 | New | Electric Quotation for PURBA TEGHARI, Water Supply Scheme , T/W-II, (Ref. ID-204072721) | BP-2023-24-307 | 01/11/2023 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
1863 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS , SM/15848 | New | Additional Electric Quotiaton for PURBA TEGHARI Water Supply Scheme, T/W- I, (Ref. ID-860281573) | BP-2023-24-339 | 10/11/2023 | 0 | WBSEDCL | 2.96 | 0 | 0 | 0
1864 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS , SM/15848 | New | Electric Quotation for PURBA TEGHARI, Water Supply Scheme , T/W-I, (Ref. ID-204072720) | BP-2023-24-308 | 01/11/2023 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
1865 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS , SM/15848 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Deshopran in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1206/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 34.45 | 0 | 0 | 53
1866 | PURBA MEDINIPUR | Tamluk Division | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS , SM/15848 | New | Material Requisition To Resource Division | 2975/TD | 12/09/2024 | 0 | Resource Division | 1.4 | 0 | 0 | 0
1867 | PURBA MEDINIPUR | Tamluk Division | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS , SM/15848 | New | Tube well, Pump House, 50 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert, CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (227 nos) under JJM with allied work for Purba Teghari and Adjoining Moujas PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 2706/TD | 20/10/2023 | 719 | CHANDIMATA CONSTRUCTION | 183.69 | 40.89 | 22.26 | 70
1868 | PURBA MEDINIPUR | Tamluk Division | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS , SM/15848 | New | Instalation of display Board at different work site of Purba Teghari & its adjoining Moujas New PWSS in Deshpran Block & Augmentation of Contai Saline Area Zone-I (Phase-A) & Augmentation of Contai Saline Area Zone-I (Phase-B) PWSS in Contai-III Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2442/CSD | 22/10/2024 | 7 | AMIT PAYRA | 0.62 | 0 | 0 | 100
1869 | PURBA MEDINIPUR | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. , SM/15850 | New | Material Requisition To Resource Division | 3010/TD | 27/02/2023 | 0 | Resource Division | 16.31 | 0 | 0 | 0
1870 | PURBA MEDINIPUR | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. , SM/15850 | New | Pump House, Laying distribution pipe line & Accommodate FHTC (50 nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | 3183/TD | 10/03/2023 | 180 | BADAL CHANDRA GOLE | 18.58 | 12.06 | 64.9 | 70
1871 | PURBA MEDINIPUR | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. , SM/15850 | New | Laying distribution pipe line, Boundary Wall & Accommodate FHTC (40 nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART- C) | 540/TD | 12/05/2023 | 750 | CHANDA AGENCIES | 19.28 | 7.04 | 36.5 | 60
1872 | PURBA MEDINIPUR | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. , SM/15850 | New | Material Requisition To Resource Division | 636/W | 20/02/2024 | 0 | Resource Division | 0.92 | 0 | 0 | 0
1873 | PURBA MEDINIPUR | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. , SM/15850 | New | Quotation bill of WBSEDCL for New Service Connection at Tube Well No.-1 of Garbar Water Supply Scheme under Tamluk Division, PHE Dte. | BP-2023-24-995 | 20/03/2024 | 0 | WBSEDCL | 5.56 | 0 | 0 | 0
1874 | PURBA MEDINIPUR | Midnapore Mechanical | GARABAR PIPED WATER SUPPLY SCHEME. , SM/15850 | New | Quotation Bill for New Service connection at T/W NO-II Of GARABAR W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004601950/QUOT/03 DT. 15-02-2024 Application NO- 2004601950 Application type-New connection Reference Id- 204217839 |  | 01/03/2024 | 0 | WBSEDCL | 6.61 | 0 | 0 | 0
1875 | PURBA MEDINIPUR | Midnapore Mechanical | GARABAR PIPED WATER SUPPLY SCHEME. , SM/15850 | New | Quotation Bill for New Service connection at T/W NO-I Of GARABAR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, MADHAKHALI C.C.C. Ref. Memo No- 2004625653/QUOT/03 DT. 01-03-2024 Application NO- 2004625653 Application type-New connection Consumer Id- 204232821 |  | 06/03/2024 | 0 | WBSEDCL | 5.56 | 0 | 0 | 0
1876 | PURBA MEDINIPUR | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. , SM/15850 | New | Payment of WBSEDCL for Quotation money for New Service Connection at Tube Well No. - II of Garbar Water Supply Scheme under Tamluk Division, PHE Dte. | BP-2024-25-113 | 10/05/2024 | 0 | WBSEDCL | 6.61 | 0 | 0 | 0
1877 | PURBA MEDINIPUR | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. , SM/15850 | New | Laying distribution pipe line & Accommodate FHTC (40 Nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART- D) | 262/TD | 19/04/2023 | 15 | PARTHA CONSTRUCTION | 9.59 | 6.69 | 69.8 | 70
1878 | PURBA MEDINIPUR | Central Drilling | GARABAR PIPED WATER SUPPLY SCHEME. , SM/15850 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 47 | 110.02 | 11
1879 | PURBA MEDINIPUR | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. , SM/15850 | New | Pump House ,50 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (20 nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART-A) | 1776/TD | 02/08/2023 | 180 | SUSIL KUMAR HAZRA | 68.66 | 0 | 0 | 35
1880 | PURBA MEDINIPUR | Tamluk Division | Piped water Supply Scheme for Chirulia-Chatla Zone-1 , SM/16284 | Augmentation | Material Requisition To Resource Division | 2993/TD | 29/11/2023 | 0 | Resource Division | 1 | 0 | 0 | 0
1881 | PURBA MEDINIPUR | Tamluk Division | Piped water Supply Scheme for Chirulia-Chatla Zone-1 , SM/16284 | Augmentation | Material Requisition To Resource Division | 2062/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0 | 0
1882 | PURBA MEDINIPUR | Tamluk Division | Piped water Supply Scheme for Chirulia-Chatla Zone-1 , SM/16284 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 162 Nos) under JJM with allied work for Chirulia-Chatla (Zone-I) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 1088/TD | 08/06/2023 | 907 | AJIT KUMAR SOM | 269.22 | 117.58 | 43.67 | 60
1883 | PURBA MEDINIPUR | Tamluk Division | Piped water Supply Scheme for Chirulia-Chatla Zone-1 , SM/16284 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- I ) | 1055/TD | 18/08/2022 | 20 | ASTER CONSULTANCY | 4.01 | 4.01 | 100 | 100
1884 | PURBA MEDINIPUR | Midnapore Mechanical | Piped water Supply Scheme for Chirulia-Chatla Zone-1 , SM/16284 | Augmentation | Quotation For New Service Connections at Tube Well-I of Chirulia Chalta, Zone-I W/S scheme under MMD PHE Dte. Chorepalia CCC Block- Egra-I Application No.-2004746276 Consumer ID.-204313776 Application Date.-29/05/2024 | BP-2024-25-254 | 06/06/2024 | 0 | WBSEDCL | 13.67 | 0 | 0 | 0
1885 | PURBA MEDINIPUR | Midnapore Mechanical | Piped water Supply Scheme for Chirulia-Chatla Zone-1 , SM/16284 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Egra - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1207/W/MMD | 25/04/2023 | 981 | BHABANI PRASAD MANNA | 59.85 | 0 | 0 | 20
1886 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Asadtaliya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16855 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
1887 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Asadtaliya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16855 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1888 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Barsundra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16885 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
1889 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Barsundra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16885 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1890 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chandanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16886 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
1891 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chandanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16886 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1892 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16948 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District Medinipur District, under JJM Program under MMD PHE Dte. | 1227/W/MMD | 25/04/2023 | 180 | SOUMEN ELECTRIC | 12.14 | 0 | 0 | 0
1893 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16948 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 0 | 0 | 48
1894 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16948 | New | Installation of 150 mm.x100 mm.x 230 mtr.(av) depth Tube well(PVC) & Providing FHTC (364 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at 09 nos Different Location Block within Purba Medinipur district under Tamluk Division, PHE Dte. | 1100/TD | 08/06/2023 | 907 | SWADHIN KUMAR CHAKRABORTY | 245.94 | 0 | 0 | 51
1895 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. , SM/16713 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1222/W/MMD | 25/04/2023 | 180 | TAPAN KUMAR SARKAR | 11.76 | 0 | 0 | 0
1896 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. , SM/16713 | Augmentation | Laying of Distribution pipe line, Rising main pipe line with allied works of Pratapdighi & its adjoining mouzas Water Supply Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (PHASE-II) | 1826/TD | 07/08/2023 | 509 | GIRI CONSTRUCTION | 55.97 | 0 | 0 | 45
1897 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Contai Saline Area, Zone-IV PWSS in the District of Purba Medinipur under JJM programme. , SM/16667 | Augmentation | Rejuvenation of Electro-Mechanical components of Contai Saline Area, Zone-IV PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 770/W/MMD | 23/03/2023 | 180 | SUBHASIS ROY | 12.67 | 0 | 0 | 0
1898 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Kanpur PWSS in the District of Purba Medinipur under JJM programme. , SM/16668 | Augmentation | Rejuvenation of Electro-Mechanical components of Kanpur PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 769/W/MMD | 23/03/2023 | 180 | SUBHASIS ROY | 12.67 | 0 | 0 | 0
1899 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chaitanyapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16898 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
1900 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chaitanyapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16898 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1901 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dakshin Dalhara PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16873 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
1902 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dakshin Dalhara PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16873 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1903 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Srirampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17715 | Solarisation | Solarization of grid connected pumping installation at Srirampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1040/W/MMD | 29/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 6.26 | 4.88 | 78.03 | 30
1904 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dona PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17875 | IOT | Supply and installation of Sign Board for depicting the scheme details of different on going Design development works for the purpose of Geotagging at different PWSS under Moyna block under MMD, P.H.E. Dte.in the Dist. of Purba Medinipur. | 625/HESD | 08/07/2024 | 7 | S.S.GHORAI | 0.9 | 0 | 0 | 0
1905 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dona PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17875 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1906 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kumirda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17897 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
1907 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kumirda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17897 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1908 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kudi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17899 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
1909 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kudi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17899 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1910 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17772 | Solarisation | Solarization of grid connected pumping installation at Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1023/W/MMD | 29/03/2023 | 180 | SUBHASIS ROY | 6.26 | 0 | 0 | 0
1911 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kolsar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17807 | Solarisation | Solarization of grid connected pumping installation at Kolsar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1022/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
1912 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Asadtaliya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17388 | Solarisation | Solarization of grid connected pumping installation at Asadtaliya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 744/W/MMD | 23/03/2023 | 180 | M/S. JIT ENTERPRISE | 6.26 | 4.88 | 78.03 | 60
1913 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Asadtaliya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17388 | Solarisation | Quotation bill for application fees for NET BILLING for solar power plant of 10KWp at Asadtaliya w/s scheme,Block-sutahata in the Dist. of Purba Medinipur under MMD,PHE,Dte. Name of C.C.C.-Chaitanyapur Application no-2004837084 Consumer ID-224044050 Quotation Date-25/07/2024 Quotation Due Date-90days from the date of issue | C082409418031 | 07/08/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
1914 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Tabakhali PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17882 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
1915 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Tabakhali PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17882 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1916 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Gholpukuria, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17883 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1917 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Haur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17826 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1918 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17825 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
1919 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17825 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1920 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dhanyaghara PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17914 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
1921 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dhanyaghara PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17914 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1922 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Sofiabad PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17854 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
1923 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Sofiabad PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17854 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1924 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Barbasudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17305 | Solarisation | Solarization of grid connected pumping installation at Barbasudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 729/W/MMD | 23/03/2023 | 180 | MEGA SOLAR ENERGY | 6.26 | 4.66 | 74.47 | 50
1925 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Panchrol PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17843 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
1926 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Panchrol PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17843 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1927 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Durmut PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17898 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
1928 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Durmut PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17898 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1929 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Uttar Khasda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17902 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
1930 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Uttar Khasda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17902 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1931 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bara Subarna Nagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17334 | Solarisation | Solarization of grid connected pumping installation at Bara Subarna Nagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 720/W/MMD | 23/03/2023 | 180 | AMITAVA CHAKRABORTY | 6.26 | 4.85 | 77.48 | 35
1932 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Barchunfali PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17331 | Solarisation | Solarization of grid connected pumping installation at Barchunfali PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 715/W/MMD | 23/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 0 | 0 | 0
1933 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mahammadpur (Nandigram) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17905 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
1934 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mahammadpur (Nandigram) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17905 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
1935 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II , Contai-II, Egra-II, Egra-I & Contai-III Block within Purba Medinipur District under Tamluk Division, PHE Dte , SM/17173 | New | Material Requisition To Resource Division | 2902/TD | 21/11/2023 | 0 | Resource Division | 2.26 | 0 | 0 | 0
1936 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II , Contai-II, Egra-II, Egra-I & Contai-III Block within Purba Medinipur District under Tamluk Division, PHE Dte , SM/17173 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 284.36 | 97.53 | 48
1937 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II , Contai-II, Egra-II, Egra-I & Contai-III Block within Purba Medinipur District under Tamluk Division, PHE Dte , SM/17173 | New | Installation of 150 mm.x100 mm.x 230 mtr.(av) depth Tube well(PVC) & Providing FHTC (364 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at 09 nos Different Location Block within Purba Medinipur district under Tamluk Division, PHE Dte. | 1100/TD | 08/06/2023 | 907 | SWADHIN KUMAR CHAKRABORTY | 245.94 | 26.01 | 16.56 | 51
1938 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Manoharpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17813 | Solarisation | Solarization of grid connected pumping installation at Manoharpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1011/W/MMD | 29/03/2023 | 180 | AMITAVA CHAKRABORTY | 6.26 | 0 | 0 | 0
1939 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-J ) | 3178/TD | 10/03/2023 | 15 | M/S SOURAV MAHAPATRA | 2.72 | 0 | 0 | 0
1940 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Material Requisition To Resource Division | 2463/TD | 16/01/2023 | 0 | Resource Division | 60.63 | 0 | 0 | 0
1941 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-I ) | 3177/TD | 10/03/2023 | 15 | DAS ENTERPRISE. | 9.58 | 0 | 0 | 0
1942 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-D) | 3174/TD | 10/03/2023 | 15 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.84 | 18.87 | 95.14 | 97
1943 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-E) | 3175/TD | 10/03/2023 | 15 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.83 | 18.92 | 95.43 | 97
1944 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-H ) | 3176/TD | 10/03/2023 | 15 | CHARUBALA ENTERPRISE | 9.93 | 0 | 0 | 0
1945 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-F ) | 174/TD | 11/04/2023 | 15 | AURGHA BHATTACHARYA | 9.97 | 9.12 | 91.44 | 100
1946 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-G) | 1006/TD | 05/06/2023 | 15 | MAHAMAYA TIMBER AND CONSTRUCTION | 9.96 | 9.56 | 95.97 | 96
1947 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Laying of Balance Distribution HDPE Pipe Line(180 mm dia) for Dakshin Shitala Piped Water Supply Scheme due to Revised drawing within Ramnagar-II Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. | 2873/TD | 17/11/2023 | 20 | HYDROTECH ASSOCIATES | 11.34 | 11.26 | 99.33 | 99
1948 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Land development of 2nd T/W Site at Dakshin Shitala & Its Adjoining Mouzas water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | 872/DSD | 27/08/2024 | 7 | ABHIJIT BERA | 0.91 | 0.9 | 100 | 100
1949 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Material Requisition To Resource Division | 92/TD | 05/01/2024 | 0 | Resource Division | 6.28 | 0 | 0 | 0
1950 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Quotation Bill for New Service connection at T/W NO-I Of DAKSHIN SHITALA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004905806/QUOT/03 DT. 18-09-2024 Application NO- 2004905806 Application type-New connection Consumer Id- 204402411 | C102415718521 | 05/10/2024 | 0 | WBSEDCL | 7.48 | 0 | 0 | 0
1951 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Quotation Bill for New Service connection at T/W NO-II Of DAKSHIN SHITALA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670651/QUOT/03 DT. 05-04-2024 Application NO- 2004670651 Application type-New connection Consumer Id- 204266386 | BP-2024-25-49 | 18/04/2024 | 0 | WBSEDCL | 7.85 | 0 | 0 | 0
1952 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Laying distribution pipe line, & Accommodate FHTC ( 128Nos) under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C) | 3173/TD | 10/03/2023 | 1148 | DHANANJOY DAS | 39.79 | 0 | 0 | 60
1953 | PURBA MEDINIPUR | Central Drilling | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 44.83 | 84.44 | 11
1954 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, & Accommodate FHTC ( 500Nos) under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-B) | 1096/TD | 08/06/2023 | 932 | ABHIJIT BERA | 119.92 | 69.06 | 57.59 | 48
1955 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS , SM/12407 | New | Laying distribution pipe line, soil investigation, 150 Cum OHR ( with pile foundation ) & Accommodate FHTC ( 392 Nos) under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-A) | 2437/TD | 19/09/2023 | 540 | EVEREST INFRATECH INC | 119.98 | 0 | 0 | 30
1956 | PURBA MEDINIPUR | Tamluk Division | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13741 | New | Material Requisition To Resource Division | 2696/TD | 06/02/2023 | 0 | Resource Division | 16.55 | 0 | 0 | 0
1957 | PURBA MEDINIPUR | Tamluk Division | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13741 | New | Material Requisition To Resource Division | 100/TD | 05/01/2024 | 0 | Resource Division | 3.57 | 0 | 0 | 0
1958 | PURBA MEDINIPUR | Midnapore Mechanical | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13741 | New | Quotation for new service connection at TW-I of Nilkanthapur ws scheme under MMD,PHE Dte , Block-Ramnagar-I, DIGHA CCC Application no-2004764563 Con ID-204324292 | BP-2024-25-289 | 18/06/2024 | 0 | WBSEDCL | 5.95 | 0 | 0 | 0
1959 | PURBA MEDINIPUR | Midnapore Mechanical | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13741 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NILKANTHAPUR and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1407/W/MMD | 02/06/2023 | 700 | SOUMEN ELECTRIC | 21.56 | 0 | 0 | 55
1960 | PURBA MEDINIPUR | Tamluk Division | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13741 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2813 Nos) For 2 nos Pipe Water Supply Scheme (Kainara & Nilkanthpur)including two years Operation & Maintainance work within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 2710/TD | 30/10/2023 | 790 | TAPAS SANTRA | 866.03 | 144.34 | 50.98 | 85
1961 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Surface Water Based Water Supply Scheme for Panskura-II Block of Purba Medinipur District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17648 | Solarisation | Solarization of grid connected pumping installation at Surface Water Based Water Supply Scheme for Panskura-II Block of Purba Medinipur District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1050/W/MMD | 29/03/2023 | 180 | JYOTY SOLAR POWER | 80.98 | 57.23 | 70.68 | 60
1962 | PURBA MEDINIPUR | Tamluk Division | SATSATMAL & ADJOINING MOUJAS PWSS , SM/12163 | New | Material Requisition To Resource Division | 351/TD | 26/04/2023 | 0 | Resource Division | 14.49 | 0 | 0 | 0
1963 | PURBA MEDINIPUR | Tamluk Division | SATSATMAL & ADJOINING MOUJAS PWSS , SM/12163 | New | Material Requisition To Resource Division | 1663/TD | 29/04/2024 | 0 | Resource Division | 16.25 | 0 | 0 | 0
1964 | PURBA MEDINIPUR | Midnapore Mechanical | SATSATMAL & ADJOINING MOUJAS PWSS , SM/12163 | New | Satsatamal W/S scheme PH-II Application no.-2004544493 Ref.-204176804 | BP-2023-24-578 | 18/01/2024 | 0 | WBSEDCL | 9.26 | 0 | 0 | 0
1965 | PURBA MEDINIPUR | Midnapore Mechanical | SATSATMAL & ADJOINING MOUJAS PWSS , SM/12163 | New | Satsatamal W/S scheme PH-I Application.-2004536916 Ref.-204169242 | BP-2023-24-533 | 11/01/2024 | 0 | WBSEDCL | 4.14 | 0 | 0 | 0
1966 | PURBA MEDINIPUR | Midnapore Mechanical | SATSATMAL & ADJOINING MOUJAS PWSS , SM/12163 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SATSATMAL and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2375/W/MMD | 31/12/2022 | 882 | AHALYA ENGINEERING WORKS | 25.25 | 18.31 | 72.49 | 90
1967 | PURBA MEDINIPUR | Tamluk Division | SATSATMAL & ADJOINING MOUJAS PWSS , SM/12163 | New | Sinking of Tube well,Pump House ,OHR of capacity 400 Cum & 150 Cum , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation, Rigid Pavement & Accommodate FHTC (3874 nos) Including 2 years of Operation & maintenace , under JJM with allied work for Satshatamal PWSS ,Tania Bila PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1670/TD | 25/07/2023 | 860 | HALDIA DEVELOPMENT CONSTRUCTION | 1214.41 | 306.53 | 38.33 | 60
1968 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme , SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village-Kotbar(CT),J.L. No-18 under JJM in Kotbar PWSS Block - Chandipur in the District of Purba Medinipur. | 2463/TD | 18/12/2020 | 30 | RAJ KUMAR SINGHA | 43.46 | 0 | 0 | 100
1969 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme , SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village-Kulapara,J.L. No-9 under JJM in Kotbar PWSS Block - Chandipur in the District of Purba Medinipur. | 2464/TD | 18/12/2020 | 25 | RAJ KUMAR SINGHA | 22.74 | 0 | 0 | 100
1970 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme , SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village-Kotbar(CT) of Kotbar Purba & Paschim Para,J.L. No-18 under JJM in Kotbar PWSS Block - Chandipur in the District of Purba Medinipur. | 2465/TD | 18/12/2020 | 25 | RAJ KUMAR SINGHA | 24.58 | 0 | 0 | 100
1971 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme , SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village - Kotbar (CT) of Kotbar Purba and Paschim Para under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 726/W | 18/02/2021 | 0 | RAJ KUMAR SINGHA | 24.17 | 0 | 0 | 0
1972 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme , SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village - Kulapara under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 223/W | 01/09/2021 | 0 | RAJ KUMAR SINGHA | 1.16 | 0 | 0 | 0
1973 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme , SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village - Kotbar (CT) under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 682/W | 27/01/2021 | 0 | RAJ KUMAR SINGHA | 42.23 | 0 | 0 | 0
1974 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme , SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village - Kulapara under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 683/W | 27/01/2021 | 0 | RAJ KUMAR SINGHA | 21.58 | 0 | 0 | 0
1975 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme , SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village - Kotbar (CT) under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 222/W | 01/09/2021 | 0 | RAJ KUMAR SINGHA | 1.23 | 0 | 0 | 0
1976 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme , SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village - Kotbar (CT) of Kotbar Purba and Paschim Para under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 217/W | 27/08/2021 | 0 | RAJ KUMAR SINGHA | 0.41 | 0 | 0 | 0
1977 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme , SM/06879 | Retrofitting | Functional Household Tap Connection to the 311 nos. Household of Bankiput Water Supply Scheme within Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Payrakola (609) ii) Bargolia (610) iii) Hajrakola (611) iv) Bhogpur (624) v) Kalichar (626) vi) Kalidasbar (627). | 2451/TD | 18/12/2020 | 20 | AHINDRA BARIK | 15.31 | 0 | 0 | 100
1978 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme , SM/06879 | Retrofitting | Functional Household Tap Connection to the 232 nos. Household of Bankiput Water Supply Scheme within Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Bankipur(629) ii ) Tiakola (630). | 2452/TD | 18/12/2020 | 20 | JASODA ENTERPRISE | 11.46 | 0 | 0 | 100
1979 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme , SM/06879 | Retrofitting | Functional Household Tap Connection to the 202 nos. Household of Bankiput Water Supply Scheme within Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Bhupatichak (628) ii ) Kaluraybar (631) iii) Kanaichatta (632). | 2453/TD | 18/12/2020 | 20 | SUBHENDU HAZRA | 10 | 0 | 0 | 100
1980 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme , SM/06879 | Retrofitting | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Bankiput W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. | 802/W | 24/02/2021 | 0 | SUBHENDU HAZRA | 9.68 | 0 | 0 | 0
1981 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme , SM/06879 | Retrofitting | Retrofitting to accomodate for 232 Nos. FHTC connection under JJM in Bankiput W/S Scheme within Contai - II Dev. Block Block under Tamluk Division, PHE Dte. | 729/W | 18/02/2021 | 0 | JASODA ENTERPRISE | 11.46 | 0 | 0 | 0
1982 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme , SM/06879 | Retrofitting | Retrofitting to accomodate for 311 Nos. FHTC connection under JJM in Bankiput W/S Scheme within Contai - II Dev. Block Block under Tamluk Division, PHE Dte. | 861/W | 16/03/2021 | 0 | AHINDRA BARIK | 15.01 | 0 | 0 | 0
1983 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme , SM/06879 | Retrofitting | Retrofitting to accommodate FHTC 19 Nos. at different School under JJM in Bankiput PWSS Block-Contai - I under Tamluk Division, PHE Dte. | 603/W | 24/02/2022 | 0 | JASODA ENTERPRISE | 0.85 | 0 | 0 | 0
1984 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme , SM/06879 | Retrofitting | Retrofitting to accommodate FHTC 19 Nos. at different School under JJM in Bankiput PWSS Block-Contai - I under Tamluk Division, PHE Dte. | BP-2021-22-279 | 25/02/2022 | 0 | JASODA ENTERPRISE | 0.66 | 0 | 0 | 0
1985 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme , SM/06879 | Retrofitting | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well of Source Augmentation of Bankiput & its adjoining mouzas Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 1000/TD | 05/06/2023 | 30 | GITA ENTERPRISE | 3.39 | 0 | 0 | 0
1986 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme , SM/06879 | Retrofitting | Construction of 3.60 mtr. x 3.00 mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well of Source Augmentation of Bankiput W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division,PHE Dte. | 1001/TD | 05/06/2023 | 60 | GITA ENTERPRISE | 3.97 | 0 | 0 | 0
1987 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Lakshya PWSS Block - Mahishadal in the District of Purba Medinipur , SM/07656 | Retrofitting | Retrofitting to accomodate FHTC of Lakshya W/S Scheme within Mahishadal under Tamluk Division, PHE Dte. | BP-2021-22-39 | 23/07/2021 | 0 | HARIPADA PATTANAYAK | 60.72 | 0 | 0 | 0
1988 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Lakshya PWSS Block - Mahishadal in the District of Purba Medinipur , SM/07656 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Lakshya PWSS Block- Mahishadal in the District of Purba Medinipur. | 2844/TD | 08/02/2021 | 70 | HARIPADA PATTANAYAK | 160.74 | 138.8 | 151.87 | 100
1989 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block , SM/07658 | Retrofitting | Retrofitting to accommodate FHTC (741 nos) under JJM in Mahammadpur PWSS within Mahammadpur JL No.-185- (Uttar Mahammadpur) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-B) | 2822/TD | 05/02/2021 | 30 | NARAYAN CHANDRA DAS | 35.29 | 0 | 0 | 100
1990 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block , SM/07658 | Retrofitting | Functional Household Tap Connection to the 370 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Benauda (16) - Part,Mabarakpur (20)] Part-E. | 112/TD | 17/05/2021 | 20 | SUBHENDU HAZRA | 17.49 | 15.92 | 91 | 100
1991 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block , SM/07658 | Retrofitting | Functional Household Tap Connection to the 411 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Chapal Ghata (13) - Part, Parial Chak (15),Benauda (16) - Part] Part-D. | 111/TD | 17/05/2021 | 20 | M/S. NEW DINDA ENTERPRISE | 19.33 | 18.1 | 93.64 | 100
1992 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block , SM/07658 | Retrofitting | Functional Household Tap Connection to the 588 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Mahammadpur (07) - Part, Durbba Chakri (14),Manoharpur (10) - Part] Part-B. | 109/TD | 17/05/2021 | 25 | JASODA ENTERPRISE | 27.79 | 27.79 | 100 | 100
1993 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block , SM/07658 | Retrofitting | Functional Household Tap Connection to the 1783 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District.[Mouza-Mahammadpur(07) - Part] Part-A. | 108/TD | 17/05/2021 | 60 | DAS CONSTRUCTION | 83.89 | 82.45 | 100 | 100
1994 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block , SM/07658 | Retrofitting | Functional Household Tap Connection to the 510 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Manoharpur (10) - Part, Tiraipur (11),Chapal Ghata (13) - Part] Part-C. | 110/TD | 17/05/2021 | 25 | MRINAL KANTI PRADHAN | 24.1 | 20.98 | 87.03 | 100
1995 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haldia Piped Water Supply Scheme , SM/07106 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Haldia PWSS Block - Ramnagar-I in the District of Purba Medinipur. | 2662/TD | 11/01/2021 | 60 | SANKHA ENTERPRISE | 96.1 | 10.96 | 11.4 | 100
1996 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haldia Piped Water Supply Scheme , SM/07106 | Retrofitting | Retrofitting to accomodate FHTC under JJM Haldia W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. | 966/W | 25/03/2021 | 0 | SANKHA ENTERPRISE | 80 | 0 | 0 | 0
1997 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haldia Piped Water Supply Scheme , SM/07106 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Haldia PWSS within Ramnagar ¿I Block under Tamluk Division, PHE Dte. | 1113/W | 30/03/2021 | 0 | SANKHA ENTERPRISE | 3.98 | 0 | 0 | 0
1998 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haldia Piped Water Supply Scheme , SM/07106 | Retrofitting | Laying of Distribution pipe line by UPVC pipes with allied works for jointing of Existing line( N.P-55A-55B, N.P-56A-56B, 58A-58B) under Haldia & its adjoining mouzas W/S Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 986/DSD | 17/01/2024 | 7 | LOKENATH ENTERPRISES | 0.97 | 0.94 | 100 | 100
1999 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS under Nandakumar Block. , SM/07481 | Retrofitting | Hiring of One No. Diesel Motor Cabs & Maxi Cab with contract carriage permit from RTA for the office of Engineer-In-Chief, Govt. of West Bengal, PHE Dte. for the month of May, 2022, June, 2022 and July, 2022 | BP-2022-23-578 | 30/12/2022 | 0 | KRISHNA MONDAL | 1.2 | 0 | 0 | 0
2000 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS under Nandakumar Block. , SM/07481 | Retrofitting | Hiring of One No. Diesel Motor Cabs & Maxi Cab with contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division, PHE Dte. for the period from November, 2021 to March, 2022. | BP-2022-23-452 | 25/11/2022 | 0 | TAPAS SANTRA | 1.97 | 0 | 0 | 0
2001 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS under Nandakumar Block. , SM/07481 | Retrofitting | Hiring of One No. Diesel Motor Cabs & Maxi Cab with contract carriage permit from RTA for the office of Assistant Engineer, Tamluk Sub-Division, PHE Dte. for the period from June, 2022 to August, 2022. | BP-2022-23-455 | 01/12/2022 | 0 | DEBNATH MAITY | 1.2 | 0 | 0 | 0
2002 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS under Nandakumar Block. , SM/07481 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS, Block- Nandakumar under Tamluk Sub-Division of Tamluk Division in the District of Purba Medinipur. | BP-2021-22-385 | 31/03/2022 | 0 | MAA ANANDAMAYEE | 3.38 | 0 | 0 | 0
2003 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS under Nandakumar Block. , SM/07481 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS, Block- Nandakumar under Tamluk Sub-Division of Tamluk Division in the District of Purba Medinipur. | 2468/TD | 18/12/2020 | 25 | MAA ANANDAMAYEE | 20.9 | 0 | 0 | 0
2004 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS under Nandakumar Block. , SM/07481 | Retrofitting | Construction of approach road at head work site of Kolsar PWSS under Tamluk Sub-division of Tamluk Division PHE Dte.( 20.0 mtr) | 2733/TSD | 13/08/2025 | 15 | M/S MONDAL CONSTRUCTION & CO. | 1.2 | 0 | 0 | 0
2005 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District (Mouza-Barsuri, JL-76.)PART-F | 2832/TD | 05/02/2021 | 20 | SHAKEEL KHAN | 9.71 | 0 | 0 | 100
2006 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Alinan, JL-39.)PART- C | 2829/TD | 05/02/2021 | 20 | S.D. CONSTRUCTION | 9.69 | 0 | 0 | 100
2007 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Saira, JL-38.)PART- D | 2830/TD | 05/02/2021 | 20 | S.D. CONSTRUCTION | 9.7 | 0 | 0 | 100
2008 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Functional Household Tap connection to the 205 nos(Barsuri-28 nos + Belun-140nos,Soyadighi-37) Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District (Mouza-Barsuri , Belun & Soyadighi, JL-76 , 75 & 36.) PART-G. | 2833/TD | 05/02/2021 | 20 | TARUN KOLEY | 9.71 | 0 | 0 | 100
2009 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District (Mouza-Saira, JL-38.)PART- E. | 2831/TD | 05/02/2021 | 20 | J.M. CONSTRUCTION | 9.7 | 0.32 | 100 | 100
2010 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Functional Household Tap connection to the 750 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Shirui, JL-74.)PART- A. | 2827/TD | 05/02/2021 | 30 | DILIP KUMAR GHOSH | 35.45 | 6.34 | 100 | 100
2011 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | unctional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Alinan, JL-39.)PART- B | 2828/TD | 05/02/2021 | 20 | DEBDUT CONSTRUCTION | 9.69 | 0.44 | 100 | 100
2012 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme within Sahid Matangini Block under Tamluk Division, PHE Dte. | 1117/W | 30/03/2021 | 0 | DILIP KUMAR GHOSH | 29.1 | 0 | 0 | 0
2013 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme under Tamluk Division, PHE Dte. | 1099/W | 30/03/2021 | 0 | S.D. CONSTRUCTION | 9.36 | 0 | 0 | 0
2014 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme under Tamluk Division, PHE Dte. | 1109/W | 30/03/2021 | 0 | S.D. CONSTRUCTION | 9.26 | 0 | 0 | 0
2015 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Functional Household Tap Connection for Alinan Zone - II W/S Scheme within Sahid Matangini Block Tamluk Division, PHE Dte. | 1111/W | 30/03/2021 | 0 | J.M. CONSTRUCTION | 9.37 | 0 | 0 | 0
2016 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Functional Household Tap Connection for Alinan Zone - II W/S Scheme within Sahid Matangini Block Tamluk Division, PHE Dte. | 1107/W | 30/03/2021 | 0 | SHAKEEL KHAN | 9.41 | 0 | 0 | 0
2017 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Retrofitting to accomodate FHTC 205 Nos. connection under JJM Alinan Zone - II W/S Scheme within Sahid Matangini Dev. Block under Tamluk Division, PHE Dte. (Part-B) | BP-2021-22-54 | 05/08/2021 | 0 | DEBDUT CONSTRUCTION | 9.25 | 0 | 0 | 0
2018 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme under Tamluk Division, PHE Dte. | 1110/W | 30/03/2021 | 0 | TARUN KOLEY | 9.48 | 0 | 0 | 0
2019 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Left out of ( 90 mm & 75 mm) OD pvc laying distribution system of pipe line and its allied works for Alinan zone-II Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1150/TD | 31/08/2022 | 15 | TARUN KOLEY | 3.39 | 3.39 | 100 | 100
2020 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Left out of 110 mm OD pvc laying distribution system of pipe line and its allied works for Alinan Zone-II Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1151/TD | 31/08/2022 | 15 | TARUN KOLEY | 4.52 | 0.41 | 100 | 100
2021 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. , SM/07485 | Retrofitting | Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | 2209/TD | 01/09/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 2.28 | 100 | 100
2022 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Work for repair of damaged pipe line due to Amphoon cyclone of Gholepukuria Zone-I Water supply Scheme within Nandigram-II Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3400/TD | 26/03/2021 | 15 | ZENITH CONSTRUCTION | 4.7 | 4.65 | 100 | 0
2023 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of SONACHURA Water Supply Scheme within Nandigram -I Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3401/TD | 26/03/2021 | 15 | RAJ KUMAR SINGHA | 4.37 | 3.66 | 100 | 0
2024 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Work for repair and construction of damaged Boundary Wall due to Amphoon Cyclone at Natshal Lakshya Store (Zone-I) Water Supply scheme Head work site cum store under Haldia Sub-Division in Tamluk Division, P.H.E. Dte. Purba Medinipur. | 3403/TD | 26/03/2021 | 15 | ZENITH CONSTRUCTION | 4.78 | 3.67 | 100 | 0
2025 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repair of damaged Boundary Wall due to Amphoon Cyclone at Head Work Site of Tabakhali Water Supply Scheme under Haldia Sub-Division in Tamluk Division, P.H.E. Dte. Purba Medinipur. | 3404/TD | 26/03/2021 | 15 | NARAYAN CHANDRA DAS | 4.85 | 4.48 | 100 | 0
2026 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Asodtalia Water supply Scheme within Sutahata Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3397/TD | 26/03/2021 | 15 | RAJ KUMAR SINGHA | 3.69 | 2.22 | 100 | 0
2027 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of CHAITANYAPUR (Zone-I) Water Supply Scheme within Sutahata Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3398/TD | 26/03/2021 | 15 | RAJ KUMAR SINGHA | 4.47 | 2.79 | 100 | 0
2028 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Work for repair of damaged pipe line due to Amphoon cyclone of Begunberia Water supply Scheme within Sutahata Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3382/TD | 26/03/2021 | 15 | RAJ KUMAR SINGHA | 3.79 | 2.03 | 100 | 0
2029 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Work for repair of damaged pipe line due to Amphoon cyclone of Tabakhali Water Supply Scheme within Sutahata Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3385/TD | 26/03/2021 | 15 | NARAYAN CHANDRA DAS | 4.49 | 2.88 | 100 | 0
2030 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Gholepukuria Zone-II Water Supply Scheme within Nandigram-II Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3384/TD | 26/03/2021 | 15 | ZENITH CONSTRUCTION | 4.85 | 4.79 | 100 | 0
2031 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3383/TD | 26/03/2021 | 15 | RAJ KUMAR SINGHA | 3.97 | 2.46 | 100 | 0
2032 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repair of damaged switch room -cum chlorine room with water supply & sanitary arrangement due to Amphoon cyclone at Head work site of Dhenkua water supply scheme under Haldia Sub-Division of Tamluk Division PHE Dte. Purba Medinipur. | 1052/TD | 02/11/2021 | 15 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.16 | 0.85 | 100 | 0
2033 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repair Construction and upgradation of damaged Boundary Wall due to Amphoon Cyclone at the office of the Assistant Engineer, under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Part-A) | 1711/TD | 01/02/2022 | 45 | RAI CONSTRUCTION | 4.74 | 4.73 | 100 | 0
2034 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repair Construction and upgradation of damaged Boundary Wall due to Amphoon Cyclone at the office of the Assistant Engineer, under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Part-B) | 1712/TD | 01/02/2022 | 45 | MODERN CONSTRUCTION | 4.45 | 4.18 | 100 | 0
2035 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Natshal Lakhya (Zone-II ) Water supply Scheme within Mahisadal Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 857/HSD | 18/03/2021 | 15 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 1.17 | 0.77 | 100 | 0
2036 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repairing of defunct Mark-II Tube Well during Amphan- 2020 at different place (25 nos.) within Nandigram-I Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. (PART-A) | 1290/TD | 13/09/2022 | 10 | TAPAN BERA | 4.38 | 4.38 | 100 | 0
2037 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Work Order for repairing of defunct Mark-II Tube well during Amphan - 2020 at different places (11 nos) within Nandigram-I Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. (Part-C) | 574/HSD | 22/08/2022 | 7 | TAPAN BERA | 1.93 | 1.93 | 100 | 0
2038 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repairing of defunct Mark-II Tube Well during Amphan- 2020 at different place (25 nos.) within Nandigram-I Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. (PART-B) | 1291/TD | 13/09/2022 | 10 | TAPAN BERA | 4.38 | 4.38 | 100 | 0
2039 | PURBA MEDINIPUR | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. , SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Dhenkua Water Supply Scheme within Sutahata Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3399/TD | 26/03/2021 | 15 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.73 | 2.82 | 100 | 0
2040 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Barasubarnanagar W/S Scheme (PHASE-II) , SM/08229 | Retrofitting | Retrofitting to accomodate FHTC under JJM Barasubarnagar W/S Scheme within Deshapran Dev. Block under Tamluk Division, PHE Dte. (Phase-II) | BP-2021-22-35 | 23/07/2021 | 0 | NARAYAN MANDAL | 30.18 | 0 | 0 | 0
2041 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Barasubarnanagar W/S Scheme (PHASE-II) , SM/08229 | Retrofitting | Retrofitting to accommodate FHTC [ 206 nos] under JJM in Barasubarnanagar PWSS [Prakash Kultalia 1st Part(500,part),Chaitanyapur(501, part),Bara Subarnanagar(502, part),Rupnagar(503, part),Krishnalal Chak(504, part),Sikdar Chak(505,part),DahaShonamui(506,part),Bamunia Nankar(510,part),Purba Bhagabanpur(517, part)] within Contai-II Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) |  | 08/06/2021 | 0 | NARAYAN MANDAL | 30.18 | 0 | 0 | 0
2042 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Mandarmani PWSS (Phase-II) under Ramnagar II Block , SM/09052 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Mandarmani PWSS (PHASE-II) Block - Ramnagar-II in the District of Purba Medinipur. (PART- A) | 1019/TD | 02/11/2021 | 20 | ABHIJIT BERA | 21.29 | 21.29 | 99.96 | 100
2043 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Mandarmani PWSS (Phase-II) under Ramnagar II Block , SM/09052 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Mandarmani PWSS (PHASE-II) Block - Ramnagar-II in the District of Purba Medinipur ( PART - B ) | 1020/TD | 02/11/2021 | 30 | UNIQUE AGENCY | 52.71 | 52.71 | 100 | 100
2044 | PURBA MEDINIPUR | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) , SM/09056 | Retrofitting | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- D) | 1018/TD | 02/11/2021 | 20 | NARAYAN CHANDRA DAS | 22.37 | 22.37 | 100 | 100
2045 | PURBA MEDINIPUR | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) , SM/09056 | Retrofitting | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- A) | 1015/TD | 02/11/2021 | 20 | MAA KALI CONSTRUCTION | 20.35 | 20.34 | 100 | 100
2046 | PURBA MEDINIPUR | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) , SM/09056 | Retrofitting | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- B) | 1016/TD | 02/11/2021 | 20 | LOKENATH ENTERPRISES | 20.29 | 20.28 | 100 | 100
2047 | PURBA MEDINIPUR | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) , SM/09056 | Retrofitting | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- C) | 1017/TD | 02/11/2021 | 20 | SHAKEEL KHAN | 22.37 | 22.37 | 100 | 100
2048 | PURBA MEDINIPUR | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) , SM/09056 | Retrofitting | Laying ( Left out ) UPVC pipe line to accommodate FHTC under JJM in PANCHROL PWSS within EGRA -I BLOCK ( to Support phase I FHTC ) (part -B )under Digha Sub Division of Tamluk Division PHE Dte. | 1541/TD | 11/01/2022 | 15 | LOKENATH ENTERPRISES | 4.76 | 0 | 0 | 100
2049 | PURBA MEDINIPUR | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) , SM/09056 | Retrofitting | Laying distribution pipe line to accommodate FHTC of Panchrol Water Supply Scheme within Egra - I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. Within (Panchrol West part ). | 1781/TD | 08/02/2022 | 20 | SHAKEEL KHAN | 11.26 | 0 | 0 | 100
2050 | PURBA MEDINIPUR | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Dulalpur PWSS. , SM/09057 | Retrofitting | Retrofitting to accomodate FHTC under JJM in DULALPUR PWSS Block - Egra-II in the District of Purba Medinipur | 1012/TD | 02/11/2021 | 30 | BIDHAN MONDAL | 57.42 | 57.41 | 99.99 | 100
2051 | PURBA MEDINIPUR | Tamluk Division | Balance work for Retrofitting to accommodate FHTC (907 Nos.) and laying of laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for , SM/09058 | Retrofitting | Balance Work for Retrofitting to accommodate FHTC (907 Nos) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water based water supply scheme for Zone-VII ,Block-Kolaghat in the District of Purba Medinipur under tamluk Division. (Phase-II) | 1069/TD | 08/11/2021 | 60 | TARUN KOLEY | 119.62 | 115.86 | 100 | 100
2052 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-II Water Supply Scheme. , SM/09338 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) PWSS (Zone - II) Water Supply under Tamluk Division, PHE Dte. | 1178/TD | 02/12/2021 | 20 | HORIZEN | 6.26 | 6.26 | 100 | 100
2053 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-II Water Supply Scheme. , SM/09338 | Augmentation | Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.12.2021 to 30.11.2022 i.e. 01 (One) year for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. | 309/RWS/TSD | 01/12/2021 | 365 | SRIMANTA PANJA | 1.48 | 2.35 | 100 | 100
2054 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-II Water Supply Scheme. , SM/09338 | Augmentation | Material Requisition To Resource Division | 641/TD | 27/06/2022 | 0 | Resource Division | 23.01 | 0 | 0 | 0
2055 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-II Water Supply Scheme. , SM/09338 | Augmentation | Material Requisition To Resource Division | 652/TD | 27/06/2022 | 0 | Resource Division | 10.05 | 0 | 0 | 0
2056 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-II Water Supply Scheme. , SM/09338 | Augmentation | Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at OHR Site and Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at 2 nd Tube Well Site for Mohisda (Zone-II) Water Supply Scheme within Sahid Matangini Dev.Block under Tamluk Sub Division,PHE Dte. | 3205/TD | 14/03/2023 | 30 | TARUN KOLEY | 16.19 | 0 | 0 | 100
2057 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-II Water Supply Scheme. , SM/09338 | Augmentation | Material Requisition To Resource Division | 1114/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
2058 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-II Water Supply Scheme. , SM/09338 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mohisda Zone-II & its adjoining mouzas Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 622/TD | 22/06/2022 | 1193 | TARUN KOLEY | 570.24 | 337.16 | 59.13 | 85
2059 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Golaranji Water Supply Scheme under Tamluk Division, PHE Dte. | 1615/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.46 | 3.04 | 100 | 100
2060 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell (Mouza - Gonara, JL No. - 187, Plot No. -41)of Golaranij Water Supply Scheme under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | 134/TD | 19/04/2022 | 21 | MENAKA ENTERPRISE | 13.26 | 0 | 0 | 0
2061 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Rejuvenation of Golaranij Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | 1835/TD | 08/08/2023 | 20 | RAMESH & SHANTI ENGINEERING WORKS | 4.2 | 4.2 | 100 | 100
2062 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Material Requisition To Resource Division | 1249/TD | 13/12/2021 | 0 | Resource Division | 10.87 | 0 | 0 | 0
2063 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Material Requisition To Resource Division | 1273/TD | 12/09/2022 | 0 | Resource Division | 18.08 | 0 | 0 | 0
2064 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 816/W/MMD | 24/03/2023 | 180 | MEGA SOLAR ENERGY | 11.79 | 0 | 0 | 85
2065 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Providing drilling crews Including Allied Materials for construction of Tube Well ( 250mm X150mm) at Golaranji W/S Scheme within Purba Medinipur District under Central Drilling Division, P.H.E. Dte. | 1412/CDD | 20/09/2023 | 149 | MENAKA ENTERPRISE | 11.26 | 9.61 | 100 | 100
2066 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Quotation Bill for New Service connection at T/W NO-III Of GOLARANIJ W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004609771/QUOT/03 DT. 21-02-2024 Application NO- 2004609771 Application type-New connection Reference Id- 204223235 | BP-2023-24-823 | 13/03/2024 | 0 | WBSEDCL | 5.82 | 0 | 0 | 0
2067 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Augmentation of ground water based Golaranij Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Potashpur-I Dev. Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 1370/TD | 23/09/2022 | 180 | KISHORE GHOSH | 392.47 | 262.56 | 66.9 | 70
2068 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Name of Work: i) Laying Rising main and other allied works Augmentation of Golaranij W/S Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Augmentation of Golaranij PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-136.00 mtr.) iii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Golaranij PWSS within Patashpur -I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | 3221/TD | 14/03/2023 | 828 | M/S. PRADIP PRADHAN | 35.86 | 4.46 | 12.44 | 80
2069 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Repair and Renovation of Pump House & Boundary Wall and others allied works for 1st Tube well site and 2nd Tube Well site at Golaranij Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 3318/TD | 22/10/2024 | 30 | BADAL CHANDRA GOLE | 4.92 | 0 | 0 | 100
2070 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Laying Distribution Pipe Line With allied Works of Left Out Area for Augmentation Of Golaranij Water Supply Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte., Purba Medinipur District. (PHASE-II) | 738/TD | 28/02/2024 | 275 | KISHORE GHOSH | 44.24 | 0 | 0 | 100
2071 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji , SM/09447 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Golaranij W/S Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | 1212/TD | 06/09/2022 | 60 | BADAL CHANDRA GOLE | 3.81 | 3.28 | 100 | 100
2072 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC (410) Nos. under JJM in Keshabpur Jalpai PWSS (Balance Part-Phase-II) under Mahishadal Dev. Block. , SM/10346 | Retrofitting | Retrofitting to accommodate FHTC (410 Nos.) under JJM in Keshabpur Jalpai PWSS (Balance Part : Phase-II) Block - Mahisadal in the District of Purba Medinipur | 2006/TD | 08/03/2022 | 25 | RAJ KUMAR SINGHA | 23.33 | 19.06 | 100 | 100
2073 | PURBA MEDINIPUR | Tamluk Division | Balance work for Retrofitting to Accommodate FHTC (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-VIII, , SM/10434 | Retrofitting | Laying damage portion of different dia. UPVC pipes within Surface Water Based Water Supply Scheme for Zone- VIII of Kolaghat Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 63/TD | 05/04/2022 | 20 | CONCORD ENGINEERING | 12.59 | 12.58 | 100 | 100
2074 | PURBA MEDINIPUR | Tamluk Division | Balance work for Retrofitting to Accommodate FHTC (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-VIII, , SM/10434 | Retrofitting | Retrofitting to accommodate FHTC(Balance work) (200 nos.) and laying of left-out portion with uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone- VIII, Block-Kolaghat in the District of Purba Medinipur(Phase-III) | 616/TD | 21/06/2022 | 20 | ARABINDA GHOSH | 78.41 | 67.03 | 100 | 100
2075 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nagua PWSS under Egra-I Block. , SM/09804 | Retrofitting | Providing FHTC under JJM in Negua PWSS within Egra-I Dev. Block under Digha Sub-Division of Tamluk Division PHE Dte.in the District of Purba Medinipur. | 1641/TD | 19/01/2022 | 120 | M/S CARE | 137.35 | 84.49 | 61.51 | 85
2076 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nagua PWSS under Egra-I Block. , SM/09804 | Retrofitting | Material Requisition To Resource Division | 1748/TD | 08/02/2022 | 0 | Resource Division | 15.3 | 0 | 0 | 0
2077 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nagua PWSS under Egra-I Block. , SM/09804 | Retrofitting | Retrofitting to accommodate FHTC (Phase-II) of Negua PWSS, Egra - I Block under Digha Sub-Division PHE Dte. of Tamluk Division PHE Dte. in the District of Purba Medinipur. | 621/TD | 17/05/2023 | 25 | SOM CONSTRUCTION | 15.44 | 15.44 | 100 | 100
2078 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Laying distribution pipe line & other allied works for water supplying arrangement to Dakhin Damodarpur PHC through Thakuachak PWSS under Tamluk Sub- Division of Tamluk Division, PHE Dte.with in Purba Mednipur District. | 1228/TD | 08/12/2021 | 40 | ANUSKA ENTERPRISE | 17.87 | 17.85 | 100 | 100
2079 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Thenkuachak (Zone - I & II) Water Supply Scheme under Tamluk Division, PHE Dte. | 1607/TD | 14/01/2022 | 20 | INDRANIL DUTTA & ASSOCIATES | 8.64 | 8.59 | 100 | 100
2080 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Additional laying distribution pipe line & other allied works for water supplying arrangement to Dakhin Damodarpur PHC through Thakuachak PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.with in Purba Mednipur District. | 292/TD | 06/05/2022 | 15 | MALLICK CONSTRUCTION | 3.91 | 3.91 | 100 | 100
2081 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES AT SITE FOR CONSTRUCTION OF TUBE WELL IN THENKUA CHAK PWSS, ZONE-II, BLOCK-NANDAKUMAR, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. | 410/CMSD-II | 12/08/2022 | 10 | PADMA ENGINEERING & CO. | 0.93 | 0.91 | 100 | 100
2082 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL DEPARTMENTAL RIG MACHINE AT NANDAKUMAR BLOCK, DIST. PURBA MEDINIPUR UNDER CDD, PHE DTE. | 143/S&WSD | 12/08/2022 | 15 | PADMA ENGINEERING & CO. | 5 | 4.4 | 100 | 100
2083 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | SUPPLY & DELIVERY OF TUBE WELL MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN THENKUA CHAK PWSS, ZONE-II, TW-II, BLOCK- NANDAKUMAR, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. | 411/CMSD-II | 12/08/2022 | 10 | PADMA ENGINEERING & CO. | 0.98 | 0.98 | 100 | 100
2084 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN THENKUA CHAK [PWSS, TW-II, ZONE-II, BLOCK - NANDAKUMAR, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. | 409/CMSD-II | 12/08/2022 | 10 | PADMA ENGINEERING & CO. | 0.98 | 0.98 | 100 | 100
2085 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR THENKUACHAK W/S SCH (TW-III), NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 1228/CDD | 16/11/2022 | 30 | PADMA ENGINEERING & CO. | 18.84 | 17.18 | 100 | 100
2086 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 240 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCH (TW-II), MOYNA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, [PHE DTE. | 387/CDD | 18/05/2022 | 30 | PADMA ENGINEERING & CO. | 14.26 | 8.65 | 100 | 100
2087 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Fuel Charges for the month of November 2022 | BP-2022-23-280 | 21/12/2022 | 0 | MIRA SERVICE STATION | 0.22 | 0 | 0 | 0
2088 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District., under JJM Program under MMD PHE Dte. | 213/W/MMD | 10/02/2023 | 180 | DAS ENTERPRISE | 40.3 | 37.84 | 93.91 | 60
2089 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR THENKUACHAUK W/S SCH UNDER PURBA MIDNAPORE DISREICT, CDD, PHE DTE. | 1382/CDD | 24/11/2022 | 30 | MENAKA ENTERPRISE | 19.39 | 16.46 | 100 | 100
2090 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Material Requisition To Resource Division | 413/TD | 25/05/2022 | 0 | Resource Division | 121.31 | 0 | 0 | 0
2091 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Material Requisition To Resource Division | 414/TD | 25/05/2022 | 0 | Resource Division | 46.43 | 0 | 0 | 0
2092 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Material Requisition To Resource Division | 1267/TD | 12/09/2022 | 0 | Resource Division | 59.51 | 0 | 0 | 0
2093 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Electric Quotation for Tube Well-III, Z-II of Thenkuachak W/S Scheme at Nandakumar CCC (2004173196) | BP-2022-23-110 | 01/03/2023 | 0 | WBSEDCL | 8.3 | 0 | 0 | 0
2094 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Electric Quotation for Tube Well-III, Z-I of Thenkuachak W/S Scheme at Nandakumar CCC (2004172999) | BP-2022-23-111 | 01/03/2023 | 0 | WBSEDCL | 1.11 | 0 | 0 | 0
2095 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Payment to WBSEDCL for Quotation Money for Thenkuachak PWSS under Tamluk Division, PHE Dte. | BP-2022-23-755 | 28/02/2023 | 0 | WBSEDCL | 4.07 | 0 | 0 | 0
2096 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Pilling work & casing pipe (GI/MS)over khal and Road crossing of various junction of Thekuachak Zone-II water supply scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 806/TD | 30/05/2023 | 30 | GHOSH ENTERPRISE | 14.63 | 5.86 | 40.08 | 50
2097 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Drum sheet walling in different nodal point under Thekuachak Zone-I water supply scheme under Tamluk Division, Purba Medinipur,PHE Dte. | 1920/TD | 07/06/2024 | 20 | GHOSH ENTERPRISE | 13.39 | 0 | 0 | 0
2098 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Thekuachak zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 3171/TD | 10/03/2023 | 60 | ANIRBAN MONDAL | 4.59 | 4.57 | 100 | 100
2099 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Thekuachak Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 3172/TD | 10/03/2023 | 60 | TARUN KHATUA | 5.11 | 5.11 | 100 | 100
2100 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Thekuachak zone-I PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 333/TD | 25/04/2023 | 480 | GHOSH ENTERPRISE | 15.05 | 5.78 | 42.08 | 70
2101 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Additional works of Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Thekuachak Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur .( Low Land ) | 1446/TD | 13/07/2023 | 40 | TARUN KHATUA | 1.86 | 1.83 | 100 | 100
2102 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Cannel crossing for DI and uPVC pipes of Thekua chak Zone-II PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. (Nodal Point 139-140, 410-528, 165-164, 636-448, 675-381, 783-789, 665-214 and 55-221= 8 nos) | 2986/TD | 29/11/2023 | 30 | GHOSH ENTERPRISE | 33.58 | 17.04 | 100 | 100
2103 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Canel crossing for DI and uPVC pipes of Thekua chak Zone-I PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. ( Nodal 167-112, 585-327,33-98,337-401 and 213-109 )= 5 nos | 2985/TD | 29/11/2023 | 30 | GHOSH ENTERPRISE | 20.97 | 20.44 | 100 | 100
2104 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Laying of DI (K7) ( Nodal point 167 to 627) ,UPVC pipe (Nodal 167-623) & Supply of of DI (Specials) under Thekuachak Zone-I Water Supply Scheme under Tamluk Division, Purba Medinipur, PHE Dte. | 1905/TD | 07/06/2024 | 20 | GHOSH ENTERPRISE | 12.87 | 0 | 0 | 100
2105 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Material Requisition To Resource Division | 670/W | 22/02/2024 | 0 | Resource Division | 16.44 | 0 | 0 | 0
2106 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 750 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Thenkuachak Zone-II Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 1021/TD | 08/08/2022 | 180 | ARABINDA GHOSH | 1009.34 | 650.99 | 64.5 | 70
2107 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 550 cum and staging height 20.00 mtr. and staging height 20.00 mtr as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Thenkuachak Zone-I Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.. | 1020/TD | 08/08/2022 | 1080 | ARABINDA GHOSH | 705.19 | 617.42 | 87.55 | 90
2108 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Thekuachak zone-II PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 332/TD | 25/04/2023 | 60 | GHOSH ENTERPRISE | 17.82 | 10.35 | 58.09 | 70
2109 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Construction of Concrete road for Kharar Pool ( Mansa Mandir) (Nodal Point -38) to Head work site of Thekuachak Zone -I(Nodal point 1158 )( Length - 350 mtr, width 2.10 mte , Depth of cincrete 150 mm ) | 2988/TD | 29/11/2023 | 30 | KRISHNENDU SEKHAR DAS | 9.63 | 9.11 | 94.65 | 100
2110 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Continuation Work Order for Hire charges of Bharat Stage-IV Diesel Motor Cabs (Luxury Taxi)/Swift Desire/Ambassador Non AC) having Contract Carriage Permit from the Reginal Transport Authority valid for the State of West Bengal on monthly Hire rate basis for the period from 15/07/2024 to 14/07/2025 (12 months) to be used by the Assistant Engineer, Head Quarters, Tamluk Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxies, Insurance, Fees etc. as applicable Fuel :- a) Diesel - 12 Km./Ltr. b) Mobile Oil 500 Km./Ltr. | 2227/TD | 11/07/2024 | 365 | THREE MAA ENTERPRISE | 1.24 | 3.77 | 304.11 | 0
2111 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Repairing & Renovation of Construction of Pump house ,Boundary wall & allied works at 1st Tube well site for Thekuachak Zone-II Water Supply Scheme in Nandakumar Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 3724/TD | 04/12/2024 | 120 | GHOSH ENTERPRISE | 7.83 | 0 | 0 | 100
2112 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10121 | Augmentation | Continuation Work Order for Hire charges of Bharat Stage-IV Diesel Motor Cabs (Luxury Taxi)/Swift Desire/Ambassador Non AC) having Contract Carriage Permit from the Reginal Transport Authority valid for the State of West Bengal on monthly Hire rate basis for the period from 15/07/2023 to 14/07/2024 (12 months) to be used by the Assistant Engineer, Head Quarters, Tamluk Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxies, Insurance, Fees etc. as applicable Fuel :- a) Diesel - 12 Km./Ltr. b) Mobile Oil 500 Km./Ltr. | 1489/TD | 14/07/2023 | 366 | THREE MAA ENTERPRISE | 1.24 | 4.56 | 367.91 | 0
2113 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) PWSS (Zone - I) Water Supply Scheme under Tamluk Division, PHE Dte. | 1177/TD | 02/12/2021 | 20 | HORIZEN | 7.73 | 7.73 | 100 | 100
2114 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well at OHR Site of Mahisda Zone-I Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 479/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.39 | 15.97 | 100 | 100
2115 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Material Requisition To Resource Division | 640/TD | 27/06/2022 | 0 | Resource Division | 31.83 | 0 | 0 | 0
2116 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Material Requisition To Resource Division | 651/TD | 27/06/2022 | 0 | Resource Division | 22.79 | 0 | 0 | 0
2117 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Additional Electric Quotation for MAHISDA Water Supply Scheme, T/W- III, Zone- I (Ref. ID-860281848) | BP-2023-24-320 | 01/11/2023 | 0 | WBSEDCL | 4.8 | 0 | 0 | 0
2118 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Electric Quotiaton for Mahisda Water Supply Scheme zone-I, T/W-III (Ref. ID-204015583) | BP-2023-24-173 | 04/08/2023 | 0 | WBSEDCL | 8.05 | 0 | 0 | 0
2119 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Amount payment to PWD Road for damaged of carriage way and road flank caused due to laying of water pipe line of Mohisda Zone-I PWSS | BP-2023-24-566 | 07/11/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.6 | 0 | 0 | 0
2120 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Laying Distribution system of Left-out portion of pipe line and its allied works to accommodate FHTC at Mahisda Zone-I Water Supply Scheme in Sahid Matangini Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 513/TD | 11/05/2023 | 30 | TAPAS SANTRA | 58.58 | 55.7 | 95.08 | 90
2121 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Interconnection with laying of 150 mm dia DI(K-9) & 200 mm dia DI (K-9) rising main from 1st.,2nd. & 3rd. T/W to OHR at Mohisda Zone-I PWSS under Tamluk Sub-Division of Tamluk Division PHE Dte. | 1494/TD | 17/07/2023 | 20 | TAPAS SANTRA | 3.84 | 0 | 0 | 0
2122 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Hire charges of Bharat Stage-IV Diesel Motor Cabs (Luxury Taxi)/Swift Desire/Ambassador Non AC) having Contract Carriage Permit from the Reginal Transport Authority valid for the State of West Bengal on monthly Hire rate basis for the period from 15/07/2022 to 14/07/2023 (12 months) to be used by the Assistant Engineer, Head Quarters, Tamluk Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxies, Insurance, Fees etc. as applicable Fuel :- a) Diesel - 12 Km./Ltr. b) Mobile Oil 500 Km./Ltr. | 821/TD | 15/07/2022 | 365 | THREE MAA ENTERPRISE | 1.24 | 4.76 | 100 | 100
2123 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Repairing & renovation of construction of switch room cum Chlorine room at 1 st.T.W. Site and Construction of switch room cum Chlorine room with water supply & sanitary arrangement at 3 rd. Tube Well Site and Repairing & renovation of existing Boundary Wall at 1 st.T.W. site for Mohisda (Zone-I) Water Supply Scheme within Sahid Matangini Dev.Block under Tamluk Sub Division,PHE Dte | 3206/TD | 14/03/2023 | 30 | TAPAS SANTRA | 17.08 | 16.83 | 100 | 100
2124 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at OHR Site and Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at 2 nd Tube Well Site and Construction of Pump House at 3 rd Tube Well site &New construction of Boundary Wall at 3 rd.T.W. site for Mohisda (Zone-I) Water Supply Scheme within Sahid Matangini Dev.Block under Tamluk Sub Division,PHE Dte | 3207/TD | 14/03/2023 | 30 | TAPAS SANTRA | 19.48 | 19.29 | 100 | 100
2125 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 850/W/MMD | 24/03/2023 | 180 | MUKHERJEE ART CENTRE | 12.37 | 11.32 | 92.81 | 65
2126 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Material Requisition To Resource Division | 1113/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
2127 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Net-Metering Solar Power Plant quotation at Mohisda water supply scheme Zone-I, Tube Well-I Matangini CCC Block-Sahid Matangini Application No.-2004795833 Consumer ID.-222091158 Quotation Date.-26/06/2024 | BP-2024-25-446 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2128 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Quotation Bill for Net Billing Mahisda Zone-I,T/W-I Matangini CCC Application No=2004795833 Consumer ID=222091158 | BP-2024-25-773 | 28/10/2024 | 0 | WBSEDCL | 0.22 | 0 | 0 | 0
2129 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 700 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mohisda Zone-I & its adjoining mouzas Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(Part-A) | 337/TD | 12/05/2022 | 1054 | TAPAS SANTRA | 417.56 | 274.52 | 65.74 | 70
2130 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. , SM/10031 | Augmentation | Laying of distribution pipe line to accommodate FHTC for Augmentation of Mohisda Zone-I & its adjoining mouzas Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(Part-B) | 338/TD | 12/05/2022 | 1080 | TAPAS SANTRA | 331.77 | 315.84 | 95.2 | 95
2131 | PURBA MEDINIPUR | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | SEALING OF SALINE ZONEAT SITE FOR CONSTRUCTION OF TUBE WELL AT RANGIBASAN W/S SCHEME (TW-III), MAHISHADAL BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 454/CMSD-I | 01/09/2022 | 7 | MENAKA ENTERPRISE | 0.47 | 0 | 0 | 100
2132 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme under Tamluk Division, PHE Dte. | 1180/TD | 02/12/2021 | 20 | HORIZEN | 5.56 | 5.56 | 100 | 100
2133 | PURBA MEDINIPUR | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 280 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR RANGIBASAN W/S SCHEME (TW-III), MAHISBADAL BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 109/CDD | 12/04/2022 | 30 | MENAKA ENTERPRISE | 18.7 | 17.85 | 100 | 100
2134 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Work Order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2022 to 31/12/2022. (12 Months) | 476/HSD, | 27/12/2021 | 365 | SANTANU PATTANAYAK | 1.5 | 1.91 | 100 | 100
2135 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Rangibasan Water Supply Scheme under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (PART-B) | 1053/TD | 07/06/2023 | 20 | MA SARADA ENTERPRISE | 0.73 | 0.73 | 100 | 100
2136 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Rangibasan Water Supply Scheme under Haldia Sub-Division of Tamluk Division in Purba Medinipur District (PART-A) | 1052/TD | 07/06/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 5.9 | 5.9 | 100 | 100
2137 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Material Requisition To Resource Division | 1258/TD | 13/12/2021 | 0 | Resource Division | 11.32 | 0 | 0 | 0
2138 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Material Requisition To Resource Division | 1867/TD | 17/02/2022 | 0 | Resource Division | 19.09 | 0 | 0 | 0
2139 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Electric Quotation Bill for Rangibasan PWSS | BP-2022-23-637 | 20/01/2023 | 0 | WBSEDCL | 0.59 | 0 | 0 | 0
2140 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Restoration work of the damaged flank portions caused for laying pipe line by PHE Dte.on Mahishadal-Geonkhali road from Ch.0.20 km to 1.10 km under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 | BP-2023-24-120 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.98 | 0 | 0 | 0
2141 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well site of Rangibasan Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1496/TD | 17/07/2023 | 45 | PULAK KUMAR SAMANTA | 4.81 | 4.6 | 100 | 60
2142 | PURBA MEDINIPUR | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 240 Mtrs. Depth) by utilising Departmental Machineries for Solat/Rangibasan W/S Scheme (T/W-II) , under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 858/CDD | 10/07/2023 | 386 | PADMA ENGINEERING & CO. | 18.74 | 17.81 | 100 | 100
2143 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Sinking of 300 mm x 200 mm dia x 280 mtr. deep tube well by direct rotary rig method at 3rd Tubewell site of Rangibasan Water Supply Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 51/TD | 04/01/2024 | 45 | AQUATECH ENGINEER | 20.68 | 19.69 | 100 | 100
2144 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Augmentation of ground water based Rangibasan Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1814/TD | 11/02/2022 | 1265 | DAS CONSTRUCTION | 481.17 | 376.05 | 78.15 | 65
2145 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Laying of supply & delivery of different dia D.I specials for Rising main line and inter connection at Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1493/TD | 17/07/2023 | 895 | S.D. CONSTRUCTION | 7.32 | 1.95 | 26.6 | 10
2146 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Repairing & Renovation of Switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube Well site of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2620/TD | 11/10/2023 | 30 | PULAK KUMAR SAMANTA | 5.98 | 0 | 0 | 3
2147 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Renovation of Boundary Wall and land development at Head Work Site of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Length - 212.00 Mtr.) | 2693/TD | 22/08/2024 | 360 | BHOWMIK & SONS | 21.73 | 0 | 0 | 30
2148 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. , SM/09283 | Augmentation | Laying Distribution System of Leftout portion, Providing Functional Household Tap Connection (FHTC) of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2013/TD | 14/06/2024 | 283 | A. R. CONSTRUCTION | 56.76 | 0 | 0 | 20
2149 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10591 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) under JJM Program under MMD PHE Dte. | 860/W/MMD | 27/03/2023 | 180 | SUBHASIS ROY | 23.7 | 0 | 0 | 0
2150 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10591 | Augmentation | Material Requisition To Resource Division | 1194/TD | 06/09/2022 | 0 | Resource Division | 108.25 | 0 | 0 | 0
2151 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10591 | Augmentation | Construction of Temporary 25(twenty five) nos. Latrine & Urinal for Krishnanagar Matrisakti Aradhana Mela at Krishnanagar within Khejuri-I Block in the year 2023, under Contai sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PART-B) Date of Mela :- 20.03.2023 to 23.03.2023,(4 days) | 395/CSD | 16/03/2023 | 3 | M/S. NEW DINDA ENTERPRISE | 0.62 | 0 | 0 | 100
2152 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10591 | Augmentation | Temporary water supply arrangement through pipe line & PVC tank connection from distribution pipe line of Mukutshila Zone-I W/S Scheme for Krishnanagar Matrisakti Aradhana Mela at Krishnanagar within Khejuri-I Block in the year 2023, under Contai sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PART-A), Date of Mela :- 20.03.2023 to 23.03.2023, (4 days) | 394/CSD | 16/03/2023 | 3 | M/S. NEW DINDA ENTERPRISE | 0.7 | 0.51 | 100 | 100
2153 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10591 | Augmentation | Construction of 3.60 mtr x 3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary and water supply arrangements including Plinth Protection at 3rd TW site for Mukutshila Zone-I water supply scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) | 2968/TD | 28/11/2023 | 60 | ABHIJIT BERA | 3.72 | 3.37 | 100 | 100
2154 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10591 | Augmentation | Way Leave permission from South Eastern Railway for Mukutshilla Zone-I PWSS for Application ID-SER-KGP-2023-WL-57 | BP-2023-24-824 | 22/01/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.27 | 0 | 0 | 0
2155 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10591 | Augmentation | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-103) | BP-2024-25-301 | 30/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.75 | 0 | 0 | 0
2156 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10591 | Augmentation | payment Wayleave plan & survey charges SER-KGP-2024-WL-103 | BP-2024-25-189 | 14/06/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.1 | 0 | 0 | 0
2157 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10591 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with Construction of R.C.C. Elevated Reservoir of Capacity 600 Cum and Staging Height of 20.0 Mtr. as per departmental drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-I Water Supply Scheme within Khejuri-I Dev. Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1575/TD | 14/10/2022 | 868 | GEE BEE NIRMAN CO PVT LTD. | 796.53 | 125.16 | 76.85 | 50
2158 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10591 | Augmentation | Rising main and other allied works Augmentation of Mukutshila Zone-I Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2190/TD | 01/09/2023 | 720 | GRAND CONSTRUCTION | 11.85 | 0 | 0 | 0
2159 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10591 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Mukutshila Zone-I PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division,PHE Dte. Purba Medinipur. (Length-60.00 mtr.) | 2277/TD | 07/09/2023 | 796 | SAMIT KUMAR MONDAL | 8.63 | 0 | 0 | 100
2160 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10591 | Augmentation | Laying of Left-Out portion HDPE Pipe line of Distribution pipe line by HDPE pipes with allied works of Mukutshila Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 113/TD | 09/01/2025 | 25 | GEE BEE NIRMAN CO PVT LTD. | 36.64 | 0 | 0 | 0
2161 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chirulia Piped Water Supply Scheme , SM/07101 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chirulia PWSS Block Egra-II in the District of Purba Medinipur. | 2768/TD | 28/01/2021 | 60 | FIROZ KHAN | 56.35 | 6.8 | 100 | 100
2162 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chirulia Piped Water Supply Scheme , SM/07101 | Retrofitting | Retrofitting to accomodate FHTC under JJM Chirulia W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. | 62/W | 08/06/2021 | 0 | FIROZ KHAN | 24.5 | 0 | 0 | 0
2163 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chirulia Piped Water Supply Scheme , SM/07101 | Retrofitting | Retrofitting to accomodate FHTC under JJM Chirulia W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. | 977/W | 25/03/2021 | 0 | FIROZ KHAN | 21.3 | 0 | 0 | 0
2164 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I,Potashpur-I & Potashpur-II Development Block under Purba Medinipur District. , SM/10585 | New | Material Requisition To Resource Division | 2892/TD | 21/11/2023 | 0 | Resource Division | 19.46 | 0 | 0 | 0
2165 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I,Potashpur-I & Potashpur-II Development Block under Purba Medinipur District. , SM/10585 | New | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0 | 0
2166 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I,Potashpur-I & Potashpur-II Development Block under Purba Medinipur District. , SM/10585 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 708.05 | 87.23 | 70
2167 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I,Potashpur-I & Potashpur-II Development Block under Purba Medinipur District. , SM/10585 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 102.85 | 63.35 | 48
2168 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme , SM/07095 | Retrofitting | Functional Household Tap Connection to the 225 nos. Household of Pratapdighi W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-C [(Jagati(244 ) part,] | 2721/TD | 21/01/2021 | 20 | M/S. NEW DINDA ENTERPRISE | 10.43 | 0 | 0 | 100
2169 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme , SM/07095 | Retrofitting | Functional Household Tap Connection to the 225 nos. Household of Pratapdighi W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-B [(Jagati(244 ) part,] | 2722/TD | 21/01/2021 | 20 | GIRI ENTERPRISE | 10.43 | 0 | 0 | 100
2170 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme , SM/07095 | Retrofitting | Functional Household Tap Connection to the 1400 nos. Household of Pratapdighi W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-A [Pratap Dighi (245), Mangalpur (249)] | 2809/TD | 04/02/2021 | 50 | GIRI CONSTRUCTION | 64.82 | 0 | 0 | 100
2171 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme , SM/07095 | Retrofitting | Retrofitting to accomodate FHTC 1400 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. | 972/W | 25/03/2021 | 0 | GIRI CONSTRUCTION | 21.89 | 0 | 0 | 0
2172 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme , SM/07095 | Retrofitting | Retrofitting to accomodate FHTC 1400 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. | 159/W | 02/08/2021 | 0 | GIRI CONSTRUCTION | 13.24 | 0 | 0 | 0
2173 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme , SM/07095 | Retrofitting | Retrofitting to accomodate FHTC 225 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. | 315/W | 08/10/2021 | 0 | GIRI ENTERPRISE | 0.38 | 0 | 0 | 0
2174 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme , SM/07095 | Retrofitting | Retrofitting to accomodate for 225 Nos. FHTC connection under JJM in Pratapdighi W/S Scheme within Potashpur - II Dev. Block Block under Tamluk Division, PHE Dte. (Part-C) | 225/W | 01/09/2021 | 0 | M/S. NEW DINDA ENTERPRISE | 0.63 | 0 | 0 | 0
2175 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme , SM/07095 | Retrofitting | Retrofitting to accomodate FHTC 225 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. | 980/W | 23/03/2021 | 0 | GIRI ENTERPRISE | 9.77 | 0 | 0 | 0
2176 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme , SM/07095 | Retrofitting | Retrofitting to accomodate for 225 Nos. FHTC connection under JJM in Pratapdighi W/S Scheme within Potashpur - II Dev. Block Block under Tamluk Division, PHE Dte. (Part-C) | 815/W | 24/02/2021 | 0 | M/S. NEW DINDA ENTERPRISE | 9.64 | 0 | 0 | 0
2177 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme , SM/07095 | Retrofitting | Renovation of existing pump house at head works & 2nd tube well site of Pratapdighi W/S Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 409 / CSD | 12/07/2022 | 30 | GIRI CONSTRUCTION | 1.36 | 1.35 | 100 | 100
2178 | PURBA MEDINIPUR | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Material Requisition To Resource Division | 2986/TD | 27/02/2023 | 0 | Resource Division | 15.66 | 0 | 0 | 0
2179 | PURBA MEDINIPUR | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Payment of WBSEDCL for Quotation of Shifting of 11 KV HTOH Line under Tamluk Division, PHE Dte. | BP-2023-24-665 | 15/12/2023 | 0 | WBSEDCL | 5.18 | 0 | 0 | 0
2180 | PURBA MEDINIPUR | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | 277/TD | 20/04/2023 | 25 | TARUN KHATUA | 19.88 | 14.27 | 71.77 | 60
2181 | PURBA MEDINIPUR | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (240 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-G+H+I) | 278/TD | 20/04/2023 | 45 | BHOLANATH DEY | 90.98 | 76.65 | 84.25 | 76
2182 | PURBA MEDINIPUR | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-J+K) | 279/TD | 20/04/2023 | 30 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.8 | 25.84 | 76.47 | 80
2183 | PURBA MEDINIPUR | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (480 nos.) work and Construction of R.C.C. Over Head Reservoir of capacity 150 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | 1097/TD | 08/06/2023 | 180 | SUSIL KUMAR HAZRA | 104.34 | 38.53 | 36.93 | 10
2184 | PURBA MEDINIPUR | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Canal Crossing Structure for Laying Distribution (Nodal Point -161-163, 378-382, R1 - 1, 12-16) Pipe line of Bamanpur Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. | 2615/TD | 11/10/2023 | 30 | TARUN KHATUA | 8.77 | 6.05 | 100 | 100
2185 | PURBA MEDINIPUR | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Material Requisition To Resource Division | 81/TD | 05/01/2024 | 0 | Resource Division | 8.39 | 0 | 0 | 0
2186 | PURBA MEDINIPUR | Midnapore Mechanical | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Quotation for new connection at Bamanpur w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. ( App No 2004732591, Ref ID 204305895) | BP-2024-25-376 | 08/07/2024 | 0 | WBSEDCL | 10.38 | 0 | 0 | 0
2187 | PURBA MEDINIPUR | Midnapore Mechanical | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAMANPUR and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 504/W/MMD | 20/03/2023 | 895 | SUJOY RANJAN BHOWMICK | 21.62 | 10.07 | 46.56 | 50
2188 | PURBA MEDINIPUR | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Ground water based Bamanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (425 nos.)work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-D+E+F) | 2678/TD | 16/10/2023 | 649 | SK. SARFARAJ | 93.13 | 35.37 | 37.98 | 10
2189 | PURBA MEDINIPUR | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Land development of Head work site at Bamanpur Water Supply Scheme within Mahishadal Development Block under Haldia Sub-Division, PEH Dte. | 638/HSD, | 12/06/2025 | 10 | M/S SOURAV MAHAPATRA | 2.27 | 0 | 0 | 0
2190 | PURBA MEDINIPUR | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS , SM/12493 | New | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 3348/TD | 22/03/2023 | 638 | M/S SYCHROTECH INDUSTRY | 62.36 | 0 | 0 | 100
2191 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Moyna Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | 1470/TD | 03/01/2022 | 20 | APEX ENGINEERING | 4.08 | 3.93 | 100 | 100
2192 | PURBA MEDINIPUR | Central Drilling | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Providing Drilling crew and other allied works for construction of Tube Well (300mm x 200mmx 230 Mtrs. Depth) by utilising Departmental Mechineries for Moyna W/S Scheme (Z-I,T/W-I)block under Purba Medinipur District CDD PHE Dte. | 537/CDD | 02/06/2023 | 30 | MENAKA ENTERPRISE | 17.76 | 16.24 | 100 | 100
2193 | PURBA MEDINIPUR | Central Drilling | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 230 Mtrs. Depth) by utilising Departmental machineries for Moyna W/S Scheme (Z-I, T/W-I), Moyna Block under Purba Medinipur District , Central Drilling Division PHE Dte. | 538/CDD | 02/06/2023 | 30 | MENAKA ENTERPRISE | 17.76 | 16.24 | 100 | 100
2194 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Material Requisition To Resource Division | 1209/TD | 06/09/2022 | 0 | Resource Division | 131.09 | 0 | 0 | 0
2195 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Material Requisition To Resource Division | 1205/TD | 06/09/2022 | 0 | Resource Division | 7.03 | 0 | 0 | 0
2196 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Material Requisition To Resource Division | 1922/TD | 14/08/2023 | 0 | Resource Division | 9.63 | 0 | 0 | 0
2197 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Payment of WBSEDCL for Quotation of Shifting of 11 KV HTOH line at Moyna Zone-I Water Supply Scheme | BP-2023-24-663 | 15/12/2023 | 0 | WBSEDCL | 3.97 | 0 | 0 | 0
2198 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Continuation work order for Hiring of one no Diesel Motor cabs (Luxury Taxi) (Standard non air conditioned) Bharat stage-IV, (Vehicle No. WB-29B-2278) on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division, PHE Dte under Tamluk Division for the period from 01.01.2024 to 31.03.2024. | 1756/TSD | 29/12/2023 | 50 | DEBNATH MAITY | 0.24 | 1.11 | 466.61 | 100
2199 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Laying of left out pipe line by 90 mm OD UPVC pipes with allied works of Moyna Zone-I & its adjoining mouzas Water Supply Scheme within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(PART-A) | 1902/TD | 07/06/2024 | 25 | GHOSH ENTERPRISE | 70.24 | 0 | 0 | 0
2200 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th. T/W Site. of Moyna Zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 2211/TD | 01/09/2023 | 40 | PRASANTA MONDAL | 5.1 | 4.9 | 100 | 10
2201 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Moyna Zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 2212/TD | 01/09/2023 | 40 | PRASANTA MONDAL | 5.1 | 5.01 | 100 | 70
2202 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Material Requisition To Resource Division | 1099/TD | 19/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
2203 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Electric Quotation for MOYNA Water Supply Scheme T/W-IV, Zone-I, (Ref. ID-204136064) | BP-2023-24-437 | 18/12/2023 | 0 | WBSEDCL | 4.91 | 0 | 0 | 0
2204 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Electric Quotation for MOYNA Water Supply Scheme T/W-III, Zone-I, (Ref. ID-204143546) | BP-2023-24-408 | 09/12/2023 | 0 | WBSEDCL | 4.7 | 0 | 0 | 0
2205 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Laying of distribution pipe line to accommodate FHTC (4679 nos) with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Moyna Zone-I Water Supply Scheme within Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1652/TD | 02/11/2022 | 903 | ARABINDA GHOSH | 612.74 | 336.18 | 54.86 | 85
2206 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Laying of 300/250/200/150 mm dia DI (K9) rising main in between OHR to T/W-I, T/W-2, T/W-3 and T/W-4 including canel crossing and dram Sheet Walling and DI specials of Moyna Zone-I PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. | 2618/TD | 11/10/2023 | 420 | KRISHNENDU SEKHAR DAS | 24.68 | 3.4 | 13.79 | 100
2207 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Repairing & Renovation of Construction of Pump house ,Boundary wall & allied works at 1st Tube well 2nd tube well site of Moyna Zone-I Water Supply Scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 3547/TD | 18/11/2024 | 30 | SANDIP MAITI | 3.06 | 0 | 0 | 0
2208 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division ,PHE Dte. Under Tamluk Division for the period from 12 (Twelve) Months. | 1468/TSD | 31/10/2023 | 239 | TAPAS SANTRA | 1.14 | 3.97 | 350.14 | 0
2209 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Moyna (Zone-I) PWSS , SM/11614 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Augmentation of Moyna (Zone-I) PWSS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 645/W/MMD | 20/03/2023 | 529 | SOUMEN ELECTRIC | 27.17 | 26.82 | 100 | 60
2210 | PURBA MEDINIPUR | Tamluk Division | KSHETRAPAL AND IT'S ADJOINING MOUJAS , SM/12513 | New | Material Requisition To Resource Division | 2456/TD | 16/01/2023 | 0 | Resource Division | 19.2 | 0 | 0 | 0
2211 | PURBA MEDINIPUR | Midnapore Mechanical | KSHETRAPAL AND IT'S ADJOINING MOUJAS , SM/12513 | New | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 0 | 50
2212 | PURBA MEDINIPUR | Tamluk Division | KSHETRAPAL AND IT'S ADJOINING MOUJAS , SM/12513 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kshetrapal PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | 2070/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
2213 | PURBA MEDINIPUR | Tamluk Division | KSHETRAPAL AND IT'S ADJOINING MOUJAS , SM/12513 | New | Material Requisition To Resource Division | 1657/TD | 29/04/2024 | 0 | Resource Division | 11.58 | 0 | 0 | 0
2214 | PURBA MEDINIPUR | Midnapore Mechanical | KSHETRAPAL AND IT'S ADJOINING MOUJAS , SM/12513 | New | Quotation Bill for New Service connection at T/W NO-I Of KSHETRAPAL W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004685984/QUOT/03 DT. 16-04-2024 Application NO- 2004685984 Application type-New connection Consumer Id- 204277213 | BP-2024-25-103 | 26/04/2024 | 0 | WBSEDCL | 3.53 | 0 | 0 | 0
2215 | PURBA MEDINIPUR | Midnapore Mechanical | KSHETRAPAL AND IT'S ADJOINING MOUJAS , SM/12513 | New | Quotation Bill for New Service connection at T/W NO-II Of KSHETRAPAL W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004686002/QUOT/03 DT. 16-04-2024 Application NO- 2004686002 Application type-New connection Consumer Id- 204277214 | BP-2024-25-104 | 26/04/2024 | 0 | WBSEDCL | 5.44 | 0 | 0 | 0
2216 | PURBA MEDINIPUR | Midnapore Mechanical | KSHETRAPAL AND IT'S ADJOINING MOUJAS , SM/12513 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KSHETRAPAL and ADJOINING MOUJAS, Block - Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 517/W/MMD | 20/03/2023 | 804 | KARUNAMOY ENGINEERING | 22.75 | 0 | 0 | 70
2217 | PURBA MEDINIPUR | Tamluk Division | KSHETRAPAL AND IT'S ADJOINING MOUJAS , SM/12513 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 255.57 | 43.18 | 51
2218 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Uttar Charikhia PWSS under Contai I Block (Phase-II). , SM/09047 | Retrofitting | Retrofitting to accommodate FHTC [180 nos.] under JJM in Uttar Charaikhia PWSS Block - Contai-I in the District of Purba Medinipur. Mouza- Saheb Khankeranibar(101),Kanchra Gerya(122),Dakshin Charai Khia(124),Uttar Charai Khia(125) (Phase-II) | 1007/TD | 02/11/2021 | 20 | M/S SREE DURGA ENTERPRISE | 17.26 | 17.26 | 100 | 100
2219 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme under Tamluk Division, PHE Dte. | 1165/TD | 01/12/2021 | 7 | HORIZEN | 5.74 | 5.61 | 100 | 100
2220 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Supply & delivery of different dia CIDF Sluice valve for Rajarampur Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-A) | 514/TD | 07/06/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.81 | 4.81 | 100 | 100
2221 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Supply & delivery of different dia CIDF Sluice valve for Rajarampur Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-B) | 515/TD | 07/06/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.7 | 3.7 | 100 | 100
2222 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Kapaseria W/S Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head work Site of Rajarampur W/S Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Tabakhali W/S Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 976/TD | 03/08/2022 | 21 | SIMPLEX DRILLING COMPANY | 58.06 | 19.28 | 100 | 100
2223 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Work Order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2022 to 31/12/2022. (12 Months) | 476/HSD | 27/12/2021 | 365 | SUSANTA PATTANAYAK | 1.5 | 0 | 0 | 100
2224 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Rajarampur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1069/TD | 22/08/2022 | 45 | TAPAN BERA | 3.96 | 3.93 | 100 | 100
2225 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Material Requisition To Resource Division | 1253/TD | 13/12/2021 | 0 | Resource Division | 40.29 | 0 | 0 | 0
2226 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Material Requisition To Resource Division | 465/W | 02/06/2022 | 0 | Resource Division | 55.01 | 0 | 0 | 0
2227 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Material Requisition To Resource Division | 2344/TD | 31/03/2022 | 0 | Resource Division | 16.03 | 0 | 0 | 0
2228 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Restoration work of the damaged flank portions caused for laying pipe line by PHE Dte.on Rautari to Terapara Jalpai road from Ch.8.5 KM to 9.85 KM under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 | BP-2023-24-122 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 5.76 | 0 | 0 | 0
2229 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Crossing permission of laying HDPE pipeline along and across of NH-116 of Rajarampur Water Supply Scheme under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3289/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 8.69 | 1.22 | 14.04 | 25
2230 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Augmentation of ground water based Rajarampur Water Supply Scheme by Providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 400 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.. | 2021/TD | 08/03/2022 | 1334 | SANKHA ENTERPRISE | 549.46 | 437.5 | 79.62 | 90
2231 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. , SM/09281 | Augmentation | Laying Rising main, laying left out pipe line and supporting work with Drum Sheet walling and Earth filling in Rajarampur Water Supply Scheme within Mahishadal Block under Haldia Sub-Division of Tamluk Division PHE Dte. | 2167/TD | 19/12/2022 | 960 | SANKHA ENTERPRISE | 78.54 | 23.06 | 29.37 | 35
2232 | PURBA MEDINIPUR | Midnapore Mechanical | GOBINDAPUR & ADJOINING MOUZAS , SM/12149 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well no - IV at GOBINDAPUR Zone-II Water supply scheme,Block : Shahid Matangini, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 2612/W/MMD | 19/09/2023 | 180 | PURUSHOTTAM ENTERPRISE | 13.17 | 0 | 0 | 0
2233 | PURBA MEDINIPUR | Tamluk Division | GOBINDAPUR & ADJOINING MOUZAS , SM/12149 | New | Material Requisition To Resource Division | 2682/TD | 06/02/2023 | 0 | Resource Division | 14.87 | 0 | 0 | 0
2234 | PURBA MEDINIPUR | Midnapore Mechanical | GOBINDAPUR & ADJOINING MOUZAS , SM/12149 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOBINDAPUR and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipurunder JJM Program under MMD PHE Dte. | 454/W/MMD | 20/03/2023 | 540 | S.S.ENTERPRISES | 21.62 | 0 | 0 | 20
2235 | PURBA MEDINIPUR | Tamluk Division | GOBINDAPUR & ADJOINING MOUZAS , SM/12149 | New | Material Requisition To Resource Division | 104/TD | 05/01/2024 | 0 | Resource Division | 5.61 | 0 | 0 | 0
2236 | PURBA MEDINIPUR | Tamluk Division | HARINAN PWSS & ADJOINING MOUJAS , SM/12152 | New | Material Requisition To Resource Division | 2465/TD | 16/01/2023 | 0 | Resource Division | 18.6 | 0 | 0 | 0
2237 | PURBA MEDINIPUR | Midnapore Mechanical | HARINAN PWSS & ADJOINING MOUJAS , SM/12152 | New | Electric Quotation for HARINAN Water Supply Scheme , (Ref. ID-204069690) | W/23-24/224 | 01/09/2023 | 0 | WBSEDCL | 3.04 | 0 | 0 | 0
2238 | PURBA MEDINIPUR | Midnapore Mechanical | HARINAN PWSS & ADJOINING MOUJAS , SM/12152 | New | Electric Quotation for HARINAN, Water Supply Scheme T/W-II , (Ref. ID-204069696) | W/23-24/225 | 01/09/2023 | 0 | WBSEDCL | 3.25 | 0 | 0 | 0
2239 | PURBA MEDINIPUR | Tamluk Division | HARINAN PWSS & ADJOINING MOUJAS , SM/12152 | New | Laying Distribution system of pipe line and its allied works for Harinan water supply scheme in Sahid Matangini Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 2736/TD | 01/11/2023 | 792 | TAPAS SANTRA | 85.07 | 76.45 | 89.86 | 75
2240 | PURBA MEDINIPUR | Midnapore Mechanical | HARINAN PWSS & ADJOINING MOUJAS , SM/12152 | New | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 60.44 | 100
2241 | PURBA MEDINIPUR | Midnapore Mechanical | HARINAN PWSS & ADJOINING MOUJAS , SM/12152 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARINAN PWSS and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2338/W/MMD | 29/12/2022 | 180 | DEY ENTERPRISE | 23.7 | 22.63 | 95.06 | 85
2242 | PURBA MEDINIPUR | Tamluk Division | HARINAN PWSS & ADJOINING MOUJAS , SM/12152 | New | Material Requisition To Resource Division | 90/TD | 05/01/2024 | 0 | Resource Division | 12.69 | 0 | 0 | 0
2243 | PURBA MEDINIPUR | Midnapore Mechanical | HARINAN PWSS & ADJOINING MOUJAS , SM/12152 | New | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 0 | 100
2244 | PURBA MEDINIPUR | Tamluk Division | BARDA AND ADJOINING MOUJAS PWSS , SM/12306 | New | Material Requisition To Resource Division | 2419/TD | 16/01/2023 | 0 | Resource Division | 27.14 | 0 | 0 | 0
2245 | PURBA MEDINIPUR | Midnapore Mechanical | BARDA AND ADJOINING MOUJAS PWSS , SM/12306 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARDA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2413/W/MMD | 31/12/2022 | 180 | ECO ENTERPRISE | 22.8 | 9.45 | 41.47 | 35
2246 | PURBA MEDINIPUR | Tamluk Division | BARDA AND ADJOINING MOUJAS PWSS , SM/12306 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Barda PWSS at Egra-I Block under Tamluk Division, PHE Dte. | 2082/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
2247 | PURBA MEDINIPUR | Tamluk Division | BARDA AND ADJOINING MOUJAS PWSS , SM/12306 | New | Quotation for new service connection at T/W-I of Barada under MMD,PHE DTE, Block-Egra-I, Chorpalia CCC Application no-2004811995 CON ID-204352240 | BP-2024-25-312 | 02/08/2024 | 0 | WBSEDCL | 20.24 | 0 | 0 | 0
2248 | PURBA MEDINIPUR | Midnapore Mechanical | BARDA AND ADJOINING MOUJAS PWSS , SM/12306 | New | Quotation Bill for New Service connection at T/W NO-II Of BARADA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004847092/QUOT/03/1184 DT. 13-08-2024 Application NO- 2004847092 Application type-New connection Consumer Id- 204372857 | C082448216760 | 02/09/2024 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
2249 | PURBA MEDINIPUR | Tamluk Division | BARDA AND ADJOINING MOUJAS PWSS , SM/12306 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 93.47 | 21.03 | 51
2250 | PURBA MEDINIPUR | Tamluk Division | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. , SM/12307 | New | Material Requisition To Resource Division | 2462/TD | 16/01/2023 | 0 | Resource Division | 17.76 | 0 | 0 | 0
2251 | PURBA MEDINIPUR | Tamluk Division | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. , SM/12307 | New | Material Requisition To Resource Division | 1651/TD | 29/04/2024 | 0 | Resource Division | 7.38 | 0 | 0 | 0
2252 | PURBA MEDINIPUR | Midnapore Mechanical | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. , SM/12307 | New | Quotation Bill for New Service connection at T/W NO-I Of KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-2004781161/QUOT/03 DT. 19-06-2024 Application NO- 2004781161 Application type-New connection Consumer Id- 204333913 | BP-2024-25-358 | 01/07/2024 | 0 | WBSEDCL | 3.42 | 0 | 0 | 0
2253 | PURBA MEDINIPUR | Midnapore Mechanical | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. , SM/12307 | New | Quotation Bill for New Service connection at T/W NO-II Of KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATSHPUR C.C.C. Ref. Memo No-2004886291/QUOT/03/582 DT. 06-09-2024 Application NO- 2004886291 Application type-New connection Consumer Id- 204391659 | C092443181197 | 27/09/2024 | 0 | WBSEDCL | 3.46 | 0 | 0 | 0
2254 | PURBA MEDINIPUR | Midnapore Mechanical | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. , SM/12307 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KALYANPUR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2359/W/MMD | 31/12/2022 | 912 | WEST BENGAL ENGINEERING CO. | 22.78 | 0 | 0 | 80
2255 | PURBA MEDINIPUR | Tamluk Division | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. , SM/12307 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 2703/TD | 20/10/2023 | 620 | S & P ENTERPRISE | 1928.99 | 23.24 | 5.48 | 30
2256 | PURBA MEDINIPUR | Tamluk Division | BASANTA CHAK AND ADJOINING MOUJAS PWSS , SM/12144 | New | Material Requisition To Resource Division | 2431/TD | 16/01/2023 | 0 | Resource Division | 21.73 | 0 | 0 | 0
2257 | PURBA MEDINIPUR | Midnapore Mechanical | BASANTA CHAK AND ADJOINING MOUJAS PWSS , SM/12144 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BASANTA CHAK and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2335/W/MMD | 29/12/2022 | 180 | ORIENTAL ENGINEERING CO. | 23.68 | 21.94 | 92.67 | 80
2258 | PURBA MEDINIPUR | Tamluk Division | BASANTA CHAK AND ADJOINING MOUJAS PWSS , SM/12144 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Basanta Chak PWSS at Moyna Block under Tamluk Division,PHE Dte. | 199/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
2259 | PURBA MEDINIPUR | Tamluk Division | BASANTA CHAK AND ADJOINING MOUJAS PWSS , SM/12144 | New | Material Requisition To Resource Division | 1560/TD | 23/04/2024 | 0 | Resource Division | 12.76 | 0 | 0 | 0
2260 | PURBA MEDINIPUR | Midnapore Mechanical | BASANTA CHAK AND ADJOINING MOUJAS PWSS , SM/12144 | New | Quotation for new service connection at Basantachak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. ( App No 2004756260, Ref ID 204319518) | BP-2024-25-492 | 29/07/2024 | 0 | WBSEDCL | 5.19 | 0 | 0 | 0
2261 | PURBA MEDINIPUR | Midnapore Mechanical | BASANTA CHAK AND ADJOINING MOUJAS PWSS , SM/12144 | New | Quotation for Basantachak w/s scheme PH-II in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608977, Ref ID-204222619) | BP-2023-24-853 | 16/03/2024 | 0 | WBSEDCL | 2.96 | 0 | 0 | 0
2262 | PURBA MEDINIPUR | Tamluk Division | RADHABALLAV CHAK & ADJOINING MOUZAS , SM/12156 | New | Material Requisition To Resource Division | 2428/TD | 16/01/2023 | 0 | Resource Division | 32.13 | 0 | 0 | 0
2263 | PURBA MEDINIPUR | Tamluk Division | RADHABALLAV CHAK & ADJOINING MOUZAS , SM/12156 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Radhaballabh Chak PWSS at Moyna Block under Tamluk Division,PHE Dte. | 197/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
2264 | PURBA MEDINIPUR | Tamluk Division | RADHABALLAV CHAK & ADJOINING MOUZAS , SM/12156 | New | Material Requisition To Resource Division | 1569/TD | 23/04/2024 | 0 | Resource Division | 12.48 | 0 | 0 | 0
2265 | PURBA MEDINIPUR | Midnapore Mechanical | RADHABALLAV CHAK & ADJOINING MOUZAS , SM/12156 | New | Quotation for new service connection at Radhaballavchak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No.2004631928, Ref ID 204238450) | BP-2023-24-908 | 28/03/2024 | 0 | WBSEDCL | 11.33 | 0 | 0 | 0
2266 | PURBA MEDINIPUR | Midnapore Mechanical | RADHABALLAV CHAK & ADJOINING MOUZAS , SM/12156 | New | Quotation for new service connection at Radhaballavchak w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.2004631522, Ref ID 204237226) | BP-2023-24-907 | 28/03/2024 | 0 | WBSEDCL | 7.1 | 0 | 0 | 0
2267 | PURBA MEDINIPUR | Midnapore Mechanical | RADHABALLAV CHAK & ADJOINING MOUZAS , SM/12156 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RADHABALLAV CHAK and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2340/W/MMD | 29/12/2022 | 914 | S.G.TECHNICAL SERVICE | 23.58 | 0 | 0 | 80
2268 | PURBA MEDINIPUR | Tamluk Division | TELAMI AND ADJOINING MOUJAS PWSS , SM/12288 | New | Material Requisition To Resource Division | 2409/TD | 16/01/2023 | 0 | Resource Division | 35.73 | 0 | 0 | 0
2269 | PURBA MEDINIPUR | Midnapore Mechanical | TELAMI AND ADJOINING MOUJAS PWSS , SM/12288 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TELAMI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2355/W/MMD | 31/12/2022 | 180 | SOUMEN ELECTRIC | 21.56 | 15.29 | 70.89 | 70
2270 | PURBA MEDINIPUR | Tamluk Division | TELAMI AND ADJOINING MOUJAS PWSS , SM/12288 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Telami PWSS at Egra-I Block under Tamluk Division, PHE Dte. | 2073/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
2271 | PURBA MEDINIPUR | Midnapore Mechanical | TELAMI AND ADJOINING MOUJAS PWSS , SM/12288 | New | Quotation Bill for New Service connection at T/W NO-II Of TELAMI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674624/QUOT/03 DT. 09-04-2024 Application NO- 2004674624 Application type-New connection Consumer Id- 204269445 | BP-2024-25-88 | 24/04/2024 | 0 | WBSEDCL | 7.55 | 0 | 0 | 0
2272 | PURBA MEDINIPUR | Midnapore Mechanical | TELAMI AND ADJOINING MOUJAS PWSS , SM/12288 | New | Quotation Bill for New Service connection at T/W NO-I Of TELAMI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674680/QUOT/03 DT. 09-04-2024 Application NO- 2004674680 Application type-New connection Consumer Id- 204269489 | BP-2024-25-89 | 24/04/2024 | 0 | WBSEDCL | 5.15 | 0 | 0 | 0
2273 | PURBA MEDINIPUR | Tamluk Division | TELAMI AND ADJOINING MOUJAS PWSS , SM/12288 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 94.37 | 31.84 | 51
2274 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) , SM/11554 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Shilaberia-Janka Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | 1647/TD | 19/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.96 | 4.95 | 100 | 100
2275 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) , SM/11554 | Augmentation | Material Requisition To Resource Division | 1659/TD | 03/11/2022 | 0 | Resource Division | 186.64 | 0 | 0 | 0
2276 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) , SM/11554 | Augmentation | Material Requisition To Resource Division | 1376/TD | 23/09/2022 | 0 | Resource Division | 13.06 | 0 | 0 | 0
2277 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) , SM/11554 | Augmentation | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-I, Zone-II (Ref. ID-204049345) | BP-2023-24-156 | 04/08/2023 | 0 | WBSEDCL | 0.97 | 0 | 0 | 0
2278 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) , SM/11554 | Augmentation | Electric Quotation for Chargeable Head, SHILLABERIA JANKA, Water Supply Scheme T/W-IV, Zone-I (Ref. ID-204049555) | BP-2023-24-159 | 04/08/2023 | 0 | WBSEDCL | 2.8 | 0 | 0 | 0
2279 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) , SM/11554 | Augmentation | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-II, Zone-II (Ref. ID-204049556) | BP-2023-24-157 | 04/08/2023 | 0 | WBSEDCL | 2.4 | 0 | 0 | 0
2280 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) , SM/11554 | Augmentation | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-IV, Zone-II (Ref. ID-204049361) | BP-2023-24-155 | 04/08/2023 | 0 | WBSEDCL | 2.97 | 0 | 0 | 0
2281 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) , SM/11554 | Augmentation | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-III, Zone-II (Ref. ID-204049047) | BP-2023-24-158 | 04/08/2023 | 0 | WBSEDCL | 2.3 | 0 | 0 | 0
2282 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) , SM/11554 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1650/TD | 02/11/2022 | 180 | TARUN KOLEY | 942.75 | 220.41 | 66.84 | 85
2283 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) , SM/11554 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II,under JJM Program under MMD PHE Dte. | 1274/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 50.28 | 34.45 | 68.51 | 70
2284 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) , SM/11948 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Khejuri Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | 1542/TD | 11/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.71 | 4.44 | 100 | 100
2285 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) , SM/11948 | Augmentation | Hiring of one no. Diesel Motor cabs (Luxury Taxi Standered non air conditioned) Bharat Stage -IV , on daily rate basis (including Govt. Holidays as and when required ) Having contract carraige permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. For the Period from 01/07/2021 to 30/06/2022. (12 Months) Vehicle No-WB-31/6974 | 157/CSD | 29/06/2021 | 12 | SABITA PRADHA | 1.49 | 4.53 | 100 | 100
2286 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) , SM/11948 | Augmentation | Material Requisition To Resource Division | 1259/TD | 12/09/2022 | 0 | Resource Division | 24.85 | 0 | 0 | 0
2287 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) , SM/11948 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.(Part-A) | 1654/TD | 02/11/2022 | 180 | SIBSANKAR CHOWDHURY | 449.19 | 165.5 | 54.02 | 40
2288 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) , SM/11948 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II)under JJM Program under MMD PHE Dte. | 1280/W/MMD | 04/05/2023 | 719 | DEBJYOTI BASU | 40.2 | 25.05 | 62.33 | 25
2289 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) , SM/11948 | Augmentation | Retrofitting to accommodate of 814 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. ( Part -C ) | 1077/TD | 23/08/2022 | 45 | J. K. BUILDERS | 109.37 | 107.91 | 100 | 95
2290 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) , SM/11948 | Augmentation | Quotation for new service connection at Khejuri Zone II w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004639938, Ref ID - 204243679) | BP-2023-24-851 | 16/03/2024 | 0 | WBSEDCL | 3.06 | 0 | 0 | 0
2291 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) , SM/11948 | Augmentation | Quotation for new service connection at Khejuri Zone II w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004640039, Ref ID - 204244094) | BP-2023-24-850 | 16/03/2024 | 0 | WBSEDCL | 4.53 | 0 | 0 | 0
2292 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) , SM/11948 | Augmentation | Retrofitting to accommodate of 860 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-B) | 1040/TD | 16/08/2022 | 1088 | M/S SREE DURGA ENTERPRISE | 110.9 | 105.16 | 94.83 | 96
2293 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) , SM/11948 | Augmentation | Continuation Work Order for the work of Hiring of one Diesel Motor cabs & Maxi cabs with Engine capacity More than 2000 C.C. with ( Air Condition) on monthly Hiring (Per day) ( including Govt. Holidays as and when required ) having contract carriage permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. Govt. of West Bengal. For the Period from 01/07/2023 to 30/06/2024 i.e.12 Months. | 1204/A/CSD | 21/06/2023 | 366 | SABITA PRADHAN | 1.49 | 0 | 0 | 0
2294 | PURBA MEDINIPUR | Tamluk Division | SAHARA AND ADJOINING MOUJAS PWSS , SM/12296 | New | Material Requisition To Resource Division | 2411/TD | 16/01/2023 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2295 | PURBA MEDINIPUR | Midnapore Mechanical | SAHARA AND ADJOINING MOUJAS PWSS , SM/12296 | New | Quotation Bill for New Service connection at T/W NO-II Of SAHARA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004769176/QUOT/03/442 DT. 11-06-2024 Application NO- 2004769176 Application type-New connection Consumer Id- 204327965 | BP-2024-25-333 | 25/06/2024 | 0 | WBSEDCL | 3.49 | 0 | 0 | 0
2296 | PURBA MEDINIPUR | Midnapore Mechanical | SAHARA AND ADJOINING MOUJAS PWSS , SM/12296 | New | Quotation Bill for New Service connection at T/W NO-I Of SAHARA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004769073/QUOT/03/443 DT. 11-06-2024 Application NO- 2004769073 Application type-New connection Consumer Id- 204327178 | BP-2024-25-334 | 25/06/2024 | 0 | WBSEDCL | 4.79 | 0 | 0 | 0
2297 | PURBA MEDINIPUR | Midnapore Mechanical | SAHARA AND ADJOINING MOUJAS PWSS , SM/12296 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAHARA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 940/W/MMD | 28/03/2023 | 856 | SUJOY RANJAN BHOWMICK | 27.69 | 16.57 | 59.85 | 60
2298 | PURBA MEDINIPUR | Tamluk Division | SAHARA AND ADJOINING MOUJAS PWSS , SM/12296 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 172.72 | 45.63 | 51
2299 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11862 | Augmentation | Material Requisition To Resource Division | 345/TD | 26/04/2023 | 0 | Resource Division | 9.11 | 0 | 0 | 0
2300 | PURBA MEDINIPUR | Midnapore Mechanical | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11862 | Augmentation | Electric quotation for Barasubarnanagar PWSS Tube Well- III in connection Mukundapur CCC (2004188348) | BP-2022-23-109 | 01/03/2023 | 0 | WBSEDCL | 0.5 | 0 | 0 | 0
2301 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11862 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 13.05 | 95.57 | 100
2302 | PURBA MEDINIPUR | Midnapore Mechanical | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11862 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Boosting Tube Well No. III for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District.under JJM Program under MMD PHE Dte. | 1354/W/MMD | 24/05/2023 | 180 | SOUMEN ELECTRIC | 13.57 | 12.5 | 92.1 | 40
2303 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11862 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Barasubarnanagar W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 472/TD | 10/05/2023 | 60 | JASODA ENTERPRISE | 3.83 | 3.58 | 100 | 100
2304 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11862 | Augmentation | Laying of 150 mm dia & 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at Replacement of 1st Tube Well & 1(One) no. Boosting Tube Well of Barasubarnanagar & its adjoining mouzas Water Supply Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 471/TD | 10/05/2023 | 30 | JASODA ENTERPRISE | 4.01 | 1.62 | 100 | 100
2305 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11862 | Augmentation | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Well (Head Work) of Mouza- Barasubarnanagar, JL No.- 502, Plot No.-297 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Ramnagar-II Block of Kanpur Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for 2nd Tube Well of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1050/TD | 18/08/2022 | 1017 | AQUATECH ENGINEERS | 45.52 | 13.07 | 95.76 | 98
2306 | PURBA MEDINIPUR | Midnapore Mechanical | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11862 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. under JJM Program under MMD PHE Dte. | 36/W/MMD | 04/01/2023 | 360 | SOUMEN ELECTRIC | 13.57 | 12.8 | 95.58 | 80
2307 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ramnagar (Zone-II) PWSS , SM/12486 | Augmentation | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 280 Mtrs. Depth) by utilising Departmental Machineries for Ramnagar W/S Scheme (TW-I, Z-II) Ramnagar-I Block under Purba Medinipur District, Central Drilling Division, PHE Dte. | 454/CDD | 02/06/2023 | 30 | UNIVERSAL ENTERPRISES | 20.47 | 16.54 | 100 | 100
2308 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ramnagar (Zone-II) PWSS , SM/12486 | Augmentation | Material Requisition To Resource Division | 2640/TD | 02/02/2023 | 0 | Resource Division | 18.12 | 0 | 0 | 0
2309 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ramnagar (Zone-II) PWSS , SM/12486 | Augmentation | Material Requisition To Resource Division | 2614/TD | 02/02/2023 | 0 | Resource Division | 65.04 | 0 | 0 | 0
2310 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ramnagar (Zone-II) PWSS , SM/12486 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ramnagar (Zone-II) PWSS, Block Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 821/W/MMD | 24/03/2023 | 180 | M/S SWAPAN BANERJEE | 27.17 | 12.76 | 46.97 | 45
2311 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ramnagar (Zone-II) PWSS , SM/12486 | Augmentation | Hiring of Diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Driller In Charge, CMSD-II(D),CDD P.H.E. Dte. | 227/CMSD-II(D) | 10/10/2023 | 61 | DILIP KAR | 0.29 | 0.53 | 100 | 50
2312 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ramnagar (Zone-II) PWSS , SM/12486 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Ramnagar W/S Scheme (Z- II,T/W-II) , Ramnagar-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 544/CDD | 02/06/2023 | 416 | UNIVERSAL ENTERPRISES | 20.47 | 17.32 | 100 | 100
2313 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ramnagar (Zone-II) PWSS , SM/12486 | Augmentation | Ramnagar W/S scheme T/W-I, Zone-II Application-2004536109 Ref.-204168170 | BP-2023-24-541 | 11/01/2024 | 0 | WBSEDCL | 5.06 | 0 | 0 | 0
2314 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ramnagar (Zone-II) PWSS , SM/12486 | Augmentation | Laying of Distribution System to accomodate FHTC(2941 Nos), Construction of Boundary Wall,Pump House ,R.C.C. Overhead Reservoir of Capacity 350 Cum and staging height 20 meter for Augmentation of Ramnagar Water Supply Scheme (Zone-II) within Ramnagar-I Block under Tamluk Division in the district of Purba Medinipur. | 2532/TD | 19/01/2023 | 803 | BASANTA KUMAR MAITY | 476.59 | 191.35 | 40.15 | 66
2315 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ramnagar (Zone-II) PWSS , SM/12486 | Augmentation | Land development of 2nd T/W Site at Ramnagar Zone-II & Its Adjoining Mouzas water Supply Scheme within Ramnagar-I BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | 905/DSD | 03/09/2024 | 7 | SRIYA CONSTRUCTION | 2.86 | 0 | 0 | 0
2316 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ramnagar (Zone-II) PWSS , SM/12486 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Ramnagar Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | 741/TD | 04/07/2022 | 20 | SANTRA ENTERPRISE. | 4.52 | 2.45 | 100 | 100
2317 | PURBA MEDINIPUR | Tamluk Division | HALUD BARI AND ADJOINING MOUJAS , SM/12821 | New | Material Requisition To Resource Division | 2708/TD | 06/02/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
2318 | PURBA MEDINIPUR | Midnapore Mechanical | HALUD BARI AND ADJOINING MOUJAS , SM/12821 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HALUD BARI and ADJOINING MOUJAS, Block - Khejuri II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 524/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 15.86 | 66.91 | 48
2319 | PURBA MEDINIPUR | Midnapore Mechanical | HALUD BARI AND ADJOINING MOUJAS , SM/12821 | New | Quotation Bill for Haludbari Water Supply scheme Tube well no.-I Khejuri CCC Block-Khejuri Application No.-2004645013 Ref ID.-204247115 Quatation Bill Date.-14/03/2024 | BP-2023-24-888 | 22/03/2024 | 0 | WBSEDCL | 4.93 | 0 | 0 | 0
2320 | PURBA MEDINIPUR | Tamluk Division | HALUD BARI AND ADJOINING MOUJAS , SM/12821 | New | Payment of WBSEDCL for Quotation of Shifting of LTOH line at Haludbari Water Supply Scheme for Construction of New OHR. | BP-2023-24-844 | 07/02/2024 | 0 | WBSEDCL | 1.52 | 0 | 0 | 0
2321 | PURBA MEDINIPUR | Midnapore Mechanical | HALUD BARI AND ADJOINING MOUJAS , SM/12821 | New | Quotation for new service connection at Haludbari w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.(App No. 2004785778, Ref ID 204336496) | BP-2024-25-377 | 08/07/2024 | 0 | WBSEDCL | 4.71 | 0 | 0 | 0
2322 | PURBA MEDINIPUR | Tamluk Division | HALUD BARI AND ADJOINING MOUJAS , SM/12821 | New | Sinking of Tube Well ,Rising main,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works, with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (4781 Nos), including 2 years Operation & Maintenance For Halud Bari, Dekhali, Pipe water supply Scheme within Khejuri-II Block, within Contai Sub-Division Under Tamluk Division PHE Dte. | 454/TD | 04/05/2023 | 912 | TAPAS SANTRA | 1701.13 | 482.25 | 73.14 | 78
2323 | PURBA MEDINIPUR | Tamluk Division | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS , SM/13696 | New | Material Requisition To Resource Division | 2703/TD | 06/02/2023 | 0 | Resource Division | 15.41 | 0 | 0 | 0
2324 | PURBA MEDINIPUR | Midnapore Mechanical | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS , SM/13696 | New | Quotation Bill for New Service connection at T/W NO-II Of AYMABAR BARIA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004878127/QUOT/03 DT. 30-08-2024 MEMO NO: AMR/PHE/350 DT. 30/08/2024 Application NO- 2004878127 Application type-New connection Consumer Id- 204387570 | C102415716055 | 05/10/2024 | 0 | WBSEDCL | 3.99 | 0 | 0 | 0
2325 | PURBA MEDINIPUR | Midnapore Mechanical | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS , SM/13696 | New | Quotation Bill for New Service connection at T/W NO-I Of AYMABAR BERYA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004775224/QUOT/03 DT. 14-06-2024 Application NO- 2004775224 Application type-New connection Consumer Id- 204330602 | BP-2024-25-355 | 01/07/2024 | 0 | WBSEDCL | 10.56 | 0 | 0 | 0
2326 | PURBA MEDINIPUR | Midnapore Mechanical | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS , SM/13696 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AYMABAR BARYA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 542/W/MMD | 20/03/2023 | 1017 | SOUMEN ELECTRIC | 21.56 | 15.29 | 70.89 | 60
2327 | PURBA MEDINIPUR | Tamluk Division | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS , SM/13696 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 2703/TD | 20/10/2023 | 620 | S & P ENTERPRISE | 1928.99 | 0 | 0 | 30
2328 | PURBA MEDINIPUR | Tamluk Division | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS , SM/13699 | New | Material Requisition To Resource Division | 2720/TD | 06/02/2023 | 0 | Resource Division | 33.64 | 0 | 0 | 0
2329 | PURBA MEDINIPUR | Tamluk Division | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS , SM/13699 | New | Laying Distribution System (Nodal-1-2,2-4,4-19,19-20,20-50,50-84,84-109,109-167 & 167-89) of pipe line and its allied works for PASCHIM BAR Water Supply Scheme in Bhgwanpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 1072/TD | 16/03/2024 | 25 | MISHRA ENTERPRISE | 23.45 | 21.38 | 91.17 | 80
2330 | PURBA MEDINIPUR | Tamluk Division | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS , SM/13699 | New | Material Requisition To Resource Division | 128/TD | 05/01/2024 | 0 | Resource Division | 19.59 | 0 | 0 | 0
2331 | PURBA MEDINIPUR | Midnapore Mechanical | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS , SM/13699 | New | Paschimbarh W/S scheme T/W No.-II (Laxmi Mandir) Applicatiot No.-2004522520 Ref.-204156806 | BP-2023-24-479 | 27/12/2023 | 0 | WBSEDCL | 4.86 | 0 | 0 | 0
2332 | PURBA MEDINIPUR | Midnapore Mechanical | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS , SM/13699 | New | Electric Quotation for PASCHIMBAR Water Supply Scheme T/W-I, (Ref. ID-204104644) | BP-2023-24-390 | 02/12/2023 | 0 | WBSEDCL | 1.05 | 0 | 0 | 0
2333 | PURBA MEDINIPUR | Tamluk Division | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS , SM/13699 | New | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3181 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of PASCHIM BAR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 447/TD | 04/05/2023 | 942 | TAPAS SANTRA | 872.64 | 595.67 | 68.26 | 40
2334 | PURBA MEDINIPUR | Tamluk Division | KASBAPATASHPUR & ADJOINING MOUJAS PWSS , SM/12172 | New | Material Requisition To Resource Division | 2451/TD | 16/01/2023 | 0 | Resource Division | 32.56 | 0 | 0 | 0
2335 | PURBA MEDINIPUR | Midnapore Mechanical | KASBAPATASHPUR & ADJOINING MOUJAS PWSS , SM/12172 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KASBAPATASHPUR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2364/W/MMD | 31/12/2022 | 180 | JAL PRAVAHIKA PVT. LTD. | 23.44 | 0 | 0 | 0
2336 | PURBA MEDINIPUR | Tamluk Division | KASBAPATASHPUR & ADJOINING MOUJAS PWSS , SM/12172 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kasba Patashpur PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | 2064/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
2337 | PURBA MEDINIPUR | Tamluk Division | KASBAPATASHPUR & ADJOINING MOUJAS PWSS , SM/12172 | New | Material Requisition To Resource Division | 1652/TD | 29/04/2024 | 0 | Resource Division | 11.55 | 0 | 0 | 0
2338 | PURBA MEDINIPUR | Tamluk Division | KASBAPATASHPUR & ADJOINING MOUJAS PWSS , SM/12172 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 13.52 | 2.46 | 51
2339 | PURBA MEDINIPUR | Tamluk Division | AMARPUR & ADJOINING MOUZAS , SM/12132 | New | Material Requisition To Resource Division | 2706/TD | 06/02/2023 | 0 | Resource Division | 24.84 | 0 | 0 | 0
2340 | PURBA MEDINIPUR | Midnapore Mechanical | AMARPUR & ADJOINING MOUZAS , SM/12132 | New | Quotation Bill for New Service connection at T/W NO-I Of AMARPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743549/QUOT/03 DT. 25-05-2024 Application NO- 2004743549 Application type-New connection Consumer Id- 204312620 | BP-2024-25-318 | 24/06/2024 | 0 | WBSEDCL | 3.67 | 0 | 0 | 0
2341 | PURBA MEDINIPUR | Midnapore Mechanical | AMARPUR & ADJOINING MOUZAS , SM/12132 | New | Quotation Bill for New Service connection at T/W NO-II Of AMARPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004793608/QUOT/03 DT. 25-06-2024 MEMO NO: AMR/PHE/223 DT. 25-06-2024 Application NO- 2004793608 Application type-New connection Consumer Id- 204340910 | BP-2024-25-373 | 08/07/2024 | 0 | WBSEDCL | 4.59 | 0 | 0 | 0
2342 | PURBA MEDINIPUR | Midnapore Mechanical | AMARPUR & ADJOINING MOUZAS , SM/12132 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMARPUR and ADJOINING MOUJAS, Block potaspur- I, District Purba Medinipur under JJM Program under MMD PHE Dte. | 937/W/MMD | 28/03/2023 | 710 | MENAKA ENTERPRISE | 22.77 | 13.33 | 58.55 | 50
2343 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sherkhanchak Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | 1511/TD | 06/01/2022 | 20 | SANTRA ENTERPRISE. | 3.71 | 3.33 | 100 | 100
2344 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN SHERKHANCHAK PWSS, BLOCK-KHEJURI -II, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. | 133/CMSD-II | 12/08/2022 | 15 | MENAKA ENTERPRISE | 5 | 4.83 | 100 | 100
2345 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN SHERKHANCHAK PWSS, ZONE-II, BLOCK-KHEJURI-II, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. | 146/S&WSD | 12/08/2022 | 15 | MENAKA ENTERPRISE | 4.38 | 4.22 | 100 | 100
2346 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SHERKHANCHAK W/S SCH, BHAGAWANPUR-I BLOCK UNDER MEDINIPUR DISTRICT, CDD, PHE DTE. | 435/CDD | 23/05/2022 | 30 | MENAKA ENTERPRISE | 14.69 | 8.86 | 100 | 100
2347 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well No I of Zone II under Sherkhan Chack water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2115/W/MMD | 28/11/2022 | 120 | BHABANI PRASAD MANNA | 11.56 | 0 | 0 | 0
2348 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for the office of The Assistant Engineer, S&WSD,CDD, PHE Dte. | 232/S&WSD | 20/12/2022 | 7 | NAGENDRA PATRA | 0.86 | 2.27 | 100 | 100
2349 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 300 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR SERKHAN CHAK W/S SCHEME, ZONE-I, TW-III, KHEJURI-II BLOCK, UNDER PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | 1381/CDD | 24/11/2022 | 30 | MENAKA ENTERPRISE | 22.11 | 17.48 | 100 | 0
2350 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | Hiring of Diesel driven motor cab (BS-IV & above) having contract carriage permit along with driver for the office of the Assistant Engineer, S&WSD, CDD, PHE Dte. | 74/S&WSD | 30/06/2023 | 30 | NAGENDRA PATRA | 0.15 | 0.4 | 100 | 100
2351 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 300 mtrs. Depth) by utilising Departmental machineries for Serkhanchak W/S Scheme (TW-III), Khejuri-II block under Purba Midnapore District, CDD PHE Dte. | 1346/CDD | 24/11/2022 | 30 | MENAKA ENTERPRISE | 22.2 | 16.22 | 100 | 100
2352 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | Material Requisition To Resource Division | 1198/TD | 06/09/2022 | 0 | Resource Division | 15.39 | 0 | 0 | 0
2353 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | Material Requisition To Resource Division | 1210/TD | 06/09/2022 | 0 | Resource Division | 15.91 | 0 | 0 | 0
2354 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Serkhan Chawk W/S Scheme (TW-¦V) , Khejuri-ll Block under Purba Midnapore Dlstrict, Central Drilling Division, P.H.E. Dte. | 1536/CDD | 08/12/2022 | 30 | MENAKA ENTERPRISE | 22.23 | 16.07 | 100 | 100
2355 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 250cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Sherkhanchak Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 816/TD | 12/07/2022 | 1005 | SRIMANTA KUMAR MAITY | 406.75 | 278.03 | 68.36 | 70
2356 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 214/W/MMD | 10/02/2023 | 445 | EMCON | 11.83 | 10.96 | 92.58 | 85
2357 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | Name of Work: i) Laying Rising main and other allied works Augmentation of Sherkhanchak Zone-II W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3222/TD | 14/03/2023 | 650 | SRIMANTA KUMAR MAITY | 7.4 | 0 | 0 | 100
2358 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11469 | Augmentation | Laying of Left-Out portion uPVC Pipe line, Repair & renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site and 2nd Tube well site under Sherkhanchak Zone-II Water Supply Scheme (Augmentation) in Khejuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 982/TD | 13/03/2024 | 330 | BIPLAB GUHA | 86.79 | 0 | 0 | 60
2359 | PURBA MEDINIPUR | Midnapore Mechanical | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12774 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GABARDHANPUR and ADJOINING MOUJAS, Block - Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 519/W/MMD | 20/03/2023 | 180 | RMD TRADING | 22.76 | 0 | 0 | 0
2360 | PURBA MEDINIPUR | Tamluk Division | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12774 | New | Material Requisition To Resource Division | 2455/TD | 16/01/2023 | 0 | Resource Division | 15.86 | 0 | 0 | 0
2361 | PURBA MEDINIPUR | Tamluk Division | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12774 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Gabardhanpur PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | 2201/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
2362 | PURBA MEDINIPUR | Tamluk Division | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12774 | New | Material Requisition To Resource Division | 1650/TD | 29/04/2024 | 0 | Resource Division | 10.35 | 0 | 0 | 0
2363 | PURBA MEDINIPUR | Midnapore Mechanical | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12774 | New | Quotation Bill for New Service connection at T/W NO-I Of Gabardhanpur W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004595896/QUOT/03 DT. 12-03-2024 Application NO- 2004595896 Application type-New connection CONSUMER ID: 204213657 | BP-2023-24-921 | 28/03/2024 | 0 | WBSEDCL | 3.29 | 0 | 0 | 0
2364 | PURBA MEDINIPUR | Midnapore Mechanical | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12774 | New | Quotation Bill for New Service connection at T/W NO-II Of GOBARDHANPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004595917/QUOT/03 DT. 12-02-2024 Application NO- 2004595917 Application type-New connection Consumer Id- 204213656 | BP-2024-25-250 | 06/06/2024 | 0 | WBSEDCL | 3.79 | 0 | 0 | 0
2365 | PURBA MEDINIPUR | Tamluk Division | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12774 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 126.18 | 22.55 | 51
2366 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-II , SM/14842 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Piped Water Supply Scheme for Sankarpur Zone-II Ramnagar I Blockunder JJM Program under MMD PHE Dte. | 887/W/MMD | 27/03/2023 | 180 | R.S. ENTERPRISE | 11.4 | 0 | 0 | 0
2367 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-II , SM/14842 | Augmentation | Laying distribution pipe line & Accommodate FHTC ( 79 Nos) under JJM with allied work for SANKARPUR (Zone-II) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 287/TD | 20/04/2023 | 20 | BUNBA CONSTRUCTION | 16.35 | 14.59 | 89.27 | 90
2368 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-II , SM/14842 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone- II) under Tamluk Division, PHE Dte. | 739/TD | 25/05/2023 | 20 | ASTER CONSULTANCY | 3.46 | 3.41 | 100 | 100
2369 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14843 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | 895/W/MMD | 27/03/2023 | 180 | SUBHASIS ROY | 11.84 | 0 | 0 | 0
2370 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14843 | Augmentation | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well of Source Augmentation of Bamunia & its adjoining mouzas Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 999/TD | 05/06/2023 | 30 | GIRI CONSTRUCTION | 3.39 | 0 | 0 | 0
2371 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14843 | Augmentation | Material Requisition To Resource Division | 340/TD | 26/04/2023 | 0 | Resource Division | 5.21 | 0 | 0 | 0
2372 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14843 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai- II ( Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 241/TD | 19/04/2023 | 30 | GITA ENTERPRISE | 7.54 | 0 | 0 | 0
2373 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14843 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 119/TD | 06/04/2023 | 703 | B. K. ENTERPRISE | 53.77 | 13.01 | 96.79 | 75
2374 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14843 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Source Augmentation of Bamunia W/S Scheme within Contai - II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 998/TD | 05/06/2023 | 660 | GIRI CONSTRUCTION | 3.72 | 0 | 0 | 100
2375 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14844 | Augmentation | Material Requisition To Resource Division | 341/TD | 26/04/2023 | 0 | Resource Division | 4.77 | 0 | 0 | 0
2376 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14844 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | 894/W/MMD | 27/03/2023 | 180 | SUBHASIS ROY | 11.84 | 11.09 | 93.64 | 85
2377 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14844 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 119/TD | 06/04/2023 | 703 | B. K. ENTERPRISE | 53.77 | 12.84 | 95.51 | 75
2378 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14844 | Augmentation | Constrution of Boundary wall (as per Departmental Desigh & Drawing) And,Augmentation of Silampur Scheme within Contai-II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | 600/TD | 17/05/2023 | 30 | M/S SOURAV MAHAPATRA | 7.01 | 4.5 | 64.24 | 100
2379 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14844 | Augmentation | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well of Source Augmentation of Silampur & its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 480/TD | 10/05/2023 | 30 | JASODA ENTERPRISE | 3.27 | 1.05 | 100 | 100
2380 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14844 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Source Augmentation of Silampur W/S Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 481/TD | 10/05/2023 | 60 | THE GODFATHER TRADING COMPANY | 3.67 | 3.56 | 100 | 100
2381 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14844 | Augmentation | Instalation of display Board at different work site of Silampur, Uttar Khasda, Barchunfali, Uttar Charaikhia Retrofitting PWSS in Contai - I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2331/CSD | 29/12/2023 | 15 | SAURAV HAZRA | 0.83 | 0.83 | 100 | 100
2382 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/14844 | Augmentation | Electric Quotation for SILAMPUR Water Supply Scheme T/W-III, (Ref. ID-204134606) | BP-2023-24-361 | 24/11/2023 | 0 | WBSEDCL | 3.71 | 0 | 0 | 0
2383 | PURBA MEDINIPUR | Tamluk Division | BAINCHA AND IT'S ADJOINING MOUJAS PWSS , SM/14455 | New | Material Requisition To Resource Division | 2712/TD | 06/02/2023 | 0 | Resource Division | 32.92 | 0 | 0 | 0
2384 | PURBA MEDINIPUR | Midnapore Mechanical | BAINCHA AND IT'S ADJOINING MOUJAS PWSS , SM/14455 | New | Quotation Bill for New Service connection at T/W NO-I Of BAINCHA W/S Scheme under MMD, PHE, Dte. Block- Egra-II, BALIGHAI C.C.C. Ref. Memo No- 2004626460/QUOT/03 DT. 01-03-2024 Application NO- 2004626460 Application type-New connection Consumer Id- 204233927 | BP-2023-24-864 | 16/03/2024 | 0 | WBSEDCL | 5.54 | 0 | 0 | 0
2385 | PURBA MEDINIPUR | Midnapore Mechanical | BAINCHA AND IT'S ADJOINING MOUJAS PWSS , SM/14455 | New | "Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAINCHA AND ITS ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. ¿" | 948/W/MMD | 28/03/2023 | 887 | A.S.ENTERPRISE | 21.57 | 9.57 | 44.38 | 90
2386 | PURBA MEDINIPUR | Tamluk Division | BAINCHA AND IT'S ADJOINING MOUJAS PWSS , SM/14455 | New | Sinking of Tube Well ,Construction of Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (880nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Baincha PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | 1566/TD | 19/07/2023 | 709 | M/S JOY | 322.5 | 136.69 | 42.39 | 45
2387 | PURBA MEDINIPUR | Tamluk Division | BAINCHA AND IT'S ADJOINING MOUJAS PWSS , SM/14455 | New | Land Development at HeadWorks site of Baincha Water Supply Scheme within Egra - II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur. | 1575/TD | 13/06/2025 | 7 | M/S JOY | 4.75 | 0 | 0 | 0
2388 | PURBA MEDINIPUR | Tamluk Division | KATNADIGHI AND IT'S ADJOINING MOUJAS PWSS , SM/14457 | New | Material Requisition To Resource Division | 2461/TD | 16/01/2023 | 0 | Resource Division | 21.8 | 0 | 0 | 0
2389 | PURBA MEDINIPUR | Tamluk Division | KATNADIGHI AND IT'S ADJOINING MOUJAS PWSS , SM/14457 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Katnadighi PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | 2197/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
2390 | PURBA MEDINIPUR | Tamluk Division | KATNADIGHI AND IT'S ADJOINING MOUJAS PWSS , SM/14457 | New | Material Requisition To Resource Division | 1653/TD | 29/04/2024 | 0 | Resource Division | 3.51 | 0 | 0 | 0
2391 | PURBA MEDINIPUR | Midnapore Mechanical | KATNADIGHI AND IT'S ADJOINING MOUJAS PWSS , SM/14457 | New | Quotation Bill for New Service connection at T/W NO-I Of KATNADIGHI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760145/QUOT/03 DT. 04-06-2024 Application NO- 2004760145 Application type-New connection Consumer Id- 204322030 | BP-2024-25-296 | 18/06/2024 | 0 | WBSEDCL | 4.71 | 0 | 0 | 0
2392 | PURBA MEDINIPUR | Tamluk Division | KATNADIGHI AND IT'S ADJOINING MOUJAS PWSS , SM/14457 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 32.79 | 12.81 | 51
2393 | PURBA MEDINIPUR | Tamluk Division | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15036 | Augmentation | Augmentation of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura-I Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | 2558/TD | 24/01/2023 | 60 | TARUN KOLEY | 73.36 | 9.62 | 100 | 100
2394 | PURBA MEDINIPUR | Central Drilling | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15036 | Augmentation | Providing drilling crew and allied works for construction of Tube Well (300mm x 200mm x 230mtrs. Depth) by utilising Departmental Machineries for Gobindanagar PWSS 1ST Boosting TW, Z-I, Panskura - I Block under Purba Medinipur District, CDD, PHE Dte. | 2113/CDD | 02/03/2023 | 30 | PADMA ENGINEERING & CO. | 17.76 | 14.72 | 100 | 100
2395 | PURBA MEDINIPUR | Tamluk Division | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15036 | Augmentation | Material Requisition To Resource Division | 344/TD | 26/04/2023 | 0 | Resource Division | 13.24 | 0 | 0 | 0
2396 | PURBA MEDINIPUR | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15036 | Augmentation | Electric Quotation for GOBINDANAGAR (ALALPARA)Water Supply Scheme Z-II, T/W-II (Ref. ID-204048367) | BP-2023-24-198 | 18/08/2023 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
2397 | PURBA MEDINIPUR | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15036 | Augmentation | Electric Quotation for GOBINDANAGAR, Water Supply Scheme T/W-I, Zone-I (Ref. ID-204056032) | BP-2023-24-177 | 08/08/2023 | 0 | WBSEDCL | 2.92 | 0 | 0 | 0
2398 | PURBA MEDINIPUR | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15036 | Augmentation | Electric Quotation for GOBINDANAGAR Water Supply Scheme Z-II, T/W-III (Ref. ID-204048353) | BP-2023-24-197 | 18/08/2023 | 0 | WBSEDCL | 12.55 | 0 | 0 | 0
2399 | PURBA MEDINIPUR | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15036 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 0 | 50
2400 | PURBA MEDINIPUR | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15036 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1(One)) No. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | 3042/W/MMD | 17/11/2023 | 501 | SHIVAM ENTERPRISE | 13.68 | 2.95 | 21.58 | 80
2401 | PURBA MEDINIPUR | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15036 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | 902/W/MMD | 27/03/2023 | 180 | M/S EMMESS | 40.78 | 40.07 | 100 | 70
2402 | PURBA MEDINIPUR | Tamluk Division | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15036 | Augmentation | Name of Work: Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Gobindanagar W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Dakshin Mechogram W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 117/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 37.12 | 16.48 | 100 | 100
2403 | PURBA MEDINIPUR | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15036 | Augmentation | Additional service connection charge at Gobindanagar, Zone-II, TW-IV Chiara, Chiara, Gobindanagar, Golghat Panskura Ref ID-860294542 Application ID-100000102262 Panskura CCC | BP-2023-24-827 | 13/03/2024 | 0 | WBSEDCL | 1.83 | 0 | 0 | 0
2404 | PURBA MEDINIPUR | Tamluk Division | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15036 | Augmentation | 3(Three) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room, Laying of Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Gobindanagar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 269/TD | 20/04/2023 | 600 | M/S. S. A. CONSTRUCTION | 49.64 | 10.88 | 20.94 | 100
2405 | PURBA MEDINIPUR | Tamluk Division | TULIA AND ADJOINING MOUJAS PWSS , SM/15037 | New | Material Requisition To Resource Division | 3018/TD | 27/02/2023 | 0 | Resource Division | 24.12 | 0 | 0 | 0
2406 | PURBA MEDINIPUR | Midnapore Mechanical | TULIA AND ADJOINING MOUJAS PWSS , SM/15037 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TULIA AND ADJOINING MOUJAS PWSS Tamluk Block under JJM Program under MMD PHE Dte. | 888/W/MMD | 27/03/2023 | 180 | M.D.ENTERPRISE | 23.65 | 11.02 | 46.62 | 35
2407 | PURBA MEDINIPUR | Tamluk Division | TULIA AND ADJOINING MOUJAS PWSS , SM/15037 | New | Sinking of Tube well ,Laying distribution pipe line, laying Rising main ,Pump House , Boundary Wall, Soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC 2059 nos) including Operation & Maintanance for Two years under JJM with allied work including supply of all labour & materials for Tulia and Adjoining Moujas Piped Water Supply Scheme in Tamluk Dev. Block within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 908/TD | 01/06/2023 | 180 | HARIPADA PATTANAYAK | 492.6 | 51.07 | 10.37 | 50
2408 | PURBA MEDINIPUR | Midnapore Mechanical | TULIA AND ADJOINING MOUJAS PWSS , SM/15037 | New | Tulia W/S scheme Application no.-2004555235 Ref.-204184819 | BP-2023-24-621 | 07/02/2024 | 0 | WBSEDCL | 16.04 | 0 | 0 | 0
2409 | PURBA MEDINIPUR | Midnapore Mechanical | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT BHERI BHARANGA AND OTHER 20 PWSS IN PURBA MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. , SM/14486 | Augmentation | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT BHERI BHARANGA AND OTHER 20 PWSS IN PURBA MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. | 266/W/MMD | 20/02/2023 | 180 | SOUMEN ELECTRIC | 41.28 | 0 | 0 | 0
2410 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 , SM/15844 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. | 1932./TD | 28/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 2.89 | 100 | 100
2411 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 , SM/15844 | Augmentation | Material Requisition To Resource Division | 2076/TD | 28/08/2023 | 0 | Resource Division | 15.05 | 0 | 0 | 0
2412 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 , SM/15844 | Augmentation | Material Requisition To Resource Division | 2996/TD | 29/11/2023 | 0 | Resource Division | 1.07 | 0 | 0 | 0
2413 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 , SM/15844 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 173 Nos) under JJM with allied work for Chirulia-Chatla (Zone-IV) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | 1759/TD | 01/08/2023 | 180 | SUSIL KUMAR HAZRA | 262.49 | 0 | 0 | 0
2414 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 , SM/15844 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Egra - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1207/W/MMD | 25/04/2023 | 981 | BHABANI PRASAD MANNA | 59.85 | 0 | 0 | 20
2415 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-IV , SM/15845 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. | 1866/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 2.98 | 100 | 100
2416 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-IV , SM/15845 | Augmentation | Material Requisition To Resource Division | 2073/TD | 28/08/2023 | 0 | Resource Division | 15.35 | 0 | 0 | 0
2417 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-IV , SM/15845 | Augmentation | Material Requisition To Resource Division | 3002/TD | 29/11/2023 | 0 | Resource Division | 0.3 | 0 | 0 | 0
2418 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-IV , SM/15845 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, ZONE-IV Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004941929/QUOT/03/769 DT. 25-10-2024 Application NO- 2004941929 Application type-New connection Consumer Id- 204428742 | C112429746394 | 25/11/2024 | 0 | WBSEDCL | 3.67 | 0 | 0 | 0
2419 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-IV , SM/15845 | Augmentation | Quotation Bill for New Service connection at T/W NO-I, ZONE-IV Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004714304/QUOT/03/142 DT. 03-05-2024 Application NO- 2004714304 Application type-New connection Consumer Id- 204294967 | BP-2024-25-337 | 25/06/2024 | 0 | WBSEDCL | 4.73 | 0 | 0 | 0
2420 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-IV , SM/15845 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1242/W/MMD | 28/04/2023 | 764 | BHABANI PRASAD MANNA | 84.29 | 0 | 0 | 70
2421 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-IV , SM/15845 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (48 nos) under JJM with allied work for Bathuari (Zone-IV) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 1762/TD | 01/08/2023 | 853 | ARABINDA GHOSH | 278.74 | 26.66 | 9.56 | 20
2422 | PURBA MEDINIPUR | Tamluk Division | DEKHALI AND ADJOINING MOUJAS PWSS , SM/15515 | New | Material Requisition To Resource Division | 2707/TD | 06/02/2023 | 0 | Resource Division | 20.88 | 0 | 0 | 0
2423 | PURBA MEDINIPUR | Midnapore Mechanical | DEKHALI AND ADJOINING MOUJAS PWSS , SM/15515 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DEKHALI and ADJOINING MOUJAS, Block ¿ Khejuri II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 474/W/MMD | 20/03/2023 | 180 | KAMAKSHYA ENTERPRISE | 27.04 | 23.1 | 85.45 | 60
2424 | PURBA MEDINIPUR | Tamluk Division | DEKHALI AND ADJOINING MOUJAS PWSS , SM/15515 | New | Quotation for new service connection at Dekhali w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.(App No. 2004783456, Ref ID 204336497) | BP-2024-25-288 | 29/07/2024 | 0 | WBSEDCL | 12.1 | 0 | 0 | 0
2425 | PURBA MEDINIPUR | Midnapore Mechanical | DEKHALI AND ADJOINING MOUJAS PWSS , SM/15515 | New | Quotation for new service connection at Dekhali w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004640113, Ref ID - 204244140) | BP-2023-24-865 | 16/03/2024 | 0 | WBSEDCL | 8.79 | 0 | 0 | 0
2426 | PURBA MEDINIPUR | Tamluk Division | DEKHALI AND ADJOINING MOUJAS PWSS , SM/15515 | New | Sinking of Tube Well ,Rising main,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works, with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (4781 Nos), including 2 years Operation & Maintenance For Halud Bari, Dekhali, Pipe water supply Scheme within Khejuri-II Block, within Contai Sub-Division Under Tamluk Division PHE Dte. | 454/TD | 04/05/2023 | 912 | TAPAS SANTRA | 1701.13 | 815.02 | 78.23 | 78
2427 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Tajpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16204 | Augmentation | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Jalpai Part-II W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Tajpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Manikpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 115/TD | 06/04/2023 | 40 | B. K. ENTERPRISE | 63.13 | 20.56 | 100 | 100
2428 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Tajpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16204 | Augmentation | Material Requisition To Resource Division | 354/TD | 26/04/2023 | 0 | Resource Division | 1.14 | 0 | 0 | 0
2429 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Tajpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16204 | Augmentation | Electric Quotation for TAJPUR Boosting, Water Supply Scheme T/W (Ref. ID-204063651) | BP-2023-24-202 | 24/08/2023 | 0 | WBSEDCL | 3.86 | 0 | 0 | 0
2430 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Tajpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16204 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1209/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 53.9 | 12.71 | 94.29 | 35
2431 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Tajpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16204 | Augmentation | Construction of Pump House, Laying Rising Main & Construction of Boundary Wall at Boosting Tube well Site of Tajpur W/S Scheme within Nandigram-I Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 331/TD | 25/04/2023 | 617 | M/S SOURAV MAHAPATRA | 12.42 | 10.79 | 88.87 | 100
2432 | PURBA MEDINIPUR | Tamluk Division | BADALPUR PIPED WATER SUPPLY SCHEME. , SM/15852 | New | Material Requisition To Resource Division | 3011/TD | 27/02/2023 | 0 | Resource Division | 6.62 | 0 | 0 | 0
2433 | PURBA MEDINIPUR | Tamluk Division | BADALPUR PIPED WATER SUPPLY SCHEME. , SM/15852 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Badalpur PWSS at Ramnagar - II Block under Tamluk Division, PHE Dte. | 208/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
2434 | PURBA MEDINIPUR | Tamluk Division | BADALPUR PIPED WATER SUPPLY SCHEME. , SM/15852 | New | Material Requisition To Resource Division | 2947/TD | 12/09/2024 | 0 | Resource Division | 1.53 | 0 | 0 | 0
2435 | PURBA MEDINIPUR | Midnapore Mechanical | BADALPUR PIPED WATER SUPPLY SCHEME. , SM/15852 | New | Quotation for new service connection at TW-1 of Badalpur ws scheme under MMD,PHE Dte. Block-Contai-I, Pichaboni CCC. Application no-2004641194. Con ID-204244743. | BP-2024-25-1 | 04/04/2024 | 0 | WBSEDCL | 0.86 | 0 | 0 | 0
2436 | PURBA MEDINIPUR | Midnapore Mechanical | BADALPUR PIPED WATER SUPPLY SCHEME. , SM/15852 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Contai - I and III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1205/W/MMD | 25/04/2023 | 859 | BHABANI PRASAD MANNA | 57.85 | 0 | 0 | 60
2437 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Jalpai Part-II Water Supply Scheme of Nandigram-II Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16206 | Augmentation | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Jalpai Part-II W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Tajpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Manikpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 115/TD | 06/04/2023 | 40 | B. K. ENTERPRISE | 63.13 | 20.56 | 100 | 100
2438 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Jalpai Part-II Water Supply Scheme of Nandigram-II Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16206 | Augmentation | Material Requisition To Resource Division | 360/TD | 26/04/2023 | 0 | Resource Division | 0.35 | 0 | 0 | 0
2439 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Jalpai Part-II Water Supply Scheme of Nandigram-II Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16206 | Augmentation | Electric Quotation for JALPAI PART-II, Water Supply Scheme , T/W-III, (Ref. ID-204076620) | BP-2023-24-257 | 26/09/2023 | 0 | WBSEDCL | 5.72 | 0 | 0 | 0
2440 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Jalpai Part-II Water Supply Scheme of Nandigram-II Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16206 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1209/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 53.9 | 12.64 | 93.77 | 35
2441 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Saripur Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16938 | Augmentation | Material Requisition To Resource Division | 350/TD | 26/04/2023 | 0 | Resource Division | 4.41 | 0 | 0 | 0
2442 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Saripur Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16938 | Augmentation | Electric Quotation for SARIPUR Water Supply Scheme T/W-I, (Ref. ID-204064849) | BP-2023-24-309 | 01/11/2023 | 0 | WBSEDCL | 3.58 | 0 | 0 | 0
2443 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Saripur Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16938 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1204/W/MMD | 25/04/2023 | 740 | BHABANI PRASAD MANNA | 77.91 | 8.1 | 64.76 | 55
2444 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Saripur Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16938 | Augmentation | Name of Work: Sinking of 3 (Three) nos.Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Kotbar W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Saripur W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Paramanandapur W/S Scheme within Moyna Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 118/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 61.66 | 17.82 | 100 | 100
2445 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Saripur Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16938 | Augmentation | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room,Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Saripur Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 1425/TD | 12/07/2023 | 60 | SK. NUR ISLAM | 13.01 | 12.98 | 100 | 100
2446 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16939 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate under JJM with allied work for Dariapur PWSS within Contai-II (Deshpran) Block including supply of all labour & materials under Contai Sub-Division of Tamluk Division, PHE Dte. Part-A | 286/TD | 20/04/2023 | 60 | BUNBA CONSTRUCTION | 28.63 | 0 | 0 | 0
2447 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16939 | Augmentation | Material Requisition To Resource Division | 343/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0 | 0
2448 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16939 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Deshopran in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1206/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 34.45 | 0 | 0 | 53
2449 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16939 | Augmentation | Instalation of display Board at different work site of Haipur, Damodarpur Retrofitting PWSS in Contai - I Block, Dariapur & Bankiput Retrofitting PWSS in Contai - II (Deshopran) Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2332/CSD | 29/12/2023 | 15 | JASODA ENTERPRISE | 0.83 | 0.83 | 100 | 100
2450 | PURBA MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16929 | Solarisation | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | 1308/W/MMD | 15/05/2023 | 90 | SONSOLITE INFRA AND POWER SOLUTION PVT. LTD. | 133.28 | 107.72 | 80.82 | 80
2451 | PURBA MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16929 | Solarisation | Net-Metering Solar Power Plant quotation at Deriachak water supply scheme Zone-V, Tube Well-I Matangini CCC Block-Panskura-II Application No.-2004795860 Consumer ID.-202743884 Quotation Date.-26/06/2024 | BP-2024-25-532 | 07/08/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2452 | PURBA MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16929 | Solarisation | Application fees for SOLAR POWER PLANT Of 10 KWp at T/W NO-I OF ALADARPUT W/S SCHEME under MMD,PHE,Dte. BLOCK- CONTAI-II WBSEDCL SUPPLY OFFICE: CONTAI C.C.C Ref. Memo No- 2004884469/APP_RECT/01 DT. 03-09-2024 APPLICATION NO: 2004884469 Consumer Id- 200883228 |  | 06/11/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2453 | PURBA MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16929 | Solarisation | Application fees for SOLAR POWER PLANT Of 10 KWp at T/W NO-I OF UTTAR KHASDA W/S SCHEME under MMD,PHE,Dte. BLOCK- CONTAI-I WBSEDCL SUPPLY OFFICE: CONTAI C.C.C Ref. Memo No- 2004790808/APP_RECT/01 DT. 24-06-2024 APPLICATION NO: 2004790808 Consumer Id- 201090792 | BP-2024-25-531 | 07/08/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2454 | PURBA MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16929 | Solarisation | Application fees for SOLAR POWER PLANT Of 10.05 KWp at T/W NO-I OF BATHUARI W/S SCHEME under MMD,PHE,Dte. BLOCK- EGRA-II WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C Ref. Memo No- 2004765511/APP_RECT/01 DT. 06-06-2024 APPLICATION NO: 2004765511 Consumer Id- 200643580 | BP-2024-25-534 | 07/08/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2455 | PURBA MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16929 | Solarisation | Application fees for SOLAR POWER PLANT Of 10.05 KWp at T/W NO-I, ZONE- I OF BARANALGERIA W/S SCHEME under MMD,PHE,Dte. BLOCK- EGRA-II WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C Ref. Memo No- 2004765495/APP_RECT/01 DT. 06-06-2024 APPLICATION NO: 2004765495 Consumer Id- 203193703 | BP-2024-25-530 | 07/08/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2456 | PURBA MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16929 | Solarisation | Application fees for SOLAR POWER PLANT Of 10.05 KWp at T/W NO-I OF DULALPUR W/S SCHEME under MMD,PHE,Dte. BLOCK- EGRA-II WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C Ref. Memo No- 2004765507/APP_RECT/01 DT. 06-06-2024 APPLICATION NO: 2004765507 Consumer Id- 202969561 | BP-2024-25-535 | 07/08/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2457 | PURBA MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16929 | Solarisation | Application for SOLAR POWER PLANT Of 10.05 KWp at T/W NO-I, ZONE- II OF BARANALGERIA W/S SCHEME under MMD,PHE,Dte. BLOCK- EGRA-II WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C Ref. Memo No- 2004765528/APP_RECT/01 DT. 06-06-2024 APPLICATION NO: 2004765528 Consumer Id- 203543000 | BP-2024-25-533 | 07/08/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2458 | PURBA MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16929 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 1.76 | 88.45 | 100
2459 | PURBA MEDINIPUR | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE , SM/16929 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 1.76 | 90.91 | 50
2460 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Anurai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16879 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
2461 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Anurai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16879 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2462 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Sonachura PWSS in the District of Purba Medinipur under JJM programme. , SM/16657 | Augmentation | Rejuvenation of Electro-Mechanical components of Sonachura PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 767/W/MMD | 23/03/2023 | 1 | M/S SWAPAN BANERJEE | 12.24 | 0 | 0 | 0
2463 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Rajarampur PWSS in the District of Purba Medinipur under JJM programme. , SM/16659 | Augmentation | Rejuvenation of Electro-Mechanical components of Rajarampur PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 772/W/MMD | 23/03/2023 | 180 | SOUMEN ELECTRIC | 12.65 | 10.53 | 83.21 | 82
2464 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Bhagabanpur, Zone-I PWSS in the District of Purba Medinipur under JJM programme. , SM/16661 | Augmentation | Rejuvenation of Electro-Mechanical components of Bhagabanpur, Zone-I PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 761/W/MMD | 23/03/2023 | 180 | SOUMEN ELECTRIC | 12.22 | 9.89 | 80.93 | 60
2465 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Madhabpur (Balighai) PWSS in the District of Purba Medinipur under JJM programme. , SM/16664 | Augmentation | Rejuvenation of Electro-Mechanical components of Madhabpur (Balighai) PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 760/W/MMD | 23/03/2023 | 180 | RAJIB COMPANY | 12.24 | 7.15 | 58.4 | 35
2466 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Silampur PWSS in the District of Purba Medinipur under JJM programme. , SM/16665 | Augmentation | Rejuvenation of Electro-Mechanical components of Silampur PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 771/W/MMD | 23/03/2023 | 180 | MENAKA ENTERPRISE | 12.66 | 6.77 | 53.46 | 30
2467 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Baharchandberya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16891 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
2468 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Baharchandberya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16891 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2469 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Amtalia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16858 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
2470 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Amtalia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16858 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2471 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bargodagoda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16893 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
2472 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bargodagoda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16893 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2473 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Anantapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16897 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2474 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Basudebberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17379 | Solarisation | Solarization of grid connected pumping installation at Basudebberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 721/W/MMD | 23/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 0 | 0 | 0
2475 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Purba Bakulda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17863 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2476 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kanktya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17870 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2477 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kulbari PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17879 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
2478 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kulbari PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17879 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2479 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Keshabpur Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17884 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
2480 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Keshabpur Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17884 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2481 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Natshallakhya, Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17757 | Solarisation | Solarization of grid connected pumping installation at Natshallakhya, Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1016/W/MMD | 29/03/2023 | 705 | MEGA SOLAR ENERGY | 6.26 | 0 | 0 | 0
2482 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Mohisda, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17762 | Solarisation | Solarization of grid connected pumping installation at Mohisda, Zone-I and Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1048/W/MMD | 29/03/2023 | 180 | JYOTY SOLAR POWER | 12.52 | 4.85 | 38.74 | 50
2483 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Paramanandapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17886 | IOT | Supply and installation of Sign Board for depicting the scheme details of different on going Design development works for the purpose of Geotagging at different PWSS under Moyna block under MMD, P.H.E. Dte.in the Dist. of Purba Medinipur. | 625/HESD | 08/07/2024 | 7 | S.S.GHORAI | 0.9 | 0 | 0 | 0
2484 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Paramanandapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17886 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2485 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Haldia (Ramnagar)PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17770 | Solarisation | Solarization of grid connected pumping installation at Haldia (Ramnagar)PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1035/W/MMD | 29/03/2023 | 180 | DURJA ENTERPRISE | 6.26 | 0 | 0 | 0
2486 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Haldia (Ramnagar)PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17770 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0.18 | 94.81 | 100
2487 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Moyna, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17782 | Solarisation | Solarization of grid connected pumping installation at Moyna, Zone-I and Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1045/W/MMD | 29/03/2023 | 180 | AMITAVA CHAKRABORTY | 12.52 | 0 | 0 | 0
2488 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Mandar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17788 | Solarisation | Solarization of grid connected pumping installation at Mandar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | 1043/W/MMD | 29/03/2023 | 180 | RSA ENTERPRISE | 6.26 | 0 | 0 | 0
2489 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Mandar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17788 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0.18 | 94.81 | 100
2490 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Dwariberia PWSS in the District of Purba Medinipur under JJM programme. , SM/16652 | Augmentation | Rejuvenation of Electro-Mechanical components of Dwariberia PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 757/W/MMD | 23/03/2023 | 180 | M/S SWAPAN BANERJEE | 11.35 | 0 | 0 | 0
2491 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chatra (Sahid Matangini) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17387 | Solarisation | Solarization of grid connected pumping installation at Chatra (Sahid Matangini) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 743/W/MMD | 23/03/2023 | 180 | SUBHASIS ROY | 6.26 | 0 | 0 | 0
2492 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Haipur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17865 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
2493 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Haipur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17865 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2494 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bhagabanpur, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17364 | Solarisation | Solarization of grid connected pumping installation at Bhagabanpur, Zone-I and Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 750/W/MMD | 23/03/2023 | 180 | RSA ENTERPRISE | 12.52 | 0 | 0 | 0
2495 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Baghaput PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17852 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
2496 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Baghaput PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17852 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2497 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Simulia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17748 | Solarisation | Solarization of grid connected pumping installation at Simulia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1039/W/MMD | 29/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 6.26 | 4.88 | 78.03 | 40
2498 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dariapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17827 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
2499 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dariapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17827 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2500 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Habichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17829 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
2501 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Habichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17829 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2502 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dhenkua PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17317 | Solarisation | Solarization of grid connected pumping installation at Dhenkua PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 747/W/MMD | 23/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 6.26 | 0 | 0 | 0
2503 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Tamalda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17919 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
2504 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Tamalda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17919 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2505 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Sapai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17921 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
2506 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Sapai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17921 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2507 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Paya (Mahapravhu) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17855 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
2508 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Paya (Mahapravhu) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17855 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2509 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Rangibasan PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17832 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
2510 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Rangibasan PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17832 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2511 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dakshin chak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17308 | Solarisation | Solarization of grid connected pumping installation at Dakshin chak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 731/W/MMD | 23/03/2023 | 711 | MEGA SOLAR ENERGY | 6.26 | 0 | 0 | 0
2512 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Gholpukuria, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17722 | Solarisation | Solarization of grid connected pumping installation at Gholpukuria, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1047/W/MMD | 29/03/2023 | 180 | S.S.GHORAI | 12.51 | 4.85 | 38.74 | 50
2513 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chapbasan PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17378 | Solarisation | Solarization of grid connected pumping installation at Chapbasan PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 749/W/MMD | 23/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 6.26 | 0 | 0 | 0
2514 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dakshin chak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17842 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
2515 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dakshin chak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17842 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2516 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Gobindanagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17862 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2517 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kanakpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17814 | Solarisation | Solarization of grid connected pumping installation at Kanakpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1033/W/MMD | 29/03/2023 | 180 | PRANAB KUMAR DAS | 6.26 | 0 | 0 | 0
2518 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Astichak (Zone-II) PWSS , SM/15035 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Astichak Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | 1471/TD | 03/01/2022 | 20 | APEX ENGINEERING | 4.75 | 4.75 | 100 | 100
2519 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Astichak (Zone-II) PWSS , SM/15035 | Augmentation | Material Requisition To Resource Division | 2079/TD | 28/08/2023 | 0 | Resource Division | 49.99 | 0 | 0 | 0
2520 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Astichak (Zone-II) PWSS , SM/15035 | Augmentation | Material Requisition To Resource Division | 3007/TD | 29/11/2023 | 0 | Resource Division | 13.53 | 0 | 0 | 0
2521 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Astichak (Zone-II) PWSS , SM/15035 | Augmentation | Quotation Bill for New Service connection at T/W NO-III Of ASTICHAK ZII W/S Scheme under MMD, PHE, Dte. Block- EGRA II, WBSEDCL SUPPLY OFFICE: BALIGHAIC.C.C. Ref. Memo No- 2004749715/QUOT/03 DT. 05-06-2024 Application NO- 2004749715 Application type-New connection Consumer Id- 204317619 | BP-2024-25-299 | 18/06/2024 | 0 | WBSEDCL | 5.53 | 0 | 0 | 0
2522 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Astichak (Zone-II) PWSS , SM/15035 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Astichak (Zone-II) PWSS Egra II Block under JJM Program under MMD PHE Dte. | 890/W/MMD | 27/03/2023 | 857 | M/S B.M. ELECTRICAL | 23.7 | 15.94 | 67.25 | 40
2523 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Astichak (Zone-II) PWSS , SM/15035 | Augmentation | Proposed Rising main and interconnection with OHR of ASTICHAK (Z-II ) & its adjoining moujas Water Supply Scheme within Egra-II Dev. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | 3326/TD | 27/12/2023 | 699 | ONKAR ENTERPRISE | 515.99 | 401.82 | 77.87 | 98
2524 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Astichak (Zone-II) PWSS , SM/15035 | Augmentation | Drum sheet piling work, Canal Crossing Structure for Distribution pipe line, Supply and delivery of different dia D.I. specials, Repairing & renovation of OHR (350 CUM), Repairing & renovation of existing H/W site Pump House & 2nd TW site Pump house with allied works under JJM for Augmentation of Astichak Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 852/TD | 19/03/2025 | 40 | ONKAR ENTERPRISE | 78.51 | 0 | 0 | 0
2525 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Astichak (Zone-II) PWSS , SM/15035 | Augmentation | Supply delivery & laying of 25sq mm AL. armored cable at Pump House No-I of Astichak Zone-II water supply scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | 586/HESD | 19/06/2025 | 7 | SOUMEN ELECTRIC | 0.19 | 0 | 0 | 0
2526 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Astichak (Zone-II) PWSS , SM/15035 | Augmentation | Making of Tube Well Foundation & others at Pump House no. III & IV of Astichak, Zone-II piped water supply scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | 603/HESD | 19/06/2025 | 7 | M/S B.M. ELECTRICAL | 0.57 | 0 | 0 | 0
2527 | PURBA MEDINIPUR | Tamluk Division | KANTHI BARI AND ADJOINING MOUJAS PWSS , SM/12289 | New | Material Requisition To Resource Division | 2977/TD | 27/02/2023 | 0 | Resource Division | 33.32 | 0 | 0 | 0
2528 | PURBA MEDINIPUR | Midnapore Mechanical | KANTHI BARI AND ADJOINING MOUJAS PWSS , SM/12289 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KANTHI BARI and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2358/W/MMD | 31/12/2022 | 180 | WEST BENGAL ENGINEERING CO. | 22.78 | 0 | 0 | 0
2529 | PURBA MEDINIPUR | Tamluk Division | KANTHI BARI AND ADJOINING MOUJAS PWSS , SM/12289 | New | Material Requisition To Resource Division | 2962/TD | 12/09/2024 | 0 | Resource Division | 7.86 | 0 | 0 | 0
2530 | PURBA MEDINIPUR | Tamluk Division | KANTHI BARI AND ADJOINING MOUJAS PWSS , SM/12289 | New | Quotation bill for Kanthi Bari Water supply scheme PH-II, new service connection (Central Drilling) Khejuri CCC Block- Khejuri-I Quotation Bill Date. -02-05-2024 Application no.-2004711606 Reference ID.-204294517 | BP-2024-25-169 | 10/06/2024 | 0 | WBSEDCL | 10.12 | 0 | 0 | 0
2531 | PURBA MEDINIPUR | Midnapore Mechanical | KANTHI BARI AND ADJOINING MOUJAS PWSS , SM/12289 | New | Quotation bill for Kanthi Bari Water supply scheme PH-I, new service connection (Central Drilling) Khejuri CCC Block- Khejuri-I Quotation Bill Date. -02-05-2024 Application no.-2004711599 Reference ID.-204294533 | BP-2024-25-161 | 15/05/2024 | 0 | WBSEDCL | 15.76 | 0 | 0 | 0
2532 | PURBA MEDINIPUR | Central Drilling | KANTHI BARI AND ADJOINING MOUJAS PWSS , SM/12289 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 29.37 | 67.78 | 11
2533 | PURBA MEDINIPUR | Tamluk Division | KANTHI BARI AND ADJOINING MOUJAS PWSS , SM/12289 | New | Tube well, Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert,CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (1582 nos) under JJM with allied work for Kanthi Bari & its adjoining moujas PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1516/TD | 17/07/2023 | 807 | TAPAS SANTRA | 565.57 | 349.77 | 61.84 | 70
2534 | PURBA MEDINIPUR | Tamluk Division | PURBA MUKUNDAPUR AND ADJOINING MOUJAS PWSS , SM/12507 | New | Material Requisition To Resource Division | 2405/TD | 16/01/2023 | 0 | Resource Division | 20.41 | 0 | 0 | 0
2535 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA MUKUNDAPUR AND ADJOINING MOUJAS PWSS , SM/12507 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA MUKUNDAPUR and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2420/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 22.8 | 14.3 | 62.73 | 51
2536 | PURBA MEDINIPUR | Tamluk Division | PURBA MUKUNDAPUR AND ADJOINING MOUJAS PWSS , SM/12507 | New | Material Requisition To Resource Division | 2974/TD | 12/09/2024 | 0 | Resource Division | 10.48 | 0 | 0 | 0
2537 | PURBA MEDINIPUR | Tamluk Division | PURBA MUKUNDAPUR AND ADJOINING MOUJAS PWSS , SM/12507 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House ,Boundary Wall & Providing Functional Household Tap Connection (3734 Nos), including 2 years Operation & Maintenance For Purba Mukundapur, Dakshin Kadua, Purba Mahammadpur Pipe water supply Scheme within Deshapran Block Under Tamluk Division PHE Dte. | 1593/TD | 21/07/2023 | 711 | JAYANTA KUMAR MONDAL | 1264.74 | 102.22 | 20.93 | 30
2538 | PURBA MEDINIPUR | Midnapore Mechanical | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS , SM/14749 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAHISHAGOT AND IT'S ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 601/W/MMD | 20/03/2023 | 180 | SHAKEEL KHAN | 11.98 | 0 | 0 | 0
2539 | PURBA MEDINIPUR | Tamluk Division | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS , SM/14749 | New | Material Requisition To Resource Division | 2408/TD | 16/01/2023 | 0 | Resource Division | 13.74 | 0 | 0 | 0
2540 | PURBA MEDINIPUR | Tamluk Division | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS , SM/14749 | New | Material Requisition To Resource Division | 2966/TD | 12/09/2024 | 0 | Resource Division | 2.62 | 0 | 0 | 0
2541 | PURBA MEDINIPUR | Tamluk Division | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS , SM/14749 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | 1674/TD | 25/07/2023 | 860 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 0 | 0 | 30
2542 | PURBA MEDINIPUR | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Basudevpur PWSS under Egra II Block (Phase-II) , SM/09055 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Basudevpur ( Phase-II ) PWSS Block-Egra-II in the District Purba Medinipur. | 1013/TD | 02/11/2021 | 30 | SNEHESH SEN | 69.11 | 67.16 | 97.18 | 100
2543 | PURBA MEDINIPUR | Tamluk Division | GOBRADAN & ADJOINING MOUZAS , SM/12161 | New | Material Requisition To Resource Division | 2426/TD | 16/01/2023 | 0 | Resource Division | 21.84 | 0 | 0 | 0
2544 | PURBA MEDINIPUR | Tamluk Division | GOBRADAN & ADJOINING MOUZAS , SM/12161 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Gobradan PWSS at Moyna Block under Tamluk Division,PHE Dte. | 196/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
2545 | PURBA MEDINIPUR | Tamluk Division | GOBRADAN & ADJOINING MOUZAS , SM/12161 | New | Material Requisition To Resource Division | 1563/TD | 23/04/2024 | 0 | Resource Division | 8.75 | 0 | 0 | 0
2546 | PURBA MEDINIPUR | Midnapore Mechanical | GOBRADAN & ADJOINING MOUZAS , SM/12161 | New | Quotation for new service connection at Gobradan w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No. 2004631559, Ref ID 204237227) | BP-2023-24-905 | 28/03/2024 | 0 | WBSEDCL | 9.24 | 0 | 0 | 0
2547 | PURBA MEDINIPUR | Midnapore Mechanical | GOBRADAN & ADJOINING MOUZAS , SM/12161 | New | Quotation for new service connection at Gobradan w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No 2004631550, 204237224) | BP-2024-25-16 | 08/04/2024 | 0 | WBSEDCL | 10.25 | 0 | 0 | 0
2548 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Uttar Dalhara, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/18912 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
2549 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Route survey and all releated field works for preparation and submission of zone wise Geo tagged reference drawing with desinged pipe network system at Chandipur Development Block and Nandakumar Development Block within Purba Medinipur District Under Tamluk Division, PHE Dte. | 844/TD | 31/05/2023 | 40 | ENVIROTECH SOLUTIONS | 85.01 | 68.61 | 80.71 | 100
2550 | PURBA MEDINIPUR | Midnapore Mechanical | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipment's at Newly sunk Tube well within NANDAKUMAR block, District - PURBA Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 3174/W/MMD | 18/12/2023 | 180 | SOUMEN ELECTRIC | 96.15 | 55.59 | 57.81 | 20
2551 | PURBA MEDINIPUR | Midnapore Mechanical | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Electro-Mechanical works for Nandakumar GLR Boosting Station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | 92/W/MMD | 24/01/2024 | 540 | ORIENTAL ENGINEERING CO. | 1405.35 | 0 | 0 | 20
2552 | PURBA MEDINIPUR | Midnapore Mechanical | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Electro-mechanical works for Nandakumar and Chandipur WTP SITE under Midnapore Mechanical Division, PHE Dte. under JJM in Purba Medinipur District. | 42/W/MMD | 10/01/2024 | 733 | MACHINE SUPPLIERS SYNDICATE (P) LTD | 734.46 | 0 | 0 | 10
2553 | PURBA MEDINIPUR | Midnapore Mechanical | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | 11/0.433 KV, 1600 KVA Electrical Substation allied Electrical works at Chandipur GLR Boosting station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | 41/W/MMD | 10/01/2024 | 540 | THE MARKET ELECTRICAL ENGINEERING WORKS | 532.18 | 97.17 | 18.26 | 20
2554 | PURBA MEDINIPUR | Midnapore Mechanical | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | 11/0.433 KV, 1600 KVA Electrical Substation with allied Electrical works at Nandakumar GLR Boosting station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | 44/W/MMD | 10/01/2024 | 540 | APEX ENGINEERING & PROJECT CO | 533.06 | 115.61 | 21.69 | 20
2555 | PURBA MEDINIPUR | Midnapore Mechanical | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Electro-Mechanical works for Chandipur GLR Boosting Station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | 43/W/MMD | 10/01/2024 | 528 | WEST BENGAL ENGINEERING CO. | 1578.72 | 0 | 0 | 20
2556 | PURBA MEDINIPUR | Midnapore Mechanical | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well within CHANDIPUR block, District - PURBA Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 903/W/MMD | 21/02/2024 | 180 | DEBJYOTI BASU | 192.31 | 102.72 | 53.41 | 20
2557 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Design & Construction of GSLR (4900 Cum) at Nandakumar Block & GSLR (3800 Cum ) at Chandipur Block including High lift Pump House, Chlorine room, Store room, Sub Station Building, Administrative Building, Guard Room, Staff quarter and other allied Structures and Construction of Zonal Overhead Reservior (27 Nos) including Soil Investigation of Different Capacity along with CW Rising Main ,Laying of Distribution Pipeline and FHTC (51946 Nos) including sinking of Big Dia Tube Wells and its connections and other allied works as per direction of EIC including 1 years Operation and Maintenance after successful Trail Run(180 Days) for Surface water based Water supply scheme for Nandakumar Block and Chandipur Block under Tamluk Division PHE Dte. | 2707/TD | 23/08/2024 | 465 | R SANDESH INFRACONTRACTS PRIVATE LIMITED | 16926.01 | 313.53 | 1.85 | 15
2558 | PURBA MEDINIPUR | Midnapore Mechanical | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
2559 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XII (Kulup) at Chandipur Block under Tamluk Division, PHE Dte. | 668/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 0 | 100
2560 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Zone-XIII (Sultanpur) at Chandipur Block under Tamluk Division, PHE Dte. | 672/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 0 | 100
2561 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-VIII (Atattar) at Chandipur Block under Tamluk Division, PHE Dte. | 669/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 0 | 100
2562 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-IX (Baroj) at Chandipur Block under Tamluk Division, PHE Dte. | 671/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 0 | 100
2563 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-V (Narandanri) at Chandipur Block under Tamluk Division, PHE Dte. | 670/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 0 | 100
2564 | PURBA MEDINIPUR | Midnapore Mechanical | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Hiring Vehicle for Site inspection of Nandakumar Chnadipur Surface based Project and Pingla Panskura Surface based Project under Midnapore Mechanical Division , P.H.E.Dte (Vehical No. WB-31A-3738) | 781//WMMD | 24/02/2025 | 365 | SUDIP KUMAR ROY | 7.78 | 0 | 0 | 70
2565 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XV (Usmanpur) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2138/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 100
2566 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Zone-XXIII (Jalpai Part - II) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2144/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 100
2567 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-II (Bhagaban Khali) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2132/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 100
2568 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XIV (Barabanki) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2137/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 0
2569 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Installation of display Board (20 nos) at different work site for P.H.E. Dept. Land within Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (Part-D) | 2437/TD | 18/09/2025 | 14 | GLOBAL TRADE | 3.33 | 0 | 0 | 100
2570 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-III (Jaukti Basan) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2133/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 0
2571 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-IV (Barneturia) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2134/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 0
2572 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Installation of display Board at different work( ZONE-XI,XXII) site of Chandipur Block, under Tamluk Division, PHE Dte. Purba Medinipur District.(PHASE-IV) | 2362/TD | 10/09/2025 | 10 | TECHNO ENTERPRISE. | 0.42 | 0 | 0 | 100
2573 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XVI (Rasik Chak) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2139/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 0
2574 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Installation of display Board (20 nos) at different work site for P.H.E. Dept. Land within Nandakumar Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (Part-C) | 2438/TD | 18/09/2025 | 14 | GLOBAL TRADE | 3.33 | 0 | 0 | 100
2575 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Dismantling of existing damaged godown staff quarter, Guard room and Go-Down at Jalpai PWSS under Tamluk Sub Division of Tamluk Division PHE Dte. | 2149/TD | 18/08/2025 | 30 | ENGINEERS CONSULTANT (INDIA) | 3.37 | 0 | 0 | 0
2576 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XX (Dibakarpur) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2141/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 0
2577 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-XXI (Baraghuni) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2142/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 100
2578 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XVII (Kulbari) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2140/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 0
2579 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Repair of existing brick bats roads after laying of 600 mm dia DI-K9 pipe from Banbhera to Calcutta public school under Nandakumar Surface based water supply scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | 3700/TSD | 21/11/2025 | 15 | PRASANTA MONDAL | 0.94 | 0 | 0 | 100
2580 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XXII (Khagda) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2143/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 0
2581 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-VI (Balibar) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2135/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 100
2582 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XI (Bamunara) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | 2136/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0 | 100
2583 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Laying UPVC pipe line 90 ( OD ) for left out portion at village Bhandarberia Jalpai under Jalpai PWSS Tamluk Sub-Division of Tamluk Division PHE Dte. | 2148/TD | 18/08/2025 | 30 | FARID UDDIN AHMED | 4.18 | 0 | 0 | 0
2584 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Installation of display Board at different work site of Chandipur Block, under Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-II) | 2360/TD | 10/09/2025 | 10 | TECHNO ENTERPRISE. | 0.83 | 0 | 0 | 100
2585 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Installation of display Board (20 nos) at different work site for P.H.E. Dept. Land within Sahid Matangini & Nandakumar Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (Part-B) | 2439/TD | 18/09/2025 | 14 | GLOBAL TRADE | 3.33 | 0 | 0 | 100
2586 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Installation of display Board at different work site of Chandipur Block, under Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE- I) | 2359/TD | 10/09/2025 | 10 | TECHNO ENTERPRISE. | 0.83 | 0 | 0 | 100
2587 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Repair of existing brick bats roads after laying of 600 mm dia DI-K9 pipe from Calcutta public school to Griha Lakshmi Brick Field under Nandakumar Surface based water supply scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | 3699/TSD | 21/11/2025 | 15 | PRASANTA MONDAL | 0.94 | 0 | 0 | 100
2588 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Installation of display Board (29 nos) at different work site within Sahid Matangini Block for P.H.E. Dept. Land under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(Part-A) | 2440/TD | 18/09/2025 | 14 | GLOBAL TRADE | 4.83 | 0 | 0 | 100
2589 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur , SM/18402 | New | Installation of display Board at different work site of Chandipur Block, under Tamluk Division, PHE Dte. Purba Medinipur District .(PHASE-III) | 2361/TD | 10/09/2025 | 10 | TECHNO ENTERPRISE. | 0.83 | 0 | 0 | 100
2590 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 2 Water Supply Scheme , SM/07120 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - II W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. | 825/W | 02/03/2021 | 0 | SWADHIN KUMAR CHAKRABORTY | 35.94 | 0 | 0 | 0
2591 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 2 Water Supply Scheme , SM/07120 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - II W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-77 | 17/09/2021 | 0 | SWADHIN KUMAR CHAKRABORTY | 6.78 | 0 | 0 | 0
2592 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 2 Water Supply Scheme , SM/07120 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - II W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. | 245/W | 13/09/2021 | 0 | SWADHIN KUMAR CHAKRABORTY | 9 | 0 | 0 | 0
2593 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 2 Water Supply Scheme , SM/07120 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - II W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. | 933/W | 18/03/2021 | 0 | SWADHIN KUMAR CHAKRABORTY | 24.96 | 0 | 0 | 0
2594 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 2 Water Supply Scheme , SM/07120 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Gholepukuria PWSS(Zone-II) Block -Nandigram-II in the District of Purba Medinipur. | 2635/TD | 05/01/2021 | 60 | SWADHIN KUMAR CHAKRABORTY | 76.69 | 0 | 0 | 100
2595 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme , SM/06887 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Habichak PWSS Block Chandipur in the District of Purba Medinipur. | 2112/TD | 05/11/2020 | 180 | TAPAS SANTRA | 96.73 | 0 | 0 | 100
2596 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme , SM/06887 | Retrofitting | Retrofitting to accomodate FHTC under JJM Habichak W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 142/W | 22/07/2021 | 0 | TAPAS SANTRA | 1.52 | 0 | 0 | 0
2597 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme , SM/06887 | Retrofitting | Retrofitting to accomodate FHTC under JJM Habichak W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 638/W | 14/01/2021 | 0 | TAPAS SANTRA | 48.82 | 0 | 0 | 0
2598 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme , SM/06887 | Retrofitting | Retrofitting to accomodate FHTC under JJM Habichak W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. | 698/W | 02/02/2021 | 0 | TAPAS SANTRA | 46.39 | 0 | 0 | 0
2599 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme , SM/06887 | Retrofitting | Left out portion for laying distribution system of pipe line and its allied works for Habichak & its adjoining mouzas Water Supply Scheme at Chandipur Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. Purba Medinipur. | 790/TD | 28/09/2021 | 20 | TAPAS SANTRA | 6.59 | 0 | 0 | 0
2600 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Jagatpur W/S Scheme , SM/06892 | Retrofitting | Retrofitting to accomodate FHTC under JJM Jagatpur W/S Scheme within Panskura - I Dev. Block under Tamluk Division, PHE Dte. | 711/W | 09/02/2021 | 0 | ARUP KUMAR DEY | 74.34 | 0 | 0 | 0
2601 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Jagatpur W/S Scheme , SM/06892 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Jagatpur PWSS Block Panskura-I in the District of Purba Medinipur. | 2111/TD | 05/11/2020 | 180 | ARUP KUMAR DEY | 88.18 | 12.62 | 100 | 100
2602 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mandarmani Piped Water Supply Scheme , SM/07107 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Mandarmani PWSS Block - Ramnagar-II in the District of Purba Medinipur. | 2688/TD | 20/01/2021 | 60 | UNIQUE AGENCY | 60.84 | 60.84 | 99.99 | 100
2603 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kudi Piped Water Supply Scheme , SM/07110 | Retrofitting | Retrofitting to accomodate FHTC under JJM Kudi W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. | 983/W | 25/03/2021 | 0 | MONDAL PRECISION PRIVATE LIMITED | 37.11 | 0 | 0 | 0
2604 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kudi Piped Water Supply Scheme , SM/07110 | Retrofitting | Retrofitting to accomodate FHTC under JJM Kudi W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. | 246/W | 14/09/2021 | 0 | MONDAL PRECISION PRIVATE LIMITED | 10.18 | 0 | 0 | 0
2605 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kudi Piped Water Supply Scheme , SM/07110 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kudi PWSS Block-Egra-I in the District of Purba Medinipur. | 2667/TD | 14/01/2021 | 60 | MONDAL PRECISION PRIVATE LIMITED | 70.47 | 0 | 0 | 75
2606 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kudi Piped Water Supply Scheme , SM/07110 | Retrofitting | Laying (Left Out) UPVC pipe line to accommodate FHTC under JJM in Kudi PWSS within Egra-I Block (to support phase-1 FHTC) under Digha Sub-Division of Tamluk Division, PHE Dte. (Mouza- Naraharipur, Usma, Kudi) | 76/TD | 08/04/2022 | 25 | MONDAL PRECISION PRIVATE LIMITED | 16.72 | 0 | 0 | 0
2607 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Argoal W/S Scheme under Potashpur-II Block , SM/07652 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Argoal PWSS Block -Potashpur-II in the District of Purba Medinipur. | 2803/TD | 04/02/2021 | 45 | DAS ENTERPRISE | 125.99 | 38.39 | 100 | 100
2608 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Argoal W/S Scheme under Potashpur-II Block , SM/07652 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Argoal Piped Water Supply Scheme | 1091/W | 30/03/2021 | 0 | DAS ENTERPRISE | 40.02 | 0 | 0 | 0
2609 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Argoal W/S Scheme under Potashpur-II Block , SM/07652 | Retrofitting | Retrofitting to accomodate FHTC under JJM Argoal W/S Scheme within Potashpur - I Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-79 | 17/09/2021 | 0 | DAS ENTERPRISE | 47.57 | 0 | 0 | 0
2610 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Argoal W/S Scheme under Potashpur-II Block , SM/07652 | Retrofitting | Retrofitting to accomodate FHTC under JJM Argoal W/S Scheme within Potashpur - I Dev. Block under Tamluk Division, PHE Dte. |  | 06/09/2021 | 0 | DAS ENTERPRISE | 47.57 | 0 | 0 | 0
2611 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN SILAMPUR PWSS UNDER CONTAI - I BLOCK PHASE II , SM/08748 | Retrofitting | Retrofitting to accomodate FHTC (700 nos.) under JJM IN Silampur PWSS under CONTAI-I BLOCK of Contai Sub-Division under Tamluk Division, PHE Dte. (PHASE-II) | 686/TD | 10/09/2021 | 30 | BASANTA KUMAR MAITY | 58.45 | 48.98 | 83.79 | 90
2612 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN SILAMPUR PWSS UNDER CONTAI - I BLOCK PHASE II , SM/08748 | Retrofitting | Re-laying of 140 mm dia UPVC pipe line due to Construction of Drain under Dulalpur GP at Silampur Mouza of Silampur W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 877 / CSD | 22/11/2022 | 21 | JASODA ENTERPRISE | 0.84 | 0.84 | 100 | 100
2613 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN SILAMPUR PWSS UNDER CONTAI - I BLOCK PHASE II , SM/08748 | Retrofitting | Re-laying of 125 mm dia UPVC & 100 mm dia DI (K-7) pipe line due to Construction of Drain under Dulalpur GP at Silampur Mouza of Silampur W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 885 / CSD | 23/11/2022 | 21 | PAL ENTERPRISE. | 0.82 | 0.81 | 100 | 100
2614 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN SILAMPUR PWSS UNDER CONTAI - I BLOCK PHASE II , SM/08748 | Retrofitting | Laying of different dia UPVC pipe line to accommodate 86 nos FHTC to make Betgerya,Eryafetepur, Khalisabhanga,, Betbani, Paryadwip, Silampur, Sitalpur & Sujulpur Mouza as Swajal Gram of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2094 /TD | 13/12/2022 | 20 | ROY & ROY CONSTRUCTION. | 5.73 | 5.63 | 100 | 100
2615 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haipur W/S Scheme under Contai-I , SM/08223 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Haipur PWSS Block- Contai-I in the District of Purba Medinipur.(Phase-II) | 2997/TD | 25/02/2021 | 60 | SRIMANTA KUMAR MAITY | 197.96 | 119.39 | 100 | 100
2616 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haipur W/S Scheme under Contai-I , SM/08223 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Haipur PWSS Block Contai - I in the district of Purba Medinipur under Tamluk Division, PHE Dte. | BP-2021-22-132 | 18/10/2021 | 0 | SRIMANTA KUMAR MAITY | 78.57 | 0 | 0 | 0
2617 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haipur W/S Scheme under Contai-I , SM/08223 | Retrofitting | Repair and Renovation of Pump House with Sanitary and water supply arrangement and others allied works for Head works & 2nd Tube well site at Haipur Water Supply Scheme in Contai-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 3336/TD | 22/10/2024 | 30 | SUBHRANGSHU SEKHAR GIRI | 3.06 | 0 | 0 | 0
2618 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Ranisai W/S Scheme (Phase - II) , SM/08228 | Retrofitting | Retrofitting to accommodate FHTC 310 Nos. under JJM in Ranisai PWSS Block Ramnagar - I in the district of Purba Medinipur under Tamluk Division, PHE Dte.(Phase-II) |  | 04/10/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.68 | 0 | 0 | 0
2619 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Ranisai W/S Scheme (Phase - II) , SM/08228 | Retrofitting | Retrofitting to accommodate FHTC 310 Nos. under JJM in Ranisai PWSS Block Ramnagar - I in the district of Purba Medinipur under Tamluk Division, PHE Dte.(Phase-II) | BP-2021-22-136 | 18/10/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.68 | 0 | 0 | 0
2620 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Ranisai W/S Scheme (Phase - II) , SM/08228 | Retrofitting | Retrofitting to accommodate FHTC 310 Nos. under JJM at Santeswarpur J.L No-8(Part), Purushottampur J.L. No-11(Part), Kholaberia J.L. No-36(part), Ranisai J.L. No-40(Part) in Ranisai PWSS within Block - Ramnagar under Digha Sub-Division of Tamluk Division, P.H.E. Dte. in the District of Purba Medinipur. ( PHASE-II) | 2922/TD | 22/02/2021 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.9 | 0 | 0 | 100
2621 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Surface Water Based W/S Scheme for Zone I (Balance Work) Block Kolaghat in the district of Purba Medinipur under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-I) , SM/09050 | Retrofitting | Retrofitting to accomodate FHTC (1050 nos.) under JJM in Surface Water Based Water Supply Scheme for Zone-I (Balance work) Block- Kolaghat in the District of Purba Medinipur under Tamluk Sub Division of Tamluk Division,PHE Dte . (Phase-II) | 1008/TD | 02/11/2021 | 45 | M/S A.R. ENTERPRISE | 60.36 | 59.87 | 100 | 100
2622 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (446 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-II) | 1770/TD | 08/02/2022 | 40 | SHAKEEL KHAN | 53.9 | 17.85 | 33.12 | 55
2623 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bar Basudevpur Water Supply Scheme under Tamluk Division, PHE Dte. | 1198/TD | 02/12/2021 | 20 | RADIANT | 4.28 | 4.21 | 100 | 100
2624 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 270 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BARBASUDEVPUR W/S SCH (REPLACEMENT TW-II), SUTAHATA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 108/CDD | 12/04/2022 | 30 | MENAKA ENTERPRISE | 18.28 | 17.82 | 100 | 100
2625 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | PROVIDING DRILLING CREW AND ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 270 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BARBASUDEVPUR W/S SCH (REPLACEMENT TW-I), SUTAHATA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 107/CDD | 12/04/2022 | 30 | MENAKA ENTERPRISE | 18.28 | 17.62 | 100 | 100
2626 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | ADDITIONAL DRILLING (DEPTH 270 MTR TO 320 MTR) AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL FOR BARBASUDEVPUR W/S SCHEME (REPLACEMENT TW-II), IN HALDIA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 402/CMSD-II | 01/08/2022 | 15 | MENAKA ENTERPRISE | 3.17 | 2.01 | 100 | 100
2627 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | ADDITIONAL DRILLING (DEPTH 270 MTR TO 320 MTR) AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL FOR BARBASUDEVPUR W/S SCH (REPLACEMENT TW-I), IN HALDIA BLOCK UNDER PURRBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 154/S&WSD | 12/08/2022 | 15 | MENAKA ENTERPRISE | 3.17 | 2.07 | 100 | 100
2628 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (346 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-IV) | 1772/TD | 08/02/2022 | 30 | FARID UDDIN AHMED | 47.43 | 43.13 | 90.95 | 80
2629 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Additional Laying Distribution System of 200 mm dia upvc pipe line and Cannel Crossing by G.I. pipes with cement concrete and M.S. structure on 110 mm dia(sec 2-14) and 180 mm dia(sec-20-23) of pipe line of Barbasudevpur Water Supply Scheme of Haldia Sub-Division under Tamluk Division P.H.E. Dte. | 1147/TD | 31/08/2022 | 20 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.88 | 24.11 | 96.89 | 100
2630 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well II under Barbasudebpur water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2119/W/MMD | 28/11/2022 | 120 | M/S B.M. ELECTRICAL | 11.26 | 10.32 | 91.65 | 100
2631 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Laying of additional 90mm dia. distribution pipe line and cannel crossing by M.S. structure for 140mm dia. distribution pipe laying of Barbasudevpur Water Supply Scheme of Haldia Sub-Division under Tamluk Division P.H.E. Dte. (Phase - II) | 2348/TD | 10/01/2023 | 20 | MAA KALI CONSTRUCTION | 13.75 | 13.66 | 99.35 | 0
2632 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | 362/W/MMD | 09/03/2023 | 180 | SHIVAM ENTERPRISE | 12.63 | 11.88 | 94.06 | 0
2633 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE EXECUTIVE ENGINEER, CDD, PHE DTE. | 217/S&WSD | 23/11/2022 | 30 | SUMAN KUMAR DEY | 0.89 | 0.35 | 39.2 | 100
2634 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (346 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part- III) | 1771/TD | 08/02/2022 | 30 | MAA KALI CONSTRUCTION | 47.34 | 46.29 | 100 | 100
2635 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room at Head work & 2nd tube well site respectively of Barbasudevpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1383/TD | 23/09/2022 | 45 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 4.13 | 3.88 | 100 | 100
2636 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES AND OTHERS WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMODGHATA W/S SCH, TW-II, HOOGHLY DISTRICT,UNDER CDD. PHE DTE. | 379/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 3.44 | 2.56 | 100 | 0
2637 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments for Augumentation of ground water based Barbasudebpur PWSS to accommodate FHTC in Haldia block under Haldia Sub Division of Tamluk Division in purba medinipur district under JJM program under MMD PHE Dte. | 623/HESD | 17/08/2023 | 15 | SHIVAM ENTERPRISE | 3.5 | 3.24 | 100 | 75
2638 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Material Requisition To Resource Division | 1300/TD | 20/12/2021 | 0 | Resource Division | 19.51 | 0 | 0 | 0
2639 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Material Requisition To Resource Division | 1834/TD | 15/02/2022 | 0 | Resource Division | 9.79 | 0 | 0 | 0
2640 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Fuel Charges for the month of January 2023 | BP-2022-23-353 | 09/03/2023 | 0 | MIRA SERVICE STATION | 0.2 | 0 | 0 | 0
2641 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | FUEL CHARGE MONTH OF FEBRUARY 2023 | BP-2022-23-387 | 29/03/2023 | 0 | MIRA SERVICE STATION | 0.2 | 0 | 0 | 0
2642 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Fuel Charges bill | BP-2022-23-326 | 06/02/2023 | 0 | MIRA SERVICE STATION | 0.46 | 0 | 0 | 0
2643 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Laying of proposed Rising main line and inter connection at Barbasudevpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 802/TD | 30/05/2023 | 20 | PULAK KUMAR SAMANTA | 6.22 | 4.72 | 100 | 100
2644 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Installation of 4 Nos. Display Board at different PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte. (for Barbasudevpur PWSS, Lakshya PWSS, Chaitanyapur Zone-II PWSS, Manoharpur PWSS) (Phase-VI) | 767/HSD | 27/02/2024 | 7 | SNEHASIS BERA | 0.83 | 0.83 | 100 | 100
2645 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (646 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-I) | 1769/TD | 08/02/2022 | 680 | ZENITH CONSTRUCTION | 84.54 | 50.24 | 59.43 | 75
2646 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09336 | Augmentation | Construction of R.C.C. Elevated Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Barbasudebpur Water Supply Scheme,with in Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. (Part-E) | 1886/TD | 24/11/2022 | 828 | MAA ANANDAMAYEE | 104.61 | 74.3 | 78.5 | 96
2647 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. , SM/10072 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baghaput Water Supply Scheme under Tamluk Division, PHE Dte. | 1548/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.62 | 3.26 | 100 | 100
2648 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. , SM/10072 | Augmentation | Repair and Renovation of 136 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir for Augmentation of Baghaput Water Supply Scheme within Contai-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 2563/TD | 24/01/2023 | 60 | NARAYAN CHANDRA DAS | 11.29 | 7.54 | 66.83 | 0
2649 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. , SM/10072 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Baghaput Water Supply Scheme in Contai II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | 1928/TD | 28/11/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 5.35 | 5.35 | 100 | 100
2650 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. , SM/10072 | Augmentation | Material Requisition To Resource Division | 406/TD | 25/05/2022 | 0 | Resource Division | 22.79 | 0 | 0 | 0
2651 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. , SM/10072 | Augmentation | Material Requisition To Resource Division | 1269/TD | 12/09/2022 | 0 | Resource Division | 11.27 | 0 | 0 | 0
2652 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. , SM/10072 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput in Purba Medinipur District under JJM Program under MMD PHE Dte. | 1225/W/MMD | 25/04/2023 | 180 | M/S. JIT ENTERPRISE | 26.93 | 0 | 0 | 0
2653 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. , SM/10072 | Augmentation | Repairing Of Boundary Wall of Head Work site and Pump House No - II under Augmentation of Baghaput Water Supply Scheme within Deshpran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 493/TD | 10/05/2023 | 30 | SUBHENDU HAZRA | 3.73 | 0 | 0 | 0
2654 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. , SM/10072 | Augmentation | Repair And renovation Of Pump House No. I & II under Augmentation of Baghaput Water Supply Scheme within Deshpran( Contai- II) Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | 421/CSD | 17/03/2023 | 30 | THE GODFATHER TRADING COMPANY | 2.24 | 1.23 | 100 | 100
2655 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. , SM/10072 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 200 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Baghaput Water Supply Scheme within Deshpran ( Contai- II)Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 813/TD | 12/07/2022 | 1147 | G. B. CONSTRUCTION & CO. | 378.59 | 267.34 | 70.61 | 70
2656 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE EXECUTIVE ENGINEER, CDD, PHE DTE. | 77/S&WSD | 27/05/2022 | 7 | SUMAN KUMAR DEY | 0.9 | 0.15 | 16.39 | 67
2657 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | LOADING UNLOADING & SHIFTING DRILLING ACCESSORIES, SUPPORTING VEHICLES ALONG WITH RIG MACHINE JOHN/DR/1500-I FROM DURMUT PWSS, BLOCK-CONTAI-III, PURBA MEDINIPUR DISTRICT TO PANCHLA STORE, HOWRAH UNDER CDD, PHE DTE. | 371/CMSD-I | 04/08/2022 | 7 | M/S B.P.TRADING CORPORATION | 0.47 | 0 | 0 | 100
2658 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Durmut Water Supply Scheme under Tamluk Division, PHE Dte. | 1612/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.09 | 3.09 | 100 | 100
2659 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | CONSTRUCTION OF TUBE WELL (300 MM X 200 MM X DEPTH 250 MTR) FOR DURMUT W/S SCHEME (REPLACEMENT TW-II), CONTAI-III BLOCK WITHIN PURBA MEDINIPUR DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | 410/CDD | 20/05/2022 | 30 | M/S B.P.TRADING CORPORATION | 14.69 | 5.56 | 100 | 100
2660 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | CONSTRUCTION OF TUBE WELL (300MM X 200MM X DEPTH 250 MTR) FOR DURMUT W/S SCHEME (TW-III), DESHPRAN BLOCK WITHIN PURBA MEDINIPUR DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | 411/CDD | 20/05/2022 | 30 | ASHUTOSH DAS & CO | 14.67 | 5.36 | 100 | 100
2661 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES AT SITE FOR CONSTRUCTION OF TUBE WELL WITHIN CONTAI-III BLOCK, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | 227/CMSD-I (D) | 20/06/2022 | 15 | M/S B.P.TRADING CORPORATION | 5 | 1.63 | 53.36 | 100
2662 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | SUPPLY & DELIVERY OF BATS AT SITE FOR MAKING APPROACH ROAD FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT DURMUT PWSS CONTAI-III BLOCK, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | 296/CMSD-I | 08/07/2022 | 7 | M/S B.P.TRADING CORPORATION | 0.81 | 0.59 | 100 | 100
2663 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE WITHIN CONTAI-III BLOCK, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | 228/CMSD-I (D) | 20/06/2022 | 15 | M/S B.P.TRADING CORPORATION | 4.05 | 3.87 | 100 | 100
2664 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Car Oil Bill for the month of October 2022 | BP-2022-23-246 | 29/11/2022 | 0 | MIRA SERVICE STATION | 0.13 | 0 | 0 | 0
2665 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Payment for Railway Application Fees. for Durmut PWSS. |  | 01/08/2022 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 17.19 | 0 | 0 | 0
2666 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Charges for Way Leave Permission under railway track permission for Durmut PWSS under Tamluk Division, PHE Dte. | BP-2022-23-271 | 29/08/2022 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 3.15 | 0 | 0 | 0
2667 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER-IN-CHARGE, CMSD-II (D), CDD, PHE DTE. | 55/CMSD-II (D) | 31/01/2022 | 7 | ASHUTOSH PAL | 0.86 | 0.15 | 26.16 | 64
2668 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | PROVIDING TUBE WELL MATERIALS TO IS : 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. | 301/CMSD-I (D) | 08/07/2022 | 15 | CHANDA ENTERPRISE | 4.69 | 0 | 0 | 50
2669 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well No I under durmut water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2162/W/MMD | 08/12/2022 | 120 | DEBJYOTI BASU | 11.13 | 4.81 | 100 | 70
2670 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Loading unloading & Shifting of Drilling Accessories, Supporting Vehicles along with rig machine JOHN/DR/1500-I from Durmut PWSS, block Contai-III, Purba Medinipur dist. to Panchla store, Howrah under CDD PHE Dte. | 371/CMSD-I(D) | 04/08/2022 | 7 | M/S B.P.TRADING CORPORATION | 0.47 | 0.43 | 100 | 100
2671 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Supply & delivery of submersible pump motor set & other electromechanical accessories at P/H No-I, under DURMUT Water Supply Scheme under MMD , P.H.E. Dte. | 462/HESD | 13/06/2023 | 15 | DEBJYOTI BASU | 7.25 | 7.25 | 100 | 60
2672 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Material Requisition To Resource Division | 91/TD | 11/04/2022 | 0 | Resource Division | 210.65 | 0 | 0 | 0
2673 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Material Requisition To Resource Division | 1271/TD | 12/09/2022 | 0 | Resource Division | 23.95 | 0 | 0 | 0
2674 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Jack Pushing of Railway Track in between Station Nachinda and Kanthi of Augmentation of Durmuth Piped Water Supply Scheme of 600 mm dia MS Casing Pipe and 150 mm dia MS Carrier Pipe in between Mast NO 54/9 TO Mast NO 54/8 With in Contai Sub Division under Tamluk Division P.H.E DTE. (TOTAL LENGTH =45 M) Section 482 TO 486. | 1744/TD | 01/08/2023 | 30 | ROY CONSTRUCTION | 72.22 | 46 | 63.69 | 64
2675 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Jack Pushing of Railway Track in between Station Nachinda and Kanthi of Augmentation of Durmuth Piped Water Supply Scheme of 600 mm dia MS Casing Pipe and 100 mm dia MS Carrier Pipe in between Mast NO 55/17 TO Mast NO 55/16 With in Contai Sub Division under Tamluk Division P.H.E DTE. (TOTAL LENGTH =127M) Section 209 TO 231. | 1745/TD | 01/08/2023 | 30 | ROY CONSTRUCTION | 75.01 | 51.79 | 69.04 | 71
2676 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Hade work site for Durmuth Water Supply Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 248/TD | 11/01/2024 | 450 | ANIRBAN MONDAL | 11.93 | 0 | 0 | 100
2677 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Construction of Pump House , Tube well , Boundary Wall, Rising main for Durmuth PWSS in Deshpran & Contai III Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 559/TD | 15/02/2024 | 40 | DEVEN ENTERPRISES | 33.8 | 0 | 0 | 0
2678 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | 2209/TD | 01/09/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 4.26 | 100 | 100
2679 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Augmentation of Durmut Water Supply Scheme for Supply and Delivery of Different dia Sluice Valves under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | 3133/TD | 07/12/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.6 | 3.6 | 100 | 100
2680 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Augmentation of Durmut Water Supply Scheme for Supply and Delivery of Different dia Sluice Valves under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | 3134/TD | 07/12/2023 | 20 | ABHIJIT BERA | 3.85 | 3.85 | 100 | 100
2681 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Tube Well (2nd Tube Well) site for Durmuth Water Supply Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 249/TD | 11/01/2024 | 30 | BISWA NIRMAN ENTERPRISE. | 5.73 | 5.7 | 100 | 100
2682 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Continuation Work Order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Augmentation Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | 2566/TD | 06/10/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 6.11 | 100 | 100
2683 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Repairing and Renovation of pump house 1 and boundary wall in Durmuth water supply scheme in Contai-II and Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 240/CSD | 07/02/2024 | 45 | BISWA NIRMAN ENTERPRISE. | 0.71 | 0.69 | 100 | 100
2684 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Durmut Water Supply Scheme within Despran & Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 394/TD | 23/05/2022 | 991 | MAHAVIR PUMPS MFG. PVT. LTD. | 430.39 | 344.05 | 79.94 | 81
2685 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut , SM/10323 | Augmentation | Repairing and Renovation of over head reservoir in Durmuth Water Supply Scheme in Contai-II and Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 3771/TD | 10/12/2024 | 294 | BISWA NIRMAN ENTERPRISE. | 7.05 | 0 | 0 | 100
2686 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Paschim Kamarda (Phase-II) PWSS under Contai-III Block. , SM/10345 | Retrofitting | Retrofitting to accomodate FHTC under JJM in PASCHIM KAMARDA PWSS ( Phase- II) Block - Contai-III in the District of Purba Medinipur. | 2005/TD | 08/03/2022 | 25 | RAJ KUMAR SINGHA | 39.32 | 0 | 0 | 100
2687 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Paschim Kamarda (Phase-II) PWSS under Contai-III Block. , SM/10345 | Retrofitting | Supply & Delivery of different dia Sluice Valves for Paschim Kamarda Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Phase-II) | 889 / CSD | 23/03/2022 | 15 | PARTHA CONSTRUCTION | 1.3 | 1.3 | 100 | 100
2688 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Paschim Kamarda (Phase-II) PWSS under Contai-III Block. , SM/10345 | Retrofitting | Repairing of inlet, outlet, washout pipe and allied works of 180 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir for PASHIM KAMARDA W/S Scheme in Contai- III Block Of Purba Medinipur District under Contai Sub Division within Tamluk division, PHE Dte. | 394 / CSD | 12/07/2022 | 30 | GIRI CONSTRUCTION | 2.26 | 2.22 | 100 | 100
2689 | PURBA MEDINIPUR | Tamluk Division | Balance work for Retrofitting to Accommodate FHTC (862 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-II, Bl , SM/10436 | Retrofitting | Balance work for Retrofitting to accommodate FHTC (620 nos.) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-II, Block- Kolaghat in the District of Purba Medinipur. (Phase-III)[PART-B] | 615/TD | 21/06/2022 | 25 | MAA ANANDAMAYEE | 65.39 | 65.43 | 100 | 100
2690 | PURBA MEDINIPUR | Tamluk Division | Balance work for Retrofitting to Accommodate FHTC (862 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-II, Bl , SM/10436 | Retrofitting | Balance work for Retrofitting to accommodate FHTC (345 nos) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-II, Block- Kolaghat in the District of Purba Medinipur. (Phase-III)[PART-A] | 614/TD | 21/06/2022 | 20 | ARABINDA GHOSH | 30.95 | 30.93 | 100 | 100
2691 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through trolley mounted PVC tank to different places under Contai-I Block in connection with YAAS for mitigation of Drinking Water crisis under Contai Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District . ( For the period from 01.06.2021 to 21.06.2021 i.e. 21 Days. Total - 8000 litre. | 82 / CSD | 01/06/2021 | 21 | JASODA ENTERPRISE | 1.53 | 1.53 | 100 | 0
2692 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through trolley mounted PVC tank to different places under Khejuri-II Block in connection with YAAS for mitigation of Drinking Water crisis under Contai Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District . ( For the period from 27.05.2021 to 24.06.2021 i.e. 29 Days. Total - 9000 litre. | 77 / CSD | 27/05/2021 | 29 | GIRI CONSTRUCTION | 2.27 | 2.27 | 100 | 0
2693 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. ( Part B ) Period from 30.05.21.to 31.05.21 Village - Soula, Habitation - Ramkrishna Misson, G.P - Kalindi | 83/DSD | 27/05/2021 | 2 | SNEHESH SEN | 0.87 | 0.87 | 100 | 0
2694 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. (From 28/05/21 to14/07/21) Gobindabasan (Padima-II G.P.) | .84/A/DSD | 27/05/2021 | 48 | CHARUBALA ENTERPRISE | 2.43 | 0 | 0 | 100
2695 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 64 days. (From 27/05/21 to 29/07/21) Tangramari-Maity Para , Ghorai Para(Talgachhari-II G.P.) | 29/Camp/TD | 27/05/2021 | 64 | LOKENATH ENTERPRISES | 4.77 | 4.77 | 100 | 100
2696 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 38 days. (From 27/05/21 to 03/07/21) Biswanathpur- Ghorai Para, Giri Para(Talgachhari-I G.P.) | 31/Camp/TD | 27/05/2021 | 38 | CHARUBALA ENTERPRISE | 3.82 | 3.81 | 100 | 100
2697 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. Period From 29.05.21 to 04.06.21 Village - Mandermoni, Habitation- Sun City Hotel comp, G.P- Kalindi. & Village - Saula, Habitation - Jana Para, G.P- Kalindi. | 83/A/DSD | 27/05/2021 | 7 | SOM CONSTRUCTION | 1.43 | 1.43 | 100 | 0
2698 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. ( Part B ) Village - Dadanpatrabar, Habitation - Patra Para, Sau Para under kalindi GP, Village - Purba Purusattampur, Habitation - Das Para, Patra Para under Kalindi GP, Village - Dakshin Purusattampur, Habitation - Nayek Para, Maity Para, under Kalindi GP. | 21/Camp/TD | 27/05/2021 | 48 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.22 | 3.22 | 100 | 0
2699 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. Village - Alampur (Balisai GP), Village - Dublabari (Talgachhari - II GP) for the period of 58 days. (From 27/05/21 to 23/07/21). | 23/Camp/TD | 27/05/2021 | 58 | ANUPAM CONSTRUCTION | 4.35 | 4.33 | 100 | 100
2700 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. ( Part A ) Village - karanjee, Habitation - Giri Para, Patra Para, Sau Para under Balisai GP, Village - Mandarmoni, Habitation - Near Police Camp, Sun City under Kalindi GP. | 22/Camp/TD | 27/05/2021 | 48 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.82 | 4.82 | 100 | 0
2701 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. Tajpur(Talgachhari-II G.P.) | 24/Camp/TD | 27/05/2021 | 48 | DHANANJOY DAS | 3.9 | 3.9 | 100 | 100
2702 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. Chandpur(Talgachhari-II G.P.) & Jaldah(Talgachhari-II G.P.) For the Period of 49 days. (From 27/05/21 to14/07/21) | 25/Camp/TD | 27/05/2021 | 49 | DHANANJOY DAS | 4.84 | 4.84 | 100 | 100
2703 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 49 days. (From 27/05/21 to14/07/21) Kshirpal(Talgachhari-II G.P.) & Bherichauli(Talgachhari-II G.P.) | 27/Camp/TD | 27/05/2021 | 49 | SNEHESH SEN | 4.84 | 4.84 | 100 | 100
2704 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 49 days. (From 27/05/21 to14/07/21) Jamra Shyampur- Kar Para(Talgachhari-II G.P.) & Dolboldia-Bamun Para, Das Para(Talgachhari-II G.P.) | 37/Camp/TD | 27/05/2021 | 48 | MAITY CONSTRUCTION | 4.84 | 4.84 | 100 | 100
2705 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 63 days. (From 27/05/21 to28/07/21) .Kaima(Talgachhari-II G.P.) | 28/Camp/TD | 27/05/2021 | 63 | LOKENATH ENTERPRISES | 3.14 | 3.14 | 100 | 100
2706 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-II Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District.( Part A ) Village - Saula, Habitation - Aila Center, Jana para, Mandal para, G.P - Kalindi & Village - Arakbonia, Habitation - Patra para, Sau Para, G.P - Kalindi Period From 29.05.21 to 16.07.21 | 40/Camp/TD | 27/05/2021 | 49 | SOM CONSTRUCTION | 4.09 | 4.06 | 100 | 0
2707 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-II Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District.( Part B ) Village - Saula, Habitation - Ramkrishna Mission G.P - Kalindi, Village - Andaman, Habitation - Bar Para, Das Para, G.P - Kalindi & Village - Sonamoy, Habitation - Mandal Para, Maity Para, G.P - Kalindi Period From 29.05.21 to 16.07.21 | 41/Camp/TD | 27/05/2021 | 49 | SOM CONSTRUCTION | 4.09 | 4.06 | 100 | 0
2708 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 65 days. (From 27/05/21 to 30/07/21) Bodhra(Talgachhari-II G.P.) | 30/Camp/TD | 27/05/2021 | 64 | LOKENATH ENTERPRISES | 4.22 | 4.22 | 100 | 100
2709 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 64 days. (From 27/05/21 to 29/07/21) Biswanathpur- Das Para, Mitra Para(Talgachhari-I G.P.) | 32/Camp/TD | 27/05/2021 | 64 | CHARUBALA ENTERPRISE | 4.77 | 4.77 | 100 | 100
2710 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 48 days. (From 27/05/21 to13/07/21) Biswanathpur- Chanda Para, Mondal Para(Talgachhari-I G.P.) | 33/Camp/TD | 27/05/2021 | 48 | BASANTA KUMAR MAITY | 4.75 | 4.75 | 100 | 100
2711 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 49 days. (From 28/05/21 to15/07/21) Jashipur- Patrapara, Das Para, Nayak Para(Talgachhari-II G.P.) | 35/Camp/TD | 27/05/2021 | 48 | MAITY CONSTRUCTION | 4.84 | 4.84 | 100 | 100
2712 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 49 days. (From 27/05/21 to 14/07/21) Panchdoria(Talgachhari-II G.P.) & Sankarpur(Talgachhari-II G.P.) | 36/Camp/TD | 27/05/2021 | 48 | MAITY CONSTRUCTION | 4.84 | 4.84 | 100 | 100
2713 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 54 (Fifty Four) days. (From 27/05/21 to 21/07/21) Jamra Shyampur-Jana Para,Bar Para,Bamun Par(Talgachhari-II G.P.) | 38/Camp/TD | 27/05/2021 | 54 | DAS ENTERPRISE. | 4.21 | 4.07 | 100 | 100
2714 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Work Order for Supply of safe Drinking water through trolley mounted PVC tank to Bhekutia Gram Panchayat at 5th part Jalpai location under Nandigram-I Block in connection with YASS for mitigation of Drinking water crisis under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. (for the period from 02.06.2021 to 30.06.2021 i.e. 29 Days) | 99/B/HSD | 01/06/2021 | 29 | RAJ KUMAR SINGHA | 0.84 | 0.84 | 100 | 0
2715 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 49 days. (From 28/05/21 to15/07/21) | 26/Camp/TD | 27/05/2021 | 49 | SNEHESH SEN | 4.84 | 4.84 | 100 | 100
2716 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 54 (Fifty Four) days. (From 27/05/21 to 21/07/21) Jamra Shyampur-Bera Para,Khatua Para(Talgachhari-II G.P.) & Jamra Shyampur-Saupara(Talgachhari-II G.P.) | 39/Camp/TD | 27/05/2021 | 54 | DAS ENTERPRISE. | 4.84 | 4.84 | 100 | 100
2717 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 61 days. (From 26/05/21 to 25/07/21) Aila Center(Talgachhari-II G.P.) | 84/DSD | 27/05/2021 | 61 | KAMAL KUMAR ROY | 1.52 | 1.51 | 100 | 100
2718 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. ( Part A ) | 356/TD | 16/07/2021 | 14 | MAITY CONSTRUCTION | 4.54 | 4.54 | 100 | 100
2719 | PURBA MEDINIPUR | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- , SM/08985 | Disaster | Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. ( Part B ) | 357/TD | 16/07/2021 | 14 | BASANTA KUMAR MAITY | 4.54 | 4.54 | 100 | 100
2720 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme under Tamluk Division, PHE Dte. | 1179/TD | 02/12/2021 | 20 | HORIZEN | 9.54 | 9.54 | 100 | 100
2721 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Gopalpur Water Supply Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 130/TD | 19/04/2022 | 21 | SIMPLEX DRILLING COMPANY | 19.03 | 18.87 | 100 | 100
2722 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Gopalpur Water Supply Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 131/TD | 19/04/2022 | 21 | SIMPLEX DRILLING COMPANY | 19.03 | 19.03 | 100 | 100
2723 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Electric quotation bill at Mahishadal CCC for T/W-II Gopalpur water supply scheme under MMD PHE Dte | 2003987573/QUOT/03 | 11/07/2022 | 365 | WBSEDCL | 0.7 | 0 | 0 | 0
2724 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Electric quotation bill at Mahishadal CCC for T/W-II Gopalpur water supply scheme under MMD PHE Dte | BP-2022-23-26 | 10/08/2022 | 0 | WBSEDCL | 0.7 | 0 | 0 | 0
2725 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Electric quotation MAHISHADAL CCC at Gopalpur, Manashathan Water supply scheme under MMD PHE Dte | BP-2022-23-61 | 23/11/2022 | 0 | WBSEDCL | 0.5 | 0 | 0 | 0
2726 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room at Head work & 2nd tube well site respectively of Gopalpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1152/TD | 31/08/2022 | 45 | RAI CONSTRUCTION | 4.12 | 4.09 | 99.27 | 0
2727 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with Water Supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well site of Gopalpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 1227/TD | 07/09/2022 | 60 | M/S SOURAV MAHAPATRA | 4.84 | 4.42 | 100 | 100
2728 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well No IV under Gopalpur water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2123/W/MMD | 28/11/2022 | 120 | MANORANJAN DEY | 13.12 | 12.89 | 100 | 75
2729 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | New Construction of boundary wall at 3rd T/W site (50mt) of Gopalpur Water Supply Scheme under Haldia Sub-Division PHE Dte.. | 2352/TD | 10/01/2023 | 45 | M/S SOURAV MAHAPATRA | 6.48 | 5.01 | 100 | 0
2730 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well site of Gopalpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 2353/TD | 10/01/2023 | 60 | GUCHHAIT ENTERPRISE | 4.63 | 3.67 | 100 | 100
2731 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Material Requisition To Resource Division | 1674/TD | 03/11/2022 | 0 | Resource Division | 96.09 | 0 | 0 | 0
2732 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Material Requisition To Resource Division | 1373/TD | 23/09/2022 | 0 | Resource Division | 37.63 | 0 | 0 | 0
2733 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Laying Distribution System of Leftout portion, Providing Functional Household Tap Connection (FHTC) and construction of new Boundary wall at Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 980/TD | 13/03/2024 | 456 | RAJ KUMAR SINGHA | 128.78 | 51.24 | 39.79 | 30
2734 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Continuation work order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2023 to 31/12/2023. (12 Months) | 815/HSD | 29/12/2022 | 365 | SANTANU PATTANAYAK | 1.5 | 4.58 | 100 | 100
2735 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well No III under Gopalpur water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2122/W/MMD | 28/11/2022 | 120 | SOUMEN ELECTRIC | 13.1 | 0.55 | 4.23 | 100
2736 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Boundery wall including land development at 4th tube well site of Gopalpur Pwss under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | 1492/TD | 17/07/2023 | 30 | GUCHHAIT ENTERPRISE | 8.53 | 4.69 | 100 | 100
2737 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Cannel crossing, Road crossing and Drum sheet pilling of Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 1470/TD | 13/07/2023 | 40 | RAJ KUMAR SINGHA | 71.38 | 68.31 | 100 | 60
2738 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. , SM/10030 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 900 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Ground Water Based Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 832/TD | 15/07/2022 | 1082 | RAJ KUMAR SINGHA | 838.35 | 739.61 | 88.22 | 62
2739 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dhanghara Water Supply Scheme under Tamluk Division, PHE Dte. | 1171/TD | 01/12/2021 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM | 10.76 | 10.07 | 100 | 100
2740 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Supply and Delivery of Different dia Sluice Valves for Dhanghara Water Supply Scheme in the District of Purba Medinipur. | 105 / CSD | 19/01/2023 | 15 | BIBEKANANDA DAS | 0.95 | 0 | 0 | 0
2741 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Supply and Delivery of Different dia Sluice Valves for Dhanghara Water Supply Scheme in the District of Purba Medinipur. | 439 / CSD | 20/03/2023 | 15 | SAURAV HAZRA | 0.95 | 0.95 | 100 | 0
2742 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | RESISTIVITY SURVEY AND OTHER WORKS OF DHANGHARA W/S SCHEME (TW-III), CONTAI-III BLOCK UNDER PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | 1538/CDD | 08/12/2022 | 30 | MENAKA ENTERPRISE | 12.67 | 9.71 | 76.69 | 0
2743 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | CONSTRUCTION OF TUBE WELL (300MM X 200MM X DEPTH 250 MTR) FOR DHANGHARA W/S SCHEME (TW-III), CONTAI-III BLOCK WITHIN PURBA MEDINIPUR DISTRICT BY UTILISING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | 413/CDD | 20/05/2022 | 30 | KARTICK BAL | 14.67 | 5.44 | 37.07 | 0
2744 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Supply & Delivery 80 mm dia Sluice Valve for Dhanghara W/S Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Phase-I) (Supply at Mukutshila Store) | 1298/TD | 13/09/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.9 | 3.9 | 100 | 100
2745 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Construction of TW (300m x 200mm x 250mtr. depth) for Dhanghara WS Scheme (Rep TW-I), Contai-III Block within purba Medinipurr Dist. by utilising skilled Departmental crew and Departmental machineries of CDD, PHE Dte. | 412/CDD | 20/05/2022 | 30 | KARTICK BAL | 14.67 | 5.45 | 100 | 100
2746 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 204/W/MMD | 10/02/2023 | 180 | M/S SREEJIT ENTERPRISE | 13.52 | 13.29 | 100 | 55
2747 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | RESISTIVITY SURVEY AND OTHER WORKS OF Dhanghara W/S SCH (TW-I), PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | 1537/CDD | 08/12/2022 | 30 | MENAKA ENTERPRISE | 12.67 | 9.5 | 100 | 100
2748 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Material Requisition To Resource Division | 1250/TD | 13/12/2021 | 0 | Resource Division | 10.79 | 0 | 0 | 0
2749 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Material Requisition To Resource Division | 1952/TD | 04/03/2022 | 0 | Resource Division | 18.66 | 0 | 0 | 0
2750 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Electric Quotation for DHANGHARA Water Supply Scheme T/W-III, (Ref. ID-204049566) | BP-2023-24-165 | 04/08/2023 | 0 | WBSEDCL | 1.35 | 0 | 0 | 0
2751 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Augmentation of Dhanghara Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block Of Purba Medinipur District. | 1947/TD | 03/03/2022 | 150 | M/S S. S. ENTERPRISE | 547.65 | 468.64 | 100 | 90
2752 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Rising main 150mm dia DI(K9) Rising main pipeline with specials and other allied works at 3rd Tube Well Site for Augmentation of Dhanghara W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1498/TD | 17/07/2023 | 622 | SUDIP MANNA | 5.27 | 2.03 | 38.48 | 100
2753 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at DHANYAGARAHA Water supply scheme, contai - III block, District -Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 2338/W/MMD | 16/12/2024 | 180 | P.K.ENGINEERING | 24.97 | 0 | 0 | 65
2754 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara , SM/09288 | Augmentation | Re-laying of Distribution pipeline, Repairing of OHR, Pump House no 1, Pump House No. 2 and Head Works Boundary Wall under JJM with allied work of Dhanghara PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 667/TD | 03/03/2025 | 40 | SRIMANTA KUMAR MAITY | 23.42 | 0 | 0 | 0
2755 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chaitanyapur (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | 1662/TD | 21/01/2022 | 20 | RADIANT | 4.13 | 4.13 | 100 | 100
2756 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (82 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-M) | 737/TD | 04/07/2022 | 15 | MAHAPRABHU ENTERPRISE | 10.01 | 9.87 | 98.65 | 100
2757 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (500 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-E) | 729/TD | 04/07/2022 | 25 | ZENITH CONSTRUCTION | 80.53 | 78.32 | 97.25 | 100
2758 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Work: Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (400 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part- F) | 730/TD | 04/07/2022 | 20 | SK. NUR ISLAM | 49.38 | 39.62 | 80.24 | 85
2759 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (840 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | 727/TD | 04/07/2022 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 70.64 | 64.02 | 90.64 | 95
2760 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (115 nos) work within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-O) | 739/TD | 04/07/2022 | 15 | CANVAS | 9.54 | 4.82 | 50.58 | 55
2761 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (350 nos)work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-H) | 732/TD | 04/07/2022 | 20 | SK MAIDUL ISLAM | 40.03 | 32.28 | 80.63 | 85
2762 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 4th Tube Well site of Chaitanyapur Zone-I Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2345/TD | 10/01/2023 | 40 | TAPAN BERA | 5.08 | 5.06 | 99.58 | 100
2763 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (50 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-C) | 715/TD | 28/06/2022 | 20 | SANTANU PATTANAYAK | 4.27 | 4.21 | 100 | 100
2764 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Chaitanyapur Zone -I Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1564/TD | 12/10/2022 | 45 | SAYAN MAITY | 3.95 | 3.93 | 100 | 0
2765 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Installation of display Board of 8 nos work site within different PWSS under Haldia Sub-Division of Tamluk Division, PHE Dte. District Purba Medinipur. (Phase - 2) Name of Work site :- 1) Chaitanyapur Zone-I (Part-A) PWSS, 2) Chaitanyapur Zone-I (Part-B) PWSS, 3) Chaitanyapur Zone-I (Part-C) PWSS, 4) Chaitanyapur Zone-I (Part-D) PWSS, 5) Chaitanyapur Zone-I (Part-E) PWSS, 6) Chaitanyapur Zone-I (Part-F) PWSS, 7) Chaitanyapur Zone-I (Part-G) PWSS & 8) Chaitanyapur Zone-I (Part-H) PWSS | 724/HSD | 28/10/2022 | 3 | TAPAN BERA | 0.93 | 0.93 | 100 | 100
2766 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Installation of display Board of 8 nos work site within different PWSS under Haldia Sub-Division of Tamluk Division, PHE Dte. District Purba Medinipur. (Phase -3) Name of Work site :- 1) Chaitanyapur Zone-I (Part-I) PWSS, 2) Chaitanyapur Zone-I (Part-J) PWSS, 3) Chaitanyapur Zone-I (Part-K) PWSS, 4) Chaitanyapur Zone-I (Part-L) PWSS, 5) Chaitanyapur Zone-I (Part-M) PWSS, 6) Chaitanyapur Zone-I (Part-N) PWSS, 7) Chaitanyapur Zone-I (Part-O) PWSS & 8) Chaitanyapur Zone-I (Part-P) PWSS | 725/HSD | 28/10/2022 | 3 | TAPAN BERA | 0.93 | 0.93 | 100 | 100
2767 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Construction of Boundary Wall at 1st tube well site of Chaitanyapur Zone-I water supply scheme, under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Part-B) | 910/HSD | 23/02/2023 | 10 | MODERN CONSTRUCTION | 0.95 | 0.92 | 100 | 100
2768 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (110 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-P) | 740/TD | 04/07/2022 | 15 | TARUN KHATUA | 10.01 | 10 | 100 | 100
2769 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Material Requisition To Resource Division | 467/TD | 02/06/2022 | 0 | Resource Division | 10.8 | 0 | 0 | 0
2770 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Material Requisition To Resource Division | 466/W | 02/06/2022 | 0 | Resource Division | 40.61 | 0 | 0 | 0
2771 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Material Requisition To Resource Division | 468/W | 02/06/2022 | 0 | Resource Division | 30.41 | 0 | 0 | 0
2772 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Material Requisition To Resource Division | 829/TD | 15/07/2022 | 0 | Resource Division | 55.98 | 0 | 0 | 0
2773 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Electric Quotation for CHAITANYAPUR Water Supply Scheme T/W-IV, zone- I, (Ref. ID-204078116) | BP-2023-24-249 | 19/09/2023 | 0 | WBSEDCL | 10.52 | 0 | 0 | 0
2774 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (200 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-J) | 734/TD | 04/07/2022 | 1072 | TAPAN BERA | 20.46 | 18.17 | 88.83 | 100
2775 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (370 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | 731/TD | 04/07/2022 | 1101 | MAA KALI CONSTRUCTION | 39.79 | 35.78 | 89.91 | 75
2776 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (200 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-I) | 733/TD | 04/07/2022 | 15 | R CONSTRUCTION | 20.34 | 15.02 | 73.84 | 78
2777 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Construction of Boundary Wall at 1st tube well site of Chaitanyapur Zone-I water supply scheme, under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Part-A) | 909/HSD | 23/02/2023 | 10 | RAI CONSTRUCTION | 0.95 | 0.92 | 97.44 | 0
2778 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Canal crossing and supporting work with Drum Sheet walling and Earth filling in Chaitanyapur Zone-I Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte (PART - J). | 3209/TD | 14/03/2023 | 20 | TAPAN BERA | 8.74 | 8.72 | 99.69 | 100
2779 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Earth filling and Making approach road at OHR site at Chaitanyapur (Zone-I) Water Supply scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of approach road -45mtr) | 2208/TD | 01/09/2023 | 490 | BAGLAMUKHI SECURITY SERVICE | 8.55 | 0 | 0 | 0
2780 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (460 nos)work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-D) | 728/TD | 04/07/2022 | 25 | NARAYAN MANDAL | 80.94 | 77.3 | 100 | 100
2781 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (96 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-L) | 736/TD | 04/07/2022 | 15 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 10 | 9.57 | 100 | 100
2782 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head Work Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 2nd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-I Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1250/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 77.68 | 20.05 | 95.03 | 100
2783 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | 851/W/MMD | 24/03/2023 | 180 | ECO ENTERPRISE | 13.46 | 13.19 | 100 | 40
2784 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Canal Crossing and supporting work with Drum Sheet walling and Earth filling in Chaitanyapur Zone-I W/S Scheme under Haldia Sub-Division of Tamluk Division,PHE Dte. | 927/TD | 01/06/2023 | 30 | NARAYAN MANDAL | 7.82 | 5.07 | 100 | 100
2785 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Construction of Damaged bitumen road from PHE office to Rampur more at Chaitanyapur (zone-1) W/S scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of approach road -330mtr) | 2281/TD | 07/09/2023 | 20 | RAI CONSTRUCTION | 9.04 | 9.01 | 100 | 100
2786 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Construction of boundary wall, Retaining wall, Approach road & Earth filling Work in 4th tubewell site of Chaitanyapur Zone-I Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) , (length of Retaining wall-13mtr) & (length of Approach road-20mtr). | 2163/TD | 31/08/2023 | 30 | TAPAN BERA | 13.62 | 9.27 | 100 | 100
2787 | PURBA MEDINIPUR | Central Drilling | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 280 Mtrs. Depth) by utilizing Departmental Machineries for Chaitanyapur W/S Scheme (Z-I, T/W-IV), SutahataBlock underPurbaMedinipur District, Central Drilling Division, P.H.E. Dte. | 1390/CDD | 19/09/2023 | 255 | MENAKA ENTERPRISE | 21.16 | 20.24 | 100 | 100
2788 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Quotation bill for new service connection at Z-I of TW-III of Chaitanyapur w/s scheme,Block-Sutahata,under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695240 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-11900W | BP-2024-25-114 | 06/05/2024 | 0 | WBSEDCL | 7.14 | 0 | 0 | 0
2789 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (104 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-N) | 738/TD | 04/07/2022 | 1252 | MODERN CONSTRUCTION | 10 | 6.81 | 68.1 | 100
2790 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (850 nos) work and Construction of R.C.C. Over Head Reservoir of capacity 700 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | 1004/TD | 08/08/2022 | 1242 | HARIPADA PATTANAYAK | 212.75 | 87.96 | 41.34 | 80
2791 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (210 nos)work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-K) | 735/TD | 04/07/2022 | 887 | SUDIP MANNA | 20.03 | 18.82 | 93.96 | 95
2792 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well no - III at CHAITANYAPUR Zone-I Water supply scheme, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 2611/W/MMD | 19/09/2023 | 439 | THE GODFATHER TRADING COMPANY | 14.94 | 10.16 | 68 | 40
2793 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Laying left out pipe line and supporting work with Drum Sheet walling and Earth filling in Chaitanyapur (Zone-I) Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | 2448/TD | 20/09/2023 | 824 | S.D. CONSTRUCTION | 69.7 | 31.16 | 44.71 | 40
2794 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Laying Rising main work of ground water based Chaitanyapur (Zone-I) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2202/TD | 01/09/2023 | 20 | ELECTIVA ENTERPRISE | 6.04 | 1.1 | 18.21 | 40
2795 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Withdrawing & Lowering of defective submersible pumping machinery set at Zone-I, Pump House no. II of Chaitanyapur water supply scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | 525/HESD | 30/05/2025 | 7 | M/S B.M. ELECTRICAL | 0.09 | 0 | 0 | 0
2796 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Replacement of valves,re-new of rising line & others pumping arrangement works at Tube Well no. II, Zone-I of Chaitanyapur water supply scheme under Midnapore Mechanical Division PHE Dte. | 429/HESD | 23/04/2025 | 7 | S.B.ENTERPRISE | 0.42 | 0 | 0 | 0
2797 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10593 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Chaitanyapur Zone-I Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1563/TD | 12/10/2022 | 720 | KRISHNENDU SEKHAR DAS | 4.78 | 0 | 0 | 100
2798 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I , SM/12487 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Amarshikashba Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | 591/TD | 17/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 3.71 | 100 | 100
2799 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I , SM/12487 | Augmentation | Material Requisition To Resource Division | 1668/TD | 03/11/2022 | 0 | Resource Division | 90.44 | 0 | 0 | 0
2800 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I , SM/12487 | Augmentation | Material Requisition To Resource Division | 2644/TD | 13/10/2023 | 0 | Resource Division | 27.1 | 0 | 0 | 0
2801 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I , SM/12487 | Augmentation | Laying Rising main and other allied works Augmentation of Amarshikasba Zone-I Water Supply Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 400/TD | 27/04/2023 | 30 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 12.14 | 4.63 | 38.17 | 75
2802 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I , SM/12487 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at 2nd TW site for Amarshikasba Zone-I PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | 591/TD | 17/05/2023 | 40 | M/S SOURAV MAHAPATRA | 9.2 | 3.76 | 40.9 | 45
2803 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I , SM/12487 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 190 Mtrs. Depth) by utilising Departmental Machineries for Amarshi Kasba W/S Scheme (Zone-II,T/W-II) , Patashpur-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 2117/CDD | 02/03/2023 | 30 | MENAKA ENTERPRISE | 15.74 | 14.1 | 100 | 100
2804 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I , SM/12487 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE- I Of AMARSHI KASBA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004775131/QUOT/03 DT. 14-06-2024 Application NO- 2004775131 MEMO NO: AMR/PHE/175 DT.14/06/2024 Application type-New connection Consumer Id- 204330575 | BP-2024-25-361 | 01/07/2024 | 0 | WBSEDCL | 4.79 | 0 | 0 | 0
2805 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I , SM/12487 | Augmentation | Laying of distribution pipe line to accommodate FHTC (4400 Nos) with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Amarshikasba Zone-I Water Supply Scheme within Patashpur-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 2592/TD | 30/01/2023 | 761 | SANKHA ENTERPRISE | 567.28 | 198.8 | 35.04 | 70
2806 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I , SM/12487 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 805/W/MMD | 24/03/2023 | 880 | RITESH AGARWALL | 12.63 | 0 | 0 | 45
2807 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I , SM/12487 | Augmentation | Laying of Left-Out portion HDPE Pipe line of Distribution system by HDPE pipes with allied works of Amarshikasba Zone-I PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 3053/TD | 19/09/2024 | 180 | M/S. NEW DINDA ENTERPRISE | 48.21 | 0 | 0 | 5
2808 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I , SM/12487 | Augmentation | Repair and Renovation of Pump House & Boundary Wall and others allied works for 1st Tube well site at Amarshi Kasba Zone-I Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 3322/TD | 22/10/2024 | 30 | M/S. NEW DINDA ENTERPRISE | 2.76 | 0 | 0 | 0
2809 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I , SM/12487 | Augmentation | Construction of 3rd Pump House & Boundary wall of Amarshi Kasba Zone-I & its adjoining moujas PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 1716/TD | 30/06/2025 | 40 | GOUTAM DEY | 9.9 | 0 | 0 | 0
2810 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. , SM/11979 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshinchak Water Supply Scheme under Tamluk Division, PHE Dte. | 51/TD | 05/04/2022 | 20 | HORIZEN | 6.01 | 6 | 99.77 | 0
2811 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. , SM/11979 | Augmentation | Material Requisition To Resource Division | 2616/TD | 02/02/2023 | 0 | Resource Division | 349.36 | 0 | 0 | 0
2812 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. , SM/11979 | Augmentation | Material Requisition To Resource Division | 2641/TD | 02/02/2023 | 0 | Resource Division | 204.6 | 0 | 0 | 0
2813 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. , SM/11979 | Augmentation | Material Requisition To Resource Division | 2638/TD | 13/10/2023 | 0 | Resource Division | 43.18 | 0 | 0 | 0
2814 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. , SM/11979 | Augmentation | Crossing permission of laying HDPE pipeline along and across of NH-116 of Dakshinchak Zone-I Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3288/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 9.38 | 2.76 | 29.43 | 30
2815 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. , SM/11979 | Augmentation | Crossing permission of laying HDPE pipeline along and across of NH-116 of Dakshinchak Zone-II Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3287/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 10.9 | 2.76 | 25.34 | 30
2816 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. , SM/11979 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Zone- II of Tube well-I and II at Dakshin Chak Water supply scheme, Haldia block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 63/W/MMD | 15/01/2024 | 180 | SUJOY RANJAN BHOWMICK | 28.21 | 16.58 | 58.79 | 30
2817 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. , SM/11979 | Augmentation | Sinking of Tube well, Reparing & Renovation of 1st & 2nd Pump House, Construction of New 3rd Tube well site Pump House, Construction of 2 nos Pump House, Soil Investigation Test, Construction of Different Capacity OHR, Laying of Rising main, Laying of Distribution pipe line & FHTC(6512 Nos) works for Augmentation of Dakshinchak Zone- I and Dakshinchak Zone-II Water Supply Scheme under Haldia Sub-Division,of Tamluk Division, PHE Dte. Purba Medinipur. | 1411/TD | 12/07/2023 | 873 | M/S S. S. ENTERPRISE | 1432.04 | 320.92 | 22.41 | 6
2818 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. , SM/11979 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of T/W- III, Zone-I for Dakshin Chak Water Supply Scheme, Block - Haldia under JJM Program under MMD PHE Dte. | 1071/W/MMD | 14/03/2024 | 180 | DEBSANKER BHATTACHARYA | 13.59 | 0 | 0 | 0
2819 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. , SM/11979 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme, Block - Haldia under JJM Program under MMD PHE Dte. | 635/W/MMD | 20/03/2023 | 799 | P.K.ENGINEERING | 27.18 | 19.11 | 75.39 | 30
2820 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) , SM/12268 | Augmentation | Renovation work of Spiral stair and related works for R.C.C. Over Head Reservoir of capacity 60000 Gallons at Keshurkunda mouza within Contai S.A. Zone-II W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur.( 2nd Part) | 497 / CSD | 18/11/2021 | 21 | SRIMANTA KUMAR MAITY | 2.06 | 0 | 0 | 0
2821 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) , SM/12268 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | 1684/TD | 28/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.86 | 4.85 | 100 | 100
2822 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) , SM/12268 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1361/TD | 22/09/2022 | 40 | B. K. ENTERPRISE | 72.46 | 15.29 | 100 | 63
2823 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) , SM/12268 | Augmentation | Material Requisition To Resource Division | 1663/TD | 03/11/2022 | 0 | Resource Division | 315.36 | 0 | 0 | 0
2824 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) , SM/12268 | Augmentation | Material Requisition To Resource Division | 612/TD | 17/05/2023 | 0 | Resource Division | 37.05 | 0 | 0 | 0
2825 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) , SM/12268 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Contai Saline Area Zone-II Water Supply Scheme within Contai-I & III Dev. Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1972/TD | 01/12/2022 | 974 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 938.66 | 272.74 | 29.06 | 45
2826 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) , SM/12268 | Augmentation | Repairing and Renovation of Boundary Wall, Construction of Pump house and allied works of Augmentation of Contai Saline Area Zone-II Water Supply Scheme within Contai- I Block under Contai Sub-Division of Tamluk Division P.H.E. DTE. Purba Medinipur. | 1906/TD | 07/06/2024 | 361 | SK. NUR ISLAM | 45.39 | 0 | 0 | 35
2827 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur W/S Scheme (Phase - II) under Ramnagar-II Block , SM/08233 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kanpur PWSS Block- Ramnagar-II in the District of Purba Medinipur.(Phase-II) | 2994/TD | 25/02/2021 | 60 | BASANTA KUMAR MAITY | 210.56 | 172.89 | 82.11 | 100
2828 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur W/S Scheme (Phase - II) under Ramnagar-II Block , SM/08233 | Retrofitting | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Well (Head Work) of Mouza- Barasubarnanagar, JL No.- 502, Plot No.-297 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Ramnagar-II Block of Kanpur Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for 2nd Tube Well of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1050/TD | 18/08/2022 | 1017 | AQUATECH ENGINEERS | 45.52 | 0 | 0 | 98
2829 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-1) , SM/11616 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-B) | 307/TD | 24/04/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 0.3 | 0.3 | 100 | 100
2830 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-1) , SM/11616 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1650/TD | 02/11/2022 | 180 | TARUN KOLEY | 942.75 | 612.99 | 100 | 85
2831 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-1) , SM/11616 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i)300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at Head Works Tube Well Site for Shillaberia Jhanka Zone-II PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. ii) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 2nd Tube Well Site for Shillaberia Jhanka Zone-II PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iii) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Shillaberia Jhanka Zone-II PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 4th Tube Well Site for Shillaberia Jhanka Zone-II PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | 3145/TD | 09/03/2023 | 40 | B. K. ENTERPRISE | 70.37 | 53.19 | 75.59 | 75
2832 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-1) , SM/11616 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-A) | 306/TD | 24/04/2023 | 20 | RAMASISH ENTERPRISE | 11.41 | 11.41 | 100 | 100
2833 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-1) , SM/11616 | Augmentation | Name of Work: i) Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW(Head Work) site for Augmentation of Shillaberia Jhanka Zone-II & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) ii) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 2nd TW site for Augmentation of Shillaberia Jhanka Zone-II & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) iii) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Shillaberia Jhanka Zone-II & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) iv) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Augmentation of Shillaberia Jhanka Zone-II & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) v) Laying Rising main and other allied works Augmentation of Shillaberia Jhanka Zone-II W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3219/TD | 14/03/2023 | 962 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 40.37 | 13.14 | 32.56 | 90
2834 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-1) , SM/11616 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) with Approach road at 2nd TW site for Augmentation of Shillaberia Jhanka Zone-II PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | 566/TD | 17/02/2025 | 40 | DAS ENTERPRISE | 9.15 | 0 | 0 | 0
2835 | PURBA MEDINIPUR | Central Drilling | BRINDABANPUR & ADJOINING MOUJAS PWSS , SM/12148 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 250 Mtrs. Depth) by utilizing Departmental Machineries for Brindabanpur W/S Scheme (T/W-I & II), Bhagawanpur-II Block underPurbaMedinipur District, Central Drilling Division, P.H.E. Dte. | 1395/CDD | 19/09/2023 | 30 | MENAKA ENTERPRISE | 28.62 | 0 | 0 | 0
2836 | PURBA MEDINIPUR | Tamluk Division | BRINDABANPUR & ADJOINING MOUJAS PWSS , SM/12148 | New | Material Requisition To Resource Division | 2965/TD | 27/02/2023 | 0 | Resource Division | 23.38 | 0 | 0 | 0
2837 | PURBA MEDINIPUR | Midnapore Mechanical | BRINDABANPUR & ADJOINING MOUJAS PWSS , SM/12148 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BRINDABANPUR and ADJOINING MOUJAS, Block Bhagawanpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2318/W/MMD | 29/12/2022 | 180 | AHALYA ENGINEERING WORKS | 21.61 | 19.67 | 91 | 75
2838 | PURBA MEDINIPUR | Tamluk Division | BRINDABANPUR & ADJOINING MOUJAS PWSS , SM/12148 | New | Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1023 nos) under JJM with allied work of BRINDABANPUR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 1017/TD | 06/06/2023 | 721 | DAS ENTERPRISE | 305.41 | 201.72 | 66.05 | 60
2839 | PURBA MEDINIPUR | Tamluk Division | BRINDABANPUR & ADJOINING MOUJAS PWSS , SM/12148 | New | Material Requisition To Resource Division | 630/W | 20/02/2024 | 0 | Resource Division | 6.3 | 0 | 0 | 0
2840 | PURBA MEDINIPUR | Midnapore Mechanical | BRINDABANPUR & ADJOINING MOUJAS PWSS , SM/12148 | New | BRINDABANPUR w/s SCHEME PH.-I APPLICATION NO.-2004567517 | BP-2023-24-610 | 07/02/2024 | 0 | WBSEDCL | 5.95 | 0 | 0 | 0
2841 | PURBA MEDINIPUR | Midnapore Mechanical | BRINDABANPUR & ADJOINING MOUJAS PWSS , SM/12148 | New | BRINDABANPUR w/s SCHEME PH.-II APPLICATION NO.-2004570658 | BP-2023-24-609 | 07/02/2024 | 0 | WBSEDCL | 4.06 | 0 | 0 | 0
2842 | PURBA MEDINIPUR | Tamluk Division | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS , SM/12140 | New | Material Requisition To Resource Division | 2467/TD | 16/01/2023 | 0 | Resource Division | 19.42 | 0 | 0 | 0
2843 | PURBA MEDINIPUR | Midnapore Mechanical | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS , SM/12140 | New | Electric Quotation for RAMCHANDRAPUR Water Supply Scheme , (Ref. ID-204075844) | BP-2023-24-239 | 12/09/2023 | 0 | WBSEDCL | 3.95 | 0 | 0 | 0
2844 | PURBA MEDINIPUR | Tamluk Division | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS , SM/12140 | New | Material Requisition To Resource Division | 114/TD | 05/01/2024 | 0 | Resource Division | 11.32 | 0 | 0 | 0
2845 | PURBA MEDINIPUR | Midnapore Mechanical | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS , SM/12140 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAMCHANDRAPUR and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2337/W/MMD | 29/12/2022 | 1068 | DEY ENTERPRISE | 23.7 | 11.09 | 46.78 | 65
2846 | PURBA MEDINIPUR | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS , SM/12281 | New | Material Requisition To Resource Division | 2983/TD | 27/02/2023 | 0 | Resource Division | 12.88 | 0 | 0 | 0
2847 | PURBA MEDINIPUR | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS , SM/12281 | New | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 3347/TD | 22/03/2023 | 40 | PRANTIK DRILLING AGENCY | 61.77 | 28.82 | 93.31 | 50
2848 | PURBA MEDINIPUR | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS , SM/12281 | New | Ground water based Mayachar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | 260/TD | 19/04/2023 | 617 | MADAN MOHAN MAITY | 24.93 | 17.53 | 70.33 | 75
2849 | PURBA MEDINIPUR | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS , SM/12281 | New | Ground water based Mayachar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 150 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | 2438/TD | 19/09/2023 | 180 | ANUSKA ENTERPRISE | 165.66 | 28.45 | 17.17 | 30
2850 | PURBA MEDINIPUR | Midnapore Mechanical | MAYACHAR AND ADJOINING MOUJAS PWSS , SM/12281 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAYACHAR and ADJOINING MOUJAS, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2408/W/MMD | 31/12/2022 | 721 | S.G.ENTERPRISE | 21.6 | 21.27 | 100 | 100
2851 | PURBA MEDINIPUR | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS , SM/12281 | New | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-III) [Chaitanyapur Zone-I PWSS, Dwariberia PWSS, Natshal Lakshya Zone-I PWSS & Mayachar PWSS] | 619/HSD, | 21/12/2023 | 7 | SANTANU PATTANAYAK | 0.83 | 0.83 | 100 | 100
2852 | PURBA MEDINIPUR | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS , SM/12281 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Mayachar PWSS at Mahishadal Block under Tamluk Division, PHE Dte. | 2062/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
2853 | PURBA MEDINIPUR | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS , SM/12281 | New | Material Requisition To Resource Division | 135/TD | 05/01/2024 | 0 | Resource Division | 8.04 | 0 | 0 | 0
2854 | PURBA MEDINIPUR | Midnapore Mechanical | MAYACHAR AND ADJOINING MOUJAS PWSS , SM/12281 | New | Quotation for new service connection at Mayachar w/s scheme PH I in the district of Purba Medinipur (Application no 1007526112, Ref ID 106467554) | BP-2023-24-711 | 20/02/2024 | 0 | WBSEDCL | 3.89 | 0 | 0 | 0
2855 | PURBA MEDINIPUR | Midnapore Mechanical | MAYACHAR AND ADJOINING MOUJAS PWSS , SM/12281 | New | Quotation for new service connection at Mayachar w/s scheme PH II in the district of Purba Medinipur (Application no 1007525986, Ref ID 106467535) | BP-2023-24-712 | 20/02/2024 | 0 | WBSEDCL | 6.18 | 0 | 0 | 0
2856 | PURBA MEDINIPUR | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS , SM/12281 | New | Ground water based Mayachar Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | 576/TD | 16/05/2023 | 596 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 139.9 | 104.51 | 74.7 | 90
2857 | PURBA MEDINIPUR | Tamluk Division | DANGAR TULSI AND ADJOINING MOUJAS PWSS , SM/12285 | New | Material Requisition To Resource Division | 2441/TD | 16/01/2023 | 0 | Resource Division | 33.17 | 0 | 0 | 0
2858 | PURBA MEDINIPUR | Midnapore Mechanical | DANGAR TULSI AND ADJOINING MOUJAS PWSS , SM/12285 | New | Quotation Bill for New Service connection at T/W NO-II Of DANGAR TULSHI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004862083/QUOT/03 DT. 16-08-2024 MEMO NO: AMR/PHE/330 DT. 16-08-2024 Application NO- 2004862083 Application type-New connection Consumer Id- 204378443 | C082448267203 | 02/09/2024 | 0 | WBSEDCL | 4.66 | 0 | 0 | 0
2859 | PURBA MEDINIPUR | Midnapore Mechanical | DANGAR TULSI AND ADJOINING MOUJAS PWSS , SM/12285 | New | Quotation Bill for New Service connection at T/W NO-I Of DANGARTULSHI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004706844/QUOT/03 DT. 29-04-2024 Application NO- 2004706844 MEMO NO: AMR/PHE/91 DT.29/04/2024 Application type-New connection Consumer Id- 204291543 | BP-2024-25-164 | 15/05/2024 | 0 | WBSEDCL | 3.95 | 0 | 0 | 0
2860 | PURBA MEDINIPUR | Midnapore Mechanical | DANGAR TULSI AND ADJOINING MOUJAS PWSS , SM/12285 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DANGAR TULSI and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2412/W/MMD | 31/12/2022 | 882 | SUJOY RANJAN BHOWMICK | 22.8 | 9.04 | 39.65 | 35
2861 | PURBA MEDINIPUR | Tamluk Division | DANGAR TULSI AND ADJOINING MOUJAS PWSS , SM/12285 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 211.9 | 38.52 | 51
2862 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11949 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Sofiabad W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 483/TD | 10/05/2023 | 60 | BABA LOKNATH CONSTRUCTION | 4.03 | 0 | 0 | 0
2863 | PURBA MEDINIPUR | Midnapore Mechanical | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11949 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. under JJM Program under MMD PHE Dte. | 637/W/MMD | 20/03/2023 | 180 | SOUMEN ELECTRIC | 13.57 | 9.66 | 71.16 | 60
2864 | PURBA MEDINIPUR | Central Drilling | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11949 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Sofiabad W/S Scheme (T/W-I & II) , Deshpran Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 856/CDD | 10/07/2023 | 398 | MENAKA ENTERPRISE | 29.23 | 0 | 0 | 50
2865 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11949 | Augmentation | Retrofitting to Accommodate 30 nos FHTC under JJM in Sofiabad PWSS Block- Contai-II ( Deshpran) of Tamluk Division, PHE Dte,in the districtof Purba Medinipur. | 1427/TD | 26/09/2022 | 15 | RELIABLE CONSTRUCTIONS | 1.28 | 1.28 | 100 | 100
2866 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11949 | Augmentation | Instalation of display Board at different work site of Bamunia, Barasubarnagar, Sofiabad, Aladarput Retrofitting PWSS in Contai - II (Deshopran) Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2333/CSD | 29/12/2023 | 15 | ABHIJIT BERA | 0.83 | 0.83 | 100 | 100
2867 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11949 | Augmentation | Laying of 150 mm dia & 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at Replacement of 2nd Tube Well & 1(One) no. Boosting Tube Well of Sofiabad & its adjoining mouzas Water Supply Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 482/TD | 10/05/2023 | 600 | KAMAL KUMAR BERA | 3.92 | 0 | 0 | 0
2868 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1361/TD | 22/09/2022 | 40 | B. K. ENTERPRISE | 72.46 | 15.29 | 100 | 63
2869 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Material Requisition To Resource Division | 1661/TD | 03/11/2022 | 0 | Resource Division | 239.21 | 0 | 0 | 0
2870 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Material Requisition To Resource Division | 611/TD | 17/05/2023 | 0 | Resource Division | 31.42 | 0 | 0 | 0
2871 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 250 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Contai Saline Area Zone-I (Phase - B) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-I) | 2313/TD | 05/01/2023 | 966 | DAS CONSTRUCTION | 439.86 | 171.68 | 39.03 | 42
2872 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II), under JJM Program under MMD PHE Dte. | 357/W/MMD | 09/03/2023 | 180 | K.S.P. ENTERPRISE | 13.57 | 0 | 0 | 60
2873 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B), under JJM Program under MMD PHE Dte. | 642/W/MMD | 20/03/2023 | 180 | M/S. JIT ENTERPRISE | 13.58 | 0 | 0 | 0
2874 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method with 200 dia UPVC Strainer of 30 M. length all complete including cost of materials for Contai Saline Area Zone-I Water Supply Scheme of Tube Well No.- II within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1085/TD | 16/03/2024 | 20 | RUPKUMAR KARMAKAR | 18.24 | 0 | 0 | 0
2875 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method with 200 dia UPVC Strainer of 30 M. length all complete including cost of materials for Contai Saline Area Zone-I Water Supply Scheme of Tube Well No.- I within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1086/TD | 16/03/2024 | 20 | RUPKUMAR KARMAKAR | 18.4 | 0 | 0 | 0
2876 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I(Phase-A) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. | 1732/CSD | 20/06/2024 | 20 | GIRI CONSTRUCTION | 1.16 | 1.16 | 100 | 100
2877 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Supply of documents for way leave permission of Railway Track Between HENRIA-KANTHI Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I(Phase-B) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (2nd Call) | 1735/CSD | 20/06/2024 | 20 | ABHIJIT BERA | 2.31 | 2.31 | 100 | 100
2878 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Way Leave Plan and Survey Charges under railway track permission for Application ID SER-KGP-2023-WL-136 under Tamluk Division, PHE Dte. | BP-2024-25-236 | 12/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.25 | 0 | 0 | 0
2879 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Payment of wayleave facility charges(SER-KGP-2024-WL-53) | BP-2024-25-84 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.41 | 0 | 0 | 0
2880 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Payment of Wayleave facility charges (SER-KGP-2024-WL-52) | BP-2024-25-83 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.28 | 0 | 0 | 0
2881 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Payment of wayleave facility charges(SER-KGP-2024-WL-49) | BP-2024-25-80 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.59 | 0 | 0 | 0
2882 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | payment of way leave facility cahrges(SER-KGP-2024-WL-51) | BP-2024-25-82 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.3 | 0 | 0 | 0
2883 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Payment of wayleave charges(SER-KGP-2024-WL-50) | BP-2024-25-81 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 9.38 | 0 | 0 | 0
2884 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Electric Quotation for CONTAI S.A. RAJ (PHASE-B) Water Supply Scheme T/W-II,Zone-III, (Ref. ID-204114270) | BP-2023-24-321 | 01/11/2023 | 0 | WBSEDCL | 4.72 | 0 | 0 | 0
2885 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Way Leave Plan and Survey Charges under railway track permission for Application ID SER-KGP-2023-WL-136 under Tamluk Division, PHE Dte. | BP-2023-24-894 | 22/02/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.65 | 0 | 0 | 0
2886 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Contai Saline Area Zone-I ( Phase - B) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-II) | 2312/TD | 05/01/2023 | 739 | DAS CONSTRUCTION | 180.42 | 14.77 | 8.19 | 45
2887 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Repairing and Renovation of Boundary Wall, Construction of Pump house and allied works of Reservoir (OHR) Site under Augmentation of Contai Saline Area Zone-I ( Phase - B) Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | 3292/TD | 05/10/2024 | 280 | DEBANANDA CONSTRUCTION | 21.34 | 0 | 0 | 35
2888 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Construction of Pump House & Boundary Wall and others allied works for 1st Tube well site under Contai Saline Area Zone-I (Phase-A) Water Supply Scheme ( Augmentation) in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. (For Low Land) | 3063/TD | 19/09/2024 | 40 | GUCHHAIT ENTERPRISE | 14.07 | 0 | 0 | 0
2889 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Construction Boundary Wall & Repairing and renovation of Pump House and others allied works for 2nd Tube well site under Contai Saline Area Zone-I (Phase-B) Water Supply scheme ( Augmentation) in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. (For Low Land) | 2680/TD | 22/08/2024 | 40 | BISWA NIRMAN ENTERPRISE. | 10.08 | 0 | 0 | 0
2890 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). , SM/12364 | Augmentation | Dismantling chlorinator room & Staff quater at Head Work Site/ Reserver site of Contai S.A. Zone I (Phase B) PWSS under Contai Sub Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 3035/TD | 18/09/2024 | 21 | SUBHENDU HAZRA | 3.53 | 0 | 0 | 0
2891 | PURBA MEDINIPUR | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Material Requisition To Resource Division | 2388/TD | 16/01/2023 | 0 | Resource Division | 34.82 | 0 | 0 | 0
2892 | PURBA MEDINIPUR | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Material Requisition To Resource Division | 632/W | 20/02/2024 | 0 | Resource Division | 8.94 | 0 | 0 | 0
2893 | PURBA MEDINIPUR | Midnapore Mechanical | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Pachahari W/S scheme PH-I Application.-2004537390 Ref.-204168886 | BP-2023-24-531 | 11/01/2024 | 0 | WBSEDCL | 4.08 | 0 | 0 | 0
2894 | PURBA MEDINIPUR | Midnapore Mechanical | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Pachahari W/S scheme PH-II Application.-2004537398 Ref.-204168891 | BP-2023-24-532 | 11/01/2024 | 0 | WBSEDCL | 3.16 | 0 | 0 | 0
2895 | PURBA MEDINIPUR | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Laying distribution pipe line & Accommodate FHTC (170 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - D) | 3211/TD | 14/03/2023 | 929 | KAMAL KUMAR BERA | 19.49 | 5.93 | 30.43 | 45
2896 | PURBA MEDINIPUR | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Pump House, Laying distribution pipe line & Accommodate FHTC (420 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | 3210/TD | 14/03/2023 | 926 | ABHIJIT BERA | 82.33 | 57.41 | 69.73 | 50
2897 | PURBA MEDINIPUR | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Laying distribution pipe line & Accommodate FHTC (75nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - E) | 3212/TD | 14/03/2023 | 20 | PARTHA CONSTRUCTION | 9.77 | 4.15 | 42.52 | 45
2898 | PURBA MEDINIPUR | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Laying distribution pipe line, Boundary Wall & Accommodate FHTC ( 430 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - C) | 3561/TD | 29/03/2023 | 785 | OM ENTERPRISE | 80.86 | 42.25 | 52.24 | 55
2899 | PURBA MEDINIPUR | Central Drilling | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 55.54 | 108.85 | 11
2900 | PURBA MEDINIPUR | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (357 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-A) | 2443/TD | 19/09/2023 | 682 | THREE MAA ENTERPRISE | 226.83 | 107.43 | 47.36 | 32
2901 | PURBA MEDINIPUR | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Laying of Left out Distribution pipe line by HDPE pipes with allied works for PACHHARI PWSS (PART-B) within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-B) | 211/TD | 15/01/2025 | 50 | SAURAV HAZRA | 12.27 | 0 | 0 | 0
2902 | PURBA MEDINIPUR | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Drum Sheet Walling & allied works of Pachhari PWSS (PART-A) in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 3222/TD | 01/10/2024 | 25 | THREE MAA ENTERPRISE | 9.45 | 0 | 0 | 0
2903 | PURBA MEDINIPUR | Midnapore Mechanical | PACHAHRI & ADJOINING MOUJAS PWSS , SM/12292 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
2904 | PURBA MEDINIPUR | Midnapore Mechanical | NAICHHANPUR AND ADJOINING MOUJAS PWSS , SM/12295 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NAICHHANPUR AND ADJOINING MOUJAS PWSS, Block Moyna, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1411/W/MMD | 02/06/2023 | 180 | P.K.ENGINEERING | 27.53 | 0 | 0 | 0
2905 | PURBA MEDINIPUR | Tamluk Division | NAICHHANPUR AND ADJOINING MOUJAS PWSS , SM/12295 | New | Material Requisition To Resource Division | 2989/TD | 27/02/2023 | 0 | Resource Division | 16.3 | 0 | 0 | 0
2906 | PURBA MEDINIPUR | Tamluk Division | NAICHHANPUR AND ADJOINING MOUJAS PWSS , SM/12295 | New | Laying distribution System & Accommodate FHTC (500 nos) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(PART-B) | 3245/TD | 15/03/2023 | 854 | ADHIKARY CONSTRUCTION | 64.64 | 32.51 | 50.29 | 60
2907 | PURBA MEDINIPUR | Tamluk Division | NAICHHANPUR AND ADJOINING MOUJAS PWSS , SM/12295 | New | Material Requisition To Resource Division | 1568/TD | 23/04/2024 | 0 | Resource Division | 9.32 | 0 | 0 | 0
2908 | PURBA MEDINIPUR | Midnapore Mechanical | NAICHHANPUR AND ADJOINING MOUJAS PWSS , SM/12295 | New | Naichanpur W/S scheme Ph-I Application No.-204543058 Ref.-204175259 | BP-2023-24-514 | 09/01/2024 | 0 | WBSEDCL | 2.78 | 0 | 0 | 0
2909 | PURBA MEDINIPUR | Midnapore Mechanical | NAICHHANPUR AND ADJOINING MOUJAS PWSS , SM/12295 | New | Naichanpur W/S scheme PH-II Application No.-2004543088 Ref.-204175260 | BP-2023-24-513 | 09/01/2024 | 0 | WBSEDCL | 4.51 | 0 | 0 | 0
2910 | PURBA MEDINIPUR | Tamluk Division | NAICHHANPUR AND ADJOINING MOUJAS PWSS , SM/12295 | New | Laying distribution System, Construction of Boundary wall at 1st. & 2nd. Tube well site, Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room, interconnection with laying of 150 mm dia & 200 mm dia DI(K-9) Rising main and Accommodate FHTC (638 nos) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-C) | 416/TD | 02/05/2023 | 660 | KRISHNENDU SEKHAR DAS | 140.04 | 117.64 | 84 | 74
2911 | PURBA MEDINIPUR | Central Drilling | NAICHHANPUR AND ADJOINING MOUJAS PWSS , SM/12295 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 47.62 | 97.87 | 11
2912 | PURBA MEDINIPUR | Tamluk Division | NAICHHANPUR AND ADJOINING MOUJAS PWSS , SM/12295 | New | Laying distribution System, Construction of Pump House & Accommodate FHTC (375 nos) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-A) | 3244/TD | 15/03/2023 | 660 | GHOSH ENTERPRISE | 90.18 | 84.46 | 95.41 | 65
2913 | PURBA MEDINIPUR | Tamluk Division | NAICHHANPUR AND ADJOINING MOUJAS PWSS , SM/12295 | New | Soil investigation & R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(PART-E) | 417/TD | 02/05/2023 | 719 | ARABINDA GHOSH | 113.16 | 90.05 | 77.85 | 46
2914 | PURBA MEDINIPUR | Tamluk Division | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13690 | New | Material Requisition To Resource Division | 2392/TD | 16/01/2023 | 0 | Resource Division | 34.34 | 0 | 0 | 0
2915 | PURBA MEDINIPUR | Tamluk Division | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13690 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Sahajadapur PWSS at Contai-I Block under Tamluk Division,PHE Dte. | 203/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.96 | 0 | 0 | 0
2916 | PURBA MEDINIPUR | Tamluk Division | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13690 | New | Material Requisition To Resource Division | 2977/TD | 12/09/2024 | 0 | Resource Division | 3.28 | 0 | 0 | 0
2917 | PURBA MEDINIPUR | Midnapore Mechanical | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13690 | New | Quotation for new service connection at TW-I of Sahajadapur ws scheme under MMD,PHE Dte. Ref. Application no-2004579826, CON ID-204204429, under PICHABONI CCC, Block-CONTAI-I | BP-2023-24-679 | 15/02/2024 | 0 | WBSEDCL | 3.19 | 0 | 0 | 0
2918 | PURBA MEDINIPUR | Tamluk Division | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13690 | New | Quotation Bill for New Service connection at T/W NO-II Of SAHAJADAPUR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004772844/QUOT/03 DT. 14-06-2024 Application NO- 2004772844 Application type-New connection Consumer Id- 204329286 | BP-2024-25-289 | 29/07/2024 | 0 | WBSEDCL | 14.1 | 0 | 0 | 0
2919 | PURBA MEDINIPUR | Midnapore Mechanical | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13690 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAHAJADAPUR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 543/W/MMD | 20/03/2023 | 772 | SOUMEN ELECTRIC | 21.56 | 16.07 | 74.54 | 100
2920 | PURBA MEDINIPUR | Central Drilling | 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/11896 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Amtalia W/S Scheme (TW-III) , Deshpran Block under Purba Midnapore District, Central Drilling Division, P.H.E. Dte. | 1230/CDD | 16/11/2022 | 30 | PADMA ENGINEERING & CO. | 19.11 | 0 | 0 | 0
2921 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/11896 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. under JJM Program under MMD PHE Dte. | 636/W/MMD | 20/03/2023 | 180 | SOUMEN ELECTRIC | 13.57 | 9.66 | 71.16 | 60
2922 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/11896 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting Tube Well for Amtalia W/S Scheme within Contai- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1420/TD | 12/07/2023 | 30 | PARIA ENTERPRISE | 9.47 | 0 | 0 | 0
2923 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS , SM/12130 | New | Material Requisition To Resource Division | 2681/TD | 06/02/2023 | 0 | Resource Division | 15.32 | 0 | 0 | 0
2924 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS , SM/12130 | New | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 54.95 | 100
2925 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS , SM/12130 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Dakshin Utaspur PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | 2078/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
2926 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS , SM/12130 | New | Material Requisition To Resource Division | 91/TD | 05/01/2024 | 0 | Resource Division | 8.11 | 0 | 0 | 0
2927 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS , SM/12130 | New | Quotation Bill for Dakshin Usutpur Water Supply Scheme T/W-II Matangini CCC,Block=Sahid Matangini Application No=2004690463 Reference ID=204279652 | BP-2024-25-166 | 15/05/2024 | 0 | WBSEDCL | 4.65 | 0 | 0 | 0
2928 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS , SM/12130 | New | Quotation Bill for Dakshin Usutpur Water Supply Scheme H/W Site Matangini CCC,Block=Sahid Matangini Application No=2004690460 Reference ID=204279646 | BP-2024-25-167 | 15/05/2024 | 0 | WBSEDCL | 3.52 | 0 | 0 | 0
2929 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS , SM/12130 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS, Block ¿ Shahid Matangini, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1272/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 22.69 | 0 | 0 | 25
2930 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS , SM/12130 | New | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 0 | 100
2931 | PURBA MEDINIPUR | Midnapore Mechanical | KALABERIA & ADJOINING MOUZAS , SM/12136 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KALABERIA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2343/W/MMD | 29/12/2022 | 180 | ORIENTAL ENGINEERING CO. | 25.24 | 0 | 0 | 0
2932 | PURBA MEDINIPUR | Tamluk Division | KALABERIA & ADJOINING MOUZAS , SM/12136 | New | Material Requisition To Resource Division | 2384/TD | 16/01/2023 | 0 | Resource Division | 19.89 | 0 | 0 | 0
2933 | PURBA MEDINIPUR | Tamluk Division | KALABERIA & ADJOINING MOUZAS , SM/12136 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1959 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of KALABERIA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 73/TD | 05/01/2024 | 696 | SRIMANTA KUMAR MAITY | 584.3 | 43.7 | 7.67 | 15
2934 | PURBA MEDINIPUR | Tamluk Division | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS , SM/13686 | New | Material Requisition To Resource Division | 2407/TD | 16/01/2023 | 0 | Resource Division | 18.82 | 0 | 0 | 0
2935 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS , SM/13686 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA MAHAMMADPUR and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 550/W/MMD | 20/03/2023 | 712 | DEBJYOTI BASU | 21.62 | 11.03 | 51.03 | 55
2936 | PURBA MEDINIPUR | Tamluk Division | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS , SM/13686 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Purba Mahammadpur PWSS at Deshpran Block under Tamluk Division, PHE Dte. | 1049/TD | 15/03/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
2937 | PURBA MEDINIPUR | Tamluk Division | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS , SM/13686 | New | Material Requisition To Resource Division | 2973/TD | 12/09/2024 | 0 | Resource Division | 6.99 | 0 | 0 | 0
2938 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS , SM/13686 | New | Quotation Bill for New Service connection at T/W NO-I Of PURBA MAHAMMADPUR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004877670/QUOT/03 DT. 12-09-2024 Application NO- 2004877670 Application type-New connection Consumer Id- 204397980 | C092445105167 | 30/09/2024 | 0 | WBSEDCL | 12.11 | 0 | 0 | 0
2939 | PURBA MEDINIPUR | Tamluk Division | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS , SM/13686 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House ,Boundary Wall & Providing Functional Household Tap Connection (3734 Nos), including 2 years Operation & Maintenance For Purba Mukundapur, Dakshin Kadua, Purba Mahammadpur Pipe water supply Scheme within Deshapran Block Under Tamluk Division PHE Dte. | 1593/TD | 21/07/2023 | 711 | JAYANTA KUMAR MONDAL | 1264.74 | 155.3 | 38.5 | 30
2940 | PURBA MEDINIPUR | Tamluk Division | BELDA AND IT'S ADJOINING MOUJAS PWSS , SM/12710 | New | Material Requisition To Resource Division | 2447/TD | 16/01/2023 | 0 | Resource Division | 22.75 | 0 | 0 | 0
2941 | PURBA MEDINIPUR | Midnapore Mechanical | BELDA AND IT'S ADJOINING MOUJAS PWSS , SM/12710 | New | Quotation Bill for New Service connection at T/W NO-I Of BELDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004607449/QUOT/03 DT. 21-02-2024 Application NO- 2004607449 Application type-New connection Consumer Id- 204223207 | BP-2023-24-824 | 13/03/2024 | 0 | WBSEDCL | 3.03 | 0 | 0 | 0
2942 | PURBA MEDINIPUR | Midnapore Mechanical | BELDA AND IT'S ADJOINING MOUJAS PWSS , SM/12710 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BELDA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2360/W/MMD | 31/12/2022 | 912 | WEST BENGAL ENGINEERING CO. | 23.67 | 0 | 0 | 50
2943 | PURBA MEDINIPUR | Tamluk Division | BELDA AND IT'S ADJOINING MOUJAS PWSS , SM/12710 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 193.47 | 31.92 | 51
2944 | PURBA MEDINIPUR | Midnapore Mechanical | JAMUASHANKARPUR PWSS , SM/14694 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JAMUASHANKARPUR PWSS, Block ¿ Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 603/W/MMD | 20/03/2023 | 180 | KRISHNA ENGINEERING | 11.94 | 0 | 0 | 0
2945 | PURBA MEDINIPUR | Tamluk Division | JAMUASHANKARPUR PWSS , SM/14694 | New | Material Requisition To Resource Division | 2400/TD | 16/01/2023 | 0 | Resource Division | 30.7 | 0 | 0 | 0
2946 | PURBA MEDINIPUR | Tamluk Division | JAMUASHANKARPUR PWSS , SM/14694 | New | Material Requisition To Resource Division | 2960/TD | 12/09/2024 | 0 | Resource Division | 1.92 | 0 | 0 | 0
2947 | PURBA MEDINIPUR | Tamluk Division | JAMUASHANKARPUR PWSS , SM/14694 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | 1674/TD | 25/07/2023 | 860 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 0 | 0 | 30
2948 | PURBA MEDINIPUR | Tamluk Division | SATKALUA AND IT'S ADJOINING MOUJAS PWSS , SM/14695 | New | Material Requisition To Resource Division | 2673/TD | 06/02/2023 | 0 | Resource Division | 19.08 | 0 | 0 | 0
2949 | PURBA MEDINIPUR | Midnapore Mechanical | SATKALUA AND IT'S ADJOINING MOUJAS PWSS , SM/14695 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SATKALUA AND IT'S ADJOINING MOUJAS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 595/W/MMD | 20/03/2023 | 180 | INDIA ENTERPRISE | 21.62 | 10.61 | 49.09 | 35
2950 | PURBA MEDINIPUR | Midnapore Mechanical | SATKALUA AND IT'S ADJOINING MOUJAS PWSS , SM/14695 | New | Satkalua W/S scheme H/W site. Application No.-2004547137 Ref.-204177910 | BP-2023-24-548 | 15/01/2024 | 0 | WBSEDCL | 4.11 | 0 | 0 | 0
2951 | PURBA MEDINIPUR | Tamluk Division | SATKALUA AND IT'S ADJOINING MOUJAS PWSS , SM/14695 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Boundary Wall, Providing Functional Household Tap Connection (1277 Nos), including 2 years Operation & Maintenance For Satkalua, Uttar Sautanchak, Pipe Water Supply Scheme within TAMLUK Block Under Tamluk Division PHE Dte. | 449/TD | 04/05/2023 | 698 | TARUN KOLEY | 549.23 | 113.39 | 36.46 | 75
2952 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Barchunfali W/S Scheme , SM/06883 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Barchunfali PWSS Block Contai-I in the District of Purba Medinipur. | 2102/TD | 05/11/2020 | 180 | DAS CONSTRUCTION | 96.5 | 1.82 | 1.89 | 100
2953 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Barchunfali W/S Scheme , SM/06883 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Barchunfali W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. | 686/W | 27/01/2021 | 0 | DAS CONSTRUCTION | 59.4 | 0 | 0 | 0
2954 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Barchunfali W/S Scheme , SM/06883 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Barchunfali W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. | 1040/W | 30/03/2021 | 0 | DAS CONSTRUCTION | 18.19 | 0 | 0 | 0
2955 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Barchunfali W/S Scheme , SM/06883 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Barchunfali W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. | 311/W | 08/10/2021 | 0 | DAS CONSTRUCTION | 16.22 | 0 | 0 | 0
2956 | PURBA MEDINIPUR | Tamluk Division | CHAK BHABANI & ADJOINING MOUJAS PWSS , SM/15512 | New | Material Requisition To Resource Division | 2996/TD | 27/02/2023 | 0 | Resource Division | 22.46 | 0 | 0 | 0
2957 | PURBA MEDINIPUR | Tamluk Division | CHAK BHABANI & ADJOINING MOUJAS PWSS , SM/15512 | New | Material Requisition To Resource Division | 1649/TD | 29/04/2024 | 0 | Resource Division | 17.51 | 0 | 0 | 0
2958 | PURBA MEDINIPUR | Midnapore Mechanical | CHAK BHABANI & ADJOINING MOUJAS PWSS , SM/15512 | New | Chakbhabani W/S scheme PH-I Application no.-2004520839 ref.-204155241 | BP-2023-24-484 | 27/12/2023 | 0 | WBSEDCL | 3.91 | 0 | 0 | 0
2959 | PURBA MEDINIPUR | Midnapore Mechanical | CHAK BHABANI & ADJOINING MOUJAS PWSS , SM/15512 | New | Chakbhabani W/S scheme PH-II Application no.-2004520828 ref.-204155254 | BP-2023-24-483 | 27/12/2023 | 0 | WBSEDCL | 3.58 | 0 | 0 | 0
2960 | PURBA MEDINIPUR | Midnapore Mechanical | CHAK BHABANI & ADJOINING MOUJAS PWSS , SM/15512 | New | Additional Quotation Bill of Erection for the Service connection at T/W NO-II Of CHAKBHABANI W/S Scheme Under Jal Jeevan Mission under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-PTP/QOT/HT/151 DT. 14-05-2024 Application NO- 100000107893 DT. 14-05-2024 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860299943 | BP-2024-25-245 | 06/06/2024 | 0 | WBSEDCL | 0.37 | 0 | 0 | 0
2961 | PURBA MEDINIPUR | Tamluk Division | CHAK BHABANI & ADJOINING MOUJAS PWSS , SM/15512 | New | Sinking of Tube well,Pump House ,Construction of 350 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2843 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Chakbhabani PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1564/TD | 19/07/2023 | 180 | TARUN KOLEY | 947.78 | 606.52 | 63.99 | 35
2962 | PURBA MEDINIPUR | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS , SM/16203 | New | Material Requisition To Resource Division | 3014/TD | 27/02/2023 | 0 | Resource Division | 9.41 | 0 | 0 | 0
2963 | PURBA MEDINIPUR | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS , SM/16203 | New | Laying distribution pipe line, Boundary Wall under JJM with allied work for BHATSALIA PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | 1454/TD | 13/07/2023 | 45 | MAHAPRABHU ENTERPRISE | 14.4 | 0 | 0 | 0
2964 | PURBA MEDINIPUR | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS , SM/16203 | New | Quotation for new service connection at TW-1 of Bhatsalia ws scheme under MMD,PHE Dte, Block-Egra-1, Chorpalia CCC Application no-2004753843 CON ID-204318364 | BP-2024-25-292 | 29/07/2024 | 0 | WBSEDCL | 5.37 | 0 | 0 | 0
2965 | PURBA MEDINIPUR | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS , SM/16203 | New | Quotation for new service connection at t/w no.-II of Bhatsalia ws scheme under MMD,PHE Dte, Block-Egra-1, Chorpalia CCC Application no-2004753851 Con ID-204322327 | BP-2024-25-293 | 29/07/2024 | 0 | WBSEDCL | 4.56 | 0 | 0 | 0
2966 | PURBA MEDINIPUR | Central Drilling | BHATSALIA & IT'S ADJOINING MOUJAS PWSS , SM/16203 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 46.63 | 113.35 | 11
2967 | PURBA MEDINIPUR | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS , SM/16203 | New | Soil investigation, Construction of 50 cum OHR (tourch type with pile foundation) under JJM with allied work for Bhatsalia PWSS within Egra-I Block including Supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-D) | 1086/TD | 08/06/2023 | 180 | GOUTAM CONSTRUCTION | 38.57 | 0 | 0 | 30
2968 | PURBA MEDINIPUR | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS , SM/16203 | New | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC (337 nos) under JJM with allied work for BHATSALIA PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | 1453/TD | 13/07/2023 | 643 | R CONSTRUCTION | 78.02 | 38.07 | 48.8 | 85
2969 | PURBA MEDINIPUR | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) , SM/16465 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 0 | 50
2970 | PURBA MEDINIPUR | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) , SM/16465 | Augmentation | Quotation Bill for New Service connection at T/W NO-III Of CHIRULIA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004692025/QUOT/03/97 DT. 25-04-2024 Application NO- 2004692025 Application type-New connection Consumer Id- 204287568 | BP-2024-25-165 | 15/05/2024 | 0 | WBSEDCL | 3.24 | 0 | 0 | 0
2971 | PURBA MEDINIPUR | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) , SM/16465 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) within Purba Medinipur District under JJM Program under MMD PHE Dte. | 896/W/MMD | 27/03/2023 | 837 | ECO ENTERPRISE | 12.63 | 8.53 | 67.49 | 85
2972 | PURBA MEDINIPUR | Tamluk Division | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. , SM/15851 | New | Material Requisition To Resource Division | 3012/TD | 27/02/2023 | 0 | Resource Division | 19.16 | 0 | 0 | 0
2973 | PURBA MEDINIPUR | Tamluk Division | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. , SM/15851 | New | Material Requisition To Resource Division | 2956/TD | 12/09/2024 | 0 | Resource Division | 1.54 | 0 | 0 | 0
2974 | PURBA MEDINIPUR | Midnapore Mechanical | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. , SM/15851 | New | Deshduttabar W/S scheme T/W-I Application-no.-2004523550 Ref.-204157344 | BP-2023-24-446 | 19/12/2023 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
2975 | PURBA MEDINIPUR | Midnapore Mechanical | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. , SM/15851 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Contai - I and III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1205/W/MMD | 25/04/2023 | 859 | BHABANI PRASAD MANNA | 57.85 | 0 | 0 | 60
2976 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BATHUARI PWSS UNDER EGRA - II BLOCK PHASE II , SM/08752 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bathuary PWSS Block- Egra-II in the District of Purba Medinipur.(Phase-II) | 693/TD | 10/09/2021 | 60 | SATYABRATA BHAUMIK | 137.67 | 137.67 | 100 | 100
2977 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BATHUARI PWSS UNDER EGRA - II BLOCK PHASE II , SM/08752 | Retrofitting | Material Requisition To Resource Division | 1235/TD | 09/12/2021 | 0 | Resource Division | 6.01 | 0 | 0 | 0
2978 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BATHUARI PWSS UNDER EGRA - II BLOCK PHASE II , SM/08752 | Retrofitting | Continuation Work Order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Augmentation Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | 2566/TD | 06/10/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 1.79 | 100 | 100
2979 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16205 | Augmentation | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Jalpai Part-II W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Tajpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Manikpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 115/TD | 06/04/2023 | 40 | B. K. ENTERPRISE | 63.13 | 20.56 | 100 | 100
2980 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16205 | Augmentation | Material Requisition To Resource Division | 353/TD | 26/04/2023 | 0 | Resource Division | 0.63 | 0 | 0 | 0
2981 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16205 | Augmentation | Electric Quotation for MANIKPUR Boosting, Water Supply Scheme T/W (Ref. ID-204063673) | BP-2023-24-203 | 24/08/2023 | 0 | WBSEDCL | 4.87 | 0 | 0 | 0
2982 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16205 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1209/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 53.9 | 12.51 | 92.86 | 35
2983 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16205 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 60.44 | 100
2984 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16205 | Augmentation | Additional Quotation of Manikpur Boosting Tube Well Application ID-100000095367 Referance ID- 860287817 | BP-2023-24-467 | 27/12/2023 | 0 | WBSEDCL | 0.29 | 0 | 0 | 0
2985 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16205 | Augmentation | Construction of Pump House, Laying Rising Main & Construction of Boundary Wall at Boosting Tube well Site of Manikpur W/S Scheme within Nandigram-I Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 624/TD | 17/05/2023 | 499 | DEEP ENTERPRISE | 12.11 | 10.51 | 86.82 | 100
2986 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16205 | Augmentation | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 0 | 100
2987 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Kotbar Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16279 | Augmentation | Material Requisition To Resource Division | 355/TD | 26/04/2023 | 0 | Resource Division | 4.41 | 0 | 0 | 0
2988 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Kotbar Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16279 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1204/W/MMD | 25/04/2023 | 740 | BHABANI PRASAD MANNA | 77.91 | 5.95 | 51.75 | 55
2989 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Kotbar Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16279 | Augmentation | Name of Work: Sinking of 3 (Three) nos.Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Kotbar W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Saripur W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Paramanandapur W/S Scheme within Moyna Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 118/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 61.66 | 17.82 | 100 | 100
2990 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Kotbar Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/16279 | Augmentation | Quotation for new service connection at Kotbar w/s scheme Boosting T/W I in the district of Purba Medinipur under MMD PHE Dte. (App No 2004689061, Ref ID 204279764) | BP-2024-25-275 | 12/06/2024 | 0 | WBSEDCL | 6.09 | 0 | 0 | 0
2991 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Material Requisition To Resource Division | 2910/TD | 21/11/2023 | 0 | Resource Division | 10.62 | 0 | 0 | 0
2992 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Installation of display Board at 55 nos. different work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 3289/TD | 05/10/2024 | 20 | MISHRA ENTERPRISE | 9.16 | 9.16 | 100 | 100
2993 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 0 | 0 | 48
2994 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
2995 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Instalation of display Board at 5 nos ( Vill:- 1. Bar Kasimpur, 2. Dhaka Chora, under Kakra Panchayat 3. Bhairabi Chak, 4. Nishkini, 5. Ramchak, Panchayat :- Kotebash all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 123/RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
2996 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Instalation of display Board at 5 nos ( Vill:- 1. Hajipur, 2.Tangabani, under Haldia-i Panchyat 3. Saripur, 4. Mirjapur, 5. Somaibasan, Panchayat :Padima-ii- all are under Ramnagar-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 114/RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
2997 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Instalation of display Board at 5 nos ( Vill:- 1. Nata Gechhia, 2 .Uttar Khas Mulda, under Boroj Panchyat, 3. Jagamohanpur, 4. Uttar Nara Basan, under Mugberia Panchyat 5. vill- Hinari, Panchayat :- Basantapur all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 115/RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
2998 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Instalation of display Board at 5 nos ( Vill:- 1. Bisha Dangar, 2. Dhangharibar, 3. Kunja Para, 4. Uttar Sukhmajhi, under Itaberia Panchyat 5. vill- Binanda Chak, Panchayat :- Basudevberia all are under Bhagawanpur-ii Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 116/RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
2999 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Instalation of display Board at 5 nos ( Vill:- 1. Nata Talya, 2. Nona Birampur, 3. Nunbar, 4. Dihi Jhanjrar, under Bhagabanpur Panchyat 5. vill- Brahmattar Bar, Panchayat :- Bibhisanpur all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 127/RWS/TSD | 03/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
3000 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Instalation of display Board at 5 nos ( Vill:- 1. Ghoshpur, 2.Raygange,under Gurgram Panchyat 3. Kotbar, Panchayat :- Simulia, 4. Baman Chak, 5. Bhabani Chak Panchayat :- Kajlagarh, all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 126/RWS/TSD | 03/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
3001 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Instalation of display Board at 5 nos ( Vill:- 1. Haripur , 2. Chak Sibrampur, 3. Danaipur , 4. Tiraipur Jalpal, under Mahammadpur-i Panchyat 5. vill- Gopal Chak, Panchayat :- Simulia all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 122/RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
3002 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Instalation of display Board at 5 nos ( Vill:- 1.Tikar Maisali, 2.Agar Mulda, 3. Gora Mulda, 4. Kalikapur, 5. Kalu Rautbar all are under Bhagwanpur-II Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 132/RWS/TSD | 04/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
3003 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Instalation of display Board at 5 nos ( Vill:- 1. Bhabanipur, 2.Digha Nagar, 3.Jamalpur , 4. Kalupur, 5, Kismat Arajibar under Gurgram Panchyat & all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 128/RWS/TSD | 03/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
3004 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Instalation of display Board at 5 nos ( Vill:- 1.Gopal Dasbar, 2.Shyampur, 3. Subodhpur, 4. Uttar Shibarampur, under Bhagabanpur Panchyat 5. vill- Harma Shani, Panchayat :- Bibhisanpur all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 129/RWS/TSD | 03/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
3005 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Instalation of display Board at 5 nos ( Vill:- 1. Haturia, 2. Haturia Dalbari, 3. Kalika Danri, under Arjunnagar Panchyat 4.. vill- Jagamohan Chak, 5.Kuchai Dighi Panchayat :- Basudevberia all are under Bhagawanpur-ii Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 121RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
3006 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/16941 | New | Instalation of display Board at 5 nos ( Vill:- 1. Mirchak , Panchayat : -Basudevberia 2. Dakshin Baroj-part-i,Panchayat :- Boroj, 3. Lochananda Chak, 4. Uttar Gobinda Chak, under Garbari-ii Panchyat 5. vill- Bargopal, Panchayat :- Itaberia all are under Bhagawanpur-ii Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 117/RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
3007 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Mukutshila, Zone-II PWSS in the District of Purba Medinipur under JJM programme. , SM/16654 | Augmentation | Rejuvenation of Electro-Mechanical components of Mukutshila, Zone-II PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 765/W/MMD | 23/03/2023 | 720 | M/S EMMESS | 12.24 | 9.08 | 74.17 | 70
3008 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Narandia PWSS in the District of Purba Medinipur under JJM programme. , SM/16663 | Augmentation | Rejuvenation of Electro-Mechanical components of Narandia PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 762/W/MMD | 23/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 12.24 | 0 | 0 | 90
3009 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Narandia PWSS in the District of Purba Medinipur under JJM programme. , SM/16663 | Augmentation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0.18 | 100 | 100
3010 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Ramnagar PWSS in the District of Purba Medinipur under JJM programme. , SM/16666 | Augmentation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0.18 | 100 | 100
3011 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Ramnagar PWSS in the District of Purba Medinipur under JJM programme. , SM/16666 | Augmentation | Rejuvenation of Electro-Mechanical components of Ramnagar PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 763/W/MMD | 23/03/2023 | 718 | UNITED TRADERS | 12.24 | 7.15 | 58.39 | 45
3012 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chatra (Sahid Matangini) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16881 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3013 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Barbasudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16888 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
3014 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Barbasudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16888 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3015 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Arjunnagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16874 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at MAHAMMADPUR and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 649/HESD | 08/07/2024 | 15 | SOUMEN ELECTRIC | 1.94 | 0 | 0 | 100
3016 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Arjunnagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16874 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3017 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17871 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
3018 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17871 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3019 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Rashikachak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17889 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
3020 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Rashikachak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17889 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3021 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Haur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17775 | Solarisation | Solarization of grid connected pumping installation at Haur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1029/W/MMD | 29/03/2023 | 180 | KAMAKSHYA ENTERPRISE | 6.26 | 0 | 0 | 70
3022 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Rajarampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17784 | Solarisation | Solarization of grid connected pumping installation at Rajarampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1017/W/MMD | 29/03/2023 | 702 | P.K.ENGINEERING | 6.26 | 0 | 0 | 80
3023 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kasbagola PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17802 | Solarisation | Solarization of grid connected pumping installation at Kasbagola PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1007/W/MMD | 29/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
3024 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kasbagola PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17802 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0.18 | 96.99 | 100
3025 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Khejuri PWSS in the District of Purba Medinipur under JJM programme. , SM/16650 | Augmentation | Rejuvenation of Electro-Mechanical components of Khejuri PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 764/W/MMD | 23/03/2023 | 1678 | ORIENTAL ENGINEERING CO. | 12.24 | 0 | 0 | 60
3026 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Alinan, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17385 | Solarisation | Solarization of grid connected pumping installation at Alinan, Zone-I and Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 752/W/MMD | 23/03/2023 | 180 | A-NIK & CO. | 12.52 | 0 | 0 | 0
3027 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Rajarampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17881 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
3028 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Rajarampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17881 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3029 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chandibeniya, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17355 | Solarisation | Solarization of grid connected pumping installation at Chandibeniya, Zone-I and Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 751/W/MMD | 23/03/2023 | 180 | RSA ENTERPRISE | 12.52 | 0 | 0 | 0
3030 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dhenkua PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17830 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
3031 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dhenkua PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17830 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3032 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Anurai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17337 | Solarisation | Solarization of grid connected pumping installation at Anurai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 724/W/MMD | 23/03/2023 | 180 | M/S B.M. ELECTRICAL | 6.26 | 4.85 | 77.48 | 80
3033 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chandiveti PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17339 | Solarisation | Solarization of grid connected pumping installation at Chandiveti PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 722/W/MMD | 23/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 4.85 | 77.48 | 35
3034 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Baichberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17318 | Solarisation | Solarization of grid connected pumping installation at Baichberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 735/W/MMD | 23/03/2023 | 180 | M/S B.M. ELECTRICAL | 6.26 | 0 | 0 | 0
3035 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dakshin Gumai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17839 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
3036 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dakshin Gumai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17839 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3037 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mahisda Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17840 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3038 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Basudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17347 | Solarisation | Solarization of grid connected pumping installation at Basudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 727/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
3039 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Basudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17347 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0.18 | 100 | 50
3040 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Anantapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17349 | Solarisation | Solarization of grid connected pumping installation at Anantapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 753/W/MMD | 23/03/2023 | 180 | JYOTY SOLAR POWER | 12.52 | 0 | 0 | 0
3041 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bishnubarh PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17322 | Solarisation | Solarization of grid connected pumping installation at Bishnubarh PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 748/W/MMD | 23/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 6.26 | 0 | 0 | 0
3042 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Gopalpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17845 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
3043 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Gopalpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17845 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3044 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Saripur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17846 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
3045 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Saripur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17846 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3046 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kotbar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17868 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
3047 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kotbar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17868 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3048 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dakshin Gumai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17336 | Solarisation | Solarization of grid connected pumping installation at Dakshin Gumai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 737/W/MMD | 23/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 4.85 | 77.48 | 60
3049 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dakshin Gumai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17336 | Solarisation | Quotation bill for application fees of NET METERING for solar power plant at Dakshin Gumai w/s scheme,Block-Nandakumar in the Dist. of Purba Medinipur under MMD PHE Dte. Name of C.C.C.-Nandakumar Application No.-2004846721 Consumer ID-222053458 Issuance Date-01/08/2024 | C092443143922 | 27/09/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
3050 | PURBA MEDINIPUR | Tamluk Division | KAINARA & IT'S ADJOING MOUJAS , SM/12514 | New | Material Requisition To Resource Division | 2698/TD | 06/02/2023 | 0 | Resource Division | 65.99 | 0 | 0 | 0
3051 | PURBA MEDINIPUR | Tamluk Division | KAINARA & IT'S ADJOING MOUJAS , SM/12514 | New | Material Requisition To Resource Division | 102/TD | 05/01/2024 | 0 | Resource Division | 13.76 | 0 | 0 | 0
3052 | PURBA MEDINIPUR | Midnapore Mechanical | KAINARA & IT'S ADJOING MOUJAS , SM/12514 | New | Quotation Bill for New Service connection at T/W NO-II Of KAINARA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004738882/QUOT/03 DT. 17-05-2024 Application NO-2004738882 Application type-New connection Consumer Id- 204309127 | BP-2024-25-226 | 31/05/2024 | 0 | WBSEDCL | 4.09 | 0 | 0 | 0
3053 | PURBA MEDINIPUR | Midnapore Mechanical | KAINARA & IT'S ADJOING MOUJAS , SM/12514 | New | Quotation for new service connection at TW-I of KAINARA WS SCHEME under MMD,PHE Dte, Block-Ramnagar-I, DIGHA CCC, Application no-2004644445, CON ID-204246842 | BP-2023-24-914 | 28/03/2024 | 0 | WBSEDCL | 6.46 | 0 | 0 | 0
3054 | PURBA MEDINIPUR | Midnapore Mechanical | KAINARA & IT'S ADJOING MOUJAS , SM/12514 | New | Quotation Bill for Shifting of LT POLE AT KAINARA T/W NO-I , BLOCK: RAMNAGRA -I WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. MEMO No- DGA/QT/1042 Dt. 17.09.2024 Application NO- 100000119117 Dt. 17/09/2024 Reference Id- 860313097 | C102415728122 | 05/10/2024 | 0 | WBSEDCL | 0.33 | 0 | 0 | 0
3055 | PURBA MEDINIPUR | Tamluk Division | KAINARA & IT'S ADJOING MOUJAS , SM/12514 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2813 Nos) For 2 nos Pipe Water Supply Scheme (Kainara & Nilkanthpur)including two years Operation & Maintainance work within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 2710/TD | 30/10/2023 | 790 | TAPAS SANTRA | 866.03 | 368.95 | 66.51 | 85
3056 | PURBA MEDINIPUR | Midnapore Mechanical | KAINARA & IT'S ADJOING MOUJAS , SM/12514 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAINARA and ADJOINING MOUJAS, Block - Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 527/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 21.72 | 91.64 | 75
3057 | PURBA MEDINIPUR | Central Drilling | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS , SM/13856 | New | Providing drilling crew and other allied works for construction of Tube Well ( 150mm X150mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Simulberia W/S Scheme (T/W-I & II) , Sutahatal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 1397/CDD | 19/09/2023 | 30 | MENAKA ENTERPRISE | 13.38 | 0 | 0 | 0
3058 | PURBA MEDINIPUR | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS , SM/13856 | New | Material Requisition To Resource Division | 3004/TD | 27/02/2023 | 0 | Resource Division | 5.27 | 0 | 0 | 0
3059 | PURBA MEDINIPUR | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS , SM/13856 | New | Installation of 1 Nos. Display Board at Simulberya PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase -VIII) | 769/HSD, | 27/02/2024 | 7 | SNEHASIS BERA | 0.21 | 0.21 | 100 | 100
3060 | PURBA MEDINIPUR | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS , SM/13856 | New | Material Requisition To Resource Division | 642/W | 20/02/2024 | 0 | Resource Division | 2.94 | 0 | 0 | 0
3061 | PURBA MEDINIPUR | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS , SM/13856 | New | payment of Wayleave plan & survey charges SER-KGP-2024-WL-104 | BP-2024-25-190 | 14/06/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0 | 0
3062 | PURBA MEDINIPUR | Midnapore Mechanical | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS , SM/13856 | New | Quotation bill for new service connection at TW-I of Simulberia w/s scheme,Block-Sutahata,under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695156 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-6000W | BP-2024-25-109 | 06/05/2024 | 0 | WBSEDCL | 8.39 | 0 | 0 | 0
3063 | PURBA MEDINIPUR | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS , SM/13856 | New | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-104) | BP-2024-25-300 | 30/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.21 | 0 | 0 | 0
3064 | PURBA MEDINIPUR | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS , SM/13856 | New | payment of Wayleave plan & survey charges SER-KGP-2024-WL-105 | BP-2024-25-191 | 14/06/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0 | 0
3065 | PURBA MEDINIPUR | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS , SM/13856 | New | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-105) | BP-2024-25-299 | 30/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.27 | 0 | 0 | 0
3066 | PURBA MEDINIPUR | Midnapore Mechanical | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS , SM/13856 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SIMULBERYA and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 553/W/MMD | 20/03/2023 | 684 | DEBJYOTI BASU | 21.62 | 8.99 | 41.59 | 46
3067 | PURBA MEDINIPUR | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS , SM/13856 | New | Sinking of Tube Well, Construction of Pump House, Boundary Wall, Laying of Rising main, Sub-Soil investigation, Construction of OHR - 50 Cum, Laying of Distribution pipe line and FHTC work (477 nos) Including 2 years of Operation & Maintenance under JJM with alied work for ground water based Simulberya Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. | 881/TD | 01/06/2023 | 914 | BARH CONSTRUCTION | 177.2 | 44.07 | 24.87 | 30
3068 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme , SM/06881 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Amtalia PWSS Block Contai-II in the District of Purba Medinipur. | 2104/TD | 05/11/2020 | 180 | ARABINDA GHOSH | 96.58 | 40.55 | 100 | 100
3069 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme , SM/06881 | Retrofitting | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. | 635/W | 13/01/2021 | 0 | ARABINDA GHOSH | 54.93 | 0 | 0 | 0
3070 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme , SM/06881 | Retrofitting | Providing FHTC with allied works of Aladarput and its adjoining mouzas water supply scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1109 / CSD | 23/12/2022 | 30 | MRINAL KANTI PRADHAN | 2.85 | 0 | 0 | 90
3071 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme , SM/06881 | Retrofitting | Instalation of display Board at different work site of Amtalia PWSS (Retrofitting) in Deshpran Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2337/CSD | 29/12/2023 | 7 | AMIT PAYRA | 0.21 | 0.21 | 100 | 100
3072 | PURBA MEDINIPUR | Tamluk Division | BARTTANA & IT'S ADJOINING MOUJAS PWSS , SM/13697 | New | Material Requisition To Resource Division | 2418/TD | 16/01/2023 | 0 | Resource Division | 43.87 | 0 | 0 | 0
3073 | PURBA MEDINIPUR | Tamluk Division | BARTTANA & IT'S ADJOINING MOUJAS PWSS , SM/13697 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Barttana PWSS at Egra-I Block under Tamluk Division, PHE Dte. | 2074/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3074 | PURBA MEDINIPUR | Midnapore Mechanical | BARTTANA & IT'S ADJOINING MOUJAS PWSS , SM/13697 | New | Quotation Bill for New Service connection at T/W NO-I Of BARTANA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004660093/QUOT/03 DT. 01-04-2024 Application NO- 2004672007 Application type-New connection Consumer Id- 204261081 | BP-2024-25-96 | 24/04/2024 | 0 | WBSEDCL | 5.33 | 0 | 0 | 0
3075 | PURBA MEDINIPUR | Tamluk Division | BARTTANA & IT'S ADJOINING MOUJAS PWSS , SM/13697 | New | Quotation Bill for New Service connection at T/W NO-II Of BARTANA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004874714/QUOT/03/296 DT. 03-09-2024 Application NO- 2004874714 Application type-New connection Consumer Id- 204386343 | BP-2024-25-631 | 26/11/2024 | 0 | WBSEDCL | 14.38 | 0 | 0 | 0
3076 | PURBA MEDINIPUR | Midnapore Mechanical | BARTTANA & IT'S ADJOINING MOUJAS PWSS , SM/13697 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARTTANA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 565/W/MMD | 20/03/2023 | 864 | DEY ENTERPRISE | 22.8 | 0 | 0 | 55
3077 | PURBA MEDINIPUR | Tamluk Division | BARTTANA & IT'S ADJOINING MOUJAS PWSS , SM/13697 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 270.06 | 54.67 | 51
3078 | PURBA MEDINIPUR | Tamluk Division | PURANDA AND IT'S ADJOINING MOUJAS PWSS , SM/12818 | New | Material Requisition To Resource Division | 2414/TD | 16/01/2023 | 0 | Resource Division | 25.18 | 0 | 0 | 0
3079 | PURBA MEDINIPUR | Tamluk Division | PURANDA AND IT'S ADJOINING MOUJAS PWSS , SM/12818 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Puronda PWSS at Egra-I Block under Tamluk Division, PHE Dte. | 2194/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3080 | PURBA MEDINIPUR | Midnapore Mechanical | PURANDA AND IT'S ADJOINING MOUJAS PWSS , SM/12818 | New | Quotation Bill for New Service connection at T/W NO-II Of PURANDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674845/QUOT/03 DT. 09-04-2024 Application NO- 2004674845 Application type-New connection Consumer Id- 204269900 | BP-2024-25-83 | 24/04/2024 | 0 | WBSEDCL | 3.69 | 0 | 0 | 0
3081 | PURBA MEDINIPUR | Midnapore Mechanical | PURANDA AND IT'S ADJOINING MOUJAS PWSS , SM/12818 | New | Quotation Bill for New Service connection at T/W NO-I Of PURANDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674832/QUOT/03 DT. 09-04-2024 Application NO- 2004674832 Application type-New connection Consumer Id- 204269889 | BP-2024-25-82 | 24/04/2024 | 0 | WBSEDCL | 6.05 | 0 | 0 | 0
3082 | PURBA MEDINIPUR | Tamluk Division | PURANDA AND IT'S ADJOINING MOUJAS PWSS , SM/12818 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 229.97 | 54.71 | 51
3083 | PURBA MEDINIPUR | Midnapore Mechanical | PURANDA AND IT'S ADJOINING MOUJAS PWSS , SM/12818 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURANDA and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 512/W/MMD | 20/03/2023 | 925 | GLACIER ENGINEERING CO. | 22.8 | 16.25 | 73.22 | 100
3084 | PURBA MEDINIPUR | Tamluk Division | BARTTAN AND ADJOINING MOUJAS PWSS , SM/12501 | New | Material Requisition To Resource Division | 2724/TD | 06/02/2023 | 0 | Resource Division | 35.45 | 0 | 0 | 0
3085 | PURBA MEDINIPUR | Tamluk Division | BARTTAN AND ADJOINING MOUJAS PWSS , SM/12501 | New | Material Requisition To Resource Division | 95/TD | 05/01/2024 | 0 | Resource Division | 18.95 | 0 | 0 | 0
3086 | PURBA MEDINIPUR | Midnapore Mechanical | BARTTAN AND ADJOINING MOUJAS PWSS , SM/12501 | New | Barttan W/S scheme T/W no.-II(Tower) Application-2004521219 Ref.-204156075 | BP-2023-24-477 | 27/12/2023 | 0 | WBSEDCL | 3.01 | 0 | 0 | 0
3087 | PURBA MEDINIPUR | Midnapore Mechanical | BARTTAN AND ADJOINING MOUJAS PWSS , SM/12501 | New | Barttan W/S scheme T/W no.-I(Tower) Application-2004521240 Ref.-204156076 | BP-2023-24-478 | 27/12/2023 | 0 | WBSEDCL | 2.93 | 0 | 0 | 0
3088 | PURBA MEDINIPUR | Tamluk Division | BARTTAN AND ADJOINING MOUJAS PWSS , SM/12501 | New | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3076 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Barttan PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 452/TD | 04/05/2023 | 876 | TARUN KOLEY | 782.24 | 344.73 | 44.07 | 45
3089 | PURBA MEDINIPUR | Midnapore Mechanical | BARTTAN AND ADJOINING MOUJAS PWSS , SM/12501 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARTTAN and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 473/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 25.26 | 18.96 | 76.79 | 100
3090 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Sofiabad Piped Water Supply Scheme , SM/07093 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS Block-Contai-II (Deshpran) in the District of Purba Medinipur. | 2792/TD | 01/02/2021 | 60 | RELIABLE CONSTRUCTIONS | 70.61 | 34.76 | 49.23 | 100
3091 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Sofiabad Piped Water Supply Scheme , SM/07093 | Retrofitting | Retrofitting to accomodate FHTC under JJM Sofiabad W/S Scheme within Deshapran Dev. Block under Tamluk Division, PHE Dte. | 993/W | 26/03/2021 | 0 | RELIABLE CONSTRUCTIONS | 35.85 | 0 | 0 | 0
3092 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla Piped Water Supply Scheme , SM/07097 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chirulia-Chatla PWSS Block Egra-I in the District of Purba Medinipur. | 2770/TD | 28/01/2021 | 60 | FIROZ KHAN | 96.97 | 0 | 0 | 100
3093 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla Piped Water Supply Scheme , SM/07097 | Retrofitting | Retrofitting to accomodate FHTC under JJM Chirulia - Chatla W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. | 229/W | 07/09/2021 | 0 | FIROZ KHAN | 35.28 | 0 | 0 | 0
3094 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla Piped Water Supply Scheme , SM/07097 | Retrofitting | Retrofitting to accomodate FHTC under JJM Chirulia - Chatla W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-80 | 17/09/2021 | 0 | FIROZ KHAN | 15.36 | 0 | 0 | 0
3095 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla Piped Water Supply Scheme , SM/07097 | Retrofitting | Retrofitting to accomodate FHTC under JJM Chirulia - Chatla W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. | 970/W | 23/03/2021 | 0 | FIROZ KHAN | 44.72 | 0 | 0 | 0
3096 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla Piped Water Supply Scheme , SM/07097 | Retrofitting | Retrofitting to accomodate FHTC under JJM Chirulia W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-40 | 23/07/2021 | 0 | FIROZ KHAN | 3.74 | 0 | 0 | 0
3097 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme , SM/06880 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Dariapur PWSS Block Contai-II in the District of Purba Medinipur. | 2108/TD | 05/11/2020 | 180 | RAJ KUMAR SINGHA | 79.23 | 0 | 0 | 100
3098 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme , SM/06880 | Retrofitting | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. | 636/W | 13/01/2021 | 0 | RAJ KUMAR SINGHA | 76.24 | 0 | 0 | 0
3099 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme , SM/06880 | Retrofitting | Land Development at Head Work Site of Dariapur PWSS within Desopran Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1584/CSD | 16/08/2023 | 15 | JASODA ENTERPRISE | 0.53 | 0.53 | 100 | 100
3100 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Aladarput W/S Scheme , SM/06882 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Aladarput PWSS Block Contai-II in the District of Purba Medinipur. | 2105/TD | 05/11/2020 | 180 | TARUN KOLEY | 96.5 | 188.57 | 195.4 | 100
3101 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Aladarput W/S Scheme , SM/06882 | Retrofitting | Providing FHTC with allied works of Aladarput and its adjoining mouzas water supply scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1109 / CSD | 23/12/2022 | 30 | MRINAL KANTI PRADHAN | 2.85 | 0 | 0 | 90
3102 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Uttar Khasda W/S Scheme , SM/06885 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Uttar Khasda PWSS Block Contai-I in the District of Purba Medinipur. | 2103/TD | 05/11/2020 | 180 | SRIMANTA KUMAR MAITY | 96.46 | 0 | 0 | 100
3103 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Uttar Khasda W/S Scheme , SM/06885 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Uttar Khasda W/S Scheme within Contai - I Block under Tamluk Division, PHE Dte. | 649/W | 25/01/2021 | 0 | SRIMANTA KUMAR MAITY | 87.27 | 0 | 0 | 0
3104 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IXA , SM/07113 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -IXA Block Panskura-II in the District of Purba Medinipur. | 2630/TD | 05/01/2021 | 60 | RAJ KUMAR SINGHA | 96.85 | 193.4 | 199.69 | 100
3105 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Baharchandberya W/S Scheme under Deshapran Block. , SM/07655 | Retrofitting | Retrofitting to accomodate FHTC under JJM Baharchand Berya W/S Scheme under Tamluk Division, PHE Dte. | 1119/W | 30/03/2021 | 0 | DIPAK KUMAR BAKLY | 23.16 | 0 | 0 | 0
3106 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Baharchandberya W/S Scheme under Deshapran Block. , SM/07655 | Retrofitting | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Baharchandberya W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land) | 484/TD | 10/05/2023 | 60 | END POINT STRUCTURAL DEPARTMENT | 3.58 | 0 | 0 | 0
3107 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Baharchandberya W/S Scheme under Deshapran Block. , SM/07655 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS Block -Contai-II (Deshpran) in the District of Purba Medinipur. | 2802/TD | 04/02/2021 | 45 | DIPAK KUMAR BAKLY | 111.16 | 39.05 | 98.04 | 70
3108 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" in between N.P.-28-30,50-51,57-58,41-42,44-46,30-31,6-7,11-14,78-76,291-293,18-20,165-167,122-123,91-92 & 90-91 under Barasubarnanagar W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 339 / CSD | 10/11/2020 | 21 | JASODA ENTERPRISE | 2.48 | 0 | 0 | 0
3109 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" in between N.P.-98-99,99-100,100-101,59-61,76-77,18-19,51-24,13-14 & 72-68 under Sofiabad W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 340 / CSD | 10/11/2020 | 21 | KAMAL KUMAR BERA | 1.99 | 0 | 0 | 0
3110 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Madhakhali W/S Scheme of Contai Sub- Division under Tamluk Division, PHE Dte, Purba Medinipur. | 399 / CSD | 24/12/2020 | 21 | SUBHRANGSHU SEKHAR GIRI | 2.45 | 0 | 0 | 0
3111 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Mukutshila Zone-II W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 347/CSD | 24/11/2020 | 21 | SUBRATA KUMAR BERA | 2.78 | 2.78 | 100 | 0
3112 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" in between 126-127,127-129,79-82,3-4,84-89,90-92,60-62,39-41,12-16,68-72,101-99,74-75 & 87-88 under HAIPUR W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 411 / CSD | 29/12/2020 | 21 | SRIMANTA KUMAR MAITY | 2.37 | 2.37 | 100 | 0
3113 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Baghaput W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 372 / CSD | 09/12/2020 | 21 | M/S MONDAL CONSTRUCTION & CO. | 1.89 | 1.89 | 100 | 0
3114 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Sapai W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 380 / CSD | 14/12/2020 | 21 | AHINDRA BARIK | 1.65 | 1.65 | 100 | 0
3115 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats supercyclonic Storm "AMPHAN" under Kanakpur W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 331 / CSD | 05/11/2020 | 21 | SRIMANTA KUMAR MAITY | 1.51 | 1.5 | 100 | 0
3116 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Bagmari W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 333 / CSD | 09/11/2020 | 21 | BIBEKANANDA DAS | 1.77 | 1.77 | 100 | 0
3117 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Murisai W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 377 / CSD | 11/12/2020 | 21 | MRINAL KANTI PRADHAN | 1.93 | 1.93 | 100 | 0
3118 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Kumirda W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 390 / CSD | 21/12/2020 | 21 | PARIA ENTERPRISE | 2.56 | 2.56 | 100 | 0
3119 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Contai Municipality W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 396 / CSD | 21/12/2020 | 21 | SUBHRANGSHU SEKHAR GIRI | 0.99 | 3.24 | 100 | 0
3120 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN"in between N.P. 103-105,106-117,127-128,142-144,160-161,111-158,118-120,157-801,120-156,140-135,164-805,170-171 &136-135 under Bamunia W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 341/CSD | 10/11/2020 | 21 | GIRI CONSTRUCTION | 2.46 | 2.46 | 100 | 0
3121 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Pratapdighi W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 338 / CSD | 10/11/2020 | 21 | GIRI CONSTRUCTION | 2.99 | 2.99 | 100 | 0
3122 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" in between N.P.-125-128,13-16,125-126,134-135,150-153 & 174-175 under BANKIPUT W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur | 345 / CSD | 23/11/2020 | 21 | GITA ENTERPRISE | 2.46 | 2.46 | 100 | 0
3123 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Nijkasba W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 410 / CSD | 29/12/2020 | 21 | PURNA CHANDRA BARH | 1.15 | 1.15 | 100 | 0
3124 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Jalpai Part-II Water supply Scheme within Nandigram-II Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 854/HSD | 18/03/2021 | 15 | BHOWMIK & SONS | 2.54 | 0 | 0 | 0
3125 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Dariapur Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 2762/TD | 27/01/2021 | 30 | S. A. ENTERPRISE | 4.81 | 0 | 0 | 0
3126 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Contai S.A. Zone-II Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 3392/TD | 26/03/2021 | 21 | SRIMANTA KUMAR MAITY | 4.82 | 4.82 | 100 | 0
3127 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Repair of damaged Boundary Wall due to Amphoon Cyclone at Head work site of Begunberia Water Supply. Scheme under Haldia Sub-Division in Tamluk Division, P.H.E. Dte. Purba Medinipur. | 3402/TD | 26/03/2021 | 15 | RAI CONSTRUCTION | 4.6 | 4.6 | 100 | 0
3128 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Contai S.A. Zone-I Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 3391/TD | 26/03/2021 | 21 | SRIMANTA KUMAR MAITY | 4.84 | 4.84 | 100 | 0
3129 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Amtalia Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 2138/TD | 09/11/2020 | 21 | PARIA ENTERPRISE | 4.84 | 4.84 | 100 | 0
3130 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Khejuri Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 3393/TD | 26/03/2021 | 21 | GIRI ENTERPRISE | 4.82 | 4.82 | 100 | 0
3131 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" in between N.P.-130-150,182-183,184-161,152-156,93-96,156-160,164-170,111-114,129-131,135-139,140-150,156-157,164-165,121-123,191-192 &160-161 under HAIPUR Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 3394/TD | 26/03/2021 | 21 | SRIMANTA KUMAR MAITY | 3.46 | 3.46 | 100 | 0
3132 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Talda Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 3396/TD | 26/03/2021 | 21 | BADAL CHANDRA GOLE | 4.26 | 4.14 | 100 | 0
3133 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Bhagwanpur Zone-I Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 3380/TD | 26/03/2021 | 21 | SRIMANTA KUMAR MAITY | 3.22 | 3.21 | 100 | 0
3134 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Bhajachauli Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 3387/TD | 26/03/2021 | 21 | BIBEKANANDA DAS | 4.81 | 4.81 | 100 | 0
3135 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Chandiveti Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 3388/TD | 26/03/2021 | 21 | SUSANTA KUMAR KAR | 4.21 | 4.21 | 100 | 0
3136 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Durmuth Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 3389/TD | 26/03/2021 | 21 | PRANAB KUMAR DAS | 4.84 | 4.84 | 100 | 0
3137 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" in between N.P.-71-72,72-79,76-80,80-86,92-98,16-17,88-89,99-118,18-26,54-64,52-48,34-35,35-36,32-34,8-10,5-7 & 29-30 under BANKIPUT Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 2139/TD | 09/11/2020 | 21 | GITA ENTERPRISE | 3.35 | 3.35 | 100 | 0
3138 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Amarshikasba Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 3390/TD | 26/03/2021 | 21 | M/S. NEW DINDA ENTERPRISE | 4.43 | 4.33 | 100 | 0
3139 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Contai S.A. Zone-III Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 3381/TD | 26/03/2021 | 21 | PRANAB KUMAR DAS | 3.4 | 3.4 | 100 | 0
3140 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats supercyclonic Storm "AMPHAN" under Contai Saline Area Zone-IV W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 368 / CSD | 03/12/2020 | 21 | SUBHENDU HAZRA | 1.23 | 1.23 | 100 | 0
3141 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Repair of pump house due to Amphoon Cyclone at 1st Tube well site of Solat water supply scheme under Haldia Sub-Division P.H.E. Dte. | 293/HSD | 15/09/2021 | 15 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 1.04 | 1.03 | 100 | 0
3142 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Repair of damaged Boundary Wall due to Amphoon Cyclone at 2nd Tube well site of Begunberia W/S. Scheme under Haldia Sub-Division in Tamluk Division, P.H.E. Dte. Purba Medinipur. (As per deptt. Drawing and design) | 856/HSD | 18/03/2021 | 15 | SK. MD. MAINUL ISLAM | 2.91 | 2.55 | 100 | 0
3143 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Mahammadpur Water supply Scheme within Nandigram-I Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 855 | 18/03/2021 | 15 | TAPAN BERA | 2.01 | 2 | 100 | 0
3144 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats supercyclonic Storm "AMPHAN" under Aladarput Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 2134/TD | 09/11/2020 | 21 | MRINAL KANTI PRADHAN | 3.33 | 3.07 | 100 | 0
3145 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm 'AMPHAN' under Dariapur W/S Scheme under Tamluk Division, PHE Dte | BP-2022-23-92 | 14/06/2022 | 0 | S.A. ENTERPRISE | 4.81 | 0 | 0 | 0
3146 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Construction of Double Durma Mat works for temporary protection of Govt. materials of Ghatua store under Cotai Sub-Division of Tamluk Division P.H.E. Dte,Purba Medinipur. | 34 / CSD | 27/05/2020 | 7 | BAGLAMUKHI SECURITY SERVICE | 0.37 | 0.37 | 100 | 0
3147 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Repairing of existing Store Room cum Guard Room with sanitary & water supply arrangements including Plinth Protection of Ghatua Store due to combats cyclonic Storm "AMPHAN" within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. | 1089/TD | 25/08/2022 | 40 | M/S. NEW DINDA ENTERPRISE | 5.79 | 0 | 0 | 0
3148 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Construction of Double Durma Mat works for temporary protection of Govt. materials of Mukutshila store under Cotai Sub-Division of Tamluk Division P.H.E. Dte,Purba Medinipur. | 35 / CSD | 27/05/2020 | 7 | BAGLAMUKHI SECURITY SERVICE | 0.22 | 0.22 | 100 | 0
3149 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Junbani Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | 3395/TD | 26/03/2021 | 21 | BASANTA KUMAR MAITY | 4.79 | 4.79 | 100 | 0
3150 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Repairing of staircase and related works for R.C.C. Over Head Reservoir of capacity 100 Cum after effect of AMPHAN at Contai-II (Deshpran) Block within Bankiput W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | 544 / CSD | 01/12/2021 | 21 | GITA ENTERPRISE | 1.65 | 1.65 | 100 | 0
3151 | PURBA MEDINIPUR | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d , SM/09357 | Disaster | Repairing & Renovation of existing Sherkhanchak Laboratory Building with sanitary & water supply arrangements including Plinth Protection,Drain,Internal road due to super cyclonic Storm "AMPHAN" within Khejuri - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 516 / CSD | 08/08/2022 | 30 | THE GOD FATHER TRADING & CO. | 2.38 | 2.32 | 100 | 0
3152 | PURBA MEDINIPUR | Central Drilling | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II , SM/08751 | Retrofitting | ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MX200MMX250 MTRS DEPTH) WITH UPVC PIPE BY DIRECT ROTARY RIG MACHINES JOHN-1000 UNDER CMSD-I (D), CDD, PHE DTE. | 1402/CDD | 10/02/2022 | 30 | ASHUTOSH DAS & CO | 11.32 | 4.77 | 42.14 | 100
3153 | PURBA MEDINIPUR | Central Drilling | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II , SM/08751 | Retrofitting | additional compressor development of the newly construction tube well at argoal w/s scheme 2nd tw site, block-pataspur -ii under CMSD-I (D), CDD, PHE DTE. | 63/CMSD-I | 18/03/2021 | 3 | ASHUTOSH DAS & CO | 0.49 | 0.12 | 100 | 100
3154 | PURBA MEDINIPUR | Central Drilling | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II , SM/08751 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL ARGOAL W/S SCHEME 2ND TW-II SITE UNDER CMSD-I (D), CDD, PHE DTE. | 51 /CMSD-I (D) | 25/02/2021 | 7 | ASHUTOSH DAS & CO | 0.95 | 0.95 | 100 | 100
3155 | PURBA MEDINIPUR | Central Drilling | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II , SM/08751 | Retrofitting | COMPRESSOR DEVELOPMENT OF THE NEWLY CONSTRUCTION TUBE WELL AT ARGOAL W/S SCHEMW 2ND TW SITE, BLOCK-PATASHPUR-II UNDER CMSD-I (D), CDD, PHE DTE. | 54/ CMSD-I (D) | 01/03/2021 | 7 | WEST BENGAL ENGINEERING CO. | 0.32 | 0.32 | 100 | 100
3156 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II , SM/08751 | Retrofitting | Retrofitting to accomodate FHTC (400 nos.) under JJM in Argoal PWSS Block - Potashpur-II under Contai Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Phase - II) | 682/TD | 10/09/2021 | 20 | DAS ENTERPRISE | 44.39 | 35.17 | 79.23 | 100
3157 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanaidighi W/S Scheme under Contai-III Block (PHASE-II) , SM/08224 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kanaidighi PWSS Block Contai - III in the district of Purba Medinipur under Tamluk Division, PHE Dte.(Phase-II) | BP-2021-22-131 | 18/10/2021 | 0 | DAS ENTERPRISE | 27.23 | 0 | 0 | 0
3158 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanaidighi W/S Scheme under Contai-III Block (PHASE-II) , SM/08224 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kanaidighi PWSS Block- Contai-III in the District of Purba Medinipur.(Phase-II) | 82/TD | 11/05/2021 | 30 | DAS ENTERPRISE | 96.02 | 59.46 | 100 | 100
3159 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanaidighi W/S Scheme under Contai-III Block (PHASE-II) , SM/08224 | Retrofitting | Repair and Renovation of Pump House & R.C.C. Elevated Reservoir of capacity 350 cum with Sanitary and water supply arrangement and others allied works for Head works & 2nd Tube well site and Boundary Wall at 2nd TW Site at Kanaidighi Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 3337/TD | 22/10/2024 | 40 | PARTHA CONSTRUCTION | 10.87 | 0 | 0 | 0
3160 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Surface Water Based W/S Scheme for Zone X (Balance Work) Block Kolaghat in the district of Purba Medinipur under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-III) , SM/09051 | Retrofitting | Laying left out pipe line and Retrofitting to accommodate FHTC (1600 Nos.) under JJM in Surface Water Based Water Supply Scheme for Zone-X (Balance work) Block- Kolaghat in the District of Purba Medinipur under Tamluk Sub Division of Tamluk Division,PHE Dte (Phase-III) . | 1066/TD | 08/11/2021 | 30 | JAYANTA KUMAR MONDAL | 84.04 | 84.01 | 100 | 100
3161 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Retrofitting to accommodate of 570 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-B) | 1791/TD | 08/02/2022 | 30 | SNEHESH SEN | 86.32 | 64.26 | 74.44 | 100
3162 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Retrofitting to accommodate of 260 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-E) | 1794/TD | 08/02/2022 | 25 | AHINDRA BARIK | 30.12 | 19.73 | 65.5 | 70
3163 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Retrofitting to accommodate of 110 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-I) | 1798/TD | 08/02/2022 | 20 | S.A. ENTERPRISE | 11.89 | 9.44 | 79.37 | 100
3164 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Dismantling of existing OHR (Capacity 55000 Gallons) at Head work Site of Murisai Water Supply Scheme including carriage of old materials to store under Contai Sub-Division of Tamluk Division, P.H.E. Dte. | 453/TD | 06/08/2021 | 30 | M/S B. N. ENTERPRISES | 7.62 | 6.4 | 100 | 100
3165 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Murisai Water Supply Scheme under Tamluk Division, PHE Dte. | 1610/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.3 | 3.67 | 100 | 100
3166 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Supply and Delivery of 80 mm & 125 mm Sluice Valve for Murisai piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 436-A/TD | 30/05/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 6.67 | 6.67 | 100 | 100
3167 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Retrofitting to accommodate of 419 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-C) | 1792/TD | 08/02/2022 | 30 | LOKENATH ENTERPRISES | 64.86 | 61.94 | 95.5 | 100
3168 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Retrofitting to accommodate of 620 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-A) | 1790/TD | 08/02/2022 | 30 | MAITY CONSTRUCTION | 89.06 | 82.85 | 93.03 | 100
3169 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Retrofitting to accommodate of 210 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-D) | 1793/TD | 08/02/2022 | 25 | MRINAL KANTI PRADHAN | 35.66 | 34.09 | 95.61 | 100
3170 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tubewell Site (Mouza- Uttar Ektarpur, JL No. - 136, Plot No. 38) of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 478/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 13.41 | 0 | 0 | 0
3171 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Canal crossing of Distribution pipe line for Augmentation of Murisai & its adjoining mouzas W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (N.P.-410-415 & N.P.-181-190) (Length = 2nos x15.00 Mtr.= 30.00 mtr.) | 1282/TD | 12/09/2022 | 21 | AHINDRA BARIK | 3.63 | 0 | 0 | 0
3172 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 811/W/MMD | 24/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 13.75 | 8.29 | 60.29 | 60
3173 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Supply and Delivery of 80 mm & 125 mm Sluice Valve for Murisai piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 450/TD | 31/05/2022 | 20 | RAMASISH ENTERPRISE | 0.31 | 0.31 | 100 | 100
3174 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Laying Distribution main for Augmentation of Murisai Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. N.P. 4-8, & 8-12 | 1426/TD | 26/09/2022 | 15 | CHANDA AGENCIES | 4.18 | 4.18 | 100 | 100
3175 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Material Requisition To Resource Division | 1345/TD | 23/12/2021 | 0 | Resource Division | 20.82 | 0 | 0 | 0
3176 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Material Requisition To Resource Division | 1835/TD | 15/02/2022 | 0 | Resource Division | 14.73 | 0 | 0 | 0
3177 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Instalation of display Board at different work site of Augmentation of Murisai-3 nos., Junbani-1 no., Bhagwanpur Zone-I- 1 no.,Bhagwanpur Zone-II- 1 no., Contai Saline Area Zone-III (Phase-A)- 1no. & Contai Saline Area Zone-III (Phase-B)- 1no. PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 811 / CSD | 21/10/2022 | 15 | MRINAL KANTI PRADHAN | 0.93 | 0.93 | 100 | 100
3178 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Basudebbrya, JL No. 428 Plot No. 2879) of Basudebberya Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tubewell Site (Mouza- Uttar Ektarpur, JL No. - 136, Plot No. 38) of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 2048/TD | 25/08/2023 | 40 | KALPANA BUILDERS | 34.03 | 0 | 0 | 40
3179 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Murisai PWSS at Contai-III Block under Tamluk Division, PHE Dte. | 2063/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3180 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Instalation of display Board at different work site of Baharchandberia Retrofitting PWSS in Contai - II (Deshopran) Block, Kanaidighi, Paschim Kamarda, Murisai Retrofitting PWSS in Contai - III Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2334/CSD | 29/12/2023 | 15 | BISWA NIRMAN ENTERPRISE. | 0.83 | 0.83 | 100 | 100
3181 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Quotation for new service connection at TW-III of Murisai w/s scheme under MMD, PHE Dte. Block-Contai-III, MARISHDA CCC Application n0-2004764433 Con ID-204324522 | BP-2024-25-285 | 18/06/2024 | 0 | WBSEDCL | 5.67 | 0 | 0 | 0
3182 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Retrofitting to accommodate of 180 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-G) | 1796/TD | 08/02/2022 | 1335 | JASODA ENTERPRISE | 25.5 | 24.33 | 95.42 | 100
3183 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Retrofitting to accommodate of 220 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-F) | 1795/TD | 08/02/2022 | 25 | ABHIJIT BERA | 25.4 | 24.03 | 94.59 | 100
3184 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Retrofitting to accommodate of 75 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART- J) | 1799/TD | 08/02/2022 | 1303 | LAKSHMI NARAYAN ENTERPRISE | 9.86 | 7.96 | 80.73 | 100
3185 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Well (Head Work) of Mouza- Barasubarnanagar, JL No.- 502, Plot No.-297 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Ramnagar-II Block of Kanpur Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for 2nd Tube Well of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1050/TD | 18/08/2022 | 1017 | AQUATECH ENGINEERS | 45.52 | 0 | 0 | 98
3186 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Retrofitting to accommodate of 155 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-H) | 1797/TD | 08/02/2022 | 1177 | PARIA ENTERPRISE | 22.19 | 21.33 | 96.14 | 100
3187 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Repairing of Pump Houses and Boundary Wall with allied work of Murisai PWSS in Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte | 3615/TD | 27/11/2024 | 30 | MRINAL KANTI PRADHAN | 3.4 | 0 | 0 | 0
3188 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Boundary Wall, Raising Main under JJM with allied work for Augmentation of Murisai Water Supply Scheme in Contai III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 2898/TD | 10/09/2024 | 279 | MRINAL KANTI PRADHAN | 53.73 | 0 | 0 | 40
3189 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well at Murisai Water supply scheme, Contai - III block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 782/W/MMD | 24/02/2025 | 180 | PADMA ENGINEERING CO. | 14.81 | 0 | 0 | 0
3190 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Land Filling at Replacement of 2nd Tube well site for Augmentation of Murisai Water Supply Scheme in Contai-III Dev. Block under Contai Sub-Division of Tamluk Division, PHE Dte. Dist-Purba Medinipur. | 2467/CSD | 25/10/2024 | 7 | MRINAL KANTI PRADHAN | 0.96 | 0 | 0 | 100
3191 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Strengthening of existing approach road for Replacement of 2nd Tube Well at Murisai Water Supply Scheme within Contai-III Block within Contai Sub-Division of Tamluk Division, PHE Dte. | 2468/CSD | 25/10/2024 | 7 | GANAPATI CONSTRUCTION | 0.97 | 0 | 0 | 100
3192 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Drum Sheet walling at Murisai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-A) | 1338/CSD | 02/06/2025 | 15 | MRINAL KANTI PRADHAN | 0.97 | 0 | 0 | 100
3193 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Drum Sheet walling at Murisai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-B) | 1339/CSD | 02/06/2025 | 15 | MRINAL KANTI PRADHAN | 0.96 | 0 | 0 | 100
3194 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai , SM/09446 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Augmentation of Murisai W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1283/TD | 12/09/2022 | 827 | MRINAL KANTI PRADHAN | 3.82 | 0 | 0 | 100
3195 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN KUMIRDA PWSS, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | 156/S&WSD | 12/08/2022 | 15 | PADMA ENGINEERING & CO. | 4.99 | 4.99 | 100 | 100
3196 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL IN KUMIRDA PWSS, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | 158/S&WSD | 12/08/2022 | 15 | PADMA ENGINEERING & CO. | 4.99 | 4.95 | 100 | 100
3197 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL IN KUMIRDA PWSS, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | 157/S&WSD | 12/08/2022 | 15 | PADMA ENGINEERING & CO. | 4.98 | 4.98 | 100 | 100
3198 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kumirda Water Supply Scheme under Tamluk Division, PHE Dte. | 1613/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.66 | 5.64 | 100 | 100
3199 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Kumirda Water Supply Scheme in Contai III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | 2262/TD | 30/12/2022 | 20 | CASTING CORPORATION OF INDIA | 8.5 | 8.5 | 100 | 100
3200 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | Material Requisition To Resource Division | 98/TD | 11/04/2022 | 0 | Resource Division | 40.13 | 0 | 0 | 0
3201 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | Material Requisition To Resource Division | 1274/TD | 12/09/2022 | 0 | Resource Division | 33.04 | 0 | 0 | 0
3202 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | Electric Quotation for KUMIRDA Water Supply Scheme T/W-IV, (Ref. ID-204050266) | BP-2023-24-166 | 04/08/2023 | 0 | WBSEDCL | 5.19 | 0 | 0 | 0
3203 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | Repairing and Renovation Of Pump House No. I , II & III under Augmentation of Kumirda Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | 422/CSD | 17/03/2023 | 30 | PARIA ENTERPRISE | 2.89 | 0 | 0 | 0
3204 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements at for Additional Tube well site J.L no. -155, Plot no. -1245, Mouza -Panichiary under Augmentation of Kumirda W/S Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur | 490/TD | 10/05/2023 | 60 | PARIA ENTERPRISE | 4.09 | 3.58 | 100 | 100
3205 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | Payment of wayleave facility charges(SER-KGP-2024-WL-46) | BP-2024-25-77 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.35 | 0 | 0 | 0
3206 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | Laying of Distribution pipe line And FHTC ( Functional Household tap connection ) with allied works including all for Augmentation of Kumirda Water Supply Scheme within Contai- III under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 601/TD | 20/06/2022 | 1140 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 799.74 | 517.9 | 64.76 | 70
3207 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Reservoir ( OHR) & 1st.Tube Well , 2nd , 3rd , Additional Tube Well Site, Mouza -kumirda under Augmentation of Kumirda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. Length 230.00 mtr. | 2562/TD | 24/01/2023 | 60 | M/S. PRADIP PRADHAN | 32.65 | 20.96 | 64.18 | 90
3208 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | Rising main with laying of 150 mm dia DI (K-9) from 4th Tube Well site to OHR site and other allied works for Kumirda in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 2357/CSD | 26/09/2024 | 30 | BISWA NIRMAN ENTERPRISE. | 1.61 | 0 | 0 | 100
3209 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda , SM/10128 | Augmentation | Draning out of washout & over flow water from 500 Cum Capacity Over Head Reservoir to the near by natural ditch of Augmentation of Kumirda Water Supply Scheme and its adjoining mouzas in Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 1162/TD | 22/04/2025 | 60 | SAURAV HAZRA | 4.34 | 0 | 0 | 0
3210 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10590 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mukutshila Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | 1678/TD | 27/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.72 | 4.71 | 100 | 100
3211 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10590 | Augmentation | Material Requisition To Resource Division | 1196/TD | 06/09/2022 | 0 | Resource Division | 29.7 | 0 | 0 | 0
3212 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10590 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) under JJM Program under MMD PHE Dte. | 845/W/MMD | 24/03/2023 | 180 | DEBJYOTI BASU | 35.54 | 24.61 | 69.23 | 50
3213 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10590 | Augmentation | Quotation for new service connection at Mukutshila Zone I w/s scheme PH III Additional TW in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004671631, Ref ID 204266595) | C112443271348 | 02/12/2024 | 0 | WBSEDCL | 4.59 | 0 | 0 | 0
3214 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) , SM/10590 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with Construction of R.C.C. Elevated Reservoir of Capacity 600 Cum and Staging Height of 20.0 Mtr. as per departmental drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-I Water Supply Scheme within Khejuri-I Dev. Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1575/TD | 14/10/2022 | 868 | GEE BEE NIRMAN CO PVT LTD. | 796.53 | 286.59 | 45.23 | 50
3215 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Khejurberia Water Supply Scheme under Tamluk Division, PHE Dte. | 1168/TD | 01/12/2021 | 7 | RADIANT | 8.76 | 8.65 | 100 | 100
3216 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well site of Khejurberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2555/TD | 24/01/2023 | 60 | PULAK KUMAR SAMANTA | 2.79 | 2.08 | 74.69 | 0
3217 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well sites of Khejurberia Water Supply Scheme under Tamluk-Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2556/TD | 24/01/2023 | 60 | PULAK KUMAR SAMANTA | 5.09 | 5.09 | 100 | 0
3218 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1428/TD | 26/09/2022 | 27 | PRANTIK DRILLING AGENCY | 49.66 | 29.84 | 100 | 80
3219 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Material Requisition To Resource Division | 1256/TD | 12/09/2022 | 0 | Resource Division | 50.95 | 0 | 0 | 0
3220 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Material Requisition To Resource Division | 1015/TD | 08/08/2022 | 0 | Resource Division | 69.9 | 0 | 0 | 0
3221 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Payment to WBSEDCL for Quotation Money of Pump House No. - 4 of Khejurberia PWSS under Tamluk Division, PHE Dte. | BP-2023-24-12 | 17/04/2023 | 0 | WBSEDCL | 3.87 | 0 | 0 | 0
3222 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Payment to WBSEDCL for Quotation Money for Khejurberia PWSS under Tamluk Division, PHE Dte. | BP-2022-23-818 | 24/03/2023 | 0 | WBSEDCL | 2.61 | 0 | 0 | 0
3223 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Payment to Haldia Development Authority for underground LT power cable restoration work of LED Street lighting system (damaged due to laying of underground pipe line by PHE Deptt.) at Nandakumar Bazar area under Nandakumar Block. | BP-2023-24-238 | 09/08/2023 | 0 | CHIEF EXECUTIVE OFFICER, HDA | 5.94 | 0 | 0 | 0
3224 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Amount payment to PWD Road for damaged of carriage way and road flank caused due to laying of water pipe line of Khejurberia PWSS | BP-2023-24-565 | 07/11/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.37 | 0 | 0 | 0
3225 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Crossing permission of laying HDPE pipeline along and across of NH-41 of Khejurberia Water Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 740/TD | 28/02/2024 | 20 | DONA ASSOCIATES | 9.48 | 0 | 0 | 0
3226 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | 363/W/MMD | 09/03/2023 | 180 | UNITED TRADERS | 23.68 | 22.93 | 100 | 60
3227 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 2nd tube well site of Khejurberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2554/TD | 24/01/2023 | 60 | RAI CONSTRUCTION | 2.8 | 2.8 | 100 | 100
3228 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall & fencing work over boundary work with allied work for Khejurberia PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 3204/TD | 14/03/2023 | 630 | TAPAS SANTRA | 29.62 | 0 | 0 | 30
3229 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Left out pipe line of Providing Functional Household Tap Connection of Khejurberia water supply scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | 622/TD | 17/05/2023 | 30 | TAPAS SANTRA | 77.24 | 77.23 | 100 | 100
3230 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Restoration work at Panskura Durgachak road from Ch. 38.400 km to Ch. 38.404 Km (length-4.40 m) after laying pipe line by PHE. | 1280/TSD | 15/09/2023 | 20 | MIHIR SAMANTA | 2.99 | 2.99 | 100 | 100
3231 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well sites of Khejurberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2553/TD | 24/01/2023 | 60 | ANIRBAN MONDAL | 4.79 | 4.19 | 100 | 100
3232 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Water supply & sanitary arrangement for Switch Room cum chlorine Room (pump House no-II) at Khejurberia PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1688/TSD | 15/12/2023 | 24 | TECHNO ENTERPRISE. | 0.96 | 0.96 | 100 | 100
3233 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Left out pipe line of Providing Functional Household Tap Connection & construction of new drain of Khejurberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | 3268/TD | 04/10/2024 | 90 | MISHRA ENTERPRISE | 44.78 | 4.96 | 10.1 | 100
3234 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Payment to Haldia Development Authority for underground LT power cable restoration work of LED Street lighting system (damaged due to laying of underground pipe line by PHE Deptt.) at Nandakumar Bazar area under Nandakumar Block. | BP-2024-25-454 | 24/09/2024 | 0 | CHIEF EXECUTIVE OFFICER, HDA | 1.31 | 0 | 0 | 0
3235 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. , SM/10684 | Augmentation | Laying of Distribution pipe line to accommodate FHTC (8284 nos) with new construction of R.C.C. Elevated Reservoir of capacity 1000cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejurberia Water Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1279/TD | 12/09/2022 | 1146 | TAPAS SANTRA | 956.75 | 865.39 | 90.45 | 90
3236 | PURBA MEDINIPUR | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, CONTAI-I, DESHAPRAN & EGRA-I BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. , SM/10666 | New | Material Requisition To Resource Division | 2900/TD | 21/11/2023 | 0 | Resource Division | 5.49 | 0 | 0 | 0
3237 | PURBA MEDINIPUR | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, CONTAI-I, DESHAPRAN & EGRA-I BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. , SM/10666 | New | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0 | 0
3238 | PURBA MEDINIPUR | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, CONTAI-I, DESHAPRAN & EGRA-I BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. , SM/10666 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 87.75 | 67.82 | 70
3239 | PURBA MEDINIPUR | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, CONTAI-I, DESHAPRAN & EGRA-I BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. , SM/10666 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 443.6 | 51.43 | 48
3240 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Ramnagar-II, Sahid Matangini & Sutahata Development Block within Purba Medinipur District. , SM/10617 | New | Material Requisition To Resource Division | 2895/TD | 21/11/2023 | 0 | Resource Division | 1.9 | 0 | 0 | 0
3241 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Ramnagar-II, Sahid Matangini & Sutahata Development Block within Purba Medinipur District. , SM/10617 | New | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0 | 0
3242 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Ramnagar-II, Sahid Matangini & Sutahata Development Block within Purba Medinipur District. , SM/10617 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 686.09 | 76.31 | 70
3243 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Ramnagar-II, Sahid Matangini & Sutahata Development Block within Purba Medinipur District. , SM/10617 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 84.19 | 100 | 48
3244 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Ramnagar-I and Ramnagar-II Development Block Within Purba Medinipur District. , SM/10621 | New | Material Requisition To Resource Division | 2899/TD | 21/11/2023 | 0 | Resource Division | 12.28 | 0 | 0 | 0
3245 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Ramnagar-I and Ramnagar-II Development Block Within Purba Medinipur District. , SM/10621 | New | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0 | 0
3246 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Ramnagar-I and Ramnagar-II Development Block Within Purba Medinipur District. , SM/10621 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 460.99 | 63.75 | 70
3247 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Ramnagar-I and Ramnagar-II Development Block Within Purba Medinipur District. , SM/10621 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 245.24 | 95.05 | 48
3248 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Material Requisition To Resource Division | 2990/TD | 27/02/2023 | 0 | Resource Division | 46.28 | 0 | 0 | 0
3249 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-I) | 375/TD | 27/04/2023 | 20 | MRITYUNJOY PARIA | 9.97 | 5.98 | 59.94 | 60
3250 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-G) | 373/TD | 27/04/2023 | 20 | ACHINTA KUMAR HALDER | 9.86 | 6 | 60.88 | 71
3251 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-H) | 374/TD | 27/04/2023 | 20 | BAGLAMUKHI SECURITY SERVICE | 10 | 6.05 | 60.55 | 56
3252 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Laying distribution System, Construction of Boundary wall at 1st. Tube well site & Accommodate FHTC (385 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-B) | 514/TD | 11/05/2023 | 898 | MAA KALI CONSTRUCTION | 77.96 | 22.14 | 28.4 | 3
3253 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Laying distribution System, Construction of Boundary Wall at 2nd. Tube well site , & Accommodate FHTC (500 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-C) | 515/TD | 11/05/2023 | 60 | SHAKEEL KHAN | 89.3 | 60.12 | 67.32 | 31
3254 | PURBA MEDINIPUR | Midnapore Mechanical | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 0 | 50
3255 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-J) | 2813/TD | 07/11/2023 | 20 | CHANDA AGENCIES | 9.93 | 6.52 | 65.69 | 81
3256 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Development of low land and construction of Link Road by carried earth at H/W Site for Dakshin Anukha PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 2738/TD | 01/11/2023 | 740 | MAA KALI CONSTRUCTION | 6.92 | 5.02 | 72.51 | 25
3257 | PURBA MEDINIPUR | Central Drilling | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Providing drilling crews Including Allied Materials for construction of Tube Well (300mm X200mm) at Dakshin Ankha PWSS within Moyna Block under Central Drilling Division, P.H.E. Dte. | 1469/CDD | 27/09/2023 | 210 | PADMA ENGINEERING & CO. | 14.74 | 0 | 0 | 100
3258 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Proposed retaining wall cum guard wall , approach road, earth filling at 2nd tube site under Dakshin Anukha and its adjoining mouzas PWSS under Moyna development block under Tamluk Sub-Division in Tamluk Division ,Dist-Pruba Medinipur. | 2941/TD | 23/11/2023 | 25 | NARAYAN MANDAL | 8.22 | 8.21 | 100 | 60
3259 | PURBA MEDINIPUR | Central Drilling | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Providing drilling crews Including Allied Materials for construction of Tube Well ( 250mm X150mm) at Dakshin Ankha W/S Scheme within Purba Medinipur District under Central Drilling Division, P.H.E. Dte. | 1414/CDD | 20/09/2023 | 210 | MENAKA ENTERPRISE | 11.26 | 9.95 | 100 | 100
3260 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Proposed Retaining wall cum Gurad Wall at Head work site under Dakshin Anukha and its Adjoning mouzas PWSS under Moyna Block Development Block under Tamluk Sub Division in Tamluk Division, Purba Medinipur. | 1928/TD | 07/06/2024 | 30 | M J A ENTERPRISE | 3.33 | 3.32 | 100 | 100
3261 | PURBA MEDINIPUR | Central Drilling | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Dakshin Ankha W/S Scheme ( TW- II) , Moyna Block under Purba Midnapur District, Central Drilling Division, P.H.E. Dte. | 1844//CDD | 18/12/2023 | 120 | PADMA ENGINEERING & CO. | 14.69 | 12.26 | 100 | 100
3262 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Material Requisition To Resource Division | 1562/TD | 23/04/2024 | 0 | Resource Division | 10.07 | 0 | 0 | 0
3263 | PURBA MEDINIPUR | Midnapore Mechanical | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Additional quotation for Dakhin Anukha w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App ID 100000112312, Ref ID 860303992) | BP-2024-25-496 | 30/07/2024 | 0 | WBSEDCL | 0.99 | 0 | 0 | 0
3264 | PURBA MEDINIPUR | Midnapore Mechanical | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Quotation for Dakhin Ankha w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608983, Ref ID-204222616) | BP-2023-24-858 | 16/03/2024 | 0 | WBSEDCL | 3.47 | 0 | 0 | 0
3265 | PURBA MEDINIPUR | Midnapore Mechanical | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Quotation for Dakhin Ankha w/s scheme PH-II in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608987, Ref ID-204222617) | BP-2023-24-859 | 16/03/2024 | 0 | WBSEDCL | 3.58 | 0 | 0 | 0
3266 | PURBA MEDINIPUR | Midnapore Mechanical | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DKSHIM ANKHA and ADJOINING MOUJAS, Block - Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 516/W/MMD | 20/03/2023 | 683 | KARUNAMOY ENGINEERING | 22.75 | 15.69 | 68.99 | 100
3267 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Laying distribution System, Switch Room cum Chlorine Room I & II , Accommodate FHTC (550 nos) & Rising Main under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-A) | 582/TD | 16/05/2023 | 896 | NARAYAN MANDAL | 138.66 | 104.99 | 75.72 | 80
3268 | PURBA MEDINIPUR | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS , SM/12515 | New | Soil investigation & R.C.C. Elevated Reservoir of capacity 250 cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-E) | 1777/TD | 02/08/2023 | 851 | NEW STAR CONSTRUCTION | 108.73 | 54.87 | 50.47 | 90
3269 | PURBA MEDINIPUR | Midnapore Mechanical | MIRJAPUR AND IT'S ADJOINING MOUJAS , SM/12516 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MIRJAPUR and ADJOINING MOUJAS, Block - Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 506/W/MMD | 20/03/2023 | 180 | M/S DILIP MITRA | 21.59 | 0 | 0 | 0
3270 | PURBA MEDINIPUR | Tamluk Division | MIRJAPUR AND IT'S ADJOINING MOUJAS , SM/12516 | New | Material Requisition To Resource Division | 2973/TD | 27/02/2023 | 0 | Resource Division | 37.6 | 0 | 0 | 0
3271 | PURBA MEDINIPUR | Tamluk Division | MIRJAPUR AND IT'S ADJOINING MOUJAS , SM/12516 | New | Laying distribution pipe line, under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-C) | 258/TD | 19/04/2023 | 25 | MENAKA ENTERPRISE | 13.21 | 0 | 0 | 0
3272 | PURBA MEDINIPUR | Midnapore Mechanical | MIRJAPUR AND IT'S ADJOINING MOUJAS , SM/12516 | New | Quotation Bill for New Service connection at T/W NO-I Of MIRJAPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671915/QUOT/03/50 DT. 05-04-2024 Application NO- 2004671915 Application type-New connection Consumer Id- 204266735 | BP-2024-25-92 | 24/04/2024 | 0 | WBSEDCL | 4.49 | 0 | 0 | 0
3273 | PURBA MEDINIPUR | Tamluk Division | MIRJAPUR AND IT'S ADJOINING MOUJAS , SM/12516 | New | Soil investigation, 150 cum OHR (Torch type with pile foundation) under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-D) | 522/TD | 11/05/2023 | 962 | SASWATA CONSTRUCTION | 86.46 | 0 | 0 | 0
3274 | PURBA MEDINIPUR | Central Drilling | MIRJAPUR AND IT'S ADJOINING MOUJAS , SM/12516 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 64.14 | 120.84 | 11
3275 | PURBA MEDINIPUR | Tamluk Division | MIRJAPUR AND IT'S ADJOINING MOUJAS , SM/12516 | New | Laying distribution pipe line, Pump House , Boundary Wall , Laying rising main pipe line & Accommodate FHTC (835 nos) under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | 1754/TD | 01/08/2023 | 708 | BARH CONSTRUCTION | 211.44 | 0 | 0 | 70
3276 | PURBA MEDINIPUR | Tamluk Division | MIRJAPUR AND IT'S ADJOINING MOUJAS , SM/12516 | New | Requirement of additional pipeline for distribution pipeline due to revised drawing for Mirjapur PWSS under JJM within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | 723/TD | 28/02/2024 | 458 | ELECTIVA ENTERPRISE | 6.28 | 0 | 0 | 0
3277 | PURBA MEDINIPUR | Central Drilling | MIRJAPUR AND IT'S ADJOINING MOUJAS , SM/12516 | New | Hiring of Diesel driven motor cab (BS-III & Above) (Non AC) having contract carriage permit along with driver for the office of the DIC/ CMSD-I P.H.E. Dte. Under CMSD-I(D), CDD, P.H.E. Dte. | 253/CMSD-I | 26/06/2024 | 182 | SUJATA BHOWMICK | 0.86 | 2.11 | 244.53 | 0
3278 | PURBA MEDINIPUR | Midnapore Mechanical | MIRJAPUR AND IT'S ADJOINING MOUJAS , SM/12516 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
3279 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-2) , SM/11618 | Augmentation | Material Requisition To Resource Division | 1372/TD | 23/09/2022 | 0 | Resource Division | 38.75 | 0 | 0 | 0
3280 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-2) , SM/11618 | Augmentation | Material Requisition To Resource Division | 1658/TD | 03/11/2022 | 0 | Resource Division | 180.08 | 0 | 0 | 0
3281 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-2) , SM/11618 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1653/TD | 02/11/2022 | 1032 | TAPAS SANTRA | 997.19 | 598.73 | 98.08 | 70
3282 | PURBA MEDINIPUR | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | 3111/TD | 02/03/2023 | 30 | SOUMYA ENTERPRISE | 49.53 | 38.52 | 77.77 | 80
3283 | PURBA MEDINIPUR | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Material Requisition To Resource Division | 2423/TD | 16/01/2023 | 0 | Resource Division | 34.51 | 0 | 0 | 0
3284 | PURBA MEDINIPUR | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Payment of WBSEDCL for Quotation of Shifting of 11 KV HTOH Line under Tamluk Division, PHE Dte. | BP-2023-24-666 | 15/12/2023 | 0 | WBSEDCL | 2.75 | 0 | 0 | 0
3285 | PURBA MEDINIPUR | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | 3108//TD | 02/03/2023 | 909 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 67.57 | 44.7 | 66.15 | 55
3286 | PURBA MEDINIPUR | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | 3109/TD | 02/03/2023 | 30 | SK SANAMAJ | 59.34 | 44.1 | 74.32 | 40
3287 | PURBA MEDINIPUR | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | 585/TD | 16/05/2023 | 180 | RAJ KUMAR SINGHA | 112.37 | 0 | 0 | 0
3288 | PURBA MEDINIPUR | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | 140/TD | 10/04/2023 | 30 | THREE MAA ENTERPRISE | 69.26 | 69.25 | 100 | 75
3289 | PURBA MEDINIPUR | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Canal Crossing Structure for Laying Distribution (Nodal Point - 17 - 18) & Rising Main Pipeline of Madhya Hingly Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. | 2609/TD | 11/10/2023 | 30 | SOUVIK GHOSAL | 7.39 | 4.72 | 100 | 100
3290 | PURBA MEDINIPUR | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Material Requisition To Resource Division | 101/TD | 05/01/2024 | 0 | Resource Division | 10.82 | 0 | 0 | 0
3291 | PURBA MEDINIPUR | Midnapore Mechanical | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Electric Quotation for MADHYA HINGLI Water Supply Scheme T/W-I, (Ref. ID-204136074) | BP-2023-24-441 | 19/12/2023 | 0 | WBSEDCL | 5.95 | 0 | 0 | 0
3292 | PURBA MEDINIPUR | Midnapore Mechanical | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Quotation for new service connection at Madhya Hingli w/s scheme PH II | BP-2023-24-682 | 15/02/2024 | 0 | WBSEDCL | 4.68 | 0 | 0 | 0
3293 | PURBA MEDINIPUR | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-F) | 3110/TD | 02/03/2023 | 30 | S. N. A. CONSTRUCTION | 58.38 | 50.43 | 86.38 | 35
3294 | PURBA MEDINIPUR | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-H) | 3112/TD | 02/02/2023 | 20 | PULAK KUMAR SAMANTA | 31.14 | 19.16 | 61.52 | 62
3295 | PURBA MEDINIPUR | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS , SM/12498 | New | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 3348/TD | 22/03/2023 | 638 | M/S SYCHROTECH INDUSTRY | 62.36 | 25.35 | 93.46 | 100
3296 | PURBA MEDINIPUR | Tamluk Division | BAKCHA AND ADJOINING MOUJAS PWSS , SM/12146 | New | Material Requisition To Resource Division | 2430/TD | 16/01/2023 | 0 | Resource Division | 26.3 | 0 | 0 | 0
3297 | PURBA MEDINIPUR | Midnapore Mechanical | BAKCHA AND ADJOINING MOUJAS PWSS , SM/12146 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAKCHA and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2336/W/MMD | 29/12/2022 | 180 | PRANAB KUMAR DAS | 23.69 | 22.11 | 93.33 | 90
3298 | PURBA MEDINIPUR | Tamluk Division | BAKCHA AND ADJOINING MOUJAS PWSS , SM/12146 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Bakcha PWSS at Moyna Block under Tamluk Division,PHE Dte. | 201/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3299 | PURBA MEDINIPUR | Tamluk Division | BAKCHA AND ADJOINING MOUJAS PWSS , SM/12146 | New | Material Requisition To Resource Division | 1559/TD | 23/04/2024 | 0 | Resource Division | 12.6 | 0 | 0 | 0
3300 | PURBA MEDINIPUR | Midnapore Mechanical | BAKCHA AND ADJOINING MOUJAS PWSS , SM/12146 | New | Quotation for new service connection at Bakcha w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.2004631507, Ref ID 204237228) | BP-2023-24-906 | 28/03/2024 | 0 | WBSEDCL | 6.12 | 0 | 0 | 0
3301 | PURBA MEDINIPUR | Midnapore Mechanical | BAKCHA AND ADJOINING MOUJAS PWSS , SM/12146 | New | Quotation for Bakcha w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004620130, Ref ID-204229481) | BP-2023-24-854 | 16/03/2024 | 0 | WBSEDCL | 2.97 | 0 | 0 | 0
3302 | PURBA MEDINIPUR | Tamluk Division | BAKCHA AND ADJOINING MOUJAS PWSS , SM/12146 | New | Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.01.2025 to 31.06.2025 i.e. 06 (Six) Months for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. | 344/RWS/TSD | 30/12/2024 | 181 | SADHAN CHANDRA SAMANTA | 0.86 | 1.08 | 126.12 | 0
3303 | PURBA MEDINIPUR | Tamluk Division | BAKCHA AND ADJOINING MOUJAS PWSS , SM/12146 | New | Installation of display Board at 5 nos { 1. GOBARDAN PWSS( PUMP HOUSE -2) , 2. UTTAR CHONGRA CHAK PWSS( PUMP HOUSE 1 & 2), 3.BAKCHA PWSS( PUMP HOUSE 1 & 2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 58/RWS/TSD | 06/05/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
3304 | PURBA MEDINIPUR | Tamluk Division | MIRJAPUR AND ADJOINING MOUJAS PWSS , SM/12153 | New | Construction boundary wall & Accommodate FHTC (200 nos) under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | 1452/TD | 13/07/2023 | 30 | HYDROTECH ASSOCIATES | 13.65 | 0 | 0 | 0
3305 | PURBA MEDINIPUR | Tamluk Division | MIRJAPUR AND ADJOINING MOUJAS PWSS , SM/12153 | New | Material Requisition To Resource Division | 2380/TD | 16/01/2023 | 0 | Resource Division | 19.37 | 0 | 0 | 0
3306 | PURBA MEDINIPUR | Midnapore Mechanical | MIRJAPUR AND ADJOINING MOUJAS PWSS , SM/12153 | New | Electric Quotation for MIRJAPUR Water Supply Scheme T/W-II, (Ref. ID-204090824) | BP-2023-24-316 | 01/11/2023 | 0 | WBSEDCL | 1.14 | 0 | 0 | 0
3307 | PURBA MEDINIPUR | Midnapore Mechanical | MIRJAPUR AND ADJOINING MOUJAS PWSS , SM/12153 | New | Electric Quotation for MIRJAPUR Water Supply Scheme T/W-I, (Ref. ID-204086227) | BP-2023-24-313 | 01/11/2023 | 0 | WBSEDCL | 3.78 | 0 | 0 | 0
3308 | PURBA MEDINIPUR | Midnapore Mechanical | MIRJAPUR AND ADJOINING MOUJAS PWSS , SM/12153 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MIRJAPUR and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2361/W/MMD | 31/12/2022 | 180 | WEST BENGAL ENGINEERING CO. | 23.67 | 23.13 | 100 | 100
3309 | PURBA MEDINIPUR | Tamluk Division | MIRJAPUR AND ADJOINING MOUJAS PWSS , SM/12153 | New | Material Requisition To Resource Division | 87/TD | 05/01/2024 | 0 | Resource Division | 14.2 | 0 | 0 | 0
3310 | PURBA MEDINIPUR | Tamluk Division | MIRJAPUR AND ADJOINING MOUJAS PWSS , SM/12153 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2305 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of MIRJAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 456/TD | 04/05/2023 | 900 | TAPAS SANTRA | 719.36 | 478.77 | 66.55 | 66
3311 | PURBA MEDINIPUR | Tamluk Division | BALGOBINDAPUR & ADJOINING MOUZAS , SM/12143 | New | Material Requisition To Resource Division | 2702/TD | 06/02/2023 | 0 | Resource Division | 14.6 | 0 | 0 | 0
3312 | PURBA MEDINIPUR | Midnapore Mechanical | BALGOBINDAPUR & ADJOINING MOUZAS , SM/12143 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BALGOBINDAPUR and ADJOINING MOUJAS, Block Potashpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2334/W/MMD | 29/12/2022 | 180 | S.S.GHORAI | 23.7 | 14.81 | 62.47 | 55
3313 | PURBA MEDINIPUR | Tamluk Division | BALGOBINDAPUR & ADJOINING MOUZAS , SM/12143 | New | Material Requisition To Resource Division | 1648/TD | 29/04/2024 | 0 | Resource Division | 13.17 | 0 | 0 | 0
3314 | PURBA MEDINIPUR | Midnapore Mechanical | BALGOBINDAPUR & ADJOINING MOUZAS , SM/12143 | New | Quotation Bill for New Service connection at T/W NO-I Of BALGOBINDAPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004675882/QUOT/03 DT. 12-04-2024 Application NO- 2004675882 Application type-New connection Consumer Id- 204270815 | BP-2024-25-100 | 26/04/2024 | 0 | WBSEDCL | 5.17 | 0 | 0 | 0
3315 | PURBA MEDINIPUR | Tamluk Division | BALGOBINDAPUR & ADJOINING MOUZAS , SM/12143 | New | Sinking Tube well,Pump House , Construction of 350 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2138 nos), Including 2 years of operation maintance under JJM with allied work for Balgobindapur- PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 2272/TD | 05/09/2023 | 695 | DAS ENTERPRISE | 693.39 | 0 | 0 | 40
3316 | PURBA MEDINIPUR | Tamluk Division | TANIA BILA AND ADJOINING MOUJAS PWSS , SM/12145 | New | Material Requisition To Resource Division | 349/TD | 26/04/2023 | 0 | Resource Division | 51.9 | 0 | 0 | 0
3317 | PURBA MEDINIPUR | Midnapore Mechanical | TANIA BILA AND ADJOINING MOUJAS PWSS , SM/12145 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TANIA BILA and ADJOINING MOUJAS, Block Potashpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2320/W/MMD | 29/12/2022 | 180 | M/S. SAJAHAN CHOWDHURY | 22.79 | 16.65 | 73.03 | 65
3318 | PURBA MEDINIPUR | Tamluk Division | TANIA BILA AND ADJOINING MOUJAS PWSS , SM/12145 | New | Material Requisition To Resource Division | 1664/TD | 29/04/2024 | 0 | Resource Division | 7.61 | 0 | 0 | 0
3319 | PURBA MEDINIPUR | Tamluk Division | TANIA BILA AND ADJOINING MOUJAS PWSS , SM/12145 | New | Sinking of Tube well,Pump House ,OHR of capacity 400 Cum & 150 Cum , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation, Rigid Pavement & Accommodate FHTC (3874 nos) Including 2 years of Operation & maintenace , under JJM with allied work for Satshatamal PWSS ,Tania Bila PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1670/TD | 25/07/2023 | 860 | HALDIA DEVELOPMENT CONSTRUCTION | 1214.41 | 165.13 | 39.81 | 60
3320 | PURBA MEDINIPUR | Central Drilling | BIJAYNAGAR & ADJOINING MOUJAS PWSS , SM/12157 | New | Providing drilling crew and other allied works for construction of Tube Well(250mm X150mm X 230 Mtrs. Depth) by utilizing Departmental Machineries for Bijaynagar W/S Scheme (T/W-I & II), Bhagawanpur-II Block underPurbaMedinipur District, Central Drilling Division, P.H.E. Dte. | 1394/CDD | 19/09/2023 | 30 | MENAKA ENTERPRISE | 27.2 | 0 | 0 | 0
3321 | PURBA MEDINIPUR | Tamluk Division | BIJAYNAGAR & ADJOINING MOUJAS PWSS , SM/12157 | New | Material Requisition To Resource Division | 2964/TD | 27/02/2023 | 0 | Resource Division | 16.56 | 0 | 0 | 0
3322 | PURBA MEDINIPUR | Tamluk Division | BIJAYNAGAR & ADJOINING MOUJAS PWSS , SM/12157 | New | Block Level Orientation Programme involving PRI functionaries on Jal Jeevan Mission at different blocks within Contai Sub- Division under Tamluk division,PHE Dte. Block Name- Contai-I, Deshpran(Contai-II), Contai-III, Bhagwanpur-I & Bhagwanpur-II ) | 562/CSD | 14/03/2024 | 10 | BISWA NIRMAN ENTERPRISE. | 0.68 | 0 | 0 | 100
3323 | PURBA MEDINIPUR | Tamluk Division | BIJAYNAGAR & ADJOINING MOUJAS PWSS , SM/12157 | New | Material Requisition To Resource Division | 629/W | 20/02/2024 | 0 | Resource Division | 10.78 | 0 | 0 | 0
3324 | PURBA MEDINIPUR | Midnapore Mechanical | BIJAYNAGAR & ADJOINING MOUJAS PWSS , SM/12157 | New | Bijoynagar W/S scheme T/W-I Application.-2004537086 Ref.-204168733 | BP-2023-24-530 | 11/01/2024 | 0 | WBSEDCL | 4.08 | 0 | 0 | 0
3325 | PURBA MEDINIPUR | Midnapore Mechanical | BIJAYNAGAR & ADJOINING MOUJAS PWSS , SM/12157 | New | Bijoynagar W/S scheme T/W-II Application.-2004537378 Ref.-204168879 | BP-2023-24-529 | 11/01/2024 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
3326 | PURBA MEDINIPUR | Tamluk Division | BIJAYNAGAR & ADJOINING MOUJAS PWSS , SM/12157 | New | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1750 nos) under JJM with allied work for BIJAYNAGAR PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1553/TD | 19/07/2023 | 652 | TARUN KOLEY | 555.04 | 265.45 | 47.83 | 70
3327 | PURBA MEDINIPUR | Tamluk Division | BIJAYNAGAR & ADJOINING MOUJAS PWSS , SM/12157 | New | Laying of Left out Distribution pipe line by HDPE pipes with allied works for Bijaynagar & adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | 3753/TD | 06/12/2024 | 50 | BHOWMIK & SONS | 10.64 | 0 | 0 | 100
3328 | PURBA MEDINIPUR | Midnapore Mechanical | BIJAYNAGAR & ADJOINING MOUJAS PWSS , SM/12157 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BIJAYNAGAR and ADJOINING MOUJAS, Block Bhagawanpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2322/W/MMD | 29/12/2022 | 723 | GOENKA ENTERPRISE | 22.8 | 21.04 | 94.39 | 100
3329 | PURBA MEDINIPUR | Tamluk Division | GAR BHERA & ADJOINING MOUZAS , SM/12159 | New | Material Requisition To Resource Division | 2382/TD | 16/01/2023 | 0 | Resource Division | 23.95 | 0 | 0 | 0
3330 | PURBA MEDINIPUR | Midnapore Mechanical | GAR BHERA & ADJOINING MOUZAS , SM/12159 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GAR BHERA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2341/W/MMD | 29/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 22.14 | 93.41 | 85
3331 | PURBA MEDINIPUR | Tamluk Division | GAR BHERA & ADJOINING MOUZAS , SM/12159 | New | Material Requisition To Resource Division | 120/TD | 05/01/2024 | 0 | Resource Division | 7.85 | 0 | 0 | 0
3332 | PURBA MEDINIPUR | Midnapore Mechanical | GAR BHERA & ADJOINING MOUZAS , SM/12159 | New | Gar Bhera W/S scheme T/W-V Application No.-2004553977 Ref.-204184071 | BP-2023-24-573 | 18/01/2024 | 0 | WBSEDCL | 5.53 | 0 | 0 | 0
3333 | PURBA MEDINIPUR | Midnapore Mechanical | GAR BHERA & ADJOINING MOUZAS , SM/12159 | New | Garbhera W/S scheme T/W-II Application No.-2004554001 Ref.-204184072 | BP-2023-24-580 | 18/01/2024 | 0 | WBSEDCL | 7.59 | 0 | 0 | 0
3334 | PURBA MEDINIPUR | Tamluk Division | GAR BHERA & ADJOINING MOUZAS , SM/12159 | New | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1594 nos) under JJM with allied work of GARBERHA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 131/TD | 10/04/2023 | 782 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 454.99 | 308.41 | 67.78 | 75
3335 | PURBA MEDINIPUR | Tamluk Division | BARA BHAGIA AND ADJOINING MOUJAS PWSS , SM/12704 | New | Material Requisition To Resource Division | 2444/TD | 16/01/2023 | 0 | Resource Division | 33.17 | 0 | 0 | 0
3336 | PURBA MEDINIPUR | Midnapore Mechanical | BARA BHAGIA AND ADJOINING MOUJAS PWSS , SM/12704 | New | Quotation Bill for New Service connection at T/W NO-I Of BARA BHAGIA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004870409/QUOT/03 DT. 23-08-2024 MEMO NO: AMR/PHE/338 DT. 23-08-2024 Application NO- 2004870409 Application type-New connection Consumer Id- 204383603 | BP-2024-25-648 | 06/09/2024 | 0 | WBSEDCL | 5.91 | 0 | 0 | 0
3337 | PURBA MEDINIPUR | Midnapore Mechanical | BARA BHAGIA AND ADJOINING MOUJAS PWSS , SM/12704 | New | Quotation Bill for New Service connection at T/W NO-II Of BARA BHAGIA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004878231/QUOT/03 DT. 30-08-2024 MEMO NO: AMR/PHE/351 DT. 30-08-2024 Application NO- 2004878231 Application type-New connection Consumer Id- 204387577 | C102415714404 | 05/10/2024 | 0 | WBSEDCL | 3.05 | 0 | 0 | 0
3338 | PURBA MEDINIPUR | Midnapore Mechanical | BARA BHAGIA AND ADJOINING MOUJAS PWSS , SM/12704 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARA BHAGIA and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 511/W/MMD | 20/03/2023 | 925 | GLACIER ENGINEERING CO. | 22.8 | 16.26 | 71.29 | 60
3339 | PURBA MEDINIPUR | Tamluk Division | BARA BHAGIA AND ADJOINING MOUJAS PWSS , SM/12704 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 2703/TD | 20/10/2023 | 620 | S & P ENTERPRISE | 1928.99 | 0 | 0 | 30
3340 | PURBA MEDINIPUR | Tamluk Division | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12402 | New | Material Requisition To Resource Division | 2721/TD | 06/02/2023 | 0 | Resource Division | 19.28 | 0 | 0 | 0
3341 | PURBA MEDINIPUR | Midnapore Mechanical | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12402 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NILKANTHAPUR and ADJOINING MOUJAS, Block ¿ Bhagwanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2423/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 22.8 | 17.44 | 76.48 | 62
3342 | PURBA MEDINIPUR | Tamluk Division | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12402 | New | Material Requisition To Resource Division | 127/TD | 05/01/2024 | 0 | Resource Division | 10.28 | 0 | 0 | 0
3343 | PURBA MEDINIPUR | Midnapore Mechanical | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12402 | New | Quotation Bill for New Service connection at T/W NO-II Of NILKANTHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE : BHAGWANPUR C.C.C. Ref. Memo No- 2004942161/QUOT/03 DT. 24-10-2024 Application NO- 2004942161 Application type-New connection CONSUMER ID: 204427729 | C112423542425 | 20/11/2024 | 0 | WBSEDCL | 2.78 | 0 | 0 | 0
3344 | PURBA MEDINIPUR | Midnapore Mechanical | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12402 | New | Quotation Bill for New Service connection at T/W NO-I Of NILKANTHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818541/QUOT/03 DT. 12-07-2024 Application NO- 2004818541 Application type-New connection Consumer Id- 204355510 | BP-2024-25-555 | 08/08/2024 | 0 | WBSEDCL | 12.51 | 0 | 0 | 0
3345 | PURBA MEDINIPUR | Tamluk Division | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12402 | New | Sinking of Tube Well ,Construction of Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1669 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of NILKANTHAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 129/TD | 10/04/2023 | 966 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 486.76 | 127.04 | 26.1 | 25
3346 | PURBA MEDINIPUR | Tamluk Division | SHIPUR AND ADJOINING MOUJAS PWSS , SM/12503 | New | Material Requisition To Resource Division | 2416/TD | 16/01/2023 | 0 | Resource Division | 19.96 | 0 | 0 | 0
3347 | PURBA MEDINIPUR | Midnapore Mechanical | SHIPUR AND ADJOINING MOUJAS PWSS , SM/12503 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SHIPUR and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2424/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 22.8 | 14.3 | 62.73 | 51
3348 | PURBA MEDINIPUR | Tamluk Division | SHIPUR AND ADJOINING MOUJAS PWSS , SM/12503 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Shipur PWSS at Egra-I Block under Tamluk Division, PHE Dte. | 2085/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
3349 | PURBA MEDINIPUR | Tamluk Division | SHIPUR AND ADJOINING MOUJAS PWSS , SM/12503 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 220.85 | 46.44 | 51
3350 | PURBA MEDINIPUR | Tamluk Division | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. , SM/12634 | New | Material Requisition To Resource Division | 2421/TD | 16/01/2023 | 0 | Resource Division | 16.01 | 0 | 0 | 0
3351 | PURBA MEDINIPUR | Tamluk Division | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. , SM/12634 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Amdai PWSS at Egra-I Block under Tamluk Division, PHE Dte. | 2084/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
3352 | PURBA MEDINIPUR | Midnapore Mechanical | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. , SM/12634 | New | Quotation for new service connection at TW-1 of Amdai w/s scheme under MMD,PHE DTE, Block-Egra-1,Chorpalia CCC,Application no-2004635540.Con ID-204242882 | BP-2023-24-886 | 22/03/2024 | 0 | WBSEDCL | 5.55 | 0 | 0 | 0
3353 | PURBA MEDINIPUR | Midnapore Mechanical | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. , SM/12634 | New | Quotation for new service connection at TW-II of AMDAI WS Scheme under MMD,PHE DTE, Block-Egra-1,Chorpalia ccc . Application no-2004635643. CON ID-204240383. | BP-2023-24-887 | 22/03/2024 | 0 | WBSEDCL | 4.92 | 0 | 0 | 0
3354 | PURBA MEDINIPUR | Midnapore Mechanical | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. , SM/12634 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMDAI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2416/W/MMD | 31/12/2022 | 882 | RITESH ENTERPRISE | 22.81 | 0 | 0 | 80
3355 | PURBA MEDINIPUR | Tamluk Division | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. , SM/12634 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 97.31 | 30.09 | 51
3356 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paniparul Water Supply Scheme under Tamluk Division, PHE Dte. | 1616/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 6.16 | 6.16 | 100 | 100
3357 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-E) | 2012/TD | 06/12/2022 | 25 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 18.56 | 3.16 | 17.03 | 0
3358 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-D) | 2011/TD | 06/12/2022 | 25 | DHANANJOY DAS | 38.53 | 9.09 | 23.59 | 25
3359 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-F) | 2013/TD | 06/12/2022 | 25 | CHARUBALA ENTERPRISE | 10.76 | 2.41 | 22.37 | 0
3360 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-G) | 2096/TD | 13/12/2022 | 15 | M/S. PRADIP PRADHAN | 4.18 | 4.18 | 100 | 100
3361 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Name of Work: Sinking of 02 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 2nd Tube well Site of Paniparul Zone-I W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Paniparul Zone-I W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 296/TD | 20/04/2023 | 40 | SPG ENTERPRISES | 37.92 | 34.74 | 100 | 100
3362 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Material Requisition To Resource Division | 1667/TD | 03/11/2022 | 0 | Resource Division | 128.58 | 0 | 0 | 0
3363 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Material Requisition To Resource Division | 2634/TD | 02/02/2023 | 0 | Resource Division | 24.04 | 0 | 0 | 0
3364 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 852/W/MMD | 24/03/2023 | 180 | ECO ENTERPRISE | 13.47 | 13.3 | 100 | 100
3365 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Site cleaning at Head work site of Paniparul (zone-I ) W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 859/DSD | 01/12/2023 | 3 | SOM CONSTRUCTION | 0.36 | 0.36 | 100 | 100
3366 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Laying distribution of pipe line, Pump House at 2nd TW site, construction of boundary wall & FHTC -100nos. (Phase-II) with allied works under JJM for Paniparul( Z-I) PWSS within Egra- II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte.Purba Medinipur. | 565/TD | 15/02/2024 | 40 | AJIT KUMAR SOM | 39.83 | 35.73 | 100 | 100
3367 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Paniparul W/S scheme TW-2 Memo No.-2004516165/Quot/03/1650 application no-2004516165 ref. id-204151594 | BP-2023-24-447 | 19/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0 | 0
3368 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Paniparul W/S scheme TW-2 Memo No.-2004516174/Quot/03/1649 application no-2004516174 ref. id-204151561 | BP-2023-24-448 | 19/12/2023 | 0 | WBSEDCL | 4.39 | 0 | 0 | 0
3369 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (Part-A) | 1449/TD | 27/09/2022 | 1131 | AJIT KUMAR SOM | 351.09 | 231.59 | 65.96 | 90
3370 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-C) | 2093/TD | 13/12/2022 | 1016 | LOKENATH ENTERPRISES | 79.14 | 47.5 | 60.02 | 95
3371 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (Part-B) | 1448/TD | 27/09/2022 | 1034 | SNEHESH SEN | 170.64 | 99.16 | 58.11 | 0
3372 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I , SM/12118 | Augmentation | Repairing & renovation of Pump House, construction of boundary wall , Land development, Supply & delivery of different dia D.I. Specials with allied works under JJM for Paniparul (Z-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 2195/TD | 01/09/2023 | 571 | AJIT KUMAR SOM | 48.26 | 0 | 0 | 90
3373 | PURBA MEDINIPUR | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Material Requisition To Resource Division | 2389/TD | 16/01/2023 | 0 | Resource Division | 33.31 | 0 | 0 | 0
3374 | PURBA MEDINIPUR | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Laying distribution pipe line & Accommodate FHTC (60 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - F) | 3187/TD | 10/03/2023 | 15 | SUSANTA KUMAR KAR | 9.8 | 4.36 | 44.54 | 45
3375 | PURBA MEDINIPUR | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Laying distribution pipe line & Accommodate FHTC (300nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - D) | 3186/TD | 10/03/2023 | 25 | BADAL CHANDRA GOLE | 37.34 | 16.56 | 44.35 | 48
3376 | PURBA MEDINIPUR | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Pump House, Laying distribution pipe line, & Accommodate FHTC (270 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | 3184/TD | 10/03/2023 | 25 | SUBHENDU HAZRA | 48.38 | 23.1 | 47.74 | 50
3377 | PURBA MEDINIPUR | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (124 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART- A) | 1018/TD | 06/06/2023 | 936 | DAS ENTERPRISE | 201.92 | 70.87 | 35.1 | 37
3378 | PURBA MEDINIPUR | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Basudeb Berya PWSS at Bhagwanpur-II Block under Tamluk Division,PHE Dte. | 382/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3379 | PURBA MEDINIPUR | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Material Requisition To Resource Division | 634/W | 20/02/2024 | 0 | Resource Division | 6.55 | 0 | 0 | 0
3380 | PURBA MEDINIPUR | Midnapore Mechanical | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Additional Quotation Bill cost due to Modification for NSC of PHE AT Site- BASUDEVBERIA W/S SCHEME, T/W NO-I Under Jal Jeevan Mission under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-MDK/QOUT/253 DT. 16-05-2024 Application NO- 100000108115 DT. 16-05-2024 Application type-ADDITIONAL QUOTATION REF. Id- 860300165 | BP-2024-25-241 | 06/06/2024 | 0 | WBSEDCL | 0.59 | 0 | 0 | 0
3381 | PURBA MEDINIPUR | Midnapore Mechanical | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Quotation Bill for New Service connection at T/W NO-II Of BASUDEVBERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004558723/QUOT/03 DT. 10-01-2024 Application NO- 2004558723 Application type-New connection Consumer Id- 204187848 | BP-2023-24-829 | 13/03/2024 | 0 | WBSEDCL | 3.14 | 0 | 0 | 0
3382 | PURBA MEDINIPUR | Midnapore Mechanical | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Quotation Bill for New Service connection at T/W NO-I Of BASUDEVBERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004558731/QUOT/03 DT. 27-02-2024 Application NO- 2004558731 Application type-New connection Consumer Id- 204187847 | BP-2023-24-828 | 13/03/2024 | 0 | WBSEDCL | 3.48 | 0 | 0 | 0
3383 | PURBA MEDINIPUR | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Laying distribution pipe line, Boundary Wall & Accommodate FHTC ( 250 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - C) | 3185/TD | 10/03/2023 | 635 | M/S. NEW DINDA ENTERPRISE | 48.13 | 23.7 | 49.24 | 50
3384 | PURBA MEDINIPUR | Central Drilling | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 25.77 | 52.05 | 11
3385 | PURBA MEDINIPUR | Midnapore Mechanical | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
3386 | PURBA MEDINIPUR | Midnapore Mechanical | BASUDEVBERYA AND ADJOINING MOUJAS PWSS , SM/12297 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
3387 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. , SM/12302 | Retrofitting | Providing FHTC with allied works of Nijkasba & its adjoining mouzas Water Supply Scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 2163/TD | 19/12/2022 | 25 | HARIPADA PATTANAYAK | 35.25 | 33.89 | 96.16 | 70
3388 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. , SM/12302 | Retrofitting | Material Requisition To Resource Division | 609/TD | 17/05/2023 | 0 | Resource Division | 4.7 | 0 | 0 | 0
3389 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. , SM/12302 | Retrofitting | Construction of Boundary Wall (as per Departmental Design & Drawing) for OHR site at Nijkasba W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (for East side, North & South Side) | 487/TD | 10/05/2023 | 45 | BIPLAB BAHNI GUCHHAIT | 4.5 | 3.79 | 100 | 100
3390 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. , SM/12302 | Retrofitting | Laying of left out pipe line by HDPE pipes with allied works of distribution system of Nijkasba W/S Scheme under Contai Sub-Division, of Tamluk Division, PHE Dte, Purba Medinipur. | 2275/CSD | 09/10/2025 | 30 | SAVORIO REALITY LLP | 0.96 | 0 | 0 | 0
3391 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11860 | Augmentation | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube well of 1st Tubewell at Mouza- Baliarpur, JL. No. -358 for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method of Boosting Tube well of 3rd Tubewell at Mouza- Madhusudhanbar, JL. No. 365, Plot No. 237 - for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Mouza -Bhaitghar, JL No. - 415, Plot No. -287, Contai- III Block of Kanaidighi Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1051/TD | 18/08/2022 | 40 | AQUATECH ENGINEER | 54.66 | 16.89 | 46.36 | 32
3392 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11860 | Augmentation | Material Requisition To Resource Division | 356/TD | 26/04/2023 | 0 | Resource Division | 11.65 | 0 | 0 | 0
3393 | PURBA MEDINIPUR | Midnapore Mechanical | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11860 | Augmentation | Electric quotation for Damodarpur PWSS Tube Well-III WS Scheme (Ref. ID - 203911304) | BP-2022-23-136 | 20/03/2023 | 0 | WBSEDCL | 0.37 | 0 | 0 | 0
3394 | PURBA MEDINIPUR | Midnapore Mechanical | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11860 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 1st Tube Well and 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District, Block Contai I,under JJM Program under MMD PHE Dte. | 1413/W/MMD | 02/06/2023 | 180 | RUBY ENTERPRISE | 27.17 | 13.44 | 49.47 | 80
3395 | PURBA MEDINIPUR | Tamluk Division | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/11860 | Augmentation | Laying Rising Main, Construction of Boundary wall at 3rd Tube Well Boosting Site of Damudarpur PWSS in Contai-I within Contai Sub-Division of Tamluk Division,PHE Dte. {Length-44.00 mtr.} (For Low Land) | 1576/TD | 19/07/2023 | 30 | M/S MONDAL CONSTRUCTION & CO. | 14.04 | 11.85 | 100 | 100
3396 | PURBA MEDINIPUR | Tamluk Division | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS , SM/13691 | New | Material Requisition To Resource Division | 2394/TD | 16/01/2023 | 0 | Resource Division | 45.39 | 0 | 0 | 0
3397 | PURBA MEDINIPUR | Midnapore Mechanical | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS , SM/13691 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAGHUSARDAR BAR JALPAI and ADJOINING MOUJAS, Block Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 549/W/MMD | 20/03/2023 | 712 | DEBJYOTI BASU | 21.62 | 10.04 | 46.44 | 80
3398 | PURBA MEDINIPUR | Tamluk Division | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS , SM/13691 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Raghusardarbar Jalpai PWSS at Contai-I Block under Tamluk Division,PHE Dte. | 204/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.96 | 0.96 | 100 | 100
3399 | PURBA MEDINIPUR | Tamluk Division | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS , SM/13691 | New | Material Requisition To Resource Division | 2976/TD | 12/09/2024 | 0 | Resource Division | 5.96 | 0 | 0 | 0
3400 | PURBA MEDINIPUR | Midnapore Mechanical | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS , SM/13691 | New | Quotation for New service connection at TW-I of Raghu Sardarbar Jalpai ws scheme under MMD,PHE ,Dte. Ref Application no-2004579837, CON ID-204204431, under PICHABONI CCC, Block-Contai-I | BP-2023-24-662 | 12/02/2024 | 0 | WBSEDCL | 4.25 | 0 | 0 | 0
3401 | PURBA MEDINIPUR | Midnapore Mechanical | CHANDPUR AND ADJOINING MOUJAS PWSS , SM/13693 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHANDPUR and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 566/W/MMD | 20/03/2023 | 180 | DEY ENTERPRISE | 22.8 | 0 | 0 | 0
3402 | PURBA MEDINIPUR | Tamluk Division | CHANDPUR AND ADJOINING MOUJAS PWSS , SM/13693 | New | Material Requisition To Resource Division | 2704/TD | 06/02/2023 | 0 | Resource Division | 22.02 | 0 | 0 | 0
3403 | PURBA MEDINIPUR | Tamluk Division | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS , SM/13694 | New | Material Requisition To Resource Division | 2690/TD | 06/02/2023 | 0 | Resource Division | 39.36 | 0 | 0 | 0
3404 | PURBA MEDINIPUR | Tamluk Division | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS , SM/13694 | New | Material Requisition To Resource Division | 119/TD | 05/01/2024 | 0 | Resource Division | 8.41 | 0 | 0 | 0
3405 | PURBA MEDINIPUR | Midnapore Mechanical | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS , SM/13694 | New | Quotation Bill for New Service connection at T/W NO-I Of KALAPUNJA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004749309/QUOT/03 DT. 28-05-2024 Application NO- 2004749309 Application type-New connection Consumer Id- 204316972 | BP-2024-25-258 | 06/06/2024 | 0 | WBSEDCL | 3.89 | 0 | 0 | 0
3406 | PURBA MEDINIPUR | Tamluk Division | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS , SM/13694 | New | Payment to WBSEDCL for Shifting of 11KV HT maithana feeder for Kalapunja PWSS | BP-2023-24-938 | 06/03/2024 | 0 | WBSEDCL | 2.16 | 0 | 0 | 0
3407 | PURBA MEDINIPUR | Midnapore Mechanical | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS , SM/13694 | New | Quotation Bill for New Service connection at T/W NO-II Of KALAPUNJA W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670828/QUOT/03 DT. 05-04-2024 Application NO- 2004670828 Application type-New connection Consumer Id- 204266383 | BP-2024-25-43 | 18/04/2024 | 0 | WBSEDCL | 8.56 | 0 | 0 | 0
3408 | PURBA MEDINIPUR | Tamluk Division | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS , SM/13694 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3154 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance for DEPAL and KALAPUNJA within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 1416/TD | 12/07/2023 | 746 | BASANTA KUMAR MAITY | 961.33 | 238.18 | 49.77 | 60
3409 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) , SM/13238 | Retrofitting | Relaying the Distribution pipe line (Damaged during the construction of RIDF road from Dakshin Purushottampur Khal Parh to House of Jugal Giri House) of Ranisai PWSS, Ramnagar- I Block under Digha Sub-Division of Tamluk Division , PHE Dte. in the district of Purba Medinipur. | 1336/TD | 16/09/2022 | 25 | SUKOMAL BERA | 27.06 | 27.05 | 99.98 | 0
3410 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) , SM/13238 | Retrofitting | Material Requisition To Resource Division | 2995/TD | 29/11/2023 | 0 | Resource Division | 2.24 | 0 | 0 | 0
3411 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) , SM/13238 | Retrofitting | Material Requisition To Resource Division | 2064/TD | 28/08/2023 | 0 | Resource Division | 17.51 | 0 | 0 | 0
3412 | PURBA MEDINIPUR | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) , SM/13238 | Retrofitting | Quotation for new service connection at tw-III of Ranisai ws scheme under MMD PHE Dte,Block-Ramnagar-I, Digha CCC Application no-2004764426 Con ID-204324285 | C062416826632 | 18/06/2024 | 0 | WBSEDCL | 4.3 | 0 | 0 | 0
3413 | PURBA MEDINIPUR | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) , SM/13238 | Retrofitting | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) under JJM Program under MMD PHE Dte. | 885/W/MMD | 27/03/2023 | 1259 | SUDIKSHA CONSTRUCTION | 12.37 | 3.05 | 24.64 | 10
3414 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) , SM/13238 | Retrofitting | Laying of Distribution pipe line,Rising main pipe line, Pump House, Boundary Wall, Sinking of 3rd Tube Well with allied works of Ranisai & its adjoining mouzas W/S Scheme within Ramnagar - I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 1027/TD | 07/06/2023 | 842 | SWASTIK ENTERPRISE | 62.09 | 12.77 | 20.56 | 21
3415 | PURBA MEDINIPUR | Central Drilling | PATNA & ADJOINING MOUZAS , SM/12164 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Patna W/S Scheme (T/W-I) ,Khejuri-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 852/CDD | 10/07/2023 | 30 | C.M. ENTERPRISE | 15.47 | 0 | 0 | 0
3416 | PURBA MEDINIPUR | Tamluk Division | PATNA & ADJOINING MOUZAS , SM/12164 | New | Material Requisition To Resource Division | 2710/TD | 06/02/2023 | 0 | Resource Division | 6.86 | 0 | 0 | 0
3417 | PURBA MEDINIPUR | Midnapore Mechanical | PATNA & ADJOINING MOUZAS , SM/12164 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PATNA and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2383/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 27.7 | 19.5 | 70.4 | 60
3418 | PURBA MEDINIPUR | Tamluk Division | PATNA & ADJOINING MOUZAS , SM/12164 | New | Material Requisition To Resource Division | 2971/TD | 12/09/2024 | 0 | Resource Division | 18.05 | 0 | 0 | 0
3419 | PURBA MEDINIPUR | Midnapore Mechanical | PATNA & ADJOINING MOUZAS , SM/12164 | New | Quotation for new service connection at Patna w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004640160, Ref ID - 204244152) | BP-2023-24-855 | 16/03/2024 | 0 | WBSEDCL | 7.46 | 0 | 0 | 0
3420 | PURBA MEDINIPUR | Tamluk Division | PATNA & ADJOINING MOUZAS , SM/12164 | New | Sinking of Tube Well ,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (5341Nos), including 2 years Operation & Maintenance For PATNA, Jahanabad, Pipe water supply Scheme within Khejuri-I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 1413/TD | 12/07/2023 | 720 | GEE BEE NIRMAN CO PVT LTD. | 1697.21 | 437.25 | 48.8 | 60
3421 | PURBA MEDINIPUR | Tamluk Division | PATNA & ADJOINING MOUZAS , SM/12164 | New | Instalation of display Board at different work site of Patna, Jahanabad & its adjoining Moujas New PWSS in Khejuri-I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2443/CSD | 22/10/2024 | 7 | M/S. NEW DINDA ENTERPRISE | 0.42 | 0 | 0 | 100
3422 | PURBA MEDINIPUR | Tamluk Division | PATNA & ADJOINING MOUZAS , SM/12164 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 400 cum RCC OHR at PATNA PWSS at Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1375/CSD | 03/06/2025 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 0
3423 | PURBA MEDINIPUR | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS , SM/12169 | New | Material Requisition To Resource Division | 2962/TD | 27/02/2023 | 0 | Resource Division | 65.74 | 0 | 0 | 0
3424 | PURBA MEDINIPUR | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS , SM/12169 | New | Laying distribution pipe line & Accommodate FHTC (370 nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-D) | 1466/TD | 13/07/2023 | 446 | R CONSTRUCTION | 69.75 | 44.91 | 64.38 | 60
3425 | PURBA MEDINIPUR | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS , SM/12169 | New | Material Requisition To Resource Division | 626/W | 20/02/2024 | 0 | Resource Division | 15.22 | 0 | 0 | 0
3426 | PURBA MEDINIPUR | Midnapore Mechanical | BAHADURPUR AND ADJOINING MOUJAS PWSS , SM/12169 | New | Quotation Bill for New Service connection at T/W NO-II Of BAHADURPUR W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004601928/QUOT/03 DT. 15-02-2024 Application NO- 2004601928 Application type-New connection Reference Id- 204217837 | BP-2023-24-794 | 06/03/2024 | 0 | WBSEDCL | 4 | 0 | 0 | 0
3427 | PURBA MEDINIPUR | Midnapore Mechanical | BAHADURPUR AND ADJOINING MOUJAS PWSS , SM/12169 | New | Additional Quotation Bill cost for Diversion of route due to RAW at the PHE Site-BAHADURPUR W/S SCHEME,T/W NO-II, MADHABPUR Under Jal Jeevan Mission under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-MDK/QOUT/260 DT. 17-05-2024 Application NO- 100000108126 DT. 17-05-2024 Application type-ADDITIONAL QUOTATION REF. Id- 860300546 | BP-2024-25-242 | 06/06/2024 | 0 | WBSEDCL | 1.41 | 0 | 0 | 0
3428 | PURBA MEDINIPUR | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS , SM/12169 | New | Quotation Bill for New Service connection at T/W NO-I Of BAHADURPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2004768458/QUOT/03 DT. 11-06-2024 Application NO- 2004768458 Application type-New connection Consumer Id- 204327319 | BP-2024-25-294 | 29/07/2024 | 0 | WBSEDCL | 10.84 | 0 | 0 | 0
3429 | PURBA MEDINIPUR | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS , SM/12169 | New | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (460 nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART- A) | 1049/TD | 07/06/2023 | 694 | TARUN KOLEY | 266.16 | 56.41 | 21.19 | 65
3430 | PURBA MEDINIPUR | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS , SM/12169 | New | Pump House, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (940 nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | 532/TD | 12/05/2023 | 880 | M/S SREE DURGA ENTERPRISE | 196.73 | 93.53 | 47.54 | 49
3431 | PURBA MEDINIPUR | Central Drilling | BAHADURPUR AND ADJOINING MOUJAS PWSS , SM/12169 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 51.53 | 81.68 | 11
3432 | PURBA MEDINIPUR | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS , SM/12169 | New | Laying distribution pipe line & Accommodate FHTC ( 700nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - C) | 531/TD | 12/05/2023 | 903 | M/S SREE DURGA ENTERPRISE | 138.34 | 71.13 | 51.42 | 53
3433 | PURBA MEDINIPUR | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS , SM/12169 | New | Laying of Distribution pipe line by HDPE pipes with allied works for Left Out Area due to Revised Drawing of BAHADURPUR PWSS within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PART-E) | 2875/TD | 17/11/2023 | 681 | M/S SREE DURGA ENTERPRISE | 33.75 | 32.61 | 96.63 | 97
3434 | PURBA MEDINIPUR | Midnapore Mechanical | BAHADURPUR AND ADJOINING MOUJAS PWSS , SM/12169 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
3435 | PURBA MEDINIPUR | Tamluk Division | PANCHET AND ADJOINING MOUJAS PWSS , SM/12170 | New | Material Requisition To Resource Division | 2452/TD | 16/01/2023 | 0 | Resource Division | 24.44 | 0 | 0 | 0
3436 | PURBA MEDINIPUR | Tamluk Division | PANCHET AND ADJOINING MOUJAS PWSS , SM/12170 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Panchet PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | 2202/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3437 | PURBA MEDINIPUR | Tamluk Division | PANCHET AND ADJOINING MOUJAS PWSS , SM/12170 | New | Material Requisition To Resource Division | 1662/TD | 29/04/2024 | 0 | Resource Division | 11.82 | 0 | 0 | 0
3438 | PURBA MEDINIPUR | Midnapore Mechanical | PANCHET AND ADJOINING MOUJAS PWSS , SM/12170 | New | Quotation Bill for New Service connection at T/W NO-II Of PANCHET W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004626644/QUOT/03 DT. 01-03-2024 Application NO- 2004626644 Application type-New connection Consumer Id- 204234144 | BP-2023-24-820 | 13/03/2024 | 0 | WBSEDCL | 3.99 | 0 | 0 | 0
3439 | PURBA MEDINIPUR | Midnapore Mechanical | PANCHET AND ADJOINING MOUJAS PWSS , SM/12170 | New | Quotation Bill for New Service connection at T/W NO-I Of PANCHET W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004649232/QUOT/03 DT. 20-03-2024 Application NO- 2004649232 Application type-New connection Consumer Id- 204250589 | BP-2024-25-3 | 04/04/2024 | 0 | WBSEDCL | 6.98 | 0 | 0 | 0
3440 | PURBA MEDINIPUR | Midnapore Mechanical | PANCHET AND ADJOINING MOUJAS PWSS , SM/12170 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PANCHET and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2378/W/MMD | 31/12/2022 | 900 | GHOSH ENGINEERING SYNDICATE | 25.24 | 0 | 0 | 45
3441 | PURBA MEDINIPUR | Tamluk Division | PANCHET AND ADJOINING MOUJAS PWSS , SM/12170 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 210.59 | 31.14 | 51
3442 | PURBA MEDINIPUR | Tamluk Division | NAIPUR & ADJOINING MOUZAS , SM/12135 | New | Material Requisition To Resource Division | 2439/TD | 16/01/2023 | 0 | Resource Division | 27.79 | 0 | 0 | 0
3443 | PURBA MEDINIPUR | Midnapore Mechanical | NAIPUR & ADJOINING MOUZAS , SM/12135 | New | Quotation Bill for New Service connection at T/W NO-I Of NAIPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004609871/QUOT/03 DT. 21-02-2024 Application NO- 2004609871 Application type-New connection Reference Id- 204223251 | BP-2023-24-821 | 13/03/2024 | 0 | WBSEDCL | 3.13 | 0 | 0 | 0
3444 | PURBA MEDINIPUR | Midnapore Mechanical | NAIPUR & ADJOINING MOUZAS , SM/12135 | New | Quotation Bill for New Service connection at T/W NO-II Of NAIPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004775287/QUOT/03 DT. 14-06-2024 Application NO- 2004775287 MEMO NO: AMR/PHE/176 DT.14/06/2024 Application type-New connection Consumer Id- 204330587 | BP-2024-25-354 | 01/07/2024 | 0 | WBSEDCL | 3.67 | 0 | 0 | 0
3445 | PURBA MEDINIPUR | Tamluk Division | NAIPUR & ADJOINING MOUZAS , SM/12135 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 150.73 | 34.61 | 51
3446 | PURBA MEDINIPUR | Midnapore Mechanical | NAIPUR & ADJOINING MOUZAS , SM/12135 | New | Making of Tube Well Foundation & others at Pump House no. I & II of Naipur piped water supply scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | 585/HESD | 19/06/2025 | 7 | SOUMEN ELECTRIC | 0.66 | 0 | 0 | 0
3447 | PURBA MEDINIPUR | Midnapore Mechanical | NAIPUR & ADJOINING MOUZAS , SM/12135 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NAIPUR and ADJOINING MOUJAS, Block Potashpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2319/W/MMD | 29/12/2022 | 824 | SOUMEN ELECTRIC | 22.78 | 16.14 | 72.6 | 90
3448 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(50 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-R) | 1126/TD | 29/08/2022 | 15 | SAYAN MAITY | 9.94 | 7.85 | 79.05 | 80
3449 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(200 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-L) | 1121/TD | 29/08/2022 | 25 | KRISHNENDU SEKHAR DAS | 78.19 | 64.98 | 83.11 | 85
3450 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(260 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-H) | 1117/TD | 29/08/2022 | 20 | ADHIKARY CONSTRUCTION | 42.21 | 23.02 | 54.52 | 60
3451 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Jalpai Water Supply Scheme under Tamluk Division, PHE Dte. | 52/TD | 05/04/2022 | 20 | HORIZEN | 5.57 | 5.56 | 100 | 100
3452 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC (350 nos) with allied works for Augmentation of Jalpai Sater Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-B) | 1114/TD | 29/08/2022 | 25 | SUDIPTA ROY | 75.72 | 48.16 | 63.61 | 65
3453 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(330 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-F) | 1130/TD | 29/08/2022 | 25 | RELIABLE CONSTRUCTIONS | 72.71 | 51.83 | 71.29 | 75
3454 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR JAIPAI W/S SCHEME (TW-I), NANDAKUMAR BLOCK UNDER PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | 1637/CDD | 20/12/2022 | 30 | DEY ENTERPRISE | 19.2 | 17.23 | 89.71 | 0
3455 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipment's for augmentation of ground water based Jaipai w/s scheme under JJM Program under Medinipur Mechanical Division P.H.E Dte. In the dist of PurbaMedinipur. | 580/HESD | 04/08/2023 | 7 | BHABANI PRASAD MANNA | 0.39 | 0 | 0 | 0
3456 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Hiring of Diesel driven motor cab (BS-IV & above) having contract carriage permit along with driver for the office of the Driller in charge, CMSD-II(D), CDD, PHE Dte. | 107/CMSD-II | 27/04/2023 | 184 | ASHUTOSH PAL | 0.87 | 2.21 | 100 | 33
3457 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Material Requisition To Resource Division | 1374/TD | 23/09/2022 | 0 | Resource Division | 48.52 | 0 | 0 | 0
3458 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Material Requisition To Resource Division | 1672/TD | 03/11/2022 | 0 | Resource Division | 373.53 | 0 | 0 | 0
3459 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Way leave charges of South Eastern Railway Track for Application ID SER-KGP-2023-WL-57 under Tamluk Division, PHE Dte. | BP-2023-24-661 | 15/12/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.28 | 0 | 0 | 0
3460 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Estimate for against damage of road flank/hard shoulder due to cutting of hard shoulder and road flank on Bhabanipur-Thekuabazar Road from 5.00 km to 7.00 km for laying of water pipe kline by PHE Department. | BP-2023-24-117 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.76 | 0 | 0 | 0
3461 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(50 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-S) | 1127/TD | 29/08/2022 | 15 | OM UDYOG | 9.85 | 7.78 | 78.94 | 100
3462 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC (100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-M) | 1122/TD | 29/08/2022 | 20 | SK SANAMAJ | 56.8 | 53.04 | 93.38 | 100
3463 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC (350 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-D) | 1116/TD | 29/08/2022 | 25 | SHAKEEL KHAN | 74.47 | 51.09 | 68.61 | 80
3464 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-J) | 1119/TD | 29/08/2022 | 25 | S.D. CONSTRUCTION | 70.82 | 43.92 | 62.02 | 70
3465 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-P) | 1128/TD | 29/08/2022 | 20 | AQUATECH ENGINEERS | 45.31 | 35.25 | 77.79 | 85
3466 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-Q) | 1125/TD | 29/08/2022 | 20 | S. N. A. CONSTRUCTION | 46.55 | 41.84 | 89.89 | 99
3467 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of Distribution pipe line to accommodate FHTC(3600 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Jalpai Water Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-A) | 1386/TD | 23/09/2022 | 180 | M/S. CARE | 454 | 191.81 | 42.25 | 30
3468 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well sites of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2350/TD | 10/01/2023 | 40 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 5.06 | 0 | 0 | 0
3469 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water based Jalpai Water Supply Scheme, Block ¿ Nanda Kumar, under JJM Program under MMD PHE Dte. | 356/W/MMD | 09/03/2023 | 180 | BHABANI PRASAD MANNA | 40.78 | 25.4 | 62.29 | 60
3470 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 5th tube well sites of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 137/TD | 10/04/2023 | 40 | GRAND CONSTRUCTION | 5.1 | 0 | 0 | 0
3471 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 2nd Tubewell Site of Natshal Lakshya Zone - I W/S Scheme within Mahishadal Block under Haldia Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 5th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 4th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | 1905/TD | 10/08/2023 | 40 | AQUATECH ENGINEER | 58.34 | 15.9 | 42.87 | 45
3472 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2349/TD | 10/01/2023 | 40 | RAI CONSTRUCTION | 5.06 | 2.88 | 56.82 | 10
3473 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(300 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-I) | 1118/TD | 29/08/2022 | 25 | NARAYAN CHANDRA DAS | 76.58 | 72.03 | 100 | 80
3474 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-O) | 1124/TD | 29/08/2022 | 20 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 56.12 | 55.6 | 100 | 100
3475 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Material Requisition To Resource Division | 1104/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
3476 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Quotation Bill For New Service Connection at TW-IV of Jalpai PWSS under MMD PHE Dte.,Block-Nandakumar C.C.C.-Na Contract Demand-12000Wndakumar Application no.-2004653153 Application Type-New Connection Quotation Date-28/03/2024 Quotation Due Date-28/03/2025 | BP-2024-25-26 | 15/04/2024 | 0 | WBSEDCL | 3.22 | 0 | 0 | 0
3477 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Jalpai W/S scheme TW-III Application No.-2004554813 Ref.-204184634 | BP-2023-24-576 | 18/01/2024 | 0 | WBSEDCL | 3.46 | 0 | 0 | 0
3478 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Way Leave permission from South Eastern Railway for Jalpai PWSS for Application ID-SER-KGP-2023-WL-59 | BP-2023-24-823 | 22/01/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 4.98 | 0 | 0 | 0
3479 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-K) | 1120/TD | 29/08/2022 | 999 | FARID UDDIN AHMED | 65.7 | 41.04 | 62.47 | 91
3480 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-C) | 1115/TD | 29/08/2022 | 778 | CHANDIMATA CONSTRUCTION | 72.07 | 48.92 | 67.88 | 90
3481 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(300 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-E) | 1129/TD | 29/08/2022 | 1200 | S.K. MONDAL | 72.41 | 53.12 | 73.36 | 75
3482 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-G) | 1131/TD | 29/08/2022 | 25 | DILIP KUMAR GHOSH | 73.9 | 50.08 | 67.77 | 99
3483 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at JALPAI Water supply scheme,T/W - V, NANDAKUMAR block, District ¿ Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 2006/W/MMD | 30/08/2024 | 180 | M/S EMMESS | 14.12 | 0 | 0 | 0
3484 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. , SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-N) | 1123/TD | 29/08/2022 | 840 | BHOLANATH DEY | 57.72 | 52.02 | 92.06 | 96
3485 | PURBA MEDINIPUR | Midnapore Mechanical | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS , SM/11883 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NILKANTHIA AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 622/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 22.81 | 0 | 0 | 0
3486 | PURBA MEDINIPUR | Tamluk Division | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS , SM/11883 | New | Soil investigation & Construction of RCC Over Head of capacity 200 cum and staging height 20.00 mtr as per Deptt. Drawing ( Intze type with pile foundation), under JJM with allied work for Nilkanthia_PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division,PHE Dte. (Part-C) | 281/TD | 20/04/2023 | 180 | HARIPADA PATTANAYAK | 93.35 | 0 | 0 | 0
3487 | PURBA MEDINIPUR | Tamluk Division | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS , SM/11883 | New | Material Requisition To Resource Division | 3006/TD | 27/02/2023 | 0 | Resource Division | 16.01 | 0 | 0 | 0
3488 | PURBA MEDINIPUR | Tamluk Division | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS , SM/11883 | New | Laying distribution system pipe line, accommodate FHTC (400 nos),Construction of switch room cum cholorine room , Construction of Boundary Wall under JJM with allied work for Nilkanthia PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (PART-A) | 280/TD | 20/04/2023 | 937 | S.K. MONDAL | 87.98 | 45.71 | 51.95 | 50
3489 | PURBA MEDINIPUR | Tamluk Division | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS , SM/11883 | New | Laying distribution system pipe line, accommodate FHTC (877 nos),Construction of switch room cum cholorine room , Laying of rising main, Construction of Boundary Wall under JJM with allied work for Nilkanthia PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-B) | 1065/TD | 08/06/2023 | 618 | SUDIPTA ROY | 123.48 | 27.8 | 22.52 | 26
3490 | PURBA MEDINIPUR | Midnapore Mechanical | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS , SM/11883 | New | Quotation Bill for Nilkunthia W/S Scheme T/W-I Application No=2004684512 Reference ID=204275851 | BP-2024-25-102 | 26/04/2024 | 0 | WBSEDCL | 4.02 | 0 | 0 | 0
3491 | PURBA MEDINIPUR | Central Drilling | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS , SM/11883 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 36.48 | 71.51 | 11
3492 | PURBA MEDINIPUR | Central Drilling | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS , SM/11883 | New | Hiring of Diesel driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | 138/S&WSD | 26/06/2024 | 182 | NAGENDRA PATRA | 0.86 | 2.15 | 249.16 | 0
3493 | PURBA MEDINIPUR | Tamluk Division | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS , SM/11883 | New | Sinking of 250 x 150 mm Dia and 230m deep tubewell ( at 2nd tube well site) Drilling by Direct Rotary method with 150 dia. UPVC. Strainer of 30m.length all complete including cost of materials for Nilkunthia Water Supply Scheme under Tamluk Block under Tamluk Sub Division of Tamluk Division, P.H.E. Dte. | 456/TD | 04/02/2025 | 20 | PRANTIK DRILLING AGENCY | 12.58 | 0 | 0 | 0
3494 | PURBA MEDINIPUR | Tamluk Division | MATHURA AND IT'S ADJOINING MOUJAS PWSS , SM/13745 | New | Material Requisition To Resource Division | 2460/TD | 16/01/2023 | 0 | Resource Division | 41.71 | 0 | 0 | 0
3495 | PURBA MEDINIPUR | Midnapore Mechanical | MATHURA AND IT'S ADJOINING MOUJAS PWSS , SM/13745 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MATHURA and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 561/W/MMD | 20/03/2023 | 180 | M/S B.M. ELECTRICAL | 22.81 | 3.13 | 13.73 | 62
3496 | PURBA MEDINIPUR | Tamluk Division | MATHURA AND IT'S ADJOINING MOUJAS PWSS , SM/13745 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Mathura PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | 2200/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3497 | PURBA MEDINIPUR | Tamluk Division | MATHURA AND IT'S ADJOINING MOUJAS PWSS , SM/13745 | New | Material Requisition To Resource Division | 1659/TD | 29/04/2024 | 0 | Resource Division | 13.37 | 0 | 0 | 0
3498 | PURBA MEDINIPUR | Midnapore Mechanical | MATHURA AND IT'S ADJOINING MOUJAS PWSS , SM/13745 | New | Quotation Bill for New Service connection at T/W NO-I Of MATHURA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-2004811805/QUOT/03 DT. 11-07-2024 Application NO- 2004811805 Application type-New connection Consumer Id- 204351926 | C082420136916 | 14/08/2024 | 0 | WBSEDCL | 4.18 | 0 | 0 | 0
3499 | PURBA MEDINIPUR | Tamluk Division | MATHURA AND IT'S ADJOINING MOUJAS PWSS , SM/13745 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 162.33 | 27.48 | 51
3500 | PURBA MEDINIPUR | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Material Requisition To Resource Division | 2691/TD | 06/02/2023 | 0 | Resource Division | 33.64 | 0 | 0 | 0
3501 | PURBA MEDINIPUR | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Laying distribution pipe line, & Accommodate FHTC ( 70 Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part - E ) | 1533/TD | 18/07/2023 | 20 | HYDROTECH ASSOCIATES | 9.99 | 5.4 | 54.1 | 60
3502 | PURBA MEDINIPUR | Central Drilling | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Hiring of Disel Driven Motor Cab ( BS-IV & Above) having contract carriage permit along with driver for the office of the Driller In Charge, CMSD-II (D) , CDD, P.H. Engineering Dte. | 264/CMSD-II(D) | 15/12/2023 | 183 | DILIP KAR | 0.86 | 2.08 | 240.89 | 70
3503 | PURBA MEDINIPUR | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Material Requisition To Resource Division | 125/TD | 05/01/2024 | 0 | Resource Division | 13.24 | 0 | 0 | 0
3504 | PURBA MEDINIPUR | Midnapore Mechanical | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Kadua W/S scheme PH-I Application No.-2004550666 Ref.-204181244 | BP-2023-24-539 | 11/01/2024 | 0 | WBSEDCL | 2.97 | 0 | 0 | 0
3505 | PURBA MEDINIPUR | Midnapore Mechanical | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Kadua W/S scheme PH-II Application No.-2004550634 Ref.-204181242 | BP-2023-24-538 | 11/01/2024 | 0 | WBSEDCL | 2.76 | 0 | 0 | 0
3506 | PURBA MEDINIPUR | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 840 Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-B) | 538/TD | 12/05/2023 | 1007 | GIRI CONSTRUCTION | 199.43 | 0 | 0 | 90
3507 | PURBA MEDINIPUR | Central Drilling | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 58.13 | 102.32 | 11
3508 | PURBA MEDINIPUR | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( Intze type with pile foundation ) & Accommodate FHTC ( 900Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-A) | 2436/TD | 19/09/2023 | 651 | BIDHAN MONDAL | 246.91 | 67.82 | 27.47 | 45
3509 | PURBA MEDINIPUR | Central Drilling | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Continuation Hiring of Disel Driven Motor Cab ( BS-IV & Above) having contract carriage permit along with driver for the office of the Driller In Charge, CMSD-II (D) , CDD, P.H. Engineering Dte. | 124/CMSD-II(D) | 27/06/2024 | 182 | DILIP KAR | 0.86 | 2.06 | 238.29 | 0
3510 | PURBA MEDINIPUR | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Land development of 2nd T/W Site at Kadua & Its Adjoining Mouzas water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | 892/DSD | 02/09/2024 | 7 | GIRI CONSTRUCTION | 1.85 | 0 | 0 | 0
3511 | PURBA MEDINIPUR | Central Drilling | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Continuation Hiring of Disel Driven Motor Cab ( BS-IV & Above) having contract carriage permit along with driver for the office of the Driller In Charge, CMSD-II (D) , CDD, P.H. Engineering Dte. | 294/CMSD-II(D) | 30/12/2024 | 182 | DILIP KAR | 0.86 | 2.08 | 240.76 | 0
3512 | PURBA MEDINIPUR | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS , SM/13689 | New | Laying distribution pipe line, & Accommodate FHTC (261Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C ) | 3553/TD | 29/03/2023 | 808 | MRINAL KANTI PRADHAN | 84.53 | 69.26 | 82.06 | 100
3513 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-2 , SM/14840 | Augmentation | Laying distribution pipe line & Accommodate FHTC (7 Nos) under JJM with allied work for Chirulia-Chatla (Zone-II) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division ,PHED , Purba Medinipur. | 542/TD | 12/05/2023 | 60 | SUBHENDU HAZRA | 71.29 | 60.07 | 84.25 | 93
3514 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-2 , SM/14840 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- II ) | 1056/TD | 18/08/2022 | 20 | ASTER CONSULTANCY | 4.01 | 4.01 | 100 | 100
3515 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Chirulia-Chatla Zone-2 , SM/14840 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Egra - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1207/W/MMD | 25/04/2023 | 981 | BHABANI PRASAD MANNA | 59.85 | 0 | 0 | 20
3516 | PURBA MEDINIPUR | Midnapore Mechanical | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS , SM/14671 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KULRAKHI AND IT'S ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 592/W/MMD | 20/03/2023 | 180 | ASHUTOSH DAS & CO. | 21.53 | 0 | 0 | 0
3517 | PURBA MEDINIPUR | Tamluk Division | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS , SM/14671 | New | Material Requisition To Resource Division | 2448/TD | 16/01/2023 | 0 | Resource Division | 26.2 | 0 | 0 | 0
3518 | PURBA MEDINIPUR | Midnapore Mechanical | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS , SM/14671 | New | Quotation Bill for New Service connection at T/W NO-II Of KULRAKHI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004769788/QUOT/03 DT. 10-06-2024 MEMO NO: AMR/PHE/171 DT. 10-06-2024 Application NO- 2004769788 Application type-New connection Consumer Id- 204327232 | BP-2024-25-339 | 25/06/2024 | 0 | WBSEDCL | 3.11 | 0 | 0 | 0
3519 | PURBA MEDINIPUR | Midnapore Mechanical | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS , SM/14671 | New | Quotation Bill for New Service connection at T/W NO-I Of KULRAKHI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743601/QUOT/03 DT. 20-05-2024 Application NO- 2004743601 Application type-New connection Consumer Id- 204312616 | BP-2024-25-322 | 24/06/2024 | 0 | WBSEDCL | 5.12 | 0 | 0 | 0
3520 | PURBA MEDINIPUR | Tamluk Division | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS , SM/14671 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 125.85 | 34.32 | 51
3521 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Barsundra PWSS in the District of Purba Medinipur under JJM programme, Block ¿ Haldia, District - Purba Medinipur under MMD PHE Dte. | 396/W/MMD | 15/03/2023 | 180 | BALAJI CONSTRUCTION | 12.4 | 11.59 | 93.47 | 60
3522 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | Land development of ditch and Approach Road with Box Culvert at 3rd T.W. site of Barsundra Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | 214/TD | 17/04/2023 | 30 | BISWANATH BHUNIA | 16.31 | 0 | 0 | 0
3523 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Barsundra Water Supply Scheme under Tamluk Division, PHE Dte. | 1518/TD | 07/01/2022 | 20 | RADIANT | 4.5 | 4.5 | 100 | 100
3524 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | Material Requisition To Resource Division | 2611/TD | 02/02/2023 | 0 | Resource Division | 118.88 | 0 | 0 | 0
3525 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | Material Requisition To Resource Division | 2643/TD | 13/10/2023 | 0 | Resource Division | 36.47 | 0 | 0 | 0
3526 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | Augmentation of ground water based Barsundra Water Supply Scheme by providing Laying of Distribution to accommodate FHTC (5920 Nos),construction of R.C.C. Elevated Reservoir of capacity 750 cum and staging height 20.00 mtr. with allied works within Haldia Dev.Block under Haldia sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur | 2860/TD | 17/02/2023 | 865 | TAPAS SANTRA | 900.87 | 651.29 | 72.3 | 73
3527 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | Crossing permission of laying HDPE pipeline along and across of NH-116 of Barsundra Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | 3285/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 9.93 | 3.64 | 36.67 | 30
3528 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 1st Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1249/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 83.68 | 40.74 | 100 | 75
3529 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments for Rejuvenation of elctro-mechanical components of Barsundra PWSS in the district of purba medinipur district under JJM program,Block-Haldia,under MMD PHE Dte. | 951/HESD | 30/11/2023 | 7 | BALAJI CONSTRUCTION | 0.69 | 0.54 | 100 | 100
3530 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | Installation of 4 Nos. Display Board at different PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte.(for Barsundra PWSS, Betkundu PWSS, Baramrit Beria PWSS, Amritberya PWSS) (Phase-VII) | 768/HSD, | 27/02/2024 | 7 | SNEHASIS BERA | 0.83 | 0.83 | 100 | 100
3531 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | Quotation bill for shifting of PHE meter room with allied works at PH-I of Barsundra w/s scheme under MMD PHE Dte. Name of C.C.C.-Brajalalchak Reference ID-860311526 Application ID-100000117246 Quotation Date-27/08/2024 Quotation Due Date-25/11/2024 | C092404597616 | 05/09/2024 | 0 | WBSEDCL | 1.38 | 0 | 0 | 0
3532 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | Laying of proposed Rising main line with inter connection ,Supply of DI Specials, at Head Work Site at Barsundara Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2698/TD | 22/08/2024 | 25 | ANIRBAN BHOWMIK | 10.21 | 0 | 0 | 0
3533 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. , SM/14113 | Augmentation | New Construction of boundary wall at 3rd T/W site (50mt) of Barsundra water supply scheme under Haldia Sub-Division PHE Dte.. | 3168/TD | 10/03/2023 | 749 | M/S SOURAV MAHAPATRA | 6.26 | 0 | 0 | 100
3534 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | 598/TD | 17/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.72 | 4.71 | 100 | 100
3535 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Material Requisition To Resource Division | 2612/TD | 02/02/2023 | 0 | Resource Division | 210.83 | 0 | 0 | 0
3536 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Material Requisition To Resource Division | 2641/TD | 13/10/2023 | 0 | Resource Division | 28.85 | 0 | 0 | 0
3537 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Pora Chingra, JL No. 155) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for Additional Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 2244/TD | 29/12/2022 | 40 | PRANTIK DRILLING AGENCY | 61.68 | 32.14 | 91.4 | 90
3538 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Laying of Distribution pipe line to accommodate FHTC (4683 Nos) with construction of R.C.C. Elevated Reservoir of capacity 400 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Bajkul Zone - III Water Supply Scheme within Bhagabanpur- I &II Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | 1887/TD | 09/08/2023 | 601 | DAS ENTERPRISE | 779.24 | 266.54 | 34.21 | 50
3539 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Repair and renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site at mouza- Bajkul,J.L- No -156, under Bajkul - III Water Supply Scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 724/TD | 28/02/2024 | 40 | PARTHA CONSTRUCTION | 10.65 | 0 | 0 | 0
3540 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Sinking of 300 mm x 200 mm dia x 225 mtr. deep tube well by direct rotary rig method for Replacement of 2nd Tube well of Bajkul Zone-III Water Supply Scheme within Bhagwanpur-I & II Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | 608/TD | 16/02/2024 | 20 | B. K. ENTERPRISE | 17.8 | 0 | 0 | 0
3541 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 600 cum RCC OHR at Bajkul Zone-III PWSS at Bhagwanpur-I & II Block under Tamluk Division,PHE Dte. | 383/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3542 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE-III Of BAJKUL W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004606772/QUOT/03/426 DT. 19-02-2024 Application NO- 2004606772 Application type-New connection Reference Id- 204221105 | BP-2023-24-760 | 01/03/2024 | 0 | WBSEDCL | 2.86 | 0 | 0 | 0
3543 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Payment of wayleave facility charges (SER-KGP-2024-WL-45) | BP-2024-25-76 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.41 | 0 | 0 | 0
3544 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Quotation money for shifting of 11 KV OH Henria Feeder at Najir Bazar for Bajukl Zone-III PWSS under Tamluk Division, PHE Dte. | BP-2023-24-743 | 04/01/2024 | 0 | WBSEDCL | 2.63 | 0 | 0 | 0
3545 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Quotation Bill for New Service connection at T/W NO-IV, ZONE-III Of BAJKUL W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004606750/QUOT/03/424 DT. 19-02-2024 Application NO- 2004606750 Application type-New connection Reference Id- 204221087 | BP-2023-24-761 | 01/03/2024 | 0 | WBSEDCL | 2.62 | 0 | 0 | 0
3546 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III, Block Bhagawanpur II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1275/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 37.71 | 22.94 | 60.85 | 76
3547 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Laying of Left-Out portion uPVC Pipe line due to uncovered area under Bajkul Zone-III Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 2679/TD | 22/08/2024 | 160 | SWARUPANANDA DAS | 83.59 | 0 | 0 | 0
3548 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk and replacement Tube well at BAJKUL zone III Water supply scheme, BHAGWANPUR - II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 1067/W/MMD | 14/03/2024 | 360 | DEBJYOTI BASU | 25.9 | 0 | 0 | 55
3549 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Pump House, Boundary Wall and others allied works for 4th Tube well site at moza- Bajkul,J.L- No -156, under Bajkul - III Water Supply scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1076/TD | 16/03/2024 | 316 | M/S. S. A. CONSTRUCTION | 11.22 | 0 | 0 | 90
3550 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Repair and renovation and others allied works of Pump House, Boundary Wall for 2nd. Tube well site at mouza- Bajkul,J.L- No -156, under Bajkul - III Water Supply Scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1077/TD | 16/03/2024 | 329 | M/S. S. A. CONSTRUCTION | 9.84 | 0 | 0 | 100
3551 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III , SM/15510 | Augmentation | Pump House, Boundary Wall and others allied works for 3rd Tube well site at moza- Bajkul,J.L- No -156, under Bajkul - III Water Supply scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 2322/TD | 23/07/2024 | 320 | M/S S M H CONSTRUCTION | 10.68 | 0 | 0 | 100
3552 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15038 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Augmentation of Barchunfali W/S Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 479/TD | 10/05/2023 | 60 | SAURAV HAZRA | 3.6 | 0 | 0 | 0
3553 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15038 | Augmentation | Laying of different dia UPVC pipe line to accommodate 70 Nos FHTC to make Benipur Mouza, Chuaphali, Ghata, Hugli, Khikina & Subdi mouzas as Swajal Gram of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | 2095/TD | 13/12/2022 | 20 | M/S UNIQUE. | 7.92 | 6.38 | 100 | 100
3554 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15038 | Augmentation | Material Requisition To Resource Division | 342/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0 | 0
3555 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15038 | Augmentation | Re- Laying od different dia. UPVC Pipe and Constrution of Boundary wall (as per Departmental Design & Drawing),Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | 242/TD | 19/04/2023 | 45 | SUBRATA KUMAR BERA | 30.48 | 17.76 | 68.42 | 60
3556 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15038 | Augmentation | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well for Augmentatuion of Barchunfali & its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 478/TD | 10/05/2023 | 30 | SUBHRANGSHU SEKHAR GIRI | 3.38 | 0 | 0 | 0
3557 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15038 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 119/TD | 06/04/2023 | 703 | B. K. ENTERPRISE | 53.77 | 11.35 | 84.44 | 75
3558 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15038 | Augmentation | Quotation Bill for New Service connection at T/W NO-III Of BARCHUNFALI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2004877553/QUOT/03 DT. 29-08-2024 Application NO- 2004877553 Application type-New connection Consumer Id- 204387021 | C092406568982 | 06/09/2024 | 0 | WBSEDCL | 6.02 | 0 | 0 | 0
3559 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/15038 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. under JJM Program under MMD PHE Dte. | 893/W/MMD | 27/03/2023 | 180 | SUDIKSHA CONSTRUCTION | 11.83 | 0 | 0 | 0
3560 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/14745 | New | Material Requisition To Resource Division | 3001/TD | 27/02/2023 | 0 | Resource Division | 9.75 | 0 | 0 | 0
3561 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/14745 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 604/W/MMD | 20/03/2023 | 180 | KRISHNA ENGINEERING | 11.95 | 5.39 | 45.12 | 45
3562 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/14745 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 50 cum RCC OHR at Dakshin Kalyanpur PWSS at Ramnagar-II Block under Tamluk Division,PHE Dte. | 379/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3563 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/14745 | New | Material Requisition To Resource Division | 132/TD | 05/01/2024 | 0 | Resource Division | 1.45 | 0 | 0 | 0
3564 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/14745 | New | Quotation Bill for New Service connection at T/W NO-II Of DAKSHIN KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004671005/QUOT/03 DT. 05-04-2024 Application NO- 2004671005 Application type-New connection Consumer Id- 204268105 | BP-2024-25-47 | 18/04/2024 | 0 | WBSEDCL | 2.16 | 0 | 0 | 0
3565 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/14745 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 50 Cum OHR & Accommodate FHTC ( 236 Nos) under JJM with allied work for DAKSHIN KALYANPUR & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 1758/TD | 01/08/2023 | 853 | PREMANANDA ROY BISWAS | 164.16 | 75.61 | 46.06 | 40
3566 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/14745 | New | Drum Sheet walling, road restoration for distribution pipe line( for FHTC) & Accommodate FHTC (80 Nos) under JJM with allied work for Dakshin Kalyanpur PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 3474/TD | 06/11/2024 | 30 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.7 | 0 | 0 | 0
3567 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-III , SM/15846 | Augmentation | Material Requisition To Resource Division | 2075/TD | 28/08/2023 | 0 | Resource Division | 14.02 | 0 | 0 | 0
3568 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-III , SM/15846 | Augmentation | Material Requisition To Resource Division | 2998/TD | 29/11/2023 | 0 | Resource Division | 1.64 | 0 | 0 | 0
3569 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-III , SM/15846 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 0 | 50
3570 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-III , SM/15846 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone- III) under Tamluk Division, PHE Dte. | 740/TD | 25/05/2023 | 20 | ASTER CONSULTANCY | 3.49 | 3.48 | 100 | 100
3571 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-III , SM/15846 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Zone-III PWSS at Ramnagar-II Block under Tamluk Division,PHE Dte. | 374/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
3572 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-III , SM/15846 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT ZONE-3, TW-II OF SHANKARPUR WS SCHEME UNDER MMD, PHE DTE, BLOCK-RAMNAGAR -1, DIGHA CCC APP. NO-2004746394 CON ID-204313991 | BP-2024-25-257 | 06/06/2024 | 0 | WBSEDCL | 0.71 | 0 | 0 | 0
3573 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-III , SM/15846 | Augmentation | Quotation Bill for New Service connection at T/W NO-I , ZONE-III Of SANKARPUR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-I, DIGHA C.C.C. Ref. Memo No- 2004626526/QUOT/03 DT. 04-03-2024 Application NO- 2004626526 Application type-New connection Consumer Id- 204233340 | BP-2023-24-809 | 11/03/2024 | 0 | WBSEDCL | 3.85 | 0 | 0 | 0
3574 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-III , SM/15846 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1211/W/MMD | 25/04/2023 | 859 | S.S.GHORAI | 23.52 | 14.1 | 59.95 | 75
3575 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-III , SM/15846 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 267 Nos) under JJM with allied work for SANKARPUR (Zone-III) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | 1756/TD | 01/08/2023 | 910 | SUSIL KUMAR HAZRA | 193.96 | 0 | 0 | 40
3576 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-III , SM/15846 | Augmentation | Laying distribution pipe line due to Re-design, & Accommodate Balance FHTC ( 98 Nos) under JJM with allied work for SANKARPUR (Zone-III) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division ,PHED , Purba Medinipur | 1903/TD | 07/06/2024 | 25 | SOUMYA ENTERPRISE | 53.79 | 0 | 0 | 65
3577 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC (Balance Work) (579 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-IV, Blo , SM/10435 | Retrofitting | Retrofitting to accommodate FHTC(Balance work) (579 nos.) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-IV, Block-Kolaghat in the District of Purba Medinipur.(Phase-II) | 62/TD | 05/04/2022 | 30 | CONCORD ENGINEERING | 91.47 | 65.2 | 71.28 | 100
3578 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) , SM/16460 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (172 nos) under JJM with allied work for Panchrol PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 243/TD | 19/04/2023 | 808 | KRISHNENDU SEKHAR DAS | 61.6 | 28.15 | 45.71 | 50
3579 | PURBA MEDINIPUR | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) , SM/16460 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 0 | 50
3580 | PURBA MEDINIPUR | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) , SM/16460 | Augmentation | Quotation For New Service Connections at Tube Well-III of Panchrol W/S scheme under MMD PHE Dte. Chorepalia CCC Block- Egra-I Application No.-2004746343 Consumer ID.-204313789 Application Date.-29/05/2024 | BP-2024-25-251 | 06/06/2024 | 0 | WBSEDCL | 4.71 | 0 | 0 | 0
3581 | PURBA MEDINIPUR | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) , SM/16460 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) within Purba Medinipur District under JJM Program under MMD PHE Dte. | 899/W/MMD | 27/03/2023 | 720 | M/S EMMESS | 12.63 | 8.28 | 65.51 | 90
3582 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) , SM/16462 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (239 nos) under JJM with allied work for Bheribaranga PWSS within Ramnagar -II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 247/TD | 19/04/2023 | 808 | KRISHNENDU SEKHAR DAS | 66.11 | 11.35 | 17.17 | 75
3583 | PURBA MEDINIPUR | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) , SM/16462 | Augmentation | Quotation for new service connection at tw-III of Bheribaranga ws under MMD,PHE Dte ,Block-Ramnagar-II. Digha CCC Application no-2004764489 CON ID-204324289 | BP-2024-25-290 | 18/06/2024 | 0 | WBSEDCL | 4.32 | 0 | 0 | 0
3584 | PURBA MEDINIPUR | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) , SM/16462 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) within Purba Medinipur District under JJM Program under MMD PHE Dte. | 897/W/MMD | 27/03/2023 | 720 | A.S.ENTERPRISE | 12.62 | 0 | 0 | 75
3585 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Dulalpur PWSS under Egra-II Block (Phase-II) , SM/16466 | Retrofitting | Retrofitting to accommodate FHTC (Phase-II) under JJM in DULALPUR PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur (Part-A) | 245/TD | 19/04/2023 | 30 | AYSAN KHAN | 25.68 | 25.66 | 100 | 100
3586 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Dulalpur PWSS under Egra-II Block (Phase-II) , SM/16466 | Retrofitting | Schedule for retrofitting to accommodate FHTC under JJM in DULALPUR PWSS within Egra-II Block under DighaSub-Division of Tamluk Division,P HE Dte. in the District of Purba Medinipur (Part-B) | 246/TD | 19/04/2023 | 560 | AYSAN KHAN | 5.16 | 0 | 0 | 100
3587 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-III , SM/16300 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | 1861./TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 2.89 | 100 | 100
3588 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-III , SM/16300 | Augmentation | Material Requisition To Resource Division | 2072/TD | 28/08/2023 | 0 | Resource Division | 15.35 | 0 | 0 | 0
3589 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-III , SM/16300 | Augmentation | Material Requisition To Resource Division | 3003/TD | 29/11/2023 | 0 | Resource Division | 0.34 | 0 | 0 | 0
3590 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-III , SM/16300 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, Zone-III Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004793307/QUOT/03/380 DT. 02-07-2024 Application NO- 2004793307 Application type-New connection Consumer Id- 204346846 | BP-2024-25-497 | 31/07/2024 | 0 | WBSEDCL | 3.96 | 0 | 0 | 0
3591 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-III , SM/16300 | Augmentation | Quotation Bill for New Service connection at T/W NO-I Of BARHUARY ZIII W/S Scheme under MMD, PHE, Dte. Block- EGRA II, WBSEDCL SUPPLY OFFICE: BALIGHAIC.C.C. Ref. Memo No- 2004737554/QUOT/03 DT. 16-05-2024 Application NO- 2004737554 Application type-New connection Consumer Id- 204309058 | BP-2024-25-292 | 18/06/2024 | 0 | WBSEDCL | 3.27 | 0 | 0 | 0
3592 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-III , SM/16300 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1242/W/MMD | 28/04/2023 | 764 | BHABANI PRASAD MANNA | 84.29 | 0 | 0 | 70
3593 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-III , SM/16300 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (55 nos) under JJM with allied work for Bathuari (Zone-III) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 1761/TD | 01/08/2023 | 853 | ARABINDA GHOSH | 261.16 | 58.13 | 22.26 | 80
3594 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-IV , SM/16305 | Augmentation | Material Requisition To Resource Division | 2070/TD | 28/08/2023 | 0 | Resource Division | 14.46 | 0 | 0 | 0
3595 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-IV , SM/16305 | Augmentation | Material Requisition To Resource Division | 2999/TD | 29/11/2023 | 0 | Resource Division | 1.81 | 0 | 0 | 0
3596 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-IV , SM/16305 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 294 Nos) under JJM with allied work for SANKARPUR (Zone-IV) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 1732/TD | 31/07/2023 | 610 | ONKAR ENTERPRISE | 216.84 | 69.71 | 32.15 | 55
3597 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-IV , SM/16305 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone- IV) under Tamluk Division, PHE Dte. | 741/TD | 25/05/2023 | 20 | ASTER CONSULTANCY | 3.46 | 3.46 | 100 | 100
3598 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-IV , SM/16305 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Z-IV PWSS at Ramnagar-I Block under Tamluk Division,PHE Dte. | 1053/TD | 15/03/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3599 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-IV , SM/16305 | Augmentation | Sankarpur W/S scheme PH.-II, zone-IV Application No.-2004565718 Ref.-204193727 | BP-2023-24-622 | 07/02/2024 | 0 | WBSEDCL | 7.26 | 0 | 0 | 0
3600 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-IV , SM/16305 | Augmentation | Sankarpur W/S scheme TW no.-I, Z-IV Ref.-204156071 Application ID-2004521698 | BP-2023-24-442 | 19/12/2023 | 0 | WBSEDCL | 2.63 | 0 | 0 | 0
3601 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-IV , SM/16305 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-IV in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1212/W/MMD | 25/04/2023 | 180 | SUBHASIS ROY | 23.93 | 22.24 | 92.93 | 90
3602 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dakhsin Mechogram PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16869 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3603 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chirulia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16856 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
3604 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chirulia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16856 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3605 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Baichberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16882 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
3606 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Baichberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16882 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3607 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bara Subarna Nagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16883 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
3608 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bara Subarna Nagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16883 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3609 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Asthichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16889 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
3610 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Asthichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16889 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3611 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bishnubarh PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16892 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3612 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Badhia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16860 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
3613 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Badhia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/16860 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3614 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Argoal PWSS in the District of Purba Medinipur under JJM programme. , SM/16670 | Augmentation | Rejuvenation of Electro-Mechanical components of Argoal PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 759/W/MMD | 23/03/2023 | 180 | MENAKA ENTERPRISE | 12.23 | 5.82 | 47.61 | 35
3615 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Khejuri Zone I & II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17872 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
3616 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Khejuri Zone I & II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17872 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3617 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at KANKTYA PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17756 | Solarisation | Solarization of grid connected pumping installation at KANKTYA PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1038/W/MMD | 29/03/2023 | 180 | SOUMEN ELECTRIC | 6.26 | 4.89 | 78.03 | 30
3618 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Silampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17890 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
3619 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Silampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17890 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3620 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bheri Bharanga PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17894 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
3621 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bheri Bharanga PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17894 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3622 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Negua PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17895 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
3623 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Negua PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17895 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3624 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kanakpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17896 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
3625 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kanakpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17896 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3626 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Rangibasan PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17764 | Solarisation | Solarization of grid connected pumping installation at Rangibasan PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1018/W/MMD | 29/03/2023 | 705 | MEGA SOLAR ENERGY | 6.26 | 0 | 0 | 0
3627 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Manikpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17771 | Solarisation | Solarization of grid connected pumping installation at Manikpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1025/W/MMD | 29/03/2023 | 180 | SUBHASIS ROY | 6.26 | 0 | 0 | 0
3628 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Purba Bakulda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17774 | Solarisation | Solarization of grid connected pumping installation at Purba Bakulda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1031/W/MMD | 29/03/2023 | 180 | KAMAKSHYA ENTERPRISE | 6.26 | 0 | 0 | 0
3629 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Saripur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17780 | Solarisation | Solarization of grid connected pumping installation at Saripur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1000/W/MMD | 29/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 4.88 | 78.03 | 80
3630 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Durmut PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17789 | Solarisation | Solarization of grid connected pumping installation at Durmut PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1004/W/MMD | 29/03/2023 | 180 | AMITAVA CHAKRABORTY | 6.26 | 0 | 0 | 0
3631 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Natshallakhya, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17803 | Solarisation | Solarization of grid connected pumping installation at Natshallakhya, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1015/W/MMD | 29/03/2023 | 180 | MEGA SOLAR ENERGY | 6.26 | 4.66 | 74.47 | 60
3632 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Rashikachak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17720 | Solarisation | Solarization of grid connected pumping installation at Rashikachak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 999/W/MMD | 29/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 4.88 | 78.03 | 60
3633 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Rashikachak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17720 | Solarisation | Processing fees for solar metering application for Rashikachak w/s scheme in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004647940, C ID 224068591) | BP-2023-24-922 | 28/03/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
3634 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chandanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17386 | Solarisation | Solarization of grid connected pumping installation at Chandanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 742/W/MMD | 23/03/2023 | 707 | PRANAB KUMAR DAS | 6.26 | 4.85 | 77.48 | 80
3635 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chandanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17386 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0.18 | 96.99 | 100
3636 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17221 | Augmentation | Material Requisition To Resource Division | 359/TD | 26/04/2023 | 0 | Resource Division | 4.41 | 0 | 0 | 0
3637 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17221 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. under JJM Program under MMD PHE Dte. | 1208/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 11.44 | 7.08 | 61.89 | 50
3638 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17221 | Augmentation | Name of Work: Sinking of 3 (Three) nos.Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Kotbar W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Saripur W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Paramanandapur W/S Scheme within Moyna Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 118/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 61.66 | 15.68 | 100 | 100
3639 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bajkul, Zone-I, Zone-II & Zone-III PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17359 | Solarisation | Solarization of grid connected pumping installation at Bajkul, Zone-I, Zone-II and Zone-III PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 754/W/MMD | 23/03/2023 | 180 | JYOTY SOLAR POWER | 18.78 | 4.85 | 25.83 | 60
3640 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mukundapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17851 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
3641 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mukundapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17851 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3642 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mahammadpur (Bhagabanpur-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17915 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at MAHAMMADPUR and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 649/HESD | 08/07/2024 | 15 | SOUMEN ELECTRIC | 1.94 | 0 | 0 | 100
3643 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mahammadpur (Bhagabanpur-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17915 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3644 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17824 | Solarisation | Solarization of grid connected pumping installation at Kanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1036/W/MMD | 29/03/2023 | 180 | SUBHASIS ROY | 6.26 | 0 | 0 | 0
3645 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17824 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0.18 | 96.99 | 100
3646 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Arjunnagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17348 | Solarisation | Solarization of grid connected pumping installation at Arjunnagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 714/W/MMD | 23/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 4.85 | 77.48 | 85
3647 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Solat PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17907 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
3648 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Solat PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17907 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3649 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Paniparul PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17916 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
3650 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Paniparul PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17916 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3651 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Baharchandberya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17315 | Solarisation | Solarization of grid connected pumping installation at Baharchandberya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 713/W/MMD | 23/03/2023 | 180 | M/S. JIT ENTERPRISE | 6.26 | 4.85 | 77.48 | 75
3652 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Amarsikasba Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17836 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
3653 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Amarsikasba Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17836 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3654 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Majna PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17892 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
3655 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Majna PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17892 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3656 | PURBA MEDINIPUR | Tamluk Division | GURGRAM & ADJOINING MOUZAS , SM/18311 | New | Material Requisition To Resource Division | 2381/TD | 16/01/2023 | 0 | Resource Division | 75.63 | 0 | 0 | 0
3657 | PURBA MEDINIPUR | Midnapore Mechanical | GURGRAM & ADJOINING MOUZAS , SM/18311 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GURGRAM & ADJOINING MOUZAS, Block- Bhagwanpur I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1628/W/MMD | 25/07/2023 | 180 | ALPHA ENTERPRISE | 23.68 | 23.17 | 100 | 80
3658 | PURBA MEDINIPUR | Tamluk Division | GURGRAM & ADJOINING MOUZAS , SM/18311 | New | Material Requisition To Resource Division | 121/TD | 05/01/2024 | 0 | Resource Division | 17.85 | 0 | 0 | 0
3659 | PURBA MEDINIPUR | Midnapore Mechanical | GURGRAM & ADJOINING MOUZAS , SM/18311 | New | Gurgram W/S scheme PH-II,(River Side) Application No.-2004523993 Ref.-204157866 | BP-2023-24-475 | 27/12/2023 | 0 | WBSEDCL | 9.17 | 0 | 0 | 0
3660 | PURBA MEDINIPUR | Midnapore Mechanical | GURGRAM & ADJOINING MOUZAS , SM/18311 | New | Gurgram W/S scheme PH-I,(Primary School) Application No.-2004523960 Ref.-204157826 | BP-2023-24-476 | 27/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0 | 0
3661 | PURBA MEDINIPUR | Tamluk Division | GURGRAM & ADJOINING MOUZAS , SM/18311 | New | Sinking of Tube Well ,Construction of Pump House ,400 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2897 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of GURGRAM PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 1689/TD | 26/07/2023 | 717 | TARUN KOLEY | 894.96 | 603.82 | 67.47 | 69
3662 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kolsar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17844 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
3663 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kolsar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17844 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
3664 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Begunberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17293 | Solarisation | Solarization of grid connected pumping installation at Begunberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 745/W/MMD | 23/03/2023 | 180 | M/S. JIT ENTERPRISE | 6.26 | 4.88 | 78.03 | 60
3665 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Begunberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17293 | Solarisation | Application fees for NET BILLING for solar power plant of 10 KWp at Begunberia w/s scheme in the Dist. of purba mediniupur under MMD PHE Dte. Name of C.C.C.-Chaitanyapur Application no.-2004837090 Consumer ID-224005300 | C082409418565 | 07/08/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
3666 | PURBA MEDINIPUR | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Material Requisition To Resource Division | 2387/TD | 16/01/2023 | 0 | Resource Division | 23.22 | 0 | 0 | 0
3667 | PURBA MEDINIPUR | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (500 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-A) | 00/TD | 10/03/2023 | 180 | SRIMANTA KUMAR MAITY | 0 | 0 | 0 | 0
3668 | PURBA MEDINIPUR | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Laying distribution pipe line & Accommodate FHTC ( 480 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-C) | 3189/TD | 10/03/2023 | 997 | SRIMANTA KUMAR MAITY | 67.29 | 30.57 | 45.43 | 50
3669 | PURBA MEDINIPUR | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Laying distribution pipe line & Accommodate FHTC (83 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-D) | 3190/TD | 10/03/2023 | 997 | KAMAL KUMAR BERA | 19.35 | 11.42 | 59 | 75
3670 | PURBA MEDINIPUR | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Laying of Distribution pipe line by HDPE pipes with allied works of URURI- PWSS in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(PART-E) | 567/TD | 15/02/2024 | 655 | KAMAL KUMAR BERA | 5.66 | 4.02 | 71.07 | 80
3671 | PURBA MEDINIPUR | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Instalation of display Board at different work site of Ururi, Garabar, Itaberia & Adjoining Moujas New PWSS in Bhagawanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2328/CSD | 29/12/2023 | 10 | KAMAL KUMAR BERA | 0.62 | 0.62 | 100 | 100
3672 | PURBA MEDINIPUR | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Material Requisition To Resource Division | 628/W | 20/02/2024 | 0 | Resource Division | 13.76 | 0 | 0 | 0
3673 | PURBA MEDINIPUR | Midnapore Mechanical | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Quotation Bill for New Service connection at T/W NO-II Under URURI W/S Scheme under MMD,PHE,Dte. Ref. Quotation no- 2004558742/Quot/03 dt. 10- Jan-24 quotation Due date- 09-Jan-25 Application NO- 2004558742 Application type-New connection Reference Id- 204188975 | BP-2023-24-676 | 15/02/2024 | 0 | WBSEDCL | 3.62 | 0 | 0 | 0
3674 | PURBA MEDINIPUR | Midnapore Mechanical | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Quotation Bill for New Service connection at T/W NO-II Of URURI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No- 2004570649/QUOT/03 DT. 22-01-2024 Application NO- 2004570649 Application type-New connection Consumer Id- 204198017 | BP-2024-25-249 | 06/06/2024 | 0 | WBSEDCL | 3.76 | 0 | 0 | 0
3675 | PURBA MEDINIPUR | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Pump House , Laying distribution pipe line, Boundary Wall & Accommodate FHTC (1170 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-B) | 687/TD | 23/05/2023 | 1034 | RELIABLE CONSTRUCTIONS | 241.87 | 121.98 | 50.43 | 52
3676 | PURBA MEDINIPUR | Central Drilling | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 53.38 | 97.45 | 11
3677 | PURBA MEDINIPUR | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (500 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-A) | 139/TD | 05/01/2024 | 481 | SRIMANTA KUMAR MAITY | 242.35 | 53.69 | 22.15 | 45
3678 | PURBA MEDINIPUR | Midnapore Mechanical | URURI AND ADJOINING MOUJAS PWSS , SM/12166 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
3679 | PURBA MEDINIPUR | Tamluk Division | TALADIHA AND ADJOINING MOUJAS PWSS , SM/12283 | New | Material Requisition To Resource Division | 2705/TD | 06/02/2023 | 0 | Resource Division | 51.54 | 0 | 0 | 0
3680 | PURBA MEDINIPUR | Tamluk Division | TALADIHA AND ADJOINING MOUJAS PWSS , SM/12283 | New | Sinking Tube well,Pump House , Construction of 200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1324 nos), Including 2 years of operation maintance under JJM with allied work for Taladiha PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1093/TD | 08/06/2023 | 876 | SUJATA CONSTRUCTION | 373.7 | 66.61 | 17.83 | 21
3681 | PURBA MEDINIPUR | Midnapore Mechanical | TALADIHA AND ADJOINING MOUJAS PWSS , SM/12283 | New | Quotation Bill for New Service connection at T/W NO-II Of TALADIHA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004969351/QUOT/03 DT. 18-11-2024 MEMO NO: AMR/PHE/512 DT. 18-11-2024 Application NO- 2004969351 Application type-New connection Consumer Id- 204448691 | C112433888301 | 27/11/2024 | 0 | WBSEDCL | 6.1 | 0 | 0 | 0
3682 | PURBA MEDINIPUR | Midnapore Mechanical | TALADIHA AND ADJOINING MOUJAS PWSS , SM/12283 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TALADIHA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2414/W/MMD | 31/12/2022 | 857 | ECO ENTERPRISE | 22.8 | 11.71 | 51.34 | 40
3683 | PURBA MEDINIPUR | Tamluk Division | GOPINATHPUR & ADJOINING MOUZAS , SM/12158 | New | Material Requisition To Resource Division | 2728/TD | 06/02/2023 | 0 | Resource Division | 36.99 | 0 | 0 | 0
3684 | PURBA MEDINIPUR | Midnapore Mechanical | GOPINATHPUR & ADJOINING MOUZAS , SM/12158 | New | Electric Quotation for GOPINATHPUR Water Supply Scheme T/W-II, (Ref. ID-204089466) | BP-2023-24-319 | 01/11/2023 | 0 | WBSEDCL | 3.17 | 0 | 0 | 0
3685 | PURBA MEDINIPUR | Midnapore Mechanical | GOPINATHPUR & ADJOINING MOUZAS , SM/12158 | New | Electric Quotation for GOPINATHPUR Water Supply Scheme T/W-I, (Ref. ID-204089465) | BP-2023-24-310 | 01/11/2023 | 0 | WBSEDCL | 3.57 | 0 | 0 | 0
3686 | PURBA MEDINIPUR | Midnapore Mechanical | GOPINATHPUR & ADJOINING MOUZAS , SM/12158 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOPINATHPUR and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | 939/W/MMD | 28/03/2023 | 180 | MENAKA ENTERPRISE | 23.67 | 21.89 | 94.6 | 100
3687 | PURBA MEDINIPUR | Tamluk Division | GOPINATHPUR & ADJOINING MOUZAS , SM/12158 | New | Material Requisition To Resource Division | 130/TD | 05/01/2024 | 0 | Resource Division | 11.4 | 0 | 0 | 0
3688 | PURBA MEDINIPUR | Tamluk Division | GOPINATHPUR & ADJOINING MOUZAS , SM/12158 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2740 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Gopinathpur PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 457/TD | 04/05/2023 | 822 | TAPAS SANTRA | 588.58 | 387.98 | 65.92 | 85
3689 | PURBA MEDINIPUR | Midnapore Mechanical | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS , SM/12404 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DWARIKAPUR and ADJOINING MOUJAS, Block ¿ Bhagwanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2419/W/MMD | 31/12/2022 | 180 | BOSE & CHATTERJEE INDUSTRIES | 22.76 | 0 | 0 | 0
3690 | PURBA MEDINIPUR | Tamluk Division | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS , SM/12404 | New | Material Requisition To Resource Division | 2386/TD | 16/01/2023 | 0 | Resource Division | 13.74 | 0 | 0 | 0
3691 | PURBA MEDINIPUR | Tamluk Division | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS , SM/12404 | New | Material Requisition To Resource Division | 85/TD | 05/01/2024 | 0 | Resource Division | 10.2 | 0 | 0 | 0
3692 | PURBA MEDINIPUR | Tamluk Division | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS , SM/12404 | New | Sinking of Big dia Tube Well, Laying distribution System, Construction of Pump House, Construction of Boundary Wall, Soil investigation, R.C.C. Elevated Reservoir of capacity 200cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation), Accommodate FHTC (1656 nos) & Two years Operation & Maintenance with allied works under JJM for Dwarikapur & It's Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 128/TD | 10/04/2023 | 628 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 407.28 | 0 | 0 | 0
3693 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I , SM/14841 | Augmentation | Material Requisition To Resource Division | 3013/TD | 29/11/2023 | 0 | Resource Division | 0.43 | 0 | 0 | 0
3694 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I , SM/14841 | Augmentation | Material Requisition To Resource Division | 2081/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0 | 0
3695 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I , SM/14841 | Augmentation | Laying distribution pipe line, Accommodate FHTC ( 69 Nos) under JJM with allied work for KANPUR (Z-I) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 2255/TD | 05/09/2023 | 60 | BASANTA KUMAR MAITY | 85.65 | 60.27 | 70.37 | 60
3696 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I , SM/14841 | Augmentation | Laying distribution pipe line (Left out), Repair and Renovation Pump House, Boundary Wall , 450 Cum OHR & Accommodate Balance FHTC ( 65 Nos) under JJM with allied work for KANPUR (Zone-I) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | 2676/TD | 22/08/2024 | 45 | MAITY CONSTRUCTION | 87.84 | 0 | 0 | 0
3697 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I , SM/14841 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- I ) | 1057/TD | 18/08/2022 | 20 | ASTER CONSULTANCY | 3.6 | 2.95 | 100 | 100
3698 | PURBA MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I , SM/14841 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 0 | 34
3699 | PURBA MEDINIPUR | Midnapore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) , SM/19188 | New | Construction of 11/0.433 KV, 800 KVA Electrical Substation with allied Electrical works at Pingla Boosting at panskura under surface water based water supply scheme for Pingla, Panskura and Khargpur-II Block in Purba & Paschim Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | 1057/W/MMD | 13/03/2024 | 180 | APEX ENGINEERING & PROJECT CO | 338.92 | 0 | 0 | 0
3700 | PURBA MEDINIPUR | Midnapore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) , SM/19188 | New | Construction of 11/0.433 KV, 1600 KVA Electrical Substation with allied Electrical works at Intake point (River bank) at panskura under surface water based water supply scheme for Pingla, Panskura and Khargpur-II Block in Purba & Paschim Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | 1058/W/MMD | 13/03/2024 | 180 | THE MARKET ELECTRICAL ENGINEERING WORKS | 485.76 | 0 | 0 | 0
3701 | PURBA MEDINIPUR | Midnapore Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) , SM/19188 | New | Material Requisition To Resource Division | 2240/MD | 22/07/2024 | 0 | Resource Division | 237.7 | 0 | 0 | 0
3702 | PURBA MEDINIPUR | Midnapore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) , SM/19188 | New | Construction of 33/0.433 KV, 3000 KVA Electrical Substation with allied Electrical works at WTP at Panskura under surface water based water supply scheme for Pingla, Panskura and Khargpur-II Block in Purba & Paschim Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | 1659/W/MMD | 29/07/2024 | 180 | THE MARKET ELECTRICAL ENGINEERING WORKS | 747.99 | 0 | 0 | 0
3703 | PURBA MEDINIPUR | Midnapore Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) , SM/19188 | New | Supplying, laying of 9 nos zone Distribution System including specials, valves & pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule (dept. supply), saddle piece etc. all complete, Construction of 9 Nos. various capacities of 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials., Soil Investigation for the work of construction of OHR, Construction of Switch room cum Chlorine Room Including Chlorination &Sanitary Arrangement, Boundary Wall, Service Road for 50 M length, Improvement of Land for each site, Renovation of 4 nos. Existing OHRs. surface Drain, Campus lighting & other provisional works etc for Pingla Block on EPC turnkey basis in a single package as per detail scope of work / direction of the E-I-C including 6(six) months Trial Run and Operation& Maintenance for 5(five) years for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Pingla, Panskura Block, District Paschim & Purba Medinipur under Western Circle, PHE Dte. (Phase-I) | 801/MD | 15/03/2024 | 915 | G B CONSTRUCTION & UMWELT JV | 7243.56 | 895.75 | 12.37 | 10
3704 | PURBA MEDINIPUR | Tamluk Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) , SM/19188 | New | Surveying, Designing, Engineering, Supplying, Construction, Erectioning, Testing, Commissioning of Raw Water Intake Jetty Structure (Fixed type) with Pump House connected by RCC carriageway with the river bank, 70 MLD capacity conventional type Water Treatment Plant, Raw Water Rising Mains, Bank protection, Substation Building for Intake and WTP, Clear Water Reservoir, High Lift Pump House, Clear Water Rising Mains, 1000 Cum capacity UGR cum Booster Pumping Station at Pingla block , Chlorine room & Guard room at UGR site with necessary sanitary arrangements including plinth protection work with surface drain, Administrative Building with centralized SCADA system, Bunglow & Staff Quarter including furniture at WTP & other necessary all Civil and Electro-Mechanical works [excluding substation equipments] etc on EPC turnkey basis as per direction of the EIC including 6(six) months Trial Run and Operation & Maintenance for 5(five) years for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Pingla, Panskura Block, District Purba & Paschim Medinipur (Phase-I) | 1012/TD | 14/03/2024 | 730 | G. B. CONSTRUCTION | 28900 | 0 | 0 | 12
3705 | PURBA MEDINIPUR | Tamluk Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) , SM/19188 | New | Supplying, laying of 22 nos zone Distribution System including specials, valves & pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule (dept. supply), saddle piece etc. all complete, Construction of 25 Nos. various capacities of 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials., Soil Investigation for the work of construction of OHR, Construction of Switch room cum Chlorine Room Including Chlorination & Sanitary Arrangement, Boundary Wall, Service Road for 50 M length & Improvement of Land for each site, surface Drain, Campus lighting & other provisional works etc for Panskura Block on EPC turnkey basis in a single package as per detail scope of work / direction of the E-I-C including 6(six) months Trial Run and Operation & Maintenance for 5(five) years for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Panskura Block, District Paschim & Purba Medinipur under Western Circle, PHE Dte. (Phase-I) | 2258/TD | 16/07/2024 | 1826 | M/S ANAND SINGH | 18090.51 | 0 | 0 | 5
3706 | PURBA MEDINIPUR | Tamluk Division | KAYEMGERYA AND ADJOINING MOUJAS PWSS , SM/12167 | New | Material Requisition To Resource Division | 2963/TD | 27/02/2023 | 0 | Resource Division | 35.87 | 0 | 0 | 0
3707 | PURBA MEDINIPUR | Tamluk Division | KAYEMGERYA AND ADJOINING MOUJAS PWSS , SM/12167 | New | Pump House, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (1165 nos) under JJM with allied work of KAYEMGIRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | 530/TD | 12/05/2023 | 80 | SWARUPANANDA DAS | 240.51 | 160.38 | 66.68 | 70
3708 | PURBA MEDINIPUR | Central Drilling | KAYEMGERYA AND ADJOINING MOUJAS PWSS , SM/12167 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 230 Mtrs. Depth) by utilizing Departmental Machineries for Kayemgeria W/S Scheme (T/W-I & II), Bhagawanpur-II Block underPurbaMedinipur District, Central Drilling Division, P.H.E. Dte. | 1393/CDD | 19/09/2023 | 210 | PADMA ENGINEERING & CO. | 27.2 | 22.74 | 100 | 100
3709 | PURBA MEDINIPUR | Tamluk Division | KAYEMGERYA AND ADJOINING MOUJAS PWSS , SM/12167 | New | Material Requisition To Resource Division | 627/W | 20/02/2024 | 0 | Resource Division | 12.66 | 0 | 0 | 0
3710 | PURBA MEDINIPUR | Midnapore Mechanical | KAYEMGERYA AND ADJOINING MOUJAS PWSS , SM/12167 | New | Quotation Bill for New Service connection at T/W NO-I Of KAYEMGERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004570684/QUOT/03 DT. 22-01-2024 Application NO- 2004570684 Application type-New connection Consumer Id- 204198020 | BP-2023-24-819 | 13/03/2024 | 0 | WBSEDCL | 4.4 | 0 | 0 | 0
3711 | PURBA MEDINIPUR | Midnapore Mechanical | KAYEMGERYA AND ADJOINING MOUJAS PWSS , SM/12167 | New | Quotation Bill for New Service connection at T/W NO-II Of KAYEMGERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004558744/QUOT/03 DT. 10-01-2024 Application NO- 2004558744 Application type-New connection Consumer Id- 204188974 | BP-2023-24-818 | 13/03/2024 | 0 | WBSEDCL | 4.19 | 0 | 0 | 0
3712 | PURBA MEDINIPUR | Midnapore Mechanical | KAYEMGERYA AND ADJOINING MOUJAS PWSS , SM/12167 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAYEMGERYA and ADJOINING MOUJAS, Block Bhagawanpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2323/W/MMD | 29/12/2022 | 1077 | MAA TARA ENTERPRISE | 22.75 | 9.67 | 42.51 | 45
3713 | PURBA MEDINIPUR | Tamluk Division | KAYEMGERYA AND ADJOINING MOUJAS PWSS , SM/12167 | New | Laying distribution pipe line & Accommodate FHTC ( 325nos) under JJM with allied work of KAYEMGIRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART - C) | 3460/TD | 27/03/2023 | 633 | GIRI ENTERPRISE | 37.99 | 16.12 | 42.43 | 45
3714 | PURBA MEDINIPUR | Tamluk Division | KAYEMGERYA AND ADJOINING MOUJAS PWSS , SM/12167 | New | Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (475 nos) under JJM with allied work of KAYEMGIRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART - A) | 2440/TD | 19/09/2023 | 681 | S.S.T ENGINEERING | 231.87 | 72.32 | 31.19 | 60
3715 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Barasubarnanagar W/S Scheme , SM/06877 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Barasubarnanagar PWSS Block Contai-II in the District of Purba Medinipur. | 2107/TD | 05/11/2020 | 180 | PRANAB KUMAR DAS | 96.08 | 31.17 | 32.44 | 100
3716 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM Barasubarnanagar W/S Scheme , SM/06877 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bara Subarnagar W/S Scheme within Deshapran Dev. Block under Tamluk Division, PHE Dte. | 992/W | 27/03/2021 | 0 | PRANAB KUMAR DAS | 56.48 | 0 | 0 | 0
3717 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IX , SM/07112 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -IX Block Panskura-II in the District of Purba Medinipur. | 2657/TD | 11/01/2021 | 60 | BARH CONSTRUCTION | 54.91 | 0.22 | 100 | 100
3718 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IX , SM/07112 | Retrofitting | Retrofitting to accomodate FHTC under JJM Surface Water Based W/S Scheme under Zone - IX under Tamluk Division, PHE Dte. | 824/W | 10/03/2021 | 0 | BARH CONSTRUCTION | 54 | 0 | 0 | 0
3719 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IX , SM/07112 | Retrofitting | Retrofitting to accomodate FHTC under JJM Surface Water Based W/S Scheme under Zone - IX under Tamluk Division, PHE Dte. | 1122/W | 30/03/2021 | 0 | BARH CONSTRUCTION | 0.69 | 0 | 0 | 0
3720 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VI , SM/07115 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -VI(Balance Work) Block Panskura-II in the District of Purba Medinipur. | 2633/TD | 05/01/2021 | 60 | JAGANNATH MAKAR | 96.81 | 193.59 | 199.96 | 100
3721 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VI , SM/07115 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-II within Panskura - II Block under Tamluk Division, PHE Dte. | 158/W | 30/07/2021 | 0 | MAA ANANDAMAYEE | 0.34 | 0 | 0 | 0
3722 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme , SM/06893 | Retrofitting | Re-laying of D.I./G.I./UPVC pipe line under Purba Bakulda W/S Scheme within Panskura Block damaged due to upgradation of moorum road under Tamluk Division, PHE Dte. | 100/W | 05/07/2021 | 0 | BIDHAN MONDAL | 12.56 | 0 | 0 | 0
3723 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme , SM/06893 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Purba Bakulda W/S Scheme within Panskura - I Dev. Block under Tamluk Division, PHE Dte. | 70/W | 24/06/2021 | 0 | BIDHAN MONDAL | 20.84 | 0 | 0 | 0
3724 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme , SM/06893 | Retrofitting | Charges of entry of Household data in J.J.M website alongwith Household Addhar Details entry in J.J.M. website under Tamluk Division, PHE Dte. | 816/W | 25/02/2021 | 0 | MISHRA ENTERPRISE | 4.85 | 0 | 0 | 0
3725 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme , SM/06893 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Purba Bakulda W/S Scheme within Panskura - I Dev. Block under Tamluk Division, PHE Dte. | 724/W | 18/02/2021 | 0 | BIDHAN MONDAL | 33.98 | 0 | 0 | 0
3726 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme , SM/06893 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Purba Bakulda PWSS Block Panskura-I in the District of Purba Medinipur. | 2110/TD | 05/11/2020 | 180 | BIDHAN MONDAL | 72.9 | 0 | 0 | 100
3727 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Srirampur PWSS under Tamluk Block. , SM/07653 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Srirampur PWSS (Part-I) Block -Tamluk in the District of Purba Medinipur. | 2835/TD | 05/02/2021 | 45 | ARABINDA GHOSH | 113.61 | 0 | 0 | 100
3728 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Srirampur PWSS under Tamluk Block. , SM/07653 | Retrofitting | Retrofitting to accomodate FHTC under JJM Srirampur W/S Scheme within Tamluk Dev. Block under Tamluk Division, PHE Dte. | 1079/W | 30/03/2021 | 0 | ARABINDA GHOSH | 100.54 | 0 | 0 | 0
3729 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Srirampur PWSS under Tamluk Block. , SM/07653 | Retrofitting | Retrofitting to accomodate FHTC under JJM Srirampur W/S Scheme under Tamluk Division, PHE Dte. |  | 12/03/2021 | 0 | ARABINDA GHOSH | 100.73 | 0 | 0 | 0
3730 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Srirampur PWSS under Tamluk Block. , SM/07653 | Retrofitting | Retrofitting to accomodate FHTC under JJM Srirampur W/S Scheme within Tamluk Dev. Block under Tamluk Division, PHE Dte. | BP-2021-22-117 | 05/10/2021 | 0 | ARABINDA GHOSH | 13.82 | 0 | 0 | 0
3731 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Majna Water Supply Scheme under Tamluk Division, PHE Dte. | 1170/TD | 01/12/2021 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM | 10.34 | 4.04 | 100 | 100
3732 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Supply & Delivery of different dia Sluice Valve for Augmentation of Majna Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. | 2216/TD | 22/03/2022 | 15 | BIBEKANANDA DAS | 4.06 | 4.06 | 100 | 100
3733 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Majna W/S Scheme (T/W-III) , Contai-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 855/CDD | 10/07/2023 | 30 | MENAKA ENTERPRISE | 14.61 | 0 | 0 | 0
3734 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) for OHR site at Majna BPHC Premises for Majna W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (for East side & South Side) | 373/TD | 17/05/2022 | 28 | BIBEKANANDA DAS | 3.85 | 3.5 | 100 | 100
3735 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at OHR site( Mouza- Nayabasan ,J.L. No-294, Plot No- 319), for Majna W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (for West side & North Side) | 344/TD | 13/05/2022 | 28 | PARTHA CONSTRUCTION | 4.84 | 3.82 | 100 | 100
3736 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Material Requisition To Resource Division | 1264/TD | 13/12/2021 | 0 | Resource Division | 13.16 | 0 | 0 | 0
3737 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Material Requisition To Resource Division | 1902/TD | 23/02/2022 | 0 | Resource Division | 13.73 | 0 | 0 | 0
3738 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Material Requisition To Resource Division | 2217/TD | 24/03/2022 | 0 | Resource Division | 20.19 | 0 | 0 | 0
3739 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Material Requisition To Resource Division | 82/TD | 08/04/2022 | 0 | Resource Division | 20.19 | 0 | 0 | 0
3740 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Electric Quotation for MAJNA Water Supply Scheme T/W-III, (Ref. ID-204068438) | BP-2023-24-235 | 08/09/2023 | 0 | WBSEDCL | 3.52 | 0 | 0 | 0
3741 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Name of Work: i) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Majna W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Majna PWSS within Contai -I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iii) Laying rising main and other allied works Augmentation of Majna W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3217/TD | 14/03/2023 | 40 | SUBRATA KUMAR BERA | 19.54 | 0 | 0 | 0
3742 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Supply Scheme for Majna, Block Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 813/W/MMD | 24/03/2023 | 180 | MEGA SOLAR ENERGY | 11.34 | 4.67 | 41.19 | 58
3743 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Augmentation of ground water based Majna Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of RCC Over Head Reservoir of Capacity 250 cum. And staging height 20.00 mtr. With allied work including Sub Soil Investigation within Contai-I Dev. Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1845/TD | 15/02/2022 | 180 | DAS ENTERPRISE | 324.35 | 303.34 | 100 | 100
3744 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Laying of Distribution pipe line by UPVC pipes with allied works due to Construction of drain by Local Panchayet of Majna and its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 1714/CSD | 31/08/2023 | 30 | SUBRATA KUMAR BERA | 2.66 | 2.65 | 100 | 100
3745 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna , SM/09335 | Augmentation | Repair and Renovation of Pump House and others allied works for OHR & 2nd Tube well site at Majna Water Supply Scheme in Contai - Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 3398/TD | 28/10/2024 | 30 | SUBRATA KUMAR BERA | 1.92 | 0 | 0 | 100
3746 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dariapur W/S Scheme (PHASE-II) , SM/08230 | Retrofitting | Retrofitting to accomodate FHTC 150 Nos. under Dariapur PWSS within Contai-II Block under Tamluk Division, PHE Dte. (Phase-II) | BP-2021-22-98 | 05/10/2021 | 0 | SK. NUR ISLAM | 10.63 | 0 | 0 | 0
3747 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dariapur W/S Scheme (PHASE-II) , SM/08230 | Retrofitting | Retrofitting to accomodate FHTC 150 Nos. under Dariapur PWSS within Contai-II Block under Tamluk Division, PHE Dte. (Phase-II) |  | 30/09/2021 | 0 | SK. NUR ISLAM | 10.63 | 0 | 0 | 0
3748 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dariapur W/S Scheme (PHASE-II) , SM/08230 | Retrofitting | Retrofitting to accommodate FHTC [ 150 nos] under JJM in Dariapur PWSS [Pratappur(507,part),Haripur(508,part),Ramchak Gopalchak(509,part),Purba Bamunia(511,part), Dariapur(512,part),Daulatpur(513,part),Kazichak(514,part),Chhota Subarnanagar(515,part),Nankar Gopinathpur(516,part),Durgapur Part-IV(608,part)] within Contai-II Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) | 2921/TD | 22/02/2021 | 20 | SK. NUR ISLAM | 10.94 | 0 | 0 | 100
3749 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla W/S Scheme (Phase - II) , SM/08231 | Retrofitting | Laying distribution system of Chirulia-Chatla & its adjoining moujas Water Supply Scheme within Egra-I Dev. Block under Digha sub-division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | 1453/TD | 31/12/2021 | 30 | AJIT KUMAR SOM | 29.22 | 29.22 | 100 | 100
3750 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla W/S Scheme (Phase - II) , SM/08231 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chirulia-Chatla PWSS Block- Egra-I in the District of Purba Medinipur.(Phase-II). | 239/TD | 23/06/2021 | 60 | FIROZ KHAN | 172.05 | 214.65 | 146.3 | 100
3751 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN KANAKPUR PWSS UNDER POTASHPUR - I BLOCK PHASE II , SM/08747 | Retrofitting | Retrofitting to accomodate FHTC (250 nos.) under JJM in Kanakpur PWSS under Potashpur -I Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PHASE-II) | 684/TD | 10/09/2021 | 20 | SRIMANTA KUMAR MAITY | 22.38 | 21.15 | 100 | 100
3752 | PURBA MEDINIPUR | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN KANAKPUR PWSS UNDER POTASHPUR - I BLOCK PHASE II , SM/08747 | Retrofitting | Repair and Renovation of Pump House with Sanitary and water supply arrangement and others allied works for Head works & 2nd Tube well site at Kanakpur Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 3319/TD | 22/10/2024 | 30 | THE GODFATHER TRADING COMPANY | 1.45 | 0 | 0 | 0
3753 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in DONA Zone-II Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. , SM/08756 | Retrofitting | Retrofitting to accomodate FHTC (899 nos.) under JJM in Dona Zone-II PWSS (Balance Work) Block - Moyna under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.(Phase- II) | 690/TD | 10/09/2021 | 30 | TARUN KOLEY | 41.48 | 0 | 0 | 100
3754 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in DONA Zone-II Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. , SM/08756 | Retrofitting | Retrofitting to accomodate FHTC (899 Nos.) under JJM in Dona Zone - II PWSS (Balance Work) Block-Moyna under Tamluk Division, PHE Dte. (Phase-II) | BP-2021-22-106 | 05/10/2021 | 0 | TARUN KOLEY | 41.31 | 0 | 0 | 0
3755 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Amtalia W/S Scheme under Contai-II Deshopran Block(PHASE-II) , SM/08222 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Amtalia PWSS Block- Contai-II in the District of Purba Medinipur.(Phase-II) | 85/TD | 11/05/2021 | 30 | ARABINDA GHOSH | 90.23 | 65.29 | 72.36 | 80
3756 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Gholpukuria PWSS (Zone I) (Phase-III) Balance Part under Nandigram - II Dev. Block. , SM/09049 | Retrofitting | Retrofitting to accommodate FHTC (505 Nos) (Mouza- Rankinipur, J.L. No.-135) & Relaying of damaged pipeline in Hanubhunia Mouza, J.L. No.-133, under JJM in Gholepukuria (Zone-I) PWSS (Phase-III) balance part, Block- Nandigram-II in the District of Purba Medinipur. (Part-B) | 1006/TD | 02/11/2021 | 30 | ZENITH CONSTRUCTION | 28.92 | 28.84 | 100 | 100
3757 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Gholpukuria PWSS (Zone I) (Phase-III) Balance Part under Nandigram - II Dev. Block. , SM/09049 | Retrofitting | Retrofitting to accommodate FHTC (505 Nos) (Mouza- Rankinipur, J.L. No.-135) & Relaying of damaged pipeline within Nodal point 160-161, 196-197, 196-199, 161-172 & 172-174 in Hanubhunia Mouza, J.L. No.-133, under JJM in Gholepukuria (Zone-I) PWSS (Phase-III) balance part, Block- Nandigram-II in the District of Purba Medinipur. (Part-A) | 1005/TD | 02/11/2021 | 30 | PULAK KUMAR SAMANTA | 11.81 | 11.81 | 100 | 100
3758 | PURBA MEDINIPUR | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Kudi PWSS under Egra I Block (Phase-II) , SM/09053 | Retrofitting | Retrofitting to accomodate FHTC under JJM in KUDI PWSS Block - Egra-I in the District of Purba Medinipur | 1022/TD | 02/11/2021 | 20 | KESHOB ENTERPRISE | 12.26 | 12.22 | 100 | 100
3759 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-H) | 1862/TD | 17/02/2022 | 20 | MAHAPRABHU ENTERPRISE | 4.83 | 4.63 | 95.8 | 100
3760 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dwariberia Water Supply Scheme under Tamluk Division, PHE Dte. | 1606/TD | 14/01/2022 | 20 | RADIANT | 3.58 | 3.56 | 100 | 100
3761 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Dwariberia Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 133/TD | 19/04/2022 | 21 | SIMPLEX DRILLING COMPANY | 19.03 | 19.03 | 100 | 100
3762 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Work order for Make approach road to access Rig Machine for Boring of Tube well at Head work site of Dwariberia Water Supply Scheme under Haldia Sub-Division of Tamluk Division, PHE Dte. | 572/HSD | 17/08/2022 | 7 | TAPAN BERA | 1.36 | 1.36 | 100 | 100
3763 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (1003 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-A) | 1851/TD | 16/02/2022 | 40 | SUDIPTA ROY | 75.32 | 73.42 | 97.48 | 100
3764 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (737 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-C) | 1853/TD | 16/02/2022 | 40 | JAI BHARAT COMMERCIAL CORPORATION | 74.58 | 74.45 | 99.83 | 100
3765 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-J) | 1864/TD | 17/02/2022 | 20 | TARUN KHATUA | 4.85 | 4.84 | 99.86 | 100
3766 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (101 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-D) | 2000/TD | 08/03/2022 | 20 | A. K. SIKDAR | 35.52 | 35.15 | 98.96 | 100
3767 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-F) | 1860/TD | 17/02/2022 | 20 | SAYAN MAITY | 4.85 | 4.82 | 100 | 100
3768 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (22 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-E) | 1854/TD | 16/02/2022 | 20 | BUNBA CONSTRUCTION | 10.38 | 10.26 | 100 | 100
3769 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (22 nos) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. " (Part-M) | 1855/TD | 16/02/2022 | 20 | TAPAN BERA | 10.79 | 10.79 | 100 | 100
3770 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-I) | 1863/TD | 17/02/2022 | 20 | MODERN CONSTRUCTION | 4.85 | 4.81 | 100 | 100
3771 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-G) | 1861/TD | 17/02/2022 | 20 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 4.8 | 4.8 | 100 | 100
3772 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (927 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-B) | 1852/TD | 16/02/2022 | 40 | PALCON | 74.59 | 69.74 | 100 | 100
3773 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Work Order for Laying of UPVC pipe line at Dwariberia Water supply Scheme (Node point 182-182A) within Haldia Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. (Part-I) | 571/HSD | 17/08/2022 | 15 | TAPAN BERA | 1.57 | 1.57 | 100 | 100
3774 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Repairing & renovation of Switch Room cum Chlorine Room at Head work & 2nd tube well site respectively of Dwariberia Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1045/TD | 16/08/2022 | 45 | TARUN KHATUA | 4.09 | 3.82 | 100 | 100
3775 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well No I under Dwariberia water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2121/W/MMD | 28/11/2022 | 120 | PRANAB KUMAR DAS | 11.12 | 9.38 | 100 | 100
3776 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Material Requisition To Resource Division | 1874/TD | 18/02/2022 | 0 | Resource Division | 16 | 0 | 0 | 0
3777 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Material Requisition To Resource Division | 2069/TD | 16/03/2022 | 0 | Resource Division | 16.85 | 0 | 0 | 0
3778 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Laying Distribution System of Leftout portion, Providing Functional Household Tap Connection (456 FHTC) of Dwariberia Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1904/TD | 07/06/2024 | 367 | SK. NUR ISLAM | 56.28 | 5.91 | 10.5 | 50
3779 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09444 | Augmentation | Construction of R.C.C. Elevated Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied works under Dwariberia & its adjoining moujas Water Supply Scheme within Haldia Block including supply of all labour & materials under Haldia Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 1887/TD | 24/11/2022 | 828 | MAA ANANDAMAYEE | 131.54 | 96.5 | 92.08 | 98
3780 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. , SM/09275 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Muradpur Water Supply Scheme under Tamluk Division, PHE Dte. | 1196/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 6.38 | 6.38 | 100 | 100
3781 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. , SM/09275 | Augmentation | Rejuvenation & Retrofitting of ground water based Muradpur PWSS & its adjoining moujas within Chandipur Dev. Block under Tamluk sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. (Part-A) | 2214/TD | 22/03/2022 | 90 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 237.6 | 236 | 99.33 | 100
3782 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. , SM/09275 | Augmentation | Rejuvenation & Retrofitting of ground water based Muradpur PWSS & its adjoining moujas within Chandipur Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. (Part-B) | 59/TD | 05/04/2022 | 60 | UCON | 164.31 | 161.84 | 100 | 100
3783 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. , SM/09275 | Augmentation | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS & its adjoining moujas with in Chandipur Dev. Block under Tamluk Sub-Division , PHE Dte. Dist. Purba Medinipur (Part-A) | 1597/TD | 18/10/2022 | 30 | G. S. CONSTRUCTION | 25.21 | 24.82 | 100 | 100
3784 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. , SM/09275 | Augmentation | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS & its adjoining moujas with in Chandipur Dev. Block under Tamluk Sub-Division , PHE Dte. Dist. Purba Medinipur (Part-B) | 1598/TD | 18/10/2022 | 25 | TARUN KHATUA | 10.28 | 10.16 | 100 | 100
3785 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. , SM/09275 | Augmentation | Material Requisition To Resource Division | 2346/TD | 31/03/2022 | 0 | Resource Division | 10.33 | 0 | 0 | 0
3786 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. , SM/09275 | Augmentation | Material Requisition To Resource Division | 1096/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
3787 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti , SM/10126 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chandiveti Water Supply Scheme under Tamluk Division, PHE Dte. | 1608/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.99 | 4.29 | 100 | 100
3788 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti , SM/10126 | Augmentation | Supply & Delivery of different dia Sluice Valve for Augmentation of Sankarpur,Basudevberia,Chandivety & Bhajachauli Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Phase-II).(Supply at Mukutshila Store). | 775/TD | 08/07/2022 | 15 | SRIMANTA KUMAR MAITY | 3.49 | 3.49 | 100 | 100
3789 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti , SM/10126 | Augmentation | Supply & Delivery of different dia Sluice Valve for Augmentation of Chandibhetti Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | 627/TD | 23/06/2022 | 15 | SRIMANTA KUMAR MAITY | 4.59 | 4.59 | 100 | 100
3790 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti , SM/10126 | Augmentation | Laying of Distribution pipeline to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Chandibhetti Water Supply Scheme within Deshpran Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte., Purba medinipur. | 593/TD | 17/06/2022 | 60 | RAJ KUMAR SINGHA | 585.56 | 564.09 | 96.33 | 95
3791 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti , SM/10126 | Augmentation | Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Additional 3rd Tubewell of Augmentation of Chandibhetti Water Supply Scheme (Mouza - Banamaliberya, JL No. - 458, Plot No. - 8) within Contai-II (Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 978/TD | 03/08/2022 | 15 | PRANTIK DRILLING AGENCY | 12.15 | 11.38 | 100 | 100
3792 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti , SM/10126 | Augmentation | Material Requisition To Resource Division | 405/TD | 25/05/2022 | 0 | Resource Division | 42.06 | 0 | 0 | 0
3793 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti , SM/10126 | Augmentation | Material Requisition To Resource Division | 1268/TD | 12/09/2022 | 0 | Resource Division | 23.08 | 0 | 0 | 0
3794 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti , SM/10126 | Augmentation | Electric quotation for Chandiveti PWSS Tube Well- III in connection Mukundapur CCC (2004186280) | BP-2022-23-131 | 14/03/2023 | 0 | WBSEDCL | 0.59 | 0 | 0 | 0
3795 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti , SM/10126 | Augmentation | Construction of (Boundary Wall(as per Departmental Design & Drawing) at 3rd TW Site for Augmentation of Chandibhetty PWSS in Deshapran Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Length 65.00 mtr.) For Low Land. | 1497/TD | 17/07/2023 | 60 | SUBHENDU HAZRA | 10.3 | 8.31 | 100 | 100
3796 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti , SM/10126 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Chandibhetti W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | 2970/TD | 28/11/2023 | 60 | BISWA NIRMAN ENTERPRISE. | 3.73 | 3.72 | 100 | 100
3797 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti , SM/10126 | Augmentation | Laying of Rising Main including interconnection of Chandibhetty PWSS in Deshapran Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte. | 928/TD | 01/06/2023 | 30 | SUDIP MANNA | 6.09 | 3.05 | 50.04 | 100
3798 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti , SM/10126 | Augmentation | Repairing of OHR, Pump House no 1, Pump House No. 2, Head Work site Boundary Wall and Boundary Wall of 2nd Tubewell Site under JJM with allied work of Chandivetty PWSS within Deshapran Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 3329/TD | 22/10/2024 | 40 | SUBHENDU HAZRA | 18.38 | 0 | 0 | 0
3799 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Junbani Water Supply Scheme under Tamluk Division, PHE Dte. | 1547/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.58 | 4.76 | 100 | 100
3800 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional (3rd) Tubewell of Augmentation of Junbani Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 979/TD | 03/08/2022 | 15 | PRANTIK DRILLING AGENCY | 12.15 | 11.12 | 100 | 100
3801 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (4th) Tubewell of Augmentation of Junbani Water Supply Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 473/TD | 10/05/2023 | 60 | SUBHENDU HAZRA | 3.68 | 3.32 | 100 | 100
3802 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Supply & Delivery of different dia Sluice Valve for Junbani Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) (Supply at Mukutshila Store) | 493/CSD | 02/08/2022 | 15 | GIRI CONSTRUCTION | 2.47 | 2.47 | 100 | 100
3803 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Material Requisition To Resource Division | 102/TD | 11/04/2022 | 0 | Resource Division | 51.5 | 0 | 0 | 0
3804 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Material Requisition To Resource Division | 1270/TD | 12/09/2022 | 0 | Resource Division | 32.32 | 0 | 0 | 0
3805 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Electric quotation for Junboni PWSS Tube Well-IV WS Scheme (Ref. ID-203911303) | BP-2022-23-137 | 20/03/2023 | 0 | WBSEDCL | 0.56 | 0 | 0 | 0
3806 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Boundary wall and Rising Main and under JJM with allied work for Jubani PWSS within Contai-I Block including supply of all labour & materials under Contai Sub-Division of Tamluk Division, PHE Dte. | 3224/TD | 13/12/2023 | 40 | MAHAPRABHU ENTERPRISE | 35.37 | 5.22 | 14.76 | 16
3807 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Junbani Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 693/TD | 27/06/2022 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 736.14 | 725.08 | 100 | 98
3808 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Additional Quotation Bill for T/W NO-IV Of JUNBONI W/S Scheme under MMD, PHE, Dte. Block- Contai-I, PICHABANI C.C.C. Ref. Memo No- 2004620649/QUOT/03 DT. 27-02-2024 Application NO- 2004620649 Reference Id- 204229267 | BP-2023-24-798 | 07/03/2024 | 0 | WBSEDCL | 6.88 | 0 | 0 | 0
3809 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani, Block ¿ Contai I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1482/W/MMD | 21/06/2023 | 467 | MAA KALI ENTERPRISE | 11.4 | 9.96 | 87.38 | 25
3810 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Continuation W/O for Hiring of one no. Diesel Motor cabs (Luxury Taxi Standered non air conditioned) Bharat Stage -IV , on daily rate basis (including Govt. Holidays as and when required ) Having contract carraige permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. For the Period from 01/07/2024 to 30/06/2025. (12 Months), Vehicle no.-WB-31/6974 | 1788/CSD | 28/06/2024 | 365 | SABITA PRADHAN | 1.49 | 0 | 0 | 0
3811 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Repairing of R.C.C. Elevated Reservoir of capacity with allied works of Junbani PWSS within Contai - I Block including supply of all labour & materials under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 3614/TD | 27/11/2024 | 40 | CHARUBALA ENTERPRISE | 11.14 | 0 | 0 | 97
3812 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani , SM/10127 | Augmentation | Left Out pipeline, Piling and Road Restoration work for Augmentation of Junbani Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur | 850/TD | 19/03/2025 | 30 | BASANTA KUMAR MAITY | 41.02 | 0 | 0 | 0
3813 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Retrofitting to accommodate of 1410 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-B) | 1078/TD | 23/08/2022 | 45 | SWADHIN KUMAR CHAKRABORTY | 241.76 | 159.66 | 100 | 95
3814 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Payment to WBSEDCL for Quotation Money of Pump House No. ¿ III of Khejuri Zone-I PWSS under Tamluk Division, PHE Dte. | BP-2023-24-583 | 22/11/2023 | 0 | WBSEDCL | 2.88 | 0 | 0 | 0
3815 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) under JJM Program under MMD PHE Dte. | 861/W/MMD | 27/03/2023 | 180 | DIAMOND ELECTRICAL WORKS | 13.43 | 12.63 | 100 | 95
3816 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Retrofitting to accommodate of 68 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-S) | 1450/TD | 13/07/2023 | 30 | DEBABRATA DAS | 9.42 | 6.64 | 70.45 | 70
3817 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Retrofitting to accommodate of 68 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-O) | 247/TD | 11/01/2024 | 20 | GITA ENTERPRISE | 9.75 | 6.62 | 67.94 | 90
3818 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 1st Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 2nd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1225/TD | 07/09/2022 | 40 | M/S SYCHROTECH INDUSTRY | 71.86 | 15.76 | 47.47 | 100
3819 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Repairing of existing Store Room with Guard Room with sanitary & water supply arrangements including Plinth Protection of OHR Site under Augmentation of Khejuri Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. | 2770/TD | 09/02/2023 | 30 | GIRI CONSTRUCTION | 9.94 | 9.82 | 100 | 100
3820 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Laying of distribution pipe line and Rising main, construction of boundary wall and construction of Switch Room with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 1838/TD | 08/08/2023 | 40 | SK. SARFARAJ | 16.93 | 13.3 | 100 | 100
3821 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Retrofitting to accommodate of 200 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-L) | 246/TD | 11/01/2024 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.96 | 42.14 | 100 | 100
3822 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Laying of Distribution pipe line by HDPE pipes with allied works of Left out portion of Barka saria Mouja under Khejuri Zone -I PWSS in Khajuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 67/TD | 05/01/2024 | 7 | AMITAVA MONDAL | 0.96 | 0.95 | 100 | 100
3823 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Laying of Distribution pipe line by HDPE pipes with allied works of Left out portion of Khejuri Mouja under Khejuri Zone -I PWSS in Khajuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 68/TD | 05/01/2024 | 7 | TECHNO ENTERPRISE. | 0.96 | 0.95 | 100 | 100
3824 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Laying of distribution pipe line to accommodate FHTC (1557 Nos)with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (Part-A) | 2551/TD | 24/01/2023 | 920 | TARUN KOLEY | 289.69 | 203.04 | 70.09 | 70
3825 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Khejuri Zone-I PWSS within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | 3769/TD | 10/12/2024 | 40 | GIRI CONSTRUCTION | 3.96 | 0 | 0 | 0
3826 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) , SM/10592 | Augmentation | Retrofitting to accommodate of 66 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-Q) | 796/TD | 12/07/2022 | 969 | SUSANTA KUMAR KAR | 9.24 | 0 | 0 | 99
3827 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Potashpur-II and Ramnagar-I Development Block Within Purba Medinipur District. , SM/10620 | New | Material Requisition To Resource Division | 2898/TD | 21/11/2023 | 0 | Resource Division | 4.92 | 0 | 0 | 0
3828 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Potashpur-II and Ramnagar-I Development Block Within Purba Medinipur District. , SM/10620 | New | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0 | 0
3829 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Potashpur-II and Ramnagar-I Development Block Within Purba Medinipur District. , SM/10620 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 539.28 | 71.53 | 70
3830 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Potashpur-II and Ramnagar-I Development Block Within Purba Medinipur District. , SM/10620 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 61.6 | 26.14 | 48
3831 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10681 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Simulia Water Supply Scheme under Tamluk Division, PHE Dte. | 1169/TD | 01/12/2021 | 7 | RADIANT | 9.35 | 9.24 | 100 | 100
3832 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10681 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN SIMULIA W/S SCH (TW-III), TAMLUK BLOCK, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | 416/CMSD-I | 10/08/2022 | 15 | PADMA ENGINEERING & CO. | 4.99 | 4.99 | 100 | 0
3833 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10681 | Augmentation | RESISTIVITY SURVEY AND OTHER WORKS OF SIMULIA W/S SCH (TW-III), TAMLUK BLOCK, PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 1539/CDD | 08/12/2022 | 30 | PADMA ENGINEERING & CO. | 12.67 | 10.25 | 80.89 | 0
3834 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10681 | Augmentation | Material Requisition To Resource Division | 408/TD | 25/05/2022 | 0 | Resource Division | 42.01 | 0 | 0 | 0
3835 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10681 | Augmentation | Material Requisition To Resource Division | 1262/TD | 12/09/2022 | 0 | Resource Division | 7.78 | 0 | 0 | 0
3836 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10681 | Augmentation | Quotation money payment to WBSEDCL for Simulia Water Supply Scheme of Tube Well No. - III | BP-2023-24-283 | 17/08/2023 | 0 | WBSEDCL | 4.34 | 0 | 0 | 0
3837 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10681 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. under JJM Program under MMD PHE Dte. | 864/W/MMD | 27/03/2023 | 180 | SWAPAN ENTERPRISE | 13.66 | 12.85 | 94.04 | 35
3838 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10681 | Augmentation | Continuation work order for Hiring of one no Diesel Motor Cabs (Luxury Taxi) (Standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division, PHE Dte under Tamluk Division for the period from 01.10.2023 to 31.12.2023 | 1341/TSD | 27/09/2023 | 50 | DEBNATH MAITY | 0.24 | 1.18 | 100 | 100
3839 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10681 | Augmentation | Material Requisition To Resource Division | 1118/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
3840 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10681 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 550 cum and staging height 20.00 mtr as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Simulia Water Supply Scheme within Tamluk Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1971/TD | 01/12/2022 | 1096 | SANKHA ENTERPRISE | 707.13 | 463.32 | 65.52 | 65
3841 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10681 | Augmentation | Laying of proposed Rising main line and supply & delivery of DI Specials M.S Structure for Canal crossing, Road crossing and Drum Sheet Piling at Simulia Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2871/TD | 17/11/2023 | 25 | SANKHA ENTERPRISE | 58.27 | 0 | 0 | 0
3842 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/10681 | Augmentation | Repairing & renovation of Boundary wall , Pump Hose at Head Work site of Simulia Water Supply Scheme underTamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Length 402 Mtr.) | 737/TD | 07/03/2025 | 45 | M J A ENTERPRISE | 44.35 | 0 | 0 | 0
3843 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. , SM/10393 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1224/W/MMD | 25/04/2023 | 180 | TAPAN KUMAR SARKAR | 24.79 | 0 | 0 | 0
3844 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. , SM/10393 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Monoharpur Water Supply Scheme under Tamluk Division, PHE Dte. | 1512/TD | 06/01/2022 | 20 | RADIANT | 3.55 | 3.45 | 100 | 100
3845 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. , SM/10393 | Augmentation | Material Requisition To Resource Division | 412/TD | 25/05/2022 | 0 | Resource Division | 47.71 | 0 | 0 | 0
3846 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. , SM/10393 | Augmentation | Material Requisition To Resource Division | 1266/TD | 12/09/2022 | 0 | Resource Division | 16.78 | 0 | 0 | 0
3847 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. , SM/10393 | Augmentation | Laying of proposed Rising main line with inter connection at Monaharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 395/TD | 30/01/2024 | 274 | G. S. CONSTRUCTION | 9.36 | 5 | 100 | 50
3848 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. , SM/10393 | Augmentation | Surging of Deep Tube well at different W/S Scheme under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-III) | 739/HSD, | 19/02/2024 | 15 | BUNBA CONSTRUCTION | 2.3 | 2.3 | 100 | 100
3849 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. , SM/10393 | Augmentation | Construction of Boundary Wall, Protection work ,Earth Filling, Laying of left-out & Parallal Distribution line at Monaharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 966/TD | 12/03/2024 | 573 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 112.45 | 85.97 | 76.46 | 10
3850 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. , SM/10393 | Augmentation | Continuation Work Order for Operation and Maintenance of distribution system including rising main, FHTC, OHR of Manoharpur & its adjoining mouzas Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. {For 12 Months} [i.e. 01/09/2024 to 31/08/2025] | 2786/TD | 30/08/2024 | 365 | G. S. CONSTRUCTION | 4.53 | 0 | 0 | 100
3851 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. , SM/10393 | Augmentation | Laying of distribution pipe line to accommodate FHTC(2729 Nos) with new construction of R.C.C. Elevated Reservoir of capacity 350 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Ground Water Based Manoharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 2861/TD | 17/02/2023 | 865 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 484.9 | 410.36 | 84.63 | 85
3852 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia , SM/12491 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Narandiha Water Supply Scheme under Tamluk Division, PHE Dte. | 1618/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.06 | 3.05 | 100 | 100
3853 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia , SM/12491 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 220 mtrs. Depth) by utilising Departmental machineries for Narandiha W/S Scheme (TW-III), Ramnagar-II block under Purba Midnapore District, CDD PHE Dte. | 14/CDD | 04/04/2023 | 30 | MENAKA ENTERPRISE | 17.39 | 13.88 | 100 | 100
3854 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia , SM/12491 | Augmentation | Material Requisition To Resource Division | 2619/TD | 02/02/2023 | 0 | Resource Division | 41.76 | 0 | 0 | 0
3855 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia , SM/12491 | Augmentation | Material Requisition To Resource Division | 2638/TD | 02/02/2023 | 0 | Resource Division | 19.64 | 0 | 0 | 0
3856 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia , SM/12491 | Augmentation | Electric Quotation for NARANDIHA Water Supply Scheme T/W-III, (Ref. ID-204068440) | BP-2023-24-236 | 08/09/2023 | 0 | WBSEDCL | 3.76 | 0 | 0 | 0
3857 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia , SM/12491 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 400cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of NARANDIA PWSS Scheme In Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(Part-A) | 2182/TD | 20/12/2022 | 180 | MAITY CONSTRUCTION | 299.31 | 120.84 | 40.37 | 42
3858 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia , SM/12491 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of Pump House for Augmentation of NARANDIHA PWSS Scheme In Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(Part-B) | 2181/TD | 20/12/2022 | 60 | MAITY CONSTRUCTION | 112.72 | 88.63 | 78.63 | 80
3859 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia , SM/12491 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 220 Mtrs. Depth) by utilising Departmental Machineries for Narandiha W/S Scheme (T/W-I) , Ramangar-II Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 13/CDD | 04/04/2023 | 574 | MENAKA ENTERPRISE | 17.39 | 16.28 | 100 | 100
3860 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia , SM/12491 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia, Block Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 817/W/MMD | 24/03/2023 | 180 | S.K.ENTERPRISE | 35.55 | 22.74 | 63.98 | 40
3861 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia , SM/12491 | Augmentation | Renovation & Repairing of existing pump house - II at 2nd tube well site of Narandiha W/S Scheme within Ramnagar-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 1315/DSD | 13/01/2025 | 7 | PURNENDU MAITY | 0.94 | 0 | 0 | 0
3862 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia , SM/12491 | Augmentation | Soil Investigation work in Connection of Construction of R.C.C. Over Head Reservoir (Capacity - 400 Cum) due to change of land with Laying of Balance Distribution Pipe Line for Provided balance FHTC and other allied works of Narandiha Piped Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division,PHE Dte., Purba Medinipur. | 851/TD | 19/03/2025 | 30 | MAITY CONSTRUCTION | 48.33 | 0 | 0 | 0
3863 | PURBA MEDINIPUR | Tamluk Division | SHWNIA AND ADJOINING MOUJAS PWSS , SM/12494 | New | Material Requisition To Resource Division | 2413/TD | 16/01/2023 | 0 | Resource Division | 19.96 | 0 | 0 | 0
3864 | PURBA MEDINIPUR | Midnapore Mechanical | SHWNIA AND ADJOINING MOUJAS PWSS , SM/12494 | New | Quotation For New Service Connections at Tube Well-I of Shwina W/S scheme under MMD PHE Dte. Chorepalia CCC Block- Egra-I Application No.-2004746256 Consumer ID.-204316922 Application Date.-29/05/2024 | BP-2024-25-253 | 06/06/2024 | 0 | WBSEDCL | 3.74 | 0 | 0 | 0
3865 | PURBA MEDINIPUR | Midnapore Mechanical | SHWNIA AND ADJOINING MOUJAS PWSS , SM/12494 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SHWNIA and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 502/W/MMD | 20/03/2023 | 864 | SRI KRISHNA NIRMAN | 21.57 | 0 | 0 | 53
3866 | PURBA MEDINIPUR | Tamluk Division | SHWNIA AND ADJOINING MOUJAS PWSS , SM/12494 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 145.8 | 48 | 51
3867 | PURBA MEDINIPUR | Tamluk Division | CHAUDDHA CHULI AND IT'S ADJOINING MOUJAS PWSS , SM/12495 | New | Material Requisition To Resource Division | 2982/TD | 27/02/2023 | 0 | Resource Division | 32.13 | 0 | 0 | 0
3868 | PURBA MEDINIPUR | Midnapore Mechanical | CHAUDDHA CHULI AND IT'S ADJOINING MOUJAS PWSS , SM/12495 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHAUDDHA CHULI and ADJOINING MOUJAS, Block - Khejuri II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 513/W/MMD | 20/03/2023 | 180 | GLACIER ENGINEERING CO. | 22.79 | 17.58 | 77.15 | 50
3869 | PURBA MEDINIPUR | Tamluk Division | CHAUDDHA CHULI AND IT'S ADJOINING MOUJAS PWSS , SM/12495 | New | Block Level Orientation Programme involving PRI functionaries on Jal Jeevan Mission at different blocks within Contai Sub- Division under Tamluk division,PHE Dte. Block Name- Khejuri-I, Khejuri-II, Patashpur-I & Patashpur-II ) | 563/CSD | 14/03/2024 | 10 | SAURAV HAZRA | 0.54 | 0.27 | 100 | 100
3870 | PURBA MEDINIPUR | Tamluk Division | CHAUDDHA CHULI AND IT'S ADJOINING MOUJAS PWSS , SM/12495 | New | Sinking Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, , Boundary Wall, Soil investigation & Accommodate FHTC (1623 nos) including 2 years of Operation Maintenance under JJM with allied work for Chauddha Chuli & its adjoining moujas PWSS in Khajuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 74/TD | 05/01/2024 | 540 | SRIMANTA KUMAR MAITY | 501.66 | 90.39 | 18.54 | 40
3871 | PURBA MEDINIPUR | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Material Requisition To Resource Division | 2472/TD | 16/01/2023 | 0 | Resource Division | 18.44 | 0 | 0 | 0
3872 | PURBA MEDINIPUR | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (30nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | 3081/TD | 28/02/2023 | 20 | HYDROTECH ASSOCIATES | 10.01 | 8.28 | 82.77 | 85
3873 | PURBA MEDINIPUR | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (483nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-F) | 3350/TD | 22/03/2023 | 30 | DILIP KUMAR GHOSH | 73.45 | 51.32 | 69.87 | 70
3874 | PURBA MEDINIPUR | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Ground water based Erekhali Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work (400 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | 511/TD | 11/05/2023 | 30 | MANAS KUMAR SAHA | 93.6 | 57.08 | 60.98 | 30
3875 | PURBA MEDINIPUR | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (300 nos) work and Construction of R.C.C. Over Head Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | 583/TD | 16/05/2023 | 634 | RAJ KUMAR SINGHA | 172.52 | 34.27 | 19.87 | 22
3876 | PURBA MEDINIPUR | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Land development at HW site, boundary wall at HW site & 2nd TW site of ground water based Erekhali Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3945/TD | 23/12/2024 | 40 | CHANDA AGENCIES | 14.78 | 0 | 0 | 0
3877 | PURBA MEDINIPUR | Central Drilling | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Erekhali W/S Scheme (T/W-I & II) , Sutahata Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 1388/CDD | 19/09/2023 | 269 | MENAKA ENTERPRISE | 31.41 | 29.24 | 100 | 100
3878 | PURBA MEDINIPUR | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Material Requisition To Resource Division | 638/W | 20/02/2024 | 0 | Resource Division | 10.55 | 0 | 0 | 0
3879 | PURBA MEDINIPUR | Midnapore Mechanical | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Quotation bill for new service connection at TW-II Of Erekhali w/s scheme, Block-Sutahata in the Dist. of purba medinipur under MMD PHE Dte. Name of C.C.C.-Chaitanyapur Application no.-2004923436 Application Type-New Connection Reference ID-204414482 Quotation Date-01/10/2024 Quotation Due Date-01/10/2025 Contract Demand-8344W | C102415718521 | 05/10/2024 | 0 | WBSEDCL | 6.17 | 0 | 0 | 0
3880 | PURBA MEDINIPUR | Midnapore Mechanical | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Quotation bill for new service connection at TW-I of Eriakhali w/s scheme,Block-Sutahata under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695183 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-8500W | BP-2024-25-108 | 06/05/2024 | 0 | WBSEDCL | 6.26 | 0 | 0 | 0
3881 | PURBA MEDINIPUR | Midnapore Mechanical | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for EREKHALI and ADJOINING MOUJAS, Block Sutahata, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2327/W/MMD | 29/12/2022 | 976 | M/S. SAJAHAN CHOWDHURY | 23.69 | 15.21 | 64.19 | 60
3882 | PURBA MEDINIPUR | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (470nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | 3349/TD | 22/03/2023 | 824 | SUNNY ELECTRIC CO | 72.51 | 49.13 | 67.76 | 52
3883 | PURBA MEDINIPUR | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS , SM/12139 | New | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (30nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | 3080/TD | 28/02/2023 | 648 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 9.86 | 8.05 | 82.97 | 100
3884 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11470 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | 210/W/MMD | 10/02/2023 | 180 | M/S S.G. ENTERPRISE | 27.26 | 0 | 0 | 0
3885 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11470 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Natshal Lakshya Water Supply Scheme (Zone- II) under Tamluk Division, PHE Dte. | 50/TD | 05/04/2022 | 20 | RADIANT | 5.44 | 5.36 | 100 | 100
3886 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11470 | Augmentation | Material Requisition To Resource Division | 2617/TD | 02/02/2023 | 0 | Resource Division | 139.61 | 0 | 0 | 0
3887 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11470 | Augmentation | Material Requisition To Resource Division | 1375/TD | 23/09/2022 | 0 | Resource Division | 52.31 | 0 | 0 | 0
3888 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11470 | Augmentation | Augmentation of ground water based Natshal Lakshya Zone-II Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2594/TD | 30/01/2023 | 180 | RAJ KUMAR SINGHA | 986.55 | 507.95 | 70.77 | 65
3889 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11470 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 101/HESD | 27/02/2023 | 184 | S.S.GHORAI | 0.9 | 0 | 0 | 53
3890 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11470 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 1st Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1249/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 83.68 | 19.47 | 100 | 75
3891 | PURBA MEDINIPUR | Central Drilling | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 230 mtrs. Depth) by utilising Departmental machineries for Sar Berya W/S Scheme(TW-IV), Bhagawanpur-I block under Purba medinipur District, CDD PHE Dte. | 55/CDD | 06/04/2023 | 30 | ASHUTOSH DAS & CO | 13.27 | 11.68 | 100 | 100
3892 | PURBA MEDINIPUR | Central Drilling | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Providing drilling crew and other allied works for construction of Tube Well (300 mm x 200 mm x 300Mtrs. Depth ) by utilising Departmental machineries for Sarberya W/S Scheme (TW-I) Block Bhagwanpur, under Purba Midnapur District, CDD PHE Dte. | 549/CDD | 02/06/2023 | 30 | CHANDA ENTERPRISE | 21.55 | 6.4 | 100 | 100
3893 | PURBA MEDINIPUR | Tamluk Division | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Material Requisition To Resource Division | 2719/TD | 06/02/2023 | 0 | Resource Division | 16.76 | 0 | 0 | 0
3894 | PURBA MEDINIPUR | Midnapore Mechanical | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Electric Quotation for SARBERYA Water Supply Scheme T/W-I, (Ref. ID-204090827) | BP-2023-24-315 | 01/11/2023 | 0 | WBSEDCL | 3.24 | 0 | 0 | 0
3895 | PURBA MEDINIPUR | Central Drilling | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | PROVIDING DRIILING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR SARBERYA W/S SCHEME (TW-I), UNDER PASCHIM MEDINIPUR DISTRICT, CDD, PHE DTE. | 1726/CDD | 29/12/2022 | 30 | MENAKA ENTERPRISE | 11.86 | 5.71 | 100 | 100
3896 | PURBA MEDINIPUR | Central Drilling | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Providing Drilling Crew and other allied works for construction of Tube Well (250mm x 150mm x280 Mtrs. Depth) by utilising Departmental machineries for Dakshin Kalamdan and Sarberya (T/W-I & II) under Purba Medinipur District, CDD, PHE Dte. | 854/CDD | 10/07/2023 | 30 | MENAKA ENTERPRISE | 31.45 | 12.17 | 100 | 100
3897 | PURBA MEDINIPUR | Central Drilling | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Sar Berya W/S Scheme (T/W-III) , Bhagawanpur-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 56/CDD | 06/04/2023 | 390 | ASHUTOSH DAS & CO | 13.27 | 10.78 | 100 | 100
3898 | PURBA MEDINIPUR | Tamluk Division | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Material Requisition To Resource Division | 289/TD | 17/01/2024 | 0 | Resource Division | 11.04 | 0 | 0 | 0
3899 | PURBA MEDINIPUR | Tamluk Division | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Material Requisition To Resource Division | 111/TD | 05/01/2024 | 0 | Resource Division | 12.91 | 0 | 0 | 0
3900 | PURBA MEDINIPUR | Midnapore Mechanical | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Electric Quotation for SARBERIYA Water Supply Scheme T/W-II, (Ref. ID-204147802) | BP-2023-24-410 | 09/12/2023 | 0 | WBSEDCL | 3.12 | 0 | 0 | 0
3901 | PURBA MEDINIPUR | Midnapore Mechanical | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Electric Quotation for SARBERIYA Water Supply Scheme T/W-I, (Ref. ID-204147803) | BP-2023-24-411 | 09/12/2023 | 0 | WBSEDCL | 3.32 | 0 | 0 | 0
3902 | PURBA MEDINIPUR | Midnapore Mechanical | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Quotation Bill for New Service connection at T/W NO-II Of SARBERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818488/QUOT/03 DT. 12-07-2024 Application NO- 2004818488 Application type-New connection Consumer Id- 204355506 | BP-2024-25-553 | 08/08/2024 | 0 | WBSEDCL | 3.6 | 0 | 0 | 0
3903 | PURBA MEDINIPUR | Midnapore Mechanical | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SARBERYA and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2372/W/MMD | 31/12/2022 | 974 | DIPALI CONSTRUCTION | 23.68 | 13.17 | 55.63 | 85
3904 | PURBA MEDINIPUR | Tamluk Division | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. , SM/12310 | New | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2095 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SARBERYA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 453/TD | 04/05/2023 | 847 | TARUN KOLEY | 640.74 | 375.92 | 58.67 | 40
3905 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | 1725/TD | 01/02/2022 | 20 | RADIANT | 4.02 | 3.64 | 100 | 100
3906 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Material Requisition To Resource Division | 1202/TD | 06/09/2022 | 0 | Resource Division | 26.9 | 0 | 0 | 0
3907 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Material Requisition To Resource Division | 1203/TD | 06/09/2022 | 0 | Resource Division | 49.51 | 0 | 0 | 0
3908 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Electric Quotation for CHAITANYAPUR Water Supply Scheme T/W-III, Zone-II, (Ref. ID-204076090) | BP-2023-24-242 | 12/09/2023 | 0 | WBSEDCL | 9.52 | 0 | 0 | 0
3909 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Electric Quotation for CHAITANYAPUR Water Supply Scheme T/W-I, Zone-II, (Ref. ID-204076083) | BP-2023-24-241 | 12/09/2023 | 0 | WBSEDCL | 3.63 | 0 | 0 | 0
3910 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-II Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (4374 Nos) work and Construction of R.C.C. Over Head Reservoir of capacity 700 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3458/TD | 27/03/2023 | 1007 | SANKHA ENTERPRISE | 625.57 | 267.79 | 42.81 | 32
3911 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head Work Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 2nd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-I Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1250/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 77.68 | 58.29 | 98.23 | 100
3912 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 3rd Tube Well site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 3169/TD | 10/03/2023 | 60 | MAITY TRADING | 4.6 | 4.49 | 100 | 85
3913 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District Block ¿Sutahata, under JJM Program under MMD PHE Dte. | 631/W/MMD | 20/03/2023 | 180 | M/S. SAJAHAN CHOWDHURY | 37.88 | 36.99 | 100 | 60
3914 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube well site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 625/TD | 17/05/2023 | 30 | SOUVIK GHOSAL | 4.16 | 3.73 | 100 | 100
3915 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Laying Rising main work & construction of Approach Road of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 2591/TD | 10/10/2023 | 20 | A. R. CONSTRUCTION | 24.5 | 17.72 | 100 | 70
3916 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Continuation work order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2024 to 31/12/2024. (12 Months) | 623/HSD, | 28/12/2023 | 366 | SANTANU PATTANAYAK | 1.5 | 4.67 | 312.3 | 20
3917 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11553 | Augmentation | Laying Left Out Distribution System for Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part Work Order I of II) | 3814/TD | 13/12/2024 | 175 | DEBASIS SAMADDAR | 58.86 | 0 | 0 | 70
3918 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS , SM/11881 | New | Material Requisition To Resource Division | 3005/TD | 27/02/2023 | 0 | Resource Division | 16.42 | 0 | 0 | 0
3919 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS , SM/11881 | New | Laying distribution system pipe line, accommodate FHTC(764 nos), Laying Rising Main under JJM with allied work for Harashankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-B) | 282/TD | 20/04/2023 | 951 | NARAYAN MANDAL | 92.86 | 61.98 | 66.74 | 65
3920 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS , SM/11881 | New | Soil investigation & Construction of RCC over Head Reservoir of capacity 300 cum and staging height 20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), under JJM with allied work for Harshankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-D) | 584/TD | 16/05/2023 | 180 | RAJ KUMAR SINGHA | 112.97 | 26.5 | 23.45 | 2
3921 | PURBA MEDINIPUR | Midnapore Mechanical | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS , SM/11881 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARASHANKAR AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 626/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 23.7 | 11.01 | 46.45 | 35
3922 | PURBA MEDINIPUR | Central Drilling | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS , SM/11881 | New | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Harashankar W/S Scheme, Tamluk Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 2114/CDD | 02/03/2023 | 30 | PADMA ENGINEERING & CO. | 17.76 | 15.45 | 100 | 100
3923 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS , SM/11881 | New | M.S. Structure for canel crossing for laying 110 mm OD uPVC pipe of Harasankar PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 825/TD | 05/03/2024 | 20 | NARAYAN MANDAL | 4.21 | 3.02 | 100 | 10
3924 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS , SM/11881 | New | Laying distribution system pipe line, accommodate FHTC construction of switch room cum chlorine room (2nd T/W site), construction of Boundary wall (2nd T/W site), under JJM with allied work for Harasankar PWSS within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-A) | 887/TD | 06/03/2024 | 35 | NARAYAN MANDAL | 4.09 | 4.09 | 100 | 100
3925 | PURBA MEDINIPUR | Midnapore Mechanical | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS , SM/11881 | New | Harasankar W/S scheme H/W site Application No.-2004562746 Ref.-204191037 | BP-2023-24-588 | 02/02/2024 | 0 | WBSEDCL | 5.1 | 0 | 0 | 0
3926 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS , SM/11881 | New | Laying distribution system pipe line, accommodate FHTC(500 nos),Construction of switch room cum cholorine room(H/W site) , Construction of Boundary Wall (H/W site) under JJM with allied work for Harashankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-C) | 590/TD | 17/05/2023 | 803 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 88.84 | 52.65 | 59.26 | 30
3927 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS , SM/11881 | New | Laying distribution system pipe line, accommodate FHTC(700 nos),Construction of switch room cum cholorine room(2nd T/W site) , Construction of Boundary Wall (2nd t/w site) under JJM with allied work for Harashankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-A) | 581/TD | 16/05/2023 | 892 | NARAYAN MANDAL | 139.9 | 99.14 | 70.87 | 76
3928 | PURBA MEDINIPUR | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS , SM/11881 | New | M.S. Structure for canel crossing for laying 150 mm DI (K9) Rising main and 200 mm DI (K7) pipes ( Nodal 379-382 ) of Harasankar PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Canal Length- = 20.00 mtr. ,Number of crossing -2 nos | 3059/TD | 19/09/2024 | 400 | NARAYAN MANDAL | 8.28 | 0 | 0 | 0
3929 | PURBA MEDINIPUR | Tamluk Division | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12400 | New | Material Requisition To Resource Division | 2445/TD | 16/01/2023 | 0 | Resource Division | 55.25 | 0 | 0 | 0
3930 | PURBA MEDINIPUR | Midnapore Mechanical | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12400 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PAHARPUR and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2411/W/MMD | 31/12/2022 | 180 | SUJOY RANJAN BHOWMICK | 21.62 | 13.57 | 62.77 | 45
3931 | PURBA MEDINIPUR | Midnapore Mechanical | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12400 | New | Quotation Bill for New Service connection at T/W NO-I Of PAHARPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743736/QUOT/03 DT. 20-05-2024 Application NO- 2004743736 Application type-New connection Consumer Id- 204312608 | BP-2024-25-320 | 24/06/2024 | 0 | WBSEDCL | 6.24 | 0 | 0 | 0
3932 | PURBA MEDINIPUR | Tamluk Division | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/12400 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 127.31 | 37.44 | 51
3933 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS , SM/12406 | New | Material Requisition To Resource Division | 2981/TD | 27/02/2023 | 0 | Resource Division | 22.62 | 0 | 0 | 0
3934 | PURBA MEDINIPUR | Central Drilling | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS , SM/12406 | New | Providing Drilling Crew and other allied works for construction of Tube Well (250mm x 150mm x280 Mtrs. Depth) by utilising Departmental machineries for Dakshin Kalamdan and Sarberya (T/W-I & II) under Purba Medinipur District, CDD, PHE Dte. | 854/CDD | 10/07/2023 | 30 | MENAKA ENTERPRISE | 31.45 | 13.69 | 100 | 100
3935 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS , SM/12406 | New | Material Requisition To Resource Division | 2955/TD | 12/09/2024 | 0 | Resource Division | 13.47 | 0 | 0 | 0
3936 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS , SM/12406 | New | Dakshin Kalamadan W/S scheme Application No.-2004527976 Ref.-204160990 | BP-2023-24-515 | 09/01/2024 | 0 | WBSEDCL | 13.12 | 0 | 0 | 0
3937 | PURBA MEDINIPUR | Midnapore Mechanical | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS , SM/12406 | New | Quotation for Dakhin Kalamdan w/s scheme PH II under MMD PHE Dte in the district of Purba Medinipur. (Ref 204221089 App No. 2004606720) | BP-2023-24-757 | 01/03/2024 | 0 | WBSEDCL | 2.81 | 0 | 0 | 0
3938 | PURBA MEDINIPUR | Tamluk Division | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS , SM/12406 | New | Sinking of Tube well, Pump House , OHR (Intze type with pile foundation), Rising main, Head work site pipe connection, Laying distribution pipe line,Rigid Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (2953 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dakshin Kalamdan, Katari, and its adjoing Mouzas- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1417/TD | 12/07/2023 | 812 | TAPAS SANTRA | 1109.38 | 553.91 | 63.64 | 75
3939 | PURBA MEDINIPUR | Tamluk Division | KHAGA AND IT'S ADJOINING MOUJAS PWSS , SM/12504 | New | Material Requisition To Resource Division | 2722/TD | 06/02/2023 | 0 | Resource Division | 37.4 | 0 | 0 | 0
3940 | PURBA MEDINIPUR | Midnapore Mechanical | KHAGA AND IT'S ADJOINING MOUJAS PWSS , SM/12504 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHAGA and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 467/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 0 | 0 | 85
3941 | PURBA MEDINIPUR | Tamluk Division | KHAGA AND IT'S ADJOINING MOUJAS PWSS , SM/12504 | New | Material Requisition To Resource Division | 89/TD | 05/01/2024 | 0 | Resource Division | 11.12 | 0 | 0 | 0
3942 | PURBA MEDINIPUR | Midnapore Mechanical | KHAGA AND IT'S ADJOINING MOUJAS PWSS , SM/12504 | New | Quotation Bill for New Service connection at T/W NO-I Of KHAGA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No-2004686929/QUOT/03 DT. 19-04-2024 Application NO- 2004686929 Application type-New connection Consumer Id- 204277584 | BP-2024-25-140 | 09/05/2024 | 0 | WBSEDCL | 2.87 | 0 | 0 | 0
3943 | PURBA MEDINIPUR | Midnapore Mechanical | KHAGA AND IT'S ADJOINING MOUJAS PWSS , SM/12504 | New | Quotation Bill for New Service connection at T/W NO-II Of KHAGA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004739171/QUOT/03 DT. 16-05-2024 Application NO- 2004739171 Application type-New connection Consumer Id- 204309281 | BP-2024-25-244 | 06/06/2024 | 0 | WBSEDCL | 3.96 | 0 | 0 | 0
3944 | PURBA MEDINIPUR | Tamluk Division | KHAGA AND IT'S ADJOINING MOUJAS PWSS , SM/12504 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1806 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of KHAGA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 698/TD | 23/05/2023 | 801 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 581.3 | 242.94 | 41.79 | 40
3945 | PURBA MEDINIPUR | Tamluk Division | KHAGA AND IT'S ADJOINING MOUJAS PWSS , SM/12504 | New | Laying Distribution System (Nodal-J-1 To J-2) of pipe line and its allied works for KHAGA water supply scheme in Bhgwanpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (As per Revised LDS Drawing) | 1080/TD | 16/03/2024 | 487 | S.S. ENTERPRISE | 23.86 | 17.47 | 73.2 | 80
3946 | PURBA MEDINIPUR | Midnapore Mechanical | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12509 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAJENDRA CHAK and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2418/W/MMD | 31/12/2022 | 180 | BOSE & CHATTERJEE INDUSTRIES | 22.73 | 0 | 0 | 0
3947 | PURBA MEDINIPUR | Tamluk Division | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12509 | New | Material Requisition To Resource Division | 2975/TD | 27/02/2023 | 0 | Resource Division | 18.5 | 0 | 0 | 0
3948 | PURBA MEDINIPUR | Tamluk Division | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12509 | New | Laying distribution pipe line, & Accommodate FHTC (163 nos) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART- C) | 259/TD | 19/04/2023 | 30 | BADAL CHANDRA GOLE | 41.58 | 31.33 | 75.36 | 77
3949 | PURBA MEDINIPUR | Tamluk Division | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12509 | New | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC ( 500 nos) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte.. (PART- B) | 553/TD | 12/05/2023 | 889 | SK. NUR ISLAM | 114.81 | 81.88 | 71.32 | 80
3950 | PURBA MEDINIPUR | Tamluk Division | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12509 | New | Soil investigation, 250 cum OHR (Intze type with pile foundation) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART- D) | 2439/TD | 19/09/2023 | 180 | ANUSKA ENTERPRISE | 104.2 | 0 | 0 | 0
3951 | PURBA MEDINIPUR | Tamluk Division | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12509 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Rajendrachak PWSS at Egra-II Block under Tamluk Division, PHE Dte. | 2071/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3952 | PURBA MEDINIPUR | Midnapore Mechanical | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12509 | New | Quotation Bill for New Service connection at T/W NO-II Of RAJENDRACHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004732464/QUOT/03/212 DT. 13-05-2024 Application NO- 2004732464 Application type-New connection Consumer Id- 204305461 | BP-2024-25-248 | 06/06/2024 | 0 | WBSEDCL | 3.9 | 0 | 0 | 0
3953 | PURBA MEDINIPUR | Midnapore Mechanical | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12509 | New | Quotation Bill for New Service connection at T/W NO-I Of RAJENDRACHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004940316/QUOT/03/770 DT. 25-10-2024 Application NO- 2004940316 Application type-New connection Consumer Id- 204428743 | C112429700471 | 25/11/2024 | 0 | WBSEDCL | 6.29 | 0 | 0 | 0
3954 | PURBA MEDINIPUR | Central Drilling | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12509 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 46.31 | 90.76 | 11
3955 | PURBA MEDINIPUR | Tamluk Division | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS , SM/12509 | New | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC ( 997 nos) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART- A) | 849/TD | 31/05/2023 | 784 | JAGANNATH MAKAR | 256.07 | 178.54 | 69.72 | 85
3956 | PURBA MEDINIPUR | Tamluk Division | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/12511 | New | Material Requisition To Resource Division | 2458/TD | 16/01/2023 | 0 | Resource Division | 40.42 | 0 | 0 | 0
3957 | PURBA MEDINIPUR | Tamluk Division | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/12511 | New | Material Requisition To Resource Division | 1665/TD | 29/04/2024 | 0 | Resource Division | 7.01 | 0 | 0 | 0
3958 | PURBA MEDINIPUR | Midnapore Mechanical | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/12511 | New | Quotation Bill for New Service connection at T/W NO-I Of TUPCHIBAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004889798/QUOT/03 DT. 12-09-2024 Application NO- 2004889798 Application type-New connection Consumer Id- 204393534 | C092445096068 | 30/09/2024 | 0 | WBSEDCL | 3.76 | 0 | 0 | 0
3959 | PURBA MEDINIPUR | Midnapore Mechanical | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/12511 | New | Quotation Bill for New Service connection at T/W NO-II Of TUPCHIBAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004657850/QUOT/03/1514 DT. 28-03-2024 Application NO- 2004657850 Application type-New connection Consumer Id- 204257679 | BP-2024-25-31 | 15/04/2024 | 0 | WBSEDCL | 4.12 | 0 | 0 | 0
3960 | PURBA MEDINIPUR | Midnapore Mechanical | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/12511 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TUPCHIBAR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 464/W/MMD | 20/03/2023 | 713 | CHOWDHURY AND BASU ENTERPRISE | 22.79 | 0 | 0 | 80
3961 | PURBA MEDINIPUR | Tamluk Division | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/12511 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 110.17 | 27.89 | 51
3962 | PURBA MEDINIPUR | Tamluk Division | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS , SM/11946 | New | Material Requisition To Resource Division | 2678/TD | 06/02/2023 | 0 | Resource Division | 38.97 | 0 | 0 | 0
3963 | PURBA MEDINIPUR | Midnapore Mechanical | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS , SM/11946 | New | Mirikpur W/S scheme H/W site Tw-I Application.-2004547150 Ref.-204177955 | BP-2023-24-545 | 15/01/2024 | 0 | WBSEDCL | 3.7 | 0 | 0 | 0
3964 | PURBA MEDINIPUR | Midnapore Mechanical | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS , SM/11946 | New | Mirikpur W/S scheme H/W site Tw-II Application.-2004547153 Ref.-204177965 | BP-2023-24-546 | 15/01/2024 | 0 | WBSEDCL | 4.21 | 0 | 0 | 0
3965 | PURBA MEDINIPUR | Tamluk Division | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS , SM/11946 | New | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(5198nos), Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of different capacity as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Chawrakalganda PWSS & Mirikpur PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 433/TD | 03/05/2023 | 820 | ARABINDA GHOSH | 1233.42 | 0 | 0 | 65
3966 | PURBA MEDINIPUR | Tamluk Division | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS , SM/11946 | New | Canal crossing for laying HDPE pipes of Mirikpur PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. ( Nodal Point J-512 to J-517 ) Canal Length- =30.00 mtr. Number of crossing -1 nos | 459/TD | 04/02/2025 | 25 | GHOSH ENTERPRISE | 6.25 | 0 | 0 | 0
3967 | PURBA MEDINIPUR | Midnapore Mechanical | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS , SM/11946 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MIRIKPUR AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 644/W/MMD | 20/03/2023 | 749 | SOUMEN ELECTRIC | 27.17 | 23.4 | 87.69 | 80
3968 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Anantapur (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | 1739/TD | 03/02/2022 | 20 | RADIANT | 3.86 | 3.83 | 100 | 100
3969 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR ANANTAPUR W/S SCH (ZONE-I) (TW-III), TAMLUK BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 2120/CDD | 02/03/2023 | 30 | MENAKA ENTERPRISE | 17.75 | 16.09 | 90.64 | 0
3970 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | Material Requisition To Resource Division | 1017/TD | 08/08/2022 | 0 | Resource Division | 67.14 | 0 | 0 | 0
3971 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | Material Requisition To Resource Division | 1208/TD | 06/09/2022 | 0 | Resource Division | 38.23 | 0 | 0 | 0
3972 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | Material Requisition To Resource Division | 1923/TD | 14/08/2023 | 0 | Resource Division | 33.23 | 0 | 0 | 0
3973 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | Payment to WBSEDCL for Quotation Money for Anantapur Zone-I PWSS under Tamluk Division, PHE Dte. | BP-2022-23-819 | 24/03/2023 | 0 | WBSEDCL | 2.38 | 0 | 0 | 0
3974 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 633/W/MMD | 20/03/2023 | 180 | DEBJYOTI BASU | 40.78 | 25.63 | 62.86 | 50
3975 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Anantapur Zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 1081/TD | 08/06/2023 | 45 | SK. SAHALAM | 5.1 | 4.79 | 100 | 100
3976 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | Laying of 400 mm dia. Additional length distribution pipe line with supply of DI specials under Anantapur Zone- I PWSS with in Tamluk Dev.Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division,PHE Dte. | 2203/TD | 01/09/2023 | 20 | TARUN KOLEY | 10.96 | 9.95 | 100 | 100
3977 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | Material Requisition To Resource Division | 1123/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
3978 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | Additional quatation for Tulia Anantapur Zone-I, TW-III , Tamluk Block Application ID.-100000099975 Reference ID.-860292305 | BP-2023-24-716 | 20/02/2024 | 0 | WBSEDCL | 0.23 | 0 | 0 | 0
3979 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | Laying of distribution pipe line to accommodate FHTC(6217 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Anantapur Zone-I Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1889/TD | 24/11/2022 | 859 | TARUN KOLEY | 622.31 | 336.89 | 54.14 | 90
3980 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11474 | Augmentation | Construction of new boundary wall around OHR and Repair and Renovation of Existing boundary wall , Pump house and chlorine room at Head work site and 2nd tube well site of Anantapur Zone-I PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 3449/TD | 30/10/2024 | 40 | M J A ENTERPRISE | 9.09 | 0 | 0 | 0
3981 | PURBA MEDINIPUR | Tamluk Division | ILASHPUR AND ADJOINING MOUJAS PWSS , SM/12294 | New | Material Requisition To Resource Division | 2385/TD | 16/01/2023 | 0 | Resource Division | 20.13 | 0 | 0 | 0
3982 | PURBA MEDINIPUR | Midnapore Mechanical | ILASHPUR AND ADJOINING MOUJAS PWSS , SM/12294 | New | Electric Quotation for ILASHPUR Water Supply Scheme T/W-I, (Ref. ID-204086226) | BP-2023-24-314 | 01/11/2023 | 0 | WBSEDCL | 3.01 | 0 | 0 | 0
3983 | PURBA MEDINIPUR | Midnapore Mechanical | ILASHPUR AND ADJOINING MOUJAS PWSS , SM/12294 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ILASHPUR and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2368/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 19.18 | 80.94 | 50
3984 | PURBA MEDINIPUR | Tamluk Division | ILASHPUR AND ADJOINING MOUJAS PWSS , SM/12294 | New | Laying Distribution System (NP-2-27,27-38,38-45,45-47,47-53,53-57,57-61,61-63,63-65,65-67 & 67-71) of pipe line and its allied works for Ilashpur Water Supply Scheme in Bhgwanpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 1923/TD | 07/06/2024 | 25 | MMS CONSTRUCTIONS PVT. LTD. | 12.61 | 12.14 | 100 | 90
3985 | PURBA MEDINIPUR | Tamluk Division | ILASHPUR AND ADJOINING MOUJAS PWSS , SM/12294 | New | Material Requisition To Resource Division | 88/TD | 05/01/2024 | 0 | Resource Division | 12.55 | 0 | 0 | 0
3986 | PURBA MEDINIPUR | Tamluk Division | ILASHPUR AND ADJOINING MOUJAS PWSS , SM/12294 | New | Payment to WBSEDCL for Shifting of LTOH Line at Siulipur for Ilashpur PWSS under Tamluk Division, PHE Dte. | BP-2024-25-382 | 29/08/2024 | 0 | WBSEDCL | 0.81 | 0 | 0 | 0
3987 | PURBA MEDINIPUR | Tamluk Division | ILASHPUR AND ADJOINING MOUJAS PWSS , SM/12294 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2038 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of ILASHPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 448/TD | 04/05/2023 | 942 | TAPAS SANTRA | 657.13 | 356.42 | 54.24 | 58
3988 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC (1841 Nos.) of Chandibenia Zone-II and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the district Purba Medinipur. , SM/12300 | Retrofitting | Retrofitting to accommodate FHTC (1841 nos.) under JJM in Chandibenia Zone- II PWSS Block - Moyna in the District of Purba Medinipur. | 1424/TD | 26/09/2022 | 25 | HARIPADA PATTANAYAK | 69.06 | 69.04 | 100 | 100
3989 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC (1841 Nos.) of Chandibenia Zone-II and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the district Purba Medinipur. , SM/12300 | Retrofitting | Material Requisition To Resource Division | 1101/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
3990 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Moyna Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | 1469/TD | 03/01/2022 | 20 | APEX ENGINEERING | 4.37 | 3.98 | 100 | 100
3991 | PURBA MEDINIPUR | Central Drilling | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300 mm x 200 mm x 230Mtrs. Depth) by utilising Departmental machineries for Moyna W/S Scheme (Z-Ii, T/W-III) Moyna Block under Purba Medinipur District CDD PHE Dte. | 539/CDD | 02/06/2023 | 30 | MENAKA ENTERPRISE | 17.76 | 15.47 | 100 | 100
3992 | PURBA MEDINIPUR | Central Drilling | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300 mm x 200 mm x 230Mtrs. Depth) by utilising Departmental machineries for Moyna W/S Scheme (Z-Ii, T/W-IV) Moyna Block under Purba Medinipur District CDD PHE Dte. | 540/CDD | 02/06/2023 | 30 | MENAKA ENTERPRISE | 17.76 | 16.14 | 100 | 100
3993 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Material Requisition To Resource Division | 1204/TD | 06/09/2022 | 0 | Resource Division | 7.03 | 0 | 0 | 0
3994 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Material Requisition To Resource Division | 1206/TD | 06/09/2022 | 0 | Resource Division | 109.03 | 0 | 0 | 0
3995 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Laying of distribution pipe line to accommodate FHTC (3870 nos) with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Moyna Zone-II Water Supply Scheme within Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1651/TD | 02/11/2022 | 1080 | ARABINDA GHOSH | 571.76 | 481.85 | 84.27 | 80
3996 | PURBA MEDINIPUR | Central Drilling | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Moyna W/S Scheme (Z-II,T/W-V ) , Moyna Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 541/CDD | 02/06/2023 | 30 | MENAKA ENTERPRISE | 17.76 | 15.8 | 100 | 100
3997 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Moyna W/S scheme T/W-III, Z-II Ref.-204143545 | BP-2023-24-436 | 18/12/2023 | 0 | WBSEDCL | 2.74 | 0 | 0 | 0
3998 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Electric Quotation for MOYNA Water Supply Scheme T/W-I,Zone-II, (Ref. ID-204143547) | BP-2023-24-409 | 09/12/2023 | 0 | WBSEDCL | 5.37 | 0 | 0 | 0
3999 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Moyna W/S scheme PH.-II, Zone-II Application No.-2004557342 Ref.-204187844 | BP-2023-24-577 | 18/01/2024 | 0 | WBSEDCL | 8.84 | 0 | 0 | 0
4000 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Bill for damage of Moyna Bridge approach road at 1.90 Km. Due to laying of water pipe line for Moyna Zone-II PWSS | BP-2024-25-496 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.41 | 0 | 0 | 0
4001 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Pump House , Boundary Wall, Rising Main, Dramsheet Pilling for Augmentation of Moyna Zone-II Water Supply Scheme under Moyna Development Block within Tamluk Sub-Division under Tamluk Division, PHE Dte.in the district Purba Medinipur. | 1445/TD | 13/07/2023 | 820 | GHOSH ENTERPRISE | 89.23 | 36.26 | 40.64 | 81
4002 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Proposed Retaining Wall cun Guard wall and Approach Road beside pond at 3rd Tube well for Augmentation of Moyna Zone-II PWSS under Moyna Development Block under Tamluk Sub- Division in Tamluk Divisionin the District of Purba Medinipur. | 2678/TD | 22/08/2024 | 25 | GHOSH ENTERPRISE | 6.98 | 0 | 0 | 0
4003 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Moyna (Zone-II) PWSS , SM/11639 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Moyna (Zone-II) PWSS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 630/W/MMD | 20/03/2023 | 530 | ALPHA ENTERPRISE | 37.86 | 35.46 | 95.26 | 70
4004 | PURBA MEDINIPUR | Tamluk Division | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. , SM/12321 | New | Material Requisition To Resource Division | 2711/TD | 06/02/2023 | 0 | Resource Division | 42.6 | 0 | 0 | 0
4005 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. , SM/12321 | New | Quotation Bill for New Service connection at T/W NO-II Of UTTAR SILAMPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004672028/QUOT/03/45 DT. 05-04-2024 Application NO- 2004672028 Application type-New connection Consumer Id- 204266730 | BP-2024-25-94 | 24/04/2024 | 0 | WBSEDCL | 5.1 | 0 | 0 | 0
4006 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. , SM/12321 | New | Quotation Bill for New Service connection at T/W NO-I Of UTTAR SILAMPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004672007/QUOT/03/46 DT. 05-04-2024 Application NO- 2004672007 Application type-New connection Consumer Id- 204266731 | BP-2024-25-93 | 24/04/2024 | 0 | WBSEDCL | 3.64 | 0 | 0 | 0
4007 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. , SM/12321 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR SILAMPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 462/W/MMD | 20/03/2023 | 713 | CHOWDHURY AND BASU ENTERPRISE | 22.79 | 20.72 | 90.9 | 80
4008 | PURBA MEDINIPUR | Tamluk Division | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. , SM/12321 | New | Sinking of Tube Well ,Construction of Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1155 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Uttar Silampur PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | 1565/TD | 19/07/2023 | 720 | ORIENT CONSTRUCTION | 431.66 | 224.96 | 52.12 | 60
4009 | PURBA MEDINIPUR | Tamluk Division | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. , SM/12484 | New | Material Requisition To Resource Division | 2992/TD | 27/02/2023 | 0 | Resource Division | 26.09 | 0 | 0 | 0
4010 | PURBA MEDINIPUR | Tamluk Division | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. , SM/12484 | New | Sinking of Tube well,Pump House ,Construction of 200 cum & 250 Cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3146 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Dhankar & Talchitkini its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1671/TD | 25/07/2023 | 860 | HALDIA DEVELOPMENT CONSTRUCTION | 895.07 | 153.74 | 37.59 | 20
4011 | PURBA MEDINIPUR | Midnapore Mechanical | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. , SM/12484 | New | Quotation Bill for New Service connection at T/W NO-I Of DHANKAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004607668/QUOT/03 DT. 21-02-2024 Application NO- 2004607668 Application type-New connection Consumer Id- 204222374 | BP-2023-24-825 | 13/03/2024 | 0 | WBSEDCL | 4.29 | 0 | 0 | 0
4012 | PURBA MEDINIPUR | Midnapore Mechanical | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. , SM/12484 | New | Quotation Bill for New Service connection at T/W NO-II Of DHANKAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743815/QUOT/03 DT. 20-05-2024 Application NO- 2004743815 Application type-New connection Consumer Id- 204312604 | BP-2024-25-321 | 24/06/2024 | 0 | WBSEDCL | 3.12 | 0 | 0 | 0
4013 | PURBA MEDINIPUR | Midnapore Mechanical | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. , SM/12484 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DHANKAR and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 515/W/MMD | 20/03/2023 | 804 | KARUNAMOY ENGINEERING | 22.75 | 10.38 | 45.64 | 51
4014 | PURBA MEDINIPUR | Tamluk Division | DURMUT AND ADJOINING MOUJAS PWSS , SM/12820 | New | Material Requisition To Resource Division | 2401/TD | 16/01/2023 | 0 | Resource Division | 41.93 | 0 | 0 | 0
4015 | PURBA MEDINIPUR | Midnapore Mechanical | DURMUT AND ADJOINING MOUJAS PWSS , SM/12820 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DURMUT AND ADJOINING MOUJAS PWSS, Block Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 815/W/MMD | 24/03/2023 | 180 | TAPAN KUMAR DEY | 22.78 | 9.45 | 41.47 | 35
4016 | PURBA MEDINIPUR | Tamluk Division | DURMUT AND ADJOINING MOUJAS PWSS , SM/12820 | New | Material Requisition To Resource Division | 2957/TD | 12/09/2024 | 0 | Resource Division | 10.46 | 0 | 0 | 0
4017 | PURBA MEDINIPUR | Tamluk Division | DURMUT AND ADJOINING MOUJAS PWSS , SM/12820 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 0 | 0 | 51
4018 | PURBA MEDINIPUR | Tamluk Division | GOKULNAGAR AND ADJOINING MOUJAS , SM/12165 | New | Material Requisition To Resource Division | 2425/TD | 16/01/2023 | 0 | Resource Division | 6.8 | 0 | 0 | 0
4019 | PURBA MEDINIPUR | Tamluk Division | GOKULNAGAR AND ADJOINING MOUJAS , SM/12165 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Gokulnagar PWSS at Moyna Block under Tamluk Division,PHE Dte. | 193/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4020 | PURBA MEDINIPUR | Tamluk Division | GOKULNAGAR AND ADJOINING MOUJAS , SM/12165 | New | Material Requisition To Resource Division | 1565/TD | 23/04/2024 | 0 | Resource Division | 14.91 | 0 | 0 | 0
4021 | PURBA MEDINIPUR | Midnapore Mechanical | GOKULNAGAR AND ADJOINING MOUJAS , SM/12165 | New | Quotation for new service connection at Gokulnagar w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No 2004635309, Ref ID 204240956) | BP-2023-24-910 | 28/03/2024 | 0 | WBSEDCL | 5.65 | 0 | 0 | 0
4022 | PURBA MEDINIPUR | Midnapore Mechanical | GOKULNAGAR AND ADJOINING MOUJAS , SM/12165 | New | Quotation for new service connection at Gokulnagar w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No 2004631965, Ref ID 204238451) | BP-2023-24-909 | 28/03/2024 | 0 | WBSEDCL | 7.06 | 0 | 0 | 0
4023 | PURBA MEDINIPUR | Midnapore Mechanical | GOKULNAGAR AND ADJOINING MOUJAS , SM/12165 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOKULNAGAR and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2376/W/MMD | 31/12/2022 | 882 | AHALYA ENGINEERING WORKS | 25.25 | 20.03 | 79.33 | 50
4024 | PURBA MEDINIPUR | Tamluk Division | KHARUI AND ADJOINING MOUZAS PWSS , SM/11945 | New | Material Requisition To Resource Division | 2685/TD | 06/02/2023 | 0 | Resource Division | 73.85 | 0 | 0 | 0
4025 | PURBA MEDINIPUR | Tamluk Division | KHARUI AND ADJOINING MOUZAS PWSS , SM/11945 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kharui PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | 2077/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4026 | PURBA MEDINIPUR | Tamluk Division | KHARUI AND ADJOINING MOUZAS PWSS , SM/11945 | New | Material Requisition To Resource Division | 136/TD | 05/01/2024 | 0 | Resource Division | 15.86 | 0 | 0 | 0
4027 | PURBA MEDINIPUR | Midnapore Mechanical | KHARUI AND ADJOINING MOUZAS PWSS , SM/11945 | New | Quotation Bill for Kharui W/S Scheme T/W-II Application No=2004614098 Reference ID=204225097 | BP-2023-24-802 | 11/03/2024 | 0 | WBSEDCL | 3.72 | 0 | 0 | 0
4028 | PURBA MEDINIPUR | Midnapore Mechanical | KHARUI AND ADJOINING MOUZAS PWSS , SM/11945 | New | Quotation Bill for Kharui W/S Scheme H/W Site Application No=2004624417 Reference ID=204231697 | BP-2023-24-801 | 11/03/2024 | 0 | WBSEDCL | 4.66 | 0 | 0 | 0
4029 | PURBA MEDINIPUR | Midnapore Mechanical | KHARUI AND ADJOINING MOUZAS PWSS , SM/11945 | New | Additional Quotation for Kharui Water Supply Scheme T/W-I Kolaghat CCC, Block-Sahaid Matangini Reference ID=860298136 Application ID=100000106136 Quotation Date=23.04.2024 | BP-2024-25-144 | 09/05/2024 | 0 | WBSEDCL | 0.62 | 0 | 0 | 0
4030 | PURBA MEDINIPUR | Midnapore Mechanical | KHARUI AND ADJOINING MOUZAS PWSS , SM/11945 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHARUI AND ADJOINING MOUZAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 625/W/MMD | 20/03/2023 | 721 | DEBJYOTI BASU | 23.7 | 15.07 | 63.6 | 90
4031 | PURBA MEDINIPUR | Tamluk Division | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. , SM/12319 | New | Material Requisition To Resource Division | 2449/TD | 16/01/2023 | 0 | Resource Division | 32.88 | 0 | 0 | 0
4032 | PURBA MEDINIPUR | Midnapore Mechanical | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. , SM/12319 | New | Quotation Bill for New Service connection at T/W NO-II Of TAPINDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835302/QUOT/03 DT. 26-07-2024 Application NO- 2004835302 MEMO NO: AMR/PHE/285 DT.26/7/2024 Application type-New connection Consumer Id- 204365759 | BP-2024-25-536 | 07/08/2024 | 0 | WBSEDCL | 1.98 | 0 | 0 | 0
4033 | PURBA MEDINIPUR | Midnapore Mechanical | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. , SM/12319 | New | Quotation Bill for New Service connection at T/W NO-I Of TAPINDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004834992/QUOT/03 DT. 26-07-2024 Application NO- 2004834992 MEMO NO: AMR/PHE/284 DT.26/7/2024 Application type-New connection Consumer Id- 204365754 | BP-2024-25-537 | 07/08/2024 | 0 | WBSEDCL | 6.84 | 0 | 0 | 0
4034 | PURBA MEDINIPUR | Tamluk Division | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. , SM/12319 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 123.85 | 34.27 | 51
4035 | PURBA MEDINIPUR | Midnapore Mechanical | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. , SM/12319 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TAPINDA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2356/W/MMD | 31/12/2022 | 974 | SOUMEN ELECTRIC | 21.61 | 15.29 | 72.23 | 61
4036 | PURBA MEDINIPUR | Tamluk Division | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. , SM/12320 | New | Material Requisition To Resource Division | 2422/TD | 16/01/2023 | 0 | Resource Division | 39.03 | 0 | 0 | 0
4037 | PURBA MEDINIPUR | Midnapore Mechanical | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. , SM/12320 | New | Quotation Bill for New Service connection at T/W NO-II Of ALANGIRI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674883/QUOT/03 DT. 09-04-2024 Application NO- 2004674883 Application type-New connection Consumer Id- 204269736 | BP-2024-25-85 | 24/04/2024 | 0 | WBSEDCL | 6.04 | 0 | 0 | 0
4038 | PURBA MEDINIPUR | Midnapore Mechanical | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. , SM/12320 | New | Quotation Bill for New Service connection at T/W NO-I Of ALANGIRI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674870/QUOT/03 DT. 09-04-2024 Application NO- 2004674870 Application type-New connection Consumer Id- 204269908 | BP-2024-25-84 | 24/04/2024 | 0 | WBSEDCL | 3.15 | 0 | 0 | 0
4039 | PURBA MEDINIPUR | Midnapore Mechanical | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. , SM/12320 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ALANGIRI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2417/W/MMD | 31/12/2022 | 882 | RITESH ENTERPRISE | 22.81 | 10.72 | 47.01 | 80
4040 | PURBA MEDINIPUR | Tamluk Division | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. , SM/12320 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 196.57 | 45.17 | 51
4041 | PURBA MEDINIPUR | Tamluk Division | BARNAN AND ITS ADJOINING MOUJAS PWSS , SM/11884 | New | Material Requisition To Resource Division | 2684/TD | 06/02/2023 | 0 | Resource Division | 19.64 | 0 | 0 | 0
4042 | PURBA MEDINIPUR | Tamluk Division | BARNAN AND ITS ADJOINING MOUJAS PWSS , SM/11884 | New | Land filling with silver sand and land development of approach road and other side at 1st. & 2nd T/W site Barnan W/S Scheme of Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | 2182/TD | 08/07/2024 | 14 | S.D. CONSTRUCTION | 3.91 | 3.91 | 100 | 100
4043 | PURBA MEDINIPUR | Tamluk Division | BARNAN AND ITS ADJOINING MOUJAS PWSS , SM/11884 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Barnan PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | 2076/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4044 | PURBA MEDINIPUR | Tamluk Division | BARNAN AND ITS ADJOINING MOUJAS PWSS , SM/11884 | New | Material Requisition To Resource Division | 82//TD | 05/01/2024 | 0 | Resource Division | 6.85 | 0 | 0 | 0
4045 | PURBA MEDINIPUR | Midnapore Mechanical | BARNAN AND ITS ADJOINING MOUJAS PWSS , SM/11884 | New | Quotation Bill for Barnan Water supply Scheme Tubewell No-I Application No=2004754441 Reference ID=204318380 | BP-2024-25-266 | 12/06/2024 | 0 | WBSEDCL | 8.5 | 0 | 0 | 0
4046 | PURBA MEDINIPUR | Midnapore Mechanical | BARNAN AND ITS ADJOINING MOUJAS PWSS , SM/11884 | New | Quotation Bill for Barnan Water supply Scheme Tubewell No-II Application No=2004756795 Reference ID=204319871 | BP-2024-25-267 | 12/06/2024 | 0 | WBSEDCL | 5.48 | 0 | 0 | 0
4047 | PURBA MEDINIPUR | Midnapore Mechanical | BARNAN AND ITS ADJOINING MOUJAS PWSS , SM/11884 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARNAN AND ITS ADJOINING MOUJAS PWSS, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 624/W/MMD | 20/03/2023 | 896 | DEBJYOTI BASU | 23.7 | 15.07 | 63.6 | 50
4048 | PURBA MEDINIPUR | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS , SM/13884 | New | Material Requisition To Resource Division | 2437/TD | 16/01/2023 | 0 | Resource Division | 25.43 | 0 | 0 | 0
4049 | PURBA MEDINIPUR | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS , SM/13884 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Gouranga Chak PWSS at Moyna block under Tamluk Division,PHE Dte. | 195/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4050 | PURBA MEDINIPUR | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS , SM/13884 | New | Material Requisition To Resource Division | 1566/TD | 23/04/2024 | 0 | Resource Division | 8.79 | 0 | 0 | 0
4051 | PURBA MEDINIPUR | Midnapore Mechanical | GOURANGA CHAK AND ADJOINING MOUJAS PWSS , SM/13884 | New | Quotation for new service connection at Gouranga chak w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004709475, Ref ID 204293707) | BP-2024-25-189 | 24/05/2024 | 0 | WBSEDCL | 4.34 | 0 | 0 | 0
4052 | PURBA MEDINIPUR | Midnapore Mechanical | GOURANGA CHAK AND ADJOINING MOUJAS PWSS , SM/13884 | New | Quotation for new service connection at Gouranga chak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004709436, Ref ID 204293706) | BP-2024-25-188 | 24/05/2024 | 0 | WBSEDCL | 7.81 | 0 | 0 | 0
4053 | PURBA MEDINIPUR | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS , SM/13884 | New | Instalation of display Board at 5 nos { 1. CHONGRA PWSS( PUMP HOUSE -2) , 2. GOURANGA CHAK PWSS( PUMP HOUSE 1 & 2), 3.GHOJINA PWSS( PUMP HOUSE 1 & 2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 63/RWS/TSD | 06/05/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 0 | 100
4054 | PURBA MEDINIPUR | Tamluk Division | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/12886 | New | Material Requisition To Resource Division | 2391/TD | 16/01/2023 | 0 | Resource Division | 18.29 | 0 | 0 | 0
4055 | PURBA MEDINIPUR | Midnapore Mechanical | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/12886 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SYAMRAIBAR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2410/W/MMD | 31/12/2022 | 180 | SUJOY RANJAN BHOWMICK | 21.62 | 7.35 | 34.02 | 35
4056 | PURBA MEDINIPUR | Tamluk Division | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/12886 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Syamraibar PWSS at Contai-I Block under Tamluk Division, PHE Dte. | 2065/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4057 | PURBA MEDINIPUR | Tamluk Division | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS , SM/12886 | New | Material Requisition To Resource Division | 2978/TD | 12/09/2024 | 0 | Resource Division | 6.44 | 0 | 0 | 0
4058 | PURBA MEDINIPUR | Tamluk Division | JUMKI AND ADJOINING MOUJAS PWSS , SM/12995 | New | Material Requisition To Resource Division | 2971/TD | 27/02/2023 | 0 | Resource Division | 19.96 | 0 | 0 | 0
4059 | PURBA MEDINIPUR | Midnapore Mechanical | JUMKI AND ADJOINING MOUJAS PWSS , SM/12995 | New | Quotation Bill for New Service connection at T/W NO-II Of JUMKI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674807/QUOT/03 DT. 09-04-2024 Application NO- 2004674807 Application type-New connection Consumer Id- 204269878 | BP-2024-25-87 | 24/04/2024 | 0 | WBSEDCL | 4.9 | 0 | 0 | 0
4060 | PURBA MEDINIPUR | Midnapore Mechanical | JUMKI AND ADJOINING MOUJAS PWSS , SM/12995 | New | Quotation Bill for New Service connection at T/W NO-I Of JUMKI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674743/QUOT/03 DT. 09-04-2024 Application NO- 2004674743 Application type-New connection Consumer Id- 204269918 | BP-2024-25-86 | 24/04/2024 | 0 | WBSEDCL | 3.36 | 0 | 0 | 0
4061 | PURBA MEDINIPUR | Midnapore Mechanical | JUMKI AND ADJOINING MOUJAS PWSS , SM/12995 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JUMKI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2371/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 17.21 | 72.63 | 85
4062 | PURBA MEDINIPUR | Tamluk Division | JUMKI AND ADJOINING MOUJAS PWSS , SM/12995 | New | Sinking of Tube Well , Laying distribution system, Pump House at Head work site & 2nd tube well site, Soil Test, OHR ( 250 Cum ) FHTC ( (1636 nos ) Boundary wall and Rising Main and 2 Years Maintenance under JJM with allied work for Jumki PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 2485/TD | 26/09/2023 | 797 | AJIT KUMAR SOM | 442.63 | 241.06 | 54.46 | 65
4063 | PURBA MEDINIPUR | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS , SM/13688 | New | Material Requisition To Resource Division | 2424/TD | 16/01/2023 | 0 | Resource Division | 39.36 | 0 | 0 | 0
4064 | PURBA MEDINIPUR | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS , SM/13688 | New | Ground water based Sar Berya Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | 3077/TD | 28/02/2023 | 668 | J.M. CONSTRUCTION | 59.34 | 45.12 | 76.04 | 35
4065 | PURBA MEDINIPUR | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS , SM/13688 | New | Ground water based Sar Berya Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-F) | 3079/TD | 28/02/2023 | 20 | MADAN MOHAN MAITY | 36.48 | 35.3 | 100 | 100
4066 | PURBA MEDINIPUR | Midnapore Mechanical | SAR BERYA AND ADJOINING MOUJAS PWSS , SM/13688 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAR BERYA and ADJOINING MOUJAS, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 544/W/MMD | 20/03/2023 | 529 | SOUMEN ELECTRIC | 21.56 | 21.13 | 100 | 100
4067 | PURBA MEDINIPUR | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS , SM/13688 | New | Installation of display board at 2 (two) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-IV) [Sarberia PWSS & Urddhabmal PWSS] | 620/HSD, | 21/12/2023 | 7 | SANTANU PATTANAYAK | 0.42 | 0.41 | 100 | 100
4068 | PURBA MEDINIPUR | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS , SM/13688 | New | Orientation Programme under Haldia Sub-Division of Tamluk Division, PHE Dte. (For 5 nos Blocks, i.e. - i) Sutahata Dev. Block, ii) Mahishadal Dev. Block, iii) Haldia Dev. Block, iv) Nandigram - I Dev. Block & v) Nandigram - II Dev. Block) | 621/HSD, | 21/12/2023 | 2 | TAPAN BERA | 0.94 | 0.94 | 100 | 100
4069 | PURBA MEDINIPUR | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS , SM/13688 | New | Material Requisition To Resource Division | 112/TD | 05/01/2024 | 0 | Resource Division | 5.39 | 0 | 0 | 0
4070 | PURBA MEDINIPUR | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS , SM/13688 | New | Ground water based Sar Berya Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | 3076/TD | 28/02/2023 | 30 | PULAK KUMAR SAMANTA | 55.08 | 45.84 | 83.22 | 62
4071 | PURBA MEDINIPUR | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS , SM/13688 | New | Ground water based Sar Berya Water Supply Scheme by providing Construction of R.C.C. Over Head Reservoir of capacity 100 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | 1468/TD | 13/07/2023 | 777 | JAGANNATH MAKAR | 80.39 | 33.31 | 41.43 | 3
4072 | PURBA MEDINIPUR | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS , SM/13688 | New | Box Culvert at HW site & Construction of Retaining wall of ground water based Sarberia Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1083/TD | 16/03/2024 | 40 | JAGANNATH MAKAR | 13.42 | 0 | 0 | 0
4073 | PURBA MEDINIPUR | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS , SM/13688 | New | Ground water based Sar Berya Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | 3078/TD | 28/02/2023 | 447 | R CONSTRUCTION | 42.52 | 39.94 | 99.32 | 100
4074 | PURBA MEDINIPUR | Midnapore Mechanical | KAPASDA & IT'S ADJOINING MOUJAS PWSS , SM/13692 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAPASDA and ADJOINING MOUJAS, Block ¿ contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 556/W/MMD | 20/03/2023 | 180 | SHIVAM ENTERPRISE | 22.78 | 0 | 0 | 0
4075 | PURBA MEDINIPUR | Tamluk Division | KAPASDA & IT'S ADJOINING MOUJAS PWSS , SM/13692 | New | Material Requisition To Resource Division | 2969/TD | 27/02/2023 | 0 | Resource Division | 34.67 | 0 | 0 | 0
4076 | PURBA MEDINIPUR | Tamluk Division | KAPASDA & IT'S ADJOINING MOUJAS PWSS , SM/13692 | New | Material Requisition To Resource Division | 2963/TD | 12/09/2024 | 0 | Resource Division | 9.09 | 0 | 0 | 0
4077 | PURBA MEDINIPUR | Tamluk Division | KAPASDA & IT'S ADJOINING MOUJAS PWSS , SM/13692 | New | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (845 nos) under JJM with allied work of KAPASDA PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte | 554/TD | 12/05/2023 | 180 | PATHIK PABAN NANDI | 453.18 | 136.77 | 30.18 | 50
4078 | PURBA MEDINIPUR | Midnapore Mechanical | KAPASDA & IT'S ADJOINING MOUJAS PWSS , SM/13692 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
4079 | PURBA MEDINIPUR | Tamluk Division | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS , SM/14456 | New | Material Requisition To Resource Division | 2694/TD | 06/02/2023 | 0 | Resource Division | 26.6 | 0 | 0 | 0
4080 | PURBA MEDINIPUR | Tamluk Division | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS , SM/14456 | New | Material Requisition To Resource Division | 105/TD | 05/01/2024 | 0 | Resource Division | 4.14 | 0 | 0 | 0
4081 | PURBA MEDINIPUR | Midnapore Mechanical | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS , SM/14456 | New | Electric Quotation for GHATASHALA Water Supply Scheme T/W-I, (Ref. ID-204135822) | BP-2023-24-359 | 24/11/2023 | 0 | WBSEDCL | 4.07 | 0 | 0 | 0
4082 | PURBA MEDINIPUR | Midnapore Mechanical | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS , SM/14456 | New | Quotation for new service connection at T/W-2 of Ghantashala ws scheme under MMD PHE DTE, Ref Application no-2004577503, Con ID-204203251 | BP-2023-24-651 | 09/02/2024 | 0 | WBSEDCL | 8.39 | 0 | 0 | 0
4083 | PURBA MEDINIPUR | Midnapore Mechanical | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS , SM/14456 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GHANTA SHALA AND IT'S ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 593/W/MMD | 20/03/2023 | 713 | ASHUTOSH DAS & CO. | 21.53 | 0 | 0 | 80
4084 | PURBA MEDINIPUR | Tamluk Division | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS , SM/14456 | New | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (672 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of GHANTA SHALA PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. | 852/TD | 31/05/2023 | 940 | GHOSH CONSTRUCTION | 288.84 | 184.54 | 63.89 | 75
4085 | PURBA MEDINIPUR | Tamluk Division | CHISTIPUR AND ADJOINING MOUJAS , SM/14672 | New | Material Requisition To Resource Division | 2994/TD | 27/02/2023 | 0 | Resource Division | 17.01 | 0 | 0 | 0
4086 | PURBA MEDINIPUR | Tamluk Division | CHISTIPUR AND ADJOINING MOUJAS , SM/14672 | New | Schedule for Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Chistipur PWSS at Patashpur-I Block under Tamluk Division, PHE Dte. | 2086/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4087 | PURBA MEDINIPUR | Midnapore Mechanical | CHISTIPUR AND ADJOINING MOUJAS , SM/14672 | New | Quotation Bill for New Service connection at T/W NO-II Of CHISTIPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835430/QUOT/03 DT. 26-07-2024 Application NO- 2004835430 MEMO NO: AMR/PHE/280 DT.26/7/2024 Application type-New connection Consumer Id- 204365756 | BP-2024-25-540 | 07/08/2024 | 0 | WBSEDCL | 5.03 | 0 | 0 | 0
4088 | PURBA MEDINIPUR | Midnapore Mechanical | CHISTIPUR AND ADJOINING MOUJAS , SM/14672 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHISTIPUR AND ITS ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 949/W/MMD | 28/03/2023 | 887 | M/S B.M. ELECTRICAL | 22.78 | 0 | 0 | 62
4089 | PURBA MEDINIPUR | Tamluk Division | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS , SM/13854 | New | Material Requisition To Resource Division | 2396/TD | 16/01/2023 | 0 | Resource Division | 35.66 | 0 | 0 | 0
4090 | PURBA MEDINIPUR | Midnapore Mechanical | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS , SM/13854 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAGURAN JALPAI AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 596/W/MMD | 20/03/2023 | 712 | T.S.CONSTRUCTION | 22.75 | 0 | 0 | 51
4091 | PURBA MEDINIPUR | Tamluk Division | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS , SM/13854 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Baguran Jalpai PWSS at Contai-I Block under Tamluk Division, PHE Dte. | 2427/TD | 30/07/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 100
4092 | PURBA MEDINIPUR | Tamluk Division | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS , SM/13854 | New | Material Requisition To Resource Division | 2948/TD | 12/09/2024 | 0 | Resource Division | 8.06 | 0 | 0 | 0
4093 | PURBA MEDINIPUR | Midnapore Mechanical | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS , SM/13854 | New | Quotation Bill for New Service connection at T/W NO-I Of BAGURANJALPAI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2004689899/QUOT/03 DT. 19-04-2024 Application NO- 2004689899 Application type-New connection Consumer Id- 204279763 | BP-2024-25-111 | 06/05/2024 | 0 | WBSEDCL | 3.63 | 0 | 0 | 0
4094 | PURBA MEDINIPUR | Tamluk Division | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS , SM/13854 | New | Shifting of 11kv HT Line (Junput feeder) at BAGURAN JALPAI WS SCHEME, BLOCK-Contai-1,CCC-CONTAI. Ref memono.-CD-322 Dated-14.05.2024 Ref. ID-860299651 Application ID-100000107869 | BP-2024-25-142 | 27/05/2024 | 0 | WBSEDCL | 2.06 | 0 | 0 | 0
4095 | PURBA MEDINIPUR | Tamluk Division | NONAKOURDA AND IT'S ADJOINING MOUJAS , SM/13857 | New | Material Requisition To Resource Division | 2997/TD | 27/02/2023 | 0 | Resource Division | 8.93 | 0 | 0 | 0
4096 | PURBA MEDINIPUR | Midnapore Mechanical | NONAKOURDA AND IT'S ADJOINING MOUJAS , SM/13857 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NONAKOURDA and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 552/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 21.62 | 0 | 0 | 55
4097 | PURBA MEDINIPUR | Tamluk Division | NONAKOURDA AND IT'S ADJOINING MOUJAS , SM/13857 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Nonakourda PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | 2068/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4098 | PURBA MEDINIPUR | Tamluk Division | NONAKOURDA AND IT'S ADJOINING MOUJAS , SM/13857 | New | Material Requisition To Resource Division | 1661/TD | 29/04/2024 | 0 | Resource Division | 6.27 | 0 | 0 | 0
4099 | PURBA MEDINIPUR | Midnapore Mechanical | NONAKOURDA AND IT'S ADJOINING MOUJAS , SM/13857 | New | Quotation Bill for New Service connection at T/W NO-II Of Nonakourda W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760157/QUOT/03 DT. 04-06-2024 Application NO- 2004760157 Application type-New connection Consumer Id- 204322028 | BP-2024-25-288 | 18/06/2024 | 0 | WBSEDCL | 3.23 | 0 | 0 | 0
4100 | PURBA MEDINIPUR | Tamluk Division | NONAKOURDA AND IT'S ADJOINING MOUJAS , SM/13857 | New | Tube well, Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1018 nos) under JJM with allied work for Nonakourda- PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 2684/TD | 16/10/2023 | 713 | RELIABLE CONSTRUCTIONS | 352.4 | 62.22 | 18.33 | 30
4101 | PURBA MEDINIPUR | Tamluk Division | BARAGECHA AND ADJOINING MOUJAS PWSS , SM/13885 | New | Material Requisition To Resource Division | 2469/TD | 16/01/2023 | 0 | Resource Division | 54.65 | 0 | 0 | 0
4102 | PURBA MEDINIPUR | Tamluk Division | BARAGECHA AND ADJOINING MOUJAS PWSS , SM/13885 | New | Material Requisition To Resource Division | 97//TD | 05/01/2024 | 0 | Resource Division | 4.84 | 0 | 0 | 0
4103 | PURBA MEDINIPUR | Midnapore Mechanical | BARAGECHA AND ADJOINING MOUJAS PWSS , SM/13885 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARAGECHA and ADJOINING MOUJAS, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 547/W/MMD | 20/03/2023 | 896 | DEBJYOTI BASU | 21.58 | 6.57 | 30.46 | 40
4104 | PURBA MEDINIPUR | Tamluk Division | BARAGECHA AND ADJOINING MOUJAS PWSS , SM/13885 | New | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (785 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of BARAGECHA PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 458/TD | 04/05/2023 | 900 | TAPAS SANTRA | 308.25 | 12.73 | 4.13 | 50
4105 | PURBA MEDINIPUR | Tamluk Division | UTTAR SAUTANCHAK Piped Water Supply Scheme. , SM/14741 | New | Material Requisition To Resource Division | 2674/TD | 06/02/2023 | 0 | Resource Division | 13.79 | 0 | 0 | 0
4106 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR SAUTANCHAK Piped Water Supply Scheme. , SM/14741 | New | New service connection at Uttar Sautanchak water supply scheme tube well no.-II Tamluk CCC Block-Tamluk Application No.-2004785533 Consumer ID.-204336033 Date.-21-06-2024 | BP-2024-25-356 | 01/07/2024 | 0 | WBSEDCL | 2.93 | 0 | 0 | 0
4107 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR SAUTANCHAK Piped Water Supply Scheme. , SM/14741 | New | Quotation bill for Uttat Sautanchak Water Supply scheme H/W site. Quotation Bill Date.-20/03/2024 Tamluk Block Tamluk CCC Application No.-2004648593 Ref. ID-204250592 | BP-2023-24-919 | 28/03/2024 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
4108 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR SAUTANCHAK Piped Water Supply Scheme. , SM/14741 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR SAUTANCHAK PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 946/W/MMD | 28/03/2023 | 719 | M/S. S.R. ENTERPRISE | 21.55 | 12.49 | 57.97 | 75
4109 | PURBA MEDINIPUR | Tamluk Division | UTTAR SAUTANCHAK Piped Water Supply Scheme. , SM/14741 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Boundary Wall, Providing Functional Household Tap Connection (1277 Nos), including 2 years Operation & Maintenance For Satkalua, Uttar Sautanchak, Pipe Water Supply Scheme within TAMLUK Block Under Tamluk Division PHE Dte. | 449/TD | 04/05/2023 | 698 | TARUN KOLEY | 549.23 | 93.52 | 39.25 | 75
4110 | PURBA MEDINIPUR | Tamluk Division | PURBA NUKHA AND ADJOINING MOUJAS , SM/14742 | New | Material Requisition To Resource Division | 3009/TD | 27/02/2023 | 0 | Resource Division | 27.4 | 0 | 0 | 0
4111 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA NUKHA AND ADJOINING MOUJAS , SM/14742 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA NUKHA AND IT'S ADJOINING MOUJAS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 598/W/MMD | 20/03/2023 | 180 | M/S. JIT ENTERPRISE | 23.7 | 11.62 | 49.04 | 35
4112 | PURBA MEDINIPUR | Tamluk Division | PURBA NUKHA AND ADJOINING MOUJAS , SM/14742 | New | Sinking of Big dia Tube Well , Laying Rising Main,Laying distribution pipe line, Pump House , Boundary Wall, Soil investigation , 350 Cum OHR (Intze type with pile foundation) and Accommodate FHTC 2344 nos including 02(Two) Years Operation & Maintanance for Two years including supply of all labour & materials with allied work under JJM for Purbanukha and Adjoining Moujas Piped Water Supply Scheme under Tamluk Block withen Tamluk Sub-Division under Tamluk Division, PHE Dte | 1567/TD | 19/07/2023 | 180 | TARUN KOLEY | 549.36 | 145.4 | 26.47 | 65
4113 | PURBA MEDINIPUR | Tamluk Division | PURBA NUKHA AND ADJOINING MOUJAS , SM/14742 | New | Payment to WBSEDCL for Shifting of LT line of Purba Nukha PWSS | BP-2023-24-937 | 06/03/2024 | 0 | WBSEDCL | 2.98 | 0 | 0 | 0
4114 | PURBA MEDINIPUR | Midnapore Mechanical | PURBA NUKHA AND ADJOINING MOUJAS , SM/14742 | New | Purbaanukha W/S scheme H/W site Application No.-2004603682 Ref.-204218679 | BP-2023-24-748 | 27/02/2024 | 0 | WBSEDCL | 3.39 | 0 | 0 | 0
4115 | PURBA MEDINIPUR | Tamluk Division | PURBA NUKHA AND ADJOINING MOUJAS , SM/14742 | New | Additional Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, bearing vehicle no-WB 29C 2260 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 01.08.2024 to 31.01.2025.(06 Months) | 1110/TSD | 31/07/2024 | 184 | KISHORE KUMAR SEN | 0.87 | 1.85 | 211.45 | 80
4116 | PURBA MEDINIPUR | Tamluk Division | PURBA NUKHA AND ADJOINING MOUJAS , SM/14742 | New | Continuation work order for Additional Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 01.02.2025 to 31.07.2025.(06 Months) | 222/TSD | 28/01/2025 | 181 | KISHORE KUMAR SEN | 0.86 | 0 | 0 | 0
4117 | PURBA MEDINIPUR | Midnapore Mechanical | JHAUGERYA PIPED WATER SUPPLY SCHEME. , SM/15842 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at JHAUGERYA PIPED WATER SUPPLY SCHEME in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1215/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 12.05 | 0 | 0 | 0
4118 | PURBA MEDINIPUR | Tamluk Division | JHAUGERYA PIPED WATER SUPPLY SCHEME. , SM/15842 | New | Material Requisition To Resource Division | 3016/TD | 27/02/2023 | 0 | Resource Division | 15.15 | 0 | 0 | 0
4119 | PURBA MEDINIPUR | Tamluk Division | JHAUGERYA PIPED WATER SUPPLY SCHEME. , SM/15842 | New | Material Requisition To Resource Division | 124/TD | 05/01/2024 | 0 | Resource Division | 0.97 | 0 | 0 | 0
4120 | PURBA MEDINIPUR | Tamluk Division | JHAUGERYA PIPED WATER SUPPLY SCHEME. , SM/15842 | New | Quotation Bill for New Service connection at T/W NO-I Of JHAUGERIA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004966048/QUOT/03 DT. 22-11-2024 Application NO- 2004966048 Application type-New connection Consumer Id- 204446057 |  | 16/12/2024 | 0 | WBSEDCL | 2.54 | 0 | 0 | 0
4121 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II , SM/15843 | Augmentation | Material Requisition To Resource Division | 2082/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0 | 0
4122 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II , SM/15843 | Augmentation | Material Requisition To Resource Division | 3011/TD | 29/11/2023 | 0 | Resource Division | 1.47 | 0 | 0 | 0
4123 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II , SM/15843 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR & Accommodate FHTC ( 238 Nos) under JJM with allied work for KANPUR (Z-II) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 2819/TD | 08/11/2023 | 180 | BASANTA KUMAR MAITY | 278.75 | 80.94 | 29.04 | 35
4124 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II , SM/15843 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- II ) | 1058/TD | 18/08/2022 | 20 | ASTER CONSULTANCY | 3.6 | 3.06 | 100 | 100
4125 | PURBA MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II , SM/15843 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT ZONE-2, TW-2 OF KANPUR WS SCHEME UNDER MMD PHE DTE,BLOCK-RAMNAGAR-II, DIGHA CCC APPLCATION NO-2004746438, CON ID-204313992 | BP-2024-25-252 | 06/06/2024 | 0 | WBSEDCL | 6.19 | 0 | 0 | 0
4126 | PURBA MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II , SM/15843 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 0 | 34
4127 | PURBA MEDINIPUR | Central Drilling | AMRITBERYA AND ADJOINING MOUJAS , SM/15511 | New | : Providing drilling crew and other allied works for construction of Tube Well ( 200mm X150mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Amrit Berya W/S Scheme (T/W-II) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 58/CDD | 06/04/2023 | 30 | MENAKA ENTERPRISE | 16.22 | 0 | 0 | 0
4128 | PURBA MEDINIPUR | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS , SM/15511 | New | Material Requisition To Resource Division | 2984/TD | 27/02/2023 | 0 | Resource Division | 27.61 | 0 | 0 | 0
4129 | PURBA MEDINIPUR | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS , SM/15511 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Amritberya PWSS at Mahisadal Block under Tamluk Division, PHE Dte. | 373/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 0
4130 | PURBA MEDINIPUR | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS , SM/15511 | New | Material Requisition To Resource Division | 77/TD | 05/01/2024 | 0 | Resource Division | 21.19 | 0 | 0 | 0
4131 | PURBA MEDINIPUR | Midnapore Mechanical | AMRITBERYA AND ADJOINING MOUJAS , SM/15511 | New | Quotation of new service connection at Amritberiya w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No. 2004714253, Ref ID 204295221) | BP-2024-25-243 | 06/06/2024 | 0 | WBSEDCL | 4.8 | 0 | 0 | 0
4132 | PURBA MEDINIPUR | Midnapore Mechanical | AMRITBERYA AND ADJOINING MOUJAS , SM/15511 | New | Quotation for new service connection at Amritbera w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No. 2004760250, Ref ID 204322037) | BP-2024-25-362 | 01/07/2024 | 0 | WBSEDCL | 5.48 | 0 | 0 | 0
4133 | PURBA MEDINIPUR | Midnapore Mechanical | AMRITBERYA AND ADJOINING MOUJAS , SM/15511 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMRITBERYA and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1270/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 27.04 | 21.2 | 78.43 | 60
4134 | PURBA MEDINIPUR | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS , SM/15511 | New | Ground water based Amritberya Water Supply Scheme by providing Sinking of Tube well, Construction of Pump House, Boundary Wall, Sub-soil Investigation, Construction of OHR (450 cum), Laying Rising main, Laying of Distribution pipe line, FHTC work and 'Operation & Maintenance' within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1688/TD | 26/07/2023 | 583 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 580.82 | 341.56 | 58.81 | 40
4135 | PURBA MEDINIPUR | Midnapore Mechanical | AMRITBERYA AND ADJOINING MOUJAS , SM/15511 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
4136 | PURBA MEDINIPUR | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS , SM/15511 | New | Continuation work order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2025 to 31/12/2025. (12 Months) | 1285/HSD, | 27/12/2024 | 365 | SANTANU PATTANAYAK | 1.5 | 1.2 | 80.09 | 40
4137 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09277 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Rasikachak Water Supply Scheme under Tamluk Division, PHE Dte. | 1194/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.62 | 4.62 | 100 | 100
4138 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09277 | Augmentation | Piling work and pond crossing of Rejuvenation & Retrofitting of ground water based Rashikachak PWSS & its adjoining mouzas within Chandipur Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2344/TD | 10/01/2023 | 25 | JAGANNATH MAKAR | 29.39 | 28.47 | 96.89 | 0
4139 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09277 | Augmentation | Rejuvenation & Retrofitting of ground water based Rashikachak PWSS & its adjoining moujas within Chandipur Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | 432/TD | 27/05/2022 | 90 | JAGANNATH MAKAR | 234.25 | 229.76 | 98.09 | 95
4140 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09277 | Augmentation | Material Requisition To Resource Division | 1095/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
4141 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09277 | Augmentation | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | 2695/TD | 22/08/2024 | 30 | HARIPADA PATTANAYAK | 38.26 | 0 | 0 | 0
4142 | PURBA MEDINIPUR | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS , SM/16200 | New | Material Requisition To Resource Division | 3015/TD | 27/02/2023 | 0 | Resource Division | 16.09 | 0 | 0 | 0
4143 | PURBA MEDINIPUR | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS , SM/16200 | New | Laying distribution pipe line, Boundary Wall & Rising main pipe line under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | 257/TD | 19/04/2023 | 60 | SOUMYA ENTERPRISE | 49.45 | 20.51 | 41.47 | 45
4144 | PURBA MEDINIPUR | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS , SM/16200 | New | Laying distribution pipe line, Pump House , & Accommodate FHTC (147 nos) under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | 256/TD | 19/04/2023 | 857 | CHANDIMATA CONSTRUCTION | 84.7 | 26.51 | 31.3 | 70
4145 | PURBA MEDINIPUR | Central Drilling | BANCHBERA AND ITS ADJOINING MOUJAS PWSS , SM/16200 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 57.54 | 220.21 | 11
4146 | PURBA MEDINIPUR | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS , SM/16200 | New | Soil investigation, 50 cum OHR ( type with pile foundation) under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-C) | 1085/TD | 08/06/2023 | 180 | GOUTAM CONSTRUCTION | 38.56 | 31.16 | 80.79 | 50
4147 | PURBA MEDINIPUR | Tamluk Division | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (1180 NOS) AND LAYNE OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XI, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA M , SM/16469 | Retrofitting | Balance work for Retrofitting to accommodate FHTC (990 nos.) and laying of left-out portion UPVC pipeline due to uncovered area at different nodel point under JJM in Surface water based Water Supply Scheme for Zone-XI, Block- Kolaghat in the District of Purba Medinipur. (Phase-III) [PART-A) | 512/TD | 11/05/2023 | 40 | TAPAS SANTRA | 81.84 | 69.61 | 85.05 | 85
4148 | PURBA MEDINIPUR | Tamluk Division | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (1180 NOS) AND LAYNE OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XI, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA M , SM/16469 | Retrofitting | Balance work for Retrofitting to accommodate FHTC (190 Nos) under JJM in Surface water Based Water Supply Scheme for Zone-XI Block - Kolaghat in the District of Purba Medinipur.(Phase-III)[PART-B] | 252/TD | 19/04/2023 | 20 | MISHRA ENTERPRISE | 9.69 | 9.69 | 100 | 100
4149 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V , SM/16295 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme (Zone-V) under Tamluk Division, PHE Dte. | 1858/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 3.13 | 100 | 100
4150 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V , SM/16295 | Augmentation | Material Requisition To Resource Division | 2997/TD | 29/11/2023 | 0 | Resource Division | 1.13 | 0 | 0 | 0
4151 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V , SM/16295 | Augmentation | Material Requisition To Resource Division | 2067/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0 | 0
4152 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V , SM/16295 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 184 Nos) under JJM with allied work for KANPUR (Zone-V) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | 1731/TD | 31/07/2023 | 610 | ONKAR ENTERPRISE | 284.7 | 166.43 | 58.46 | 5
4153 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V , SM/16295 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kanpur Zone-V PWSS at Ramnagar - II Block under Tamluk Division,PHE Dte. | 190/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4154 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V , SM/16295 | Augmentation | Payment to WBSEDCL for Shifting of 33 KV FEEDER HT Line at Sabitrapur for Kanpur Water Supply Scheme for Zone-V under Tamluk Division, PHE Dte. | BP-2023-24-957 | 14/03/2024 | 0 | WBSEDCL | 3.05 | 0 | 0 | 0
4155 | PURBA MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V , SM/16295 | Augmentation | Kanpur W/S scheme TW no.-II, Z-V Ref.-204156068 Application ID-2004521673 | BP-2023-24-445 | 19/12/2023 | 0 | WBSEDCL | 2.57 | 0 | 0 | 0
4156 | PURBA MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V , SM/16295 | Augmentation | Quotation for new service connection at TW-I,ZONE-V of KANPUR WS SCHEME under MMD,PHE Dte, Block-Ramnagar-II, DIGHA CCC, Application no-2004644488, CON ID-204246837 | BP-2023-24-913 | 28/03/2024 | 0 | WBSEDCL | 4.81 | 0 | 0 | 0
4157 | PURBA MEDINIPUR | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V , SM/16295 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 0 | 34
4158 | PURBA MEDINIPUR | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V , SM/16295 | Augmentation | Drum Sheet walling, road restoration for distribution pipe line ( for FHTC) & Accommodate FHTC (215 Nos) under JJM with allied work for KANPUR (Zone-V) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 491/TD | 06/02/2025 | 120 | GHOSH CONSTRUCTION | 87.4 | 0 | 0 | 80
4159 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bhagabanpur, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16875 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at MAHAMMADPUR and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 649/HESD | 08/07/2024 | 15 | SOUMEN ELECTRIC | 1.94 | 0 | 0 | 100
4160 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bhagabanpur, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16875 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4161 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Kapasharia PWSS in the District of Purba Medinipur under JJM programme. , SM/16660 | Augmentation | Rejuvenation of Electro-Mechanical components of Kapasharia PWSS in the District of Purba Medinipur under JJM programme. | 1083/W/MMD | 30/03/2023 | 180 | S.S.GHORAI | 11.86 | 0 | 0 | 0
4162 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chirulia Chalta PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16884 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
4163 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Chirulia Chalta PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16884 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4164 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bagmari (Potashpur - II) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16890 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
4165 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bagmari (Potashpur - II) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16890 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4166 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bankiput PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16859 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
4167 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bankiput PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16859 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4168 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bamunia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16868 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
4169 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bamunia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16868 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4170 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Mahammadpur (Nandigram) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17717 | Solarisation | Solarization of grid connected pumping installation at Mahammadpur (Nandigram) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1024/W/MMD | 29/03/2023 | 180 | SUBHASIS ROY | 6.26 | 0 | 0 | 0
4171 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Srirampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17873 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4172 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17761 | Solarisation | Solarization of grid connected pumping installation at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1010/W/MMD | 29/03/2023 | 180 | MEGA SOLAR ENERGY | 6.26 | 4.66 | 74.47 | 50
4173 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17761 | Solarisation | Quotation bill for application fees for NET BILLING for solar power plant of 10KWp at Dwariberia w/s scheme,Block-sutahata in the Dist. of Purba Medinipur under MMD,PHE,Dte. Name of C.C.C.-Chaitanyapur Application no-2004837078 Consumer ID-224041892 Quotation Date-25/07/2024 Quotation Due Date-90days from the date of issue | BP-2024-25-550 | 07/08/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
4174 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Gopalpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17800 | Solarisation | Solarization of grid connected pumping installation at Gopalpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1013/W/MMD | 29/03/2023 | 702 | P.K.ENGINEERING | 6.26 | 0 | 0 | 80
4175 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Khejurberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17878 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
4176 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Khejurberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17878 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4177 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Palduhi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17909 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
4178 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Palduhi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17909 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4179 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Monoharpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17911 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
4180 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Monoharpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17911 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4181 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chaitanyapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17361 | Solarisation | Solarization of grid connected pumping installation at Chaitanyapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 746/W/MMD | 23/03/2023 | 708 | M/S. JIT ENTERPRISE | 6.26 | 0 | 0 | 0
4182 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Guria PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17853 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
4183 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Guria PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17853 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4184 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kapasharia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17860 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
4185 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kapasharia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17860 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4186 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Uttar Sonamui PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17747 | Solarisation | Solarization of grid connected pumping installation at Uttar Sonamui PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1041/W/MMD | 29/03/2023 | 180 | SOUMEN ELECTRIC | 6.26 | 4.89 | 78.03 | 30
4187 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Bargodagoda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17372 | Solarisation | Solarization of grid connected pumping installation at Bargodagoda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 736/W/MMD | 23/03/2023 | 180 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
4188 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Ranisai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17920 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
4189 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Ranisai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17920 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4190 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mandar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17857 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
4191 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mandar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17857 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4192 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Keshabpur Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17791 | Solarisation | Solarization of grid connected pumping installation at Keshabpur Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1019/W/MMD | 29/03/2023 | 702 | P.K.ENGINEERING | 6.26 | 0 | 0 | 80
4193 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Manikpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17833 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
4194 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Manikpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17833 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4195 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Uttar Sonamui PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17885 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4196 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Uttar Charaikhea PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17893 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
4197 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Uttar Charaikhea PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17893 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4198 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17901 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
4199 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17901 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4200 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Paschimbatya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17877 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
4201 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Paschimbatya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17877 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4202 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Gobra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17880 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
4203 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Gobra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17880 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4204 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kumirda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17816 | Solarisation | Solarization of grid connected pumping installation at Kumirda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1006/W/MMD | 29/03/2023 | 180 | AMITAVA CHAKRABORTY | 6.26 | 4.85 | 77.48 | 35
4205 | PURBA MEDINIPUR | Tamluk Division | FULESHWAR AND ADJOINING MOUJAS PWSS , SM/12500 | New | Material Requisition To Resource Division | 2403/TD | 16/01/2023 | 0 | Resource Division | 34.22 | 0 | 0 | 0
4206 | PURBA MEDINIPUR | Midnapore Mechanical | FULESHWAR AND ADJOINING MOUJAS PWSS , SM/12500 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for FULESHWAR and ADJOINING MOUJAS, Block - Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 508/W/MMD | 20/03/2023 | 180 | M/S DILIP MITRA | 22.77 | 9.98 | 43.83 | 60
4207 | PURBA MEDINIPUR | Tamluk Division | FULESHWAR AND ADJOINING MOUJAS PWSS , SM/12500 | New | Material Requisition To Resource Division | 2958/TD | 12/09/2024 | 0 | Resource Division | 7.81 | 0 | 0 | 0
4208 | PURBA MEDINIPUR | Tamluk Division | FULESHWAR AND ADJOINING MOUJAS PWSS , SM/12500 | New | Bill for payment to WBSEDCL for New Pipe Construction at Panchgachia new Sawsahan for Fuleshwar PWSS under Tamluk Division, PHE Dte. | BP-2023-24-962 | 14/03/2024 | 0 | WBSEDCL | 0.27 | 0 | 0 | 0
4209 | PURBA MEDINIPUR | Midnapore Mechanical | FULESHWAR AND ADJOINING MOUJAS PWSS , SM/12500 | New | Quotation bill for Fuleswar W/S scheme T/W. No.-I, P.S- Contai, Block.-Contai-II Application No.-2004626938 Ref ID.-204233452 Date.-01/03/2024 Quotation Date.-01-03-2024 Mukundapur CCC | BP-2023-24-808 | 11/03/2024 | 0 | WBSEDCL | 3.24 | 0 | 0 | 0
4210 | PURBA MEDINIPUR | Midnapore Mechanical | FULESHWAR AND ADJOINING MOUJAS PWSS , SM/12500 | New | Quotation Bill for New Service connection at T/W NO-II Of FULESWAR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004767027/QUOT/03 DT. 07-06-2024 Application NO- 2004767027 Application type-New connection Consumer Id- 204325420 | BP-2024-25-301 | 18/06/2024 | 0 | WBSEDCL | 12.7 | 0 | 0 | 0
4211 | PURBA MEDINIPUR | Tamluk Division | FULESHWAR AND ADJOINING MOUJAS PWSS , SM/12500 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 167.92 | 33.56 | 51
4212 | PURBA MEDINIPUR | Tamluk Division | SHOULA BHERI AND ADJOINING MOUJAS PWSS , SM/12496 | New | Material Requisition To Resource Division | 2442/TD | 16/01/2023 | 0 | Resource Division | 19.52 | 0 | 0 | 0
4213 | PURBA MEDINIPUR | Midnapore Mechanical | SHOULA BHERI AND ADJOINING MOUJAS PWSS , SM/12496 | New | Quotation Bill for New Service connection at T/W NO-II Of SHOULABHERI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004790382/QUOT/03 DT. 24-06-2024 MEMO NO: AMR/PHE/212 DT. 24-06-2024 Application NO- 2004790382 Application type-New connection Consumer Id- 204339027 | BP-2024-25-374 | 08/07/2024 | 0 | WBSEDCL | 2.17 | 0 | 0 | 0
4214 | PURBA MEDINIPUR | Midnapore Mechanical | SHOULA BHERI AND ADJOINING MOUJAS PWSS , SM/12496 | New | Quotation Bill for New Service connection at T/W NO-I Of SHOULABHERI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004790353/QUOT/03 DT. 24-06-2024 MEMO NO: AMR/PHE/211 DT. 24-06-2024 Application NO- 2004790353 Application type-New connection Consumer Id- 204339004 | BP-2024-25-375 | 08/07/2024 | 0 | WBSEDCL | 5.65 | 0 | 0 | 0
4215 | PURBA MEDINIPUR | Midnapore Mechanical | SHOULA BHERI AND ADJOINING MOUJAS PWSS , SM/12496 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SHOULA BHERI and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 529/W/MMD | 20/03/2023 | 889 | BHABANI PRASAD MANNA | 25.26 | 0 | 0 | 50
4216 | PURBA MEDINIPUR | Tamluk Division | SHOULA BHERI AND ADJOINING MOUJAS PWSS , SM/12496 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 255.59 | 33.96 | 51
4217 | PURBA MEDINIPUR | Tamluk Division | JAHANABAD AND IT'S ADJOINING MOUJAS , SM/12813 | New | Material Requisition To Resource Division | 2709/TD | 06/02/2023 | 0 | Resource Division | 14.75 | 0 | 0 | 0
4218 | PURBA MEDINIPUR | Central Drilling | JAHANABAD AND IT'S ADJOINING MOUJAS , SM/12813 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Jahanabad W/S Scheme (T/W-I), Khejuri-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 851/CDD | 10/07/2023 | 300 | UNIVERSAL ENTERPRISES | 15.71 | 13.39 | 100 | 100
4219 | PURBA MEDINIPUR | Tamluk Division | JAHANABAD AND IT'S ADJOINING MOUJAS , SM/12813 | New | Material Requisition To Resource Division | 2959/TD | 12/09/2024 | 0 | Resource Division | 14.85 | 0 | 0 | 0
4220 | PURBA MEDINIPUR | Midnapore Mechanical | JAHANABAD AND IT'S ADJOINING MOUJAS , SM/12813 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JAHANABAD and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1267/W/MMD | 04/05/2023 | 697 | MENAKA ENTERPRISE | 25.14 | 0 | 0 | 0
4221 | PURBA MEDINIPUR | Tamluk Division | JAHANABAD AND IT'S ADJOINING MOUJAS , SM/12813 | New | Sinking of Tube Well ,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (5341Nos), including 2 years Operation & Maintenance For PATNA, Jahanabad, Pipe water supply Scheme within Khejuri-I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 1413/TD | 12/07/2023 | 720 | GEE BEE NIRMAN CO PVT LTD. | 1697.21 | 327.94 | 40.93 | 60
4222 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I and Potashpur-I Development Block under Purba Medinipur District. , SM/10618 | New | Material Requisition To Resource Division | 2896/TD | 21/11/2023 | 0 | Resource Division | 14.27 | 0 | 0 | 0
4223 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I and Potashpur-I Development Block under Purba Medinipur District. , SM/10618 | New | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0 | 0
4224 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I and Potashpur-I Development Block under Purba Medinipur District. , SM/10618 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 359.75 | 63.22 | 70
4225 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I and Potashpur-I Development Block under Purba Medinipur District. , SM/10618 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 92.45 | 23.47 | 48
4226 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bathuary Piped Water Supply Scheme , SM/07099 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bathuary PWSS Block-Egra-II in the District of Purba Medinipur. | 2661/TD | 11/01/2021 | 60 | SATYABRATA BHAUMIK | 96.25 | 53.35 | 100 | 100
4227 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bathuary Piped Water Supply Scheme , SM/07099 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bathuari W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. | 141/W | 22/07/2021 | 0 | SATYABRATA BHAUMIK | 22.86 | 0 | 0 | 0
4228 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bathuary Piped Water Supply Scheme , SM/07099 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bathuari W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. | 981/W | 25/03/2021 | 0 | SATYABRATA BHAUMIK | 20.03 | 0 | 0 | 0
4229 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bathuary Piped Water Supply Scheme , SM/07099 | Retrofitting | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | 895/TD | 07/03/2024 | 300 | MISHRA ENTERPRISE | 9.53 | 2.67 | 100 | 65
4230 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Badhia Piped Water Supply Scheme , SM/07102 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Badhia PWSS Block Ramnagar-I in the District of Purba Medinipur. | 2636/TD | 05/01/2021 | 60 | AJIT KUMAR SOM | 96.85 | 21.21 | 100 | 100
4231 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Badhia Piped Water Supply Scheme , SM/07102 | Retrofitting | Retrofitting to accomodate FHTC under JJM Badhia W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. | 978/W | 26/03/2021 | 0 | AJIT KUMAR SOM | 54.53 | 0 | 0 | 0
4232 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Badhia Piped Water Supply Scheme , SM/07102 | Retrofitting | Retrofitting to accomodate FHTC under JJM Badhia W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. | 230/W | 07/09/2021 | 0 | AJIT KUMAR SOM | 21.1 | 0 | 0 | 0
4233 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Badhia Piped Water Supply Scheme , SM/07102 | Retrofitting | Preparation and submission of Revised Detailed Project Report for Retrofitting to accommodate FHTC under JJM in BADHIA piped water supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur District. | 144/DSD | 14/05/2025 | 7 | ASTER CONSULTANCY | 2.76 | 0 | 0 | 0
4234 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) , SM/07976 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VII(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | 2779/TD | 29/01/2021 | 120 | TARUN KOLEY | 253.33 | 506.67 | 200.01 | 100
4235 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) , SM/07976 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-I (Balance Work) Block-Kolaghat in the District of Purba Medinipur. | 2821/TD | 05/02/2021 | 100 | M/S A.R. ENTERPRISE | 216.86 | 433.43 | 199.86 | 100
4236 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) , SM/07976 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface water Based Water Supply Scheme for Zone-III(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | 2780/TD | 29/01/2021 | 120 | JAYANTA KUMAR MONDAL | 259.53 | 512.89 | 197.62 | 100
4237 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) , SM/07976 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface water Based Water Supply Scheme for Zone-V(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | 2785/TD | 01/02/2021 | 120 | M/S EL-CON | 241.65 | 450.27 | 199.75 | 100
4238 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) , SM/07976 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface water Based Water Supply Scheme for Zone-IV(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | 2845/TD | 08/02/2021 | 120 | CONCORD ENGINEERING | 267.73 | 375.47 | 140.24 | 100
4239 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chandanpur Piped Water Supply Scheme , SM/07105 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandanpur PWSS Block Ramnagar-I in the District of Purba Medinipur. | 2481/TD | 21/12/2020 | 60 | TAPAS SANTRA | 96.74 | 2.45 | 100 | 100
4240 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chandanpur Piped Water Supply Scheme , SM/07105 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Chandanpur W/S Scheme | 827/W | 03/03/2021 | 0 | TAPAS SANTRA | 16.22 | 0 | 0 | 0
4241 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chandanpur Piped Water Supply Scheme , SM/07105 | Retrofitting | Retrofitting to accomodate FHTC under JJM Chandanpur W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. | 714/W | 09/02/2021 | 0 | TAPAS SANTRA | 78 | 0 | 0 | 0
4242 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chandanpur Piped Water Supply Scheme , SM/07105 | Retrofitting | Preparation and submission of Revised Detailed Project Report for Retrofitting to accommodate FHTC under JJM in CHANDANPUR piped water supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division,Purba Medinipur District. | 147/DSD | 14/05/2025 | 7 | ASTER CONSULTANCY | 2.66 | 0 | 0 | 0
4243 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Silampur W/S Scheme Under Contai-I Block , SM/07479 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Silampur PWSS Block -Contai-I in the District of Purba Medinipur. | 2876/TD | 11/02/2021 | 30 | BASANTA KUMAR MAITY | 77.79 | 21.22 | 100 | 100
4244 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Silampur W/S Scheme Under Contai-I Block , SM/07479 | Retrofitting | Retrofitting to accomodate FHTC under JJM Silampur W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. | 1092/W | 30/03/2021 | 0 | BASANTA KUMAR MAITY | 55.45 | 0 | 0 | 0
4245 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Silampur W/S Scheme Under Contai-I Block , SM/07479 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Silampur PWSS within Contai ¿I Block under Tamluk Division, PHE Dte. |  | 17/03/2021 | 0 | BASANTA KUMAR MAITY | 55.45 | 0 | 0 | 0
4246 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) , SM/07482 | Retrofitting | Retrofitting to accommodate FHTC (520 nos) under JJM in Gholepukuria PWSS (Zone-II) (Phase -II) within Baishnab Chak (JL-136) - (Baishnab Chak Uttar Paschim Para, Baishnab Chak Purba Dakshin Para &Gholepukuria [JL134(P)] - (Jaykhali Paschim Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. ,PART-A | 2753/TD | 27/01/2021 | 25 | ZENITH CONSTRUCTION | 26.93 | 0 | 0 | 100
4247 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) , SM/07482 | Retrofitting | Retrofitting to accommodate FHTC (480 nos) under JJM in Gholepukuria PWSS (Zone-II) (Phase -II) within Gholepukuria [JL-134(P)] - (Purba Dakshin Para & Madhya Jana Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-B | 2754/TD | 27/01/2021 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.38 | 0 | 0 | 100
4248 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) , SM/07482 | Retrofitting | Retrofitting to accomodate FHTC 480 Nos. connection under JJM Gholpukuria Zone - II W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-B) | BP-2021-22-59 | 13/08/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.49 | 0 | 0 | 0
4249 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) , SM/07482 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gholpukuria - II W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  | 12/03/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.88 | 0 | 0 | 0
4250 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) , SM/07482 | Retrofitting | Retrofitting to accomodate FHTC 520 Nos. connection under JJM Gholpukuria Zone - II W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-A) | BP-2021-22-44 | 29/07/2021 | 0 | ZENITH CONSTRUCTION | 3.86 | 0 | 0 | 0
4251 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) , SM/07482 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gholpukuria - II W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) | 1103/W | 30/03/2021 | 0 | ZENITH CONSTRUCTION | 23.02 | 0 | 0 | 0
4252 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) , SM/07482 | Retrofitting | Retrofitting to accomodate FHTC 480 Nos. connection under JJM Gholpukuria Zone - II W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-B) | 1104/W | 30/03/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.88 | 0 | 0 | 0
4253 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- I PWSS under Sahid Matangini Block. , SM/07484 | Retrofitting | Retrofitting to accommodate (175) nos FHTC under JJM of Balarampur & Joyrampur village in Alinan Zone-I PWSS Block- Sahid Matangini under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District . | 1717/TD | 01/02/2022 | 20 | MUKHERJEE ENTERPRISE | 10.37 | 0 | 0 | 100
4254 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- I PWSS under Sahid Matangini Block. , SM/07484 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Alinan Zone-I PWSS Block -Sahid Matangini in the District of Purba Medinipur. | 2819/TD | 05/02/2021 | 45 | TAPAS SANTRA | 97.45 | 193.36 | 200 | 100
4255 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanakpur W/S Scheme Potashpur-I Block , SM/07654 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kanakpur PWSS Block -Potashpur-I in the District of Purba Medinipur. | 2801/TD | 04/02/2021 | 45 | SRIMANTA KUMAR MAITY | 114.41 | 41.4 | 100 | 100
4256 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanakpur W/S Scheme Potashpur-I Block , SM/07654 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Kanakpur Piped Water Supply Scheme | 1085/W | 30/03/2021 | 0 | SRIMANTA KUMAR MAITY | 41.89 | 0 | 0 | 0
4257 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanakpur W/S Scheme Potashpur-I Block , SM/07654 | Retrofitting | Providing Balance FHTC with allied works of Kanakpur mouzas under Kanakpur water supply scheme of Contai Sub Division under Tamluk Division, PHE Dte. Purba Medinipur. | 1301/TD | 13/09/2022 | 30 | THE GODFATHER TRADING COMPANY | 3.52 | 3.51 | 99.87 | 100
4258 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Anurai Water Supply Scheme under Tamluk Division, PHE Dte. | 1184/TD | 02/12/2021 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 8.21 | 6.31 | 100 | 100
4259 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tube well (Additional) Site of Anurai Water Supply Scheme (Mouza - Anurai, JL No. - 439, Plot No. - 1289) within Contai-III & Deshpran Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 1992/TD | 07/03/2022 | 21 | AQUATECH ENGINEER | 12.17 | 11.85 | 100 | 100
4260 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 1st Tube well Site of Anurai Water Supply Scheme (Mouza - Anurai, JL No. - 439, Plot No. - 1407) within Contai-III & Deshpran Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 1991/TD | 07/03/2022 | 21 | AQUATECH ENGINEER | 12.17 | 11.65 | 100 | 100
4261 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Renovation work of Spiral staircase and related works for R.C.C. Over Head Reservoir of capacity 250 Cum at Anurai Mouza within Anurai W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | 493 / CSD | 16/11/2021 | 21 | SUBRATA KUMAR BERA | 2.43 | 2.26 | 100 | 100
4262 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Electric quotation Bill of T/W-III of Anurai water suplly scheme under MMD PHE Dte. under Marishda CCC | 2004006184/QUOT/03 | 30/07/2022 | 365 | WBSEDCL | 0.7 | 0.7 | 100 | 0
4263 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Supply & Delivery of different dia. Sluice Valve for Augmentation of Anurai Water Supply Scheme under Contai Sub-Division, of Tamluk Division, PHE Dte, Purba Medinipur. | 426/TD | 27/05/2022 | 15 | PARTHA CONSTRUCTION | 4.59 | 4.59 | 100 | 100
4264 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Supply and Delivery of Different dia Sluice Valves for Anurai Water Supply Scheme in the District of Purba Medinipur. | 441 / CSD | 20/03/2023 | 15 | KAMAL KUMAR BERA | 0.95 | 0.95 | 100 | 0
4265 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Additional Tube Well (3rd Tube Well) site for Anurai Water Supply Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. | 1088/TD | 25/08/2022 | 40 | ABHIJIT BERA | 5.47 | 5.31 | 100 | 100
4266 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additiona Tube Well (3rd Tube Well) site for Anurai Water Supply Scheme within Deshpran & Contai - III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 843/TD | 20/07/2022 | 30 | ABHIJIT BERA | 3.63 | 3.57 | 100 | 100
4267 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Instalation of display Board at different work site of Augmentation of Anurai- 1 no, Bhajachauli- 1 no, Dhanghara- 1 no, Basudebberiya- 1 no, Shankarpur- 1 no, Mukutshila Zone-II- 1 no. & Chandibhetti- 1 no. PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 810 / CSD | 21/10/2022 | 15 | SAURAV HAZRA | 0.81 | 0.81 | 100 | 100
4268 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Material Requisition To Resource Division | 1265/TD | 13/12/2021 | 0 | Resource Division | 42.96 | 0 | 0 | 0
4269 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Material Requisition To Resource Division | 1729/TD | 02/02/2022 | 0 | Resource Division | 13.95 | 0 | 0 | 0
4270 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-I under Anurai water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | 1861/W/MMD | 22/09/2022 | 120 | SUBHAM ENTERPRISE | 11.67 | 8.29 | 71.03 | 20
4271 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Land Filling & Construction of Approch Road for 3rd TW site of Anurai W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 307/CSD | 27/02/2023 | 15 | ABHIJIT BERA | 1.25 | 1.23 | 98.78 | 0
4272 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Augmentation of Anurai Water Supply Scheme by Providing Laying Distribution System and FHTC in In Contai-III & Deshpran Block Of in the District of Purba Medinipur. | 1639/TD | 19/01/2022 | 1295 | MAHAVIR PUMPS MFG. PVT. LTD. | 391.92 | 332.51 | 84.84 | 90
4273 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Supply & delivery D.I. Specials for Rising main and other allied works for Augmentation of Anurai W/S Scheme within Contai - II & Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | 690 / CSD | 22/09/2022 | 15 | SUBRATA KUMAR BERA | 0.76 | 0 | 0 | 100
4274 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional 3rd Tube well under Anurai water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | 2201/W/MMD | 14/12/2022 | 837 | A G ENTERPRISE | 12.25 | 11.41 | 93.18 | 100
4275 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Rising main and other allied works for Augmentation of Anurai W/S Scheme within Contai - II & Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-A) | 1992/TD | 01/12/2022 | 30 | SUBRATA KUMAR BERA | 4.49 | 0 | 0 | 100
4276 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Repairing of OHR, Pump House no 1, Pump House No. 2 under JJM with allied work of Anurai PWSS within Deshpran Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 2906/TD | 10/09/2024 | 40 | RAI CONSTRUCTION | 12.9 | 0 | 0 | 100
4277 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. , SM/09334 | Augmentation | Laying of Left out Distribution pipe line by HDPE pipes with allied works for providing FHTC for Augmentation of Anurai PWSS within Deshpran Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 2262/CSD | 09/10/2025 | 30 | ANJANI ENTERPRISE | 0.94 | 0 | 0 | 0
4278 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in DONA Zone-I Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. , SM/08755 | Retrofitting | Retrofitting to accomodate FHTC (1897 nos.) under JJM in Dona Zone-I PWSS (Balance Work) Block - Moyna under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.(Phase- II) | 689/TD | 10/09/2021 | 60 | ARABINDA GHOSH | 88.68 | 0 | 0 | 100
4279 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in DONA Zone-I Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. , SM/08755 | Retrofitting | Retrofitting to accomodate FHTC 1125 Nos. connection under JJM under Dona Zone - I W/S Scheme within Moyna Block under Tamluk Division, PHE Dte. (Phase - I) | BP-2021-22-148 | 09/11/2021 | 0 | ARABINDA GHOSH | 21.94 | 0 | 0 | 0
4280 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in DONA Zone-I Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. , SM/08755 | Retrofitting | Retrofitting to accomodate FHTC (1897 nos.) under JJM in Dona Zone-I PWSS (Balance Work) Block - Moyna under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.(Phase- II) | BP-2021-22-391 | 31/03/2022 | 0 | ARABINDA GHOSH | 75.2 | 0 | 0 | 0
4281 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari W/S Scheme Potashpur-II Block (PHASE-II) , SM/08226 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bagmari PWSS Block- Potashpur-II in the District of Purba Medinipur.(Phase-II) | 83/TD | 11/05/2021 | 30 | DAS ENTERPRISE | 88.69 | 115.43 | 130.15 | 100
4282 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Ranisai Piped Water Supply Scheme , SM/07104 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Ranisai PWSS Block Ramnagar-I in the District of Purba Medinipur. | 2480/TD | 21/12/2020 | 60 | TARUN KOLEY | 94.35 | 0 | 0 | 100
4283 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Ranisai Piped Water Supply Scheme , SM/07104 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Ranisai W/S Scheme | 828/W | 02/03/2021 | 0 | TARUN KOLEY | 4.71 | 0 | 0 | 0
4284 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Ranisai Piped Water Supply Scheme , SM/07104 | Retrofitting | Retrofitting to accomodate FHTC under JJM Ranisai W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. | 712/W | 09/02/2021 | 0 | TARUN KOLEY | 80 | 0 | 0 | 0
4285 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Talda Water Supply Scheme under Tamluk Division, PHE Dte. | 1611/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.3 | 3.97 | 100 | 100
4286 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-I) | 1823/TD | 11/02/2022 | 20 | SUBRATA KUMAR BERA | 18.89 | 18.64 | 100 | 100
4287 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-F) | 1820/TD | 11/02/2022 | 20 | M/S. NEW DINDA ENTERPRISE | 23.24 | 23.09 | 100 | 100
4288 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- K) | 1825/TD | 11/02/2022 | 20 | SUKOMAL BERA | 14.52 | 14.44 | 100 | 100
4289 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. . (PART-G) | 1821/TD | 11/02/2022 | 20 | BADAL CHANDRA GOLE | 19.35 | 19.13 | 100 | 100
4290 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-H) | 1822/TD | 11/02/2022 | 20 | GIRI ENTERPRISE | 19.36 | 19.19 | 100 | 100
4291 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- L) | 1826/TD | 11/02/2022 | 20 | ANUPAM CONSTRUCTION | 9.6 | 9.53 | 100 | 100
4292 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Supply and Delivery of different dia. Sluice Valve for Talda piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 437-A/TD | 30/05/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.88 | 7.88 | 100 | 100
4293 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Supply & Delivery of different dia Sluice Valve for Augmentation of Talda,Murisai & Anurai Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. | 278 / CSD | 14/06/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 2.34 | 2.34 | 100 | 100
4294 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- B) | 1816/TD | 11/02/2022 | 45 | M/S SREE DURGA ENTERPRISE | 95.89 | 89.58 | 100 | 100
4295 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-C) | 1817/TD | 11/02/2022 | 40 | AJIT KUMAR SOM | 77.52 | 75.76 | 97.73 | 100
4296 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District.(PART- M) | 1827/TD | 11/02/2022 | 20 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.62 | 9.54 | 99.2 | 100
4297 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-E) | 1819/TD | 11/02/2022 | 20 | SUBHENDU HAZRA | 24.07 | 23.63 | 100 | 100
4298 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Supply and Delivery of different dia. Sluice Valve for Talda piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 451/TD | 31/05/2022 | 20 | RAMASISH ENTERPRISE | 0.24 | 0.24 | 100 | 100
4299 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Instalation of display Board at different work site of Augmentation of Talda- 1 no, Sapai- 1 no, Baghaput- 1 no & Kumirda - 1 no. PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 812 / CSD | 21/10/2022 | 15 | ABHIJIT BERA | 0.46 | 0.46 | 100 | 100
4300 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Material Requisition To Resource Division | 1875/TD | 18/02/2022 | 0 | Resource Division | 17.42 | 0 | 0 | 0
4301 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Material Requisition To Resource Division | 2190/TD | 21/03/2022 | 0 | Resource Division | 39.93 | 0 | 0 | 0
4302 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-D) | 1818/TD | 11/02/2022 | 40 | GIRI CONSTRUCTION | 58.08 | 56.04 | 96.48 | 100
4303 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Providing FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-01) | 287/TD | 05/05/2022 | 60 | DAS CONSTRUCTION | 124.25 | 89.94 | 72.38 | 95
4304 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube well of Talda Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | 607/TD | 16/02/2024 | 20 | KALPANA BUILDERS | 14.29 | 0 | 0 | 0
4305 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell (Mouza - Gonara, JL No. - 187, Plot No. -41)of Talda Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 613/TD | 21/06/2022 | 21 | M/S BISWANATH CONSTRUCTION | 13.38 | 10.35 | 100 | 100
4306 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Repairing Of Pump House ( House No-I & II) and Boundary Wall of Pump House No- II under Augmentation of Talda Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | 485/TD | 10/05/2023 | 30 | M/S SREE DURGA ENTERPRISE | 3.65 | 0 | 0 | 100
4307 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- J) | 1824/TD | 11/02/2022 | 20 | DHANANJOY DAS | 19.35 | 18.93 | 100 | 100
4308 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Laying Distribution System (Nodal-36-89,89-131 & 131-139A,Part) of pipe line and its allied works for Talda water supply scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | 3068/TD | 30/11/2023 | 25 | ACHINTA KUMAR HALDER | 10.08 | 8.42 | 100 | 80
4309 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Quotation Bill for New Service connection at T/W NO-III Of TALDA W/S Scheme under MMD, PHE, Dte. Block- CONTAI-III, WBSEDCL SUPPLY OFFICE: MARISHDA C.C.C. Ref. Memo No- 2004815942/QUOT/03 DT. 10-07-2024 Application NO-2004815942 Application type-New connection Consumer Id- 204353932 | C072443922958 | 29/07/2024 | 0 | WBSEDCL | 3.1 | 0 | 0 | 0
4310 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Talda, Block Contai III, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1412/W/MMD | 02/06/2023 | 718 | SHIVAM ENTERPRISE | 12.63 | 0 | 0 | 90
4311 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Construction of Pump House & Boundary Wall and others allied works for 3rd Tube well site under Talda Water Supply Scheme (Augmentation) in Contai III Block within Contai Sub Division under Tamluk Division, PHE Dte. | 2897/TD | 10/09/2024 | 40 | BISWA NIRMAN ENTERPRISE. | 11.34 | 0 | 0 | 0
4312 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda , SM/09445 | Augmentation | Washout Pipe line by UPVC Pipe for Augmentation of Talda Water Supply Scheme and its adjoining mouzas in Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 697/CSD | 25/03/2025 | 30 | BHARAT NIRMAN ENTERPRISE | 1.91 | 0 | 0 | 0
4313 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda , SM/10344 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kamarda Water Supply Scheme under Tamluk Division, PHE Dte. | 1614/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.2 | 3.6 | 100 | 100
4314 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda , SM/10344 | Augmentation | Instalation of display Board at different work site of Augmentation of Kamarda-1 no, Sherkhanchak Zone-I-1 no, Sherkhanchak Zone-II-1 no, Majna-1 no, Madhakhali Zone-I-1 no , Madhakhali Zone-I-1 no, Arjunnagar-1 no & Nijkasba-1 no PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 808 / CSD | 21/10/2022 | 15 | ABHIJIT BERA | 0.93 | 0.93 | 100 | 100
4315 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda , SM/10344 | Augmentation | Material Requisition To Resource Division | 407/TD | 25/05/2022 | 0 | Resource Division | 50.49 | 0 | 0 | 0
4316 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda , SM/10344 | Augmentation | Material Requisition To Resource Division | 1261/TD | 12/09/2022 | 0 | Resource Division | 19.4 | 0 | 0 | 0
4317 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda , SM/10344 | Augmentation | Laying of Left-Out portion HDPE Pipe line of Distribution pipe line by HDPE pipes and FHTC works under Kamarda Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 1071/TD | 16/03/2024 | 25 | TARUN KHATUA | 34.31 | 23.75 | 69.22 | 30
4318 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda , SM/10344 | Augmentation | Land Development at 3rd Tube Well site of Kamarda Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur | 222/CSD | 06/02/2024 | 15 | GIRI CONSTRUCTION | 0.97 | 0 | 0 | 0
4319 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda , SM/10344 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Kamarda Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | 305/TD | 24/04/2023 | 20 | RAMASISH ENTERPRISE | 4.15 | 4.15 | 100 | 100
4320 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda , SM/10344 | Augmentation | Quotation for new service connection at Kamarda w/s scheme PH III Additional TW in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004671499, Ref ID 204266596) | BP-2024-25-48 | 18/04/2024 | 0 | WBSEDCL | 3.07 | 0 | 0 | 0
4321 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda , SM/10344 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 400cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Kamarda Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1076/TD | 23/08/2022 | 948 | HARIPADA PATTANAYAK | 499.3 | 405.37 | 81.19 | 86
4322 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda , SM/10344 | Augmentation | Name of Work: i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Kamarda PWSS within Khejuri -I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) Rising main and other allied works Augmentation of Kamarda W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. iii) construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Kamarda W/S Scheme within Khejuri - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Low Land). | 3220/TD | 14/03/2023 | 800 | GIRI CONSTRUCTION | 20.1 | 0 | 0 | 70
4323 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda , SM/10344 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well no - III at Kamarda Water supply scheme, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 2610/W/MMD | 19/09/2023 | 712 | M/S SREEJIT ENTERPRISE | 14.77 | 10.79 | 73.04 | 50
4324 | PURBA MEDINIPUR | Tamluk Division | Balance Work for Retrofitting to Accommodate FHTC (750 Nos.) and Laying of left-out portion UPVC pipeline due to uncovered area of this Zone at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-XI, Block-Kolaghat in this , SM/10095 | Retrofitting | Balance work for Retrofitting to accommodate FHTC (750 nos) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone at different nodal point under JJM in Surface water based water supply scheme for Zone-XI, Block-Kolaghat in the District of Purba Medinipur. (Phase-II) | 1800/TD | 08/02/2022 | 40 | TAPAS SANTRA | 92.64 | 92.89 | 100 | 100
4325 | PURBA MEDINIPUR | Tamluk Division | Balance work for Retrofitting to Accommodate FHTC (951 Nos.) and laying of Left-out portion UPVC pipeline due to uncovered area of this Zone and Damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme under Zone-III , SM/10096 | Retrofitting | Retrofitting to accommodate FHTC (Balance work) (951 nos.) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-III, Block-Kolaghat in the District of Purba Medinipur. (Phase-II) | 1907/TD | 23/02/2022 | 40 | JAYANTA KUMAR MONDAL | 82.25 | 77.04 | 100 | 100
4326 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme under Tamluk Division, PHE Dte. | 1182/TD | 02/12/2021 | 20 | HORIZEN | 2.94 | 2.94 | 100 | 100
4327 | PURBA MEDINIPUR | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TW BY DEPARTMENTAL RIG MACHINE IN RAMNAGAR-II BLOCK, UNDER CDD,PHE DTE. | 183/CMSD-I(D) | 10/06/2022 | 15 | PADMA ENGINEERING & CO. | 4.92 | 4.66 | 100 | 100
4328 | PURBA MEDINIPUR | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | PROVIDING TW MATERIALS CONFORMING TO 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TW AT RAMNAGAR-II BLOCK, UNDER CMSD-I(D), CDD,PHE DTE. | 184/CMSD-I(D) | 10/06/2022 | 15 | PADMA ENGINEERING & CO. | 5 | 4.97 | 100 | 100
4329 | PURBA MEDINIPUR | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | PROVIDING PEA SIZE GRAVELS AND OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TW AT RAMNAGAR-II BLOCK, UNDER CMSD-I(D), CDD,PHE DTE. | 185/CMSD-I(D) | 10/06/2022 | 15 | PADMA ENGINEERING & CO. | 5 | 3.13 | 100 | 100
4330 | PURBA MEDINIPUR | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | ADDITIONAL CARRIAGE OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT MADAR PWSS (T/W-III), BLOCK - RAMNAGAR-II UNDER CMSD-I (D), CDD, PHE DTE. | 352/CMSD-I (D) | 26/07/2022 | 10 | PADMA ENGINEERING & CO. | 0.16 | 0.16 | 100 | 100
4331 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | Augmentation of ground water based Mandar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 150 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Ramnagar-II Dev. Block under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1813/TD | 11/02/2022 | 180 | BASANTA KUMAR MAITY | 199.91 | 122.57 | 61.31 | 70
4332 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | Supply of C.I D.F Sluice valve for Augmentation of ground water based Mander W/S Scheme to accommodate FHTC within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 324/DSD | 15/07/2022 | 7 | BASANTA KUMAR MAITY | 2.86 | 2.86 | 100 | 100
4333 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | Material Requisition To Resource Division | 1261/TD | 13/12/2021 | 0 | Resource Division | 5.63 | 0 | 0 | 0
4334 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | Material Requisition To Resource Division | 1869/TD | 17/02/2022 | 0 | Resource Division | 5.31 | 0 | 0 | 0
4335 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | Quotation money payment to WBSEDCL for Mandar Water Supply Scheme of Tube Well No. - III | BP-2023-24-237 | 09/08/2023 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
4336 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | Laying of Distribution pipe line, Rising main pipe line, Pump House, Boundary Wall, Sinking of 3rd Tube Well with allied works of Mandar & its adjoining mouzas Water Supply Scheme within RAMNAGAR -II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | 244/TD | 19/04/2023 | 45 | BASANTA KUMAR MAITY | 59.1 | 28.91 | 48.92 | 50
4337 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | Valve operator (one no) in head work site at Mandar & its adjoining mouzas water supply scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division PHE Dte. (From 01.10.2024 to 03.04.2025 i.e. 185 days) | 1026/DSD | 01/10/2024 | 185 | DAS ENTERPRISE. | 1.2 | 0 | 0 | 0
4338 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. , SM/09274 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1220/W/MMD | 25/04/2023 | 360 | S.G.TECHNICAL SERVICE | 11.96 | 0 | 0 | 100
4339 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09279 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paramanandapur Water Supply Scheme under Tamluk Division, PHE Dte. | 1193/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.74 | 4.74 | 100 | 100
4340 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09279 | Augmentation | Augmentation of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | 2557/TD | 24/01/2023 | 60 | M/S. S. A. CONSTRUCTION | 41.95 | 41.3 | 100 | 100
4341 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09279 | Augmentation | Rejuvenation & Retrofitting of ground water based Paramanandapur PWSS to accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (Part- B) | 743/TD | 05/07/2022 | 60 | SATYABRATA BHAUMIK | 165 | 165.43 | 100.26 | 100
4342 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09279 | Augmentation | Proposed Rejuvenation &Retrofitting of Laying Distribution System of proposed left out portion pipe line at Paramanandapur PWSS | 3170/TD | 10/03/2023 | 20 | PURNA CHANDRA BARH | 7.63 | 7.46 | 100 | 100
4343 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09279 | Augmentation | Rejuvenation & Retrofitting of ground water based Paramanandapur PWSS to accommodate FHTC in Moyna Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part- A) | 58/TD | 05/04/2022 | 60 | BARH CONSTRUCTION | 130.82 | 130.17 | 100 | 100
4344 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09279 | Augmentation | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room,Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Paramanandapur Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 330/TD | 25/04/2023 | 811 | SUDIP MANNA | 13.09 | 0 | 0 | 100
4345 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Erasole Water Supply Scheme under Tamluk Division, PHE Dte. | 1646/TD | 19/01/2022 | 20 | HORIZEN | 5.37 | 5.37 | 100 | 100
4346 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site(Boosting T/W) of Bagmari Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1094/TD | 25/08/2022 | 40 | AQUATECH ENGINEERS | 70.49 | 33.7 | 100 | 100
4347 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Material Requisition To Resource Division | 409/TD | 25/05/2022 | 0 | Resource Division | 114.93 | 0 | 0 | 0
4348 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Material Requisition To Resource Division | 1263/TD | 12/09/2022 | 0 | Resource Division | 44.05 | 0 | 0 | 0
4349 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Electric Quotiaton for Erashal Water Supply Scheme TW-IV (Ref. ID-203949710) | BP-2023-24-36 | 04/05/2023 | 0 | WBSEDCL | 0.5 | 0 | 0 | 0
4350 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Way leave charges of South Eastern Railway Track for Application ID SER-KGP-2023-WL-58 under Tamluk Division, PHE Dte. | BP-2023-24-737 | 29/12/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.07 | 0 | 0 | 0
4351 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Electric Quotiaton for Erashal Water Supply Scheme TW-III (Ref. ID-203949718) | BP-2023-24-37 | 04/05/2023 | 0 | WBSEDCL | 0.5 | 0 | 0 | 0
4352 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Repairing & Renovation of Construction of switch Room cum Chlorine Room at OHR site and 2 nd.Tube Well site and Renovation of existing Boundary Wall at OHR site and 2 nd.Tube Well site and New construction of Boundary Wall at 3rd.& 4 th Tube Well site for Erasal Water Supply Scheme under Tamluk Sub Division,PHE Dte.. | 3019/TD | 27/02/2023 | 60 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 40.17 | 39.66 | 100 | 100
4353 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1226/W/MMD | 25/04/2023 | 180 | SOUMEN ELECTRIC | 26.95 | 26.58 | 100 | 100
4354 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Jack Pushing of Railway Track Between NANDAKUMAR P.H. & LAVAN SATYAGARH SMARAK P.H. Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of ERASOLE Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 250 mm Dia DI (K7) Carrier Pipe within Tamluk Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =48 Mtr) Nodal Point J393 to J338. | 2942/TD | 23/11/2023 | 20 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 68.57 | 53.19 | 100 | 100
4355 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Way leave charges of South Eastern Railway Track for Application ID SER-KGP-2023-WL-58 of Erashole PWSS under Tamluk Division, PHE Dte. | BP-2023-24-853 | 08/02/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.38 | 0 | 0 | 0
4356 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Augmentation of ground water based Erasol Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Chandipur Dev. Block under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1888/TD | 24/11/2022 | 1038 | TARUN KOLEY | 1110.82 | 768.23 | 69.16 | 80
4357 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | Interconnection with laying of 150 mm dia,200 mm dia & 250 mm dia DI(K-9) rising main from 3rd & 4th. T/W to OHR at Erasole PWSS under Tamluk Sub-Division of Tamluk Division PHE Dte. | 1476/TD | 14/07/2023 | 843 | SAYAN MAITY | 10.15 | 0 | 0 | 100
4358 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. , SM/10396 | Augmentation | MS structure for canel crossing, NH road boring with casing and concrete piller for Laying distribution system and rising main pipe line at Erasole Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 3105/TD | 23/09/2024 | 407 | TARUN KOLEY | 28.12 | 0 | 0 | 100
4359 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenkua Water Supply Scheme under Tamluk Division, PHE Dte. | 1164/TD | 01/12/2021 | 7 | HORIZEN | 5.92 | 5.83 | 100 | 100
4360 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Supply & delivery of different dia CIDF Sluice Valve for Dhenkua Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte.(Part-B) | 347/TD | 13/05/2022 | 20 | TAPAS SANTRA | 3.67 | 3.67 | 100 | 100
4361 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Supply & delivery of different dia CIDF Sluice Valve for Dhenkua Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte.(PART-A) | 346/TD | 13/05/2022 | 20 | TAPAS SANTRA | 4.49 | 4.49 | 100 | 100
4362 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | G.I pipe column with M.S. Structure for laying of D.I pipe line & HDPE pipe line with Casing at Dhenkua Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. (Total Length= 65.00 mtr, {i) NP-116 to 46= 20mt + ii) NP-90 to 5= 2.5mt + iii) NP 10 to 11 = 2.5 Mtr. + iv) NP - 199 to 168 = 20.0mt + NP - 151 to 154 =20.0mtr.} | 974/TD | 03/08/2022 | 20 | RAJ KUMAR SINGHA | 9.49 | 4.79 | 100 | 100
4363 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well site of Dhenkua Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 1133/TD | 30/08/2022 | 90 | DIPANKAR MALAKAR | 4.75 | 2.74 | 100 | 100
4364 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well No I under Dhenkua water supply scheme under Midnapore Mechanical Division, PHE Dte. | 2120/W/MMD | 28/11/2022 | 120 | DIPALI CONSTRUCTION | 11.1 | 10.95 | 100 | 100
4365 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Material Requisition To Resource Division | 1255/TD | 13/12/2021 | 0 | Resource Division | 12.45 | 0 | 0 | 0
4366 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Material Requisition To Resource Division | 2345/TD | 31/03/2022 | 0 | Resource Division | 15.83 | 0 | 0 | 0
4367 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Electric Quotation for Denkua Water Supply SchemeT/W-I (Ref. ID-224005066 ) | BP-2023-24-135 | 20/07/2023 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
4368 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Augmentation of ground water based Dhenkua Water Supply Scheme by Providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 400 cum and staging height 20.00 mtr. With allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 57/TD | 05/04/2022 | 180 | RAJ KUMAR SINGHA | 563.22 | 508.91 | 100 | 100
4369 | PURBA MEDINIPUR | Central Drilling | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Dhenuka W/S Scheme (T/W-II), Sutahata Block under Purba Midnapur District, Central Drilling Division, P.H.E. Dte. | 877/CDD | 11/07/2023 | 358 | MENAKA ENTERPRISE | 21.16 | 19.85 | 100 | 100
4370 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Laying of Left-out portion Distribution pipe line and Household Tap Connection (FHTC) for Dhenkua Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | 3466/TD | 06/11/2024 | 96 | RAJ KUMAR SINGHA | 54.66 | 0 | 0 | 70
4371 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Dhenkua Water supply scheme, Sutahata block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 2005/W/MMD | 30/08/2024 | 180 | P.K.ENGINEERING | 9.29 | 0 | 0 | 80
4372 | PURBA MEDINIPUR | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme , SM/09284 | Augmentation | Laying Rising main and supporting work with Drum Sheet walling and Earth filling in Dhenkua Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | 975/TD | 03/08/2022 | 875 | RAJ KUMAR SINGHA | 87.92 | 79.54 | 96.62 | 100
4373 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Begunberia Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1000/TD | 01/11/2021 | 20 | SAYAN MAITY | 4.25 | 3.26 | 100 | 100
4374 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme under Tamluk Division, PHE Dte. | 1183/TD | 02/12/2021 | 20 | HORIZEN | 7 | 7 | 100 | 100
4375 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Supply & delivery of different dia CIDF Sluice valve of Begunberia Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-A) | 355/TD | 13/05/2022 | 20 | SANTRA ENTERPRISE. | 4.85 | 4.85 | 100 | 100
4376 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Supply & delivery of different dia CIDF Sluice valve of Begunberia Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-B) | 356/TD | 13/05/2022 | 20 | SANTRA ENTERPRISE. | 4.42 | 4.42 | 100 | 100
4377 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Begunberia Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 132/TD | 19/04/2022 | 21 | SIMPLEX DRILLING COMPANY | 19.03 | 19.03 | 100 | 100
4378 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Material Requisition To Resource Division | 1257/TD | 13/12/2021 | 0 | Resource Division | 71.92 | 0 | 0 | 0
4379 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Material Requisition To Resource Division | 2347/TD | 31/03/2022 | 0 | Resource Division | 25.41 | 0 | 0 | 0
4380 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Payment to WBSEDCL for Electric Quotation money of Begunberia Tube Well No. ¿ III | BP-2023-24-206 | 25/07/2023 | 0 | WBSEDCL | 0.56 | 0 | 0 | 0
4381 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Restoration work of the damaged flank portions caused for laying pipe line by PHE Dte.on Terapara Jalpai to Jaganathpur (Basulia Hospital to Horikhali) road from Ch.0.42 KM to 2.00 KM under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 | BP-2023-24-123 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.68 | 0 | 0 | 0
4382 | PURBA MEDINIPUR | Midnapore Mechanical | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Sutahata and Tamluk in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1218/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 40.43 | 12.76 | 94.67 | 60
4383 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Laying Left Out Distribution System, FHTC work & Pilling work with Drum sheet Augmentation of ground water based Begunberia Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2200/TD | 01/09/2023 | 520 | TAPAS SANTRA | 97.5 | 0 | 0 | 50
4384 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Construction of boundary wall, Retaining wall, Approach road & Earth filling Work in 3rd tubewell site of Begunberia Water Supply scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) , (length of Retaining wall-16mtr) & (length of Approach road-10mtr). | 2162/TD | 31/08/2023 | 30 | M/S SOURAV MAHAPATRA | 22.85 | 16.96 | 100 | 20
4385 | PURBA MEDINIPUR | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. , SM/09285 | Augmentation | Augmentation of ground water based Begunberia Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 600 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2335/TD | 29/03/2022 | 1282 | TAPAS SANTRA | 681.46 | 590.71 | 86.68 | 92
4386 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II, Moyna, Nandakumar & Panskura-I Development Block under Purba Medinipur District. , SM/10586 | New | Material Requisition To Resource Division | 2894/TD | 21/11/2023 | 0 | Resource Division | 2.04 | 0 | 0 | 0
4387 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II, Moyna, Nandakumar & Panskura-I Development Block under Purba Medinipur District. , SM/10586 | New | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0 | 0
4388 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II, Moyna, Nandakumar & Panskura-I Development Block under Purba Medinipur District. , SM/10586 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 614.75 | 76.8 | 70
4389 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II, Moyna, Nandakumar & Panskura-I Development Block under Purba Medinipur District. , SM/10586 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 108.99 | 64.67 | 48
4390 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II, Moyna, Nandakumar & Panskura-I Development Block under Purba Medinipur District. , SM/10586 | New | Installation of 150 mm.x100 mm.x 230 mtr.(av) depth Tube well(PVC) & Providing FHTC (364 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at 09 nos Different Location Block within Purba Medinipur district under Tamluk Division, PHE Dte. | 1100/TD | 08/06/2023 | 907 | SWADHIN KUMAR CHAKRABORTY | 245.94 | 17.6 | 100 | 51
4391 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. , SM/10683 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme under Tamluk Division, PHE Dte. | 1166/TD | 01/12/2021 | 7 | HORIZEN | 7.85 | 7.74 | 100 | 100
4392 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. , SM/10683 | Augmentation | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Kapaseria W/S Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head work Site of Rajarampur W/S Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Tabakhali W/S Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 976/TD | 03/08/2022 | 21 | SIMPLEX DRILLING COMPANY | 58.06 | 19.26 | 100 | 100
4393 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. , SM/10683 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Tabakhali Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1284/TD | 12/09/2022 | 60 | ELECTIVA ENTERPRISE | 4.77 | 3.37 | 100 | 100
4394 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. , SM/10683 | Augmentation | Material Requisition To Resource Division | 410/TD | 25/05/2022 | 0 | Resource Division | 205.42 | 0 | 0 | 0
4395 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. , SM/10683 | Augmentation | Material Requisition To Resource Division | 1264/TD | 12/09/2022 | 0 | Resource Division | 34 | 0 | 0 | 0
4396 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. , SM/10683 | Augmentation | Payment to WBSEDCL for Electric Quotation money of Tabakhali Tube Well No. ¿ III | BP-2023-24-205 | 25/07/2023 | 0 | WBSEDCL | 0.56 | 0 | 0 | 0
4397 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. , SM/10683 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 750 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Ground Water Based Tabakhali Water Supply Scheme within Sutahata Dev. Block under Haldia sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1578/TD | 14/10/2022 | 180 | RAJ KUMAR SINGHA | 709.93 | 448.02 | 63.11 | 55
4398 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. , SM/10683 | Augmentation | Laying left out pipe line,Canal crossing & Rising main of ground water based Tabakhali Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 933/TD | 01/06/2023 | 561 | RAJ KUMAR SINGHA | 81.39 | 65.01 | 79.89 | 88
4399 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. , SM/10683 | Augmentation | Construction of boundary wall in 3rd tubewell site of Tabakhali W/S scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) | 1084/TD | 08/06/2023 | 30 | M/S SOURAV MAHAPATRA | 5.91 | 3 | 100 | 100
4400 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. , SM/10683 | Augmentation | Jack Pushing of Railway Track Between BASULYA - BARADA Railway Station on Tamluk-Haldia Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Tabakhali Piped Water Supply Scheme of 150 mm Dia G.I. Casing Pipe and 125 mm Dia HDPE (PE-100) Carrier Pipe in between OHE MAST NO H50/11 & H50/13, H50/12 & H50/14 within Haldia Sub-Division under Tamluk Division, P.H.E DTE. (Total Length = 80 Mtr) Nodal Point J38 - J40. | 2944/TD | 23/11/2023 | 20 | KRISHNENDU SEKHAR DAS | 72.62 | 59.1 | 100 | 100
4401 | PURBA MEDINIPUR | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. , SM/10683 | Augmentation | Way Leave permission from South Eastern Railway for Tabakhali PWSS for Application ID-SER-KGP-2023-WL-67 | BP-2023-24-822 | 22/01/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.17 | 0 | 0 | 0
4402 | PURBA MEDINIPUR | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. , SM/10683 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme Block - Sutahata under JJM Program under MMD PHE Dte. | 862/W/MMD | 27/03/2023 | 180 | M/S B ENTERPRISE | 13.41 | 0 | 0 | 70
4403 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II , SM/10594 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madhabpur (Balighai) Water Supply Scheme under Tamluk Division, PHE Dte. | 1617/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.71 | 5.71 | 100 | 100
4404 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II , SM/10594 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madhabpur Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | 599/TD | 17/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.61 | 100 | 100
4405 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II , SM/10594 | Augmentation | Material Requisition To Resource Division | 1666/TD | 03/11/2022 | 0 | Resource Division | 141.02 | 0 | 0 | 0
4406 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II , SM/10594 | Augmentation | Material Requisition To Resource Division | 2637/TD | 02/02/2023 | 0 | Resource Division | 15.45 | 0 | 0 | 0
4407 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II , SM/10594 | Augmentation | Electric Quotation for MADHABPUR Water Supply Scheme T/W-I, Zone-II (Ref. ID-204047955) | W/23-24/222 | 01/09/2023 | 0 | WBSEDCL | 4.9 | 0 | 0 | 0
4408 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II , SM/10594 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-I Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1909/TD | 25/11/2022 | 912 | OSMAN SEKH | 69.99 | 16.02 | 30.52 | 100
4409 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II , SM/10594 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, ZONE-II Of MADHABPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671978/QUOT/03/48 DT. 05-04-2024 Application NO- 2004671978 Application type-New connection Consumer Id- 204266733 | BP-2024-25-90 | 24/04/2024 | 0 | WBSEDCL | 1 | 0 | 0 | 0
4410 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II , SM/10594 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhabpur Zone-II Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1576/TD | 14/10/2022 | 991 | BASANTA KUMAR MAITY | 495.32 | 136.92 | 27.64 | 75
4411 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II , SM/10594 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 846/W/MMD | 24/03/2023 | 180 | AHALYA ENGINEERING WORKS | 37.88 | 28.29 | 74.7 | 60
4412 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II , SM/10594 | Augmentation | Construction of Pump House, Boundary Wall, Laying Rising main pipe line & Land development under JJM with allied work for Madhabpur (Z-II ) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 1024/TD | 07/06/2023 | 60 | BASANTA KUMAR MAITY | 45.82 | 0 | 0 | 90
4413 | PURBA MEDINIPUR | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. , SM/10619 | New | Material Requisition To Resource Division | 2897/TD | 21/11/2023 | 0 | Resource Division | 4.61 | 0 | 0 | 0
4414 | PURBA MEDINIPUR | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. , SM/10619 | New | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0 | 0
4415 | PURBA MEDINIPUR | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. , SM/10619 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 229.79 | 63.24 | 70
4416 | PURBA MEDINIPUR | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. , SM/10619 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 206.03 | 34.02 | 48
4417 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10664 | Augmentation | Earth Work in filling in Ditches, Low Land at Head Work Site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-I) | 1858/TD | 09/08/2023 | 10 | TECHNO ENTERPRISE. | 0.96 | 0.96 | 100 | 100
4418 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10664 | Augmentation | Earth Work in filling in Ditches, Low Land at Head Work Site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-II) | 1859/TD | 09/08/2023 | 10 | TECHNO ENTERPRISE. | 0.95 | 0.94 | 100 | 100
4419 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10664 | Augmentation | Material Requisition To Resource Division | 828/TD | 15/07/2022 | 0 | Resource Division | 60.29 | 0 | 0 | 0
4420 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10664 | Augmentation | Quotation money payment to WBSEDCL for Khejuri Zone-II Water Supply Scheme of Tube Well No. - III | BP-2023-24-284 | 17/08/2023 | 0 | WBSEDCL | 1.41 | 0 | 0 | 0
4421 | PURBA MEDINIPUR | Midnapore Mechanical | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10664 | Augmentation | Electric Quotation for Chargeable Head, KHEJURI, Water Supply Scheme T/W-III, Zone-II (Ref. ID-204049542) |  | 01/08/2023 | 0 | WBSEDCL | 1.41 | 0 | 0 | 0
4422 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10664 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.(Part-A) | 1654/TD | 02/11/2022 | 180 | SIBSANKAR CHOWDHURY | 449.19 | 0 | 0 | 40
4423 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10664 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 1st Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 2nd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1225/TD | 07/09/2022 | 40 | M/S SYCHROTECH INDUSTRY | 71.86 | 55.24 | 49.88 | 100
4424 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10664 | Augmentation | Construction of boundary wall and construction of Switch Room with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | 1502/TD | 17/07/2023 | 40 | RAI CONSTRUCTION | 9.19 | 7.99 | 100 | 100
4425 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10664 | Augmentation | Earth Work in filling in Ditches, Low Land at Head Work Site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-III) | 3147/TD | 07/12/2023 | 10 | TECHNO ENTERPRISE. | 0.91 | 0.9 | 100 | 100
4426 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10664 | Augmentation | Earth Work in filling in Ditches, Low land at Head Work site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 1909/TD | 07/06/2024 | 7 | TECHNO ENTERPRISE. | 2.02 | 2.02 | 100 | 100
4427 | PURBA MEDINIPUR | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) , SM/10664 | Augmentation | Construction of Pump Houses and Laying Rising Main for water connection between 1st , 2nd and 3rd Tube Well at Khejuri Water Supply Scheme (Zone-II) within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 2984/TD | 29/11/2023 | 45 | M/S SOURAV MAHAPATRA | 22.43 | 10.21 | 45.52 | 70
4428 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Aladarput W/S Scheme under Contai-II Deshopran Block(PHASE-II) , SM/08227 | Retrofitting | Retrofitting to accomodate FHTC 427 Nos. under JJM Aladarput W/S Scheme within Contai - II Dev. Block under Tamluk Division, PHE Dte. (Phase-II) | BP-2021-22-93 | 05/10/2021 | 0 | BARH CONSTRUCTION | 20.48 | 0 | 0 | 0
4429 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Aladarput W/S Scheme under Contai-II Deshopran Block(PHASE-II) , SM/08227 | Retrofitting | Retrofitting to accomodate FHTC 427 Nos. under JJM Aladarput W/S Scheme within Contai - II Dev. Block under Tamluk Division, PHE Dte. (Phase-II) |  | 01/10/2021 | 0 | BARH CONSTRUCTION | 20.48 | 0 | 0 | 0
4430 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Aladarput W/S Scheme under Contai-II Deshopran Block(PHASE-II) , SM/08227 | Retrofitting | Relaying of 125 mm dia GI Pipe & 150 mm dia GI pipe line for canal crossing with allied works due to damage of pipe line of N.P.-97-99 (part) for construction of culvert of Strengthening & Widening Contai Junput Road of Aladarput Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. | 569 / CSD | 08/12/2021 | 21 | MRINAL KANTI PRADHAN | 2.24 | 0 | 0 | 0
4431 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Aladarput W/S Scheme under Contai-II Deshopran Block(PHASE-II) , SM/08227 | Retrofitting | Retrofitting to accommodate FHTC [ 427 nos] under JJM in Aladarput PWSS [Sarsa(532, part),Uttar Dauki(549,part),Dakshin Paikbar(574,part),Faridpur(575, part),Biswanathpur(576, part),Aladarput(578, part),Hosenaput(579, part),Kalaminaput(580, part),Dakshin Murabanya(581, part),Bichina(584, part),Purba Chechuraput(585,part )] within Contai-II Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) | 2919/TD | 22/02/2021 | 20 | BARH CONSTRUCTION | 26.62 | 4.66 | 100 | 100
4432 | PURBA MEDINIPUR | Tamluk Division | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12428 | New | Material Requisition To Resource Division | 2692/TD | 06/02/2023 | 0 | Resource Division | 14.58 | 0 | 0 | 0
4433 | PURBA MEDINIPUR | Tamluk Division | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12428 | New | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (618 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Purba Puroshattampur PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | 880/TD | 01/06/2023 | 180 | BARH CONSTRUCTION | 281.85 | 169.52 | 60.15 | 66
4434 | PURBA MEDINIPUR | Tamluk Division | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12428 | New | Material Requisition To Resource Division | 98/TD | 05/01/2024 | 0 | Resource Division | 3.81 | 0 | 0 | 0
4435 | PURBA MEDINIPUR | Midnapore Mechanical | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12428 | New | Purushottampur W/S scheme PH-I Application no.-2004522734 ref.-204156888 | BP-2023-24-472 | 27/12/2023 | 0 | WBSEDCL | 2.75 | 0 | 0 | 0
4436 | PURBA MEDINIPUR | Midnapore Mechanical | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12428 | New | Additional Quotation Bill for New Service connection at T/W NO-I & II Of PURBA PURUSHOTTAMPUR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, PICHABANI C.C.C. Ref. Memo No- PBN/SM/958 DT. 28-02-2024 Application NO- T/W NO-I: 2004522734 Con. Id- 204156888 ( T/W NO-I) Application NO- T/W NO-II: 2004522748 Con. Id- 204156889 ( T/W NO-II) | BP-2023-24-795 | 06/03/2024 | 0 | WBSEDCL | 3.26 | 0 | 0 | 0
4437 | PURBA MEDINIPUR | Midnapore Mechanical | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12428 | New | Purushottampur W/S scheme PH-II Application no.-2004522748 ref.-204156889 | BP-2023-24-471 | 27/12/2023 | 0 | WBSEDCL | 2.78 | 0 | 0 | 0
4438 | PURBA MEDINIPUR | Midnapore Mechanical | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12428 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBO PURUSHOTTAMPUR and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 541/W/MMD | 20/03/2023 | 530 | SOUMEN ELECTRIC | 21.56 | 19.72 | 93.04 | 80
4439 | PURBA MEDINIPUR | Tamluk Division | KAJI BASAN AND ADJOINING MOUJAS PWSS , SM/12499 | New | Material Requisition To Resource Division | 2402/TD | 16/01/2023 | 0 | Resource Division | 11.28 | 0 | 0 | 0
4440 | PURBA MEDINIPUR | Midnapore Mechanical | KAJI BASAN AND ADJOINING MOUJAS PWSS , SM/12499 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAJI BASAN and ADJOINING MOUJAS, Block - Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 509/W/MMD | 20/03/2023 | 180 | SANJIB SAHA | 22.79 | 0 | 0 | 0
4441 | PURBA MEDINIPUR | Tamluk Division | KAJI BASAN AND ADJOINING MOUJAS PWSS , SM/12499 | New | Material Requisition To Resource Division | 2961/TD | 12/09/2024 | 0 | Resource Division | 7.86 | 0 | 0 | 0
4442 | PURBA MEDINIPUR | Midnapore Mechanical | KAJI BASAN AND ADJOINING MOUJAS PWSS , SM/12499 | New | Quotation Bill for New Service connection at T/W NO-I Of KAJIBASAN W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004767101/QUOT/03 DT. 07-06-2024 Application NO- 2004767101 Application type-New connection Consumer Id- 204325527 | BP-2024-25-300 | 18/06/2024 | 0 | WBSEDCL | 16.47 | 0 | 0 | 0
4443 | PURBA MEDINIPUR | Tamluk Division | KAJI BASAN AND ADJOINING MOUJAS PWSS , SM/12499 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 146.95 | 33.02 | 51
4444 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Amarshikashba Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | 617/TD | 21/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 3.32 | 100 | 100
4445 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300 mm X 200mm X 190mm Depth) by utilising Departmental Machineries for Amarshi Kasba W/S Scheme(Z-II,TW-I), Patashpur -I Block under Purba Medinipur District, CDD,P.H.E.Dte. | 2122/CDD | 02/03/2023 | 30 | MENAKA ENTERPRISE | 15.74 | 12.47 | 100 | 100
4446 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Material Requisition To Resource Division | 1669/TD | 03/11/2022 | 0 | Resource Division | 57.23 | 0 | 0 | 0
4447 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Material Requisition To Resource Division | 2645/TD | 13/10/2023 | 0 | Resource Division | 14.4 | 0 | 0 | 0
4448 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Electric Quotation for AMARSIKASBA Water Supply Scheme T/W-I, Zone -II, (Ref. ID-204098661) | BP-2023-24-311 | 01/11/2023 | 0 | WBSEDCL | 3.28 | 0 | 0 | 0
4449 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Rising main and other allied works Augmentation of Amarshikasba Zone-II W/S Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 399/TD | 27/04/2023 | 25 | AURGHA BHATTACHARYA | 7.68 | 2.41 | 31.37 | 80
4450 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Augmentation of Amarshikasba Zone-II PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-136.00 mtr.) | 592/TD | 17/05/2023 | 45 | ANUSKA ENTERPRISE | 21.29 | 7.74 | 36.37 | 40
4451 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW(Head Work) site for Augmentation of Amarshikasba Zone-II & its adjoining moujas PWSS in Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | 593/TD | 17/05/2023 | 60 | M/S SOURAV MAHAPATRA | 7.26 | 5.78 | 100 | 100
4452 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 190 Mtrs. Depth) by utilising Departmental Machineries for Amarshi Kasba W/S Scheme (Zone-I,T/W-III) , Patashpur-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 2123/CDD | 02/03/2023 | 300 | MENAKA ENTERPRISE | 15.74 | 12.78 | 100 | 100
4453 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, ZONE-II Of AMARSI KASBA W/S Scheme under MMD, PHE, Dte. Block- Potashpur-I, AMARSI C.C.C. Ref. Memo No- 2004607907/QUOT/03 DT. 21-02-2024 Application NO- 2004607907 Application type-New connection Reference Id- 204223198 | BP-2023-24-822 | 13/03/2024 | 0 | WBSEDCL | 3.18 | 0 | 0 | 0
4454 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 814/W/MMD | 24/03/2023 | 180 | S.K.ENTERPRISE | 22.8 | 19.87 | 87.13 | 10
4455 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Laying of distribution pipe line to accommodate FHTC (2238 Nos) with construction of R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Amarshikasba Zone-II water Supply Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 2593/TD | 30/01/2023 | 878 | DAS ENTERPRISE | 372.65 | 254.87 | 68.39 | 100
4456 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II , SM/12488 | Augmentation | Drum Sheet walling 1.40m. (av.) high on sal-bullah / Eucalyptus bullah pilling with allied works of Amarshi Kasba Zone-II & its adjoining moujas PWSS within Patashpur-I Block under Contai-Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | 130/CSD | 16/01/2025 | 7 | GHOSH CONSTRUCTION (GST : 19AXMPG8403A1ZO) | 0.97 | 0 | 0 | 100
4457 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation to accommodate FHTC under JJM of Chandanpur PWSS within Ramnagar I Block under Digha Sub-Division of Tamluk Division PHE Dte Purba Medinipur Phase II , SM/08749 | Retrofitting | Rejuvenation to accommodate FHTC (450 nos.) under JJM of Chandanpur PWSS within Ramnagar I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Phase-II) | 683/TD | 10/09/2021 | 20 | TAPAS SANTRA | 63.43 | 124.51 | 196.29 | 100
4458 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AND OTHERS AT SITE FOR CONSTRUCTION OF TUBE WELL IN BARGODAGODAR W/S SCH, NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 146/CMSD-I | 30/05/2022 | 3 | PADMA ENGINEERING & CO. | 0.35 | 0 | 0 | 0
4459 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bargodagodar Water Supply Scheme under Tamluk Division, PHE Dte. | 1199/TD | 02/12/2021 | 20 | RADIANT | 8.93 | 8.93 | 100 | 100
4460 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BATGODAGODAR W/S SCHEME, NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 434/CDD | 23/05/2022 | 30 | PADMA ENGINEERING & CO. | 13.86 | 13.01 | 100 | 100
4461 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Electric Quotation Bill under Nandakumar CCC at Bargodagodar PWSS under Tamluk Division, PHE Dte. within Purba Medinipur District. | BP-2022-23-511 | 22/12/2022 | 0 | WBSEDCL | 2.57 | 0 | 0 | 0
4462 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well site of Bargodagodar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 1208/TSD | 15/09/2022 | 30 | S.K. MONDAL | 2.66 | 2.3 | 86.2 | 0
4463 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Jungle cutting at Head work site in connection repair & renovation of Boundary of Boargodagodar W/S Scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | 1659/TSD | 11/12/2023 | 7 | PURNA CHANDRA BARH | 0.24 | 0 | 0 | 0
4464 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Bargodagodar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | 1445/TD | 27/09/2022 | 30 | TARUN KHATUA | 4.85 | 4.85 | 100 | 100
4465 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Land filling work at 3rd tube well site of Bargodagodar water supply scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 74/TSD | 11/01/2023 | 15 | TARUN KHATUA | 0.95 | 0.95 | 100 | 100
4466 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 1.99 | 100 | 0
4467 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AND OTHERS AT SITE FOR CONSTRUCTION OF TUBE WELL IN BARGODAGODAR W/S SCHEME, NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | 146/CMSD-I | 30/05/2022 | 3 | PADMA ENGINEERING & CO. | 0.31 | 0.3 | 100 | 100
4468 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Material Requisition To Resource Division | 645/TD | 27/06/2022 | 0 | Resource Division | 37.93 | 0 | 0 | 0
4469 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Material Requisition To Resource Division | 97/TD | 11/04/2022 | 0 | Resource Division | 41.98 | 0 | 0 | 0
4470 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Restoration estimate with Bituminous Surfacing ,sand filling and jhama -metal consolidation of Tamluk -Moyna road from 10 KM to 11.30 KM due to cutting of Hard shoulder for laying water pipe lines by PHE Dte. within Tamluk Highway Sub-Division in the district of Purba Medinipur during the year 2022-23 | BP-2023-24-118 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.09 | 0 | 0 | 0
4471 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Payment to WBSEDCL for Quotation Money for Bargodagodar PWSS under Tamluk Division, PHE Dte. | BP-2022-23-820 | 24/03/2023 | 0 | WBSEDCL | 8.99 | 0 | 0 | 0
4472 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Restoration estimate with sand filling and jhama -metal consolidation of Thekuabazar- Pursaghat Road due to lcutting of hard shoulder for laying water pipelines by PHE Dte. within Tamluk Highway Sub-Division under Tamluk Highway Division in the district of Purba Medinipur during the year 2022-23 | BP-2023-24-116 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.12 | 0 | 0 | 0
4473 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr.and repairing & renovation of 450 cum OHR and staging height 20.00 mtr as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bargodagodar Water Supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | 812/TD | 12/07/2022 | 180 | CONCORD ENGINEERING | 774.2 | 589.81 | 76.18 | 76
4474 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Laying left out portion of 90 mm dia UPVC pipe lines with allied works to facilitate the FHTC connection for Bargodagodar water supply scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 2205/TD | 01/09/2023 | 30 | SK. NUR ISLAM | 27.66 | 24.78 | 89.57 | 60
4475 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | New Construction of boundary wall (Length-50 m) with R.C.C structures including provision of M.S. gate at Head work site under Bargodagodar W/S Scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | 2214/TD | 01/09/2023 | 40 | BARH CONSTRUCTION | 6.22 | 0 | 0 | 0
4476 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. under JJM Program under MMD PHE Dte. | 207/W/MMD | 10/02/2023 | 180 | SOUMEN ELECTRIC | 40.4 | 37.91 | 100 | 100
4477 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Sinking of 300 mm x 200 mm dia x 240 mtr. deep tube well by direct rotary rig method for Replacement of head work site Tube well of Bargodagudar Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | 1084/TD | 16/03/2024 | 20 | MANNA COMPUTER | 17.87 | 16.15 | 100 | 100
4478 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Bargodagodar PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 3167/TD | 10/03/2023 | 632 | BARH CONSTRUCTION | 33.83 | 28.07 | 93.23 | 80
4479 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Left out pipe line of Providing Functional Household Tap Connection & construction of new drain of Khejurberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | 3268/TD | 04/10/2024 | 90 | MISHRA ENTERPRISE | 44.78 | 0.55 | 50 | 100
4480 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Material Requisition To Resource Division | 1102/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
4481 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Functional Household Tap Connection (FHTC-796 nos) of Bargodagodar water supply scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | 2206/TD | 01/09/2023 | 30 | SK. NUR ISLAM | 27.14 | 16.19 | 59.63 | 60
4482 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Dismentling of existing damaged staff quarter and godown of Bargodagodar and its adjoining mouza Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | 337/TSD | 17/02/2025 | 30 | SK. INJAMUL ALI | 2.81 | 0 | 0 | 100
4483 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09913 | Augmentation | Laying of 150/200 mm dia DI(K-9) for Rising main line from T/W-1 to Existing delivery main including CI/DI specials supply under Bargodagodar PWSS with in Nandakumar Dev. Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division,PHE Dte. | 2828/TSD | 08/09/2025 | 30 | BARH CONSTRUCTION | 0.89 | 0 | 0 | 100
4484 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kulbari Water Supply Scheme under Tamluk Division, PHE Dte. | 1195/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 10.5 | 10.5 | 100 | 100
4485 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. (Part- B) | 60/TD | 05/04/2022 | 60 | TAPAS SANTRA | 154.84 | 129.6 | 83.7 | 100
4486 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part- A) | 54/TD | 05/04/2022 | 90 | HARIPADA PATTANAYAK | 273.36 | 272.86 | 100 | 100
4487 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Sinking of 1 (One) no Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at OHR Site of Kulbari Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 977/TD | 03/08/2022 | 15 | PRANTIK DRILLING AGENCY | 17.17 | 16.45 | 100 | 100
4488 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Supply of DI Specials for Proposed Rejuvenation & Retrofitting of Laying Distribution System of KULBARI PWSS under tamluk Sub-Division of Tamluk Division, PHE Dte. | 1229/TD | 07/09/2022 | 15 | BAGLAMUKHI SECURITY SERVICE | 4.81 | 4.81 | 100 | 100
4489 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Material Requisition To Resource Division | 642/TD | 27/06/2022 | 0 | Resource Division | 27.12 | 0 | 0 | 0
4490 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Material Requisition To Resource Division | 418/TD | 25/05/2022 | 0 | Resource Division | 4.92 | 0 | 0 | 0
4491 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Material Requisition To Resource Division | 96/TD | 11/04/2022 | 0 | Resource Division | 43.14 | 0 | 0 | 0
4492 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part-D) | 55/TD | 05/04/2022 | 90 | MAA ANANDAMAYEE | 251.38 | 251.38 | 100 | 100
4493 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Sal-bullah /Eucalyptus bullah piling of pipe line and its allied works to accommodate FHTC at Kulbari water supply scheme in Chandipur Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur(PART-A) | 926/TD | 01/06/2023 | 20 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12.86 | 12.86 | 100 | 100
4494 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Material Requisition To Resource Division | 1097/TD | 19/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
4495 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Quotation bill for new service connection at Kulbari Boosting TW IV Application No.-2004567339, Ref ID.-204195755 | BP-2023-24-725 | 23/02/2024 | 0 | WBSEDCL | 11.01 | 0 | 0 | 0
4496 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Quotation bill for new service connection at Kulbari w/s scheme boosting TW III Application No.-2004567719, Ref.-204195754 | BP-2023-24-724 | 23/02/2024 | 0 | WBSEDCL | 10.34 | 0 | 0 | 0
4497 | PURBA MEDINIPUR | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/09914 | Augmentation | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. (Part- C) | 138/TD | 19/04/2022 | 1009 | BIDHAN MONDAL | 184.94 | 90.33 | 48.84 | 55
4498 | PURBA MEDINIPUR | Tamluk Division | BAGMARI AND IT'S ADJOINING MOUJAS PWSS , SM/12429 | New | Material Requisition To Resource Division | 2700/TD | 06/02/2023 | 0 | Resource Division | 46.45 | 0 | 0 | 0
4499 | PURBA MEDINIPUR | Tamluk Division | BAGMARI AND IT'S ADJOINING MOUJAS PWSS , SM/12429 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 200 Cum Capacity OHR ( Intze type with pile foundatio ) & Accommodate FHTC ( 1230 Nos) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Bagmari & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 294/TD | 20/04/2023 | 180 | BASANTA KUMAR MAITY | 401.59 | 256.63 | 63.9 | 63
4500 | PURBA MEDINIPUR | Tamluk Division | BAGMARI AND IT'S ADJOINING MOUJAS PWSS , SM/12429 | New | Sinking of 250mm x 150mm dia Tube well of 210 mtr deep tubewell Drilling by Direct Rotary method with 150 dia.uPVC. Strainer of 30m.length all complete including cost of materials for Replacement of 2nd Tubewell at Bagmari & its adjoining mouzas Water Supply Scheme within Egra- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1913/TD | 07/06/2024 | 20 | MAITY CONSTRUCTION | 12.06 | 10.45 | 100 | 100
4501 | PURBA MEDINIPUR | Tamluk Division | BAGMARI AND IT'S ADJOINING MOUJAS PWSS , SM/12429 | New | Material Requisition To Resource Division | 79/TD | 05/01/2024 | 0 | Resource Division | 7.58 | 0 | 0 | 0
4502 | PURBA MEDINIPUR | Midnapore Mechanical | BAGMARI AND IT'S ADJOINING MOUJAS PWSS , SM/12429 | New | Electric Quotation for BAGMARI (RAMNAGAR-I) Water Supply Scheme T/W-I, (Ref. ID-204134070) | BP-2023-24-358 | 24/11/2023 | 0 | WBSEDCL | 4.02 | 0 | 0 | 0
4503 | PURBA MEDINIPUR | Midnapore Mechanical | BAGMARI AND IT'S ADJOINING MOUJAS PWSS , SM/12429 | New | Electric Quotation for BAGMARI (RAMNAGAR-I) Water Supply Scheme T/W-II, (Ref. ID-204143154) | BP-2023-24-376 | 02/12/2023 | 0 | WBSEDCL | 4.91 | 0 | 0 | 0
4504 | PURBA MEDINIPUR | Tamluk Division | BAGMARI AND IT'S ADJOINING MOUJAS PWSS , SM/12429 | New | Laying of balance distribution pipe line to provide Balance FHTC with allied works for Bagmari & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHE Dte, Purba Medinipur | 568/TD | 17/02/2025 | 50 | MAITY CONSTRUCTION | 23.23 | 0 | 0 | 0
4505 | PURBA MEDINIPUR | Tamluk Division | KAKRA & ADJOINING MOUZAS , SM/12138 | New | Material Requisition To Resource Division | 2727/TD | 06/02/2023 | 0 | Resource Division | 18.4 | 0 | 0 | 0
4506 | PURBA MEDINIPUR | Midnapore Mechanical | KAKRA & ADJOINING MOUZAS , SM/12138 | New | Electric Quotation for KAKRA Water Supply Scheme T/W-I, (Ref. ID-204090826) | BP-2023-24-318 | 01/11/2023 | 0 | WBSEDCL | 3.34 | 0 | 0 | 0
4507 | PURBA MEDINIPUR | Midnapore Mechanical | KAKRA & ADJOINING MOUZAS , SM/12138 | New | Electric Quotation for KAKRA Water Supply Scheme T/W-II, (Ref. ID-204090825) | BP-2023-24-317 | 01/11/2023 | 0 | WBSEDCL | 2.85 | 0 | 0 | 0
4508 | PURBA MEDINIPUR | Midnapore Mechanical | KAKRA & ADJOINING MOUZAS , SM/12138 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAKRA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2326/W/MMD | 29/12/2022 | 180 | EASTERN INDIA SALES & SERVICE | 23.69 | 23.22 | 100 | 95
4509 | PURBA MEDINIPUR | Tamluk Division | KAKRA & ADJOINING MOUZAS , SM/12138 | New | Material Requisition To Resource Division | 126/TD | 05/01/2024 | 0 | Resource Division | 12.56 | 0 | 0 | 0
4510 | PURBA MEDINIPUR | Tamluk Division | KAKRA & ADJOINING MOUZAS , SM/12138 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2039 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of KAKRA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | 450/TD | 04/05/2023 | 897 | TARUN KOLEY | 666.45 | 467.04 | 70.08 | 85
4511 | PURBA MEDINIPUR | Tamluk Division | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12151 | New | Material Requisition To Resource Division | 2466/TD | 16/01/2023 | 0 | Resource Division | 21.59 | 0 | 0 | 0
4512 | PURBA MEDINIPUR | Midnapore Mechanical | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12151 | New | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 60.44 | 100
4513 | PURBA MEDINIPUR | Tamluk Division | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12151 | New | Crossing permission of laying HDPE pipeline along and across of NH-116 (from Mecheda bus stop to Hakola Bus stop) of Santipur Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 741/TD | 28/02/2024 | 20 | DONA ASSOCIATES | 9.24 | 0 | 0 | 0
4514 | PURBA MEDINIPUR | Tamluk Division | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12151 | New | Material Requisition To Resource Division | 117/TD | 05/01/2024 | 0 | Resource Division | 14.4 | 0 | 0 | 0
4515 | PURBA MEDINIPUR | Midnapore Mechanical | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12151 | New | Santipur W/S scheme H/W Site Application No.-2004562690 Ref.-204191008 | BP-2023-24-589 | 02/02/2024 | 0 | WBSEDCL | 10.61 | 0 | 0 | 0
4516 | PURBA MEDINIPUR | Midnapore Mechanical | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12151 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SANTIPUR and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2345/W/MMD | 29/12/2022 | 895 | GOENKA ENTERPRISE | 25.26 | 0 | 0 | 30
4517 | PURBA MEDINIPUR | Midnapore Mechanical | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12151 | New | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 0 | 100
4518 | PURBA MEDINIPUR | Tamluk Division | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS , SM/12151 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Santipur PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | 3764/TD | 10/12/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
4519 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11549 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Anantapur (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | 1740/TD | 03/02/2022 | 20 | RADIANT | 3.89 | 3.86 | 100 | 100
4520 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11549 | Augmentation | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 230 mtrs. depth) by utilising Departmental machineries for Anantapur W/S Scheme (Z-II, TW-III) Tamluk block under purba medinipur district, CDD, PHE Dte. | 2116/CDD | 02/03/2023 | 30 | MENAKA ENTERPRISE | 17.75 | 16.11 | 90.74 | 0
4521 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11549 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Anantapur Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 1082/TD | 08/06/2023 | 45 | TARUN KHATUA | 5.1 | 5.1 | 100 | 100
4522 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11549 | Augmentation | Material Requisition To Resource Division | 1018/TD | 08/08/2022 | 0 | Resource Division | 88.34 | 0 | 0 | 0
4523 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11549 | Augmentation | Material Requisition To Resource Division | 1207/TD | 06/09/2022 | 0 | Resource Division | 2.44 | 0 | 0 | 0
4524 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11549 | Augmentation | Electric Quotation for ANANTAPUR, Water Supply Scheme ,Zone-I, T/W-III, (Ref. ID-204060666) | BP-2023-24-189 | 14/08/2023 | 0 | WBSEDCL | 6.18 | 0 | 0 | 0
4525 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11549 | Augmentation | Electric Quotation for ANANTAPUR Water Supply Scheme Z-II, T/W-III (Ref. ID-204048948) | BP-2023-24-188 | 11/08/2023 | 0 | WBSEDCL | 9.99 | 0 | 0 | 0
4526 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11549 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work Site of Anantapur Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 2213/TD | 01/09/2023 | 40 | TARUN KHATUA | 5.14 | 5.12 | 100 | 100
4527 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11549 | Augmentation | Laying of 200 /250/300mm dia DI(K-9) for Rising main line from T/W-1 , T/W-2 ,T/W-3 and interconnection betn. T/W-1 to OHR including supply of DI specials , Construction of approach road at 3rd tube well site under Anantapur Zone- II PWSS with in Tamluk Dev. Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division, PHE Dte. | 2201/TD | 01/09/2023 | 20 | TARUN KHATUA | 8.66 | 8.49 | 100 | 80
4528 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11549 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 641/W/MMD | 20/03/2023 | 180 | M/S. JIT ENTERPRISE | 13.59 | 9.63 | 41.74 | 35
4529 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11549 | Augmentation | Material Requisition To Resource Division | 1122/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0 | 0
4530 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11549 | Augmentation | Laying of distribution pipe line to accommodate FHTC (5686 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Anantapur Zone-II Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 1885/TD | 24/11/2022 | 859 | TAPAS SANTRA | 609.95 | 450.15 | 73.8 | 75
4531 | PURBA MEDINIPUR | Tamluk Division | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS , SM/12398 | New | Material Requisition To Resource Division | 2457/TD | 16/01/2023 | 0 | Resource Division | 24.12 | 0 | 0 | 0
4532 | PURBA MEDINIPUR | Tamluk Division | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS , SM/12398 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Mustaphapur PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | 2199/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4533 | PURBA MEDINIPUR | Tamluk Division | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS , SM/12398 | New | Material Requisition To Resource Division | 1660/TD | 29/04/2024 | 0 | Resource Division | 11.12 | 0 | 0 | 0
4534 | PURBA MEDINIPUR | Midnapore Mechanical | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS , SM/12398 | New | Quotation Bill for New Service connection at T/W NO-I Of MUSTAFAPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004649225/QUOT/03 DT. 20-03-2024 Application NO- 2004649225 Application type-New connection Consumer Id- 204250590 | BP-2024-25-2 | 04/04/2024 | 0 | WBSEDCL | 3.29 | 0 | 0 | 0
4535 | PURBA MEDINIPUR | Midnapore Mechanical | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS , SM/12398 | New | Quotation Bill for New Service connection at T/W NO-II Of MUSTAPHAPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATSHPUR C.C.C. Ref. Memo No-2004886313/QUOT/03/583 DT. 06-09-2024 Application NO- 2004886313 Application type-New connection Consumer Id- 204391660 | C092443181607 | 27/09/2024 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
4536 | PURBA MEDINIPUR | Midnapore Mechanical | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS , SM/12398 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MUSTAPHAPUR and ADJOINING MOUJAS, Block - Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 507/W/MMD | 20/03/2023 | 742 | M/S DILIP MITRA | 22.77 | 0 | 0 | 85
4537 | PURBA MEDINIPUR | Tamluk Division | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS , SM/12398 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 170.24 | 32.93 | 51
4538 | PURBA MEDINIPUR | Tamluk Division | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS , SM/12517 | New | Material Requisition To Resource Division | 2718/TD | 06/02/2023 | 0 | Resource Division | 38.35 | 0 | 0 | 0
4539 | PURBA MEDINIPUR | Midnapore Mechanical | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS , SM/12517 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NAYAPUT and ADJOINING MOUJAS, Block - Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 523/W/MMD | 20/03/2023 | 180 | S.G.TECHNICAL SERVICE | 23.69 | 16.85 | 71.14 | 55
4540 | PURBA MEDINIPUR | Tamluk Division | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS , SM/12517 | New | Material Requisition To Resource Division | 2969/TD | 12/09/2024 | 0 | Resource Division | 12.36 | 0 | 0 | 0
4541 | PURBA MEDINIPUR | Midnapore Mechanical | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS , SM/12517 | New | Nayaput W/S scheme PH-II Application no.-2004522675 ref.-204156884 | BP-2023-24-474 | 27/12/2023 | 0 | WBSEDCL | 4.44 | 0 | 0 | 0
4542 | PURBA MEDINIPUR | Midnapore Mechanical | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS , SM/12517 | New | Nayaput W/S scheme PH-I Application no.-2004522692 ref.-204156883 | BP-2023-24-473 | 27/12/2023 | 0 | WBSEDCL | 4.81 | 0 | 0 | 0
4543 | PURBA MEDINIPUR | Tamluk Division | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS , SM/12517 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | 1674/TD | 25/07/2023 | 860 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 219.1 | 40.88 | 30
4544 | PURBA MEDINIPUR | Tamluk Division | KURPAI AND ADJOINING MOUJAS PWSS , SM/11882 | New | Material Requisition To Resource Division | 2679/TD | 06/02/2023 | 0 | Resource Division | 19.42 | 0 | 0 | 0
4545 | PURBA MEDINIPUR | Midnapore Mechanical | KURPAI AND ADJOINING MOUJAS PWSS , SM/11882 | New | Quotation Bill for Kurpai T/W-II Tamluk CCC Application No=2005004861 Reference ID=204470853 |  | 18/12/2024 | 0 | WBSEDCL | 5.23 | 0 | 0 | 0
4546 | PURBA MEDINIPUR | Midnapore Mechanical | KURPAI AND ADJOINING MOUJAS PWSS , SM/11882 | New | Kurpai W/S scheme H/W site. Application.-2004547144 Ref.-204177947 | BP-2023-24-547 | 15/01/2024 | 0 | WBSEDCL | 8.64 | 0 | 0 | 0
4547 | PURBA MEDINIPUR | Tamluk Division | KURPAI AND ADJOINING MOUJAS PWSS , SM/11882 | New | Sinking of Tube Well ,Laying distribution system pipe line, accommodate FHTC(1309 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of 200 Cum. capacity RCC over Head Reservoir and staging height20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Kurpai PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 461/TD | 04/05/2023 | 912 | MAA ANANDAMAYEE | 396.25 | 57.75 | 14.57 | 75
4548 | PURBA MEDINIPUR | Midnapore Mechanical | KURPAI AND ADJOINING MOUJAS PWSS , SM/11882 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KURPAI AND ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1271/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 22.69 | 0 | 0 | 35
4549 | PURBA MEDINIPUR | Tamluk Division | KURPAI AND ADJOINING MOUJAS PWSS , SM/11882 | New | Laying Distribution System (missing nodal as per drawing) of 110 mm dia & 125 mm dia HDPE pipe line, Drumpsheet Pilling and Cannel Crossing by G.I. pipes with cement concrete and M.S. structure on 110 mm dia (sec 203-206, 132-133, 437-443, 639-638, 705-713 and 183-155) of pipe line of Kurpai Water Supply Scheme of Tamluk Sub-Division under Tamluk Division P.H.E. Dte. | 201/TD | 15/01/2025 | 330 | MAA ANANDAMAYEE | 36.38 | 0 | 0 | 80
4550 | PURBA MEDINIPUR | Tamluk Division | MAKRAMPUR AND ADJOINING MOUJAS PWSS , SM/12282 | New | Material Requisition To Resource Division | 2440/TD | 16/01/2023 | 0 | Resource Division | 30.48 | 0 | 0 | 0
4551 | PURBA MEDINIPUR | Midnapore Mechanical | MAKRAMPUR AND ADJOINING MOUJAS PWSS , SM/12282 | New | Quotation Bill for New Service connection at T/W NO-II Of MAKRAMPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004944304/QUOT/03 DT. 25-10-2024 Application NO- 2004944304 Application type-New connection Consumer Id- 204428639 | C112423561463 | 19/11/2024 | 0 | WBSEDCL | 3.18 | 0 | 0 | 0
4552 | PURBA MEDINIPUR | Midnapore Mechanical | MAKRAMPUR AND ADJOINING MOUJAS PWSS , SM/12282 | New | Quotation Bill for New Service connection at T/W NO-I Of MAKRAMPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004707237/QUOT/03 DT. 29-04-2024 Application NO- 2004707237 MEMO NO: AMR/PHE/90 DT.29/04/2024 Application type-New connection Consumer Id- 204291521 | BP-2024-25-163 | 15/05/2024 | 0 | WBSEDCL | 5.32 | 0 | 0 | 0
4553 | PURBA MEDINIPUR | Midnapore Mechanical | MAKRAMPUR AND ADJOINING MOUJAS PWSS , SM/12282 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAKRAMPUR and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2415/W/MMD | 31/12/2022 | 882 | RITESH ENTERPRISE | 22.79 | 0 | 0 | 50
4554 | PURBA MEDINIPUR | Tamluk Division | MAKRAMPUR AND ADJOINING MOUJAS PWSS , SM/12282 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 75.02 | 12.24 | 51
4555 | PURBA MEDINIPUR | Tamluk Division | DEPAL AND ADJOINING MOUJAS PWSS , SM/12287 | New | Material Requisition To Resource Division | 2999/TD | 27/02/2023 | 0 | Resource Division | 22.33 | 0 | 0 | 0
4556 | PURBA MEDINIPUR | Midnapore Mechanical | DEPAL AND ADJOINING MOUJAS PWSS , SM/12287 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DEPAL and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2370/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 21.72 | 91.65 | 85
4557 | PURBA MEDINIPUR | Tamluk Division | DEPAL AND ADJOINING MOUJAS PWSS , SM/12287 | New | Material Requisition To Resource Division | 108/TD | 05/01/2024 | 0 | Resource Division | 11.02 | 0 | 0 | 0
4558 | PURBA MEDINIPUR | Midnapore Mechanical | DEPAL AND ADJOINING MOUJAS PWSS , SM/12287 | New | DEPAL w/s SCHEME PH -II APPLICATION nO.-2004566534 REF.-204194525 | BP-2023-24-612 | 07/02/2024 | 0 | WBSEDCL | 24.63 | 0 | 0 | 0
4559 | PURBA MEDINIPUR | Midnapore Mechanical | DEPAL AND ADJOINING MOUJAS PWSS , SM/12287 | New | Depal W/S scheme TW no.-I Ref.-204156070 Application ID-2004521731 | BP-2023-24-439 | 19/12/2023 | 0 | WBSEDCL | 5.4 | 0 | 0 | 0
4560 | PURBA MEDINIPUR | Tamluk Division | DEPAL AND ADJOINING MOUJAS PWSS , SM/12287 | New | Additional Quotation for Additional Service connection Charges against APP NO: 2004521731 IRO DEPAL W/S Scheme T/W no-I AT DEPAL Under Jal Jeevan Mission under MMD, PHE, Dte. Block- RAMNAGAR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No-DGA/776 DT. 05-08-2024 Application NO- 100000115575 DT. 05-08-2024 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860310305 | BP-2024-25-381 | 29/08/2024 | 0 | WBSEDCL | 11.8 | 0 | 0 | 0
4561 | PURBA MEDINIPUR | Tamluk Division | DEPAL AND ADJOINING MOUJAS PWSS , SM/12287 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3154 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance for DEPAL and KALAPUNJA within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 1416/TD | 12/07/2023 | 746 | BASANTA KUMAR MAITY | 961.33 | 200.93 | 41.62 | 60
4562 | PURBA MEDINIPUR | Tamluk Division | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS , SM/12431 | New | Material Requisition To Resource Division | 2979/TD | 27/02/2023 | 0 | Resource Division | 17 | 0 | 0 | 0
4563 | PURBA MEDINIPUR | Tamluk Division | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS , SM/12431 | New | Material Requisition To Resource Division | 2953/TD | 12/09/2024 | 0 | Resource Division | 14.49 | 0 | 0 | 0
4564 | PURBA MEDINIPUR | Midnapore Mechanical | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS , SM/12431 | New | Quotation for New service connection at Chingurdaniya w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004620601 , Ref ID 204229471) | BP-2023-24-812 | 11/03/2024 | 0 | WBSEDCL | 3.19 | 0 | 0 | 0
4565 | PURBA MEDINIPUR | Midnapore Mechanical | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS , SM/12431 | New | Chingurdania W/S scheme PH No.-I Application No.-2004565714 Ref.-204193544 | BP-2023-24-594 | 02/02/2024 | 0 | WBSEDCL | 3.68 | 0 | 0 | 0
4566 | PURBA MEDINIPUR | Central Drilling | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS , SM/12431 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 42.76 | 89.44 | 11
4567 | PURBA MEDINIPUR | Tamluk Division | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS , SM/12431 | New | Tube well, Pump House, 350 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2353 nos) under JJM with allied work for Chingur Dania- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. | 1552/TD | 19/07/2023 | 866 | DAS ENTERPRISE | 764.26 | 293.31 | 38.38 | 70
4568 | PURBA MEDINIPUR | Tamluk Division | BAISPUR AND ADJOINING MOUJAS PWSS , SM/12290 | New | Material Requisition To Resource Division | 2410/TD | 16/01/2023 | 0 | Resource Division | 21.35 | 0 | 0 | 0
4569 | PURBA MEDINIPUR | Midnapore Mechanical | BAISPUR AND ADJOINING MOUJAS PWSS , SM/12290 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAISPUR and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2357/W/MMD | 31/12/2022 | 180 | WEST BENGAL ENGINEERING CO. | 22.78 | 0 | 0 | 0
4570 | PURBA MEDINIPUR | Tamluk Division | BAISPUR AND ADJOINING MOUJAS PWSS , SM/12290 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Baispur PWSS at Egra-I Block under Tamluk Division, PHE Dte. | 2195/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4571 | PURBA MEDINIPUR | Tamluk Division | BAISPUR AND ADJOINING MOUJAS PWSS , SM/12290 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 189.99 | 45.64 | 51
4572 | PURBA MEDINIPUR | Tamluk Division | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS , SM/12291 | New | Material Requisition To Resource Division | 2714/TD | 06/02/2023 | 0 | Resource Division | 61 | 0 | 0 | 0
4573 | PURBA MEDINIPUR | Tamluk Division | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS , SM/12291 | New | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1648 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Uttar Daidpur PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | 1568/TD | 19/07/2023 | 180 | M/S JOY MAA DURGA ENTERPRISE | 488.61 | 243.96 | 49.93 | 60
4574 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS , SM/12291 | New | Quotation Bill for New Service connection at T/W NO-II Of UTTAR DAUDPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004852092/QUOT/03/562 DT. 07-08-2024 Application NO- 2004852092 Application type-New connection Consumer Id- 204373375 | C092403062421 | 04/09/2024 | 0 | WBSEDCL | 6.07 | 0 | 0 | 0
4575 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS , SM/12291 | New | Uttar Daudpur W/S scheme PH-I Application no.-2004523051 ref.-204157004 | BP-2023-24-485 | 27/12/2023 | 0 | WBSEDCL | 3.69 | 0 | 0 | 0
4576 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS , SM/12291 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR DAIDPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2369/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 11.06 | 46.68 | 85
4577 | PURBA MEDINIPUR | Tamluk Division | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. , SM/12322 | New | Material Requisition To Resource Division | 2701/TD | 06/02/2023 | 0 | Resource Division | 27.23 | 0 | 0 | 0
4578 | PURBA MEDINIPUR | Tamluk Division | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. , SM/12322 | New | Material Requisition To Resource Division | 113/TD | 05/01/2024 | 0 | Resource Division | 9.76 | 0 | 0 | 0
4579 | PURBA MEDINIPUR | Midnapore Mechanical | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. , SM/12322 | New | QUOTATION FOR NEW SERVICE CONNECTION AT TW-1 OF SANTRA WS SCHEME UNDER MMD PHE DTE , BLOCK-RAMNAGAR-1, DIGHA CCC APPLICATION NO-2004746369 CON ID-204313990 | BP-2024-25-255 | 06/06/2024 | 0 | WBSEDCL | 6.93 | 0 | 0 | 0
4580 | PURBA MEDINIPUR | Midnapore Mechanical | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. , SM/12322 | New | Quotation Bill for New Service connection at T/W NO-II Of SANTRA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004746350/QUOT/03 DT. 22-05-2024 Application NO- 2004746350 Application type-New connection Consumer Id- 204313989 | BP-2024-25-256 | 06/06/2024 | 0 | WBSEDCL | 6.93 | 0 | 0 | 0
4581 | PURBA MEDINIPUR | Midnapore Mechanical | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. , SM/12322 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SANTRA and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 463/W/MMD | 20/03/2023 | 712 | CHOWDHURY AND BASU ENTERPRISE | 22.79 | 12.6 | 55.26 | 90
4582 | PURBA MEDINIPUR | Tamluk Division | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. , SM/12322 | New | Sinking of Tube Well ,Construction of 250 Cu.m. Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2852 Nos) For 2 nos Pipe Water Supply Scheme including (Santra & Purba Mukundapur) including two years Operation & Maintainance within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | 2711/TD | 30/10/2023 | 790 | TAPAS SANTRA | 938.36 | 235.32 | 56.5 | 40
4583 | PURBA MEDINIPUR | Central Drilling | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. , SM/11887 | Augmentation | Providing drilling crew and other allied works for construction of TW (300mm x 200mm x 260 mtrs. depth) by utilising Departmental machineries for uttar Khasda WS Scheme (TW-III) contai-I block under Purba midnapore District , CDD, PHE Dte. | 1345/CDD | 24/11/2022 | 30 | MENAKA ENTERPRISE | 19.77 | 14.04 | 100 | 0
4584 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. , SM/11887 | Augmentation | Electric Quotation for UTTAR KHASDA Water Supply SchemeT/W-III (Ref. ID-204049279) | BP-2023-24-136 | 27/07/2023 | 0 | WBSEDCL | 2.59 | 0 | 0 | 0
4585 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. , SM/11887 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Uttar Khasda Water Supply Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 233/TD | 10/01/2024 | 60 | KAMAL KUMAR BERA | 4.02 | 3.82 | 100 | 100
4586 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. , SM/11887 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting Tube Well for Uttar Khasda W/S Scheme within Contai- I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | 1419/TD | 12/07/2023 | 30 | PULAK KUMAR SAMANTA | 8.31 | 7.06 | 85.04 | 100
4587 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. , SM/11887 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. under JJM Program under MMD PHE Dte. | 638/W/MMD | 20/03/2023 | 772 | SOUMEN ELECTRIC | 13.57 | 9.66 | 72.57 | 100
4588 | PURBA MEDINIPUR | Tamluk Division | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13695 | New | Ground water based Mohanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (400 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | 3044/TD | 27/02/2023 | 60 | NARAYAN CHANDRA DAS | 135.23 | 0 | 0 | 0
4589 | PURBA MEDINIPUR | Tamluk Division | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13695 | New | Material Requisition To Resource Division | 2474/TD | 16/01/2023 | 0 | Resource Division | 27.14 | 0 | 0 | 0
4590 | PURBA MEDINIPUR | Tamluk Division | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13695 | New | Ground water based Mohanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (700nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | 3045/TD | 27/02/2023 | 30 | FARID UDDIN AHMED | 89.21 | 23.55 | 26.39 | 30
4591 | PURBA MEDINIPUR | Tamluk Division | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13695 | New | Ground water based Mohanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (591 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | 3046/TD | 27/02/2023 | 30 | ANUSKA ENTERPRISE | 71.82 | 0 | 0 | 0
4592 | PURBA MEDINIPUR | Central Drilling | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13695 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Mohanpur W/S Scheme (T/W-I & II) , Sutahata Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | 1387/CDD | 19/09/2023 | 318 | MENAKA ENTERPRISE | 31.41 | 29 | 100 | 100
4593 | PURBA MEDINIPUR | Tamluk Division | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13695 | New | Material Requisition To Resource Division | 640/W | 20/02/2024 | 0 | Resource Division | 12.26 | 0 | 0 | 0
4594 | PURBA MEDINIPUR | Tamluk Division | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13695 | New | Quotation bill for new service connection at TW-II of Mohanpur w/s scheme,Block-Sutahata under MMD, PHE Dte. Name of C.C.C.-Chaitanyapur Application No.-2004818907 Application type-new connection Reference ID-204355767 Quotation Date-12/07/2024 Quotation Due Date-14/07/2025 Contract Demand-6479 W | BP-2024-25-311 | 02/08/2024 | 0 | WBSEDCL | 3.21 | 0 | 0 | 0
4595 | PURBA MEDINIPUR | Midnapore Mechanical | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13695 | New | Quotation bill for new service connection at TW-I of Mohanpur w/s scheme,Block-Sutahata,under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695195 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-6800W | BP-2024-25-112 | 06/05/2024 | 0 | WBSEDCL | 16.83 | 0 | 0 | 0
4596 | PURBA MEDINIPUR | Midnapore Mechanical | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13695 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MOHANPUR and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 567/W/MMD | 20/03/2023 | 925 | M/S B.M. ELECTRICAL | 22.81 | 16.19 | 71.01 | 70
4597 | PURBA MEDINIPUR | Tamluk Division | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13695 | New | Ground water based Mohanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (400 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | 418/TD | 02/05/2023 | 907 | NARAYAN CHANDRA DAS | 135.23 | 68.23 | 50.45 | 30
4598 | PURBA MEDINIPUR | Tamluk Division | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13695 | New | Ground water based Mohanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (300nos) and Construction of R.C.C. Over Head Reservoir of capacity 300 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | 525/TD | 11/05/2023 | 966 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 175.05 | 32.44 | 18.53 | 25
4599 | PURBA MEDINIPUR | Tamluk Division | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13695 | New | Box Culvert at HW site ,Land Development work & Construction of Retaining wall of ground water based Mohanpur Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2981/TD | 29/11/2023 | 540 | M/S SOURAV MAHAPATRA | 14.92 | 5.92 | 39.69 | 30
4600 | PURBA MEDINIPUR | Tamluk Division | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS , SM/11885 | New | Material Requisition To Resource Division | 3008/TD | 27/02/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
4601 | PURBA MEDINIPUR | Tamluk Division | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS , SM/11885 | New | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(1127 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of capacity 200 cum and staging height 20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall ,Instalation of display Board and 2 yeras Operation & Maintenance under JJM with allied work for Mamudpur PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 1094/TD | 08/06/2023 | 872 | SUJATA CONSTRUCTION | 315 | 83.66 | 26.56 | 20
4602 | PURBA MEDINIPUR | Midnapore Mechanical | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS , SM/11885 | New | Quotation bill for new service connection at TW-I of Mamudpur W/S scheme under MMD PHE Dte. Block-Tamluk Tamluk CCC Application No.-2004916353 Consumer ID.-204409669 | C112402770847 | 05/11/2024 | 0 | WBSEDCL | 3.64 | 0 | 0 | 0
4603 | PURBA MEDINIPUR | Midnapore Mechanical | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS , SM/11885 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 623/W/MMD | 20/03/2023 | 1198 | BHABANI PRASAD MANNA | 23.7 | 0 | 0 | 40
4604 | PURBA MEDINIPUR | Tamluk Division | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS , SM/11885 | New | Land development at Head work site and 2nd Tube well site of Mamudpur Water Supply Scheme within Tamluk Block under Tamluk Sub-Division, PHE Dte. | 1921/TD | 07/06/2024 | 161 | SAYAN CONSTRUCTION | 7.12 | 0 | 0 | 95
4605 | PURBA MEDINIPUR | Tamluk Division | AJAYA & ADJOINING MOUJAS PWSS , SM/12174 | New | Material Requisition To Resource Division | 2976/TD | 27/02/2023 | 0 | Resource Division | 32.62 | 0 | 0 | 0
4606 | PURBA MEDINIPUR | Tamluk Division | AJAYA & ADJOINING MOUJAS PWSS , SM/12174 | New | Material Requisition To Resource Division | 2946/TD | 12/09/2024 | 0 | Resource Division | 11.38 | 0 | 0 | 0
4607 | PURBA MEDINIPUR | Midnapore Mechanical | AJAYA & ADJOINING MOUJAS PWSS , SM/12174 | New | Ajaya W/S scheme T/W -II Application No.-2004565730 Ref.-204193622 | BP-2023-24-592 | 02/02/2024 | 0 | WBSEDCL | 8.24 | 0 | 0 | 0
4608 | PURBA MEDINIPUR | Midnapore Mechanical | AJAYA & ADJOINING MOUJAS PWSS , SM/12174 | New | Ajaya W/S scheme T/W -I Application No.-2004565721 Ref.-204193605 | BP-2023-24-593 | 02/02/2024 | 0 | WBSEDCL | 3.19 | 0 | 0 | 0
4609 | PURBA MEDINIPUR | Central Drilling | AJAYA & ADJOINING MOUJAS PWSS , SM/12174 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 7.83 | 31.7 | 11
4610 | PURBA MEDINIPUR | Tamluk Division | AJAYA & ADJOINING MOUJAS PWSS , SM/12174 | New | Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1847 nos) under JJM with allied work for AJAYA- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1515/TD | 17/07/2023 | 807 | TAPAS SANTRA | 664.53 | 432.68 | 65.11 | 70
4611 | PURBA MEDINIPUR | Midnapore Mechanical | AJAYA & ADJOINING MOUJAS PWSS , SM/12174 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AJAYA and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 2384/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 27.7 | 12.66 | 91.41 | 45
4612 | PURBA MEDINIPUR | Tamluk Division | KHARAT KATBAR & ADJOINING MOUJAS PWSS , SM/12175 | New | Material Requisition To Resource Division | 2450/TD | 16/01/2023 | 0 | Resource Division | 31.66 | 0 | 0 | 0
4613 | PURBA MEDINIPUR | Midnapore Mechanical | KHARAT KATBAR & ADJOINING MOUJAS PWSS , SM/12175 | New | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 0 | 50
4614 | PURBA MEDINIPUR | Tamluk Division | KHARAT KATBAR & ADJOINING MOUJAS PWSS , SM/12175 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kharat Katbar PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | 2198/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4615 | PURBA MEDINIPUR | Tamluk Division | KHARAT KATBAR & ADJOINING MOUJAS PWSS , SM/12175 | New | Material Requisition To Resource Division | 1656/TD | 29/04/2024 | 0 | Resource Division | 11.67 | 0 | 0 | 0
4616 | PURBA MEDINIPUR | Midnapore Mechanical | KHARAT KATBAR & ADJOINING MOUJAS PWSS , SM/12175 | New | Quotation Bill for New Service connection at T/W NO-I Of KHARAT KOTBAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760152/QUOT/03 DT. 04-06-2024 Application NO- 2004760152 Application type-New connection Consumer Id- 204322027 | BP-2024-25-319 | 24/06/2024 | 0 | WBSEDCL | 3.85 | 0 | 0 | 0
4617 | PURBA MEDINIPUR | Midnapore Mechanical | KHARAT KATBAR & ADJOINING MOUJAS PWSS , SM/12175 | New | Quotation Bill for New Service connection at T/W NO-II Of KHARATKOTBAR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-2004811790/QUOT/03 DT. 11-07-2024 Application NO- 2004811790 Application type-New connection Consumer Id- 204351927 | BP-2024-25-565 | 14/08/2024 | 0 | WBSEDCL | 5.76 | 0 | 0 | 0
4618 | PURBA MEDINIPUR | Midnapore Mechanical | KHARAT KATBAR & ADJOINING MOUJAS PWSS , SM/12175 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHARAT KATBAR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 2381/W/MMD | 31/12/2022 | 857 | ECO ENTERPRISE | 25.26 | 15.54 | 61.53 | 85
4619 | PURBA MEDINIPUR | Tamluk Division | KHARAT KATBAR & ADJOINING MOUJAS PWSS , SM/12175 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 69.77 | 12.67 | 51
4620 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. , SM/12177 | Retrofitting | Material Requisition To Resource Division | 2645/TD | 02/02/2023 | 0 | Resource Division | 16.37 | 0 | 0 | 0
4621 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. , SM/12177 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block within Digha Sub-Division of Tamluk Division. | 1890/TD | 24/11/2022 | 60 | H. SAMANTA | 123.68 | 64.87 | 52.46 | 53
4622 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. , SM/12177 | Retrofitting | Construction of approach road at H/W site & 2nd T/W site of Sarrang Water Supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. | 209/TD | 15/01/2025 | 30 | ASEMA ENTERPRISE | 1.95 | 0 | 0 | 0
4623 | PURBA MEDINIPUR | Midnapore Mechanical | AGAR & ADJOINING MOUJAS PWSS , SM/12131 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AGAR & ADJOINING MOUJAS PWSS, Block ¿ Shahid Matangini, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1409/W/MMD | 02/06/2023 | 180 | M/S B.M. ELECTRICAL | 21.62 | 0 | 0 | 0
4624 | PURBA MEDINIPUR | Tamluk Division | AGAR & ADJOINING MOUJAS PWSS , SM/12131 | New | Material Requisition To Resource Division | 3003/TD | 27/02/2023 | 0 | Resource Division | 20.51 | 0 | 0 | 0
4625 | PURBA MEDINIPUR | Tamluk Division | AGAR & ADJOINING MOUJAS PWSS , SM/12131 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Agar PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | 2075/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4626 | PURBA MEDINIPUR | Tamluk Division | AGAR & ADJOINING MOUJAS PWSS , SM/12131 | New | Material Requisition To Resource Division | 76/TD | 05/01/2024 | 0 | Resource Division | 5.13 | 0 | 0 | 0
4627 | PURBA MEDINIPUR | Midnapore Mechanical | AGAR & ADJOINING MOUJAS PWSS , SM/12131 | New | Quotation Bill for Agar Water Supply Scheme T/W-II Matangini CCC,Block=Sahid Matangini Application No=2004676891 Reference ID=204270379 | BP-2024-25-168 | 15/05/2024 | 0 | WBSEDCL | 0.29 | 0 | 0 | 0
4628 | PURBA MEDINIPUR | Midnapore Mechanical | AGAR & ADJOINING MOUJAS PWSS , SM/12131 | New | Quotation Bill for Agar Water Supply Scheme H/W Site Matangini CCC,Block=Sahid Matangini Application No=2004699675 Reference ID=204286135 | BP-2024-25-169 | 15/05/2024 | 0 | WBSEDCL | 5.63 | 0 | 0 | 0
4629 | PURBA MEDINIPUR | Tamluk Division | AGAR & ADJOINING MOUJAS PWSS , SM/12131 | New | Laying distribution pipe line, Pump House , Boundary Wall ,Rising main , O&M and accommodate FHTC (832 nos) under JJM with allied work for AGAR PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (PART-A) | 850/TD | 31/05/2023 | 915 | JAGANNATH MAKAR | 196.83 | 75.94 | 38.58 | 60
4630 | PURBA MEDINIPUR | Central Drilling | AGAR & ADJOINING MOUJAS PWSS , SM/12131 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 44.37 | 86.92 | 11
4631 | PURBA MEDINIPUR | Tamluk Division | AGAR & ADJOINING MOUJAS PWSS , SM/12131 | New | Soil investigation & construction of R.C.C. Elevated Reservoir of capacity 100 cum and staging height 20.00 mtr. with allied works under Agar & its adjoining moujas Water Supply Scheme in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-C) | 1087/TD | 08/06/2023 | 897 | GOUTAM CONSTRUCTION | 75.53 | 0 | 0 | 60
4632 | PURBA MEDINIPUR | Tamluk Division | KHAR & IT'S ADJOINING MOUJAS PWSS , SM/13743 | New | Material Requisition To Resource Division | 2459/TD | 16/01/2023 | 0 | Resource Division | 53.73 | 0 | 0 | 0
4633 | PURBA MEDINIPUR | Tamluk Division | KHAR & IT'S ADJOINING MOUJAS PWSS , SM/13743 | New | Material Requisition To Resource Division | 1655/TD | 29/04/2024 | 0 | Resource Division | 17.55 | 0 | 0 | 0
4634 | PURBA MEDINIPUR | Midnapore Mechanical | KHAR & IT'S ADJOINING MOUJAS PWSS , SM/13743 | New | Quotation Bill for New Service connection at T/W NO-I Of KHAR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATSHPUR C.C.C. Ref. Memo No-2004886304/QUOT/03/581 DT. 06-09-2024 Application NO- 2004886304 Application type-New connection Consumer Id- 204391661 | C092443182184 | 27/09/2024 | 0 | WBSEDCL | 3.56 | 0 | 0 | 0
4635 | PURBA MEDINIPUR | Midnapore Mechanical | KHAR & IT'S ADJOINING MOUJAS PWSS , SM/13743 | New | Quotation Bill for New Service connection at T/W NO-II Of KHAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004671992/QUOT/03/40 DT. 08-04-2024 Application NO- 2004671992 Application type-New connection Consumer Id- 204266827 | BP-2024-25-95 | 24/04/2024 | 0 | WBSEDCL | 5.83 | 0 | 0 | 0
4636 | PURBA MEDINIPUR | Tamluk Division | KHAR & IT'S ADJOINING MOUJAS PWSS , SM/13743 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 22.13 | 2.78 | 51
4637 | PURBA MEDINIPUR | Tamluk Division | KHAR & IT'S ADJOINING MOUJAS PWSS , SM/13743 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Khar at Patashpur - II Block under Tamluk Division, PHE Dte. | 462/TD | 04/02/2025 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
4638 | PURBA MEDINIPUR | Midnapore Mechanical | KHAR & IT'S ADJOINING MOUJAS PWSS , SM/13743 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHAR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 569/W/MMD | 20/03/2023 | 864 | DEY ENTERPRISE | 27.17 | 0 | 0 | 52
4639 | PURBA MEDINIPUR | Tamluk Division | BARAMRIT BERE AND IT'S ADJOINING MOUJAS PWSS , SM/12816 | New | Material Requisition To Resource Division | 2985/TD | 27/02/2023 | 0 | Resource Division | 18.82 | 0 | 0 | 0
4640 | PURBA MEDINIPUR | Tamluk Division | BARAMRIT BERE AND IT'S ADJOINING MOUJAS PWSS , SM/12816 | New | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 3347/TD | 22/03/2023 | 40 | PRANTIK DRILLING AGENCY | 61.77 | 0 | 0 | 50
4641 | PURBA MEDINIPUR | Midnapore Mechanical | BARAMRIT BERE AND IT'S ADJOINING MOUJAS PWSS , SM/12816 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARAMRIT BERE and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 514/W/MMD | 20/03/2023 | 180 | GLACIER ENGINEERING CO. | 22.79 | 20.88 | 91.66 | 100
4642 | PURBA MEDINIPUR | Tamluk Division | BARAMRIT BERE AND IT'S ADJOINING MOUJAS PWSS , SM/12816 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Bar Amrit Bere PWSS at Mahisadal Block under Tamluk Division,PHE Dte. | 384/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4643 | PURBA MEDINIPUR | Tamluk Division | BARAMRIT BERE AND IT'S ADJOINING MOUJAS PWSS , SM/12816 | New | Material Requisition To Resource Division | 96/TD | 05/01/2024 | 0 | Resource Division | 9.24 | 0 | 0 | 0
4644 | PURBA MEDINIPUR | Midnapore Mechanical | BARAMRIT BERE AND IT'S ADJOINING MOUJAS PWSS , SM/12816 | New | Quotation Bill for Baramritberia Water Supply scheme Tube well no.-I Mahishadal CCC Block-Mahishadal Application No.-2004603891 Ref ID.-204219157 Quatation Bill Date.-15/03/2024 | BP-2023-24-890 | 22/03/2024 | 0 | WBSEDCL | 14.61 | 0 | 0 | 0
4645 | PURBA MEDINIPUR | Tamluk Division | BARAMRIT BERE AND IT'S ADJOINING MOUJAS PWSS , SM/12816 | New | Quotation for new service connection at Bar Amritbera w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App No. 2004755767, Ref ID 204319519) | BP-2024-25-295 | 29/07/2024 | 0 | WBSEDCL | 24.37 | 0 | 0 | 0
4646 | PURBA MEDINIPUR | Tamluk Division | BARAMRIT BERE AND IT'S ADJOINING MOUJAS PWSS , SM/12816 | New | Ground water based Bar Amrit Bere Water Supply Scheme by providing Sinking of Tube well, Construction of Pump House, Boundary Wall, Sub-soil Investigation, Construction of OHR (200 Cum), Laying Rising main, Laying of Distribution pipe line, FHTC work and 'Operation & Maintenance' within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1048/TD | 07/06/2023 | 629 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 412.67 | 268.46 | 65.06 | 45
4647 | PURBA MEDINIPUR | Tamluk Division | BARMUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/12878 | New | Material Requisition To Resource Division | 2995/TD | 27/02/2023 | 0 | Resource Division | 26.96 | 0 | 0 | 0
4648 | PURBA MEDINIPUR | Tamluk Division | BARMUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/12878 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Barmunda PWSS at Patashpur-II Block under Tamluk Division,PHE Dte. | 380/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4649 | PURBA MEDINIPUR | Tamluk Division | BARMUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/12878 | New | Material Requisition To Resource Division | 1647/TD | 29/04/2024 | 0 | Resource Division | 9.41 | 0 | 0 | 0
4650 | PURBA MEDINIPUR | Midnapore Mechanical | BARMUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/12878 | New | Quotation Bill for New Service connection at T/W NO-II Of BAMUNDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004889786/QUOT/03 DT. 12-09-2024 Application NO- 2004889786 Application type-New connection Consumer Id- 204393533 | C092445097329 | 30/09/2024 | 0 | WBSEDCL | 4.5 | 0 | 0 | 0
4651 | PURBA MEDINIPUR | Midnapore Mechanical | BARMUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/12878 | New | Quotation Bill for New Service connection at T/W NO-I Of BAMUNDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004657865/QUOT/03 DT. 28-03-2024 Application NO- 2004657865 Application type-New connection Consumer Id- 204257681 | BP-2024-25-29 | 15/04/2024 | 0 | WBSEDCL | 4.23 | 0 | 0 | 0
4652 | PURBA MEDINIPUR | Midnapore Mechanical | BARMUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/12878 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARMUNDA and ADJOINING MOUJAS, Block Potashpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | 938/W/MMD | 28/03/2023 | 180 | MENAKA ENTERPRISE | 22.77 | 17.51 | 76.91 | 65
4653 | PURBA MEDINIPUR | Tamluk Division | BARMUNDA AND IT'S ADJOINING MOUJAS PWSS , SM/12878 | New | Sinking of Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, , Soil investigation & Accommodate FHTC (1527 nos) under JJM with allied work for BARMUNDA- PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | 1672/TD | 25/07/2023 | 707 | HALDIA DEVELOPMENT CONSTRUCTION | 584.47 | 0 | 0 | 48
4654 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II , SM/13716 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paniparul Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | 590/TD | 17/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.77 | 3.77 | 100 | 100
4655 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II , SM/13716 | Augmentation | Material Requisition To Resource Division | 2615/TD | 02/02/2023 | 0 | Resource Division | 122.45 | 0 | 0 | 0
4656 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II , SM/13716 | Augmentation | Material Requisition To Resource Division | 2635/TD | 02/02/2023 | 0 | Resource Division | 23.91 | 0 | 0 | 0
4657 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II , SM/13716 | Augmentation | Electric Quotation for PANIPARUL Water Supply Scheme T/W-II, Zone -II, (Ref. ID-204087320) | BP-2023-24-312 | 01/11/2023 | 0 | WBSEDCL | 2.76 | 0 | 0 | 0
4658 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II , SM/13716 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Paniparul Zone-II Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | 2534/TD | 19/01/2023 | 894 | BASANTA KUMAR MAITY | 644.68 | 352.62 | 54.7 | 78
4659 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II , SM/13716 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well at PANIPARUL ZONE - II Water supply scheme, Egra -II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | 1051/W/MMD | 13/03/2024 | 385 | GLACIER ENGINEERING CO. | 14 | 9.07 | 64.76 | 54
4660 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II , SM/13716 | Augmentation | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 2nd Tube well site of Paniparul Zone-II W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well site of Paniparul Zone-II W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at Head Work site Tube well of Paniparul Zone-II W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 120/TD | 06/04/2023 | 40 | KALPANA BUILDERS | 57.98 | 52.05 | 100 | 100
4661 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II , SM/13716 | Augmentation | Electric Quotation for PANIPARUL Water Supply Scheme T/W-I, Zone- II, (Ref. ID-204128964) | BP-2023-24-389 | 02/12/2023 | 0 | WBSEDCL | 4.9 | 0 | 0 | 0
4662 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II , SM/13716 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE-II Of PANIPARUL W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004773750/QUOT/03/483 DT. 18-06-2024 Application NO- 2004773750 Application type-New connection Consumer Id- 204332477 | BP-2024-25-360 | 01/07/2024 | 0 | WBSEDCL | 3.41 | 0 | 0 | 0
4663 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II , SM/13716 | Augmentation | Construction of Pump House, Boundary Wall, Laying Rising main pipe line & Land development under JJM with allied works for Paniparul (Z-II ) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 2194/TD | 01/09/2023 | 60 | BASANTA KUMAR MAITY | 55.17 | 0 | 0 | 75
4664 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II , SM/13716 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 853/W/MMD | 24/03/2023 | 799 | M/S S.G. ENTERPRISE | 26.86 | 24.84 | 93.95 | 80
4665 | PURBA MEDINIPUR | Tamluk Division | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13740 | New | Material Requisition To Resource Division | 2393/TD | 16/01/2023 | 0 | Resource Division | 30.99 | 0 | 0 | 0
4666 | PURBA MEDINIPUR | Midnapore Mechanical | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13740 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MUKUNDAPUR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 554/W/MMD | 20/03/2023 | 712 | DEBJYOTI BASU | 22.8 | 0 | 0 | 55
4667 | PURBA MEDINIPUR | Tamluk Division | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13740 | New | Material Requisition To Resource Division | 2968/TD | 12/09/2024 | 0 | Resource Division | 8.17 | 0 | 0 | 0
4668 | PURBA MEDINIPUR | Midnapore Mechanical | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13740 | New | Quotation Bill for New Service connection at T/W NO-I Of MUKUNDAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004749319/QUOT/03 DT. 28-05-2024 Application NO- 2004749319 Application type-New connection Consumer Id- 204315788 | BP-2024-25-259 | 06/06/2024 | 0 | WBSEDCL | 2.83 | 0 | 0 | 0
4669 | PURBA MEDINIPUR | Tamluk Division | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS , SM/13740 | New | Bill for payment to WBSEDCL for Shifting of Electric Line for Mukundapur Water Supply Scheme under Tamluk Division, PHE Dte. | BP-2023-24-961 | 14/03/2024 | 0 | WBSEDCL | 2.93 | 0 | 0 | 0
4670 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-I , SM/14839 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | 1859/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 2.95 | 100 | 100
4671 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-I , SM/14839 | Augmentation | Material Requisition To Resource Division | 2080/TD | 28/08/2023 | 0 | Resource Division | 14.36 | 0 | 0 | 0
4672 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-I , SM/14839 | Augmentation | Material Requisition To Resource Division | 3012/TD | 29/11/2023 | 0 | Resource Division | 0.14 | 0 | 0 | 0
4673 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-I , SM/14839 | Augmentation | Laying distribution pipe line, Repair of Pump House , Repair Boundary Wall , land development for approch road & Accommodate FHTC (70 nos) under JJM with allied work for Bathuari (Zone-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | 2600/TD | 10/10/2023 | 813 | DILIP KUMAR GHOSH | 110.33 | 84.13 | 76.25 | 82
4674 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-I , SM/14839 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1242/W/MMD | 28/04/2023 | 764 | BHABANI PRASAD MANNA | 84.29 | 0 | 0 | 70
4675 | PURBA MEDINIPUR | Tamluk Division | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Material Requisition To Resource Division | 2966/TD | 27/02/2023 | 0 | Resource Division | 171.72 | 0 | 0 | 0
4676 | PURBA MEDINIPUR | Tamluk Division | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Material Requisition To Resource Division | 631/W | 20/02/2024 | 0 | Resource Division | 12.74 | 0 | 0 | 0
4677 | PURBA MEDINIPUR | Midnapore Mechanical | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Quotation Bill for New Service connection at T/W NO-I Of ITABERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004601903/QUOT/03 DT. 15-02-2024 Application NO- 2004601903 Application type-New connection Reference Id- 204217836 |  | 24/04/2024 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
4678 | PURBA MEDINIPUR | Midnapore Mechanical | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Quotation Bill for Shifting of 33 KV FEEDER HT LINE AT SABITRAPUR( KANPUR W/S SCHEME ZONE-V, T/W NO-I) , RAMNAGRA -II BLOCK , DIGHA CCC, DIST.-PURBA MEDINIPUR. Ref. MEMO No- CD/1971 Dt. 22.02.2024 Application NO- 100000101137 Dt. 22/02/2024 Reference Id- 860292957 | BP-2023-24-813 | 13/03/2024 | 0 | WBSEDCL | 3.05 | 0 | 0 | 0
4679 | PURBA MEDINIPUR | Midnapore Mechanical | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Electric Quotation for ITABERIA Water Supply Scheme, T/W-I, (Ref. ID-204217836) | BP-2023-24-813 | 13/03/2024 | 0 | WBSEDCL | 0.49 | 0 | 0 | 0
4680 | PURBA MEDINIPUR | Tamluk Division | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Laying distribution pipe line & Accommodate FHTC (120 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-C) | 3461/TD | 27/03/2023 | 988 | JASODA ENTERPRISE | 62.76 | 52.07 | 82.97 | 85
4681 | PURBA MEDINIPUR | Tamluk Division | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Pump House, Laying distribution pipe line & Accommodate FHTC (250 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-D) | 3462/TD | 27/03/2023 | 219 | R CONSTRUCTION | 82.45 | 61.21 | 74.24 | 80
4682 | PURBA MEDINIPUR | Tamluk Division | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Laying distribution pipe line, Boundary Wall & Accommodate FHTC (320 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-E) | 3463/TD | 27/03/2023 | 849 | PARIA ENTERPRISE | 82.41 | 50.9 | 61.76 | 65
4683 | PURBA MEDINIPUR | Tamluk Division | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Laying distribution pipe line & Accommodate FHTC (74 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-F) | 3464/TD | 27/03/2023 | 980 | LAKSHMI NARAYAN ENTERPRISE | 19.34 | 13.18 | 68.17 | 70
4684 | PURBA MEDINIPUR | Central Drilling | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 49.1 | 94.02 | 11
4685 | PURBA MEDINIPUR | Tamluk Division | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Laying distribution pipe line, & Accommodate FHTC (430 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-B) | 565/TD | 12/05/2023 | 867 | JASODA ENTERPRISE | 125.59 | 86.85 | 69.15 | 75
4686 | PURBA MEDINIPUR | Midnapore Mechanical | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
4687 | PURBA MEDINIPUR | Tamluk Division | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | 250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line,Pump House , Boundary Wall, Soil investigation & Accommodate FHTC (460 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur Block within Contai Sub-Division under Tamluk Division, PHE Dte.(PART-A) | 578/TD | 19/02/2025 | 180 | ARABINDA GHOSH | 217.97 | 0 | 0 | 0
4688 | PURBA MEDINIPUR | Midnapore Mechanical | ITA BARIA & ADJOINING MOUZAS , SM/14042 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
4689 | PURBA MEDINIPUR | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Laying distribution pipe line, & Accommodate FHTC (116 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part- E) | 3558/TD | 29/03/2023 | 20 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 14.49 | 8.15 | 56.25 | 60
4690 | PURBA MEDINIPUR | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Material Requisition To Resource Division | 2687/TD | 06/02/2023 | 0 | Resource Division | 21.28 | 0 | 0 | 0
4691 | PURBA MEDINIPUR | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Laying distribution pipe line, & Accommodate FHTC (275 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part- D) | 3557/TD | 29/03/2023 | 30 | BUNBA CONSTRUCTION | 39.82 | 34.71 | 87.17 | 65
4692 | PURBA MEDINIPUR | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 695 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - B ) | 534/TD | 12/05/2023 | 893 | M/S SREE DURGA ENTERPRISE | 199.79 | 154.02 | 77.09 | 75
4693 | PURBA MEDINIPUR | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Laying distribution pipe line, & Accommodate FHTC ( 288 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part- C) | 533/TD | 12/05/2023 | 924 | M/S SREE DURGA ENTERPRISE | 111.4 | 91.22 | 81.89 | 82
4694 | PURBA MEDINIPUR | Central Drilling | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Hiring of Diesel Driven Motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub Division-ll (D),CDD, P.H.Enginering Dte. for supervision of JJM Related works. | 04/CMSD-II(D) | 11/01/2024 | 198 | MD NIZAMUDDIN | 0.94 | 2.36 | 250.95 | 45
4695 | PURBA MEDINIPUR | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Uttar Gopalpur PWSS at Ramnagar-II Block under Tamluk Division,PHE Dte. | 377/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4696 | PURBA MEDINIPUR | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Material Requisition To Resource Division | 109/TD | 05/01/2024 | 0 | Resource Division | 11.75 | 0 | 0 | 0
4697 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Quotation for new service connection at TW-1 of Uttar Gopalpur ws scheme under MMD, PHE Dte. Ref. Application no-2004579816, Ref Con ID-204204428. PICHABONI CCC, Block-Ramnagar-II | BP-2023-24-677 | 15/02/2024 | 0 | WBSEDCL | 4.27 | 0 | 0 | 0
4698 | PURBA MEDINIPUR | Midnapore Mechanical | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Quotation for new service connection at TW-II of Uttar Gopalpur ws scheme under MMD,PHE Dte. Ref Application no-2004579836, CON ID-204204432, PICABONI CCC,Block-Ramnagar II | BP-2023-24-677 | 15/02/2024 | 0 | WBSEDCL | 3.18 | 0 | 0 | 0
4699 | PURBA MEDINIPUR | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( with pile foundation ) & Accommodate FHTC ( 534 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - A) | 1095/TD | 08/06/2023 | 837 | RELIABLE CONSTRUCTIONS | 253.87 | 107.87 | 42.49 | 25
4700 | PURBA MEDINIPUR | Central Drilling | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 55.51 | 101.35 | 11
4701 | PURBA MEDINIPUR | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Drum Sheet walling, left out pipe line, road restoration, Accommodate FHTC (27 Nos) and others allied works under JJM for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - B ) | 3067/TD | 19/09/2024 | 30 | DHANANJOY DAS | 34.51 | 0 | 0 | 0
4702 | PURBA MEDINIPUR | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS , SM/13855 | New | Drum Sheet walling , pipe line(for FHTC), road restoration, Accommodate FHTC (60 Nos) and others allied works under JJM for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part ¿ A ) | 210/TD | 15/01/2025 | 30 | RELIABLE CONSTRUCTIONS | 23.37 | 0 | 0 | 0
4703 | PURBA MEDINIPUR | Tamluk Division | MASHAGON AND ITS ADJOINING MOUJAS PWSS , SM/13883 | New | Material Requisition To Resource Division | 2399/TD | 16/01/2023 | 0 | Resource Division | 3.44 | 0 | 0 | 0
4704 | PURBA MEDINIPUR | Midnapore Mechanical | MASHAGON AND ITS ADJOINING MOUJAS PWSS , SM/13883 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MASHAGON and ADJOINING MOUJAS, Block ¿ contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | 559/W/MMD | 20/03/2023 | 180 | DIPALI CONSTRUCTION | 22.6 | 0 | 0 | 0
4705 | PURBA MEDINIPUR | Tamluk Division | MASHAGON AND ITS ADJOINING MOUJAS PWSS , SM/13883 | New | Material Requisition To Resource Division | 2967/TD | 12/09/2024 | 0 | Resource Division | 2.47 | 0 | 0 | 0
4706 | PURBA MEDINIPUR | Tamluk Division | MASHAGON AND ITS ADJOINING MOUJAS PWSS , SM/13883 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | 1674/TD | 25/07/2023 | 860 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 0 | 0 | 30
4707 | PURBA MEDINIPUR | Midnapore Mechanical | AILAN AND IT'S ADJOINING MOUJAS PWSS , SM/15514 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AILAN and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | 1268/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 27.04 | 0 | 0 | 0
4708 | PURBA MEDINIPUR | Tamluk Division | AILAN AND IT'S ADJOINING MOUJAS PWSS , SM/15514 | New | Material Requisition To Resource Division | 2415/TD | 16/01/2023 | 0 | Resource Division | 25.14 | 0 | 0 | 0
4709 | PURBA MEDINIPUR | Tamluk Division | AILAN AND IT'S ADJOINING MOUJAS PWSS , SM/15514 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Ailan PWSS at Egra-I Block under Tamluk Division, PHE Dte. | 2196/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4710 | PURBA MEDINIPUR | Tamluk Division | AILAN AND IT'S ADJOINING MOUJAS PWSS , SM/15514 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | 2702/TD | 20/10/2023 | 712 | MACKINTOSH BURN LIMITED | 19507.71 | 257.69 | 32.02 | 51
4711 | PURBA MEDINIPUR | Midnapore Mechanical | AILAN AND IT'S ADJOINING MOUJAS PWSS , SM/15514 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
4712 | PURBA MEDINIPUR | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. , SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Chandipur Dev. Block (Av. depth 230 mtr.) = 02 Unit, Haldia Dev. Block (Av. depth 260mtr.) = 01 Unit, Panskura-I Dev. Block (Av. depth 205 mtr.) = 01 Unit & Patashpur-II Dev. Block (Av. depth 230 mtr.) = 02 Unit ] Total 06 Unit. | 1531/TD | 11/01/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 64.74 | 63.36 | 100 | 100
4713 | PURBA MEDINIPUR | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. , SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Bhagwanpur-II Dev. Block (Av. depth 230 mtr.) = 07 Unit ] Total 07 Unit. | 1530/TD | 11/01/2022 | 50 | MIDNAPUR PIPE CONCERN | 66.72 | 65.61 | 100 | 100
4714 | PURBA MEDINIPUR | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. , SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Deshpran Dev. Block (Av. depth 230 mtr.) = 01 Unit ] Total 01 Unit. Name of Site : i) G.P.- Basntia, Mouza- Purba Mukundapur, J.L. No.- 488, Plot No.- 120 under Deshpran Dev. Block | 1528/TD | 11/01/2022 | 20 | SUBRATA KUMAR BERA | 11.09 | 11.03 | 100 | 100
4715 | PURBA MEDINIPUR | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. , SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Ramnagar-I Dev. Block (Av. depth 230mtr.) = 01 Unit, Ramnagar-II Dev. Block (Av. depth 205mtr.) = 02 Unit & Egra-II Dev. Block (Av. depth 205mtr.) = 02 Unit ] Total 05 Unit. Name of Site : i) G.P.- Talgachari-I, Mouza- Talgachari, J.L. No.-108, Plot No.- 633 under Ramnagar-I Dev. Block, ii) G.P.- Balisai, Mouza- Bararankua, J.L. No.-200, Plot No.-307 under Ramnagar-II Dev. Block, iii) G.P.-Maithana, Mouza - Demuria Paikbar, J.L. No.-142, Plot No.-275 under Ramnagar-II Dev. Block, iv) G.P.- Paniparul, Mouza -Paniparul, J.L. No.-203, Plot No.-3329 under Egra-II Dev. Block & v) G.P.- Dubda, Mouza- Dubda, J.L. No.-191, Plot No.-38 under Egra-II Dev. Block. | 1526/TD | 11/01/2022 | 45 | BASANTA KUMAR MAITY | 53.79 | 53.72 | 100 | 100
4716 | PURBA MEDINIPUR | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. , SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Nandakumar Dev. Block (Av. depth 260 mtr.) = 02 Unit, Mahishadal Dev. Block (Av. depth 260mtr.) = 01 Unit, Sutahata Dev. Block (Av. depth 260 mtr.) = 02 Unit & Kolaghat Dev. Block (Av. depth 205 mtr.) = 01 Unit ] Total 06 Unit. | 1529/TD | 11/01/2022 | 45 | ARABINDA GHOSH | 69.7 | 65.53 | 100 | 100
4717 | PURBA MEDINIPUR | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. , SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the New Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Tamluk Dev. Block (Av. depth 205 mtr.) = 03 Unit, Sahid Matangini Dev. Block (Av. depth 205mtr.) = 01 Unit & Egra-II Dev. Block (Av. depth 205mtr.) = 02 Unit ] Total 06 Unit. Name of Site : i) G.P.- Anantapur-I, Mouza- Maisali, J.L. No.-127, Plot No.- 16 under Tamluk Dev. Block, ii) G.P.- Municipality, Mouza- Daharpur, J.L. No.- 276, Plot No.- 442 under Tamluk Dev. Block, iii) G.P.- Pipulberia-I, Mouza - Gaurangapur, J.L. No.-150, Plot No.- 373 under Tamluk Dev. Block, iv) G.P.- Balluk-I, Mouza - Janubasan RH, J.L. No.- 44, Plot No.- 40 under Sahid Matangini Dev. Block, v) G.P.- Sarbodaya, Mouza- Naskarpur, J.L. No.-262, Plot No.- 120 under Egra-II Dev. Block & vi) G.P.- Basudevpur, Mouza- Shyamharibar, J.L. No.- 266, Plot No.- 3611 under Egra-II Dev. Block. | 175/TD | 25/04/2022 | 45 | CHANDA AGENCIES | 62.48 | 59.93 | 100 | 100
4718 | PURBA MEDINIPUR | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. , SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Khejuri-II Dev. Block (Av. depth 260 mtr.) = 01 Unit ] Total 01Unit. Name of Site : i) G.P.- Nijkasba, Mouza- Thanaberia, J.L. No.- 98, Plot No.- 328 under Khejuri-II Dev. Block. | 296/TD | 06/05/2022 | 25 | SK. NUR ISLAM | 11.05 | 10.88 | 100 | 100
4719 | PURBA MEDINIPUR | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. , SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Bhagwanpur-I Dev. Block (Av. depth 230 mtr.) = 03 Unit & Khejuri-II Dev. Block (Av. depth 260 mtr.) = 02 Unit ] Total 05 Unit. | 1532/TD | 11/01/2022 | 45 | MIDNAPUR PIPE CONCERN | 50.45 | 48.67 | 100 | 100
4720 | PURBA MEDINIPUR | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. , SM/08759 | Retrofitting | Continuation Work Order for Hiring of Diesel Motor Cab/ Luxury Taxy (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.12.2022 to 31.05.2023 i.e. 06 b(Six) months for the use of the office of the Assistant Engineer, RWS Tamluk Sub-Division, PHE Dte. | 375/RWS/TSD | 30/11/2022 | 156 | SRIMANTA PANJA | 0.74 | 2.35 | 100 | 100
4721 | PURBA MEDINIPUR | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. , SM/08759 | Retrofitting | Diesel Motor Cab/Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage IV) on daily rate basis for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, PHE Dte. from 01.07.2023 to 31.12.2023 (Six) Months. | 1299/TD | 30/06/2023 | 184 | JOY MAA TARA TRAVELS & TRANSPORT | 0.87 | 0.37 | 100 | 100
4722 | PURBA MEDINIPUR | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. , SM/08759 | Retrofitting | Installation of display Board at 54 nos. different work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | 3288/TD | 05/10/2024 | 20 | MISHRA ENTERPRISE | 9 | 0 | 0 | 100
4723 | PURBA MEDINIPUR | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. , SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Contai-I Dev. Block (Av. depth 205 mtr.) = 01 Unit & Contai-III Dev. Block (Av. depth 260 mtr.) = 01 Unit ] Total 02 Unit. Name of Site : i) G.P.- Sabajpur, Mouza- Sabajpur, J.L. No.- 296, Plot No.- 503 under Contai-I Dev. Block, & ii) G.P.- Debendra, Mouza- Balageria, J.L. No.- 79, Plot No.- 250 under Contai-III Dev. Block, | 1527/TD | 11/01/2022 | 30 | SRIMANTA KUMAR MAITY | 22.46 | 10.79 | 50.43 | 100
4724 | PURBA MEDINIPUR | Tamluk Division | PANCHBERYA PIPED WATER SUPPLY SCHEME , SM/16201 | New | Material Requisition To Resource Division | 3017/TD | 27/02/2023 | 0 | Resource Division | 7.21 | 0 | 0 | 0
4725 | PURBA MEDINIPUR | Midnapore Mechanical | PANCHBERYA PIPED WATER SUPPLY SCHEME , SM/16201 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at PANCHBERYA PIPED WATER SUPPLY SCHEME in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1217/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 11.87 | 0 | 0 | 40
4726 | PURBA MEDINIPUR | Tamluk Division | PANCHBERYA PIPED WATER SUPPLY SCHEME , SM/16201 | New | Material Requisition To Resource Division | 116/TD | 05/01/2024 | 0 | Resource Division | 0.81 | 0 | 0 | 0
4727 | PURBA MEDINIPUR | Tamluk Division | PANCHBERYA PIPED WATER SUPPLY SCHEME , SM/16201 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 50 cum OHR & Accommodate FHTC (131 nos) under JJM with allied work for PANCHBERRYA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | 1742/TD | 01/08/2023 | 719 | S.D. CONSTRUCTION | 141.9 | 0 | 0 | 0
4728 | PURBA MEDINIPUR | Tamluk Division | Balance Work for Retrofitting to Accommodate FHTC (610 Nos.) and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different Nodal Point under JJM in Dona Zone-I Water Supply Scheme for Block-Moyna in the District of Purba Me , SM/16452 | Retrofitting | Laying of Left-Out portion uPVC Pipe line due to uncovered area under Dona Zone-I Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte.(Phase-II) | 249/TD | 19/04/2023 | 30 | GHOSH ENTERPRISE | 85.84 | 79.22 | 92.29 | 95
4729 | PURBA MEDINIPUR | Tamluk Division | Balance Work for Retrofitting to Accommodate FHTC (610 Nos.) and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different Nodal Point under JJM in Dona Zone-I Water Supply Scheme for Block-Moyna in the District of Purba Me , SM/16452 | Retrofitting | Retrofitting to accommodate FHTC (610 nos.) under JJM in Dona Zone-I Water Supply Scheme within Moyan Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-II) | 250/TD | 19/04/2023 | 25 | GHOSH ENTERPRISE | 23.24 | 0 | 0 | 0
4730 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block (Phase-II) , SM/16453 | Retrofitting | Material Requisition To Resource Division | 2096/TD | 29/08/2023 | 0 | Resource Division | 26.91 | 0 | 0 | 0
4731 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block (Phase-II) , SM/16453 | Retrofitting | Material Requisition To Resource Division | 2636/TD | 13/10/2023 | 0 | Resource Division | 8.14 | 0 | 0 | 0
4732 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block (Phase-II) , SM/16453 | Retrofitting | Providing 1321 Nos FHTC (Functional Household Tap Connection) with allied works of Arjunnagar & its adjoining mouzas Water Supply Scheme under Bhagawanpur-II Block under Contai Sub Division of Tamluk Division, PHE DTe.Purba Medinipur (Phase -II) | 1069/TD | 08/06/2023 | 45 | TAPAS SANTRA | 91.09 | 0 | 0 | 0
4733 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Paya (Mahaprabhu) PWSS under Ramnagar-I Block (Phase-II) , SM/16467 | Retrofitting | Retrofitting to accommodate FHTC under JJM in PAYA ( MAHAPRABHU) PWSS ( Phase-II) Block - Ramnagar-I in the District of Purba Medinipur. | 240/TD | 19/04/2023 | 30 | MAITY CONSTRUCTION | 67.92 | 57.26 | 100 | 100
4734 | PURBA MEDINIPUR | Tamluk Division | DAHA DAYA PIPED WATER SUPPLY SCHEME. , SM/15849 | New | Material Requisition To Resource Division | 2672/TD | 06/02/2023 | 0 | Resource Division | 10.22 | 0 | 0 | 0
4735 | PURBA MEDINIPUR | Tamluk Division | DAHA DAYA PIPED WATER SUPPLY SCHEME. , SM/15849 | New | Material Requisition To Resource Division | 93//TD | 05/01/2024 | 0 | Resource Division | 1.66 | 0 | 0 | 0
4736 | PURBA MEDINIPUR | Midnapore Mechanical | DAHA DAYA PIPED WATER SUPPLY SCHEME. , SM/15849 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at DAHA DAYA PIPED WATER SUPPLY SCHEME in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1214/W/MMD | 25/04/2023 | 889 | THE GODFATHER TRADING COMPANY | 12.14 | 5.32 | 43.85 | 65
4737 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bajkul, Zone-I, Zone-II & Zone-III PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16887 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at MAHAMMADPUR and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 649/HESD | 08/07/2024 | 15 | SOUMEN ELECTRIC | 1.94 | 0 | 0 | 100
4738 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Bajkul, Zone-I, Zone-II & Zone-III PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16887 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4739 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Barsundra PWSS in the District of Purba Medinipur under JJM programme. , SM/16662 | Augmentation | Quotation Bill for new service connection at TW-III of Barsundra w/s scheme,under MMD,PHE,Dte.,Purba Medinipur Block-Haldia, C.C.C.-Brajalalchak Application no.-2004651015 Application Type-New connection Quotation Date-22/03/2024 Quotation Due Date-24/03/2025 Contract Demand-10209 W | BP-2024-25-17 | 08/04/2024 | 0 | WBSEDCL | 4.22 | 0 | 0 | 0
4740 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Basudebberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16861 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
4741 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Basudebberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16861 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4742 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Begunberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16862 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
4743 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Begunberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/16862 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4744 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amtalia Accommodate FHTC under Contai-II (Deshapran) Block within Purba Medinipur District. , SM/15635 | Augmentation | Laying of different dia HDPE Pipe line to accommodate remaining FHTC under Augmentation of Amtalia PWSS within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division,PHE Dte., in the District of Purba Medinipur | 285/TD | 20/04/2023 | 40 | GHOSH ENTERPRISE | 56.31 | 55.82 | 100 | 100
4745 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Baranalgeria Zone I & II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17864 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
4746 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Baranalgeria Zone I & II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17864 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4747 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at lakshya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17768 | Solarisation | Solarization of grid connected pumping installation at lakshya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1014/W/MMD | 29/03/2023 | 180 | MEGA SOLAR ENERGY | 6.26 | 4.79 | 76.55 | 70
4748 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at lakshya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17768 | Solarisation | Electric Quotation for LAKSHYA Water Supply Scheme T/W-I, (Ref. ID-202988902) | BP-2023-24-269 | 10/10/2023 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
4749 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at lakshya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17768 | Solarisation | Quotation for net billing meter at Lakshya w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (Con ID - 202988902 & Application No.- 2004450559) | BP-2023-24-681 | 15/02/2024 | 0 | WBSEDCL | 0.37 | 0 | 0 | 0
4750 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kapaseria PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17769 | Solarisation | Solarization of grid connected pumping installation at Kapaseria PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1042/W/MMD | 29/03/2023 | 180 | SUBHASIS ROY | 6.26 | 0 | 0 | 0
4751 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kudi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17773 | Solarisation | Solarization of grid connected pumping installation at Kudi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1008/W/MMD | 29/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
4752 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kudi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17773 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0.18 | 96.99 | 100
4753 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Dona PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17777 | Solarisation | Solarization of grid connected pumping installation at Dona PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1044/W/MMD | 29/03/2023 | 180 | AMITAVA CHAKRABORTY | 12.52 | 0 | 0 | 0
4754 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Gobra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17783 | Solarisation | Solarization of grid connected pumping installation at Gobra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1034/W/MMD | 29/03/2023 | 180 | UTTAM KUMAR CHATTERJEE | 6.26 | 0 | 0 | 0
4755 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Gobra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17783 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0.18 | 96.99 | 100
4756 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Haipur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17786 | Solarisation | Solarization of grid connected pumping installation at Haipur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1001/W/MMD | 29/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 0 | 0 | 0
4757 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Kotbar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17787 | Solarisation | Solarization of grid connected pumping installation at Kotbar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 996/W/MMD | 29/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 4.88 | 78.03 | 80
4758 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Gobindanagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17801 | Solarisation | Solarization of grid connected pumping installation at Gobindanagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1027/W/MMD | 29/03/2023 | 180 | KAMAKSHYA ENTERPRISE | 6.26 | 0 | 0 | 0
4759 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Tajpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17804 | Solarisation | Solarization of grid connected pumping installation at Tajpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1026/W/MMD | 29/03/2023 | 180 | SUBHASIS ROY | 6.26 | 0 | 0 | 0
4760 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Uttardalhara Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17809 | Solarisation | Solarization of grid connected pumping installation at Uttardalhara Zone-I and Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1049/W/MMD | 29/03/2023 | 180 | A-NIK & CO. | 12.52 | 0 | 0 | 40
4761 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Dhanghara PWSS to Accommodate FHTC under JJM with Allied works under Contai-III Block (Phase-II) , SM/16946 | Augmentation | Laying Distribution Pipe Line With allied Works for Augmentation Of Dhanghara Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division,PHE Dte., Purba Medinipur District. (PHASE-II) | 665/TD | 19/05/2023 | 30 | M/S S. S. ENTERPRISE | 58.98 | 56.28 | 95.42 | 100
4762 | PURBA MEDINIPUR | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Bajkul, Zone-I PWSS in the District of Purba Medinipur under JJM programme. , SM/16653 | Augmentation | Rejuvenation of Electro-Mechanical components of Bajkul, Zone-I PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | 758/W/MMD | 23/03/2023 | 1269 | SOUMEN ELECTRIC | 11.85 | 5.47 | 58.53 | 40
4763 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Junbani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17718 | Solarisation | Solarization of grid connected pumping installation at Junbani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1002/W/MMD | 29/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 6.26 | 4.85 | 77.48 | 35
4764 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Murisai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17861 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
4765 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Murisai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17861 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4766 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Moyna, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17866 | IOT | Supply and installation of Sign Board for depicting the scheme details of different on going Design development works for the purpose of Geotagging at different PWSS under Moyna block under MMD, P.H.E. Dte.in the Dist. of Purba Medinipur. | 625/HESD | 08/07/2024 | 7 | S.S.GHORAI | 0.9 | 0 | 0 | 0
4767 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Moyna, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17866 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4768 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mandarmani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17900 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
4769 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mandarmani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17900 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4770 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kalindi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17910 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
4771 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kalindi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17910 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4772 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Pratapdighi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17848 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
4773 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Pratapdighi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17848 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4774 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kasbagola PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17849 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
4775 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kasbagola PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17849 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4776 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Thenkuachak Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17746 | Solarisation | Solarization of grid connected pumping installation at Thenkuachak Zone-I and Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1046/W/MMD | 29/03/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 12.52 | 4.85 | 38.74 | 47
4777 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Thenkuachak Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17746 | Solarisation | Quotation bill for application fees of NET METERING for solar power plant at Thenkuachak Z-I w/s scheme, Block-Nandakumar in the Dist. of Purba Medinipur under MMD PHE Dte. Name of C.C.C.-Nandakumar Application No.-2004846740 Consumer ID-222053439 Issuance Date-01/08/2024 | C092443151789 | 27/09/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
4778 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Betkundu PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17298 | Solarisation | Solarization of grid connected pumping installation at Betkundu PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 732/W/MMD | 23/03/2023 | 180 | MEGA SOLAR ENERGY | 6.26 | 4.79 | 76.55 | 70
4779 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Betkundu PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17298 | Solarisation | Quotation for net billing meter at Betkundu w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (Con ID - 222016853 & Application No.- 2004450537) | BP-2023-24-674 | 15/02/2024 | 0 | WBSEDCL | 0.42 | 0 | 0 | 0
4780 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chirulia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17323 | Solarisation | Solarization of grid connected pumping installation at Chirulia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 728/W/MMD | 23/03/2023 | 180 | P.K.ENGINEERING | 6.26 | 0 | 0 | 0
4781 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chirulia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17323 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0.18 | 100 | 50
4782 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Dakshin Mechogram Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17193 | Augmentation | Material Requisition To Resource Division | 346/TD | 26/04/2023 | 0 | Resource Division | 4.41 | 0 | 0 | 0
4783 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Dakshin Mechogram Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17193 | Augmentation | Electric Quotation for DAKSHIN MECHOGRAM Water Supply Scheme T/W- III, (Ref. ID-204066734) | BP-2023-24-205 | 24/08/2023 | 0 | WBSEDCL | 3.77 | 0 | 0 | 0
4784 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Dakshin Mechogram Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17193 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1209/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 53.9 | 12.51 | 92.86 | 35
4785 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Dakshin Mechogram Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17193 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 54.95 | 100
4786 | PURBA MEDINIPUR | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Dakshin Mechogram Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17193 | Augmentation | Name of Work: Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Gobindanagar W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Dakshin Mechogram W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 117/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 37.12 | 16.48 | 100 | 100
4787 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Dakshin Mechogram Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17193 | Augmentation | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 0 | 100
4788 | PURBA MEDINIPUR | Tamluk Division | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17194 | Augmentation | Material Requisition To Resource Division | 348/TD | 26/04/2023 | 0 | Resource Division | 8.83 | 0 | 0 | 0
4789 | PURBA MEDINIPUR | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17194 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 1204/W/MMD | 25/04/2023 | 740 | BHABANI PRASAD MANNA | 77.91 | 0 | 0 | 55
4790 | PURBA MEDINIPUR | Tamluk Division | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17194 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 116/TD | 06/04/2023 | 40 | AQUATECH ENGINEERS | 74.22 | 35.83 | 100 | 100
4791 | PURBA MEDINIPUR | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17194 | Augmentation | Additional quotation for Kulbari w/s scheme PH III in the district of Purba Medinipur under MMD PHE Dte. (App ID 100000118086, Con ID 860311696) | C102415733205 | 05/10/2024 | 0 | WBSEDCL | 0.38 | 0 | 0 | 0
4792 | PURBA MEDINIPUR | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17194 | Augmentation | Quotation bill for new service connection at Kulbari Boosting TW IV Application No.-2004567339, Ref ID.-204195755 | BP-2023-24-725 | 23/02/2024 | 0 | WBSEDCL | 11.01 | 0 | 0 | 0
4793 | PURBA MEDINIPUR | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. , SM/17194 | Augmentation | Quotation bill for new service connection at Kulbari w/s scheme boosting TW III Application No.-2004567719, Ref.-204195754 | BP-2023-24-724 | 23/02/2024 | 0 | WBSEDCL | 10.34 | 0 | 0 | 0
4794 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dulalpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17908 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0 | 0 | 50
4795 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Dulalpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17908 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4796 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kanaidighi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17912 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
4797 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Kanaidighi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17912 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4798 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Solat PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17726 | Solarisation | Solarization of grid connected pumping installation at Solat PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1012/W/MMD | 29/03/2023 | 180 | AMITAVA CHAKRABORTY | 6.26 | 0 | 0 | 0
4799 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Sarrang PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17834 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
4800 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Sarrang PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17834 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4801 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Narandia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17835 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0 | 0 | 100
4802 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Narandia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17835 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4803 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Jagatpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte , SM/17891 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4804 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Paschim Kamarda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17903 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
4805 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Paschim Kamarda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17903 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4806 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Asthichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17329 | Solarisation | Solarization of grid connected pumping installation at Asthichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 726/W/MMD | 23/03/2023 | 707 | P.K.ENGINEERING | 6.26 | 0 | 0 | 80
4807 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Asthichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17329 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 532/HESD | 10/06/2024 | 15 | THE GODFATHER TRADING COMPANY | 5.28 | 0.18 | 100 | 50
4808 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chirulia Chalta PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17352 | Solarisation | Solarization of grid connected pumping installation at Chirulia Chalta PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 755/W/MMD | 23/03/2023 | 180 | JYOTY SOLAR POWER | 24.67 | 0 | 0 | 0
4809 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Chirulia Chalta PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17352 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0.18 | 25.15 | 100
4810 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Madhakhali PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17904 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at MAHAMMADPUR and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 649/HESD | 08/07/2024 | 15 | SOUMEN ELECTRIC | 1.94 | 0 | 0 | 100
4811 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Madhakhali PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17904 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4812 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Natshallakhya, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17847 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | 727/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
4813 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Natshallakhya, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17847 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4814 | PURBA MEDINIPUR | Midnapore Mechanical | Solarization of grid connected pumping installation at Majna PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/17817 | Solarisation | Solarization of grid connected pumping installation at Majna PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | 1003/W/MMD | 29/03/2023 | 180 | S.S.GHORAI | 6.25 | 0 | 0 | 0
4815 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11471 | Augmentation | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube well site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1876/TD | 22/11/2022 | 30 | PRASANTA MONDAL | 4.13 | 4 | 96.97 | 0
4816 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11471 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 3rt Tube Well site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | 1879/TD | 22/11/2022 | 60 | DIPANKAR MALAKAR | 5.11 | 5.09 | 99.71 | 100
4817 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11471 | Augmentation | Construction of boundary wall in 3rd tubewell site of Natshal Lakshya Zone II under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) | 1080/TD | 08/06/2023 | 30 | M/S SOURAV MAHAPATRA | 5.91 | 5.27 | 100 | 100
4818 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11471 | Augmentation | Electric Quotation for NATSHALLAKHYA Water Supply Scheme Z-II, T/W-III (Ref. ID-204048971) | BP-2023-24-140 | 27/07/2023 | 0 | WBSEDCL | 4.26 | 0 | 0 | 0
4819 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11471 | Augmentation | Augmentation of ground water based Natshal Lakshya Zone-II Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | 2594/TD | 30/01/2023 | 180 | RAJ KUMAR SINGHA | 986.55 | 183.73 | 68.36 | 65
4820 | PURBA MEDINIPUR | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11471 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | 634/W/MMD | 20/03/2023 | 180 | JOYSHREE CONCERN | 13.56 | 13.46 | 100 | 90
4821 | PURBA MEDINIPUR | Central Drilling | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11471 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Natshal Lakshya W/S Scheme (Z-II, T/W-II), Mahisadal Block under Purba Midnapur District, Central Drilling Division, P.H.E. Dte. | 876/CDD | 11/07/2023 | 386 | MENAKA ENTERPRISE | 21.16 | 19.11 | 100 | 100
4822 | PURBA MEDINIPUR | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. , SM/11471 | Augmentation | Installation of 4 Nos. Display Board at different PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte.(for Tabakhali PWSS, Dakshinchak Zone-1 PWSS, Dakshinchak Zone-II PWSS, Natshal lakshya Zone-II PWSS) (Phase-V) | 766/HSD, | 27/02/2024 | 7 | SNEHASIS BERA | 0.83 | 0.83 | 100 | 100
4823 | PURBA MEDINIPUR | Tamluk Division | HOGALBERYA AND ADJOINING MOUJAS PWSS , SM/12150 | New | Material Requisition To Resource Division | 2683/TD | 06/02/2023 | 0 | Resource Division | 16.55 | 0 | 0 | 0
4824 | PURBA MEDINIPUR | Midnapore Mechanical | HOGALBERYA AND ADJOINING MOUJAS PWSS , SM/12150 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HOGALBERYA and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | 2344/W/MMD | 29/12/2022 | 180 | BHABANI PRASAD MANNA | 25.26 | 0 | 0 | 40
4825 | PURBA MEDINIPUR | Tamluk Division | HOGALBERYA AND ADJOINING MOUJAS PWSS , SM/12150 | New | Material Requisition To Resource Division | 122/TD | 05/01/2024 | 0 | Resource Division | 16.51 | 0 | 0 | 0
4826 | PURBA MEDINIPUR | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/18765 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur Districtunder JJM Program under MMD PHE Dte. | 3091/W/MMD | 29/11/2023 | 180 | M/S. S.R. ENTERPRISE | 11.83 | 0 | 0 | 0
4827 | PURBA MEDINIPUR | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. , SM/18765 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | 119/TD | 06/04/2023 | 703 | B. K. ENTERPRISE | 53.77 | 0 | 0 | 75
4828 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I , SM/18766 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | 1933/TD | 28/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.37 | 100 | 100
4829 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I , SM/18766 | Augmentation | Material Requisition To Resource Division | 2074/TD | 28/08/2023 | 0 | Resource Division | 13.25 | 0 | 0 | 0
4830 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I , SM/18766 | Augmentation | Material Requisition To Resource Division | 3001/TD | 29/11/2023 | 0 | Resource Division | 2.99 | 0 | 0 | 0
4831 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I , SM/18766 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Zone-I PWSS at Ramnagar-I Block under Tamluk Division,PHE Dte. | 375/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4832 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-I , SM/18766 | Augmentation | Quotation for new service connection at Zone-1, TW-1 of Shankarpur (Ramnagar)ws scheme under MMD,PHE Dte Ref. Application no.-2004577423, Con ID-204203250 | BP-2023-24-675 | 15/02/2024 | 0 | WBSEDCL | 7.83 | 0 | 0 | 0
4833 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I , SM/18766 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, ZONE-I Of SANKARPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004721008/QUOT/03 DT. 07-05-2024 Application NO- 2004721008 Application type-New connection Consumer Id- 204298882 | BP-2024-25-170 | 10/06/2024 | 0 | WBSEDCL | 31.79 | 0 | 0 | 0
4834 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I , SM/18766 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 355 Nos) under JJM with allied work for SANKARPUR (Zone-I) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | 1757/TD | 01/08/2023 | 909 | SUSIL KUMAR HAZRA | 193.96 | 49.81 | 25.68 | 55
4835 | PURBA MEDINIPUR | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-I , SM/18766 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-I in Purba Medinipur District,under JJM Program under MMD PHE Dte. | 2289/W/MMD | 29/08/2023 | 701 | S.S.GHORAI | 23.52 | 11.31 | 48.11 | 90
4836 | PURBA MEDINIPUR | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I , SM/18766 | Augmentation | Laying distribution pipe line due to Re-design, & Accommodate Balance FHTC ( 155 Nos) under JJM with allied work for SANKARPUR (Zone-I) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. (Part Work Order 1/2) | 315/TD | 22/01/2025 | 30 | PRANAB KUMAR DAS | 49.33 | 0 | 0 | 0
4837 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Thenkuachak, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/18913 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at DAKSHIN GUMAI and adjacent PWSS under Nandakumar, Sutahata, Haldia and Nandigram-I under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | 533/HESD | 10/06/2024 | 15 | S.S.GHORAI | 3.23 | 0 | 0 | 90
4838 | PURBA MEDINIPUR | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Thenkuachak, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. , SM/18913 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | 2068/W/MMD | 03/12/2025 | 153 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 0
4839 | PURBA MEDINIPUR | Tamluk Division | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computer of Different Water Testing Laboratories Under Tamluk Division P.H.E. Dte. , SM/19271 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plastic ware etc. required for smooth running of the Laboratories for the year 2024- 2025 in the District of Purba Medinipur Under Tamluk Division P.H.E. Dte. Total Nos of Laboratories = 17 Nos including Digha S.D. Lab & 7 Nos N.G.O managed. | 1245/TD | 30/04/2025 | 40 | UTSAV AGENCY | 99.24 | 0 | 0 | 85
4840 | PURBA MEDINIPUR | Tamluk Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/09021 | Support-WQMSP | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. |  | 03/11/2022 | 0 | DISTRICT HEALTH AND FAMILY WELFARE SAMITI TAMLUK HEALTH DISTRICT | 13 | 0 | 0 | 0
4841 | PURBA MEDINIPUR | Tamluk Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/09021 | Support-WQMSP | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. |  | 03/11/2022 | 0 | DISTRICT HEALTH AND FAMILY WELFARE SAMITI NANDIGRAM HEALTH DISTRICT | 7 | 0 | 0 | 0
4842 | PURBA MEDINIPUR | Tamluk Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/09021 | Support-WQMSP | Drinking Water Sample Collection & testing through Filed Test Kids (FTKS) & uploading charges for the same related to water quality monitoring & surveillance programme. | BP-2022-23-48 | 30/05/2022 | 0 | DIST HWALTH FW SAMITY AC MAIN ACCOUNT FOR NON NHM | 11.63 | 0 | 0 | 0
4843 | PURBA MEDINIPUR | Tamluk Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/09021 | Support-WQMSP | Drinking Water Sample Collection & testing through Filed Test Kids (FTKS) & uploading charges for the same related to water quality monitoring & surveillance programme. | BP-2022-23-47 | 30/05/2022 | 0 | DISTRICT HEALTH AND FAMILY WELFARE SAMITI NANDIGRAM HEALTH DISTRICT | 10.09 | 0 | 0 | 0
4844 | PURBA MEDINIPUR | Tamluk Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/09021 | Support-WQMSP | Supply and delivery of FTK Kit, training programme of facilitators, Drinking Water Sample Collection & Testing through Field Test Kit (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme within Tamluk Division, PHE Dte. under Jal Jiban Mission. | 1132/TD | 25/11/2021 | 90 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 74.92 | 22.03 | 30.82 | 0
4845 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Operation and Maintenance of laboratory activity for Physical, Chemical and Bacteriological testing of water at Contai Sub Divisional Laboratory of Public Health Engineer Dte. at Contai under Tamluk Division for the period from 01/01/2021 to 30/09/2021.( 9 months) | 2581/TD | 30/12/2020 | 274 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.54 | 4.54 | 100 | 100
4846 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Operation and Maintenance of laboratory activity for Physical, Chemical and Bacteriological testing of water at Contai Sub Divisional Laboratory of Public Health Engineer Dte. at Contai under Tamluk Division for the period from 01/10/2021 to 30/06/2022.( 9 months) | 806-A/TD | 29/09/2021 | 273 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.36 | 4.36 | 100 | 100
4847 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Providing services for operation of 07 (Seven) nos. PHED managed Sub-District laboratories under Tamluk Division, PHE Dte. by engaging one Chemist/Bacteriologist and one Laboratory Assistant for each laboratory capable to analyze chemical, bacteriological and physical parameter of water with sophisticated and prescribed electronic equipment including sending data through smart phone, preparation of test result, cleaning of instruments, glassware furniture etc. and other laboratory related works as per guidelines of WSSO, PHE Department for 12 (Twelve) Months. | 2354/TD | 31/03/2022 | 365 | UTSAV AGENCY | 24.85 | 24.18 | 100 | 0
4848 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Engagement of 3 Nos. Laboratory Personnel (One No. Chemist / Bacteriologist, One no. Laboratory Assistant & One no. Sampling Assistant) for regular analysis, testing, and monitoring of water sample and other allied minor mtc. Work of Digha Sub-Divisional Laboratory under Digha Sub-Division of Tamluk Division, PHE Dte. for the period from 01/04/2020 to 31/03/2021 i.e. 12 (twelve) months. | 2497/TD | 31/03/2020 | 0 | ARUNALOY SCIENTIFIC HOUSE | 4.81 | 0.56 | 100 | 0
4849 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. | BP-2023-24-31 | 29/04/2023 | 0 | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 1.32 | 0 | 0 | 0
4850 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Bill for contingency expenses of Sri Ramkrishna Guchha Samity Water testing laboratory for the period of April-2022 to March-2023 | BP-2023-24-260 | 17/08/2023 | 0 | SRIRAMAKRISHNA GUCHHA SAMITY | 0.75 | 0 | 0 | 0
4851 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-409 | 26/09/2023 | 0 | LOKAJAGARAN | 1.35 | 0 | 0 | 0
4852 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-140 | 19/06/2023 | 0 | ABHYUDAYA HALDIA | 1.35 | 0 | 0 | 0
4853 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Bill for contingency expenses of Bhagwanpur-II Vivekananda Kalyan Parishad Water testing laboratory for the period of April-2022 to March-2023 | BP-2023-24-261 | 17/08/2023 | 0 | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 0.75 | 0 | 0 | 0
4854 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Bill for contingency expenses of Vivekananda Yuba Parishad Water testing laboratory for the period of April-2022 to March-2023 | BP-2023-24-263 | 17/08/2023 | 0 | VIVEKANANDA YUBA PARISHADISP | 0.75 | 0 | 0 | 0
4855 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. | BP-2023-24-33 | 29/04/2023 | 0 | GRAMMANGAL WATER TESTING LAB | 1.32 | 0 | 0 | 0
4856 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-138 | 19/06/2023 | 0 | GRAMMANGAL WATER TESTING LAB | 1.35 | 0 | 0 | 0
4857 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-410 | 26/09/2023 | 0 | ABHYUDAYA HALDIA | 1.35 | 0 | 0 | 0
4858 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-411 | 26/09/2023 | 0 | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 1.35 | 0 | 0 | 0
4859 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-134 | 19/06/2023 | 0 | TAMRALIPTA GUCHHA SAMITY | 1.35 | 0 | 0 | 0
4860 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-136 | 19/06/2023 | 0 | SRIRAMAKRISHNA GUCHHA SAMITY | 1.35 | 0 | 0 | 0
4861 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-412 | 26/09/2023 | 0 | VIVEKANANDA YUBA PARISHADISP | 1.35 | 0 | 0 | 0
4862 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. | BP-2023-24-30 | 29/04/2023 | 0 | SRIRAMAKRISHNA GUCHHA SAMITY | 1.32 | 0 | 0 | 0
4863 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-139 | 19/06/2023 | 0 | VIVEKANANDA YUBA PARISHADISP | 1.35 | 0 | 0 | 0
4864 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-137 | 19/06/2023 | 0 | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 1.35 | 0 | 0 | 0
4865 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Bill for contingency expenses of Gram Mangal Water testing laboratory for the period of April-2022 to March-2023 | BP-2023-24-259 | 17/08/2023 | 0 | GRAMMANGAL WATER TESTING LAB | 0.75 | 0 | 0 | 0
4866 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Bill for contingency expenses of Lokajagaran Water testing laboratory for the period of April-2022 to March-2023 | BP-2023-24-262 | 17/08/2023 | 0 | LOKAJAGARAN | 0.75 | 0 | 0 | 0
4867 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. | BP-2023-24-28 | 29/04/2023 | 0 | TAMRALIPTA GUCHHA SAMITY | 1.32 | 0 | 0 | 0
4868 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. | BP-2023-24-35 | 29/04/2023 | 0 | ABHYUDAYA HALDIA | 1.32 | 0 | 0 | 0
4869 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-135 | 19/06/2023 | 0 | LOKAJAGARAN | 1.35 | 0 | 0 | 0
4870 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-413 | 26/09/2023 | 0 | GRAMMANGAL WATER TESTING LAB | 1.35 | 0 | 0 | 0
4871 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-414 | 26/09/2023 | 0 | SRIRAMAKRISHNA GUCHHA SAMITY | 1.35 | 0 | 0 | 0
4872 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. | BP-2023-24-32 | 29/04/2023 | 0 | LOKAJAGARAN | 1.32 | 0 | 0 | 0
4873 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. | BP-2023-24-34 | 29/04/2023 | 0 | VIVEKANANDA YUBA PARISHADISP | 1.32 | 0 | 0 | 0
4874 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Bill for contingency expenses of Tamralipta Guchha Samity Water testing laboratory for the period of April-2022 to March-2023 | BP-2023-24-257 | 17/08/2023 | 0 | TAMRALIPTA GUCHHA SAMITY | 0.75 | 0 | 0 | 0
4875 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Bill for contingency expenses of Abhyudaya- Haldia Water testing laboratory for the period of April-2022 to March-2023 | BP-2023-24-258 | 17/08/2023 | 0 | ABHYUDAYA HALDIA | 0.75 | 0 | 0 | 0
4876 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-408 | 26/09/2023 | 0 | TAMRALIPTA GUCHHA SAMITY | 1.35 | 0 | 0 | 0
4877 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Engagement of 03 nos. Sampling Assistants and 06 nos. Laboratory Attendants for different PHED Managed Water Testing Laboratories under Tamluk Division, PHE Dte. For the period 06 (Six) Months from 01.01.2023 to 30.06.2023 | 2257/TD | 30/12/2022 | 182 | UTSAV AGENCY | 7.99 | 6.74 | 100 | 100
4878 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Continuation Work Order for Providing services for operation of 07 (Seven) nos. PHED managed Sub-District laboratories under Tamluk Division, PHE Dte. by engaging one Chemist/Bacteriologist and one Laboratory Assistant for each laboratory capable to analyze chemical, bacteriological and physical parameter of water with sophisticated and prescribed electronic equipment including sending data through smart phone, preparation of test result, cleaning of instruments, glassware furniture etc. and other laboratory related works as per guidelines of WSSO, PHE Department for 02 (Two) Months. (From 01.04.2023 to 31.05.2023) | 3583/TD | 30/03/2023 | 61 | UTSAV AGENCY | 4.02 | 3.9 | 100 | 100
4879 | PURBA MEDINIPUR | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/11816 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition (16 nos.) Labs under Tamluk Division PHE Dte. | 1534/TD | 18/07/2023 | 30 | UTSAV AGENCY | 6.18 | 6.18 | 100 | 100
4880 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Different work under Tamluk Division, PHE Dte. | 8443/77 | 14/09/2020 | 0 | DIFFERENT CONTRACTOR OF TAMLUK DIVISION, PHE DTE. | 0.97 | 0 | 0 | 0
4881 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Different work under Tamluk Division, PHE Dte. | 121 | 26/06/2020 | 0 | DIFFERENT CONTRACTOR OF TAMLUK DIVISION, PHE DTE. | 12.93 | 0 | 0 | 0
4882 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Providing services for Operation of 7 (seven) Nos. PHED managed Laboratory by engaging laboratory personnel under Tamluk Division, PHE Dte. (Period from 01/11/20 to 31/12/20). | 818/W | 24/02/2021 | 0 | UTSAV AGENCY | 3.85 | 0 | 0 | 0
4883 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Chemical and Glassware etc. required for routine water testing of 17 (seventeen) nos. Water Testing Laboratories under Tamluk Division, PHE Dte. | 1041/W | 30/03/2021 | 0 | UTSAV AGENCY | 34 | 0 | 0 | 0
4884 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Providing services for Operation of 7 (seven) Nos. PHED managed Laboratory by engaging laboratory personnel under Tamluk Division, PHE Dte. (Period from 01/11/19 to 31/10/20). | 817/W | 24/02/2021 | 0 | UTSAV AGENCY | 1.93 | 0 | 0 | 0
4885 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Chemical and Glassware etc. required for routine water testing of 17 (seventeen) nos. Water Testing Laboratories under Tamluk Division, PHE Dte. | BP-2021-22-31 | 19/07/2021 | 0 | UTSAV AGENCY | 8.12 | 0 | 0 | 0
4886 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Engagement of 2 (two) nos. Laboratory personnel for Digha Sub-Divisional laboratory under Tamluk Division, PHE Dte. (Period from 11/12/19 to 10/04/20) | 860/W | 12/03/2021 | 0 | ARUNALOY SCIENTIFICE HOUSE | 1.14 | 0 | 0 | 0
4887 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Supply and Delivery of Chemical and Regents for Onsite Mobile Analysis System (OMAS) for different laboratories under Tamluk Division, PHE Dte. | BP-2021-22-61 | 13/08/2021 | 0 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 3.85 | 0 | 0 | 0
4888 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Engagement of 03 nos. Sampling Assistants and 06 nos. Laboratory Attendants for different PHED Managed Water Testing Laboratories under Tamluk Division, PHE Dte. For the period 1 (One) Year. | 1123/TD | 22/11/2021 | 1 | CANVAS | 12.35 | 5.06 | 40.98 | 0
4889 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Regular analysis, testing and monitoring of water sample by experienced & trained personnel of District Laboratory activities of Tamluk District Water Testing Laboratory of PHE Dte at Tamluk PHE Complex, Purba Medinipur under Tamluk Sub-division of Tamluk Division PHE Dte. For the period from 01.10.2021 to 30.09.2022 = 12 Months. | 809/TD | 30/09/2021 | 12 | M/S EL-CON | 7.13 | 2.38 | 100 | 0
4890 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Engagement of 3 nos. laboratory Personal (one no. Chemist / Bacteriologist, one no. laboratory Assistant & one no. Sampling Assistant) for regular analysis, testing and monitoring of water sample and others allied minor Mtc. works of Digha Sub-Divisional Laboratory under Digha Sub-Division of Tamluk Division, P.H.E.Dte. for the period from 01/10/2021 to 30/09/2022 i.e. 12 (twelve) months. | 811-A/TD | 30/09/2021 | 12 | ARUNALOY SCIENTIFIC HOUSE | 4.84 | 4.83 | 100 | 0
4891 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Procurement of Chemicals and Reagents for On site mobile analysis system (OMAS) kits for 03 (Three) nos. laboratories under Tamluk Division, PHE Dte. | 357/TD | 17/05/2022 | 7 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 3.86 | 3.86 | 100 | 0
4892 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Procurement of required items for testing of water samples (collected from different sources of JJM sites) at Purba Medinipur District Laboratory on emergency basis under Tamluk Division, PHE Dte. | 55/RWS./TSD | 06/05/2022 | 7 | UTSAV AGENCY | 0.53 | 0.53 | 100 | 0
4893 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under SRIRAMAKRISHNA GUCHHA SAMITY Laboratory for the period from March, 22 to May, 22 | BP-2022-23-220 | 05/08/2022 | 0 | SRIRAMAKRISHNA GUCHHA SAMITY | 0.99 | 0 | 0 | 0
4894 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under BHAGWANPURII VIVEKANANDA KALYAN PARISHAD Laboratory for the period from March, 22 to May, 22 | BP-2022-23-222 | 05/08/2022 | 0 | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 0.99 | 0 | 0 | 0
4895 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under VIVEKANANDA YUBA PARISHADISP Laboratory for the period from March, 22 to May, 22 | BP-2022-23-224 | 05/08/2022 | 0 | VIVEKANANDA YUBA PARISHADISP | 0.99 | 0 | 0 | 0
4896 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under TAMRALIPTA GUCHHA SAMITYLaboratory for the period from March, 22 to May, 22 | BP-2022-23-223 | 05/08/2022 | 0 | TAMRALIPTA GUCHHA SAMITY | 0.99 | 0 | 0 | 0
4897 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under ABHYUDAYA HALDIA Laboratory for the period from March, 22 to May, 22 | BP-2022-23-226 | 05/08/2022 | 0 | ABHYUDAYA HALDIA | 0.99 | 0 | 0 | 0
4898 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Engagement of 03 Nos. Sampling Assistants and 06 Nos. Laboratory Attendants for different PHED managed water testing laboratories under Tamluk Division, PHE Dte. w.e.f. 01/10/2021 to 30/11/2021 | BP-2022-23-278 | 16/09/2022 | 0 | CLIFFORD FACILITY SERVICES PVT LTD | 1.54 | 0 | 0 | 0
4899 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under LOKAJAGARAN Laboratory for the period from March, 22 to May, 22 | BP-2022-23-221 | 05/08/2022 | 0 | LOKAJAGARAN | 0.99 | 0 | 0 | 0
4900 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under Grammangal Laboratory for the period from March, 22 to May, 22 | BP-2022-23-225 | 05/08/2022 | 0 | GRAMMANGAL WATER TESTING LAB | 0.99 | 0 | 0 | 0
4901 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Annual Maintenance of Computer and Peripherals (One set of Monitor, CPU, Keyboard, UPS, Mouse and Printer all without major spare parts) including refilling of cartridge of the printers, replacement of battery of UPS (if required), software up-gradation & installation, troubleshooting, supervision and service charge for configuration for different laboratories in Purba Medinipur District under Tamluk Division, PHE Dte. for the period from 01/11/2021 to 31/10/2022. | 262/RWS/TSD | 28/10/2021 | 12 | MISHRA ENTERPRISE | 2.33 | 1.16 | 50 | 100
4902 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Supply and Delivery of 02 (two) nos. Printers for one no. RWS Tamluk Sub-Division, PHE Dte. and one no. Kudi Sub-District Laboratory and one no. Monitor of Moyna Sub-District Laboratory under Tamluk Division, PHE Dte. | 251/RWS/TSD | 01/09/2022 | 7 | MISHRA ENTERPRISE | 0.45 | 0.45 | 100 | 100
4903 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Electrical item works of Erashal Sub-District Laboratory under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 1079/TSD | 18/08/2022 | 15 | SUDIP MANNA | 0.42 | 0.42 | 100 | 0
4904 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Electrical item works of Tamluk District Laboratory due to application for NABL Accreditation under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | 1080/TSD | 18/08/2022 | 15 | SUDIP MANNA | 0.38 | 0.38 | 100 | 0
4905 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus | BP-2022-23-603 | 11/01/2023 | 0 | LOKAJAGARAN | 1.13 | 0 | 0 | 0
4906 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus. | BP-2022-23-602 | 11/01/2023 | 0 | SRIRAMAKRISHNA GUCHHA SAMITY | 1.13 | 0 | 0 | 0
4907 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus | BP-2022-23-607 | 11/01/2023 | 0 | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 1.13 | 0 | 0 | 0
4908 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus | BP-2022-23-606 | 11/01/2023 | 0 | GRAMMANGAL WATER TESTING LAB | 1.13 | 0 | 0 | 0
4909 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus | BP-2022-23-604 | 11/01/2023 | 0 | ABHYUDAYA HALDIA | 1.13 | 0 | 0 | 0
4910 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus | BP-2022-23-605 | 11/01/2023 | 0 | TAMRALIPTA GUCHHA SAMITY | 1.13 | 0 | 0 | 0
4911 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. , SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus | BP-2022-23-608 | 11/01/2023 | 0 | VIVEKANANDA YUBA PARISHADISP | 1.13 | 0 | 0 | 0
4912 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Haldia, Mahishadal, Sutahata Block of Purba Medimipur district in connection with Jal Jeevan Mission. | 1785-H/TD | 03/08/2023 | 31 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4913 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Khejuri-II, Egra-I, Egra-II Block of Purba Medimipur district in connection with Jal Jeevan Mission. | 1785-C/TD | 03/08/2023 | 31 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4914 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Chandipur, Moyna, Nandakumar Block of Purba Medimipur district in connection with Jal Jeevan Mission. | 1785-F/TD | 03/08/2023 | 31 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4915 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Contai - I, Contai-II(Deshpran), Contai-III Block of Purba Medimipur district in connection with Jal Jeevan Mission. | 1785-E/TD | 03/08/2023 | 31 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4916 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Kolaghat, Panskura, Sahid Matangini Block of Purba Medimipur district in connection with Jal Jeevan Mission. | 1785-A/TD | 03/08/2023 | 31 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4917 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Bhagwanpur -I , Bhagwanpur -II, Khejuri-I Block of Purba Medimipur district in connection with Jal Jeevan Mission. | 1785-B/TD | 03/08/2023 | 31 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4918 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Ramnagar-I, Ramnagar - II, Patashpur -I Block of Purba Medimipur district in connection with Jal Jeevan Mission. | 1785-D/TD | 03/08/2023 | 31 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4919 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Nandigram-I, Nandigram - II, Patashpur-II Block of Purba Medimipur district in connection with Jal Jeevan Mission. | 1785-G/TD | 03/08/2023 | 31 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4920 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Tamluk Block of Purba Medimipur district in connection with Jal Jeevan Mission. | 1785-I/TD | 03/08/2023 | 31 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 3.39 | 3.39 | 100 | 100
4921 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Kolaghat, Panskura, Sahid Matangini Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | 2176/TD | 01/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.52 | 100 | 100
4922 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Bhagwanpur -I , Bhagwanpur -II, Khejuri-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | 2177/TD | 01/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.33 | 100 | 100
4923 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Khejuri-II, Egra-I, Egra-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | 2178/TD | 01/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.03 | 100 | 100
4924 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Tamluk Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | 2182-A/TD | 01/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 3.39 | 3.39 | 100 | 100
4925 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Contai-I, Contai-II (Deshapran), Contai-III Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | 2180/TD | 01/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.36 | 100 | 100
4926 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Ramnagar-I, Ramnagar-II, Patashpur-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | 2179/TD | 01/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.62 | 100 | 100
4927 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Chandipur, Moyna, Nandakumar Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | 2181/TD | 01/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4928 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Haldia, Mahishadal, Sutahata Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | 2182/TD | 01/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4929 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Kolaghat, Panskura, Sahid Matangini Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | 2517/TD | 29/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4930 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Chandipur, Moyna, Nandakumar Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | 2724/TD | 31/10/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4931 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Nandigram-I, Nandigram-II, Patashpur-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | 2181-A/TD | 01/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.52 | 100 | 100
4932 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Kolaghat, Panskura, Sahid Matangini Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | 2719/TD | 31/10/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4933 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Contai-I, Contai-II (Deshapran), Contai-III Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | 2723/TD | 31/10/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4934 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Khejuri-II, Egra-I, Egra-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | 2721/TD | 31/10/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4935 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Tamluk Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | 2727/TD | 31/10/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 3.39 | 3.39 | 100 | 100
4936 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Nandigram-I, Nandigram-II, Patashpur-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | 2725/TD | 31/10/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4937 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Contai-I, Contai-II (Deshapran), Contai-III Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | 2517-D/TD | 29/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4938 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Nandigram-I, Nandigram-II, Patashpur-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | 2518-A/TD | 29/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4939 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Chandipur, Moyna, Nandakumar Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | 2518/TD | 29/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4940 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Bhagwanpur -I , Bhagwanpur -II, Khejuri-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | 2517-A/TD | 29/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4941 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Khejuri-II, Egra-I, Egra-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | 2517-B/TD | 29/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4942 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Tamluk Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | 2518-C/TD | 29/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 3.39 | 3.39 | 100 | 100
4943 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Ramnagar-I, Ramnagar-II, Patashpur-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days | 2517-C/TD | 29/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4944 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Haldia, Mahishadal, Sutahata Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | 2518-B/TD | 29/09/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4945 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Haldia, Mahishadal, Sutahata Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | 2726/TD | 31/10/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4946 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Bhagwanpur -I , Bhagwanpur -II, Khejuri-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | 2720/TD | 31/10/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4947 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Ramnagar-I, Ramnagar-II, Patashpur-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days | 2722/TD | 31/10/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4948 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Khejuri-II, Egra-I, Egra-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | 2977/TD | 29/11/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4949 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Ramnagar-I, Ramnagar-II, Patashpur-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days | 2965/TD | 28/11/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4950 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Contai-I, Contai-II (Deshapran), Contai-III Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | 3027/TD | 29/11/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4951 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Chandipur, Moyna, Nandakumar Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | 2951/TD | 24/11/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4952 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Nandigram-I, Nandigram-II, Patashpur-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | 3028/TD | 29/11/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4953 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Haldia, Mahishadal, Sutahata Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | 2952/TD | 24/11/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4954 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Tamluk Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | 2934/TD | 23/11/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 3.39 | 3.39 | 100 | 100
4955 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Kolaghat, Panskura, Sahid Matangini Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | 2976/TD | 29/11/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4956 | PURBA MEDINIPUR | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. , SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Bhagwanpur -I , Bhagwanpur -II, Khejuri-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | 2964/TD | 28/11/2023 | 30 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
4957 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of 10 Pices 88A Black Original Laser Jet Compatible Toner Cartridge for the office of the Executive Engineer, Tamluk Division, PHE Dte. through GEM Portal Direct Purchase. | BP-2022-23-582 | 10/01/2023 | 0 | SAHIL COMPUTERS | 0.04 | 0 | 0 | 0
4958 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of 5 Nos. Cannon NPG-59 toner cartridge from Gem for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-234 | 09/08/2023 | 0 | LIVE PRINT SOLUTION | 0.11 | 0 | 0 | 0
4959 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of 2 Nos. Desk Top Computer through GEM for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-235 | 09/08/2023 | 0 | SSE FORM HOUSE | 0.96 | 0 | 0 | 0
4960 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of 4 (Four) Nos. HP Desk Top Computer for the office of the Executive Engineer, Tamluk Division, PHE Dte. through GEM Portal. | BP-2022-23-581 | 10/01/2023 | 0 | SUN SYSTEMS | 2.18 | 0 | 0 | 0
4961 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of One no. Canon Multifunction Machines Mfm. On site OEM warranty 3 years from GEM for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-289 | 22/08/2023 | 0 | IONET | 1.86 | 0 | 0 | 0
4962 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase Formujet Compatible Cartridge 88A through GEM for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-66 | 22/05/2023 | 0 | SANDEEP FORMS CENTRE | 0.1 | 0 | 0 | 0
4963 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of 1 no. HP intel core i3 12100 8GB / 1000 GB HDD / Windows 11 professional desktop computer for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-290 | 22/08/2023 | 0 | EASY DAY ENTERPRISE | 0.45 | 0 | 0 | 0
4964 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of 3 Nos. HP Intel Core i5 Desk Top Computer through GEM Potal for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2022-23-713 | 21/02/2023 | 0 | IONET | 1.94 | 0 | 0 | 0
4965 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase through GEM Compatible Toner Cartridge 110A for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-65 | 22/05/2023 | 0 | NAMO SALES | 0.16 | 0 | 0 | 0
4966 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of 10 Nos. Microtek UPS 650va through GEM Potal for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2022-23-714 | 21/02/2023 | 0 | KENDRIYA BHANDAR | 0.22 | 0 | 0 | 0
4967 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of 7 Nos. HP Leaser Jet 108A Printer for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2022-23-756 | 28/02/2023 | 0 | TECH ELECON PVT. LTD. | 0.73 | 0 | 0 | 0
4968 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of Printline HP 12A Black Original Laser Jet Toner cartridge class compatible from Gem for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-233 | 09/08/2023 | 0 | NEXT ENTERPRISES | 0.05 | 0 | 0 | 0
4969 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of hp CIS integrated sheet Fed & Flat Bed Scanner, On site OEM through GEM for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-769 | 05/01/2024 | 0 | EASY DAY ENTERPRISE | 0.34 | 0 | 0 | 0
4970 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of 3 nos. hp Laser Mono Computer Printers for A4 paper size through GEM for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-768 | 05/01/2024 | 0 | EASY DAY ENTERPRISE | 0.53 | 0 | 0 | 0
4971 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Supply of 2 Nos. Cannon NPG 87 Toner through GEM for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-831 | 31/01/2024 | 0 | IONET | 0.2 | 0 | 0 | 0
4972 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Supply of 2 Nos. Canon Document Scanner P -20811 through GEM for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-833 | 31/01/2024 | 0 | IONET | 0.22 | 0 | 0 | 0
4973 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Supply of 3 Nos. Canon Multifunction Machines Mfm, On site OEM through GEM for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-832 | 31/01/2024 | 0 | IONET | 0.47 | 0 | 0 | 0
4974 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | SUPPLY OF THREE NOS HP PRINTER LJ PRO MFP 4104 DW | BP-2024-25-75 | 06/05/2024 | 0 | IONET | 1.05 | 0 | 0 | 0
4975 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Purchase of 3 Nos. Intel Core i3 12100 8 GB/1000 GB HDD / Window 11 Profession through GEM for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-767 | 05/01/2024 | 0 | IONET | 1.5 | 0 | 0 | 0
4976 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Supply of 3 nos. Microtek line Interactive UPS through GEM for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2023-24-830 | 31/01/2024 | 0 | EASY DAY ENTERPRISE | 0.09 | 0 | 0 | 0
4977 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | SUPPLY OF 3(THREE) NOS COMPUTER DESKTOP | BP-2024-25-74 | 06/05/2024 | 0 | IONET | 1.99 | 0 | 0 | 0
4978 | PURBA MEDINIPUR | Tamluk Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. , SM/13369 | Support-MIS | Procurement of HP Printer LJ PRO MFP 4104DW through GEM for the office of the Executive Engineer, Tamluk Division, PHE Dte. | BP-2024-25-135 | 22/05/2024 | 0 | EASY DAY ENTERPRISE | 0.35 | 0 | 0 | 0
4979 | PURBA MEDINIPUR | Tamluk Division | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Purba Medinipur District July 2023 , SM/19093 | Support-IEC | Organize one day Sub Division level orientation programme on JJM involving PRI Functionaries & VWSC members at Purba Medinipur district and conceptualization, design , implementation of community sensitization / mobilization activities using various mediums on JJM, provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water quality issues , water conservation and WASH related issues as per operational guideline of JJM and preparation of web based Digital (A/V) training material (Bengali) at Purba Medinipur District under Tamluk Division, PHE Dte, , Govt. of West Bengal. | 3284/TD | 20/12/2023 | 183 | DEBNATH BROTHERS | 59.2 | 0 | 0 | 58
4980 | PURBA MEDINIPUR | Tamluk Division | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Purba Medinipur District July 2023 , SM/19093 | Support-IEC | Organize one day Sub Division level orientation programme on JJM involving PRI Functionaries & VWSC members at Purba Medinipur district and conceptualization, design , implementation of community sensitization / mobilization activities using various mediums on JJM, provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water quality issues , water conservation and WASH related issues as per operational guideline of JJM and preparation of web based Digital (A/V) training material (Bengali) at Purba Medinipur District under Tamluk Division, PHE Dte, , Govt. of West Bengal (PART-B). | 1043/TD | 15/03/2024 | 184 | DEBNATH BROTHERS | 33.97 | 0 | 0 | 100
4981 | PURBA MEDINIPUR | Tamluk Division | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Purba Medinipur District July 2023 , SM/19093 | Support-IEC | Wall writing about the benefits of tap water, efficient use of water and water conservation prominent places like Health Center, GP office , BDO Office and other such prominent places for assessment of functionality of Tap water connections under JJM at Purba Medinipur District under Tamluk Division, PHE Dte. Govt of West Bengal | 2131/TD | 28/06/2024 | 183 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 49.88 | 0 | 0 | 0
4982 | PURBA MEDINIPUR | Tamluk Division | Requirement of chemicals, glassware and instrument equipment of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Division , SM/08683 | Support-WQMSP | Supply, Delivery, Installation & Calibration of Analytical Balance, Distillation Plant required for NABL of Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | 337 / CSD | 21/09/2021 | 10 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.62 | 1.62 | 100 | 0
4983 | PURBA MEDINIPUR | Tamluk Division | Requirement of chemicals, glassware and instrument equipment of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Division , SM/08683 | Support-WQMSP | Supply of Glassware and Instrument Requirement of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Sub-Division of Tamluk Division, PHE Dte. | 571/TD | 25/08/2021 | 15 | UTSAV AGENCY | 3.12 | 3.12 | 100 | 0
4984 | PURBA MEDINIPUR | Tamluk Division | Requirement of chemicals, glassware and instrument equipment of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Division , SM/08683 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereof for Haldia Sub-District Water Testing Laboratory under Digha Sub-Division, of Tamluk Division, PHE Dte. | BP-2022-23-75 | 10/06/2022 | 0 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 0 | 0 | 0
4985 | PURBA MEDINIPUR | Tamluk Division | Requirement of chemicals, glassware and instrument equipment of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Division , SM/08683 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereof for Serkhanchak Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | 597/TD | 31/08/2021 | 3 | ARUNALOY SCIENTIFIC HOUSE | 4.78 | 4.78 | 100 | 100
4986 | PURBA MEDINIPUR | Tamluk Division | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computers of Different Water Testing Laboratories under Tamluk Division, PHE Dte. , SM/11710 | Support-WQMSP | Chemical, glassware etc. required for routine water testing at 16 nos. water testing laboratories under Tamluk Division, PHE Dte. | 310/TD | 10/05/2022 | 20 | UTSAV AGENCY | 73.74 | 73.74 | 100 | 0
4987 | PURBA MEDINIPUR | Tamluk Division | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computers of Different Water Testing Laboratories under Tamluk Division, PHE Dte. , SM/11710 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from July, 2023 to October, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-720 | 26/12/2023 | 0 | TAMRALIPTA GUCHHA SAMITY | 1.8 | 0 | 0 | 0
4988 | PURBA MEDINIPUR | Tamluk Division | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computers of Different Water Testing Laboratories under Tamluk Division, PHE Dte. , SM/11710 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from July, 2023 to October, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-716 | 26/12/2023 | 0 | VIVEKANANDA YUBA PARISHADISP | 1.8 | 0 | 0 | 0
4989 | PURBA MEDINIPUR | Tamluk Division | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computers of Different Water Testing Laboratories under Tamluk Division, PHE Dte. , SM/11710 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from July, 2023 to October, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-717 | 26/12/2023 | 0 | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 1.8 | 0 | 0 | 0
4990 | PURBA MEDINIPUR | Tamluk Division | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computers of Different Water Testing Laboratories under Tamluk Division, PHE Dte. , SM/11710 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from July, 2023 to October, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-714 | 26/12/2023 | 0 | SRIRAMAKRISHNA GUCHHA SAMITY | 1.8 | 0 | 0 | 0
4991 | PURBA MEDINIPUR | Tamluk Division | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computers of Different Water Testing Laboratories under Tamluk Division, PHE Dte. , SM/11710 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from July, 2023 to October, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-718 | 26/12/2023 | 0 | ABHYUDAYA HALDIA | 1.8 | 0 | 0 | 0
4992 | PURBA MEDINIPUR | Tamluk Division | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computers of Different Water Testing Laboratories under Tamluk Division, PHE Dte. , SM/11710 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from July, 2023 to October, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-715 | 26/12/2023 | 0 | GRAMMANGAL WATER TESTING LAB | 1.8 | 0 | 0 | 0
4993 | PURBA MEDINIPUR | Tamluk Division | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computers of Different Water Testing Laboratories under Tamluk Division, PHE Dte. , SM/11710 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from July, 2023 to October, 2023 under Tamluk Division, PHE Dte. | BP-2023-24-719 | 26/12/2023 | 0 | LOKAJAGARAN | 1.8 | 0 | 0 | 0
4994 | PURBA MEDINIPUR | Tamluk Division | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computers of Different Water Testing Laboratories under Tamluk Division, PHE Dte. , SM/11710 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plastic ware etc. required for smooth running of the Laboratories for the year 2023- 2024 in the District of Purba Medinipur Under Tamluk Division P.H.E. Dte. Total Nos of Laboratories = 16 Nos including 7 Nos N.G.O mannaged. | 2975/TD | 28/11/2023 | 40 | UTSAV AGENCY | 88.87 | 56 | 100 | 100
4995 | PURBA MEDINIPUR | Tamluk Division | Drinking Water Sample Collection & testing through Filed Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission. , SM/19087 | Support-WQMSP | Data uploading charges of FTK test results into State Water Quality Dashboard tested by ASHA workers using Field Test Kit (FTKs) related with Water Quality Monitoring & Surveillance under JJM | 251/TD | 11/01/2024 | 60 | MISHRA ENTERPRISE | 8 | 6.96 | 100 | 100
Total | [9 empty] | 2290994.04 | 114336.22 | 4.99