## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme , SM/07197 | Retrofitting | Withdrawing & relaying & laying of pipeline and other misc. works for retrofitting of GARGENDA PWSS under Alipurduar Division PHED. | 698/ALD | 16/09/2020 | 120 | M/S SSB CONSTRUCTION | 30.51 | 5.88 | 100 | 60
2 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme , SM/07197 | Retrofitting | Construction of 300cum OHR for Augmentation of Jagijhora Barabak Water Supply Scheme under Alipurduar Division, PHE Dte. | 2582/ALD | 17/02/2022 | 180 | ASHIM KUMAR GHOSH | 63.76 | 12.04 | 100 | 43
3 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme , SM/07197 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 7.5 | 100 | 0
4 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme , SM/07197 | Retrofitting | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | 2732/ALD | 30/12/2022 | 365 | PARITOSH SUTRADHAR | 4.8 | 0 | 0 | 90
5 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme , SM/07197 | Retrofitting | Construction of Pump House, Boundary Wall, laying distribution system and providing FHTC for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2379/ALD | 31/01/2022 | 90 | DILIP MAHATO | 92.34 | 0 | 0 | 98
6 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme , SM/07197 | Retrofitting | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for GARGENDA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2391/ALD | 31/01/2022 | 90 | MITHUN DAS | 27.16 | 20.13 | 43.84 | 100
7 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme , SM/07197 | Retrofitting | Laying of UPVC/DI pipe line at flank of Asian Highway Road at Jateswar to towards Kazali Bazar under Jateswar PWSS under Alipurduar Division, PHE Dte. | 2944/ALD | 20/01/2023 | 60 | TAPASH DAS | 16.1 | 4.72 | 100 | 95
8 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) , SM/07182 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Loknathpur WSS under Alipurduar Division, PHE Dte. Part-5 | 1851/ALD | 13/12/2021 | 30 | GOUTAM KUMAR DAS | 5.04 | 4.86 | 100 | 63
9 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) , SM/07182 | Retrofitting | Retrofitting of pipeline etc. for the 'Jal Sapna' programme (FHTC for every house hold) under Loknathpur PWSS under Alipurduar Division, PHE Dte. | 2296/ALD | 24/01/2022 | 60 | GOUTAM KUMAR DAS | 45.8 | 22.25 | 100 | 94
10 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) , SM/07182 | Retrofitting | Laying of distribution pipeline with DI and UPVC pipes for interconnection of Dhaolajhora PWSS with Loknathpur PWSS under Alipurduar Division, PHE Dte. | 3192/ALD | 28/03/2022 | 60 | GOUTAM KUMAR DAS | 49.89 | 5.43 | 49.68 | 81
11 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) , SM/07182 | Retrofitting | Construction of boundary wall at 2nd TW site at Loknathpur WSS under Alipurduar Division PHE Dte. | 2109/ALD | 05/01/2022 | 45 | GOUTAM KUMAR DAS | 4.67 | 4.7 | 100 | 62
12 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) , SM/07182 | Retrofitting | Providing House connection for LOKNATHPUR water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | 864/ALD | 14/10/2020 | 30 | MATARA CONSTRUCTION CO | 4.98 | 9.97 | 100 | 0
13 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme , SM/07184 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under JHOSHODANGA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | 1284/ALD | 05/01/2021 | 60 | MADHAB SAHA | 24.66 | 42.78 | 94.89 | 99
14 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme , SM/07184 | Retrofitting | Providing House connection for Jashodanga water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte. Part-II | 1159/ALD | 15/12/2020 | 60 | TAPASH KUMAR BHOWMICK | 29.89 | 17.18 | 50 | 98
15 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme , SM/07184 | Retrofitting | Providing House connection and construction of different dia. sluice valve chamber including supply of CI materials for Jashodanga WSS under Alipurduar Division, PHE Dte. | 1316/ALD | 05/10/2021 | 45 | HARI CONSTRUCTION | 12.88 | 12.83 | 50 | 99
16 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme , SM/07184 | Retrofitting | Supply delivery & installation of various machineries at Alipurduar Division Office & allied Sub-Division Offices and laboratories under Alipurduar Division, PHE Dte. | 1287/ALD | 01/10/2021 | 15 | MATRI ENTERPRISE | 1.75 | 1.75 | 100 | 97
17 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme , SM/07184 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 18 | 100 | 100
18 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme , SM/07184 | Retrofitting | Providing House connection for CHANDIRJHAR water supply scheme at ALIPURDUAR-II Block under Alipuduar Division, P.H.E. Dte. | 909/ALD | 16/10/2020 | 30 | SREE MAA CONSTRUCTION & CO. | 4.98 | 9.96 | 200 | 0
19 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) , SM/07062 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Kamakhyaguri PWSS, Kumargram Block under Alipurduar Division, PHE Dte. | 2289/ALD | 24/01/2022 | 60 | GOUTAM KUMAR DAS | 27.39 | 8.81 | 32.15 | 93
20 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) , SM/07062 | Retrofitting | Providing House connection for KAMAKHYAGURI water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | 861/ALD | 14/10/2020 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.94 | 4.94 | 100 | 98
21 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) , SM/07062 | Retrofitting | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte.(Part-A) | 1306/ALD | 05/10/2021 | 60 | GOUTAM KUMAR DAS | 25.34 | 21.65 | 100 | 74
22 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) , SM/07062 | Retrofitting | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline and Providing House Connection of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | 1574/ALD | 22/11/2021 | 60 | M/S PALIT ENTERPRISE | 48.63 | 6.78 | 100 | 78
23 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) , SM/07062 | Retrofitting | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte.(Part-A) | 1307/ALD | 05/10/2021 | 60 | TAPASH DAS | 25.34 | 17.32 | 100 | 76
24 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) , SM/07062 | Retrofitting | Construction of Pump House ,Boundary Wall and laying distribution system for Uttar Kamkhyaguri Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2608/ALD | 17/02/2022 | 90 | GOUTAM KUMAR DAS | 90.8 | 0 | 0 | 74
25 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) , SM/07062 | Retrofitting | Providing House connection for KAMAKHYAGURI water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | 1163/ALD | 15/12/2020 | 60 | TAPASH DAS | 19.94 | 8.85 | 200 | 77
26 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) , SM/07062 | Retrofitting | Providing FHTC of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte. (Part-4) | 1304/ALD | 05/10/2021 | 60 | DULAL MAJUMDER | 34.38 | 0 | 0 | 76
27 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) , SM/07062 | Retrofitting | Construction of 400cum OHR for Augmentation of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. | 2580/ALD | 17/02/2022 | 180 | DILIP MAHATO | 77.31 | 18.21 | 100 | 74
28 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) , SM/07062 | Retrofitting | Preparation of Augmentation D.P.R after investigation For Bhatibari W/S scheme under Alipurduar Division. | 913/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.62 | 5.25 | 100 | 0
29 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME , SM/09903 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC and school & others) at Chhoto Salkumar WSS under Alipurduar Division, PHE Dte.Part-5 | 2303/ALD | 25/01/2022 | 30 | AASHIRBAD ENTERPRISE | 5.03 | 0 | 0 | 61
30 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME , SM/09903 | Augmentation | Laying distribution line of UPVC and providing FHTC connection for Chhoto Salkumar Water Supply Scheme Area under Alipurduar Division, P.H.E. Dte. | 2311/ALD | 25/01/2022 | 45 | AASHIRBAD ENTERPRISE | 5.01 | 0 | 0 | 62
31 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME , SM/09903 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of CHHOTO SALKUMAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2194/ALD | 11/01/2022 | 90 | KAJAL KUMAR DE | 21.92 | 14.23 | 100 | 46
32 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME , SM/09903 | Augmentation | Providing FHTC at surrounding area of Chhoto Salkumar Under Alipurduar Division, PHE DTE. | 2754/ALD | 24/02/2022 | 60 | KAJAL KUMAR DE | 34.67 | 3.29 | 100 | 45
33 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME , SM/09903 | Augmentation | Laying of UPVC/DI/MS/CI distribution pipeline for Gap filling of Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | 3132/ALD | 25/03/2022 | 30 | PRITAM DAS | 5.04 | 0.82 | 100 | 71
34 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME , SM/09903 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVINATION OF CHOTO SALKUMAR water supply scheme, TW no III under Jal Jeevan Mission under NMD-II, PHE Dte. APD. | 635/NMD-II | 22/03/2023 | 30 | PRAGATI CONSTRUCTION COMPANY | 10.86 | 7.93 | 74.84 | 100
35 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME , SM/09903 | Augmentation | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar and Munshipara Water Supply Scheme Area under Alipurduar Division, PHE Dte. | 1317/ALD | 05/10/2021 | 1679 | DILIP MAHATO | 58.07 | 0 | 0 | 85
36 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME , SM/09903 | Augmentation | Supply & delivery of Stand by pumping machinery for Choto Salkumar water supply scheme, P/H No. II under JJM project in the dist. of Alipurduar under NMD-II, PHE Dte. | 179/AMSD | 02/04/2024 | 15 | M/S RATAN KUMAR DASGUPTA & CO. | 0.77 | 0 | 0 | 100
37 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME , SM/09903 | Augmentation | Supply & delivery of Stand by pumping machinery for Choto Salkumar water supply scheme, P/H No. I under JJM project in the dist. of Alipurduar under NMD-II, PHE Dte. | 127/AMSD | 05/03/2024 | 15 | CHOWDHURY AND BASU ENTERPRISE | 0.77 | 0 | 0 | 100
38 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME , SM/09903 | Augmentation | Supply & delivery of Stand by pumping machinery for Choto Salkumar and adjucent mouza water supply scheme, under JJM project in the dist. of Alipurduar under NMD-II, PHE Dte. | 116./AMSD | 29/02/2024 | 15 | TAPAN BISWAS | 0.77 | 0 | 0 | 100
39 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Laying Distribution pipe with DI and UPVC pipe of Baniadabri and Garokhota Area under SAMUKTALA WSS under Alipurduar Division, PHE Dte. | 1665/ALD | 19/09/2022 | 180 | GOUTAM KUMAR DAS | 101.2 | 95.1 | 93.97 | 47
40 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Laying Distribution pipe with DI and UPVC pipe of SAMUKTALA ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-A) | 1662/ALD | 19/09/2022 | 180 | M/S SSB CONSTRUCTION CO. | 100.42 | 92.48 | 92.09 | 48
41 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Laying Distribution pipe with DI and UPVC pipe of Baniadabri and Samuktala Bazar Area under SAMUKTALA WSS under Alipurduar Division, PHE Dte. | 1664/ALD | 19/09/2022 | 180 | DILIP MAHATO | 100.58 | 92.15 | 91.63 | 46
42 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of Boundary wall at 3rd TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | 1666/ALD | 19/09/2022 | 30 | PRITAM DAS | 4.74 | 4.74 | 100 | 47
43 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of Pump House at 4th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | 1672/ALD | 19/09/2022 | 60 | PROJIT HALDER | 4.77 | 0 | 0 | 0
44 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Laying distribution pipeline with UPVC pipe of Samuktala Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. | 1660/ALD | 19/09/2022 | 60 | LONGLAST PIPES (INDIA)PVT.LTD. | 97.26 | 95.08 | 97.76 | 50
45 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Laying distribution system with new UPVC/DI pipeline along with rising and delivery line connection, providing FHTC and other allied works for Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | 2659/ALD | 22/12/2022 | 120 | ESCON INDIA | 90.53 | 50.31 | 55.57 | 50
46 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Laying of UPVC pipeline for filling of Gap in distribution system Samuktala Zone-I PWSS under Alipurduar Division, PHE Dte. | 3321/ALD | 13/03/2023 | 60 | CHANDAN KIRTONIA | 5.37 | 5.37 | 100 | 0
47 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Cons. Of pathway, surface drain and chatal, Installation of Paver block, land development along with the other allied works at Samuktala Zone-II H/W, 2nd site and 3rd Tube well Site under Alipurduar Division, PHE Dte. | 2519/ALD | 24/11/2023 | 60 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 23.26 | 0 | 0 | 0
48 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Soil investigation work at 3 different places of Samuktala within Alipurduar District under Alipurduar Division PHE Dte. | 1657/ALD | 19/09/2022 | 30 | ASIS ENTERPRISE | 3.65 | 3.65 | 100 | 50
49 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of Pump House at 3rd TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | 1671/ALD | 19/09/2022 | 60 | SWADESH DEV | 4.75 | 4.65 | 100 | 100
50 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of Pump House at 2nd TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | 1670/ALD | 19/09/2022 | 60 | M/S SADHAN SAHA & CO. | 4.76 | 4.6 | 100 | 100
51 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | 5 nos Tube well boring by ODEX - 165 Method of drilling for the works of augmentation of SAMUKTALA PWSS under Alipurduar Division ,PHE Dte | 2221/ALD | 21/11/2022 | 30 | S.G. CONSTRUCTION | 32.14 | 25.17 | 100 | 50
52 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of Boundary wall at 4th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | 1667/ALD | 19/09/2022 | 45 | DHANENDRA SARKAR | 4.77 | 4.74 | 100 | 100
53 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR SAMUKTALA ZONE -III P/H NO.I | BP-2023-24-219 | 13/07/2023 | 0 | WBSEDCL | 1.54 | 0 | 0 | 0
54 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR SAMUKTALA ZONE -III P/H NO.II | BP-2023-24-220 | 13/07/2023 | 0 | WBSEDCL | 1.54 | 0 | 0 | 0
55 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | New Service Connection Charge For Samuktala Z-I P/H No.I | BP-2023-24-222 | 13/07/2023 | 0 | WBSEDCL | 1.54 | 0 | 0 | 0
56 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | NEW SEVICE CONNECTION CHARGES FOR SAMUKTALA PWSS ZONE-IIP/H NO.I | BP-2023-24-218 | 13/07/2023 | 0 | WBSEDCL | 1.54 | 0 | 0 | 0
57 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | New Service Connection Charge For Samuktala Z-I P/H NO-II | BP-2023-24-221 | 13/07/2023 | 0 | WBSEDCL | 1.54 | 0 | 0 | 0
58 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Laying distribution system with new UPVC pipeline, providing FHTC and other allied works for Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | 2501/ALD | 13/12/2022 | 120 | MADHAB SAHA | 93.21 | 81.56 | 87.49 | 49
59 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of SAMUKTALA water supply scheme, TW no I AND II OF ZONE-I , TW no I AND II OF ZONE-II , TW no I AND II OF ZONE-III under Jal Jeevan Mission under NMD-II, PHE Dte.APD. | 759/NMD-II | 04/04/2023 | 30 | AHALYA ENGINEERING WORKS | 63.4 | 50.9 | 80.28 | 40
60 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of pathway, surface drain and chatal, installation of paver block, land development along with the others allied works at Samuktala Zone-I head work site PWSS under Alipurduar Division, PHE Dte. | 1495/ALD | 16/08/2023 | 60 | DIPAK DAS | 13.04 | 0 | 0 | 25
61 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Laying of rising main and delivery line connection, construction of boundary wall at headwork site of Samuktala Zone-I PWSS under Alipurduar Division, PHE Dte. | 2541/ALD | 28/11/2023 | 360 | DIPAK DAS | 28.74 | 0 | 0 | 100
62 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing in connection with the FHTC, fixing of FHTC by means of PCC concrete block fixing of FHTC by mean of PCC concrete block at Samuktalata Zone-III PWSS under Alipurduar Division, PHE Dte. (SM/12561) | 3774/ALD | 13/11/2024 | 90 | DAS CONSTRUCTION | 60.38 | 0 | 0 | 0
63 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of Boundary wall at 5th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | 1668/ALD | 19/09/2022 | 270 | ROY & PANDIT CONSTRUCTIONS | 4.76 | 4.13 | 87.68 | 100
64 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of Pump House at 1st TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | 1669/ALD | 19/09/2022 | 60 | KOUSHIK BHOWMICK | 4.77 | 3 | 62.9 | 95
65 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of Pump House at 5th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | 1673/ALD | 19/09/2022 | 60 | CHITTA RANJAN DEY | 4.75 | 0 | 0 | 100
66 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of 400cum OHR for SAMUKTALA ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | 1659/ALD | 19/09/2022 | 180 | DILIP MAHATO | 77.32 | 68.31 | 88.38 | 100
67 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of 350cum OHR for SAMUKTALA ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | 1661/ALD | 19/09/2022 | 180 | MATARA CONSTRUCTION CO | 71.41 | 51.76 | 41.81 | 100
68 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Land development works at headwork site and laying of new UPVC/DI pipeline for filling gap in distribution system Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | 3320/ALD | 13/03/2023 | 60 | BHAGWATI BHUJEL | 9.19 | 0 | 0 | 100
69 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Repairing of HW Site Boundary Wall (15M) Samuktala WSS under Alipurduar Division, PHE Dte. | 3501/ALD | 23/03/2023 | 120 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 2.14 | 0 | 0 | 100
70 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of boundary wall (remaining portion) at Headwork site under Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | 1903/ALD | 07/09/2023 | 360 | SWAPAN MALAKAR | 6 | 0 | 0 | 100
71 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Tube well boring by ODEX-165 Method of drilling, Construction of Pump House, Boundary wall at proposed 6th site of SAMUKTALA PWSS under Alipurduar Division, PHE Dte. | 2421/ALD | 09/11/2023 | 360 | DULAL DAS | 17.57 | 0 | 0 | 100
72 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Samuktala Water Supply Scheme under Alipurduar Division P.H.E. Dte. (SM/12561) | 673/ALD | 06/03/2024 | 30 | BHAGWATI BHUJEL | 11.36 | 0 | 0 | 15
73 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Fabrication,Erection of Signage (127 nos) of Pump house/OHR site democration with in Alipurduar-I Block for Different PWSS of JJM Project Under Alipurduar Division P.H.E.Dte. | 3443/ALD | 27/09/2024 | 15 | M/S SARKAR & CO | 13.95 | 0 | 0 | 100
74 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
75 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of 100cum. OHR for SAMUKTALA ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | 1658/ALD | 19/09/2022 | 1140 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 43.9 | 13.54 | 30.83 | 100
76 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Laying distribution system with new UPVC pipeline, providing FHTC and other allied works for Samuktala Zone-II PWSS under Alipurduar Division, PHE Dte. | 2500/ALD | 13/12/2022 | 120 | TAPASH KUMAR BHOWMICK | 88.46 | 80.56 | 91.06 | 50
77 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
78 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Reparing of Pump House no 2 at HW site of SAMUKTALA PWSS Under Alipurduar Division PHE DTE.(2nd call) | 5601/ALD | 27/03/2025 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.96 | 0 | 0 | 0
79 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Interconnection of distribution system by laying of DI and HDPE pipes along with bridge/culvert crossing and other allied works at Shrinathpur TG Adjacent to Samuktala PWSS (Zone-I) under Alipurduar Division, PHE Dte. | 5288/ALD | 07/03/2025 | 60 | DEBAJYOTI SUTRADHAR | 18.28 | 0 | 0 | 0
80 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Supply and installation of sign board at different PWSS site of Alipurduar-II Block under Alipurduar Division, PHE Dte. | 969/ALD | 12/06/2025 | 45 | HARI CONSTRUCTION | 4.92 | 0 | 0 | 0
81 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Restoration of FHTCs and withdrawing and relaying a pipeline (125 mm) at Patotola area at 5th site Samuktala PWSS under Alipurduar Division, PHE Dte. | 678/ALD | 21/05/2025 | 45 | DULAL DAS | 4.5 | 0 | 0 | 0
82 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Repairing of Pump House no1 at HW site of SAMUKTALA PWSS Under Alipurduar Division PHE DTE. | 1590/ALD | 31/07/2025 | 60 | PRITAM DAS | 0.97 | 0 | 0 | 0
83 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Laying Distribution pipe with DI and UPVC pipe of SAMUKTALA ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-B) | 1663/ALD | 19/09/2022 | 180 | MATARA CONSTRUCTION CO | 101.06 | 92.43 | 99.57 | 100
84 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Laying distribution system with new UPVC/DI pipeline along with rising and delivery line connection, providing FHTC and others allied works for Samuktala Zone-II PWSS under Alipurduar Division, PHE Dte. | 2658/ALD | 22/12/2022 | 900 | HARIDAS GHOSH | 88.71 | 79.04 | 93.21 | 48
85 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME , SM/12561 | Augmentation | Construction of excess work of Boundary wall & 3m Span open Foundation Culvert with Boulder Protection works and other alied works at 2nd Site of Samuktala PWSS Zone-I PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/12561) | 2281/ALD | 05/08/2024 | 240 | PRITAM DAS | 12.58 | 0 | 0 | 100
86 | ALIPURDUAR | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | Providing balance FHTC for KAYAKHATA PWSS under Alipurduar Division, PHE Dte. | 1788/ALD | 29/08/2023 | 60 | HARI CONSTRUCTION | 11.22 | 0 | 0 | 0
87 | ALIPURDUAR | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | Supply of CIDF & CISS Pipes and specials for Kayakhata WSS Under Alipurduar Division P.H.E Dte. | 1775/ALD | 28/08/2023 | 30 | HARI CONSTRUCTION | 6.76 | 6.76 | 49.98 | 100
88 | ALIPURDUAR | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | Material Requisition To Resource Division | 3048/ALD | 08/02/2023 | 0 | Resource Division | 29.21 | 0 | 0 | 0
89 | ALIPURDUAR | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | Supply of CIPE Special & CI Jeffy Coupling for Kayakhata Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 698/ALD | 07/03/2024 | 30 | HARI CONSTRUCTION | 15.33 | 0 | 0 | 85
90 | ALIPURDUAR | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | Material Requisition To Resource Division | 140/ALD | 10/01/2024 | 0 | Resource Division | 9.76 | 0 | 0 | 0
91 | ALIPURDUAR | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | Material Requisition To Resource Division | 4274/ALD | 13/12/2024 | 0 | Resource Division | 11.82 | 0 | 0 | 0
92 | ALIPURDUAR | Northern Mechanical Division II | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | New Service Connection Charges for Kayakhata PWSS PH NO-II | BP-282/24-25 | 20/08/2024 | 0 | WBSEDCL | 9.9 | 0 | 0 | 0
93 | ALIPURDUAR | Northern Mechanical Division II | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | NEW SERVICE CONNECTION CHARGE FOR KAYAKHATA PWSS PH NO -I | BP-13/24-25 | 08/04/2024 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
94 | ALIPURDUAR | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. big dia. TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 200 cum OHR as per Departmental Design & drawing including soil investigation works, providing FHTC and others allied works for KAYAKHATA PWSS Under Alipurduar Division PHE DTE. (2nd call) | 3395/ALD | 16/03/2023 | 1022 | GOUTAM KUMAR DAS | 316.2 | 136.19 | 43.07 | 43
95 | ALIPURDUAR | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
96 | ALIPURDUAR | Northern Mechanical Division II | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
97 | ALIPURDUAR | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | Laying of UPVC pipeline at opposite flank of Higher dia in the distribution system and const. of culvert at front of HW site at Kayakhata PWSS under Alipurduar Division, PHE Dte. | 975/ALD | 12/06/2025 | 90 | HARI CONSTRUCTION | 22.06 | 0 | 0 | 0
98 | ALIPURDUAR | Northern Mechanical Division II | KAYAKHATA PIPED WATER SUPPLY SCHEME , SM/13299 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar -I & II Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1293/NMD-II | 12/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 26.61 | 0 | 0 | 0
99 | ALIPURDUAR | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Material Requisition To Resource Division | 221/ALD | 03/05/2023 | 0 | Resource Division | 9.77 | 0 | 0 | 0
100 | ALIPURDUAR | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PAKRIGURI PWSS PH NO-II | BP-2023-24-46 | 12/05/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
101 | ALIPURDUAR | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PAKRIGURI PWSS PH NO-III | BP-2023-24-45 | 12/05/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
102 | ALIPURDUAR | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PAKRIGURI PWSS PH NO-I | BP-2023-24-47 | 12/05/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
103 | ALIPURDUAR | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Providing balance FHTC for PAKRIGURI PWSSunder Alipurduar Division, PHE Dte. | 1566/ALD | 23/08/2023 | 30 | SREE MAA CONSTRUCTION | 3.43 | 0 | 0 | 15
104 | ALIPURDUAR | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Material Requisition To Resource Division | 122/ALD | 10/01/2024 | 0 | Resource Division | 3.71 | 0 | 0 | 0
105 | ALIPURDUAR | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Material Requisition To Resource Division | 3987/ALD | 27/11/2024 | 0 | Resource Division | 3.71 | 0 | 0 | 0
106 | ALIPURDUAR | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Material Requisition To Resource Division | 4269/ALD | 13/12/2024 | 0 | Resource Division | 25.24 | 0 | 0 | 0
107 | ALIPURDUAR | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Additional quotation for Pakriguri PH NO-1 | BP-263/24-25 | 09/08/2024 | 0 | WBSEDCL | 3.01 | 0 | 0 | 0
108 | ALIPURDUAR | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Additional quotation for PAKRIGURI PH NO-3 | BP-264/24-25 | 09/08/2024 | 0 | WBSEDCL | 5.46 | 0 | 0 | 0
109 | ALIPURDUAR | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Additional quotation for PAKRIGURI PH NO-2 | BP-262/24-25 | 09/08/2024 | 0 | WBSEDCL | 5.41 | 0 | 0 | 0
110 | ALIPURDUAR | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Cons of PH and Sinking of 250 mm x 200 mm X 150 mtr Big dia TW at HW site , 2nd site and 3rd TW site LDS with UPVC p/line , cons of 100 Cum OHR incl the Soil investigation works providing FHTC and others allied works for Pakriguri PWSS Under Alipurduar Division PHE DTE. | 3637/ALD | 31/03/2023 | 1080 | DEBAJYOTI SUTRADHAR | 183.6 | 0 | 0 | 65
111 | ALIPURDUAR | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Supply of CIDF Specials & Jeffy Coupling for Pakriguri (SM/14223) under Alipurduar Division, PHE Dte. | 4265/ALD | 13/12/2024 | 60 | BARMAN ENTERPRISE | 19.64 | 0 | 0 | 51
112 | ALIPURDUAR | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Construction of pumphouse & boundary wall for 3rd site, laying of distribution system with UPVC and DI pipeline, providing FHTC, Rising main and other allied works for Pakriguri PWSS under Alipurduar Division, PHE Dte. | 4906/ALD | 31/01/2025 | 90 | DEBAJYOTI SUTRADHAR | 23.9 | 0 | 0 | 0
113 | ALIPURDUAR | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
114 | ALIPURDUAR | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
115 | ALIPURDUAR | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini, Madarihat -Birpara ,kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1332/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
116 | ALIPURDUAR | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1347/NMD-II | 19/06/2025 | 30 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
117 | ALIPURDUAR | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. , SM/14223 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Pakriguri water supply scheme, TW no I,II and III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | 2415/NMD-II | 10/08/2023 | 631 | ALPHA ENTERPRISE | 27.58 | 0 | 0 | 100
118 | ALIPURDUAR | Northern Mechanical Division II | Implementation of Affordable IOT System at Makrapara TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. , SM/16912 | IOT | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Different Block of Alipurduar and Coochbehar District in West Bengal | 807/NMD-II | 04/03/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 594.37 | 0 | 0 | 0
119 | ALIPURDUAR | Alipurduar Division | MALSAGAON PIPED WATER SUPPLY SCHEME , SM/16818 | New | Material Requisition To Resource Division | 2776/ALD | 18/12/2023 | 0 | Resource Division | 9.12 | 0 | 0 | 0
120 | ALIPURDUAR | Alipurduar Division | MALSAGAON PIPED WATER SUPPLY SCHEME , SM/16818 | New | Rising Main, Laying of DI (K7), gap filling of HDPE pipe, construction of sluice valve chamber for washout purpose in the command area of Malsagaon PWSS under Alipurduar Division, PHE Dte. | 2542/ALD | 28/11/2023 | 90 | BHAGWATI BHUJEL | 76.02 | 0 | 0 | 100
121 | ALIPURDUAR | Northern Mechanical Division II | MALSAGAON PIPED WATER SUPPLY SCHEME , SM/16818 | New | NEW SERVICE CONNECTION CHARGES FOR MALSAGAON PWSS TW NO-II IN THE DIST OF ALIPURDUAR. | BP-174/24-25 | 03/07/2024 | 0 | WBSEDCL | 0.5 | 0 | 0 | 0
122 | ALIPURDUAR | Northern Mechanical Division II | MALSAGAON PIPED WATER SUPPLY SCHEME , SM/16818 | New | New Service connection charges under Malsagaon pwss TW no-I in the dist of Alipurduar. | BP-175/24-25 | 03/07/2024 | 0 | WBSEDCL | 9.94 | 0 | 0 | 0
123 | ALIPURDUAR | Alipurduar Division | MALSAGAON PIPED WATER SUPPLY SCHEME , SM/16818 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site, soil investigation at HW site, constructions of 350 Cum OHR at HW, construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Malsagaon PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 1874/ALD | 07/09/2023 | 991 | DILIP MAHATO | 517.3 | 0 | 0 | 90
124 | ALIPURDUAR | Northern Mechanical Division II | MALSAGAON PIPED WATER SUPPLY SCHEME , SM/16818 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 821/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
125 | ALIPURDUAR | Northern Mechanical Division II | MALSAGAON PIPED WATER SUPPLY SCHEME , SM/16818 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM DEOGAON and others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1385/NMD-II | 26/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 20.56 | 0 | 0 | 0
126 | ALIPURDUAR | Northern Mechanical Division II | MALSAGAON PIPED WATER SUPPLY SCHEME , SM/16818 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
127 | ALIPURDUAR | Alipurduar Division | MALSAGAON PIPED WATER SUPPLY SCHEME , SM/16818 | New | Laying of HDPE pipeline (new and Parallel ) at Malsagaon PWSS under Alipurduar Division, PHE Dte. | 1625/ALD | 04/08/2025 | 75 | DILIP MAHATO | 65.97 | 0 | 0 | 0
128 | ALIPURDUAR | Northern Mechanical Division II | MALSAGAON PIPED WATER SUPPLY SCHEME , SM/16818 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of MALSAGAON water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | 2572/NMD-II | 22/08/2023 | 680 | M/S ANJALI ENTERPRISE | 22.82 | 0 | 0 | 100
129 | ALIPURDUAR | Alipurduar Division | BENGKANDI PIPED WATER SUPPLY SCHEME , SM/16820 | New | Material Requisition To Resource Division | 1482/ALD | 16/08/2023 | 0 | Resource Division | 21.99 | 0 | 0 | 0
130 | ALIPURDUAR | Alipurduar Division | BENGKANDI PIPED WATER SUPPLY SCHEME , SM/16820 | New | Material Requisition To Resource Division | 2782/ALD | 18/12/2023 | 0 | Resource Division | 12.78 | 0 | 0 | 0
131 | ALIPURDUAR | Alipurduar Division | BENGKANDI PIPED WATER SUPPLY SCHEME , SM/16820 | New | Material Requisition To Resource Division | 2699/ALD | 12/12/2023 | 0 | Resource Division | 68.94 | 0 | 0 | 0
132 | ALIPURDUAR | Alipurduar Division | BENGKANDI PIPED WATER SUPPLY SCHEME , SM/16820 | New | Supply of CI Sluice Valve and Special & CI Jeffy Coupling for Benkandi Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 754/ALD | 12/03/2024 | 90 | SSPR VALVE MANUFACTURING PVT LTD | 12.88 | 0 | 0 | 15
133 | ALIPURDUAR | Northern Mechanical Division II | BENGKANDI PIPED WATER SUPPLY SCHEME , SM/16820 | New | NEW SERVICE CONNECTION CHARGES AT BENGKANDI PWSS P/H NO-I DIST- ALIPURDUAR. | BP-2023-24-660 | 04/03/2024 | 0 | WBSEDCL | 5.92 | 0 | 0 | 0
134 | ALIPURDUAR | Northern Mechanical Division II | BENGKANDI PIPED WATER SUPPLY SCHEME , SM/16820 | New | New service Connection Charges at Bengkandi PWSS P/H No- II in the Dist of Alipurduar. | BP-2023-24-659 | 04/03/2024 | 0 | WBSEDCL | 4.74 | 0 | 0 | 0
135 | ALIPURDUAR | Alipurduar Division | BENGKANDI PIPED WATER SUPPLY SCHEME , SM/16820 | New | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , soil investigation at OHR site, constructions of 400 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Bengkandi PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 1114/ALD | 28/07/2023 | 793 | M/S ELITE CONSTRUCTION | 655.41 | 0 | 0 | 51
136 | ALIPURDUAR | Northern Mechanical Division II | BENGKANDI PIPED WATER SUPPLY SCHEME , SM/16820 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of BENGKANDI water supply scheme, TW no I AND II under JJM under NMD-II,PHE Dte. APD | 2541/NMD-II | 16/08/2023 | 1342 | A.S. ENTERPRISE | 22.88 | 0 | 0 | 90
137 | ALIPURDUAR | Alipurduar Division | BENGKANDI PIPED WATER SUPPLY SCHEME , SM/16820 | New | Laying of different dia. HDPE Pipe line and other allied works in connection with Jal Jeevan Mission for Bengkandi PWSS under Alipurduar Division, PHE DTE. | 4948/ALD | 06/02/2025 | 90 | M/S ELITE CONSTRUCTION | 106.35 | 0 | 0 | 0
138 | ALIPURDUAR | Northern Mechanical Division II | BENGKANDI PIPED WATER SUPPLY SCHEME , SM/16820 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM DEOGAON and others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1385/NMD-II | 26/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 20.56 | 0 | 0 | 0
139 | ALIPURDUAR | Northern Mechanical Division II | BENGKANDI PIPED WATER SUPPLY SCHEME , SM/16820 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1344/NMD-II | 19/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
140 | ALIPURDUAR | Northern Mechanical Division II | BENGKANDI PIPED WATER SUPPLY SCHEME , SM/16820 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
141 | ALIPURDUAR | Alipurduar Division | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme , SM/18157 | New | Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Purba Majherdabri TG Water Supply Scheme (SM/18157) of Alipurduar-II Block under Alipurduar Division P.H.E. Dte. | 2069/ALD | 12/07/2024 | 30 | GUHA ENTERPRISE | 8.02 | 0 | 0 | 100
142 | ALIPURDUAR | Alipurduar Division | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme , SM/18157 | New | Material Requisition To Resource Division | 39818/ALD | 27/11/2024 | 0 | Resource Division | 9.47 | 0 | 0 | 0
143 | ALIPURDUAR | Northern Mechanical Division II | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme , SM/18157 | New | NEW SERVICE CONNECTION CHARGE FOR PURBA MAJHERDABRI W/S/SCHEME PH NO.I | BP-2023-24-640 | 29/02/2024 | 0 | WBSEDCL | 3.89 | 0 | 0 | 0
144 | ALIPURDUAR | Northern Mechanical Division II | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme , SM/18157 | New | NEW SERVICE CONNECTION CHARGE AT PURBA MAJHERDABRI W/S/SCHEME PH NO.II | BP-2023-24-641 | 29/02/2024 | 0 | WBSEDCL | 6.04 | 0 | 0 | 0
145 | ALIPURDUAR | Alipurduar Division | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme , SM/18157 | New | Cons. of pump house and Tube well Boring by ODEX-165 Method of drilling at HW site and 2nd site, LDS with HDPE pipeline including rising main and delivery connection, Cons. of 100 Cum OHR as per Dept. Design and drawing along with the Soil investigation works, providing FHTC and other allied works for Purba Majherdabri TG PWSS Under Alipurduar Division PHE DTE. | 406/ALD | 22/05/2023 | 680 | DAS CONSTRUCTION | 212.4 | 0 | 0 | 35
146 | ALIPURDUAR | Northern Mechanical Division II | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme , SM/18157 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for PURBBA MAJHERDABRI T.G. AREA water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | 2624/NMD-II | 25/08/2023 | 610 | BONANZA ENTERPRISE | 21.27 | 0 | 0 | 100
147 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Soil investigation work at 3 different places of Dalimpur within Alipurduar District under Alipurduar Division PHE Dte. | 965/ALD | 12/07/2023 | 30 | CITY ENGINEERING & TESTING LABORATORY | 3.67 | 3.67 | 100 | 100
148 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site along with repairing of office godown for Dalimpur Zone-I PWSS Under Alipurduar Division PHE DTE. | 973/ALD | 12/07/2023 | 360 | NARAYAN CHANDRA SAHA | 48.31 | 0 | 0 | 65
149 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Dalimpur PWSS under Alipurduar Division, PHE Dte. Part-3 | 966/ALD | 12/07/2023 | 180 | TAPASH DAS | 34.77 | 0 | 0 | 15
150 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Laying of distribution of UPVC/DI/GI pipeline including FHTC for DALIMPUR PWSS under Alipurduar Division, PHE DTE. PART-2 | 970/ALD | 12/07/2023 | 480 | MITHUN DAS | 67.93 | 40.29 | 59.31 | 65
151 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Laying of Rising Main, road and culvert crossing and distribution pipeline in DALIMPUR PWSS (Zone-III) under Alipurduar Division, PHE Dte | 2411/ALD | 09/11/2023 | 240 | NARENDRA BHADANI. | 17.66 | 0 | 0 | 10
152 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Road crossing, hume pipe culvert crossing, and bridge crossing by G.I. pipe at Dalimpur Zone-III PWSS including Laying of UPVC Pipeline for left out household connection of Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. (SM/18254) | 830/ALD | 14/03/2024 | 60 | MITHUN DAS | 9.04 | 0 | 0 | 10
153 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Laying of rising Main,Road and Calvert crossing and Balance distribution pipeline in Dalimpur(Zone-I) under Alipurduar Division,PHE Dte of North Bengal Circle-I, PHE Dte. under JJM Programme. | 670/ALD | 06/03/2024 | 300 | UJJWAL ROY | 132.1 | 0 | 0 | 80
154 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Construction of 150cum. OHR for DALIMPUR ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | 972/ALD | 12/07/2023 | 360 | UJJWAL ROY | 50.43 | 0 | 0 | 100
155 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Material Requisition To Resource Division | 3947/ALD | 26/11/2024 | 0 | Resource Division | 25.05 | 0 | 0 | 0
156 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | New service connection Charges for Dalimpur PWSS Zone-I PH NO-I under NMD-II | BP-426/24-25 | 16/12/2024 | 0 | WBSEDCL | 5.05 | 0 | 0 | 0
157 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | New Service Connection Charges For Aug of Dalimpur Zone-III PH NO-I under NMD-II | BP-425/24-25 | 16/12/2024 | 0 | WBSEDCL | 16.01 | 0 | 0 | 0
158 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | New Service Connection Charges for Aug of Dalimpur Zone-I PH NO-II under NMD-II | BP-424/24-25 | 16/12/2024 | 0 | WBSEDCL | 5.85 | 0 | 0 | 0
159 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Construction of 400cum OHR for DALIMPUR ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | 968/ALD | 12/07/2023 | 900 | NARAYAN CHANDRA SAHA | 77.28 | 0 | 0 | 60
160 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for AUGUMENTATION OF DALIMPUR water supply scheme, TW no I and II of Zone - I and TW no I and II of Zone - II and TW no I and II of Zone - III under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | 2453/NMD-II | 11/08/2023 | 540 | ALPHA ENTERPRISE | 65.55 | 0 | 0 | 35
161 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Providing FHTC from existing distribution system as per specification for DALIMPUR PWSS under Alipurduar Division, PHE Dte. | 1995/ALD | 15/09/2023 | 780 | SREE MAA CONSTRUCTION | 28.8 | 0 | 0 | 45
162 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Balance work of rising main, delivery main, bypass arrangement, land development, pipeline for left out household connection and other allied works at Augmentation of Dalimpur(Zone-3)(H/W site) of Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/18254) | 820/ALD | 14/03/2024 | 480 | UJJWAL ROY | 41.61 | 0 | 0 | 40
163 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | LAYING OF DISTRIBUTION PIPELINE AT DALIMPUR (ZONE-II, PART-A) PWSS UNDER ALIPURDUAR DIVISION, PHE DTE. | 4537/ALD | 26/12/2024 | 120 | HITANGSHU CHOUDHURY | 55.82 | 0 | 0 | 80
164 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | LAYING OF DISTRIBUTION PIPELINE AT DALIMPUR (ZONE-II, PART-B) PWSS UNDER ALIPURDUAR DIVISION, PHE DTE. | 5169/ALD | 25/02/2025 | 240 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 55.35 | 0 | 0 | 10
165 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS , SM/18254 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Dalimpur Zone-III PWSS Under Alipurduar Division PHE DTE. | 967/ALD | 12/07/2023 | 750 | NARENDRA BHADANI. | 45.9 | 0 | 0 | 100
166 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) , SM/07138 | Retrofitting | Laying of HDPE/DI pipe line at different area of flank of Lankapara road/village road and Lankapara Bazar Area under Alipurduar Division, PHE Dte. | 1007/ALD | 12/11/2020 | 60 | MADHAB SAHA | 33.79 | 13.57 | 100 | 99
167 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) , SM/07138 | Retrofitting | Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS (TULSHIPARA TG) under Alipurduar Division, PHE Dte. Dist-Alipurduar. | 1280/ALD | 05/01/2021 | 60 | UMWELT ENGINEER PVT. LTD. | 30.9 | 22.49 | 160.25 | 98
168 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) , SM/07138 | Retrofitting | Sinking of 1no. Tube Well for replacement and another 1no. new Tube Well near factory line by ODEX-195 method of drilling at Lankapara Water Supply Scheme under Alipurduar Division, PHE Dte. | 1345/ALD | 08/10/2021 | 30 | SASANKA ROY | 33 | 0 | 0 | 96
169 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) , SM/07138 | Retrofitting | Development of rig Bore TW by ODEX-165 method of drilling at Lankapara WSS under Alipurduar Division, PHE Dte. | 1608/ALD | 22/11/2021 | 20 | DILIP MAHATO | 0.66 | 0 | 0 | 99
170 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) , SM/07138 | Retrofitting | Construction of balance portion of boundary wall at CWR site under LANKAPARA (TULSHIPARA TG ) WSS under Alipurduar Division PHE Dte . | 448/ALD | 13/05/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.91 | 0 | 0 | 97
171 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) , SM/07138 | Retrofitting | Sinking of Rig Bore Tube well by Odex-165 method of drilling and installation of Raising Main and laying of DI/MS/HDPE pipe line for the Tulshipara and Lankapara Water Supply Scheme. | 1006/ALD | 12/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 32.34 | 3.86 | 10.65 | 97
172 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) , SM/07138 | Retrofitting | PROVIDING HOUSE CONNECTION FOR DIMDIMA Z-I PWSS AT MADARIHAT-BIRPARA BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-2 | 1025/ALD | 18/11/2020 | 60 | DILIP MAHATO | 28.87 | 22.95 | 200 | 0
173 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) , SM/07138 | Retrofitting | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-1 | 1449/ALD | 25/01/2021 | 45 | MAHENDRA CHHETRI | 43.86 | 7.27 | 100 | 67
174 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) , SM/07126 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | 2764/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 0.17 | 100 | 60
175 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) , SM/07126 | Retrofitting | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | 3082/ALD | 22/03/2022 | 60 | AASHIRBAD ENTERPRISE | 13.46 | 6.83 | 100 | 70
176 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) , SM/07126 | Retrofitting | Laying of UPVC & DI (with pillar) pipeline for Barobisha Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | 1320/ALD | 05/10/2021 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 79.02 | 6.22 | 100 | 66
177 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) , SM/07126 | Retrofitting | Construction of approach road & car parking area with paver block & chequered tiles at Jainty WSS under Alipurduar Division, PHE Dte. | 2107/ALD | 05/01/2022 | 30 | DAS ENTERPRISE | 5.02 | 0.87 | 100 | 77
178 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) , SM/07126 | Retrofitting | Providing House connection for BAROBISHA ZONE-II piped water supply scheme under Alipuduar Division, P.H.E. Dte. Part-4 | 1249/ALD | 28/12/2020 | 60 | TAPAN CHANDA | 39.91 | 79.82 | 100 | 0
179 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) , SM/07126 | Retrofitting | Providing House connection for BAROBISHA Zone-II water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | 1161/ALD | 15/12/2020 | 60 | TAPAN CHANDA | 29.9 | 59.81 | 100 | 0
180 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme , SM/07195 | Retrofitting | Extension pipeline (HDPE) for providing FHTC at 28th and 29th mile busty area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | 1576/ALD | 22/11/2021 | 60 | DEBAJYOTI SUTRADHAR | 25.75 | 6.6 | 100 | 69
181 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme , SM/07195 | Retrofitting | Extension of pipeline for Jainti TG including connection from Reservoir-2 under Jainti TG Water Supply Scheme (Part-A). | 795/ALD | 01/10/2020 | 60 | CALCON CONSTRUCTIONS | 40.62 | 64.59 | 100 | 90
182 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme , SM/07195 | Retrofitting | Laying of HDPE pipeline & other misc work related to Jayanti WSS under Alipurduar Division, PHE Dte. | 2119/ALD | 05/01/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.28 | 3.87 | 100 | 71
183 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme , SM/07195 | Retrofitting | Balance work of Jainty Rest Shed along with laying of delivery line from CWR of Jainti WSS under Alipurduar Division, PHE Dte. | 2629/ALD | 18/02/2022 | 60 | GHOSH & SAHA CONSTRUCTION | 13.4 | 8.21 | 100 | 64
184 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) , SM/07189 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | 877/ALD | 03/09/2021 | 60 | M/S STAR INDIA CONSTRUCTION | 33.42 | 27.31 | 100 | 73
185 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) , SM/07189 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of North side of Pukuritola area under Tapshikatha PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | 2292/ALD | 24/01/2022 | 60 | DEBAJYOTI SUTRADHAR | 26.52 | 0 | 0 | 78
186 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) , SM/07189 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Tapshikhata WSS under Alipurduar Division, PHE Dte. Part-6 | 2143/ALD | 06/01/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 5.03 | 3.02 | 98.13 | 76
187 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) , SM/07189 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Tapshikhata PWSS Under Alipurduar Division, PHE DTE. | 2750/ALD | 24/02/2022 | 60 | AMBITIOUS ENTERPRISE | 36.94 | 0.87 | 100 | 68
188 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) , SM/07189 | Retrofitting | Withdrawing and relaying of UPVC and DI pipeline due to damaged during bitumen road construction and other misc works at Tapshikhata PWSS under Alipurduar Division, PHE Dte. | 941/ALD | 19/10/2020 | 60 | KAMALESH ROY | 10.81 | 3.01 | 100 | 77
189 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) , SM/07189 | Retrofitting | Providing extension of distribution line, AT TAPSHIKATHA G.P from the commissioned TAPSHIKATHA PWSS (UID-APD-022) UNDER ALIPURDUAR DIVISION PHE DTE. | 1481/ALD | 27/01/2021 | 60 | KAMALESH ROY | 12.16 | 0 | 0 | 76
190 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) , SM/07189 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Simlabari area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | 876/ALD | 03/09/2021 | 60 | M/S AMIT KUMAR GUPTA | 35.43 | 6.67 | 100 | 75
191 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) , SM/07189 | Retrofitting | Providing House connection for Tapshikhata water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. | 719/ALD | 22/09/2020 | 30 | KAMALESH ROY | 4.98 | 9.96 | 100 | 0
192 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) , SM/07189 | Retrofitting | Providing House connection for Purba Chepani water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte.(Part-IV | 1132/ALD | 10/12/2020 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.93 | 6.82 | 200 | 0
193 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) , SM/07189 | Retrofitting | Providing House connection for Tapshikatha water supply scheme at Alipurduar-I Block under Alipuduar Division, P.H.E. Dte.(Part-III) | 1136/ALD | 10/12/2020 | 30 | KAMALESH ROY | 4.98 | 9.95 | 200 | 0
194 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) , SM/07189 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of TAPSHIKHATA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2197/ALD | 11/01/2022 | 1116 | DEBABRATA DUTTA | 21.58 | 0 | 0 | 69
195 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'BAKLA WATER SUPPLY SCHEME' , SM/09890 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVINATION OF BAKLA water supply scheme, TW no III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | 478/NMD-II | 02/03/2023 | 30 | M/S A.D. ENTERPRISE | 10.86 | 10.19 | 94.94 | 80
196 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF 'BAKLA WATER SUPPLY SCHEME' , SM/09890 | Augmentation | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Bakla PWSS Under Alipurduar Division, PHE DTE. | 2753/ALD | 24/02/2022 | 1200 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 43.78 | 0 | 0 | 43
197 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF 'BAKLA WATER SUPPLY SCHEME' , SM/09890 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method)and Rising Main for Additional T/W of BAKLA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2190/ALD | 11/01/2022 | 1081 | SHYAMAL ROY | 21.81 | 10.18 | 66.15 | 100
198 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Jateswar PWSS under Alipurduar Division, PHE Dte. Part-4 | 411/ALD | 11/05/2022 | 45 | SOUVIK ROY PALADHI | 24.47 | 10.14 | 41.43 | 63
199 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Jateswar PWSS under Alipurduar Division, PHE Dte. Part-5 | 412/ALD | 11/05/2022 | 45 | AASHIRBAD ENTERPRISE | 24.1 | 0 | 0 | 65
200 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Construction of 450cum OHR for Bhutnirghat Water Supply Scheme under Alipurduar Division, PHE Dte. | 2186/ALD | 11/01/2022 | 180 | DILIP MAHATO | 87.59 | 12.6 | 100 | 80
201 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Material Requisition To Resource Division | 2107/ALD | 09/11/2022 | 0 | Resource Division | 10.92 | 0 | 0 | 0
202 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Laying of UPVC/DI/MS/CI distribution pipe line for gap filling and FHTC connection for Sahapara and adjoining area of Jateswar PWSS under Alipurduar Division, PHE Dte. | 3191/ALD | 28/03/2022 | 60 | AASHIRBAD ENTERPRISE | 12.35 | 10.78 | 99.5 | 78
203 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Construction of 500cum OHR for Augmentation of Jateswar Water Supply Scheme under Alipurduar Division, PHE Dte. | 2525/ALD | 11/02/2022 | 180 | ASHIT KUMAR SINGHA | 91.76 | 82.23 | 100 | 80
204 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-I | 2812/ALD | 28/02/2022 | 60 | SOUVIK ROY PALADHI | 98.49 | 96.3 | 100 | 63
205 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-II | 2747/ALD | 24/02/2022 | 60 | TAPASH DAS | 49.62 | 39.08 | 100 | 59
206 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-II | 2748/ALD | 24/02/2022 | 60 | KAMALESH ROY | 49.62 | 47.81 | 100 | 63
207 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Laying of UPVC/DI/MS/CI distribution pipe line for gap filling and FHTC connection for Beltali Road and adjoining area of Jateswar PWSS under Alipurduar Division, PHE Dte. | 24/ALD | 01/04/2022 | 60 | AASHIRBAD ENTERPRISE | 12.35 | 12.33 | 50 | 80
208 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58
209 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Laying of UPVC/DI distribution pipeline including road and culvert crossing of different area for augmentation of Jateswar Water Supply Scheme under Alipurduar Division, PHE Dte. | 1225/ALD | 10/08/2022 | 60 | SOUVIK ROY PALADHI | 41.01 | 39.23 | 54.27 | 63
210 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Laying of UPVC/DI distribution pipeline including road and culvert crossing of different area for augmentation of Jateswar Water Supply Scheme under Alipurduar Division, PHE Dte. | 1226/ALD | 10/08/2022 | 120 | TAPASH DAS | 41.01 | 38.71 | 99.74 | 63
211 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Material Requisition To Resource Division | 2928/ALD | 10/03/2022 | 0 | Resource Division | 17.75 | 0 | 0 | 0
212 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Quotation for New Connection in Dalgaon | 446/22-23/PFMS | 21/01/2023 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
213 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT JATESWAR PWSS PH NO-IV | BP-2023-24-21 | 27/04/2023 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
214 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Construction of Pump House ,Boundary Wall, and Tube well Boring by Reverse Rotary method of drilling including Rising main for JATESWAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2527/ALD | 11/02/2022 | 990 | ASHIT KUMAR SINGHA | 44.59 | 9.03 | 20.24 | 63
215 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Jateswar water supply scheme, TW no. IV and V under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 889/NMD-II | 02/05/2023 | 30 | HARA PROSAD DAS | 21.7 | 0 | 0 | 60
216 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Providing FHTC from existing distribution system as per specification for JATESWAR PWSS under Alipurduar Division, PHE Dte. | 235/ALD | 17/01/2024 | 90 | BILTU DAS | 63.54 | 0 | 0 | 0
217 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Sinking big dia. Tube well of 250mm X 200mm dia. Using MS slotted strainer at required depth by Reverse Rotary Method of drilling at 2nd site for Aug. of Jateswar PWSS (SM/10156) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | 750/ALD | 12/03/2024 | 90 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 20.48 | 0 | 0 | 100
218 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Laying of UPVC/DI pipe line at flank of Asian Highway Road at Jateswar to towards Kazali Bazar under Jateswar PWSS under Alipurduar Division, PHE Dte. | 2944/ALD | 20/01/2023 | 60 | TAPASH DAS | 16.1 | 5.76 | 34.14 | 95
219 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | New Service Connection charges for Dalimpur Zone-II PH NO-II,JATESWAR | BP-140/24-25 | 11/06/2024 | 0 | WBSEDCL | 4.35 | 0 | 0 | 0
220 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | New Service Connection Charges for Dalimpur Zone-II, PH NO-I Jateswar | BP-141/24-25 | 11/06/2024 | 0 | WBSEDCL | 3.72 | 0 | 0 | 0
221 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME , SM/10156 | Augmentation | Cons. of pump house at 2nd site, laying of UPVC pipeline for left out household connection and rising main with CIDF pipe and specials and other allied works for Augmentation of Jateswar PWSS of Birpara Sub-Division under Alipurduar Division, PHE Dte.(SM/10156) | 822/ALD | 14/03/2024 | 480 | TAPASH DAS | 50.51 | 0 | 0 | 75
222 | ALIPURDUAR | Alipurduar Division | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10038 | New | Providing FHTC from existing distribution system as per specification for Dekhlapara PWSS. | 2423/ALD | 09/11/2023 | 60 | SHYAMAL ROY | 7.21 | 0 | 0 | 0
223 | ALIPURDUAR | Alipurduar Division | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10038 | New | CONS. FOR RESERVOIR (200 M3), RISING MAIN AND DISTRIBUTION LINE FOR DHEKLAPARA MAIN DIVISION CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | 284/ALD | 26/04/2022 | 150 | SUBHAS CHANDRA ROY | 86.68 | 66.06 | 93.24 | 100
224 | ALIPURDUAR | Alipurduar Division | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10038 | New | New service connection charges for Dheklapara T.G PWSS P/H no-I (Cha Sundari) | 325/24-25/PFMS | 02/12/2024 | 0 | WBSEDCL | 5.04 | 0 | 0 | 0
225 | ALIPURDUAR | Northern Mechanical Division II | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10038 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Dheklapara TG Water Supply Scheme TW No.-I (Chha sundari) under Jal Jeevan Mission NMD-II,PHE.Dte, Alipurduar. | 59/NMD-II | 07/01/2025 | 212 | M/S CHANDRANATH MUKHERJEE | 14.22 | 0 | 0 | 100
226 | ALIPURDUAR | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10039 | New | New Connection for Toorsa TG Zone-I Phase-II | 357/22-23/PFMS | 12/12/2022 | 0 | WBSEDCL | 1.19 | 0 | 0 | 0
227 | ALIPURDUAR | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10039 | New | New Connection for Torsa TG Zone-II Phase-I | 358/22-23/PFMS | 12/12/2022 | 0 | WBSEDCL | 1.19 | 0 | 0 | 0
228 | ALIPURDUAR | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10039 | New | New Connection for Torsa TG Zone-II | 359/22-23/PFMS | 12/12/2022 | 0 | WBSEDCL | 1.19 | 0 | 0 | 0
229 | ALIPURDUAR | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10039 | New | CONS. OF RESERVOIR (100M3), BOUNDARY WALL (80m), PUMP HOUSE (1No.), TUBE WELL (2 Nos.), RISING MAIN AND LAND DEVELOPMENT FOR TORSHA (Hat Khola Line, Naya Line, 3 No. Line (A) AND (B) and Khoyar line) 256 unit CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | 282/ALD | 26/04/2022 | 150 | DILIP MAHATO | 104 | 103.66 | 99.67 | 88
230 | ALIPURDUAR | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10039 | New | Soil investigation work for Cha Sundori Project at 4 different places of Torsha TG & Dekhlapara TG within Alipurduar District under Alipurduar Division PHE Dte. | 2655/ALD | 21/02/2022 | 30 | M/S HAZRA CONSTRUCTION | 4.9 | 4.9 | 100 | 87
231 | ALIPURDUAR | Northern Mechanical Division II | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10039 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component for Torsa TG Sawa Line, Chhetri Line, Gopa Line, Jiten Line 220 unit cha Sundari Water Supply Scheme , Zone-II ,P.H No.- I and II under NMD-II ,PHE.Dte,Alipurduar. | 70/NMD-II | 09/01/2023 | 30 | SARKAR ELECTRIC | 26.05 | 26.05 | 100 | 100
232 | ALIPURDUAR | Northern Mechanical Division II | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10039 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component for Torsa TG [Hatkhola Line,Naya Line, 3 no. Line (A) Khoyar Line ] 256 unit cha Sundari Water Supply Scheme , Zone-I ,P.H No.-IandIIunder NMD-II ,PHE.Dte,Alipurduar. | 71/NMD-II | 09/01/2023 | 30 | B.B CONCERNED | 26.05 | 26.05 | 100 | 87
233 | ALIPURDUAR | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10039 | New | New Connection for Torsa TG Zone-I Phase-I | 360/22-23/PFMS | 12/12/2022 | 0 | WBSEDCL | 1.19 | 0 | 0 | 0
234 | ALIPURDUAR | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10039 | New | CONS. OF RESERVOIR (100M3), BOUNDARY WALL (80 m), PUMPHOUSE( 1.Nos) ,TUBEWELL (2 Nos.), RISING MAIN AND LAND DEVELOPMENT FOR TORSHA (Sawa Line, Chetri Line, Bancha Line,Gopal Line, Jiten Line)220 unit CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | 283/ALD | 26/04/2022 | 300 | MAHENDRA CHHETRI | 100.66 | 90.19 | 63.66 | 86
235 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME , SM/10668 | Augmentation | Providing balance FHTC for Jashodanga PWSSunder Alipurduar Division, PHE Dte. | 1559/ALD | 23/08/2023 | 30 | JUGAL CHOUDHURY | 1.67 | 0 | 0 | 0
236 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME , SM/10668 | Augmentation | Providing FHTC in school in Josodanga PWSS under Alipurduar Division P.H.E Dte. | 3362/ALD | 14/03/2023 | 30 | HARI CONSTRUCTION | 0.36 | 0.36 | 100 | 100
237 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME , SM/10668 | Augmentation | Laying of new UPVC/DI pipeline for replacement of 75mm dia UPVC pipe with 90mm dia pipeline, gap filling and re distribution system along with the others allied works under Jashodanga PWSS under Alipurduar Division, PHE Dte. | 26/ALD | 06/04/2023 | 540 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 44.98 | 0 | 0 | 45
238 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME , SM/10668 | Augmentation | Reparing of Pump House at HW site and 2nd TW site of Jashodanga PWSS Under Alipurduar Division PHE DTE. | 5384/ALD | 17/03/2025 | 60 | TAPASH KUMAR BHOWMICK | 0.96 | 0 | 0 | 0
239 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME , SM/10669 | Augmentation | Retrofitting of pipeline etc. for "Jal Swapno Program" (FHTC for every house hold) under Purba Chenpani PWSS under Alipurduar-II Block under Alipurduar Division, PHE Dte.(Re-tenter) | 443/ALD | 13/05/2022 | 30 | MATRI ENTERPRISE | 4.2 | 4.06 | 50 | 10
240 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME , SM/10669 | Augmentation | Construction of pump House, boundary wall, laying of UPVC pipe linr & Rising main connection for Purba Chepani PWSS proposed 4th TW SITE under Alipurduar Division, PHE Dte. | 3494/ALD | 23/03/2023 | 90 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 41.66 | 0 | 0 | 48
241 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME , SM/10669 | Augmentation | Providing balance FHTC for Purba Chepani PWSS under Alipurduar Division, PHE Dte. | 1589/ALD | 25/08/2023 | 30 | ANIRBAN KAR | 3.32 | 0 | 0 | 0
242 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME , SM/10669 | Augmentation | New Laying of UPVC/DI pipeline, Providing FHTC and other allied works for Augmentation of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | 1220/ALD | 10/08/2022 | 60 | SREE MAA CONSTRUCTION | 21.55 | 4.64 | 49.62 | 94
243 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME , SM/10669 | Augmentation | Material Requisition To Resource Division | 3607/ALD | 24/10/2024 | 0 | Resource Division | 5.11 | 0 | 0 | 0
244 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME , SM/10669 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
245 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME , SM/10669 | Augmentation | Sinking of 250 mm x 200 mm x 150 mtr Big dia TW by reverse rotary drilling method at 4th TW site of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | 437/ALD | 30/04/2025 | 30 | MADHAB SAHA | 11.51 | 0 | 0 | 0
246 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME , SM/10669 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
247 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME , SM/10669 | Augmentation | Laying of UPVC Pipeline Distrbutation system, Delivery line connection, Cons. of surface drain, Pathway and Land Development works for 4th site at Paschim Chepani under Purba Chepani PWSS under Alipurduar Division, PHE Dte. | 970/ALD | 12/06/2025 | 90 | PROGRESSIVE UN EMPLOYED CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD | 38.43 | 0 | 0 | 0
248 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME , SM/10669 | Augmentation | Reparing of Pump House at 2nd TW site of PURBA CHEPANI PWSS Under Alipurduar Division PHE DTE.(2nd call) | 5602/ALD | 27/03/2025 | 120 | KOUSHIK BHOWMICK | 0.85 | 0 | 0 | 100
249 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. , SM/10670 | Augmentation | Construction of pumphouse, boundary wall,laying of UPVC pipeline & rising main connection for Salsalabari PWSS proposed 4th TW site PWSS under Alipurduar Division, PHE Dte. | 3400/ALD | 16/03/2023 | 90 | BRAJA GOPAL SAHA | 39.58 | 0 | 0 | 0
250 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. , SM/10670 | Augmentation | Laying of new UPVC / DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, Land Development works, Construction of surface drain, supply of CIDF specials and other allied works in connection with the Salsalabari PWSS under Alipurduar Division, PHE Dte. | 2745/ALD | 14/12/2023 | 420 | MATRI ENTERPRISE | 16.16 | 0 | 0 | 100
251 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. , SM/10670 | Augmentation | Providing FHTC in school in Salsalabari PWSS under Alipurduar Division P.H.E Dte. | 3361/ALD | 14/03/2023 | 30 | HARIDAS GHOSH | 0.29 | 0 | 0 | 100
252 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. , SM/10670 | Augmentation | Sinking of 250 mm x 200 mm x 150 mtr Big dia TW by reverse rotary drilling method at 4th TW site of Salsalabari PWSS under Alipurduar Division, PHE Dte. | 438/ALD | 30/04/2025 | 30 | MADHAB SAHA | 11.51 | 0 | 0 | 0
253 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. , SM/10670 | Augmentation | Restoration of damaged FHTCs and replacement of Old damaged pipelines at Salsalabari PWSS under Alipurduar Division, PHE Dte. | 977/ALD | 12/06/2025 | 60 | KOUSHIK BHOWMICK | 3.88 | 0 | 0 | 0
254 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. , SM/10670 | Augmentation | Reparing of Pump House at HW and 2nd TW site of SALSALABARI PWSS Under Alipurduar Division PHE DTE. | 5383/ALD | 17/03/2025 | 60 | HARI CONSTRUCTION | 0.96 | 0 | 0 | 0
255 | ALIPURDUAR | Alipurduar Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER ALIPURDUAR DISTRICT PIPED WATER SUPPLY SCHEME , SM/10776 | New | Material Requisition To Resource Division | 967/ALD | 15/07/2022 | 0 | Resource Division | 1.43 | 0 | 0 | 0
256 | ALIPURDUAR | Alipurduar Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER ALIPURDUAR DISTRICT PIPED WATER SUPPLY SCHEME , SM/10776 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME IN 4(Four) nos. villages under different blocks having less than 100 household under Alipurduar district in connection with Jal Swapna. | 605/ALD | 31/05/2022 | 946 | M/S KAMAK ENGINEERS AND CO | 159.94 | 97.37 | 67.52 | 90
257 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME , SM/13240 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PASCHIM CHENGMARI PWSS PH NO-II | BP-2023-24-27 | 27/04/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
258 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME , SM/13240 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PASCHIM CHENGMARI PWSS PH NO-I | BP-2023-24-14 | 27/04/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
259 | ALIPURDUAR | Alipurduar Division | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME , SM/13240 | New | Providing balance FHTC for PASCHIM CHENGMARI PWSS under Alipurduar Division, PHE Dte. | 1590/ALD | 25/08/2023 | 90 | ANKIT SARKAR | 1.66 | 0 | 0 | 90
260 | ALIPURDUAR | Alipurduar Division | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME , SM/13240 | New | Laying of new UPVC/DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, land development works, construction of surface drain, pathway, supply of CIDF specials and other allied works in connection with the Paschim Chengmari PWSS under Alipurduar Division, PHE Dte. | 2523/ALD | 24/11/2023 | 270 | M/S SSB CONSTRUCTION CO. | 83.57 | 0 | 0 | 57
261 | ALIPURDUAR | Alipurduar Division | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME , SM/13240 | New | Material Requisition To Resource Division | 133/ALD | 10/01/2024 | 0 | Resource Division | 5.72 | 0 | 0 | 0
262 | ALIPURDUAR | Alipurduar Division | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME , SM/13240 | New | Cons. of P/H and T/W Boring by ODEX-165 Method of drilling at HW and 2nd site , LDS with UPVC P/L including rising main and delivery connection, Cons. of 200 Cum OHR as per Departmental Design & drawing , providing FHTC and others allied works for PASCHIM CHENGMARI PWSS Under Alipurduar Division PHE DTE. | 2862/ALD | 17/01/2023 | 806 | M/S SSB CONSTRUCTION CO. | 312.15 | 201.82 | 64.66 | 65
263 | ALIPURDUAR | Alipurduar Division | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME , SM/13240 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
264 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME , SM/13240 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
265 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME , SM/13240 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1347/NMD-II | 19/06/2025 | 30 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
266 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME , SM/13240 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Paschim Chengmari Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd | 2484/NMD-II | 11/08/2023 | 541 | DILIP MAHATO | 20.14 | 0 | 0 | 100
267 | ALIPURDUAR | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | Material Requisition To Resource Division | 3044/ALD | 08/02/2023 | 0 | Resource Division | 21.01 | 0 | 0 | 0
268 | ALIPURDUAR | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | NEW SERVICE CONNECTION CHARGE FOR PURBA KHALISHAMARI W/S/S P/H NO.2 | BP-2023-24-182 | 15/06/2023 | 0 | WBSEDCL | 1.41 | 0 | 0 | 0
269 | ALIPURDUAR | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | NEW SERVICE CONNECTIO CHARGE FOR PURBA KHALISHAMARI W/S/S P/H NO.1 | BP-2023-24-181 | 15/06/2023 | 0 | WBSEDCL | 1.41 | 0 | 0 | 0
270 | ALIPURDUAR | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | Constructions of pump house & Sinking of 250 mm x 200 mm X 150 mtr. Big dia. Tube well at HW site & 2nd site , laying of distribution system with UPVC pipeline , Constructions of 250 Cum OHR as per Departmental Design & drawing including soil test, providing FHTC and others allied works for Purba Khalisamari PWSS Under Alipurduar Division PHE DTE. | 3577/ALD | 27/03/2023 | 840 | HARIDAS GHOSH | 438.25 | 281.97 | 64.34 | 72
271 | ALIPURDUAR | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | Supply of CIDF & CISS Pipes and specials for Purba Khalshamari WSS Under Alipurduar Division P.H.E Dte. | 1604/ALD | 25/08/2023 | 30 | HARI CONSTRUCTION | 6.76 | 0 | 0 | 100
272 | ALIPURDUAR | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing, Land development works, construction of surface drain, pathway, trial run and others allied works in connection with the Purba Khailshmari PWSS under Alipurduar Division, PHE Dte. | 4236/ALD | 12/12/2024 | 60 | HARI CONSTRUCTION | 75.41 | 0 | 0 | 0
273 | ALIPURDUAR | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PURBA KHALISHAMARI water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 2365/NMD-II | 08/08/2023 | 30 | MENAKA ENTERPRISE | 21.73 | 0 | 0 | 100
274 | ALIPURDUAR | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | Supply of CIDF/CIPE Pipes and Special & CI Jeffy Coupling for Purba Khalishamari Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 699/ALD | 07/03/2024 | 30 | HARI CONSTRUCTION | 15.31 | 0 | 0 | 70
275 | ALIPURDUAR | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | Material Requisition To Resource Division | 106/ALD | 10/01/2024 | 0 | Resource Division | 11.82 | 0 | 0 | 0
276 | ALIPURDUAR | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | Material Requisition To Resource Division | 3613/ALD | 24/10/2024 | 0 | Resource Division | 7.78 | 0 | 0 | 0
277 | ALIPURDUAR | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | Material Requisition To Resource Division | 4273/ALD | 13/12/2024 | 0 | Resource Division | 11.33 | 0 | 0 | 0
278 | ALIPURDUAR | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
279 | ALIPURDUAR | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
280 | ALIPURDUAR | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
281 | ALIPURDUAR | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. , SM/13243 | New | Solarization of grid connected pumping installation at different PWSS at Alipurduar -II block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 819/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
282 | ALIPURDUAR | Alipurduar Division | NAOTHOARTARI PIPED WATER SUPPLY SCHEME , SM/12754 | New | Material Requisition To Resource Division | 3045/ALD | 08/02/2023 | 0 | Resource Division | 7.53 | 0 | 0 | 0
283 | ALIPURDUAR | Northern Mechanical Division II | NAOTHOARTARI PIPED WATER SUPPLY SCHEME , SM/12754 | New | QUOTATION FOR NEW SERVICE CONNECTION AT NATHUATARI PWSS P/H NO. II | BP-2023-24-285 | 21/08/2023 | 0 | WBSEDCL | 5.45 | 0 | 0 | 0
284 | ALIPURDUAR | Northern Mechanical Division II | NAOTHOARTARI PIPED WATER SUPPLY SCHEME , SM/12754 | New | QUOTATION FOR NEW SERVICE CONNECTION AT NATHUATARI PWSS P/H NO.I | BP-2023-24-294 | 21/08/2023 | 0 | WBSEDCL | 5.92 | 0 | 0 | 0
285 | ALIPURDUAR | Alipurduar Division | NAOTHOARTARI PIPED WATER SUPPLY SCHEME , SM/12754 | New | Material Requisition To Resource Division | 4256/ALD | 13/12/2024 | 0 | Resource Division | 9.16 | 0 | 0 | 0
286 | ALIPURDUAR | Alipurduar Division | NAOTHOARTARI PIPED WATER SUPPLY SCHEME , SM/12754 | New | Construction of Tube Well, Pump House, Boundary Wall, OHR, Laying Of Rising Main, Distribution System including soil test and providing FHTC for Naothoartari PWSS Under Alipurduar Division, PHE Dte. | 3638/ALD | 31/03/2023 | 1080 | CHINMOY BHATTACHARJEE | 267.68 | 0 | 0 | 40
287 | ALIPURDUAR | Northern Mechanical Division II | NAOTHOARTARI PIPED WATER SUPPLY SCHEME , SM/12754 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Naothoatari water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | 2389/NMD-II | 09/08/2023 | 601 | MUSTAFI CONCERN | 18.11 | 0 | 0 | 90
288 | ALIPURDUAR | Alipurduar Division | NAOTHOARTARI PIPED WATER SUPPLY SCHEME , SM/12754 | New | Gap Filling of distribution line, land development at Pump House and others allied works for NAOTHOARTARI PWSS within Alipurduar Block-I under Alipuduar Division PHE.Dte. | 973/ALD | 12/06/2025 | 90 | CHINMOY BHATTACHARJEE | 42.38 | 0 | 0 | 0
289 | ALIPURDUAR | Northern Mechanical Division II | NAOTHOARTARI PIPED WATER SUPPLY SCHEME , SM/12754 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar-I Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 822/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
290 | ALIPURDUAR | Northern Mechanical Division II | NAOTHOARTARI PIPED WATER SUPPLY SCHEME , SM/12754 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
291 | ALIPURDUAR | Alipurduar Division | NAOTHOARTARI PIPED WATER SUPPLY SCHEME , SM/12754 | New | "Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Augmentation of Nathoatari Water Supply Scheme (SM/12754) of Alipurduar-I Block under Alipurduar Division P.H.E. Dte. " | 843/ALD | 14/03/2024 | 183 | MAKALI ENGINEERING CORPORATION | 14.43 | 0 | 0 | 25
292 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Soil investigation works for proposed overhead reservoir of KAIJALI BUSTI PWSS under Alipurduar Division, PHE Dte. | 2248/ALD | 21/11/2022 | 30 | K S GROUP | 0.65 | 0.65 | 100 | 11
293 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Tubewell boring by ODEX-165 method of drilling, construction of Pump House, Boundary wall at proposed 4th TW site of Kaijali PWSS under Alipurduar Division, PHE Dte. | 07/ALD | 04/04/2023 | 120 | PRITAM DAS | 17.41 | 5.58 | 34.52 | 100
294 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Material Requisition To Resource Division | 1588/ALD | 14/09/2022 | 0 | Resource Division | 30.75 | 0 | 0 | 0
295 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | QUATATION | BP-2023-24-484 | 12/12/2023 | 0 | WBSEDCL | 5.11 | 0 | 0 | 0
296 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | QUOTATION | BP-2023-24-485 | 12/12/2023 | 0 | WBSEDCL | 11.22 | 0 | 0 | 0
297 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Land development works, Construction of surface drain, pathway, and other allied works at Kaijali Busty 3rd tube well site with the Augmentation of Kaijili Busty PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE.(SM/11958) | 2274/ALD | 05/08/2024 | 60 | KAMALESH ROY | 3.84 | 0 | 0 | 50
298 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Laying of new HDPE pipeline for interconnection in the distribution system and bridge/culvert crossing land developmentworks, construction of surface drain, pathway and other allied works in connection with the Augmentation of KAijali Basty PWSS (SM/11958) under Alipurduar Division, PHE Dte. | 3958/ALD | 26/11/2024 | 60 | MAHENDRA CHHETRI | 29.4 | 0 | 0 | 0
299 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Tube well Boring by ODEX-165 method of drilling at 3rd TWsite including laying Distribution system with new HDPE Pipeline (Part-A), Providing FHTC and other allied works for augmentation of KAIJALI BUSTY PWSS under Alipurduar Division, PHE Dte. | 2240/ALD | 21/11/2022 | 600 | KAMALESH ROY | 70.16 | 44.79 | 71.21 | 68
300 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Construction of 200 cum OHR as per Departmental Design and drawing at KAIJALI BUSTY PWSS under Alipurduar Division, PHE Dte. | 2497/ALD | 13/12/2022 | 540 | MAHENDRA CHHETRI | 68.63 | 0 | 0 | 70
301 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Material Requisition To Resource Division | 3609/ALD | 24/10/2024 | 0 | Resource Division | 11.11 | 0 | 0 | 0
302 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Kaijali Basty Water Supply Scheme TW No.- I and II under NMD-II,PHE.Dte,Apd. | 2480/NMD-II | 11/08/2023 | 30 | DIAMOND ELECTRICAL WORKS | 25.08 | 0 | 0 | 90
303 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Reparing of Pump House at 2nd TW site of Kaijali Basty PWSS Under Alipurduar Division PHE DTE. | 5382/ALD | 17/03/2025 | 60 | TAPASH KUMAR BHOWMICK | 0.92 | 0 | 0 | 0
304 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
305 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Reparing of Pump House at Headwork site of Kaijali Basty PWSS Under Alipurduar Division PHE DTE. | 5381/ALD | 17/03/2025 | 60 | TAPASH KUMAR BHOWMICK | 0.94 | 0 | 0 | 0
306 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Laying Rising Main, providing FHTC, Repairing existing Pipe line, Restoration of FHTC at 4th TW site and Gap filing in distribution system at Kaijali Busty PWSS under Alipurduar Division, PHE Dte. | 1186/ALD | 26/06/2025 | 75 | RAMEN DEY & CO | 15.59 | 0 | 0 | 0
307 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Restoration of damaged FHTCs of Kaijali Busty PWSS under Alipurduar Division, PHE Dte. | 1187/ALD | 26/06/2025 | 45 | RAMEN DEY & CO | 4 | 0 | 0 | 0
308 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME , SM/11958 | Augmentation | Land development works, Construction of surface drain, pathway, and other allied works at Kaijali Busty 4th tube well site with the Augmentation of Kaijali Busty PWSS Under Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE.(SM/11958) | 2273/ALD | 05/08/2024 | 180 | RAMEN DEY & CO | 4.28 | 0 | 0 | 100
309 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME , SM/11959 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Uttar Sishubari PWSS under Alipurduar Division, PHE Dte. Part-4 | 1492/ALD | 05/09/2022 | 90 | MITHUN DAS | 24.32 | 0 | 0 | 0
310 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME , SM/11959 | Augmentation | Providing FHTC from existing distribution system as per specification for UTTAR SISHUBARI PWSS under Alipurduar Division, PHE Dte. | 1991/ALD | 15/09/2023 | 90 | MITHUN DAS | 57.24 | 0 | 0 | 0
311 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME , SM/11959 | Augmentation | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main, laying of DI and UPVC pipeline for Uttar Sishubari PWSS under Alipurduar Division, PHE Dte. | 387/ALD | 19/05/2023 | 480 | MITHUN DAS | 93.44 | 0 | 0 | 62
312 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME , SM/11959 | Augmentation | Construction of Tubewell by ODEX-165 method of drilling at HWS, construction of pump house and boundary wall at HWS, laying of rising main for Aug. Of Uttar Sishubari PWSS under Alipurduar Division, PHE Dte. | 691/ALD | 07/03/2024 | 45 | MITHUN DAS | 31.88 | 0 | 0 | 0
313 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME , SM/11959 | Augmentation | Soil investigation at OHR site and construction of 450cum OHR at Uttar Sishubari under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 1767/ALD | 07/06/2024 | 300 | BISWAJIT DUTTA | 118.67 | 0 | 0 | 0
314 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME , SM/11959 | Augmentation | Laying of distribution pipe in Uttar Sishubari Bazar area and Madarihat Bazar Area and allied works Under Birpara Sub-division, Alipurduar Division PHE DTE. | .2663/ALD | 22/12/2022 | 120 | MITHUN DAS | 25.68 | 17.13 | 68.06 | 100
315 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME , SM/11959 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR UTTAR SISHUBARI MADARIHAT GOPAL BAGAN PWSS | BP-170/24-25 | 03/07/2024 | 0 | WBSEDCL | 5.41 | 0 | 0 | 0
316 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME , SM/11959 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of UTTAR SISHUBARI Water Supply Scheme TWNo- I AND II under NMDII,PHE.Dte,APD. | 2887/NMD-II | 17/10/2023 | 762 | S.D CONCERN WORKSHOP | 22.02 | 0 | 0 | 45
317 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME , SM/11959 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
318 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME , SM/11959 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1048/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
319 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Laying of CI/DI/MS/HDPE pipe and providing FHTC for BIRPARA TEA GARDEN (ZONE-3) AREA PWSS Under Alipurduar Division PHE DTE. PART-A | 2870/ALD | 17/01/2023 | 60 | ANUP KUNDU CONSTRUCTION CO. | 95.98 | 81.06 | 84.46 | 7
320 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Birpara (South) PWSS under Alipurduar Division, PHE Dte. | 2876/ALD | 17/01/2023 | 45 | DILIP MAHATO | 34.6 | 0 | 0 | 0
321 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Laying of CI/DI/MS/HDPE pipe and providing FHTC for BIRPARA TEA GARDEN (ZONE-2) AREA PWSS Under Alipurduar Division PHE DTE. PART-A | 2869/ALD | 17/01/2023 | 60 | AMBITIOUS ENTERPRISE | 97.44 | 41.77 | 42.87 | 7
322 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Birpara Zone-II (Middle) PWSS under Alipurduar Division, PHE Dte. | 2875/ALD | 17/01/2023 | 45 | NARENDRA BHADANI. | 24.11 | 0 | 0 | 0
323 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main for Zone-I 1st TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | 386/ALD | 19/05/2023 | 120 | KAJAL KUMAR DE | 32.74 | 6.57 | 20.07 | 30
324 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main for Zone-III 2nd TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | 962/ALD | 12/07/2023 | 120 | SUBIR GHOSH | 32.45 | 0 | 0 | 0
325 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Providing FHTC from existing distribution system as per specification for BIRPARA PWSS under Alipurduar Division, PHE Dte. | 2105/ALD | 29/09/2023 | 60 | GIRIRAJ ENTERPRISE | 34.39 | 0 | 0 | 0
326 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Birpara Zone-I (North) PWSS under Alipurduar Division, PHE Dte. Part-2 | 2874/ALD | 17/01/2023 | 45 | BILTU DAS | 24.22 | 0 | 0 | 0
327 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Laying of HDPE pipe line for the Birpara Water Supply Scheme under Alipurduar Division,PHE Dte.(Part-2) | 1571/ALD | 22/11/2021 | 60 | PRAMESH LAMA | 51.34 | 44.47 | 86.62 | 7
328 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | 1453/ALD | 25/01/2021 | 45 | PRAMESH LAMA | 33.97 | 0 | 0 | 100
329 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Material Requisition To Resource Division | 2722/ALD | 13/12/2023 | 0 | Resource Division | 137.01 | 0 | 0 | 0
330 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | SHIFTING OF LTOH LINE AT BHANUNAGAR UNDER BIRPARA CCC | BP-2023-24-130 | 23/05/2023 | 0 | WBSEDCL | 0.47 | 0 | 0 | 0
331 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | NEW CONNECTION FOR BIRPARA(AUG) ZONE- IPHNO-II | BP-2023-24-460 | 07/12/2023 | 0 | WBSEDCL | 4.26 | 0 | 0 | 0
332 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | NEW CONNECTION FOR BIRPARA (AUG) ZONE-I PHNO-III | BP-2023-24-461 | 07/12/2023 | 0 | WBSEDCL | 5.5 | 0 | 0 | 0
333 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | QUOTATION FOR BURNT METER AT BIRPARA | BP-2023-24-329 | 27/09/2023 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
334 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Laying of HDPE pipe line for the Birpara Water Supply Scheme under Alipurduar Division,PHE Dte.(Part-3) | 1570/ALD | 22/11/2021 | 420 | SOUVIK ROY PALADHI | 37.07 | 0 | 0 | 61
335 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Construction of 550cum. OHR for Birpara TG (Middle) Water Supply Scheme under Alipurduar Division, PHE Dte. | 2867/ALD | 17/01/2023 | 180 | DILIP MAHATO | 98.12 | 23.46 | 23.9 | 85
336 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Laying of CI/DI/MS/HDPE pipe and providing FHTC for BIRPARA TEA GARDEN (ZONE-3) AREA PWSS Under Alipurduar Division PHE DTE. PART-C | 2872/ALD | 17/01/2023 | 60 | DILIP MAHATO | 96.76 | 62.86 | 64.96 | 65
337 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Construction of pump house boundary wall Tubewell boring (by ODEX-165 method of drilling) and rising main for Zone-III 3rd TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | 166/ALD | 26/04/2023 | 480 | RATAN DUTTA | 31.78 | 0 | 0 | 65
338 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Construction of pump house boundary wall Tubewell boring (by ODEX-165 method of drilling) and rising main for Zone-II 3rd TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | 93/ALD | 18/04/2023 | 120 | SUBHAK CHIK BARAIK | 31.63 | 0 | 0 | 100
339 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main for Zone-II 1st TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | 663/ALD | 07/06/2023 | 480 | BRAJA GOPAL SAHA | 31.58 | 0 | 0 | 20
340 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Construction of Pump House, B/wall, TW boring by ODEX-165 method of drilling and rising main for Zone-I 3rd TW Site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | 2602/ALD | 04/12/2023 | 482 | FAUDA SINGH CHHETRI | 31.46 | 0 | 0 | 61
341 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | "Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II P.H.E. Dte." | 419/AMSD | 16/10/2023 | 61 | MUSTAFI CONCERN | 0.69 | 0 | 0 | 100
342 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | SOIL INVESTIGATION AT OHR AND CONS. OF 450 CUM OHR AT ZONE-3 FOR AUGMENTATIN OF BIRPARA PWSS UNDER ALIPURDUAR DIVISION OF NORTH BENGAL CIRCLE-I, PHE DTE. | 234/ALD | 17/01/2024 | 381 | AMBITIOUS ENTERPRISE | 239.31 | 0 | 0 | 55
343 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Tube well Boring by ODEX-165 Method of drilling at TUBE WELL site including laying distribution system with new HDPE pipeline ,One nos pump house & boundary wall, providing FHTC and others allied works for Bhutri Forest PWSS Under Alipurduar Division PHE DTE. | 94/ALD | 18/04/2023 | 120 | FAUDA SINGH CHHETRI | 34.7 | 29.27 | 100 | 100
344 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Supply of drinking water through tanker by hired vehicle to mitigate drinking water crisis at Huntapara TG, Dhumchipara TG and Gargenda TG and lankapara TG under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | 2174/ALD | 06/10/2023 | 45 | BHAGWATI BHUJEL | 9.82 | 0 | 0 | 100
345 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Protective and Decorative Acrylic exterior paint on existing 350 cum OHR at Birpara of Birpara Sub-Division under Alipurduar Division, P.H.E.Dte. (SM/14233) | 824/ALD | 14/03/2024 | 60 | BHAGWATI BHUJEL | 1.96 | 0 | 0 | 10
346 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Sinking of Big dia. Tubewell (200 x 150 mm dia.)by modified DTH -ODEX method of drilling at Paschim Khairbari PWSS(SM/10672) and Birpara PWSS Zone-II, 4th TW site(SM/14233)of Birpara Sub-Division under Alipurduar Division, PHE Dte. | 749/ALD | 12/03/2024 | 135 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 33.26 | 0 | 0 | 50
347 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Material Requisition To Resource Division | 138/ALD | 10/01/2024 | 0 | Resource Division | 61.13 | 0 | 0 | 0
348 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Material Requisition To Resource Division | 3980/ALD | 27/11/2024 | 0 | Resource Division | 30.8 | 0 | 0 | 0
349 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR KFC GROUND AUGUMENTATION OF BIRPARA PWSS ZONE-III P/H NO-II | BP-2023-24-644 | 29/02/2024 | 0 | WBSEDCL | 7.01 | 0 | 0 | 0
350 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR AUGUMENTATION OF BIRPARA ZONE-I P/HNO-I | BP-2023-24-696 | 14/03/2024 | 0 | WBSEDCL | 7.9 | 0 | 0 | 0
351 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | New Service Connection for Birpara Thana PWSS, Zone-II, P/H No-II | BP-2023-24-618 | 16/02/2024 | 0 | WBSEDCL | 3.74 | 0 | 0 | 0
352 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR AUGUMENTATION OF BIRPARA Z-II P/HNO-IV | BP-2023-24-688 | 14/03/2024 | 0 | WBSEDCL | 6.55 | 0 | 0 | 0
353 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | NEW SERVICE CONNECTION FOR Augumentation of Birpara PWSS ZONE-IIII P/H NO-III | BP-2023-24-572 | 01/02/2024 | 0 | WBSEDCL | 12.06 | 0 | 0 | 0
354 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR BIRPARA CIRCUS GROUND ZONE-III, P/H NO-I | BP-2023-24-695 | 14/03/2024 | 0 | WBSEDCL | 9.12 | 0 | 0 | 0
355 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for BirparaZone-I (North) PWSS under Alipurduar Division, PHE Dte. Part-1 | 2873/ALD | 17/01/2023 | 888 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 24.27 | 0 | 0 | 58
356 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro mechanical component along with Cu. wound line voltage corrector for Augmentation of Birpara water supply scheme TW No.- I,II and III of Zone-I and TW No.- I,II,III and IV of Zone-II and TW No.- I,II and III of Zone-III under Northern Mechanical Division-II, PHE Dte, Alipurduar. | 2873/NMD-II | 17/10/2023 | 808 | EASTERN INDIA SALES & SERVICE | 176.42 | 0 | 0 | 80
357 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Construction of Pump House, B/wall, TW boring by ODEX-165 method of drilling and rising main for Zone-I Headwork TW Site at Augmentation od Birpara PWSS under Alipurduar Division, PHE Dte. | 2543/ALD | 28/11/2023 | 600 | KAMALESH ROY | 44.55 | 0 | 0 | 50
358 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Construction of Pump House, B/wall, TW boring by ODEX-165 method of drilling and rising main for Zone-III Headwork TW Site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | 2544/ALD | 28/11/2023 | 850 | RATAN DUTTA | 46.23 | 0 | 0 | 5
359 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Soil investigation at OHR site and construction of 450cum OHR at Zone-1 for Augmentation of Birpara PWSS under Alipurduar Divisionof North Bengal Circle-I, PHE Dte. | 495/ALD | 16/02/2024 | 585 | KAMALESH ROY | 120.29 | 0 | 0 | 10
360 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Fabrication,Erection of Signage (268 nos) of Pump house/OHR site democration with in Kumargram, Falakata,Madarihat-Birpara Block for Different PWSS of JJM Project Under Alipurduar Division P.H.E.Dte. | 3520/ALD | 04/10/2024 | 330 | LIMRA SOCIAL WELFARE SOCIETY | 31.26 | 0 | 0 | 92
361 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Laying of DI & HDPE Pipe line, Construction of sluice valve chamber, trenchless pipe laying & other works for providing FHTC at Birpara Zone-I Area under Birpara PWSS under Alipurduar Division, PHE DTE. | 4595/ALD | 03/01/2025 | 225 | KAMALESH ROY | 149.76 | 0 | 0 | 1
362 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Cons. of pump house, boundary wall and Rising Main for Zone-II 4thTube well site at Aug. of Birpara PWSS of Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/14233) | 850/ALD | 14/03/2024 | 360 | RATAN DUTTA | 18.26 | 0 | 0 | 65
363 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer ,Birpara Sub- Division ,P.H.E. Dte..(from 01.04.2024 to 01.03.2025) | 893/ALD | 15/03/2024 | 365 | PARITOSH SUTRADHAR | 4.8 | 0 | 0 | 0
364 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Laying of DI & HDPE Pipe line, Construction of sluice valve chamber, trenchless pipe laying & other works for providing FHTC AT BIRPARA Zone-II Area under BIRPARA PWSS under Alipurduar Division, PHE Laying of DI & HDPE Pipe line, Construction of sluice valve chamber, trenchless pipe laying & other works for providing FHTC AT BIRPARA Zone-II Area under BIRPARA PWSS under Alipurduar Division, PHE DTE.. | 111/ALD | 16/04/2025 | 45 | RATAN DUTTA | 120.16 | 0 | 0 | 0
365 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
366 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME , SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1048/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
367 | ALIPURDUAR | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | Providing balance FHTC for MARAKHATA PWSS under Alipurduar Division, PHE Dte. | 1569/ALD | 23/08/2023 | 30 | HARI CONSTRUCTION | 4.69 | 0 | 0 | 0
368 | ALIPURDUAR | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | Supply of CIDF & CISS Pipes and specials for Marakhata WSS Under Alipurduar Division P.H.E Dte. | 1598/ALD | 25/08/2023 | 30 | HARI CONSTRUCTION | 6.76 | 6.76 | 100 | 100
369 | ALIPURDUAR | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | Material Requisition To Resource Division | 1475/ALD | 16/08/2023 | 0 | Resource Division | 29.72 | 0 | 0 | 0
370 | ALIPURDUAR | Northern Mechanical Division II | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MARAKHATA PWSS PH NO-II | BP-2023-24-26 | 27/04/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
371 | ALIPURDUAR | Northern Mechanical Division II | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MARAKHATA PWSS PH NO-I | BP-2023-24-15 | 27/04/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
372 | ALIPURDUAR | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | Constructions of P/H and T/W Boring by ODEX-165 Method of drilling at HW and 2nd site , LDS with UPVC P/L inclu. rising main and delivery connection, Cons. of 200 Cum OHR as per Departmental Design & drawing alongwith soil investigation, providing FHTC and others allied works for MARAKHATA PWSS Under Alipurduar Division PHE DTE. | 2863/ALD | 17/01/2023 | 900 | HARIDAS GHOSH | 355.8 | 207.72 | 58.38 | 27
373 | ALIPURDUAR | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, Supply of DI pipe and specials, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at MARAKHATA HW site PWSS under Alipurduar Division, PHE Dte. | 85/ALD | 10/01/2024 | 360 | HARIDAS GHOSH | 65.13 | 0 | 0 | 35
374 | ALIPURDUAR | Northern Mechanical Division II | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MARAKHATA water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 2160/NMD-II | 27/07/2023 | 30 | S.S ENTERPRISES | 19.12 | 0 | 0 | 100
375 | ALIPURDUAR | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | Material Requisition To Resource Division | 131/ALD | 10/01/2024 | 0 | Resource Division | 8.44 | 0 | 0 | 0
376 | ALIPURDUAR | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | Material Requisition To Resource Division | 3615/ALD | 24/10/2024 | 0 | Resource Division | 8.11 | 0 | 0 | 0
377 | ALIPURDUAR | Northern Mechanical Division II | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | ADDITIONAL QUOTATION FOR MARAKHATA PWSS PH NO-2 | BP-01/24-25 | 08/04/2024 | 0 | WBSEDCL | 4.3 | 0 | 0 | 0
378 | ALIPURDUAR | Northern Mechanical Division II | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | Solarization of grid connected pumping installation at Different PWSS at Kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 820/NMD-II | 06/03/2025 | 30 | WATER TECH | 29.68 | 0 | 0 | 0
379 | ALIPURDUAR | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
380 | ALIPURDUAR | Northern Mechanical Division II | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
381 | ALIPURDUAR | Northern Mechanical Division II | MARAKHATA PIPED WATER SUPPLY SCHEME. , SM/13304 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1347/NMD-II | 19/06/2025 | 30 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
382 | ALIPURDUAR | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Providing balance FHTC for Dakshin Majidkhana PWSS under Alipurduar Division, PHE Dte. | 1564/ALD | 23/08/2023 | 45 | HARI CONSTRUCTION | 6.77 | 0 | 0 | 0
383 | ALIPURDUAR | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Material Requisition To Resource Division | 1472/ALD | 16/08/2023 | 0 | Resource Division | 24.3 | 0 | 0 | 0
384 | ALIPURDUAR | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Material Requisition To Resource Division | 2395/ALD | 08/11/2023 | 0 | Resource Division | 8.64 | 0 | 0 | 0
385 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | QUOTATION FOR NEW SERVICE CONNECTION AT DAKSHIN MAJIDKHANA PWSS P/H NO. II | BP-2023-24-292 | 21/08/2023 | 0 | WBSEDCL | 5.99 | 0 | 0 | 0
386 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | NEW SERVICE CONNECTIO CHARGE FOR DAKSHIN MAJIDKHANA W/S/S P/H NO.1 | BP-2023-24-178 | 15/06/2023 | 0 | WBSEDCL | 1.41 | 0 | 0 | 0
387 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN MAJIDKHANA water supply scheme, TW no I & II under Northern Mechanical Division-II, PHE Dte. Alipurduar | 1165/NMD-II | 15/06/2023 | 30 | SUBODH KUMAR BANIK | 21.66 | 0 | 0 | 100
388 | ALIPURDUAR | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. Big dia. TW at HW and 2nd site, LDS with UPVC pipeline, Cons. of 200 cum OHR as per Departmental Design and drawing inclu. Soil testing, providing FHTC and others allied works for Dakshin Majidkhana PWSS Under Alipurduar Division PHE DTE. | 2854/ALD | 17/01/2023 | 1020 | HARIDAS GHOSH | 390.45 | 279.48 | 71.58 | 75
389 | ALIPURDUAR | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Supply of CIDF Specials and Jeffy Coupling for Dakshin Majidkhana (SM/13305) WSS under Alipurduar Division, PHE Dte. | 4264/ALD | 13/12/2024 | 60 | GUHA ENTERPRISE | 19.58 | 0 | 0 | 50
390 | ALIPURDUAR | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Continuation of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte.(from 01.01.2024 to 29.02.2024) | 2905/ALD | 29/12/2023 | 62 | MATRI ENTERPRISE | 0.8 | 0 | 0 | 0
391 | ALIPURDUAR | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
392 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Solarization of grid connected pumping installation at Different PWSS at APD-I ,APD-II , Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1333/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
393 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
394 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Solarization of grid connected pumping installation at different PWSS at Alipurduar -II block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 819/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
395 | ALIPURDUAR | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Supply of DI pipe & CI special for Dakhin Majidkhana PWSS under Alipurduar Division PHE Dte. | 392/ALD | 19/05/2023 | 801 | TAPASH KUMAR BHOWMICK | 40.11 | 5.64 | 15.39 | 80
396 | ALIPURDUAR | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Supply of CIDF & CISS Pipes and specials for Dakshin Majidkhana WSS Under Alipurduar Division P.H.E Dte. | 1605/ALD | 25/08/2023 | 640 | HARI CONSTRUCTION | 6.76 | 0 | 0 | 80
397 | ALIPURDUAR | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. , SM/13305 | New | Laying of rising main/distribution pipeline, supply of DI pipe and specials, horizontal boring by HDD method, bridge and culvert crossing, along with the other allied works at Dakshin Majidkhana PWSS under under Alipurduar Division, PHE Dte. | 206/ALD | 16/01/2024 | 510 | HARIDAS GHOSH | 41.16 | 0 | 0 | 25
398 | ALIPURDUAR | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | Providing balance FHTC for CHALNIPAK PWSS under Alipurduar Division, PHE Dte. | 1568/ALD | 23/08/2023 | 45 | SOUVIK ROY PALADHI | 9.97 | 0 | 0 | 0
399 | ALIPURDUAR | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | Material Requisition To Resource Division | 224/ALD | 03/05/2023 | 0 | Resource Division | 13.14 | 0 | 0 | 0
400 | ALIPURDUAR | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | Material Requisition To Resource Division | 2399/ALD | 08/11/2023 | 0 | Resource Division | 10.15 | 0 | 0 | 0
401 | ALIPURDUAR | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | QUOTATION FOR NEW SERVICE CONNECTION AT CHALNIPAK PWSS P/H NO-III | BP-2023-24-286 | 21/08/2023 | 0 | WBSEDCL | 5.44 | 0 | 0 | 0
402 | ALIPURDUAR | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | NEW SERVICE CONNECTIO CHARGE FOR CHALNIPAK W/S/S P/H NO.2 | BP-2023-24-177 | 15/06/2023 | 0 | WBSEDCL | 1.41 | 0 | 0 | 0
403 | ALIPURDUAR | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | QUOTATION FOR NEW SERVICE CONNECTION AT CHALNIPAK PWSS P/H NO. I | BP-2023-24-291 | 21/08/2023 | 0 | WBSEDCL | 8.12 | 0 | 0 | 0
404 | ALIPURDUAR | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | Constructions of pump house and Sinking of 250 mm x 200 mm X 150 mtr Big dia Tubewel at HW site , 2nd site and 3 rd Site Laying of distribution system with UPVC pipeline , Constructions of 200 Cum OHR as per Departmental Design and drawing , including the Soil investigation works providing FHTC and others allied works for Chalnipak PWSS Under Alipurduar Division PHE DTE. | 3156/ALD | 22/02/2023 | 720 | SOUVIK ROY PALADHI | 481.77 | 300.74 | 62.42 | 50
405 | ALIPURDUAR | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | Supply of CIDF & CISS Pipes and specials for Chalnipak WSS Under Alipurduar Division P.H.E Dte. | 1607/ALD | 25/08/2023 | 30 | SOUVIK ROY PALADHI | 7.89 | 0 | 0 | 0
406 | ALIPURDUAR | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | Supply of CIDF Specials & Jeffy Coupling for Chalnipak (SM/15534) WSS under Alipurduar Division, PHE Dte. | 4540/ALD | 26/12/2024 | 30 | SOUVIK ROY PALADHI | 19.94 | 0 | 0 | 0
407 | ALIPURDUAR | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/ culvert crossing , Land developement works , Constructions of surface drain , pathway and others allied works in connection with the Chalnipak PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/15534) | 2276/ALD | 05/08/2024 | 60 | SOUVIK ROY PALADHI | 77.22 | 0 | 0 | 0
408 | ALIPURDUAR | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | ADDITIONAL QUOTATION FOR CHALNIRPAK PH NO-III | BP-06/24-25 | 08/04/2024 | 0 | WBSEDCL | 0.38 | 0 | 0 | 0
409 | ALIPURDUAR | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
410 | ALIPURDUAR | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte. (from01.05.2025 to 30.04.2026) | 419/ALD | 30/04/2025 | 365 | APSARI BHOWMICK | 4.8 | 0 | 0 | 0
411 | ALIPURDUAR | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
412 | ALIPURDUAR | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | Solarization of grid connected pumping installation at different PWSS at Alipurduar -II block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 819/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
413 | ALIPURDUAR | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. , SM/15534 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Chalnipak water supply scheme, TW no I,II and III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | 2287/NMD-II | 31/07/2023 | 30 | QUAZI NOZRUL ISLAM | 27.85 | 0 | 0 | 100
414 | ALIPURDUAR | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14214 | New | Material Requisition To Resource Division | 220/ALD | 03/05/2023 | 0 | Resource Division | 36.92 | 0 | 0 | 0
415 | ALIPURDUAR | Northern Mechanical Division II | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14214 | New | NEW SERVICE CONNECTION FOR BEECH TG PWSS P/H NO II,HASIMARA APPLICATION NO 4003208193 | BP-2023-24-324 | 27/09/2023 | 0 | WBSEDCL | 5.67 | 0 | 0 | 0
416 | ALIPURDUAR | Northern Mechanical Division II | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14214 | New | NEW SERVICE CONNECTION FOR BEECH TG PWSS P/H NO I,HASIMARA APPLICATION NO 4003208190 | BP-2023-24-323 | 27/09/2023 | 0 | WBSEDCL | 5.4 | 0 | 0 | 0
417 | ALIPURDUAR | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14214 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new HDPE pipeline , Constructions of 150 Cum OHR as per Departmental Design & drawing , TWO nos. pump house & boundary wall, providing FHTC, Soil Investigation work and others allied works for BEECH TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. (2nd call) | 3398/ALD | 16/03/2023 | 540 | MAHENDRA CHHETRI | 309.23 | 202.99 | 40.72 | 91
418 | ALIPURDUAR | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14214 | New | Providing balance FHTC from existing distribution system as per specification for BEECH TG PWSS under Alipurduar Division, PHE Dte. | 2184/ALD | 06/10/2023 | 300 | D. K. & SONS | 16.37 | 0 | 0 | 100
419 | ALIPURDUAR | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14214 | New | Supply of DIDF pipes and specials and Sluice Valve for Beech TG Water Supply Scheme (SM/14214) under Alipurduar Division P.H.E. Dte. | 1953/ALD | 02/07/2024 | 30 | KAMALA VALVES AND ENGINEERING PRIVATE LIMITED | 15.43 | 0 | 0 | 85
420 | ALIPURDUAR | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14214 | New | Material Requisition To Resource Division | 100/ALD | 10/01/2024 | 0 | Resource Division | 9.73 | 0 | 0 | 0
421 | ALIPURDUAR | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14214 | New | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Head Quarter, Alipurduar Division, P.H.E. Dte.(from 01.01.2024 to 31.12.2024) | 161/ALD | 11/01/2024 | 366 | DIPAK DAS | 4.8 | 0 | 0 | 0
422 | ALIPURDUAR | Northern Mechanical Division II | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14214 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
423 | ALIPURDUAR | Northern Mechanical Division II | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14214 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1331/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
424 | ALIPURDUAR | Northern Mechanical Division II | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14214 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Beech TG water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | 2336/NMD-II | 01/08/2023 | 394 | KARMAKAR CONSTRUCTION | 21.39 | 0 | 0 | 100
425 | ALIPURDUAR | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14214 | New | Restoration of pipeline, FHTC and Allied works under Beech Tea Garden PWSS Under Alipurduar Division ,PHE DTE. | 71/ALD | 09/04/2025 | 90 | PRAPTI DUTTA | 0.73 | 0 | 0 | 100
426 | ALIPURDUAR | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME , SM/15207 | New | Material Requisition To Resource Division | 187/ALD | 28/04/2023 | 0 | Resource Division | 24.01 | 0 | 0 | 0
427 | ALIPURDUAR | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME , SM/15207 | New | Gap filling in main and branch road of Nabanagar area by HDPE/DI pipe as required under Pashchim Deogaon PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 81/ALD | 10/01/2024 | 90 | SOUVIK ROY PALADHI | 38.2 | 0 | 0 | 0
428 | ALIPURDUAR | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME , SM/15207 | New | Laying of DI & HDPE pipeline, construction of sluice valve chamber, trenchless pipe, laying & other works for providing FHTC at Paschim deogaon PWSS under Birpara Sub-Division, PHE Dte. | 3420/ALD | 26/09/2024 | 60 | SOUVIK ROY PALADHI | 35.92 | 0 | 0 | 0
429 | ALIPURDUAR | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME , SM/15207 | New | Supply of CI Sluice Valve and Special and CI Jeffy Coupling for Paschim Deogaon Water Supply Scheme(SM/15207) of Falakata Block under Alipurduar Division P.H.E. Dte. | 848/ALD | 14/03/2024 | 90 | SOUVIK ROY PALADHI | 18.86 | 0 | 0 | 90
430 | ALIPURDUAR | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME , SM/15207 | New | Material Requisition To Resource Division | 121/ALD | 10/01/2024 | 0 | Resource Division | 12.92 | 0 | 0 | 0
431 | ALIPURDUAR | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME , SM/15207 | New | Material Requisition To Resource Division | 3985/ALD | 27/11/2024 | 0 | Resource Division | 12.92 | 0 | 0 | 0
432 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME , SM/15207 | New | New Service Connection Charges for Paschim Deogaon PWSS, P/H-II under NMD-II | BP-436/24-25 | 16/12/2024 | 0 | WBSEDCL | 2.53 | 0 | 0 | 0
433 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME , SM/15207 | New | NEW SERVICE CONNECTION CHARGES AT PASCHIM DEOGAON PWSS TW NO- I IN THE DIST OF ALIPURDUAR. | BP-171/24-25 | 03/07/2024 | 0 | WBSEDCL | 6.77 | 0 | 0 | 0
434 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME , SM/15207 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Paschim Deogaon Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | 2477/NMD-II | 11/08/2023 | 30 | SUNLIT | 21.78 | 0 | 0 | 50
435 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME , SM/15207 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM DEOGAON and others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1385/NMD-II | 26/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 20.56 | 0 | 0 | 0
436 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME , SM/15207 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1344/NMD-II | 19/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
437 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME , SM/15207 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
438 | ALIPURDUAR | Northern Mechanical Division II | Implementation of Affordable IOT System at Dhaolajhora TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. , SM/16907 | IOT | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Different Block of Alipurduar and Coochbehar District in West Bengal | 807/NMD-II | 04/03/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 594.37 | 0 | 0 | 0
439 | ALIPURDUAR | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | Material Requisition To Resource Division | 1479/ALD | 16/08/2023 | 0 | Resource Division | 21.37 | 0 | 0 | 0
440 | ALIPURDUAR | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | Material Requisition To Resource Division | 2723/ALD | 13/12/2023 | 0 | Resource Division | 84.45 | 0 | 0 | 0
441 | ALIPURDUAR | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling , soil investigation at OHR site, constructions of 450 Cum OHR at HW , construction of pump house and boundary wall at HW site and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Uttar Deogaon PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 1046/ALD | 20/07/2023 | 661 | DILIP MAHATO | 539.38 | 0 | 0 | 61
442 | ALIPURDUAR | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | Laying of DI & HDPE pipeline, construction of sluice valve chamber, trenchless pipe, laying & other works for providing FHTC at Uttar deogaon PWSS under Birpara Sub-Division, PHE Dte. | 3230/ALD | 10/09/2024 | 60 | DILIP MAHATO (OPC) PRIVATE LIMITED | 43.7 | 0 | 0 | 0
443 | ALIPURDUAR | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | "Supply of DIDF Special and CI Jeffy Coupling for Uttar Deogaon TG Water Supply Scheme(SM/16817) of Falakata Block under Alipurduar Division P.H.E. Dte. " | 847/ALD | 14/03/2024 | 90 | SOUVIK ROY PALADHI | 16.48 | 0 | 0 | 59
444 | ALIPURDUAR | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | Material Requisition To Resource Division | 3955/ALD | 26/11/2024 | 0 | Resource Division | 9.86 | 0 | 0 | 0
445 | ALIPURDUAR | Northern Mechanical Division II | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | New Service connection charges for UTTAR DEOGAON PWSS TW No-I under Alipurduar District | BP-09/24-25 | 08/04/2024 | 0 | WBSEDCL | 5.67 | 0 | 0 | 0
446 | ALIPURDUAR | Northern Mechanical Division II | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | New Service Connection Cgarges for UTTAR DEOGAON PWSS P/H NO-II | BP-11/24-25 | 08/04/2024 | 0 | WBSEDCL | 8.77 | 0 | 0 | 0
447 | ALIPURDUAR | Northern Mechanical Division II | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of UTTAR DEOGAON water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | 2558/NMD-II | 18/08/2023 | 30 | SUNLIT | 22.2 | 0 | 0 | 50
448 | ALIPURDUAR | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | Continuation work order for the work of "Construction of tube wells (2 nos.) by Reverse rotary method of drilling , soil investigation at OHR site, constructions of 450 Cum OHR at HW , construction of pump house and boundary wall at HW site and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Uttar Deogaon PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/4/2024-EE(ALI_D) SEC-DPHE (Computer No-973240)) | 1912/ALD | 26/06/2024 | 60 | DILIP MAHATO | 21.25 | 0 | 0 | 100
449 | ALIPURDUAR | Northern Mechanical Division II | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 821/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
450 | ALIPURDUAR | Northern Mechanical Division II | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | Yard lighting arrangement at Head Work Site for Different PWSS (KADAMBINI TG and Others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1346/NMD-II | 19/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 23.98 | 0 | 0 | 0
451 | ALIPURDUAR | Northern Mechanical Division II | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME , SM/16817 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
452 | ALIPURDUAR | Alipurduar Division | Malangi Tea Garden Area Piped Water Supply Scheme , SM/18150 | New | Providing balance FHTC from existing distribution system as per specification for MALANGI TG PWSS under Alipurduar Division, PHE Dte. | 1989/ALD | 15/09/2023 | 60 | KAMALESH ROY | 10.86 | 0 | 0 | 0
453 | ALIPURDUAR | Alipurduar Division | Malangi Tea Garden Area Piped Water Supply Scheme , SM/18150 | New | Material Requisition To Resource Division | 99/ALD | 10/01/2024 | 0 | Resource Division | 13.03 | 0 | 0 | 0
454 | ALIPURDUAR | Alipurduar Division | Malangi Tea Garden Area Piped Water Supply Scheme , SM/18150 | New | Material Requisition To Resource Division | 3982/ALD | 27/11/2024 | 0 | Resource Division | 13.03 | 0 | 0 | 0
455 | ALIPURDUAR | Northern Mechanical Division II | Malangi Tea Garden Area Piped Water Supply Scheme , SM/18150 | New | QUOTATION CHARGES FOR MALANGI TG PWSS | BP-66/24-25 | 09/05/2024 | 0 | WBSEDCL | 1.36 | 0 | 0 | 0
456 | ALIPURDUAR | Northern Mechanical Division II | Malangi Tea Garden Area Piped Water Supply Scheme , SM/18150 | New | New Service connection charges for Malongi TG PWSS PH NO-01, HASHIMARA | BP-195/24-25 | 09/07/2024 | 0 | WBSEDCL | 5.06 | 0 | 0 | 0
457 | ALIPURDUAR | Northern Mechanical Division II | Malangi Tea Garden Area Piped Water Supply Scheme , SM/18150 | New | New Service Connection Charges for Malongi TG PWSS PH NO-02 | BP-196/24-25 | 09/07/2024 | 0 | WBSEDCL | 9.66 | 0 | 0 | 0
458 | ALIPURDUAR | Alipurduar Division | Malangi Tea Garden Area Piped Water Supply Scheme , SM/18150 | New | Tube well Boring by ODEX-165 Method of drilling at HW, 2nd TUBE WELL site including two nos. pump house and boundary wall, providing FHTC and others allied works for MALANGI TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | 236/ALD | 04/05/2023 | 748 | RAMESH SHARMA | 139.9 | 0 | 0 | 10
459 | ALIPURDUAR | Alipurduar Division | Malangi Tea Garden Area Piped Water Supply Scheme , SM/18150 | New | Constructions of 300 Cum OHR as per Departmental Design & drawing, including laying distribution system with new HDPE pipeline , Rising Main, Soil Investigation work and others allied works for MALANGI TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | 1049/ALD | 20/07/2023 | 720 | CAPITAL ENGINEERS | 201.31 | 0 | 0 | 45
460 | ALIPURDUAR | Northern Mechanical Division II | Malangi Tea Garden Area Piped Water Supply Scheme , SM/18150 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for MALANGI T.G water supply scheme, TW no I and II under JJM under NMD-II, PHE Dte. APD. | 2620/NMD-II | 25/08/2023 | 578 | B.B CONCERNED | 21.9 | 0 | 0 | 40
461 | ALIPURDUAR | Alipurduar Division | Malangi Tea Garden Area Piped Water Supply Scheme , SM/18150 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
462 | ALIPURDUAR | Alipurduar Division | Malangi Tea Garden Area Piped Water Supply Scheme , SM/18150 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kalchini Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1052/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
463 | ALIPURDUAR | Alipurduar Division | Dhantali Piped Water Supply Scheme , SM/18153 | New | Constructions of pump house and Tube well Boring by ODEX-165 Method of drilling at HW site and 2nd site, Laying of distribution system with HDPE/DI pipeline, providing FHTC and others allied works for Dhantali PWSS Under Alipurduar Division PHE DTE. | 234/ALD | 04/05/2023 | 240 | SOUVIK ROY PALADHI | 190.55 | 0 | 0 | 70
464 | ALIPURDUAR | Alipurduar Division | Dhantali Piped Water Supply Scheme , SM/18153 | New | Material Requisition To Resource Division | 123/ALD | 10/01/2024 | 0 | Resource Division | 1.27 | 0 | 0 | 0
465 | ALIPURDUAR | Alipurduar Division | Dhantali Piped Water Supply Scheme , SM/18153 | New | Material Requisition To Resource Division | 4271/ALD | 13/12/2024 | 0 | Resource Division | 19.92 | 0 | 0 | 0
466 | ALIPURDUAR | Northern Mechanical Division II | Dhantali Piped Water Supply Scheme , SM/18153 | New | New Service Connection Charges for Dhantali PH NO-2 | BP-406/24-25 | 30/10/2024 | 0 | WBSEDCL | 5.21 | 0 | 0 | 0
467 | ALIPURDUAR | Northern Mechanical Division II | Dhantali Piped Water Supply Scheme , SM/18153 | New | New Service Connection Charges for Dhantali PWSS PH NO-1 | BP-404/24-25 | 30/10/2024 | 0 | WBSEDCL | 9.12 | 0 | 0 | 0
468 | ALIPURDUAR | Northern Mechanical Division II | Dhantali Piped Water Supply Scheme , SM/18153 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for DHANTALI water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | 2623/NMD-II | 25/08/2023 | 677 | RUBY ENTERPRISE | 22 | 0 | 0 | 80
469 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Providing House connection for KAMAKHYAGURI water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte.(PART-2) | 917/ALD | 16/10/2020 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.98 | 4.9 | 100 | 57
470 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | New Laying of UPVC/DI Pipe Line, Providing FHTC & Other allied works at Uttar Kamakhyaguri PWSS Under Alipurduar Division, PHE DTE. | 1306/ALD | 22/08/2022 | 60 | DILIP MAHATO | 28.04 | 21 | 100 | 57
471 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 706/ALD | 08/06/2022 | 30 | DEBAJYOTI SUTRADHAR | 4.95 | 4.95 | 50 | 57
472 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Installation of additional new tube well by ODEX-165 method of drilling for Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division PHE DTE. | 776/ALD | 20/06/2022 | 30 | ANUP GUPTA | 6.99 | 5.44 | 50 | 57
473 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Uttar Kamakhya guri, T/W no. V, Application no. 4002930579, Ref no. 402824641, | BP-27/22-23 | 15/07/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
474 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte.(Part-A) | 1306/ALD | 05/10/2021 | 60 | GOUTAM KUMAR DAS | 25.34 | 0 | 0 | 74
475 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline and Providing House Connection of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | 1574/ALD | 22/11/2021 | 60 | M/S PALIT ENTERPRISE | 48.63 | 29.64 | 87.4 | 78
476 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte.(Part-A) | 1307/ALD | 05/10/2021 | 60 | TAPASH DAS | 25.34 | 0 | 0 | 76
477 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Construction of Pump House ,Boundary Wall and laying distribution system for Uttar Kamkhyaguri Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2608/ALD | 17/02/2022 | 90 | GOUTAM KUMAR DAS | 90.8 | 77.36 | 99.88 | 74
478 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Construction of Pump House ,Boundary Wall, and Tube well Boring by Reverse Rotary method of drilling including Rising main for UTTAR KAMAKHYAGURI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2610/ALD | 17/02/2022 | 90 | ANUP GUPTA | 23.99 | 0 | 0 | 0
479 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Uttar Kamakhyaguri Water Supply Scheme TW No.- V under NMD-II, PHE. Dte, Alipurduar. | 0406/NMD-II | 22/03/2022 | 30 | GURUKRIPA ENTERPRISE | 2.37 | 0 | 0 | 0
480 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Uttar Kamakhyaguri water supply scheme TW No. V under NMD-II, PHE Dte. Alipurduar. | 557/NMD-II | 26/04/2022 | 30 | BLUE PINE | 7.85 | 0 | 0 | 0
481 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Providing House connection for KAMAKHYAGURI water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | 1163/ALD | 15/12/2020 | 60 | TAPASH DAS | 19.94 | 7.66 | 49.36 | 77
482 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Providing FHTC of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte. (Part-4) | 1304/ALD | 05/10/2021 | 60 | DULAL MAJUMDER | 34.38 | 32.66 | 64.41 | 76
483 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Construction of 400cum OHR for Augmentation of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. | 2580/ALD | 17/02/2022 | 180 | DILIP MAHATO | 77.31 | 58.71 | 100 | 74
484 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Land development and laying of UPVC pipeline at additional TW Site of Uttar Kamakhyaguri PWSS under Alipurduar Division, PHE Dte. | 1556/ALD | 23/08/2023 | 60 | SREE MAA CONSTRUCTION | 8.6 | 0 | 0 | 100
485 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Material Requisition To Resource Division | 715/ALD | 13/06/2022 | 0 | Resource Division | 71.41 | 0 | 0 | 0
486 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Laying of new UPVC/DI pipeline for filling of gap in the distribution system and laying of delivery line connection, providing FHTC, land development cons. Of surface drain, pathway and other allied work in connection with the Uttar Kamakhyaguri PWSS under Alipurduar Division, PHE Dte. | 2564/ALD | 29/11/2023 | 540 | DEBAJYOTI SUTRADHAR | 46.9 | 0 | 0 | 65
487 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Head Quarter, Alipurduar Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | 2729/ALD | 30/12/2022 | 365 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.8 | 0 | 0 | 100
488 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/10170 | Augmentation | Laying of pipeline at PASCHIM NARATHALI by extension of pipeline from Uttar Kamakhyaguri PWSS under Alipurduar Division, PHE DTE. | 2746/ALD | 24/02/2022 | 1020 | AKANSHA COMMERCIAL PRIVATE LTD. | 93.92 | 23.12 | 65.47 | 100
489 | ALIPURDUAR | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Providing balance FHTC for Chhoto Daldali PWSS under Alipurduar Division, PHE Dte. | 1562/ALD | 23/08/2023 | 30 | DAS CONSTRUCTION | 3.35 | 0 | 0 | 0
490 | ALIPURDUAR | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Material Requisition To Resource Division | 1276/ALD | 11/08/2023 | 0 | Resource Division | 11.58 | 0 | 0 | 0
491 | ALIPURDUAR | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | QUOTATION FOR NEW SERVICE CONNECTION AT CHOTO DALDALI PWSS PH NO-II | BP-2023-24-44 | 12/05/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
492 | ALIPURDUAR | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | QUOTATION FOR NEW SERVICE CONNECTION AT CHOTO DALDALI PWSS PH NO-I | BP-2023-24-43 | 12/05/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
493 | ALIPURDUAR | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Material Requisition To Resource Division | 125/ALD | 10/01/2024 | 0 | Resource Division | 6.17 | 0 | 0 | 0
494 | ALIPURDUAR | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Material Requisition To Resource Division | 3951/ALD | 26/11/2024 | 0 | Resource Division | 6.17 | 0 | 0 | 0
495 | ALIPURDUAR | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Material Requisition To Resource Division | 4262/ALD | 13/12/2024 | 0 | Resource Division | 22.34 | 0 | 0 | 0
496 | ALIPURDUAR | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Additional Quotation for CHOTO DALDALI PH NO-2 | BP-266/24-25 | 09/08/2024 | 0 | WBSEDCL | 5.79 | 0 | 0 | 0
497 | ALIPURDUAR | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Additional Quotation for CHOTO DALDALI PH NO-1 | BP-265/24-25 | 09/08/2024 | 0 | WBSEDCL | 3.48 | 0 | 0 | 0
498 | ALIPURDUAR | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Constructions of pump house & Tube well Boring by ODEX-165 Method of drilling at HW site & 2nd site , laying of distribution system with UPVC pipeline , Constructions of 200 Cum OHR as per Departmental Design & drawing , providing FHTC and others allied works for Chuota Daldali PWSS Under Alipurduar Division PHE DTE. | 3393/ALD | 16/03/2023 | 777 | DAS CONSTRUCTION | 278.2 | 0 | 0 | 65
499 | ALIPURDUAR | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Solarization of grid connected pumping installation at Different PWSS at Kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 820/NMD-II | 06/03/2025 | 30 | WATER TECH | 29.68 | 0 | 0 | 0
500 | ALIPURDUAR | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
501 | ALIPURDUAR | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
502 | ALIPURDUAR | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1347/NMD-II | 19/06/2025 | 30 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
503 | ALIPURDUAR | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Laying of new UPVC p/l, bridge and culvert crossing, construction of pathway, surface drain and chatal, instalation of paver block, land development along with the other allied works, chhoto Daldali PWSS under Alipurduar Division, PHE Dte. | 2350/ALD | 10/11/2025 | 90 | DAS CONSTRUCTION | 86.28 | 0 | 0 | 0
504 | ALIPURDUAR | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. , SM/13242 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHOTO DALDALI water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 2424/NMD-II | 10/08/2023 | 637 | M/S SAJAHAN CHOWDHURY | 21.72 | 0 | 0 | 100
505 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-2) , SM/07122 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | 2764/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 0.89 | 100 | 60
506 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-2) , SM/07122 | Retrofitting | Laying Distribution line of UPVC, DI Pipe (with pillar) and cons. Of new toilet, repairing of pump house (2nd site), Land Development at Barobisa Zone-I Water Supply Scheme under Alipurduar Division, PHE Dte. | 1319/ALD | 05/10/2021 | 60 | M/S SURAJIT DEY & CO | 81.49 | 48.46 | 100 | 70
507 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-2) , SM/07122 | Retrofitting | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | 3082/ALD | 22/03/2022 | 60 | AASHIRBAD ENTERPRISE | 13.46 | 0 | 0 | 70
508 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-2) , SM/07122 | Retrofitting | Providing House connection for BAROBISHA Zone-III water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-II | 1162/ALD | 15/12/2020 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 19.93 | 19.93 | 50 | 77
509 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-2) , SM/07122 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-I) Under Alipurduar Division, PHE DTE. | 2763/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 29.41 | 100 | 69
510 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme , SM/07129 | Retrofitting | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | 571/20-21 | 26/03/2021 | 0 | PRAMESH LAMA | 10 | 0 | 0 | 0
511 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme , SM/07129 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 17.04 | 100 | 100
512 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme , SM/07129 | Retrofitting | Providing House connection for JOGENDRAPUR water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | 1168/ALD | 15/12/2020 | 60 | SASANKA ROY | 29.9 | 13.08 | 200 | 67
513 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme , SM/07129 | Retrofitting | Providing House connection for Jogijhora water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte.(Part-I) | 1334/ALD | 11/01/2021 | 30 | BHAGWATI BHUJEL | 4.98 | 9.96 | 100 | 0
514 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme , SM/07129 | Retrofitting | Construction of 300cum OHR for Augmentation of Jagijhora Barabak Water Supply Scheme under Alipurduar Division, PHE Dte. | 2582/ALD | 17/02/2022 | 180 | ASHIM KUMAR GHOSH | 63.76 | 11.26 | 100 | 43
515 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme , SM/07129 | Retrofitting | Laying of distribution of HDPE/DI pipeline for Jogijhora Barabak PWSS under Alipurduar Division, PHE DTE. | 2896/ALD | 08/03/2022 | 960 | MS DEYS CONSTRUCTION | 56.01 | 0 | 0 | 100
516 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) , SM/07067 | Retrofitting | Laying HDPE pipe , Road crossing and other misc woks related to Radharani WSS under Alipurduar Division PHE Dte. | 1838/ALD | 10/12/2021 | 45 | UMWELT ENGINEER PVT. LTD. | 3.01 | 0 | 0 | 91
517 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) , SM/07067 | Retrofitting | Providing FHTC at surrounding area of Radharani Piped Water Supply Scheme Under Alipurduar Division, PHE DTE. | 2762/ALD | 25/02/2022 | 60 | SOUVIK ROY PALADHI | 34.95 | 0 | 0 | 92
518 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) , SM/07067 | Retrofitting | PROVIDING HOUSE CONNECTION FOR RADHARANI PWSS AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-2 | 1028/ALD | 18/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 37.24 | 32.53 | 100 | 91
519 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) , SM/07067 | Retrofitting | Balance work of OHR Construction of PHouse B/Wall Godown & ODEX-165 Tubewell incl. laying of DI/HDPE Pipe for Nayabasti SSB Camp at RADHARANI PWSS under Alipurduar Division PHED. | 627/ALD | 03/09/2020 | 120 | UMWELT ENGINEER PVT. LTD. | 65.53 | 0 | 0 | 92
520 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) , SM/07067 | Retrofitting | PROVIDING HOUSE CONNECTION FOR RADHARANI PWSS AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-1 | 1027/ALD | 18/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 37.24 | 22.54 | 100 | 92
521 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) , SM/07067 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 9.97 | 100 | 0
522 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) , SM/07067 | Retrofitting | Balance work of construction of RADHARANI GODOWN cum REST SHED at RADHARANI WSS under Alipurduar Division , PHE Dte ( Part - A) | 454/ALD | 13/05/2022 | 30 | BHAGWATI BHUJEL | 5.02 | 0 | 0 | 92
523 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) , SM/07067 | Retrofitting | Construction of Approach Road with paver Block at RADHARANI WSS under Alipurduar Division , PHE Dte | 455/ALD | 13/05/2022 | 30 | BHAGWATI BHUJEL | 4.96 | 0 | 0 | 92
524 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) , SM/07067 | Retrofitting | Balance work of Radharani Godown cum rest shed under Radharani WSS under Alipurduar Division, PHE Dte. (Part-B) | 1020/ALD | 21/07/2022 | 30 | ASHOK PRADHAN | 2.82 | 0 | 0 | 89
525 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) , SM/07067 | Retrofitting | Laying of HDPE pipe line for Bijaynagar Busty Area under Radharani Water Supply Scheme, Alipurduar Division, PHE Dte. | 2201/ALD | 11/01/2022 | 60 | SOUVIK ROY PALADHI | 41.96 | 33.82 | 100 | 92
526 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-2) , SM/07069 | Retrofitting | Balance part of laying of HDPE/DI pipe line alongwith construction of RCC piller at different area of DIMDIMA TG under ALIPURDUAR Division, PHED. | 622/ALD | 03/09/2020 | 120 | M/S SSB CONSTRUCTION | 34.11 | 0 | 0 | 88
527 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-2) , SM/07069 | Retrofitting | Laying of DI/MS/HDPE pipe line from Nepali School (H.S.) towards Birpara Boro Houda WSS providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-I) | 1452/ALD | 25/01/2021 | 45 | GOUTAM KUMAR DAS | 43.73 | 0 | 0 | 87
528 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-2) , SM/07069 | Retrofitting | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | 1453/ALD | 25/01/2021 | 45 | PRAMESH LAMA | 33.97 | 0 | 0 | 100
529 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-2) , SM/07069 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 2.53 | 100 | 0
530 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-2) , SM/07069 | Retrofitting | Laying of DI/MS/HDPE Pipe line for the Dimdima Zone-II and Nangdala Extension, Dimdima WSS under Alipurduar Division, PHE Dte. | 1795/ALD | 22/02/2021 | 60 | DILIP MAHATO | 31.27 | 9.09 | 100 | 87
531 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) , SM/07060 | Retrofitting | Providing House connection for PATLAKHAWA water supply scheme at Alipurduar-I Block under Alipuduar Division, P.H.E. Dte. Part-IV | 1172/ALD | 15/12/2020 | 60 | SOUVIK ROY PALADHI | 23.92 | 0 | 0 | 79
532 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) , SM/07060 | Retrofitting | Providing House connection and extension of pipe line for Silbarihat area within PATLAKHAWA PWSS under Alipurduar Division PHE Dte. | 879/ALD | 03/09/2021 | 60 | TAPASH KUMAR BHOWMICK | 45.7 | 0 | 0 | 76
533 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) , SM/07060 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | 877/ALD | 03/09/2021 | 60 | M/S STAR INDIA CONSTRUCTION | 33.42 | 0 | 0 | 73
534 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) , SM/07060 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Silbarihat under Patlakhawa PWSS. | 2766/ALD | 25/02/2022 | 60 | TAPASH KUMAR BHOWMICK | 42.34 | 0 | 0 | 75
535 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) , SM/07060 | Retrofitting | Laying of DI pipeline, painting, plastering, land development and other misc works related to Patlakhawa OHR under Patlakhawa PWSS at Alipurduar-I Block, under Alipurduar Division, PHE Dte. | 1855/ALD | 13/12/2021 | 45 | TAPAN CHANDA | 4.26 | 1.65 | 100 | 77
536 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) , SM/07060 | Retrofitting | Construction of boulder apron and land development at Patlakhawa WSS (Pump House no-2) under Alipurduar Division, PHE Dte. | 1339/ALD | 11/01/2021 | 30 | SHIBA ENTERPRISE | 4.98 | 9.95 | 100 | 0
537 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) , SM/07060 | Retrofitting | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | 1008/ALD | 12/11/2020 | 60 | JAI BHARAT COMMERCIAL CORPORATION | 14.4 | 9 | 200 | 100
538 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) , SM/07060 | Retrofitting | Providing House connection for PURBA KATHALBARI water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. Part-II | 1173/ALD | 15/12/2020 | 60 | MADHAB SAHA | 19.93 | 11.96 | 100 | 0
539 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) , SM/07060 | Retrofitting | Providing House connection for BAROBISHA ZONE- I water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | 858/ALD | 14/10/2020 | 30 | TAPAN CHANDA | 4.98 | 9.97 | 200 | 0
540 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme , SM/07064 | Retrofitting | Laying of DI/MS/HDPE pipe line from Nepali School (H.S.) towards Birpara Boro Houda WSS providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-I) | 570/20-21 | 26/03/2021 | 0 | GOUTAM KUMAR DAS | 15 | 0 | 0 | 0
541 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme , SM/07064 | Retrofitting | Laying of DI/MS/HDPE pipeline for the Hantapara WSS (Jamtala Area) under Alipurduar Division, PHE Dte. | 1455/ALD | 25/01/2021 | 45 | M/S SURAJIT DEY & CO | 8.92 | 7.79 | 200 | 98
542 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme , SM/07064 | Retrofitting | Laying of HDPE pipeline for Hantapara Topline under Hatapara WSS within Alipurduar Division, PHE Dte. | 2627/ALD | 18/02/2022 | 60 | DILIP MAHATO | 16.19 | 0 | 0 | 69
543 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme , SM/07064 | Retrofitting | Road crossing (by NP3 Hume pipe) at Dhupguri Road under under Zone-II of augmentation of Falakata WSS and infront of bhutnirghat WSS due to widening of PWD Road under Alipurduar Division, PHE Dte. (3 nos) | 2308/ALD | 25/01/2022 | 30 | ASSOCIATE CONSTRUCTION COMPANY | 2.49 | 0 | 0 | 89
544 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme , SM/07064 | Retrofitting | Repair of Gate, Drainage System & Rest Shed infront of Office cum Godown building at H/W Site of Birpara WSS under Alipuduar Division, P.H.E. Dte. | 875/ALD | 14/10/2020 | 45 | DILIP MAHATO | 4.97 | 9.61 | 200 | 0
545 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme , SM/07064 | Retrofitting | House connection Providing for MAKRAPARA TG PWSS at MADARIHAT-BIRPARA Block under Alipurduar Division PHED . | 697/ALD | 16/09/2020 | 120 | DILIP MAHATO | 25.73 | 15.24 | 200 | 0
546 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme , SM/07064 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | 1281/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 37.84 | 26.98 | 200 | 94
547 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme , SM/07064 | Retrofitting | PROVIDING HOUSE CONNECTION FOR DIMDIMA Z-II PWSS AT MADARIHAT-BIRPARA BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-2 | 1026/ALD | 18/11/2020 | 60 | ASHIT KUMAR SINGHA | 19.61 | 30.28 | 100 | 0
548 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) , SM/07181 | Retrofitting | Providing House connection for KAIJALI BUSTY water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte.(PART-2) | 913/ALD | 16/10/2020 | 30 | DAS ENTERPRISE | 4.96 | 4.96 | 50 | 67
549 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) , SM/07181 | Retrofitting | Providing House connection for KAIJALI BASTYI water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | 862/ALD | 14/10/2020 | 30 | DAS ENTERPRISE | 4.96 | 4.96 | 50 | 68
550 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) , SM/07181 | Retrofitting | Providing House connection for KAIJALI BUSTY water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | 1164/ALD | 15/12/2020 | 60 | GHOSH & SAHA CONSTRUCTION | 19.93 | 14.95 | 100 | 68
551 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) , SM/07181 | Retrofitting | Restoration of pipe line for Turturi Khanda (Kaijali Busty Area), Culvert crossing and Laying Delivery line with DI and MS under Kaijali Busty TG WSS under Alipurduar Division, PHE Dte. | 2202/ALD | 11/01/2022 | 60 | TAPASH KUMAR BHOWMICK | 41.95 | 24.34 | 100 | 66
552 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) , SM/07181 | Retrofitting | Laying of distribution of HDPE/DI pipeline for TURTURI TG area, Kaijali Busty PWSS under Alipurduar Division, PHE DTE. | 2899/ALD | 08/03/2022 | 60 | ASHOK SAPKOTA | 34.24 | 32.92 | 74.73 | 68
553 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) , SM/07181 | Retrofitting | Laying Delivary line with M.S FOR Connection of KAIJALI BUSTY WSS under Jainti TG Water Supply Scheme . | 451/ALD | 13/05/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.94 | 4.86 | 50 | 66
554 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' , SM/09893 | Augmentation | Construction of pump House, boundary wall, laying of UPVC pipe linr & Rising main connection for Purba Chepani PWSS proposed 4th TW SITE under Alipurduar Division, PHE Dte. | 3494/ALD | 23/03/2023 | 90 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 41.66 | 20.16 | 87.69 | 48
555 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' , SM/09893 | Augmentation | New Laying of UPVC/DI pipeline, Providing FHTC and other allied works for Augmentation of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | 1220/ALD | 10/08/2022 | 60 | SREE MAA CONSTRUCTION | 21.55 | 0 | 0 | 94
556 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' , SM/09893 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Purba Chenpani Water Supply Scheme TW No.-III under NMD-II PHE Dte Alipurduar. | 1379/NMD-II | 22/12/2021 | 30 | TAPAN BISWAS | 2.39 | 2.37 | 100 | 0
557 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' , SM/09893 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Purba Chenpani Water Supply Scheme TW No.-III under NMD-II,PHE Dte Alipurduar. | 63/NMD-II | 21/01/2022 | 30 | M/S KUNDU CONSTRUCTION | 7.75 | 7.73 | 100 | 0
558 | ALIPURDUAR | Alipurduar Division | Rejuvenation Of Dima T.G. W.S.S , SM/09904 | Augmentation | Laying of DI / UPVC Pipeline & other Misc. works related to DIMA PWSS under Alipurduar Division PHED. | 623/ALD | 03/09/2020 | 120 | TILAK SHARMA | 29.43 | 8.26 | 50 | 30
559 | ALIPURDUAR | Alipurduar Division | Rejuvenation Of Dima T.G. W.S.S , SM/09904 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 3.06 | 100 | 72
560 | ALIPURDUAR | Northern Mechanical Division II | Rejuvenation Of Dima T.G. W.S.S , SM/09904 | Augmentation | Supply, delivery of Electro mechanical components at Dima T.G Water Supply Scheme, in the dist. of ALIPURDUAR under NMD-II, PHE. Dte, Alipurduar. | 307/NMD-II | 10/03/2022 | 30 | DIAMOND ELECTRICAL WORKS | 8.32 | 0.85 | 100 | 30
561 | ALIPURDUAR | Northern Mechanical Division II | Rejuvenation Of Dima T.G. W.S.S , SM/09904 | Augmentation | Quotation for new service connection at Dima TG TW No III | BP-120/22-23 | 09/01/2023 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
562 | ALIPURDUAR | Northern Mechanical Division II | Rejuvenation Of Dima T.G. W.S.S , SM/09904 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of DIMA T.G water supply scheme, TW no III under NMD-II, PHE Dte 106. APD. | 2766/NMD-II | 04/10/2023 | 668 | ASHWIRBAD WOOD CRAFT | 10.68 | 0 | 0 | 90
563 | ALIPURDUAR | Alipurduar Division | Rejuvenation Of Dima T.G. W.S.S , SM/09904 | Augmentation | Reparing of Pump House at Headwork site of Dima TG PWSS Under Alipurduar Division PHE DTE. | 1579/ALD | 31/07/2025 | 60 | TAPASH DAS | 0.79 | 0 | 0 | 0
564 | ALIPURDUAR | Alipurduar Division | Rejuvenation Of Dima T.G. W.S.S , SM/09904 | Augmentation | Reparing of Pump House at 2nd site of Dima TG PWSS Under Alipurduar Division PHE DTE. | 1578/ALD | 31/07/2025 | 60 | TAPASH DAS | 0.99 | 0 | 0 | 0
565 | ALIPURDUAR | Northern Mechanical Division II | Rejuvenation of Gargenda Tea Garden Water Supply Scheme , SM/09906 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Gargenda TG water supply scheme, TW no IV in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte. | 519/NMD-II | 14/03/2023 | 30 | DEY ENTERPRISE (BALLY) | 13.6 | 12.91 | 95.97 | 90
566 | ALIPURDUAR | Northern Mechanical Division II | Rejuvenation of Gargenda Tea Garden Water Supply Scheme , SM/09906 | Augmentation | Quotation for new service connection at Gargenda TG TW No- IV | BP-139/22-23 | 23/02/2023 | 0 | WBSEDCL | 1.49 | 0 | 0 | 0
567 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' , SM/09908 | Augmentation | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Tapshikhata PWSS Under Alipurduar Division, PHE DTE. | 2750/ALD | 24/02/2022 | 60 | AMBITIOUS ENTERPRISE | 36.94 | 15.64 | 49.81 | 68
568 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' , SM/09908 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Tapshikhata WSS under Alipurduar Division, PHE Dte. Part-5 | 2142/ALD | 06/01/2022 | 30 | DEBAJYOTI SUTRADHAR | 5.02 | 0 | 0 | 52
569 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' , SM/09908 | Augmentation | Supply, delivery of Standby PDB Cum MCC Panel and Submersible pumping machinery under Rejuvination of Tapshikhata water supply scheme under NMD-II,PHE Dte. | 93/NMD-II | 10/01/2023 | 15 | ALPHA ENTERPRISE | 4.86 | 4.7 | 100 | 55
570 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' , SM/09908 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT TAPSHIKHATA PH NO III | BP-2023-24-137 | 24/05/2023 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
571 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' , SM/09908 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of TAPSHIKHATA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2197/ALD | 11/01/2022 | 1116 | DEBABRATA DUTTA | 21.58 | 0 | 0 | 69
572 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' , SM/09908 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Tapsikhata water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar | 2036/NMD-II | 26/07/2023 | 30 | RUBY ENTERPRISE | 10.88 | 0 | 0 | 100
573 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Jogijhora WSS under Alipurduar Division, PHE Dte. Part-3 (2 nd call) | 3145/ALD | 25/03/2022 | 30 | M/S SURAJIT DEY & CO | 5.02 | 0 | 0 | 0
574 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Providing FHTC from existing distribution system as per specification for JAGIJHORA PWSS under Alipurduar Division, PHE Dte. | 1993/ALD | 15/09/2023 | 60 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 33.81 | 0 | 0 | 0
575 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Construction of 300cum OHR for Augmentation of Jagijhora Barabak Water Supply Scheme under Alipurduar Division, PHE Dte. | 2582/ALD | 17/02/2022 | 180 | ASHIM KUMAR GHOSH | 63.76 | 43.25 | 100 | 43
576 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-2 Venue: 1) Jogijhora 2)Jateswar 3)Gopalpur 4)Madhya Parokata | 2122/ALD | 05/01/2022 | 30 | MOYTEC | 4.9 | 4.9 | 100 | 26
577 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT JOGOJHORA BARABAK TW NO-III | BP-2023-24-66 | 13/05/2023 | 0 | WBSEDCL | 1.46 | 0 | 0 | 0
578 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Construction of boundary wall for Jogijhora Barabak PWSS of Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. (SM/10169) | 827/ALD | 14/03/2024 | 60 | MANI PRADHAN | 2.5 | 0 | 0 | 0
579 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Construction of Pump House ,Boundary Wall and Tube well Boring by ODEX-165 Method of drilling including Rising Main for JAGIJHORA BARABAK PWSS under Alipurduar Division PHE DTE | 2609/ALD | 17/02/2022 | 90 | SUBHAS CHANDRA ROY | 21.13 | 6.02 | 45.44 | 100
580 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Jogijhora Barabak water supply scheme, TW no. III under Northern Mechanical Division-II,PHE Dte. | 907/NMD-II | 04/05/2023 | 30 | A.K SIKDAR | 10.36 | 0 | 0 | 100
581 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Laying of distribution of HDPE/DI pipeline for Jogijhora Barabak PWSS under Alipurduar Division, PHE DTE. | 2896/ALD | 08/03/2022 | 960 | MS DEYS CONSTRUCTION | 56.01 | 26.33 | 49.48 | 100
582 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Material Requisition To Resource Division | 3606/ALD | 24/10/2024 | 0 | Resource Division | 9.11 | 0 | 0 | 0
583 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Laying of HDPE pipe line for left out house hold connection at Ethelbari TG PWSS(SM/13449) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | 894/ALD | 15/03/2024 | 360 | DILIP MAHATO | 18.65 | 0 | 0 | 100
584 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Reparing of Pump House at 2nd site of Jogijhora Barabak PWSS Under Alipurduar Division PHE DTE. | 5600/ALD | 27/03/2025 | 60 | NARENDRA BHADANI. | 0.79 | 0 | 0 | 0
585 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
586 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Reparing of Pump House at 3nd site of Jogijhora Barabak PWSS Under Alipurduar Division PHE DTE. | 5604/ALD | 27/03/2025 | 60 | NARENDRA BHADANI. | 0.95 | 0 | 0 | 0
587 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Reparing of Pump House at 1st site of Jogijhora Barabak PWSS Under Alipurduar Division PHE DTE. | 5599/ALD | 27/03/2025 | 60 | NARENDRA BHADANI. | 0.78 | 0 | 0 | 0
588 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1629/ALD | 04/08/2025 | 60 | NARENDRA BHADANI. | 18.13 | 0 | 0 | 0
589 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME , SM/10169 | Augmentation | Gap filling by DI and HDPE pipeline in Jagijhora Barabak PWSS under Alipurduar Division, PHE Dte. | 2605/ALD | 04/12/2023 | 240 | MONORAMA ENTERPRISE | 9.99 | 0 | 0 | 80
590 | ALIPURDUAR | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Supply of CIPE Special & CI Jeffy Coupling for Dakshin Paitkapara Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 699/ALD | 08/06/2022 | 30 | HARIDAS GHOSH | 4.92 | 4.92 | 50 | 84
591 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Quotation for new service connection at Dakshin Patkapara, P/H no.II, Application no.403007835 | BP-86/22-23 | 11/11/2022 | 0 | WBSEDCL | 1.01 | 0 | 0 | 0
592 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Quotation for new service connection for DAKSHIN PATKAPARA. Tube well no. I, Application no. 4003007857 |  | 07/11/2022 | 0 | WBSEDCL | 1.01 | 0 | 0 | 0
593 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Quotation for new service connection for DAKSHIN PATKAPARA. Tube well no. II, Application no. 4003007835 |  | 07/11/2022 | 0 | WBSEDCL | 1.01 | 0 | 0 | 0
594 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Quotation for new service connection at Dakshin Patkapara, P/H no.I, Application no.4003007857 | BP-85/22-23 | 11/11/2022 | 0 | WBSEDCL | 1.01 | 0 | 0 | 0
595 | ALIPURDUAR | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Construction of 300cum OHR for Dakshin Paitkapara Water Supply Scheme under Alipurduar Division, PHE Dte. | 2584/ALD | 17/02/2022 | 180 | Z STAR COMMOTRADE PVT LTD. | 63.78 | 33.8 | 59.92 | 83
596 | ALIPURDUAR | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 160 | 100 | 0
597 | ALIPURDUAR | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Material Requisition To Resource Division | 394/ALD | 11/05/2022 | 0 | Resource Division | 11.54 | 0 | 0 | 0
598 | ALIPURDUAR | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at H/W site including laying distribution system and providing FHTC for DAKSHIN PAITKAPARA PWSS Under Alipurduar Division PHE DTE | 16/ALD | 01/04/2022 | 240 | HARIDAS GHOSH | 230.68 | 200.3 | 86.83 | 86
599 | ALIPURDUAR | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for DAKSHIN PAITKAPARA PWSS under Alipurduar Division PHE DTE | 21/ALD | 01/04/2022 | 120 | SOUVIK ROY PALADHI | 230.7 | 199.21 | 91.94 | 55
600 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN PATKAPARA AREA PWSS, TW no I (H/W SITE) in the district of ALIPURDUAR under Northern Mechanical Division-II, PHE Dte. | 0568/NMD-II | 17/03/2023 | 625 | TALUKDAR ENTERPRISE | 9.88 | 0 | 0 | 100
601 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector of Dakshin Paitkapara PWSS, TW no .II in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte | 625/NMD-II | 21/03/2023 | 30 | SARKAR ELECTRIC | 9.93 | 9.24 | 93.04 | 100
602 | ALIPURDUAR | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of PAITKAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 1994/ALD | 27/12/2021 | 90 | ANUP GUPTA | 20.99 | 5.91 | 100 | 80
603 | ALIPURDUAR | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Construction of Boundary Wall and pathway for Dakshin Paitkapara PWSS under Alipurduar Division PHE DTE. | 1329/ALD | 24/08/2022 | 1064 | M/S BASU CONSTRUCTION AND CO | 36.21 | 10.83 | 29.9 | 82
604 | ALIPURDUAR | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME , SM/10174 | New | Cons. Of balance portion of pump house, boundary wall, rising main, laying of DI and HDPE pipeline for 3rd site of Dakshin Paitkapara PWSS under Alipurduar Division, PHE Dte. | 1787/ALD | 29/08/2023 | 120 | ANUP GUPTA | 22.82 | 0 | 0 | 40
605 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/Jal Swapna (Schools, AWC and others) for Bhutnirghat PWSS under Birpara Sub-Division under Alipurduar Division, PHE Dte. Part-4 | 1605/ALD | 22/11/2021 | 30 | GOUTAM KUMAR DAS | 5.04 | 5.04 | 100 | 95
606 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Laying of CIDF, Rising Main, Delivery line, Hydraulic Testing, disinfection of UPVC pipeline and other allied works at Bhutnirghat WSS under Alipurduar Division, PHE Dte. | 1688/ALD | 20/09/2022 | 60 | DILIP MAHATO | 5.82 | 0 | 0 | 0
607 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Extension of pipeline and connection with main line by UPVC, GI, DI pipe and construction of valve chamberand others at Bhutnirghat WSS under Alipurduar Division, PHE Dte. | 342/ALD | 02/05/2022 | 45 | DILIP MAHATO | 25.7 | 16.89 | 67.49 | 92
608 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Gap filling by UPVC/DI pipe for Bhutnirghat WSS under Alipurduar Division, PHE Dte. | 1600/ALD | 22/11/2021 | 30 | GOUTAM KUMAR DAS | 4.99 | 4.99 | 100 | 98
609 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Construction of 450cum OHR for Bhutnirghat Water Supply Scheme under Alipurduar Division, PHE Dte. | 2186/ALD | 11/01/2022 | 180 | DILIP MAHATO | 87.59 | 74.96 | 100 | 80
610 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Supply of 250 mm dia CI Sluice Valve for Augmentation of Bhutnirghat Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 709/ALD | 08/06/2022 | 30 | DILIP MAHATO | 4.93 | 4.93 | 50 | 98
611 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/Jal Swapna for Bhutnirghat PWSS under Birpara Sub-Division under Alipurduar Division, PHE Dte. Part-5 | 1606/ALD | 22/11/2021 | 30 | GOUTAM KUMAR DAS | 5.04 | 0 | 0 | 97
612 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Sinking of Big Dia T/Well P/House B/Wall & Rising Main of 3rd T/Well Site at FALAKATA Aug. PWSS under Alipurduar Division PHED. | 655/ALD | 08/09/2020 | 120 | BILTU DAS | 22.65 | 16.12 | 100 | 82
613 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Loop Connention between West Falakata & Barodoba area via Mujnai River Bridge incl interconnection with the existing BHUTNIRGHAT PWSS under FALAKATA Aug. PWSS under Alipurduar Division PHED. | 626/ALD | 03/09/2020 | 120 | GOUTAM KUMAR DAS | 26.08 | 1.53 | 100 | 83
614 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Road crossing (by NP3 Hume pipe) at Dhupguri Road under under Zone-II of augmentation of Falakata WSS and infront of bhutnirghat WSS due to widening of PWD Road under Alipurduar Division, PHE Dte. (3 nos) | 2308/ALD | 25/01/2022 | 30 | ASSOCIATE CONSTRUCTION COMPANY | 2.49 | 2.45 | 100 | 89
615 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 50 | 100 | 100
616 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-3 VENUE : 1)Chuniajhora TG 2) Dakshin Paitkapara 3)Jay Birpara 4) Bhutnirghat | 2123/ALD | 05/01/2022 | 30 | R B TESTING | 4.86 | 4.86 | 100 | 67
617 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BHUTNIRGHAT TW NO-III | BP-2023-24-69 | 13/05/2023 | 0 | WBSEDCL | 1.43 | 0 | 0 | 0
618 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Shifting and Laying distribution of P/line due to Widening of Falkata to Dhupguri rd. & other allied works to Bhutnirghat PWSS under Alipurduar Division PHED. part (II). | 08/ALD | 02/04/2020 | 1826 | SHIB RATAN BHOWMIK | 17.51 | 6.68 | 100 | 0
619 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Construction of Pump House, Boundary Wall, laying distribution system and providing FHTC for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2379/ALD | 31/01/2022 | 90 | DILIP MAHATO | 92.34 | 80.57 | 100 | 98
620 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Laying of UPVC pipeline and Tube well Boring by Reverse Rotary method of drilling for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2380/ALD | 31/01/2022 | 60 | DILIP MAHATO | 95.15 | 81.04 | 100 | 97
621 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Bhutnirghat water supply scheme, TW no. III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 1194/NMD-II | 23/06/2023 | 30 | ANUP BASU | 10.59 | 0 | 0 | 100
622 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME , SM/09885 | Augmentation | "Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II P.H.E. Dte." | 716/AMSD | 30/12/2024 | 60 | D.K AND SONS | 0.75 | 0 | 0 | 0
623 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME , SM/10674 | Augmentation | Cons. Of balance portion of pump house, boundary wall, rising main, laying of DI and UPVC pipeline for Aug. of Banchukamari PWSS under Alipurduar Division, PHE Dte. | 1580/ALD | 24/08/2023 | 120 | HITANGSHU CHOUDHURY | 20.36 | 0 | 0 | 35
624 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME , SM/10674 | Augmentation | Material Requisition To Resource Division | 1705/ALD | 21/09/2022 | 0 | Resource Division | 61.6 | 0 | 0 | 0
625 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME , SM/10674 | Augmentation | Construction of Piller and Repairing of pipeline with GI Pipe near the house of Durga Oraon, kamal Roy & Banchukamari 1No. BFP School for Banchukamari WSS unedr Alipurduar Division, PHE Dte | 1229/ALD | 10/08/2022 | 30 | TAPASH DAS | 3.07 | 0 | 0 | 80
626 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME , SM/10674 | Augmentation | Laying of UPVC and DI distribution line, repairing and renovation of 2nos pump house for Aug. Of Banchukamari PWSS Alipurduar Division, PHE Dte. | 695/ALD | 07/03/2024 | 180 | DAS CONSTRUCTION | 50.59 | 0 | 0 | 2
627 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME , SM/10674 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
628 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME , SM/10674 | Augmentation | Gap filling of distribution pipeline and other allied works for Satkodali and adjoining area under Banchukamari PWSS within Alipurduar-I Block under Alipurduar Division, PHE Dte. | 2351/ALD | 10/11/2025 | 75 | DAS CONSTRUCTION | 68.41 | 0 | 0 | 0
629 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF MUNSHIPARA WATER SUPPLY SCHEME , SM/10675 | Augmentation | Reparing of Pump House at HEADWORK site of MUNSHIPARA PWSS Under Alipurduar Division PHE DTE. | 5393/ALD | 17/03/2025 | 60 | TAPASH DAS | 0.94 | 0 | 0 | 0
630 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF MUNSHIPARA WATER SUPPLY SCHEME , SM/10675 | Augmentation | Reparing of Pump House at 2nd TW site of MUNSHIPARA PWSS Under Alipurduar Division PHE DTE. | 5395/ALD | 17/03/2025 | 60 | TAPASH DAS | 0.79 | 0 | 0 | 0
631 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Supply Installation Commissioning and Trial Operation of Electro Mechanical components at Bandapani TG Hindi High School withing Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Part-2) | 1231/ALD | 10/08/2022 | 30 | BHAGWATI BHUJEL | 3.8 | 3.3 | 86.91 | 24
632 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | SUPPLY, INSTALLATION,COMMISSIONING AND TRIAL OPERATION OF ELECTRO MECHANICAL COMPONENTS OF RIGBORE T/W(2NOS.) FOR BANDAPANI AREA ALONG WITH CONS. OF 2NOS. P/H OF SIZE 3.00M X 3.60M | 1485/ALD | 27/01/2021 | 60 | DILIP MAHATO | 22 | 3.75 | 49.79 | 25
633 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Supply Installation Commissioning and Trial Operation of Electro Mechanical components at Bandapani TG Hindi High School within Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Part-1) | 1230/ALD | 10/08/2022 | 30 | BHAGWATI BHUJEL | 3.92 | 3.88 | 100 | 25
634 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Soil investigation works at head works site for BANDAPANI TG AREA PWSS (ZONE-I) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 2134/ALD | 10/11/2022 | 30 | MOYTEC | 0.7 | 0.64 | 91.89 | 0
635 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Soil investigation works at head works site for BANDAPANI TG AREA PWSS (ZONE-2) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 2136/ALD/ | 10/11/2022 | 30 | MOYTEC | 0.66 | 0.61 | 91.89 | 0
636 | ALIPURDUAR | Northern Mechanical Division II | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BANDAPANI TG TW NO-II | BP-2023-24-60 | 13/05/2023 | 0 | WBSEDCL | 1.6 | 0 | 0 | 0
637 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | New Connection for Assistant Engineer Alipurduar RWS Sub-Division PHE Reti Forest, Bandapani | 444/22-23/PFMS | 21/01/2023 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
638 | ALIPURDUAR | Northern Mechanical Division II | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BANDAPANI TG TW NO-I | BP-2023-24-59 | 13/05/2023 | 0 | WBSEDCL | 1.6 | 0 | 0 | 0
639 | ALIPURDUAR | Northern Mechanical Division II | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | QUOTATION FOR 3 PHASE UNIT METER ID -402728652 | BP-2023-24-330 | 27/09/2023 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
640 | ALIPURDUAR | Northern Mechanical Division II | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Additional Quotation for BANDAPANI TG P/HNO-II(Application No-4003127203) | BP-2023-24-471 | 12/12/2023 | 0 | WBSEDCL | 25.52 | 0 | 0 | 0
641 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Construction of 150 cum OHR as per Departmental Design and drawing, Tube well Boring by ODEX-165 method of drilling 1 nos. respectively at H/W site, Rising main and distribution line (part-1) for BANDAPANI TG AREA PWSS (ZONE-II) under Birpara Sub-Division , Alipurduar Division, PHE Dte. | 2250/ALD | 21/11/2022 | 540 | SAMIRON PODDER | 88.7 | 65.98 | 74.39 | 85
642 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Construction of 1 no. Pump House, 1 no. Boundary wall at headwork site, distribution of pipeline and providing FHTC for BANDAPANI TG AREA PWSS (ZONE-II) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 1687/ALD | 20/09/2022 | 720 | MITHUN DAS | 53.39 | 16.83 | 31.53 | 78
643 | ALIPURDUAR | Northern Mechanical Division II | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bandapani TG water supply scheme, TW no I and II of Zone-I and TW no I and II of Zone-II under NMD-II, PHE Dte.APD | 936/NMD-II | 10/05/2023 | 30 | ALPHA ENTERPRISE | 37.32 | 0 | 0 | 35
644 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Construction of pump house, boundary wall, TW boring (by ODEX-165 method of drilling) and Rising main for 2nd TW site at Bandapani PWSS (Zone-II) under Alipurduar Division, PHE Dte. | 83/ALD | 10/01/2024 | 240 | MITHUN DAS | 24.21 | 0 | 0 | 85
645 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Supply of drinking water through tanker by hired vehicle to mitigate drinking water crisis at Bandapani TG under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | 2175/ALD | 06/10/2023 | 45 | NARENDRA BHADANI. | 3.48 | 0 | 0 | 100
646 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Construction of 150cum. OHR for Bandapani ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | 974/ALD | 15/07/2022 | 540 | MITHUN DAS | 49.89 | 35.22 | 70.59 | 86
647 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Tube well Boring by ODEX-165 method of drilling at Head work site, Construction of 1 no. Pump house and Boundary wall at headwork site, Rising Main and Distribution line with FHTC (Part-1) for BANDAPANI TG AREA PWSS (ZONE-I) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 1639/ALD | 19/09/2022 | 775 | PRAMESH LAMA | 43.08 | 20.04 | 46.52 | 50
648 | ALIPURDUAR | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. , SM/11483 | New | Laying distribution system (Part-2) and providing FHTC for BANDAPANI TG AREA PWSS (ZONE-I) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 2249/ALD | 21/11/2022 | 130 | PRAMESH LAMA | 52.84 | 30.31 | 57.37 | 83
649 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Schedule for: Supply, delivery and installation of 30 KVA servo motor operated Copper wound line voltage corrector at Purba Kathalbari Water Supply Scheme TW No.-II under NMD-II,PHE.Dte,Alipurduar. | 1097/NMD-II | 20/09/2021 | 30 | NIRMAN | 3.94 | 3.94 | 100 | 0
650 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Purba Kathalbari Zone-III PWSS Under Alipurduar Division PHE DTE. | 1008/ALD | 15/07/2022 | 90 | MADHAB SAHA | 45.9 | 39.6 | 86.27 | 86
651 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying of different dia. Pipeline and providing FHTC for Southern side of Purba Kathalbari Zone (II) PWSS and surrounding areas at Alipurduar-I Block under Alipurduar Division, PHE Dte. | 997/ALD | 15/07/2022 | 60 | M/S JHA CONSTRUCTION | 99.69 | 76.99 | 77.23 | 27
652 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying of different dia. Pipeline and providing FHTC for Purba Kathalbari Zone(IV) PWSS area and surrounding, Alipurduar-I Block under Alipurduar Division, PHE Dte.(Part-A) | 995/ALD | 15/07/2022 | 60 | DAS ENTERPRISE | 99.06 | 67.23 | 67.87 | 27
653 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Purba Kathalbari PWSS under Alipurduar Division, PHE Dte. Part-3 | 981/ALD | 15/07/2022 | 45 | MAHENDRA CHHETRI | 24.2 | 7.33 | 30.29 | 26
654 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for PurbaKathalbari PWSS under Alipurduar Division, PHE Dte. Part-4 | 982/ALD | 15/07/2022 | 45 | DAS CONSTRUCTION | 24.14 | 0 | 0 | 27
655 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying Distribution of pipeline with DI and UPVC pipeline along with FHTC Connection at Jogendranagar area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | 989/ALD | 15/07/2022 | 60 | UTTAM KUMAR DUTTA | 98.45 | 87.43 | 88.8 | 27
656 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying of different dia. Pipeline and providing FHTC for Purba Kathalbari Zone(IV) PWSS area and surrounding area of NH-31D at Alipurduar-I Block under Alipurduar Division, PHE Dte.(Part-B) | 996/ALD | 15/07/2022 | 60 | NARAYAN CHANDRA SAHA | 99.18 | 75.08 | 75.7 | 76
657 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Development of TW, Yield testing with BHT Pump and water sample collection and chemical test at different tubewell of Purba Kathal Bari PWSS at Alipurduar-I Block, Alipurduar Division PHED. | 2495/ALD | 13/12/2022 | 60 | SAMIRON PODDER | 5.68 | 0 | 0 | 0
658 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Providing FHTC from existing distribution system as per specification for PURBA KATHALBARI PWSS under Alipurduar Division, PHE Dte. | 1996/ALD | 15/09/2023 | 60 | M/S SIBU DEY AND CO | 24.2 | 0 | 0 | 0
659 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site along with repairing of 1 no. pump house for Purba Kathalbari Zone-I PWSS Under Alipurduar Division PHE DTE. | 1007/ALD | 15/07/2022 | 90 | SAMIRON PODDER | 43.06 | 40.49 | 94.02 | 0
660 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Soil investigation work at 4 different places of Purba Kanthalbari within Alipurduar District under Alipurduar Division PHE Dte. | 1006/ALD | 15/07/2022 | 30 | MABCO CONSULTANT, | 4.87 | 4.87 | 100 | 27
661 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Material Requisition To Resource Division | 1590/ALD | 14/09/2022 | 0 | Resource Division | 130.15 | 0 | 0 | 0
662 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR PURBA KATHALBARI zONE-III P/H NO.I | BP-2023-24-197 | 22/06/2023 | 0 | WBSEDCL | 1.71 | 0 | 0 | 0
663 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT PURBA KATHALBARI PWSS PALASHBARI, FLOOD SHELTER, ZONE-I,P/H NO-I | BP-2023-24-293 | 21/08/2023 | 0 | WBSEDCL | 6.38 | 0 | 0 | 0
664 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR PURBA KATHALBARI zONE-III P/H NO.II | BP-2023-24-196 | 22/06/2023 | 0 | WBSEDCL | 1.71 | 0 | 0 | 0
665 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR PURBA KATHALBARI zONE-IV P/H NO.I | BP-2023-24-198 | 22/06/2023 | 0 | WBSEDCL | 1.71 | 0 | 0 | 0
666 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR PURBA KATHALBARI zONE-I P/H NO.II | BP-2023-24-195 | 22/06/2023 | 0 | WBSEDCL | 1.71 | 0 | 0 | 0
667 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying Distribution of pipeline with DI and UPVC pipeline along with FHTC Connection for Purba Kathalbari area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | 988/ALD | 15/07/2022 | 60 | NEOGI ENTERPRISE | 98.79 | 80.1 | 81.08 | 30
668 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Construction of 150cum. OHR for PURBA KATHALBARI ZONE-IV Water Supply Scheme under Alipurduar Division, PHE Dte. | 984/ALD | 15/07/2022 | 720 | MAHENDRA CHHETRI | 50.44 | 20.26 | 40.17 | 52
669 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying of different dia. Pipeline and providing FHTC for Northern side of Purba Kathalbari Zone (II) PWSS and surrounding areas at Alipurduar-I Block under Alipurduar Division, PHE Dte. | 978/ALD | 15/07/2022 | 60 | DILIP MAHATO | 99.77 | 76.96 | 77.14 | 15
670 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection surrounding Sirubari area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | 993/ALD | 15/07/2022 | 783 | MS DEYS CONSTRUCTION | 99.93 | 48.16 | 48.19 | 85
671 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection surrounding Palashbari area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | 994/ALD | 15/07/2022 | 180 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 87.56 | 35.88 | 40.98 | 28
672 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | 2731/ALD | 30/12/2022 | 365 | KAMALESH ROY | 4.8 | 0 | 0 | 100
673 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Purba Kanthalbari water supply scheme, TW no I and II of Zone-IV under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 1107/NMD-II | 05/06/2023 | 30 | SUMON ELECTRICAL | 22.86 | 0 | 0 | 70
674 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Construction of 250cum OHR for PURBA KATHALBARI ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | 987/ALD | 15/07/2022 | 180 | NEOGI ENTERPRISE | 57.61 | 0 | 0 | 35
675 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Construction of OHR 200cum for PURBA KATHALBARI ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | 986/ALD | 15/07/2022 | 180 | MADHAB SAHA | 55.36 | 23.86 | 43.1 | 51
676 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Purba Kanthalbari water supply scheme, TW no I and II of Zone-III under Northern Mechanical Division-II, PHE Dte,Apd. | 1085/NMD-II | 01/06/2023 | 30 | M/S P.P ELECTRICALS | 22.85 | 0 | 0 | 100
677 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Material Requisition To Resource Division | 3612/ALD | 24/10/2024 | 0 | Resource Division | 7.78 | 0 | 0 | 0
678 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR PURBA KATHALBARI PWSS ZONE-II P/H NO-II | BP-2023-24-646 | 29/02/2024 | 0 | WBSEDCL | 9.8 | 0 | 0 | 0
679 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | QUOTATION CHARGES FOR PURBAKATHALBARI PWSS, ZONE-II PH NO-II | BP-80/24-25 | 16/05/2024 | 0 | WBSEDCL | 11.03 | 0 | 0 | 0
680 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | New Service Connection charges for Purba Kathalbari Zone-IV PH NO-II under NMD-II | BP-444/24-25 | 16/12/2024 | 0 | WBSEDCL | 6.36 | 0 | 0 | 0
681 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
682 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Purba Kanthalbari water supply scheme, TW no I and II of Zone-II under Northern Mechanical Division-II, PHE Dte.Alipurduar | 2366/NMD-II | 08/08/2023 | 604 | SUMON ELECTRICAL | 22.5 | 0 | 0 | 80
683 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2024 to 31.12.2024) | 488/ALD | 15/02/2024 | 366 | SASANKA ROY | 4.8 | 0 | 0 | 0
684 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying of DI and HDPE pipeline, Trenchless Pipe laying by HDD Process & other works for PURBA KATHALBARI ZONE-I 3rd pump house area for Purba Kathalbari PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/11459) | 821/ALD | 14/03/2024 | 480 | KAJAL KUMAR DE | 39.26 | 0 | 0 | 70
685 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying of different dia., CIDF, DI, UPVC, HDPE Pipeline, Trenchless Pipe laying by HDD Process, HDPE pipe line for left out household connection,Trial and run the entire PURBA KATHALBARI ZONE-3 PWSS Scheme with maintaining for 3 months after successfully running water, cons. of surface drain, pathway at H/W site and other works works for Purba Kathalbari PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/11459) | 892/ALD | 15/03/2024 | 355 | MADHAB SAHA | 49.29 | 0 | 0 | 60
686 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
687 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Replacement of damaged pipeline with HDPE pipes for Purba Kathalbari Zone-I PWSS under Alipurduar Division, PHE Dte. | 1223/ALD | 01/07/2025 | 60 | DILIP MAHATO (OPC) PRIVATE LIMITED | 5.3 | 0 | 0 | 0
688 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying of pipeline distribution system (Parallel and left out Area) and other allied works at Purba Kathalbari Zone-I PWSS within APD-I Block under Alipurduar Division, PHE Dte. | 2414/ALD | 18/11/2025 | 60 | ANIRBAN DEY SARKAR CONSTRUCTION | 54.38 | 0 | 0 | 0
689 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying of pipeline distribution system (Parallel and left out Area) and other allied works at Purba Kathalbari Zone-II PWSS within APD-I Block under Alipurduar Division, PHE Dte. | 1743/ALD | 13/08/2025 | 60 | ANIRBAN DEY SARKAR CONSTRUCTION | 41.04 | 0 | 0 | 0
690 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Purba Kathalbari Zone-II PWSS Under Alipurduar Division PHE DTE. | 979/ALD | 15/07/2022 | 1081 | JYOTI CHHETRI | 45.88 | 0 | 0 | 61
691 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Purba Kanthalbari water supply scheme, TW no I and II of Zone-I under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 368/NMD-II | 22/02/2023 | 649 | ALPHA ENTERPRISE | 22.84 | 0 | 0 | 100
692 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying of different dia., CIDF, DI, UPVC, HDPE Pipeline, Trenchless Pipe laying by HDD Process, HDPE pipe line for left out household connection, Trial and run the entire PURBA KATHALBARI ZONE-4 PWSS Scheme with maintaining for 3 months after successfully running water, cons. of surface drain, pathway at H/W site and other works for Purba Kathalbari PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/11459) | 849/ALD | 14/03/2024 | 360 | NARENDRA BHADANI. | 57.56 | 0 | 0 | 100
693 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME , SM/11459 | Augmentation | Laying of different dia., CIDF, DI Pipeline, UPVC pipe line for left out household connection and other works at PURBA KATHALBARI ZONE-I area of Purba Kathalbari PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. | 5360/ALD | 12/03/2025 | 60 | ANIRBAN DEY SARKAR CONSTRUCTION | 3 | 0 | 0 | 70
694 | ALIPURDUAR | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | Supply of CIPE Special & CI Jeffy Coupling for Mechpara Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 708/ALD | 08/06/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.89 | 4.89 | 50 | 40
695 | ALIPURDUAR | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-A) | 1967/ALD | 24/12/2021 | 90 | HARIDAS GHOSH | 0.96 | 0.96 | 50 | 39
696 | ALIPURDUAR | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-A) | 359/ALD | 08/06/2021 | 90 | HARIDAS GHOSH | 0.96 | 0.96 | 100 | 40
697 | ALIPURDUAR | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | Supply ,delivery and installation of split type air condition for the Chamber of Division Account Office under Alipurduar Division , P.H.E Dte. | 3363/ALD | 14/03/2023 | 30 | HARI CONSTRUCTION | 0.64 | 0 | 0 | 0
698 | ALIPURDUAR | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | Supply ,delivery and installation of split type air condition for the Accounts section under Alipurduar Division , P.H.E Dte. | 3364/ALD | 14/03/2023 | 30 | HARI CONSTRUCTION | 0.64 | 0 | 0 | 0
699 | ALIPURDUAR | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58
700 | ALIPURDUAR | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 120 | 100 | 0
701 | ALIPURDUAR | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | Material Requisition To Resource Division | 826/ALD | 28/06/2022 | 0 | Resource Division | 30.31 | 0 | 0 | 0
702 | ALIPURDUAR | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling including laying distribution system, Rising main and providing FHTC for MECHPARA TEA GARDEN AREA PWSS under Alipurduar Division PHE DTE | 14/ALD | 01/04/2022 | 120 | SHREE RANISATI ENTERPRISE | 224.94 | 5.16 | 2.29 | 38
703 | ALIPURDUAR | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 08.08.2022 to 31.10.2022) | 1191/ALD | 05/08/2022 | 92 | NIRANJAN KIRTANIA | 0.7 | 0 | 0 | 100
704 | ALIPURDUAR | Northern Mechanical Division II | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | New Service Connection for Mechpara T.G Area P/HNo-II, Kalchini. | BP-2023-24-508 | 05/01/2024 | 0 | WBSEDCL | 6.53 | 0 | 0 | 0
705 | ALIPURDUAR | Northern Mechanical Division II | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | New Service Connection for Mechpara TG Area PWSS P/H No-I,Kalchini | BP-2023-24-510 | 05/01/2024 | 0 | WBSEDCL | 5.93 | 0 | 0 | 0
706 | ALIPURDUAR | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | Construction of OHR 200cum for Mechpara Water Supply Scheme under Alipurduar Division, PHE Dte. | 2600/ALD | 17/02/2022 | 180 | M/S KAMAK ENGINEERS AND CO | 55.33 | 21.1 | 38.13 | 80
707 | ALIPURDUAR | Northern Mechanical Division II | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10176 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Mechpara TG water supply scheme, TW no I and II of under NMD-II, PHE Dte.APD | 2385/NMD-II | 09/08/2023 | 632 | B.B CONCERNED | 21.97 | 0 | 0 | 50
708 | ALIPURDUAR | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | Material Requisition To Resource Division | 3485/ALD | 23/03/2023 | 0 | Resource Division | 11.64 | 0 | 0 | 0
709 | ALIPURDUAR | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | Material Requisition To Resource Division | 1473/ALD | 16/08/2023 | 0 | Resource Division | 35.41 | 0 | 0 | 0
710 | ALIPURDUAR | Northern Mechanical Division II | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | NEW SERVICE CONNECTIO CHARGE FOR PURBA CHIKLIGURI W/S/S P/H NO.2 | BP-2023-24-180 | 15/06/2023 | 0 | WBSEDCL | 1.41 | 0 | 0 | 0
711 | ALIPURDUAR | Northern Mechanical Division II | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | NEW SERVICE CONNECTIO CHARGE FOR PURBA CHIKLIGURI W/S/S P/H NO.1 | BP-2023-24-179 | 15/06/2023 | 0 | WBSEDCL | 1.41 | 0 | 0 | 0
712 | ALIPURDUAR | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | Material Requisition To Resource Division | 109/ALD | 10/01/2024 | 0 | Resource Division | 11.51 | 0 | 0 | 0
713 | ALIPURDUAR | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | Road Restoration of Volka Road against PURBA CHIKLIGURI PWSS | 190/24-25/PFMS | 10/09/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 8.85 | 0 | 0 | 0
714 | ALIPURDUAR | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | Constructions of pump house & Sinking of 250 mm x 200 mm X 150 mtr Big dia Tubewel at HW site & 2nd site , laying of distribution system with UPVC pipeline , Constructions of 200 Cum OHR as per Departmental Design & drawing including soil test, providing FHTC and others allied works for Purba Chikliguri PWSS Under Alipurduar Division PHE DTE. | 2858/ALD | 17/01/2023 | 815 | SOUVIK ROY PALADHI | 481.73 | 245.08 | 50.87 | 65
715 | ALIPURDUAR | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | Laying of new UPVC/DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, land development works, construction of surface drain, pathway, supply of CIDF specials and other allied works in connection with the PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | 198/ALD | 16/01/2024 | 450 | SOUVIK ROY PALADHI | 60.36 | 0 | 0 | 5
716 | ALIPURDUAR | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | Laying of rising main line with HDPE PN10, horizontal boring by HDD method, bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block along with the others allied works at Madhya Parokata head works site PWSS adjacent to adjacent to Purba Chikliguri WSS under Alipurduar Division, PHE Dte. | 742/ALD | 12/03/2024 | 450 | SOUVIK ROY PALADHI | 57.31 | 0 | 0 | 30
717 | ALIPURDUAR | Northern Mechanical Division II | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
718 | ALIPURDUAR | Northern Mechanical Division II | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | Solarization of grid connected pumping installation at different PWSS at Alipurduar -II block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 819/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
719 | ALIPURDUAR | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | Supply of CIDF & CISS Pipes and specials for Purba Chikliguri WSS Under Alipurduar Division P.H.E Dte. | 1603/ALD | 25/08/2023 | 541 | SOUVIK ROY PALADHI | 6.76 | 0 | 0 | 100
720 | ALIPURDUAR | Northern Mechanical Division II | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Purba Chikliguri Water Supply Scheme TW No.- I AND II under NMD-II,PHE.Dte,APD | 2911/NMD-II | 31/10/2023 | 459 | M/S CHANDRANATH MUKHERJEE | 18.82 | 0 | 0 | 90
721 | ALIPURDUAR | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME , SM/13301 | New | "Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Purba Chikliguri Water Supply Scheme(SM/13301) of Alipurduar-II Block under Alipurduar Division P.H.E. Dte. " | 844/ALD | 14/03/2024 | 186 | MAKALI ENGINEERING CORPORATION | 15.23 | 0 | 0 | 25
722 | ALIPURDUAR | Alipurduar Division | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME , SM/14216 | New | Material Requisition To Resource Division | 1953/ALD | 12/09/2023 | 0 | Resource Division | 33.29 | 0 | 0 | 0
723 | ALIPURDUAR | Northern Mechanical Division II | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME , SM/14216 | New | QUOTATION FOR NEW SERVICE CONNECTION AT GAROCHIRA BANDAPANI TW NO-I | BP-2023-24-58 | 13/05/2023 | 0 | WBSEDCL | 1.46 | 0 | 0 | 0
724 | ALIPURDUAR | Alipurduar Division | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME , SM/14216 | New | Construction of Tubewell by ODEX-165 method of drilling at HW site, construction of pump house and boundary wall at H/W site, laying of distribution line and providing FHTC as per Departmental Design & drawing for Garochera Bandapani PWSS Under Birpara Sub-division, Alipurduar Division PHE DTE. | 2922/ALD | 19/01/2023 | 120 | RATAN DUTTA | 73.26 | 35.62 | 48.62 | 62
725 | ALIPURDUAR | Northern Mechanical Division II | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME , SM/14216 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Garochira Bandapani Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Apd. | 1674/NMD-II | 17/07/2023 | 30 | PRAGATI CONSTRUCTION COMPANY | 9.38 | 0 | 0 | 100
726 | ALIPURDUAR | Northern Mechanical Division II | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME , SM/14216 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
727 | ALIPURDUAR | Northern Mechanical Division II | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME , SM/14216 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini, Madarihat -Birpara ,kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1332/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
728 | ALIPURDUAR | Alipurduar Division | NURPUR PIPED WATER SUPPLY SCHEME. , SM/14218 | New | Supply of CIDF & CISS Pipes and specials for NURPUR WSS Under Alipurduar Division P.H.E Dte. | 1591/ALD | 25/08/2023 | 30 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 6.76 | 0 | 0 | 0
729 | ALIPURDUAR | Alipurduar Division | NURPUR PIPED WATER SUPPLY SCHEME. , SM/14218 | New | Material Requisition To Resource Division | 1258/ALD | 10/08/2023 | 0 | Resource Division | 13.15 | 0 | 0 | 0
730 | ALIPURDUAR | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. , SM/14218 | New | Quotation for NSC at P/H No.I under Nurpur W/S/S | BP-2023-24-175 | 15/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
731 | ALIPURDUAR | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. , SM/14218 | New | Quotation for NSC at P/H No.II under Nurpur W/S/S | BP-2023-24-176 | 15/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
732 | ALIPURDUAR | Alipurduar Division | NURPUR PIPED WATER SUPPLY SCHEME. , SM/14218 | New | Gap filling of distribution line with DI/CI/UPVC pipe at Nurpur WSS under Alipurduar Division, PHE Dte. | 1468/ALD | 16/08/2023 | 60 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 20.69 | 0 | 0 | 70
733 | ALIPURDUAR | Alipurduar Division | NURPUR PIPED WATER SUPPLY SCHEME. , SM/14218 | New | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at NURPUR HW site PWSS under Alipurduar Division, PHE Dte. | 84/ALD | 10/01/2024 | 90 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 33.28 | 0 | 0 | 0
734 | ALIPURDUAR | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. , SM/14218 | New | New Service Connection Charges for Nurpur, Uttar Rampur, PWSS PH NO-3 | BP-292/24-25 | 20/08/2024 | 0 | WBSEDCL | 13.73 | 0 | 0 | 0
735 | ALIPURDUAR | Alipurduar Division | NURPUR PIPED WATER SUPPLY SCHEME. , SM/14218 | New | Cons. Of pump house & TW boring by ODEX-165 method of drilling at HW & 2nd site, LDS with UPVC pipeline including rising main & delivery connection, cons. Of 100cum OHR as per departmental design & drawing along with soil investigation works, providing FHTC including platform and others allied works for NURPUR PWSS Under Alipurduar Division PHE DTE. (2nd call) | 3195/ALD | 27/02/2023 | 721 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 182.4 | 111 | 60.86 | 95
736 | ALIPURDUAR | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. , SM/14218 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Nurpur Water Supply Scheme TW No.- I ,II and III under NMD-II,PHE.Dte,APD. | 983/NMD-II | 15/05/2023 | 30 | RMD TRADING | 28.75 | 0 | 0 | 100
737 | ALIPURDUAR | Alipurduar Division | NURPUR PIPED WATER SUPPLY SCHEME. , SM/14218 | New | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte. (from 01.01.2024 to 31.12.2024) | 487/ALD | 15/02/2024 | 366 | MATRI ENTERPRISE | 4.8 | 0 | 0 | 0
738 | ALIPURDUAR | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. , SM/14218 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
739 | ALIPURDUAR | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. , SM/14218 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar -I & II Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1293/NMD-II | 12/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 26.61 | 0 | 0 | 0
740 | ALIPURDUAR | Alipurduar Division | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14222 | New | Providing FHTC from existing distribution system as per specification for Uttar Rangalibazna PWSS under Alipurduar Division, PHE Dte. | 2135/ALD | 03/10/2023 | 30 | MANI PRADHAN | 1.08 | 0 | 0 | 0
741 | ALIPURDUAR | Alipurduar Division | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14222 | New | Material Requisition To Resource Division | 2701/ALD | 12/12/2023 | 0 | Resource Division | 84.45 | 0 | 0 | 0
742 | ALIPURDUAR | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14222 | New | NEW CONNECTION SERVICE FOR UTTAR RANGALIBAZNA PWSS P/H NO II | BP-2023-24-363 | 27/09/2023 | 0 | WBSEDCL | 5.74 | 0 | 0 | 0
743 | ALIPURDUAR | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14222 | New | NEW CONNECTION SETRVICE FOR UTTAR RANGALIBAZNA PWSS P/H NO I APPLICATION NO 4003065172 | BP-2023-24-362 | 27/09/2023 | 0 | WBSEDCL | 7.7 | 0 | 0 | 0
744 | ALIPURDUAR | Alipurduar Division | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14222 | New | Material Requisition To Resource Division | 114/ALD | 10/01/2024 | 0 | Resource Division | 4.49 | 0 | 0 | 0
745 | ALIPURDUAR | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14222 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1334/NMD-II | 18/06/2025 | 90 | M. M. ENTERPRISE | 16.38 | 0 | 0 | 0
746 | ALIPURDUAR | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14222 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
747 | ALIPURDUAR | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14222 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for UTTAR RANGALIBAZNA water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | 2139/NMD-II | 27/07/2023 | 615 | DILIP MAHATO | 18.33 | 0 | 0 | 100
748 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) , SM/07125 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | 2764/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 30.98 | 100 | 60
749 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) , SM/07125 | Retrofitting | Laying Distribution line of UPVC, DI Pipe (with pillar) and cons. Of new toilet, repairing of pump house (2nd site), Land Development at Barobisa Zone-I Water Supply Scheme under Alipurduar Division, PHE Dte. | 1319/ALD | 05/10/2021 | 60 | M/S SURAJIT DEY & CO | 81.49 | 0 | 0 | 70
750 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) , SM/07125 | Retrofitting | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | 3082/ALD | 22/03/2022 | 60 | AASHIRBAD ENTERPRISE | 13.46 | 0 | 0 | 70
751 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) , SM/07125 | Retrofitting | Laying of UPVC and DI (with pillar) pipeline Barobisa Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | 1575/ALD | 22/11/2021 | 90 | TAPAN CHANDA | 75.74 | 39.37 | 100 | 69
752 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) , SM/07125 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-I) Under Alipurduar Division, PHE DTE. | 2763/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 19.82 | 100 | 69
753 | ALIPURDUAR | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Providing balance FHTC for MADHYA KAMAKHYAGURI PWSS under Alipurduar Division, PHE Dte. | 1850/ALD | 04/09/2023 | 45 | MONORAMA ENTERPRISE | 5.85 | 0 | 0 | 0
754 | ALIPURDUAR | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Material Requisition To Resource Division | 1277/ALD | 11/08/2023 | 0 | Resource Division | 49.36 | 0 | 0 | 0
755 | ALIPURDUAR | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MADHYA KAMAKHYAGURI PWSS PH NO-I | BP-2023-24-41 | 12/05/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
756 | ALIPURDUAR | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MADHYA KAMAKHYAGURI PWSS PH NO-II | BP-2023-24-42 | 12/05/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
757 | ALIPURDUAR | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. big dia. TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 350 cum OHR as per Departmental Design & drawing , providing FHTC and others allied works for MADHYA KAMAKHYAGURI PWSS Under Alipurduar Division PHE DTE. | 3155/ALD | 22/02/2023 | 180 | GHOSH & SAHA CONSTRUCTION | 478.58 | 369.03 | 77.11 | 85
758 | ALIPURDUAR | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Supply of DI pipe & CI special for Madhya Kamakhyaguri PWSS under Alipurduar Division PHE Dte. | 390/ALD | 19/05/2023 | 30 | DILIP MAHATO | 71.61 | 0 | 0 | 75
759 | ALIPURDUAR | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Supply of DI/DIDF Specials for Madhya Kamakhyaguri (SM/15517)WSS under Alipurduar Division, PHE Dte. | 4235/ALD | 12/12/2024 | 30 | MADHAB SAHA | 16.91 | 0 | 0 | 0
760 | ALIPURDUAR | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Material Requisition To Resource Division | 128/ALD | 10/01/2024 | 0 | Resource Division | 10.13 | 0 | 0 | 0
761 | ALIPURDUAR | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Material Requisition To Resource Division | 4261/ALD | 13/12/2024 | 0 | Resource Division | 13.19 | 0 | 0 | 0
762 | ALIPURDUAR | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
763 | ALIPURDUAR | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Madhya Kamakhyaguri Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | 2466/NMD-II | 11/08/2023 | 30 | M/S PARITOSH BHOWMICK & CO. | 21.92 | 0 | 0 | 100
764 | ALIPURDUAR | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing, Construction of surface drain, pathway other allied works in connection with the Madhya Kamakhyaguri PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/15517) | 2279/ALD | 05/08/2024 | 180 | GHOSH & SAHA CONSTRUCTION | 61.08 | 0 | 0 | 70
765 | ALIPURDUAR | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
766 | ALIPURDUAR | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Continuation of work of Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte. (from 01.04.2025 to 30.04.2025) | 5591/ALD | 26/03/2025 | 31 | APSARI BHOWMICK | 0.4 | 0 | 0 | 0
767 | ALIPURDUAR | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
768 | ALIPURDUAR | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME , SM/15517 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1347/NMD-II | 19/06/2025 | 30 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
769 | ALIPURDUAR | Alipurduar Division | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | Material Requisition To Resource Division | 2720/ALD | 13/12/2023 | 0 | Resource Division | 68.94 | 0 | 0 | 0
770 | ALIPURDUAR | Alipurduar Division | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , Soil investigation at OHR site, constructions of 350 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for MAIRADANGA PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 334/ALD | 16/05/2023 | 720 | MESSRS A.B.G CONSTRUCTION | 653.77 | 0 | 0 | 65
771 | ALIPURDUAR | Alipurduar Division | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | Material Requisition To Resource Division | 120/ALD | 10/01/2024 | 0 | Resource Division | 15.91 | 0 | 0 | 0
772 | ALIPURDUAR | Northern Mechanical Division II | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | New Servivce Connection for Marindanga PH NO-I PWSS | BP-279/24-25 | 22/08/2024 | 0 | WBSEDCL | 7.07 | 0 | 0 | 0
773 | ALIPURDUAR | Northern Mechanical Division II | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | New Service Connection for Mairadanga PH NO-II PWSS | BP-278/24-25 | 22/08/2024 | 0 | WBSEDCL | 5.22 | 0 | 0 | 0
774 | ALIPURDUAR | Northern Mechanical Division II | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Mairadanga Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | 2475/NMD-II | 11/08/2023 | 753 | SUBODH KUMAR BANIK | 21.06 | 0 | 0 | 80
775 | ALIPURDUAR | Alipurduar Division | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | Construction of slab culvert, pathway and other allied works at 3rd TW Site, painting existing boundary wall, pump house, roof treatment, plinth protection at 2nd TW site of Chhoto Salkumar WSS adjacent to Mairadanga PWSS including gap filling in distribution line (90mm dia) under Alipurduar Division, PHE Dte. | 2606/ALD | 04/12/2023 | 692 | ASSOCIATE CONSTRUCTION COMPANY | 23.88 | 0 | 0 | 95
776 | ALIPURDUAR | Alipurduar Division | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
777 | ALIPURDUAR | Northern Mechanical Division II | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | Yard lighting arrangement at Head Work Site for Different PWSS (KADAMBINI TG and Others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1346/NMD-II | 19/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 23.98 | 0 | 0 | 0
778 | ALIPURDUAR | Northern Mechanical Division II | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1344/NMD-II | 19/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
779 | ALIPURDUAR | Northern Mechanical Division II | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
780 | ALIPURDUAR | Alipurduar Division | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | Laying of additional DI & HDPE pipeline, Costruction of Sluice Valve chamber & other works for Providing FHTC at Mairadanga PWSS under Alipurduar Division, PHE Dte. | 677/ALD | 21/05/2025 | 90 | ANIRBAN DEY SARKAR CONSTRUCTION | 44.3 | 0 | 0 | 0
781 | ALIPURDUAR | Alipurduar Division | MAIRADANGA PIPED WATER SUPPLY SCHEME , SM/15206 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1629/ALD | 04/08/2025 | 60 | NARENDRA BHADANI. | 18.13 | 0 | 0 | 0
782 | ALIPURDUAR | Alipurduar Division | Uttar Dhalkar Piped Water Supply Scheme , SM/18154 | New | Constructions of pump house and Tube well Boring by ODEX-165 Method of drilling at HW site and 2nd site , Laying of distribution system with HDPE pipeline including rising main & delivery connection , Constructions of 100 Cum OHR as per Departmental Design & drawing along with the Soil investigation works , providing FHTC and others allied works for Uttar Dhalkar PWSS Under Alipurduar Division PHE DTE. | 237/ALD | 04/05/2023 | 720 | TAPASH KUMAR BHOWMICK | 226.42 | 0 | 0 | 45
783 | ALIPURDUAR | Alipurduar Division | Uttar Dhalkar Piped Water Supply Scheme , SM/18154 | New | Construction of balance portion of boundary wall, pathway, surface drain and chatal, land development, laying of rising main line & delivery line connection along with the other allied works at Putimari PWSS adj. To Uttar Dhalkar PWSS under Alipurduar Division, PHE Dte. | 2540/ALD | 28/11/2023 | 90 | TAPASH KUMAR BHOWMICK | 25.47 | 0 | 0 | 100
784 | ALIPURDUAR | Alipurduar Division | Uttar Dhalkar Piped Water Supply Scheme , SM/18154 | New | Material Requisition To Resource Division | 3984/ALD | 27/11/2024 | 0 | Resource Division | 3.66 | 0 | 0 | 0
785 | ALIPURDUAR | Northern Mechanical Division II | Uttar Dhalkar Piped Water Supply Scheme , SM/18154 | New | New Service Connection Charges for Uttar Dhalkar PWSS PH NO-2 under NMD-II | BP-428/24-25 | 16/12/2024 | 0 | WBSEDCL | 5.25 | 0 | 0 | 0
786 | ALIPURDUAR | Northern Mechanical Division II | Uttar Dhalkar Piped Water Supply Scheme , SM/18154 | New | New Service Connection for Uttar Dhalkar PWSS PH NO-I in the dist of Alipurduar | BP-328/24-25 | 03/10/2024 | 0 | WBSEDCL | 4.9 | 0 | 0 | 0
787 | ALIPURDUAR | Northern Mechanical Division II | Uttar Dhalkar Piped Water Supply Scheme , SM/18154 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for UTTAR DHALKAR Water Supply Scheme TW No.- I AND II under NMD-II,PHE.Dte,APD. | 2578/NMD-II | 22/08/2023 | 818 | M/S B ENTERPRISE | 21.17 | 0 | 0 | 75
788 | ALIPURDUAR | Northern Mechanical Division II | Parpatla Khawa Piped Water Supply Scheme , SM/18158 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for PARPATLA KHAWA water supply scheme, TW no I and II of under JJM under NMD-II, PHE Dte. APD. | 2625/NMD-II | 25/08/2023 | 30 | HARA PROSAD DAS | 21.25 | 0 | 0 | 40
789 | ALIPURDUAR | Northern Mechanical Division II | Parpatla Khawa Piped Water Supply Scheme , SM/18158 | New | NEW SERVICE CONNECTION CHARGES FOR PAR PATLAKHAWA PWSS P/H NO-I | BP-235/24-25 | 29/07/2024 | 0 | WBSEDCL | 6.17 | 0 | 0 | 0
790 | ALIPURDUAR | Northern Mechanical Division II | Parpatla Khawa Piped Water Supply Scheme , SM/18158 | New | New Service Connection Charges for Parpatlakhowa PWSS PH NO-II under NMD-II | BP-427/24-25 | 16/12/2024 | 0 | WBSEDCL | 13.63 | 0 | 0 | 0
791 | ALIPURDUAR | Alipurduar Division | Parpatla Khawa Piped Water Supply Scheme , SM/18158 | New | Boring of Tube Well by reverse rotary method, Construction of Pump House, Boundary Wall, Laying Of Distribution System and providing FHTC for Parpatlakhawa PWSS under Alipurduar Division, PHE Dte. | 235/ALD | 04/05/2023 | 720 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 113.69 | 0 | 0 | 16
792 | ALIPURDUAR | Alipurduar Division | Parpatla Khawa Piped Water Supply Scheme , SM/18158 | New | Supply and installation of sign board at different PWSS site of Kumargram Block under Alipurduar Division, PHE Dte. | 679/ALD | 21/05/2025 | 45 | TAPASH DAS | 4.69 | 0 | 0 | 100
793 | ALIPURDUAR | Alipurduar Division | Parpatla Khawa Piped Water Supply Scheme , SM/18158 | New | Gap filling of distribution line, land development and other allied works for ParpatlaKhawa Piped Water Supply Scheme within Alipurduar Block-I under Alipurduar Division, PHE Dte. | 818/ALD | 03/06/2025 | 75 | CHITTA RANJAN DEY | 20.25 | 0 | 0 | 0
794 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) , SM/07127 | Retrofitting | Restoration of laying distribution system by replacing of damaged AC pipeline with DI and UPVC pipe of Kumargram WSS under Alipurduar Division, PHE Dte. | 980/ALD | 13/09/2021 | 60 | DILIP MAHATO | 48.35 | 0 | 0 | 68
795 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) , SM/07127 | Retrofitting | Laying Distribution line of UPVC, DI Pipe (with pillar) and cons. Of new toilet, repairing of pump house (2nd site), Land Development at Barobisa Zone-I Water Supply Scheme under Alipurduar Division, PHE Dte. | 1319/ALD | 05/10/2021 | 60 | M/S SURAJIT DEY & CO | 81.49 | 0 | 0 | 70
796 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) , SM/07127 | Retrofitting | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | 3082/ALD | 22/03/2022 | 60 | AASHIRBAD ENTERPRISE | 13.46 | 0 | 0 | 70
797 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) , SM/07127 | Retrofitting | Providing House connection for BAROBISHA Zone-I water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | 1160/ALD | 15/12/2020 | 60 | M/S SURAJIT DEY & CO | 29.98 | 0 | 0 | 69
798 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) , SM/07127 | Retrofitting | Laying of UPVC & DI (with pillar) pipeline for Barobisha Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | 1320/ALD | 05/10/2021 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 79.02 | 61.39 | 100 | 66
799 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) , SM/07127 | Retrofitting | Providing House connection for BAROBISHA Zone-III water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-II | 1162/ALD | 15/12/2020 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 19.93 | 0 | 0 | 77
800 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) , SM/07127 | Retrofitting | Laying of UPVC and DI (with pillar) pipeline Barobisa Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | 1575/ALD | 22/11/2021 | 90 | TAPAN CHANDA | 75.74 | 0 | 0 | 69
801 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) , SM/07127 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-I) Under Alipurduar Division, PHE DTE. | 2763/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 0 | 0 | 69
802 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) , SM/07133 | Retrofitting | Fuel bill for the month of August 2021 | 121/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.22 | 0 | 0 | 0
803 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) , SM/07133 | Retrofitting | Fuel bill for the month of August 2021 | 117/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.11 | 0 | 0 | 0
804 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) , SM/07133 | Retrofitting | Laying of balance DI/MS/HDPE pipeline for the Dalmore-Ramjhora WSS under Alipurduar Division, PHE Dte. | 1456/ALD | 25/01/2021 | 45 | ASHIT KUMAR SINGHA | 21.28 | 4.28 | 38.77 | 59
805 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) , SM/07133 | Retrofitting | Retrofitting of pipeline for Ramjhora TG PWSS area at Madarihat-Birpara Block under Alipurduar Division, P.H.E. Dte. | 1447/ALD | 25/01/2021 | 45 | ASHIT KUMAR SINGHA | 16.96 | 3.58 | 40.64 | 58
806 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) , SM/07133 | Retrofitting | Laying of HDPE pipe line for Dalmore Water Supply Scheme under Alipurduar Division, PHE Dte. | 2996/ALD | 15/03/2022 | 60 | MS DEYS CONSTRUCTION | 8.33 | 7.04 | 100 | 58
807 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) , SM/07133 | Retrofitting | Construction of Pump House with Sanitary & Plumbing arrangement at 2nd Pump House Site of Dalmore-Ramjhora WSS (Ramjhora Pump House no-2) under Alipurduar Division PHE Dte. | 893/ALD | 03/09/2021 | 60 | PRAMESH LAMA | 4.96 | 4.97 | 100 | 60
808 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) , SM/07133 | Retrofitting | Retrofitting work of pipeline of Dalmore PWSS under Alipurduar Division, PHE Dte. | 971/ALD | 13/09/2021 | 30 | MS DEYS CONSTRUCTION | 5.04 | 5.04 | 50 | 59
809 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) , SM/07133 | Retrofitting | Construction of Pump House with Sanitary & Plumbing arrangement at H/W Site (Old) of Dalmore Water supply scheme under Alipurduar Division. P.H.E. Dte. | 538/ALD | 20/08/2020 | 120 | PRAPTI DUTTA | 4.75 | 8.4 | 100.71 | 0
810 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) , SM/07133 | Retrofitting | Construction of Pump House with Sanitary & Plumbing arrangement at Headwork Site of Dalmore-Ramjhora WSS (Ramjhora Pump House no-1) under Alipurduar Division PHE Dte. | 894/ALD | 03/09/2021 | 60 | PRAMESH LAMA | 4.96 | 4.97 | 50 | 0
811 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dhaolajhora T.G Piped Water Supply Scheme , SM/07191 | Retrofitting | Laying of distribution pipeline with DI and UPVC pipes for interconnection of Dhaolajhora PWSS with Loknathpur PWSS under Alipurduar Division, PHE Dte. | 3192/ALD | 28/03/2022 | 60 | GOUTAM KUMAR DAS | 49.89 | 1.8 | 12.53 | 81
812 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dhaolajhora T.G Piped Water Supply Scheme , SM/07191 | Retrofitting | Repairing of old UPVC pipe line , FHTC and other misc. work related to DHAOLAJHORA PWSS Alipurduar - II Block under Alipurduar Division , PHE Dte | 436/ALD | 13/05/2022 | 30 | MATARA CONSTRUCTION CO | 3.3 | 3.29 | 50 | 27
813 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dhaolajhora T.G Piped Water Supply Scheme , SM/07191 | Retrofitting | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, left out portion of household connection with HDPE pipe, providing balance FHTC, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at DHAOLAJHORA (SM/07191) 3rd TW site PWSS of Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | 1954/ALD | 02/07/2024 | 270 | CHANDAN KIRTONIA | 33.15 | 0 | 0 | 70
814 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme , SM/07192 | Retrofitting | Fuel bill for the month of August 2021 | 121/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.22 | 0 | 0 | 0
815 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme , SM/07192 | Retrofitting | Providing House connection for Munshipara piped water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. | 722/ALD | 22/09/2020 | 30 | TAPASH DAS | 4.98 | 9.97 | 200 | 0
816 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme , SM/07192 | Retrofitting | Construction of Soak well, Fencing and other works at Madhu TG PWSS under Alipurduar Division, PHE Dte. | 516/ALD | 20/08/2020 | 60 | TAPASH KUMAR BHOWMICK | 3.91 | 7.82 | 200 | 0
817 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme , SM/07192 | Retrofitting | Construction of Fire hydrant, parking area for water collecting vehicles, surface drain and other miscellaneous works for Madhu T.G. P/W/S/S, Under Alipurduar Division P.H.E. Dte. | 530/ALD | 20/08/2020 | 60 | TAPASH KUMAR BHOWMICK | 5 | 10 | 200 | 0
818 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme , SM/07192 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc. work for retrofitting of Mujnai PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 943/ALD | 19/10/2020 | 60 | VEDATRAYEE AND CO | 29.81 | 57.1 | 200 | 92
819 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme , SM/07192 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | 1281/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 37.84 | 2.8 | 200 | 94
820 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme , SM/07192 | Retrofitting | Extension of pipeline to Bharnabari TG area under Hasimara PWSS for providing at Kalchini Block under Alipurduar Division, P.H.E. Dte.(Part-B) | 1010/ALD | 12/11/2020 | 60 | ASHIT KUMAR SINGHA | 39.34 | 49.96 | 100 | 0
821 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) , SM/07174 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under BAKLA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | 1283/ALD | 05/01/2021 | 60 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 45.19 | 56.51 | 100 | 74
822 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) , SM/07174 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 5 | 100 | 0
823 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) , SM/07174 | Retrofitting | Providing House connection for Bakla Piped water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. | 728/ALD | 22/09/2020 | 30 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.98 | 9.96 | 200 | 0
824 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) , SM/07174 | Retrofitting | "Providing House connection for Bakla water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. (Part-II)" | 1137/ALD | 10/12/2020 | 30 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.98 | 9.96 | 100 | 0
825 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) , SM/07174 | Retrofitting | Preparation of Augmentation D.P.R after investigation For SamuktalaW/S scheme under Alipurduar Division. | 915/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.81 | 5.61 | 100 | 0
826 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) , SM/07174 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Bakla PWSS Under Alipurduar Division, PHE DTE. | 2753/ALD | 24/02/2022 | 1200 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 43.78 | 0 | 0 | 43
827 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-2) , SM/07183 | Retrofitting | Retrofitting of pipeline etc. for the 'Jal Sapna' programme (FHTC for every house hold) under Loknathpur PWSS under Alipurduar Division, PHE Dte. | 2296/ALD | 24/01/2022 | 60 | GOUTAM KUMAR DAS | 45.8 | 16.58 | 100 | 94
828 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-2) , SM/07183 | Retrofitting | Laying of distribution pipeline with DI and UPVC pipes for interconnection of Dhaolajhora PWSS with Loknathpur PWSS under Alipurduar Division, PHE Dte. | 3192/ALD | 28/03/2022 | 60 | GOUTAM KUMAR DAS | 49.89 | 24.57 | 100 | 81
829 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-2) , SM/07183 | Retrofitting | Restoration of pipe line by providing steel piles at Turturi River for LOKNATHPUR Water Supply Scheme Under Alipurduar Division PHE Dte. | 692/ALD | 16/09/2020 | 120 | MATARA CONSTRUCTION CO | 6.04 | 0 | 0 | 100
830 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) , SM/07187 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Banchukamari WSS under Alipurduar Division, PHE Dte. Part-4 | 1844/ALD | 10/12/2021 | 30 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.04 | 0.94 | 37.22 | 87
831 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) , SM/07187 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Banchukamari PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | 2378/ALD | 31/01/2022 | 60 | SHIBA ENTERPRISE | 51.82 | 0 | 0 | 87
832 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) , SM/07187 | Retrofitting | Providing House connection for Banchukamari piped water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. | 721/ALD | 22/09/2020 | 30 | DAS CONSTRUCTION | 4.99 | 9.99 | 100 | 0
833 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) , SM/07187 | Retrofitting | Providing House connection for BHOLARDABRI PWSS under Alipuduar Division, P.H.E. Dte. | 1767/ALD | 19/02/2021 | 60 | HARIDAS GHOSH | 10.03 | 20.07 | 200 | 0
834 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) , SM/07187 | Retrofitting | Providing House connection for BHOLARDABRI water supply scheme at ALIPURDUAR-I Block under Alipuduar Division, P.H.E. Dte.(Part-2) | 1462/ALD | 25/01/2021 | 30 | HARI CONSTRUCTION | 5.01 | 10.02 | 200 | 0
835 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) , SM/07187 | Retrofitting | Providing House connection for KALCHINI water supply scheme at KALCHINI Block under Alipuduar Division, P.H.E. Dte.(Part-3) | 1463/ALD | 25/01/2021 | 30 | HARI CONSTRUCTION | 4.98 | 5.66 | 200 | 97
836 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) , SM/07187 | Retrofitting | Providing House connection for BHOLARDABRI WSS at Alipurduar-II Block under Alipurduar Division, PHE Dte. (Part-5) | 1586/ALD | 10/02/2021 | 60 | HARIDAS GHOSH | 4.98 | 9.97 | 100 | 0
837 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) , SM/07187 | Retrofitting | Providing House connection for BHOLARDABRI WSS at Alipurduar-II Block under Alipurduar Division, PHE Dte. (Part-4) | 1585/ALD | 10/02/2021 | 60 | HARIDAS GHOSH | 4.98 | 9.96 | 100 | 0
838 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) , SM/07187 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Banchukamari WSS under Alipurduar Division, PHE Dte. Part-3 | 1843/ALD | 10/12/2021 | 1422 | PROJIT HALDER | 5.02 | 0 | 0 | 87
839 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme , SM/08880 | Retrofitting | Laying of HDPE pipeline and interconnection of other different dia pipe line with CIDF Specials & Providing house connection (FHTC) at Uttar Madarihat WSS under Alipurduar Division PHE Dte. | 1241/ALD | 27/09/2021 | 60 | M/S SURAJIT DEY & CO | 47.32 | 22.91 | 48.41 | 96
840 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme , SM/08880 | Retrofitting | Laying of HDPE pipe line for Madarihat Water Supply Scheme under Alipurduar Division, PHE Dte. | 2284/ALD | 21/01/2022 | 60 | DILIP MAHATO | 37.73 | 35.81 | 94.89 | 97
841 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme , SM/08880 | Retrofitting | Laying of HDPE pipe line for Madarihat Water Supply Scheme under Alipurduar Division, PHE Dte. | 2285/ALD | 21/01/2022 | 60 | MAHENDRA CHHETRI | 37.73 | 32.37 | 85.78 | 99
842 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme , SM/08880 | Retrofitting | Providing House connection for MADARIHAT PWSS under Alipuduar Division, P.H.E. Dte. | 1806/ALD | 22/02/2021 | 60 | DILIP MAHATO | 20.13 | 18.11 | 50 | 90
843 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme , SM/08880 | Retrofitting | Construction of RCC boundary wall for Uttar Latabari WSS Pump House (rabindra nagar) at Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | 1834/ALD | 10/12/2021 | 45 | SHIB RATAN BHOWMIK | 4.9 | 0 | 0 | 75
844 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme , SM/08880 | Retrofitting | Repair of Pump House with additional Toilet at 2nd Pump House site of Madarihat WSS under Alipuduar Division, P.H.E. | 877/ALD | 14/10/2020 | 45 | DILIP MAHATO | 2.13 | 1.86 | 100 | 91
845 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme , SM/08880 | Retrofitting | Retrofitting work of pipeline of Madarihat PWSS under Alipurduar Division, PHE Dte. | 972/ALD | 13/09/2021 | 30 | MS DEYS CONSTRUCTION | 4.99 | 4.99 | 50 | 99
846 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme , SM/08880 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna for AWC and school under Madarihat WSS under Alipurduar Division, PHE Dte. | 1831/ALD | 10/12/2021 | 30 | RATAN DUTTA | 5.04 | 4.07 | 100 | 59
847 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme , SM/08880 | Retrofitting | Construction of 350cum OHR for Madarihat TG Water Supply Scheme under Alipurduar Division, PHE Dte. | 2586/ALD | 17/02/2022 | 180 | DILIP MAHATO | 71.4 | 20.13 | 100 | 90
848 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme , SM/08881 | Retrofitting | Replacement of old existing AC pipeline with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Uttar Sishubari WSS under Alipurduar Division, PHE Dte. (Opposite of Rail line area) | 1577/ALD | 22/11/2021 | 60 | ASHOK SAPKOTA | 22.55 | 20.81 | 92.3 | 54
849 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme , SM/08881 | Retrofitting | Replacement of old existing AC pipeline with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Uttar Sishubari WSS under Alipurduar Division, PHE Dte. (Opposite of Rail line area) | 1578/ALD | 22/11/2021 | 60 | KAMALESH ROY | 22.55 | 20.81 | 92.3 | 55
850 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme , SM/08881 | Retrofitting | Laying of UPVC/DI/MS/CI Distribution pipe line for Gap filling of Chapaguri area at Uttar Sishubari PWSS under Alipurduar Division PHE Dte. | 2652/ALD | 21/02/2022 | 45 | KAMALESH ROY | 4.94 | 4.68 | 49.99 | 55
851 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme , SM/08881 | Retrofitting | Extension/Merging of Distribution pipeline (UPVC/DI/MS/CI) from Paschim Khairbari WSS to Uttar Sishubari WSS and others misc. work under Alipurduar Division, PHE Dte. | 1255/ALD | 28/12/2020 | 60 | MITHUN DAS | 45.83 | 9 | 100 | 80
852 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme , SM/08881 | Retrofitting | Construction of boundary wall at 2nd PH Site of Uttar Sishubari WSS under Alipurduar Division. | 895/ALD | 03/09/2021 | 45 | MITHUN DAS | 4.98 | 4.99 | 100 | 56
853 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme , SM/08881 | Retrofitting | Material Requisition To Resource Division | 718/ALD | 13/06/2022 | 0 | Resource Division | 87.66 | 0 | 0 | 0
854 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme , SM/08881 | Retrofitting | Repairing of 2 nos. P/H with toilet block (PH-1 and 2) and Replacement of old existing AC p/l with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Uttar Sishubari WSS under Alipurduar Division, PHE Dte. (Sishubari High School and adjacent area) | 1309/ALD | 05/10/2021 | 60 | MITHUN DAS | 45.4 | 26.14 | 59.07 | 100
855 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME , SM/09894 | Augmentation | Additional quotation for Munshipara p/h-III | BP-2023-24-479 | 12/12/2023 | 0 | WBSEDCL | 3.86 | 0 | 0 | 0
856 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME , SM/09894 | Augmentation | QUOTATION FOR NSC AT MUNSHIPARA PH NO-III | BP-2023-24-359 | 27/09/2023 | 0 | WBSEDCL | 1 | 0 | 0 | 0
857 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME , SM/09894 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of MUNSHIPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2227/ALD | 14/01/2022 | 90 | TAPASH DAS | 21.92 | 4 | 18.26 | 25
858 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME , SM/09894 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Munshipara water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar | 2173/NMD-II | 27/07/2023 | 403 | M/S KUNDU CONSTRUCTION | 10.81 | 0 | 0 | 100
859 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME , SM/09894 | Augmentation | ADDITIONAL QUOTATION CHARGES FOR MUNSHIPARA PWSS . | BP-42/24-25 | 29/04/2024 | 0 | WBSEDCL | 0.36 | 0 | 0 | 0
860 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME , SM/09896 | Augmentation | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for DHUMCHIPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2390/ALD | 31/01/2022 | 90 | DILIP MAHATO | 27.18 | 0 | 0 | 18
861 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME , SM/09896 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for DHUMCHIPARA TG Water Supply Scheme TW No.-IV under NMD-II,PHE Dte. Alipurduar. | 247/NMD-II | 13/02/2023 | 30 | ALPHA ENTERPRISE | 13.78 | 13.24 | 96.06 | 100
862 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME , SM/09896 | Augmentation | Quotation for new service connection at Dhumchipara TW No- IV | BP-140/22-23 | 23/02/2023 | 0 | WBSEDCL | 1.99 | 0 | 0 | 0
863 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME , SM/09896 | Augmentation | Sinking of Big dia. Tubewell (200 x 150 mm dia.)By modified DTH -ODEX method of drilling at Dhumchipara-2nos. site (SM/09896 & SM/16824) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | 891/ALD | 15/03/2024 | 180 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 34.47 | 0 | 0 | 10
864 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME , SM/09896 | Augmentation | Quotation for Meter Burn at DUMCHIPARA TG PH NO-2 |  | 23/04/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
865 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME , SM/09896 | Augmentation | QUOTATION CHARGES FOR METER BURN AT DHUMCHIPARA TG PH NO-I |  | 23/04/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
866 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME , SM/09896 | Augmentation | Renovation of Pump house and boundary wall at 2nd Pump house site of Dhumchipara TG PWSS under Alipurduar Division, PHE Dte | 1176/ALD | 26/06/2025 | 90 | AVNI CONSTRUCTION | 1.04 | 0 | 0 | 0
867 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME , SM/09896 | Augmentation | Renovation of Pump house and boundary wall at 3rd Pump house of Dhumchipara TG PWSS under Alipurduar Division, PHE Dte | 1175/ALD | 26/06/2025 | 90 | MANI PRADHAN | 1.05 | 0 | 0 | 0
868 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME , SM/09897 | Augmentation | Laying of Distribution Line (HDPE and DI) for retrofitting of FHTC for BIRPARA WSS under Alipurduar Division, PHE Dte. | 1754/ALD | 19/02/2021 | 45 | BILTU DAS | 47.98 | 15 | 100 | 61
869 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME , SM/09897 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of BIRPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2192/ALD | 11/01/2022 | 90 | DAS CONSTRUCTION | 22.03 | 7.86 | 100 | 65
870 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME , SM/09897 | Augmentation | Extension and replacement of damaged pipeline under Birpara APD PWSS at Alipurduar-I under Alipurduar Division, P.H.E. Dte. | 883/ALD | 03/09/2021 | 45 | KAMALESH ROY | 15.92 | 3.32 | 100 | 0
871 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME , SM/09897 | Augmentation | Quotation for new service connection at Birpara (apd) TG P/H No-III. Application No- 4003027982 | BP-110/22-23 | 19/12/2022 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
872 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME , SM/09897 | Augmentation | Extension work order for Hiring of Diesel vehicle Maxi Cab(At least 7 seater) for Executive Engineer, Alipurduar Division under Alipurduar Division, PHE Dte.( 01.04.2021 to 30.06.2021) | 3051/ALD | 31/03/2021 | 91 | APSARI BHOWMICK | 0.54 | 0 | 0 | 100
873 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME , SM/09897 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of Birpara (APD) water supply scheme, TW no III under JJM under NMD-II, PHE Dte. APD | 991/NMD-II | 15/05/2023 | 30 | P K ENGINEERING | 10.95 | 0 | 0 | 80
874 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF SALSALABARI WATER SUPPLY SCHEME , SM/09907 | Augmentation | Construction of pumphouse, boundary wall,laying of UPVC pipeline & rising main connection for Salsalabari PWSS proposed 4th TW site PWSS under Alipurduar Division, PHE Dte. | 3400/ALD | 16/03/2023 | 90 | BRAJA GOPAL SAHA | 39.58 | 0 | 0 | 0
875 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF SALSALABARI WATER SUPPLY SCHEME , SM/09907 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Salsalabari Water Supply Scheme TW No.-III under NMD-II,PHE. Dte, Alipurduar. | 1377/NMD-II | 22/12/2021 | 30 | PRAGATI CONSTRUCTION COMPANY | 2.39 | 2.39 | 100 | 0
876 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF SALSALABARI WATER SUPPLY SCHEME , SM/09907 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector forGround Water Based Piped Water Supply Scheme AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME.,P/H-I (Aug) under Jal Jeevan Mission NMD-II,PHE.Dte,Alipurduar. | 1149/NMD-II | 16/05/2025 | 30 | SUBODH KUMAR BANIK | 11.29 | 0 | 0 | 0
877 | ALIPURDUAR | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Construction of Pump House,Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for NEWLANDS TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | 1307/ALD | 22/08/2022 | 120 | MADHAB SAHA | 97.2 | 91.59 | 94.23 | 94
878 | ALIPURDUAR | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Providing balance FHTC for NEWLAND TG PWSS under Alipurduar Division, PHE Dte. | 1792/ALD | 29/08/2023 | 60 | SUBHAK CHIK BARAIK | 13.39 | 0 | 0 | 0
879 | ALIPURDUAR | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Material Requisition To Resource Division | 188/ALD | 28/04/2023 | 0 | Resource Division | 18.72 | 0 | 0 | 0
880 | ALIPURDUAR | Northern Mechanical Division II | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Quotation for new service connection at Newland TG P/H No-II. Application No- 4003039064 | BP-104/22-23 | 19/12/2022 | 0 | WBSEDCL | 1.58 | 0 | 0 | 0
881 | ALIPURDUAR | Northern Mechanical Division II | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Quotation for new service connection at Newland TG P/H No-I. Application No- 4003039040 | BP-103/22-23 | 19/12/2022 | 0 | WBSEDCL | 1.58 | 0 | 0 | 0
882 | ALIPURDUAR | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.08.2022 to 31.10.2022) | 1122/ALD | 29/07/2022 | 92 | NIRANJAN KIRTANIA | 0.5 | 0 | 0 | 100
883 | ALIPURDUAR | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.11.2022 to 31.01.2023) | 2013/ALD | 28/10/2022 | 92 | NIRANJAN KIRTANIA | 0.7 | 0 | 0 | 100
884 | ALIPURDUAR | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.11.2022 to 31.01.2023) | 2014/ALD | 28/10/2022 | 92 | NIRANJAN KIRTANIA | 0.5 | 0 | 0 | 100
885 | ALIPURDUAR | Northern Mechanical Division II | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for New Land TG water supply scheme, TW no II in the district of Alipurduar under Northern Mechanical Division-II PHE Dte. APD. | 664/NMD-II | 24/03/2023 | 30 | SARKAR ELECTRIC | 10.46 | 0 | 0 | 90
886 | ALIPURDUAR | Northern Mechanical Division II | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for New Land TG water supply scheme, TW no I in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte. | 1254/NMD-II | 04/07/2023 | 30 | MALAY KUMAR SAHA | 10.44 | 0 | 0 | 90
887 | ALIPURDUAR | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Material Requisition To Resource Division | 4259/ALD | 13/12/2024 | 0 | Resource Division | 11.34 | 0 | 0 | 0
888 | ALIPURDUAR | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
889 | ALIPURDUAR | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Construction of Pump House,Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for NEWLANDS TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | 1275/ALD | 17/08/2022 | 501 | TAPASH KUMAR BHOWMICK | 96.78 | 63.79 | 65.91 | 95
890 | ALIPURDUAR | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Laying of Rising Main line with HDPE PN 10, bridge and culvert crossing, cons. Of pathway, surface drain and chatal, Installation of Paver block, land development along with the other allied works at Newlands TG H/W Site under Alipurduar Division, PHE Dte. | 391/ALD | 05/02/2024 | 450 | K S ENTERPRISE | 48.23 | 0 | 0 | 65
891 | ALIPURDUAR | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Construction of 250cum. OHR for Newlands TG Water Supply Scheme under Alipurduar Division, PHE Dte. | 975/ALD | 15/07/2022 | 1143 | TAPASH KUMAR BHOWMICK | 57.61 | 41.99 | 62.43 | 75
892 | ALIPURDUAR | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME , SM/11484 | New | Supply of CIDF & CISS Pipes and specials for New Land TG WSS Under Alipurduar Division P.H.E Dte. | 1593/ALD | 25/08/2023 | 631 | MADHAB SAHA | 6.76 | 0 | 0 | 100
893 | ALIPURDUAR | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Construction of Pump House,Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for SANKOSH TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | 1276/ALD | 17/08/2022 | 120 | SOUVIK ROY PALADHI | 96.66 | 90.94 | 94.08 | 50
894 | ALIPURDUAR | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for SANKOSH TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | 1277/ALD | 17/08/2022 | 120 | SOUVIK ROY PALADHI | 83.75 | 73.88 | 88.21 | 70
895 | ALIPURDUAR | Northern Mechanical Division II | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sankosh water supply scheme, TW no II under Northern Mechanical Division-II, PHEDte.Alipurduar. | 864/NMD-II | 26/04/2023 | 30 | KARMAKAR CONSTRUCTION | 10.74 | 0 | 0 | 90
896 | ALIPURDUAR | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Material Requisition To Resource Division | 1591/ALD | 14/09/2022 | 0 | Resource Division | 6.68 | 0 | 0 | 0
897 | ALIPURDUAR | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Material Requisition To Resource Division | 189/ALD | 28/04/2023 | 0 | Resource Division | 15.48 | 0 | 0 | 0
898 | ALIPURDUAR | Northern Mechanical Division II | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Quotation for new service connection at Sankosh TG P/H No-I. Application No- 4003039354 | BP-105/22-23 | 19/12/2022 | 0 | WBSEDCL | 1.58 | 0 | 0 | 0
899 | ALIPURDUAR | Northern Mechanical Division II | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Quotation for new service connection at Sankosh TG P/H No-II. Application No- 4003039376 | BP-106/22-23 | 19/12/2022 | 0 | WBSEDCL | 1.58 | 0 | 0 | 0
900 | ALIPURDUAR | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Construction of 250cum. OHR for Sankosh TG Water Supply Scheme under Alipurduar Division, PHE Dte. | 977/ALD | 15/07/2022 | 180 | SOUVIK ROY PALADHI | 57.62 | 0 | 0 | 80
901 | ALIPURDUAR | Northern Mechanical Division II | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sankosh water supply scheme, TW no I(H/W Site) under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 860/NMD-II | 26/04/2023 | 30 | SAIKAT SINHA | 10.76 | 0 | 0 | 100
902 | ALIPURDUAR | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Providing balance FHTC for SANKOSH TG PWSS under Alipurduar Division, PHE Dte. | 1790/ALD | 29/08/2023 | 533 | SOUVIK ROY PALADHI | 12.27 | 0 | 0 | 75
903 | ALIPURDUAR | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Laying of Rising Main line with HDPE PN 10, bridge and culvert crossing, cons. Of pathway, surface drain and chatal, Installation of Paver block, land development along with the other allied works at Sankosh TG H/W Site under Alipurduar Division, PHE Dte. | 390/ALD | 05/02/2024 | 450 | K S ENTERPRISE | 48.17 | 0 | 0 | 65
904 | ALIPURDUAR | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Laying of HDPE/DI Pipeline for filling up the gap & bridge / culvert crossing, specials repair with trial run of pipeline and allied works at Sankosh TG PWSS under Alipurduar Division, PHE Dte. | 209/ALD | 16/01/2024 | 450 | SOUVIK ROY PALADHI | 19.84 | 0 | 0 | 80
905 | ALIPURDUAR | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME , SM/11485 | New | Supply of CIDF & CISS Pipes and specials for Sankos TG WSS Under Alipurduar Division P.H.E Dte. | 1592/ALD | 25/08/2023 | 541 | SOUVIK ROY PALADHI | 6.76 | 0 | 0 | 100
906 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Quotation for new service connection at Hasimara W/SS Tw No-III Application No- 4002954503 |  | 02/08/2022 | 0 | WBSEDCL | 1.63 | 0 | 0 | 0
907 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Quotation for new service connection for HASIMARA W/SS T/W no. III , Application no. 4002954503 | BP-40/22-23 | 08/08/2022 | 0 | WBSEDCL | 1.63 | 0 | 0 | 0
908 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Quotation for new service connection at Hasimara W/SS Tw No-IV Application No- 4002954692 |  | 02/08/2022 | 0 | WBSEDCL | 1.63 | 0 | 0 | 0
909 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Quotation for new connection service connection at HASIMARA W/SS T/W no. IV ,Application no.4002954692 | BP-39/22-23 | 08/08/2022 | 0 | WBSEDCL | 1.63 | 0 | 0 | 0
910 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Laying of HDPE pipeline for Malangi Tea Garden Area within Hasimara Water Supply Scheme under Alipurduar Division, PHE Dte. | 2375/ALD | 31/01/2022 | 60 | MADHAB SAHA | 74.82 | 5.1 | 97.2 | 94
911 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Extension of pipeline from Malangi TW to Bharnobari TG area (booster line) under Hasimara PWSS at Kalchini Block under Alipurduar Division, PHE Dte. | 20/ALD | 01/04/2022 | 60 | AASHIRBAD ENTERPRISE | 14.64 | 0 | 0 | 50
912 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Supply, delivery & installation of 30 KVA, Servo Motor operated Copper wound line voltage stabilizer of Hasimara Water Supply scheme T/W No.III NMD-II, PHE. Dte, Alipurduar. | 408/NMD-II | 22/03/2022 | 30 | MAA TARA ENTERPRISE | 3.16 | 3.16 | 100 | 0
913 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Supply, delivery & installation of Electro Mechanical Compopnents at HASIMARA W/S Scheme, P/H No. I(Handedover), under NMD-II, PHE, Dte. in the dist of Alipurduar. | 243/AMSD | 29/07/2022 | 15 | S.K ELECTRICALS | 1.06 | 0 | 0 | 0
914 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | "Hiring of Motor Cab for site visit of the Assistant Engineer , Alipurduar Mechanical Sub- Division, P.H.E. Dte. under Northern Mechanical Division -II, P.H.E. Dte." | 202/AMSD | 28/07/2023 | 366 | DILIP MAHATO | 4.16 | 0 | 0 | 0
915 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Extension of pipeline from Santali TG connection line to upper line of Madhu TG area (booster line) under Hasimara TG PWSS at Kalchini Block under Alipurduar Division, PHE Dte. | 19/ALD | 01/04/2022 | 60 | AASHIRBAD ENTERPRISE | 12.61 | 0 | 0 | 49
916 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Hasimara Water Supply Scheme TW No.-III under NMD-II,PHE Dte Alipurduar. | 534/NMD-II | 20/04/2022 | 30 | M/S RATAN KUMAR DASGUPTA & CO. | 8.46 | 7.95 | 93.92 | 100
917 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Construction of valve chamber, dismantling concrete road and other misc works at Malangi TG area within Hasimara W/S/S under Alipurduar Division, PHE Dte. | 442/ALD | 13/05/2022 | 30 | MADHAB SAHA | 4.9 | 0 | 0 | 49
918 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Hasimara Water Supply Scheme TW No.-IV under NMD-II PHE Dte Alipurduar. | 595/NMD-II | 05/05/2022 | 30 | M/S B ENTERPRISE | 8.49 | 7.98 | 93.93 | 100
919 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Supply, delivery & installation of 30 KVA, Servo Motor operated Copper wound line voltage stabilizer of HASIMARA Water Supply Scheme TW No.- IV under NMD-II, PHE. Dte. | 400/NMD-II | 22/03/2022 | 30 | M/S A.D. ENTERPRISE | 3.17 | 3.17 | 100 | 0
920 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of HASIMARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 1992/ALD | 27/12/2021 | 90 | MAHENDRA CHHETRI | 42.03 | 0 | 0 | 49
921 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Material Requisition To Resource Division | 717/ALD | 13/06/2022 | 0 | Resource Division | 49.83 | 0 | 0 | 0
922 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Construction of HP Culvert for drainage purpose with 900 mm dia humepipe and construction of screening and inspection chamber at Hasimara PWSS HWS under Alipurduar Division PHE Dte.,Part-B | 1105/ALD | 29/07/2022 | 30 | ALATYA CONSTRUCTION & CO. | 3.6 | 0 | 0 | 100
923 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Construction of HP Culvert for drainage purpose with 900 mm dia humepipe and construction of screening and inspection chamber at Hasimara PWSS HWS under Alipurduar Division PHE Dte., Part-C | 1106/ALD | 29/07/2022 | 30 | ALATYA CONSTRUCTION & CO. | 4.08 | 0 | 0 | 100
924 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Material Requisition To Resource Division | 107/ALD | 10/01/2024 | 0 | Resource Division | 12.32 | 0 | 0 | 0
925 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME , SM/09887 | Augmentation | Laying of DI pipe and connection with Tubewell, Construction of Pathway, Fencing work and other works at Malangi TG Pump House under Alipurduar Division, PHE Dte. | 1110/ALD | 29/07/2022 | 990 | MAHENDRA CHHETRI | 4.99 | 0 | 0 | 100
926 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME , SM/10155 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Totpara WSS under Alipurduar Division, PHE Dte. | 1852/ALD | 13/12/2021 | 30 | HARI CONSTRUCTION | 5.04 | 5.04 | 100 | 96
927 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME , SM/10155 | Augmentation | Restoration of Laying Distribution system by replacing damaged AC pipeline with DI and UPVC pipe for TATPARA WSS under Alipurduar Division, PHE Dte. (Part-B) | 3003/ALD | 15/03/2022 | 60 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 39.2 | 37.8 | 52.02 | 98
928 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME , SM/10155 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Totpara Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 704/ALD | 08/06/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.92 | 4.92 | 50 | 99
929 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME , SM/10155 | Augmentation | Laying Distribution pipe with DI pipe with pillar of TATPARA WSS under Alipurduar Division, PHE Dte. | 3106/ALD | 24/03/2022 | 60 | HARI CONSTRUCTION | 7.06 | 6.94 | 50 | 98
930 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME , SM/10155 | Augmentation | Construction of 250cum OHR for TATPARA Piped Water Supply Scheme under Alipurduar Division, PHE Dte. | 2749/ALD | 24/02/2022 | 180 | M/S DUTTA AND CO | 57.62 | 42.05 | 49.58 | 99
931 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME , SM/10155 | Augmentation | Repairing and renovation of 2 nos. pump house, boundary wall (H/W Site, 2nd site), Pathway, Cons. Of 2 nos New Toilet and restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipe at Totpara Water Supply Scheme under Alipurduatr Division, PHE Dte. | 1579/ALD | 22/11/2021 | 1200 | NARENDRA BHADANI. | 22.78 | 19.7 | 87.77 | 100
932 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME , SM/10155 | Augmentation | Repairing and renovation of 2 nos. pump house, boundary wall (H/W Site, 2nd site), Pathway, Cons. Of 2 nos New Toilet and restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipe at Totpara Water Supply Scheme under Alipurduatr Division, PHE Dte. | 1580/ALD | 22/11/2021 | 1200 | SASANKA ROY | 22.78 | 20.11 | 96.19 | 100
933 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME , SM/11401 | Augmentation | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | 1009/ALD | 12/11/2020 | 60 | M/S PALIT ENTERPRISE | 14.4 | 0.28 | 50 | 70
934 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME , SM/11401 | Augmentation | Supply & delivery,of Electro mechanical components at Patlakhawa Water Supply Scheme,TW-I in the dist of ALIPURDUAR under NMD-II,PHE.Dte,Alipurduar. | 632/AMSD | 03/03/2022 | 15 | MADHAB SAHA | 2.35 | 2.35 | 100 | 68
935 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME , SM/11401 | Augmentation | Providing House connection and extension of pipe line for Silbarihat area within PATLAKHAWA PWSS under Alipurduar Division PHE Dte. | 879/ALD | 03/09/2021 | 60 | TAPASH KUMAR BHOWMICK | 45.7 | 12.33 | 100 | 76
936 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME , SM/11401 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Silbarihat under Patlakhawa PWSS. | 2766/ALD | 25/02/2022 | 60 | TAPASH KUMAR BHOWMICK | 42.34 | 30.19 | 100 | 75
937 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME , SM/11401 | Augmentation | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | 1008/ALD | 12/11/2020 | 60 | JAI BHARAT COMMERCIAL CORPORATION | 14.4 | 0.25 | 100 | 100
938 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME , SM/11401 | Augmentation | Quotation for new service connection at PATLAKHAWA w/s scheme T/W no. III, Application no. 4003028004 |  | 30/11/2022 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
939 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME , SM/11401 | Augmentation | Quotation for new service connection at Patlakhawa P/H No- III, Application NO- 4003028004 | BP-97/22-23 | 02/12/2022 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
940 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME , SM/11401 | Augmentation | Laying of Different Dia pipeline And providing FHTC For Patlakhowa and Adjoining area under Patlakhowa PWSS at Alipurduar-I Block under Alipurduar Division, PHE Dte. | 919/ALD | 07/07/2022 | 45 | M/S DUTTA AND CO | 72.26 | 40.46 | 55.99 | 70
941 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME , SM/11401 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with cu wound line voltage corrector for Augmentation of PATLAKHAWA Water Supply Scheme,TW no .I under NMD-II, PHE Dte. Apd. | 968/NMD-II | 13/05/2023 | 30 | SUMON ELECTRICAL | 11.02 | 10.34 | 94.99 | 100
942 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME , SM/11401 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of Patlakhawa Piped Water Supply Scheme | 1331/ALD | 24/08/2022 | 60 | UTTAM SAHA | 29.37 | 28.52 | 97.1 | 97
943 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11960 | Augmentation | Soil investigation work for proposed overhead reservoir, cons. Of 150cum OHR at Dalmore, 2nos. Of TW boring by ODEX-165 method of drilling at Dalmore and Ramjhora, cons. of pump house and boundary wall at both TW site, LDS as per Departmental Design & drawing for DALMORE & RAMJHORA TG PWSS under Birpara Sub-Division, Alipurduar Division PHE DTE. | 638/ALD | 06/06/2023 | 180 | SUKAMAL GHOSH | 158.82 | 0 | 0 | 0
944 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11960 | Augmentation | Providing FHTC from existing distribution system as per specification for DALMORE RAMJHORA PWSS under Alipurduar Division, PHE Dte. | 2024/ALD | 19/09/2023 | 60 | SUDDHYA SING LAMA | 23.76 | 0 | 0 | 0
945 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11960 | Augmentation | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | 2732/ALD | 30/12/2022 | 365 | PARITOSH SUTRADHAR | 4.8 | 2.3 | 100 | 90
946 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11960 | Augmentation | Soil investigation work for proposed overhead reservoir , Constructions of 150 Cum OHR at HW site and providing FHTC as per Departmental Design & drawing for Ramjhora PWSS Under Birpara Sub-division, Alipurduar Division PHE DTE. | 2661/ALD | 22/12/2022 | 600 | SUDDHYA SING LAMA | 91.76 | 56.93 | 63.29 | 90
947 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11960 | Augmentation | Material Requisition To Resource Division | 3610/ALD | 24/10/2024 | 0 | Resource Division | 11.11 | 0 | 0 | 0
948 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11960 | Augmentation | New Service Connection Charges for Dalmore & Ramjhora TG PH NO-IV | BP-412/24-25 | 20/11/2024 | 0 | WBSEDCL | 6.75 | 0 | 0 | 0
949 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11960 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR DALMORE& RAMJHORA T.G P/H NO-V PWSS | BP-2023-24-550 | 18/01/2024 | 0 | WBSEDCL | 5.99 | 0 | 0 | 0
950 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11960 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME,TW No.- I of Zone-I AND II under NMD-II,PHE.Dte,Alipurduar. | 2968/NMD-II | 21/11/2023 | 469 | B.B CONCERNED | 28.76 | 0 | 0 | 90
951 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11960 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
952 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11960 | Augmentation | Laying of additional HDPE pipeline at Ramjhora TG under Ranjhora WSS under Alipurduar Division, PHE Dte. | 1536/ALD | 29/07/2025 | 45 | SUNIL HAJANG THAKUR | 13.14 | 0 | 0 | 0
953 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) , SM/07137 | Retrofitting | Laying of UPVC/DI/MS Distribution pipe line and FHTC in connection with Jaldhara Jal Sapna and other misc work for Dalimpur WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 1178/ALD | 15/12/2020 | 60 | M/S PALIT ENTERPRISE | 45.48 | 54.37 | 119.54 | 86
954 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) , SM/07137 | Retrofitting | Extension of pipeline and connection with main line by UPVC, GI, DI pipe and construction of valve chamberand others at Bhutnirghat WSS under Alipurduar Division, PHE Dte. | 342/ALD | 02/05/2022 | 45 | DILIP MAHATO | 25.7 | 0.68 | 100 | 92
955 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) , SM/07137 | Retrofitting | Providing House connection for DALIMPUR water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. | 866/ALD | 14/10/2020 | 30 | SANJIT SAHA | 4.93 | 4.93 | 50 | 88
956 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) , SM/07137 | Retrofitting | Providing House connection for Dalimpur water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte.(Part-II) | 1134/ALD | 10/12/2020 | 30 | PARAMJYOTI ENTERPRISE | 4.98 | 4.98 | 50 | 85
957 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) , SM/07137 | Retrofitting | Laying of UPVC/DI/MS Distribution pipe line and FHTC in connection with Jaldhara Jal Sapna and other misc work for Dalimpur WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte.(under Jateswar-I GP area) | 1179/ALD | 15/12/2020 | 60 | NARAYAN CHANDRA SAHA | 45.66 | 21.5 | 55.59 | 0
958 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) , SM/07137 | Retrofitting | Extension of Distribution line with UPVC pipe line (From B.Ed College to Pulin Biswas House) under Dalimpur Water Supply Scheme under Alipurduar Division,PHE Dte. | 878/ALD | 14/10/2020 | 30 | NARAYAN CHANDRA SAHA | 3.14 | 5.95 | 100 | 0
959 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) , SM/07137 | Retrofitting | Extension of Distribution line with UPVC pipe line (From Pulin Biswas House to Bipul Islam House) under Dalimpur Water Supply Scheme under Alipurduar Division,PHE Dte. | 879/ALD | 14/10/2020 | 30 | PARAMJYOTI ENTERPRISE | 3.14 | 5.94 | 100 | 0
960 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) , SM/07137 | Retrofitting | Extension of Distribution line with UPVC pipe line (From Bhaben Biswas House to Ghughurertala Hridoy Barman's House) at Deodanga under Dalimpur Water Supply Scheme under Alipurduar Division,PHE Dte. | 918/ALD | 16/10/2020 | 30 | PARAMJYOTI ENTERPRISE | 3.16 | 5.96 | 100 | 0
961 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) , SM/07137 | Retrofitting | Preparation of Augmentation D.P.R after investigation For Dalimpur W/S scheme under Alipurduar Division. | 920/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.18 | 4.37 | 100 | 0
962 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) , SM/07137 | Retrofitting | Extension of Distribution line with UPVC pipe line (From Bamoner Bhangha Nagesh barman's House to Kashikanta Biswas House) near Bulet Club under Dalimpur Water Supply Scheme under Alipurduar Division,PHE Dte. | 919/ALD | 16/10/2020 | 30 | NARAYAN CHANDRA SAHA & SONS | 3.16 | 5.99 | 100 | 0
963 | ALIPURDUAR | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | Providing FHTC from existing distribution system as per specification for Rangamati TG PWSS under Alipurduar Division, PHE Dte. | 1880/ALD | 07/09/2023 | 30 | ASHOK PRADHAN | 9.49 | 0 | 0 | 0
964 | ALIPURDUAR | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | Material Requisition To Resource Division | 104/ALD | 10/01/2024 | 0 | Resource Division | 9.73 | 0 | 0 | 0
965 | ALIPURDUAR | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | Material Requisition To Resource Division | 3953/ALD | 26/11/2024 | 0 | Resource Division | 13.97 | 0 | 0 | 0
966 | ALIPURDUAR | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | New Service Connection for Rangamati PWSS, Zone-II, P/H no.-I | BP-2023-24-524 | 11/01/2024 | 0 | WBSEDCL | 5.58 | 0 | 0 | 0
967 | ALIPURDUAR | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | Hydro-Geologica! investigation aboutWater evaluation, availability and quality parameterfor both ground and surface sources at Lankapara and Gentral Dooars Tea Estate within Alipuduar district. | 429/23-24/PFMS | 28/03/2024 | 0 | IIT CONSULTATIVE PRACTICE | 2.36 | 0 | 0 | 0
968 | ALIPURDUAR | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | New Service connection for Rangamati TG PWSS, Zone-I, P/H-I | BP-2023-24-526 | 11/01/2024 | 0 | WBSEDCL | 6.39 | 0 | 0 | 0
969 | ALIPURDUAR | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | New Service Connection for Rangamati TG PWSS, Zone-II, P/H no.-II | BP-2023-24-527 | 11/01/2024 | 0 | WBSEDCL | 6.97 | 0 | 0 | 0
970 | ALIPURDUAR | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | New Service Connection for Rangamati TG PWSS, Zone-I, P/H-II | BP-2023-24-525 | 11/01/2024 | 0 | WBSEDCL | 5.22 | 0 | 0 | 0
971 | ALIPURDUAR | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | Constructions of 2(TWO) NOS 150 Cum OHR as per Departmental Design & drawing including laying distribution system with new HDPE pipeline, RISING MAIN, Construction of BOUNDARY WALL, 4(FOUR) NOS ODEX-165 TUBE WELL, 4(FOUR) NOS PUMP HOUSE, Soil Investigation work, providing FHTC and others allied works for RANGAMATI TEA GAEDEN PWSS(ZONE-I+ZONE-II), Alipurduar Division, PHE DTE. | 1171/ALD | 03/08/2023 | 720 | M/S RADHASWAMI ENTERPRISE | 440.2 | 0 | 0 | 40
972 | ALIPURDUAR | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
973 | ALIPURDUAR | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
974 | ALIPURDUAR | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1331/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
975 | ALIPURDUAR | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | Supply of DIDF pipes and specials and Sluice Valve for Rangamati TG Water Supply Scheme (SM/14213) of Kalchini Block under Alipurduar Division P.H.E. Dte. | 839/ALD | 14/03/2024 | 360 | SSPR VALVE MANUFACTURING PVT LTD | 16.24 | 0 | 0 | 15
976 | ALIPURDUAR | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14213 | New | Sinking of 1nos Big dia Tubewell (250 x 200 x 150 mm dia) by modified DTH-ODEX of drilling for Rangamati Zone-II PWSS site within Kalchini Block under Alipurduar Division, PHE Dte. | 4592/ALD | 03/01/2025 | 88 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 24.05 | 0 | 0 | 100
977 | ALIPURDUAR | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME , SM/15208 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Dhanirampur Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | 2473/NMD-II | 11/08/2023 | 508 | SARKAR ELECTRIC | 21.08 | 0 | 0 | 60
978 | ALIPURDUAR | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME , SM/15208 | New | Laying of rising main, delivery main, bypass arrangement, Laying of HDPE Pipeline for left out household connection and other allied works at Dhanirampur PWSS (both H/W and 2nd site) of Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. (SM/15208) | 829/ALD | 14/03/2024 | 45 | DILIP MAHATO | 58.7 | 0 | 0 | 70
979 | ALIPURDUAR | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME , SM/15208 | New | Supply of DIDF pipes and DI specials and CI Jeffy Coupling for Dhanirampur Water Supply Scheme (SM/15208) of Falakata Block under Alipurduar Division P.H.E. Dte. | 838/ALD | 14/03/2024 | 30 | BARMAN ENTERPRISE | 9.78 | 0 | 0 | 90
980 | ALIPURDUAR | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME , SM/15208 | New | Material Requisition To Resource Division | 119/ALD | 10/01/2024 | 0 | Resource Division | 9.56 | 0 | 0 | 0
981 | ALIPURDUAR | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME , SM/15208 | New | NEW SERVICE CONNECTION CHARGES FOR DHANIRAMPURPH NO-I | BP-2023-24-691 | 14/03/2024 | 0 | WBSEDCL | 4.08 | 0 | 0 | 0
982 | ALIPURDUAR | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME , SM/15208 | New | NEW SERVICE CONNECTION CHARGE DHANIRAMPUR PH NO-II | BP-2023-24-693 | 14/03/2024 | 0 | WBSEDCL | 5.85 | 0 | 0 | 0
983 | ALIPURDUAR | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME , SM/15208 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , Soil investigation at OHR site, constructions of 250 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for DHANIRAMPUR PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 3636/ALD | 31/03/2023 | 900 | DILIP MAHATO | 457.51 | 133.71 | 29.23 | 95
984 | ALIPURDUAR | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME , SM/15208 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM DEOGAON and others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1385/NMD-II | 26/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 20.56 | 0 | 0 | 0
985 | ALIPURDUAR | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME , SM/15208 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1344/NMD-II | 19/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
986 | ALIPURDUAR | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME , SM/15208 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
987 | ALIPURDUAR | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME , SM/15208 | New | Laying of HDPE pipeline (left out ) at Dhanirampur PWSS under Alipurduar Division, PHE Dte. | 1626/ALD | 04/08/2025 | 60 | DILIP MAHATO | 30.28 | 0 | 0 | 0
988 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF SIDHABARI PIPED WATER SUPPLY SCHEME , SM/16115 | Augmentation | Laying of HDPE and distribution pipes in different suitable locations of Sidhabari PWSS under Alipurduar Division, PHE Dte. | 2970/ALD | 31/01/2023 | 90 | BILTU DAS | 165.16 | 0 | 0 | 61
989 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF SIDHABARI PIPED WATER SUPPLY SCHEME , SM/16115 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
990 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF SIDHABARI PIPED WATER SUPPLY SCHEME , SM/16115 | Augmentation | Replacement of damaged pipeline with HDPE pipes for Sidhabari PWSS under Alipurduar Division, PHE Dte. | 974/ALD | 12/06/2025 | 60 | SANKAR ROY | 8.53 | 0 | 0 | 0
991 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Material Requisition To Resource Division | 186/ALD | 28/04/2023 | 0 | Resource Division | 246.11 | 0 | 0 | 0
992 | ALIPURDUAR | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PURBA NARTHALI PWSS PH NO-I | BP-2023-24-49 | 12/05/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
993 | ALIPURDUAR | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PURBA NARTHALI PWSS PH NO-II | BP-2023-24-48 | 12/05/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
994 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at PURBA NARATHALI HW site PWSS under Alipurduar Division, PHE Dte. | 87/ALD | 10/01/2024 | 90 | MADHAB SAHA | 34.86 | 0 | 0 | 45
995 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Supply of DI specials and CI Jeffy coupling for Purba Narathali Water Supply Scheme(SM/16537) of Kumargram Block under Alipurduar Division P.H.E. Dte. | 833/ALD | 14/03/2024 | 30 | DILIP MAHATO | 13.51 | 0 | 0 | 0
996 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Laying of new UPVC/DI pipeline for interconnection in the distribution system, fixing of FHTC by means of PCC Concrete Block and others allied works in connection with the Purba Narathali (SM/16537) PWSS under Alipurduar Division, PHE Dte. | 3418/ALD | 26/09/2024 | 60 | MADHAB SAHA | 57.8 | 0 | 0 | 0
997 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Supply of CIDF Specials and Jeffy Coupling for Purba Narathali (SM/16537) WSS under Alipurduar Division, PHE Dte. | 4266/ALD | 13/12/2024 | 30 | HITANGSHU CHOUDHURY | 19.67 | 0 | 0 | 0
998 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Land Development, repairing of Pump house, construction of Pathway and protection work of 3rd TW site of Narathali PWSS under Alipurduar Divn, PHE Dte. | 2520/ALD | 24/11/2023 | 60 | SREE MAA CONSTRUCTION | 6.99 | 0 | 0 | 100
999 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Repairing of HW site boundary wall (40M), construction of pathway, surface drain, chatal and other misc works related to Narathali PWSS under Alipurduar Division, PHE Dte. | 2524/ALD | 24/11/2023 | 60 | TAPAN CHANDA | 5.33 | 0 | 0 | 100
1000 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Material Requisition To Resource Division | 26/ALD | 10/01/2024 | 0 | Resource Division | 10.95 | 0 | 0 | 0
1001 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Material Requisition To Resource Division | 4267/ALD | 13/12/2024 | 0 | Resource Division | 13.19 | 0 | 0 | 0
1002 | ALIPURDUAR | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | ADDITIONAL QUOTATION FOR PURBA NARARTHALI PH NO-2 | BP-05/24-25 | 08/04/2024 | 0 | WBSEDCL | 12.74 | 0 | 0 | 0
1003 | ALIPURDUAR | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | ADDITIONAL QUOTATION FOR PURBA NARARTHALI PH NO-I | BP-04/24-25 | 08/04/2024 | 0 | WBSEDCL | 2.27 | 0 | 0 | 0
1004 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
1005 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Constructions of pump house & Tube well Boring by ODEX-165 Method of drilling at HW site & 2nd site , laying of distribution system with UPVC pipeline including rising main & delivery connection, Constructions of 250 Cum OHR as per Departmental Design & drawing along with the Soil investigation works , providing FHTC and others allied works for Purba Narathali PWSS Under Alipurduar Division PHE DTE. | 3573ALD | 27/03/2023 | 1011 | MADHAB SAHA | 373.15 | 203.35 | 54.49 | 5
1006 | ALIPURDUAR | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Solarization of grid connected pumping installation at Different PWSS at Kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 820/NMD-II | 06/03/2025 | 30 | WATER TECH | 29.68 | 0 | 0 | 0
1007 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1008 | ALIPURDUAR | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1009 | ALIPURDUAR | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Laying Rising Main and delivery main connection along with laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing and other allied works for Nararthali PWSS adjacent to Purba Narathali WSS under Alipurduar Division, PHE Dte. | 819/ALD | 03/06/2025 | 90 | NARAYANIMAA EXIM PVT. LTD. | 32.53 | 0 | 0 | 0
1010 | ALIPURDUAR | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. , SM/16537 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Purba Narthali Water Supply Scheme TW No.- I and,II under NMD-II,PHE.Dte,APD. | 2693/NMD-II | 14/09/2023 | 849 | P K ENGINEERING | 21.75 | 0 | 0 | 100
1011 | ALIPURDUAR | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | Supply of CIDF & CISS Pipes and specials for Uttar Majidkhana WSS Under Alipurduar Division P.H.E Dte. | 1606/ALD | 25/08/2023 | 30 | TAPASH KUMAR BHOWMICK | 7.89 | 7.88 | 100 | 100
1012 | ALIPURDUAR | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | Material Requisition To Resource Division | 223/ALD | 03/05/2023 | 0 | Resource Division | 16.73 | 0 | 0 | 0
1013 | ALIPURDUAR | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | Material Requisition To Resource Division | 2396/ALD | 08/11/2023 | 0 | Resource Division | 11.63 | 0 | 0 | 0
1014 | ALIPURDUAR | Northern Mechanical Division II | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | New Service Connection at Uttar Masjidkhana P/H No.I | BP-2023-24-337 | 27/09/2023 | 0 | WBSEDCL | 6.58 | 0 | 0 | 0
1015 | ALIPURDUAR | Northern Mechanical Division II | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | New service connection charge for Uttar majidkhana p/h-II | BP-2023-24-472 | 12/12/2023 | 0 | WBSEDCL | 6.2 | 0 | 0 | 0
1016 | ALIPURDUAR | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | Continuation order of "Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte." | 314/ALD | 25/01/2024 | 180 | TAPASH KUMAR BHOWMICK | 4.29 | 0 | 0 | 100
1017 | ALIPURDUAR | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | Continuation order of "Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (in soft copy) to PHE Dte. PART-B" | 313/ALD | 25/01/2024 | 180 | TAPASH KUMAR BHOWMICK | 4.67 | 0 | 0 | 100
1018 | ALIPURDUAR | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | Material Requisition To Resource Division | 4275/ALD | 13/12/2024 | 0 | Resource Division | 26.21 | 0 | 0 | 0
1019 | ALIPURDUAR | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
1020 | ALIPURDUAR | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | CONS of PH and Sinking of 250 mm x 200 mm X 150 mtr Big dia TW at HW site and 2nd site , LDS with UPVC P/LINE , CONS of 200 Cum OHR , incl the Soil investigation works, providing FHTC and others allied works for Uttar Majidkhana PWSS Under Alipurduar Division PHE DTE. | 3416/ALD | 17/03/2023 | 925 | TAPASH KUMAR BHOWMICK | 490.21 | 233.92 | 47.72 | 95
1021 | ALIPURDUAR | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | Providing balance FHTC for UTTAR MAJIDKHANA PWSSunder Alipurduar Division, PHE Dte. | 1567/ALD | 23/08/2023 | 225 | TAPASH KUMAR BHOWMICK | 9.36 | 0 | 0 | 0
1022 | ALIPURDUAR | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1023 | ALIPURDUAR | Northern Mechanical Division II | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | Solarization of grid connected pumping installation at Different PWSS at APD-I ,APD-II , Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1333/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
1024 | ALIPURDUAR | Northern Mechanical Division II | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1025 | ALIPURDUAR | Northern Mechanical Division II | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME , SM/16538 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR MAJIDKHANA water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | 2167/NMD-II | 27/07/2023 | 615 | MALAY KUMAR SAHA | 21.13 | 0 | 0 | 90
1026 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Construction of 200cum OHR as per departmental design and drawing, providing FHTC for 28 and 29 mile Busty PWSS under Alipurduar Division, PHE Dte. | 05/ALD | 04/04/2023 | 180 | A B TECHNO ENTERPRISE | 91.25 | 0 | 0 | 0
1027 | ALIPURDUAR | Northern Mechanical Division II | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Rejuvention of 28 AND 29 MILE BASTI Water Supply Scheme TW No.- I and II under NMD-II,PHE.Dte,Apd. | 2543/NMD-II | 16/08/2023 | 30 | DILIP MAHATO | 22.96 | 0 | 0 | 0
1028 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Providing balance FHTC from existing distribution system as per specification for 28 and 29 MILE BASTY PWSS under Alipurduar Division, PHE Dte. | 2103/ALD | 29/09/2023 | 60 | EVEREST INFRATECH INC | 47.79 | 0 | 0 | 0
1029 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Laying distribution system with new UPVC pipeline, Construction of 2 Nos Pump House ,Pipe Support Structure, Land Development, Boundary Wall, Path way, Providing FHTC, and other allied works for Gram Busty Area Under 28 & 29 Mile Basty (Zone-IV) PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | 2608/ALD | 04/12/2023 | 270 | HITANGSHU CHOUDHURY | 70.82 | 0 | 0 | 45
1030 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Hiring of additional Diesel Vehicle Maxi Cab (At least 7 seater) for Assistant Engineer, Head Quarter, Alipurduar Division, P.H.E. Dte. | 3883/ALD | 22/11/2024 | 365 | SOUVIK ROY PALADHI | 4.8 | 0 | 0 | 0
1031 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Arrangement for online application in Paribesh Portal for getting Forest permission at 7nos BOPs under Alipurduar Division P.H.E Dte. | 496/ALD | 16/02/2024 | 30 | HILL GROUND CONSULTANCY | 1.83 | 0 | 0 | 100
1032 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Conceptualization, design and implementing mass awareness generation through Wall writing at 113 nos. villages (Block - Falakata, Kalchini, Madarihat) by dissemination of awareness generation IEC messages FHTC, Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation and WASH related issues as per guideline of JJM at Alipurduar district under Alipurduar Division, PHE Dte, Govt. of West Bengal.(SM/16506) | 751/ALD | 12/03/2024 | 130 | LIMRA SOCIAL WELFARE SOCIETY | 27.08 | 0 | 0 | 100
1033 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Material Requisition To Resource Division | 98/ALD | 10/01/2024 | 0 | Resource Division | 10.79 | 0 | 0 | 0
1034 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Material Requisition To Resource Division | 4251/ALD | 13/12/2024 | 0 | Resource Division | 31.69 | 0 | 0 | 0
1035 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | payment against proposal No : FP/WB/Others/443310/2023for boundary demarcation and construction of boundary pillar for diversion of forest land of area 0.0464 ha for 28 and 29 mile basty PWSS ( Z-IV) Garam basty under JJM at garam basty forest Village under BTR ( West) Division under WDPO Range . | 144/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.94 | 0 | 0 | 0
1036 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Payment against proposal no . FP/ WB/ Others/ 442029/2023- for erection of Boundary pillar at diverted site against In - principal ( stage - I ) approval of water supply scheme for Buxa Forest PWSS uder Jal Jeevan Mission at 28 & 29 Mile Basty , Buxa tiger Reserve ( East) Division - reg |  | 18/09/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.21 | 0 | 0 | 0
1037 | ALIPURDUAR | Northern Mechanical Division II | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | New Service Connection Charges for REJUVINATION OF 28 & 29 Mile Basti PH NO-2 | BP-120/24-25 | 24/05/2024 | 0 | WBSEDCL | 8.22 | 0 | 0 | 0
1038 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | payment for NPV Demand Note against In-principal (Stage-l) approval of Central Government under Section 2 (1) (ii) of the Van (Sanrakshan Evam Samvardhan) Adhiniyam-1980 for non-forestry use of 0.1458 ha. of forest land in favour of West Bengal Public Health Engineering Directorate for Gravity Based Water Supply Scheme (GBWSS) under Jal Jeevan Mission (JJM) 28 & 29 Mile Basty PWSS under Buxa Tiger Reserve (East) Forest Division. (Proposal No. FPWBIOTHERSI442029/2023). | 147/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 15.59 | 0 | 0 | 0
1039 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Cost of raising and maintenance of the compensatory afforestation ( 100 trees plantation and mtc for 10 years ) against proposed diversion of forest land for 28 and 29 mile basty PWSS (Z-IV) Garam Basty under JJM against Proposal No : FP/WB/Others/443310/2023 | 146/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0 | 0
1040 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Payment for NPV for diversion of forest land of 0.0464 ha area against proposal No : FP/WB/Others/443310/2023 for water supply scheme 28 and 29 Mile Basty PWSS ( Z-VI) Garam Basty under JJM Garam Basty Forest Village under BTR(West ) Division under WDPO Range under DPO_9 Compartment | 145/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 5.18 | 0 | 0 | 0
1041 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Payment against proposal no . FP/ WB/ Others/ 442029/2023- for erection of Boundary pillar at diverted site against In - principal ( stage - I ) approval of water supply scheme for Buxa Forest PWSS uder Jal Jeevan Mission at 28 & 29 Mile Basty , Buxa tiger Reserve ( East) Division - reg | 329/24-25/PFMS | 19/12/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.31 | 0 | 0 | 0
1042 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Cost of raising and maintenance of the Compensatory Afforestation demand note against In-principal (Stage-l) approval of Central Government under Section 2 (1) (ü) of the Van (Sanrakshan Evam Samvardhan) Adhiniyam-1980 for Directorate non-forestry use of 0.1458 ha. of forest land in favour of West Bengal Public Health Engineering for Gravity Based Water Supply Scheme (GBWSS) under Jal Jeevan Mission (JJM) 28 & 29 Mile Basty PWSS under Buxa Tiger Reserve (East) Forest Division. (Proposal No. FPWBIOTHERS/442029/2023 | 148/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0 | 0
1043 | ALIPURDUAR | Northern Mechanical Division II | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | New Service Connection Charges For Rejuvination of 28 & 29 Mile Basti PWSS PH NO-1 | BP-119/24-25 | 24/05/2024 | 0 | WBSEDCL | 3.9 | 0 | 0 | 0
1044 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Construction of 2nos Tw boring by ODEX-165 method of drilling including distribution system with new UPVC pipeline, 2 nos Pump house, Boundary wall, pathway, providing FHTC and other allied works for 28 and 29 mile busty PWSS under Alipurduar Division, PHE Dte. | 3502/ALD | 23/03/2023 | 600 | HITANGSHU CHOUDHURY | 76.18 | 0 | 0 | 80
1045 | ALIPURDUAR | Northern Mechanical Division II | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 823/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
1046 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1047 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kalchini Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1052/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
1048 | ALIPURDUAR | Northern Mechanical Division II | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1049 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Continuation of work of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Head Quarter, Alipurduar Division, P.H.E. Dte.(from 01.01.2025 to 31.03.2025) | 4553/ALD | 30/12/2024 | 90 | DIPAK DAS | 1.2 | 0 | 0 | 0
1050 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Continuation of work of Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 01.01.2025 to 31.03.2025) | 4552/ALD | 30/12/2024 | 90 | APSARI BHOWMICK | 1.2 | 0 | 0 | 0
1051 | ALIPURDUAR | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME , SM/16506 | New | Cons. of 100 cum OHR,BOUNDARY WALL, PUMP HOUSE, TUBE, RISING MAIN FOR Mouza-MUJNAI TEA GARDEN(JL NO.39,RL Plot No.121,129 &155) 410 unit CHA SUNDARI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION, PHE DTE. of North Bengal Circle-I, PHE Dte. | 436/ALD | 07/02/2024 | 660 | MITHUN DAS | 108.05 | 0 | 0 | 80
1052 | ALIPURDUAR | Northern Mechanical Division II | Implementation of Affordable IoT System at Rahimabad TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. , SM/16916 | IOT | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Different Block of Alipurduar and Coochbehar District in West Bengal | 807/NMD-II | 04/03/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 594.37 | 0 | 0 | 0
1053 | ALIPURDUAR | Northern Mechanical Division II | Implementation of Affordable IOT System at Dima TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. , SM/16909 | IOT | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Different Block of Alipurduar and Coochbehar District in West Bengal | 807/NMD-II | 04/03/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 594.37 | 0 | 0 | 0
1054 | ALIPURDUAR | Alipurduar Division | NARASINGPUR PIPED WATER SUPPLY SCHEME , SM/15758 | New | Material Requisition To Resource Division | 1480/ALD | 16/08/2023 | 0 | Resource Division | 21.43 | 0 | 0 | 0
1055 | ALIPURDUAR | Alipurduar Division | NARASINGPUR PIPED WATER SUPPLY SCHEME , SM/15758 | New | Material Requisition To Resource Division | 2774 | 18/12/2023 | 0 | Resource Division | 15.16 | 0 | 0 | 0
1056 | ALIPURDUAR | Alipurduar Division | NARASINGPUR PIPED WATER SUPPLY SCHEME , SM/15758 | New | Material Requisition To Resource Division | 2774/ALD | 18/12/2023 | 0 | Resource Division | 15.16 | 0 | 0 | 0
1057 | ALIPURDUAR | Northern Mechanical Division II | NARASINGPUR PIPED WATER SUPPLY SCHEME , SM/15758 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Narsingpur Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | 2474/NMD-II | 11/08/2023 | 541 | SUMON ELECTRICAL | 21.78 | 0 | 0 | 90
1058 | ALIPURDUAR | Alipurduar Division | NARASINGPUR PIPED WATER SUPPLY SCHEME , SM/15758 | New | Rising Main, Laying of DI (K7), gap filling of HDPE pipe, construction of sluice valve chamber for washout purpose in the command area of NARASINGPUR PWSS under Alipurduar Division, PHE Dte. | 2417/ALD | 09/11/2023 | 60 | DILIP MAHATO | 36.67 | 0 | 0 | 80
1059 | ALIPURDUAR | Alipurduar Division | NARASINGPUR PIPED WATER SUPPLY SCHEME , SM/15758 | New | Laying of Rising main, delivery main, bypass arrangement, laying of HDPE pipeline for left out household connecting to Narasingpur PWSS (both H/W and 2nd site) (SM/15758) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | 748/ALD | 12/03/2024 | 120 | DILIP MAHATO | 91.41 | 0 | 0 | 85
1060 | ALIPURDUAR | Northern Mechanical Division II | NARASINGPUR PIPED WATER SUPPLY SCHEME , SM/15758 | New | NEW SERVICE CONNECTION CHARGE FOR NARSINGHPUR PH NO-I | BP-2023-24-694 | 14/03/2024 | 0 | WBSEDCL | 7.52 | 0 | 0 | 0
1061 | ALIPURDUAR | Northern Mechanical Division II | NARASINGPUR PIPED WATER SUPPLY SCHEME , SM/15758 | New | NEW SERVICE CONNECTION CHARGES FOR NARASINGPUR PWSS TW NO-II | BP-2023-24-689 | 14/03/2024 | 0 | WBSEDCL | 7.52 | 0 | 0 | 0
1062 | ALIPURDUAR | Alipurduar Division | NARASINGPUR PIPED WATER SUPPLY SCHEME , SM/15758 | New | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , Soil investigation at OHR site, constructions of 400 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Narasingpur PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 1048/ALD | 20/07/2023 | 672 | DILIP MAHATO | 567.48 | 142.25 | 25.07 | 90
1063 | ALIPURDUAR | Northern Mechanical Division II | NARASINGPUR PIPED WATER SUPPLY SCHEME , SM/15758 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM DEOGAON and others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1385/NMD-II | 26/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 20.56 | 0 | 0 | 0
1064 | ALIPURDUAR | Northern Mechanical Division II | NARASINGPUR PIPED WATER SUPPLY SCHEME , SM/15758 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1344/NMD-II | 19/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
1065 | ALIPURDUAR | Northern Mechanical Division II | NARASINGPUR PIPED WATER SUPPLY SCHEME , SM/15758 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1066 | ALIPURDUAR | Alipurduar Division | Rejuvenation of Makrapara TG WSS. , SM/09895 | Augmentation | Shifting of pipeline along the road of Birpara-Makrapara Gomtu Road under Alipurduar Division, PHE Dte. | 2654/ALD | 21/02/2022 | 30 | DILIP MAHATO | 3.62 | 3.11 | 50 | 0
1067 | ALIPURDUAR | Alipurduar Division | Rejuvenation of Makrapara TG WSS. , SM/09895 | Augmentation | Laying of HDPE pipeline near existing PH No-01 village for the Makrapara PWSS under Alipurduar Division, PHE Dte. | 3046/ALD | 21/03/2022 | 30 | DILIP MAHATO | 4.95 | 0 | 0 | 42
1068 | ALIPURDUAR | Alipurduar Division | Rejuvenation of Makrapara TG WSS. , SM/09895 | Augmentation | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for MAKRAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2389/ALD | 31/01/2022 | 90 | INDRAYOODH BHOWAL | 27.18 | 23.11 | 70.24 | 0
1069 | ALIPURDUAR | Northern Mechanical Division II | Rejuvenation of Makrapara TG WSS. , SM/09895 | Augmentation | Quotation for new service connection at Makrapara TW No- IV | BP-130/22-23 | 13/01/2023 | 0 | WBSEDCL | 1.49 | 0 | 0 | 0
1070 | ALIPURDUAR | Northern Mechanical Division II | Rejuvenation of Makrapara TG WSS. , SM/09895 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Rejuvenation of Makrapara TG Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Apd. | 415/NMD-II | 24/02/2023 | 30 | BONANZA ENTERPRISE | 15.21 | 13.17 | 87.21 | 100
1071 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME , SM/10678 | Augmentation | NEW SERVICE CONNECTION AT JOGENDRAPUR TW III | BP-2023-24-462 | 07/12/2023 | 0 | WBSEDCL | 5.36 | 0 | 0 | 0
1072 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME , SM/10678 | Augmentation | Laying distribution line, providing road and culvert crossing, and providing FHTC for Jogendrapur and Satpukuria Mouzas and adjacent areas, Cons. of Tubewell by ODEX-165 method of drilling, cons. of pump house and boundary wall for augmentation of JOGENDRAPUR PWSS. (2nd call) | 3198/ALD | 27/02/2023 | 180 | BIJOY ROY | 159.61 | 23.86 | 14.95 | 25
1073 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME , SM/10678 | Augmentation | Laying of different dia DI,UPVC pipeline, bridge and culvert crossing and other works for providing FHTC at Jogendrapur and Satpukuri mouza at Augmentation of Jogendrapur PWSS under Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/10678) | 2283/ALD | 05/08/2024 | 60 | MONORAMA ENTERPRISE | 21.88 | 0 | 0 | 0
1074 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME , SM/10678 | Augmentation | Supply of fuel for Diesel Vehicle Maxi Cab(At least 7 seater ) (Preferably TUV) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte.(from 08/08/2022 to 31.12.2022) | 1184/ALD | 05/08/2022 | 153 | MATRI ENTERPRISE | 1.27 | 0 | 0 | 0
1075 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME , SM/10678 | Augmentation | Painting of Old OHR at Jogendrapur PWSS (400cum) under Alipurduar Division, PHE Dte. | 5044/ALD | 17/02/2025 | 45 | DILIP MAHATO (OPC) PRIVATE LIMITED | 3.14 | 0 | 0 | 0
1076 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME , SM/10678 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1629/ALD | 04/08/2025 | 60 | NARENDRA BHADANI. | 18.13 | 0 | 0 | 0
1077 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME , SM/10678 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of JOGENDRAPUR water supply scheme, TW no III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | 2144/NMD-II | 27/07/2023 | 702 | BEE GEE CONSTRUCTION | 10.57 | 0 | 0 | 100
1078 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Tube well Boring by ODEX-165 method of drilling at 2nd TW site, Construction of Pump house and Boundary wall at 2nd site, Laying of Rising and delivery line connection, Providing FHTC and other allied works for KOHINUR TG PWSS under Alipurduar Division, PHE Dte. | 2235/ALD | 21/11/2022 | 120 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 96.96 | 53.89 | 55.58 | 56
1079 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Providing balance FHTC for KOHINUR TG PWSS (PART-II) under Alipurduar Division, PHE Dte. | 1789/ALD | 29/08/2023 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 16.73 | 0 | 0 | 0
1080 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Soil investigation works for proposed overhead reservoir of KOHINUR TG PWSS under Alipurduar Division, PHE Dte. | 2223/ALD | 21/11/2022 | 30 | K S GROUP | 0.65 | 0.65 | 100 | 16
1081 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Tubewell boring by ODEX-165 method of drilling, construction of Pump House, Boundary Wall at Proposed 3rd TW site of Kohinur TG PWSS under Alipurduar Division, PHE Dte. | 370/ALD | 18/05/2023 | 120 | DILIP MAHATO | 17.39 | 10 | 57.91 | 100
1082 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Material Requisition To Resource Division | 218/ALD | 03/05/2023 | 0 | Resource Division | 35.18 | 0 | 0 | 0
1083 | ALIPURDUAR | Northern Mechanical Division II | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Quotation for NSC at P/H No.III under Kohinoor TG W/S/S | BP-2023-24-174 | 15/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
1084 | ALIPURDUAR | Northern Mechanical Division II | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Quotation for NSC at P/H No.I under Kohinoor TG W/S/S | BP-2023-24-172 | 15/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
1085 | ALIPURDUAR | Northern Mechanical Division II | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Quotation for NSC at P/H No.II under Kohinoor TG W/S/S | BP-2023-24-173 | 15/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
1086 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Providing balance FHTC for KOHINUR TG PWSS (PART-I) under Alipurduar Division, PHE Dte. | 1852/ALD | 04/09/2023 | 60 | TAPASH DAS | 16.73 | 9.09 | 54.33 | 81
1087 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Laying of HDPE/DI pipe line near Dangi Aashram Ground and Kohinur Gram Panchayat office area for interconnection in the distribution system and bridge /culvert crossing under KOHINUR TEA GARDEN PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/12113) | 4179/ALD | 03/12/2024 | 60 | MAHAPRABHU ENTERPRISE | 61.89 | 0 | 0 | 0
1088 | ALIPURDUAR | Northern Mechanical Division II | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kohinur TG water supply scheme, TW no I,II and III of under Northern Mechanical Division-II, PHE Dte.APD | 2340/NMD-II | 01/08/2023 | 30 | ALPHA ENTERPRISE | 32.93 | 0 | 0 | 70
1089 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Kohinur TG Water Supply Scheme under Alipurduar Division P.H.E. Dte.(SM/12113) | 674/ALD | 06/03/2024 | 150 | BHAGWATI BHUJEL | 11.36 | 0 | 0 | 80
1090 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Material Requisition To Resource Division | 4272/ALD | 13/12/2024 | 0 | Resource Division | 12.78 | 0 | 0 | 0
1091 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 400 cum OHR as per Departmental Design & drawing, Providing FHTC and other allied works for KOHINUR TEA GARDEN PWSS under Alipurduar Division, PHE Dte. | 2979/ALD | 02/02/2023 | 360 | DILIP MAHATO | 237.14 | 203.99 | 86.02 | 86
1092 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Laying of HDPE/DI pipe line near kohinur TG factory area for interconnection in the distribution system and bridge /culvert crossing , Construction of Pump House, Boundary Wall at Head work site of KOHINUR TEA GARDEN PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/12113). | 2282/ALD | 05/08/2024 | 240 | DILIP MAHATO | 60.91 | 0 | 0 | 95
1093 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Laying of HDPE/DI pipe line near Dangi Bazar area for interconnection in the distribution system and bridge /culvert crossing under KOHINUR TEA GARDEN PWSS , Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/12113) | 2280/ALD | 05/08/2024 | 240 | JAYDAB ADHIKARI | 26.67 | 0 | 0 | 85
1094 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1095 | ALIPURDUAR | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12113 | New | Supply of CIDF & CISS Pipes and specials for Kohinur TG WSS Under Alipurduar Division P.H.E Dte. | 1600/ALD | 25/08/2023 | 541 | DILIP MAHATO | 6.76 | 0 | 0 | 85
1096 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for DESHBANDHUPARA, FALAKATA AUG. PWSS ZONE-III under Alipurduar Division, P.H.E. Dte. | 1760/ALD | 19/02/2021 | 60 | ASHIT KUMAR SINGHA | 40.25 | 40.25 | 50 | 65
1097 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for existing PWSS, JAIGAON DEVLOPMENT AREA ZONE- 1 and 2 under Alipurduar Division, P.H.E. Dte. | 1765/ALD | 19/02/2021 | 60 | MAHENDRA CHHETRI | 40.23 | 40.23 | 50 | 63
1098 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-1 | 1449/ALD | 25/01/2021 | 45 | MAHENDRA CHHETRI | 43.86 | 33.73 | 54.09 | 67
1099 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Fuel bill for the month of August 2021 | 120/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.18 | 0 | 0 | 0
1100 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Fuel bill for the month of August 2021 | 122/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.22 | 0 | 0 | 0
1101 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for SOUTH FALAKATA AREA, FALAKATA AUG. PWSS ZONE-III under Alipuduar Division, P.H.E. Dte. | 1761/ALD | 19/02/2021 | 60 | HARIDAS GHOSH | 40.13 | 20.44 | 107.86 | 66
1102 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply scheme (Barodoba Area) under Alipuduar Division, P.H.E. Dte. Part-1 | 1254/ALD | 28/12/2020 | 60 | HARIDAS GHOSH | 43.86 | 74.64 | 170.18 | 66
1103 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Replacement of old existing AC pipeline with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Augmentation of Falakata WSS under Alipurduar Division, PHE Dte.( Subhaspally and adjacent area.) | 1314/ALD | 05/10/2021 | 60 | SOUVIK ROY PALADHI | 41.3 | 26.04 | 63.07 | 67
1104 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Road crossing (by NP3 Hume pipe) at Dhupguri Road under under Zone-II of augmentation of Falakata WSS due to widening of PWD Road under Alipurduar Division, PHE Dte. (3 nos) | 1836/ALD | 10/12/2021 | 45 | SASANKA ROY | 2.49 | 2.49 | 100 | 67
1105 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Gap filling by UPVC pipe at different zone of Falakata water supply scheme under Alipurduar Division, PHE Dte. Part-5 | 1583/ALD | 10/02/2021 | 60 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.01 | 5.01 | 100 | 67
1106 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Laying of CI/DI/MS Pipe for delivery line, cons. of RCC Pillar with ISMB and balance part of boundary wall of CWR Project Area and earth filling at River Bed site of JDA (JAIGAON DEVELOPMENT AUTHORITY) Area Water Supply Scheme under Alipurduar Division, PHE Dte. | 405/ALD | 17/06/2021 | 30 | DILIP MAHATO | 49.78 | 4 | 200 | 67
1107 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Replacement of old existing AC pipeline with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Augmentation of Falakata WSS under Alipurduar Division, PHE Dte.( Masterpara, BDO Office and adjacent area.) | 979/ALD | 13/09/2021 | 60 | MESSRS R N TRADERS | 40.51 | 38.36 | 100 | 67
1108 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Laying of DI pipe line for discharge of washed out water from Tube well No. 1 within Falakata PWSS(Existing) under Alipurduar Division PHED. | 57/PHE-Brp | 03/02/2022 | 30 | KANKAN SARKAR | 0.22 | 0 | 0 | 67
1109 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Repairing of old UPVC pipe line , FHTC and other misc. work related to FALAKATA PWSS FALAKATA Block under Alipurduar Division , PHE Dte | 437/ALD | 13/05/2022 | 30 | NARENDRA BHADANI. | 4.66 | 3.81 | 100 | 66
1110 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply (Masalapatty area, left side of NH)under Alipuduar Division, P.H.E. Dte. Part-6 | 1252/ALD | 28/12/2020 | 60 | SOUVIK ROY PALADHI | 30.05 | 57.06 | 100 | 60
1111 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Laying of UPVC/DI/MS/CI Distribution pipe line for Gap filling and FHTC connection at different location of AUG. of Falakata PWSS (ZONE -II & III) under Alipurduar Division , PHE Dte. | 439/ALD | 13/05/2022 | 30 | SASANKA ROY | 4.73 | 4.75 | 100 | 66
1112 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Carrying of AC pipe and DI pipe and specials from Bhutnirghat PWSS to Falakata Stackyard due to widening PWD Road under Alipurduar Division, PHE Dte. | 1108/ALD | 29/07/2022 | 30 | SASANKA ROY | 0.92 | 0.92 | 50 | 67
1113 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Laying of Distribution Line (by using metal Pipes) of Zone-I for JDA (Jaigaon Development Authority) Area Water Supply Scheme under Alipurduar District. | 789/ALD | 01/10/2020 | 150 | M/S SSB CONSTRUCTION CO. | 185.6 | 22.05 | 102.81 | 65
1114 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply scheme (Falakata-Birpara Road) under Alipuduar Division, P.H.E. Dte. Part-3 | 1257/ALD | 28/12/2020 | 60 | BILTU DAS | 43.41 | 33.23 | 137.35 | 70
1115 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for MADARI ROAD/ PARANGERPAR, FALAKATA AUG. PWSS ZONE-I under Alipuduar Division, P.H.E. Dte. | 1758/ALD | 19/02/2021 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 39.97 | 48.77 | 125.77 | 63
1116 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing Functional Household Tap connection (FHTC) in connection with Jaldhara Jal Sapno for Jogendrapur PWSS under Alipurduar Division, PHE Dte. | 1381/ALD | 19/01/2021 | 45 | ASSOCIATE CONSTRUCTION COMPANY | 15.78 | 14.66 | 100 | 67
1117 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | 877/ALD | 03/09/2021 | 60 | M/S STAR INDIA CONSTRUCTION | 33.42 | 0 | 0 | 73
1118 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for public/Govt. organisations etc. ) at JDA WSS (Zone-II) under Alipurduar Division, PHE Dte. Part-3 | 2137/ALD | 06/01/2022 | 30 | D. K. & SONS | 5.02 | 0 | 0 | 65
1119 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Laying of different dia. Of HDPE pipeline inclu. Providing FHTC and other works at JDA PWSS Zone-IV under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | 2373/ALD | 31/01/2022 | 60 | AQUEDUCT PLASTICS PVT. LTD. | 55.55 | 1.23 | 19.12 | 71
1120 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Laying of water Supply pipeline due to widening of Road at industrial park by JDA (Jaigaon Development Authority Area) at Jaigaon Zone-2 WSS under Alipurduar District. | 1115/ALD | 29/07/2022 | 30 | D. K. & SONS | 4.84 | 0 | 0 | 0
1121 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Laying of UPVC/DI/MS/CI Distribution line for gap filling and FHTC Connection in ward no. 03, 04, 07, 08, 11, 15 location of augmentation of Falakata PWSS (Zone-I AND Zone-III) under Alipurduar Division, PHE Dte. | 2236/ALD/ | 21/11/2022 | 60 | NARENDRA BHADANI. | 33.38 | 33.37 | 99.98 | 0
1122 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for public/Govt. organisations etc. ) at JDA WSS (Zone-II) under Alipurduar Division, PHE Dte. Part-2 | 2136/ALD | 06/01/2022 | 30 | D. K. & SONS | 5.02 | 0 | 0 | 67
1123 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Sinking of Big Dia T/Well P/House B/Wall & Rising Main of 3rd T/Well Site at FALAKATA Aug. PWSS under Alipurduar Division PHED. | 655/ALD | 08/09/2020 | 120 | BILTU DAS | 22.65 | 0 | 0 | 82
1124 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply scheme (College Para Area) under Alipuduar Division, P.H.E. Dte. Part-2 | 1256/ALD | 28/12/2020 | 60 | BILTU DAS | 43.41 | 78.8 | 100 | 62
1125 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Loop Connention between West Falakata & Barodoba area via Mujnai River Bridge incl interconnection with the existing BHUTNIRGHAT PWSS under FALAKATA Aug. PWSS under Alipurduar Division PHED. | 626/ALD | 03/09/2020 | 120 | GOUTAM KUMAR DAS | 26.08 | 0 | 0 | 83
1126 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Construction of gasious chlorine room for Zone-VB of JDA water supply scheme Alipurduar Division PHE Dte. | 1333/ALD | 11/01/2021 | 90 | MAHENDRA CHHETRI | 5 | 0 | 0 | 65
1127 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Construction of gasious chlorine room for Zone-IV of JDA water supply scheme Alipurduar Division PHE Dte. | 1331/ALD | 11/01/2021 | 90 | MAHENDRA CHHETRI | 5 | 0 | 0 | 60
1128 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for JOGENDRAPUR water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | 1168/ALD | 15/12/2020 | 60 | SASANKA ROY | 29.9 | 23.36 | 62.08 | 67
1129 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply scheme (Subhaspally area, right side of NH) under Alipuduar Division, P.H.E. Dte. Part-5 | 1248/ALD | 28/12/2020 | 60 | BILTU DAS | 29.59 | 29.5 | 54.87 | 82
1130 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc. work for interconnection between Jogendrapur and Augmentation of Falakata PWSS under Alipurduar Division, PHE Dte.(Part-II) | 1382/ALD | 19/01/2021 | 45 | SASANKA ROY | 15.06 | 15.06 | 100 | 100
1131 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Construction of gasious chlorine room for Zone-IIIB of JDA water supply scheme Alipurduar Division PHE Dte. | 1330/ALD | 11/01/2021 | 90 | MAHENDRA CHHETRI | 5 | 0 | 0 | 67
1132 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Gap filling by UPVC pipe at different zone of Falakata water supply scheme under Alipurduar Division, PHE Dte. Part-4 | 1582/ALD | 10/02/2021 | 60 | SWAPAN SAHA | 5.01 | 5.06 | 100 | 64
1133 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Laying of CI/DI/MS Pipe for Rising and delivery line, cons. Of valve chamber and other allied works for Zone-II and III at JDA (Jaigaon Development Authority) Area Water Supply Scheme under Alipurduar District. | 1572/ALD | 22/11/2021 | 60 | DILIP MAHATO | 26.46 | 0 | 0 | 66
1134 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Simlabari area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | 876/ALD | 03/09/2021 | 60 | M/S AMIT KUMAR GUPTA | 35.43 | 3.03 | 100 | 75
1135 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Gap filling by UPVC/DI pipe and bridge crossing near Hat Khola Bazar Area for Augmenttion of Falakata WSS under Alipurduar Division, PHE Dte. | 1603/ALD | 22/11/2021 | 30 | NARENDRA BHADANI. | 5 | 4.82 | 100 | 67
1136 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Gap filling by UPVC/DI pipe at Parangerpar (near rail gate) of Augmenttion of Falakata WSS under Alipurduar Division, PHE Dte. | 1604/ALD | 22/11/2021 | 30 | ASSOCIATE CONSTRUCTION COMPANY | 4.98 | 5 | 100 | 61
1137 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Repairing of drainage system & painting of office cum Godown building at Head Work site of Falakata WSS (OLD) under Alipurduar Division, PHE Dte. | 1832/ALD | 10/12/2021 | 60 | NARENDRA BHADANI. | 4.47 | 4.36 | 100 | 63
1138 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC and school & others) at JDA WSS (Zone-1) under Alipurduar Division, PHE Dte. Part-2 | 2153/ALD | 06/01/2022 | 30 | MAHENDRA CHHETRI | 5.02 | 0 | 0 | 66
1139 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC, school & public/Govt. organisations etc. ) at JDA WSS (Existing) under Alipurduar Division, PHE Dte. | 2154/ALD | 06/01/2022 | 30 | MAHENDRA CHHETRI | 5.02 | 0 | 0 | 62
1140 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for public/Govt. organisations etc. ) at JDA WSS (Zone-1) under Alipurduar Division, PHE Dte. Part-3 | 2152/ALD | 06/01/2022 | 30 | D. K. & SONS | 5.02 | 0 | 0 | 61
1141 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Laying of CI/ DI, HDPE pipe including valve chamber and other misc. works at JDA PWSS ZONE-II under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | 3005/ALD | 15/03/2022 | 30 | DILIP MAHATO | 30.59 | 0 | 0 | 60
1142 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Installation of 125mm X 80mm X 90 mtr. Deep Tube Well (Mark-II TW) for fresh drinking water sources(with provision of lowering of sub-merssible pump) by ODEX-115 method of Drilling at Truck Stand of Jaigaon PS (West side) within Alipurduar District under Alipurduar Division, PHE Dte. | 3140/ALD | 25/03/2022 | 20 | D. K. & SONS | 3.32 | 0 | 0 | 61
1143 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Construction of pathway with paver block and repairing of old H/W site's Guest House of Jaigaon WSS under Alipurduar Division, PHE Dte. | 3143/ALD | 25/03/2022 | 30 | D. K. & SONS | 4.86 | 0 | 0 | 67
1144 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Laying of UPVC/DI/MS/CI Distribution pipe line for Gap filling and FHTC connection at different location of AUG. of Falakata PWSS (ZONE - I & III) under Alipurduar Division , PHE Dte. | 453/ALD | 13/05/2022 | 30 | NARENDRA BHADANI. | 5.05 | 5.04 | 100 | 65
1145 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Gap filling and culvert crossing along the main road at Zone-II and Zone-I by MS, DI Pipe and other allied works at JDA WSS under Alipurduar Division, PHE Dte | 341/ALD | 02/05/2022 | 45 | DILIP MAHATO | 10.82 | 0 | 0 | 63
1146 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Construction of Boundary wall 2nd TW site of Jaigaon PWSS (near Hanuman Mandir) under Alipurduar Division, PHE Dte. | 3144/ALD | 25/03/2022 | 45 | D. K. & SONS | 4.75 | 0 | 0 | 62
1147 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Preparation of DPR after investigation for Tasti Tea Garden, Dalgaon Tea Garden and Dalmoney Tea Garden Piped Water Supply Scheme under Falakata Block, Alipurduar Division, PHE Dte. | 1392/ALD | 29/08/2022 | 30 | M/S SOBHA AND CO | 6.51 | 6.51 | 100 | 100
1148 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Laying of HDPE pipeline including Providing FHTC at Jaigaon Development Area Zone-II from Krishna Pradhan house to Geeta Chhetri house within Kalchini Block under Alipurduar Division, PHE Dte. | 1222/ALD | 10/08/2022 | 60 | MAHENDRA CHHETRI | 36.35 | 0 | 0 | 67
1149 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Installation of 125mm X 80mm X 90 mtr. Deep Tube Well (Mark-II TW) for fresh drinking water sources(with provision of lowering of sub-merssible pump) by ODEX-115 method of Drilling at Truck Stand of Jaigaon PS (East side) within Alipurduar District under Alipurduar Division, PHE Dte. | 3139/ALD | 25/03/2022 | 20 | MAHENDRA CHHETRI | 3.32 | 0 | 0 | 67
1150 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Preparation of detailed Additional cost Requirement D.P.R. booklets in connection to various PWSS under Block Faakata & Madarihat Block under Alipurduar Division P.H.E Dte. | 1205/ALD | 07/08/2023 | 30 | ANIK BHATTACHARJEE | 0.78 | 0.78 | 100 | 100
1151 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply scheme (Falakata-Dhupguri Road) under Alipuduar Division, P.H.E. Dte. Part-4 | 1246/ALD | 28/12/2020 | 60 | TAPASH KUMAR BHOWMICK | 30.04 | 54.27 | 100 | 67
1152 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Construction of roof truss, field development and other allied works at Headwork site of Old Jaigaon WSS under Alipurduar Division, PHE Dte. | 2307/ALD | 25/01/2022 | 30 | DILIP MAHATO | 4.17 | 4.14 | 100 | 75
1153 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Material Requisition To Resource Division | 917/ALD | 07/07/2022 | 0 | Resource Division | 61.6 | 0 | 0 | 0
1154 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for RABINDRANAGAR, FALAKATA AUG. PWSS ZONE-III under Alipuduar Division, P.H.E. Dte. | 1759/ALD | 19/02/2021 | 1320 | BILTU DAS | 39.46 | 5.13 | 13 | 86
1155 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Constrcution of Pump House with Sanitary & Plumbing arrangement at 2nd Site (Old) of Dalmore Water supply scheme under Alipurduar Division. P.H.E. Dte. | 537/ALD | 20/08/2020 | 120 | M/S MONORAMA ENTERPRISE | 4.75 | 8.4 | 200 | 0
1156 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for DALSINGPARA, JAIGAON DEVLOPMENT AREA ZONE-5A under Alipurduar Division, P.H.E. Dte. | 1762ALD | 19/02/2021 | 60 | AQUEDUCT PLASTICS PVT. LTD. | 40.17 | 40.17 | 66.67 | 0
1157 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for BHUTNIRGHAT water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. | 865/ALD | 14/10/2020 | 30 | GOUTAM KUMAR DAS | 4.98 | 3.68 | 50 | 0
1158 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for BHUTNIRGHAT water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte.(PART-2) | 905/ALD | 16/10/2020 | 30 | GOUTAM KUMAR DAS | 4.98 | 9.97 | 100.01 | 0
1159 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for BHUTNIRGHAT water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | 1167/ALD | 15/12/2020 | 60 | GOUTAM KUMAR DAS | 19.91 | 39.83 | 100 | 0
1160 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for BANGSHIDHARPUR piped water supply scheme under Alipuduar Division, P.H.E. Dte. Part-1 | 1247/ALD | 28/12/2020 | 60 | MESSRS R N TRADERS | 40.06 | 40.06 | 100 | 0
1161 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for JAIGAON DEVLOPMENT AREA ZONE-5B under Alipurduar Division, P.H.E. Dte. | 1763ALD | 19/02/2021 | 60 | AQUEDUCT PLASTICS PVT. LTD. | 40.17 | 40.17 | 50 | 0
1162 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under BAKLA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | 1283/ALD | 05/01/2021 | 60 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 45.19 | 0.45 | 200 | 74
1163 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | PROVIDING FHTC IN CONNECTION WITH JALDHARA JAL SAPNA FOR AUGMENTATION OF FALAKATA WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION, PHE DTE. (COMMAND AREA : OLD OHR) | 579/ALD | 15/07/2021 | 45 | NARENDRA BHADANI. | 21.24 | 35.05 | 83.33 | 0
1164 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Preparation of Agumentation D.P.R after investigation For Kumargram W/Sscheme under Alipurduar Division. | 912/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.77 | 2.58 | 200 | 0
1165 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Installation of rising main with CI/DI pipeline and others misc. works for augmentation of Falakata PWSS (For Old OHR) under Alipurduar Division, PHE Dte. | 460/ALD | 13/05/2022 | 30 | ASSOCIATE CONSTRUCTION COMPANY | 5.02 | 4.25 | 84.72 | 100
1166 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-2 | 1451/ALD | 25/01/2021 | 45 | AQUEDUCT PLASTICS PVT. LTD. | 43.86 | 30 | 100 | 90
1167 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Providing House connection for TORSA TG AREA, JAIGAON DEVLOPMENT AREA ZONE-3B under Alipuduar Division, P.H.E. Dte. | 1764/ALD | 19/02/2021 | 60 | AQUEDUCT PLASTICS PVT. LTD. | 40.17 | 0 | 0 | 67
1168 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Laying of different dia. Of HDPE pipeline inclu. Providing FHTC and other works at JDA PWSS Zone-5A and 5B under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | 2374/ALD | 31/01/2022 | 60 | AQUEDUCT PLASTICS PVT. LTD. | 52.63 | 0 | 0 | 80
1169 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. , SM/08080 | Retrofitting | Remaining portion of pipeline of JDA Zone-I & Zone-II and special Road repairing of Zone-I and II and Zone-4B, providing pipeline and FHTC of Ramgaon. | 3623/ALD | 30/03/2023 | 810 | D. K. & SONS | 54.46 | 11.23 | 20.73 | 96
1170 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) , SM/07121 | Retrofitting | Laying of Distribution Line (HDPE and DI) for retrofitting of FHTC for BIRPARA WSS under Alipurduar Division, PHE Dte. | 1754/ALD | 19/02/2021 | 45 | BILTU DAS | 47.98 | 3.97 | 56.1 | 61
1171 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) , SM/07121 | Retrofitting | Providing House Connection (FHTC) at Birpara (APD) WSS under Alipurduar Division, PHE Dte. Part-7 | 2118/ALD | 05/01/2022 | 30 | DAS CONSTRUCTION | 5 | 0 | 0 | 96
1172 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) , SM/07121 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Alipurduar ITI College area under Birpara PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte | 2200/ALD | 11/01/2022 | 60 | DAS CONSTRUCTION | 42.69 | 30.1 | 100 | 98
1173 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) , SM/07121 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at Alipurduar Birpara Bazar Chowpathi and surrounding area under Birpara PWSS under Alipurduar Division, PHE Dte. | 1308/ALD | 05/10/2021 | 60 | DAS CONSTRUCTION | 43.41 | 23.31 | 100 | 99
1174 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) , SM/07121 | Retrofitting | Repairing of office Quarter and construction of attached toilet for Assistant Engineer Chamber of Birpara Sub-Division Office under Alipurduar Division PHE Dte. | 1853/ALD | 13/12/2021 | 45 | DAS ENTERPRISE | 4.91 | 0 | 0 | 97
1175 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) , SM/07121 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Birpara PWSS (APD) Under Alipurduar Division, PHE DTE. | 2751/ALD | 24/02/2022 | 60 | R.K.CONSTRUCTION | 31.74 | 17.01 | 100 | 60
1176 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) , SM/07121 | Retrofitting | Dismantling Concrete road and re -casting the same for providing FHTC at different area of BIRPARA (APD) PWSS AND Alipurduar - I Block under Alipurduar Division , PHE Dte. | 441/ALD | 13/05/2022 | 30 | R.K.CONSTRUCTION | 4.96 | 4.95 | 100 | 71
1177 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme , SM/07130 | Retrofitting | "Collectio of house hold details at prescribrd format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. (for the financial year 2022-2023 from 01/04/2022 onwards)" | 3223/ALD | 31/03/2022 | 365 | DILIP MAHATO | 4.96 | 1.89 | 100 | 54
1178 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme , SM/07130 | Retrofitting | Withdrawing & relaying & laying of pipeline and other misc. works for retrofitting of DHUMCHIPARA PWSS under Alipurduar Division PHED. | 688/ALD | 16/09/2020 | 120 | MITHUN DAS | 24.86 | 0.51 | 100 | 37
1179 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme , SM/07130 | Retrofitting | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for DHUMCHIPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2390/ALD | 31/01/2022 | 90 | DILIP MAHATO | 27.18 | 26.69 | 69.3 | 18
1180 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme , SM/07130 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 10 | 100 | 0
1181 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme , SM/07130 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI distribution pipeline and other misc. works for Dhumchipara PWSS under Alipurduar Division, PHE Dte. | 2900/ALD | 08/03/2022 | 60 | MITHUN DAS | 25.93 | 25.83 | 53.43 | 100
1182 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme , SM/07130 | Retrofitting | Preparation of detailed Additional cost Requirement D.P.R. booklets in connection to various PWSS under Alipurduar-I and Alipurduar- II Block under Alipurduar Division P.H.E Dte. | 1203/ALD | 07/08/2023 | 30 | ANIK BHATTACHARJEE | 0.78 | 0.78 | 100 | 100
1183 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme , SM/07130 | Retrofitting | Preparation of operation and maintenance DPR booklet in connection to 92 no's piped water supply scheme under Alipurduar Division P.H.E Dte | 1202/ALD | 07/08/2023 | 30 | ANIK BHATTACHARJEE | 0.78 | 0.78 | 100 | 100
1184 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme , SM/07130 | Retrofitting | Repairing of boundary wall with Gate and pump house at 2nd Tubewell site of Dhumchipara WSS under Alipurduar Division, PHE Dte. | 1114/ALD | 29/07/2022 | 30 | KAMALESH ROY | 2.58 | 1.66 | 100 | 37
1185 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme , SM/07130 | Retrofitting | Construction of Pump House, Boundary Wall, laying distribution system and providing FHTC for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2379/ALD | 31/01/2022 | 90 | DILIP MAHATO | 92.34 | 0 | 0 | 98
1186 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) , SM/07068 | Retrofitting | Balance part of laying of HDPE/DI pipe line alongwith construction of RCC piller at different area of DIMDIMA TG under ALIPURDUAR Division, PHED. | 622/ALD | 03/09/2020 | 120 | M/S SSB CONSTRUCTION | 34.11 | 3 | 15.1 | 88
1187 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) , SM/07068 | Retrofitting | Laying of DI/MS/HDPE pipe line from Nepali School (H.S.) towards Birpara Boro Houda WSS providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-I) | 1452/ALD | 25/01/2021 | 45 | GOUTAM KUMAR DAS | 43.73 | 11.67 | 100 | 87
1188 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) , SM/07068 | Retrofitting | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | 1453/ALD | 25/01/2021 | 45 | PRAMESH LAMA | 33.97 | 6.5 | 100 | 100
1189 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) , SM/07068 | Retrofitting | Extension of pipeline for implementation of FHTC at Bandapani TG Area attached with Nangdala TG (for Dimdima PWSS Zone-II) under Alipurduar Division, PHE Dte. | 2997/ALD | 15/03/2022 | 60 | DILIP MAHATO | 15.04 | 15.04 | 90.41 | 87
1190 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) , SM/07068 | Retrofitting | Laying of DI/MS/HDPE Pipe line for the Dimdima Zone-II and Nangdala Extension, Dimdima WSS under Alipurduar Division, PHE Dte. | 1795/ALD | 22/02/2021 | 60 | DILIP MAHATO | 31.27 | 0 | 0 | 87
1191 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) , SM/07068 | Retrofitting | Quotation for New Connection for Dangapara, Sishujumra | 445/22-23/PFMS | 21/01/2023 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
1192 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) , SM/07068 | Retrofitting | Laying of UPVC pipeline and Tube well Boring by Reverse Rotary method of drilling for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2380/ALD | 31/01/2022 | 60 | DILIP MAHATO | 95.15 | 0 | 0 | 97
1193 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) , SM/07068 | Retrofitting | Protective and Decorative Acrylic exterior paint on existing 350 cum OHR at Dimdima of Birpara Sub-Division under Alipurduar Division, P.H.E.Dte. (SM/07068) | 825/ALD | 14/03/2024 | 60 | BHAGWATI BHUJEL | 1.96 | 0 | 0 | 10
1194 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme , SM/07193 | Retrofitting | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | 571/20-21 | 26/03/2021 | 0 | PRAMESH LAMA | 10 | 0 | 0 | 0
1195 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme , SM/07193 | Retrofitting | Extension pipeline (HDPE) for providing FHTC at 28th and 29th mile busty area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | 1576/ALD | 22/11/2021 | 60 | DEBAJYOTI SUTRADHAR | 25.75 | 17.07 | 100 | 69
1196 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme , SM/07193 | Retrofitting | Laying balance portion pipeline and providing house connection at Jayanti Water Supply Scheme and Bhutiya Busty Area under Alipurduar Division, PHE Dte. | 975/ALD | 13/09/2021 | 30 | GHOSH & SAHA CONSTRUCTION | 5.04 | 0 | 0 | 54
1197 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme , SM/07193 | Retrofitting | Extension of pipeline for Jainti TG including connection from Reservoir-2 under Jainti TG Water Supply Scheme (Part-A). | 795/ALD | 01/10/2020 | 60 | CALCON CONSTRUCTIONS | 40.62 | 0 | 0 | 90
1198 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme , SM/07193 | Retrofitting | Providing House connection for Bhutia Basty and Jayanti water supply scheme at Kalchini Block under Alipuduar Division, P.H.E. Dte | 724/ALD | 22/09/2020 | 30 | M/S BHOWMICK CONSTRUCTION | 4.99 | 9.99 | 100 | 0
1199 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme , SM/07193 | Retrofitting | Providing House connection for JAYANTI water supply scheme at KALCHINI Block under Alipuduar Division, P.H.E. Dte.(PART-2) | 916/ALD | 16/10/2020 | 30 | M/S BHOWMICK CONSTRUCTION | 4.95 | 9.9 | 100 | 0
1200 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme , SM/07198 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc. work for retrofitting of Mujnai PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 943/ALD | 19/10/2020 | 60 | VEDATRAYEE AND CO | 29.81 | 1.8 | 100 | 92
1201 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme , SM/07198 | Retrofitting | Supplying & laying of UPVC/DI/GI Distribution pipeline for Mujnai PWSS under Alipurduar Division, PHE Dte. | 902/ALD | 03/09/2021 | 30 | DILIP MAHATO | 4.99 | 3.81 | 100 | 91
1202 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme , SM/07198 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 10 | 100 | 100
1203 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme , SM/07198 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 25 | 100 | 0
1204 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme , SM/07198 | Retrofitting | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 01.08.2022 to 31.12.2022) | 1121/ALD | 29/07/2022 | 153 | MITHU DAS | 0.84 | 0 | 0 | 100
1205 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme , SM/07198 | Retrofitting | Supply of fuel for Diesel Vehicle Maxi Cab(At least 7 seater) (Preferably Scorpio) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 08.08.2022 to 31.12.2022) | 1187/ALD | 05/08/2022 | 153 | MITHU DAS | 1.16 | 0 | 0 | 100
1206 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme , SM/07198 | Retrofitting | Soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-5 Venue : 1)Madarihat (1 no.) 2)Mujnai (2 nos) 3)Sidhabari (1 no.) | 2125/ALD | 05/01/2022 | 30 | G. MITRA & ASSOCIATES, | 4.9 | 4.9 | 100 | 50
1207 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme , SM/07198 | Retrofitting | CONS. OF BOUNDARY WALL (80 m), PUMPHOUSE( 1.Nos) ,TUBEWELL (2 Nos.), RISING MAIN AND DISTRIBUTION LINE FOR MUJNAI T.G (All Other Division & Line 60 unit) CHA SUNDARI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | 1946/ALD | 25/02/2021 | 840 | GHOSH & SAHA CONSTRUCTION | 36.68 | 6.84 | 100 | 100
1208 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) , SM/07175 | Retrofitting | Laying of Distribution Line (HDPE and DI) for retrofitting of FHTC for BIRPARA WSS under Alipurduar Division, PHE Dte. | 1754/ALD | 19/02/2021 | 45 | BILTU DAS | 47.98 | 4.42 | 56.02 | 61
1209 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) , SM/07175 | Retrofitting | Providing House Connection (FHTC) at Birpara (APD) WSS under Alipurduar Division, PHE Dte. Part-7 | 2118/ALD | 05/01/2022 | 30 | DAS CONSTRUCTION | 5 | 4.38 | 100 | 96
1210 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) , SM/07175 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Alipurduar ITI College area under Birpara PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte | 2200/ALD | 11/01/2022 | 60 | DAS CONSTRUCTION | 42.69 | 0 | 0 | 98
1211 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) , SM/07175 | Retrofitting | Providing House connection for Birpara water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. Part-II | 1157/ALD | 15/12/2020 | 60 | DAS CONSTRUCTION | 29.9 | 29.9 | 50 | 97
1212 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) , SM/07175 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at Alipurduar Birpara Bazar Chowpathi and surrounding area under Birpara PWSS under Alipurduar Division, PHE Dte. | 1308/ALD | 05/10/2021 | 60 | DAS CONSTRUCTION | 43.41 | 13.05 | 61.33 | 99
1213 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) , SM/07175 | Retrofitting | Repairing of damaged pipe line, arrangement of water supply pipe line on emergency basis and other works due to widening and strengthening of PWD road at Sonapur PWSS under Alipurduar Division, PHE Dte. | 1835/ALD | 10/12/2021 | 30 | HARI CONSTRUCTION | 2.56 | 2.56 | 100 | 97
1214 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) , SM/07175 | Retrofitting | Providing House Connection (FHTC) at Birpara (APD) WSS under Alipurduar Division, PHE Dte.Part-6 | 2117/ALD | 05/01/2022 | 30 | DAS CONSTRUCTION | 5 | 5 | 100 | 96
1215 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) , SM/07175 | Retrofitting | Repairing of office Quarter and construction of attached toilet for Assistant Engineer Chamber of Birpara Sub-Division Office under Alipurduar Division PHE Dte. | 1853/ALD | 13/12/2021 | 45 | DAS ENTERPRISE | 4.91 | 4.75 | 100 | 97
1216 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) , SM/07175 | Retrofitting | Providing House connection for Birpara water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. | 720/ALD | 22/09/2020 | 30 | KAMALESH ROY | 4.98 | 9.96 | 200 | 0
1217 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) , SM/07175 | Retrofitting | Laying of 90mm & 110 mm dia UPVC pipeline for Bholardabri Water Supply Scheme uner Alipurduar Division, PHE Dte. | 1467/ALD | 25/01/2021 | 45 | HARI CONSTRUCTION | 5.08 | 10.16 | 100 | 0
1218 | ALIPURDUAR | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10054 | New | Construction of boundary wall, pump house, tubewell, rising main and land development for (Mouza- Lankapara TG, JL No. 30, Sheet No. 7, Plot No. 920,921, 922 & 923 ) 375 units Cha Sundori Water Supply Scheme under Alipurduar Division PHE DTE. | 1486/ALD | 16/08/2023 | 120 | SUBIR GHOSH | 55.7 | 0 | 0 | 0
1219 | ALIPURDUAR | Northern Mechanical Division II | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10054 | New | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Lankapara Water Supply Scheme TW No.-V under NMD-II,PHE Dte Alipurduar. | 202/NMD-II | 24/02/2022 | 30 | M/S RATAN KUMAR DASGUPTA & CO. | 10.44 | 10.44 | 100 | 100
1220 | ALIPURDUAR | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10054 | New | Soil investigation work for Cha Sundori Project at 4 different places of Lankapara TG (3 nos GLR & 1 No OHR) within Alipurduar District under Alipurduar Division PHE Dte. | .2660/ALD | 21/02/2022 | 30 | GLORY ENGINEERS SYNDICATE | 4.89 | 0 | 0 | 80
1221 | ALIPURDUAR | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10054 | New | Laying of proposed Rising main (Length- 1085 mtr, 4817 mtr & 1320 mtr.) of Cha-Sundori Project (JJM- SM/10054) within Lankapara Tea Garden Area Piped Water Supply Scheme, Madarihat-Birpara block of Birpara Sub-Division under Alipurduar Division, PHE Dte.[As per new DPR guided by Planning Circle-II, PHE Dte.] | 3116/ALD | 30/08/2024 | 45 | DILIP MAHATO (OPC) PRIVATE LIMITED | 36.54 | 0 | 0 | 28
1222 | ALIPURDUAR | Northern Mechanical Division II | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10054 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Lankapara in Relation With Chaa Sundori Water Supply Scheme TWNo- I,II,III,IV under NMD-II,PHE.Dte,APD. | 2988/NMD-II | 28/11/2023 | 30 | SARKAR ELECTRIC | 59.29 | 0 | 0 | 58
1223 | ALIPURDUAR | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10054 | New | New Service Connection Charges for Lankapara TG PWSS PH NO-VII ( AT VES-4) Near Chha Sundari | 324/24-25/PFMS | 22/11/2024 | 0 | WBSEDCL | 16.11 | 0 | 0 | 0
1224 | ALIPURDUAR | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10054 | New | Hydro Geological investigation about water evaluation availability and quality parameter for both Ground and surface sources at Lankapara central Dooars Tea Estates within Alipurduar District | 164/24-25/PFMS | 12/08/2024 | 0 | IIT CONSULTATIVE PRACTICE | 9.74 | 0 | 0 | 0
1225 | ALIPURDUAR | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10054 | New | Construction of boundary wall, pump house, tubewell, rising main for (Mouza- Lankapara TG, JL NO. 30, Sheet No. 8, Plot No. 1052) 117 units Cha Sundori Water Supply Scheme under Alipurduar Division PHE DTE. | 1460/ALD | 14/08/2023 | 540 | SUDDHYA SING LAMA | 39.38 | 0 | 0 | 61
1226 | ALIPURDUAR | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10054 | New | Construction of boundary wall, pump house, tubewell, rising main for (Mouza- Lankapara TG, JL No. 30, Sheet No. 5, Plot No. 704) 327 units Cha Sundori Water Supply Scheme under Alipurduar Division PHE DTE. | 1280/ALD | 11/08/2023 | 827 | ASHOK PRADHAN | 57.36 | 0 | 0 | 35
1227 | ALIPURDUAR | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10054 | New | Making arrangement for pumping test with suitable pump and required column pipes etc. including all charges at 6 locations. | 1825/ALD | 14/06/2024 | 360 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 15.96 | 0 | 0 | 30
1228 | ALIPURDUAR | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10054 | New | Route surveying and revalidation of Household data with digitization of LDS for Cha Sundari Cluster-I,, Cluster-II, Cluster-III & Cluster-IV (with 2 options) PWSS under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | 1182/ALD | 26/06/2025 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 6.4 | 0 | 0 | 0
1229 | ALIPURDUAR | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. , SM/10054 | New | Sinking of one no. Big dia Tube Well (250 x 200 x 150 mm dia 270mtr) by Modified DTH - ODEX method of Cha-Sundori Project (JJM- SM/10054) within Lankapara Tea Garden Area Piped Water Supply Scheme, Madarihat-Birpara block of Birpara Sub-Division under Alipurduar Division, PHE Dte. | 3339/ALD | 20/09/2024 | 105 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 32.35 | 0 | 0 | 51
1230 | ALIPURDUAR | Northern Mechanical Division II | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10179 | New | Quotation for new service connection at Chuniya Jhora W/SS TW No- I | BP-14/22-23 | 14/10/2022 | 0 | WBSEDCL | 1.23 | 0 | 0 | 0
1231 | ALIPURDUAR | Northern Mechanical Division II | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10179 | New | Quotation for new service connection at Chuniya Jhora W/SS TW No- II | BP-73/22-23 | 14/10/2022 | 0 | WBSEDCL | 1.23 | 0 | 0 | 0
1232 | ALIPURDUAR | Alipurduar Division | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10179 | New | Construction of OHR 200cum for Chuniajhora TG Water Supply Scheme under Alipurduar Division, PHE Dte. | 2598/ALD | 17/02/2022 | 180 | AKANSHA COMMERCIAL PRIVATE LTD. | 55.36 | 47.96 | 100 | 65
1233 | ALIPURDUAR | Alipurduar Division | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10179 | New | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58
1234 | ALIPURDUAR | Alipurduar Division | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10179 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling including laying distribution system, Rising main and providing FHTC for CHUNIAJHORA TEA GARDEN AREA PWSS under Alipurduar Division PHE DTE | 12/ALD | 01/04/2022 | 120 | AKANSHA COMMERCIAL PRIVATE LTD. | 168.43 | 118.84 | 35.23 | 100
1235 | ALIPURDUAR | Alipurduar Division | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10179 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 100 | 100 | 0
1236 | ALIPURDUAR | Northern Mechanical Division II | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10179 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHUNIAJHORA TG AREA PWSS, TW no I (H/W Site)in the district of ALIPURDUAR under Northern Mechanical Division-II, PHE Dte. | 95/NMD-II | 10/01/2023 | 30 | DIAMOND ELECTRICAL WORKS | 9.83 | 9.25 | 94.46 | 65
1237 | ALIPURDUAR | Northern Mechanical Division II | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10179 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHUNIAJHORA TG AREA PWSS, TW no II in the district of ALIPURDUAR under Northern Mechanical Division-II, PHE Dte | 94/NMD-II | 10/01/2023 | 30 | BONANZA ENTERPRISE | 9.84 | 9.24 | 94.45 | 65
1238 | ALIPURDUAR | Alipurduar Division | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10179 | New | Material Requisition To Resource Division | 397/ALD | 11/05/2022 | 0 | Resource Division | 3.59 | 0 | 0 | 0
1239 | ALIPURDUAR | Alipurduar Division | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10179 | New | Laying of HDPE/DI Pipeline, horizontal boring by HDD method, bridge and culvert crossing, providing FHTC, specials repair with trial run of pipeline and allied works at Chuniajhora PWSS under Alipurduar Division, PHE Dte.(SM/14219 & SM/10179) | 672/ALD | 06/03/2024 | 240 | ASHOK SAPKOTA | 19.39 | 0 | 0 | 100
1240 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-10 | 1842/ALD | 10/12/2021 | 30 | HARIDAS GHOSH | 5.02 | 4.39 | 87.59 | 63
1241 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-8 | 1840/ALD | 10/12/2021 | 30 | HARI CONSTRUCTION | 5 | 4.72 | 94.48 | 66
1242 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-9 | 1841/ALD | 10/12/2021 | 30 | HARI CONSTRUCTION | 5.04 | 4.42 | 87.59 | 65
1243 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-12 | 2141/ALD | 06/01/2022 | 60 | HARIDAS GHOSH | 5.04 | 4.66 | 92.41 | 65
1244 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Restoration of laying distribution system by replacing of Damaged AC pipeline with UPVC pipeline of Bholardabri WSS under Alipurduar Division, PHE Dte. | 992/ALD | 13/09/2021 | 30 | MANORAMA ENTERPRISE | 4.89 | 4.62 | 100 | 65
1245 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Repairing and renovation of 2 nos. P/H, cons. Of 2 nos. Toilet (for 1st and 2nd site) and laying of UPVC pipe line with providing House connection at Bholardabri WSS under Alipurduar Division, PHE Dte. | 1313/ALD | 05/10/2021 | 60 | HARI CONSTRUCTION | 33.81 | 33.47 | 100 | 64
1246 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-11 | 2140/ALD | 06/01/2022 | 30 | HARIDAS GHOSH | 5.04 | 5.04 | 100 | 64
1247 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Bholardabri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 697/ALD | 08/06/2022 | 30 | KAMALESH ROY | 4.84 | 4.84 | 50 | 63
1248 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Quotation for new service connection at Bholardabri, P/H no.III, Application no.4003012374 | bp-87/22-23 | 11/11/2022 | 0 | WBSEDCL | 1.23 | 0 | 0 | 0
1249 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Quotation for new service connection for Bholardabri, near Modakpara t/W no. III, Application no. 4003012374 |  | 07/11/2022 | 0 | WBSEDCL | 1.23 | 0 | 0 | 0
1250 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) (Preferably TUV) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2022 to 31.12.2022) | 2014/ALD | 29/12/2021 | 365 | KAMALESH ROY | 1.76 | 1.49 | 84.24 | 61
1251 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Construction of 450cum OHR for Bholardabri water Supply Scheme under Alipurduar Division, PHE Dte. | 2187/ALD | 11/01/2022 | 180 | HARIDAS GHOSH | 87.58 | 86.43 | 100 | 63
1252 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-1 Places : 1)Uttar Kamakhyaguri 2)Uttar Majherdabri. 3)Bholardabri. 4) Narathali. | 2121/ALD | 05/01/2022 | 30 | MOYTEC | 4.9 | 4.9 | 100 | 69
1253 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 10 | 100 | 0
1254 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Restoration of laying distribution system by replacing of damaged AC Pipeline with UPVC pipeline of Bholardabri Water Supply Scheme under Alipurduar Division, PHE Dte. | 3107/ALD | 24/03/2022 | 60 | HARI CONSTRUCTION | 56.51 | 46.1 | 88.97 | 100
1255 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Bholardabri Water Supply Scheme TW No.- III (Aug) under NMD-II,PHE. Dte Alipurduar. | 2061/NMD-II | 20/12/2022 | 30 | SUMON ELECTRICAL | 10.5 | 8.32 | 80.21 | 100
1256 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Construction of Rig Machine Approach Road of Bholardabri 3rd TW Site under Alipurduar Division, PHE Dte. | 2792/ALD | 10/01/2023 | 30 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.33 | 0.32 | 100 | 64
1257 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Providing FHTC in school in Bholardabri PWSS under Alipurduar Division P.H.E Dte. | 3359/ALD | 14/03/2023 | 30 | HARIDAS GHOSH | 0.25 | 0.25 | 100 | 100
1258 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Construction of Pump House ,Boundary Wall and Providing FHTC including Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Bholardabri PWSS under Alipurduar Division PHE DTE. | 2382/ALD | 31/01/2022 | 1080 | HARIDAS GHOSH | 82.3 | 46.48 | 56.48 | 80
1259 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Laying of new UPVC/DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, supply of CIDF specials, land development works, construction of surface drain, pathway at 3rd TW site and other allied works in connection with the Augmentation of Bholardabri PWSS under Alipurduarn Division, PHE Dte. | 2410/ALD | 09/11/2023 | 450 | HARI CONSTRUCTION | 30.3 | 0 | 0 | 100
1260 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Construction of Pump House ,Boundary Wall and Providing FHTC including Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Bholardabri PWSS under Alipurduar Division PHE DTE.(2382/ALD DT:31/01/2022) Construction of 450cum OHR for Bholardabri water Supply Scheme under Alipurduar Division, PHE Dte. (2187/ALD DT:29/02/2022) | 449/23-24/PFMS | 30/03/2024 | 0 | HARIDAS GHOSH | 1.19 | 0 | 0 | 0
1261 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Construction of Pump House ,Boundary Wall and Providing FHTC including Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Bholardabri PWSS under Alipurduar Division PHE DTE.(2382/ALD DT:31/01/2022) Construction of 450cum OHR for Bholardabri water Supply Scheme under Alipurduar Division, PHE Dte. (2187/ALD DT:29/02/2022) |  | 29/02/2024 | 0 | HARIDAS GHOSH | 2.68 | 0 | 0 | 0
1262 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
1263 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Construction of Pump House ,Boundary Wall and Providing FHTC including Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Bholardabri PWSS under Alipurduar Division PHE DTE.(2382/ALD DT:31/01/2022) Construction of 450cum OHR for Bholardabri water Supply Scheme under Alipurduar Division, PHE Dte. (2187/ALD DT:29/02/2022) | 448/23-24/PFMS | 30/03/2024 | 0 | HARIDAS GHOSH | 1.49 | 0 | 0 | 0
1264 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Drilling Rigbore tube well (ODEX-115 method) at Modakpara, Paschim Bholardabri under Alipurduar Division, PHE Dte. | 1943/ALD | 17/10/2022 | 30 | HARIDAS GHOSH | 2.77 | 0 | 0 | 0
1265 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Laying of new UPVC/DI pipeline for interconnection in the distribution system and other allied works under Bholardabri PWSS, Alipurduar Division, PHE Dte. (SM/09883) | 3423/ALD | 26/09/2024 | 180 | TAPASH DAS | 20.57 | 0 | 0 | 70
1266 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Repairing of pump house at 2nd TW site of Bholardabri PWSS under Alipurduar Division, PHE Dte. | 1772/ALD | 18/08/2025 | 30 | TAPASH DAS | 1.01 | 0 | 0 | 0
1267 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Laying rising main line from 2nd side to HW Site of Bholardabri WSS and construction of different dia valve chamber and restoration of damaged FHTC connection and other allied work at Bholardabri PWSS under JJM Programme under Alipurduar Division, PHE Dte. | 1778/ALD | 18/08/2025 | 60 | TAPASH DAS | 2.88 | 0 | 0 | 0
1268 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME , SM/09883 | Augmentation | Reparing of Pump House at HEADWORK site of BHOLARDABRI PWSS Under Alipurduar Division PHE DTE. | 5605/ALD | 27/03/2025 | 120 | CHANDAN DAS | 0.88 | 0 | 0 | 100
1269 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME , SM/10673 | Augmentation | Retrofitting of pipeline with DI/UPVC pipeline for JAL SWAPNO programme (FHTC for every household) for LOKNATHPUR WSS under Alipurduar Division, PHE Dte. | 3004/ALD | 15/03/2022 | 60 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 20.09 | 16.34 | 81.31 | 0
1270 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME , SM/10673 | Augmentation | Construction of pathway with paver block & land development of Loknathpur HW site WSS (Western part of GADA rivert) under Alipurduar Division, PHE Dte. | 446/ALD | 13/05/2022 | 30 | MATARA CONSTRUCTION CO | 4.21 | 0 | 0 | 0
1271 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME , SM/10673 | Augmentation | Construction of pathway with paver block & land development of Loknathpur HW site & 2nd site WSS (Western part of GADA rivet) under Alipurduar Division, PHE Dte. | 447/ALD | 13/05/2022 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.19 | 0 | 0 | 0
1272 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME , SM/10673 | Augmentation | Providing FHTC in school in Loknathpur PWSS under Alipurduar Division P.H.E Dte. | 3358/ALD | 14/03/2023 | 30 | HARIDAS GHOSH | 0.22 | 0 | 0 | 100
1273 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME , SM/10673 | Augmentation | Providing FHTC in school in Loknathpur PWSS under Alipurduar Division P.H.E Dte. | .3358/ALD | 14/03/2023 | 30 | HARIDAS GHOSH | 0.22 | 0 | 0 | 100
1274 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME , SM/10673 | Augmentation | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing, construction of RCC pillars for supporting DI Pipe, surface drain and others allied works in connection with the Augmentation of Loknathpur PWSS under Alipurduar Division, PHE Dte. | 4535/ALD | 26/12/2024 | 60 | SOUVIK ROY PALADHI | 80.87 | 0 | 0 | 0
1275 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME , SM/10673 | Augmentation | Laying of rising main line HDPE PN10, horizontal boring by HDD method, bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block along with the others allied works at Loknathpur PWSS under Alipurduar Division, PHE Dte. | 204/ALD | 16/01/2024 | 450 | SOUVIK ROY PALADHI | 26.65 | 0 | 0 | 60
1276 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME , SM/10673 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1277 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME , SM/11766 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Nepania Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,,Apd | 2491/NMD-II | 14/08/2023 | 30 | M/S DE ENGINEERING CONCERN | 12.95 | 0 | 0 | 0
1278 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME , SM/11766 | Augmentation | Quotation for Nepania P/H NO-I |  | 01/12/2023 | 0 | WBSEDCL | 28.07 | 0 | 0 | 0
1279 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME , SM/11766 | Augmentation | Tube well boring by ODEX-195 Method of drilling, Construction of 1no. of Pump house, boundary wall an distribution line with FHTC for Augmentation of NEPANIA PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 2489/ALD | 13/12/2022 | 120 | BHAGWATI BHUJEL | 59.01 | 30.66 | 51.95 | 80
1280 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME , SM/11766 | Augmentation | Gap filling of HDPE pipeline at Nepania Division area under Alipurduar Division, PHE Dte. | 2422/ALD | 09/11/2023 | 60 | BHAGWATI BHUJEL | 5.01 | 0 | 0 | 100
1281 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Laying distribution system with new HDPE and DI pipeline, Supply of necessary specials, construction of sluice valve chamber, boundary wall at 2nd site of RAYDAK TG AREA PWSS under Alipurduar Division, PHE Dte. | 2232/ALD | 21/11/2022 | 90 | ALATYA CONSTRUCTION & CO. | 13.65 | 0 | 0 | 0
1282 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Soil investigation works for proposed overhead reservoir of RAYDAK TG PWSS under Alipurduar Division, PHE Dte. | 2222/ALD | 21/11/2022 | 30 | K S GROUP | 0.65 | 0.65 | 100 | 0
1283 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Laying of new HDPE pipeline in the balance portion distribution system of Raydak TG PWSS under Alipurduar Division, PHE Dte. (Part-A) | 92/ALD | 18/04/2023 | 60 | TILAK SHARMA | 12.11 | 0 | 0 | 0
1284 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Laying of new HDPE pile line in the balance portion distribution system at Sanialine & adj. Area of Raydak TG PWSS under Alipurduar Division PHE Dte. | 362/ALD | 18/05/2023 | 60 | SUMAN CHAKRABORTY | 7.99 | 0 | 0 | 0
1285 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Providing balance FHTC for Raydak TG PWSS under Alipurduar Division, PHE Dte. | 1561/ALD | 23/08/2023 | 45 | BRAJA GOPAL SAHA | 6.69 | 0 | 0 | 0
1286 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Material Requisition To Resource Division | 207/ALD/2023-2024 | 02/05/2023 | 0 | Resource Division | 44.73 | 0 | 0 | 0
1287 | ALIPURDUAR | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | New Service Connection at Raydak TG p/h-I | BP-2023-24-193 | 22/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
1288 | ALIPURDUAR | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | New Service Connection at Raydak TG p/h-II | BP-2023-24-192 | 22/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
1289 | ALIPURDUAR | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | New Service Connection at Raydak TG p/h-III | BP-2023-24-191 | 22/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
1290 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Laying distribution system with new HDPE and DI pipeline, Supply of necessary specials, construction of sluice valve chamber, boundary wall at Head work site of RAYDAK TG AREA PWSS under Alipurduar Division, PHE Dte. | 2234/ALD | 21/11/2022 | 90 | HITANGSHU CHOUDHURY | 15.63 | 0 | 0 | 61
1291 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Laying of new HDPE pipe line, Construction of Pump House at Head Work Site and providing FHTC and other allied works for Raydak TG PWSS under Alipurduar Division, PHE Dte. | 2229/ALD | 21/11/2022 | 120 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 13.78 | 0 | 0 | 61
1292 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Tube well Boring by ODEX-165 method of drilling at 2nd TW Site, Construction of Pump house at 2nd site, laying of Rising Main and delivery line connection, providing FHTC and other allied works for RAYDAK Tea Garden PWSS under Alipurduar Division, PHE Dte. | 2237/ALD | 21/11/2022 | 600 | DAS CONSTRUCTION | 95.24 | 52.81 | 55.45 | 65
1293 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 300 cum OHR as per Departmental Design & drawing, Providing FHTC and other allied works for RAYDAK TEA GARDEN PWSS under Alipurduar Division, PHE Dte. | 2978/ALD | 02/02/2023 | 180 | CHINMOY BHATTACHARJEE | 233.78 | 76.01 | 32.51 | 54
1294 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Tubewell boring by ODEX-165 method of drilling, construction of Pump House, Boundary Wall at Proposed 3rd TW site of Raydak TG PWSS under Alipurduar Division, PHE Dte. | 363/ALD | 18/05/2023 | 360 | POLY CONSTRUCTION | 17.71 | 0 | 0 | 3
1295 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Laying of new HDPE pile line in the balance portion distribution system at khuruline & four line of Raydak TG PWSS under Alipurduar Division PHE Dte. | 369/ALD | 18/05/2023 | 60 | PRAPTI DUTTA | 10 | 0 | 0 | 80
1296 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Supply of CIDF & CISS Pipes and specials for Raydak TG WSS Under Alipurduar Division P.H.E Dte. | 1595/ALD | 25/08/2023 | 30 | DAS CONSTRUCTION | 6.76 | 0 | 0 | 95
1297 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Material Requisition To Resource Division | 129/ALD | 10/01/2024 | 0 | Resource Division | 12.31 | 0 | 0 | 0
1298 | ALIPURDUAR | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | ADDITIONAL QUOTATION FOR RAYDAK T.G P/H NO-II | BP-2023-24-682 | 12/03/2024 | 0 | WBSEDCL | 4.7 | 0 | 0 | 0
1299 | ALIPURDUAR | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | ADDITIONAL QUOTATION FOR RAYDAK P/H NO-III | BP-162/24-25 | 21/06/2024 | 0 | WBSEDCL | 5.9 | 0 | 0 | 0
1300 | ALIPURDUAR | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Raydak TG water supply scheme, TW no I,II and III of under Northern Mechanical Division-II, PHE Dte.APD | 998/NMD-II | 16/05/2023 | 30 | DEY ENTERPRISE (BALLY) | 28.63 | 0 | 0 | 95
1301 | ALIPURDUAR | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12114 | New | Supply of DI specials and CI Jeffy coupling for Raydak TG Water Supply Scheme(SM/12114) of Kumargram Block under Alipurduar Division P.H.E. Dte. | 835/ALD | 14/03/2024 | 360 | HARI CONSTRUCTION | 15.18 | 0 | 0 | 80
1302 | ALIPURDUAR | Alipurduar Division | SISHA JUMRHA PIPED WATER SUPPLY SCHEME , SM/12753 | New | Material Requisition To Resource Division | 1275/ALD | 11/08/2023 | 0 | Resource Division | 54.68 | 0 | 0 | 0
1303 | ALIPURDUAR | Northern Mechanical Division II | SISHA JUMRHA PIPED WATER SUPPLY SCHEME , SM/12753 | New | NEW SERVICE CONNECTION FOR SISHUJHUMRA PWSS P/H NO-I,BIRPARA,ALIPURDUAR, APPLICATION NO 4003068997 | BP-2023-24-366 | 27/09/2023 | 0 | WBSEDCL | 6.89 | 0 | 0 | 0
1304 | ALIPURDUAR | Northern Mechanical Division II | SISHA JUMRHA PIPED WATER SUPPLY SCHEME , SM/12753 | New | NEW SERVICE CONNECTION FOR SISHUJHUMRA PWSS,P/H NO II,BIRPARA,ALIPURDUAR, APPLICATION NO 4003068181 | BP-2023-24-365 | 27/09/2023 | 0 | WBSEDCL | 9.33 | 0 | 0 | 0
1305 | ALIPURDUAR | Northern Mechanical Division II | SISHA JUMRHA PIPED WATER SUPPLY SCHEME , SM/12753 | New | NEW SERVICE CONNECTION FOR SISHUJHUMRA PWSS,P/H NO- III,BIRPARA, ALIPURDUAR, APPLICATION NO 4003068999 | BP-2023-24-364 | 27/09/2023 | 0 | WBSEDCL | 6.65 | 0 | 0 | 0
1306 | ALIPURDUAR | Alipurduar Division | SISHA JUMRHA PIPED WATER SUPPLY SCHEME , SM/12753 | New | Construction of boulder apron for Dimdima PWSS in sishujhumra mouza for protection of existing HW site under Alipurduar Division. | 743/ALD | 12/03/2024 | 135 | SUBIR GHOSH | 4.03 | 0 | 0 | 10
1307 | ALIPURDUAR | Northern Mechanical Division II | SISHA JUMRHA PIPED WATER SUPPLY SCHEME , SM/12753 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SISHU JUMRHA water supply scheme, TW no I , II and III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | 2357/NMD-II | 07/08/2023 | 30 | GEETA CONSTRUCTION | 27.96 | 0 | 0 | 100
1308 | ALIPURDUAR | Alipurduar Division | SISHA JUMRHA PIPED WATER SUPPLY SCHEME , SM/12753 | New | Material Requisition To Resource Division | 113/ALD | 10/01/2024 | 0 | Resource Division | 16.53 | 0 | 0 | 0
1309 | ALIPURDUAR | Alipurduar Division | SISHA JUMRHA PIPED WATER SUPPLY SCHEME , SM/12753 | New | 3 nos. of Tube well Boring by ODEX-165 Method of drilling at HW site, 2nd TW and 3rd site site and Constructions of 350 Cum OHR at HW site inclu. soil testing , construction of pump house and boundary wall at H/W, 2nd site and 3rd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for SISHA JUMRHA PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 3576/ALD | 27/03/2023 | 902 | DILIP MAHATO | 539.73 | 116.21 | 21.53 | 23
1310 | ALIPURDUAR | Northern Mechanical Division II | SISHA JUMRHA PIPED WATER SUPPLY SCHEME , SM/12753 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1311 | ALIPURDUAR | Alipurduar Division | SISHA JUMRHA PIPED WATER SUPPLY SCHEME , SM/12753 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1048/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
1312 | ALIPURDUAR | Northern Mechanical Division II | SISHA JUMRHA PIPED WATER SUPPLY SCHEME , SM/12753 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini, Madarihat -Birpara ,kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1332/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
1313 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Kumargram PWSS, Kumargram Block under Alipurduar Division, PHE Dte. | 1009/ALD | 15/07/2022 | 60 | DILIP MAHATO | 43.79 | 13.32 | 30.41 | 6
1314 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Providing House connection for KUMARGRAM water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | 857/ALD | 14/10/2020 | 30 | ASHIM KUMAR CHAKRABORTY | 4.98 | 4.98 | 50 | 8
1315 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | 2764/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 11.6 | 50 | 60
1316 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Restoration of Laying distribution system by replacing of Damaged AC pipeline with UPVC pipe of Kumargram WSS under Alipurduar Division, PHE Dte. | 1004/ALD | 15/07/2022 | 30 | DILIP MAHATO | 4.92 | 4.65 | 100 | 8
1317 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | NEW CONNECTION FOR TUTURIKHANDA | 394/22-23/PFMS | 21/12/2022 | 0 | WBSEDCL | 0.08 | 0 | 0 | 0
1318 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Soil investigation work at 4 different places of Kumargram within Alipurduar District under Alipurduar Division PHE Dte. | 1502/ALD | 05/09/2022 | 30 | MOYTEC | 4.88 | 4.88 | 100 | 7
1319 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Repairing and renovation of pump house, boundary wall and construction of new toilet of 2nd T/W site at Kumargram Water Supply Scheme under Alipurduar Division, PHE Dte. | 1944/ALD | 17/10/2022 | 60 | TAPASH DAS | 4.73 | 3.99 | 100 | 8
1320 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Preparation of detailed Additional cost Requirement D.P.R. booklets in connection to various PWSS under Kumargram and Kalchini Block under Alipurduar Division P.H.E Dte. | 1204/ALD | 07/08/2023 | 30 | ANIK BHATTACHARJEE | 0.78 | 0.78 | 100 | 100
1321 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Material Requisition To Resource Division | 1702/ALD | 21/09/2022 | 0 | Resource Division | 61.6 | 0 | 0 | 0
1322 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Material Requisition To Resource Division | 3483/ALD | 23/03/2023 | 0 | Resource Division | 61.6 | 0 | 0 | 0
1323 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Material Requisition To Resource Division | 2721/ALD | 13/12/2023 | 0 | Resource Division | 97.75 | 0 | 0 | 0
1324 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Tube well boring by ODEX-165, Construction of pump house and boundary wall including laying distribution system with new UPVC pipeline with rising and delivery line connection, Providing FHTC and other allied works for KUMARGRAM PWSS under Alipurduar Division, PHE Dte. | 3000/ALD | 06/02/2023 | 180 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 1152.29 | 340.71 | 29.57 | 50
1325 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Laying of rising main line /distribution pipeline, supply of DI pipe and specials, horizontal boring by HDD method, bridge and culvert crossing, specials repair with trial run of pipeline and allied works at Aug. of Kumargram WSS under Alipurduar Division, PHE Dte. | 689/ALD | 07/03/2024 | 270 | HARI CONSTRUCTION | 40.9 | 0 | 0 | 0
1326 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Construction of 250cum OHR for KUMARGRAM ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | 1489/ALD | 05/09/2022 | 720 | GOUTAM KUMAR DAS | 57.3 | 27.18 | 51.4 | 95
1327 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Construction of 150cum. OHR for KUMARGRAM ZONE-IV Water Supply Scheme under Alipurduar Division, PHE Dte. | 1486/ALD | 05/09/2022 | 180 | MATRI ENTERPRISE | 50.41 | 39.75 | 86.15 | 100
1328 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Construction of OHR 200cum for KUMARGRAM ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | 1487/ALD | 05/09/2022 | 180 | S.G ENTERPRISE | 55.09 | 40.92 | 87.8 | 100
1329 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Construction of OHR 200cum for KUMARGRAM ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | 1488/ALD | 05/09/2022 | 720 | UNIVERSAL ENTERPRISES | 55.33 | 35.44 | 74.42 | 100
1330 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Material Requisition To Resource Division | 3950/ALD | 26/11/2024 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1331 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | New Service Connection Charges for AUGMENTATION OF KUMARGRAM (Uttar Haldibari) pwss ph NO-I Zone-III | BP-289/24-25 | 22/08/2024 | 0 | WBSEDCL | 3.22 | 0 | 0 | 0
1332 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | New Service Connection Charges for AUGMENTATION OF KUMARGRAM (AMARPUR) pwss PH NO-I Zone-IV | BP-290/24-25 | 22/08/2024 | 0 | WBSEDCL | 5.75 | 0 | 0 | 0
1333 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | New service connection charges for Aug of Kumargram Z-I, P/H-I under NMD-II | BP-443/24-25 | 16/12/2024 | 0 | WBSEDCL | 6.26 | 0 | 0 | 0
1334 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
1335 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | New service connection charges for AUG of Kumargram Zone-IV, P/H-II(Amarpur) under NMD-II | BP-443/24-25 | 16/12/2024 | 0 | WBSEDCL | 7.59 | 0 | 0 | 0
1336 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | New Service Connection Charges for AUGMENTATION OF KUMARGRAM (Uttar Haldibari) pwss PH NO-II Zone-III | BP-288/24-25 | 22/08/2024 | 0 | WBSEDCL | 4.46 | 0 | 0 | 0
1337 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR MADHYA HALDIBARI PWSS ZONE-II P/H NO-II | BP-2023-24-642 | 29/02/2024 | 0 | WBSEDCL | 12.17 | 0 | 0 | 0
1338 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | NEW SERVICE CONNECTION FOR MADHYA HALDIBARI PWSS ZONE-II P/H NO-I | BP-2023-24-643 | 29/02/2024 | 0 | WBSEDCL | 6.22 | 0 | 0 | 0
1339 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of KUMARGRAM Water Supply Scheme TW No.-I,II,III,IV,V,VI,VII and VIII under NMD-II,PHE.Dte,APD | 2512/NMD-II | 14/08/2023 | 829 | ALPHA ENTERPRISE | 93.39 | 0 | 0 | 70
1340 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte..(from 01.02.2024 to 31.01.2025) | 372/ALD | 31/01/2024 | 366 | CHANDAN KIRTONIA | 4.8 | 0 | 0 | 0
1341 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1342 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Repairing of pump house at headwork site (existing) of Kumargram PWSS under Alipurduar Division, PHE Dte. | 5061/ALD | 18/02/2025 | 60 | DULAL DAS | 1.35 | 0 | 0 | 100
1343 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME , SM/11985 | Augmentation | Repairing of pump house at 3rd site (existing) of Kumargram PWSS under Alipurduar Division, PHE Dte. | 5063/ALD | 18/02/2025 | 60 | DULAL DAS | 1.05 | 0 | 0 | 100
1344 | ALIPURDUAR | Northern Mechanical Division II | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Buxa Forest (Raja bhatKhawa) water supply scheme, TW no I of Zone-I and TW-I and II of Zone-II and TW No-I of Zone-III of under NMD-II, PHE Dte.APD | 2418/NMD-II | 10/08/2023 | 30 | M/S P.P ELECTRICALS | 38.78 | 0 | 0 | 0
1345 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Providing balance FHTC from existing distribution system as per specification for BUXA FOREST (RAJABHATKHAWA) PWSS under Alipurduar Division, PHE Dte. | 2416/ALD | 09/11/2023 | 60 | SHIB RATAN BHOWMIK | 17.96 | 0 | 0 | 0
1346 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Material Requisition To Resource Division | 3047/ALD | 08/02/2023 | 0 | Resource Division | 61.86 | 0 | 0 | 0
1347 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Material Requisition To Resource Division | 1259/ALD | 10/08/2023 | 0 | Resource Division | 61.75 | 0 | 0 | 0
1348 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Cons. 4 nos Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Cons. of 250 cum OHR as per Departmental Design & drawing, Pump House , Boundary Wall, Path way, Providing FHTC, Soil Testing and other allied works for BUXA FOREST(RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | 1112/ALD | 28/07/2023 | 644 | CAPITAL ENGINEERS | 518.6 | 0 | 0 | 30
1349 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Payment for boundary demarcation and construction of boundary pillar for the principal ( stage-I) approval for diversion of forest land of area 0.157 ha for Buxa forest PwSS ( Z-II ) Garo BastyUnder Proposal No: FP/WB/Others/443377/2023 | 156/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.94 | 0 | 0 | 0
1350 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Payment against proposal No : FP/WB/Others /442047/2023-compensatory Levies ( Demand Note)against in- principal ( stage-I) approval of Gravity based WSS for boundary demarcation and construction of boundary pillar for Buxa forest PWSS under JJM at Uttar Poro Forest village -reg | 149/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.52 | 0 | 0 | 0
1351 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Payment for compensatory afforestation under proposal no : FP/WB/Others/443377/2023-Compensatory levies ( Demand note) against In - Principal ( Stage-I) approval of Water supply scheme for Buxa Forest PWSS ( Z-II) Garo Basty under jal Jeevan Mission at Garo Basti Forest Village- reg | 155/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0 | 0
1352 | ALIPURDUAR | Northern Mechanical Division II | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | NEW SERVICE CONNECTION CHARGES FOR BUXA FOREST ZONE-2 PH NO-2 | BP-172/24-25 | 03/07/2024 | 0 | WBSEDCL | 4.94 | 0 | 0 | 0
1353 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | payment for boundary demarcation and constuction of boundary pillar for the principal ( Stage - I ) approval for diversion of forest land of .0232 ha area for Buxa forest PWSS ( Z-II) Panijhora under JJM at Panijhora forest village - reg under Proposal No: FP/WB/Others /443397/2023 | 160/24-25/PFMS | 09/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.52 | 0 | 0 | 0
1354 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Payement aginst proposal no : FP/WB/Others/ 442047/2023 of Net Present Value of 0.0232 ha ( As per Annexure-1) forest land for diversion for gravity base water supply scheme for Buxa forest PWSS at Uttor Poro under JJM under BTR(WEST) Diivision under WDPO range Poro7Compartment | 150/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.59 | 0 | 0 | 0
1355 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Cost of raising and maintenance of the compensatory afforestation for Ca area 0.04 ha ( 100 trees plantation and maintenance for 10 years) against proposed diversion of forrest land for water supply scheme Buxa forest PWSS ( Z-II) panijhora under JJM at panijhora forest Village reg under proposal NO: FP/WB/Others/443397/2023 | 159/24-25/PFMS | 09/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0 | 0
1356 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Payment for compensatory afforestation under proposal no FP/WB/others/443394/2023-C0mpenatory Levies(demand note) against In- principal of water supply scheme Buxa forest pwss ( Z-II)Pampu Basty under Jal Jeevan misson at pampu basti forest village - reg as per annexture-2 | 153/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0 | 0
1357 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Payment of Net Present Value ( NPV) against proposal No : FP/WB/Others/ 443397/2023 - Compensatory Levies ( Demand Note) against in- Principal ( Stage-I) approval of water supply Scheme for Buxa Forest PWSS (Z-II) Panijhora under JJM at Panijhora forest village reg | 158/24-25/PFMS | 09/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.59 | 0 | 0 | 0
1358 | ALIPURDUAR | Northern Mechanical Division II | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | NEW SERVICE CONNECTION CHARGES FOR BUXA FOREST PWSS ZONE-3 TW NO-1 | BP-173/24-25 | 03/07/2024 | 0 | WBSEDCL | 5.98 | 0 | 0 | 0
1359 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Payment of Net Present value ( NPV) against proposal no : FP/WB/Others/443377/2023- Compensatory levies ( Demand Note ) against In Principal ( Stage-I) approval of water supply scheme for Buxa Forest PWSS ( Z-II)Garo Basty under JJM at Garo Basti Forest Village- reg | 157/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 17.54 | 0 | 0 | 0
1360 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Payment as per annexure -2 against proposal No : FP/WB/Others/442047/2023 for raising and maintenance of the compensatory afforestation ( 100 trees plantation and maintence for 1o years ) agaist proposed diversion of forest land forgravity based piped water supply scheme for Buxa forest PWSS under JJm at Uttar Poro | 151/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0 | 0
1361 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Payment for boundary demarcation and construction of boundary pillar for the principal ( stage-I) approval for diversion of the forest land of area 0.0232 ha for water supply scheme Buxa forest PWSS(Z-II) Pampu Basty under proposal No :FP/WB/Others/443394/2023 | 152/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.52 | 0 | 0 | 0
1362 | ALIPURDUAR | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Payment of Net Present value( NPV) against proposal no:FP/WB/Others /443394/2023- Cornpensatory levies {demand rote) againstIn-principal (Stage-l) approval of Water Supply Scheme Buxa forest PWSS {Z-Il} Pampu Basty under,Jal Jeelan Mission at Pampu Basti Forest Village - reg"(Annexure- I) | 154/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.59 | 0 | 0 | 0
1363 | ALIPURDUAR | Northern Mechanical Division II | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Yard lighting arrangement at Head Work Site for Different PWSS (NIMTI DOMOHANI and Others) under JJM in the BLOCK: Kalchini, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1386/NMD-II | 26/06/2025 | 30 | AMUSAR IMPEX PVT LTD | 22.95 | 0 | 0 | 0
1364 | ALIPURDUAR | Northern Mechanical Division II | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME , SM/13249 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1365 | ALIPURDUAR | Alipurduar Division | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14217 | New | Cons. of Rig bored TW(2nos) by ODEX-165 method of drilling at HW and 2nd site, cons of 100 cum OHR at HW including soil testing, cons. of P/H and B/W at HW,2nd site, Laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Dakshin Rangalibazna PWSS under Birpara Sub-Division, Alipurduar Division, PHE DTE. | 3396/ALD | 16/03/2023 | 180 | S.G. CONSTRUCTION | 247.26 | 77.23 | 31.23 | 32
1366 | ALIPURDUAR | Alipurduar Division | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14217 | New | Providing FHTC from existing distribution system as per specification for Dakshin Rangalibazna PWSS under Alipurduar Division, PHE Dte. | 2134/ALD | 03/10/2023 | 30 | MANI PRADHAN | 3.25 | 0 | 0 | 0
1367 | ALIPURDUAR | Alipurduar Division | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14217 | New | Material Requisition To Resource Division | 3487ALD | 23/03/2023 | 0 | Resource Division | 4.89 | 0 | 0 | 0
1368 | ALIPURDUAR | Alipurduar Division | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14217 | New | Material Requisition To Resource Division | 2702 | 12/12/2023 | 0 | Resource Division | 68.94 | 0 | 0 | 0
1369 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14217 | New | NEW CONNECTION SERVICE FOR DAKSHIN RANGALIBAZNA PWSS P/H NO II APPLICATION NO 4003065179 | BP-2023-24-381 | 27/09/2023 | 0 | WBSEDCL | 11.63 | 0 | 0 | 0
1370 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14217 | New | NEW CONNECTION SERVICE FOR DAKSHIN RANGALIBAZNA PWSS P/H NO I APPLICATION NO 4003065178 | BP-2023-24-382 | 27/09/2023 | 0 | WBSEDCL | 11.71 | 0 | 0 | 0
1371 | ALIPURDUAR | Alipurduar Division | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14217 | New | Material Requisition To Resource Division | 112/ALD | 10/01/2024 | 0 | Resource Division | 4.89 | 0 | 0 | 0
1372 | ALIPURDUAR | Alipurduar Division | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14217 | New | Material Requisition To Resource Division | 3988/ALD | 27/11/2024 | 0 | Resource Division | 4.89 | 0 | 0 | 0
1373 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14217 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Dakhshin Rangalibazna Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | 2464/NMD-II | 11/08/2023 | 605 | S.D CONCERN WORKSHOP | 20.48 | 0 | 0 | 49
1374 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14217 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1334/NMD-II | 18/06/2025 | 90 | M. M. ENTERPRISE | 16.38 | 0 | 0 | 0
1375 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME , SM/14217 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1376 | ALIPURDUAR | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME , SM/14210 | New | QUOTATION FOR NSC AT FOSKARDANGA TW NO-II | BP-2023-24-370 | 27/09/2023 | 0 | WBSEDCL | 13.41 | 0 | 0 | 0
1377 | ALIPURDUAR | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME , SM/14210 | New | QUOTATION FOR NSC AT FOSKADANGA PH NO-I | BP-2023-24-371 | 27/09/2023 | 0 | WBSEDCL | 14.07 | 0 | 0 | 0
1378 | ALIPURDUAR | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME , SM/14210 | New | Providing FHTC from existing distribution system as per specification for Foskadanga PWSS PWSS under Alipurduar Division, PHE Dte. | 1888/ALD | 07/09/2023 | 30 | MADHAB SAHA | 7 | 0 | 0 | 70
1379 | ALIPURDUAR | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME , SM/14210 | New | Material Requisition To Resource Division | 116/ALD | 10/01/2024 | 0 | Resource Division | 4.21 | 0 | 0 | 0
1380 | ALIPURDUAR | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME , SM/14210 | New | Material Requisition To Resource Division | 3986/ALD | 27/11/2024 | 0 | Resource Division | 4.21 | 0 | 0 | 0
1381 | ALIPURDUAR | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME , SM/14210 | New | Material Requisition To Resource Division | 4258/ALD | 13/12/2024 | 0 | Resource Division | 1.53 | 0 | 0 | 0
1382 | ALIPURDUAR | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME , SM/14210 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR (100cum) including soil testing, Laying Of Rising Main, Distribution System and providing FHTC for Foskadanga PWSS Under Alipurduar Division, PHE Dte. | 3572/ALD | 27/03/2023 | 737 | MADHAB SAHA | 321.67 | 0 | 0 | 10
1383 | ALIPURDUAR | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME , SM/14210 | New | Laying of new HDPE pipeline for providing FHTC and land filling at Headwork site & 2nd site at Foskadanga PWSS under Alipurduar Division, PHE Dte. | 439/ALD | 30/04/2025 | 60 | MADHAB SAHA | 52.23 | 0 | 0 | 0
1384 | ALIPURDUAR | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME , SM/14210 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar-I Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 822/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
1385 | ALIPURDUAR | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME , SM/14210 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1386 | ALIPURDUAR | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME , SM/14210 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for FOKSHADANGA water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | 2457/NMD-II | 11/08/2023 | 584 | SAIKAT SINHA | 18.31 | 0 | 0 | 100
1387 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Extension of UPVC pipeline for Putimari WSS under Dakshin Dhalkar Mousa under Alipurduar Division, P.H.E. Dte. | 2305/ALD | 25/01/2022 | 30 | PRAPTI DUTTA | 5.04 | 4.55 | 90.28 | 95
1388 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Providing FHTC including Rising main and laying distribution system for PUTIMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2388/ALD | 31/01/2022 | 60 | HARI CONSTRUCTION | 71.64 | 68.88 | 100 | 94
1389 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-4 Venue : Putimari 2)Mechpara 3)Mathura 4)Gangutia. | 2124/ALD | 05/01/2022 | 30 | MABCO CONSULTANT, | 4.86 | 4.86 | 100 | 94
1390 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Extension of UPVC pipeline for Putimari WSS under Dakshin Shibkata Mousa under Alipurduar Division, P.H.E. Dte. | 2304/ALD | 25/01/2022 | 30 | HARI CONSTRUCTION | 5.05 | 5.05 | 100 | 91
1391 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Extension of UPVC pipeline for Putimari WSS under Putimari Mousa under Alipurduar Division, P.H.E. Dte. | 2313/ALD | 25/01/2022 | 30 | AASHIRBAD ENTERPRISE | 5.04 | 5.04 | 100 | 93
1392 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Extension of UPVC pipeline for Putimari WSS under Uttar Dhalkar Mousa under Alipurduar Division, P.H.E. Dte. | 2314/ALD | 25/01/2022 | 30 | PRAPTI DUTTA | 5.04 | 5.04 | 100 | 92
1393 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Extension of UPVC pipeline for Putimari WSS under Putimari Mousa under Alipurduar Division, P.H.E. Dte. | 2312/ALD | 25/01/2022 | 30 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.04 | 5.04 | 100 | 94
1394 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Laying Distribution line with UPVC pipe at PUTIMARI WSS under Alipurduar Division , PHE Dte(Part - III) | 434/ALD | 13/05/2022 | 30 | HARI CONSTRUCTION | 5.02 | 4.74 | 100 | 93
1395 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Putimari Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 698/ALD | 08/06/2022 | 30 | TAPASH DAS | 4.83 | 4.83 | 50 | 93
1396 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Supply & delivery of Desktop CPU-AMD Ryzen5 2400, H320 Gigabyte Mother Board, 8GB DDR4 Ram, ATX Cabinet, SMPS 450 Watt,240 GB SSD,1 TB HDD & Epson printer L-1100 for the use at office of the Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte. | 1152/ALD | 02/08/2022 | 7 | CYBER NET | 0.99 | 0.99 | 100 | 94
1397 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Laying distribution system for Putimari PWSS under Alipurduar Division, PHE Dte. | 1104/ALD | 29/07/2022 | 30 | HARIDAS GHOSH | 2.92 | 2.92 | 100 | 95
1398 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Quotation for new service connection at putimari W/SS TW No III Application No-4002956347 |  | 04/08/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1399 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Quotation for new service connection for PUTIMARI (Aug) Application no. 40025956347 | BP-43/22-23 | 08/08/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1400 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Construction of Pump House, Boundary Wall and laying distribution system for PUTIMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2386/ALD | 31/01/2022 | 90 | TAPASH KUMAR BHOWMICK | 93.77 | 93.18 | 99.37 | 96
1401 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Providing balance FHTC for Putimari PWSS under Alipurduar Division, PHE Dte. | 1558/ALD | 23/08/2023 | 30 | HARI CONSTRUCTION | 3.35 | 0 | 0 | 0
1402 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for PUTIMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2387/ALD | 31/01/2022 | 60 | TAPASH KUMAR BHOWMICK | 76.84 | 75.28 | 100 | 97
1403 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 50 | 100 | 100
1404 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Putimari Water Supply Scheme TW No.-III under NMD-II,PHE.Dte, Alipurduar. | 407/NMD-II | 22/03/2022 | 30 | MALAY KUMAR SAHA | 2.39 | 0 | 0 | 100
1405 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Putimari Water Supply Scheme TW No.-III under NMD-II,PHE Dte Alipurduar. | 533/NMD-II | 20/04/2022 | 30 | TAPAN BISWAS | 7.83 | 5.95 | 77.08 | 100
1406 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Providing FHTC including Rising main and laying distribution system for PUTIMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. |  | 29/02/2024 | 0 | HARI CONSTRUCTION | 1.21 | 0 | 0 | 0
1407 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Construction of 350cum OHR for Putimari TG Water Supply Scheme under Alipurduar Division, PHE Dte. | 2188/ALD | 11/01/2022 | 429 | TAPASH KUMAR BHOWMICK | 71.4 | 53.44 | 74.85 | 95
1408 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Putimari PWSS, Alipurduar Block under Alipurduar Division, PHE Dte. | 2291/ALD | 24/01/2022 | 1200 | HARI CONSTRUCTION | 45.52 | 42.55 | 93.48 | 100
1409 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | New Laying of UPVC/DI pipeline, Providing FHTC and other allied works for Augmentation of Putimari PWSS under Alipurduar Division, PHE Dte. | 1221/ALD | 10/08/2022 | 1020 | HARI CONSTRUCTION | 38.9 | 25.91 | 66.59 | 100
1410 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME , SM/09884 | Augmentation | Supply, delivery of standby Automatically controlled diaphragm type chlorinator for accurate dosing of chlorine solution at Putimari Water Supply Scheme ,in the dist. of COOCHBEHAR under NMD-II, PHE. Dte. Alipurduar. | 270/NMD-II | 16/02/2023 | 15 | DILIP MAHATO | 1.8 | 0 | 0 | 100
1411 | ALIPURDUAR | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14212 | New | Providing balance FHTC from existing distribution system as per specification for BHATPARA TG PWSS under Alipurduar Division, PHE Dte. | 2185/ALD | 06/10/2023 | 60 | MAHENDRA CHHETRI | 17.77 | 0 | 0 | 0
1412 | ALIPURDUAR | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14212 | New | Material Requisition To Resource Division | 1270/ALD | 11/08/2023 | 0 | Resource Division | 17.99 | 0 | 0 | 0
1413 | ALIPURDUAR | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14212 | New | Material Requisition To Resource Division | 110/ALD | 10/01/2024 | 0 | Resource Division | 14.3 | 0 | 0 | 0
1414 | ALIPURDUAR | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14212 | New | Material Requisition To Resource Division | 99/ALD | 10/01/2024 | 0 | Resource Division | 14.3 | 0 | 0 | 0
1415 | ALIPURDUAR | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14212 | New | Material Requisition To Resource Division | 4248/ALD | 13/12/2024 | 0 | Resource Division | 3.63 | 0 | 0 | 0
1416 | ALIPURDUAR | Northern Mechanical Division II | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14212 | New | New Service connection for Bhatpara TG PWSS, P/H-II | BP-2023-24-532 | 11/01/2024 | 0 | WBSEDCL | 5.26 | 0 | 0 | 0
1417 | ALIPURDUAR | Northern Mechanical Division II | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14212 | New | New Service Connection Charge for Bhatpara TG PWSS P/HNO-I | BP-2023-24-601 | 15/02/2024 | 0 | WBSEDCL | 21.27 | 0 | 0 | 0
1418 | ALIPURDUAR | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14212 | New | T/W Boring by ODEX-165 Method of drilling at HW FIRST TW site including LDS with new HDPE P/L, Cons. of 250 Cum OHR as per Departmental Design and drawing including soil investigation works, 2nos. pumphouse and boundary wall, providing FHTC and others allied works for BHATPARA TG PWSS under Alipurduar Division PHE DTE | 2969/ALD | 31/01/2023 | 1260 | MAHENDRA CHHETRI | 362.78 | 128.59 | 35.44 | 90
1419 | ALIPURDUAR | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14212 | New | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.02.2023 to 30.04.2023) | 2952/ALD | 24/01/2023 | 90 | NIRANJAN KIRTANIA | 0.7 | 0 | 0 | 0
1420 | ALIPURDUAR | Northern Mechanical Division II | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14212 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1421 | ALIPURDUAR | Northern Mechanical Division II | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14212 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1331/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
1422 | ALIPURDUAR | Northern Mechanical Division II | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14212 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bhatpara TG water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. APD | 2414/NMD-II | 10/08/2023 | 570 | SARKAR ELECTRIC | 21.92 | 0 | 0 | 90
1423 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Retrofitting and Extension of pipeline for Kalchini area under DIMA PWSS at Kalchini Block under Alipurduar Division. PHE Dte. Part-B | 1769/ALD | 19/02/2021 | 60 | RAMESH SHARMA | 49.52 | 0 | 0 | 93
1424 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 3rd & 4th site including laying distribution system , Rising main and providing FHTC for KALCHINI TG ZONE-II PWSS Under Alipurduar Division PHE DTE. | 3227/ALD | 27/02/2023 | 120 | SHREE RANISATI ENTERPRISE | 179.1 | 0 | 0 | 0
1425 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site & 2nd site including laying distribution system and providing FHTC for KALCHINI TG ZONE-II PWSS Under Alipurduar Division PHE DTE | 3228/ALD | 27/02/2023 | 120 | SHREE RANISATI ENTERPRISE | 179.69 | 0 | 0 | 0
1426 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Construction of 350cum OHR for Kalchini TG Water Supply Scheme under Alipurduar Division, PHE Dte. | 3233/ALD | 27/02/2023 | 180 | Z STAR COMMOTRADE PVT LTD. | 71.41 | 0 | 0 | 0
1427 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Material Requisition To Resource Division | 3484/ALD | 23/03/2023 | 0 | Resource Division | 36.96 | 0 | 0 | 0
1428 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Material Requisition To Resource Division | 1272/ALD | 11/08/2023 | 0 | Resource Division | 77.78 | 0 | 0 | 0
1429 | ALIPURDUAR | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | NEW CONNECTION SETRVICE FOR KALCHINI T.G.,PWSS P/H NO I,ZONE II, KALCHINI APPLICATION NO 4003208203 | BP-2023-24-380 | 27/09/2023 | 0 | WBSEDCL | 5.6 | 0 | 0 | 0
1430 | ALIPURDUAR | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | NEW SERVICE CONNECTION FOR KALCHINI TG PWSS P/H NO II,ZONE-II,KALCHINI APPLICATION NO 4003208210 | BP-2023-24-322 | 27/09/2023 | 0 | WBSEDCL | 9.42 | 0 | 0 | 0
1431 | ALIPURDUAR | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | NEW SERVIVCE CONNECTION FOR KALCHINI TG PWSS P/H NO II,ZONE-I,KALCHINI APPLICATION NO 4003208205 | BP-2023-24-321 | 27/09/2023 | 0 | WBSEDCL | 5.56 | 0 | 0 | 0
1432 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd & 3rd site including laying distribution system , Rising main and providing FHTC for KALCHINI TG ZONE-I PWSS Under Alipurduar Division PHE DTE. | 3229/ALD. | 27/02/2023 | 120 | SHREE RANISATI ENTERPRISE | 143.22 | 30 | 20.95 | 30
1433 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for KALCHINI TG ZONE-I PWSS Under Alipurduar Division PHE DTE | 3230/ALD. | 27/02/2023 | 240 | SHREE RANISATI ENTERPRISE | 190.87 | 40 | 20.96 | 10
1434 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Construction of 500cum OHR for Kalchini TG Water Supply Scheme under Alipurduar Division, PHE Dte. | 3234ALD | 27/02/2023 | 360 | SHREE RANISATI ENTERPRISE | 91.81 | 0 | 0 | 40
1435 | ALIPURDUAR | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for KALCHINI TG AREA Water Supply Scheme TW No.-I,II,III of Zone-I and TW No.-I,II,III,IV of Zone-II under NMD-II,Apd | 2490/NMD-II | 14/08/2023 | 30 | M/S P.P ELECTRICALS | 81.19 | 0 | 0 | 40
1436 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Supply of CIDF/CIPE pipes and specials & CI Jeffy Coupling for Kalchini TG Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 739/ALD | 12/03/2024 | 30 | MADHAB SAHA | 13.81 | 0 | 0 | 0
1437 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Retrofitting and Extension of pipeline for Kalchini area under DIMA PWSS at Kalchini Block under Alipurduar Division. PHE Dte. Part-A | 1768/ALD | 19/02/2021 | 60 | SUNDAR SING LAMA | 41.98 | 0 | 0 | 86
1438 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Conceptualization, design and implementing mass awareness generation through Wall writing at 22 nos. villages (Block - Madarihat) by dissemination of awareness generation IEC messages FHTC, Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation and WASH related issues as per guideline of JJM at Alipurduar district under Alipurduar Division, PHE Dte, Govt. of West Bengal.( SM/15482) | 753/ALD | 12/03/2024 | 30 | BARMAN ENTERPRISE | 5.27 | 0 | 0 | 100
1439 | ALIPURDUAR | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | New Service Connection for Kalchini TG PWSS, Zone-II, P/H-II | BP-2023-24-530 | 11/01/2024 | 0 | WBSEDCL | 7.15 | 0 | 0 | 0
1440 | ALIPURDUAR | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | New Service connection for Kalchini TG PWSS, Zone-II, P/H-IV | BP-2023-24-529 | 11/01/2024 | 0 | WBSEDCL | 5.43 | 0 | 0 | 0
1441 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
1442 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Reparing of Pump House at Headwork site of Kalchini PWSS Under Alipurduar Division PHE DTE. | 5421/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.98 | 0 | 0 | 0
1443 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Reparing of Pump House at 3nd site of Kalchini PWSS Under Alipurduar Division PHE DTE. | 5423/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.98 | 0 | 0 | 0
1444 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1445 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Reparing of Pump House at 2nd site of Kalchini PWSS Under Alipurduar Division PHE DTE. | 5422/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.93 | 0 | 0 | 0
1446 | ALIPURDUAR | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15482 | New | Road Restoration at kalchini Old Scheme area within Kalchini block under Alipurduar Division, PHE Dte. | 4536/ALD | 26/12/2024 | 60 | RK DISTRIBUTORS | 2.08 | 0 | 0 | 100
1447 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. , SM/15210 | Augmentation | Additional works in connection with yard lighting arrangement at Dalmore water supply scheme (Aug), P/H No. III under Northern Mechanical Division II, PHE Dte. | 147/AMSD | 06/07/2023 | 20 | M/S P.P ELECTRICALS | 1.93 | 0 | 0 | 100
1448 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. , SM/15210 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Dhumchipara TG Water Supply Scheme TW No.- I under NMD-II,PHE.Dte,Apd. | 2468/NMD-II | 11/08/2023 | 479 | M/S ANJALI ENTERPRISE | 14.86 | 0 | 0 | 100
1449 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. , SM/15210 | Augmentation | Construction of boulder apron for Dhumchipara PWSS for protection of existing Pump house under Alipurduar Division. | 744/ALD | 12/03/2024 | 45 | MANI PRADHAN | 3.59 | 0 | 0 | 50
1450 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. , SM/15210 | Augmentation | Nee Service Connection for Dhumchipara T.G PWSS | BP-2023-24-503 | 05/01/2024 | 0 | WBSEDCL | 6.73 | 0 | 0 | 0
1451 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. , SM/15210 | Augmentation | Construction of 2nos pump house, boundary wall, TW boring by ODEX-195 method of drilling for Augmentation of Dhumchipara PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 200/ALD | 16/01/2024 | 480 | MITHUN DAS | 54.27 | 0 | 0 | 50
1452 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. , SM/15210 | Augmentation | Replacement of damaged pipeline with HDPE and DI pipes for Dhumchipara PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/09896) | 823/ALD | 14/03/2024 | 60 | MONORAMA ENTERPRISE | 5.73 | 0 | 0 | 5
1453 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. , SM/15210 | Augmentation | Boring of TW, Construction of Pumphouse, Boundary wall, Laying of Distribution system for Augmentation of Dhumchipara PWSS under Alipurduar Division, PHE Dte. | 3324/ALD | 13/03/2023 | 840 | GIRIRAJ ENTERPRISE | 22.78 | 8.44 | 37.1 | 70
1454 | ALIPURDUAR | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | Material Requisition To Resource Division | 2775/ALD | 18/12/2023 | 0 | Resource Division | 18.81 | 0 | 0 | 0
1455 | ALIPURDUAR | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site, Soil investigation at OHR site, constructions of 500 Cum OHR at HW, construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Uma Charanpur PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 1873/ALD | 07/09/2023 | 270 | TAPASH KUMAR BHOWMICK | 608.41 | 0 | 0 | 37
1456 | ALIPURDUAR | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | Laying of rising main DI (K7), interconnection work with HDPE pipe , Construction of sluice valve chamber for Umacharanpur PWSS under Birpara Sub- Division ,Alipurduar Division PHE Dte. under North Bengal Circle-I PHE DTE. | 2061/ALD | 12/07/2024 | 300 | TAPASH KUMAR BHOWMICK | 101.24 | 0 | 0 | 90
1457 | ALIPURDUAR | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | Supply of CI Sluice Valve and Special & CI Jeffy Coupling for Umachndrapur Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 608/ALD | 29/02/2024 | 30 | MANSAROVAR CASTING | 11.95 | 0 | 0 | 85
1458 | ALIPURDUAR | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | New Service Connection Charges for UMACHARANPUR PWSS P/H NO-I,10 mile | BP-10/24-25 | 08/04/2024 | 0 | WBSEDCL | 12.04 | 0 | 0 | 0
1459 | ALIPURDUAR | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | New Service Connection for Umacharanpur PH NO-II PWSS | BP-276/24-25 | 22/08/2024 | 0 | WBSEDCL | 10.48 | 0 | 0 | 0
1460 | ALIPURDUAR | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Umacharanpur Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | 2476/NMD-II | 11/08/2023 | 30 | CINZANO | 21.9 | 0 | 0 | 0
1461 | ALIPURDUAR | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | Supply of CIDF Specials and Jeffy Coupling for Umacharanpur (SM/16114) WSS under Alipurduar Division, PHE Dte. | 4591/ALD | 03/01/2025 | 30 | TAPASH KUMAR BHOWMICK | 19.81 | 0 | 0 | 0
1462 | ALIPURDUAR | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1463 | ALIPURDUAR | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | Yard lighting arrangement at Head Work Site for Different PWSS (KADAMBINI TG and Others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1346/NMD-II | 19/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 23.98 | 0 | 0 | 0
1464 | ALIPURDUAR | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1344/NMD-II | 19/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
1465 | ALIPURDUAR | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1466 | ALIPURDUAR | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME , SM/16114 | New | Laying of HDPE pipeline (parallel and balance line ) at Umacharanpur PWSS under Alipurduar Division, PHE Dte. | 2077/ALD | 19/09/2025 | 75 | TAPASH KUMAR BHOWMICK | 80.25 | 0 | 0 | 0
1467 | ALIPURDUAR | Northern Mechanical Division II | BUXA PIPE WATER SUPPLY SCHEME , SM/16507 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for BUXA PWSS,TW No.-I and II under NMDII, PHE.Dte,Alipurduar. | 2532/NMD-II | 16/08/2023 | 30 | MUSTAFI CONCERN | 25.54 | 0 | 0 | 0
1468 | ALIPURDUAR | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME , SM/16507 | New | Material Requisition To Resource Division | 1260/ALD | 10/08/2023 | 0 | Resource Division | 2.17 | 0 | 0 | 0
1469 | ALIPURDUAR | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME , SM/16507 | New | Material Requisition To Resource Division | 102/ALD | 10/01/2024 | 0 | Resource Division | 16.34 | 0 | 0 | 0
1470 | ALIPURDUAR | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME , SM/16507 | New | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum, laying distribution system and providing FHTC at Buxa PWSS under Alipurduar Division, PHE Dte. | 3506/ALD | 23/03/2023 | 180 | ASHOK SAPKOTA | 30.8 | 0 | 0 | 100
1471 | ALIPURDUAR | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME , SM/16507 | New | Route surveying and revalidation of Household data with digitization of LDS for Lepchakha and Santalebari PWSS under Kalchini Block under Alipurduar Division, PHE Dte. | 1180/ALD | 26/06/2025 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.58 | 0 | 0 | 0
1472 | ALIPURDUAR | Northern Mechanical Division II | BUXA PIPE WATER SUPPLY SCHEME , SM/16507 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1334/NMD-II | 18/06/2025 | 90 | M. M. ENTERPRISE | 16.38 | 0 | 0 | 0
1473 | ALIPURDUAR | Northern Mechanical Division II | BUXA PIPE WATER SUPPLY SCHEME , SM/16507 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1474 | ALIPURDUAR | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME , SM/16507 | New | LAYING OF 25 MM DIA PP-R PIPES FROM TASHIGAON RIVER TO LEPCHAKHA AND LEPCHAKHA TO DUMBA AND OTHER ALLIED WORKS UNDER JJM PROGRAMME UNDER ALIPURDUAR DIVISION, PHE DTE. | 5042/ALD | 17/02/2025 | 120 | S.D. PROJECT | 8.33 | 0 | 0 | 100
1475 | ALIPURDUAR | Alipurduar Division | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME , SM/15914 | New | Providing FHTC from existing distribution system as per specification for Uttar Barajhar PWSS PWSS under Alipurduar Division, PHE Dte. | 1887/ALD | 07/09/2023 | 30 | TAPASH DAS | 4.24 | 0 | 0 | 0
1476 | ALIPURDUAR | Northern Mechanical Division II | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME , SM/15914 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Uttar Barajhar FOREST Water Supply Scheme TW No.- I AND II under NMD-II,PHE.Dte,APD. | 2809/NMD-II | 09/10/2023 | 30 | SUBODH KUMAR BANIK | 19.86 | 0 | 0 | 0
1477 | ALIPURDUAR | Alipurduar Division | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME , SM/15914 | New | Material Requisition To Resource Division | 3014/ALD, | 07/02/2023 | 0 | Resource Division | 10.87 | 0 | 0 | 0
1478 | ALIPURDUAR | Alipurduar Division | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME , SM/15914 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new UPVC pipeline , Constructions of 100 Cum OHR as per Departmental Design & drawing including soil investigation works, TWO nos. pump house & boundary wall, providing FHTC and others allied works for UTTAR BARAJHAR FOREST PWSS Under Alipurduar Division PHE DTE. (2nd call) | 134/ALD | 24/04/2023 | 180 | TAPASH DAS | 193.2 | 15 | 7.76 | 15
1479 | ALIPURDUAR | Alipurduar Division | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME , SM/15914 | New | Material Requisition To Resource Division | 103/ALD | 10/01/2024 | 0 | Resource Division | 3.49 | 0 | 0 | 0
1480 | ALIPURDUAR | Alipurduar Division | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME , SM/15914 | New | Material Requisition To Resource Division | 3983/ALD | 27/11/2024 | 0 | Resource Division | 3.49 | 0 | 0 | 0
1481 | ALIPURDUAR | Northern Mechanical Division II | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME , SM/15914 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1482 | ALIPURDUAR | Northern Mechanical Division II | Implementation of Affordable IOT System at Dalmore-Ramjhora TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. , SM/16906 | IOT | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Different Block of Alipurduar and Coochbehar District in West Bengal | 807/NMD-II | 04/03/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 594.37 | 0 | 0 | 0
1483 | ALIPURDUAR | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME , SM/16819 | New | Material Requisition To Resource Division | 1476/ALD | 16/08/2023 | 0 | Resource Division | 21.37 | 0 | 0 | 0
1484 | ALIPURDUAR | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME , SM/16819 | New | Material Requisition To Resource Division | 2773/ALD | 18/12/2023 | 0 | Resource Division | 7.84 | 0 | 0 | 0
1485 | ALIPURDUAR | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME , SM/16819 | New | Material Requisition To Resource Division | 2700/ALD | 12/12/2023 | 0 | Resource Division | 84.45 | 0 | 0 | 0
1486 | ALIPURDUAR | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME , SM/16819 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , soil investigation at OHR site, constructions of 300 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Lachhimandabri PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 1172/ALD | 03/08/2023 | 900 | M/S T M CONSTRUCTION | 433.46 | 0 | 0 | 35
1487 | ALIPURDUAR | Northern Mechanical Division II | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME , SM/16819 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of LACHHIAMANDABRI water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | 2571/NMD-II | 22/08/2023 | 30 | DEY ENTERPRISE (MALDA) | 22.2 | 0 | 0 | 100
1488 | ALIPURDUAR | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME , SM/16819 | New | Supply of CIDF/CIPE pipes and specials & CI Jeffy Coupling for Lachman Dabri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 696/ALD | 07/03/2024 | 300 | HARIDAS GHOSH | 18.07 | 0 | 0 | 65
1489 | ALIPURDUAR | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME , SM/16819 | New | Material Requisition To Resource Division | 3952/ALD | 26/11/2024 | 0 | Resource Division | 7.84 | 0 | 0 | 0
1490 | ALIPURDUAR | Northern Mechanical Division II | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME , SM/16819 | New | New Service Connection Charges for Lacchi Mendabari, Lacchi Mendabari PWSS, TW No-I Under NMD-II | BP-431/24-25 | 16/12/2024 | 0 | WBSEDCL | 3.47 | 0 | 0 | 0
1491 | ALIPURDUAR | Northern Mechanical Division II | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME , SM/16819 | New | Yard lighting arrangement at Head Work Site for Different PWSS (KADAMBINI TG and Others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1346/NMD-II | 19/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 23.98 | 0 | 0 | 0
1492 | ALIPURDUAR | Northern Mechanical Division II | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME , SM/16819 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1344/NMD-II | 19/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
1493 | ALIPURDUAR | Northern Mechanical Division II | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME , SM/16819 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1494 | ALIPURDUAR | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. Part-B | 394/ALD | 19/05/2023 | 120 | TAPASH KUMAR BHOWMICK | 4.67 | 4.67 | 100 | 0
1495 | ALIPURDUAR | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | Material Requisition To Resource Division | 1478/ALD | 16/08/2023 | 0 | Resource Division | 40.6 | 0 | 0 | 0
1496 | ALIPURDUAR | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | Material Requisition To Resource Division | 2772/ALD | 18/12/2023 | 0 | Resource Division | 7.29 | 0 | 0 | 0
1497 | ALIPURDUAR | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | Supply of CIDF/CIPE Pipes and Special & CI Jeffy Coupling for Tasati TG Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 741/ALD | 12/03/2024 | 30 | MADHAB SAHA | 12.19 | 0 | 0 | 0
1498 | ALIPURDUAR | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | Material Requisition To Resource Division | 3954/ALD | 26/11/2024 | 0 | Resource Division | 7.29 | 0 | 0 | 0
1499 | ALIPURDUAR | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | NEW SERVICE CONNECTION CHARGES FOR TASTI TG ( NEAR- FOOTBALL MATH) PWSS PH NO-II | BP-142/24-25 | 11/06/2024 | 0 | WBSEDCL | 5.12 | 0 | 0 | 0
1500 | ALIPURDUAR | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | NEW SERVICE CONNECTION CHARGES FOR TASTI TG (NEAR-RATION SHOP) PWSS PH NO-I. | BP-143/24-25 | 11/06/2024 | 0 | WBSEDCL | 4.53 | 0 | 0 | 0
1501 | ALIPURDUAR | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , constructions of 200 Cum OHR at HW including soil investigation, construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Tasti Tea Garden PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE.(2nd call) | 975/ALD | 12/07/2023 | 994 | MADHAB SAHA | 298.87 | 0 | 0 | 15
1502 | ALIPURDUAR | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | Supply, delivery, installation, commissioning andtrial run of electro-mechanical components alongwith Cu wound line voltage corrector forRejuvenation of TASTI T.G water supply scheme,TW no I AND II under JJM under NMD-II,PHE Dte.APD. | 2542/NMD-II | 16/08/2023 | 30 | MADHAB SAHA | 21.86 | 0 | 0 | 50
1503 | ALIPURDUAR | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1504 | ALIPURDUAR | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1344/NMD-II | 19/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
1505 | ALIPURDUAR | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1506 | ALIPURDUAR | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16822 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1629/ALD | 04/08/2025 | 60 | NARENDRA BHADANI. | 18.13 | 0 | 0 | 0
1507 | ALIPURDUAR | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. | 395/ALD | 19/05/2023 | 120 | TAPASH KUMAR BHOWMICK | 4.29 | 0 | 0 | 20
1508 | ALIPURDUAR | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | Material Requisition To Resource Division | 1954/ALD | 12/09/2023 | 0 | Resource Division | 40.05 | 0 | 0 | 0
1509 | ALIPURDUAR | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | "Supply of DIDF Special and CI Jeffy Coupling for Dalgaon TG Water Supply Scheme(SM/16823) of Falakata Block under Alipurduar Division P.H.E. Dte. " | 846/ALD | 14/03/2024 | 90 | MADHAB SAHA | 16.41 | 0 | 0 | 62
1510 | ALIPURDUAR | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | NEW SERIVICE CONNECTION CHARGES FOR DALGAON TG PWSS TW NO-I | BP-2023-24-687 | 14/03/2024 | 0 | WBSEDCL | 21.42 | 0 | 0 | 0
1511 | ALIPURDUAR | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
1512 | ALIPURDUAR | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | NEW SERVICE CONNECTION CHARGE FOR DALGAON TG P/H NO-II | BP-2023-24-692 | 14/03/2024 | 0 | WBSEDCL | 4.69 | 0 | 0 | 0
1513 | ALIPURDUAR | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , constructions of 200 Cum OHR at HW including soil investigation , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Dalgaon Tea Garden PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 3634/ALD | 31/03/2023 | 1091 | M/S MRITYUNJAY PAUL AND SONS | 390.34 | 65.7 | 16.83 | 51
1514 | ALIPURDUAR | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | Supply, delivery, installation, commissioning andtrial run of electro-mechanical components alongwith Cu wound line voltage corrector forRejuvenation of DALGAON T.G water supplyscheme, TW no I AND II underJJM under NMD II,PHE Dte. APD. | 2544/NMD-II | 16/08/2023 | 762 | M/S MATRI CONSTRUCTION | 21.85 | 0 | 0 | 80
1515 | ALIPURDUAR | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | Supply of DI/DIDF Specials for Dalgaon TG (SM/16823)WSS under Alipurduar Division, PHE Dte. | 4582/ALD | 02/01/2025 | 30 | TAPASH KUMAR BHOWMICK | 16.98 | 0 | 0 | 0
1516 | ALIPURDUAR | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1517 | ALIPURDUAR | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | Solarization of grid connected pumping installation at Different PWSS at APD-I ,APD-II , Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1333/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
1518 | ALIPURDUAR | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1519 | ALIPURDUAR | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/16823 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1629/ALD | 04/08/2025 | 60 | NARENDRA BHADANI. | 18.13 | 0 | 0 | 0
1520 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme , SM/07190 | Retrofitting | Laying of DI / UPVC Pipeline & other Misc. works for Bhutiya Basti area at PAITKAPARA PWSS under Alipurduar Division PHED. | 625/ALD | 03/09/2020 | 120 | DAS CONSTRUCTION | 16.33 | 7.8 | 100 | 99
1521 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme , SM/07190 | Retrofitting | Retrofitting work of pipeline of Madarihat PWSS under Alipurduar Division, PHE Dte. | 972/ALD | 13/09/2021 | 30 | MS DEYS CONSTRUCTION | 4.99 | 0 | 100 | 99
1522 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme , SM/07190 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 17 | 100 | 100
1523 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme , SM/07190 | Retrofitting | Providing House connection for DHEKLAPARA PWSS at MADARIHAT-BIRPARA Block under Alipurduar Division PHED PART 1 | 634/ALD | 03/09/2020 | 90 | DILIP MAHATO | 21.8 | 18.74 | 200 | 0
1524 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme , SM/07190 | Retrofitting | Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS (TULSHIPARA TG) under Alipurduar Division, PHE Dte. Dist-Alipurduar. | 1280/ALD | 05/01/2021 | 60 | UMWELT ENGINEER PVT. LTD. | 30.9 | 28.62 | 200 | 98
1525 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme , SM/07190 | Retrofitting | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | 1008/ALD | 12/11/2020 | 60 | JAI BHARAT COMMERCIAL CORPORATION | 14.4 | 17.22 | 200 | 100
1526 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme , SM/07190 | Retrofitting | Providing House connection for PURBA KATHALBARI water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. Part-II | 1173/ALD | 15/12/2020 | 60 | MADHAB SAHA | 19.93 | 27.91 | 100 | 0
1527 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme , SM/07190 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of PAITKAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 1994/ALD | 27/12/2021 | 90 | ANUP GUPTA | 20.99 | 0 | 0 | 80
1528 | ALIPURDUAR | Alipurduar Division | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' , SM/09888 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DHAOLAJHORA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2226/ALD | 14/01/2022 | 90 | MADHAB SAHA | 20.99 | 17.04 | 100 | 100
1529 | ALIPURDUAR | Alipurduar Division | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' , SM/09888 | Augmentation | Repairing of old UPVC pipe line , FHTC and other misc. work related to DHAOLAJHORA PWSS Alipurduar - II Block under Alipurduar Division , PHE Dte | 436/ALD | 13/05/2022 | 30 | MATARA CONSTRUCTION CO | 3.3 | 0 | 0 | 27
1530 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' , SM/09888 | Augmentation | Quotation for NSC at P/H No.III under Dhaoljhora TG W/S/S | BP-2023-24-169 | 15/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
1531 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' , SM/09888 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Rejuvination of Dhaolajhora TG Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Apd. | 986/NMD-II | 15/05/2023 | 30 | MASSK ENGINEERING WORKS | 10.82 | 0 | 0 | 100
1532 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. (Part-D) | 3002/ALD | 15/03/2022 | 60 | M/S DUTTA AND CO | 95.57 | 74.72 | 78.18 | 71
1533 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. (Part-C) | 2872/ALD | 07/03/2022 | 60 | MAHENDRA CHHETRI | 94.52 | 77.53 | 82.02 | 73
1534 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Balance work of construction of boundary wall & repairing of pump house at 2nd Tubewell site of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. | 2659/ALD | 21/02/2022 | 45 | TAPASH KUMAR BHOWMICK | 4.49 | 3.62 | 33.33 | 73
1535 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Uttar Majherdabri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 701/ALD | 08/06/2022 | 30 | HARIDAS GHOSH | 4.96 | 4.96 | 50 | 73
1536 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Quotation for new service connection at Uttar majherdabri W/SS TW No IV Application No-4002956335 |  | 04/08/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1537 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Quotation for new service connection for UTTAR MAJHER DABRI w/ss T/W no. IV. Application no. 4002956335 | BP-42/22-23 | 08/08/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1538 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Quotation for new service connection for uttar majher Dabri w/s scheme t/W no. II , Application no. 40025956327 | BP-41/22-23 | 08/08/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1539 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Quotation for new service connection at uttar majherdabri W/SS TW No III Application No-4002956327 |  | 04/08/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1540 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Construction of boundary wall (H/W) Site, Toilet, Repairing of Pump House & 125 nos. house connection of Uttar Majherdabri Water Supply Scheme under Alipurduar Division, PHE Dte. | 1287/ALD | 05/01/2021 | 60 | TAPASH KUMAR BHOWMICK | 20.49 | 12.7 | 61.96 | 73
1541 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Uttar Majherdabri Water Supply Scheme TW No.-III under NMD-II,PHE. Dte Alipurduar. | 532/NMD-II | 20/04/2022 | 30 | M/S P.P ELECTRICALS | 7.82 | 5.85 | 74.72 | 69
1542 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Uttar Majherdabri Water Supply Scheme TW No.-III under NMD-II,PHE.Dte,Alipurduar. | 411/NMD-II | 22/03/2022 | 30 | QUAZI NOZRUL ISLAM | 2.39 | 2.37 | 99.03 | 0
1543 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Extension of UPVC pipeline for augmentation of Uttar Majherdabri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | 1224/ALD | 10/08/2022 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 46.73 | 40.43 | 86.52 | 70
1544 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Construction of Pump House ,Boundary Wall, and Tube well Boring by Reverse Rotary method of drilling including Rising main for UTTAR MAJHERDABRI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2611/ALD | 17/02/2022 | 90 | HIGHLIFE INTERNATIONAL | 44.39 | 43.93 | 100 | 100
1545 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Providing FHTC in school in Uttar Majherdabri PWSS under Alipurduar Division P.H.E Dte. | 3360/ALD | 14/03/2023 | 30 | HARIDAS GHOSH | 0.22 | 0.22 | 100 | 100
1546 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Material Requisition To Resource Division | 1589/ALD | 14/09/2022 | 0 | Resource Division | 12.3 | 0 | 0 | 0
1547 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Construction of 450cum OHR for Augmentation of Uttar Majher Dabri Water Supply Scheme under Alipurduar Division, PHE Dte. | 2581/ALD | 17/02/2022 | 720 | M/S DUTTA AND CO | 87.59 | 51.24 | 58.8 | 99
1548 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Uttar Majherdabri Water Supply Scheme TW No.-IV under NMD-II, PHE. Dte, Alipurduar. | 0401/NMD-II | 22/03/2022 | 30 | S P ENTERPRISE (KOLKATA) | 2.39 | 0 | 0 | 100
1549 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Material Requisition To Resource Division | 108/ALD | 10/01/2024 | 0 | Resource Division | 4.47 | 0 | 0 | 0
1550 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. (Part-A) | 2870/ALD | 07/03/2022 | 1080 | DILIP MAHATO | 101.03 | 96.04 | 95.06 | 80
1551 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. (Part-B) | 2871/ALD | 07/03/2022 | 1200 | TAPAN CHANDA | 100.9 | 74.42 | 73.75 | 100
1552 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Extension of UPVC pipeline for augmentation of Uttar Majherdabri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | 1223/ALD | 10/08/2022 | 960 | DILIP MAHATO | 56.93 | 54.35 | 57.74 | 100
1553 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME , SM/10171 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Uttar Majherdabri Water Supply Scheme TW No.- IV under NMD-II PHE Dte Alipurduar. | 475/NMD-II | 07/04/2022 | 817 | DEB CONSTRUCTION | 7.85 | 5.8 | 42.85 | 100
1554 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) , SM/07066 | Retrofitting | Construction of Boundary wall near head work site of Lankapara PWSS under Alipurduar Division, PHE Dte. | 2309/ALD | 25/01/2022 | 45 | ASHOK SAPKOTA | 4.78 | 3.04 | 50 | 98
1555 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) , SM/07066 | Retrofitting | Construction of Pump House with sanitary & plumbing arrangement near head work site of Lankapara PWSS under Alipurduar Division, PHE Dte. | 2310/ALD | 25/01/2022 | 60 | ASHOK SAPKOTA | 5.03 | 4.68 | 49.51 | 98
1556 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) , SM/07066 | Retrofitting | Laying of HDPE/DI pipe line at different area of flank of Lankapara road/village road and Lankapara Bazar Area under Alipurduar Division, PHE Dte. | 1007/ALD | 12/11/2020 | 60 | MADHAB SAHA | 33.79 | 13.5 | 100 | 99
1557 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) , SM/07066 | Retrofitting | Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS (TULSHIPARA TG) under Alipurduar Division, PHE Dte. Dist-Alipurduar. | 1280/ALD | 05/01/2021 | 60 | UMWELT ENGINEER PVT. LTD. | 30.9 | 0 | 0 | 98
1558 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) , SM/07066 | Retrofitting | Sinking of 1no. Tube Well for replacement and another 1no. new Tube Well near factory line by ODEX-195 method of drilling at Lankapara Water Supply Scheme under Alipurduar Division, PHE Dte. | 1345/ALD | 08/10/2021 | 30 | SASANKA ROY | 33 | 32.32 | 100 | 96
1559 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) , SM/07066 | Retrofitting | Development of rig Bore TW by ODEX-165 method of drilling at Lankapara WSS under Alipurduar Division, PHE Dte. | 1608/ALD | 22/11/2021 | 20 | DILIP MAHATO | 0.66 | 0.5 | 100 | 99
1560 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) , SM/07066 | Retrofitting | Construction of balance portion of boundary wall at CWR site under LANKAPARA (TULSHIPARA TG ) WSS under Alipurduar Division PHE Dte . | 448/ALD | 13/05/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.91 | 4.8 | 49.94 | 97
1561 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) , SM/07066 | Retrofitting | Sinking of Rig Bore Tube well by Odex-165 method of drilling and installation of Raising Main and laying of DI/MS/HDPE pipe line for the Tulshipara and Lankapara Water Supply Scheme. | 1006/ALD | 12/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 32.34 | 0 | 0 | 97
1562 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) , SM/07066 | Retrofitting | Bridge Crossing and Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS under Alipurduar Division, PHE Dte. Dist-Alipurduar. | 1282/ALD | 05/01/2021 | 726 | GHOSH & SAHA CONSTRUCTION | 23.75 | 4.66 | 23 | 100
1563 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) , SM/07066 | Retrofitting | Providing House connection at LANKAPARA TG (Part-A) PWSS under Alipuduar Division, P.H.E. Dte. | 1807/ALD | 22/02/2021 | 920 | GHOSH & SAHA CONSTRUCTION | 41.88 | 10.17 | 100 | 50
1564 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Fuel bill for the month of August 2021 | 118/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.21 | 0 | 0 | 0
1565 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Laying of UPVC/DI/MS Distribution pipe line and FHTC in connection with Jaldhara Jal Sapna and other misc. work for Jateswar WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 1180/ALD | 15/12/2020 | 60 | SANJIT SAHA | 41.94 | 61.91 | 90.37 | 96
1566 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Laying of UPVC/DI/MS/CI distribution pipe line for gap filling and FHTC connection for Sahapara and adjoining area of Jateswar PWSS under Alipurduar Division, PHE Dte. | 3191/ALD | 28/03/2022 | 60 | AASHIRBAD ENTERPRISE | 12.35 | 0 | 0 | 78
1567 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Construction of 500cum OHR for Augmentation of Jateswar Water Supply Scheme under Alipurduar Division, PHE Dte. | 2525/ALD | 11/02/2022 | 180 | ASHIT KUMAR SINGHA | 91.76 | 0 | 0 | 80
1568 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 25 | 100 | 100
1569 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 3.2 | 100 | 0
1570 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Laying of UPVC/DI/MS/CI distribution pipe line for gap filling and FHTC connection for Beltali Road and adjoining area of Jateswar PWSS under Alipurduar Division, PHE Dte. | 24/ALD | 01/04/2022 | 60 | AASHIRBAD ENTERPRISE | 12.35 | 0 | 0 | 80
1571 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Construction of roof truss, field development and other allied works at Headwork site of Old Jaigaon WSS under Alipurduar Division, PHE Dte. | 2307/ALD | 25/01/2022 | 30 | DILIP MAHATO | 4.17 | 0 | 0 | 75
1572 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Extension of Distribution line with UPVC pipe line near Narendra Nath Sishu Siksha Kendra under Jateswar Water Supply Scheme under Alipurduar Division,PHE Dte. | 880/ALD | 14/10/2020 | 30 | NARAYAN CHANDRA SAHA | 2.02 | 3.71 | 99.67 | 0
1573 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Providing House connection for JATESWAR water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. PART-1 | 867/ALD | 14/10/2020 | 30 | PARAMJYOTI ENTERPRISE | 4.93 | 9.87 | 200 | 0
1574 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Providing House connection for JATESWAR water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. PART-2 | 868/ALD | 14/10/2020 | 30 | NARAYAN CHANDRA SAHA & SONS | 4.93 | 9.87 | 100 | 0
1575 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | 1453/ALD | 25/01/2021 | 45 | PRAMESH LAMA | 33.97 | 5.88 | 200 | 100
1576 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-I | 2812/ALD | 28/02/2022 | 60 | SOUVIK ROY PALADHI | 98.49 | 0.03 | 100 | 63
1577 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) , SM/07057 | Retrofitting | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-II | 2747/ALD | 24/02/2022 | 60 | TAPASH DAS | 49.62 | 8.38 | 100 | 59
1578 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) , SM/07177 | Retrofitting | Providing House connection for SALSALABARI water supply scheme at Alipurduar -II Block underAlipuduar Division, P.H.E. Dte. Part-II | 572/20-21 | 26/03/2021 | 0 | TAPASH KUMAR BHOWMICK | 14 | 0 | 0 | 0
1579 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) , SM/07177 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under SALSALABARI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | 1279/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 45.43 | 30.3 | 200 | 97
1580 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) , SM/07177 | Retrofitting | Providing House connection for Putimari water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. | 725/ALD | 22/09/2020 | 30 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.02 | 10.04 | 200 | 0
1581 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) , SM/07177 | Retrofitting | Providing House connection for SALSALABARI water supply scheme at ALIPURDUAR-II Block under Alipuduar Division, P.H.E. Dte. | 910/ALD | 16/10/2020 | 30 | M/S BHOWMICK CONSTRUCTION | 4.96 | 9.91 | 200 | 0
1582 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) , SM/07177 | Retrofitting | Providing House connection for Jashodanga water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte. Part-II | 1159/ALD | 15/12/2020 | 60 | TAPASH KUMAR BHOWMICK | 29.89 | 25.43 | 200 | 98
1583 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) , SM/07177 | Retrofitting | Providing House connection for Purba Chepani water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte.(Part-IV | 1132/ALD | 10/12/2020 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.93 | 2.88 | 200 | 0
1584 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) , SM/07177 | Retrofitting | Construction of Boundary Wall at Dalda Bari of Jaigaon WSS, Zone-II under Alipurduar Division, PHE Dte. | 551/ALD | 14/07/2021 | 45 | TAPASH DAS | 4.9 | 0 | 200 | 0
1585 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) , SM/07177 | Retrofitting | Preparation of Augmentation D.P.R after investigation For Jateswar W/S scheme under Alipurduar Division. | 914/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.31 | 0.01 | 100 | 0
1586 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) , SM/07179 | Retrofitting | Providing House connection for Munshipara piped water supply scheme at Alipurduar-I Block under Alipuduar Division, P.H.E. Dte.Part-II | 1158/ALD | 15/12/2020 | 60 | TAPASH DAS | 19.93 | 0 | 0 | 82
1587 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) , SM/07179 | Retrofitting | Providing FHTC and other allied works at Munshipara WSS under Alipurduar Division, PHE Dte. | 1303/ALD | 05/10/2021 | 60 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 44.94 | 31.33 | 100 | 82
1588 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) , SM/07179 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Munshipara WSS under Alipurduar Division, PHE Dte. Part-5 | 1845/ALD | 10/12/2021 | 30 | RATAN DUTTA | 4.35 | 2.57 | 100 | 82
1589 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) , SM/07179 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Munshipara WSS under Alipurduar Division, PHE Dte. Part-6 | 1846/ALD | 10/12/2021 | 30 | AASHIRBAD ENTERPRISE | 4.34 | 0 | 0 | 80
1590 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) , SM/07179 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 0 | 0 | 72
1591 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) , SM/07179 | Retrofitting | Laying of DI/UPVC pipeline along with PMGSY Road and other misc. works related to Munshipara PWSS under Alipurduar Division PHE DTE. | 1012/ALD | 12/11/2020 | 60 | TAPASH DAS | 35.88 | 8.78 | 59.94 | 83
1592 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) , SM/07179 | Retrofitting | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar and Munshipara Water Supply Scheme Area under Alipurduar Division, PHE Dte. | 1317/ALD | 05/10/2021 | 1679 | DILIP MAHATO | 58.07 | 0 | 0 | 85
1593 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) , SM/07059 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc. work for retrofitting at Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | 1379/ALD | 19/01/2021 | 45 | SASANKA ROY | 17.09 | 5.84 | 58.89 | 100
1594 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) , SM/07059 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line for retrofitting and providing functional household tap connection (FHTC) in connection with Jaldhara Jal Sapno of Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | 1378/ALD | 19/01/2021 | 45 | M/S PALIT ENTERPRISE | 43.75 | 30.3 | 139 | 68
1595 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) , SM/07059 | Retrofitting | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumar Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | 1243/ALD | 27/09/2021 | 60 | TAPASH DAS | 25.25 | 7.05 | 100 | 78
1596 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) , SM/07059 | Retrofitting | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar Water Supply Scheme Area under Alipurduar Division, PHE Dte. | 1318/ALD | 05/10/2021 | 60 | TAPASH KUMAR BHOWMICK | 35.38 | 0 | 0 | 85
1597 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) , SM/07059 | Retrofitting | Laying distribution line of UPVC and providing FHTC connection for Chhoto Salkumar Water Supply Scheme Area under Alipurduar Division, P.H.E. Dte. | 2311/ALD | 25/01/2022 | 45 | AASHIRBAD ENTERPRISE | 5.01 | 3.88 | 100 | 62
1598 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) , SM/07059 | Retrofitting | Construction of 300 m3 capacity RCC Over Head Reservoir For SALKUMARHAT PWSS under Alipurduar Division PHE Dte. | 632/ALD | 03/09/2020 | 90 | HARIDAS GHOSH | 63.58 | 24.64 | 100 | 80
1599 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) , SM/07059 | Retrofitting | Providing House connection for CHOTO SALKUMAR water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | 1169/ALD | 15/12/2020 | 60 | SASANKA ROY | 29.9 | 43.77 | 200 | 70
1600 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) , SM/07059 | Retrofitting | Repairing & renovation of Pump House, Pathway, Boundary wall (2nd site) & laying DI Pipe line at Salkumarhat WSS under Alipurduar Division PHE Dte. | 898/ALD | 03/09/2021 | 45 | TAPASH DAS | 4.82 | 0 | 0 | 62
1601 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) , SM/07059 | Retrofitting | Preparation of Augmentation D.P.R after investigation For Salkumarhat W/S scheme under Alipurduar Division. | 921/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 1.08 | 2.15 | 100 | 0
1602 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) , SM/07059 | Retrofitting | Providing FHTC at surrounding area of Chhoto Salkumar Under Alipurduar Division, PHE DTE. | 2754/ALD | 24/02/2022 | 60 | KAJAL KUMAR DE | 34.67 | 19.28 | 100 | 45
1603 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) , SM/07059 | Retrofitting | Sinking of Rig Bore Tube well by Odex-165 method of drilling and installation of Raising Main and laying of DI/MS/HDPE pipe line for the Tulshipara and Lankapara Water Supply Scheme. | 1006/ALD | 12/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 32.34 | 8.88 | 200 | 97
1604 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme , SM/08882 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Chandirjhar PWSS under Alipurduar Division, PHE DTE. | 2761/ALD | 25/02/2022 | 60 | MATRI ENTERPRISE | 58 | 45.22 | 100 | 49
1605 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme , SM/08882 | Retrofitting | Retrofitting of pipeline for the 'Jal Sapno' programme and providing FHTC Connection under Chandirjhar WSS under Alipurduar Division, PHE Dte. | 1305/ALD | 05/10/2021 | 60 | SASANKA ROY | 50.06 | 42.97 | 100 | 36
1606 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme , SM/08882 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Chandirjhar WSS under Alipurduar Division, PHE Dte. Part-4 | 2138/ALD | 06/01/2022 | 30 | SASANKA ROY | 5.04 | 5.04 | 100 | 49
1607 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme , SM/08882 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of CHANDIRJHAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2193/ALD | 11/01/2022 | 90 | DULAL DAS | 21.92 | 8.72 | 100 | 100
1608 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme , SM/08882 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Chandirjhar WSS under Alipurduar Division, PHE Dte. Part-5 | 2139/ALD | 06/01/2022 | 30 | SASANKA ROY | 5.04 | 5.04 | 100 | 49
1609 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme , SM/08882 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 1.8 | 100 | 0
1610 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme , SM/08882 | Retrofitting | Providing House connection for CHANDIRJHAR water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte. Part-II | 1174/ALD | 15/12/2020 | 60 | TAPASH KUMAR BHOWMICK | 19.93 | 19.93 | 50 | 0
1611 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme , SM/08883 | Retrofitting | Providing FHTC connection for AWC, School, Health Centre etc. of Salkumarhat WSS under Alipurduar Division, PHE Dte. Part-C | 1596/ALD | 22/11/2021 | 30 | DEBABRATA DUTTA | 4.92 | 3.03 | 61.54 | 98
1612 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme , SM/08883 | Retrofitting | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumarhat Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | 983/ALD | 13/09/2021 | 60 | TAPASH DAS | 25.25 | 0 | 0 | 97
1613 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme , SM/08883 | Retrofitting | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumar Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | 1243/ALD | 27/09/2021 | 60 | TAPASH DAS | 25.25 | 11.36 | 100 | 78
1614 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme , SM/08883 | Retrofitting | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar Water Supply Scheme Area under Alipurduar Division, PHE Dte. | 1318/ALD | 05/10/2021 | 60 | TAPASH KUMAR BHOWMICK | 35.38 | 23.09 | 100 | 85
1615 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme , SM/08883 | Retrofitting | Construction of 300 m3 capacity RCC Over Head Reservoir For SALKUMARHAT PWSS under Alipurduar Division PHE Dte. | 632/ALD | 03/09/2020 | 90 | HARIDAS GHOSH | 63.58 | 19.14 | 50 | 80
1616 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme , SM/08883 | Retrofitting | Repairing & renovation of Pump House, Pathway, Boundary wall (2nd site) & laying DI Pipe line at Salkumarhat WSS under Alipurduar Division PHE Dte. | 898/ALD | 03/09/2021 | 45 | TAPASH DAS | 4.82 | 4.16 | 51.68 | 62
1617 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme , SM/08883 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Salkumarhat PWSS, Alipurduar-I Block under Alipurduar Division, PHE Dte. | 2898/ALD | 08/03/2022 | 1381 | DILIP MAHATO | 48.52 | 6.4 | 55.38 | 65
1618 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/09892 | Augmentation | Quotation for new service connection at Loknathpur W/SS Application No-4002943882 |  | 14/07/2022 | 0 | WBSEDCL | 0.95 | 0 | 0 | 0
1619 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/09892 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT CHANDIJHAR W/SS TW NO-III |  | 14/07/2022 | 0 | WBSEDCL | 0.95 | 0 | 0 | 0
1620 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/09892 | Augmentation | New Connection Chandirjhar P/H no. III, Appplication no. 402943882,Ref no. 402837622 (SM/09892) | BP-38/22-23 | 08/08/2022 | 0 | WBSEDCL | 0.95 | 0 | 0 | 0
1621 | ALIPURDUAR | Alipurduar Division | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/09892 | Augmentation | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Chandirjhar PWSS under Alipurduar Division, PHE DTE. | 2761/ALD | 25/02/2022 | 60 | MATRI ENTERPRISE | 58 | 0 | 0 | 49
1622 | ALIPURDUAR | Alipurduar Division | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/09892 | Augmentation | Retrofitting of pipeline for the 'Jal Sapno' programme and providing FHTC Connection under Chandirjhar WSS under Alipurduar Division, PHE Dte. | 1305/ALD | 05/10/2021 | 60 | SASANKA ROY | 50.06 | 6.75 | 50 | 36
1623 | ALIPURDUAR | Alipurduar Division | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/09892 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of CHANDIRJHAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2193/ALD | 11/01/2022 | 90 | DULAL DAS | 21.92 | 13.2 | 100 | 100
1624 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/09892 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Chandijhar Water Supply Scheme TW No.- III under NMD-II, PHE. Dte, Alipurduar. | 409/NMD-II | 22/03/2022 | 30 | M/S J.K ENGINEERING CO. | 2.39 | 2.38 | 100 | 0
1625 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/09892 | Augmentation | supply, delivery,of standby Automatically controlled diaphragm type chlorinator for accurate dosing of chlorine solution at Chandijhar Water Supply Scheme ,in the dist. of Alipurduar under NMD-II ,PHE Dte. Alipurduar. | 2100/NMD-II | 29/12/2022 | 15 | M/S ANJALI ENTERPRISE | 1.8 | 1.8 | 100 | 0
1626 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/09892 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Chandijhar Water Supply Scheme TW No.-III under NMD-II,PHE.Dte,Alipurduar. | 427/NMD-II | 25/03/2022 | 30 | KASHI NATH DEY | 7.85 | 5.95 | 76.75 | 100
1627 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' , SM/09905 | Augmentation | Supply, installation, commissioning and Trial operation of Electro Mechanical components of LOKNATHPUR Water Supply Scheme TW No.-IV (NEAR DANGI AREA)under NMD-II,PHE.Dte,Alipurduar. | 1034/NMD-II | 03/09/2020 | 90 | SUBODH KUMAR BANIK | 6.41 | 0 | 0 | 0
1628 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' , SM/09905 | Augmentation | Quotation for new service connection at Loknathpur W/SS Application No-4002937212 |  | 14/07/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1629 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' , SM/09905 | Augmentation | Quotation for new service connection at Loknathpur W/SS TW No-V Application No-4002937212 |  | 14/07/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1630 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' , SM/09905 | Augmentation | Quotation for Loknath pur w/s scheme T/W no. Y, under NMD-II PHE Dte. application no. 4002937212( New Connection) Ref no. 402828607 | BP-37/22-23 | 08/08/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1631 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' , SM/09905 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Loknathpur WSS under Alipurduar Division, PHE Dte. Part-5 | 1851/ALD | 13/12/2021 | 30 | GOUTAM KUMAR DAS | 5.04 | 0 | 0 | 63
1632 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' , SM/09905 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of LOKNATHPUR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2195/ALD | 11/01/2022 | 90 | GOUTAM KUMAR DAS | 20.89 | 0 | 0 | 0
1633 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' , SM/09905 | Augmentation | Balance work of construction of boundary wall (2nd site) at Loknathpur WSS under Alipurduar Division PHE Dte. | .2657/ALD | 21/02/2022 | 45 | GOUTAM KUMAR DAS | 4.47 | 0 | 0 | 0
1634 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' , SM/09905 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Loknathpur Water Supply Scheme TW No.- V under NMD-II, PHE. Dte, Alipurduar. | 410/NMD-II | 22/03/2022 | 30 | MITRA ENTERPRISE | 2.39 | 2.38 | 100 | 0
1635 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' , SM/09905 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Loknathpur water supply scheme TW No. V under NMD-II, PHE Dte. Alipurduar. | 556/NMD-II | 26/04/2022 | 30 | S.S ENTERPRISES | 7.85 | 5.96 | 76.01 | 100
1636 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) , SM/07058 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under BAKLA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | 1283/ALD | 05/01/2021 | 60 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 45.19 | 7.25 | 100 | 74
1637 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) , SM/07058 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bakla WSS under Alipurduar Division, PHE Dte. Part-6 | 2151/ALD | 06/01/2022 | 30 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5 | 5 | 100 | 73
1638 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) , SM/07058 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bakla WSS under Alipurduar Division, PHE Dte. Part-5 | 2150/ALD | 06/01/2022 | 30 | SHIB RATAN BHOWMIK | 4.99 | 4.99 | 100 | 73
1639 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) , SM/07058 | Retrofitting | Restoration of laying distribution system of Totpara PWSS by replacing of damaged AC pipeline with UPVC and DI pipeline including interconnection with Bakla Water Supply Scheme under Alipurduar Division, PHE Dte. | 1573/ALD | 22/11/2021 | 120 | HARIDAS GHOSH | 55.38 | 25 | 86.82 | 100
1640 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) , SM/07058 | Retrofitting | Hiring of Diesel vehicle maxi cab (at least 7 seater) for Executive Engineer, Alipurduar Division.(01.09.2020 to 31.03.2021) | 600/ALD | 31/08/2020 | 212 | APSARI BHOWMICK | 1.25 | 0 | 0 | 0
1641 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) , SM/07058 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Bakla PWSS Under Alipurduar Division, PHE DTE. | 2753/ALD | 24/02/2022 | 1200 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 43.78 | 34.75 | 100 | 43
1642 | ALIPURDUAR | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | Supply of CIPE Special & CI Jeffy Coupling for Mathura Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 705/ALD | 08/06/2022 | 30 | SASANKA ROY | 4.79 | 4.79 | 50 | 65
1643 | ALIPURDUAR | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-C) | 1969/ALD | 24/12/2021 | 90 | TAPASH KUMAR BHOWMICK | 0.96 | 0.96 | 100 | 64
1644 | ALIPURDUAR | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | Entry of data of Functional Household Tap Connection (FHTC under JJM) of PWSS in Website under Alipurduar Division, PHE Dte. (Part-A) | 743/ALD | 11/08/2021 | 90 | TAPASH KUMAR BHOWMICK | 0.96 | 0.96 | 100 | 65
1645 | ALIPURDUAR | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | Construction of 400cum OHR for Mathura Water Supply Scheme under Alipurduar Division, PHE Dte. | 2583/ALD | 17/02/2022 | 180 | M/S SURAJIT DEY & CO | 77.51 | 58.47 | 75.44 | 63
1646 | ALIPURDUAR | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for MATHURA TG AREA PWSS Under Alipurduar Division PHE DTE | 22/ALD | 01/04/2022 | 120 | TAPASH KUMAR BHOWMICK | 246.44 | 231.69 | 94.02 | 65
1647 | ALIPURDUAR | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 100 | 100 | 0
1648 | ALIPURDUAR | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | Material Requisition To Resource Division | 395/ALD | 11/05/2022 | 0 | Resource Division | 3.16 | 0 | 0 | 0
1649 | ALIPURDUAR | Northern Mechanical Division II | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | Quotation for new service connection at Mathura TG P/H No-I. Application No- 4003027935 | BP-109/22-23 | 19/12/2022 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
1650 | ALIPURDUAR | Northern Mechanical Division II | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MATHURA TG PWSS PH NO-II | BP-2023-24-9 | 20/04/2023 | 0 | WBSEDCL | 1.41 | 0 | 0 | 0
1651 | ALIPURDUAR | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at H/W site including laying distribution system and providing FHTC for MATHURA TG AREA PWSS Under Alipurduar Division PHE DTE | 17/ALD | 01/04/2022 | 120 | M/S SURAJIT DEY & CO | 246.1 | 90.37 | 36.72 | 69
1652 | ALIPURDUAR | Northern Mechanical Division II | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MATHURA TG water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte. Alipurduar. | 393/NMD-II | 23/02/2023 | 30 | B.B CONCERNED | 22.77 | 20.28 | 89.41 | 100
1653 | ALIPURDUAR | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | Supply of DI Special and CI Jeffy Coupling for Mathura TG Water Supply Scheme (SM/10172) of Alipurduar-I Block under Alipurduar Division P.H.E. Dte. | 831/ALD | 14/03/2024 | 60 | TAPASH KUMAR BHOWMICK | 11.6 | 0 | 0 | 50
1654 | ALIPURDUAR | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Mathura Tea Garden Area Piped Water Supply Scheme (SM-10172) of Alipurduar - I Block under Alipurduar Division PHE Dte. | 852/ALD | 14/03/2024 | 30 | GUHA ENTERPRISE | 11.62 | 0 | 0 | 75
1655 | ALIPURDUAR | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10172 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
1656 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME , SM/10671 | Augmentation | Extension and replacement of damaged pipeline of Birpara PWSS, Alipurduar-I Block under Alipurduar Division, PHE Dte. | 1686/ALD | 20/09/2022 | 60 | KAMALESH ROY | 5.01 | 0 | 0 | 0
1657 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME , SM/10671 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of BIRPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2192/ALD | 11/01/2022 | 90 | DAS CONSTRUCTION | 22.03 | 0 | 0 | 65
1658 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME , SM/10671 | Augmentation | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Birpara PWSS (APD) Under Alipurduar Division, PHE DTE. | 2751/ALD | 24/02/2022 | 60 | R.K.CONSTRUCTION | 31.74 | 14.75 | 50 | 60
1659 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME , SM/10671 | Augmentation | Dismantling Concrete road and re -casting the same for providing FHTC at different area of BIRPARA (APD) PWSS AND Alipurduar - I Block under Alipurduar Division , PHE Dte. | 441/ALD | 13/05/2022 | 30 | R.K.CONSTRUCTION | 4.96 | 0 | 0 | 71
1660 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME , SM/10671 | Augmentation | Laying of UPVC / DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, Land Development works, Construction of surface drain, supply of CIDF specials and other allied works in connection with the Birpara(APD) PWSS under Alipurduar Division, PHE Dte. | 2600/ALD | 04/12/2023 | 540 | DAS CONSTRUCTION | 38.1 | 0 | 0 | 30
1661 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME , SM/10671 | Augmentation | Reparing of Pump House at 2nd site of BIRPARA (APD) PWSS Under Alipurduar Division PHE DTE. | 5394/ALD | 17/03/2025 | 60 | DAS CONSTRUCTION | 0.79 | 0 | 0 | 0
1662 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME , SM/10671 | Augmentation | Reparing of Pump House at HEADWORK site of BIRPARA (APD) PWSS Under Alipurduar Division PHE DTE. | 5392/ALD | 17/03/2025 | 60 | DAS CONSTRUCTION | 0.94 | 0 | 0 | 0
1663 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME , SM/10676 | Augmentation | Laying of DI pipe of Different Dia and other works For TAPSHIKHATA PWSS at Alipurduar -I Block under Alipurduar Division , PHE Dte. | 435/ALD | 13/05/2022 | 30 | KAMALESH ROY | 4.76 | 0 | 0 | 0
1664 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME , SM/10676 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Tapshikhata WSS under Alipurduar Division, PHE Dte. Part-5 | 2142/ALD | 06/01/2022 | 30 | DEBAJYOTI SUTRADHAR | 5.02 | 5.02 | 50 | 52
1665 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME , SM/10676 | Augmentation | Material Requisition To Resource Division | 3608/ALD | 24/10/2024 | 0 | Resource Division | 4.11 | 0 | 0 | 0
1666 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME , SM/10676 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
1667 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME , SM/10676 | Augmentation | Laying of distribution line with HDPE,UPVC and CI/DI pipes, laying of paver block at pump house no-1 and 2 and providing FHTC for Aug. Of Tapshikhata PWSS under Alipurduar Division. | 675/ALD | 06/03/2024 | 720 | TAPASH DAS | 43.25 | 0 | 0 | 10
1668 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME , SM/10676 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1669 | ALIPURDUAR | Alipurduar Division | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11696 | New | Soil investigation works at head works site for HOASINBAD TG AREA PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 2133/ALD | 10/11/2022 | 30 | MOYTEC | 0.7 | 0.64 | 91.89 | 0
1670 | ALIPURDUAR | Northern Mechanical Division II | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11696 | New | QUOTATION FOR NEW SERVICE CONNECTION AT HOASINABAD TG TW NO-I | BP-2023-24-56 | 13/05/2023 | 0 | WBSEDCL | 1.6 | 0 | 0 | 0
1671 | ALIPURDUAR | Northern Mechanical Division II | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11696 | New | QUOTATION FOR NEW SERVICE CONNECTION AT HOASINABAD TG TW NO-II | BP-2023-24-57 | 13/05/2023 | 0 | WBSEDCL | 1.6 | 0 | 0 | 0
1672 | ALIPURDUAR | Alipurduar Division | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11696 | New | Laying of DI and HDPE pipeline, trenchless pipe laying by HDD process, providing FHTC and others for Hossainabad PWSS under Alipurduar Division, PHE Dte. | 690/ALD | 07/03/2024 | 270 | SASANKA ROY | 62.82 | 0 | 0 | 80
1673 | ALIPURDUAR | Northern Mechanical Division II | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11696 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Hosainbad TG water supply scheme, TW no. I and II under Northern Mechanical Division-II, PHE Dte.APD | 485/NMD-II | 02/03/2023 | 30 | MITRA ENTERPRISE | 27.77 | 0 | 0 | 99
1674 | ALIPURDUAR | Alipurduar Division | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11696 | New | Construction of 2nos. Pump house, 2nos. Boundary wall at headwork site and 2nd Tubewell site including providing FHTC for HOASINBAD TG AREA PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 1636/ALD | 19/09/2022 | 954 | RATAN DUTTA | 37.7 | 30.66 | 81.33 | 80
1675 | ALIPURDUAR | Alipurduar Division | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11696 | New | Laying of distribution system (Part-2) and providing FHTC for HOASINBAD TG AREA PWSS under Alipurduar Division, PHE Dte. | 1637/ALD | 19/09/2022 | 345 | SASANKA ROY | 81.64 | 75.12 | 92.01 | 92
1676 | ALIPURDUAR | Alipurduar Division | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11696 | New | Construction of 200 cum OHR as per Departmental Design and drawing in headwork site, Tube well Boring by ODEX-165 method of drilling 2nos. respectively at Headwork site and 2nd Tubewell site, Rising Main and distribution line (Part-1) for HOASINBAD TG AREA PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte | 1635/ALD | 19/09/2022 | 929 | SASANKA ROY | 96.32 | 57.12 | 59.3 | 95
1677 | ALIPURDUAR | Alipurduar Division | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11696 | New | Laying of additional HDPE pipeline for Gap filling and providing FHTC at Hoasinbad TG under Hoasinbad PWSS under Alipurduar Division, PHE Dte. | 966/ALD | 12/06/2025 | 60 | SASANKA ROY | 26.04 | 0 | 0 | 0
1678 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Gap filling in laying distribution system by making culvert crossing and laying of DI and UPVC pipes under Narathali Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | 2226/ALD | 21/11/2022 | 45 | MADHAB SAHA | 4.65 | 0 | 0 | 0
1679 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Restoration of Laying distribution system by replacing of damaged AC pipeline with UPVC pipeline and constructon of boundary wall, toilet and repairing of pump house (2nd site) at Narathali Water Supply Scheme under Alipurduar Division, PHE Dte | 1312/ALD | 05/10/2021 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 11.97 | 3.92 | 32.76 | 69
1680 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Laying of distribution of UPVC pipeline including FHTC for MADHYA NARATHALI AREA under NARATHALI PWSS under Alipurduar Division, PHE DTE. | 2744/ALD | 24/02/2022 | 60 | DAS CONSTRUCTION | 87.58 | 66.41 | 75.83 | 68
1681 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Laying of distribution of UPVC pipeline including FHTC for PASCHI NARATHALI MOUZA under NARATHALI PWSS under Alipurduar Division, PHE DTE. | 2742/ALD | 24/02/2022 | 60 | MADHAB SAHA | 87.55 | 78.76 | 89.97 | 71
1682 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Laying of distribution of UPVC pipeline including FHTC for NARATHALI MOUZA under NARATHALI PWSS under Alipurduar Division, PHE DTE. | 2745/ALD | 24/02/2022 | 60 | SASANKA ROY | 87.59 | 78.42 | 89.54 | 70
1683 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Providing extension of distribution line, repair of water pipeline in 10/142 booth at Khoardanga 2 G.P from the commissioned NARATHALI PWSS (UID-APD-166) UNDER ALIPURDUAR DIVISION PHE DTE. | 1483/ALD | 27/01/2021 | 60 | TAPASH DAS | 15.73 | 1.42 | 100 | 70
1684 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Construction of boundary wall, repairing of pump house of 3rd T/W site and interconnection between 2nd and 3rd site by using DI pipe with pillar including supply of CI materials at Narathali Water Supply Scheme under Alipurduar Division, P.H.E. Dte. | 881/ALD | 03/09/2021 | 60 | SREE MAA CONSTRUCTION & CO. | 13.19 | 8.13 | 67.47 | 71
1685 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | "Collectio of house hold details at prescribrd format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. (for the financial year 2022-2023 from 01/04/2022 onwards)" | 3223/ALD | 31/03/2022 | 365 | DILIP MAHATO | 4.96 | 3.06 | 100 | 54
1686 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Narathali Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 700/ALD | 08/06/2022 | 30 | M/S SHIB RATAN BHOWMICK & CO | 4.88 | 4.88 | 50 | 70
1687 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | NARATHALI T/W no.IV, Alipurduar II, Application no. 4002930565, Ref no. 402824639, SM10154/159 | BP-25/22-23 | 15/07/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1688 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | NARATHALI T/W no.V, Alipurduar II, Application no. 4002930550, Ref no. 402824235, SM/10154/159 | BP-24/22-23 | 15/07/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1689 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Laying of distribution of UPVC pipeline including FHTC for KHOARDANGA AREA under NARATHALI PWSS under Alipurduar Division, PHE DTE. | 2743/ALD | 24/02/2022 | 60 | HARIDAS GHOSH | 87.82 | 87.69 | 99.86 | 99
1690 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Narthali Water Supply Scheme TW No.-V under NMD-II, PHE. Dte, Alipurduar. | 405/NMD-II | 22/03/2022 | 30 | HARAGOURI ENTERPRISE | 2.38 | 2.38 | 100 | 0
1691 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Renovation of the electrical installation of NARARTHALI W/S scheme P/H No. I under NMD-II , PHE, Dte. Alipurduar . | 494/NMD-II | 02/03/2023 | 15 | SARKAR ELECTRIC | 1.09 | 0 | 0 | 0
1692 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Narthali Water Supply Scheme TW No. - V under NMD-II, PHE Dte., Alipurduar. | 473/NMD-II | 07/04/2022 | 30 | M/S PARITOSH BHOWMICK & CO. | 7.85 | 7.33 | 93.44 | 100
1693 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Narthali Water Supply Scheme TW No.-IV under NMD-II,PHE.Dte, Alipurduar. | 403/NMD-II | 22/03/2022 | 30 | RMD TRADING | 2.39 | 2.39 | 100 | 100
1694 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Material Requisition To Resource Division | 716/ALD | 13/06/2022 | 0 | Resource Division | 51.21 | 0 | 0 | 0
1695 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Construction of 550cum OHR for Augmentation of Narathali Water Supply Scheme under Alipurduar Division, PHE Dte. | 2524/ALD | 11/02/2022 | 180 | TAPAN CHANDA | 98.12 | 89.52 | 94.38 | 72
1696 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Laying of distribution of UPVC pipeline including FHTC for KHOARDANGA AREA under NARATHALI PWSS under Alipurduar Division, PHE DTE 2743/ALD DT:24/02/2022 | 447/23-24/PFMS | 30/03/2024 | 0 | HARIDAS GHOSH | 1.98 | 0 | 0 | 0
1697 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Laying of pipeline at PASCHIM NARATHALI by extension of pipeline from Uttar Kamakhyaguri PWSS under Alipurduar Division, PHE DTE. | 2746/ALD | 24/02/2022 | 1020 | AKANSHA COMMERCIAL PRIVATE LTD. | 93.92 | 58.61 | 100 | 100
1698 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Gap filling in laying distribution system by making culvert crossing and laying of DI and UPVC pipes under Narathali Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | 2227./ALD | 21/11/2022 | 45 | HARI CONSTRUCTION | 3.45 | 0 | 0 | 0
1699 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Construction of Pump House ,Boundary Wall and Tube well Boring by ODEX-165 Method of drilling including Rising Main for NARATHALI PWSS under Alipurduar Division PHE DTE. | 2526/ALD | 11/02/2022 | 990 | TAPAN CHANDA | 41.03 | 27.14 | 83.32 | 100
1700 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME , SM/10154 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Narthali Water Supply Scheme TW No.- IV under NMD-II,PHE.Dte,Alipurduar. | 437/ NMD-II | 29/03/2022 | 579 | ASHOKE ADHIKARY | 7.85 | 7.33 | 93.5 | 100
1701 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Extension and replacement of damaged pipeline and providing house connection at Dakshin Sonapur Area under Sonapur PWSS under Alipurduar Division, PHE Dte. | 976/ALD | 13/09/2021 | 60 | MADHAB SAHA | 44.48 | 43.57 | 97.97 | 17
1702 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | River crossing for laying DI pipe line, Extension and replacement of damaged pipeline and providing FHTC at Sonapur and surrounding area of Sonapur PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | 2236/ALD | 14/01/2022 | 60 | M/S SIBU DEY AND CO | 38.07 | 34.93 | 98.23 | 91
1703 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at Dakshin Kashigram area under Sonapur PWSS under Alipurduar Division, Division, PHE Dte. | 2294/ALD | 24/01/2022 | 60 | SASANKA ROY | 50.15 | 47.18 | 100 | 18
1704 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Soil investigation work for Augmentaion of Dakshin Sonapur PWSS under Alipurduar Division PHE Dte. | 2791/ALD | 10/01/2023 | 30 | MOYTEC | 0.95 | 0.95 | 100 | 0
1705 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Construction of platform for FHTC laying of different dia. UPVC and DI pipe line at Dakshin Sonapur PWSS and adjoining mouzas under Alipurduar Division, PHE Dte. | 2415/ALD | 09/11/2023 | 60 | MADHAB SAHA | 31.16 | 0 | 0 | 15
1706 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Providing FHTC from existing distribution system as per specification for Augmentation of DAKSHIN SONAPUR PWSS at Uttar Sonapur and adjoining moujas under Alipurduar Division, PHE Dte. | 2546/ALD | 28/11/2023 | 90 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.34 | 0 | 0 | 0
1707 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Providing FHTC from existing distribution system as per specification for Augmentation of DAKSHIN SONAPUR PWSS at Kumarpara and adjoining moujas under Alipurduar Division, PHE Dte. | 2746/ALD | 14/12/2023 | 60 | KAMALESH ROY | 34 | 0 | 0 | 0
1708 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT DAKSHIN SONAPUR WS SCHEME P/H NO.-VI | BP-2023-24-290 | 21/08/2023 | 0 | WBSEDCL | 4.2 | 0 | 0 | 0
1709 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT DAKSHIN SONAPUR W/S SCHEME P/H NO.-V | BP-2023-24-289 | 21/08/2023 | 0 | WBSEDCL | 4.2 | 0 | 0 | 0
1710 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Dakshin Sonapur Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | 2827/NMD-II | 11/10/2023 | 30 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 21.93 | 0 | 0 | 50
1711 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Laying HDPE pipeline from Dakshin Sonapur aath mile bazaar to head work site due to widening of NH and providing FHTC at Dakshin Sonapur PWSS Area, Alipurduar-I Block under Alipurduar Division, PHE Dte. | 06/ALD | 04/04/2023 | 450 | PINTU SAHA | 46.56 | 0 | 0 | 80
1712 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Procurement of Laptop,Tab .Assemble Deskton Printer VC accessories and Other related accessories Tor all Permanent & contractual JE. all Assistant Engineer and Divisional Staff at Alipurduar PHED. | 77/24-25/PFMS | 21/06/2024 | 0 | CYBERNET | 31.34 | 0 | 0 | 0
1713 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
1714 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Extension and replacement of damaged pipeline and providing house connection at Panchkolguri area under Sonapur PWSS under Alipurduar Division, PHE Dte. | 977/ALD | 13/09/2021 | 1355 | M/S JHA CONSTRUCTION | 43.59 | 40.35 | 92.57 | 60
1715 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Laying of Different Dia pipeline And providing FHTC For Uttar Simlabari and adjoing area under Patlakhowa PWSS at Alipurduar-I Block under Alipurduar Division, PHE Dte. | 1491/ALD | 05/09/2022 | 766 | SHREE RANISATI ENTERPRISE | 100.02 | 0 | 0 | 30
1716 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Construction of 700cum OHR for Augmentation of DAKSHIN SONAPUR Water Supply Scheme under Alipurduar Division, PHE Dte. | 1495/ALD | 05/09/2022 | 1080 | SHREE RANISATI ENTERPRISE | 123.17 | 0 | 0 | 5
1717 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. Part-1 | 1493/ALD | 05/09/2022 | 945 | MADHAB SAHA | 34.59 | 0 | 0 | 27
1718 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. Part-2 | 1494/ALD | 05/09/2022 | 1080 | KAJAL KUMAR DE | 34.44 | 0 | 0 | 15
1719 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Boring of Tube Well, Construction of Pump House, Boundary Wall, Laying Of Rising Main, Distribution System for Augmentation of Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. (2nd call) | 3197/ALD | 27/02/2023 | 900 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 171.88 | 0 | 0 | 35
1720 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01/02/2023 to 30/04/2023) | 2953/ALD | 24/01/2023 | 90 | NIRANJAN KIRTANIA | 0.5 | 0 | 0 | 0
1721 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Continuation of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2024 to 29.02.2024) | 2907/ALD | 29/12/2023 | 62 | PARITOSH SUTRADHAR | 0.8 | 0 | 0 | 0
1722 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Laying of distribution line with HDPE, UPVC & CI/DI Pipes at Kumarpara & adjoining areas and others allied works for Augmentation of Dakshin Sonapur PWSS within Alipurduar-I Block under Alipurduar Division, PHE DTE. | 706/ALD | 22/05/2025 | 75 | S.D. PROJECT | 150.21 | 0 | 0 | 0
1723 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1724 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Dakshin Sonapur Water Supply Scheme TW No.-III (Additional) under NMD-II,PHE.Dte,Alipurduar. | 785/ALD | 30/05/2025 | 30 | DILIP MAHATO (OPC) PRIVATE LIMITED | 11.09 | 0 | 0 | 0
1725 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Repairing of pump house at 2nd site of Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. | 2352/ALD | 10/11/2025 | 60 | DIPAK DAS | 2.29 | 0 | 0 | 0
1726 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Road crossing and laying of different dia pipeline for Dakshin Sonapur WSS under Alipurduar-I Block under Alipurduar Division, P.H.E. Dte. | 2664/ALD/ | 22/12/2022 | 610 | M/S AMIT KUMAR GUPTA | 31.75 | 28.1 | 94.72 | 88
1727 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Fabrication,Erection of Signage (135 nos) of Pump house/OHR site democration with in Alipurduar-II and Kalchini Block for Different PWSS of JJM Project Under Alipurduar Division P.H.E.Dte. | 3442/ALD | 27/09/2024 | 196 | M/S SARKAR & CO | 14.84 | 0 | 0 | 100
1728 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Sinking of Big dia Tube Well (250 x 200 mm dia) by R.C. drilling for Aug. of Dakshin Sonapur PWSS within Alipurduar-I Block of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/11970) | 2295/ALD | 07/08/2024 | 207 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 20.72 | 0 | 0 | 100
1729 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME , SM/11970 | Augmentation | Painting of Old OHR at Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. | 5046/ALD | 17/02/2025 | 60 | SANKAR ROY | 3.78 | 0 | 0 | 100
1730 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Providing House Connection (FHTC) at Kumargram WSS under Alipurduar Division, PHE Dte. Part-4 | 1002/ALD | 15/07/2022 | 30 | DILIP MAHATO | 5.04 | 0 | 0 | 43
1731 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Providing House Connection (FHTC) at Kumargram WSS under Alipurduar Division, PHE Dte. Part-5 | 1003/ALD | 15/07/2022 | 30 | DILIP MAHATO | 5.04 | 0 | 0 | 42
1732 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Construction of 150cum. OHR for KUMARGRAM ZONE-IV Water Supply Scheme under Alipurduar Division, PHE Dte. | 983/ALD | 15/07/2022 | 180 | MATRI ENTERPRISE | 50.41 | 0 | 0 | 0
1733 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Soil investigation work at 4 different places of Kumargram within Alipurduar District under Alipurduar Division PHE Dte. | 1005/ALD | 15/07/2022 | 30 | MOYTEC | 4.88 | 0 | 0 | 0
1734 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Providing FHTC at Kumargram WSS under Alipurduar Division, PHE Dte. Part-3 | 1001/ALD | 15/07/2022 | 30 | DILIP MAHATO | 5.04 | 0 | 0 | 0
1735 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Land development, construction of pathway of HWS and culvert crossing with DI pipe under Kumargram TG WSS under Alipurduar Division, PHE Dte. | 2492/ALD | 13/12/2022 | 90 | HARIDAS GHOSH | 12.45 | 12.33 | 100 | 43
1736 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Material Requisition To Resource Division | 206/ALD/2023-2024 | 02/05/2023 | 0 | Resource Division | 5.44 | 0 | 0 | 0
1737 | ALIPURDUAR | Northern Mechanical Division II | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Quotation for new service connection at kumargram TG P/H No-II. Application No- 4003039118 | BP-107/22-23 | 19/12/2022 | 0 | WBSEDCL | 1.58 | 0 | 0 | 0
1738 | ALIPURDUAR | Northern Mechanical Division II | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Quotation for new service connection at kumargram TG P/H No-I. Application No- 4003039105 | BP-108/22-23 | 19/12/2022 | 0 | WBSEDCL | 1.58 | 0 | 0 | 0
1739 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Construction of 250cum. OHR for Kumargram TG Water Supply Scheme under Alipurduar Division, PHE Dte. | 976/ALD | 15/07/2022 | 180 | HARIDAS GHOSH | 57.62 | 19.81 | 34.38 | 100
1740 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for KUMARGRAM TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | 1305/ALD | 22/08/2022 | 720 | HARIDAS GHOSH | 81.11 | 60.75 | 74.89 | 90
1741 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for KUMARGRAM TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | 1304/ALD | 22/08/2022 | 120 | GOUTAM KUMAR DAS | 94.63 | 57.55 | 60.82 | 80
1742 | ALIPURDUAR | Northern Mechanical Division II | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Hiring of Motor Cab (Non-air conditioned) for site visit of the Assistant Engineer , Alipurduar Mechanical Sub- Division, P.H.E. Dte. for Inspection of different PWSS under JJM like Newland TG , Kumargram TG & Sankosh TG under Northern Mechanical Division -II, P.H.E. Dte. | 139/AMSD | 30/06/2023 | 62 | MUSTAFI CONCERN | 0.69 | 0 | 0 | 100
1743 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Providing balance FHTC for KUMARGRAM TG PWSS under Alipurduar Division, PHE Dte. | 1791/ALD | 29/08/2023 | 360 | HARI CONSTRUCTION | 13.16 | 0 | 0 | 81
1744 | ALIPURDUAR | Northern Mechanical Division II | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kumargram TG water supply scheme, TW no II under Northern Mechanical Division-II, PHE Dte.Alipurduar | 770/NMD-II | 06/04/2023 | 30 | BEE GEE CONSTRUCTION | 10.74 | 0 | 0 | 90
1745 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Supply of CIDF special for Kumargram TG Pwss Under Alipurduar Division PHE Dte. | 1608/ALD | 25/08/2023 | 30 | HARI CONSTRUCTION | 7.67 | 0 | 0 | 95
1746 | ALIPURDUAR | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Material Requisition To Resource Division | 130/ALD | 10/01/2024 | 0 | Resource Division | 9.2 | 0 | 0 | 0
1747 | ALIPURDUAR | Northern Mechanical Division II | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME , SM/11482 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kumargram TG water supply scheme, TW no I(H/W Site) under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 902/NMD-II | 04/05/2023 | 30 | MAA ENTERPRISES | 10.74 | 0 | 0 | 0
1748 | ALIPURDUAR | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | Material Requisition To Resource Division | 1274/ALD | 11/08/2023 | 0 | Resource Division | 34.39 | 0 | 0 | 0
1749 | ALIPURDUAR | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KADAMBINI TG TW NO-I,Z-II | BP-2023-24-54 | 15/05/2023 | 0 | WBSEDCL | 1.37 | 0 | 0 | 0
1750 | ALIPURDUAR | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KADAMBINI TG TW NO-I,Z-I | BP-2023-24-53 | 15/05/2023 | 0 | WBSEDCL | 1.37 | 0 | 0 | 0
1751 | ALIPURDUAR | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KADAMBINI TG TW NO-II,Z-II | BP-2023-24-52 | 15/05/2023 | 0 | WBSEDCL | 1.37 | 0 | 0 | 0
1752 | ALIPURDUAR | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KADAMBINI TG TW NO-II,Z-I | BP-2023-24-55 | 15/05/2023 | 0 | WBSEDCL | 1.37 | 0 | 0 | 0
1753 | ALIPURDUAR | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kadambini water supply scheme, TW no I and II of Zone-II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 2437/NMD-II | 11/08/2023 | 30 | A.G ENTERPRISE | 18.46 | 0 | 0 | 90
1754 | ALIPURDUAR | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | "Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Kadambini TG Water Supply Scheme (SM/13239) of Falakata Block under Alipurduar Division P.H.E. Dte. " | 845/ALD | 14/03/2024 | 30 | MANSAROVAR CASTING | 13.2 | 0 | 0 | 0
1755 | ALIPURDUAR | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | Continuation work order for the work of "Sinking of Rig bore T/W (4nos.) by Reverse Rotary method of drilling, cons. of 100 cum. OHR (2nos), cons. of P/H and B/W, Rising main, distribution line and providing FHTC at H/W and 2nd site inclu. Soil testing for KADAMBINI TG PWSS (ZONE-I and ZONE-II) under Birpara Sub-Division, Alipurduar Division, PHE Dte." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/5/2024-EE(ALI_D) SEC-DPHE (Computer No-973264)) | 1913/ALD | 26/06/2024 | 60 | DILIP MAHATO | 14.57 | 0 | 0 | 90
1756 | ALIPURDUAR | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | Additional Quotation for New Service connection charges for Kadambini T.G PWSS, Zone-I,P/H No-I | BP-2023-24-588 | 02/02/2024 | 0 | WBSEDCL | 11.92 | 0 | 0 | 0
1757 | ALIPURDUAR | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | ADDITIONAL QUOTATION FOR NEW SERVICE CONNECTION CHARGES FOR KADAMBINI T.G PWSS, ZONE-I,P/HNO-II | BP-2023-24-621 | 20/02/2024 | 0 | WBSEDCL | 5.15 | 0 | 0 | 0
1758 | ALIPURDUAR | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | Sinking of Rig bore T/W (4nos.) by Reverse Rotary method of drilling, cons. of 100 cum. OHR (2nos), cons. of P/H and B/W, Rising main, distribution line and providing FHTC at H/W and 2nd site inclu. Soil testing for KADAMBINI TG PWSS (ZONE-I and ZONE-II) under Birpara Sub-Division, Alipurduar Division, PHE Dte | 2857/ALD | 17/01/2023 | 874 | DILIP MAHATO | 498.42 | 352.5 | 70.72 | 95
1759 | ALIPURDUAR | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | Continuation order for Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II, PHE Dte. | 578/AMSD | 25/10/2024 | 61 | MUSTAFI CONCERN | 0.75 | 0 | 0 | 0
1760 | ALIPURDUAR | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 821/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
1761 | ALIPURDUAR | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | Yard lighting arrangement at Head Work Site for Different PWSS (KADAMBINI TG and Others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1346/NMD-II | 19/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 23.98 | 0 | 0 | 0
1762 | ALIPURDUAR | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1763 | ALIPURDUAR | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | Restoration of DI pipe crossing near CHOR TORSHA and other repair works in Banshidharpur area under Alipurduar Division, PHE Dte. | 366/ALD | 18/05/2023 | 30 | NARENDRA BHADANI. | 1.42 | 0 | 0 | 100
1764 | ALIPURDUAR | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kadambini water supply scheme, TW no I and II of Zone-I under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 2792/NMD-II | 06/10/2023 | 485 | ASHUTOSH DAS & CO. | 18.45 | 0 | 0 | 100
1765 | ALIPURDUAR | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13239 | New | Laying leftout pipeline (not including at Lop of pipeline) at kadambini TG PWSS (Zone-I & II) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 3233/ALD | 10/09/2024 | 120 | DILIP MAHATO (OPC) PRIVATE LIMITED | 25.1 | 0 | 0 | 80
1766 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME , SM/13245 | New | New Service connection charge for Paschim Satali PWSS P/H No-III | BP-2023-24-186 | 22/06/2023 | 0 | WBSEDCL | 1.36 | 0 | 0 | 0
1767 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME , SM/13245 | New | New Service connection charge for Paschim Satali PWSS P/H No-I. | BP-2023-24-188 | 22/06/2023 | 0 | WBSEDCL | 1.36 | 0 | 0 | 0
1768 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME , SM/13245 | New | New Service connection charge for Paschim Satali PWSS P/H No-II | BP-2023-24-187 | 22/06/2023 | 0 | WBSEDCL | 1.36 | 0 | 0 | 0
1769 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME , SM/13245 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Paschim Satali water supply scheme, TW no I, II and III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | 944/NMD-II | 11/05/2023 | 722 | M/S BHOWMIK & CO. | 27.59 | 0 | 0 | 55
1770 | ALIPURDUAR | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME , SM/13245 | New | Providing FHTC from existing distribution system as per specification for Paschim Satali PWSS under Alipurduar Division, PHE Dte. | 1879/ALD | 07/09/2023 | 270 | SATYABRATA BHATTACHERJEE | 7.02 | 0 | 0 | 1
1771 | ALIPURDUAR | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME , SM/13245 | New | Supply of CIDF/CIPE pipes and specials & Sluice Valve for Paschim Satali Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 697/ALD | 07/03/2024 | 90 | SSPR VALVE MANUFACTURING PVT LTD | 18.08 | 0 | 0 | 80
1772 | ALIPURDUAR | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME , SM/13245 | New | Constructions of 300 Cum OHR as per Departmental Design & drawing including laying distribution system with new HDPE pipeline (Part-A), RISING MAIN, CONSTRUCTION OF THREE(3) NOS OF BOUNDARY WALL, PATHWAY including soil test, providing FHTC and others allied works for PASCHIM SATALI PWSS Under Alipurduar Division PHE DTE | 2860/ALD | 17/01/2023 | 1082 | DILIP MAHATO | 497.97 | 365.27 | 73.35 | 74
1773 | ALIPURDUAR | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME , SM/13245 | New | Balance portion of boundary wall and Gap joint of new HDPE/DI pipeline, and land development of HW Site,1st and 2nd site of Paschim Satali PWSS (Part) Kalchini Block Alipurduar Division, PHE Dte. | 692/ALD | 07/03/2024 | 509 | DILIP MAHATO | 61.82 | 0 | 0 | 45
1774 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME , SM/13245 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 823/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
1775 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME , SM/13245 | New | Yard lighting arrangement at Head Work Site for Different PWSS (NIMTI DOMOHANI and Others) under JJM in the BLOCK: Kalchini, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1386/NMD-II | 26/06/2025 | 30 | AMUSAR IMPEX PVT LTD | 22.95 | 0 | 0 | 0
1776 | ALIPURDUAR | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME , SM/13245 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1777 | ALIPURDUAR | Northern Mechanical Division II | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME , SM/13448 | New | QUOTATION | BP-2023-24-483 | 12/12/2023 | 0 | WBSEDCL | 3.05 | 0 | 0 | 0
1778 | ALIPURDUAR | Northern Mechanical Division II | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME , SM/13448 | New | Qutation for Jayani TG-2 P/HNO-I | BP-2023-24-470 | 12/12/2023 | 0 | WBSEDCL | 16.18 | 0 | 0 | 0
1779 | ALIPURDUAR | Alipurduar Division | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME , SM/13448 | New | Tubewell boring by ODEX-195 method of drilling including rising main connection, repair & renovation of PH, B/wall and Main building of inspection bungalow including painting works, cons of pathway, surface drain, cons of balance civil works of annex building other allied works at Jayanti Inspection bungalow under Alipurduar Divn, PHE Dte. | 2424/ALD | 10/11/2023 | 90 | TAPASH KUMAR BHOWMICK | 53.99 | 0 | 0 | 25
1780 | ALIPURDUAR | Alipurduar Division | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME , SM/13448 | New | Supply of CIDF/CIPE pipes and specials for Jayanti TG-II Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 607/ALD | 29/02/2024 | 30 | BARMAN ENTERPRISE | 8.6 | 0 | 0 | 61
1781 | ALIPURDUAR | Alipurduar Division | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME , SM/13448 | New | Material Requisition To Resource Division | 132/ALD | 10/01/2024 | 0 | Resource Division | 3.47 | 0 | 0 | 0
1782 | ALIPURDUAR | Alipurduar Division | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME , SM/13448 | New | Cons of PH AND TW Boring by ODEX-165 drilling at HW site and 2nd site , LDS with HDPE P/LINE INCL RM and delivery connection , CONS of 100 Cum OHR along with the Soil investigation works , providing FHTC and others for Jayanti Tea Garden-II PWSS Under Alipurduar Division PHE DTE. | 637/ALD | 06/06/2023 | 901 | ACHINTA SAHA | 170.77 | 40 | 23.42 | 70
1783 | ALIPURDUAR | Northern Mechanical Division II | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME , SM/13448 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Jayanti Area TG II water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | 2390/NMD-II | 09/08/2023 | 762 | SUNLIT | 18.09 | 0 | 0 | 80
1784 | ALIPURDUAR | Northern Mechanical Division II | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME , SM/13448 | New | Yard lighting arrangement at Head Work Site for Different PWSS (NIMTI DOMOHANI and Others) under JJM in the BLOCK: Kalchini, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1386/NMD-II | 26/06/2025 | 30 | AMUSAR IMPEX PVT LTD | 22.95 | 0 | 0 | 0
1785 | ALIPURDUAR | Northern Mechanical Division II | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME , SM/13448 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1786 | ALIPURDUAR | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Providing balance FHTC for TELIPARA PWSS under Alipurduar Division, PHE Dte. | 1570/ALD | 23/08/2023 | 30 | DHANENDRA SARKAR | 4.32 | 0 | 0 | 0
1787 | ALIPURDUAR | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Material Requisition To Resource Division | 222/ALD | 03/05/2023 | 0 | Resource Division | 12.68 | 0 | 0 | 0
1788 | ALIPURDUAR | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Material Requisition To Resource Division | 2398/ALD | 08/11/2023 | 0 | Resource Division | 6.34 | 0 | 0 | 0
1789 | ALIPURDUAR | Northern Mechanical Division II | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | QUOTATION FOR NEW SERVICE CONNECTION AT TELIPARA PWSS PH NO-I | BP-2023-24-51 | 12/05/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
1790 | ALIPURDUAR | Northern Mechanical Division II | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | QUOTATION FOR NEW SERVICE CONNECTION AT TELIPARA PWSS PH NO-II | BP-2023-24-50 | 12/05/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
1791 | ALIPURDUAR | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Constructions of P/H and T/W Boring by ODEX-165 Method of drilling at HW and 2nd site , LDS with UPVC P/L including rising main and delivery connection, Cons. of 200 Cum OHR as per Departmental Design & drawing along with soil investigation works, providing FHTC and others allied works for TELIPARA PWSS Under Alipurduar Division PHE DTE. | 3640/ALD | 31/03/2023 | 180 | MATRI ENTERPRISE | 225.29 | 74.91 | 33.25 | 85
1792 | ALIPURDUAR | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Material Requisition To Resource Division | 4268/ALD | 13/12/2024 | 0 | Resource Division | 13.19 | 0 | 0 | 0
1793 | ALIPURDUAR | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
1794 | ALIPURDUAR | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Laying of new additional pipeline opposite flanks of the higher dia UPVC pipeline and to connect the scattered house with the distribution system in view of providing FHTC, Construction of RCC pillars for supporting DI Pipe, trial run and others allied works in connection with the Telipara PWSS under Alipurduar Division, PHE Dte. | 4907/ALD | 31/01/2025 | 45 | MATRI ENTERPRISE | 39.9 | 0 | 0 | 0
1795 | ALIPURDUAR | Northern Mechanical Division II | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Solarization of grid connected pumping installation at Different PWSS at Kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 820/NMD-II | 06/03/2025 | 30 | WATER TECH | 29.68 | 0 | 0 | 0
1796 | ALIPURDUAR | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1797 | ALIPURDUAR | Northern Mechanical Division II | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1798 | ALIPURDUAR | Northern Mechanical Division II | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1347/NMD-II | 19/06/2025 | 30 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
1799 | ALIPURDUAR | Northern Mechanical Division II | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for TELIPARA water supply scheme, TW no I & II under Northern Mechanical Division-II, PHE Dte.Alipurduar | 2421/NMD-II | 10/08/2023 | 572 | QUAZI NOZRUL ISLAM | 21.7 | 0 | 0 | 100
1800 | ALIPURDUAR | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Laying of rising main line HDPE PN10, horizontal boring by HDD method, bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block, Land development along with the others allied works at Telipara Headwork site PWSS under Alipurduar Division, PHE Dte. | 205/ALD | 16/01/2024 | 360 | HARIDAS GHOSH | 31.65 | 0 | 0 | 90
1801 | ALIPURDUAR | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. , SM/13303 | New | Supply of DI specials and CI Jeffy coupling for Telipara Water Supply Scheme (SM/13303) of Kumargram Block under Alipurduar Division P.H.E. Dte. | 834/ALD | 14/03/2024 | 360 | HARI CONSTRUCTION | 13.58 | 0 | 0 | 80
1802 | ALIPURDUAR | Alipurduar Division | KALABERIA PIPED WATER SUPPLY SCHEME , SM/13306 | New | Providing FHTC from existing distribution system as per specification for Kalaberia PWSS PWSS under Alipurduar Division, PHE Dte. | 1890/ALD | 07/09/2023 | 30 | SASANKA ROY | 7.46 | 0 | 0 | 0
1803 | ALIPURDUAR | Northern Mechanical Division II | KALABERIA PIPED WATER SUPPLY SCHEME , SM/13306 | New | QUOTATION FOR NSC AT KALABARIA PH NO-II | BP-2023-24-372 | 27/09/2023 | 0 | WBSEDCL | 3.72 | 0 | 0 | 0
1804 | ALIPURDUAR | Northern Mechanical Division II | KALABERIA PIPED WATER SUPPLY SCHEME , SM/13306 | New | QUOTATION FOR NSC AT KALABARIA PH NO-I | BP-2023-24-373 | 27/09/2023 | 0 | WBSEDCL | 4.76 | 0 | 0 | 0
1805 | ALIPURDUAR | Northern Mechanical Division II | KALABERIA PIPED WATER SUPPLY SCHEME , SM/13306 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kalaberia water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | 2163/NMD-II | 27/07/2023 | 463 | M/S PARITOSH BHOWMICK & CO. | 18.12 | 0 | 0 | 100
1806 | ALIPURDUAR | Alipurduar Division | KALABERIA PIPED WATER SUPPLY SCHEME , SM/13306 | New | Material Requisition To Resource Division | 118/ALD | 10/01/2024 | 0 | Resource Division | 6.56 | 0 | 0 | 0
1807 | ALIPURDUAR | Alipurduar Division | KALABERIA PIPED WATER SUPPLY SCHEME , SM/13306 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
1808 | ALIPURDUAR | Alipurduar Division | KALABERIA PIPED WATER SUPPLY SCHEME , SM/13306 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR, Laying Of Rising Main, Distribution System including soil test and providing FHTC for Kolaberia PWSS Under Alipurduar Division, PHE Dte | 3578/ALD | 27/03/2023 | 900 | SASANKA ROY | 283.27 | 47.11 | 16.63 | 12
1809 | ALIPURDUAR | Alipurduar Division | KALABERIA PIPED WATER SUPPLY SCHEME , SM/13306 | New | Gap filling of distribution line river crossing and other allied works for Kalaberia village under Kalaberia PWSS within Alipurduar-I block under Alipurduar Division, PHE Dte. | 968/ALD | 12/06/2025 | 90 | SASANKA ROY | 73.92 | 0 | 0 | 0
1810 | ALIPURDUAR | Northern Mechanical Division II | KALABERIA PIPED WATER SUPPLY SCHEME , SM/13306 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar-I Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 822/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
1811 | ALIPURDUAR | Northern Mechanical Division II | KALABERIA PIPED WATER SUPPLY SCHEME , SM/13306 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1812 | ALIPURDUAR | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | Providing FHTC from existing distribution system as per specification for Pararpar PWSS PWSS under Alipurduar Division, PHE Dte. | 1889/ALD | 07/09/2023 | 30 | INDRAYOODH BHOWAL | 8.26 | 0 | 0 | 0
1813 | ALIPURDUAR | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PARARPAR PWSS P/H NO-I | BP-2023-24-287 | 21/08/2023 | 0 | WBSEDCL | 5.89 | 0 | 0 | 0
1814 | ALIPURDUAR | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | ADDITIONAL QUOTATION FOR APPLICATION NO 4003209532 SITE PARARPAR PWSS ALIPURDUAR. | BP-2023-24-331 | 27/09/2023 | 0 | WBSEDCL | 2.44 | 0 | 0 | 0
1815 | ALIPURDUAR | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PARARPAR PWSS P/H-II | BP-2023-24-288 | 21/08/2023 | 0 | WBSEDCL | 5.63 | 0 | 0 | 0
1816 | ALIPURDUAR | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for PARARPAR water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | 2121/NMD-II | 27/07/2023 | 30 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 18.45 | 0 | 0 | 75
1817 | ALIPURDUAR | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | Gap filling and replacing lower dia pipe and FHTC connection at Pararpar PWSS under Alipurduar Division, PHE Dte. | 3505/ALD | 23/03/2023 | 180 | TAPASH DAS | 6.38 | 6.07 | 95.56 | 98
1818 | ALIPURDUAR | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | Sinking of Big dia Tube Well (250 x 200 mm dia) by R.C. drilling for Aug. of Pararpar PWSS within Alipurduar-I Block of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/14209) | 2294/ALD | 07/08/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 20.72 | 0 | 0 | 100
1819 | ALIPURDUAR | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | Material Requisition To Resource Division | 4257/ALD | 13/12/2024 | 0 | Resource Division | 36.71 | 0 | 0 | 0
1820 | ALIPURDUAR | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR (150 cum) including soil testing, Laying Of Rising Main, Distribution System and providing FHTC for Pararpar PWSS Under Alipurduar Division, PHE Dte. (2nd call) | 3397/ALD | 16/03/2023 | 900 | SASANKA ROY | 324.42 | 11.86 | 3.66 | 3
1821 | ALIPURDUAR | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | CONSTRUCTION OF PUMP HOUSE & BOUNDARY WALL FOR ADDITIONAL TUBEWELL FOR PROVIDING FHTC AND CONSTRUCTION OF RIVER BANK PROTECTION WALL WITH WIRE CREATE AND FILLING NEAR HWS AT PARARPAR PWSS WITHIN ALIPURDUAR-I BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. | 434/ALD | 30/04/2025 | 60 | SASANKA ROY | 21 | 0 | 0 | 0
1822 | ALIPURDUAR | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1823 | ALIPURDUAR | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Pararpar Water Supply Scheme TW No.-III (Additional) under NMD-II,PHE.Dte,Alipurduar. | 787/ALD | 30/05/2025 | 30 | SUBODH KUMAR BANIK | 11.09 | 0 | 0 | 0
1824 | ALIPURDUAR | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | Solarization of grid connected pumping installation at Different PWSS at APD-I ,APD-II , Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1333/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
1825 | ALIPURDUAR | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
1826 | ALIPURDUAR | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME , SM/14209 | New | Gap filling of distribution line, land development and others allied works for augmentation of Pararpar PWSS within APD-I Block under Alipurduar Division, PHE Dte. | 971/ALD | 12/06/2025 | 90 | SASANKA ROY | 60.73 | 0 | 0 | 0
1827 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) , SM/07178 | Retrofitting | Providing House connection for Munshipara piped water supply scheme at Alipurduar-I Block under Alipuduar Division, P.H.E. Dte.Part-II | 1158/ALD | 15/12/2020 | 60 | TAPASH DAS | 19.93 | 27.63 | 155.03 | 82
1828 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) , SM/07178 | Retrofitting | Providing FHTC and other allied works at Munshipara WSS under Alipurduar Division, PHE Dte. | 1303/ALD | 05/10/2021 | 60 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 44.94 | 7.94 | 58.36 | 82
1829 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) , SM/07178 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Munshipara WSS under Alipurduar Division, PHE Dte. Part-5 | 1845/ALD | 10/12/2021 | 30 | RATAN DUTTA | 4.35 | 0 | 0 | 82
1830 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) , SM/07178 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Munshipara WSS under Alipurduar Division, PHE Dte. Part-6 | 1846/ALD | 10/12/2021 | 30 | AASHIRBAD ENTERPRISE | 4.34 | 2.47 | 96.84 | 80
1831 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) , SM/07178 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 0.05 | 3.48 | 72
1832 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) , SM/07178 | Retrofitting | Laying of DI/UPVC pipeline along with PMGSY Road and other misc. works related to Munshipara PWSS under Alipurduar Division PHE DTE. | 1012/ALD | 12/11/2020 | 60 | TAPASH DAS | 35.88 | 47.5 | 96.51 | 83
1833 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) , SM/07178 | Retrofitting | Construction of approach road & car parking area with paver block & chequered tiles at Jainty WSS under Alipurduar Division, PHE Dte. | 2107/ALD | 05/01/2022 | 30 | DAS ENTERPRISE | 5.02 | 0.21 | 100 | 77
1834 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) , SM/07178 | Retrofitting | Providing House connection for BHUTNIRGHAT water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. | 865/ALD | 14/10/2020 | 30 | GOUTAM KUMAR DAS | 4.98 | 2.6 | 200 | 0
1835 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) , SM/07178 | Retrofitting | Sinking of Rig Bore Tube well by Odex-165 method of drilling and installation of Raising Main and laying of DI/MS/HDPE pipe line for the Tulshipara and Lankapara Water Supply Scheme. | 1006/ALD | 12/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 32.34 | 9.4 | 200 | 97
1836 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) , SM/07178 | Retrofitting | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar and Munshipara Water Supply Scheme Area under Alipurduar Division, PHE Dte. | 1317/ALD | 05/10/2021 | 1679 | DILIP MAHATO | 58.07 | 39.35 | 100 | 85
1837 | ALIPURDUAR | Northern Mechanical Division II | Implementation of Affordable IOT System at Paitkapara TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. , SM/16914 | IOT | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Different Block of Alipurduar and Coochbehar District in West Bengal | 807/NMD-II | 04/03/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 594.37 | 0 | 0 | 0
1838 | ALIPURDUAR | Alipurduar Division | Chengmari Piped Water Supply Scheme , SM/18152 | New | Supply of CIDF & CISS Pipes and specials for Paschim Chegmari WSS Under Alipurduar Division P.H.E Dte. | 1597/ALD | 25/08/2023 | 30 | M/S SSB CONSTRUCTION CO. | 6.77 | 0 | 0 | 0
1839 | ALIPURDUAR | Alipurduar Division | Chengmari Piped Water Supply Scheme , SM/18152 | New | Material Requisition To Resource Division | 2698/ALD | 12/12/2023 | 0 | Resource Division | 21.43 | 0 | 0 | 0
1840 | ALIPURDUAR | Alipurduar Division | Chengmari Piped Water Supply Scheme , SM/18152 | New | Laying of distribution system with HDPE/DI pipeline, Providing FHTC and others allied works for Chengmari PWSS Under Alipurduar Division PHE DTE. | 233/ALD | 04/05/2023 | 270 | HARIDAS GHOSH | 248.85 | 205.79 | 82.7 | 65
1841 | ALIPURDUAR | Alipurduar Division | Chengmari Piped Water Supply Scheme , SM/18152 | New | Material Requisition To Resource Division | 214/ALD | 10/01/2024 | 0 | Resource Division | 10.47 | 0 | 0 | 0
1842 | ALIPURDUAR | Alipurduar Division | Chengmari Piped Water Supply Scheme , SM/18152 | New | Material Requisition To Resource Division | 3948/ALD | 26/11/2024 | 0 | Resource Division | 10.47 | 0 | 0 | 0
1843 | ALIPURDUAR | Alipurduar Division | Chengmari Piped Water Supply Scheme , SM/18152 | New | Material Requisition To Resource Division | 4270/ALD | 13/12/2024 | 0 | Resource Division | 22.34 | 0 | 0 | 0
1844 | ALIPURDUAR | Northern Mechanical Division II | Chengmari Piped Water Supply Scheme , SM/18152 | New | New Service Connection Charges for Chegmari PWSS PH NO-1 | BP-193/24-25 | 09/07/2024 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
1845 | ALIPURDUAR | Northern Mechanical Division II | Chengmari Piped Water Supply Scheme , SM/18152 | New | New Service Connection for Chengmari PWSS P/H NO-2 | BP-272/24-25 | 12/08/2024 | 0 | WBSEDCL | 0.76 | 0 | 0 | 0
1846 | ALIPURDUAR | Alipurduar Division | Chengmari Piped Water Supply Scheme , SM/18152 | New | Constructions of pump house and Tube well Boring by ODEX-165 Method of drilling at HW site and 2nd site, Laying of distribution system with HDPE pipeline including rising main and delivery connection, Constructions of 200 Cum OHR as per Departmental Design and drawing along with the Soil investigation works, providing FHTC and others allied works for Chengmari PWSS Under Alipurduar Division PHE DTE. | 423/ALD | 24/05/2023 | 678 | HARIDAS GHOSH | 240.7 | 0 | 0 | 85
1847 | ALIPURDUAR | Alipurduar Division | Chengmari Piped Water Supply Scheme , SM/18152 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1848 | ALIPURDUAR | Alipurduar Division | Chengmari Piped Water Supply Scheme , SM/18152 | New | Laying of new HDPE pipeline for interconnection in the distributation system and bridge/culvert crossing and other allied works in connection with Chengmari PWSS under Alipurduar Division, PHE Dte. | 976/ALD | 12/06/2025 | 90 | HARI CONSTRUCTION | 49.29 | 0 | 0 | 0
1849 | ALIPURDUAR | Northern Mechanical Division II | Chengmari Piped Water Supply Scheme , SM/18152 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for CHENGMARI water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | 2622/NMD-II | 25/08/2023 | 588 | P K ENGINEERING | 22 | 0 | 0 | 100
1850 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) , SM/07123 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | 2764/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 4.02 | 100 | 60
1851 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) , SM/07123 | Retrofitting | Restoration of laying distribution system by replacing of damaged AC pipeline with DI and UPVC pipe of Kumargram WSS under Alipurduar Division, PHE Dte. | 980/ALD | 13/09/2021 | 60 | DILIP MAHATO | 48.35 | 39.41 | 100 | 68
1852 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) , SM/07123 | Retrofitting | Laying of UPVC & DI (with pillar) pipeline for Barobisha Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | 1320/ALD | 05/10/2021 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 79.02 | 6.06 | 100 | 66
1853 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) , SM/07123 | Retrofitting | Laying of UPVC and DI (with pillar) pipeline Barobisa Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | 1575/ALD | 22/11/2021 | 90 | TAPAN CHANDA | 75.74 | 30.67 | 100 | 69
1854 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) , SM/07123 | Retrofitting | Providing House connection for BAROBISHA ZONE- III water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | 860/ALD | 14/10/2020 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 2.5 | 33.37 | 79
1855 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) , SM/07123 | Retrofitting | Distribution line for Barobisha (Zone-III) water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | 730/ALD | 22/09/2020 | 45 | TAPAN CHANDA | 5 | 0.74 | 12.1 | 0
1856 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) , SM/07123 | Retrofitting | Distribution line for Barobisha (Zone-III) water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | 729/ALD | 22/09/2020 | 45 | TAPAN CHANDA | 4.97 | 9.27 | 72.67 | 0
1857 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) , SM/07123 | Retrofitting | Providing House connection for BAROBISHA ZONE- I water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte.(PART-2) | 911/ALD | 16/10/2020 | 30 | TAPAN CHANDA | 4.98 | 9.97 | 200 | 0
1858 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) , SM/07123 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | 1281/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 37.84 | 6.95 | 200 | 94
1859 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) , SM/07123 | Retrofitting | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-1 | 1449/ALD | 25/01/2021 | 45 | MAHENDRA CHHETRI | 43.86 | 2.86 | 100 | 67
1860 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) , SM/07065 | Retrofitting | Construction of Truss roof for office cum Godown Path way at KAIJALI BUSTY WSS under Alipurduar Division PHE Dte. | 449/ALD | 13/05/2022 | 30 | DAS ENTERPRISE | 4.79 | 0 | 0 | 0
1861 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) , SM/07065 | Retrofitting | Providing House connection for KAIJALI BUSTY water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | 1164/ALD | 15/12/2020 | 60 | GHOSH & SAHA CONSTRUCTION | 19.93 | 4.39 | 100 | 68
1862 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) , SM/07065 | Retrofitting | Restoration of pipe line for Turturi Khanda (Kaijali Busty Area), Culvert crossing and Laying Delivery line with DI and MS under Kaijali Busty TG WSS under Alipurduar Division, PHE Dte. | 2202/ALD | 11/01/2022 | 60 | TAPASH KUMAR BHOWMICK | 41.95 | 14.92 | 50 | 66
1863 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) , SM/07065 | Retrofitting | Laying of distribution of HDPE/DI pipeline for TURTURI TG area, Kaijali Busty PWSS under Alipurduar Division, PHE DTE. | 2899/ALD | 08/03/2022 | 60 | ASHOK SAPKOTA | 34.24 | 0 | 0 | 68
1864 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) , SM/07065 | Retrofitting | Laying Delivary line with M.S FOR Connection of KAIJALI BUSTY WSS under Jainti TG Water Supply Scheme . | 451/ALD | 13/05/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.94 | 0 | 0 | 66
1865 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) , SM/07065 | Retrofitting | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Kaijali Basti Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 702/ALD | 08/06/2022 | 30 | NARENDRA BHADANI. | 4.98 | 4.98 | 50 | 66
1866 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) , SM/07065 | Retrofitting | Material Requisition To Resource Division | 396/ALD | 11/05/2022 | 0 | Resource Division | 9.83 | 0 | 0 | 0
1867 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-1) , SM/07135 | Retrofitting | Providing House connection for PASCHIM KHAYERBARI water supply scheme at MADARIHAT-BIRPARA Block under Alipuduar Division, P.H.E. Dte. | 871/ALD | 14/10/2020 | 30 | NARENDRA BHADANI. | 4.98 | 8.97 | 180 | 93
1868 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-1) , SM/07135 | Retrofitting | Extension/Merging of Distribution pipeline (UPVC/DI/MS/CI) from Paschim Khairbari WSS to Uttar Sishubari WSS and others misc. work under Alipurduar Division, PHE Dte. | 1255/ALD | 28/12/2020 | 60 | MITHUN DAS | 45.83 | 36.48 | 100 | 80
1869 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-1) , SM/07135 | Retrofitting | Providing House connection for Paschim Khayerbari water supply scheme at Madarihat-Birpara Block under Alipuduar Division, P.H.E. Dte.(Part-III) | 1133/ALD | 10/12/2020 | 30 | NARENDRA BHADANI. | 4.98 | 4.98 | 50 | 92
1870 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-1) , SM/07135 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS Distribution pipe line and other misc. work for retrofitting of Paschim Khayerbari WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte.(Part-II) | 1177/ALD | 15/12/2020 | 60 | MATARA CONSTRUCTION CO | 45.1 | 42.34 | 100 | 92
1871 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-1) , SM/07135 | Retrofitting | Restotation of pipeline by providing steel piles for JJM at Paschim Khairbari WSS under Alipurduar Division, PHE Dte. | 1227/ALD | 10/08/2022 | 30 | MATARA CONSTRUCTION CO | 1.3 | 0 | 0 | 62
1872 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-1) , SM/07135 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc work for retrofitting of PASCHIM KHAYERBAR WSS under Birpara Sub-Division, Alipurduar Division,PHE Dte. Part-I | 1181/ALD | 15/12/2020 | 60 | SANJIT SAHA | 43.88 | 16.68 | 72.98 | 100
1873 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) , SM/07136 | Retrofitting | Extension/Merging of Distribution pipeline (UPVC/DI/MS/CI) from Paschim Khairbari WSS to Uttar Sishubari WSS and others misc. work under Alipurduar Division, PHE Dte. | 1255/ALD | 28/12/2020 | 60 | MITHUN DAS | 45.83 | 0 | 0 | 80
1874 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) , SM/07136 | Retrofitting | Providing House connection for PASCHIM KHAYERBARI water supply scheme at Madarihat-Birpara Block under Alipuduar Division, P.H.E. Dte. Part-II | 1170/ALD | 15/12/2020 | 60 | MITHUN DAS | 29.88 | 29.88 | 93.28 | 91
1875 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) , SM/07136 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS Distribution pipe line and other misc. work for retrofitting of Paschim Khayerbari WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte.(Part-II) | 1177/ALD | 15/12/2020 | 60 | MATARA CONSTRUCTION CO | 45.1 | 21.58 | 100 | 92
1876 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) , SM/07136 | Retrofitting | Restotation of pipeline by providing steel piles for JJM at Paschim Khairbari WSS under Alipurduar Division, PHE Dte. | 1227/ALD | 10/08/2022 | 30 | MATARA CONSTRUCTION CO | 1.3 | 1.26 | 50 | 62
1877 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) , SM/07136 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc work for retrofitting of PASCHIM KHAYERBAR WSS under Birpara Sub-Division, Alipurduar Division,PHE Dte. Part-I | 1181/ALD | 15/12/2020 | 60 | SANJIT SAHA | 43.88 | 14.43 | 68.66 | 100
1878 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme , SM/07131 | Retrofitting | Fuel bill for the month of August 2021 | 120/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.18 | 0 | 0 | 0
1879 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme , SM/07131 | Retrofitting | Laying of HDPE/DI pipe line at different area of flank of Dheklapara Bandapani under Alipurduar Division, PHE Dte. | 1005/ALD | 12/11/2020 | 60 | M/S PALIT ENTERPRISE | 11.75 | 41.37 | 172.94 | 48
1880 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme , SM/07131 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 15 | 100 | 100
1881 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme , SM/07131 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 5 | 100 | 0
1882 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme , SM/07131 | Retrofitting | Providing House connection for DHEKLAPARA PWSS at MADARIHAT-BIRPARA Block under Alipurduar Division PHED PART 1 | 634/ALD | 03/09/2020 | 90 | DILIP MAHATO | 21.8 | 14.92 | 61.42 | 0
1883 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme , SM/07131 | Retrofitting | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | 1009/ALD | 12/11/2020 | 60 | M/S PALIT ENTERPRISE | 14.4 | 8.95 | 200 | 70
1884 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme , SM/07131 | Retrofitting | Preparation of Augmentation D.P.R after investigation For Jateswar W/S scheme under Alipurduar Division. | 914/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.31 | 0.32 | 100 | 0
1885 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) , SM/07132 | Retrofitting | Supply, delivery and Installation of split type Air Conditioner for Junior Engineer Section of Alipurduar, Sadar Sub-Division, P.H.E Dte. | 1732/ALD | 22/09/2022 | 7 | M/S BADAL CHANDRA SAHA | 0.64 | 0.64 | 100 | 20
1886 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) , SM/07132 | Retrofitting | Supply, delivery and Installation of split type Air Conditioner for Chamber of Assistant Engineer, Alipurduar, Sadar Sub-Division, P.H.E Dte. | 1731/ALD | 22/09/2022 | 7 | M/S BADAL CHANDRA SAHA | 0.64 | 0.64 | 100 | 20
1887 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) , SM/07132 | Retrofitting | Laying of balance DI/MS/HDPE pipeline for the Dalmore-Ramjhora WSS under Alipurduar Division, PHE Dte. | 1456/ALD | 25/01/2021 | 45 | ASHIT KUMAR SINGHA | 21.28 | 0 | 0 | 59
1888 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) , SM/07132 | Retrofitting | Retrofitting of pipeline for Ramjhora TG PWSS area at Madarihat-Birpara Block under Alipurduar Division, P.H.E. Dte. | 1447/ALD | 25/01/2021 | 45 | ASHIT KUMAR SINGHA | 16.96 | 0 | 0 | 58
1889 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) , SM/07132 | Retrofitting | Laying of HDPE pipe line for Dalmore Water Supply Scheme under Alipurduar Division, PHE Dte. | 2996/ALD | 15/03/2022 | 60 | MS DEYS CONSTRUCTION | 8.33 | 0 | 0 | 58
1890 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) , SM/07132 | Retrofitting | Repairing bottom dome, conical, shell wall etc. of existing Dalmore 350 cum OHR including protective and Decorative Acrylic exterior paint of Birpara Sub-Division under Alipurduar Division, P.H.E.Dte. (SM/07132) | 826/ALD | 14/03/2024 | 90 | BHAGWATI BHUJEL | 4.79 | 0 | 0 | 100
1891 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-2) , SM/07061 | Retrofitting | Providing House connection for PATLAKHAWA water supply scheme at Alipurduar-I Block under Alipuduar Division, P.H.E. Dte. Part-IV | 1172/ALD | 15/12/2020 | 60 | SOUVIK ROY PALADHI | 23.92 | 12.68 | 100 | 79
1892 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-2) , SM/07061 | Retrofitting | Providing House connection and extension of pipe line for Silbarihat area within PATLAKHAWA PWSS under Alipurduar Division PHE Dte. | 879/ALD | 03/09/2021 | 60 | TAPASH KUMAR BHOWMICK | 45.7 | 25.94 | 100 | 76
1893 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-2) , SM/07061 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | 877/ALD | 03/09/2021 | 60 | M/S STAR INDIA CONSTRUCTION | 33.42 | 0 | 0 | 73
1894 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-2) , SM/07061 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Silbarihat under Patlakhawa PWSS. | 2766/ALD | 25/02/2022 | 60 | TAPASH KUMAR BHOWMICK | 42.34 | 0 | 0 | 75
1895 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-2) , SM/07061 | Retrofitting | Laying of DI pipeline, painting, plastering, land development and other misc works related to Patlakhawa OHR under Patlakhawa PWSS at Alipurduar-I Block, under Alipurduar Division, PHE Dte. | 1855/ALD | 13/12/2021 | 45 | TAPAN CHANDA | 4.26 | 2.62 | 100 | 77
1896 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-2) , SM/07061 | Retrofitting | Providing House connection for BAROBISHA ZONE- III water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | 860/ALD | 14/10/2020 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 0.24 | 100 | 79
1897 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-2) , SM/07061 | Retrofitting | Preparation of Augmentation D.P.R after investigation For Purba Kathalbari W/S scheme under Alipurduar Division. | 911/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.14 | 4.28 | 100 | 0
1898 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme , SM/07180 | Retrofitting | Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. (Part-B) | 845/ALD | 13/10/2020 | 60 | TAPASH KUMAR BHOWMICK | 0.96 | 1.92 | 100 | 0
1899 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme , SM/07180 | Retrofitting | Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. (Part-C) | 1092/ALD | 02/12/2020 | 60 | HARIDAS GHOSH | 0.96 | 1.92 | 100 | 0
1900 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme , SM/07180 | Retrofitting | Collectio of house hold details at prescribrd format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same to PHE Dte. in soft copy.(Part-B) | 844/ALD | 13/10/2020 | 60 | TAPASH KUMAR BHOWMICK | 0.98 | 1.96 | 100 | 0
1901 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme , SM/07180 | Retrofitting | Collectio of house hold details at prescribrd format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same to PHE Dte. in soft copy.(Part-C) | 1091/ALD | 02/12/2020 | 60 | HARIDAS GHOSH | 0.98 | 1.96 | 100 | 0
1902 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme , SM/07180 | Retrofitting | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) (Preferably TUV) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte.(from 01.01.2022 to 31.12.2022) | 2013/ALD | 29/12/2021 | 365 | MATRI ENTERPRISE | 1.76 | 0 | 0 | 0
1903 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme , SM/07180 | Retrofitting | Providing FHTC from existing distribution system as per specification for TOTOPARA PWSS under madarihat - Birpara Block under Alipurduar Division PHE Dte. | 669/ALD | 21/05/2025 | 90 | DULAL DAS | 23.27 | 0 | 0 | 0
1904 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | Construction of Approach road for 2nd TWS & others misc work of Radharani WSS under Alipurduar Division PHE Dte. | 904/ALD | 03/09/2021 | 30 | SOUVIK ROY PALADHI | 4.98 | 1.35 | 100 | 86
1905 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 0 | 0 | 72
1906 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | Laying HDPE pipe , Road crossing and other misc woks related to Radharani WSS under Alipurduar Division PHE Dte. | 1838/ALD | 10/12/2021 | 45 | UMWELT ENGINEER PVT. LTD. | 3.01 | 2.35 | 100 | 91
1907 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | Providing FHTC at surrounding area of Radharani Piped Water Supply Scheme Under Alipurduar Division, PHE DTE. | 2762/ALD | 25/02/2022 | 60 | SOUVIK ROY PALADHI | 34.95 | 24.47 | 100 | 92
1908 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | PROVIDING HOUSE CONNECTION FOR RADHARANI PWSS AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-2 | 1028/ALD | 18/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 37.24 | 0 | 0 | 91
1909 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | Balance work of OHR Construction of PHouse B/Wall Godown & ODEX-165 Tubewell incl. laying of DI/HDPE Pipe for Nayabasti SSB Camp at RADHARANI PWSS under Alipurduar Division PHED. | 627/ALD | 03/09/2020 | 120 | UMWELT ENGINEER PVT. LTD. | 65.53 | 6.18 | 100 | 92
1910 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | PROVIDING HOUSE CONNECTION FOR RADHARANI PWSS AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-1 | 1027/ALD | 18/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 37.24 | 0 | 0 | 92
1911 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | Balance work of office cum Godown at Radharani WSS under Alipurduar Division PHE Dte. | 1839/ALD | 10/12/2021 | 60 | UMWELT ENGINEER PVT. LTD. | 4.97 | 5.18 | 100 | 92
1912 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | Balance work of construction of RADHARANI GODOWN cum REST SHED at RADHARANI WSS under Alipurduar Division , PHE Dte ( Part - A) | 454/ALD | 13/05/2022 | 30 | BHAGWATI BHUJEL | 5.02 | 4.79 | 50 | 92
1913 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | Construction of Approach Road with paver Block at RADHARANI WSS under Alipurduar Division , PHE Dte | 455/ALD | 13/05/2022 | 30 | BHAGWATI BHUJEL | 4.96 | 4.66 | 50 | 92
1914 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | Plinth protection of office cum GODOWN surface dressing & land development (H/W) at RADHARANI WSS under Alipurduar Division , PHE Dte | 457/ALD | 13/05/2022 | 30 | DILIP MAHATO | 4.39 | 3.84 | 100 | 82
1915 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | Balance work of Radharani Godown cum rest shed under Radharani WSS under Alipurduar Division, PHE Dte. (Part-B) | 1020/ALD | 21/07/2022 | 30 | ASHOK PRADHAN | 2.82 | 2.77 | 50 | 89
1916 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | Laying of HDPE pipe line for Bijaynagar Busty Area under Radharani Water Supply Scheme, Alipurduar Division, PHE Dte. | 2201/ALD | 11/01/2022 | 60 | SOUVIK ROY PALADHI | 41.96 | 6.57 | 100 | 92
1917 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) , SM/07186 | Retrofitting | Construction of Pump House, Boundary wall, Tube well boring (ODEX- 165 Method) Rising main of 4th T/W site of Radharani TG WSS under Alipurduar Division, PHE Dte. | 1689/ALD | 20/09/2022 | 120 | BHAGWATI BHUJEL | 20.53 | 17.04 | 87.45 | 100
1918 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) , SM/07188 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Banchukamari WSS under Alipurduar Division, PHE Dte. Part-4 | 1844/ALD | 10/12/2021 | 30 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.04 | 2.02 | 80.02 | 87
1919 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) , SM/07188 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Banchukamari PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | 2378/ALD | 31/01/2022 | 60 | SHIBA ENTERPRISE | 51.82 | 9.81 | 37.84 | 87
1920 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) , SM/07188 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of BANCHUKAMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2191/ALD | 11/01/2022 | 90 | HITANGSHU CHOUDHURY | 21.92 | 19.14 | 100 | 56
1921 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) , SM/07188 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Banchukamari WSS under Alipurduar Division, PHE Dte. Part-3 | 1843/ALD | 10/12/2021 | 1422 | PROJIT HALDER | 5.02 | 2.18 | 86.9 | 87
1922 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) , SM/07063 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply scheme (Subhaspally area, right side of NH) under Alipuduar Division, P.H.E. Dte. Part-5 | 1248/ALD | 28/12/2020 | 60 | BILTU DAS | 29.59 | 0.09 | 100 | 82
1923 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) , SM/07063 | Retrofitting | "Providing House Connection (FHTC) at Salsalabari WSS under Alipurduar Division, PHE Dte. Part-5" | 2115/ALD | 05/01/2022 | 30 | MATRI ENTERPRISE | 5.04 | 5.04 | 100 | 97
1924 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) , SM/07063 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 10 | 100 | 100
1925 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) , SM/07063 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 5 | 100 | 0
1926 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) , SM/07063 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under SALSALABARI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | 1279/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 45.43 | 37.63 | 132.44 | 97
1927 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) , SM/07063 | Retrofitting | Providing House connection for BAROBISHA ZONE- III water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | 860/ALD | 14/10/2020 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 0.09 | 100 | 79
1928 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) , SM/07063 | Retrofitting | Extension and replacement of damaged pipeline and providing house connection at Salsalabari area under Alipurduar Division, PHE Dte. | 978/ALD | 13/09/2021 | 180 | HARIDAS GHOSH | 17.44 | 5.95 | 50.87 | 100
1929 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) , SM/07063 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Salsalabari Under Alipurduar Division, PHE DTE. | 2765/ALD | 25/02/2022 | 1140 | NARENDRA BHADANI. | 47.7 | 29.58 | 62.03 | 97
1930 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' , SM/09901 | Augmentation | Laying of HDPE pipeline for Hantapara Topline under Hatapara WSS within Alipurduar Division, PHE Dte. | 2627/ALD | 18/02/2022 | 60 | DILIP MAHATO | 16.19 | 0 | 0 | 69
1931 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' , SM/09901 | Augmentation | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for HANTUPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2713/ALD | 23/02/2022 | 90 | SUBIR GHOSH | 25.31 | 7.67 | 57.83 | 41
1932 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' , SM/09901 | Augmentation | Laying of additional dedicated HDPE pipeline near PH No-1 village for the Hantapara WSS under Alipurduar Division, PHE Dte. | 2904/ALD | 08/03/2022 | 60 | SUBIR GHOSH | 11.78 | 8.03 | 68.13 | 39
1933 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' , SM/09901 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Hantapara T.G water supply scheme TW No. III under NMD-II, PHE Dte. Alipurduar. | 598/NMD-II | 05/05/2022 | 30 | MIHIR SARKAR | 10.66 | 10.15 | 95.17 | 100
1934 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' , SM/09901 | Augmentation | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at Hantapara T.G Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Alipurduar. | 610/NMD-II | 20/03/2023 | 20 | S.K ENTERPRISE | 3.3 | 3.3 | 100 | 100
1935 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' , SM/09901 | Augmentation | Quotation for new service connection at Hantapara TW No- III | BP-129/22-23 | 13/01/2023 | 0 | WBSEDCL | 1.81 | 0 | 0 | 0
1936 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME , SM/09910 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Paitkapara Tea Garden Water Supply Scheme TW No.-III under NMD-II,PHE.Dte, Alipurduar. | 404/NMD-II | 22/03/2022 | 30 | SAIKAT SINHA | 2.39 | 2.39 | 100 | 0
1937 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME , SM/09910 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for DAKSHIN PAITKAPARA PWSS under Alipurduar Division PHE DTE | 21/ALD | 01/04/2022 | 120 | SOUVIK ROY PALADHI | 230.7 | 0 | 0 | 55
1938 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME , SM/09910 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of PAITKAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 1994/ALD | 27/12/2021 | 90 | ANUP GUPTA | 20.99 | 10.6 | 100 | 80
1939 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME , SM/09910 | Augmentation | Reparing of Pump House at 2nd TW site of PAITKAPARA PWSS Under Alipurduar Division PHE DTE. | 5387/ALD | 17/03/2025 | 60 | DAS CONSTRUCTION | 0.79 | 0 | 0 | 0
1940 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME , SM/09910 | Augmentation | Reparing of Pump House at HEADWORK site of PAITKAPARA PWSS Under Alipurduar Division PHE DTE. | 5389/ALD | 17/03/2025 | 60 | DAS CONSTRUCTION | 0.95 | 0 | 0 | 0
1941 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Quotation for new service connection at Salkumarhat TW No-III, Application No- 4002994687 |  | 21/11/2022 | 0 | WBSEDCL | 1.42 | 0 | 0 | 0
1942 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Quotation for new service connection at SALKUMAR HAT, P/H no. III, Application no. 4002994687 | BP-93/22-23 | 22/11/2022 | 0 | WBSEDCL | 1.42 | 0 | 0 | 0
1943 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumarhat Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | 1242/ALD | 27/09/2021 | 60 | KAMALESH ROY | 25.25 | 4.65 | 48.38 | 9
1944 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Repairing & renovation of Pump House, Pathway, Boundary wall (2nd site) & laying DI Pipe line at Salkumarhat WSS under Alipurduar Division PHE Dte. | 898/ALD | 03/09/2021 | 45 | TAPASH DAS | 4.82 | 0 | 0 | 62
1945 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR MUNSHIPARA P/H NO.III |  | 06/06/2023 | 0 | WBSEDCL | 1 | 0 | 0 | 0
1946 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR SALKUMARHAT P/H NO.IV | BP-2023-24-194 | 22/06/2023 | 0 | WBSEDCL | 1.48 | 0 | 0 | 0
1947 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Cons. Of Rising line, pathway, surface drain, laying of DI and UPVC pipeline and restoration of FHTC at Salkumarhat PWSS under Alipurduar Division, PHE Dte. | 1582/ALD | 24/08/2023 | 90 | TAPASH DAS | 18.46 | 0 | 0 | 5
1948 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Salkumarhat PWSS, Alipurduar-I Block under Alipurduar Division, PHE Dte. | 2898/ALD | 08/03/2022 | 1381 | DILIP MAHATO | 48.52 | 0 | 0 | 65
1949 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at 4th site for SALKUMARHAT PWSS Under Alipurduar Division PHE DTE | 339/ALD | 02/05/2022 | 980 | SHYAMAL ROY | 24.17 | 9.7 | 40.13 | 100
1950 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1951 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Laying of pipeline distribution system (Parallel and left out Area) and other allied works at Salkumarhat PWSS within APD-I Block under Alipurduar Division, PHE Dte. | 1222/ALD | 01/07/2025 | 60 | DILIP MAHATO (OPC) PRIVATE LIMITED | 53.57 | 0 | 0 | 0
1952 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Reparing of Pump House at 2nd site of SALKUMARHAT PWSS Under Alipurduar Division PHE DTE. | 5385/ALD | 17/03/2025 | 60 | TAPASH DAS | 0.79 | 0 | 0 | 0
1953 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Providing balance FHTC and construction of new sluice valve chamber for controlling water including laying UPVC pipe at leftout area of Chhoto Salkumar PWSS and other allied works adjacent to Augmentation of Salkumarhat PWSS under Alipurduar Division, PHE Dte. | 1188/ALD | 26/06/2025 | 90 | M/S DUTTA AND CO | 26.37 | 0 | 0 | 0
1954 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Reparing of Pump House at HEADWORK site of SALKUMARHAT PWSS Under Alipurduar Division PHE DTE. | 5390/ALD | 17/03/2025 | 60 | TAPASH DAS | 0.94 | 0 | 0 | 0
1955 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Painting of Old OHR (350 cum) at Chhoto Salkumar adjacent to Augmentation of Salkumarhat PWSS under Alipurduar Division, PHE Dte. | 2105/ALD | 23/09/2025 | 60 | NARENDRA BHADANI. | 3.04 | 0 | 0 | 0
1956 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Repairing of Pump house at 3rd site of Chhoto Salkumar adjacent to Augmentation of Salkumarhat PWSS under Alipurduar Division, PHE Dte. | 1744/ALD | 13/08/2025 | 60 | ANIRBAN DEY SARKAR CONSTRUCTION | 2.31 | 0 | 0 | 0
1957 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at 3rd site for SALKUMARHAT PWSS Under Alipurduar Division PHE DTE. | 338/ALD | 02/05/2022 | 883 | SUBRATA DAS | 24.16 | 22.94 | 99.55 | 8
1958 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME , SM/10316 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Salkumarhat Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | 2299/NMD-II | 31/07/2023 | 30 | MADHAB SAHA | 20.89 | 0 | 0 | 100
1959 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme , SM/07194 | Retrofitting | Laying of DI/MS/HDPE pipe line from Nepali School (H.S.) towards Birpara Boro Houda WSS providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-I) | 570/20-21 | 26/03/2021 | 0 | GOUTAM KUMAR DAS | 15 | 0 | 0 | 0
1960 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme , SM/07194 | Retrofitting | Extension pipeline (HDPE) for providing FHTC at 28th and 29th mile busty area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | 1576/ALD | 22/11/2021 | 60 | DEBAJYOTI SUTRADHAR | 25.75 | 0.49 | 100 | 69
1961 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme , SM/07194 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 2.89 | 100 | 72
1962 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme , SM/07194 | Retrofitting | Distribution line for Barobisha (Zone-III) water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | 730/ALD | 22/09/2020 | 45 | TAPAN CHANDA | 5 | 9.21 | 200 | 0
1963 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme , SM/07194 | Retrofitting | Providing House connection for PURBA KATHALBARI water supply scheme at ALIPURDUAR-I Block under Alipuduar Division, P.H.E. Dte. | 908/ALD | 16/10/2020 | 30 | SREE MAA CONSTRUCTION & CO. | 4.98 | 6.89 | 200 | 0
1964 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme , SM/07194 | Retrofitting | Providing House connection for UTTAR LATABARI piped water supply scheme under Alipuduar Division, P.H.E. Dte. Part-1 | 1244/ALD | 28/12/2020 | 60 | SHIB RATAN BHOWMIK | 9.97 | 9.97 | 100 | 0
1965 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme , SM/07194 | Retrofitting | Retrofitting of pipeline for UTTAR LATABARAI PWSS (Rabindranagar & surroundings) area at Kalchini Block under Alipurduar Division, PHE Dte. Part-A | 1285/ALD | 05/01/2021 | 60 | ASHOK SAPKOTA | 22.45 | 38.24 | 100 | 46
1966 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME , SM/10667 | Augmentation | Quotation for new service connection at Bakla P/H No- III, Application NO- 4003022080 |  | 28/11/2022 | 0 | WBSEDCL | 1.37 | 0 | 0 | 0
1967 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME , SM/10667 | Augmentation | Land Development, Paver Block installation and Laying and distribution of UPVC pipeline at 2nd Pumphouse site and Adjacent Area of Bakla PWSS under Alipurduar Division, PHE Dte. | 3319/ALD | 13/03/2023 | 90 | SHYAMAL ROY | 11.1 | 10.92 | 100 | 100
1968 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME , SM/10667 | Augmentation | Laying of new UPVC / DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, Land Development works, Construction of surface drain, supply of CIDF specials and other allied works in connection with the Bakla PWSS under Alipurduar Division, PHE Dte. | 2603/ALD | 04/12/2023 | 90 | SHYAMAL ROY | 32.04 | 0 | 0 | 50
1969 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME , SM/10667 | Augmentation | Providing balance FHTC for Bakla PWSSunder Alipurduar Division, PHE Dte. | 1560/ALD | 23/08/2023 | 30 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 2.47 | 0 | 0 | 99
1970 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME , SM/10667 | Augmentation | Laying distribution system with new UPVC pipeline and others allied works for providing functional household Tap Connection(FHTC) in connection with the Augmentation of Bakla PWSS under Alipurduar Division, PHE Dte. | 2230/ALD | 21/11/2022 | 840 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 42.04 | 40.79 | 97.04 | 23
1971 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME , SM/10667 | Augmentation | Restoration of damaged FHTCs, Replacement of old damaged pipeline at Bakla PWSS under Alipurduar Division, PHE Dte. | 815/ALD | 03/06/2025 | 60 | SHYAMAL ROY | 6.23 | 0 | 0 | 0
1972 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME , SM/10667 | Augmentation | Repairing of pump house at headwork site of Bakla PWSS under Alipurduar Division, PHE Dte. | 666/ALD | 21/05/2025 | 60 | SHYAMAL ROY | 1.02 | 0 | 0 | 0
1973 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME , SM/10667 | Augmentation | Repairing of Pump House at 2nd TW site of BAKLA PWSS Under Alipurduar Division PHE DTE. | 1591/ALD | 31/07/2025 | 60 | SHYAMAL ROY | 0.95 | 0 | 0 | 0
1974 | ALIPURDUAR | Alipurduar Division | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME , SM/10180 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling including providing FHTC, laying distribution system and Rising main for Gangutia Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 13/ALD | 01/04/2022 | 120 | SHREE RANISATI ENTERPRISE | 193.63 | 124.7 | 64.4 | 67
1975 | ALIPURDUAR | Alipurduar Division | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME , SM/10180 | New | Supply of CIPE Special & CI Jeffy Coupling for Gangutia Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 707/ALD | 08/06/2022 | 30 | DAS CONSTRUCTION | 4.89 | 4.89 | 50 | 68
1976 | ALIPURDUAR | Alipurduar Division | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME , SM/10180 | New | Construction of OHR 200cum for Gangutia Water Supply Scheme under Alipurduar Division, PHE Dte. | 2599/ALD | 17/02/2022 | 180 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 55.36 | 24.23 | 43.78 | 68
1977 | ALIPURDUAR | Alipurduar Division | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME , SM/10180 | New | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58
1978 | ALIPURDUAR | Alipurduar Division | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME , SM/10180 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 100 | 100 | 0
1979 | ALIPURDUAR | Alipurduar Division | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME , SM/10180 | New | Material Requisition To Resource Division | 1704/ALD | 21/09/2022 | 0 | Resource Division | 61.51 | 0 | 0 | 0
1980 | ALIPURDUAR | Northern Mechanical Division II | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME , SM/10180 | New | Quotation for new service connection at Gangutia TG TW No I | BP-121/22-23 | 09/01/2023 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
1981 | ALIPURDUAR | Northern Mechanical Division II | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME , SM/10180 | New | New Service Connection Charges for Gangutia TG PWSS P/HNO-II | BP-2023-24-600 | 15/02/2024 | 0 | WBSEDCL | 6.02 | 0 | 0 | 0
1982 | ALIPURDUAR | Northern Mechanical Division II | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME , SM/10180 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GANGUTIA TG water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar | 571/NMD-II | 17/03/2023 | 30 | SUMON ELECTRICAL | 21.73 | 17.9 | 83.95 | 100
1983 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/10677 | Augmentation | New Laying of UPVC/DI pipeline,and other allied works including filling of gap in the distribution system for Augmentation of Chandirjhar PWSS under Alipurduar Division, PHE Dte. | 1228/ALD | 10/08/2022 | 30 | MATRI ENTERPRISE | 3.21 | 2.87 | 100 | 8
1984 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/10677 | Augmentation | Retrofitting of pipeline for the 'Jal Sapno' programme and providing FHTC Connection under Chandirjhar WSS under Alipurduar Division, PHE Dte. | 1305/ALD | 05/10/2021 | 60 | SASANKA ROY | 50.06 | 0 | 0 | 36
1985 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/10677 | Augmentation | Laying Distribution pipe line by DI pipe(with piller ) along the flack of Alipurduar - Bhatibari - Salsalabari Road of Chandijhar WSS under Alipurduar Division , PHE Dte. | 440/ALD | 13/05/2022 | 30 | SREE MAA CONSTRUCTION | 4.59 | 4.52 | 100 | 9
1986 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/10677 | Augmentation | Land development of 3rd Tubewell site at Chandirjhar WSS under Alipurduar Division, PHE Dte. | 1232/ALD | 10/08/2022 | 30 | DULAL DAS | 1.36 | 1.26 | 100 | 9
1987 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/10677 | Augmentation | Supply of CIDF Specials & Jeffy Coupling for Augmentation of Chandirjhar (SM/10677) under Alipurduar Division, PHE Dte. | 4538/ALD | 26/12/2024 | 30 | MAHENDRA CHHETRI | 19.05 | 0 | 0 | 0
1988 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/10677 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
1989 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/10677 | Augmentation | Repairing of pump house at headwork site of Chandirjhar PWSS under Alipurduar Division, PHE Dte. | 1857/ALD | 26/08/2025 | 60 | HARI CONSTRUCTION | 1.01 | 0 | 0 | 0
1990 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME , SM/10677 | Augmentation | Laying of new UPVC/DI pipeline for filling of Gap in the distribution system and other allied works in connection with the complain address in the CMRO portal in the command area of Chandirjhar PWSS under Alipurduar Division, PHE Dte. | 202/ALD | 16/01/2024 | 480 | KAMALESH ROY | 14.05 | 0 | 0 | 65
1991 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying distribution system with new HDPE pipeline (Part-F) with Rising Main and delivery line connection, providing FHTC and other allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte | 1644/ALD | 19/09/2022 | 60 | TAPAN CHANDA | 49.13 | 35.12 | 71.48 | 44
1992 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying distribution system with new DI line & Supply of necessary specials, construction of sluice valve chamber, Construction of pump house and boundary wall at HW site of Shrinathpur TG Area PWSS under Alipurduar Division, PHE Dte. | 2245/ALD | 21/11/2022 | 120 | TRIBENI CONSTRUCTION | 14.48 | 0 | 0 | 0
1993 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | 2 nos Tube well boring by ODEX-165 Method of drilling for the works implementation of Shrinathpur Tea Garden Area PWSS under Alipurduar Division, PHE Dte. | 2499/ALD | 13/12/2022 | 45 | S.G. CONSTRUCTION | 13.14 | 10.24 | 77.94 | 0
1994 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying distribution system with new HDPE pipeline (Part- E) and providing FHTC and others allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | 1643/ALD | 19/09/2022 | 60 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 55.49 | 49.11 | 88.5 | 45
1995 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Soil investigation works at head works site for SRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | 2135/ALD | 10/11/2022 | 30 | MOYTEC | 0.7 | 0.7 | 100 | 100
1996 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying distribution system with new HDPE pipeline for providing FHTC in the Command area of Shrinathpur TG PWSS under Alipurduar Division, PHE Dte. | 1469/ALD | 16/08/2023 | 60 | CHANDAN KIRTONIA | 13 | 13 | 100 | 100
1997 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Material Requisition To Resource Division | 1269/ALD | 11/08/2023 | 0 | Resource Division | 21.78 | 0 | 0 | 0
1998 | ALIPURDUAR | Northern Mechanical Division II | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | New Service Connection Charge For Shrinathpur TG | BP-2023-24-224 | 13/07/2023 | 0 | WBSEDCL | 0.81 | 0 | 0 | 0
1999 | ALIPURDUAR | Northern Mechanical Division II | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | New Service Connection Charge For Shrinathpur TG T/W NO.I | BP-2023-24-223 | 13/07/2023 | 0 | WBSEDCL | 0.81 | 0 | 0 | 0
2000 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying distribution system with new HDPE pipeline (Part- D) and providing FHTC and others allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | 1642/ALD | 19/09/2022 | 900 | KAMALESH ROY | 45.33 | 31.15 | 68.72 | 100
2001 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Construction of pathway, surface drain and chatal, land development, along with other allied works at Shrinathpur PWSS under Alipurduar Division, PHE Dte. | 1470/ALD | 16/08/2023 | 420 | KAMALESH ROY | 12.83 | 0 | 0 | 50
2002 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying distribution system the new HDPE pipeline (Part-A) with rising and delivery line connection, providing FHTC and others allied works for Shrinathpur Tea Garden Area PWSS under Alipurduar Division, PHE Dte. | 2657/ALD/ | 22/12/2022 | 600 | DEBAJYOTI SUTRADHAR | 96.35 | 70.41 | 74.54 | 95
2003 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying distribution system with new HDPE pipeline (Part- G) with Rising Main and delivery line connection for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | 1645/ALD | 19/09/2022 | 360 | DEBAJYOTI SUTRADHAR | 62.99 | 60.44 | 98.59 | 45
2004 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying distribution system with new DI line and Supply of necessary specials, construction of sluice valve chamber, Construction of pump house and boundary wall at 2nd site of Shrinathpur TG Area PWSS under Alipurduar Division, PHE Dte. | 2246/ALD | 21/11/2022 | 660 | PRAPTI DUTTA | 11.32 | 5.12 | 46.29 | 100
2005 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying distribution system with new HDPE pipeline (Part-H) with Rising Main and delivery line connection for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | 1646/ALD | 19/09/2022 | 60 | MADHAB SAHA | 56.38 | 53.81 | 99.34 | 45
2006 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Construction of 300 cum OHR as per departmental design and drawing, soil investigation work, laying of DI/CI pipeline, supplying of CI Specials and other allied works at headwork site of Shrinathpur Tea Garden Area PWSS under Alipurduar Division, PHE Dte. | 2690/ALD | 23/12/2022 | 180 | KAMALESH ROY | 93.98 | 59.28 | 65.85 | 100
2007 | ALIPURDUAR | Northern Mechanical Division II | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Shrinathpur TG water supply scheme, TW no I and II of under NMD-II, PHE Dte.APD | 1217/NMD-II | 27/06/2023 | 30 | JAL PRAVAHIKA PVT. LTD. | 21.6 | 0 | 0 | 100
2008 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying distribution system with new HDPE/DI pipeline and other allied works for providing FHTC in connection with the Shrinathpur TG PWSS under Alipurduar Division, PHE Dte. | 1471/ALD | 16/08/2023 | 420 | KAMALESH ROY | 32.95 | 0 | 0 | 100
2009 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Supply of CIDF & CISS Pipes and specials for Srinathpur TG WSS Under Alipurduar Division P.H.E Dte. | 1599/ALD | 25/08/2023 | 30 | GIRIRAJ ENTERPRISE | 6.7 | 0 | 0 | 98
2010 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Land Development, paver block installation and laying of distribution of UPVC Pipeline at 2nd Pump House site and adjacent area of Shrinathpur TG Area PWSS under Alipurduar Division, PHE Dte. | 2014/ALD | 15/09/2023 | 60 | SAMIR SARKAR | 6.97 | 0 | 0 | 100
2011 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Material Requisition To Resource Division | 142/ALD | 10/01/2024 | 0 | Resource Division | 10.48 | 0 | 0 | 0
2012 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
2013 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying distribution system with new HDPE pipeline (Part- B) and providing FHTC and others allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | 1640/ALD | 19/09/2022 | 60 | TAPASH KUMAR BHOWMICK | 55.91 | 45.38 | 81.18 | 50
2014 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying of 90 mm HDPE pipeline in uncovered area and construction of excess work of boundary wall and 3 m span open foundation culvert with boulder protection works and other allied works at 2nd site of Shrinathpur TG PWSS under alipurduar Division, PHE Dte. | 1628/ALD | 04/08/2025 | 75 | PRAPTI DUTTA | 11.82 | 0 | 0 | 0
2015 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying distribution system with new HDPE pipeline (Part- C) and providing FHTC and others allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte | 1641/ALD | 19/09/2022 | 960 | DAS CONSTRUCTION | 58.4 | 54.08 | 96.68 | 45
2016 | ALIPURDUAR | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11709 | New | Laying of HDPE/DI Pipeline for filling up the gap and bridge / culvert crossing, specials repair with trial run of pipeline and allied works at Shrinnathpur TG PWSS under Alipurduar Division, PHE Dte. | 210/ALD | 16/01/2024 | 540 | DEBAJYOTI SUTRADHAR | 29.55 | 0 | 0 | 10
2017 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME , SM/11402 | Augmentation | Laying distribution system along with the other allied works at Santalabari under Augmentation of Jainti Wter Supply Scheme under Alipurduar Division PHE DTE. | 1278/ALD | 17/08/2022 | 60 | ASHOK SAPKOTA | 22.72 | 22.51 | 100 | 63
2018 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME , SM/11402 | Augmentation | Land development, construction of pathway of HWS and 2nd site of different sluice valve chamber and concrete blocks for MS pipe Jainti TG (Nimbu Dhora) WSS under Alipurduar Division, PHE Dte. | 2491/ALD | 13/12/2022 | 60 | DAS CONSTRUCTION | 9.41 | 0 | 0 | 0
2019 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME , SM/11402 | Augmentation | Land development, construction of new pathway, surface drain (2nd site near Tea Factory) and other misc. works related to Jayanti TG PWSS under Alipurduar Division, PHE Dte. | 3503/ALD | 23/03/2023 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.39 | 0 | 0 | 0
2020 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME , SM/11402 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Jayanti Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,,Apd. | 2913/NMD-II | 31/10/2023 | 30 | MUSTAFI CONCERN | 12.17 | 0 | 0 | 0
2021 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME , SM/11402 | Augmentation | Extension pipeline (HDPE) for providing FHTC at Santalbari area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | 1619/ALD | 23/11/2021 | 60 | M/S BHOWMICK CONSTRUCTION | 24.53 | 23.54 | 100 | 60
2022 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME , SM/11402 | Augmentation | Laying of HDPE pipeline & other misc work related to Jayanti WSS under Alipurduar Division, PHE Dte. | 2119/ALD | 05/01/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.28 | 0 | 0 | 71
2023 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME , SM/11402 | Augmentation | Complete elctrification of renovated existing Building Cum Rest Shed AT Jayanti W/S Scheme ,in the dist. Alipurduar. Under NMD-II, P.H E Dte. | 627/NMD-II | 13/05/2022 | 30 | ALPHA ENTERPRISE | 3.52 | 3.39 | 100 | 64
2024 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME , SM/11402 | Augmentation | Laying of HDPE pipeline for restoration of damaged pipeline and others allied works for Jainty WSS under Alipurduar Division, PHE Dte. | 2490/ALD | 13/12/2022 | 30 | TAPASH KUMAR BHOWMICK | 2.14 | 2.14 | 100 | 64
2025 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME , SM/11402 | Augmentation | Balance work of Jainty Rest Shed along with laying of delivery line from CWR of Jainti WSS under Alipurduar Division, PHE Dte. | 2629/ALD | 18/02/2022 | 60 | GHOSH & SAHA CONSTRUCTION | 13.4 | 3.48 | 50 | 64
2026 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME , SM/11402 | Augmentation | Material Requisition To Resource Division | 1261/ALD | 10/08/2023 | 0 | Resource Division | 7.92 | 0 | 0 | 0
2027 | ALIPURDUAR | Northern Mechanical Division II | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARUIPARA TG water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 2412/NMD-II | 10/08/2023 | 30 | A.S. ENTERPRISE | 18.42 | 0 | 0 | 0
2028 | ALIPURDUAR | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Providing balance FHTC for Baruipara PWSS under Alipurduar Division, PHE Dte. | 1565/ALD | 24/08/2023 | 30 | RAMEN DEY & CO | 4.89 | 0 | 0 | 0
2029 | ALIPURDUAR | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Material Requisition To Resource Division | 1278/ALD | 11/08/2023 | 0 | Resource Division | 12.57 | 0 | 0 | 0
2030 | ALIPURDUAR | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Supply of DI pipe & CI special for Baruipara PWSS under Alipurduar Division PHE Dte. | 391/ALD | 19/05/2023 | 30 | HARI CONSTRUCTION | 34.33 | 0 | 0 | 90
2031 | ALIPURDUAR | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Material Requisition To Resource Division | 127/ALD | 10/01/2024 | 0 | Resource Division | 8.85 | 0 | 0 | 0
2032 | ALIPURDUAR | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Material Requisition To Resource Division | 4260/ALD | 13/12/2024 | 0 | Resource Division | 13.75 | 0 | 0 | 0
2033 | ALIPURDUAR | Northern Mechanical Division II | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | New Service Connection Charges for Baruipara pwss PH NO-II | BP-261/24-25 | 09/08/2024 | 0 | WBSEDCL | 5.87 | 0 | 0 | 0
2034 | ALIPURDUAR | Northern Mechanical Division II | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | New Service Connection Charges for Baruipara pwss PH NO-I under NMD-II | BP-326/24-25 | 04/10/2024 | 0 | WBSEDCL | 5.85 | 0 | 0 | 0
2035 | ALIPURDUAR | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr Big dia TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 200 Cum OHR as per Departmental Design and drawing inclu. Soil testing, providing FHTC and others allied works for BARUIPARA PWSS under Alipurduar Division PHE DTE. | 2856/ALD | 17/01/2023 | 985 | TAPAN CHANDA | 403.77 | 186.44 | 46.17 | 80
2036 | ALIPURDUAR | Northern Mechanical Division II | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Solarization of grid connected pumping installation at Different PWSS at Kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 820/NMD-II | 06/03/2025 | 30 | WATER TECH | 29.68 | 0 | 0 | 0
2037 | ALIPURDUAR | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
2038 | ALIPURDUAR | Northern Mechanical Division II | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2039 | ALIPURDUAR | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Laying of new UPVC/DI Pipeline for interconnection in the distribution system and bridge/culvert crossing and other allied works in connection with Baruipara PWSS Alipurduar Division, PHE Dte. | 675/ALD | 21/05/2025 | 90 | TAPAN CHANDA | 29.05 | 0 | 0 | 50
2040 | ALIPURDUAR | Northern Mechanical Division II | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1347/NMD-II | 19/06/2025 | 30 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
2041 | ALIPURDUAR | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME , SM/13241 | New | Supply of DI specials and CI Jeffy coupling for Baruipara Water Supply Scheme (SM/13241) of Kumargram Block under Alipurduar Division P.H.E. Dte. | 842/ALD | 14/03/2024 | 187 | MAKALI ENGINEERING CORPORATION | 15.15 | 0 | 0 | 55
2042 | ALIPURDUAR | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | Providing FHTC from existing distribution system as per specification for Nimti Domohani PWSS under Alipurduar Division, PHE Dte. | 1885/ALD | 07/09/2023 | 30 | DEBAJYOTI SUTRADHAR | 5.22 | 0 | 0 | 0
2043 | ALIPURDUAR | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | Supply of DIDF pipes and DI specials and CI Jeffy Coupling for Nimtijhora Domohoni Water Supply Scheme (SM/13244) of Kalchini Block under Alipurduar Division P.H.E. Dte. | 2067/ALD | 12/07/2024 | 30 | MANSAROVAR CASTING | 9.63 | 0 | 0 | 100
2044 | ALIPURDUAR | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | Supply of DI specials and CI Jeffy coupling for Nimjhora TG Water Supply Scheme(SM/14215) of Kalchini Block under Alipurduar Division P.H.E. Dte. | 851/ALD | 14/03/2024 | 30 | MANSAROVAR CASTING | 13.34 | 0 | 0 | 50
2045 | ALIPURDUAR | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | Material Requisition To Resource Division | 105/ALD | 10/01/2024 | 0 | Resource Division | 9.02 | 0 | 0 | 0
2046 | ALIPURDUAR | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | New Service connection for Nimti Jhora Domohani PWSS, P/H no.-II | BP-2023-24-531 | 11/01/2024 | 0 | WBSEDCL | 6.47 | 0 | 0 | 0
2047 | ALIPURDUAR | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | New Service Connection for Nimti Jhora Domohani PWSS P/H NO-I | BP-2023-24-505 | 05/01/2024 | 0 | WBSEDCL | 5.68 | 0 | 0 | 0
2048 | ALIPURDUAR | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | Construction of 2 nos. Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 200 cum OHR as per Departmental Design & drawing, Pump House , Boundary Wall, Path way including soil test, Providing FHTC and other allied works for NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | 3571/ALD | 27/03/2023 | 480 | DOOARS CONSTRUCTION COMPANY | 446.14 | 104.66 | 23.46 | 90
2049 | ALIPURDUAR | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Nimti Domohini Water Supply Scheme TWNo-I and II under NMD-II,PHE.Dte,APD. | 2909/NMD-II | 31/10/2023 | 562 | GURUKRIPA ENTERPRISE | 21.48 | 0 | 0 | 50
2050 | ALIPURDUAR | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | Balance portion of 110 mm HDPE/DI pipe laying, boundary wall, pump house, land development for HWS and 1st site and platform for FHTC for Nimti Domohoni PWSS Alipurduar Division, PHE Dte. | 693/ALD | 07/03/2024 | 449 | PINTU SAHA | 79.36 | 0 | 0 | 30
2051 | ALIPURDUAR | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 823/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
2052 | ALIPURDUAR | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | 1 Nos TW boring of ODEX-165 for additional T/W for 3rd site of Nimti Domohani PWSS under Alipurduar Division, PHE Dte. | 967/ALD | 12/06/2025 | 30 | CHINMOY BHATTACHARJEE | 8.07 | 0 | 0 | 0
2053 | ALIPURDUAR | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | Yard lighting arrangement at Head Work Site for Different PWSS (NIMTI DOMOHANI and Others) under JJM in the BLOCK: Kalchini, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1386/NMD-II | 26/06/2025 | 30 | AMUSAR IMPEX PVT LTD | 22.95 | 0 | 0 | 0
2054 | ALIPURDUAR | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2055 | ALIPURDUAR | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Nimti Domohini Water Supply Scheme TW No.-III (Additional) under NMD-II,PHE.Dte,Alipurduar. | 786/ALD | 30/05/2025 | 30 | MADHAB SAHA. | 10.8 | 0 | 0 | 0
2056 | ALIPURDUAR | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME , SM/13244 | New | Construction of 1no Pump house, boundary wall and other allied works at 3rd TW Site of Nimti Domohani PWSS under Alipurduar Division, PHE Dte. | 1771/ALD | 18/08/2025 | 120 | SATYABRATA BHATTACHERJEE | 21.28 | 0 | 0 | 0
2057 | ALIPURDUAR | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME , SM/11991 | New | Soil investigation works for proposed overhead reservoir of KARTIKA TG PWSS under Alipurduar Division, PHE Dte. | 2224/ALD | 21/11/2022 | 30 | K S GROUP | 0.65 | 0.65 | 100 | 0
2058 | ALIPURDUAR | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME , SM/11991 | New | Tube well Boring by ODEX-165 method at 2nd TW Site, Cons. of Pump house and boundary wall at HW site, LDS with new HDPE pipeline (Part-B) with Rising Main and delivery line connection, providing FHTC and other allied works for Kartika Tea Garden PWSS under Alipurduar Division, PHE Dte. | 2239/ALD | 21/11/2022 | 120 | TAPASH DAS | 79.55 | 66.61 | 83.74 | 84
2059 | ALIPURDUAR | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME , SM/11991 | New | Material Requisition To Resource Division | 217/ALD | 03/05/2023 | 0 | Resource Division | 18.8 | 0 | 0 | 0
2060 | ALIPURDUAR | Northern Mechanical Division II | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME , SM/11991 | New | Quotation for NSC at P/H No.II under Kartika TG Area W/S/S | BP-2023-24-171 | 15/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
2061 | ALIPURDUAR | Northern Mechanical Division II | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME , SM/11991 | New | Quotation for NSC at P/H No.I under Kartika TG Area W/S/S | BP-2023-24-170 | 15/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
2062 | ALIPURDUAR | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME , SM/11991 | New | Laying distribution system with new DI line and Supply of necessary specials, construction of sluice valve chamber, Construction of pump house and boundary wall at 2nd site of Kartika TG Area PWSS under Alipurduar Division, PHE Dte. | 2247/ALD | 21/11/2022 | 120 | MONORAMA ENTERPRISE | 10.8 | 0 | 0 | 78
2063 | ALIPURDUAR | Northern Mechanical Division II | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME , SM/11991 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kartika TG water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | 2085/NMD-II | 26/07/2023 | 30 | DIAMOND ELECTRICAL WORKS | 18.63 | 0 | 0 | 90
2064 | ALIPURDUAR | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME , SM/11991 | New | Supply of CIDF & CISS Pipes and specials for Kartika TG WSS Under Alipurduar Division P.H.E Dte. | 1594/ALD | 25/08/2023 | 30 | JUGAL CHOUDHURY | 6.76 | 0 | 0 | 68
2065 | ALIPURDUAR | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME , SM/11991 | New | Supply of DI specials and CI Jeffy coupling for Kartika TG Water Supply Scheme (SM/11991) of Kumargram Block under Alipurduar Division P.H.E. Dte. | 841/ALD | 14/03/2024 | 30 | MANSAROVAR CASTING | 13.34 | 0 | 0 | 92
2066 | ALIPURDUAR | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME , SM/11991 | New | Material Requisition To Resource Division | 134/ALD | 10/01/2024 | 0 | Resource Division | 6.95 | 0 | 0 | 0
2067 | ALIPURDUAR | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME , SM/11991 | New | Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 200 cum OHR as per Departmental Design & drawing, Providing FHTC and other allied works for KARTIKA TEA GARDEN PWSS under Alipurduar Division, PHE Dte. | 2976/ALD | 02/02/2023 | 180 | MAHENDRA CHHETRI | 238.07 | 142.5 | 59.86 | 90
2068 | ALIPURDUAR | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME , SM/11991 | New | Repairing and relaying of 90 mm dia damaged HDPE pipeline (from node-33 to 32 to 29 to 25) for Kartika PWSS under Alipurduar Division, PHE Dte. | 1777/ALD | 18/08/2025 | 45 | TAPASH DAS | 1.4 | 0 | 0 | 0
2069 | ALIPURDUAR | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11992 | New | Laying distribution system with new HDPE and DI pipeline, Supply of necessary specials, construction of sluice valve chamber, boundary wall at 2nd site of Phaskhawa TG AREA PWSS under Alipurduar Division, PHE Dte. | 2233/ALD | 21/11/2022 | 90 | RAMEN DEY & CO | 9.7 | 9.17 | 94.52 | 94
2070 | ALIPURDUAR | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11992 | New | Soil investigation works for proposed overhead reservoir of PHASKHAWA TG PWSS under Alipurduar Division, PHE Dte. | 2225/ALD | 21/11/2022 | 30 | K S GROUP | 0.65 | 0.65 | 100 | 0
2071 | ALIPURDUAR | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11992 | New | Material Requisition To Resource Division | 219/ALD | 03/05/2023 | 0 | Resource Division | 13.81 | 0 | 0 | 0
2072 | ALIPURDUAR | Northern Mechanical Division II | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11992 | New | QUOTATION FOR NSC AT PHASKHAWA PH NO-I | BP-2023-24-153 | 01/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
2073 | ALIPURDUAR | Northern Mechanical Division II | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11992 | New | QUOTATION FOR NSC AT PHASKHAWA TG PH NO-II | BP-2023-24-152 | 01/06/2023 | 0 | WBSEDCL | 1.31 | 0 | 0 | 0
2074 | ALIPURDUAR | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11992 | New | Construction of Pump House at Head Work site and providing FHTC and other allied works for Phaskhawa TG PWSS under Alipurduar Division, PHE Dte. | 2228/ALD | 21/11/2022 | 360 | PRITAM DAS | 9.88 | 0 | 0 | 51
2075 | ALIPURDUAR | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11992 | New | Laying distribution system with new HDPE and DI pipeline, Supply of necessary specials, construction of sluice valve chamber, boundary wall at Head work site of Phaskhawa TG AREA PWSS under Alipurduar Division, PHE Dte. | 2231/ALD | 21/11/2022 | 90 | SANKAR ROY | 13.56 | 0 | 0 | 65
2076 | ALIPURDUAR | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11992 | New | Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 200 cum OHR as per Departmental Design & drawing, Providing FHTC and other allied works for PHASKHAWA TEA GARDEN PWSS under Alipurduar Division, PHE Dte | 2977/ALD | 02/02/2023 | 180 | DILIP MAHATO | 133.11 | 55.44 | 41.65 | 61
2077 | ALIPURDUAR | Northern Mechanical Division II | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11992 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Phaskhawa TG water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.APD | 2076/NMD-II | 26/07/2023 | 657 | M/S PARITOSH BHOWMICK & CO. | 18.54 | 0 | 0 | 100
2078 | ALIPURDUAR | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11992 | New | Tube well Boring by ODEX-165 method of drilling at 2nd TW Site, Construction of Pump house at 2nd site, laying of Rising Main and delivery line connection, providing FHTC and other allied works for Phaskhawa Tea Garden PWSS under Alipurduar Division, PHE Dte. | 2238/ALD | 21/11/2022 | 549 | ASHOK SAPKOTA | 22.24 | 6.03 | 27.13 | 100
2079 | ALIPURDUAR | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/11992 | New | Supply of CIDF & CISS Pipes and specials for Phashawa TG WSS Under Alipurduar Division P.H.E Dte. | 1596/ALD | 25/08/2023 | 542 | DILIP MAHATO | 5.64 | 0 | 0 | 85
2080 | ALIPURDUAR | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Supply of CIDF & CISS Pipes and specials for Brajerkuti WSS Under Alipurduar Division P.H.E Dte. | 1602/ALD | 25/08/2023 | 30 | TAPASH KUMAR BHOWMICK | 6.76 | 6.76 | 100 | 99
2081 | ALIPURDUAR | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Material Requisition To Resource Division | 1474/ALD | 16/08/2023 | 0 | Resource Division | 38.52 | 0 | 0 | 0
2082 | ALIPURDUAR | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Laying of new UPVC / DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, Land Development works, Construction of surface drain, supply of CIDF specials and other allied works in connection with the Brajerkuti PWSS under Alipurduar Division, PHE Dte. | 2601/ALD | 04/12/2023 | 404 | TAPASH KUMAR BHOWMICK | 77.06 | 0 | 0 | 25
2083 | ALIPURDUAR | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Brajerkuthi water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | 2377/NMD-II | 09/08/2023 | 30 | SARKAR ELECTRIC | 18.59 | 0 | 0 | 100
2084 | ALIPURDUAR | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Supply of CIDF/CIPE Pipes and Special & CI Jeffy Coupling for Brajerkuthi Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 740/ALD | 12/03/2024 | 30 | TAPASH KUMAR BHOWMICK | 17.3 | 0 | 0 | 51
2085 | ALIPURDUAR | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Material Requisition To Resource Division | 141/ALD | 10/01/2024 | 0 | Resource Division | 11.38 | 0 | 0 | 0
2086 | ALIPURDUAR | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | New Service Connection For Brajerkuthi PWSS P/H No-II | BP-2023-24-492 | 21/12/2023 | 0 | WBSEDCL | 0.71 | 0 | 0 | 0
2087 | ALIPURDUAR | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Additional quotation For Brajerkuthi P/H No.I | BP-2023-24-560 | 19/01/2024 | 0 | WBSEDCL | 4.21 | 0 | 0 | 0
2088 | ALIPURDUAR | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | New Service Connection for Brajerkuti PWSS P/HNo-I | BP-2023-24-493 | 21/12/2023 | 0 | WBSEDCL | 0.71 | 0 | 0 | 0
2089 | ALIPURDUAR | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Road Restoration of Volka Road against Brajerkuthi PWSS | 189/24-25/PFMS | 10/09/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 10.73 | 0 | 0 | 0
2090 | ALIPURDUAR | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Additional service Connection Charge for Brajerkuthi Ph No.II | BP-2023-24-559 | 19/01/2024 | 0 | WBSEDCL | 6 | 0 | 0 | 0
2091 | ALIPURDUAR | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. Big dia. TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 200 Cum OHR as per Departmental Design and drawing inclu. Soil testing, providing FHTC and others allied works for Brajerkuthi PWSS Under Alipurduar Division PHE DTE. | 2855/ALD | 17/01/2023 | 804 | TAPASH KUMAR BHOWMICK | 460.44 | 308.85 | 67.08 | 95
2092 | ALIPURDUAR | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Providing balance FHTC for Brajerkuthi PWSS under Alipurduar Division, PHE Dte. | 1563/ALD | 23/08/2023 | 508 | TAPASH KUMAR BHOWMICK | 6.25 | 0 | 0 | 0
2093 | ALIPURDUAR | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Continuation for the work of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.11.2023 to 31.01.2024) | 2341/ALD | 30/10/2023 | 92 | NIRANJAN KIRTANIA | 0.7 | 0 | 0 | 0
2094 | ALIPURDUAR | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.11.2023 to 31.01.2024) | 2340/ALD | 30/10/2023 | 92 | NIRANJAN KIRTANIA | 0.5 | 0 | 0 | 0
2095 | ALIPURDUAR | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Laying of new additional pipeline opposite flanks of the higher dia UPVC pipeline and to connect the scattered house with the distribution system in view of providing FHTC, bridge/culvert crossing, Construction of Sluice Valve Chamber, trial run and others allied works in connection with the Brajerkuthi PWSS under Alipurduar Division, PHE Dte. | 4583/ALD | 02/01/2025 | 60 | TAPASH KUMAR BHOWMICK | 35.65 | 0 | 0 | 0
2096 | ALIPURDUAR | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
2097 | ALIPURDUAR | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2098 | ALIPURDUAR | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME , SM/13300 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar -I & II Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1293/NMD-II | 12/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 26.61 | 0 | 0 | 0
2099 | ALIPURDUAR | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Providing FHTC from existing distribution system as per specification for Atiabari TG PWSS under Alipurduar Division, PHE Dte. | 1881/ALD | 07/09/2023 | 30 | SOUVIK ROY PALADHI | 9.84 | 0 | 0 | 0
2100 | ALIPURDUAR | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Material Requisition To Resource Division | 1271/ALD | 11/08/2023 | 0 | Resource Division | 35.15 | 0 | 0 | 0
2101 | ALIPURDUAR | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Material Requisition To Resource Division | 1952/ALD | 12/09/2023 | 0 | Resource Division | 129.38 | 0 | 0 | 0
2102 | ALIPURDUAR | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Material Requisition To Resource Division | 2785/ALD | 18/12/2023 | 0 | Resource Division | 11.61 | 0 | 0 | 0
2103 | ALIPURDUAR | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | QUOTATION FOR NSC AT ATIABARI PH NO-II | BP-2023-24-326 | 27/09/2023 | 0 | WBSEDCL | 4.7 | 0 | 0 | 0
2104 | ALIPURDUAR | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new UPVC pipeline , Constructions of 250 Cum OHR as per Departmental Design & drawing including soil investigation works , 2nos pump house & boundary wall, providing FHTC and others allied works for ATIABARI TEA GARDEN PWSS Under Alipurduar Division PHE DTE. | 2981/ALD | 02/02/2023 | 540 | SOUVIK ROY PALADHI | 438.53 | 215 | 49.03 | 75
2105 | ALIPURDUAR | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Laying of CIDI Pipes & UPVC pipeline and other allied works for Atiabari Tea Garden PWSS under ALipurduar Division, PHE Dte. | 3421/ALD | 26/09/2024 | 60 | SOUVIK ROY PALADHI | 35.9 | 0 | 0 | 0
2106 | ALIPURDUAR | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Continuation work order for the work of 'Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new UPVC pipeline , Constructions of 250 Cum OHR as per Departmental Design & drawing including soil investigation works , 2nos pump house & boundary wall, providing FHTC and others allied works for ATIABARI TEA GARDEN PWSS Under Alipurduar Division PHE DTE." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/9/2024-EE(ALI_D) SEC-DPHE (Computer No-974282)) | 1915/ALD | 26/06/2024 | 60 | SOUVIK ROY PALADHI | 15.17 | 0 | 0 | 0
2107 | ALIPURDUAR | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Material Requisition To Resource Division | 4250/ALD | 13/12/2024 | 0 | Resource Division | 31.17 | 0 | 0 | 0
2108 | ALIPURDUAR | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | New Service Connection for Atiabari T.G PWSS P/H No-I, Kalchini | BP-2023-24-509 | 05/01/2024 | 0 | WBSEDCL | 5.81 | 0 | 0 | 0
2109 | ALIPURDUAR | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
2110 | ALIPURDUAR | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Supply of CIDF/CIPE pipes and specials and Sluice Valve for Atiabari TG Water Supply Scheme(SM/14092) of Kalchini Block under Alipurduar Division P.H.E. Dte. | 840/ALD | 14/03/2024 | 459 | MADHAB SAHA | 16.01 | 0 | 0 | 15
2111 | ALIPURDUAR | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
2112 | ALIPURDUAR | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Yard lighting arrangement at Head Work Site for Different PWSS (NIMTI DOMOHANI and Others) under JJM in the BLOCK: Kalchini, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1386/NMD-II | 26/06/2025 | 30 | AMUSAR IMPEX PVT LTD | 22.95 | 0 | 0 | 0
2113 | ALIPURDUAR | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2114 | ALIPURDUAR | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1331/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
2115 | ALIPURDUAR | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14092 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Atiabari TG water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | 2942/NMD-II | 09/11/2023 | 30 | M/S ABHISEK ENGINEERING CONCERN | 21.5 | 0 | 0 | 100
2116 | ALIPURDUAR | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | Material Requisition To Resource Division | 3015/ALD/2022-23 | 07/02/2023 | 0 | Resource Division | 13.69 | 0 | 0 | 0
2117 | ALIPURDUAR | Northern Mechanical Division II | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | NEW CONNECTION SETRVICE FOR RAJABHAT T.G. PWSS P/H I,KALCHINI APPLICATION NO 4003210055 | BP-2023-24-379 | 27/09/2023 | 0 | WBSEDCL | 4.08 | 0 | 0 | 0
2118 | ALIPURDUAR | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | Tube well Boring by ODEX-165 Method drilling at HW, First TW Site including laying distribution system with new UPVC PIPELINE, Cons. of 150cum OHR as per departmental Design & drawing , 2nos Pump House & boundary wall, providing FHTC, soil investigation works and others allied works for Rajabhat Tea Garden PWSS Under Alipurduar Division PHE DTE. (2nd call) | 3194/ALD | 27/02/2023 | 720 | ASHIM KUMAR GHOSH | 219.89 | 123.33 | 60.34 | 77
2119 | ALIPURDUAR | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | Providing FHTC from existing distribution system as per specification for Rajabhat TG PWSS under Alipurduar Division, PHE Dte. | 1884/ALD | 07/09/2023 | 300 | PRITAM DAS | 7.83 | 0 | 0 | 100
2120 | ALIPURDUAR | Northern Mechanical Division II | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | New Service Connection for Rajabhat T.G PWSS P/H NO-II,Kalchini | BP-2023-24-504 | 05/01/2024 | 0 | WBSEDCL | 3.76 | 0 | 0 | 0
2121 | ALIPURDUAR | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
2122 | ALIPURDUAR | Northern Mechanical Division II | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Raja Bhat TG Water Supply Scheme TWNo-I and II under NMD-II,PHE.Dte,APD. | 2679/NMD-II | 11/09/2023 | 577 | RMD TRADING | 21.66 | 0 | 0 | 80
2123 | ALIPURDUAR | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
2124 | ALIPURDUAR | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kalchini Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1052/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
2125 | ALIPURDUAR | Northern Mechanical Division II | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | Yard lighting arrangement at Head Work Site for Different PWSS (NIMTI DOMOHANI and Others) under JJM in the BLOCK: Kalchini, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1386/NMD-II | 26/06/2025 | 30 | AMUSAR IMPEX PVT LTD | 22.95 | 0 | 0 | 0
2126 | ALIPURDUAR | Northern Mechanical Division II | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2127 | ALIPURDUAR | Northern Mechanical Division II | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1331/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
2128 | ALIPURDUAR | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/14093 | New | Laying of UPVC pipes & other allied works for Rajhabhat TG PWSS under Alipurduar Division, PHE Dte. | 4234/ALD | 12/12/2024 | 210 | PRITAM DAS | 19.98 | 0 | 0 | 100
2129 | ALIPURDUAR | Alipurduar Division | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | Providing FHTC from existing distribution system as per specification for Bariguri PWSS under Alipurduar Division, PHE Dte. | 1877/ALD | 07/09/2023 | 30 | DAS CONSTRUCTION | 8.1 | 0 | 0 | 0
2130 | ALIPURDUAR | Northern Mechanical Division II | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | New Service Connection at Bairaguri P/H No.II | BP-2023-24-348 | 27/09/2023 | 0 | WBSEDCL | 3.88 | 0 | 0 | 0
2131 | ALIPURDUAR | Northern Mechanical Division II | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | New Service Connection at Bairaguri P/H No.I | BP-2023-24-347 | 27/09/2023 | 0 | WBSEDCL | 7.58 | 0 | 0 | 0
2132 | ALIPURDUAR | Northern Mechanical Division II | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | New Service Connection at Bairaguri P/H No.III | BP-2023-24-349 | 27/09/2023 | 0 | WBSEDCL | 6.08 | 0 | 0 | 0
2133 | ALIPURDUAR | Alipurduar Division | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | Providing FHTC in school in Banchukamari PWSS under Alipurduar Division P.H.E Dte. | 3357/ALD | 14/03/2023 | 30 | HARI CONSTRUCTION | 0.87 | 0 | 0 | 100
2134 | ALIPURDUAR | Alipurduar Division | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Bairiguri Water Supply(SM/13246) of Alipurduar-I Block Scheme under Alipurduar Division P.H.E. Dte. | 2068/ALD | 12/07/2024 | 30 | BARMAN ENTERPRISE | 11.35 | 0 | 0 | 100
2135 | ALIPURDUAR | Alipurduar Division | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | Providing FHTC in school in Paitkapara PWSS under Alipurduar Division P.H.E Dte. | 3356/ALD | 14/03/2023 | 30 | HARIDAS GHOSH | 0.07 | 0 | 0 | 100
2136 | ALIPURDUAR | Alipurduar Division | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | Material Requisition To Resource Division | 4254/ALD | 13/12/2024 | 0 | Resource Division | 38.94 | 0 | 0 | 0
2137 | ALIPURDUAR | Alipurduar Division | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | Boring of TW, Cons. Of Pump House, boundary wall, OHR (400 cum) inclu. Soil investigation works, Laying of rising main, distribution system and providing FHTC for BARIGURI PWSS under Alipurduar Division PHE DTE. (2nd call) | 333/ALD | 16/05/2023 | 720 | MESSRS A.B.G CONSTRUCTION | 592.24 | 15.83 | 2.67 | 4
2138 | ALIPURDUAR | Northern Mechanical Division II | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bariguri water supply scheme, TW no I,II and III of under Northern Mechanical Division-II, PHE Dte.APD | 2664/NMD-II | 04/09/2023 | 475 | A.S. ENTERPRISE | 27.56 | 0 | 0 | 100
2139 | ALIPURDUAR | Alipurduar Division | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
2140 | ALIPURDUAR | Northern Mechanical Division II | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2141 | ALIPURDUAR | Northern Mechanical Division II | BARIGURI PIPED WATER SUPPLY SCHEME , SM/13246 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar -I & II Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1293/NMD-II | 12/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 26.61 | 0 | 0 | 0
2142 | ALIPURDUAR | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME , SM/13247 | New | QUOTATION FOR NSC AT PRADHAN PARA PH NO-I | BP-2023-24-374 | 27/09/2023 | 0 | WBSEDCL | 3.96 | 0 | 0 | 0
2143 | ALIPURDUAR | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME , SM/13247 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Pradhan Para water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | 2170/NMD-II | 27/07/2023 | 494 | SAIKAT SINHA | 18.2 | 0 | 0 | 100
2144 | ALIPURDUAR | Alipurduar Division | PRODHANPARA PIPED WATER SUPPLY SCHEME , SM/13247 | New | Material Requisition To Resource Division | 117/ALD | 10/01/2024 | 0 | Resource Division | 8.33 | 0 | 0 | 0
2145 | ALIPURDUAR | Alipurduar Division | PRODHANPARA PIPED WATER SUPPLY SCHEME , SM/13247 | New | Material Requisition To Resource Division | 3614/ALD | 24/10/2024 | 0 | Resource Division | 8.11 | 0 | 0 | 0
2146 | ALIPURDUAR | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME , SM/13247 | New | NEW SERVICE CONNECTION CHARGES FOR PRADHAN PARA PWSS P/H NO-II | BP-2023-24-622 | 20/02/2024 | 0 | WBSEDCL | 7.75 | 0 | 0 | 0
2147 | ALIPURDUAR | Alipurduar Division | PRODHANPARA PIPED WATER SUPPLY SCHEME , SM/13247 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR, Laying Of Rising Main, Distribution System including soil test and providing FHTC for Prodhanpara PWSS Under Alipurduar Division, PHE Dte. (2nd call) | 3394/ALD | 16/03/2023 | 838 | MESSRS A.B.G CONSTRUCTION | 425.86 | 0 | 0 | 20
2148 | ALIPURDUAR | Alipurduar Division | PRODHANPARA PIPED WATER SUPPLY SCHEME , SM/13247 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
2149 | ALIPURDUAR | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME , SM/13247 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar-I Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 822/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
2150 | ALIPURDUAR | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME , SM/13247 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2151 | ALIPURDUAR | Alipurduar Division | BALLALGURI PIPED WATER SUPPLY SCHEME , SM/14221 | New | Providing FHTC from existing distribution system as per specification for Ballalguri PWSS under Alipurduar Division, PHE Dte. | 1876/ALD | 07/09/2023 | 30 | RATAN DUTTA | 4.38 | 0 | 0 | 0
2152 | ALIPURDUAR | Northern Mechanical Division II | BALLALGURI PIPED WATER SUPPLY SCHEME , SM/14221 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BALLALGURI TW NO-I | BP-2023-24-68 | 13/05/2023 | 0 | WBSEDCL | 1.6 | 0 | 0 | 0
2153 | ALIPURDUAR | Northern Mechanical Division II | BALLALGURI PIPED WATER SUPPLY SCHEME , SM/14221 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BALLALGURI TW NO-II | BP-2023-24-67 | 13/05/2023 | 0 | WBSEDCL | 1.6 | 0 | 0 | 0
2154 | ALIPURDUAR | Alipurduar Division | BALLALGURI PIPED WATER SUPPLY SCHEME , SM/14221 | New | Material Requisition To Resource Division | 136/ALD | 10/01/2024 | 0 | Resource Division | 3.5 | 0 | 0 | 0
2155 | ALIPURDUAR | Alipurduar Division | BALLALGURI PIPED WATER SUPPLY SCHEME , SM/14221 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR (100cum) including soil testing, Laying Of Rising Main, Distribution System and providing FHTC for Ballalguri PWSS Under Alipurduar Division, PHE Dte. | 2980/ALD | 02/02/2023 | 847 | DILIP MAHATO | 255.82 | 120.85 | 47.24 | 70
2156 | ALIPURDUAR | Northern Mechanical Division II | BALLALGURI PIPED WATER SUPPLY SCHEME , SM/14221 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for BALLALGURI water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | 1266/NMD-II | 05/07/2023 | 609 | MADHAB SAHA | 18.4 | 0 | 0 | 50
2157 | ALIPURDUAR | Northern Mechanical Division II | BALLALGURI PIPED WATER SUPPLY SCHEME , SM/14221 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2158 | ALIPURDUAR | Northern Mechanical Division II | BALLALGURI PIPED WATER SUPPLY SCHEME , SM/14221 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini, Madarihat -Birpara ,kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1332/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
2159 | ALIPURDUAR | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | Quotation for new service connection at MUJNAI T.G . P/H no. V, Application no.4002997419 | BP-84/22-23 | 04/11/2022 | 0 | WBSEDCL | 1.06 | 0 | 0 | 0
2160 | ALIPURDUAR | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | Quotation for new service connection at Mujnai TG P/H No-V |  | 02/11/2022 | 0 | WBSEDCL | 1.06 | 0 | 0 | 0
2161 | ALIPURDUAR | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Mujnai T.G Water Supply scheme T/W No. III under NMD-II,PHE Dte Alipurduar. | 193/NMD-II | 24/02/2022 | 30 | RIPON DAS | 6.83 | 6.83 | 100 | 100
2162 | ALIPURDUAR | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Mujnai T.G Water Supply scheme T/W No.IV under NMD-II,PHE Dte Alipurduar. | 191/NMD-II | 24/02/2022 | 30 | SUMON ELECTRICAL | 6.86 | 6.86 | 100 | 28
2163 | ALIPURDUAR | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | Supply, delivery of Electro mechanical components at Mujnai T.G Water Supply Scheme in the dist of ALIPURDUAR under NMD-II PHE Dte Alipurduar. | 332/NMD-II | 14/03/2022 | 30 | SARKAR ELECTRIC | 11.5 | 11.5 | 51.99 | 27
2164 | ALIPURDUAR | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MUJNAI TG Under CHAA SUNDARI water supply scheme, TW no V under Jal Jeevan Mission under NMD-II, PHE Dte. APD | 2106/NMD-II | 29/12/2022 | 30 | MUSTAFI CONCERN | 9.39 | 8.85 | 94.29 | 28
2165 | ALIPURDUAR | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | Supply, delivery & installation of 10 KVA, Servo Motor operated Copper wound line voltage stabilizer of Mujnai T.G Water Supply Scheme TW No.-III under NMD-II,PHE.Dte,Alipurduar. | 186/NMD-II | 23/02/2022 | 30 | ASHWIRBAD WOOD CRAFT | 1.82 | 1.33 | 50 | 27
2166 | ALIPURDUAR | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | Supply, delivery & installation of 10 KVA, Servo Motor operated Copper wound line voltage stabilizer of Mujnai T.G Water Supply Scheme TW No.-IV under NMD-II,PHE.Dte,Alipurduar. | 169/NMD-II | 22/02/2022 | 30 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 1.81 | 1.81 | 57.67 | 28
2167 | ALIPURDUAR | Alipurduar Division | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | Supply and installation of sign board for different Cha Sundori projects under Madarihat -Birpara Block under Alipurduar Division, PHE Dte. | 208/ALD | 16/01/2024 | 30 | KOUSHIK BHOWMICK | 1.09 | 0 | 0 | 100
2168 | ALIPURDUAR | Alipurduar Division | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | New service connection charges for Mujnai Cha Sundori PH NO-VI under NMD-II | 20249706 | 02/12/2024 | 0 | WBSEDCL | 8.09 | 0 | 0 | 0
2169 | ALIPURDUAR | Alipurduar Division | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | CONS. OF RESERVOIR (100M3), BOUNDARY WALL (80 m), PUMPHOUSE( 1.Nos) ,TUBEWELL (2 Nos.), RISING MAIN AND DISTRIBUTION LINE FOR MUJNAI T.G (All Other Division & Line 475 unit) CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | 1947/ALD | 25/02/2021 | 812 | BILTU DAS | 113.04 | 82.72 | 73.18 | 80
2170 | ALIPURDUAR | Alipurduar Division | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | CONS. OF BOUNDARY WALL (80 m), PUMPHOUSE( 1.Nos) ,TUBEWELL (2 Nos.), RISING MAIN AND DISTRIBUTION LINE FOR MUJNAI T.G (All Other Division & Line 60 unit) CHA SUNDARI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | 1946/ALD | 25/02/2021 | 840 | GHOSH & SAHA CONSTRUCTION | 36.68 | 22.22 | 91.33 | 100
2171 | ALIPURDUAR | Alipurduar Division | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | Cons. of 100 cum OHR,BOUNDARY WALL, PUMP HOUSE, TUBE, RISING MAIN FOR Mouza-MUJNAI TEA GARDEN(JL NO.39,RL Plot No.121,129 &155) 410 unit CHA SUNDARI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION, PHE DTE. of North Bengal Circle-I, PHE Dte. | 436/ALD | 07/02/2024 | 660 | MITHUN DAS | 108.05 | 0 | 0 | 80
2172 | ALIPURDUAR | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. , SM/08580 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Mujnai Water Supply Scheme (Chha Sundari) TW No.-VI under NMD-II,PHE.Dte,Alipurduar. | 2634/NMD-II | 05/12/2024 | 211 | MITRA ENTERPRISE | 10.74 | 0 | 0 | 100
2173 | ALIPURDUAR | Northern Mechanical Division II | Implementation of Affordable IOT System at Jayanti TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. , SM/16911 | IOT | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Different Block of Alipurduar and Coochbehar District in West Bengal | 807/NMD-II | 04/03/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 594.37 | 0 | 0 | 0
2174 | ALIPURDUAR | Northern Mechanical Division II | Implementation of Affordable IOT System at Radharani Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. , SM/16915 | IOT | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Different Block of Alipurduar and Coochbehar District in West Bengal | 807/NMD-II | 04/03/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 594.37 | 0 | 0 | 0
2175 | ALIPURDUAR | Alipurduar Division | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/16821 | New | Material Requisition To Resource Division | 1481/ALD | 16/08/2023 | 0 | Resource Division | 16.32 | 0 | 0 | 0
2176 | ALIPURDUAR | Northern Mechanical Division II | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/16821 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for DALMONI T.G water supply scheme, TW no I and II of ZONE-I AND TW NO.I OF ZONE-II under JJM under NMD-II, PHE Dte. APD. | 2559/NMD-II | 18/08/2023 | 30 | B.B CONCERNED | 31.29 | 0 | 0 | 45
2177 | ALIPURDUAR | Alipurduar Division | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/16821 | New | Material Requisition To Resource Division | 135/ALD | 10/01/2024 | 0 | Resource Division | 2.16 | 0 | 0 | 0
2178 | ALIPURDUAR | Northern Mechanical Division II | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/16821 | New | New Service connection charges for DALMUNI Zone-I PHNO-II under NMD-II | BP-430/24-25 | 16/12/2024 | 0 | WBSEDCL | 5.16 | 0 | 0 | 0
2179 | ALIPURDUAR | Northern Mechanical Division II | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/16821 | New | NEW SERVICE CONNECTION FOR DALMONI TG PWSS TW NO-I | BP-2023-24-690 | 14/03/2024 | 0 | WBSEDCL | 6.67 | 0 | 0 | 0
2180 | ALIPURDUAR | Alipurduar Division | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/16821 | New | Construction of tube wells (3 nos.) by Reverse rotary method of drilling Method of drilling at HW site, 2nd TW site and 3rd site, soil investigation at HW site, constructions of 100 Cum OHR at HW, construction of pump house and boundary wall at H/W, 2nd site and 3rd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Dalmoney Tea Garden PWSS (Zone-I & Zone-II) Under Birpara Subdivision, Alipurduar Division PHE DTE. | 3635/ALD | 31/03/2023 | 180 | M/S HARI BHUSHAN GHOSH AND CO. | 202.87 | 0 | 0 | 10
2181 | ALIPURDUAR | Northern Mechanical Division II | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/16821 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 821/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
2182 | ALIPURDUAR | Northern Mechanical Division II | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/16821 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM DEOGAON and others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1385/NMD-II | 26/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 20.56 | 0 | 0 | 0
2183 | ALIPURDUAR | Northern Mechanical Division II | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/16821 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2184 | ALIPURDUAR | Northern Mechanical Division II | Implementation of Affordable IOT System at Dheklapara TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. , SM/16908 | IOT | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Different Block of Alipurduar and Coochbehar District in West Bengal | 807/NMD-II | 04/03/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 594.37 | 0 | 0 | 0
2185 | ALIPURDUAR | Alipurduar Division | Khagenhat Piped Water Supply Scheme , SM/18151 | New | Providing FHTC from existing distribution system as per specification for Khagenhat PWSS under Alipurduar Division, PHE Dte. | 2170/ALD | 06/10/2023 | 60 | TAPASH DAS | 5.58 | 0 | 0 | 0
2186 | ALIPURDUAR | Alipurduar Division | Khagenhat Piped Water Supply Scheme , SM/18151 | New | Soil investigation at OHR site, constructions of 300 Cum OHR at HW , distribution line and providing FHTC as per Departmental Design & drawing for Khagenhat PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 258/ALD | 08/05/2023 | 180 | DILIP MAHATO | 217.32 | 0 | 0 | 80
2187 | ALIPURDUAR | Alipurduar Division | Khagenhat Piped Water Supply Scheme , SM/18151 | New | Cons. of tube wells at 2nd site by Reverse rotary method of drilling, cons. of pump house and boundary wall at 2nd site, rising main, distribution line(C) and providing FHTC as per Departmental Design & drawing for Khagenhat PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 257/ALD | 08/05/2023 | 120 | PRAMESH LAMA | 176.9 | 0 | 0 | 10
2188 | ALIPURDUAR | Northern Mechanical Division II | Khagenhat Piped Water Supply Scheme , SM/18151 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for KHAGENHAT water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | 2621/NMD-II | 25/08/2023 | 30 | ASHOKE ADHIKARY | 21.88 | 0 | 0 | 40
2189 | ALIPURDUAR | Alipurduar Division | Khagenhat Piped Water Supply Scheme , SM/18151 | New | Material Requisition To Resource Division | 101/ALD | 10/01/2024 | 0 | Resource Division | 12.67 | 0 | 0 | 0
2190 | ALIPURDUAR | Alipurduar Division | Khagenhat Piped Water Supply Scheme , SM/18151 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
2191 | ALIPURDUAR | Northern Mechanical Division II | Khagenhat Piped Water Supply Scheme , SM/18151 | New | New Service Connection charges for Khagenhat PWSS PH NO-1 under NMD-II | BP-327/24-25 | 03/10/2024 | 0 | WBSEDCL | 7.59 | 0 | 0 | 0
2192 | ALIPURDUAR | Northern Mechanical Division II | Khagenhat Piped Water Supply Scheme , SM/18151 | New | New service connection charges for Khagenhat PWSS PH NO-2 | BP-330/24-25 | 03/10/2024 | 0 | WBSEDCL | 1.07 | 0 | 0 | 0
2193 | ALIPURDUAR | Alipurduar Division | Khagenhat Piped Water Supply Scheme , SM/18151 | New | Cons. Of tube wells at H/W site by Reverse rotary method of drilling , cons. of pump house and boundary wall at H/W , rising main, distribution line(B) and providing FHTC as per Departmental Design & drawing for Khagenhat PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | 422/ALD | 24/05/2023 | 1003 | MADHAB SAHA | 201.45 | 0 | 0 | 50
2194 | ALIPURDUAR | Alipurduar Division | Khagenhat Piped Water Supply Scheme , SM/18151 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
2195 | ALIPURDUAR | Northern Mechanical Division II | Khagenhat Piped Water Supply Scheme , SM/18151 | New | Solarization of grid connected pumping installation at Different PWSS at APD-I ,APD-II , Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1333/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
2196 | ALIPURDUAR | Alipurduar Division | Khagenhat Piped Water Supply Scheme , SM/18151 | New | Laying of HDPE pipeline (parallel and balance line ) at Khagenhat PWSS under Alipurduar Division, PHE Dte. | 1627/ALD | 04/08/2025 | 75 | DILIP MAHATO | 77.79 | 0 | 0 | 0
2197 | ALIPURDUAR | Northern Mechanical Division II | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Quotation for new connection of Sidahabari W/Ss P/H no-II, Application no. 4002994719, Ref: 402875931 | BP-70/22-23 | 30/09/2022 | 0 | WBSEDCL | 1.75 | 0 | 0 | 0
2198 | ALIPURDUAR | Northern Mechanical Division II | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Quotation for new connection of Sidahabari PWSS P/H no-I, Application no. 4002994696, Ref: 402875912 | BP-71/22-23 | 30/09/2022 | 0 | WBSEDCL | 1.75 | 0 | 0 | 0
2199 | ALIPURDUAR | Northern Mechanical Division II | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Quotation for new service connection at SIDHABARI P/H NO-II |  | 27/09/2022 | 0 | WBSEDCL | 1.75 | 0 | 0 | 0
2200 | ALIPURDUAR | Northern Mechanical Division II | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Quotation for new service connection at SIDHABARI P/H NO-I |  | 27/09/2022 | 0 | WBSEDCL | 1.75 | 0 | 0 | 0
2201 | ALIPURDUAR | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Construction of 250cum OHR for Sidhabari Water Supply Scheme under Alipurduar Division, PHE Dte. | 2585/ALD | 17/02/2022 | 180 | MS CTR CONSTRUCTION | 57.53 | 35.97 | 62.52 | 55
2202 | ALIPURDUAR | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including providing FHTC and Rising main for SIDHABARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 15/ALD | 01/04/2022 | 120 | BILTU DAS | 181.3 | 88.54 | 48.83 | 56
2203 | ALIPURDUAR | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58
2204 | ALIPURDUAR | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 60 | 100 | 0
2205 | ALIPURDUAR | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Preparation of detailed D.P.R. booklets in connection to Sidhabari PWSS under Alipurduar-I Block under Alipurduar Division P.H.E Dte. | 2821/ALD | 11/01/2023 | 30 | ANIK BHATTACHARJEE | 0.97 | 0.97 | 100 | 56
2206 | ALIPURDUAR | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Material Requisition To Resource Division | 827/ALD | 28/06/2022 | 0 | Resource Division | 25.2 | 0 | 0 | 0
2207 | ALIPURDUAR | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Laying of HDPE and distribution pipes in different suitable locations of Sidhabari PWSS under Alipurduar Division, PHE Dte. | 2970/ALD | 31/01/2023 | 90 | BILTU DAS | 165.16 | 58.58 | 70.94 | 61
2208 | ALIPURDUAR | Northern Mechanical Division II | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SIDHABARI water supply scheme, TW no II in the district of Alipurduar under Northern Mechanical Division-II, | 489/NMD-II | 02/03/2023 | 30 | MITRA ENTERPRISE | 9.85 | 7.53 | 77.64 | 85
2209 | ALIPURDUAR | Northern Mechanical Division II | SIDHABARI PIED WATER SUPPLY SCHEME , SM/10175 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sidhabari water supply scheme, TW no I in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte. APD. | 674/NMD-II | 27/03/2023 | 767 | SOUMEN ELECTRIC | 9.87 | 0 | 0 | 100
2210 | ALIPURDUAR | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | Providing balance FHTC from existing distribution system as per specification for UTTAR MANDABARI PWSS under Alipurduar Division, PHE Dte. | 1988/ALD | 15/09/2023 | 60 | SHYAMAL ROY | 11.35 | 0 | 0 | 0
2211 | ALIPURDUAR | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | Material Requisition To Resource Division | 1257/ALD | 10/08/2023 | 0 | Resource Division | 35.74 | 0 | 0 | 0
2212 | ALIPURDUAR | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | Supply of DIDF pipes and specials and Sluice Valve for Uttar Mendabari Water Supply (SM/16539) Scheme OF Kalchini Block under Alipurduar Division P.H.E. Dte. | 1952/ALD | 02/07/2024 | 30 | KAMALA VALVES AND ENGINEERING PRIVATE LIMITED | 16.5 | 0 | 0 | 85
2213 | ALIPURDUAR | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | Material Requisition To Resource Division | 111/ALD | 10/01/2024 | 0 | Resource Division | 14.35 | 0 | 0 | 0
2214 | ALIPURDUAR | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | Material Requisition To Resource Division | 4253/ALD | 13/12/2024 | 0 | Resource Division | 43.88 | 0 | 0 | 0
2215 | ALIPURDUAR | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | Material Requisition To Resource Division | 3946/ALD | 26/11/2024 | 0 | Resource Division | 14.35 | 0 | 0 | 0
2216 | ALIPURDUAR | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | NEW SERVICE CONNECTION FOR UTTAR MENDABARI PWSS ZONE-I P/H NO-I | BP-2023-24-549 | 18/01/2024 | 0 | WBSEDCL | 10.65 | 0 | 0 | 0
2217 | ALIPURDUAR | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | New Service Connection Charges for Uttar Medabari PWSS PH NO-I Zone-II Under NMD-II | BP-432/24-25 | 16/12/2024 | 0 | WBSEDCL | 8.13 | 0 | 0 | 0
2218 | ALIPURDUAR | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | New Service connection for Uttar Mendabari PWSS, Zone-I, P/H no.-I | BP-2023-24-528 | 11/01/2024 | 0 | WBSEDCL | 6.69 | 0 | 0 | 0
2219 | ALIPURDUAR | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | Constructions of 250 Cum OHR as per Departmental Design & drawing including laying distribution system with new HDPE pipeline, RISING MAIN, Construction of 2(TWO) NOS of BOUNDARY WALL, 3(THREE) NOS ODEX-165 TUBE WELL, 3(THREE) NOS PUMP HOUSE, Soil Investigation work, providing FHTC and others allied works for UTTAR MANDABARI PWSS(ZONE-I+ZONE-II), Alipurduar Division, PHE DTE. | 1113/ALD | 28/07/2023 | 720 | MAHENDRA CHHETRI | 736.75 | 0 | 0 | 77
2220 | ALIPURDUAR | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Uttar Mandabari Water Supply Scheme TW No.- I and II of Zone-I and TW No- I of Zone-II under NMD-II,PHE.Dte,APD. | 2481/NMD-II | 11/08/2023 | 30 | DEY ENTERPRISE (MALDA) | 32.91 | 0 | 0 | 60
2221 | ALIPURDUAR | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
2222 | ALIPURDUAR | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | Construction of 1 no. pump house, boundary wall, 1 no. T/W boring by ODEX- 165 method of drilling at Uttar Mendabari pwss area under Alipurduar Division, PHE Dte. | 5297/ALD | 07/03/2025 | 120 | D.K & SONS | 20.47 | 0 | 0 | 0
2223 | ALIPURDUAR | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2224 | ALIPURDUAR | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME , SM/16539 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini, Madarihat -Birpara ,kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 1332/NMD-II | 18/06/2025 | 90 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
2225 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-2) , SM/07124 | Retrofitting | Providing House connection for PURBA CHEPANI water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. Part-II | 1165/ALD | 15/12/2020 | 60 | TAPAN CHANDA | 23.9 | 23.9 | 100 | 94
2226 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-2) , SM/07124 | Retrofitting | Providing House connection for PURBA CHEPANI water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. Part-III | 1166/ALD | 15/12/2020 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 23.91 | 23.91 | 100 | 95
2227 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-2) , SM/07124 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | 1281/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 37.84 | 0 | 0 | 94
2228 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) , SM/07128 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | 877/ALD | 03/09/2021 | 60 | M/S STAR INDIA CONSTRUCTION | 33.42 | 0 | 0 | 73
2229 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) , SM/07128 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of North side of Pukuritola area under Tapshikatha PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | 2292/ALD | 24/01/2022 | 60 | DEBAJYOTI SUTRADHAR | 26.52 | 24.9 | 100 | 78
2230 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) , SM/07128 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Tapshikhata WSS under Alipurduar Division, PHE Dte. Part-6 | 2143/ALD | 06/01/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 5.03 | 0 | 0 | 76
2231 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) , SM/07128 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Tapshikhata PWSS Under Alipurduar Division, PHE DTE. | 2750/ALD | 24/02/2022 | 60 | AMBITIOUS ENTERPRISE | 36.94 | 4.68 | 100 | 68
2232 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) , SM/07128 | Retrofitting | Withdrawing and relaying of UPVC and DI pipeline due to damaged during bitumen road construction and other misc works at Tapshikhata PWSS under Alipurduar Division, PHE Dte. | 941/ALD | 19/10/2020 | 60 | KAMALESH ROY | 10.81 | 0 | 0 | 77
2233 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) , SM/07128 | Retrofitting | Providing extension of distribution line, AT TAPSHIKATHA G.P from the commissioned TAPSHIKATHA PWSS (UID-APD-022) UNDER ALIPURDUAR DIVISION PHE DTE. | 1481/ALD | 27/01/2021 | 60 | KAMALESH ROY | 12.16 | 2.26 | 100 | 76
2234 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) , SM/07128 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Simlabari area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | 876/ALD | 03/09/2021 | 60 | M/S AMIT KUMAR GUPTA | 35.43 | 25.8 | 100 | 75
2235 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) , SM/07128 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of TAPSHIKHATA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2197/ALD | 11/01/2022 | 1116 | DEBABRATA DUTTA | 21.58 | 4.43 | 68.13 | 69
2236 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-1) , SM/07134 | Retrofitting | New Laying of UPVC/DI pipeline, Providing FHTC and other allied works for Augmentation of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | 1220/ALD | 10/08/2022 | 60 | SREE MAA CONSTRUCTION | 21.55 | 11.07 | 100 | 94
2237 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-1) , SM/07134 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | 1281/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 37.84 | 15.88 | 100 | 94
2238 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-1) , SM/07134 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 40 | 100 | 100
2239 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-1) , SM/07134 | Retrofitting | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | 2730/ALD | 30/12/2022 | 365 | MATRI ENTERPRISE | 4.8 | 0 | 0 | 10
2240 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line for retrofitting and providing functional household tap connection (FHTC) in connection with Jaldhara Jal Sapno of Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | 1378/ALD | 19/01/2021 | 45 | M/S PALIT ENTERPRISE | 43.75 | 0 | 0 | 68
2241 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumar Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | 1243/ALD | 27/09/2021 | 60 | TAPASH DAS | 25.25 | 4.11 | 60.03 | 78
2242 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar Water Supply Scheme Area under Alipurduar Division, PHE Dte. | 1318/ALD | 05/10/2021 | 60 | TAPASH KUMAR BHOWMICK | 35.38 | 3.16 | 82.91 | 85
2243 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC and school & others) at Chhoto Salkumar WSS under Alipurduar Division, PHE Dte.Part-5 | 2303/ALD | 25/01/2022 | 30 | AASHIRBAD ENTERPRISE | 5.03 | 3.99 | 100 | 61
2244 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Laying distribution line of UPVC and providing FHTC connection for Chhoto Salkumar Water Supply Scheme Area under Alipurduar Division, P.H.E. Dte. | 2311/ALD | 25/01/2022 | 45 | AASHIRBAD ENTERPRISE | 5.01 | 0 | 0 | 62
2245 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Construction of 300 m3 capacity RCC Over Head Reservoir For SALKUMARHAT PWSS under Alipurduar Division PHE Dte. | 632/ALD | 03/09/2020 | 90 | HARIDAS GHOSH | 63.58 | 0 | 0 | 80
2246 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Providing House connection for CHOTO SALKUMAR water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | 1169/ALD | 15/12/2020 | 60 | SASANKA ROY | 29.9 | 5.13 | 100 | 70
2247 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Repairing & renovation of Pump House, Pathway, Boundary wall (2nd site) & laying DI Pipe line at Salkumarhat WSS under Alipurduar Division PHE Dte. | 898/ALD | 03/09/2021 | 45 | TAPASH DAS | 4.82 | 0 | 0 | 62
2248 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 20 | 100 | 100
2249 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 10 | 100 | 0
2250 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Laying of UPVC/DI/MS/CI distribution pipeline for Gap filling of Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | 3132/ALD | 25/03/2022 | 30 | PRITAM DAS | 5.04 | 4.19 | 100 | 71
2251 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of CHHOTO SALKUMAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2194/ALD | 11/01/2022 | 90 | KAJAL KUMAR DE | 21.92 | 5.65 | 100 | 46
2252 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Providing FHTC at surrounding area of Chhoto Salkumar Under Alipurduar Division, PHE DTE. | 2754/ALD | 24/02/2022 | 60 | KAJAL KUMAR DE | 34.67 | 0.03 | 0.22 | 45
2253 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) , SM/07176 | Retrofitting | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar and Munshipara Water Supply Scheme Area under Alipurduar Division, PHE Dte. | 1317/ALD | 05/10/2021 | 1679 | DILIP MAHATO | 58.07 | 0 | 0 | 85
2254 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Providing FHTC for Bharnobari / Santali TG area including supply of CI materials and other misc. works under Alipurduar Division, P.H.E. Dte. | 880/ALD | 03/09/2021 | 60 | SOUVIK ROY PALADHI | 30.69 | 19.4 | 63.23 | 95
2255 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | PROVIDNG HOUSE CONNECTION FOR BHARNOBARI TG AREA NEAR DALSINGPARA AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. | 582/ALD | 15/07/2021 | 30 | M/S BHOWMICK CONSTRUCTION | 20.03 | 20.03 | 83.33 | 96
2256 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Construction of Culvert at Hasimara WSS Head Work Site within Alipurduar Division, PHE Dte. | 1597/ALD | 22/11/2021 | 45 | ALATYA CONSTRUCTION & CO. | 4.92 | 4.54 | 92.27 | 98
2257 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Providing FHTC at Southern side of Hasimara Piped Water Supply Scheme Under Alipurduar Division, PHE DTE. | 2811/ALD | 28/02/2022 | 60 | MAHENDRA CHHETRI | 34.74 | 31.27 | 90 | 91
2258 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Extension of pipeline to Bharnabari TG area under Hasimara PWSS for providing at Kalchini Block under Alipurduar Division, P.H.E. Dte.(Part-A) | 794/ALD | 01/10/2020 | 60 | TAPASH KUMAR BHOWMICK | 40.85 | 17.5 | 100 | 98
2259 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Providing House connection for KALCHINI water supply scheme at KALCHINI Block under Alipuduar Division, P.H.E. Dte.(Part-3) | 1463/ALD | 25/01/2021 | 30 | HARI CONSTRUCTION | 4.98 | 2.15 | 33.33 | 97
2260 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar Water Supply Scheme Area under Alipurduar Division, PHE Dte. | 1318/ALD | 05/10/2021 | 60 | TAPASH KUMAR BHOWMICK | 35.38 | 5.13 | 100 | 85
2261 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Laying of HDPE pipeline for Malangi Tea Garden Area within Hasimara Water Supply Scheme under Alipurduar Division, PHE Dte. | 2375/ALD | 31/01/2022 | 60 | MADHAB SAHA | 74.82 | 69.57 | 100 | 94
2262 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Extension of pipeline from Malangi TW to Bharnobari TG area (booster line) under Hasimara PWSS at Kalchini Block under Alipurduar Division, PHE Dte. | 20/ALD | 01/04/2022 | 60 | AASHIRBAD ENTERPRISE | 14.64 | 11.92 | 100 | 50
2263 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Extension of pipeline from Santali TG connection line to upper line of Madhu TG area (booster line) under Hasimara TG PWSS at Kalchini Block under Alipurduar Division, PHE Dte. | 19/ALD | 01/04/2022 | 60 | AASHIRBAD ENTERPRISE | 12.61 | 8.47 | 82.76 | 49
2264 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 50 | 100 | 100
2265 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Providing FHTC at Northern side of Hasimara Piped Water Supply Scheme Under Alipurduar Division, PHE DTE. | 2714/ALD | 23/02/2022 | 60 | ASHIM KUMAR GHOSH | 34.64 | 34.64 | 100 | 49
2266 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Construction of valve chamber, dismantling concrete road and other misc works at Malangi TG area within Hasimara W/S/S under Alipurduar Division, PHE Dte. | 442/ALD | 13/05/2022 | 30 | MADHAB SAHA | 4.9 | 4.55 | 100 | 49
2267 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Hasimara Water Supply Scheme under Alipurduar Division P.H.E. Dte. | 703/ALD | 08/06/2022 | 30 | MADHAB SAHA | 4.84 | 4.84 | 50 | 50
2268 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of HASIMARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 1992/ALD | 27/12/2021 | 90 | MAHENDRA CHHETRI | 42.03 | 42.02 | 64.67 | 49
2269 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Providing House connection for BAROBISHA ZONE- III water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | 860/ALD | 14/10/2020 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 2.15 | 100 | 79
2270 | ALIPURDUAR | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme , SM/08884 | Retrofitting | Laying of HDPE pipeline for New Hasimara Area within Hasimara Water Supply Scheme under Alipurduar Division, PHE Dte. | 2376/ALD | 31/01/2022 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 73.83 | 58.99 | 79.9 | 99
2271 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF BANCHUKAMARI WATER SUPPLY SCHEME , SM/09891 | Augmentation | Quotation for new service connection at banchukamari W/SS TW No-III, Application No-4002956342 |  | 04/08/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
2272 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF BANCHUKAMARI WATER SUPPLY SCHEME , SM/09891 | Augmentation | Quotation for new service connection for BANCHUKAMARI T/W no. III Application no. 4002956342 | BP-44/22-23 | 08/08/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
2273 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF BANCHUKAMARI WATER SUPPLY SCHEME , SM/09891 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at Satkodali and surrounding area of Banchukamari PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte | 2377/ALD | 31/01/2022 | 60 | MATRI ENTERPRISE | 56.5 | 10.74 | 40.47 | 0
2274 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF BANCHUKAMARI WATER SUPPLY SCHEME , SM/09891 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of BANCHUKAMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2191/ALD | 11/01/2022 | 90 | HITANGSHU CHOUDHURY | 21.92 | 0 | 0 | 56
2275 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF BANCHUKAMARI WATER SUPPLY SCHEME , SM/09891 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Banchukamari Water Supply Scheme TW No.-III under NMD-II,PHE.Dte Alipurduar. | 527/NMD-II | 19/04/2022 | 30 | B.B CONCERNED | 7.75 | 6.05 | 44.25 | 100
2276 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF BANCHUKAMARI WATER SUPPLY SCHEME , SM/09891 | Augmentation | Supply, installation, commissioning of 15KVA copper wound line voltage corrector for BANCHUKAMARI water supply scheme TW no- III under JJM under Northern Mechanical Division-II, PHE Dte. | 1207/NMD-II | 13/03/2024 | 30 | D.K AND SONS | 2.39 | 0 | 0 | 100
2277 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME , SM/09898 | Augmentation | Construction of Pump House Boundary Wall Land development & pathway TW Boring (2nd Suite of OHR-1 ODEX 165) Raising Main for Jainti TG PWSS at Kumargram under Alipurduar Division. | 2020/ALD | 20/03/2020 | 0 | DAS CONSTRUCTION | 17.19 | 4.28 | 100 | 0
2278 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME , SM/09898 | Augmentation | Extension pipeline (HDPE) for providing FHTC at 28th and 29th mile busty area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | 1576/ALD | 22/11/2021 | 60 | DEBAJYOTI SUTRADHAR | 25.75 | 1.06 | 100 | 69
2279 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME , SM/09898 | Augmentation | Supply, Delivery and laying of Al. Ar cable for yard Lighting arrangement at jayanti Bungalow in the dist. Of Alipurduar under NMD-II ,P.H.E Dte. | 1385/NMD-II | 22/12/2021 | 30 | MUSTAFI CONCERN | 4.7 | 4.16 | 100 | 0
2280 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME , SM/09898 | Augmentation | Supplying and delivery and fitting fixing of different outdoor decorative lighting fixture in front of new building at Jayanti bunglow in the dist. Of Alipurduar under NMD-II ,P.H.E Dte | 1376/NMD-II | 22/12/2021 | 30 | MUSTAFI CONCERN | 4.38 | 4.38 | 100 | 0
2281 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME , SM/09898 | Augmentation | Supplying and delivery and fitting fixing of different outdoor decorative lighting fixture infront of new building at Jayanti bungalow in the district of Alipurduar under NMD-II, PHE Dte. | 622/NMD-II | 13/05/2022 | 30 | MUSTAFI CONCERN | 3.74 | 3.74 | 100 | 54
2282 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME , SM/09898 | Augmentation | Laying balance portion pipeline and providing house connection at Jayanti Water Supply Scheme and Bhutiya Busty Area under Alipurduar Division, PHE Dte. | 975/ALD | 13/09/2021 | 30 | GHOSH & SAHA CONSTRUCTION | 5.04 | 5.03 | 100 | 54
2283 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME , SM/09898 | Augmentation | Tube well Boring by ODEX-195 method of drilling including Rising main for JAYANTI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2392/ALD | 31/01/2022 | 90 | TAPASH KUMAR BHOWMICK | 12.78 | 11.81 | 92.39 | 44
2284 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME , SM/09898 | Augmentation | Upgradation of Internal illumination system and allied works at Newly Constructed Rest Shed in Jayanti under Jayanti W/S Scheme under Northern Mechanical Division-II, PHE Dte. | 45/NMD-II | 04/01/2023 | 30 | ALPHA ENTERPRISE | 4.03 | 2.72 | 67.47 | 100
2285 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME , SM/09898 | Augmentation | Extension pipeline (HDPE) for providing FHTC at Santalbari area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | 1619/ALD | 23/11/2021 | 60 | M/S BHOWMICK CONSTRUCTION | 24.53 | 0 | 0 | 60
2286 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME , SM/09898 | Augmentation | Laying of HDPE pipeline & other misc work related to Jayanti WSS under Alipurduar Division, PHE Dte. | 2119/ALD | 05/01/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.28 | 0 | 0 | 71
2287 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME , SM/09898 | Augmentation | Supply ,delivery and Installation of pumping machinery of at newly constructed tubewell at Jayanti ,in the dist. Alipurduar , AMSD ,PHE Dte. | 259/AMSD | 23/07/2021 | 15 | MUSTAFI CONCERN | 0.96 | 0 | 0 | 0
2288 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME , SM/09898 | Augmentation | Balance work of Jainty Rest Shed along with laying of delivery line from CWR of Jainti WSS under Alipurduar Division, PHE Dte. | 2629/ALD | 18/02/2022 | 60 | GHOSH & SAHA CONSTRUCTION | 13.4 | 1.53 | 100 | 64
2289 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF 'PASCHIM KHAIRBARI WATER SUPPLY SCHEME' , SM/09900 | Augmentation | Supply, delivery & installation of Electro Mechanical Compopnents at PASCHIM KHAIRBARI W/S Scheme, T.W No. I (Replacement), under NMD-II, PHE, Dte. in the dist of Alipurduar. | 638/NMD-II | 20/05/2022 | 30 | ALPHA ENTERPRISE | 2.87 | 2.87 | 100 | 0
2290 | ALIPURDUAR | Alipurduar Division | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' , SM/09902 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of UTTAR MADARIHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2198/ALD | 11/01/2022 | 90 | DILIP MAHATO | 20.99 | 0 | 0 | 72
2291 | ALIPURDUAR | Alipurduar Division | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' , SM/09902 | Augmentation | Replacement of damaged pipeline in Madarihat Bazar Area PWSS under Alipurduar Division, PHE Dte. | 389/ALD | 19/05/2023 | 180 | KAMALESH ROY | 5.46 | 4.63 | 100 | 95
2292 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' , SM/09902 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Uttar Madarihat water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 2435/NMD-II | 11/08/2023 | 30 | TALUKDAR ENTERPRISE | 12.13 | 0 | 0 | 100
2293 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' , SM/09902 | Augmentation | New service connection charges for UTTAR MADARIHAT PWSS PH NO-III | BP-2023-24-623 | 20/02/2024 | 0 | WBSEDCL | 7.47 | 0 | 0 | 0
2294 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' , SM/09902 | Augmentation | ADDITIONAL QUOTATION FOR AUGUMANTION OF MADHARIHAT | BP-41/24-25 | 26/04/2024 | 0 | WBSEDCL | 0.58 | 0 | 0 | 0
2295 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME , SM/09909 | Augmentation | Supply and Delivery of Al. armoured cable for Breakdown purpose at REJUVENATION OF MADHU TG WATER SUPPLY SCHEME in the dist. Alipurduar under,AMSD,PHE Dte. | 226/AMSD | 21/07/2022 | 15 | MUSTAFI CONCERN | 2.39 | 2.39 | 100 | 52
2296 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME , SM/09909 | Augmentation | Quotation for new service connection at Madhu T.G, P/H no. III, Application no. 4003018858 | BP-94/22-23 | 25/11/2022 | 0 | WBSEDCL | 0.98 | 0 | 0 | 0
2297 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME , SM/09909 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 0 | 0 | 72
2298 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME , SM/09909 | Augmentation | Hiring of Motor cab for site of the Executive Engineer, Northern Mechanical Division-II, PHE Dte. | 201/AMSD | 28/07/2023 | 366 | DILIP MAHATO | 4.16 | 0 | 0 | 0
2299 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME , SM/09909 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of MADHU TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE | 2196/ALD | 11/01/2022 | 90 | NARENDRA BHADANI. | 20.88 | 21.06 | 77.86 | 50
2300 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME , SM/09909 | Augmentation | upply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION of MADHU TG PWSS, TW no .III in the district of ALIPURDUAR under Northern Mechanical Division-II, PHE Dte. | 388/NMD-II | 23/02/2023 | 30 | HARAGOURI ENTERPRISE | 11.59 | 4.73 | 41.23 | 100
2301 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) , SM/07185 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | 2764/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 1.08 | 100 | 60
2302 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) , SM/07185 | Retrofitting | Restoration of laying distribution system by replacing of damaged AC pipeline with DI and UPVC pipe of Kumargram WSS under Alipurduar Division, PHE Dte. | 980/ALD | 13/09/2021 | 60 | DILIP MAHATO | 48.35 | 0 | 0 | 68
2303 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) , SM/07185 | Retrofitting | Laying Distribution line of UPVC, DI Pipe (with pillar) and cons. Of new toilet, repairing of pump house (2nd site), Land Development at Barobisa Zone-I Water Supply Scheme under Alipurduar Division, PHE Dte. | 1319/ALD | 05/10/2021 | 60 | M/S SURAJIT DEY & CO | 81.49 | 0 | 0 | 70
2304 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) , SM/07185 | Retrofitting | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | 3082/ALD | 22/03/2022 | 60 | AASHIRBAD ENTERPRISE | 13.46 | 2.56 | 100 | 70
2305 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) , SM/07185 | Retrofitting | Providing House connection for BAROBISHA Zone-I water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | 1160/ALD | 15/12/2020 | 60 | M/S SURAJIT DEY & CO | 29.98 | 47.09 | 164.07 | 69
2306 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) , SM/07185 | Retrofitting | Providing House connection for BAROBISHA Zone-III water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-II | 1162/ALD | 15/12/2020 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 19.93 | 0 | 0 | 77
2307 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) , SM/07185 | Retrofitting | Providing House connection for BAROBISHA ZONE- II water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | 859/ALD | 14/10/2020 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 9.96 | 200 | 0
2308 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) , SM/07185 | Retrofitting | Preparation of Agumentation D.P.R after investigation For Kumargram W/Sscheme under Alipurduar Division. | 912/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.77 | 2.95 | 69.59 | 0
2309 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) , SM/07185 | Retrofitting | Providing House connection for BAROBISHA ZONE- II water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte.(PART-2) | 912/ALD | 16/10/2020 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 9.97 | 200 | 0
2310 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) , SM/07185 | Retrofitting | Laying of rising main and delivery line connection, horizontal boring by HDD method with HDPE pipe, distribution gap filling with UPVC pipe and others allied works at Barobisha Zone-I PWSS under Alipurduar Division, PHE Dte. | 199/ALD | 16/01/2024 | 540 | SREE MAA CONSTRUCTION | 22.86 | 0 | 0 | 100
2311 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Providing House connection for BIRPARA PWSS, MADARIHAT-BIRPARA Block under Alipuduar Division, P.H.E. Dte | 1766/ALD | 19/02/2021 | 60 | BILTU DAS | 39.46 | 33.54 | 85 | 83
2312 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Providing House connection for MADARIHAT PWSS under Alipuduar Division, P.H.E. Dte. | 1806/ALD | 22/02/2021 | 60 | DILIP MAHATO | 20.13 | 2.01 | 50 | 90
2313 | ALIPURDUAR | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Quotation for new service connection at Madarihat TG P/H No-I |  | 02/11/2022 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
2314 | ALIPURDUAR | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Quotation for new service connection at Madarihat TG P/H No-II |  | 02/11/2022 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
2315 | ALIPURDUAR | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Quotation for new service connection at MADARIHAT T.G, P/H no. II, Application no.4002997569 | BP-81/22-23 | 04/11/2022 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
2316 | ALIPURDUAR | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Quotation for new service connection at Madarihat TG P/H No-III |  | 02/11/2022 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
2317 | ALIPURDUAR | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Quotation for new service connection at MADARIHAT T.G, P/H no. III, Application no.4002997498 | BP-83/22-23 | 04/11/2022 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
2318 | ALIPURDUAR | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Quotation for new service connection at MADARIHAT T.G, P/H no. I, Application no.4002997527 | BP-82/22-23 | 04/11/2022 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
2319 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 0 | 0 | 72
2320 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd & 3rd site including laying distribution system , Rising main and providing FHTC for MADARIHAT TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE | 23/ALD | 01/04/2022 | 120 | DILIP MAHATO | 213.9 | 154.11 | 72.05 | 84
2321 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Repair of Pump House with additional Toilet at 2nd Pump House site of Madarihat WSS under Alipuduar Division, P.H.E. | 877/ALD | 14/10/2020 | 45 | DILIP MAHATO | 2.13 | 0 | 0 | 91
2322 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna for AWC and school under Madarihat WSS under Alipurduar Division, PHE Dte. | 1831/ALD | 10/12/2021 | 30 | RATAN DUTTA | 5.04 | 0.97 | 100 | 59
2323 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Construction of 350cum OHR for Madarihat TG Water Supply Scheme under Alipurduar Division, PHE Dte. | 2586/ALD | 17/02/2022 | 180 | DILIP MAHATO | 71.4 | 51.24 | 63.53 | 90
2324 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 260 | 100 | 0
2325 | ALIPURDUAR | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector of Madarihat TG PWSS, TW no .I in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte | 291/NMD-II | 17/02/2023 | 30 | SUNLIT | 10.73 | 10.04 | 93.59 | 80
2326 | ALIPURDUAR | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector of Madarihat TG PWSS, TW no .III in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte | 299/NMD-II | 18/02/2023 | 30 | MUSTAFI CONCERN | 10.72 | 10.17 | 94.95 | 90
2327 | ALIPURDUAR | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector of Madarihat TG PWSS, TW no .II in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte | 585/NMD-II | 18/03/2023 | 30 | M/S MATRI CONSTRUCTION | 10.82 | 10.17 | 94.9 | 100
2328 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna for Govt office and other Institution under Madarihat WSS under Alipurduar Division, PHE Dte. | 1830/ALD | 10/12/2021 | 30 | BHAGWATI BHUJEL | 5.04 | 5.04 | 100 | 61
2329 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Material Requisition To Resource Division | 491/ALD | 18/05/2022 | 0 | Resource Division | 149.46 | 0 | 0 | 0
2330 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Replacement of damaged pipeline in Madarihat Bazar Area PWSS under Alipurduar Division, PHE Dte. | 389/ALD | 19/05/2023 | 180 | KAMALESH ROY | 5.46 | 0 | 0 | 95
2331 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for MADARIHAT TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE | 18/ALD | 01/04/2022 | 120 | DILIP MAHATO | 216.89 | 197.43 | 49.99 | 100
2332 | ALIPURDUAR | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10173 | New | Material Requisition To Resource Division | 137/ALD | 10/01/2024 | 0 | Resource Division | 14.03 | 0 | 0 | 0
2333 | ALIPURDUAR | Alipurduar Division | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10177 | New | Laying of Distribution Line (HDPE and DI) for retrofitting of FHTC for BIRPARA WSS under Alipurduar Division, PHE Dte. | 1754/ALD | 19/02/2021 | 45 | BILTU DAS | 47.98 | 0 | 0 | 61
2334 | ALIPURDUAR | Alipurduar Division | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10177 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling including providing FHTC and Rising main for JAY BIRPARA TG AREA PWSS under Alipurduar Division PHE DTE. | 2911/ALD | 08/03/2022 | 120 | ALOK ENTERPRISE | 156.25 | 64.37 | 41.2 | 50
2335 | ALIPURDUAR | Alipurduar Division | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10177 | New | Construction of OHR 200cum for Jay Birpara TG Water Supply Scheme under Alipurduar Division, PHE Dte. | 2601/ALD | 17/02/2022 | 180 | SUBHAS CHANDRA ROY | 55.36 | 46.9 | 100 | 80
2336 | ALIPURDUAR | Alipurduar Division | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10177 | New | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58
2337 | ALIPURDUAR | Alipurduar Division | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10177 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 100 | 100 | 0
2338 | ALIPURDUAR | Alipurduar Division | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10177 | New | Material Requisition To Resource Division | 1273/ALD | 11/08/2023 | 0 | Resource Division | 20.82 | 0 | 0 | 0
2339 | ALIPURDUAR | Northern Mechanical Division II | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10177 | New | QUOTATION FOR NEW SERVICE CONNECTION AT JAYBIRPARA TG TW NO-I | BP-2023-24-64 | 13/05/2023 | 0 | WBSEDCL | 1.46 | 0 | 0 | 0
2340 | ALIPURDUAR | Northern Mechanical Division II | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10177 | New | QUOTATION FOR NEW SERVICE CONNECTION AT JAYBIRPARA TG TW NO-II | BP-2023-24-65 | 13/05/2023 | 0 | WBSEDCL | 1.46 | 0 | 0 | 0
2341 | ALIPURDUAR | Northern Mechanical Division II | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10177 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for JAY BIRPARA TG water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar | 2398/NMD-II | 09/08/2023 | 601 | GEETA CONSTRUCTION | 21.71 | 0 | 0 | 65
2342 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | SUPPLY, INSTALLATION, COMMISSIONING AND TRIAL OPERATION OF ELECTRO MECHANICAL COMPONENTS OF RIGBORE T/W (1 NOS) FOR GOPALPUR TG ALONG WITH CONS. OF 1 NO. P/H OF SIZE 3.00M X 3.60M | 1486/ALD | 27/01/2021 | 60 | DILIP MAHATO | 11 | 1.94 | 49.74 | 78
2343 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Construction of 250cum OHR for Gopalpur Tea Garden Water Supply Scheme under Alipurduar Division, PHE Dte. | 2602/ALD | 17/02/2022 | 180 | SASANKA ROY | 57.59 | 57.96 | 55.79 | 72
2344 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-B) | 1968/ALD | 24/12/2021 | 90 | TAPASH DAS | 0.96 | 0.96 | 100 | 78
2345 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-C) | 745/ALD | 11/08/2021 | 90 | HARIDAS GHOSH | 0.96 | 0.96 | 50 | 74
2346 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-C) | 361/ALD | 08/06/2021 | 90 | TAPASH DAS | 0.96 | 0.96 | 100 | 77
2347 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58
2348 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 200 | 100 | 0
2349 | ALIPURDUAR | Northern Mechanical Division II | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Gopalpur TG water supply scheme, TW no II in the district of Alipurduar under Northern Mechanical Division-II PHE Dte APD | 659/NMD-II | 24/03/2023 | 30 | M/S ABHISEK ENGINEERING CONCERN | 9.91 | 9.37 | 94.53 | 90
2350 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Material Requisition To Resource Division | 825/ALD | 28/06/2022 | 0 | Resource Division | 26.08 | 0 | 0 | 0
2351 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Material Requisition To Resource Division | 828/ALD | 28/06/2022 | 0 | Resource Division | 34.42 | 0 | 0 | 0
2352 | ALIPURDUAR | Northern Mechanical Division II | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Quotation for new service connection at gopalpur tg TW No- I | BP-128/22-23 | 13/01/2023 | 0 | WBSEDCL | 1.23 | 0 | 0 | 0
2353 | ALIPURDUAR | Northern Mechanical Division II | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Quotation for new service connection at Gopalpur TG TW No- II | BP-131/22-23 | 13/01/2023 | 0 | WBSEDCL | 1.23 | 0 | 0 | 0
2354 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Providing FHTC from existing distribution system as per specification for Gopalpur TG PWSS under Alipurduar Division, PHE Dte. | 1875/ALD | 07/09/2023 | 300 | NARENDRA BHADANI. | 7.03 | 0 | 0 | 90
2355 | ALIPURDUAR | Northern Mechanical Division II | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Gopalpur TG water supply scheme, TW no I in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte. | 651/NMD-II | 24/03/2023 | 30 | RMD TRADING | 9.91 | 9.08 | 92.97 | 100
2356 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Material Requisition To Resource Division | 139/ALD | 10/01/2024 | 0 | Resource Division | 9.16 | 0 | 0 | 0
2357 | ALIPURDUAR | Northern Mechanical Division II | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | New Service Connection Charges for Gopalpur TG | BP-405/24-25 | 30/10/2024 | 0 | WBSEDCL | 5.59 | 0 | 0 | 0
2358 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC fo GOPALPUR TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | 26/ALD | 01/04/2022 | 1320 | ASHIT KUMAR SINGHA | 136.46 | 60 | 43.97 | 95
2359 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Construction of Tubewell by ODEX-165 method of drilling, construction of of pump house and boundary wall for Gopalpur PWSS under Alipurduar Division, PHE Dte. | 364/ALD | 18/05/2023 | 775 | SWAPAN KUMAR SAHA | 24.47 | 8.5 | 34.74 | 100
2360 | ALIPURDUAR | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for GOPALPUR TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | 27/ALD | 01/04/2022 | 840 | M/S DUTTA AND CO | 138.71 | 102.09 | 54.62 | 90
2361 | ALIPURDUAR | Northern Mechanical Division II | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10178 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for GOPALPUR TG Water Supply Scheme TW No.-III under NMD-II,PHE.Dte, Alipurduar. | 2638/NMD-II | 06/12/2024 | 178 | M/S P.P ELECTRICALS | 10.74 | 0 | 0 | 100
2362 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME , SM/10672 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Paschim Khairbari water supply scheme, TW no IV under Northern Mechanical Division-II, PHE Dte.Alipurduar | 2438/NMD-II | 11/08/2023 | 30 | M/S MATRI CONSTRUCTION | 10.95 | 0 | 0 | 0
2363 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME , SM/10672 | Augmentation | Construction of pump house, boundary wall and Rising main for 4th Tube well site at Paschim Khairbari PWSS of Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/10672) | 819/ALD | 14/03/2024 | 807 | TAPASH KUMAR BHOWMICK | 16.68 | 0 | 0 | 70
2364 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME , SM/10672 | Augmentation | Continuation of work of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2025 to 31.03.2025) | 4555/ALD | 30/12/2024 | 90 | SASANKA ROY | 1.2 | 0 | 0 | 0
2365 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME , SM/10672 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
2366 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME , SM/10672 | Augmentation | Laying of new HDPE/DI pipeline and replacement of Old distribution line and repairing of FHTC for Augmentation of paschim Khairbari PWSS under Alipurduar Division, PHE Dte. | 5504/ALD | 21/03/2025 | 60 | MONORAMA ENTERPRISE | 13.99 | 0 | 0 | 0
2367 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME , SM/09886 | Augmentation | Providing FHTC including Rising main for Madhya Parokata Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2385/ALD | 31/01/2022 | 60 | SOUVIK ROY PALADHI | 74.19 | 64.79 | 87.34 | 94
2368 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME , SM/09886 | Augmentation | Providing House Connection (FHTC) at Parokata WSS under Alipurduar Division, PHE Dte. | 2116/ALD | 05/01/2022 | 30 | SREE MAA CONSTRUCTION | 5.02 | 5.02 | 100 | 95
2369 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME , SM/09886 | Augmentation | Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Madhya Parokata Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2384/ALD | 31/01/2022 | 60 | SOUVIK ROY PALADHI | 96.14 | 101.62 | 70.95 | 95
2370 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME , SM/09886 | Augmentation | MADHYA PAROKATA T/W no. III, Application no. 4002930511, Ref no. 402824640, SM/09886/160 | BP-26/22-23 | 15/07/2022 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
2371 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME , SM/09886 | Augmentation | Construction of 350cum OHR for Madhya Parokata Water Supply Scheme under Alipurduar Division, PHE Dte. | 2189/ALD | 11/01/2022 | 180 | SOUVIK ROY PALADHI | 71.4 | 32 | 44.81 | 96
2372 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME , SM/09886 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Madhya Parokata Water Supply Scheme TW No.-III under NMD-II,PHE.Dte, Alipurduar. | 402/NMD-II | 22/03/2022 | 30 | TALUKDAR ENTERPRISE | 2.38 | 2.36 | 99.04 | 0
2373 | ALIPURDUAR | Alipurduar Division | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME , SM/09886 | Augmentation | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 30 | 100 | 100
2374 | ALIPURDUAR | Northern Mechanical Division II | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME , SM/09886 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Madhya Parokata water supply scheme TW No. III under NMD-II, PHE Dte. Alipurduar. | 555/NMD-II | 26/04/2022 | 30 | M/S UTPAL CHAKRABORTY & CO. | 7.85 | 7.21 | 93.37 | 100
2375 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME , SM/11765 | Augmentation | Supply, installation, commissioning and Trial operation of Electro Mechanical components of TOTOPARA Water Supply Scheme TW No.-IV under NMD-II,PHE Dte Alipurduar. | 69/NMD-II | 24/01/2022 | 30 | SUNLIT | 7.57 | 7.57 | 100 | 0
2376 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME , SM/11765 | Augmentation | Supply, delivery and installation of 15 KVA servo motor operated Copper wound line voltage corrector at TOTOPARA Water Supply Scheme TW No.-III under NMD-II, PHE.Dte, Alipurduar. | 1096/NMD-II | 20/09/2021 | 30 | SUNLIT | 2.38 | 2.38 | 100 | 0
2377 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME , SM/11765 | Augmentation | Supply, delivery & installation of 15 KVA, Servo Motor operated Copper wound line voltage stabilizer of Totopara Water Supply Scheme TW No.-IV under NMD-II, PHE. Dte, Alipurduar. | 1374/NMD-II | 22/12/2021 | 30 | SANJIB SAHA | 2.15 | 2.15 | 100 | 0
2378 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME , SM/11765 | Augmentation | Laying of overground distribution system by using HDPE pipes under Augmentation of Totopara PWSS under Alipurduar Division PHE Dte. | 04/ALD | 04/04/2023 | 60 | DULAL DAS | 39.82 | 39.61 | 100 | 100
2379 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME , SM/11765 | Augmentation | Construction of intake structure ground level reservoir, boundary wall, Pump House, laying of distribution network and providing FHTC under Augmentation of Totopara PWSS under Alipurduar Division, PHE Dte. | 2604/ALD | 04/12/2023 | 600 | DULAL DAS | 63.1 | 0 | 0 | 35
2380 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME , SM/11765 | Augmentation | Sinking of Big dia Tube Well (250 x 200 x 150 mm dia) by Modified DTH - ODEX of drilling for Aug. of Totopara PWSS within Madarihat-Birpara Block of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/11765) | 2296/ALD | 07/08/2024 | 270 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 27.04 | 0 | 0 | 100
2381 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Supply, delivery & installation of 30 KVA, Servo Motor operated Copper wound line voltage stabilizer of Lankapara Water Supply scheme T/W No.VI NMD-II,PHE.Dte,Alipurduar. | 166/NMD-II | 22/02/2022 | 30 | M/S A.D ENTERPRISE | 3.17 | 2.42 | 100 | 11
2382 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Supply,deliver and installation of open well pumping machineries and allied works at CWR of Lankapara W/S SCHEME under NMD-II, in the dist. of Alipurduar | 30/AMSD | 28/04/2023 | 20 | SARKAR ELECTRIC | 6.6 | 6.6 | 100 | 0
2383 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Yard lighting arrangement at Lankapara Water supply scheme ( Head Work site ) Under Northern Mechanical Division-II P.H.E Dte. | 1103/NMD-II | 20/09/2021 | 30 | SAIKAT SINHA | 3.16 | 3.16 | 100 | 12
2384 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Lankapara Water Supply Scheme TW No.-VI under NMD-II,PHE Dte Alipurduar. | 204/NMD-II | 24/02/2022 | 30 | SARKAR ELECTRIC | 10.46 | 6.99 | 66.77 | 10
2385 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Supply, delivery & installation of 30 KVA, Servo Motor operated Copper wound line voltage stabilizer Lankapara Water Supply Scheme TW No.-V under NMD-II,PHE.Dte,Coochbehar. | 185/ NMD-II | 23/02/2022 | 30 | M/S PALI DEB ENGINEERING | 3.16 | 3.16 | 100 | 12
2386 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Tube well Boring by ODEX-195 Method of drilling of Constructions of 1no. pump house, boundary wall, distribution line with FHTC for Lankapara 20no. Line for Augmentation of Lankapara TG for Lonkapara Hat Area PWSS Under Birpara Sub-Division, Alipurduar Division PHE DTE. | 2920/ALD | 19/01/2023 | 240 | SUDDHYA SING LAMA | 40.15 | 10.04 | 24.99 | 51
2387 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Laying of DI & HDPE pipeline, River and road crossing construction of valve chamber, community water tank and other misc. works for Lonkapara PWSS, Birpara Sub-Division, PHE Dte. | 86/ALD | 10/01/2024 | 90 | SUDDHYA SING LAMA | 27.7 | 0 | 0 | 0
2388 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Laying of DI & HDPE pipeline, construction of valve chamber and other works for Tulshipara TG at Lonkapara PWSS, Birpara Sub-Division, PHE Dte. | 82/ALD | 10/01/2024 | 135 | SUBIR GHOSH | 6.78 | 0 | 0 | 10
2389 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Construction of river bank protection wall with wire create and land filling near 3 No. PHE pump house at SK Line under Lankapara GP within Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | 2496/ALD | 13/12/2022 | 90 | RATAN DUTTA | 1.31 | 0 | 0 | 100
2390 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | New service connection charges for LANKAPARA HAT 20 NO LINE PWSS PH NO-1 | BP-194/24-25 | 09/07/2024 | 0 | WBSEDCL | 5.07 | 0 | 0 | 0
2391 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Distribution line for Lankapara Sukundi line and adjoining areas for Augmentation of Lankapara TG for Lonkapara Hat PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 3318/ALD | 13/03/2023 | 714 | SHYAMAL ROY | 18.77 | 12.6 | 67.12 | 87
2392 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Route surveying and revalidation of Household data with digitization of LDS for Lankapara (Zone-I, Zone-II & Zone-III) PWSS under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | 1181/ALD | 26/06/2025 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 6.65 | 0 | 0 | 0
2393 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Bridge Crossing and Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS under Alipurduar Division, PHE Dte. Dist-Alipurduar. | 1282/ALD | 05/01/2021 | 726 | GHOSH & SAHA CONSTRUCTION | 23.75 | 0 | 0 | 100
2394 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME , SM/11767 | Augmentation | Providing House connection at LANKAPARA TG (Part-A) PWSS under Alipuduar Division, P.H.E. Dte. | 1807/ALD | 22/02/2021 | 920 | GHOSH & SAHA CONSTRUCTION | 41.88 | 0 | 0 | 50
2395 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Providing balance FHTC from existing distribution system as per specification for HASIMARA PWSS under Alipurduar Division, PHE Dte. | 1990/ALD | 15/09/2023 | 90 | BRAJA GOPAL SAHA | 73.9 | 0 | 0 | 0
2396 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Special repairing of road for providing of FHTC at Northen side of Hasimara PWSS under Alipurduar, Division, PHE Dte. | 2178/ALD | 06/10/2023 | 30 | SHIB RATAN BHOWMIK | 0.93 | 0 | 0 | 0
2397 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Soil investigation work at proposed OHR construction site of Hasimara PWSS under Alipurduar Division PHE Dte. | 2790/ALD | 10/01/2023 | 30 | MOYTEC | 0.95 | 0.95 | 100 | 100
2398 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Material Requisition To Resource Division | 185/ALD | 28/04/2023 | 0 | Resource Division | 33.51 | 0 | 0 | 0
2399 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Construction of 700cum OHR for Augmentation of HASIMARA Water Supply Scheme under Alipurduar Division, PHE Dte.(3rd call) | 3196/ALD | 27/02/2023 | 180 | BRAJA GOPAL SAHA | 121.92 | 48.9 | 40.11 | 90
2400 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Continuation order for the work of "Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same to PHE Dte. (in soft copy) Part-B" | 3424/ALD | 26/09/2024 | 181 | TAPASH KUMAR BHOWMICK | 4.67 | 0 | 0 | 100
2401 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Material Requisition To Resource Division | 3611/ALD | 24/10/2024 | 0 | Resource Division | 9.89 | 0 | 0 | 0
2402 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Restoration of pipeline for Gap filling and other allied works under Hasimara PWSS under Alipurduar Division, PHE Dte. | 5170/ALD | 25/02/2025 | 60 | BRAJA GOPAL SAHA | 4.47 | 0 | 0 | 0
2403 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Construction of 1no. Pump House boundary wall, at new Hasimara PWSS Area under Alipurduar Division, PHE Dte. | 5171/ALD | 25/02/2025 | 120 | BRAJA GOPAL SAHA | 17.18 | 0 | 0 | 0
2404 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
2405 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Reparing of Pump House at Headwork site of HASIMARA PWSS Under Alipurduar Division PHE DTE. | 5427/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.78 | 0 | 0 | 0
2406 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kalchini Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1052/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
2407 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Construction of deep TW by ODEX-165 method of drilling for Subhashini TG under Hasimara PWSS under Alipurduar Division, PHE Dte. | 1184/ALD | 26/06/2025 | 60 | SWARAN ENTERPRISE | 8.73 | 0 | 0 | 0
2408 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Continuation for the work of Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. | 343/ALD | 29/04/2025 | 180 | TAPASH KUMAR BHOWMICK | 4.29 | 0 | 0 | 0
2409 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Reparing of Pump House at 3rd site of MADHU TG PWSS Under Alipurduar Division PHE DTE. | 1576/ALD | 31/07/2025 | 60 | NARENDRA BHADANI. | 0.78 | 0 | 0 | 0
2410 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Reparing of Pump House at Headwork site of MADHU TG PWSS Under Alipurduar Division PHE DTE. | 1577/ALD | 31/07/2025 | 60 | NARENDRA BHADANI. | 0.94 | 0 | 0 | 0
2411 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Reparing of Pump House at 2nd site of MADHU TG PWSS Under Alipurduar Division PHE DTE. | 1575/ALD | 31/07/2025 | 60 | NARENDRA BHADANI. | 0.94 | 0 | 0 | 0
2412 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Restoration of pipeline and FHTC and allied works at Madhu TG under Augmentation of Hasimara PWSS under Alipurduar Division, PHE Dte. | 2103/ALD | 23/09/2025 | 60 | NARENDRA BHADANI. | 6.46 | 0 | 0 | 0
2413 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Painting of Old OHR of 300 cum at Madhu under Augmentation of Hasimara PWSS under Alipurduar Division, PHE Dte. | 2104/ALD | 23/09/2025 | 60 | NARENDRA BHADANI. | 3.39 | 0 | 0 | 0
2414 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Continuation for the work of "Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. " | 3425/ALD | 26/09/2024 | 181 | TAPASH KUMAR BHOWMICK | 4.29 | 0 | 0 | 100
2415 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Construction of a pump house at Old Hasimara HW Site PWSS under Alipurduar Division, PHE Dte. | 694/ALD | 07/03/2024 | 380 | AMIT BARDHAN | 7.2 | 0 | 0 | 100
2416 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME , SM/12361 | Augmentation | Sinking of 1nos Big dia Tubewell (250 x 200 x 150 mm dia) by modified DTH-ODEX of drilling for Augmentation of new Hasimara PWSS site within Kalchini Block under Alipurduar Division, PHE Dte. | 4593/ALD | 03/01/2025 | 60 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 15.95 | 0 | 0 | 100
2417 | ALIPURDUAR | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | Construction of Rig Bored tubewells (1 nos.) by Reverse rotary method of drilling at HW site , construction of pump house and boundary wall at H/W, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Ethelbari Tea Garden PWSS (zone-2) Under Birpara Subdivision, Alipurduar Division PHE DTE. | 2660/ALD | 22/12/2022 | 600 | M/S DUTTA AND CO | 87.73 | 39.95 | 45.53 | 26
2418 | ALIPURDUAR | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | Material Requisition To Resource Division | 3486/ALD | 23/03/2023 | 0 | Resource Division | 11.43 | 0 | 0 | 0
2419 | ALIPURDUAR | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | Material Requisition To Resource Division | 2781/ALD | 18/12/2023 | 0 | Resource Division | 11.43 | 0 | 0 | 0
2420 | ALIPURDUAR | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | Material Requisition To Resource Division | 2719/ALD | 13/12/2023 | 0 | Resource Division | 60.01 | 0 | 0 | 0
2421 | ALIPURDUAR | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | QUOTATION FOR NEW SERVICE CONNECTION AT ETHELBARI TG TW NO-I,Z-II | BP-2023-24-62 | 13/05/2023 | 0 | WBSEDCL | 1.6 | 0 | 0 | 0
2422 | ALIPURDUAR | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | QUOTATION FOR NEW SERVICE CONNECTION AT ETHELBARI TG TW NO-I,Z-I | BP-2023-24-61 | 13/05/2023 | 0 | WBSEDCL | 1.6 | 0 | 0 | 0
2423 | ALIPURDUAR | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | QUOTATION FOR NEW SERVICE CONNECTION AT ETHELBARI TG TW NO-II,Z-I | BP-2023-24-63 | 13/05/2023 | 0 | WBSEDCL | 1.6 | 0 | 0 | 0
2424 | ALIPURDUAR | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | Gap filling by HDPE/DI pipe in Ethelbari TG under Birpara Sub-Division, Alipurduar Division, PHE Dte. | 203/ALD | 16/01/2024 | 60 | BHAGWATI BHUJEL | 14.02 | 0 | 0 | 85
2425 | ALIPURDUAR | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Ethelbari water supply scheme, TW no I and II of Zone-I under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 2082/NMD-II | 26/07/2023 | 30 | DIAMOND ELECTRICAL WORKS | 20.86 | 0 | 0 | 100
2426 | ALIPURDUAR | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | Additional Quotation Charges for Ethelbari Zone-II,PH NO-I PWSS | BP-271/24-25 | 12/08/2024 | 0 | WBSEDCL | 6.53 | 0 | 0 | 0
2427 | ALIPURDUAR | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | Cons. of Rig bored TW(2nos) by Reverse Rotary method of drilling at HW and 2nd site, cons of 200 cum OHR at HW including soil testing, cons. of P/H and B/W at HW,2nd site, Laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for ETHELBARI TG PWSS (ZONE-I)under Birpara Sub-Division, Alipurduar Division, PHE DTE. | 2861/ALD | 17/01/2023 | 180 | DILIP MAHATO | 385.44 | 241.33 | 62.61 | 90
2428 | ALIPURDUAR | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 821/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
2429 | ALIPURDUAR | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | Yard lighting arrangement at Head Work Site for Different PWSS (KADAMBINI TG and Others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | 1346/NMD-II | 19/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 23.98 | 0 | 0 | 0
2430 | ALIPURDUAR | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2431 | ALIPURDUAR | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/13449 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Ethelbari water supply scheme, TW no I of Zone-II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | 2834/NMD-II | 12/10/2023 | 30 | MITRA ENTERPRISE | 9.72 | 0 | 0 | 100
2432 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13302 | New | QUOTATION FOR NEW SERVICE CONNECTION AT DAKSHIN BARAJHAR FOREST PWSS P/H NO. I | BP-2023-24-284 | 21/08/2023 | 0 | WBSEDCL | 5.32 | 0 | 0 | 0
2433 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13302 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Dakhshin Barajhar Forest Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Apd. | 2193/NMD-II | 28/07/2023 | 30 | MAA TARA ENTERPRISE | 9.85 | 0 | 0 | 100
2434 | ALIPURDUAR | Alipurduar Division | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13302 | New | Material Requisition To Resource Division | 4255/ALD | 13/12/2024 | 0 | Resource Division | 20.1 | 0 | 0 | 0
2435 | ALIPURDUAR | Alipurduar Division | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13302 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, Laying Of Rising Main, Distribution System and providing FHTC for Dakshin Barajhar Forest PWSS Under Alipurduar Division, PHE Dte. | 2921/ALD | 19/01/2023 | 120 | BHAGWATI BHUJEL | 85.2 | 45.88 | 53.85 | 33
2436 | ALIPURDUAR | Alipurduar Division | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13302 | New | Laying of DI/HDPE distribution line, land filling at HW site, trial run and allied works at Dakshin Barajhar Forest under Aipurduar Division, PHE Dte. | 3231/ALD | 10/09/2024 | 60 | DILIP MAHATO (OPC) PRIVATE LIMITED | 19.62 | 0 | 0 | 5
2437 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13302 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2438 | ALIPURDUAR | Northern Mechanical Division II | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13302 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar -I & II Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | 1293/NMD-II | 12/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 26.61 | 0 | 0 | 0
2439 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Providing house connection from Bhatibari Water Supply Scheme (Specially for schools & FHTC) under Alipurduar Division P.H.E. Dte.Part-1 | 887/ALD | 03/09/2021 | 30 | SREE MAA CONSTRUCTION | 4.87 | 4.87 | 100 | 21
2440 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Providing house connection from Bhatibari Water Supply Scheme (Specially for ICDS & FHTC) under Alipurduar Division P.H.E. Dte.Part-2 | 888/ALD | 03/09/2021 | 30 | SREE MAA CONSTRUCTION | 4.86 | 4.86 | 100 | 20
2441 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipe at Bhatibari WSS under Alipurduar Division PHE Dte. | 2120/ALD | 05/01/2022 | 30 | SREE MAA CONSTRUCTION | 4.95 | 4.66 | 94.22 | 0
2442 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Laying distribution pipe with DI and UPVC pipe of Chilurghat, Bhatibari area under Bhatibari Zone-III WSS under Alipurduar Division, PHE Dte.(Part-I) | 2633/ALD | 21/12/2022 | 60 | DAS CONSTRUCTION | 98.5 | 86.88 | 88.2 | 88
2443 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-IV WSS under Alipurduar Division, PHE Dte. (Part-A) | 2631/ALD | 21/12/2022 | 60 | DEBAJYOTI SUTRADHAR | 75.53 | 61.22 | 81.06 | 20
2444 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Laying distribution pipe with DI and UPVC pipe of Chilurghat, Kumarijan area under Bhatibari Zone-III WSS under Alipurduar Division, PHE Dte.(Part-II) | 2634/ALD | 21/12/2022 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 83.66 | 62.39 | 74.57 | 19
2445 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Laying distribution pipe with DI and UPVC pipe of Chikliguri area under Bhatibari Zone-III WSS under Alipurduar Division, PHE Dte.(Part-III) | 2635/ALD | 21/12/2022 | 60 | TAPASH DAS | 74.46 | 43.73 | 58.74 | 21
2446 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Bhatibari PWSS under Alipurduar Division, PHE Dte. Part-8 | 2615/ALD | 21/12/2022 | 45 | GOUTAM KUMAR DAS | 34.6 | 0 | 0 | 0
2447 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Bhatibari PWSS under Alipurduar Division, PHE Dte. Part-9 | 2616/ALD | 21/12/2022 | 45 | TAPASH KUMAR BHOWMICK | 34.47 | 0 | 0 | 0
2448 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-I WSS under Alipurduar Division, PHE Dte. (Part-A) | 2627/ALD/ | 21/12/2022 | 60 | SHIBA ENTERPRISE | 100.55 | 73.39 | 72.99 | 72
2449 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Providing House Connection (FHTC) at Bhatibari WSS under Alipurduar Division, PHE Dte.Part-5 | 2620/ALD | 21/12/2022 | 30 | DEBAJYOTI SUTRADHAR | 5.02 | 5.02 | 100 | 22
2450 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Soil investigation work at 4 different places of Bhatibari within Alipurduar District under Alipurduar Division PHE Dte. | 2622/ALD | 21/12/2022 | 30 | R B TESTING | 4.86 | 0 | 0 | 0
2451 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of pathway, surface drain and chatal, land development, along with the other allied works at Bhatibari Zone-IV PWSS under Alipurduar Division PHE DTE. | 1950/ALD | 12/09/2023 | 60 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 13.54 | 0 | 0 | 0
2452 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of pathway, surface drain and chatal, land development, along with the other allied works at Bhatibari Zone-III PWSS under Alipurduar Division PHE DTE. | 1949/ALD | 12/09/2023 | 60 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 9.75 | 0 | 0 | 0
2453 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of pathway, surface drain and chatal, land development, along with the other allied works at Bhatibari Zone-I PWSS under Alipurduar Division PHE DTE. | 1947/ALD | 12/09/2023 | 60 | SAHA ENTERPRISE | 12.4 | 0 | 0 | 0
2454 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Balance work of construction of boundary wall of 2nd Site at Bhatibari WSS under Alipurduar Division PHE Dte. | 1598/ALD | 22/11/2021 | 45 | SREE MAA CONSTRUCTION | 4.79 | 4.77 | 100 | 19
2455 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Restoration of Laying distribution system by replacing of damaged AC pipeline with UPVC pipeline & constructon of boundary wall, new toilet, repairing of pump house (H/W site) at Bhatibari Water Supply Scheme under Alipurduar Division, PHE Dte. | 1311/ALD | 05/10/2021 | 60 | DEBAJYOTI SUTRADHAR | 14.02 | 12 | 100 | 21
2456 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Providing House Connection (FHTC) at Bhatibari WSS under Alipurduar Division, PHE Dte.Part-4 | 2619/ALD | 21/12/2022 | 30 | SREE MAA CONSTRUCTION | 5.02 | 4.88 | 100 | 21
2457 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | QUOTATION | BP-2023-24-475 | 12/12/2023 | 0 | WBSEDCL | 4.13 | 0 | 0 | 0
2458 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | New service connection for Bhatibari zone-II, P/HNO-I | BP-2023-24-474 | 12/12/2023 | 0 | WBSEDCL | 3.91 | 0 | 0 | 0
2459 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | QUOTATION | BP-2023-24-477 | 12/12/2023 | 0 | WBSEDCL | 8.14 | 0 | 0 | 0
2460 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | QUOTATION | BP-2023-24-478 | 12/12/2023 | 0 | WBSEDCL | 5.17 | 0 | 0 | 0
2461 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | New service connection for Bhatibari PWSS ZONE-III P/HNO-2 | BP-2023-24-473 | 12/12/2023 | 0 | WBSEDCL | 5.17 | 0 | 0 | 0
2462 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site along with repairing of office godown for Bhatibari Zone-I PWSS Under Alipurduar Division PHE DTE | 2636/ALD | 21/12/2022 | 180 | DULAL DAS | 51.35 | 17.74 | 34.55 | 85
2463 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of 1no. Boundary Wall and 2nos. Pump House for BHATIBARI ZONE-III and ZONE-IV PWSS Under Alipurduar Division PHE DTE. | 2637/ALD | 21/12/2022 | 810 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 17.67 | 0 | 0 | 100
2464 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Bhatibari PWSS under Alipurduar Division, PHE Dte. Part-7 | 2614/ALD | 21/12/2022 | 45 | HARIDAS GHOSH | 34.76 | 13.04 | 37.5 | 21
2465 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Electrification and Earthing of the Newly Renovated pump house No. I and same other allied work ar Bhatibari water supply scheme under JJM. in the Dist. of Alipurduar. | 652/AMSD | 02/03/2023 | 15 | TALUKDAR ENTERPRISE | 0.93 | 0 | 0 | 100
2466 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-I WSS under Alipurduar Division, PHE Dte. (Part-B) | 2629/ALD/ | 21/12/2022 | 60 | MATRI ENTERPRISE | 100.29 | 87.24 | 86.99 | 87
2467 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of 1no. Boundary Wall and 2nos. Tube well Boring by Reverse Rotary Method of drilling for BHATIBARI ZONE-III and ZONE-IV PWSS Under Alipurduar Division PHE DTE. | 2612/ALD | 21/12/2022 | 540 | AASHIRBAD ENTERPRISE | 24.63 | 0 | 0 | 100
2468 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of concrete platform, pathway and drain along with the repairing of existing boundary wall and drain for effectively stacking the various pipe/ specials items at Alipurduar Sadar Sub-Division Stackyard under the head of augmentation of Bhatibari PWSS under Alipurduar, Division, PHE Dte. | 03/ALD | 04/04/2023 | 90 | HARIDAS GHOSH | 6.38 | 0 | 0 | 100
2469 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | QUOTATION | BP-2023-24-476 | 12/12/2023 | 0 | WBSEDCL | 5.51 | 0 | 0 | 0
2470 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
2471 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-A) | 2628/ALD/ | 21/12/2022 | 148 | TAPASH KUMAR BHOWMICK | 100.89 | 76.17 | 75.5 | 50
2472 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-B) | 2630/ALD | 21/12/2022 | 840 | HARIDAS GHOSH | 98.45 | 80.75 | 82.02 | 18
2473 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-IV WSS under Alipurduar Division, PHE Dte. (Part-B) | 2632/ALD | 21/12/2022 | 780 | KAMALESH ROY | 74.77 | 65.08 | 87.05 | 87
2474 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Laying distribution pipe line by DI pipe (with pillar) along the flank of Alipurduar-Bhatibari PWD Road (From Charmile to Bhatibari) of Bhatibari WSS under Alipurduar Division, PHE Dte. | 2621/ALD | 21/12/2022 | 553 | DEBAJYOTI SUTRADHAR | 28.2 | 23.43 | 83.1 | 83
2475 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.05.2023 to 31.07.2023) | 181/ALD | 27/04/2023 | 91 | NIRANJAN KIRTANIA | 0.7 | 0 | 0 | 0
2476 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01/05/2023 to 31/07/2023) | 180/ALD | 27/04/2023 | 91 | NIRANJAN KIRTANIA | 0.5 | 0 | 0 | 85
2477 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.08.2023 to 31.10.2023) | 1109/ALD | 28/07/2023 | 92 | NIRANJAN KIRTANIA | 0.7 | 0 | 0 | 0
2478 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of pathway, surface drain and chatal, land development, along with the other allied works at Bhatibari Zone-II PWSS under Alipurduar Division PHE DTE. | 1948/ALD | 12/09/2023 | 60 | SWAPAN MALAKAR | 13 | 0 | 0 | 100
2479 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01/08/2023 to 31/10/2023) | 1108/ALD | 28/07/2023 | 92 | NIRANJAN KIRTANIA | 0.5 | 0 | 0 | 0
2480 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Bhatibari PWSS under Alipurduar Division, PHE Dte. Part-6 | 2613/ALD | 21/12/2022 | 211 | TAPASH KUMAR BHOWMICK | 34.47 | 24.13 | 70 | 70
2481 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | "Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II P.H.E. Dte." | 588/AMSD | 29/12/2023 | 62 | MUSTAFI CONCERN | 0.75 | 0 | 0 | 0
2482 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of 250cum OHR as per Departmental Design, laying of rising main & delivery connection . Supply of CIDF Specials and others allied works for Bhatibari Z-III PWSS Under Alipurduar Division PHE Dte. | 1766/ALD | 07/06/2024 | 573 | HARIDAS GHOSH | 103.38 | 0 | 0 | 50
2483 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of 150 cum OHR as per Departmental Design & drawing, laying of rising main & delivery connection . Supply of CIDF Specials and others allied works for Bhatibari Z-II PWSS Under Alipurduar Division PHE Dte. | 4898/ALD | 30/01/2025 | 180 | MATRI ENTERPRISE | 95.67 | 0 | 0 | 0
2484 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of 300 cum OHR as per Departmental Design, laying of rising main & delivery connection . Supply of CIDF Specials and others allied works for Bhatibari Z-IPWSS Under Alipurduar Division PHE Dte. | 1931/ALD | 28/06/2024 | 300 | TAPASH KUMAR BHOWMICK | 114.7 | 0 | 0 | 45
2485 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of 150cum OHR as per Departmental Design & drawing, laying of rising main & delivery connection, Supply of CIDF specials and others allied works for Bhatibari Zone -IV PWSS Under Alipurduar Division PHE Dte. | 895/ALD | 15/03/2024 | 690 | KAMALESH ROY | 98.47 | 0 | 0 | 50
2486 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Continuation order for "Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II P.H.E. Dte." | 102/AMSD | 21/02/2024 | 60 | MUSTAFI CONCERN | 0.75 | 0 | 0 | 0
2487 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Continuation order for Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II, PHE Dte. | 340/AMSD | 27/06/2024 | 61 | MUSTAFI CONCERN | 0.75 | 0 | 0 | 0
2488 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Laying of new UPVC/DI pipeline for filling of left out portion in the distribution system and other allied works in connection with the Augmentation of Bhatibari (Zone-III) PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/14096) | 2275/ALD | 05/08/2024 | 360 | HARI CONSTRUCTION | 37.43 | 0 | 0 | 65
2489 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Constructions of pump house, Boundary wall, laying of UPVC pipeline & Rising main connection for Purba Barachouki area under Bhatibari PWSS proposed Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/14096) | 2277/ALD | 05/08/2024 | 360 | HARI CONSTRUCTION | 32.72 | 0 | 0 | 35
2490 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II, PHE Dte. | 220/AMSD | 26/04/2024 | 61 | MUSTAFI CONCERN | 0.75 | 0 | 0 | 0
2491 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Continuation order for Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II, PHE Dte. | 476/AMSD | 29/08/2024 | 61 | MUSTAFI CONCERN | 0.75 | 0 | 0 | 0
2492 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Reparing of Pump House at 3nd site of BHATIBARI PWSS Under Alipurduar Division PHE DTE.(2nd call) | 5603/ALD | 27/03/2025 | 60 | SREE MAA CONSTRUCTION | 0.97 | 0 | 0 | 0
2493 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector forGround Water Based Piped Water Supply Scheme AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME,Zone-II,P/H No-III and IV under Jal Jeevan Mission NMD-II,PHE.Dte,Alipurduar. | 1150/NMD-II | 16/05/2025 | 30 | M/S SAJAHAN CHOWDHURY | 22.58 | 0 | 0 | 0
2494 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at Bhatibari Zone-II PWSS Under Alipurduar Division PHE DTE | 2611/ALD/ | 21/12/2022 | 630 | RATAN DUTTA | 24.73 | 0 | 0 | 60
2495 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Construction of pump house & sinking of 250 mm x 200 mm x 150mtr Big dia Tubewell at 2nd site of Bhatibari Zone-IV PWSS under Alipurduar Division, PHE Dte. | 365/ALD | 18/05/2023 | 600 | MONORAMA ENTERPRISE | 22.01 | 0 | 0 | 100
2496 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for BHATIBARI Water Supply Scheme TWNo- I,II,of Zone-I TWNo- I,II,of Zone-II TWNo- I,II,of Zone-III under NMD-II,PHE.Dte,APD.. | 2826/NMD-II | 11/10/2023 | 508 | DEY ENTERPRISE (BALLY) | 65.07 | 0 | 0 | 100
2497 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Interconnection of distribution system by laying of DI pipe resting over RCC pillars/hanging support by M.S. Structural works to cross Gadhadhar River and other allied works at Bhatibari PWSS under Alipurduar Division, PHE Dte.(SM/14096) | 3521/ALD | 04/10/2024 | 90 | DEBAJYOTI SUTRADHAR | 5.34 | 0 | 0 | 100
2498 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Constructions of balance portion of Boundary Wall ,path way, Surface drain and chatal, Land development, laying of Rising main line & delivery line connection( for direct supply of water) along with the others allied works at Bhatibari Zone-II PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/14096) | 2278/ALD | 05/08/2024 | 360 | DULAL DAS | 16.03 | 0 | 0 | 100
2499 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Sinking of 250mm x 200 mmx 150 mtr big dia Tubewell by Reverse rotary drilling method at Purba barachauki Area for Augmentation of Bhatibari PWSS under Alipurduar Division, PHE Dte. | 3775/ALD | 13/11/2024 | 150 | DAS CONSTRUCTION | 11.48 | 0 | 0 | 100
2500 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME , SM/14096 | Augmentation | Repairing of pump house at 4th site of Bhatibari PWSS under Alipurduar Division, PHE Dte. | 5043/ALD | 17/02/2025 | 120 | AN CONSTRUCTION | 1.01 | 0 | 0 | 100
2501 | ALIPURDUAR | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | Providing FHTC from existing distribution system as per specification for MADHYA KHAIRBARI PWSS under Alipurduar Division, PHE Dte. | 1992/ALD | 15/09/2023 | 360 | DINABANDHU RAY | 16.91 | 0 | 0 | 0
2502 | ALIPURDUAR | Northern Mechanical Division II | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | NEW CONNECTION SETRVICE FOR MADHYA KHAIRBARI PWSS P/H NO III APPLICATION NO 4003065168 | BP-2023-24-369 | 27/09/2023 | 0 | WBSEDCL | 5.82 | 0 | 0 | 0
2503 | ALIPURDUAR | Northern Mechanical Division II | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | NEW SERVICE CONNECTION FOR MADHYA KHAIRBARI PWSS P/H NO I APPLICATION NO 4003065159 | BP-2023-24-367 | 27/09/2023 | 0 | WBSEDCL | 15.45 | 0 | 0 | 0
2504 | ALIPURDUAR | Northern Mechanical Division II | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | NEW CONNECTION SETRVICE FOR MADHYA KHAIRBARI PWSS P/H NO II APPLICATION NO 4003065166 | BP-2023-24-368 | 27/09/2023 | 0 | WBSEDCL | 8.34 | 0 | 0 | 0
2505 | ALIPURDUAR | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | Continuation work order of the work of "Boring of TW, Cons. Of Pump House, boundary wall, OHR (300 cum) inclu. Soil investigation works, Laying of rising main, distribution system and providing FHTC for MADHYA KHAIRBARI PWSS under Alipurduar Division PHE DTE." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/10/2024-EE(ALI_D) SEC-DPHE (Computer No-974292)) | 1914/ALD | 26/06/2024 | 60 | DILIP MAHATO | 26.54 | 0 | 0 | 90
2506 | ALIPURDUAR | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | Conceptualization, design and implementing mass awareness generation through Wall writing at 20 nos. villages (Block - Kalchini) by dissemination of awareness generation IEC messages FHTC, Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation and WASH related issues as per guideline of JJM at Alipurduar district under Alipurduar Division, PHE Dte, Govt. of West Bengal. (SM/13248) | 752/ALD | 12/03/2024 | 60 | M/S SARKAR & CO | 4.76 | 0 | 0 | 100
2507 | ALIPURDUAR | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | Sinking of Big dia Tube Well (250 x 200 x 150 mm dia) by Modified DTH - ODEX of drilling at Madhya Khairbari PWSS within Madarihat-Birpara Block of RWS SUB-Division under Alipurduar Division, PHE Dte. (SM/13248) | 2297/ALD | 07/08/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 18.06 | 0 | 0 | 80
2508 | ALIPURDUAR | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | Material Requisition To Resource Division | 115/ALD | 10/01/2024 | 0 | Resource Division | 15.17 | 0 | 0 | 0
2509 | ALIPURDUAR | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
2510 | ALIPURDUAR | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | Boring of TW, Cons. Of Pump House, boundary wall, OHR (300 cum) inclu. Soil investigation works, Laying of rising main, distribution system and providing FHTC for MADHYA KHAIRBARI PWSS under Alipurduar Division PHE DTE. | 3575/ALD | 27/03/2023 | 900 | DILIP MAHATO | 553.32 | 0 | 0 | 85
2511 | ALIPURDUAR | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | CONSTRUCTION OF PUMP HOUSE and BOUNDARY WALL FOR ADDITIONAL TUBEWELL and LAYING DISTRIBUTION SYSTEM FOR PROVIDING FHTC AND LAND DEVELOPMENT AT HW SITE and 2ND SITE AT MADHYA KHAIRBARI PWSS WITHIN MADARIHAT-BIRPARA BLOCK. | 3419/ALD | 26/09/2024 | 240 | MITHUN DAS | 64.12 | 0 | 0 | 50
2512 | ALIPURDUAR | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
2513 | ALIPURDUAR | Northern Mechanical Division II | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2514 | ALIPURDUAR | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Madhya Khairbari Water Supply Scheme TW No.-IV (Additional) under NMD-II,PHE.Dte,Alipurduar. | 788/ALD | 30/05/2025 | 30 | M/S. BHOWMIK & CO | 10.78 | 0 | 0 | 0
2515 | ALIPURDUAR | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | 1048/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
2516 | ALIPURDUAR | Northern Mechanical Division II | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME , SM/13248 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Madhya Khairbari Water Supply Scheme TW No.- I,II AND III under NMDII, PHE.Dte,APD. | 2886/NMD-II | 17/10/2023 | 473 | M/S BHOWMIK & CO. | 29.84 | 0 | 0 | 100
2517 | ALIPURDUAR | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14215 | New | Material Requisition To Resource Division | 2784/ALD | 18/12/2023 | 0 | Resource Division | 6.17 | 0 | 0 | 0
2518 | ALIPURDUAR | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14215 | New | New Service connection charge for Nimti Jhora tea garden PWSS P/H No-I. | BP-2023-24-190 | 22/06/2023 | 0 | WBSEDCL | 1.36 | 0 | 0 | 0
2519 | ALIPURDUAR | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14215 | New | New Service connection charge for Nimti Jhora tea garden PWSS P/H No-II | BP-2023-24-189 | 22/06/2023 | 0 | WBSEDCL | 1.36 | 0 | 0 | 0
2520 | ALIPURDUAR | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14215 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new HDPE pipeline , Constructions of 100 Cum OHR as per Departmental Design & drawing , TWO nos. pump house & boundary wall, providing FHTC, Soil Investigation work and others allied works for NIMTIJHORA TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE | 3639/ALD | 31/03/2023 | 720 | SAMIRON PODDER | 207.36 | 60 | 32.33 | 95
2521 | ALIPURDUAR | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14215 | New | Material Requisition To Resource Division | 4252/ALD | 13/12/2024 | 0 | Resource Division | 1.61 | 0 | 0 | 0
2522 | ALIPURDUAR | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14215 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 823/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
2523 | ALIPURDUAR | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14215 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2524 | ALIPURDUAR | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14215 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Nimtijhora TG water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | 2413/NMD-II | 10/08/2023 | 358 | SUNLIT | 18.75 | 0 | 0 | 100
2525 | ALIPURDUAR | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14215 | New | Providing FHTC from existing distribution system as per specification for Nimtijhora TG PWSS under Alipurduar Division, PHE Dte. | 1882/ALD | 07/09/2023 | 537 | M/S A. B. ENTERPRISE | 7.09 | 0 | 0 | 100
2526 | ALIPURDUAR | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14215 | New | Laying of CIDI pipes & HDPE (PN-10) pipeline and other allied works for Nimtijhora Tea Garden PWSS under Alipurduar Division, PHE Dte. | 207/ALD | 16/01/2024 | 450 | SAMIRON PODDER | 44.44 | 0 | 0 | 100
2527 | ALIPURDUAR | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Material Requisition To Resource Division | 3046/ALD | 08/02/2023 | 0 | Resource Division | 25.4 | 0 | 0 | 0
2528 | ALIPURDUAR | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Material Requisition To Resource Division | 2397/ALD | 08/11/2023 | 0 | Resource Division | 6.18 | 0 | 0 | 0
2529 | ALIPURDUAR | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | NEW SEVICE CONNECTION CHARGES FOR TURTURI PWSS P/H NO.I | BP-2023-24-282 | 18/08/2023 | 0 | WBSEDCL | 1.48 | 0 | 0 | 0
2530 | ALIPURDUAR | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | NEW SEVICE CONNECTION CHARGES FOR TURTURI PWSS P/H NO.II | BP-2023-24-273 | 18/08/2023 | 0 | WBSEDCL | 1.48 | 0 | 0 | 0
2531 | ALIPURDUAR | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Tube well boring by ODEX-165 Method of drilling, Construction of Pump House, Boundary wall at proposed 3rd site of Turturi under Alipurduar Division, PHE Dte | 2420/ALD | 09/11/2023 | 431 | TAPASH KUMAR BHOWMICK | 17.4 | 0 | 0 | 70
2532 | ALIPURDUAR | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Laying of HDPE/DI Pipeline, horizontal boring by HDD method, bridge and culvert crossing, providing FHTC, specials repair with trial run of pipeline and allied works at Chuniajhora PWSS under Alipurduar Division, PHE Dte.(SM/14219 & SM/10179) | 672/ALD | 06/03/2024 | 240 | ASHOK SAPKOTA | 19.39 | 0 | 0 | 100
2533 | ALIPURDUAR | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Supply of CIDF Specials & Jeffy Coupling for Turturi (SM/14219) WSS under Alipurduar Division, PHE Dte. | 4539/ALD | 26/12/2024 | 30 | SOUVIK ROY PALADHI | 19.99 | 0 | 0 | 0
2534 | ALIPURDUAR | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Supply of CIDF & CISS Pipes and specials for Turturi Water Supply Scheme under Alipurduar Division, PHE Dte. | 1579/ALD | 24/08/2023 | 30 | TAPASH KUMAR BHOWMICK | 11.27 | 0 | 0 | 85
2535 | ALIPURDUAR | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Continuation for the work of Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. Part-B | 1107/ALD | 28/07/2023 | 120 | TAPASH KUMAR BHOWMICK | 4.67 | 0 | 0 | 100
2536 | ALIPURDUAR | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Material Requisition To Resource Division | 3949/ALD | 26/11/2024 | 0 | Resource Division | 6.18 | 0 | 0 | 0
2537 | ALIPURDUAR | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Material Requisition To Resource Division | 4276/ALD | 13/12/2024 | 0 | Resource Division | 7.63 | 0 | 0 | 0
2538 | ALIPURDUAR | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | ADDITIONAL QUOTATION FOR TURTURI PH NO-II | BP-02/24-25 | 08/04/2024 | 0 | WBSEDCL | 7.36 | 0 | 0 | 0
2539 | ALIPURDUAR | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | ADDITIONAL QUOTATION FOR INFRASTRUCTURE DEVELOPMENT FOR TURTURI P/H NO-I | BP-03/24-25 | 08/04/2024 | 0 | WBSEDCL | 4.54 | 0 | 0 | 0
2540 | ALIPURDUAR | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Cons. of Pump House & Tube well Boring by ODEX-165 Method drilling at HW Site & 2nd Site, laying distribution system with UPVC pipeline including rising main & delivery connection, Cons. of 150cum OHR as per departmental Design & drawing along with soil investigation works, providing FHTC including cons. of platform and others allied works for TURTURI PWSS Under Alipurduar Division, PHE DTE | 3574/ALD | 27/03/2023 | 720 | TAPASH KUMAR BHOWMICK | 399.05 | 208.06 | 52.14 | 90
2541 | ALIPURDUAR | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Providing balance FHTC for TURTURI PWSS under Alipurduar Division, PHE Dte. | 1571/ALD | 23/08/2023 | 496 | TAPASH KUMAR BHOWMICK | 6.81 | 0 | 0 | 0
2542 | ALIPURDUAR | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
2543 | ALIPURDUAR | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2544 | ALIPURDUAR | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Solarization of grid connected pumping installation at different PWSS at Alipurduar -II block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 819/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
2545 | ALIPURDUAR | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. , SM/14219 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Turturi water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | 2339/NMD-II | 01/08/2023 | 489 | M/S J.K ENGINEERING CO. | 18.77 | 0 | 0 | 80
2546 | ALIPURDUAR | Northern Mechanical Division II | TORSHA FOREST PIPED WATER SUPPLY SCHEME , SM/14220 | New | QUOTATION FOR NSC AT TORSHA FOREST PH NO-I | BP-2023-24-375 | 27/09/2023 | 0 | WBSEDCL | 4.07 | 0 | 0 | 0
2547 | ALIPURDUAR | Alipurduar Division | TORSHA FOREST PIPED WATER SUPPLY SCHEME , SM/14220 | New | Boring of Tubewell, Construction of pump house, boundary wall, Laying of Rising main, distribution system and providing FHTC for Torsha Forest PWSS under Alipurduar Division PHE Dte. | 2919/ALD | 19/01/2023 | 600 | KAMALESH ROY | 79.66 | 68.99 | 86.61 | 94
2548 | ALIPURDUAR | Northern Mechanical Division II | TORSHA FOREST PIPED WATER SUPPLY SCHEME , SM/14220 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Torsha Forest Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Apd. | 1060/NMD-II | 26/05/2023 | 30 | DIPA CHHETRI | 9.38 | 7.42 | 80.2 | 100
2549 | ALIPURDUAR | Alipurduar Division | TORSHA FOREST PIPED WATER SUPPLY SCHEME , SM/14220 | New | Laying of remaining Distribution Line and providing FHTC at different areas under Torsha FOREST PWSS under Alipurduar Division, PHE Dte | 1581/ALD | 24/08/2023 | 60 | KAMALESH ROY | 10.84 | 0 | 0 | 100
2550 | ALIPURDUAR | Northern Mechanical Division II | TORSHA FOREST PIPED WATER SUPPLY SCHEME , SM/14220 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar-I Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 822/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
2551 | ALIPURDUAR | Northern Mechanical Division II | TORSHA FOREST PIPED WATER SUPPLY SCHEME , SM/14220 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2552 | ALIPURDUAR | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14211 | New | Material Requisition To Resource Division | 2783/ALD | 18/12/2023 | 0 | Resource Division | 9.88 | 0 | 0 | 0
2553 | ALIPURDUAR | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14211 | New | QUOTATION FOR NSC AT BHATKHAWA TG TW NO-II | BP-2023-24-391 | 06/10/2023 | 0 | WBSEDCL | 7.97 | 0 | 0 | 0
2554 | ALIPURDUAR | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14211 | New | QUOTATION FOR NSC AT BHATKHAWA TG PH NO-I | BP-2023-24-325 | 27/09/2023 | 0 | WBSEDCL | 12.3 | 0 | 0 | 0
2555 | ALIPURDUAR | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14211 | New | QUOTATION FOR NSC AT ATIABARI PH NO-II |  | 25/09/2023 | 0 | WBSEDCL | 7.97 | 0 | 0 | 0
2556 | ALIPURDUAR | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14211 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new HDPE pipeline , Constructions of 150 Cum OHR as per Departmental Design & drawing , TWO nos pump house & boundary wall, providing FHTC, Soil Investigation work and other allied works for BHATKHAWA TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | 3193/ALD | 27/02/2023 | 673 | S.G. CONSTRUCTION | 325.36 | 109.18 | 33.56 | 60
2557 | ALIPURDUAR | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14211 | New | Providing FHTC from existing distribution system as per specification for Bhatkhawa TG PWSS under Alipurduar Division, PHE Dte. | 1883/ALD | 07/09/2023 | 240 | PRANAB GHOSH | 7.16 | 0 | 0 | 100
2558 | ALIPURDUAR | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14211 | New | Material Requisition To Resource Division | 4249/ALD | 13/12/2024 | 0 | Resource Division | 29.54 | 0 | 0 | 0
2559 | ALIPURDUAR | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14211 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
2560 | ALIPURDUAR | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14211 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bhatkhawa TG water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | 2147/NMD-II | 27/07/2023 | 30 | MUSTAFI CONCERN | 18.76 | 0 | 0 | 45
2561 | ALIPURDUAR | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14211 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | 823/NMD-II | 06/03/2025 | 30 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
2562 | ALIPURDUAR | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14211 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | 1155/NMD-II | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
2563 | ALIPURDUAR | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14211 | New | Laying of HDPE (PN-6) bring crossing work including land development and allied work at Bhatkhawa Tea Garden Piped Water Supply Scheme Alipurduar Division, PHE Dte. | 1884/ALD | 27/08/2025 | 90 | PRITAM DAS | 21.91 | 0 | 0 | 0
2564 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme , SM/07196 | Retrofitting | Providing house connection from Rahimabad Water Supply Scheme (Specially for School & FHTC) under Alipurduar Division P.H.E. Dte.Part-4 | 890/ALD | 03/09/2021 | 30 | SOUVIK ROY PALADHI | 4.3 | 3.54 | 50 | 71
2565 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme , SM/07196 | Retrofitting | LAYING DISTRIBUTION LINE FOR RETROFITTING OF FHTC AT KHASRU LINE UNDER RAHIMABAD TG PWSS UNDER ALIPURDUAR DIVISION, PHE DTE. | 580/ALD | 15/07/2021 | 30 | M/S BHOWMICK CONSTRUCTION | 12.75 | 0 | 0 | 71
2566 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme , SM/07196 | Retrofitting | Construction of pump house, Boundary Wall, Tube well Boring (ODEX-165 method), rising main of 3rd TW site of Rahimabad WSS under Alipurduar Division, PHE Dte. | 2493/ALD | 13/12/2022 | 120 | DULAL DAS | 23.52 | 6.32 | 26.85 | 27
2567 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme , SM/07196 | Retrofitting | Providing house connection from Rahimabad Water Supply Scheme (Specially for School & FHTC) under Alipurduar Division P.H.E. Dte.Part-3 | 889/ALD | 03/09/2021 | 30 | POLY CONSTRUCTION | 4.3 | 8.6 | 100 | 0
2568 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. , SM/15209 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR HANTUPARA P/H NO-IV PWSS | BP-2023-24-551 | 18/01/2024 | 0 | WBSEDCL | 5.27 | 0 | 0 | 0
2569 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. , SM/15209 | Augmentation | Renovation of Pump house and boundary wall at H/W site of Hantapara TG PWSS under Alipurduar Division, PHE Dte. | 1172/ALD | 26/06/2025 | 90 | MANI PRADHAN | 1.28 | 0 | 0 | 0
2570 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. , SM/15209 | Augmentation | Renovation of Pump house and boundary wall at 2nd site of Hantapara TG PWSS under Alipurduar Division, PHE Dte | 1173/ALD | 26/06/2025 | 90 | MANI PRADHAN | 1.07 | 0 | 0 | 0
2571 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. , SM/15209 | Augmentation | Renovation of Pump house and boundary wall at 3rd site of Hantapara TG PWSS under Alipurduar Division, PHE Dte | 1174/ALD | 26/06/2025 | 90 | MANI PRADHAN | 1.05 | 0 | 0 | 0
2572 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. , SM/15209 | Augmentation | Boring of TW, Construction of Pumphouse, Boundary wall, Laying of Distribution system for Augmentation of Hantupara PWSS under Alipurduar Division, PHE Dte. | 3317/ALD | 13/03/2023 | 585 | DULAL DAS | 23.8 | 6.2 | 26.08 | 98
2573 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. , SM/15209 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of HANTUPARA water supply scheme, TW no- I Under JJM under Northern Mechanical Division-II, PHE Dte. | 1187/NMD-II | 11/03/2024 | 266 | DEY ENTERPRISE (MALDA) | 11.26 | 0 | 0 | 100
2574 | ALIPURDUAR | Northern Mechanical Division II | Implementation of Affordable IOT System at Dimdima TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. , SM/16910 | IOT | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Different Block of Alipurduar and Coochbehar District in West Bengal | 807/NMD-II | 04/03/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 594.37 | 0 | 0 | 0
2575 | ALIPURDUAR | Northern Mechanical Division II | Implementation of Affordable IOT System at Mujnai TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. , SM/16913 | IOT | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Different Block of Alipurduar and Coochbehar District in West Bengal | 807/NMD-II | 04/03/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 594.37 | 0 | 0 | 0
2576 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of GARGENDA TG Water Supply Scheme TW No.-I,II ,III and IV of Zone-I under NMD-II,PHE.Dte,Alipurduar. | 2561/NMD-II | 18/08/2023 | 30 | SARKAR ELECTRIC | 54.5 | 0 | 0 | 5
2577 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | Construction of boundary wall, Pump house, TW, Rising main for Gargenda PWSS under Alipurduar Division, PHE Dte. | 196/ALD | 16/01/2024 | 120 | DILIP MAHATO | 27.12 | 0 | 0 | 0
2578 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | Supply of MSREW Pipe for modified DTH - ODEX of drilling at Site no. 01 of GARGENDA TE of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/16824) | 2292/ALD | 06/08/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 8.77 | 0 | 0 | 100
2579 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | Sinking of Big dia. Tubewell (200 x 150 mm dia.)by modified DTH -ODEX method of drilling at Gargenda-1 no site (SM/16824) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | 890/ALD | 15/03/2024 | 180 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 17.23 | 0 | 0 | 5
2580 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | Sinking of Big dia. Tubewell (200 x 150 mm dia.)By modified DTH -ODEX method of drilling at Dhumchipara-2nos. site (SM/09896 & SM/16824) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | 891/ALD | 15/03/2024 | 180 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 34.47 | 0 | 0 | 10
2581 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | Supply of MSREW Pipe for modified DTH - ODEX of drilling at 2 different locations under Madarihat-Birpara Block of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/16824) | 2293/ALD | 06/08/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 14.15 | 0 | 0 | 100
2582 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR GARGENDA TG JR. SCHOOL PWSS ZONE-I, TW NO-II | BP-81/24-25 | 16/05/2024 | 0 | WBSEDCL | 4.54 | 0 | 0 | 0
2583 | ALIPURDUAR | Northern Mechanical Division II | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR 15 NO LINE GARGENDA TG PWSS ZONE-I, TW NO-I | BP-82/24-25 | 16/05/2024 | 0 | WBSEDCL | 3.74 | 0 | 0 | 0
2584 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | Boring of TW, Construction of PH, B/Wall and LDS for Augmentation of Gargenda PWSS under Alipurduar Division, PHE Dte. | 3473/ALD | 22/03/2023 | 480 | SHYAMAL ROY | 36.57 | 0 | 0 | 60
2585 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | Construction of boundary wall, Pump house, TW, Rising main for Gargenda (Near Dukhiya Line) PWSS under Alipurduar Division, PHE Dte. | 197/ALD | 16/01/2024 | 600 | MANI PRADHAN | 27.78 | 0 | 0 | 70
2586 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | Renovation of Pump house and boundary wall at 2nd Pump house site of Gargenda TG PWSS under Alipurduar Division, PHE Dte | 1178/ALD | 26/06/2025 | 90 | AVNI CONSTRUCTION | 1.04 | 0 | 0 | 0
2587 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | Renovation of Pump house and boundary wall at 3rd Pump house site of Gargenda TG PWSS under Alipurduar Division, PHE Dte | 1177/ALD | 26/06/2025 | 90 | AVNI CONSTRUCTION | 1.04 | 0 | 0 | 0
2588 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. , SM/16824 | Augmentation | Renovation of Pump house and boundary wall at H/W site of Gargenda TG PWSS under Alipurduar Division, PHE Dte | 1179/ALD | 26/06/2025 | 90 | AVNI CONSTRUCTION | 1.3 | 0 | 0 | 0
2589 | ALIPURDUAR | Northern Mechanical Division II | Bhutri Forest Piped Water Supply Scheme , SM/18156 | New | NEW SERVICE CONNECTION FOR BHUTRI FOREST PWSS P/H NO I,KALCHINI APPLICATION NO 4003208197 | BP-2023-24-320 | 27/09/2023 | 0 | WBSEDCL | 4.1 | 0 | 0 | 0
2590 | ALIPURDUAR | Alipurduar Division | Bhutri Forest Piped Water Supply Scheme , SM/18156 | New | Tube well Boring by ODEX-165 Method of drilling at TUBE WELL site including laying distribution system with new HDPE pipeline ,One nos pump house & boundary wall, providing FHTC and others allied works for Bhutri Forest PWSS Under Alipurduar Division PHE DTE. | 94/ALD | 18/04/2023 | 120 | FAUDA SINGH CHHETRI | 34.7 | 0 | 0 | 100
2591 | ALIPURDUAR | Northern Mechanical Division II | Bhutri Forest Piped Water Supply Scheme , SM/18156 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for BHUTRI FOREST Water Supply Scheme TW No- I under NMDII, PHE.Dte,APD. | 2836/NMD-II | 12/10/2023 | 30 | PRAGATI CONSTRUCTION COMPANY | 10.18 | 0 | 0 | 100
2592 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Installation of 125mm X 80mm X 90 mtr. Deep Tube Well (Mark-II TW) for fresh drinking water sources(with provision of lowering of sub-merssible pump) by ODEX-115 method of Drilling Near House of Lt. Jhagru Rai, East Hirdaypur of Angrabhasa GP-I under Nagrakata Block under Jalpaiguri District. | 1827/ALD | 23/02/2021 | 15 | RAMESH SHARMA | 4.08 | 0 | 0 | 40
2593 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Retrofitting of pipeline for UTTAR LATABARAI PWSS (Rabindranagar & surroundings) area at Kalchini Block under Alipurduar Division, PHE Dte. Part-A | 1285/ALD | 05/01/2021 | 60 | ASHOK SAPKOTA | 22.45 | 3.32 | 50 | 46
2594 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Retrofitting of pipeline for UTTAR LATABARAI PWSS (Rabindranagar & surroundings) area at Kalchini Block under Alipurduar Division, PHE Dte. Part-B | 1286/ALD | 05/01/2021 | 60 | ASHOK SAPKOTA | 19.09 | 6.87 | 50 | 45
2595 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Construction of RCC boundary wall for Uttar Latabari WSS Pump House (rabindra nagar) at Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | 1834/ALD | 10/12/2021 | 45 | SHIB RATAN BHOWMIK | 4.9 | 4.48 | 100 | 75
2596 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Uttar Latabari PWSS under Alipurduar Division, PHE Dte. Part-3 | 407/ALD | 11/05/2022 | 45 | SHIB RATAN BHOWMIK | 24.21 | 8.68 | 35.86 | 46
2597 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Laying of DI and HDPE pipeline from Kalchini BDO Office towards Hamiltonganj Bazar at Uttar Latabari PWSS area under Alipurduar Division, PHE Dte. | 1685/ALD | 20/09/2022 | 60 | SUNDAR SING LAMA | 24.01 | 23.09 | 96.16 | 45
2598 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Providing balance FHTC from existing distribution system as per specification for UTTAR LATABARI PWSS under Alipurduar Division, PHE Dte. | 2104/ALD | 29/09/2023 | 90 | DIPANKAR DUTTA | 65.07 | 0 | 0 | 0
2599 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Uttar Latabari PWSS under Alipurduar Division, PHE Dte. Part-2 | 406/ALD | 11/05/2022 | 45 | ASHOK SAPKOTA | 24.2 | 20.74 | 85.71 | 42
2600 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Providing Functional Tap Connection from existing pipeline to the schools, AWC, Community centres, Govt. Office Buildings and Households at Southern Part of Uttar Latabari Area under Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | 1594/ALD | 22/11/2021 | 30 | M/S SHIB RATAN BHOWMICK & CO | 4.99 | 4.99 | 50 | 76
2601 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Providing Functional Tap Connection from existing pipeline to the schools, AWC, Community centres, Govt. Office Buildings and Households at Northern Part of Uttar Latabari Area under Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | 1595/ALD | 22/11/2021 | 30 | M/S SHIB RATAN BHOWMICK & CO | 4.99 | 4.99 | 50 | 75
2602 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Laying of HDPE pipeline for providing FHTC at Uttar Latabari PWSS area, Kalchini Block under Alipurduar Division PHE DTE. | 1330/ALD | 24/08/2022 | 60 | DIPANKAR DUTTA | 47.46 | 47.24 | 100 | 46
2603 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Reparing of Pump House at Headwork site of Uttar Latabari PWSS Under Alipurduar Division PHE DTE. | 5424/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.93 | 0 | 0 | 0
2604 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Reparing of Pump House at 2nd site of Uttar Latabari PWSS Under Alipurduar Division PHE DTE. | 5426/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.93 | 0 | 0 | 0
2605 | ALIPURDUAR | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. , SM/10637 | Augmentation | Reparing of Pump House at 4th site of Uttar Latabari PWSS Under Alipurduar Division PHE DTE | 5425/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.93 | 0 | 0 | 0
2606 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF JASHODANGA WATER SUPPLY SCHEME , SM/09899 | Augmentation | Jashodanga W/S scheme T/W no. III, near Jashodanga Hospital campus | BP-40/21-22 | 26/03/2022 | 0 | WBSEDCL | 1.22 | 0 | 0 | 0
2607 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF JASHODANGA WATER SUPPLY SCHEME , SM/09899 | Augmentation | Quotation for new service connection at Jasodanga W/SS TW No- III | BP-75/22-23 | 14/10/2022 | 0 | WBSEDCL | 1.23 | 0 | 0 | 0
2608 | ALIPURDUAR | Alipurduar Division | REJUVINATION OF JASHODANGA WATER SUPPLY SCHEME , SM/09899 | Augmentation | Construction of Pump House ,Boundary Wall, and Tube well Boring by Reverse Rotary method of drilling including Rising main for JASHODANGA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2394/ALD | 31/01/2022 | 90 | MATRI ENTERPRISE | 24.02 | 17.8 | 69.15 | 44
2609 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF JASHODANGA WATER SUPPLY SCHEME , SM/09899 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Jashodanga Water Supply Scheme TW No.-III (Near Jashodanga Rural Hospital Premises) under NMD-II,PHE.Dte,Alipurduar. | 167/NMD-II | 22/02/2022 | 30 | BEE GEE CONSTRUCTION | 2.39 | 2.39 | 100 | 43
2610 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF JASHODANGA WATER SUPPLY SCHEME , SM/09899 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Rejuvenation of Jashodanga Water Supply Scheme TW No.- IV under NMD-II,PHE.Dte,Alipurduar. | 46/NMD-II | 04/01/2023 | 30 | M/S KUNDU CONSTRUCTION | 4.31 | 3.68 | 87.18 | 100
2611 | ALIPURDUAR | Northern Mechanical Division II | REJUVINATION OF JASHODANGA WATER SUPPLY SCHEME , SM/09899 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Jashodanga Water Supply Scheme TW No.-III (Near Jashodanga Rural Hospital Premises) under NMD-II,PHE Dte Alipurduar. | 197/NMD-II | 24/02/2022 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO- OPERATIVE SOCIETY LTD. | 7.74 | 7.71 | 100 | 44
2612 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme , SM/07199 | Retrofitting | Fuel bill for the month of August 2021 | 118/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.21 | 0 | 0 | 0
2613 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme , SM/07199 | Retrofitting | Laying of HDPE / DI Pipeline at different area of MAKRAPARA PWSS under Alipurduar Division PHED. | 624/ALD | 03/09/2020 | 120 | DILIP MAHATO | 14.63 | 8.7 | 53.86 | 84
2614 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme , SM/07199 | Retrofitting | Laying of balance DI/MS/HDPE pipeline for Makrapara WSS under Alipurduar Division, PHE Dte. | 1457/ALD | 25/01/2021 | 45 | DILIP MAHATO | 13.65 | 8.83 | 100 | 85
2615 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme , SM/07199 | Retrofitting | Water supply for Makrapara Kali Mandir at Makarapara within Birpara Sub-Division under Alipurduar Division, PHE Dte. | 3216/ALD | 30/03/2022 | 45 | RATAN DUTTA | 4.4 | 0 | 0 | 0
2616 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme , SM/07199 | Retrofitting | Laying of HDPE pipeline near existing PH No-01 village for the Makrapara PWSS under Alipurduar Division, PHE Dte. | 3046/ALD | 21/03/2022 | 30 | DILIP MAHATO | 4.95 | 2.22 | 77.77 | 42
2617 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme , SM/07199 | Retrofitting | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for MAKRAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | 2389/ALD | 31/01/2022 | 90 | INDRAYOODH BHOWAL | 27.18 | 0 | 0 | 0
2618 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme , SM/07199 | Retrofitting | Construction of Balance boundary wall at CWR under Makrapara WSS under Alipurduar Division PHE Dte. | 892/ALD | 03/09/2021 | 45 | DILIP MAHATO | 4.76 | 4.9 | 50 | 0
2619 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED MANAGED LABORATORIES , SM/12752 | Support-WQMSP | Procurement of necessary Chemicals/reagents, Glasswares for regular water sample testing purpose for all Laboratories under Alipurduar Division. PHE. Dte. | 3632/ALD | 31/03/2023 | 30 | LAB SOLUTION | 0.74 | 0.74 | 100 | 100
2620 | ALIPURDUAR | Alipurduar Division | Supply , Delivery and Installation of Computer & Peripherial Device for Official use Under Office of Executive Engineer , Alipurduar Division,P.H.E , SM/12120 | Support-MIS | Supply delivery & installation of Desktop Computer for smooth running of office at Shamuktala Sub-District Laboratory under Alipurduar Diviison, PHE Dte | 2558/ALD | 16/12/2022 | 7 | CYBER NET | 0.68 | 0 | 0 | 0
2621 | ALIPURDUAR | Alipurduar Division | Supply , Delivery and Installation of Computer & Peripherial Device for Official use Under Office of Executive Engineer , Alipurduar Division,P.H.E , SM/12120 | Support-MIS | SUPPLY DELIVERY AND INSTATLLATION OF DESKTOP COMPUTER FOR SMOOTH RUNNIG OF OFFICE AT SHAMUKHTALA SUB-DISTRICT LABORATORY UNDER ALIPURDUAR DIVISION PHED | 558/22-23/PFMS | 23/03/2023 | 0 | CYBER NET | 0.68 | 0 | 0 | 0
2622 | ALIPURDUAR | Alipurduar Division | Supply , Delivery and Installation of Computer & Peripherial Device for Official use Under Office of Executive Engineer , Alipurduar Division,P.H.E , SM/12120 | Support-MIS | Purchase five nos digital photo copier machine having network printing facility, Eleven nos branded desktop, One nos Assemble Desktop, Twelve nos UPS and windows pro 64bit through GeM portal | 111/23-24/PFMS | 21/07/2023 | 0 | CYBER NET | 9.23 | 0 | 0 | 0
2623 | ALIPURDUAR | Northern Mechanical Division II | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. , SM/17189 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. | BP-2023-24-301 | 07/09/2023 | 0 | ESSJAY TECHNOMEASURE PVT LIMITED | 4.51 | 0 | 0 | 0
2624 | ALIPURDUAR | Northern Mechanical Division II | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. , SM/17189 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. | BP-2023-24-300 | 07/09/2023 | 0 | IONET | 0.9 | 0 | 0 | 0
2625 | ALIPURDUAR | Northern Mechanical Division II | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. , SM/17189 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. | BP-2023-24-298 | 07/09/2023 | 0 | IONET | 0.95 | 0 | 0 | 0
2626 | ALIPURDUAR | Northern Mechanical Division II | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. , SM/17189 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. | BP-2023-24-299 | 07/09/2023 | 0 | IONET | 3.8 | 0 | 0 | 0
2627 | ALIPURDUAR | Northern Mechanical Division II | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. , SM/17189 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. | BP-2023-24-297 | 07/09/2023 | 0 | IONET | 0.15 | 0 | 0 | 0
2628 | ALIPURDUAR | Alipurduar Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. , SM/06623 | Support-WQMSP | Supply and delivery of portable multi-parameter water quality testing device including training on operation of the device of all Gram Panchayats of Alipuduar-I & kalchini Blocks of Alipurduar District : Alipurduar Division: P.H.E. Dte. | 432/ALD | 23/06/2021 | 15 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT. LTD. | 2.29 | 2.16 | 77.33 | 0
2629 | ALIPURDUAR | Alipurduar Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. , SM/06623 | Support-WQMSP | Supply and delivery of portable multi-parameter water quality testing device including training on operation of the device of all Gram Panchayats of Falakata & Madarihat- Birpara Blocks of Alipurduar District : Alipurduar Division: P.H.E. Dte | 433/ALD | 23/06/2021 | 15 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT. LTD. | 2.28 | 2.2 | 76.33 | 0
2630 | ALIPURDUAR | Alipurduar Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. , SM/06623 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Samuktala Sub-District Water Testing Laboratory under Alipurduar Division, PHE Dte. | 787/ALD | 18/08/2021 | 15 | LAB SOLUTION | 4.83 | 4.81 | 100 | 0
2631 | ALIPURDUAR | Alipurduar Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. , SM/06623 | Support-WQMSP | Procurement of Chemicals, Consumables & Glassware for all laboratories under Alipurduar Division , PHE Dte. | 1859/ALD | 13/12/2021 | 30 | DULAL MAJUMDER | 4.76 | 4.76 | 100 | 0
2632 | ALIPURDUAR | Alipurduar Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. , SM/06623 | Support-WQMSP | Supply and delivery of portable multi-parameter water quality testing device including training on operation of the device of all Gram Panchayats of Alipuduar-II & Kumargram Blocks of Alipurduar District : Alipurduar Division: P.H.E. Dte. | 431/ALD | 23/06/2021 | 15 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT. LTD. | 2.28 | 2.28 | 74.97 | 0
2633 | ALIPURDUAR | Alipurduar Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. , SM/06623 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Birpara Sub-District Water Testing Laboratory under Alipurduar Division, PHE Dte. | 786/ALD | 18/08/2021 | 15 | LAB SOLUTION | 4.83 | 4.81 | 100 | 0
2634 | ALIPURDUAR | Alipurduar Division | INFORMATION EDUCATION COMMUNICATION (IEC) ACTIVITIES RELATED TO JUDICIOUS & SAFE USE OF DRINKING WATER,WATER CONSERVATION,WATER QUALITY ISSUES AND WASH ISSUES UNDER JALJEEVAN MISSION (JJM) SUPPORT ACTIVITIES AT ALIPURDUAR DISTRICT- July-2023 , SM/19170 | Support-IEC | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM for For Alipurduar I & II Block under Alipurduar District under Alipurduar Division, PHE Dte, , Govt. of West Bengal. (Package 1 ) | 494/ALD | 07/05/2025 | 181 | LIMRA SOCIAL WELFARE SOCIETY | 30.97 | 0 | 0 | 30
2635 | ALIPURDUAR | Alipurduar Division | INFORMATION EDUCATION COMMUNICATION (IEC) ACTIVITIES RELATED TO JUDICIOUS & SAFE USE OF DRINKING WATER,WATER CONSERVATION,WATER QUALITY ISSUES AND WASH ISSUES UNDER JALJEEVAN MISSION (JJM) SUPPORT ACTIVITIES AT ALIPURDUAR DISTRICT- July-2023 , SM/19170 | Support-IEC | "Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM For Falakata & Kalchini Block under Alipurduar District under Alipurduar Division, PHE Dte, , Govt. of West Bengal. (Package -2 )" | 495/ALD | 07/05/2025 | 181 | BARMAN ENTERPRISE | 30.97 | 0 | 0 | 40
2636 | ALIPURDUAR | Alipurduar Division | INFORMATION EDUCATION COMMUNICATION (IEC) ACTIVITIES RELATED TO JUDICIOUS & SAFE USE OF DRINKING WATER,WATER CONSERVATION,WATER QUALITY ISSUES AND WASH ISSUES UNDER JALJEEVAN MISSION (JJM) SUPPORT ACTIVITIES AT ALIPURDUAR DISTRICT- July-2023 , SM/19170 | Support-IEC | "Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM For Kumargram & Madarihat Block under Alipurduar District under Alipurduar Division, PHE Dte, , Govt. of West Bengal. ( Package -3 )" | 496/ALD | 07/05/2025 | 181 | LIMRA SOCIAL WELFARE SOCIETY | 30.47 | 0 | 0 | 26
2637 | ALIPURDUAR | Alipurduar Division | DRINKINH WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KIT (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION , SM/11752 | Support-WQMSP | Uploading Charges of FTK results under Alipurduar Division PHE Dte. | 1206/ALD | 07/08/2023 | 120 | TAPASH KUMAR BHOWMICK | 0.4 | 0.4 | 100 | 100
2638 | ALIPURDUAR | Alipurduar Division | DRINKINH WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KIT (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION , SM/11752 | Support-WQMSP | PLAN TO TEST SCHOOLS AND ANGANAWADI CENTRES WRT "SWACHH JAL SURAKSHA" CAMPAIGN | 141/23-24/PFMS | 22/08/2023 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.81 | 0 | 0 | 0
2639 | ALIPURDUAR | Alipurduar Division | DRINKINH WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KIT (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION , SM/11752 | Support-WQMSP | Sample collection from different facilator less gram panchayat for 12 months under Alipurduar Division, PHE Dte. | 2545/ALD | 28/11/2023 | 366 | JAYDAB ADHIKARI | 9.81 | 0 | 0 | 100
2640 | ALIPURDUAR | Alipurduar Division | DRINKINH WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KIT (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION , SM/11752 | Support-WQMSP | Procurement of Field Test Kits (FTK) For water quality testing using FTK/H2S vials in the district of Alipurduar related to Water Quality Monitoring & Surveillance Activities under Jal Jeevan Mission under PHE DTE. | 5598/ALD | 27/03/2025 | 60 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT. LTD. | 0.89 | 0 | 0 | 100
2641 | ALIPURDUAR | Alipurduar Division | OPERATION CHARGES-PROCUREMENT OF CHEMICALS-GLASSWARE-COMPUTER MAINTENANCE OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/19081 | Support-WQMSP | Continuation work of "Monthly remuneration of PHE managed Alipurduar District water testing laboratory personnel (5 Nos), Samuktalasub-district water testing laboratory personnel (3 Nos), Birpara Sub-district Water testing Laboratory personnel (3 Nos), for 12 months including arrear for 4 months, under Alipurduar Division, PHE Dte." (from 01/09/2024 to 30/09/2024) | 3110/ALD | 29/08/2024 | 31 | TAPAN CHANDA | 2.22 | 0 | 0 | 100
2642 | ALIPURDUAR | Alipurduar Division | OPERATION CHARGES-PROCUREMENT OF CHEMICALS-GLASSWARE-COMPUTER MAINTENANCE OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/19081 | Support-WQMSP | Continuation work of "Monthly remuneration of PHE managed Alipurduar District water testing laboratory personnel (5 Nos), Samuktalasub-district water testing laboratory personnel (3 Nos), Birpara Sub-district Water testing Laboratory personnel (3 Nos), for 12 months including arrear for 4 months, under Alipurduar Division, PHE Dte." (from 01/05/2024 to 31/08/2024) | 1315/ALD | 24/04/2024 | 122 | TAPAN CHANDA | 8.9 | 0 | 0 | 100
2643 | ALIPURDUAR | Alipurduar Division | OPERATION CHARGES-PROCUREMENT OF CHEMICALS-GLASSWARE-COMPUTER MAINTENANCE OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/19081 | Support-WQMSP | Monthly Remuneration and day to day operation and maintenance of PHED managed Alipurduar District water testing laboratory personnel (5 Nos), Samuktalasub-district water testing laboratory personnel (3 Nos), Birpara Sub-district Water testing Laboratory personnel (3 Nos) and day to day operation and maintenance of the laboratories for 06 months , under Alipurduar Division, PHE Dte. (from 01.10.2024 to 31.03.2025) | 3473/ALD | 30/09/2024 | 182 | TAPAN CHANDA | 16.68 | 0 | 0 | 100
2644 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF SAMUKTALA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 , SM/12909 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar Division(HQ), PHE Dte. | 2826/ALD | 11/01/2023 | 7 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
2645 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF SAMUKTALA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 , SM/12909 | Support-WQMSP | Calibration of necessary Instrument, Glasswares & as per ISO/IEC 17025:2017 for Birpara Sub District Lab & Samuktala Sub District Lab under Alipurduar Division. PHE. Dte. | 3631/ALD | 31/03/2023 | 30 | LAB SOLUTION | 0.93 | 0.93 | 100 | 100
2646 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF SAMUKTALA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 , SM/12909 | Support-WQMSP | Continuation for the work of Calibration of laboratory instrument/equipment related to NABL Recognition of Samuktala Sub District Laboratory and Birpara Sub District Laboratory as per ISO/IEC 17025- 2017 and procurement of Chemicals/Reagents/Water sample testing equipment/Kits for 03 No's Laboratories under Alipurduar Division, PHE. Dte. | 2376/ALD | 12/11/2025 | 60 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 8.12 | 0 | 0 | 0
2647 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF BIRPARA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 , SM/12910 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for PHE Office Conferrence Room (left side) under Alipurduar Division, PHE Dte. | 2827/ALD | 11/01/2023 | 7 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
2648 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF BIRPARA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 , SM/12910 | Support-WQMSP | Procurement of chemical and glasswares for all laboratories under Alipurduar Division, PHE Dte. | 2829/ALD | 11/01/2023 | 15 | DULAL MAJUMDER | 0.49 | 0 | 0 | 100
2649 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF BIRPARA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 , SM/12910 | Support-WQMSP | Calibration of laboratory instrument/equipment related to NABL Recognition of Samuktala Sub District Laboratory and Birpara Sub District Laboratory as per ISO/IEC 17025- 2017 and procurement of Chemicals/Reagents/Water sample testing equipment/Kits for 03 No's Laboratories under Alipurduar Division, PHE. Dte. | 3777/ALD | 13/11/2024 | 60 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 8.12 | 0 | 0 | 20
2650 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 , SM/12911 | Support-WQMSP | Providing consultancy services including calibration of measuring instruments for NABL Accreditation of Alipuduar District water testing Laboratory (Asper ISO-17025 Protocol) under Alipurduar Division: P.H.E. Dte. | 873/ALD | 02/09/2021 | 6 | INSTITUTE OF APPLIED QUALITY MANAGEMENT | 3.31 | 1.93 | 100 | 0
2651 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 , SM/12911 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for PHE Office Conferrence Room (right side) under Alipurduar Division, PHE Dte. | 2828/ALD | 11/01/2023 | 7 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
2652 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 , SM/12911 | Support-WQMSP | Procurement of necessary glasswares for water sample testing as per NABL scope and routine tests for all laboratories under Alipurduar Division, PHE Dte. | 963/ALD | 12/07/2023 | 30 | LAB SOLUTION | 1.48 | 1.48 | 100 | 100
2653 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 , SM/12911 | Support-WQMSP | Instruments procurement related to NABL accredititation/recognition works & smooth functioning of all laboratories as per ISO/IEC 17025: 2017 Under Alipurduar Division, P.H.E Dte. | 1467/ALD | 16/08/2023 | 60 | LAB SOLUTION | 8.33 | 7.27 | 87.56 | 60
2654 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 , SM/12911 | Support-WQMSP | Procurement of reagents/chemicals for water sample testing by NABL laboratories of Alipurduar Div | 113/24-25/PFMS | 29/07/2024 | 0 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 8.69 | 0 | 0 | 0
2655 | ALIPURDUAR | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 , SM/12911 | Support-WQMSP | PROCUREMENT OF NABL RELATED CONSUMABLES FOR TESTING LAB SUPPLY AND DELIVERY MATERIALS | 21/24-25/PFMS | 21/05/2024 | 0 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 6.96 | 0 | 0 | 0
2656 | ALIPURDUAR | Alipurduar Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11878 | Support-WQMSP | Monthly remuneration to the Laboratory Personnel of Birpara Water Testing Laboratory under Alipurduar Division, PHE Dte.(from 01.01.2022 to 30.06.2022) | 1950/ALD | 24/12/2021 | 182 | TAPAN CHANDA | 2.6 | 2.6 | 50 | 0
2657 | ALIPURDUAR | Alipurduar Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11878 | Support-WQMSP | Monthly remuneration to the Laboratory Personnel of Samuktala Water Testing Laboratory under Alipurduar Division, PHE Dte. (from 01.01.2022 to 30.06.2022) | 1949/ALD | 24/12/2021 | 182 | TAPAN CHANDA | 2.6 | 2.6 | 50 | 0
2658 | ALIPURDUAR | Alipurduar Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11878 | Support-WQMSP | Monthly remuneration to the PHE managed Alipurduar District Laboratory Personnel under Alipurduar Division, PHE Dte. ((from 01.01.2022 to 30.06.2022) | 1951/ALD | 24/12/2021 | 182 | TAPAN CHANDA | 3.62 | 3.62 | 50 | 0
2659 | ALIPURDUAR | Alipurduar Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11878 | Support-WQMSP | Day to day operation and maintenance of Alipurduar District Laboratory & Samuktala Sub-district laboratory and Birpara Sub-district laboratory under Alipurduar Division P.H.E. Dte.(from 01.03.2022 to 28.02.2023) | 2768/ALD | 25/02/2022 | 365 | TAPAN CHANDA | 2.78 | 2.78 | 100 | 0
2660 | ALIPURDUAR | Alipurduar Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11878 | Support-WQMSP | Monthly remuneration of Data Entry Operator in Alipurduar District Water Testing Laboratory from February to April, 2023. | 284/RWS | 21/02/2023 | 90 | PRITAM DAS | 0.51 | 0 | 0 | 60
Total | [9 empty] | 185908.04 | 26574.93 | 14.29