## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM THUKCHUK KHOLA TO 20TH MILE , SM/09594 | New | Material Requisition To Resource Division | 1370/NKWSMD | 22/09/2022 | 0 | Resource Division | 2.96 | 0 | 0 | 0
2 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM THUKCHUK KHOLA TO 20TH MILE , SM/09594 | New | P.W.S SCHEME FROM THUKCHUK KHOLA 20TH MILE AND ITS ADJOINING AREA UNDER SAKIYONG G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT-KALIMPONG | 10/NKWSMD | 04/04/2022 | 1230 | THUPDEN BHUTIA | 740.54 | 582.85 | 78.71 | 70
3 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM KAMZER KHOLA TO LOLAY DOKAN DARA , SM/09616 | New | Material Requisition To Resource Division | 646/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.27 | 0 | 0 | 0
4 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM KAMZER KHOLA TO LOLAY DOKAN DARA , SM/09616 | New | Piped Water Supply Scheme from Kamzer Khola to Lolay Dokan Dara Busty under Lolay G.P. Kalimpaong under Jal Swapno Programme within Kalimpong District | 428/NKWSMD | 07/01/2022 | 1000 | DIPESH RAI | 138.85 | 123.24 | 88.76 | 100
5 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM SISNEY JHORA TO NORTH PEDONG , SM/09665 | New | Material Requisition To Resource Division | 661/NKWSMD | 23/02/2022 | 0 | Resource Division | 1.21 | 0 | 0 | 0
6 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM SISNEY JHORA TO NORTH PEDONG , SM/09665 | New | P.W.S. Scheme from Sisney Jhora to North Pedong under Pedong G.P. Block II under Kalimpong under Jal Jeevan Mission and Jal Swapno Programme | 450/NKWSMD | 14/01/2022 | 90 | GETEN NAMGYAL BHUTIA | 138.27 | 45.78 | 33.11 | 95
7 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM NIMBONG KHOLA TO SALDARA , SM/09670 | New | Material Requisition To Resource Division | 640/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.36 | 0 | 0 | 0
8 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM NIMBONG KHOLA TO SALDARA , SM/09670 | New | P.W.S SCHEME FROM NIMBONG KHOLA TO SALDARA MAIDAN, DOVAN AND ITS ADJOINING AREA UNDER NIMBONG G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 420/NKWSMD | 07/01/2022 | 90 | SANTOSH TAMANG | 117.78 | 106.55 | 90.46 | 100
9 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. , SM/10787 | New | SURFACE WATER BASED NABGAON KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG WITHIN KALIMPONG DISTRICT UNDER BLOCK UNDER NEORAKHOLA W/S & Mtc DIVISION IN KALIMPONG DISTRICT. | 961/NKWSMD | 12/07/2022 | 300 | M/S KAMAK ENGINEERS AND CO. | 910.66 | 874.39 | 96.02 | 100
10 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. , SM/10787 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
11 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. , SM/10787 | New | ADDITIONAL WORK FOR SURFACE WATER BASED NABGAON KHASMAHAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KALIMPONG WITHIN KALIMPONG DISTRICT UNDER BLOCK UNDER NEORAKHOLA WATER SUPPLY AND MAINTENANCE DIVISION IN KALIMPONG DISTRICT. | 2195/NKWSMD | 29/11/2024 | 60 | RAMESH AGARWAL | 46.56 | 0 | 0 | 0
12 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. , SM/10787 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1579/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
13 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte , SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for gairigoan primary school dalim G.P under Gorubathan Block in the District of kalimpong under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | 593/NKWSMD | 10/02/2022 | 30 | THE ELECTRIC SPHERE | 3.9 | 3.64 | 62.83 | 0
14 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte , SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for Kumai Khas primary school in Samsing G.P under Gorubathan Block in the District of kalimpong under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | 594/NKWSMD | 10/02/2022 | 30 | THE ELECTRIC SPHERE | 4.02 | 3.8 | 63.14 | 0
15 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte , SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 26 Numbers of school under Kalimpong Block 1 (Part -3) in the district of Kalimpong under Neorakhola water Suppply Division, Kalimpong PHE Dte | 748/NKWSMD | 28/02/2022 | 90 | SONAM TOPGAY BHUTIA | 79.08 | 77.99 | 100 | 0
16 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte , SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 34 Numbers of school under Gorubathan Block 1 (Part -1) in the district of Kalimpong under Neorakhola water Suppply Division, Kalimpong PHE Dte | 752/NKWSMD | 28/02/2022 | 90 | THUPDEN BHUTIA | 130.14 | 120.3 | 93.23 | 100
17 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte , SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 26 Numbers of school under Kalimpong Block II (Part -2) in the district of Kalimpong under Neorakhola water Suppply Division, Kalimpong PHE Dte | 750/NKWSMD | 28/02/2022 | 180 | JUSTINE BHUTIA | 87.87 | 70.58 | 57.57 | 98
18 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte , SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 15 Numbers of school under Kalimpong Block II (Part -1) in the district of Kalimpong under Neorakhola water Suppply Division, Kalimpong PHE Dte | 887/NKWSMD | 28/03/2022 | 90 | MS. SURYA I PVT. LTD COMPANY | 93.6 | 73.32 | 78.34 | 100
19 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte , SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 36 Numbers of school under Kalimpong Block II (Part -3) in the district of Kalimpong under Neorakhola water Suppply Division, Kalimpong PHE Dte | 751/NKWSMD | 28/02/2022 | 990 | BINOD TAMANG | 130.7 | 101.45 | 77.62 | 70
20 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte , SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 34 Numbers of school under Mirik Sub-Division in the district of Darjeeling under Neorakhola water Suppply Division, Kalimpong PHE Dte | 888/NKWSMD | 28/03/2022 | 1080 | MS. SURYA I PVT. LTD COMPANY | 107.23 | 77.12 | 71.92 | 97
21 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte , SM/10214 | School | Additional works in connection with Creating gravity based Provision Of Drinking water from spring water source for 15 number of Schools under Gorubathan Block (Part -1) in the District of Kalimpong under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 1157/NKWSMD | 16/08/2022 | 90 | ASHIT RAI | 4.85 | 0 | 0 | 100
22 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte , SM/10214 | School | Additional works in connection with Creating gravity based Provision Of Drinking water from spring water source for 12 number of Schools under Gorubathan Block (Part -1) in the District of Kalimpong under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 1158/NKWSMD | 16/08/2022 | 90 | ASHIT RAI | 4.85 | 0 | 0 | 100
23 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for chumang forest under Gitdabling G.P Kalimpong Block-II, Dist- Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10599 | New | Creating Gravity based piped water supply scheme for Chumang Forest under Gitdabling G.P kalimpong Block -II, Dist- Kalimpong in connection with JJM & Jal Swapna under Neorakhola w/s & MtC Division , PHE Dte, Kalimpong | 569/NKWSMD | 26/05/2022 | 90 | SITA SHARMA | 64.02 | 52.65 | 45.95 | 95
24 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Dalapchand slip reserve forest Village under Dalapchand GP in Kalimpong Block II in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10601 | New | Creating gravity based Provision Of Drinking water from spring water source Dalapchand Slip reserve forest village under Dalapchand Gram Panchayat under Kalimpong Block - 1 in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte PART (A) | 577/NKWSMD | 26/05/2022 | 30 | SONAM TOPGAY BHUTIA | 4.7 | 3.91 | 46.46 | 95
25 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Dalapchand slip reserve forest Village under Dalapchand GP in Kalimpong Block II in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10601 | New | Creating gravity based Provision Of Drinking water from spring water source Dalapchand Slip reserve forest village under Dalapchand Gram Panchayat under Kalimpong Block - 1 in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte (B) | 579/NKWSMD | 26/05/2022 | 30 | SONAM TOPGAY BHUTIA | 4.79 | 4.79 | 100 | 100
26 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Paren forest Village under Paten Godak GP in Gorubathan Block in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10576 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-302 | 09/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0 | 0
27 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Paren forest Village under Paten Godak GP in Gorubathan Block in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10576 | New | Creating gravity based Provision Of Drinking water from spring water source Paren forest village under Paten Godak Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | 571/NKWSMD | 26/05/2022 | 630 | SACHIN RAI | 47.13 | 29.69 | 62.99 | 100
28 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. , SM/10729 | New | Material Requisition To Resource Division | 1552/NKWSMD | 19/10/2022 | 0 | Resource Division | 0.89 | 0 | 0 | 0
29 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. , SM/10729 | New | Material Requisition To Resource Division | 1527/NKWSMD | 18/10/2022 | 0 | Resource Division | 1.21 | 0 | 0 | 0
30 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. , SM/10729 | New | new connection | BP-2022-23-239 | 21/12/2022 | 0 | WBSEDCL | 0.26 | 0 | 0 | 0
31 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. , SM/10729 | New | new connection | BP-2022-23-238 | 21/12/2022 | 0 | WBSEDCL | 0.26 | 0 | 0 | 0
32 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. , SM/10729 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-298 | 07/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0 | 0
33 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. , SM/10729 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
34 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. , SM/10729 | New | PIPED WATER SUPPLY SCHEME FOR CHUNABHATTI BAZAR D.I.F & LISH FOREST UNDER KALIMPONG-I BLOCK, DISTRICT KALIMPONG, UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PHE DTE. | 590/NKWSMD | 26/05/2022 | 1080 | SRINIWAS AGARWAL | 112.55 | 86.71 | 77.04 | 100
35 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. , SM/10729 | New | Supplementary Piped Water Supply Scheme for Chunabatti Bazar D.I.F & Lish Forest under Kalimpong-I Block District Kalimpong under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate. | 156/NKWSMD | 30/01/2024 | 180 | SRINIWAS AGARWAL | 20.6 | 0 | 0 | 100
36 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Icha forest Village under Sangsey GP Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10624 | New | Creating gravity based Provision Of Drinking water from spring water source Icha forest village under Sangseer Gram Panchayat under Kalimpong Block - II in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | 533/NKWSMD | 25/05/2022 | 90 | SAINATH CONSTRUCTION COMPANY | 38.89 | 38.03 | 62.42 | 100
37 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/10793 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
38 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/10793 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
39 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/10793 | New | Visit of National Jal Jeevan Mission Team to hills and with an aim to arrange logistical support. | 1274/NKWSMD | 16/10/2023 | 30 | YAMA CONSTRUCTIONS LLP | 11.22 | 11.22 | 100 | 100
40 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/10793 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
41 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/10793 | New | Providing Piped Water Supply Scheme at Nimbong Khasmahal Zone (VII) Under Fourteen Village, Under Kalimpong Block-I & Kalimpong Block -II In the District of Kalimpong Under Neorakhola Water Supply & Maintenance Division Public Health Engineering Directorate under 14 Village. (PART WORK ORDER) | 762/NKWSMD | 27/05/2025 | 90 | DHANJIT TAMANG | 35.94 | 0 | 0 | 100
42 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/10793 | New | SURFACE WATER BASED NIMBONG KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE | 963/NKWSMD | 12/07/2022 | 860 | SRINIWAS AGARWAL | 677.16 | 572.53 | 72.29 | 85
43 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/10793 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | 1593/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 100 | 100
44 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10703 | New | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P. BLOCK-1 KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 589/NKWSMD | 26/05/2022 | 300 | M/S. ASHOK KUMAR PERIWAL | 277.69 | 252.26 | 90.84 | 100
45 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10703 | New | Left out scheme for Piped Water Supply Scheme form Bulbuley Jhora to Suruk Block-Kalimpong I, District Kalimpong in connection with Jal Jeevan Mission, under PHED DD-II GTA. | 489/NKWSMD | 09/04/2025 | 60 | M/S. ASHOK KUMAR PERIWAL | 7.69 | 0 | 0 | 0
46 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Mangber forest Village under Teesta GP in Kalimpong Block-I in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10739 | New | Creating gravity based Provision Of Drinking water from spring water source Mangber forest village under Teesta Gram Panchayat under Kalimpong Block - I in the District of Kalimpong Under Neorakhola water Supply Division, Kalimpong PHE Dte | 576/NKWSMD | 26/05/2022 | 30 | DORJEE SHERPA | 4.86 | 4.77 | 100 | 100
47 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE , SM/10741 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
48 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE , SM/10741 | New | FOREST PAYMENT | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
49 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE , SM/10741 | New | PIPED WATER SUPPLY SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE UNDER GORUBATHAN BLOCK KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 591/NKWSMD | 26/05/2022 | 880 | MAHADEO PRASAD AGARWAL & CO | 82.95 | 63.3 | 76.31 | 100
50 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE , SM/10741 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1579/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
51 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM UTISHEY JHORA TO LOWER YOGDA , SM/10743 | New | PIPED WATER SUPPLY SCHEME FROM UTISHEY JHORA TO LOWER YOGDA UNDER SANGSEY G.P. BLOCK-II KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 521/NKWSMD | 25/05/2022 | 900 | ANAND MANI PRADHAN | 76.69 | 69.1 | 90.1 | 90
52 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM OKHERBOTEY JHORA TO DUN , SM/10745 | New | PIPED WATER SUPPLY SCHEME FROM OKHERBOTEY TO DUN UNDER LOLAY G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 616/NKWSMD | 26/05/2022 | 645 | DIL KUMAR RAI | 88.59 | 74.93 | 84.58 | 100
53 | KALIMPONG | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. , SM/11376 | New | Material Requisition To Resource Division | 1371/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.91 | 0 | 0 | 0
54 | KALIMPONG | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. , SM/11376 | New | new connection | BP-2023-24-6 | 25/04/2023 | 0 | WBSEDCL | 0.26 | 0 | 0 | 0
55 | KALIMPONG | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. , SM/11376 | New | PIPED WATER SUPPLY SCHEME FOR RIYONG FOREST & RIYANG RAILWAY STATION WATER SUPPLY SCHEME UNDER TISTA GRAM PANCHAYAT, KALIMPONG BLOCK-I, UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG. | 927/NKWSMD | 12/07/2022 | 180 | GREEN VALLEY CONSTRUCTION | 185.43 | 106.63 | 57.5 | 85
56 | KALIMPONG | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. , SM/11376 | New | Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.02.2024 to 31.03.2024. | 168/NKWSMD | 31/01/2024 | 60 | YAMA CONSTRUCTIONS LLP | 0.79 | 0.79 | 100 | 99
57 | KALIMPONG | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. , SM/11376 | New | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.04.2024 to 31.05.2024. | 718/NKWSMD | 29/03/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.79 | 0.79 | 100 | 100
58 | KALIMPONG | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. , SM/11376 | New | Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply and Maintenance Division Public Health Engineering Directorate for the period from July 2024 to December 2024. | 1205/NKWSMD | 10/07/2024 | 180 | YAMA CONSTRUCTIONS LLP | 0.99 | 2.29 | 231.12 | 60
59 | KALIMPONG | Neorakhola W/S & Mtc.Div. | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME , SM/13602 | New | Material Requisition To Resource Division | 2601/NKWSMD | 17/02/2023 | 0 | Resource Division | 2.74 | 0 | 0 | 0
60 | KALIMPONG | Neorakhola W/S & Mtc.Div. | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME , SM/13602 | New | Material Requisition To Resource Division | 2711/NKWSMD | 03/03/2023 | 0 | Resource Division | 2.74 | 0 | 0 | 0
61 | KALIMPONG | Neorakhola W/S & Mtc.Div. | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME , SM/13602 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-302 | 09/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0 | 0
62 | KALIMPONG | Neorakhola W/S & Mtc.Div. | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME , SM/13602 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
63 | KALIMPONG | Neorakhola W/S & Mtc.Div. | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME , SM/13602 | New | PROPOSED GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MONGPONG FOREST (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. | 2147/NKWSMD | 20/01/2023 | 180 | SANTOSH TAMANG | 319.48 | 182.56 | 57.14 | 80
64 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM HARESAY JHORA TO MUNSI DHURA and KARBUTAR , SM/11354 | New | P.W.S SCHEME FROM HARESAY JHORA TO LOWER MUNSI DHURA AND KARBUTAR UNDER SANGSAY G.P. UNDER KALIMPONG BLOCK-II, DIST. KALIMPONG. | 1357/NKWSMD | 21/09/2022 | 710 | DINESH SHERPA | 135.69 | 126.58 | 93.28 | 95
65 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/13615 | New | Material Requisition To Resource Division | 2554/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.22 | 0 | 0 | 0
66 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/13615 | New | Proposed Gravity Based Piped Water Supply Scheme For Lava Forest Under Lava Gitbeong G.P, Block : Kalimpong - II, District:Kalimpong | 2350/NKWSMD | 01/02/2023 | 180 | BHUTIA AND SONS | 93.5 | 54.28 | 36.76 | 100
67 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SAMABIYONG TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/13611 | New | Material Requisition To Resource Division | 2553/NKWSMD | 17/02/2023 | 0 | Resource Division | 2.36 | 0 | 0 | 0
68 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SAMABIYONG TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/13611 | New | Material Requisition To Resource Division | 2712/NKWSMD | 03/03/2023 | 0 | Resource Division | 2.36 | 0 | 0 | 0
69 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLINGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT : Kalimpong , SM/14192 | New | Material Requisition To Resource Division | 2747/NKWSMD | 06/03/2023 | 0 | Resource Division | 4.25 | 0 | 0 | 0
70 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLINGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT : Kalimpong , SM/14192 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
71 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLINGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT : Kalimpong , SM/14192 | New | Cost of Construction of 20 nos. of boundary pillers @ Rs. 3866 (Total no of executed is 5 nos including source tanks. Therefore one tank to be needs 4 nos. of pillers in four corners. |  | 20/11/2024 | 0 | WBSFDA | 0.77 | 0 | 0 | 0
72 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLINGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT : Kalimpong , SM/14192 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
73 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLINGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT : Kalimpong , SM/14192 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLING KHASMAHAL UNDER BLOCK: KALIMPONG - I, DISTRICT:KALIMPONG | 2735/NKWSMD | 03/03/2023 | 730 | ALLIED INSTRUMENTS | 785.88 | 435.29 | 35.7 | 100
74 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YANG MAKUM KHASMAHAL (PART) UNDER YANGMAKUM G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/16232 | New | Material Requisition To Resource Division | 447/NKWSMD | 07/06/2023 | 0 | Resource Division | 1.23 | 0 | 0 | 0
75 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YANG MAKUM KHASMAHAL (PART) UNDER YANGMAKUM G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/16232 | New | WATER SUPPLY SCHEME FOR YANGMAKUM KHASMAHAL (PART-2) UNDER BLOCK KALIMPONG-I DISTRICT KALIMPONG. | 414/NKWSMD | 05/06/2023 | 720 | EVERSHINE CONSTRUCTION | 376.97 | 0 | 0 | 60
76 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KUMAI KHASMAHAL & KUMAI TEA GARDEN PWSS , SM/15937 | New | Material Requisition To Resource Division | 2748/NKWSMD | 06/03/2023 | 0 | Resource Division | 4.82 | 0 | 0 | 0
77 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KUMAI KHASMAHAL & KUMAI TEA GARDEN PWSS , SM/15937 | New | KUMAI KHASMAHAL & KUMAI TEA GARDEN (PART) PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME (TSM/015530) | 2732/NKWSMD | 03/03/2023 | 365 | RAMESH KUMAR AGARWAL & CO | 637.5 | 480.99 | 75.45 | 88
78 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM BHUPALEY KHOLA TO PAREN , SM/09607 | New | Piped Water Supply Scheme from Bhupaley Khola to Paren and and its surrounding area in Paren Godak G.P. Gorubathan Block Kalimpong, under Jal Swapno Programme within Kalimpong District | 453/NKWSMD | 14/01/2022 | 90 | RAMESH KUMAR AGARWAL & CO | 105.63 | 74.3 | 70.34 | 85
79 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM BHUPALEY KHOLA TO PAREN , SM/09607 | New | Material Requisition To Resource Division | 656/NKWSMD | 23/02/2022 | 0 | Resource Division | 1.14 | 0 | 0 | 0
80 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) UNDER PEDONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/12629 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) ,work includes construvtion of Catchment chamber.Desilting tank. RCC Tank (Main Tank and Zonal Tank) ,Laying of gravity main HDPE PIPE, distribution HDPE pipe, and construction of Switch Room , boundary wall under 5 nos of zone inside the pedong Khasmahal under pedong Gram Panchayat , under Kalimpong Block -II , under Kalimpong district. | 1448/NKWSMD | 29/09/2022 | 300 | SRINIWAS AGARWAL | 713.75 | 425.76 | 59.65 | 70
81 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) UNDER PEDONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/12629 | New | ELECTRO-MECHANICAL WORK FOR GRAVITY BASED AND PUMPING BASED P.W.S SCHEME FOR PEDONG KHASMAHAL(PART) UNDER PEDONG G.P. UNDER KALIMPONG BLOCK-II, DIST. KALIMPONG | 1779/NKWSMD | 28/11/2022 | 60 | THE ELECTRIC SPHERE | 19.28 | 0 | 0 | 0
82 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAGEY KHOLA TO KATAREY GAON , SM/09615 | New | P.W.S Scheme From Chagey Khola To Katarey Gaon And Its Adjoining Area Under Nimbong G.P. Block-I, Kalimpong Under Jal Jeevan Mission And Jal Swapno Programme. | 451/NKWSMD | 14/01/2022 | 90 | NIM TSHERING LEPCHA | 114.97 | 114.63 | 100 | 100
83 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAGEY KHOLA TO KATAREY GAON , SM/09615 | New | Engagement of 2(Two) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2022 to 31.05.2023 | 680/NKWSMD | 31/05/2022 | 12 | THE ELECTRIC SPHERE | 4.98 | 2.36 | 100 | 95
84 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAGEY KHOLA TO KATAREY GAON , SM/09615 | New | Material Requisition To Resource Division | 648/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.3 | 0 | 0 | 0
85 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWSS SCHEME FROM KHANI KHOLA TO WEST SAMALBONG , SM/09669 | New | Material Requisition To Resource Division | 643/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.31 | 0 | 0 | 0
86 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG , SM/09547 | New | Material Requisition To Resource Division | 630/NKWSMD | 21/02/2022 | 0 | Resource Division | 1.65 | 0 | 0 | 0
87 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG , SM/09547 | New | (Continuation) Hiring of Diesel run Maxi Cab (Non AC) on daily rate basis for official purpose for the Office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate from 01.05.2023 to 31.10.2023 (Assistant Engineer-I). | 111/NKWSMD | 28/04/2023 | 184 | DHURBA KUMAR PRADHAN | 1.01 | 2.18 | 100 | 100
88 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG , SM/09547 | New | (Continuation) Hiring of Diesel run Maxi Cab (Non AC) on daily rate basis for official purpose for the Office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate from 01.08.2022 to 31.01.2023 (Assistant Engineer-I). | 1094/NKWSMD | 29/07/2022 | 184 | DHURBA KUMAR PRADHAN | 1.01 | 1.79 | 100 | 100
89 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG , SM/09547 | New | (Continuation) Hiring of Diesel run Maxi Cab (Non AC) on daily rate basis for official purpose for the Office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate from 01.02.2022 to 31.07.2022 (Assistant Engineer-I). | 578/NKWSMD | 31/01/2022 | 181 | DHURBA KUMAR PRADHAN | 1 | 2.34 | 100 | 100
90 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG , SM/09547 | New | (Continuation) Hiring of Diesel run Maxi Cab (Non AC) on daily rate basis for official purpose for the Office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate from 01.02.2023 to 30.04.2023 (Assistant Engineer-I). | 2254/NKWSMD | 31/01/2023 | 89 | DHURBA KUMAR PRADHAN | 0.49 | 1.13 | 100 | 100
91 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG , SM/09547 | New | P.W.S SCHEME FROM OKHERBOTEY KHOLA TO UPPER PEDONG AND ITS ADJOINING AREA UNDER PEDONG G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 445/NKWSMD | 14/01/2022 | 1335 | GETEN NAMGYAL BHUTIA | 230.25 | 119.6 | 51.94 | 85
92 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS from Samphong Khola to Kagey Busty District Kalimpong , SM/09548 | New | P.W.S SCHEME FROM SAMPHONG KHOLA TO KAGEY BUSTY UNDER KAGEY G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | 626/NKWSMD | 21/02/2022 | 150 | GARGO TRADERS | 475.53 | 409.03 | 86.02 | 85
93 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS from Samphong Khola to Kagey Busty District Kalimpong , SM/09548 | New | Material Requisition To Resource Division | 837/NKWSMD | 21/03/2022 | 0 | Resource Division | 3.54 | 0 | 0 | 0
94 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS from Samphong Khola to Kagey Busty District Kalimpong , SM/09548 | New | SUPPLEMENARY ESTIMATE OF PWS SCHEME FOR SAMPHONG KHOLA TO KAGEY BUSTY UNDER KAGEY G.P., BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT-KALIMPONG. | 1654/NKWSMD | 04/11/2022 | 90 | ALLIED INSTRUMENTS | 196.63 | 186.41 | 94.8 | 50
95 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS from Samphong Khola to Kagey Busty District Kalimpong , SM/09548 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1579/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
96 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME BHERI POSHYER KHOLA TO KOTHI LINE , SM/09606 | New | Material Requisition To Resource Division | 645/NKWSMD | 23/02/2022 | 0 | Resource Division | 1.26 | 0 | 0 | 0
97 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME BHERI POSHYER KHOLA TO KOTHI LINE , SM/09606 | New | P.W.S. Scheme from Bheri Posher Khola to Kothi Line via 6 nos. village in Nim G.P. Gorubathan Block under Lal Jeevan Mission and Jal Swapno Programme | 427/NKWSMD | 07/01/2022 | 980 | M/S R.S. CONSTRUCTION | 192.09 | 174.94 | 91.07 | 100
98 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM BARA SUKAY KHOLA TO CHOTTA MANZING , SM/09540 | New | Material Requisition To Resource Division | 662/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.33 | 0 | 0 | 0
99 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM BARA SUKAY KHOLA TO CHOTTA MANZING , SM/09540 | New | P.W.S SCHEME FROM BARA SUKEY KHOLA TO CHOTTA MANZING IN POKHRAIBONG G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 446/NKWSMD | 14/01/2022 | 1210 | PRAKASH TAMANG | 89.04 | 71.94 | 80.8 | 100
100 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI , SM/09541 | New | ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.01.2023 TO 30.04.2023. | 2043/NKWSMD | 31/12/2022 | 120 | QRT SECURITY AND MANPOWER SERVICE | 0.85 | 0.79 | 100 | 100
101 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI , SM/09541 | New | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.05.2023 TO 31.08.2023. | 126/NKWSMD | 28/04/2023 | 122 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0.78 | 100 | 100
102 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI , SM/09541 | New | P.W.S SCHEME FROM GAIRIBAS KHOLA AND GEET KHOLA TO JHANDI AND ITS 20 ADJOINING VILLAGES COVERING 3 G.P (GORUBATHAN-II, NIM, POKHRAIBONG) IN GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO, DISTRICT-KALIMPONG. | 9/NKWSMD | 04/04/2022 | 900 | M/S. ASHOK KUMAR PERIWAL | 551.65 | 403.78 | 73.2 | 100
103 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHINDAY JHORA TO YONZON, BOMZON, LAMA GAON , SM/09542 | New | Material Requisition To Resource Division | 1377/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.54 | 0 | 0 | 0
104 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHINDAY JHORA TO YONZON, BOMZON, LAMA GAON , SM/09542 | New | P.W.S SCHEME FROM CHINDAY JHORA TO YONZON, BOMZON, LAMA GAON AND ITS ADJOINING AREAS IN POKRAIBONG G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 889/NKWSMD | 28/03/2022 | 900 | MS. SURYA I PVT. LTD COMPANY | 96.11 | 89.57 | 93.2 | 100
105 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM JHOLUNG KHOLA TO UPPER, LOWER AND MIDDLE DHAP , SM/09667 | New | P.W.S SCHEME FROM JHOLUNG KHOLA TO UPPER,MIDDLE AND LOWER DHAP IN RANGO G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | 623/NKWSMD | 21/02/2022 | 150 | RAMESH KUMAR AGARWAL & CO | 462.38 | 460.69 | 71.12 | 100
106 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM JHOLUNG KHOLA TO UPPER, LOWER AND MIDDLE DHAP , SM/09667 | New | Material Requisition To Resource Division | 834/NKWSMD | 21/03/2022 | 0 | Resource Division | 1.93 | 0 | 0 | 0
107 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. , SM/10267 | Retrofitting | Pro vidin g Functional household Tap connection under JJM & JSP Programme for Dws scheme from Chamlakha Bhotia to Sangseer Mangal Dhura(Na rak) Sangsey GP | BP-2022-23-47 | 18/05/2022 | 0 | DINESH SHERPA | 13.62 | 0 | 0 | 0
108 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. , SM/10267 | Retrofitting | Pr oviding Functional household Tap connection under JJM & JSP Programme for Dws scheme from Dhaula Khola to Lava lava GP | BP-2022-23-38 | 06/05/2022 | 0 | NIMA TCHERING BHUTIA | 33.95 | 0 | 0 | 0
109 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. , SM/10267 | Retrofitting | Pro vidin g Functional household tap connection under JJM & JSP Prog ramm e for Dw s. scheme from Dabaipani Jh ora to Ran gpoo FV Sangsay GP | BP-2022-23-4 | 11/04/2022 | 0 | SANTOSH TAMANG | 13.5 | 0 | 0 | 0
110 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. , SM/10267 | Retrofitting | Pro viding Functiona l household Tap connec tio n under JJM & JSP Pro gramme for Dw sche me from Tarchu Khola to Tarkhola FV 10mile Sangsey GP | BP-2022-23-43 | 06/05/2022 | 0 | ANAND MANI PRADHAN | 12.85 | 0 | 0 | 0
111 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. , SM/10267 | Retrofitting | Pr vidin g Functional household Tap connect ion und er JJ_M & J$P Programme for Pws scheme fro m Odam Khola to Sa nyasi Dara Nav gaon Pa bringtar GP | BP-2022-23-12 | 11/04/2022 | 0 | CHEMJONG ENTERPRISE | 17.69 | 0 | 0 | 0
112 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. , SM/10267 | Retrofitting | Providing Functional household Tap connection under JJM & jSP Programme for Dws sche me from Narag Jhora to Munshi Dhura Gao n Sangsay Gp | BP-2022-23-48 | 18/05/2022 | 0 | DINESH SHERPA | 10.62 | 0 | 0 | 0
113 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. , SM/10267 | Retrofitting | "Providing house connecti on for Dws scheme from salsalay Jhora to Bhutia Bust y and Lower Meerong(Bull Farm) Pedong gp" | BP-2022-23-103 | 04/08/2022 | 0 | GETEN NAMGYAL BHUTIA | 5.98 | 0 | 0 | 0
114 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. , SM/10267 | Retrofitting | Addition Estimate for the FHTC under JJM Programme 8 nos existing schemes to be provided with FHTC under Kalimpong Block-II in the district of Kalimpong, FHTC under JJM Programme 14 nos existing schemes to be provided with FHTC, FHTC under JJM Programme 10 nos existing schemes to be provided with FHTC under Block-III, Gorubathan. | 1875/NKWSMD | 14/12/2022 | 60 | YAMA CONSTRUCTIONS LLP | 62.3 | 1.74 | 100 | 100
115 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. , SM/10267 | Retrofitting | Material Requisition To Resource Division | 2597/NKWSMD | 17/02/2023 | 0 | Resource Division | 6.87 | 0 | 0 | 0
116 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED KANKE BONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/10791 | New | SURFACE WATER BASED KANKE BONG KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE. | 816/NKWSMD | 30/06/2022 | 300 | GARGO TRADERS | 448.31 | 351.96 | 78.51 | 70
117 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Rissium forest Village under Santook GP in Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10602 | New | Creating gravity based Provision Of Drinking water from spring water source Rissium forest village under Santook Gram Panchayat under Kalimpong Block-II in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | 570/NKWSMD | 26/05/2022 | 90 | DAWA TANGEE SHERPA | 21.57 | 10.13 | 46.96 | 80
118 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM KHANI KHOLA TO CHUKIM , SM/10753 | New | PIPED WATER SUPPLY SCHEME FROM KHANI KHOLA TO CHUKIM UNDER KALIMPONG BLOCK-I, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 529/NKWSMD | 25/05/2022 | 704 | PASANG LAMA | 134.25 | 117.83 | 87.76 | 100
119 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM REON KHOLA TO LOWER PEMBLING , SM/09609 | New | Material Requisition To Resource Division | 657/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.41 | 0 | 0 | 0
120 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM REON KHOLA TO LOWER PEMBLING , SM/09609 | New | Piped Water Supply Scheme from Reon Khola to Lower Pembling under Nimbong G.P. Block l, Kalimpong under Jal Swapno Programme within Kalimpong District | 431/NKWSMD | 07/01/2022 | 1250 | SANTOSH TAMANG | 95.07 | 80.38 | 84.55 | 100
121 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM BHADRA JHORA TO CHOTTA SURUK , SM/10747 | New | Piped Water Supply Scheme from Bhadra Jhora to Chotta Suruk. | 834/NKWSMD | 30/06/2022 | 340 | ANAND KUMAR LAKHOTIA | 70.29 | 62.34 | 88.68 | 100
122 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PURBA KABI GAON GRAVITY BASED PIPE WATER SUPPLY SCHEME , SM/11312 | New | Piped Water Supply Scheme for Purba Kabi Gaon under Samthar G.P Kalimpong Block -I, Kalimpong Block-I, under Neorakhola W/S & Mtc Division, PHE Dte. | 815/NKWSMD | 30/06/2022 | 508 | DIPENDRA CHETTRI | 96.46 | 66.22 | 68.64 | 95
123 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of Drinking water from spring water source for 13 Numbers Health care Facilities in Kalimpong Block- I under the District of kalimpong , under Neorakhola water supply Division, kalimpong PHE Dte. , SM/11368 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for 13 Numbers of Health Care facilities in Kalimpong Block -I under the District of Kalimpong, under Neorakhola Water Supply & Maintenence Division, P.H.E Directorate, Kalimpong. | 935/ NKWSMD | 12/07/2022 | 90 | DIPESH RAI | 49.48 | 14 | 28.29 | 50
124 | KALIMPONG | Neorakhola W/S & Mtc.Div. | LOLAY KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG , SM/13603 | New | Material Requisition To Resource Division | 2596/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.09 | 0 | 0 | 0
125 | KALIMPONG | Neorakhola W/S & Mtc.Div. | LOLAY KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG , SM/13603 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
126 | KALIMPONG | Neorakhola W/S & Mtc.Div. | LOLAY KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG , SM/13603 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-321 | 25/12/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0 | 0
127 | KALIMPONG | Neorakhola W/S & Mtc.Div. | LOLAY KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG , SM/13603 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | 2352/NKWSMD | 01/02/2023 | 1025 | DIL KUMAR RAI | 326.83 | 199.16 | 60.94 | 80
128 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GODAK BUSTY PIPED WATER SUPPLY SCHEME. , SM/13608 | New | Creating Gravity Based Water Supply Scheme for Godak Busty, under Gorubathan Block, District:- Kalimpong, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 825/NKWSMD | 24/07/2023 | 600 | SANJAY BHUJEL | 350.72 | 165.11 | 47.08 | 85
129 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GIT DUBLING KHASMAHAL (PART) (POCHAK HABITATION) UNDER GITDABLING G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/13617 | New | Material Requisition To Resource Division | 2564/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.48 | 0 | 0 | 0
130 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GIT DUBLING KHASMAHAL (PART) (POCHAK HABITATION) UNDER GITDABLING G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/13617 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
131 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 27 numbers school, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11357 | School | Creating gravity based Provision Of Drinking water from spring water source for 27 Numbers of school in Gorubathan Block under the District of Kalimpong, under Neorakhola Water Supply and Maintenance Division, P.H.E Directorate, Kalimpong. | 929/NKWSMD | 12/07/2022 | 180 | SRINIWAS AGARWAL | 136.95 | 136.89 | 100 | 0
132 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 49 Numbers of school in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/11359 | School | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/04/2024 TO 30/06/2024 (3 MONTHS). | 706/NKWSMD | 27/03/2024 | 92 | NIM TSHERING LEPCHA | 6.36 | 0 | 0 | 0
133 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 49 Numbers of school in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/11359 | School | Creating gravity based Provision Of Drinking water from spring water source for 49 Numbers of School in Kalimpong Block-II in the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. | 931/NKWSMD | 12/07/2022 | 960 | JUSTINE BHUTIA | 253.45 | 218.29 | 86.4 | 100
134 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 48 Nos of Aganwadi under Gorubathan Block, in the District of Kalimpong under Neorakhola water supply Division, kalimpong PHE Directorate. , SM/11363 | Anganwadi | Creating gravity based Provision Of Drinking water from spring water source for 48 Numbers of Aganwadi in Gorubathan Block under the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. | 934/NKWSMD | 12/07/2022 | 180 | BHUTIA AND SONS | 232.03 | 215.85 | 93.03 | 95
135 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM HIGHEST POINT JHORA TO UGEN MINDRU SAMTENLING GUMBA , SM/09597 | New | Material Requisition To Resource Division | 653/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.41 | 0 | 0 | 0
136 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM HIGHEST POINT JHORA TO UGEN MINDRU SAMTENLING GUMBA , SM/09597 | New | P.W.S SCHEME FROM HIGHEST POINT JHORA TO UGEN MINDRU SAMTENLING GUMBA AND ITS ADJOINING AREA UNDER GITKOLBONG G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 454/NKWSMD | 14/01/2022 | 90 | SANTOSH TAMANG | 192.88 | 171.97 | 89.16 | 100
137 | KALIMPONG | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS , SM/14171 | New | Material Requisition To Resource Division | 2562/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.9 | 0 | 0 | 0
138 | KALIMPONG | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS , SM/14171 | New | Material Requisition To Resource Division | 207/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.08 | 0 | 0 | 0
139 | KALIMPONG | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS , SM/14171 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
140 | KALIMPONG | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS , SM/14171 | New | PROPOSED Creating gravity based piped water supply scheme for Zone 4 under Today Tangta Khasmahal under Gorubathan Block under Kalimpong District under PHE Dte | 2361/NKWSMD | 01/02/2023 | 970 | MAHADEO PRASAD AGARWAL & CO | 298.82 | 212.25 | 71.03 | 70
141 | KALIMPONG | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS , SM/14171 | New | PROPOSED Creating gravity based piped water supply scheme for Zone 1 under Today Tangta Khasmahal under Gorubathan Block under Kalimpong District under PHE Dte | 2353/NKWSMD | 01/02/2023 | 970 | TASHI BHUTIA | 364.86 | 250.83 | 68.75 | 65
142 | KALIMPONG | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS , SM/14171 | New | PROPOSED Creating gravity based piped water supply scheme for Zone 2 under Today Tangta Khasmahal under Gorubathan Block under Kalimpong District under PHE Dte. | 2354/NKWSMD | 01/02/2023 | 1085 | TASHI BHUTIA | 438.07 | 0 | 0 | 60
143 | KALIMPONG | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS , SM/14171 | New | Proposed Creating gravity based piped water supply scheme for Zone 3 under Today Tangta Khasmahal under Gorubathan Block under Kalimpong District under PHE Dte. | 102/NKWSMD | 28/04/2023 | 905 | MAHADEO PRASAD AGARWAL & CO | 493.17 | 215.01 | 43.6 | 60
144 | KALIMPONG | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS , SM/14171 | New | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.11.2024 TO 31.12.2024. | 2025/NKWSMD | 25/10/2024 | 75 | QRT SECURITY AND MANPOWER SERVICE | 0.39 | 0 | 0 | 100
145 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED & PUMPING BASED WATER SUPPLY SCHEME FOR BHALUKHOP KHAS MAHAL PWSS, BLOCK : KALIMPONG - I, District : Kalimpong , SM/14194 | New | Material Requisition To Resource Division | 758/NKWSMD | 19/07/2023 | 0 | Resource Division | 7.79 | 0 | 0 | 0
146 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED & PUMPING BASED WATER SUPPLY SCHEME FOR BHALUKHOP KHAS MAHAL PWSS, BLOCK : KALIMPONG - I, District : Kalimpong , SM/14194 | New | PROPOSED GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR BHALUKHOP KHASMAHAL PIPED WATER SUPPLY SCHEME, BLOCK-KALIMPONG-I, DISTRICT-KALIMPONG. | 672/NKWSMD | 12/07/2023 | 575 | SRINIWAS AGARWAL | 678.82 | 385.98 | 56.86 | 70
147 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED & PUMPING BASED WATER SUPPLY SCHEME FOR BHALUKHOP KHAS MAHAL PWSS, BLOCK : KALIMPONG - I, District : Kalimpong , SM/14194 | New | Leftout Scheme Proposed Gravity Based Piped Water Supply Scheme for Bhalukhop Khasmahal under Kalimpong Block-I District-Kalimpong. | 2231/NKWSMD | 09/12/2024 | 90 | SRINIWAS AGARWAL | 53.33 | 0 | 0 | 0
148 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PAGRAN BONG KHASMAHAL PWSS , SM/16854 | New | Material Requisition To Resource Division | 775/NKWSMD | 19/07/2023 | 0 | Resource Division | 1.15 | 0 | 0 | 0
149 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PAGRAN BONG KHASMAHAL PWSS , SM/16854 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
150 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PAGRAN BONG KHASMAHAL PWSS , SM/16854 | New | FOREST PAYMENT | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
151 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PAGRAN BONG KHASMAHAL PWSS , SM/16854 | New | WATER SUPPLY SCHEME FOR PAGRANG BONG KHASMAHAL PIPED WATER SUPPLY SCHEME GORUBATHAN BLOCK UNDER KALIMPONG DISTRICT. | 684/NKWSMD | 12/07/2023 | 480 | MS. SURYA I PVT. LTD COMPANY | 388.09 | 316.1 | 81.45 | 80
152 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG , SM/15645 | New | Material Requisition To Resource Division | 250/NKWSMD | 12/05/2023 | 0 | Resource Division | 2.99 | 0 | 0 | 0
153 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG , SM/15645 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT : KALIMPONG. | 220/NKWSMD | 10/05/2023 | 545 | SRINIWAS AGARWAL | 940.34 | 703.56 | 74.82 | 85
154 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/16649 | New | Material Requisition To Resource Division | 277/NKWSMD | 17/05/2023 | 0 | Resource Division | 1.95 | 0 | 0 | 0
155 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/16649 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
156 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/16649 | New | FOREST PAYMENT | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
157 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/16649 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG-II, DISTRICT:KALIMPONG. | 105/NKWSMD | 28/04/2023 | 240 | M/S. ASHOK KUMAR PERIWAL | 378.99 | 0 | 0 | 50
158 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/16649 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | 1593/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 100 | 100
159 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/13616 | New | Material Requisition To Resource Division | 2549/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.76 | 0 | 0 | 0
160 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/13616 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-421 | 16/01/2024 | 0 | WBSEDCL | 1.83 | 0 | 0 | 0
161 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/13616 | New | Proposed Pumping Based Piped Water Supply Scheme For Maria Khasmahal (Part) (Upper Rabek) Under Kagay G.P, Block : Kalimpong - II, District:Kalimpong | 2149/NKWSMD | 20/01/2023 | 1080 | THUPDEN BHUTIA | 251.88 | 101.27 | 40.21 | 100
162 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG , SM/18322 | New | Material Requisition To Resource Division | 771/NKWSMD | 19/07/2023 | 0 | Resource Division | 6.36 | 0 | 0 | 0
163 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG , SM/18322 | New | Continuation Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.04.2024 to 31.05.2024. | 717/NKWSMD | 29/03/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.39 | 0.39 | 100 | 100
164 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG , SM/18322 | New | Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.02.2024 to 31.03.2024. | 167/NKWSMD | 31/01/2024 | 60 | YAMA CONSTRUCTIONS LLP | 0.39 | 0.39 | 100 | 99
165 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG , SM/18322 | New | WATER SUPPLY SCHEME FOR ICCHA KHASAMAHAL PIPED WATER SUPPLY SCHEME IN KALIMPONG-I BLOCK, UNDER KALIMPONG DISTRICT. | 722/NKWSMD | 18/07/2023 | 1095 | M/S. ASHOK KUMAR PERIWAL | 920.85 | 0 | 0 | 40
166 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR YANGMAKHUM KHAS MAHAL (Part) PWSS,BLOCK : KALIMPONG - I, DISTRICT : Kalimpong , SM/14193 | New | Material Requisition To Resource Division | 777/NKWSMD | 19/07/2023 | 0 | Resource Division | 4.46 | 0 | 0 | 0
167 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR YANGMAKHUM KHAS MAHAL (Part) PWSS,BLOCK : KALIMPONG - I, DISTRICT : Kalimpong , SM/14193 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR YANG MAKHUM KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. | 359/NKWSMD | 26/05/2023 | 725 | M/S. ASHOK KUMAR PERIWAL | 644.99 | 0 | 0 | 61
168 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Material Requisition To Resource Division | 1286/NKWSMD | 17/10/2023 | 0 | Resource Division | 1.14 | 0 | 0 | 0
169 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Material Requisition To Resource Division | 1287/NKWSMD | 17/10/2023 | 0 | Resource Division | 1.9 | 0 | 0 | 0
170 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Material Requisition To Resource Division | 1284/NKWSMD | 17/10/2023 | 0 | Resource Division | 0.43 | 0 | 0 | 0
171 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing piped water Supply Scheme for Household in Nimbong Khasmahal (Part) under Nimbong G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 1091/NKWSMD | 21/09/2023 | 230 | SANTOSH TAMANG | 166.29 | 0 | 0 | 80
172 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing piped water Supply Scheme for Household in Lower Tunglabong, Lower Suntalay in Pokhrabong khasmahal, (Part), Pokhrabong G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 819/NKWSMD | 24/07/2023 | 120 | PRAKASH TAMANG | 173 | 115.65 | 66.85 | 85
173 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing piped water SupplyScheme for Household in Jhandi Rai Goan, Chhetri Goan, Budrathoki Goan, Upper Suntalay, lower Suntalay, & Tunglabong in Pokhrabong khasmahal (Part), Pokhrabong G.P under Kalimpong Block-II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 823/NKWSMD | 24/07/2023 | 480 | MS. SURYA I PVT. LTD COMPANY | 282.37 | 164.16 | 58.14 | 65
174 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing piped water Supply Scheme for Household in Nechaligaon, Dangmmu Gaon & Sona Gaon, Paypang khasmahal, l (Part), Gitdabling G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 818/NKWSMD | 24/07/2023 | 240 | SITA SHARMA | 142.71 | 15.05 | 10.55 | 70
175 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing piped water Supply Scheme for Household in Malthung Gaon, in Samthar G.P under Kalimpong Block -I in the district of Kalimpong in connection with JJM , under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 1308/NKWSMD | 31/10/2023 | 60 | BINOD CHANDRA BHUJEL | 23.81 | 16.85 | 70.79 | 95
176 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing Piped Water Supply Scheme for 16th mile, Pagang Gumba area for left out households under Paiyong G.P under Kalimpong Block-II in the district of Kalimpong in connection with JJM, Under Neorakhola W/S & Mtc Division, PHE Dte, Kalimpong. | 972/NKWSMD | 18/06/2024 | 180 | EVERSHINE CONSTRUCTION | 231.87 | 0 | 0 | 0
177 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0.43 | 100 | 80
178 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing Piped Water Supply Scheme for Household in Sillery Gaon, in Paiengaon Forest village (Part), Santook G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 824/NKWSMD | 24/07/2023 | 720 | JUSTINE BHUTIA | 152.07 | 0 | 0 | 45
179 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing piped water Supply Scheme for Household in Gairi Gaon, Barmiak Thingdara, Rubasta & 10th mile Mangchu forest village, Sangsey Khashamal (Part), Sangsey G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 817/NKWSMD | 24/07/2023 | 720 | M/S. ASHOK KUMAR PERIWAL | 360.01 | 0 | 0 | 56
180 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing piped water Supply Scheme for Household in Middle & Lower Dabling, Gitdabling Khasmahal l (Part), Gitdabling G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 821/NKWSMD | 24/07/2023 | 780 | NIM TSHERING LEPCHA | 108.29 | 60.29 | 55.68 | 100
181 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing piped water Supply Scheme for Household in, SantookKhasmahal (Part) in Santook G.P, under Kalimpong Block-II in the District of Kalimpong in connection with Jal Jeevan Mission , under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 822/NKWSMD | 24/07/2023 | 720 | JUSTINE BHUTIA | 240.27 | 0 | 0 | 70
182 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing Piped Water Supply Scheme for Household in Bomfoktar Gaon, Bhujel Goan, Sunwar Goan and sorrounding areas in Samthar G.P under Kalimpong Block -I in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 1307/NKWSMD | 31/10/2023 | 473 | D AND B GRACE | 39.16 | 0 | 0 | 70
183 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing piped water Supply Scheme for Household in Manay Gumba, Cashier Gaon, MLA Gaon & Karbari Gaon, Sindibong Khasmahal (Part), Sindibong G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 119/NKWSMD | 16/01/2024 | 715 | SANTOSH TAMANG | 611.7 | 0 | 0 | 60
184 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing Piped Water Supply Scheme for Household in 29th mile & Galekhola under Teesta G.P under Kalimpong block-I in the district of Kalimpong connection with JJM, under Neorakhola W/S Mtc Division, P.H.E. Dte, Kalimpong. | 973/NKWSMD | 18/06/2024 | 330 | KAMAKHYA CONSTRUCTION | 172.8 | 0 | 0 | 70
185 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing Piped Water Supply Scheme for Household in Samalbongay, Suntallay, Lepcha Gaon under Samthar G.P under Kalimpong Block-I in the district of Kalimpong in connection with JJM, Under Neorakhola W/S & Mtc Division, PHE Dte, Kalimpong. | 974/NKWSMD | 18/06/2024 | 360 | YADI LEPCHA | 117.35 | 18.08 | 15.41 | 80
186 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Additional work for PWS Scheme from Dhobi Khola to Kashyone G.P., Block-II Kalimpong in connection with JJM, under Neorakhola W/S & Mtc Division, PHE, Dte. | 982/NKWSMD | 18/06/2024 | 180 | SAINATH CONSTRUCTION COMPANY | 19.83 | 0 | 0 | 100
187 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Additional work for proposed Gravity based Piped Water Supply Scheme for Char Dhungey & Kela Busty under Pankasari Gram Panchayat under Gorubathan-II, block: Gorubathan, District: Kalimpong. | 1583/NKWSMD | 05/09/2024 | 240 | MS JAGANNATH PRASAD | 71.24 | 0 | 0 | 50
188 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Providing Piped Water Supply Scheme for Fourteen 14 Nos of Villages (Part) Under Kalimpong Block-I & Kalimpong Block-II in The District of Kalimpong under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Sillary Gaon Leftout. | 598/NKWSMD | 29/04/2025 | 120 | SUNIL BAJLA | 69.71 | 0 | 0 | 0
189 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. , SM/18443 | New | Additional Work for Proposed Surface Water Based Yakprintam Khasmahal (Part) Piped Water Supply Scheme to accommodate Functional Household Tap Connection (FHTC) in Kalimpong-I, Block within Kalimpong District under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate. | 1325/NKWSMD | 29/07/2024 | 180 | RELLI PALA CONSTRUCTION | 20.76 | 0 | 0 | 100
190 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. , SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE III (MALI BASSEY, KHAMDONG ) (TSM/013034) | 258/NKWSMD | 20/02/2024 | 360 | SANTOSH TAMANG | 365.87 | 56.77 | 15.52 | 45
191 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. , SM/19176 | New | WATER SUPPLY SCHEME TO SANGSER KHASMAHAL ZONE II (BHANGAY, BIMBONG) (TSM/013034) | 257/NKWSMD | 20/02/2024 | 540 | KHALING ENTERPRISES | 325.39 | 0 | 0 | 45
192 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. , SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE VI (KHARKA) (TSM/013034) | 260/NKWSMD | 20/02/2024 | 720 | SUNNY CONSTRUCTION | 96.88 | 0 | 0 | 35
193 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. , SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE IV (KHARKA) (TSM/013034) | 255/NKWSMD | 20/02/2024 | 720 | SUNNY CONSTRUCTION | 418.78 | 16.02 | 3.83 | 40
194 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. , SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE I (BHANGAY, SANGSER KHASMAHAL (11,12)) (TSM/013034) | 256/NKWSMD | 20/02/2024 | 1095 | DINESH SHERPA | 732.17 | 0 | 0 | 50
195 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. , SM/19176 | New | Additional work for water supply scheme for Sangser Khasmahal Piped Water Supply Scheme (Zone - I, II, III, IV, V, VI, VII & VIII) in Kalimpong District. (TSM/013034) under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 458/NKWSMD | 03/04/2025 | 180 | MS. SURYA I PVT. LTD COMPANY | 99.75 | 0 | 0 | 0
196 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. , SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE V (SANGSER KHASMAHAL (11,12) (TSM/013034) | 259/NKWSMD | 20/02/2024 | 550 | DIPESH RAI | 170.34 | 0 | 0 | 100
197 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. , SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE VIII (MAN KHOLA FOREST VILLAGE), (TSM/013034) | 262/NKWSMD | 20/02/2024 | 540 | MS. SURYA I PVT. LTD COMPANY | 79.99 | 24.56 | 23.93 | 100
198 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. , SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE VII (TARA KHOLA FOREST VILLAGE), (TSM/013034) | 261/NKWSMD | 20/02/2024 | 540 | SANTOSH TAMANG | 236.31 | 0 | 0 | 50
199 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM UNEAK KHOLA TO DABLING , SM/09595 | New | P.W.S. Scheme from Uneak Khola to Dabling and its adjoining area under Gitdabling G.P. Block II under Kalimpong under Jal Swapno Programme within Darjeeling | 425/NKWSMD | 07/01/2022 | 90 | YAMA CONSTRUCTIONS LLP | 123.23 | 122.66 | 100 | 100
200 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM UNEAK KHOLA TO DABLING , SM/09595 | New | Material Requisition To Resource Division | 658/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.52 | 0 | 0 | 0
201 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWSS SCHEME FROM NIMBONG KHOLA TO UPPER AND LOWER GESHOK AND GAIRIGAON , SM/09545 | New | Details of Additional Pipeline for the work Piped Water Supply Scheme from Nimbong Khola to Upper and Lower Gashok under Nimbong Gram Panchayat. | 852/NKWSMD | 28/07/2023 | 30 | SANTOSH TAMANG | 4.86 | 0 | 0 | 0
202 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWSS SCHEME FROM NIMBONG KHOLA TO UPPER AND LOWER GESHOK AND GAIRIGAON , SM/09545 | New | Material Requisition To Resource Division | 638/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.69 | 0 | 0 | 0
203 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM DHOBI KHOLA TO LOWER DALEP , SM/10755 | New | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO LOWER DALEP UNDER BLOCK-II, KALIMPONG, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 534/NKWSMD | 25/05/2022 | 1080 | GETEN NAMGYAL BHUTIA | 199.1 | 114.88 | 57.7 | 100
204 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA UNDER BHALUKHOP G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10704 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-321 | 25/12/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0 | 0
205 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA UNDER BHALUKHOP G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10704 | New | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA AND ADJOINING AREA UNDER BHALUKHOP G.P. BLOCK-1 KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 1112/NKWSMD | 05/08/2022 | 1691 | SUNNY CONSTRUCTION | 327.77 | 300.53 | 66.64 | 100
206 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Paiengoan forest Village under Santook GP in Kalimpong Block-II in the district of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10625 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
207 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Paiengoan forest Village under Santook GP in Kalimpong Block-II in the district of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10625 | New | Material Requisition To Resource Division | 1373/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.38 | 0 | 0 | 0
208 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Paiengoan forest Village under Santook GP in Kalimpong Block-II in the district of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10625 | New | Creating gravity based Provision Of Drinking water from spring water source Paiengoan forest village under Santook Gram Panchayat under Kalimpong Block-II in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | 573/NKWSMD | 26/05/2022 | 90 | JUSTINE BHUTIA | 47.59 | 42.76 | 89.83 | 100
209 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED SAMALBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/10792 | New | SURFACE WATER BASED SAMALBONG KHASMAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE. | 960/NKWSMD | 12/07/2022 | 300 | M/S. ASHOK KUMAR PERIWAL | 583.66 | 380.26 | 65.15 | 70
210 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED SAMALBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/10792 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
211 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Mini Piped Water Supply Scheme for Lehti Forest Village under Block Gorubathan District Kalimpong , SM/10820 | New | Material Requisition To Resource Division | 2369/NKWSMD | 03/02/2023 | 0 | Resource Division | 2.13 | 0 | 0 | 0
212 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Mini Piped Water Supply Scheme for Lehti Forest Village under Block Gorubathan District Kalimpong , SM/10820 | New | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. | 826/NKWSMD | 30/06/2022 | 1530 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 0 | 0 | 100
213 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM MANDIR KHOLA TO TANYANG , SM/10751 | New | PIPED WATER SUPPLY SCHEME FROM MANDIR KHOLA TO TANYANG UNDER KALIMPONG BLOCK-I, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 551/NKWSMD | 26/05/2022 | 900 | AMIT KUMAR THAPA | 211.87 | 175.66 | 82.91 | 100
214 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF SURUK KHASMAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG , SM/11578 | New | SURUK KHAS MAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTAHAR G.P, KALIMPONG BLOCK-I, UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE, KALIMPONG | BP-2024-25-341 | 01/10/2024 | 0 | WBSEDCL | 4.86 | 0 | 0 | 0
215 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF SURUK KHASMAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG , SM/11578 | New | SURUK KHAS MAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTAHAR G.P, KALIMPONG BLOCK-I, UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE, KALIMPONG | 1496/NKWSMD | 14/10/2022 | 180 | M/S. ASHOK KUMAR PERIWAL | 369.37 | 292.7 | 79.24 | 100
216 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 03 Numbers of Health Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte. , SM/11369 | Health Center | Creating Gravity based Provision Of Drinking water from spring water source for Upper Dalep Health Center, Pedong G.P in Kalimpong Block -II under the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. | 985/NKWSMD | 12/07/2022 | 30 | YAMA CONSTRUCTIONS LLP | 4.85 | 4.24 | 87.34 | 0
217 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 03 Numbers of Health Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte. , SM/11369 | Health Center | Creating gravity based Provision of Drinking water from spring water source for Kashyone Health sub center, Kashyone G.P in Kalimpong Block -II under the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E. Directorate, Kalimpong. | 986/NKWSMD | 12/07/2022 | 30 | YAMA CONSTRUCTIONS LLP | 4.85 | 4.09 | 84.29 | 0
218 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 03 Numbers of Health Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte. , SM/11369 | Health Center | Creating gravity based Provision Of Drinking water from spring water source Tendrabong health sub Center, Sakyong G.P Kalimpong Block -II under the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E. Directorate, Kalimpong. | 987/NKWSMD | 12/07/2022 | 30 | YAMA CONSTRUCTIONS LLP | 4.85 | 4.09 | 84.3 | 0
219 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SUNTALAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG , SM/11377 | New | PAYMENT FOR WBSEDCL | BP-2023-24-525 | 21/02/2024 | 0 | WBSEDCL | 5.57 | 0 | 0 | 0
220 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SUNTALAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG , SM/11377 | New | PIPED WATER SUPPLY SCHEME FOR SUNTALAY KHASMAHAL UNDER TISTA G.P., KALIMPONG BLOCK-I, UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, P.H.E DIRECTORATE, KALIMPONG. | 949/NKWSMD | 12/07/2022 | 1080 | M/S. ASHOK KUMAR PERIWAL | 86.51 | 46.2 | 53.4 | 56
221 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 07 (Seven) Numbers of Gram Panchayat office in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/11372 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for 07 Numbers of Gram panchayat Office in Kalimpong Block -II under the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. | 937/NKWSMD | 12/07/2022 | 180 | DAWA TANGEE SHERPA | 42.17 | 37.34 | 88.54 | 95
222 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED WATER SUPPLY SCHEME FOR PUDDUNG KHAS MAHAL PWSS,BLOCK : KALIMPONG - I, DISTRICT : KALIMPONG , SM/13606 | New | PROPOSED SURFACE BASED PIPED WATER SUPPLY SCHEME FOR PUDDUNG KHASMAHAL PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. | 826/NKWSMD | 24/07/2023 | 785 | M/S. ASHOK KUMAR PERIWAL | 345.67 | 0 | 0 | 90
223 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS , SM/13953 | New | Material Requisition To Resource Division | 2552/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.08 | 0 | 0 | 0
224 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS , SM/13953 | New | Material Requisition To Resource Division | 2716/NKWSMD | 03/03/2023 | 0 | Resource Division | 4.08 | 0 | 0 | 0
225 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS , SM/13953 | New | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER SOURCE FOR SAKAM FOREST UNDER BLOCK:- GORUBATHAN, DISTRICT:- KALIMPONG, P.H.E Dte. | 2491/NKWSMD | 09/02/2023 | 545 | M/S. ASHOK KUMAR PERIWAL | 874.4 | 476.33 | 54.47 | 65
226 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS , SM/15554 | New | Material Requisition To Resource Division | 2749/NKWSMD | 06/03/2023 | 0 | Resource Division | 0.86 | 0 | 0 | 0
227 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS , SM/15554 | New | KUMAI FOREST(PART) & KUMAI TEA GARDEN (PART) PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME (TSM/016058) | 2731/NKWSMD | 03/03/2023 | 180 | PUSHPA KUMAR RIZAL | 195.31 | 108.88 | 55.75 | 50
228 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS , SM/15554 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1579/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
229 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/16512 | New | Material Requisition To Resource Division | 279/NKWSMD | 17/05/2023 | 0 | Resource Division | 0.84 | 0 | 0 | 0
230 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/16512 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
231 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/16512 | New | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission / Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024. | 1468/NKWSMD | 01/12/2023 | 62 | THE ELECTRIC SPHERE | 0.81 | 0 | 0 | 0
232 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/16512 | New | FOREST PAYMENT | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
233 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/16512 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG-I, DISTRICT : KALIMPONG. | 96/NKWSMD | 28/04/2023 | 700 | PASANG LAMA | 156.78 | 0 | 0 | 68
234 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/16512 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1578/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 100 | 100
235 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15641 | New | Material Requisition To Resource Division | 2722/NKWSMD | 03/03/2023 | 0 | Resource Division | 1.69 | 0 | 0 | 0
236 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15641 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-321 | 25/12/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0 | 0
237 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15641 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
238 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15641 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT: KALIMPONG | 2668/NKWSMD | 28/02/2023 | 720 | DIPESH RAI | 202.99 | 140.73 | 69.33 | 90
239 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15642 | New | Material Requisition To Resource Division | 2718/NKWSMD | 03/03/2023 | 0 | Resource Division | 96.35 | 0 | 0 | 0
240 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15642 | New | Proposed Pumping based Piped water supply scheme for Rambi Bazar DIF under Teesta G.P. Kalimpong Block I District Kalimpong. |  | 26/09/2024 | 0 | WBSEDCL | 5.15 | 0 | 0 | 0
241 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15642 | New | PAYMENT FOR WBSEDCL | BP-2023-24-655 | 23/03/2024 | 0 | WBSEDCL | 5.15 | 0 | 0 | 0
242 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15642 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 142.95 | 137.52 | 80
243 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) , SM/07872 | Retrofitting | Retrofitting for Functional Household Tap Connection (FHTC) of Piped Water Supply Scheme for Pedong Bazar and adjoining areas , Under Neorakhola W/S & Maintenance Division, P.H.Engineering Directorate, District- Kalimpong. | 187/NKWSMD | 12/10/2020 | 60 | LEGDEN PRADHAN | 21.21 | 42.12 | 198.59 | 100
244 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) , SM/07872 | Retrofitting | Retrofitting in connection with improvement of piped water supply scheme for Pedong Bazar and adjoining areas under Neorakhola W/S & Mtc. Division, P.H.Engineering Directorate, District- Kalimpong. | 297/NKWSMD | 25/01/2021 | 60 | LEGDEN PRADHAN | 35.86 | 51.65 | 169.23 | 100
245 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) , SM/07872 | Retrofitting | Laying of 65mm G.I. pipe from Upper Thukchu khola towards Pipli Dara under piped water supply scheme for Pedong Bazar and Adjoining Area in Dist-Kalimpong, Block-II, under Neorakhola W/S & Mtc Division under PHE Dte Kalimpong. | 269/NKWSMD | 23/11/2021 | 30 | LEGDEN PRADHAN | 4.08 | 3.41 | 100 | 100
246 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) , SM/07872 | Retrofitting | Laying of 65mm G.I. pipe from Link road towards Pedong Bazar under piped water supply scheme for Pedong Bazar and Adjoining Area in Dist-Kalimpong, Block-II, under Neorakhola W/S & Mtc Division under PHE Dte Kalimpong. | 270/NKWSMD | 23/11/2021 | 30 | LEGDEN PRADHAN | 4.71 | 4.09 | 100 | 100
247 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) , SM/07872 | Retrofitting | Restoration of pipeline of Piped Water Supply Scheme for Pedong Bazar adjoining areas damaged during this monsoon season. | 303/NKWSMD | 27/02/2024 | 60 | LEGDEN PRADHAN | 8.56 | 5.13 | 60 | 100
248 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO KASHYONE. , SM/09599 | New | P.W.S SCHEME FROM DHOBI KHOLA TO KASHYONE AND ITS ADJOINING AREA UNDER KASHYONE G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | 627/NKWSMD | 21/02/2022 | 150 | DINESH SHERPA | 302.88 | 225.03 | 74.29 | 80
249 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO KASHYONE. , SM/09599 | New | Material Requisition To Resource Division | 838/NKWSMD | 21/03/2022 | 0 | Resource Division | 2.76 | 0 | 0 | 0
250 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO KASHYONE. , SM/09599 | New | Material Requisition To Resource Division | 1380/NKWSMD | 22/09/2022 | 0 | Resource Division | 2.76 | 0 | 0 | 0
251 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM JHOLUNG KHOLA TO 45 DHURA , SM/09584 | New | Material Requisition To Resource Division | 649/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.88 | 0 | 0 | 0
252 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM HARI KHOLA TO UPPER LOWER GUMTI , SM/09539 | New | Material Requisition To Resource Division | 654/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.66 | 0 | 0 | 0
253 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM HARI KHOLA TO UPPER LOWER GUMTI , SM/09539 | New | Piped Water Supply Scheme from Hari Khola to Upper and Lower Gumti in Samsing G.P. Gorubathan Block under Jal Swapno Programme within Kalimpong District | 456/NKWSMD | 14/01/2022 | 1088 | SUBAN RAI | 147.06 | 120.7 | 82.08 | 100
254 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 100 to 150 (1500 meters) between thockchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | 763/NKWSMD | 28/02/2022 | 180 | SONAM TOPGAY BHUTIA | 70.73 | 0 | 0 | 0
255 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 25 to 32 from Dhaula source towards lava (ch no 194 to 284) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | 770/NKWSMD | 28/02/2022 | 180 | DAWA LAMA | 86.29 | 85.38 | 98.95 | 80
256 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 150 to 200 (1500 meters) between Thockchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | 764/NKWSMD | 28/02/2022 | 180 | HEMANT MOKTAN | 70.72 | 0 | 0 | 0
257 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 200 to 262 (1860 meters) between thockchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | 765/NKWSMD | 28/02/2022 | 180 | JUSTINE BHUTIA | 91.64 | 0 | 0 | 0
258 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 1 to 9 from Neora source towards Dhalua source (ch no -29 to 219), under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | 767/NKWSMD | 28/02/2022 | 180 | DHURBA KUMAR PRADHAN | 98.22 | 98.1 | 99.88 | 100
259 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 200 to ch no 250 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | 759/NKWSMD | 28/02/2022 | 180 | KUMAR THAPA | 73.24 | 0 | 0 | 0
260 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 250 to thukchu source (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | 760/NKWSMD | 28/02/2022 | 180 | BINOD TAMANG | 73.24 | 0 | 0 | 0
261 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 50 to 100 (1500 meters) between thockchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | 762/NKWSMD | 28/02/2022 | 180 | SANJAY GURUNG | 72.79 | 0 | 0 | 0
262 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from Off take structure to ch no 50 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | 755/NKWSMD | 28/02/2022 | 180 | DHURBA KUMAR PRADHAN | 71.47 | 0 | 0 | 0
263 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from thukchu source to ch no 50 (1500 meters) between thockchu source to Alagarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | 761/NKWSMD | 28/02/2022 | 180 | SONAM TOPGAY BHUTIA | 72.76 | 0 | 0 | 0
264 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 50 to ch no 100 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | 756/NKWSMD | 28/02/2022 | 180 | DAWA LAMA | 71.25 | 0 | 0 | 0
265 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 150 to ch no 200 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | 758/NKWSMD | 28/02/2022 | 180 | THUPDEN BHUTIA | 73.05 | 0 | 0 | 0
266 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 59 & 66 from saddle back towards thokchu (ch no-183 -300) under Neorakhola Water Supply & Mtc Division, PHE Dte Kalimpong. | 774/NKWSMD | 28/02/2022 | 180 | BINOD TAMANG | 50.59 | 22.65 | 44.78 | 47
267 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 41 to 47 from dolay transit camp towards lava (ch no 395 to 487) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | 772/NKWSMD | 28/02/2022 | 180 | MOHAN KR. RAI | 74.69 | 74.21 | 99.36 | 80
268 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 100 to ch no 150 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | 757/NKWSMD | 28/02/2022 | 180 | MOHAN KUMAR RAI | 71.21 | 0 | 0 | 0
269 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 48 to 54 from dolay transit camp towards lava (ch no 520 to 612) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | 773/NKWSMD | 28/02/2022 | 180 | KUMAR THAPA | 82.45 | 79.7 | 96.66 | 71
270 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 262 to Algarah v notch (1890 meters) between thukchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch of Neorakhola water supply & Mtc Division, PHE Dte Kalimpong | 766/NKWSMD | 28/02/2022 | 180 | JUSTINE BHUTIA | 92.4 | 0 | 0 | 0
271 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 33 to 40 from dolay transit camp towards lava (ch no 303 to 395) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | 771/NKWSMD | 28/02/2022 | 180 | JUSTINE BHUTIA | 74.38 | 74.04 | 44.02 | 75
272 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 10 to 17 from Dhaula source towards lava (ch no 14 to 104) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | 768/NKWSMD | 28/02/2022 | 180 | BHUTIA AND SONS | 86.41 | 86.3 | 57.74 | 85
273 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 18 to 24 from Dhaula source towards lava (ch no 104 to 194) ,under Neorakhola Water Supply & Mtc Division, PHE Dte Kalimpong. | 769/NKWSMD | 28/02/2022 | 180 | THUPDEN BHUTIA | 86.63 | 86.4 | 100 | 80
274 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Replacement of 4 nos Damaged Steel Bridge with 3 nos New Steel bridge of 15m span in between ch no-119-120 (Bridge no-58), steel bridge 10m span chain no ¿ 144 (Bridge no-69) new tubular Steel bridge of 10m span in between ch no-95 (Bridge no-61) and construction of RCC bridge at ch no-92 in place of bridge no 15(Dhalua to Dolay), including resting over concrete abutment on both the sides including construction of slope protection works for abutments under Neorakhola Water Supply Scheme under PHE Dte. | 105/NKWSMD | 13/04/2022 | 360 | THUPDEN BHUTIA | 173.91 | 87 | 50.03 | 90
275 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months, other than G.T.A Area from 01/02/2024 to 31/07/2024. Note: With effect from the date of issuing work order. | 170/NKWSMD | 31/01/2024 | 180 | SUJIT DEB | 0.99 | 1.16 | 117.6 | 0
276 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months for G.T.A Area from 01/02/2024 to 31/07/2024. Note: With effect from the date of issuing work order. | 169/NKWSMD | 31/01/2024 | 182 | YAMA CONSTRUCTIONS LLP | 0.99 | 2.35 | 237.55 | 0
277 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong , SM/10052 | Augmentation | Replacement of existing RCC bridge locally known as OLD English Bridge Bridge No 70 with New Steel bridge of 20m Span in between chain no-129 to 130 Span resting over concrete abutment on both the sides including construction of slope protection works for abutments under Neorakhola Water Supply Scheme under PHE Dte, Kalimpong | 104/NKWSMD | 13/04/2022 | 180 | JUSTINE BHUTIA | 50.25 | 43.61 | 46.59 | 99
278 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Bokhim khasmahal & paygang khasmahal (PC) under Gitdabling G.P. Kalimpong Blick-II in the District of Kalimpong in connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. , SM/10562 | New | Creating Gravity based piped water supply scheme for Bokhim Khasmaha & Paygang Khasmal (PC) under Gitdabling G.P kalimpong Block -II in the district of Kalimpong in connection with JJM & Jal Swapna, under Neorakhola w/s & MtC Division , PHE Dte, Kalimpong | 501/NKWSMD | 24/05/2022 | 180 | TIKARAM SHARMA | 126.49 | 106.04 | 45.95 | 85
279 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM PARANG KHOLA TO MUNSONG CINCHONA PLANTATION , SM/10744 | New | PIPED WATER SUPPLY SCHEME FROM PARANG KHOLA TO MUNSONG CINCHONA PLANTATION UNDER SANGSEY G.P. BLOCK-II, KALIMPONG, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 531/NKWSMD | 25/05/2022 | 180 | YAMA CONSTRUCTIONS LLP | 222.09 | 218.46 | 65.12 | 100
280 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10603 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
281 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10603 | New | Creating gravity based Provision Of Drinking water from spring water source Noam forest village under Pokhriabong Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | 568/NKWSMD | 26/05/2022 | 90 | PRAKASH TAMANG | 44.19 | 37.19 | 46.38 | 100
282 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10603 | New | Material Requisition To Resource Division | 1553/NKWSMD | 19/10/2022 | 0 | Resource Division | 0.34 | 0 | 0 | 0
283 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 8 12 AND KHOTILINE UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10696 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by Public Health Engineering Directorate by engaging skilled artist and helper artist in different location within 332 Villages in Different Block under Darjeeling and Kalimpong District under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate all complete as per direction of EIC. In Each Village in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by Public Health Engineering Directorate, Writing area should be Geo Tagged in appropriate portal as guided by Public Health Engineering Department. | 179/AE-II/NKWSMD | 05/03/2024 | 31 | RADIANT | 10 | 0 | 0 | 40
284 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 8 12 AND KHOTILINE UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10696 | New | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 12,8 NO. & KOTHIDARA UNDER GORUBATHAN BLOCK KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 526/NKWSMD | 25/05/2022 | 180 | MAHADEO PRASAD AGARWAL & CO | 97.89 | 80.87 | 82.62 | 100
285 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM KATHAREY KHOLA TO BHUTIA BUSTY UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10697 | New | PIPED WATER SUPPLY SCHEME FROM KATHAREY KHOLA TO BHUTIA BUSTY UNDER GORUBATHAN BLOCK KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 1096/NKWSMD | 01/08/2022 | 910 | BRISTI CONSTRUCTION | 120.9 | 73.25 | 60.59 | 100
286 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of Lolaygoan Bazar Water Supply Scheme (IMIS Code-0001723403) for providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission (JJM) under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. , SM/10705 | Augmentation | Augmentation of Lolaygaon Bazar Water Supply Scheme (IMIS Code-0001723403) for providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna & Jal Jevan Mission(JJM) under Neorakhola W/S & Mtc. Division, P.H. E. Dte, Kalimpong | 108/NKWSMD | 13/04/2022 | 450 | SANTOSH TAMANG | 95.54 | 67.31 | 70.45 | 100
287 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SINGI KAHSMAHAL PWSS IN KALIMPONG-I BLOCK , SM/12181 | New | Additional FHTC estimate for the work Piped Water Supply Scheme from Khani Khola to West Samalbong SM Code 09669 / IMIS ID 40012989 | 1282/NKWSMD | 17/10/2023 | 30 | BASANT PRADHAN | 4.64 | 0 | 0 | 0
288 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SINGI KAHSMAHAL PWSS IN KALIMPONG-I BLOCK , SM/12181 | New | WATER SUPPLY SCHEME FOR SINGI KHASAMAHAL PIPED WATER SUPPLY SCHEME IN KALIMPONG-I BLOCK UNDER KALIMPONG DISTRICT. | 1621/NKWSMD | 03/11/2022 | 820 | SRINIWAS AGARWAL | 657.41 | 367.45 | 55.89 | 95
289 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 02 numbers of Health centers, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong. , SM/11367 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Gairibas SSK/SC under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Maintenance Division ,Kalimpong PHE Dte(Part2) | 626/NKWSMD | 26/05/2022 | 30 | DORJEE SHERPA | 4.84 | 4.43 | 100 | 0
290 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 02 numbers of Health centers, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong. , SM/11367 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Kumai Sub Centre under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply Division ,Kalimpong PHE Dte(Part 2) | 624/NKWSMD | 26/05/2022 | 30 | DORJEE SHERPA | 4.76 | 4.32 | 100 | 0
291 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 02 numbers of Health centers, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong. , SM/11367 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Kumai Sub Centre under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply Division ,Kalimpong PHE Dte. (Part1) | 625/NKWSMD | 26/05/2022 | 30 | TOPGAY BHUTIA | 1.46 | 0.65 | 100 | 0
292 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 02 numbers of Health centers, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong. , SM/11367 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Gairibas SSK/SC under Gorubathan Block in the District of Kalimpong Under Neorakhola Water Supply & Maintenance Division, Kalimpong P.H.E. Dte (Part1) | 627/ NKWSMD | 26/05/2022 | 30 | TOPGAY BHUTIA | 1.2 | 0.37 | 100 | 100
293 | KALIMPONG | Neorakhola W/S & Mtc.Div. | UPPER FAGU PIPED WATER SUPPLY SCHEME. , SM/13954 | New | Material Requisition To Resource Division | 814/NKWSMD | 24/07/2023 | 0 | Resource Division | 5.69 | 0 | 0 | 0
294 | KALIMPONG | Neorakhola W/S & Mtc.Div. | UPPER FAGU PIPED WATER SUPPLY SCHEME. , SM/13954 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
295 | KALIMPONG | Neorakhola W/S & Mtc.Div. | UPPER FAGU PIPED WATER SUPPLY SCHEME. , SM/13954 | New | Piped Water Supply Scheme For Upper Fagu Tea Garden Under Jal Jeevan Mission. | 723/NKWSMD | 18/07/2023 | 715 | M/S R.S. CONSTRUCTION | 801.86 | 0 | 0 | 65
296 | KALIMPONG | Neorakhola W/S & Mtc.Div. | UPPER FAGU PIPED WATER SUPPLY SCHEME. , SM/13954 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1578/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 100 | 100
297 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/15042 | New | Material Requisition To Resource Division | 2550/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.99 | 0 | 0 | 0
298 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/15042 | New | Material Requisition To Resource Division | 2724/NKWSMD | 03/03/2023 | 0 | Resource Division | 0.99 | 0 | 0 | 0
299 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/15042 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | 2489/NKWSMD | 09/02/2023 | 960 | THUPDEN BHUTIA | 194.1 | 94.23 | 48.55 | 90
300 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER KALIMPONG G.P, BLOCK:-KALIMPONG-I, DISTRICT:-KALIMPONG , SM/16231 | New | Material Requisition To Resource Division | 366/NKWSMD | 29/05/2023 | 0 | Resource Division | 7.2 | 0 | 0 | 0
301 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER KALIMPONG G.P, BLOCK:-KALIMPONG-I, DISTRICT:-KALIMPONG , SM/16231 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG KHASMAHAL PIPED WATER SUPPLY SCHEME, UNDER KALIMPONG G.P BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. | 360/NKWSMD | 26/05/2023 | 665 | RAMESH KUMAR AGARWAL & CO | 848.05 | 474.49 | 55.95 | 80
302 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/16514 | New | Material Requisition To Resource Division | 449/NKWSMD | 07/06/2023 | 0 | Resource Division | 3.33 | 0 | 0 | 0
303 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/16514 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. | 417/NKWSMD | 05/06/2023 | 725 | THUPDEN BHUTIA | 875.98 | 222.83 | 25.44 | 60
304 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/16234 | New | Material Requisition To Resource Division | 769/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.25 | 0 | 0 | 0
305 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/16234 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-319 | 17/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 4.74 | 0 | 0 | 0
306 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/16234 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-298 | 07/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0 | 0
307 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/16234 | New | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG-I, DISTRICT : KALIMPONG. | 679/NKWSMD | 12/07/2023 | 890 | DIPENDRA CHETTRI | 52.63 | 0 | 0 | 40
308 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG , SM/15646 | New | Material Requisition To Resource Division | 2721/NKWSMD | 03/03/2023 | 0 | Resource Division | 1.05 | 0 | 0 | 0
309 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG , SM/15646 | New | PROPOSED GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PALLA KHASMAHAL(MULPALA PART) UNDER LOLAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | 2662/NKWSMD | 28/02/2023 | 240 | SRINIWAS AGARWAL | 197.88 | 87.32 | 44.13 | 50
310 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG , SM/15646 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm. underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Darjeeling Division-II, P.H.E.D., GTA. | 158/AE-II/NKWSMD | 10/01/2024 | 195 | SANTOSH TAMANG | 18.72 | 0 | 0 | 100
311 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG , SM/15646 | New | Proposed Gravity Based and Pumping Based PWSS for Palla Khasmahal (Mulpala part) under Lolay G.P Block: Kalimpong - II,District: Kalimpong. | "BP-2024-25-236 | 03/09/2024 | 0 | WBSEDCL | 11.27 | 0 | 0 | 0
312 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DALINGKOT FOREST & DALINGMA KHASMAHAL PWSS , SM/19112 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Neorakhola W/S & Mtc. Division, P.H.E. Dte. | 157/AE-II/NKWSMD | 10/01/2024 | 15 | SANTOSH TAMANG | 14.76 | 0 | 0 | 100
313 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DALINGKOT FOREST & DALINGMA KHASMAHAL PWSS , SM/19112 | New | Material Requisition To Resource Division | 41/NKWSMD | 09/01/2024 | 0 | Resource Division | 4.82 | 0 | 0 | 0
314 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DALINGKOT FOREST & DALINGMA KHASMAHAL PWSS , SM/19112 | New | DALINGKOT FOREST PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME, UNDER BLOCK:- GORUBATHAN. DISTRICT:- KALIMPONG. | 4/NKWSMD | 03/01/2024 | 365 | THUPDEN BHUTIA | 1388.85 | 0 | 0 | 15
315 | KALIMPONG | Neorakhola W/S & Mtc.Div. | RANGO FOREST PWSS , SM/18823 | New | Material Requisition To Resource Division | 1173/NKWSMD | 05/10/2023 | 0 | Resource Division | 11.65 | 0 | 0 | 0
316 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM KAMZER KHOLA TO LOWER LOLAY , SM/10754 | New | PIPED WATER SUPPLY SCHEME FROM KAMZER KHOLA TO LOWER LOLAY UNDER KALIMPONG BLOCK-I UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 552/NKWSMD | 26/05/2022 | 810 | SHASHI LEPCHA | 174.61 | 157.47 | 69.74 | 100
317 | KALIMPONG | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. , SM/18589 | New | WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL (Part-II) PIPED WATER SUPPLY SCHEME IN KALIMPONG-II BLOCK UNDER KALIMPONG DISTRICT. | 891/NKWSMD | 07/08/2023 | 635 | SRINIWAS AGARWAL | 1057.74 | 758.96 | 41.9 | 100
318 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM KAIJARBOTEY JHORA TO LOWER POSHYER BHASMEY , SM/09614 | New | Piped Water Supply Scheme from Kaijarbotay Jhora to Lower Poshyer Bhasmey under Tashiding G.P. Block l, Kalimpong under Jal Swapno Programme Kalimpong District | 452/NKWSMD | 14/01/2022 | 90 | SUDEN TAMANG | 85.69 | 68.54 | 79.99 | 90
319 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM KAIJARBOTEY JHORA TO LOWER POSHYER BHASMEY , SM/09614 | New | Material Requisition To Resource Division | 660/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.33 | 0 | 0 | 0
320 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM MAWATAR TO UPPER DABLING , SM/09546 | New | P.W.S SCHEME FROM MAWATAR TO UPPER DABLING UNDER GITDABLING G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 419/NKWSMD | 07/01/2022 | 90 | TIKARAM SHARMA | 186.55 | 185.9 | 100 | 100
321 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM MAWATAR TO UPPER DABLING , SM/09546 | New | Material Requisition To Resource Division | 652/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.27 | 0 | 0 | 0
322 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM MAWATAR TO UPPER DABLING , SM/09546 | New | computer operator payment | BP-2023-24-193 | 30/09/2023 | 0 | KASHYAP COMPUTERS | 0.51 | 0 | 0 | 0
323 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM MAWATAR TO UPPER DABLING , SM/09546 | New | Acceptance order for Engagement of DEO(Data Entry Operator) through agency/contractor for office of the Executive Engineer, Kurseong Divisaion, PHED, for Operation proper e-Governance activity i.e. JJM at kurseong under kurseong Division PHE Dte. |  | 18/04/2023 | 0 | KASHYAP COMPUTERS | 0.85 | 0 | 0 | 0
324 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM JHOLUNGAY KHOLA(BANDUKEY) TO DOKAN DARA , SM/09605 | New | Material Requisition To Resource Division | 651/NKWSMD | 23/02/2022 | 0 | Resource Division | 1.21 | 0 | 0 | 0
325 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM JHOLUNGAY KHOLA(BANDUKEY) TO DOKAN DARA , SM/09605 | New | P.W.S. Scheme from Jholungay Khola (Bandukey) to Dokan dara in Rangpo G.P. Gorubathan Block, Kalimpong under Jal Jeevan Mission and Jal Swapno Programme | 449/NKWSMD | 14/01/2022 | 1000 | MAHADEO PRASAD AGARWAL & CO | 159.62 | 130.66 | 81.86 | 100
326 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAR CHAREY JHORA TO PUBUNG BUSTY , SM/09543 | New | Material Requisition To Resource Division | 840/NKWSMD | 21/03/2022 | 0 | Resource Division | 1.17 | 0 | 0 | 0
327 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAR CHAREY JHORA TO PUBUNG BUSTY , SM/09543 | New | P.W.S SCHEME FROM CHAR CHAREY JHORA TO PUBUNG BUSTY AND ITS ADJOINING AREAS IN POKRAIBONG G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | 628/NKWSMD | 21/02/2022 | 330 | SRINIWAS AGARWAL | 353.99 | 283.07 | 79.97 | 80
328 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. , SM/10266 | Retrofitting | "Providing Func tional household Tap connection under JJM & JSP Pro gram me for Pws sche me from Jhandi Jhora to Upper & lower Mangzing Pokhrebong GP" | BP-2022-23-5 | 11/04/2022 | 0 | ASHOK CHETTRI | 10.86 | 0 | 0 | 0
329 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. , SM/10266 | Retrofitting | Pr oviding house connection for Dws Scheme from Ambiok Khola to dalimtarr Busty Dalim GP | BP-2022-23-58 | 01/06/2022 | 0 | ASHOK SUNAM | 14.43 | 0 | 0 | 0
330 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. , SM/10266 | Retrofitting | "Prov iding Function al household Tap connection under JJM & JSP Programme for Dws scheme from Dobaney Jhora to 2 no phase six bus stand Paten Godak Gp" | BP-2022-23-178 | 25/10/2022 | 0 | JOJO CONSTUCTION | 7.66 | 0 | 0 | 0
331 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. , SM/10266 | Retrofitting | Providin g Functional household Tap connection under JJM and JSP Programme for Dws scheme by Pumpin g fo r Malbusty Chettri Gaon Gorubathan GP | BP-2022-23-30 | 20/04/2022 | 0 | NEMESH LAMA | 9.28 | 0 | 0 | 0
332 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. , SM/10266 | Retrofitting | providing Functional household Tap connect ion under JJM & JSP Programme for Dws scheme from Jholung khola to Sangam Gaon under Rongo GP | BP-2022-23-28 | 20/04/2022 | 0 | PREM KUMAR GURUNG | 16.91 | 0 | 0 | 0
333 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. , SM/10266 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Pro grammme for Dws schem e from KAii KHola to Upper Fagu Fac tory line Nim GP | BP-2022-23-29 | 20/04/2022 | 0 | NEMESH LAMA | 8.59 | 0 | 0 | 0
334 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. , SM/10266 | Retrofitting | "Prov iding Function al household Tap connection under JJM & JSP Programme for Dws scheme from Dobaney Jhora to 2 no phase six bus stand Paten Godak Gp" | BP-2022-23-166 | 11/10/2022 | 0 | JOJO CONSTUCTION | 6 | 0 | 0 | 0
335 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. , SM/10266 | Retrofitting | Addition Estimate for the FHTC under JJM Programme 8 nos existing schemes to be provided with FHTC under Kalimpong Block-II in the district of Kalimpong, FHTC under JJM Programme 14 nos existing schemes to be provided with FHTC, FHTC under JJM Programme 10 nos existing schemes to be provided with FHTC under Block-III, Gorubathan. | 1875/NKWSMD | 14/12/2022 | 60 | YAMA CONSTRUCTIONS LLP | 62.3 | 34.3 | 100 | 100
336 | KALIMPONG | Darjeeling Division II (Kalimpong) | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. , SM/10266 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme for Dws scheme from Ashale Khola to Samsing Fari Busty Samsing Gp | 658/DD-II | 18/02/2021 | 60 | SUBAN RAI | 18.62 | 18.46 | 100 | 100
337 | KALIMPONG | Darjeeling Division II (Kalimpong) | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. , SM/10266 | Retrofitting | Providing Function household Tap connecti on under JJM & JSP programme for Dws scheme from asahalay Khola to Samsing Compound Busty Sam sing Gp | 656/DD-II | 18/02/2021 | 60 | SUBAN RAI | 18.61 | 18.49 | 100 | 100
338 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. , SM/10266 | Retrofitting | Material Requisition To Resource Division | 2598/NKWSMD | 17/02/2023 | 0 | Resource Division | 10.9 | 0 | 0 | 0
339 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. , SM/10266 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme for Dws scheme from Simsaray Jhora t o Upper Ka mzer in Lolay GP | BP-2023-24-663 | 29/03/2024 | 0 | DIPESH RAI | 7.89 | 0 | 0 | 0
340 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM GURUNG JHORA TO PACHIM KABI GAON UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10695 | New | PIPED WATER SUPPLY SCHEME FROM GURUNG JHORA TO PACHIM KABI GAON UNDER BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 553/NKWSMD | 26/05/2022 | 180 | PASANG LAMA & SONS(HUF) | 133.86 | 111.81 | 83.53 | 100
341 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM DADALEY JHORA TO BURMAIK UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10699 | New | PIPED WATER SUPPLY SCHEME FROM DADALEY JHORA TOBURMAIK UNDER SANGSEY G.P. BLOCK-II KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 528/NKWSMD | 25/05/2022 | 180 | M/S. ASHOK KUMAR PERIWAL | 147.75 | 64.76 | 43.83 | 50
342 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM HARISEY JHORA TO LOWER BHAGEY UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10702 | New | PIPED WATER SUPPLY SCHEME FROM HARISEY JHORA TO LOWER BHAGEY UNDER G.P. BLOCK-II KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. GO2223001538PH | 291/NKWSMD | 13/05/2022 | 180 | PEMA BHUTIA | 100.81 | 79.21 | 78.58 | 85
343 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM SISNEY KHOLA TO NAJOK BUSTY , SM/10752 | New | PIPED WATER SUPPLY SCHEME FROM SISNEY KHOLA TO NAJOK BUSTY UNDER KALIMPONG BLOCK-I UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 833/NKWSMD | 30/06/2022 | 360 | RABIN RAI | 73.59 | 62.73 | 85.24 | 100
344 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM SAWRENI KHOLA TO NIM BUSTY , SM/11340 | New | PIPED WATER SUPPLY SCHEME FROM SAWRENI KHOLA TO NIM BUSTY UNDER GORUBATHAN BLOCK, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 790/NKWSMD | 30/06/2022 | 180 | PRAKASH TAMANG | 174.02 | 111.36 | 63.99 | 85
345 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM DEORALI KHOLA TO PAKANG , SM/11341 | New | PIPED WATER SUPPLY SCHEME FROM DEORALI KHOLA TO PAKANG SONAGAON UNDER GITABLING G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 788/NKWSMD | 30/06/2022 | 1060 | TIKARAM SHARMA | 113.45 | 89.7 | 79.06 | 100
346 | KALIMPONG | Neorakhola W/S & Mtc.Div. | AMBEOK TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/13610 | New | Material Requisition To Resource Division | 2565/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.9 | 0 | 0 | 0
347 | KALIMPONG | Neorakhola W/S & Mtc.Div. | AMBEOK TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/13610 | New | Creating Gravity Based Piped Water Supply For Today Ambeok Tea Garden Under Gorubathan Block Under Kalimpong District Under P.H.E Dte. | 2151/NKWSMD | 20/01/2023 | 180 | M/S R.S. CONSTRUCTION | 255.72 | 197.85 | 77.37 | 85
348 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/13621 | New | Material Requisition To Resource Division | 2588/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.76 | 0 | 0 | 0
349 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/13621 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-298 | 07/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0 | 0
350 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/13621 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-319 | 17/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 4.74 | 0 | 0 | 0
351 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/13621 | New | Pumping Based Piped Water Supply Scheme for Turzam Forest under Teesta G.P. Block Kalimpong-I, District: Kalimpong. | 2005/NKWSMD | 23/12/2022 | 180 | SANTOSH TAMANG | 221.13 | 90.27 | 40.82 | 50
352 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/13621 | New | Pumping based Piped water supply scheme for Turzum Forest under Teesta G.P. Kalimpong Block- I District Kalimpong. | BP-2024-25-446 | 28/11/2024 | 0 | WBSEDCL | 14.53 | 0 | 0 | 0
353 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/13621 | New | Pumping Based Piped Water Supply Scheme for Turzum Forest under Teesta G.P. Block Kalimpong -I , District- Kalimpong. |  | 31/07/2024 | 0 | WBSEDCL | 14.53 | 0 | 0 | 0
354 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong , SM/13604 | New | Material Requisition To Resource Division | 2029/NKWSMD | 29/12/2022 | 0 | Resource Division | 6.25 | 0 | 0 | 0
355 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong , SM/13604 | New | Material Requisition To Resource Division | 2586/NKWSMD | 17/02/2023 | 0 | Resource Division | 6.25 | 0 | 0 | 0
356 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong , SM/13604 | New | PAYMENT FOR WBSEDCL | BP-2023-24-521 | 21/02/2024 | 0 | WBSEDCL | 7.83 | 0 | 0 | 0
357 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong , SM/13604 | New | PAYMENT FOR WBSEDCL | BP-2023-24-520 | 21/02/2024 | 0 | WBSEDCL | 5.66 | 0 | 0 | 0
358 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong , SM/13604 | New | SURFACE WATER BASED BONG KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE | 1876/NKWSMD | 14/12/2022 | 720 | SRINIWAS AGARWAL | 534.86 | 480.59 | 89.85 | 100
359 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong , SM/13604 | New | Logistic arrangement and hand holding support to Jalpaiguri Government Engineering College for conducting Geo-Technical investigation at GLR sites in different locations of Darjeeling & Kalimpong District under Jal Jeevan Mission. | 137/AE-II/NKWSMD | 08/12/2023 | 62 | YAMA CONSTRUCTIONS LLP | 6.99 | 0 | 0 | 100
360 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PANKHASARI KHASMAHAL PWSS , SM/14170 | New | Material Requisition To Resource Division | 2582/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.1 | 0 | 0 | 0
361 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PANKHASARI KHASMAHAL PWSS , SM/14170 | New | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER SOURCE FOR PANKHASARI KHASMAHAL PWSS (ZONE -1) to (ZONE-V) UNDER BLOCK:- GORUBATHAN, DISTRICT:- KALIMPONG, P.H.E Dte. | 2470/NKWSMD | 06/02/2023 | 365 | THUPDEN BHUTIA | 1193.6 | 980.9 | 82.18 | 80
362 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15640 | New | Material Requisition To Resource Division | 2775/NKWSMD | 10/03/2023 | 0 | Resource Division | 4.22 | 0 | 0 | 0
363 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15640 | New | Material Requisition To Resource Division | 2710/NKWSMD | 03/03/2023 | 0 | Resource Division | 4.22 | 0 | 0 | 0
364 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15640 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | 2659/NKWSMD | 28/02/2023 | 720 | M/S. ASHOK KUMAR PERIWAL | 474.98 | 248.42 | 52.3 | 90
365 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15640 | New | Demand note for Proposal of Diversion of 0.03917 ha of forest land for Gravity Based Water supply scheme for Teesta DIF fund by West Bengal Public Health Engineering Directorate under Jal Jeevan Mission. | BP-2024-25-221 | 28/08/2024 | 0 | WBSFDA | 1.76 | 0 | 0 | 0
366 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/15640 | New | Demand note for proposal of Diversion of 0.03917 ha of forest land for Gravity based water supply scheme for Teesta DIF fund by West Bengal Public Health Engineering Directorate under Jal Jeevan mission. | BP-2024-25-222 | 28/08/2024 | 0 | WBSFDA | 2.6 | 0 | 0 | 0
367 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL (PART) UNDER KAGEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG , SM/16235 | New | Material Requisition To Resource Division | 774/NKWSMD | 19/07/2023 | 0 | Resource Division | 1.22 | 0 | 0 | 0
368 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL (PART) UNDER KAGEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG , SM/16235 | New | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL PIPED WATER SUPPLY SCHEME, UNDER KAGEY G.P BLOCK : KALIMPONG-II, DISTRICT: KALIMPONG. | 678/NKWSMD | 12/07/2023 | 720 | NEOCON CONSTRUCTION CO | 208.69 | 69.36 | 33.23 | 75
369 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM 9TH MILE JHORA TO 18TH MILE , SM/09603 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
370 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM 9TH MILE JHORA TO 18TH MILE , SM/09603 | New | Material Requisition To Resource Division | 839/NKWSMD | 21/03/2022 | 0 | Resource Division | 0.66 | 0 | 0 | 0
371 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM 9TH MILE JHORA TO 18TH MILE , SM/09603 | New | Material Requisition To Resource Division | 1374/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.66 | 0 | 0 | 0
372 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM 9TH MILE JHORA TO 18TH MILE , SM/09603 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
373 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM 9TH MILE JHORA TO 18TH MILE , SM/09603 | New | P.W.S SCHEME FROM 9th MILE JHORA TO 18th MILE AND ITS ADJOINING AREA UNDERPAIYONG G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | 629/NKWSMD | 21/02/2022 | 750 | SUNIL BAJLA | 251.13 | 212.78 | 84.73 | 100
374 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PATEN GODAK KHASMAHAL PWSS , SM/18255 | New | Material Requisition To Resource Division | 763/NKWSMD | 19/07/2023 | 0 | Resource Division | 5.38 | 0 | 0 | 0
375 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PATEN GODAK KHASMAHAL PWSS , SM/18255 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
376 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PATEN GODAK KHASMAHAL PWSS , SM/18255 | New | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER FOR PATEN GODAK KHASMAHAL, UNDER BLOCK: GORUBATHAN, DISTRICT KALIMPONG, UNDER PUBLIC HEALTH ENGINEERING DIRECTORATE. | 710/NKWSMD | 17/07/2023 | 730 | THUPDEN BHUTIA | 1116.3 | 338.86 | 30.36 | 45
377 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PATEN GODAK KHASMAHAL PWSS , SM/18255 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | 1593/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 100 | 100
378 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM OKHERBOTEY JHORA TO DARA GAON , SM/09598 | New | P.W.S. Scheme from Okherbotay Jhora to Dara Gaon Lower Burmek under Munsung G.P. Block II Kalimpong under Jal Jeevan Mission and Jal Swapno Programme | 426/NKWSMD | 07/01/2022 | 90 | DINESH SHERPA | 93.5 | 93.21 | 49.98 | 100
379 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM OKHERBOTEY JHORA TO DARA GAON , SM/09598 | New | Material Requisition To Resource Division | 639/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.31 | 0 | 0 | 0
380 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAWA KHOLA TO RELLI , SM/09610 | New | Piped Water Supply Scheme from Chawa Khola to Relli and its adjoining area under Lolay G.P. Block II under Jal Swapno Programme within kalimpong District | 424/NKWSMD | 07/01/2022 | 90 | DIPESH RAI | 117.87 | 117.19 | 65.01 | 100
381 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAWA KHOLA TO RELLI , SM/09610 | New | Material Requisition To Resource Division | 644/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.69 | 0 | 0 | 0
382 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWSS SCHEME FROM SISNEY KHOLA TO UPPER AND LOWER KAMBAL & DINGALI GAON , SM/09613 | New | Piped Water Supply Scheme from Sisney Khola to Upper and Lower Kambal and Dingali Gaon in Yangmakum G.P. Block l, Kalimpong under Jal Swapno Programme within Kalimpong District | 754/NKWSMD | 28/02/2022 | 90 | MR. DAWA LAMA | 107.34 | 81.5 | 75.93 | 80
383 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWSS SCHEME FROM SISNEY KHOLA TO UPPER AND LOWER KAMBAL & DINGALI GAON , SM/09613 | New | Material Requisition To Resource Division | 1378/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.54 | 0 | 0 | 0
384 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM ARDHALI JHORA TO TINKATAREY, CHAPLATEY, BARAL, GURDAY GAON , SM/09668 | New | Material Requisition To Resource Division | 655/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.77 | 0 | 0 | 0
385 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM ARDHALI JHORA TO TINKATAREY, CHAPLATEY, BARAL, GURDAY GAON , SM/09668 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
386 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM ARDHALI JHORA TO TINKATAREY, CHAPLATEY, BARAL, GURDAY GAON , SM/09668 | New | FOREST PAYMENT | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
387 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM ARDHALI JHORA TO TINKATAREY, CHAPLATEY, BARAL, GURDAY GAON , SM/09668 | New | P.W.S SCHEME FROM ARDHALI JHORA TO TINKATAREY, CHAPLATEY, BARAL, GURDAY GAON KUMAI G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 455/NKWSMD | 14/01/2022 | 1210 | SAMSHER RAI | 177.01 | 144.58 | 51.64 | 100
388 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM ARDHALI JHORA TO TINKATAREY, CHAPLATEY, BARAL, GURDAY GAON , SM/09668 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1578/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 100 | 100
389 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR , SM/09608 | New | Material Requisition To Resource Division | 835/NKWSMD | 21/03/2022 | 0 | Resource Division | 2.46 | 0 | 0 | 0
390 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR , SM/09608 | New | P.W.S SCHEME FROM AMBOIK KHOLA (PARBALAKHA) TO GORUBATHAN TAR IN DALIM G.P. GORUBATHAN BLOCK UNDER JAL SWAPNO PROGRAMME WITHIN DISTRICT- KALIMPONG. | 624/NKWSMD | 21/02/2022 | 150 | M/S. ASHOK KUMAR PERIWAL | 356.75 | 266.87 | 74.81 | 85
391 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR , SM/09608 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-321 | 25/12/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0 | 0
392 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR , SM/09608 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
393 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | "Providing Functional househol d Tap connection under JJM &JSP Programme for Dws scheme from Khani Khola to Baidar, Karki, Basnet, Lusuney& Sansari Dara Gaon" | BP-2022-23-3 | 11/04/2022 | 0 | SANTOSH TAMANG | 14.01 | 0 | 0 | 0
394 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme for Pws scheme from Mai teraj Jhora to Upper Gairi gaon Bhalukhop GP | BP-2022-23-10 | 11/04/2022 | 0 | GABAC AND COMPANY | 11.97 | 0 | 0 | 0
395 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | Prnviding Functional house hold Tap connection under JJM & JSP Programmne Pws sc heme from Kafal dhara And aheri Jhora to SinJee Bazar } Samaibong GP | BP-2022-23-2 | 11/04/2022 | 0 | SANTOSH TAMANG | 18.15 | 0 | 0 | 0
396 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | Providing Functional. household Tap connection under JJM & JSP Programme for Dws scheme from Badiya Dhara to Dara Gaon Bhalukhop GP | BP-2022-23-55 | 18/05/2022 | 0 | GABAC AND COMPANY | 12.44 | 0 | 0 | 0
397 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | providin g Functional hou sehold Tap connection under J.JM &. JSP Pro gramme for Pws scheme from Kafleykhola to Gairigaon Bong GP | BP-2022-23-7 | 11/04/2022 | 0 | TEKENDRA ADHIKARI | 10.64 | 0 | 0 | 0
398 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | "Pro vidin g Fun ctional household Tap connect ion under .IJM & JS P Pro gramm e for Dw s scheme by Pumping for Chaikaar, Bha nga and Mongpong Fv Pabringtar GP" | BP-2022-23-87 | 30/06/2022 | 0 | ANAND KUMAR LAKHOTIA | 14.91 | 0 | 0 | 0
399 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | "Providing Functional househo ld Tap co nnection under JJM & JSP Pro gramm e for Dws scheme fr om Rabling Khola to Munt hung Busty Ka ffer Kankebong GP" | BP-2022-23-9 | 11/04/2022 | 0 | SANGAM GURUNG | 10.89 | 0 | 0 | 0
400 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | Pro viding Functional househo ld Tap connection under JJM & JSP Prow amm e Dws sch eme from Reank Khola to Pembling Khare Gaon Nimbong GP | BP-2022-23-11 | 11/04/2022 | 0 | SANGAM GURUNG | 8.51 | 0 | 0 | 0
401 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme for Dws scheme from Jurant , Khola to Middle& Lowe r Chuimkhim Pabringtar | BP-2022-23-56 | 20/05/2022 | 0 | DILIP CHHETRI ACHARYA | 13.44 | 0 | 0 | 0
402 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | Providing Functional household Tap connectionunder JJM & JSP Prog ramme Pws sche me from Sarki dhara to Yok Primtam Acha rya Subba Gaon Seokbir GP | BP-2022-23-6 | 11/04/2022 | 0 | SUKRAJ SUBBA | 13.95 | 0 | 0 | 0
403 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | Providing Fun ct ional h ou sehold Tap connection under JJM & JSP Pro gramme for Dws scheme fr om Bhalu Khola to Lower New ar Gaon Bhalukhop GP | BP-2022-23-8 | 11/04/2022 | 0 | SUPER SAJAN CONSTRUCTION | 17.16 | 0 | 0 | 0
404 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | Pr oviding Fu n ctional h ousehold Tap connection und er JJM & JSP Programm e Dws sch eme from Sangbir Jhora to Barbot Pab ringt ar GP | BP-2022-23-42 | 06/05/2022 | 0 | SITA SHARMA | 18 | 0 | 0 | 0
405 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | Addition Estimate for the FHTC under JJM Programme 8 nos existing schemes to be provided with FHTC under Kalimpong Block-II in the district of Kalimpong, FHTC under JJM Programme 14 nos existing schemes to be provided with FHTC, FHTC under JJM Programme 10 nos existing schemes to be provided with FHTC under Block-III, Gorubathan. | 1875/NKWSMD | 14/12/2022 | 60 | YAMA CONSTRUCTIONS LLP | 62.3 | 25.97 | 100 | 100
406 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. , SM/10265 | Retrofitting | Material Requisition To Resource Division | 2599/NKWSMD | 17/02/2023 | 0 | Resource Division | 9.09 | 0 | 0 | 0
407 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM PAREN KHOLA TO RANGPO DIVISON , SM/10746 | New | PIPED WATER SUPPLY SCHEME FROM PAREN KHOLA TO RANGPO DIVISION UNDER SANGSEY G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 532/NKWSMD | 25/05/2022 | 180 | YAMA CONSTRUCTIONS LLP | 190.09 | 189.16 | 83.55 | 100
408 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM PAREN KHOLA TO RANGPO DIVISON , SM/10746 | New | Material Requisition To Resource Division | 1376/NKWSMD | 22/09/2022 | 0 | Resource Division | 1.26 | 0 | 0 | 0
409 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM SIRISE KHOLA TO ROCKY ISLAND UNDER KALIMPONG GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10700 | New | PIPED WATER SUPPLY SCHEME FROM SIRISE KHOLA TO ROCKY ISLAND UNDER GORUBATHAN BLOCK UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 491/NKWSMD | 24/05/2022 | 180 | SRINIWAS AGARWAL | 164.25 | 136.83 | 83.3 | 80
410 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM SETHI KHOLA TO UPPER KHANI UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10701 | New | Piped Water Supply Scheme from Sethi Khola to Upper Khani. | 832/NKWSMD | 30/06/2022 | 820 | SANGAM GURUNG | 104.88 | 81.26 | 77.48 | 100
411 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of Drinking water from spring water source for 12 Numbers of Gram panchayat Buildings in Kalimpong Block- I under the District of kalimpong , under Neorakhola water supply Division, kalimpong PHE Dte. , SM/11371 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for 12 Numbers of Gram Panchayat in Kalimpong Block -I under the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E. Directorate, Kalimpong. | 936/ NKWSMD | 12/07/2022 | 90 | SANTOSH TAMANG | 39.26 | 18.15 | 46.22 | 78
412 | KALIMPONG | Neorakhola W/S & Mtc.Div. | BINDU PIPED WATER SUPPLY SCHEME , SM/13622 | New | Material Requisition To Resource Division | 2600/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.07 | 0 | 0 | 0
413 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SURUK PIPED WATER SUPPLY SCHEME , SM/13607 | New | Material Requisition To Resource Division | 2620/NKWSMD | 17/02/2023 | 0 | Resource Division | 2.08 | 0 | 0 | 0
414 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SURUK PIPED WATER SUPPLY SCHEME , SM/13607 | New | Material Requisition To Resource Division | 2713/NKWSMD | 03/03/2023 | 0 | Resource Division | 2.08 | 0 | 0 | 0
415 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SURUK PIPED WATER SUPPLY SCHEME , SM/13607 | New | Water Supply Scheme For Suruk Under Jal Jeevan Mission In Gorubathan Block Under Kalimpong District, Under P.H.E Dte. | 2490/NKWSMD | 09/02/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 636.52 | 223.97 | 35.19 | 60
416 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. , SM/13613 | New | Material Requisition To Resource Division | 367/NKWSMD | 29/05/2023 | 0 | Resource Division | 1.87 | 0 | 0 | 0
417 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. , SM/13613 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
418 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. , SM/13613 | New | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER SOURCE FOR SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME, UNDER BLOCK:-GORUBATHAN. DISTRICT:-KALIMPONG, UNDER P.H.E Dte. | 358/NKWSMD | 26/05/2023 | 716 | THUPDEN BHUTIA | 348.89 | 50.41 | 14.45 | 50
419 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM THAKALEY JHORA TO VATTY DARA 3RD MILE , SM/09666 | New | Material Requisition To Resource Division | 659/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.77 | 0 | 0 | 0
420 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM THAKALEY JHORA TO VATTY DARA 3RD MILE , SM/09666 | New | Piped Water Supply Scheme from Thakalay Jhora to Vatty Dara 3rd Mile under Santook G.P. Block ll Kalimpong under Jal Swapno Programme within Kalimpong | 430/NKWSMD | 07/01/2022 | 90 | M/S. ASHOK KUMAR PERIWAL | 134.62 | 102.3 | 75.99 | 100
421 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM SAMTHARA KHOLA TO CENTRE GAON, PINTALAY GAON, GUDARA GAON, BICH GAON, CHETTRI GAON , SM/09612 | New | Piped Water Supply Scheme from Samthara Khola to Centre Gaon, Pintalay Gaon, Gudara Gaon, Bich Gaon and Chettri Gaon in Nimbong G.P. Block under Jal Swapno Programme within Kalimpong District | 749/NKWSMD | 28/02/2022 | 90 | DINESH SHERPA | 154.6 | 90.46 | 58.51 | 100
422 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. , SM/13612 | New | Material Requisition To Resource Division | 450/NKWSMD | 07/06/2023 | 0 | Resource Division | 1.5 | 0 | 0 | 0
423 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. , SM/13612 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
424 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. , SM/13612 | New | Creating Gravity Based Water Supply Scheme for Kumai Forest Under Gorubathan Block Under Kalimpong District Under P.H.E Dte. | 416/NKWSMD | 05/06/2023 | 900 | SACHIN RAI | 279.21 | 113 | 40.47 | 65
425 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. , SM/13612 | New | FOREST PAYMENT | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
426 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/16233 | New | Material Requisition To Resource Division | 768/NKWSMD | 19/07/2023 | 0 | Resource Division | 3.98 | 0 | 0 | 0
427 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/16233 | New | PROPOSED GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. | 673/NKWSMD | 12/07/2023 | 1025 | EVERSHINE CONSTRUCTION | 878.08 | 0 | 0 | 70
428 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHASMAHAL (PART) UNDER KAGAY G.P, BLOCK:KALIMPONG - II, DISTRICT:KALIMPONG , SM/15643 | New | Material Requisition To Resource Division | 2719/NKWSMD | 03/03/2023 | 0 | Resource Division | 1.04 | 0 | 0 | 0
429 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHASMAHAL (PART) UNDER KAGAY G.P, BLOCK:KALIMPONG - II, DISTRICT:KALIMPONG , SM/15643 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHAS MAHAL UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | 2653/NKWSMD | 28/02/2023 | 180 | MS. SURYA I PVT. LTD COMPANY | 283.56 | 48.06 | 16.95 | 70
430 | KALIMPONG | Neorakhola W/S & Mtc.Div. | NIM KHASMAHAL & PHASINTING KHASMAL PWSS , SM/18415 | New | Material Requisition To Resource Division | 957/NKWSMD | 21/08/2023 | 0 | Resource Division | 2.91 | 0 | 0 | 0
431 | KALIMPONG | Neorakhola W/S & Mtc.Div. | NIM KHASMAHAL & PHASINTING KHASMAL PWSS , SM/18415 | New | NIM & PHASINTING KHASMAHAL SPRING WATER SUPPLY SCHEME, UNDER BLOCK:- GORUBATHAN. DISTRICT:- KALIMPONG | 945/NKWSMD | 17/08/2023 | 730 | M/S. ASHOK KUMAR PERIWAL | 954.32 | 306.22 | 32.09 | 85
432 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Pws scheme from 7th Mile Jhora to Algarah , SM/09602 | New | Material Requisition To Resource Division | 833/NKWSMD | 21/03/2022 | 0 | Resource Division | 2.48 | 0 | 0 | 0
433 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Pws scheme from 7th Mile Jhora to Algarah , SM/09602 | New | Material Requisition To Resource Division | 1375/NKWSMD | 22/09/2022 | 0 | Resource Division | 2.77 | 0 | 0 | 0
434 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Pws scheme from 7th Mile Jhora to Algarah , SM/09602 | New | P.W.S SCHEME FROM 7TH MILE TO ALGARAH BAZAR UNDER SANTOOK G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | 622/NKWSMD | 21/02/2022 | 1050 | JUSTINE BHUTIA | 297.77 | 235.28 | 63.05 | 80
435 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAGEY KHOLA TO SAURENI , SM/09664 | New | Material Requisition To Resource Division | 641/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.33 | 0 | 0 | 0
436 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAGEY KHOLA TO SAURENI , SM/09664 | New | P.W.S SCHEME FROM CHAGAY KHOLA TO SAURENI IN AHALAY G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 421/NKWSMD | 07/01/2022 | 180 | THUPDEN BHUTIA | 133.48 | 123.84 | 40.17 | 100
437 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Detail Project Report on Extension of pipeline by way of Retrofitting of Neorakhola Piped water Scheme to provide Functional Household Tap Connection to the remaining households of en-route villages of the Scheme in Kalimpong Block I-II , under Kalimpong , SM/10512 | Retrofitting | Preparation of Presentation Slideof SAJAL GRAM Village i.c.w Jal Jeevan Mission(JJM)Programme and Video graph the Whole events of Successful Story of SAJAL GRAM at various Gram Panchayet (G.P) under Kalimpong District ; And involving of all Necessary equipments(Mike, External HDD,Projector with Screen , Flash Light for Camera along with Stands etc) and deployment of essential labour for the Work etc) for Integrated work up to the Completion of all activities in the name of IEC(Information, Education &Communication) for educate the rural inhabitants of the locality/command Area of Sajal Gram regarding importance of Potable Drinking Water & it¿s conservation in future ,Protection from theft etc in future as per Operational Guidelines of Jal Jeevan Mission (JJM) of Kalimpong District, covering tentatively39Villages at Present under Neorakhola W/S & Mtc Division, PHE Dte. | 78/AE-II /NKWSMD | 03/03/2023 | 5 | SAMRAT GHATAK | 0.98 | 0.2 | 20.51 | 50
438 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Detail Project Report on Extension of pipeline by way of Retrofitting of Neorakhola Piped water Scheme to provide Functional Household Tap Connection to the remaining households of en-route villages of the Scheme in Kalimpong Block I-II , under Kalimpong , SM/10512 | Retrofitting | Extension of pipeline by Retrofitting of Neorakhola Piped water supply scheme for providing Functional Household Tap connection (FHTC) to the remaining en-route households (P.C) in between Jhilkey Dhara and Sangsey V-Notch in Kalimpong Block I & ll ,in the District of Kalimpong , under JJM and Jalswapna programme under Neorakhola w/s & Mtc. Division P.H.E. Dte (PART C) | 139/NKWSMD | 20/04/2022 | 180 | SONAM TOPGAY BHUTIA | 162.35 | 162.49 | 100 | 100
439 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Detail Project Report on Extension of pipeline by way of Retrofitting of Neorakhola Piped water Scheme to provide Functional Household Tap Connection to the remaining households of en-route villages of the Scheme in Kalimpong Block I-II , under Kalimpong , SM/10512 | Retrofitting | Extension of pipeline by Retrofitting of Neorakhola Piped water supply scheme for providing Functional Household Tap connection (FHTC) to the remaining en-route households (P.C) in between Sangsey V-Notch and Delo Middle Lake in Kalimpong Block I ,in the District of Kalimpong , under JJM and Jalswapna programme under Neorakhola w/s & Mtc. Division P.H.E. Dte (PART -B) | 106/NKWSMD | 13/04/2022 | 180 | GETEN NAMGYAL BHUTIA | 80.78 | 80.04 | 100 | 100
440 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Detail Project Report on Extension of pipeline by way of Retrofitting of Neorakhola Piped water Scheme to provide Functional Household Tap Connection to the remaining households of en-route villages of the Scheme in Kalimpong Block I-II , under Kalimpong , SM/10512 | Retrofitting | Extension of pipeline by Retrofitting of Neorakhola Piped water supply scheme for providing Functional Household Tap connection (FHTC) to the remaining en-route households (P.C) in between Jhilkey Dhara and Sangsey V-Notch in Kalimpong Block I & ll ,in the District of Kalimpong , under JJM and Jalswapna programme under Neorakhola w/s & Mtc. Division P.H.E. Dte (PART D) | 107/NKWSMD | 13/04/2022 | 180 | DHURBA KUMAR PRADHAN | 88.12 | 72.66 | 82.45 | 90
441 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Detail Project Report on Extension of pipeline by way of Retrofitting of Neorakhola Piped water Scheme to provide Functional Household Tap Connection to the remaining households of en-route villages of the Scheme in Kalimpong Block I-II , under Kalimpong , SM/10512 | Retrofitting | Extension of pipeline by Retrofitting of Neorakhola Piped water supply scheme for providing Functional Household Tap connection (FHTC) to the remaining en-route households (P.C) in between Sangsey V-Notch and Delo Middle Lake in Kalimpong Block I ,in the District of Kalimpong , under JJM and Jalswapna programme under Neorakhola w/s & Mtc. Division P.H.E. Dte (PART -A) | 290/NKWSMD | 13/05/2022 | 240 | DHURBA KUMAR PRADHAN | 152.1 | 93.65 | 40.38 | 100
442 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Detail Project Report on Extension of pipeline by way of Retrofitting of Neorakhola Piped water Scheme to provide Functional Household Tap Connection to the remaining households of en-route villages of the Scheme in Kalimpong Block I-II , under Kalimpong , SM/10512 | Retrofitting | Additional Work for Extension of Pipeline by Way of Retrofitting of Neorakhola Piped Water Supply Scheme to Provide Functional Household Tap Connection to The Remain Household of En-Route Village Under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 599/NKWSMD | 29/04/2025 | 120 | SONAM TOPGAY BHUTIA | 18.95 | 0 | 0 | 100
443 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Kolbong Forest Village under Lava Gitbeong G.P. Kalimpong Block-II, in the District of Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. , SM/10623 | New | Creating Gravity based piped water supply scheme for Kolbong Forest village under lava Gitbeong G.P kalimpong Block -II,in the dist of Kalimpong in connection with JJM & Jal Swapna, under Neorakhola w/s & MtC Division , PHE Dte, Kalimpong | 502/NKWSMD | 25/05/2022 | 90 | BHUTIA AND SONS | 38.82 | 33.46 | 86.19 | 60
444 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM PHENTO SOURCE TO DUKA , SM/10748 | New | PIPED WATER SUPPLY SCHEME FROM PHENTO SOURCE TO DUKA UNDER KALIMPONG BLOCK-II, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 535/NKWSMD | 25/05/2022 | 1080 | SUNIL BAJLA | 155.54 | 137.75 | 88.57 | 100
445 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM KHARKHOLA TO SARDAR AND LOWER TOP LINE , SM/10749 | New | PIPED WATER SUPPLY SCHEME FROM KHARKHOLA TO SADAR AND LOWER TOP LINE UNDER KALIMPONG GORUBATHAN BLOCK, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 503/NKWSMD | 25/05/2022 | 810 | PRAYOG RAI | 102.55 | 97.81 | 83.49 | 100
446 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SEOKBIR KHASMAHAL PWSS IN KALIMPONG-1 BLOCK, UNDER KALIMPONG DISTRICT , SM/12180 | New | WATER SUPPLY SCHEME FOR SEOKBIR KHASMAHAL PWSS IN KALIMPONG-I BLOCK, UNDER KALIMPONG DISTRICT (TSM/012581) | 1528/NKWSMD | 18/10/2022 | 720 | SRINIWAS AGARWAL | 400.34 | 372.38 | 57.79 | 80
447 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/11313 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
448 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/11313 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-302 | 09/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0 | 0
449 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/11313 | New | SURFACE WATER BASED PARINGAR KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE. | 962/NKWSMD | 12/07/2022 | 590 | THUPDEN BHUTIA | 757.27 | 630.04 | 83.2 | 90
450 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/11313 | New | Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/08/2023 to 30/11/2023 | 851/NKWSMD | 28/07/2023 | 123 | THE ELECTRIC SPHERE | 0.87 | 0.39 | 100 | 90
451 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/11313 | New | (Continuation) Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024 (2 Months) | 1458/NKWSMD | 30/11/2023 | 62 | THE ELECTRIC SPHERE | 0.39 | 0.39 | 100 | 100
452 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/11313 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
453 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/11313 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1578/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 100 | 100
454 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KASHONE KHASMAHAL (PART) UNDER KASHONE G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/12630 | New | ELECTRO-MECHANICAL WORK FOR GRAVITY BASED AND PUMPING BASED P.W.S SCHEME FOR KASHONE KHASMAHAL UNDER KASHONE G.P. UNDER KALIMPONG BLOCK-II, DIST. KALIMPONG. | 1778/NKWSMD | 28/11/2022 | 60 | THE ELECTRIC SPHERE | 19.28 | 0 | 0 | 0
455 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KASHONE KHASMAHAL (PART) UNDER KASHONE G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG , SM/12630 | New | PROPOSED GRAVITY Based & Pumping Based piped water supply scheme, work includes construction of Catchment chamber. Desilting tank. RCC Tank (Main Tank and Zonal Tank) ,Laying of gravity main HDPE PIPE, distribution HDPE pipe, and construction of Switch Room , boundary wall under 5 nos of zone inside the Kashone Khasmahal under Kashone Gram Panchayat , under Kalimpong Block -II , under Kalimpong District. | 1450/NKWSMD | 29/09/2022 | 1067 | GARGO TRADERS | 869.52 | 685.16 | 49.79 | 100
456 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF Dr. GRAHAM'S HOME (PART) PIPED WATER SUPPLY SCHEME (PWSS) UNDER DR. GRAHAM'S HOME G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG , SM/11955 | New | Piped Water Supply Scheme (PWSS) under Dr. Graham's Home G.P, Kalimpong Block-I, Under Neorakhola Water Supply & Maintenance Division, PHE Dte, Kalimpong work includes construction of intake, sedimentation tank, RCC tanks of different sizes, laying of GI, HDPE pipes, boundary wall and providing FHTC. | 1652/NKWSMD | 04/11/2022 | 1813 | BASANT PRADHAN | 229.27 | 156.13 | 40.81 | 100
457 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PAREN FOREST PIPED WATER SUPPLY SCHEME , SM/13609 | New | Material Requisition To Resource Division | 756/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.31 | 0 | 0 | 0
458 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PAREN FOREST PIPED WATER SUPPLY SCHEME , SM/13609 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-302 | 09/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0 | 0
459 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PAREN FOREST PIPED WATER SUPPLY SCHEME , SM/13609 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
460 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PAREN FOREST PIPED WATER SUPPLY SCHEME , SM/13609 | New | FOREST PAYMENT | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
461 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PAREN FOREST PIPED WATER SUPPLY SCHEME , SM/13609 | New | CREATING GRAVITY BASED PROVISION OF DRINKING WATER FROM SPRING WATER SOURCE FOR PAREN FOREST VILLAGE, DHAULA (PART) UNDER PATEN GODAK GRAM PANCHAYAT UNDER GORUBATHAN BLOCK IN THE DISTRICT OF KALIMPONG UNDER NEORAKHOLA WATER SUPPLY AND MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG (SM/13609) | 711/NKWSMD | 17/07/2023 | 550 | SILAN GURUNG | 92.4 | 68.23 | 73.84 | 100
462 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 42 Numbers of school in Kalimpong Block -I under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte , SM/11358 | School | Creating gravity based Provision Of Drinking water from spring water source for 42 Numbers of school in Kalimpong Block -I under the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E. Directorate, Kalimpong | 930/NKWSMD | 12/07/2022 | 180 | GETEN NAMGYAL BHUTIA | 177.33 | 126.23 | 71.18 | 80
463 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 79 Numbers of Anganwadi Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/11364 | Anganwadi | Creating gravity based Provision Of Drinking water from spring water source for 79 Numbers of Anganwadi Centers in Kalimpong Block-II in the District of Kalimpong, under Neorakhola Water & Maintenance Supply Division, P.H.E Directorate, Kalimpong. | 932/NKWSMD | 12/07/2022 | 240 | ALLIED INSTRUMENTS | 392.81 | 386.94 | 30.55 | 0
464 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 79 Numbers of Anganwadi Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/11364 | Anganwadi | Hiring of vehicle for the office of Superintending Engineer, G.T.A-Circle, P.H. Engineering Directorate for the period of 6 (Six) months for GTA Area. Note: With effect from date of issuing work order | 2228/NKWSMD | 31/01/2023 | 180 | YAMA CONSTRUCTIONS LLP | 0.99 | 2.19 | 100 | 100
465 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong , SM/13605 | New | Preparation of draft proposal including preparation of Maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH portal for forest land diversion in 05 (five) numbers of Scheme under Jal Jeevan Mission (JJM). | 75/AE-II/NKWSMD | 28/02/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.95 | 100 | 100
466 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong , SM/13605 | New | Preparation of draft proposal including preparation of Maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH portal for forest land diversion in 05 (five) numbers of Scheme under Jal Jeevan Mission (JJM). | 74/AE-II/NKWSMD | 28/02/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.95 | 100 | 100
467 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong , SM/13605 | New | Preparation of draft proposal including preparation of Maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH portal for forest land diversion in 05 (five) numbers of Scheme under Jal Jeevan Mission (JJM). | 76/AE-II/NKWSMD | 28/02/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.95 | 100 | 100
468 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong , SM/13605 | New | Material Requisition To Resource Division | 249/NKWSMD | 12/05/2023 | 0 | Resource Division | 6.1 | 0 | 0 | 0
469 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong , SM/13605 | New | PROPOSED GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. | 181/NKWSMD | 04/05/2023 | 365 | MS. SURYA I PVT. LTD COMPANY | 393.31 | 52.69 | 13.4 | 70
470 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong , SM/13605 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-321 | 25/12/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0 | 0
471 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong , SM/13605 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
472 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER TASHIDING G.P, BLOCK-KALIMPONG-I, DISTRICT:-KALIMPONG , SM/16230 | New | Material Requisition To Resource Division | 533/NKWSMD | 13/06/2023 | 0 | Resource Division | 6.58 | 0 | 0 | 0
473 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER TASHIDING G.P, BLOCK-KALIMPONG-I, DISTRICT:-KALIMPONG , SM/16230 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG KHASMAHAL PIPED WATER SUPPLY SCHEME, UNDER TASHIDING G.P BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. | 363/NKWSMD | 29/05/2023 | 365 | YAMA CONSTRUCTIONS LLP | 896.8 | 664.52 | 74.1 | 80
474 | KALIMPONG | Neorakhola W/S & Mtc.Div. | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER TASHIDING G.P, BLOCK-KALIMPONG-I, DISTRICT:-KALIMPONG , SM/16230 | New | ADDITIONAL WORK FOR LEFT OUT HOUSEHOLD IN CONNECTION WITH TASHIDING KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER KALIMPONG BLOCK-I, DISTRICT-KALIMPONG IN CONNECTION WITH JAL JEEVAN MISSION, UNDER PHED DD-II, GTA. | 2334/NKWSMD | 17/12/2024 | 60 | YAMA CONSTRUCTIONS LLP | 16.08 | 0 | 0 | 0
475 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG , SM/15644 | New | Material Requisition To Resource Division | 246/NKWSMD | 12/05/2023 | 0 | Resource Division | 3.31 | 0 | 0 | 0
476 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG , SM/15644 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
477 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG , SM/15644 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. | 222/NKWSMD | 10/05/2023 | 1015 | SITA SHARMA | 625.46 | 0 | 0 | 50
478 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR DUNGRA KHASMAHAL (PART) UNDER DUNGRA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/18247 | New | Material Requisition To Resource Division | 773/NKWSMD | 19/07/2023 | 0 | Resource Division | 4.38 | 0 | 0 | 0
479 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR DUNGRA KHASMAHAL (PART) UNDER DUNGRA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG , SM/18247 | New | PROPOSED GRAVITY PUMPING PIPED WATER SUPPLY SCHEME FOR DUNGRA KHASMAHAL G.P, UNDER BLOCK: KALIMPONG-I, DISTRICT: KALIMPONG. | 717/NKWSMD | 18/07/2023 | 1095 | SRINIWAS AGARWAL | 1228.4 | 0 | 0 | 60
480 | KALIMPONG | Darjeeling Division II (Kalimpong) | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON , SM/09596 | New | Hiring of vehicle (bolero) no. WB-79B-0359 of daily hire basis for the office of the Executive Engineer Kalimpong Division, PHE Department. W.E.F 01/02/2022 TO 01/02/2023 | 962/EE/DDII/PHE/GTA | 27/01/2022 | 365 | AVASH RAI | 2.15 | 3.84 | 100 | 100
481 | KALIMPONG | Darjeeling Division II (Kalimpong) | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON , SM/09596 | New | Hiring of vehicle (bolero) no. WB-74BJ-6606 of daily hire basis for the office of the Executive Engineer Kalimpong Division, PHE Department. | 963/EE/DD-II/PHE/GTA | 27/01/2022 | 365 | SARASWATI SINGH | 2.15 | 3.93 | 100 | 100
482 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON , SM/09596 | New | P.W.S SCHEME FROM DHATURAY JHORA TO DEWRALI GAON, GUMBA GAON AND BICH GAON AREA UNDER KAFFER-KANKEBONG G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | 625/NKWSMD | 21/02/2022 | 150 | SANTOSH TAMANG | 305.11 | 303.46 | 73.3 | 100
483 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON , SM/09596 | New | Material Requisition To Resource Division | 836/NKWSMD | 21/03/2022 | 0 | Resource Division | 1.76 | 0 | 0 | 0
484 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON , SM/09596 | New | Material Requisition To Resource Division | 1369/NKWSMD | 22/09/2022 | 0 | Resource Division | 1.76 | 0 | 0 | 0
485 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA , SM/09600 | New | Material Requisition To Resource Division | 636/NKWSMD | 23/02/2022 | 0 | Resource Division | 1.29 | 0 | 0 | 0
486 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA , SM/09600 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
487 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA , SM/09600 | New | Piped Water Supply Scheme from Sisney and Ankurey Jhora to Nokdara and its adjoining area under Lava- Gitbeong G.P. Block ll, Kalimpong under Jal Swapno Programme within Kalimpong District | 458/NKWSMD | 14/01/2022 | 90 | DIPESH RAI | 162.74 | 133.39 | 81.97 | 80
488 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA , SM/09600 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
489 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR , SM/09601 | New | Material Requisition To Resource Division | 647/NKWSMD | 23/02/2022 | 0 | Resource Division | 1.35 | 0 | 0 | 0
490 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR , SM/09601 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-298 | 07/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0 | 0
491 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR , SM/09601 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
492 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR , SM/09601 | New | Piped Water Supply Scheme from Chamung Khola to Gitdabling Bazar and adjoining area under Gitdabling G.P. Block ll Kalimpong under Jal Swapno Programme within Kalimpong District | 429/NKWSMD | 07/01/2022 | 1228 | SITA SHARMA | 196.23 | 168.43 | 85.83 | 100
493 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR , SM/09601 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | 1593/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 100 | 100
494 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM BICHRI DHARA TO LOWER SUNGDUNG , SM/09611 | New | Material Requisition To Resource Division | 642/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.38 | 0 | 0 | 0
495 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM BICHRI DHARA TO LOWER SUNGDUNG , SM/09611 | New | P.W.S SCHEME FROM BICHARI DHARA TO LOWER SUNDUNG UNDER PUDUNG G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 422/NKWSMD | 07/01/2022 | 1050 | SUNNY CONSTRUCTION | 78.39 | 70.48 | 89.92 | 100
496 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE , SM/09617 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
497 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE , SM/09617 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-298 | 07/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0 | 0
498 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE , SM/09617 | New | P.W.S. Scheme from Mali khola to Kasmi Forest Village under Bong G.P. Block I, Kalimpong under Jal Jeevan Mission and Jal Swapno Programme | 457/NKWSMD | 14/01/2022 | 90 | ANAND MANI PRADHAN | 90.35 | 72.35 | 56.92 | 100
499 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE , SM/09617 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
500 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme , SM/08693 | Retrofitting | Retrofitting of Neorakhola piped water supply scheme to Provide Functional House Hold Tap connection to the en-route villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme under Neorakhola Water Supply & Mtc Division under PHE Dte , Kalimpong | 167/NKWSMD | 06/09/2021 | 30 | SONAM TOPGAY BHUTIA | 49.43 | 49.08 | 100 | 90
501 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme , SM/08693 | Retrofitting | Retrofitting of Neorakhola piped water supply scheme to Provide Functional House Hold Tap connection to the en-route villages of the scheme in Kalimpong Block I in Kalimpong District under JJM & JAL SWAPNA Programme under Neorakhola Water Supply & Mtc Division under PHE Dte , Kalimpong | 166/NKWSMD | 06/09/2021 | 30 | SONAM TOPGAY BHUTIA | 48.79 | 48.32 | 100 | 90
502 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme , SM/08693 | Retrofitting | Engagement of 1(One) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the S.E. GTA, P.H.E. Dte from 01.06.2022 to 31.05.2023 | 681/NKWSMD | 31/05/2022 | 365 | THE ELECTRIC SPHERE | 2.47 | 0.39 | 66.67 | 45
503 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme , SM/08693 | Retrofitting | Engagement of 2(Two) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2022 to 31.05.2023 | 680/NKWSMD | 31/05/2022 | 12 | THE ELECTRIC SPHERE | 4.98 | 0.79 | 66.67 | 95
504 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM CHISO PANI PEEPAL DHARA TO LAMINI,RAI, DHAJEY GOAN. , SM/09544 | New | P.W.S SCHEME FROM CHISO PANI PEEPAL DHARA TO LAMINI, RAI, DHAJEY GAON UNDER BHALUKHOP G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 448/NKWSMD | 14/01/2022 | 90 | SUNIL BAJLA | 192.85 | 185.65 | 96.27 | 100
505 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM CHISO PANI PEEPAL DHARA TO LAMINI,RAI, DHAJEY GOAN. , SM/09544 | New | Material Requisition To Resource Division | 650/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.8 | 0 | 0 | 0
506 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for pemling forest under Kaffer - Kankebong G.P. Kalimpong Block-I, Dist-Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10563 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
507 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for pemling forest under Kaffer - Kankebong G.P. Kalimpong Block-I, Dist-Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. , SM/10563 | New | Material Requisition To Resource Division | 1379/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.21 | 0 | 0 | 0
508 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10694 | New | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER BLOCK-1 KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 522/NKWSMD | 25/05/2022 | 60 | SRINIWAS AGARWAL | 84.96 | 55.95 | 65.85 | 70
509 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10694 | New | Left out scheme from Nerola Jhora to Lower Ecchey Block- Kalimpong I, District Kalimpong in connection with Jal Jeevan Mission, under PHED Darjeeling Division-II GTA. | 453/NKWSMD | 02/04/2025 | 60 | DIPENDRA CHETTRI | 8.12 | 0 | 0 | 0
510 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for BIRIK FOREST VILLAGE under G.P. Kalimpong Block-I, District- Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. , SM/10575 | New | Creating Gravity based piped water supply scheme for Birik Forest Village under Teesta G.P kalimpong Block -I,District- Kalimpong in Copnnection with JJM & Jal Swapna, under Neorakhola w/s & MtC Division , PHE Dte, Kalimpong | 574/NKWSMD | 26/05/2022 | 90 | HEMANT MOKTAN | 43.83 | 28.68 | 65.43 | 90
511 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for BIRIK FOREST VILLAGE under G.P. Kalimpong Block-I, District- Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. , SM/10575 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
512 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for BIRIK FOREST VILLAGE under G.P. Kalimpong Block-I, District- Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. , SM/10575 | New | Material Requisition To Resource Division | 1372/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.26 | 0 | 0 | 0
513 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM DORKHOLA TO LUNGSEL UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME , SM/10698 | New | PIPED WATER SUPPLY SCHEME FROM DORKHOLA TO LUNGSEL UNDER KALIMPONG GORUBATHAN BLOCK UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 527/NKWSMD | 25/05/2022 | 180 | SRINIWAS AGARWAL | 197.08 | 186.41 | 74 | 98
514 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM BANGLA JHORA TO JOGITAR , SM/10750 | New | PIPED WATER SUPPLY SCHEME FROM BANGLA JHORA TO JOGITAR UNDER GORUBATHAN BLOCK KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 523/NKWSMD | 25/05/2022 | 810 | M/S R.S. CONSTRUCTION | 48.43 | 12.32 | 25.44 | 100
515 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM BANGLA JHORA TO JOGITAR , SM/10750 | New | Leftout Scheme Proposed Pumping Based Water Supply Scheme for BANGLA JHORA TO JOGITAR, Gorubathan Block in the District of Kalimpong in connection with Jal Jeean Mission, under PHED Darjeeling Division-II GTA. | 459/NKWSMD | 03/04/2025 | 60 | SATEN LAMA | 12.78 | 0 | 0 | 0
516 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. , SM/11577 | New | SEPKHOLA PIPED WATER SUPPLY SCHEME UNDER MAZEOK FOREST VILLAGE, SAMTHAR G.P, Kalimpong Block-I, Under Neorakhola Water Supply & Maintainance Division, PHE Dte, Kalimpong. | 1444/NKWSMD | 28/09/2022 | 270 | D AND B GRACE | 40.88 | 18.08 | 44.24 | 95
517 | KALIMPONG | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. , SM/11577 | New | Leftout Estimate for Piped Water Supply Scheme from under Mezeko Forest, Samthar G.P, Block:-Kalimpong-I P.S:- Kalimpong District:Kalimpong. | 2329/NKWSMD | 17/12/2024 | 60 | D AND B GRACE | 5.88 | 0 | 0 | 0
518 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Rongo Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply Division ,Kalimpong PHE Dte(Part1) | 619/NKWSMD | 26/05/2022 | 30 | BINOD TAMANG | 1.45 | 0.67 | 100 | 0
519 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Gorubathan I Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply Division ,Kalimpong PHE Dte | 621/NKWSMD | 26/05/2022 | 30 | TOPGAY BHUTIA | 3.84 | 2.39 | 100 | 0
520 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Rongo Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply Division ,Kalimpong PHE Dte(Part2) | 618/NKWSMD | 26/05/2022 | 30 | DORJEE SHERPA | 4.76 | 4.33 | 100 | 0
521 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Kumai Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Supply Division, Kalimpong PHE Dte | 620/NKWSMD | 26/05/2022 | 30 | DORJEE SHERPA | 4.85 | 4.52 | 100 | 0
522 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Samsing Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola Water Supply & Maintenance Division, PHE Dte, Kalimpong | 617/NKWSMD | 26/05/2022 | 30 | BINOD TAMANG | 3.72 | 2.69 | 100 | 0
523 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Placement of 1 nos of site inspection vehicle at the disposal of SE-GTA Circle for inspection of JJM works (for the month of Nov 22 ) | BP-2023-24-112 | 17/07/2023 | 0 | ORCHID TRAVELS | 0.4 | 0 | 0 | 0
524 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Placement of 1 nos of site inspection vehicle at the disposal of SE-GTA Circle for inspection of JJM works (for the month of DEC 22 ) | BP-2023-24-113 | 17/07/2023 | 0 | ORCHID TRAVELS | 0.4 | 0 | 0 | 0
525 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | STATIONARY BILL FOR JJM | BP-2023-24-191, | 26/09/2023 | 0 | WEST BENGAL GENERAL SERVICE CO-OPERATIVE SOCIETY LTD. | 3.3 | 0 | 0 | 0
526 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Placement of 1 nos of site inspection vehicle at the disposal of SE-GTA Circle for inspection of JJM works (for the month of JAN-23) | BP-2023-24-114 | 17/07/2023 | 0 | ORCHID TRAVELS | 0.4 | 0 | 0 | 0
527 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Ahalay Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply Division ,Kalimpong PHE Dte | 622/ NKWSMD | 26/05/2022 | 30 | DORJEE SHERPA | 4.38 | 2.54 | 45.03 | 100
528 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Dalim Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Supply Division, Kalimpong PHE Dte | 623/ NKWSMD | 26/05/2022 | 30 | BINOD TAMANG | 3.7 | 3.09 | 100 | 100
529 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for the period of 6 (Six) months. Note: With effect from date of issuing work order. | 2899/NKWSMD | 31/03/2023 | 183 | S S CONSTRUCTIONS | 0.99 | 2.3 | 100 | 80
530 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | STATIONARY BILL FOR JJM |  | 08/01/2024 | 0 | WEST BENGAL GENERAL SERVICE CO-OPERATIVE SOCIETY LTD. | 0.96 | 0 | 0 | 0
531 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | STATIONARY BILL FOR JJM |  | 08/01/2024 | 0 | WEST BENGAL GENERAL SERVICE CO-OPERATIVE SOCIETY LTD. | 0.32 | 0 | 0 | 0
532 | KALIMPONG | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. , SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | STATIONARY BILL FOR JJM |  | 08/01/2024 | 0 | WEST BENGAL GENERAL SERVICE CO-OPERATIVE SOCIETY LTD. | 0.81 | 0 | 0 | 0
533 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Mayrong Forest & Tendrabong Village ( Partly) Piped Water Supply Scheme (PWSS) under Sakyong G.P, Block- Kalimpong-II, P.S- Kalimpong, District: Kalimpong. , SM/11806 | New | new connection | BP-2023-24-5 | 25/04/2023 | 0 | WBSEDCL | 0.44 | 0 | 0 | 0
534 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Mayrong Forest & Tendrabong Village ( Partly) Piped Water Supply Scheme (PWSS) under Sakyong G.P, Block- Kalimpong-II, P.S- Kalimpong, District: Kalimpong. , SM/11806 | New | Piped Water Supply Scheme for Mayrong Forest & Tendrabong Village (Partly) under Sakyong G.P, Block- Kalimpong-II, under Neorakhola Water Supply & Maintenence Division, P.H.Engineering Directorate, District-Kalimpong. | 1155/NKWSMD | 12/08/2022 | 180 | JUSTINE BHUTIA | 186.36 | 138.04 | 74.07 | 75
535 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG , SM/15463 | New | Material Requisition To Resource Division | 2774/NKWSMD | 10/03/2023 | 0 | Resource Division | 1.02 | 0 | 0 | 0
536 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG , SM/15463 | New | Material Requisition To Resource Division | 2709/NKWSMD | 03/03/2023 | 0 | Resource Division | 1.02 | 0 | 0 | 0
537 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG , SM/15463 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG | 2660/NKWSMD | 28/02/2023 | 480 | THUPDEN BHUTIA | 200.56 | 174.65 | 95.3 | 97
538 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GORUBATHAN-I PWSS , SM/14172 | New | Material Requisition To Resource Division | 772/NKWSMD | 19/07/2023 | 0 | Resource Division | 11.19 | 0 | 0 | 0
539 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GORUBATHAN-I PWSS , SM/14172 | New | GORUBATHAN KHASMAHAL PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME, UNDER BLOCK:- GORUBATHAN. DISTRICT:- KALIMPONG. | 716/NKWSMD | 18/07/2023 | 365 | M/S R.S. CONSTRUCTION | 1121.37 | 0 | 0 | 15
540 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SANTUK KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG , SM/14191 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
541 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SANTUK KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG , SM/14191 | New | FOREST PAYMENT | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
542 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SANTUK KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG , SM/14191 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR SANTUK KHASMAHAL UNDER BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | 2492/NKWSMD | 09/02/2023 | 665 | JUSTINE BHUTIA | 676.59 | 442.98 | 65.47 | 92
543 | KALIMPONG | Neorakhola W/S & Mtc.Div. | SANTUK KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG , SM/14191 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1578/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 100 | 100
544 | KALIMPONG | Neorakhola W/S & Mtc.Div. | LINGSAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER BLOCK: KALIMPONG-II, DISTRICT:-KALIMPONG , SM/16511 | New | Material Requisition To Resource Division | 448/NKWSMD | 07/06/2023 | 0 | Resource Division | 6.24 | 0 | 0 | 0
545 | KALIMPONG | Neorakhola W/S & Mtc.Div. | LINGSAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER BLOCK: KALIMPONG-II, DISTRICT:-KALIMPONG , SM/16511 | New | PROPOSED LINGSAY KHASMAHAL PIPED WATER SUPPLY SCHEME, UNDER KALIMPONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. | 412/NKWSMD | 05/06/2023 | 910 | M/S. ASHOK KUMAR PERIWAL | 926.38 | 272.24 | 29.39 | 80
546 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPOO FOREST UNDER SANGASEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG , SM/16513 | New | Material Requisition To Resource Division | 206/NKWSMD | 10/05/2023 | 0 | Resource Division | 2.27 | 0 | 0 | 0
547 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPOO FOREST UNDER SANGASEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG , SM/16513 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
548 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPOO FOREST UNDER SANGASEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG , SM/16513 | New | FOREST PAYMENT | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
549 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPOO FOREST UNDER SANGASEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG , SM/16513 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPO FOREST PIPED WATER SUPPLY SCHEME, UNDER SANGASEY G.P BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | 97/NKWSMD | 28/04/2023 | 752 | SANTOSH TAMANG | 259.19 | 85.97 | 24.97 | 90
550 | KALIMPONG | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPOO FOREST UNDER SANGASEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG , SM/16513 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | 1593/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 100 | 100
551 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Tashiding forest Village under Tashiding GP in Kalimpong Block I in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte., Kalimpong. , SM/10600 | New | Material Requisition To Resource Division | 1554/NKWSMD | 19/10/2022 | 0 | Resource Division | 0.08 | 0 | 0 | 0
552 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Tashiding forest Village under Tashiding GP in Kalimpong Block I in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte., Kalimpong. , SM/10600 | New | Creating gravity based Provision Of Drinking water from spring water source Tashiding forest village under Tashiding Gram Panchayat under Kalimpong Block-I in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | 572/NKWSMD | 26/05/2022 | 267 | SONAM TSHERING LEPCHA | 10.2 | 0 | 0 | 75
553 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/10635 | New | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | 830/NKWSMD | 30/06/2022 | 810 | SANTOSH TAMANG | 127.14 | 119.03 | 93.62 | 95
554 | KALIMPONG | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. , SM/10635 | New | Additional Work for Proposed Surface Water Based Yakprintam Khasmahal (Part) Piped Water Supply Scheme to accommodate Functional Household Tap Connection (FHTC) in Kalimpong-I, Block within Kalimpong District under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate. | 1325/NKWSMD | 29/07/2024 | 180 | RELLI PALA CONSTRUCTION | 20.76 | 0 | 0 | 100
555 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-I , SM/18442 | Augmentation | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir / Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-II under Neorakhola Water Supply Scheme. | 1501/NKWSMD | 06/12/2023 | 725 | TAJ CONSTRUCTION | 3802.55 | 472.55 | 12.43 | 25
556 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-I , SM/18442 | Augmentation | Submission of Topo Survey report, Design and Drawing of all components of the whole project including final as built drawing after being vetted by the recognised Government Institute and getting necessary approval from the Expert Committee for Augmentation of source Cum creation of spring water storage of 80ml water for improvement of and upgradation of open ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I, & Kalimpong Block-II, under Neorakhola Water Supply Scheme. | 2230/NKWSMD | 09/12/2024 | 30 | THUPDEN BHUTIA | 28.69 | 0 | 0 | 100
557 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-I , SM/18442 | Augmentation | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/10/2024 TO 31/12/2024 (3 MONTHS). | 1924/NKWSMD | 30/09/2024 | 92 | NIM TSHERING LEPCHA | 6.36 | 0 | 0 | 100
558 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Upper Tanek piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 371/NKWSMD | 31/12/2021 | 30 | LEMNISCATE | 4.29 | 0 | 0 | 0
559 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Seokbir Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 370/NKWSMD | 31/12/2021 | 30 | LEMNISCATE | 4.64 | 0 | 0 | 0
560 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Upper Echhay piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 948/NKWSMD | 31/03/2022 | 30 | A3D A CIVIL ENGINEERING CONSULTANCY | 4.47 | 0 | 0 | 0
561 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Kaffir Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 913/NKWSMD | 31/03/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.11 | 0 | 0 | 0
562 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Mansong Chinchona Plantation piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 922/NKWSMD | 31/03/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.47 | 0 | 0 | 0
563 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Riayang Railway Station piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 357/NKWSMD | 31/12/2021 | 15 | GOUTAM KUMAR BHADURI | 3.5 | 3.08 | 100 | 0
564 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Riyong Forest piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 358/NKWSMD | 31/12/2021 | 15 | GOUTAM KUMAR BHADURI | 3.42 | 2.77 | 100 | 0
565 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village :Suntalay Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 359/NKWSMD | 31/12/2021 | 15 | A3D A CIVIL ENGINEERING CONSULTANCY | 3.93 | 2.8 | 100 | 0
566 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Pudung Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 361/NKWSMD | 31/12/2021 | 30 | M/S R. DUTTA & CO. | 4.64 | 4.64 | 100 | 100
567 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Paringar Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 362/NKWSMD | 31/12/2021 | 30 | M/S R. DUTTA & CO. | 4.61 | 4.61 | 100 | 0
568 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Nobgaon Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 363/NKWSMD | 31/12/2021 | 30 | LEMNISCATE | 4.43 | 4.43 | 100 | 0
569 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Pemling Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 364/NKWSMD | 31/12/2021 | 30 | M/S R. DUTTA & CO. | 4.4 | 4.4 | 100 | 100
570 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Nimbong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 365/NKWSMD | 31/12/2021 | 30 | M/S R. DUTTA & CO. | 4.9 | 4.9 | 100 | 0
571 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Kankaebong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 366/NKWSMD | 31/12/2021 | 30 | LEMNISCATE | 4.14 | 4.14 | 100 | 0
572 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Chunabhatti Bazar D.I.F & Lish Forest piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 355/NKWSMD | 31/12/2021 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.64 | 3.05 | 100 | 0
573 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Samalbong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 369/NKWSMD | 31/12/2021 | 30 | LEMNISCATE | 4.5 | 4.5 | 100 | 0
574 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : samethar Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 356/NKWSMD | 31/12/2021 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.78 | 3.85 | 100 | 0
575 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Rongpo Forest piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 923/NKWSMD | 31/03/2022 | 30 | INDRANIL DUTTA & ASSOCIATES | 3.75 | 3.75 | 100 | 100
576 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Kalimpong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 912/NKWSMD | 31/03/2022 | 30 | LEMNISCATE | 4.79 | 4.79 | 100 | 100
577 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Yokprintam Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 941/ NKWSMD | 31/03/2022 | 30 | INDRANIL DUTTA & ASSOCIATES | 3.39 | 3.39 | 100 | 100
578 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Slokbhir Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 939/NKWSMD | 31/03/2022 | 30 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 3.4 | 3.4 | 100 | 0
579 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Suruk Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 940/NKWSMD | 31/03/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 3.75 | 3.75 | 50 | 0
580 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Mazeok Forest piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 938/NKWSMD | 31/03/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.54 | 2.91 | 50 | 0
581 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features,Preparation of piped network & design of pipe network &Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED in Upper & Lower Pochak, Majong Dara in GItdabling GP under Block-Kalimpong-I Kalimpong District under Neorakhola water Supply & Maintenance Division PHE Dte. | 284/NKWSMD | 23/11/2021 | 30 | CIVIL ENGINEERING CONSULTANCY | 2.3 | 2.29 | 100 | 0
582 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Singi Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 937/NKWSMD | 31/03/2022 | 30 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 3.4 | 3.4 | 100 | 0
583 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Sangser Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 949/NKWSMD | 31/03/2022 | 30 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 4.58 | 4.58 | 100 | 0
584 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Icha Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 935/NKWSMD | 31/03/2022 | 30 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 4.48 | 4.48 | 100 | 0
585 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features,Preparation of piped network & design of pipe network &Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED in Purba Kabigaon & Deurali(GP- Shamthar) , Tamyang(Part)(GP-Parbintar) in Block-Kalimpong-I Kalimpong District under Neorakhola water Supply & Maintenance Division PHE Dte. | 283/NKWSMD | 31/03/2022 | 30 | GOUTAM KUMAR BHADURI | 2.3 | 2.29 | 50 | 0
586 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Ladam piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 916/NKWSMD | 31/03/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 3.75 | 3.75 | 100 | 0
587 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Lava- Gitbeong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 918/NKWSMD | 31/03/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.11 | 4.11 | 100 | 0
588 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Palla Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 919/NKWSMD | 31/03/2022 | 30 | A3D A CIVIL ENGINEERING CONSULTANCY | 3.75 | 3.27 | 100 | 0
589 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Git Dubling Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 928/NKWSMD | 31/03/2022 | 30 | GOUTAM KUMAR BHADURI | 4.47 | 4.47 | 100 | 0
590 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Kashone Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 917/NKWSMD | 31/03/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.65 | 4.65 | 50 | 0
591 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Homes St. and Graihms piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 933/NKWSMD | 31/03/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.54 | 4.3 | 50 | 0
592 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village :LAVA FOREST Village piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 22/AE-II/NKWSMD | 02/09/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.76 | 3.85 | 100 | 0
593 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD¿GIS drawing incl. preparation of project Report for Village :DUNGRA KHASMAHAL Village piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 23/AE-II/NKWSMD | 02/09/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.65 | 4.65 | 100 | 0
594 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD¿GIS drawing incl. preparation of project Report for Village :Upper Rubek piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 21/AE-II/NKWSMD | 02/09/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.58 | 3.47 | 100 | 0
595 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD¿GIS drawing incl. preparation of project Report for Village:TARZUM FOREST Village piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 24/AE-II/NKWSMD | 02/09/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.07 | 3.68 | 100 | 0
596 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD¿GIS drawing incl. preparation of project Report for Village::PANKHASARI KHASMAHAL(PART) Village piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 25/AE-II/NKWSMD | 02/09/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 3.43 | 3.43 | 100 | 0
597 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing including preparation of project Report for Village: Kalimpong Dansong Forest Piped Water Supply Scheme as per latest Jal Jeevan Mission and WBPHED Norms under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, District-Kalimpong. | 01/NKWSMD | 01/04/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 3.39 | 3.39 | 100 | 0
598 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing including preparation of project Report for Village: Kalimpong Rambi Bazar DIF Piped Water Supply Scheme as per latest Jal Jeevan Mission and WBPHED Norms under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, District-Kalimpong. | 11/NKWSMD | 04/04/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.54 | 3.51 | 100 | 0
599 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing including preparation of project Report for Village: Kalimpong Teesta Bazar DIF Piped Water Supply Scheme as per latest Jal Jeevan Mission and WBPHED Norms under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, District-Kalimpong. | 64/NKWSMD | 11/04/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.54 | 4.54 | 100 | 0
600 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Mayrong piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 360/NKWSMD | 31/12/2021 | 15 | CIVIL ENGINEERING CONSULTANCY | 3.35 | 3.35 | 100 | 0
601 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Bong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 367/NKWSMD | 31/12/2021 | 30 | LEMNISCATE | 4.57 | 4.57 | 100 | 100
602 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Pedong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 920/NKWSMD | 31/03/2022 | 30 | CIVIL ENGINEERING CONSULTANCY | 4.47 | 4.47 | 50 | 0
603 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village :Yang Makum Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 372/NKWSMD | 31/12/2021 | 30 | LEMNISCATE | 4.68 | 0 | 0 | 100
604 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Dalapchand Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 373/NKWSMD | 31/12/2021 | 30 | LEMNISCATE | 4.5 | 0 | 0 | 100
605 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Lingsaykha Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 374/NKWSMD | 31/12/2021 | 30 | LEMNISCATE | 4.57 | 0 | 0 | 100
606 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Lingsay Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 375/NKWSMD | 31/12/2021 | 30 | ROY CHOWDHURY ASSOCIATES | 4.75 | 0 | 0 | 100
607 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : sakiyong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 378/NKWSMD | 31/12/2021 | 30 | ROY CHOWDHURY ASSOCIATES | 4.82 | 0 | 0 | 100
608 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Lolay Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 376/NKWSMD | 31/12/2021 | 30 | ROY CHOWDHURY ASSOCIATES | 4.21 | 0 | 0 | 100
609 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : paiyong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 377/NKWSMD | 31/12/2021 | 30 | ROY CHOWDHURY ASSOCIATES | 4.97 | 0 | 0 | 100
610 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village :Santuk Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 379/NKWSMD | 31/12/2021 | 30 | ROY CHOWDHURY ASSOCIATES | 4.79 | 0 | 0 | 100
611 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Kagay Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 915/NKWSMD | 31/03/2022 | 30 | INDRANIL DUTTA & ASSOCIATES | 3.75 | 0 | 0 | 100
612 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Mong Pong Forest piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 914/NKWSMD | 31/03/2022 | 30 | LEMNISCATE | 3.39 | 0 | 0 | 100
613 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Mangwa Forest piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 945/ NKWSMD | 31/03/2022 | 30 | INDRANIL DUTTA & ASSOCIATES | 3.21 | 0 | 0 | 100
614 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Singibong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 942/NKWSMD | 31/03/2022 | 30 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 0 | 0 | 100
615 | KALIMPONG | Resource | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. | 1997/RS | 03/11/2021 | 180 | NABCONS PRIVATE LIMITED | 5500 | 17.28 | 100 | 80
616 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W , SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Bhalukhop Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | 368/NKWSMD | 31/12/2021 | 30 | LEMNISCATE | 4.93 | 0 | 0 | 100
617 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Supply Delivery and Installation of Computer & peripherals for official use under office of the Superintending Engineer, G.T.A Circle, P.H.E Dte. and Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. , SM/10513 | Support-MIS | supply of Multi-Function Monochrome Laser Printer |  | 18/07/2022 | 0 | IONET | 1.8 | 0 | 0 | 0
618 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Supply Delivery and Installation of Computer & peripherals for official use under office of the Superintending Engineer, G.T.A Circle, P.H.E Dte. and Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. , SM/10513 | Support-MIS | HP Desktop M01-F2237in PC |  | 18/07/2022 | 0 | IONET | 8.22 | 0 | 0 | 0
619 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Supply Delivery and Installation of Computer & peripherals for official use under office of the Superintending Engineer, G.T.A Circle, P.H.E Dte. and Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. , SM/10513 | Support-MIS | HP Desktop M01-F2237in PC | BP-2022-23-95 | 29/07/2022 | 0 | IONET | 8.22 | 0 | 0 | 0
620 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Supply Delivery and Installation of Computer & peripherals for official use under office of the Superintending Engineer, G.T.A Circle, P.H.E Dte. and Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. , SM/10513 | Support-MIS | Brother DCP-B7500D Multi-Function Monochrome Laser Printer | BP-2022-23-94 | 29/07/2022 | 0 | IONET | 1.8 | 0 | 0 | 0
621 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Supply Delivery and Installation of Computer & peripherals for official use under office of the Superintending Engineer, G.T.A Circle, P.H.E Dte. and Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. , SM/10513 | Support-MIS | "Canon Multifunction Machines Mfm, On Site OEM Warranty 3 Year " | BP-2022-23-96 | 29/07/2022 | 0 | IONET | 2.61 | 0 | 0 | 0
622 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Supply Delivery and Installation of Computer & peripherals for official use under office of the Superintending Engineer, G.T.A Circle, P.H.E Dte. and Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. , SM/10513 | Support-MIS | supply of Canon Multifunction Machines Mfm, On Site OEM |  | 18/07/2022 | 0 | IONET | 2.61 | 0 | 0 | 0
623 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Collection of Water Samples from different drinking water sources, tanks and reservoir etc. under Kalimpong district and submitting the same to the respective water testing laboratories (Neorakhola sub-district laboratory and Algarah sub-district laborato , SM/15669 | Support-WQMSP | COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG. | 2729/NKWSMD | 03/03/2023 | 366 | NIM TSHERING LEPCHA | 25.49 | 19.52 | 76.6 | 60
624 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Darjeeling Division-II, PHE-GTA, Kalimpong. , SM/13680 | Support-MIS | SUPPLY FOR hp Intel Core i5 11500 16 GB/1000 GB HDD/ Windows 10 Professional | BP-2023-24-32 | 10/05/2023 | 0 | IONET | 4.41 | 0 | 0 | 0
625 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Darjeeling Division-II, PHE-GTA, Kalimpong. , SM/13680 | Support-MIS | SUPPLY FOR Canon Multifunction Machines Mfm, On Site OEM Warranty 3 Year | BP-2023-24-33 | 10/05/2023 | 0 | IONET | 1.24 | 0 | 0 | 0
626 | KALIMPONG | Neorakhola W/S & Mtc.Div. | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Darjeeling Division-II, PHE-GTA, Kalimpong. , SM/13680 | Support-MIS | SUPPLY FOR brother Multifunction Machines Mfm, On Site OEM Warranty 3 Year | BP-2023-24-34 | 10/05/2023 | 0 | IONET | 0.35 | 0 | 0 | 0
Total | [9 empty] | 72894.37 | 31700.01 | 43.49