## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. , SM/06834 | Retrofitting | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443460 | 26/03/2021 | 0 | PAPPU SHAW | 0.2 | 0 | 0 | 0
2 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. , SM/06834 | Retrofitting | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443460 | 26/03/2021 | 0 | KOUSHIK PAL | 0.26 | 0 | 0 | 0
3 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. , SM/06834 | Retrofitting | DATA ENTRY FOR FHTC | 844389 | 13/09/2021 | 0 | PARTHA PRATIM PAL | 0.04 | 0 | 0 | 0
4 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. , SM/06834 | Retrofitting | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443460 | 26/03/2021 | 0 | SANDIP BISWAS | 0.16 | 0 | 0 | 0
5 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. , SM/06834 | Retrofitting | DATA ENTRY FOR FHTC | 844389 | 13/09/2021 | 0 | GANESH CH NANDY | 0.02 | 0 | 0 | 0
6 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. , SM/06834 | Retrofitting | DATA ENTRY FOR FHTC | 844389 | 13/09/2021 | 0 | SOVANDEB MANNA | 0.02 | 0 | 0 | 0
7 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. , SM/06834 | Retrofitting | DATA ENTRY FOR FHTC | 844389 | 13/09/2021 | 0 | TANMOY BERA | 0.08 | 0 | 0 | 0
8 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. , SM/06834 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barasukjora(zone-I)PWSS | 84438 | 02/08/2021 | 0 | ASIS KUMAR SARANGI | 6.18 | 0 | 0 | 0
9 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. , SM/06834 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) PWSS of Binpur-II Block under Jhargram Division, PHE Dte. | 844340 | 09/03/2022 | 0 | ASIS KUMAR SARANGI | 7.15 | 0 | 0 | 0
10 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. , SM/06834 | Retrofitting | INSTALLATION OF FHTCs FOR LAFT OUT HOUSEHOLD AT MOUZA METALDIHI UNDER BARASUKJORA W/S SCHEME (ZONE-1) WITHIN BINPUR-II DEVELOPMENT BLOCK UNDER JHARGRAM DIVISION, PHE DTE. | 1076/JSD | 27/11/2024 | 14 | SAIKAT DANDAPAT | 0.71 | 0 | 0 | 0
11 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. , SM/06834 | Retrofitting | INSTALLATION OF FHTCs FOR LAFT OUT HOUSEHOLD AT MOUZAS BARASUKJORA, CHHOTOKHARPAL & BARAKHARPAL UNDER BARASUKJORA W/S SCHEME (ZONE-I) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE | 1077/JSD | 27/11/2024 | 14 | SAIKAT DANDAPAT | 0.77 | 0 | 0 | 0
12 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At NAYAGRAM NO-07 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_17_38) | 222/JHD | 16/02/2023 | 30 | GAUTAM SENAPATI | 11.47 | 0 | 0 | 0
13 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At ARRHA NO-11 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_27_38) | 204/JHD | 10/02/2023 | 45 | DHUMKETU ENGINEERING PRIVATE LIMITED | 32.68 | 0 | 0 | 0
14 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_36_38) | 164/GPSD | 20/01/2023 | 30 | KOUSIK PATRA | 3.15 | 0 | 0 | 0
15 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At MALAM NO-04 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_12_38) | 155/GPSD | 20/01/2023 | 30 | TAPAS PAL | 4.04 | 0 | 0 | 0
16 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BARA NEGUI NO-05 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_14_38) | 156/GPSD | 20/01/2023 | 30 | M/S. R.K.TRADERS | 3.96 | 0 | 0 | 0
17 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BARA KHAKRI NO-03 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_8_38) | 152/GPSD | 20/01/2023 | 30 | IMRAN KHAN | 4.52 | 0 | 0 | 0
18 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At MALAM NO-04 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_10_38) | 153/GPSD | 20/01/2023 | 30 | S.R. ENTERPRISE | 4.02 | 0 | 0 | 0
19 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At JAMIRAPAL NO-08 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_19_38) | 434/JHD | 22/03/2023 | 45 | TAPAN KUMAR UPADHYAY | 15.16 | 0 | 0 | 0
20 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_37_38) | 165/GPSD | 20/01/2023 | 30 | SOURAV MASANTA | 3.16 | 0 | 0 | 100
21 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHANDABILA GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_3_38) | 146/JHD | 03/02/2023 | 30 | ENVOTECH INFRA SOLUTION | 12.11 | 0 | 0 | 0
22 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At JAMIRAPAL NO-08 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_20_38) v | 157/GPSD | 20/01/2023 | 30 | KOUSIK MUKHERJEE | 3.06 | 0 | 0 | 100
23 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_38_38) | 223/JHD | 16/02/2023 | 45 | BRAJENDRANATH SENAPATI | 25.55 | 0 | 0 | 100
24 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At MALAM NO-04 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_11_38) | 154/GPSD | 20/01/2023 | 30 | BRAJENDRANATH SENAPATI | 4 | 0 | 0 | 100
25 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_33_38) | 161/GPSD | 20/01/2023 | 30 | DEBDATTA MANNA | 3 | 0 | 0 | 0
26 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_34_38) | 162/GPSD | 20/01/2023 | 30 | ASHIS SHEE | 3.14 | 0 | 0 | 0
27 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHANDABILA GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_2_38) | 267/JHD | 21/02/2023 | 30 | TAPAS KUMAR JANA | 12.1 | 0 | 0 | 100
28 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHANDABILA GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_5_38) | 151/GPSD | 20/01/2023 | 30 | MAA LAXMI ENTERPRISE | 3.13 | 0 | 0 | 100
29 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for AnganwadiCenters At BALIGERIANO-10 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_25_38) | 213/JHD | 15/02/2023 | 45 | PROVAT KUMAR DE | 20.48 | 0 | 0 | 100
30 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for AnganwadiCentersAt CHANDABILA GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Nayagram_1_38) | 214/JHD | 15/02/2023 | 30 | BIDYUT KUMAR SANTRA | 12.97 | 0 | 0 | 100
31 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BERAJAL NO-09 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_21_38) | 345/JHD | 10/03/2023 | 45 | LALIT BIHARI MAITY | 52.61 | 0 | 0 | 100
32 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BARA KHAKRI NO-03 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_6_38) | 565/JHD | 24/04/2023 | 45 | SAI TUBE CO. | 52.05 | 0 | 0 | 80
33 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BERAJAL NO-09 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_22_38) | 853/JHD | 08/06/2023 | 30 | RITESH AGARWALL | 11.53 | 0 | 0 | 50
34 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At KHARIKAMATHANI NO-06 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_29_38) | 855/JHD | 08/06/2023 | 45 | SRIMANTA KUMAR DE | 50.58 | 0 | 0 | 100
35 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers at ARRHA No-11 GP under Nayagram block in Jhargram District under Jhargram Division PHE Dte. (Location ID: AWC_Nayagram _26_38) | 792/JHD | 31/05/2023 | 45 | PROVAT KUMAR DE | 51.49 | 0 | 0 | 66
36 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHANDRAREKHA NO-12 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_23_38) | 1112/JHD | 18/07/2023 | 45 | M/S BLUE BIRD | 20.54 | 0 | 0 | 100
37 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_31_38) | 159/GPSD | 20/01/2023 | 30 | HYDRO TECH ASSOCIATES | 4.04 | 0 | 0 | 95
38 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At NAYAGRAM NO-07 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_16_38) | 216/JHD | 15/02/2023 | 45 | ASIS KUMAR SARANGI | 31.61 | 0 | 0 | 60
39 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BARA KHAKRI NO-03 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_7_38) | 217/JHD | 15/02/2023 | 45 | ASSOCIATED ENGINEERS & TRADERS | 20.91 | 0 | 0 | 62
40 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_32_38) | 160/GPSD | 20/01/2023 | 30 | M/S SAGAR SAIKAT PARIA | 3.15 | 0 | 0 | 100
41 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_35_38) | 163/GPSD | 20/01/2023 | 30 | JULFIKAR ALI KHAN | 3.15 | 0 | 0 | 100
42 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHANDABILA GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Nayagram_4_38) | 212/JHD | 15/02/2023 | 30 | MAHAVIR SAMPARK PVT. LTD. | 11.56 | 0 | 0 | 100
43 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BALIGERIA NO-10 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_24_38) | 852/JHD | 08/06/2023 | 45 | ASIS KUMAR SARANGI | 77.99 | 0 | 0 | 65
44 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At KHARIKAMATHANI NO-06 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_30_38) | 1092/JHD | 14/07/2023 | 45 | SAI TUBE CO. | 52.7 | 0 | 0 | 100
45 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BARA NEGUI NO-05 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Nayagram_13_38) ) 3rd Call,( Ref eNIT_14 of 2022-23 2nd Call , SL No.-2 ) | 1883/JHD | 03/11/2023 | 45 | SUJOY RANJAN BHOWMICK | 53.17 | 0 | 0 | 100
46 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers 1 1 At JAMIRAPAL NO-08 GP under Nayagram Block in Jhargram District Jhargram Division PHE Dte. (LocationID: AWC_Nayagram_18_38) (Ref. eNit No._14 of 2022-23 2nd call SL-4) | 1995/JHD | 01/12/2023 | 45 | THE BUSINESS ENGINEERS INDIA | 32.29 | 0 | 0 | 100
47 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At MALAM NO-04 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Nayagram_9_38) 3rd Call, ( Ref eNIT_14 of 2022-23 2nd Call , SL No.-1 ) | 2071/JHD | 08/12/2023 | 45 | TAPAN KUMAR MANDAL | 42.47 | 0 | 0 | 100
48 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. , SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At NAYAGRAM NO-07 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Nayagram_15_38) ) 3rd Call,( Ref eNIT_14 of 2022-23 2nd Call , SL No.-3 ) | 1952/JHD | 22/11/2023 | 45 | JOY GURU TRADING | 31.6 | 0 | 0 | 70
49 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. , SM/06835 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barasukjora(zone-II)PWSS | 84437 | 02/08/2021 | 0 | ASIS KUMAR SARANGI | 1.99 | 0 | 0 | 0
50 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. , SM/06835 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443109 | 12/02/2021 | 0 | MAHADEV DAS | 0.09 | 0 | 0 | 0
51 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. , SM/06835 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443109 | 12/02/2021 | 0 | DEBAPRASAD PAL | 0.03 | 0 | 0 | 0
52 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. , SM/06835 | Retrofitting | FHTC data entry. | 844365 | 18/01/2022 | 0 | NABOGOPAL ADHIKARI | 0.1 | 0 | 0 | 0
53 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. , SM/06835 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-II) PWSS of Binpur-II Block under Jhargram Division, PHE Dte. | 844357 | 08/03/2022 | 0 | ASIS KUMAR SARANGI | 0.37 | 0 | 0 | 0
54 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. , SM/06835 | Retrofitting | For payment of liabilities. | 844365 | 18/01/2022 | 0 | RINTU SAMANTA | 0.07 | 0 | 0 | 0
55 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. , SM/06835 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-II) PWSS of Binpur-II Block under Jhargram Division, PHE Dte. | 844357 | 08/03/2022 | 0 | ASIS KUMAR SARANGI | 20.82 | 0 | 0 | 0
56 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. , SM/06835 | Retrofitting | FHTC Data Entry. | 844365 | 18/01/2022 | 0 | PRATHA PRATIM PAL | 0.11 | 0 | 0 | 0
57 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. , SM/06835 | Retrofitting | REPAIRING OF EXISTING F.H.T.C AT MOUZA ORGONDA UNDER BARASUKJORA W/S SCHEME (ZONE-II) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE (Phase-I) | 317/JSD | 04/04/2025 | 14 | ASSOCIATED ENGINEERS & TRADERS | 0.81 | 0 | 0 | 0
58 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. , SM/06835 | Retrofitting | REPAIRING OF EXISTING F.H.T.C AT MOUZA ORGONDA UNDER BARASUKJORA W/S SCHEME (ZONE-II) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE (Phase-II) | 318/JSD | 04/04/2025 | 14 | ASSOCIATED ENGINEERS & TRADERS | 0.45 | 0 | 0 | 0
59 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10491 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Kultikri PWSS in Sankrail Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 60/JSD | 18/06/2021 | 14 | ROY CHOWDHURY ASSOCIATES | 4.65 | 0 | 0 | 1
60 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10491 | Augmentation | Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January-2023 and February-2023 under Jhargram Division, PHE Dte. | 29A/JRWS | 28/12/2022 | 60 | PROVAT KUMAR DE | 0.93 | 0 | 0 | 100
61 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10491 | Augmentation | Hatigeria Kultikri Rohini rogra road restoration work for laying pipelines along CH. 8.80 km to 12.50 Km done by PHE Jhargram under Jhargram Highway Division, in the District of Jhargram | BP-2023-24-108 | 28/06/2023 | 0 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 18.27 | 0 | 0 | 0
62 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10491 | Augmentation | Balance road restoration charge for laying pipeling alogn hatigeria-Kultikri - Rohini Road under Kultikri W/S scheme under Jhrgram Highway Division, PHE Dte. | BP-2023-24-347 | 22/12/2023 | 0 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 18.27 | 0 | 0 | 0
63 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10491 | Augmentation | Augmentation of Ground Water based Kultikri Water Supply Scheme by providing laying of Distribution pipe lie and FHTC work and Construction of RCC Over Head Reservoir of capacity 200 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sankrail Dev. Block under Jhargram Division, PHE Dte. | 373/JHD | 18/10/2022 | 180 | SIBSANKAR CHOWDHURY | 274.15 | 0 | 0 | 95
64 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10491 | Augmentation | Supply delivery of CIDF S/V for the work Augmentation Kultikri Water Supply Scheme under Jhargram Sub Division within Jhargram Division, PHE Dte. | 978/JSD | 17/11/2023 | 7 | NRIPENDRA NATH SINGHA | 0.92 | 0 | 0 | 100
65 | JHARGRAM | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Material Requisition To Resource Division | 1600/JHD | 08/09/2023 | 0 | Resource Division | 34.47 | 0 | 0 | 0
66 | JHARGRAM | Jhargram Mechanical Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chenchur Geria & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1246/JMD | 26/05/2023 | 180 | M/S. SAMRIDDHI ENTERPRISE | 21.88 | 0 | 0 | 50
67 | JHARGRAM | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Construction of Laying distribution pipe line under JJM with allied work for CHENCHUR GERYA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 790/JHD | 31/05/2023 | 90 | PROVAT KUMAR DE | 69.24 | 0 | 0 | 100
68 | JHARGRAM | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Construction of Boundary wall and allied works at 1st. Tube well site of Chenchur Geriya and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 2411/JHD | 12/12/2024 | 30 | K.D.CONSTRUCTION | 8.17 | 0 | 0 | 0
69 | JHARGRAM | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Supplying and Delivery of Different Dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Chenchur Gerya and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | 2295/JHD | 04/12/2024 | 30 | BIKASH MANDAL | 7.92 | 0 | 0 | 0
70 | JHARGRAM | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Chandri GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | 1839/JHD | 20/09/2024 | 10 | GOPAL JANA | 0.75 | 0 | 0 | 100
71 | JHARGRAM | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Chubka GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | 1840/JHD | 20/09/2024 | 10 | PRINT PREVIEW | 0.59 | 0 | 0 | 100
72 | JHARGRAM | Jhargram Mechanical Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | new service connection charges at Chenchurgerya water supply scheme | 114/JMD | 13/05/2024 | 0 | WBSEDCL | 8.71 | 0 | 0 | 0
73 | JHARGRAM | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Accommodate FHTC ( 1553 nos) under JJM with allied work for CHENCHUR GERYA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 791/JHD | 31/05/2023 | 90 | PROVAT KUMAR DE | 65.48 | 0 | 0 | 90
74 | JHARGRAM | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Construction of Laying distribution pipe line under JJM with allied work for CHENCHUR GERYA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1317/JHD | 10/08/2023 | 90 | RAMENDRA NATH KAR | 43.66 | 0 | 0 | 90
75 | JHARGRAM | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Sinking of Tube Well , Pump House , 250 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation under JJM with allied work for CHENCHUR GERYA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_19 of 2022-23 , SL No.-1 ) | 1515/JHD | 05/09/2023 | 210 | SATYANARAYAN BISWAS | 205.51 | 0 | 0 | 80
76 | JHARGRAM | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Trial run for CHENCHUR GERYA AND ADJOINING MOUZAS PWSS scheme within Jhargram Block under Jhargram Division, PHE Dte. for 3 months. (Effected from 01/09/2025) | 735/JHD | 02/04/2025 | 91 | SANDIP GURIA | 1.22 | 0 | 0 | 100
77 | JHARGRAM | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Sinking of Tube Well , Interconnection pipe line, Laying distribution pipe line, under JJM with allied work for CHENCHUR GERYAAND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_19 of 2022-23 , SL No.-4 ) | 1343/JHD | 10/08/2023 | 90 | NIMAI LAL GURIA | 18.79 | 0 | 0 | 100
78 | JHARGRAM | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS , SM/12445 | New | Construction of Boundary wall and allied works at 1st. Tube well site of Chenchur Geriya and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 1316/JHD | 05/09/2024 | 30 | KAUSTAV SARKAR | 3.75 | 0 | 0 | 85
79 | JHARGRAM | Jhargram Division | ANKRO AND ADJOINING MOUJAS PWSS , SM/12447 | New | Material Requisition To Resource Division | 1536/JHD | 06/09/2023 | 0 | Resource Division | 28.21 | 0 | 0 | 0
80 | JHARGRAM | Jhargram Division | ANKRO AND ADJOINING MOUJAS PWSS , SM/12447 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Ankro and its Adjoining Mouzas PWSS , Block Binpur-I, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | 774/JSD | 09/08/2024 | 30 | SAURABH KAR | 4.77 | 0 | 0 | 0
81 | JHARGRAM | Central Drilling | ANKRO AND ADJOINING MOUJAS PWSS , SM/12447 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
82 | JHARGRAM | Jhargram Mechanical Division | KENDANA AND ADJOINING MOUJAS PWSS , SM/12346 | New | Quotation for new service connection at Kanduana T/W - II water supply scheme. | 102/JMD | 08/05/2024 | 0 | WBSEDCL | 5.18 | 0 | 0 | 0
83 | JHARGRAM | Jhargram Mechanical Division | KENDANA AND ADJOINING MOUJAS PWSS , SM/12346 | New | New Service connection charges. | 200/JMD | 14/06/2024 | 0 | WBSEDCL | 2.93 | 0 | 0 | 0
84 | JHARGRAM | Central Drilling | KENDANA AND ADJOINING MOUJAS PWSS , SM/12346 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
85 | JHARGRAM | Jhargram Division | KENDANA AND ADJOINING MOUJAS PWSS , SM/12346 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
86 | JHARGRAM | Jhargram Division | KENDANA AND ADJOINING MOUJAS PWSS , SM/12346 | New | Field Level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in fferent Pipe Water Supply Scheme (7 nos PWSS of 130 PWSS) within Gopiballavpur-II Block in the District of Jhargram under Jhargram Division. PHE Dte. Location- i) Chingra PWSS, ii) Gohalmara PWSS iii) Kendana PWSS iv) Kulina PWSS v) Sonakinia PWSS Vi) Tentilia PWSS vii) Chorchita PWSS | 368/JSD | 29/04/2025 | 150 | TECHVISION | 3.72 | 0 | 0 | 10
87 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Mahuli T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3073/JMD | 28/09/2022 | 120 | SUBHASIS ROY | 5.7 | 0 | 0 | 0
88 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) for Jamboni Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | 365/JSD | 21/07/2022 | 15 | SUNIL DULE | 4.8 | 0 | 0 | 1
89 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bag Doba mouza , tube well no. 2 and others of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 655/JMD | 31/12/2021 | 7 | P.K. ENGINEERING | 8.69 | 0 | 0 | 1
90 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking and providing manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amlasol mouza, tube well no.2 and others of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 83/JMD | 31/01/2022 | 7 | DEBJYOTI BASU | 3.77 | 0 | 0 | 1
91 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Chhota Jharia mouza , tube well no. 3 and others of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 669/JMD | 31/12/2021 | 7 | SUBHASIS ROY | 5.53 | 0 | 0 | 1
92 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bam Diha mouza and others of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 709/JMD | 31/12/2021 | 7 | M/S. BIKASH DE | 4.21 | 0 | 0 | 1
93 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. (Furniture and computer tools supply) |  | 23/09/2022 | 0 | IONET | 0.44 | 0 | 0 | 0
94 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone units for Drought like situation Prone 08 Blocks of Jhargram District (Model standalone Grid power operated W/S System for Habitations/mouzas with 400 & more population) under mid-trem plan of master plan. | BP-2022-23-57 | 13/05/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 73.7 | 0 | 0 | 0
95 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | WBSEDCL Payment for New service connection. | 1/JMD/PFMS/OCT | 18/10/2022 | 0 | WBSEDCL | 4.58 | 0 | 0 | 0
96 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Requisition of fund for ASHA Incentive in the activity of onsite drinking water testing at the village level by trained ASHAs in Jhargram District. | BP-2022-23-157 | 12/07/2022 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITI JHARGRAM HEALTH DISTRICT | 3.65 | 0 | 0 | 0
97 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Payment for new service connection of WBSEDCL. | 23/JMD/PFMS/SEP | 09/09/2022 | 0 | WBSEDCL | 6.27 | 0 | 0 | 0
98 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | WBSEDCL payment for new Service Connection. | 2/JMD/PFMS/OCT | 25/10/2022 | 0 | WBSEDCL | 6.46 | 0 | 0 | 0
99 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | For WBSEDCL quotations i.c.t. Construction of RBTW under standalone pipe water supply scheme. | BP-2022-23-230 | 22/08/2022 | 0 | EXECUTIVE ENGINEER, JHARGRAM MECHANICAL DIVISION, PHE DTE. | 4.18 | 0 | 0 | 0
100 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone units for drought line situation prone 8 blocks of Jhargram District. | BP-2022-23-121 | 18/06/2022 | 0 | EXECUTIVE ENGINEER, JHARGRAM MECHANICAL DIVISION, PHE DTE. | 75.97 | 0 | 0 | 0
101 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Payment for new service connection of WBSEDCL. | 22/JMD/PFMS/SEP | 29/09/2022 | 0 | WBSEDCL | 1.87 | 0 | 0 | 0
102 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_6 under Jhargram Division in the District of Jhargram. | 192/MD | 01/02/2022 | 180 | M/S. B. N. ENTERPRISES | 107.25 | 0 | 0 | 0
103 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jamui stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1455/JMD | 19/07/2022 | 120 | SUBHAM ENTERPRISE | 6.86 | 0 | 0 | 0
104 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garkhelar stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1459/JMD | 19/07/2022 | 120 | M/S D.G.B. ENTERPRISE | 6.87 | 0 | 0 | 0
105 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kank Para stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1416/JMD | 14/07/2022 | 120 | SHOVAN KUMAR DAS | 6.86 | 0 | 0 | 0
106 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghmari stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1472/JMD | 19/07/2022 | 120 | MAA BHABOTARINE ENTERPRISE | 6.86 | 0 | 0 | 0
107 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garkhelar stand alone piped water supply scheme, tube well no.-III of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1461/JMD | 19/07/2022 | 120 | BALAJI CONSTRUCTION | 6.86 | 0 | 0 | 0
108 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Lakshanpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1414/JMD | 14/07/2022 | 120 | M/S. EMMESS | 6.83 | 0 | 0 | 100
109 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garkhelar stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1460/JMD | 19/07/2022 | 120 | JAL PRAVAHIKA PVT. LTD. | 6.87 | 0 | 0 | 0
110 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kank Para stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1415/JMD | 14/07/2022 | 120 | KAMAKHYA ENTERPRISE | 6.8 | 0 | 0 | 0
111 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1419/JMD | 14/07/2022 | 120 | SUJOY RANJAN BHOWMICK | 6.86 | 0 | 0 | 100
112 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jhaurishol stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1738/JMD | 17/08/2022 | 120 | M/S. P.P. ELECTRICALS | 6.85 | 0 | 0 | 0
113 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dhobani Sol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1735/JMD | 17/08/2022 | 120 | DAS CONSTRUCTION | 6.85 | 0 | 0 | 0
114 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chhota Tal Pada stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1734/JMD | 17/08/2022 | 120 | GOENKA ENTERPRISE | 6.86 | 0 | 0 | 0
115 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhirighutu T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3162/JMD | 19/10/2022 | 120 | JAGANNATH ENTERPRISE | 5.72 | 0 | 0 | 0
116 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dubrajpur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3193/JMD | 28/10/2022 | 120 | BOSE AND CHATTERJEE INDUSTRIES | 5.68 | 0 | 0 | 0
117 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Aguibil T/W no. I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3064/JMD | 28/09/2022 | 120 | MENAKA ENTERPRISE | 6.79 | 0 | 0 | 0
118 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Barighati T/W no. I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 4210/JMD | 28/12/2022 | 120 | MAA BHABOTARINE ENTERPRISE | 6.84 | 0 | 0 | 0
119 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Lekraanchra T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 4211/JMD | 28/12/2022 | 120 | MANAS KUMAR SAHA | 6.84 | 0 | 0 | 0
120 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Rajgram Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4197/JMD | 28/12/2022 | 120 | DIPALI CONSTRUCTION | 5.78 | 0 | 0 | 0
121 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amla Kora T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3082/JMD | 28/09/2022 | 120 | MAA BHABOTARINE ENTERPRISE | 5.71 | 0 | 0 | 0
122 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Choto Jharia T/W no. -III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3080/JMD | 28/09/2022 | 120 | ASHUTOSH DAS & CO. | 5.63 | 0 | 0 | 0
123 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amla Kora T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3081/JMD | 28/09/2022 | 120 | A.M.S. ENTERPRISE | 5.7 | 0 | 0 | 0
124 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Balia Geria T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3157/JMD | 19/10/2022 | 120 | BUSR ENGINEERING | 5.7 | 0 | 0 | 0
125 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bag Doba T/W no. II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3165/JMD | 19/10/2022 | 120 | M/S. NABIN GOPAL SENGUPTA | 5.71 | 0 | 0 | 0
126 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluk Chua T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3161/JMD | 19/10/2022 | 120 | KAMAKHYA ENTERPRISE | 5.71 | 0 | 0 | 0
127 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kendisol T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3067/JMD | 28/09/2022 | 120 | SOUMEN ELECTRIC | 6.79 | 0 | 0 | 0
128 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Lakhipara T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3074/JMD | 28/09/2022 | 120 | SWAPAN ENTERPRISE | 5.71 | 0 | 0 | 0
129 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Shutpipal, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 147/JMD | 19/01/2023 | 120 | M/S. NABIN GOPAL SENGUPTA | 5.78 | 0 | 0 | 95
130 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rukhni Mara (Pry. School) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3164/JMD | 19/10/2022 | 120 | S.S. GHORAI | 5.71 | 0 | 0 | 0
131 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Sol, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 261/JMD | 03/02/2023 | 120 | JAL PRAVAHIKA PVT. LTD. | 5.78 | 0 | 0 | 0
132 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Purna Pani stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3516/JMD | 29/11/2022 | 7 | SUBHASIS ROY | 0.07 | 0 | 0 | 0
133 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Purba Para) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3486/JMD | 29/11/2022 | 7 | DEB KUMAR BASU | 0.07 | 0 | 0 | 0
134 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Ramchandrapur) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3490/JMD | 29/11/2022 | 7 | DEB KUMAR BASU | 0.07 | 0 | 0 | 0
135 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sankisol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3541/JMD | 29/11/2022 | 7 | DEB KUMAR BASU | 0.07 | 0 | 0 | 0
136 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rajpara T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3519/JMD | 29/11/2022 | 7 | DEB KUMAR BASU | 0.07 | 0 | 0 | 0
137 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Mura Kati (G.P. - Barakhankri) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 268/JMD | 03/02/2023 | 120 | DAS CONSTRUCTION | 5.76 | 0 | 0 | 95
138 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Marchi Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 143/JMD | 19/01/2023 | 120 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 5.78 | 0 | 0 | 0
139 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Tukurya mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 567/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.77 | 0 | 0 | 0
140 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Shahari mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 576/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 0
141 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Shahari mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 575/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.77 | 0 | 0 | 0
142 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Ningui, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 960/JMD | 25/04/2023 | 120 | MENAKA ENTERPRISE | 5.78 | 0 | 0 | 95
143 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.2 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 144/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.15 | 0 | 0 | 0
144 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Ramkrishnapur, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 966/JMD | 25/04/2023 | 120 | M/S. EMMESS | 5.78 | 0 | 0 | 95
145 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Rangua mouza, tube well no.2 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 485/JMD | 23/12/2021 | 4 | SUJOY RANJAN BHOWMICK | 2.62 | 0 | 0 | 0
146 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Salika mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 558/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 0
147 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Dhadka mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 543/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.59 | 0 | 0 | 0
148 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Dhadka mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 544/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 0
149 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply and delivery of Silpaulin for Drilling works at Rig Store of MMSD(D) in Jhargram Dist. under Jhargram Mechanical Division, P.H.E Dte. | 1011/JMD | 26/05/2022 | 7 | MONORANJAN DEY | 1.84 | 0 | 0 | 0
150 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amadubi mouza, tube well no.1 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 94/JMD | 31/01/2022 | 2 | DEBJYOTI BASU | 0.15 | 0 | 0 | 0
151 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Rangua mouza, tube well no.2 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 486/JMD | 23/12/2021 | 4 | SUJOY RANJAN BHOWMICK | 0.33 | 0 | 0 | 0
152 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.2 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 143/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0 | 0
153 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Salika mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 557/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.77 | 0 | 0 | 0
154 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking & Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Rangua & others mouza, of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 484/JMD | 23/12/2021 | 16 | DEBJYOTI BASU | 2.39 | 0 | 0 | 0
155 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amadubi mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 96/JMD | 31/01/2022 | 2 | DEBJYOTI BASU | 0.15 | 0 | 0 | 0
156 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bara Mara mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 721/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 0
157 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bali Muri mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 708/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 0
158 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Paschim Gholai stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3513/JMD | 29/11/2022 | 7 | M/S. NABIN GOPAL SENGUPTA | 0.07 | 0 | 0 | 0
159 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Sal Bani mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 722/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 2.6 | 0 | 0 | 0
160 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Sal Bani mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 723/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 0
161 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bihankuria mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 645/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 2.6 | 0 | 0 | 0
162 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bihankuria mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 646/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 0
163 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bara Mara mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 720/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 2.6 | 0 | 0 | 0
164 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amadubi mouza, tube well no.1 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 93/JMD | 31/01/2022 | 2 | DEBJYOTI BASU | 0.71 | 0 | 0 | 0
165 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amadubi mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 95/JMD | 31/01/2022 | 2 | DEBJYOTI BASU | 0.71 | 0 | 0 | 0
166 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Birbhanpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1349/JMD | 06/06/2023 | 120 | JAGANNATH ENTERPRISE | 5.78 | 0 | 0 | 95
167 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluk Ghara Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 663/JMD | 24/03/2023 | 120 | T.N. BANERJEE | 5.77 | 0 | 0 | 0
168 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bhadai stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3535/JMD | 29/11/2022 | 7 | P.K. ENGINEERING | 0.07 | 0 | 0 | 0
169 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Tukurya mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 568/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 0
170 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-II_1_2 under Jhargram Division in the District of Jhargram. | 285/MD | 15/02/2022 | 180 | J.K. BUILDERS | 75.35 | 0 | 0 | 0
171 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghjhapa stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3517/JMD | 29/11/2022 | 7 | M/S. SAMRIDDHI ENTERPRISE | 0.07 | 0 | 0 | 0
172 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sonamui stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3515/JMD | 29/11/2022 | 7 | P.K. ENGINEERING | 0.07 | 0 | 0 | 0
173 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chandabila, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1293/JMD | 30/05/2023 | 120 | S.S. GHORAI | 5.78 | 0 | 0 | 95
174 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Chilkigar mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 564/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 0
175 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rangua T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1713/JMD | 13/07/2023 | 120 | SUBHASIS ROY | 5.77 | 0 | 0 | 0
176 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Chilkigar mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 563/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.6 | 0 | 0 | 0
177 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bag Doba T/W no. II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3497/JMD | 29/11/2022 | 7 | M/S. NABIN GOPAL SENGUPTA | 0.07 | 0 | 0 | 0
178 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3483/JMD | 29/11/2022 | 7 | M/S. SAMRIDDHI ENTERPRISE | 0.07 | 0 | 0 | 0
179 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Salgaria (Near Club) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3481/JMD | 29/11/2022 | 7 | SAMARPITA ENGINEERING | 0.07 | 0 | 0 | 0
180 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kundal Pahari T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 1710/JMD | 13/07/2023 | 180 | DAS CONSTRUCTION | 6.89 | 0 | 0 | 0
181 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amlasol T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3445/JMD | 29/11/2022 | 7 | P.K. ENGINEERING | 0.07 | 0 | 0 | 0
182 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gohalberya T/W no. -III & IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 1707/JMD | 13/07/2023 | 180 | SUJOY RANJAN BHOWMICK | 6.89 | 0 | 0 | 0
183 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rupai T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 1708/JMD | 13/07/2023 | 180 | DEBJYOTI BASU | 6.89 | 0 | 0 | 0
184 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bali Muri mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 707/JMD | 31/12/2021 | 4 | M/S. BIKASH DE | 2.6 | 0 | 0 | 0
185 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Baradhansol, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1731/JMD | 14/07/2023 | 120 | M/S. SAMRIDDHI ENTERPRISE | 5.78 | 0 | 0 | 0
186 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Baradhansol, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1732/JMD | 14/07/2023 | 120 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 5.78 | 0 | 0 | 0
187 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Metyalsol Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1733/JMD | 14/07/2023 | 120 | SAMARPITA ENGINEERING | 5.78 | 0 | 0 | 0
188 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-VI Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1769/JMD | 19/07/2023 | 120 | ECO ENTERPRISE | 5.77 | 0 | 0 | 0
189 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking & Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Murar & other mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 498/JMD | 23/12/2021 | 32 | SUJOY RANJAN BHOWMICK | 4.31 | 0 | 0 | 0
190 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply and delivery of Silpaulin for Drilling works at Rig Store of MMSD(D) in Jhargram Dist. under Jhargram Mechanical Division, P.H.E Dte. | 1011/JMD | 26/05/2022 | 7 | MONORANJAN DEY | 1.34 | 0 | 0 | 0
191 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing one no. 10 MT capacity truck along with licensed driver on daily basis for Rig unit no. 21D/LT/500 of MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | 1027/JMD | 30/05/2022 | 90 | MONORANJAN DEY | 0.92 | 0 | 0 | 0
192 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluk Chua T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3493/JMD | 29/11/2022 | 7 | KAMAKHYA ENTERPRISE | 0.07 | 0 | 0 | 0
193 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply & delivery of different size hydraulic hose & filter membrane for Hydraulic unit , cross member for shaft line ,lubricants for engine and others works for KLR /DR/DTH -500 & 21D/LT-500 rig unit & brake shoe assembly for LMP-500 rig unit . | 494/JMD | 15/03/2022 | 30 | B. P. TRADING CORPORATION | 4.41 | 0 | 0 | 0
194 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1767/JMD | 19/07/2023 | 120 | PRANAB KUMAR DAS | 5.78 | 0 | 0 | 0
195 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-V Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1768/JMD | 19/07/2023 | 120 | RITESH ENTERPRISE | 5.78 | 0 | 0 | 0
196 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing one no. 10 MT capacity truck & one no 32 BHP Capacity Tractor along with licensed driver on daily basis for Rig unit no. 41D/LMP/500 of MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | 366/JMD | 23/02/2023 | 20 | M/S. SAMRIDDHI ENTERPRISE | 0.97 | 0 | 0 | 0
197 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kadokota Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1825/JMD | 24/07/2023 | 120 | BHABANI PRASAD MANNA | 5.78 | 0 | 0 | 0
198 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Jharia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1798/JMD | 24/07/2023 | 120 | SWAPAN ENTERPRISE | 5.78 | 0 | 0 | 0
199 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Narda, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1772/JMD | 19/07/2023 | 120 | MAA BHABOTARINE ENTERPRISE | 5.78 | 0 | 0 | 0
200 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kul Diha, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1827/JMD | 24/07/2023 | 120 | RITESH ENTERPRISE | 5.78 | 0 | 0 | 0
201 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of 1(One) Nos. 150 mm X 100 mm X 135 Mtr. RBTW, for lowering of Submersible Pumping Machinery at Kamapukuria - II Village Stand Alone PWSS for Nayagram Block under Jhargram Division, P.H.E. Dte. | 653/JSD | 18/07/2023 | 30 | PASCHIMANCHAL ADIBASI ENGINEERS CO-OPERATIVE SOCIETY LIMITED. | 4.32 | 0 | 0 | 0
202 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhalia Chati Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 2022/JMD | 02/08/2023 | 120 | A. G. ENTERPRISE | 5.78 | 0 | 0 | 0
203 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of 1(One) Nos. 150 mm X 100 mm X 135 Mtr. RBTW, for lowering of Submersible Pumping Machinery at Kamapukuria - V Village Stand Alone PWSS for Nayagram Block under Jhargram Division, P.H.E. Dte. | 665/JSD | 24/07/2023 | 30 | ANANGA MOHAN GHOSH | 4.3 | 0 | 0 | 0
204 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of 1(One) Nos. 150 mm X 100 mm X 135 Mtr. RBTW, for lowering of Submersible Pumping Machinery at Kamapukuria - VI Village Stand Alone PWSS for Nayagram Block under Jhargram Division, P.H.E. Dte. | 666/JSD | 24/07/2023 | 30 | GOUTAM KUMAR BOSE | 4.29 | 0 | 0 | 0
205 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dumuria, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1831/JMD | 24/07/2023 | 120 | ARATI ENGINEERING | 5.78 | 0 | 0 | 0
206 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nandalalpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1837/JMD | 24/07/2023 | 120 | SUBHASIS ROY | 5.77 | 0 | 0 | 0
207 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dulki, Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1795/JMD | 24/07/2023 | 120 | BHABANI PRASAD MANNA | 5.78 | 0 | 0 | 0
208 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1804/JMD | 24/07/2023 | 120 | SUBHASIS ROY | 5.77 | 0 | 0 | 0
209 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bankati Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1839/JMD | 24/07/2023 | 120 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD | 5.77 | 0 | 0 | 0
210 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bardhan Sola (G.P.- Kharikamathani), Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1836/JMD | 24/07/2023 | 120 | M.D. ENTERPRISE | 5.77 | 0 | 0 | 0
211 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kuldiha Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 2032/JMD | 02/08/2023 | 120 | EASTERN INDIA SALES AND SERVICE | 5.77 | 0 | 0 | 0
212 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nara Singha Pur, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1801/JMD | 24/07/2023 | 120 | M/S. SAJAHAN CHOWDHURY | 5.78 | 0 | 0 | 0
213 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1805/JMD | 24/07/2023 | 120 | SUBHASIS ROY | 5.77 | 0 | 0 | 0
214 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1969/JMD | 31/07/2023 | 120 | M/S B.M. ELECTRICAL | 5.78 | 0 | 0 | 0
215 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nagri Pada, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1971/JMD | 31/07/2023 | 120 | SHOVAN KUMAR DAS | 5.78 | 0 | 0 | 95
216 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sal Bani Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1833/JMD | 24/07/2023 | 120 | JAGANNATH ENTERPRISE | 5.78 | 0 | 0 | 96
217 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bardhan Sola (G.P.- Kharikamathani), Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1834/JMD | 24/07/2023 | 120 | P.K. ENGINEERING | 5.78 | 0 | 0 | 0
218 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bardhan Sola (G.P.- Kharikamathani), Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1835/JMD | 24/07/2023 | 120 | AMIT DAS | 5.77 | 0 | 0 | 0
219 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nara Singha Pur, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1802/JMD | 24/07/2023 | 120 | DAS CONSTRUCTION | 5.78 | 0 | 0 | 0
220 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kukrasole, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1826/JMD | 24/07/2023 | 120 | SWAPAN ENTERPRISE | 5.78 | 0 | 0 | 0
221 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dumuria, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1830/JMD | 24/07/2023 | 120 | A.S. ENTERPRISE | 5.78 | 0 | 0 | 0
222 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Malam, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1819/JMD | 24/07/2023 | 120 | DEBJYOTI BASU | 5.77 | 0 | 0 | 0
223 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of 1(One) Nos. 150 mm X 100 mm X 135 Mtr. RBTW, for lowering of Submersible Pumping Machinery at Kamapukuria - III Village Stand Alone PWSS for Nayagram Block under Jhargram Division, P.H.E. Dte. | 661/JSD | 20/07/2023 | 30 | ANANGA MOHAN GHOSH | 4.33 | 0 | 0 | 0
224 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Swarup Narayanpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1840/JMD | 24/07/2023 | 120 | ECO ENTERPRISE | 5.78 | 0 | 0 | 95
225 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bankra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3537/JMD | 29/11/2022 | 7 | MONORANJAN DEY | 0.07 | 0 | 0 | 0
226 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Koima (Pal) T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3467/JMD | 29/11/2022 | 7 | M/S. EMMESS | 0.07 | 0 | 0 | 0
227 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bara Khankri stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3458/JMD | 29/11/2022 | 7 | M/S. EMMESS | 0.07 | 0 | 0 | 0
228 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Narda stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3450/JMD | 29/11/2022 | 7 | ECO ENTERPRISE | 0.07 | 0 | 0 | 0
229 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under Jamboni Block location Id Jamboni_4_2 under Jhargram Division in the District of Jhargram. | 1436/JHD | 24/08/2023 | 60 | TAPAN KUMAR MANDAL | 19.76 | 0 | 0 | 0
230 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Lakhipara (School) T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3466/JMD | 29/11/2022 | 7 | MONORANJAN DEY | 0.07 | 0 | 0 | 0
231 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3484/JMD | 29/11/2022 | 7 | ECO ENTERPRISE | 0.07 | 0 | 0 | 0
232 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Koima (A.W.C.) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3499/JMD | 29/11/2022 | 7 | M/S. EMMESS | 0.07 | 0 | 0 | 0
233 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kargonala stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3442/JMD | 29/11/2022 | 7 | ECO ENTERPRISE | 0.07 | 0 | 0 | 0
234 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bankati mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 507/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0 | 0
235 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bankati mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 508/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0 | 0
236 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1419./JMD | 14/06/2022 | 120 | SUJOY RANJAN BHOWMICK | 6.86 | 0 | 0 | 100
237 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1429./JMD | 14/06/2022 | 120 | SUJOY RANJAN BHOWMICK | 6.86 | 0 | 0 | 100
238 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Nischinta stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3508/JMD | 29/11/2022 | 7 | S.S. GHORAI | 0.07 | 0 | 0 | 0
239 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kalma Pukhuria stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3457/JMD | 29/11/2022 | 7 | S.S. GHORAI | 0.07 | 0 | 0 | 0
240 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nara Singha Pur mouza , tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 657/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 2.6 | 0 | 0 | 0
241 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 673/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 2.6 | 0 | 0 | 0
242 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nara Singha Pur mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 660/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 0.33 | 0 | 0 | 0
243 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1419../JMD | 14/07/2022 | 120 | SUJOY RANJAN BHOWMICK | 6.86 | 0 | 0 | 70
244 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 674/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 0.33 | 0 | 0 | 0
245 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nara Singha Pur mouza , tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 658/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 0.33 | 0 | 0 | 0
246 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rukhni Mara (Pry. School) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3496/JMD | 29/11/2022 | 7 | S.S. GHORAI | 0.07 | 0 | 0 | 0
247 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Shibanandapur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3465/JMD | 29/11/2022 | 7 | BALAJI CONSTRUCTION | 0.07 | 0 | 0 | 0
248 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 146/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0 | 0
249 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 145/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0 | 0
250 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Narda mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 652/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 0
251 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kadokata, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 1066/JMD | 01/06/2022 | 5 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 0
252 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Chandabila mouza, tube well no.2 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 140/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0 | 0
253 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Swarup Narayanpur mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 516/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0 | 0
254 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Metyalsol mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 506/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0 | 0
255 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Baradhansol mouza, tube well no.2 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 504/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0 | 0
256 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Muniada mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 135/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0 | 0
257 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Muniada mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 136/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0 | 0
258 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Narda mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 651/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 2.62 | 0 | 0 | 0
259 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Baradhansol mouza, tube well no.1 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 501/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0 | 0
260 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Metyalsol mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 505/JMD | 30/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0 | 0
261 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Muniada mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 133/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0 | 0
262 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 147/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0 | 0
263 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 148/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0 | 0
264 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kukrasol, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 1073/JMD | 01/06/2022 | 5 | SAMARPITA ENGINEERING | 0.33 | 0 | 0 | 0
265 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Chandabila mouza, tube well no.2 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 139/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0 | 0
266 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Muniada mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 134/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0 | 0
267 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Baradhansol mouza, tube well no.2 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 503/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0 | 0
268 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Swarup Narayanpur mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 515/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0 | 0
269 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kukrasol, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 1072/JMD | 01/06/2022 | 5 | SAMARPITA ENGINEERING | 2.8 | 0 | 0 | 0
270 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kadokata, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 1065/JMD | 01/06/2022 | 5 | M/S. SAMRIDDHI ENTERPRISE | 2.8 | 0 | 0 | 0
271 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nandalalpur mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 481/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0 | 0
272 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Baradhansol mouza, tube well no.1 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 502/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0 | 0
273 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kukrasol, tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 1075/JMD | 01/06/2022 | 5 | SAMARPITA ENGINEERING | 0.33 | 0 | 0 | 0
274 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Nandalalpur mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 482/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0 | 0
275 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nara Singha Pur mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 659/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 2.6 | 0 | 0 | 0
276 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kukrasol, tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 1074/JMD | 01/06/2022 | 5 | SAMARPITA ENGINEERING | 2.8 | 0 | 0 | 0
277 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Mara Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 666/JMD | 24/03/2023 | 120 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 5.78 | 0 | 0 | 95
278 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Hiring of Diesel driven Commercial Covered four wheeler vehicle on daily basis along with LMV licensed driver for official purpose of Assistant Engineer, Jhargram Mechanical Division under office of Executive Engineer, Jhargram Mechanical Division, PHE Dte. | 340/JMD | 03/03/2022 | 362 | SUBHASIS ROY | 1.68 | 0 | 0 | 100
279 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bhalki Sol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1470/JMD | 19/07/2022 | 120 | M/S. EMMESS | 6.83 | 0 | 0 | 100
280 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghmari stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1471/JMD | 19/07/2022 | 120 | SOUMEN ELECTRIC | 6.86 | 0 | 0 | 100
281 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kulghagri stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1465/JMD | 19/07/2022 | 120 | SOUMEN ELECTRIC | 6.86 | 0 | 0 | 100
282 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) for Binpur-II & Gopiballavpur-I Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | 351/JSD | 12/07/2022 | 15 | SANKAR KUMAR NAG | 4.72 | 0 | 0 | 1
283 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) at Baligeria and Barakhakri GP of Nayagram Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | 44/GPSD | 29/08/2022 | 15 | DIPAK KUMAR BAKLY | 4.8 | 0 | 0 | 1
284 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) at Chandabila and Patina GP of Nayagram Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | 43/GPSD | 29/08/2022 | 15 | GOBINDA MAITY | 4.8 | 0 | 0 | 1
285 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) for Binpur-I Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | 354/JSD | 15/07/2022 | 15 | BIDYUT KUMAR SANTRA | 4.8 | 0 | 0 | 1
286 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) at Sankrail Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | 45/GPSD | 29/08/2022 | 15 | DIPAK KUMAR BAKLY | 4.76 | 0 | 0 | 1
287 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tiakati T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3167/JMD | 19/10/2022 | 120 | AMIT DAS | 5.71 | 0 | 0 | 0
288 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Salgaria (Near School) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3160/JMD | 19/10/2022 | 120 | M/S MANABESH ROY | 5.71 | 0 | 0 | 0
289 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Ramchandrapur) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3158/JMD | 19/10/2022 | 120 | DEB KUMAR BASU | 5.71 | 0 | 0 | 0
290 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpir-I_2_1_B under Jhargram Division in the District of Jhargram. | 618/JHD | 25/11/2022 | 120 | DEBABRATA DUTTA | 22.25 | 0 | 0 | 100
291 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jirapara Stand Alone piped water supply scheme, tube well no-I of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4209/JMD | 28/12/2022 | 120 | ABHIJIT BASU | 5.78 | 0 | 0 | 0
292 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_4_Dunder Jhargram Division in the District of Jhargram. | 345/JHD | 28/09/2022 | 120 | NIMAI LAL GURIA | 22.16 | 0 | 0 | 1
293 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Topoban T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3076/JMD | 28/09/2022 | 120 | JAL PRAVAHIKA PVT. LTD. | 5.71 | 0 | 0 | 0
294 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Sankrail_3_1 under Jhargram Division in the District of Jhargram. | 877/MD | 10/05/2022 | 180 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 150.3 | 0 | 0 | 100
295 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Topoban T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3075/JMD | 28/09/2022 | 120 | M/S D.G.B. ENTERPRISE | 5.71 | 0 | 0 | 0
296 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Laying of Clear Water Rising Main & Distribution pipe line in Patharchakri Dakshin para under 269 stand alone in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | 64/JHD | 16/01/2023 | 7 | ENVOTECH INFRA SOLUTION | 4.76 | 0 | 0 | 0
297 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Degaria and others mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 545/JMD | 23/12/2021 | 7 | SUJOY RANJAN BHOWMICK | 11.37 | 0 | 0 | 1
298 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Shutpipal stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3435/JMD | 29/11/2022 | 7 | DEBJYOTI BASU | 0.07 | 0 | 0 | 100
299 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Jugi Bandh and others mouza, tube well no.1 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 571/JMD | 23/12/2021 | 7 | CHAKRABORTY MINING & ENGINEERING | 11.59 | 0 | 0 | 1
300 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghmari stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3511/JMD | 29/11/2022 | 7 | SOUMEN ELECTRIC | 0.07 | 0 | 0 | 100
301 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Laying of Distribution pipe line , Construction of Valve Chember& Inter Connection at Rupai Habitation (Rupai Mouza) under Barasukjora W/S Scheme in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | 321/JSD | 27/04/2023 | 45 | SHRI RANISATI VENTURES | 3.74 | 0 | 0 | 100
302 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January-2023 and February-2023 under Jhargram Division, PHE Dte. | 29A/JRWS | 28/12/2022 | 60 | PROVAT KUMAR DE | 0.93 | 0 | 0 | 100
303 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kulghagri stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3505/JMD | 29/11/2022 | 7 | SOUMEN ELECTRIC | 0.07 | 0 | 0 | 100
304 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Goal Danga stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3440/JMD | 29/11/2022 | 7 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.07 | 0 | 0 | 100
305 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Laying of Distribution pipe line , Construction of Valve Chember& Inter Connection at Baliguma Habitation (Rupai Mouza) under Barasukjora W/S Scheme in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | 320/JSD | 27/04/2023 | 45 | SHRI RANISATI VENTURES | 4.06 | 0 | 0 | 100
306 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Continuation Work for Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for March-2023 to May-2023 under Jhargram Division, PHE Dte. | 50A/JRWS | 28/02/2023 | 90 | PROVAT KUMAR DE | 0.83 | 0 | 0 | 100
307 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Arra , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 1058/JMD | 01/06/2022 | 5 | M/S. SAMRIDDHI ENTERPRISE | 2.78 | 0 | 0 | 100
308 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Arra, tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 1059/JMD | 01/06/2022 | 5 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 100
309 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Dhengabahara, Tube Well no.-II under Jamboni Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 2634/JMD | 29/08/2023 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.37 | 0 | 0 | 100
310 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply and delivery of Bentonite Powder sodium based (Rajasthan Varity) at MMSD(D) store room for sinking of Rig Bored Tube Wells under MMSD(D) under JMD PHE Dte. | 2635/JMD | 29/08/2023 | 10 | DEBJYOTI BASU | 2.24 | 0 | 0 | 100
311 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Dingla mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 528/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0 | 100
312 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Tikra Para mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 705/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 0 | 0 | 100
313 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 3 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 676/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0 | 0 | 100
314 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply and Delivery of Ø 7-7/8 " Drag Bit with Tungsten Carbide insert for Mud Rotary Drilling at MMSD(D) store room for sinking of Rig Bored Tube Wells under MMSD(D) under JMD PHE Dte. | 2636/JMD | 29/08/2023 | 10 | B. P. TRADING CORPORATION | 2.77 | 0 | 0 | 100
315 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply and Delivery of Ø 9 " Drag Bit with Tungsten Carbide insert for Mud Rotary Drilling at MMSD(D) store room for sinking of Rig Bored Tube Wells under MMSD(D) under JMD PHE Dte. | 2637/JMD | 29/08/2023 | 10 | SUDIP ENGINEERING CO. | 1.5 | 0 | 0 | 100
316 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Dhadka and others mouza of Jamboni and others blocks block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 543/JMD | 23/12/2021 | 120 | CHAKRABORTY MINING & ENGINEERING | 10.58 | 0 | 0 | 100
317 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Amadubuand others mouza of Binpur-II and others blocks block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 93/JMD | 31/01/2022 | 120 | DEBJYOTI BASU | 1.83 | 0 | 0 | 100
318 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bali Muri mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 707/JMD | 31/12/2021 | 10 | M/S. BIKASH DE | 2.1 | 0 | 0 | 100
319 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Rangua and others mouza of Binpur-Iand others blocks block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 485/JMD | 23/12/2021 | 120 | SUJOY RANJAN BHOWMICK | 3.5 | 0 | 0 | 100
320 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bihankuriaand others mouza of Nayagram and others blocks block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 645/JMD | 31/12/2021 | 1200 | M/S. SAMRIDDHI ENTERPRISE | 6.7 | 0 | 0 | 100
321 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bankisol mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 493/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0 | 100
322 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Malam mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 699/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 0 | 0 | 100
323 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Dingla mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 527/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0 | 100
324 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Lakshanpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3436/JMD | 29/11/2022 | 7 | M/S. EMMESS | 0.07 | 0 | 0 | 100
325 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Malam mouza , tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 698/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0 | 0 | 100
326 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Khatkura Junior High School under Jamboni Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 2785/JMD | 07/09/2023 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.37 | 0 | 0 | 100
327 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bankisol mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 494/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0 | 100
328 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Dismantling the differential gear portion of HALCO Rig unit under Bankura Mechanical Division (BMD) and carrying the same from BMD to Jhargram Mechanical Division (JMD) for fitting fixing in 238/AR/HALCO Rig unit under MMSD(D) under JMD, P.H.E. Dte. | 350/JMD | 04/03/2022 | 10 | CHAKRABORTY MINING & ENGINEERING | 0.14 | 0 | 0 | 100
329 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpir-I_2_1_A under Jhargram Division in the District of Jhargram. | 617/JHD | 25/11/2022 | 120 | J.S.S. ENTERPRISE | 22.26 | 0 | 0 | 100
330 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_4 under Jhargram Division in the District of Jhargram. | 876/MD | 10/05/2022 | 180 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 177.59 | 0 | 0 | 0
331 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_14 under Jhargram Division in the District of Jhargram. | 186/MD | 01/02/2022 | 180 | GOBINDA MAITY | 177.71 | 0 | 0 | 1
332 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_2 under Jhargram Division in the District of Jhargram. | 302/MD | 15/02/2022 | 180 | LALIT BIHARI MAITY | 132.67 | 0 | 0 | 1
333 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpur-II_2_1 under Jhargram Division in the District of Jhargram. | 301/MD | 15/02/2022 | 180 | ASIS KUMAR SARANGI | 135.09 | 0 | 0 | 1
334 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_2 under Jhargram Division in the District of Jhargram. | 190/MD | 01/02/2022 | 180 | SUJATA CONSTRUCTION | 106.99 | 0 | 0 | 1
335 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_1 under Jhargram Division in the District of Jhargram. | 189/MD | 01/02/2022 | 180 | PROVAT KUMAR DE | 106.64 | 0 | 0 | 0
336 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_5 under Jhargram Division in the District of Jhargram. | 185/MD | 01/02/2022 | 180 | GOBINDA MAITY | 177.73 | 0 | 0 | 0
337 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_3 under Jhargram Division in the District of Jhargram. | 196/MD | 01/02/2022 | 180 | SUNIL DULE | 134.69 | 0 | 0 | 1
338 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_1 under Jhargram Division in the District of Jhargram. | 195/MD | 01/02/2022 | 180 | KISHORE GHOSH | 133.21 | 0 | 0 | 0
339 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_7 under Jhargram Division in the District of Jhargram. | 193/MD | 01/02/2022 | 180 | DIPAK KUMAR BAKLY | 108.29 | 0 | 0 | 0
340 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_15 under Jhargram Division in the District of Jhargram. | 187/MD | 01/02/2022 | 180 | GOBINDA MAITY | 177.7 | 0 | 0 | 1
341 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Material Requisition To Resource Division | 1851/MD | 07/09/2022 | 0 | Resource Division | 30.75 | 0 | 0 | 0
342 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Material Requisition To Resource Division | 1868/MD | 08/09/2022 | 0 | Resource Division | 30.75 | 0 | 0 | 0
343 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Material Requisition To Resource Division | 963-JHD | 23/06/2023 | 0 | Resource Division | 142.21 | 0 | 0 | 0
344 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | New service connection charges. | 8/JMD//PFMS/JAN | 11/01/2023 | 0 | WBSEDCL | 2.5 | 0 | 0 | 0
345 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | New service connection charges. | 27/JMD/PFMS/DEC | 20/12/2022 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
346 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Charges for WBSEDCL new service connection. | 7/JMD/PFMS/DEC | 07/12/2022 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
347 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | WBSEDCL payment for new service connection | 39/JMD/PFMS/DEC | 29/12/2022 | 0 | WBSEDCL | 19.57 | 0 | 0 | 0
348 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Fuel & Lubricant bill for supporting truck & Departmental Rig. Units for construction of Rig Bore tube wells under 269 mini scheme at different block of Jhargram district under P.H.E. Dte. (Scheme code:- SM/09915) | BP-2022-23-155 | 01/03/2023 | 0 | SURAJ SERVICE STATION | 24 | 0 | 0 | 0
349 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Transfer to EE/JSD, PHE Dte. ( Standalone PWSS) |  | 20/12/2022 | 0 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 102.67 | 0 | 0 | 0
350 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Transfer to EE/JSD, PHE Dte. ( Standalone PWSS) | BP-2022-23-465 | 24/12/2022 | 0 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 94.84 | 0 | 0 | 0
351 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Fuel and lubricant bill for Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Salika and others mouza of Jamboni and others blocks under stand alone piped water supply scheme (SM/09915) of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | BP-2023-24-195B | 15/09/2023 | 0 | SURAJ SERVICE STATION | 1.1 | 0 | 0 | 0
352 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | For new service connection charges for Goyaldanga, t/w-II w/s scheme. | 6/JMD/PFMS/DEC | 01/12/2022 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
353 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | New service connection charges | 15/JMD/PFMS/MAR | 06/03/2023 | 0 | WBSEDCL | 1.46 | 0 | 0 | 0
354 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing Fuel & Lubricants for construction of RBTW under 269 Stand Alone mini PWSS. | BP-2022-23-81 | 17/12/2022 | 0 | SURAJ SERVICE STATION | 14.34 | 0 | 0 | 0
355 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Fuel and lubricant bill for Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Tukurya and others mouza of Jamboni and others blocks under stand alone piped water supply scheme (SM/09915) of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | BP-2023-24-204 | 24/09/2023 | 0 | SURAJ SERVICE STATION | 9.93 | 0 | 0 | 0
356 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Fuel & Lubricant bill for Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Dhengabahara, Tube Well no.-II and others under Jamboni and other Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | BP-2023-24-286 | 08/11/2023 | 0 | SURAJ SERVICE STATION | 6.39 | 0 | 0 | 0
357 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Fuel & Lubricant bill for supporting truck & Departmental Rig. Units for construction of Rig Bore tube wells under 269 mini scheme at different block of Jhargram district under P.H.E. Dte. (Scheme code:- SM/09915) | BP-2022-23-204 | 30/03/2023 | 0 | SURAJ SERVICE STATION | 8.68 | 0 | 0 | 0
358 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | New service connection charges under 269 mini pwss (Scheme code:- SM/09915) | 16/JMD/PFMS/MAR | 06/03/2023 | 0 | WBSEDCL | 3.15 | 0 | 0 | 0
359 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | New service connection | 22/AUG | 25/08/2023 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
360 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | New service connection. | 10/JMD | 11/10/2023 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
361 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing PVC pipes and fittings for sinking of tube wells under Stand Alone Piped water supply scheme (SM/09915). | BP-2023-24-294 | 17/11/2023 | 0 | DURGAPUR POLYMERS PVT. LTD. | 4.89 | 0 | 0 | 0
362 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | New service connection charges. | 17JMD//PFMS/JAN | 20/01/2023 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
363 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | New service connection charges. | 13/JMD/PFMS/DEC | 17/12/2022 | 0 | WBSEDCL | 0.62 | 0 | 0 | 0
364 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Fuel and lubricant bill for Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Dhadka and others mouza of Jamboni and others blocks block under stand alone piped water supply scheme (SM/09915) of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | BP-2023-24-195 | 12/09/2023 | 0 | SURAJ SERVICE STATION | 4.5 | 0 | 0 | 0
365 | JHARGRAM | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Sankrail_3_1 under Jhargram Division in the District of Jhargram. | 877/MD | 10/05/2022 | 180 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 150.3 | 0 | 0 | 99
366 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) at Bara Negui and Kharikamathani GP of Nayagram Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | 350/JSD | 12/07/2022 | 15 | GOBINDA MAITY | 4.8 | 0 | 0 | 100
367 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Logistic and other support activities for training in 08 (eight) Blocks of Jhargram District for Skilling of Manpower to Generate Employment Opportunities and to Support Implementation of Jal Jeevan Mission under Jhargram Division P.H.E Dte. (1st Phase) | 168/JHD | 05/08/2022 | 180 | J.S.S. ENTERPRISE | 4.94 | 0 | 0 | 100
368 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_5 under Jhargram Division in the District of Jhargram. | 185/MD | 01/02/2022 | 1308 | GOBINDA MAITY | 177.73 | 0 | 0 | 100
369 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_15 under Jhargram Division in the District of Jhargram. | 187/MD | 01/02/2022 | 1308 | GOBINDA MAITY | 177.7 | 0 | 0 | 20
370 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_9 under Jhargram Division in the District of Jhargram. | 284/MD | 15/02/2022 | 180 | SRIMANTA KUMAR DE | 72.19 | 0 | 0 | 70
371 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-I_1_4 under Jhargram Division in the District of Jhargram. | 283/MD | 15/02/2022 | 180 | M/S. D.K.H.CONSTRUCTION | 72.23 | 0 | 0 | 90
372 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amlasol T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3065/JMD | 28/09/2022 | 120 | P.K. ENGINEERING | 6.79 | 0 | 0 | 0
373 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Salika Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4198/JMD | 28/12/2022 | 120 | DIPALI CONSTRUCTION | 5.78 | 0 | 0 | 80
374 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nargi Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4200/JMD | 28/12/2022 | 120 | A. G. ENTERPRISE | 5.77 | 0 | 0 | 75
375 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply,delivery, installation, commisioning & trial run of submersible pumping machinary and other Electro Mechanical accessories for Chandabila Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4194/JMD | 28/12/2022 | 120 | BINAPANI ENTERPRISE | 5.78 | 0 | 0 | 80
376 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khanderpara T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3098/JMD | 28/09/2022 | 120 | SANJIB SAHA | 5.72 | 0 | 0 | 90
377 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_14 under Jhargram Division in the District of Jhargram. | 186/MD | 01/02/2022 | 1308 | GOBINDA MAITY | 177.71 | 0 | 0 | 67
378 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_10 under Jhargram Division in the District of Jhargram. | 305/MD | 16/02/2022 | 180 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 177.75 | 0 | 0 | 51
379 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_2 under Jhargram Division in the District of Jhargram. | 302/MD | 15/02/2022 | 180 | LALIT BIHARI MAITY | 132.67 | 0 | 0 | 100
380 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Jamboni_1_1 under Jhargram Division in the District of Jhargram. | 188/MD | 01/02/2022 | 1335 | SUNIL DULE | 108 | 0 | 0 | 85
381 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_4_C under Jhargram Division in the District of Jhargram. | 276/JHD | 13/09/2022 | 120 | DHUMKETU ENGINEERING PRIVATE LIMITED | 20.52 | 0 | 0 | 100
382 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bam Diha T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3078/JMD | 28/09/2022 | 120 | BIJAN ENTERPRISE | 5.7 | 0 | 0 | 80
383 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_7 under Jhargram Division in the District of Jhargram. | 193/MD | 01/02/2022 | 180 | DIPAK KUMAR BAKLY | 108.29 | 0 | 0 | 95
384 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-I_1_3 under Jhargram Division in the District of Jhargram. | 292/MD | 15/02/2022 | 180 | BIDYUT KUMAR SANTRA | 89.66 | 0 | 0 | 90
385 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpur-I_4_2 under Jhargram Division in the District of Jhargram. | 217/MD | 03/02/2022 | 180 | MAHAVIR PUMPS MFG. PVT. LTD. | 118.44 | 0 | 0 | 30
386 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-I_3_2 under Jhargram Division in the District of Jhargram. | 197/MD | 01/02/2022 | 180 | MAHAVIR PUMPS MFG. PVT. LTD. | 100.58 | 0 | 0 | 40
387 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Jamboni_1_2 under Jhargram Division in the District of Jhargram. | 424/MD | 04/03/2022 | 180 | MIDNAPUR PIPE CONCERN | 104.95 | 0 | 0 | 50
388 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bali Muri Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 264/JMD | 03/02/2023 | 120 | P.K. ENGINEERING | 5.78 | 0 | 0 | 80
389 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-II_1_1 under Jhargram Division in the District of Jhargram. | 299/MD | 15/02/2022 | 180 | SAIKAT DANDAPAT | 100.15 | 0 | 0 | 100
390 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Hanri Bhanga stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3504/JMD | 29/11/2022 | 7 | PRANAB KUMAR DAS | 0.07 | 0 | 0 | 0
391 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-II_3_1 under Jhargram Division in the District of Jhargram. | 198/MD | 01/02/2022 | 180 | FIDERE MARINE SERVICES PVT. LTD. | 161 | 0 | 0 | 80
392 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Phul Berya stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3538/JMD | 29/11/2022 | 7 | DEB KUMAR BASU | 0.07 | 0 | 0 | 100
393 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Bardanga) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3488/JMD | 29/11/2022 | 7 | SUJOY RANJAN BHOWMICK | 0.07 | 0 | 0 | 0
394 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhulaburari T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3529/JMD | 29/11/2022 | 7 | SUJOY RANJAN BHOWMICK | 0.07 | 0 | 0 | 0
395 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-I_1_1 under Jhargram Division in the District of Jhargram. | 291/MD | 15/02/2022 | 180 | NIRMAL DUTTA | 89.46 | 0 | 0 | 80
396 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Maubhandar, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 462/JMD | 09/03/2023 | 120 | DEY ENTERPRISE | 5.78 | 0 | 0 | 100
397 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paika T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3487/JMD | 29/11/2022 | 7 | DEBJYOTI BASU | 0.07 | 0 | 0 | 0
398 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kankrajhor T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3446/JMD | 29/11/2022 | 7 | DEBJYOTI BASU | 0.07 | 0 | 0 | 0
399 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_4 under Jhargram Division in the District of Jhargram. | 191/MD | 01/02/2022 | 180 | FIDERE MARINE SERVICES PVT. LTD. | 107.15 | 0 | 0 | 100
400 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Baksa Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 665/JMD | 24/03/2023 | 120 | MENAKA ENTERPRISE | 5.78 | 0 | 0 | 95
401 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Totasai, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 661/JMD | 24/03/2023 | 285 | AMIT DAS | 5.77 | 0 | 0 | 70
402 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Thuria, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 962/JMD | 25/04/2023 | 120 | A.S. ENGINEERING | 5.78 | 0 | 0 | 90
403 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_3 under Jhargram Division in the District of Jhargram. | 300/MD | 15/02/2022 | 1090 | ASIS KUMAR SARANGI | 108.29 | 0 | 0 | 50
404 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Ramkrishnapur, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 965/JMD | 25/04/2023 | 120 | SUBHASIS ROY | 5.77 | 0 | 0 | 95
405 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Thuria, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 961/JMD | 25/04/2023 | 120 | GOENKA ENTERPRISE | 5.78 | 0 | 0 | 90
406 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kadam Diha, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 964/JMD | 25/04/2023 | 120 | TAPAN BISWAS | 5.77 | 0 | 0 | 95
407 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, Delivery & fitting fixing of fast moving spares (Air filter, ELGI Air lube plus) for preventive maintenance of compressor unit (Model:- 600-200, Make:- ELGI) attached with DR/DTH -500 (make:- KLR) rig unit under MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | 363/JMD | 23/02/2023 | 7 | B. P. TRADING CORPORATION | 0.82 | 0 | 0 | 0
408 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Jamboni_3_1 under Jhargram Division in the District of Jhargram. | 426/MD | 04/03/2022 | 1442 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 125.73 | 0 | 0 | 14
409 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Jamboni_3_2 under Jhargram Division in the District of Jhargram. | 427/MD | 04/03/2022 | 1442 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 100.58 | 0 | 0 | 25
410 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_13 under Jhargram Division in the District of Jhargram. | 431/MD | 04/03/2022 | 1440 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 177.59 | 0 | 0 | 40
411 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kankrajhor T/W no. -IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 1711/JMD | 13/07/2023 | 180 | MASSK ENGINEERING WORKS | 5.98 | 0 | 0 | 100
412 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gohalberya T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 1706/JMD | 13/07/2023 | 180 | DEBJYOTI BASU | 6.89 | 0 | 0 | 100
413 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nischintapur T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 1709/JMD | 13/07/2023 | 180 | M/S. EMMESS | 6.89 | 0 | 0 | 80
414 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rajpahari Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1762/JMD | 19/07/2023 | 120 | ASHOKE ADHIKARY | 5.76 | 0 | 0 | 95
415 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Damodarpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1763/JMD | 19/07/2023 | 120 | RS ELECTROMECHANICAL CORPORATION | 5.78 | 0 | 0 | 90
416 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Phulbani, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1766/JMD | 19/07/2023 | 120 | JAL PRAVAHIKA PVT. LTD. | 5.78 | 0 | 0 | 80
417 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Panisol Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1758/JMD | 19/07/2023 | 120 | K.S.P. ENTERPRISE | 5.74 | 0 | 0 | 75
418 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rai Gani, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1759/JMD | 19/07/2023 | 120 | DEBJYOTI BASU | 5.77 | 0 | 0 | 92
419 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dumaria Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1761/JMD | 19/07/2023 | 120 | S. PATHAK & CO. | 5.76 | 0 | 0 | 95
420 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tikra Para Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1821/JMD | 24/07/2023 | 120 | JIBON GHOSH | 5.78 | 0 | 0 | 80
421 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pathar Bandh, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1823/JMD | 24/07/2023 | 120 | CHAKRABORTY MINING & ENGINEERING | 5.77 | 0 | 0 | 100
422 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pathar Bandh, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1822/JMD | 24/07/2023 | 599 | ECO ENTERPRISE | 5.77 | 0 | 0 | 80
423 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tiyakati, Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1970/JMD | 31/07/2023 | 120 | SUBHAM ENTERPRISE | 5.78 | 0 | 0 | 60
424 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bankisol Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1838/JMD | 24/07/2023 | 120 | MENAKA ENTERPRISE | 5.78 | 0 | 0 | 100
425 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jadabpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1803/JMD | 24/07/2023 | 120 | PADMA ENGINEERING CO. | 5.78 | 0 | 0 | 80
426 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Malam, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1820/JMD | 24/07/2023 | 120 | ABHIJIT BASU | 5.78 | 0 | 0 | 70
427 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khas Jangal (G.P. - Malam) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1974/JMD | 31/07/2023 | 120 | J.K. ENGINEERING CO. | 5.78 | 0 | 0 | 90
428 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution pipeline with Community Tank & provision of FHTC for drought like situation situation prone area at different location under location ID Binpur_I_1_2 under Jhargram Division, in the district of Jhargram. | 868/MD | 10/05/2022 | 180 | SUBRATA DAS | 89.83 | 0 | 0 | 40
429 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Arra, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1829/JMD | 24/07/2023 | 120 | SRI KRISHNA NIRMAN | 5.78 | 0 | 0 | 80
430 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gokhur Pal Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1797/JMD | 24/07/2023 | 120 | BUSR ENGINEERING | 5.77 | 0 | 0 | 95
431 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bans Pat Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1799/JMD | 24/07/2023 | 120 | SOUMEN ELECTRIC | 5.78 | 0 | 0 | 70
432 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1806/JMD | 24/07/2023 | 120 | M/S. EMMESS | 5.78 | 0 | 0 | 90
433 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-V Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1807/JMD | 24/07/2023 | 120 | SOUMEN ELECTRIC | 5.78 | 0 | 0 | 100
434 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Kuldiha under Jamboni Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 2286/JMD | 10/08/2023 | 510 | CHAKRABORTY MINING & ENGINEERING | 3.37 | 0 | 0 | 100
435 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of 1(One) Nos. 150 mm X 100 mm X 135 Mtr. RBTW, for lowering of Submersible Pumping Machinery at Kamapukuria - IV Village Stand Alone PWSS for Nayagram Block under Jhargram Division, P.H.E. Dte. | 662/JSD | 20/07/2023 | 30 | GOUTAM KUMAR BOSE | 4.26 | 0 | 0 | 100
436 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Gohalberya mouza, tube well no.3 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 122/JMD | 31/01/2022 | 1125 | DEBJYOTI BASU | 0.15 | 0 | 0 | 100
437 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Gohalberya mouza, tube well no.4 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 123/JMD | 31/01/2022 | 1048 | DEBJYOTI BASU | 0.71 | 0 | 0 | 100
438 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Gohalberya mouza, tube well no.3 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 121/JMD | 31/01/2022 | 1125 | DEBJYOTI BASU | 0.71 | 0 | 0 | 100
439 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Gohalberya mouza, tube well no.4 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 124/JMD | 31/01/2022 | 1148 | DEBJYOTI BASU | 0.15 | 0 | 0 | 100
440 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Nischintapur mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 127/JMD | 31/01/2022 | 1125 | DEBJYOTI BASU | 0.71 | 0 | 0 | 100
441 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Nischintapur mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 128/JMD | 31/01/2022 | 1125 | DEBJYOTI BASU | 0.16 | 0 | 0 | 100
442 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Hiring of 1 (one) no Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new not older than 30 thirty) months from the date of 1st registration on daily hire rate basis for 04 (Four) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram Sub-Division, PHE Dte. (from 01.05.2023 to 31.08.2023). | 318/JSD | 26/04/2023 | 122 | BIDYUT KUMAR SANTRA | 0.69 | 0 | 0 | 100
443 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty) months from the date of Ist registration on daily hire rate basis for 6 (Six) months [from 01.08.2023 to 31.01.2024] only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram H.Q./RWS/Gopiballavpur Sub-Division PHE Dte. | 680/JSD | 27/07/2023 | 184 | JAGOMOHAN SETUA | 0.98 | 0 | 0 | 100
444 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Continuation work order for Providing one no. 10 MT capacity truck & one no 32 BHP Capacity Tractor along with licensed driver on daily basis for Rig unit no. 41D/LMP/500 of MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | 716/JMD | 28/03/2023 | 20 | M/S. SAMRIDDHI ENTERPRISE | 0.97 | 0 | 0 | 0
445 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Logistic and other support activities for training in 08 (eight) Blocks of Jhargram District for Skilling of Manpower to Generate Employment Opportunities and to Support Implementation of Jal Jeevan Mission under Jhargram Division P.H.E Dte. (2nd Phase) | 1367/JHD | 14/08/2023 | 56 | J.S.S. ENTERPRISE | 4.3 | 0 | 0 | 100
446 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | "Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority for the Office of the Executive Engineer, Jhargram Division, PHE Dte. for the period of 2 (Two) Month's, from 01.05.2023 to 30.06.2023. | 319/JSD | 27/04/2023 | 61 | SUNIL DULE | 0.29 | 0 | 0 | 100
447 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Installation of Iron Elimination Plant including PCC Concrete Platform at Maju Gora Stand Alone PWSS of Binpir-II Block under Jhargram Division PHE Dte. | 2291/JHD | 04/12/2024 | 60 | TREATAQUA | 7.1 | 0 | 0 | 0
448 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 02 (Two) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram H.Q./ RWS /Gopiballavpur Sub- Division PHE Dte.(from 01.05.2024 to 30.06.2024) | 507/JSD | 30/04/2024 | 61 | JAGOMOHAN SETUA | 0.32 | 0 | 0 | 100
449 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Balance FHTC Work of Augmentation of Khamar Piped Water Supply Scheme in Binpur-II Block within Jhargram District under Jhargram Division, P.H.E. Dte. | 209/JSD | 13/03/2024 | 21 | SAIKAT DANDAPAT | 1.32 | 0 | 0 | 0
450 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bhararu mouza of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 542/JMD | 23/12/2021 | 4 | DEBJYOTI BASU | 0.33 | 0 | 0 | 0
451 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under Binpur-II Block location Id Binpur-II_3_2_C under Jhargram Division in the District of Jhargram. | 445/JHD | 14/03/2024 | 60 | KOUSIK MONDAL | 19.87 | 0 | 0 | 20
452 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Hudhudi T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3518/JMD | 29/11/2022 | 7 | RMD TRADING | 0.07 | 0 | 0 | 0
453 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under Jamboni Block location Id Jamboni_4_1 under Jhargram Division in the District of Jhargram. 3rd Call (Ref: 1st Call eNIT_39 of 2022-23, SL No.-1, 2nd Call eNIT_11 of EE/JHD of 2023-24, SL No.-13) | 1133/JHD | 06/08/2024 | 60 | RUPKUMAR KARMAKAR | 19.2 | 0 | 0 | 0
454 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sankisol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1587/JMD | 27/07/2022 | 120 | DEB KUMAR BASU | 6.86 | 0 | 0 | 100
455 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sonamui stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1589/JMD | 27/07/2022 | 120 | P.K. ENGINEERING | 6.86 | 0 | 0 | 10
456 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Purna Pani stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1590/JMD | 27/07/2022 | 120 | SUBHASIS ROY | 6.86 | 0 | 0 | 100
457 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghjhapa stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1591/JMD | 27/07/2022 | 120 | M/S. SAMRIDDHI ENTERPRISE | 7.02 | 0 | 0 | 100
458 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Narcha stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1411/JMD | 14/07/2022 | 120 | ABHIJIT BASU | 6.86 | 0 | 0 | 50
459 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Nischinta stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1468/JMD | 19/07/2022 | 120 | S.S. GHORAI | 6.86 | 0 | 0 | 100
460 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Nischinta stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1469/JMD | 19/07/2022 | 120 | RITESH ENTERPRISE | 6.89 | 0 | 0 | 95
461 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Paschim Gholai stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1473/JMD | 19/07/2022 | 120 | M/S. NABIN GOPAL SENGUPTA | 6.87 | 0 | 0 | 100
462 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Tungadhua stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1467/JMD | 19/07/2022 | 120 | DEY ENTERPRISE | 6.79 | 0 | 0 | 95
463 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sri Ram Pur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1462/JMD | 19/07/2022 | 120 | MENAKA ENTERPRISE | 6.87 | 0 | 0 | 100
464 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Damujana stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1417/JMD | 14/07/2022 | 120 | SUBHASIS ROY | 6.87 | 0 | 0 | 100
465 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Goal Danga stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1418/JMD | 14/07/2022 | 120 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 7.02 | 0 | 0 | 100
466 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jarkasol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1452/JMD | 19/07/2022 | 120 | BUSR ENGINEERING | 6.86 | 0 | 0 | 100
467 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Rai Sol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1457/JMD | 19/07/2022 | 120 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 6.87 | 0 | 0 | 100
468 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Phul Berya stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1453/JMD | 19/07/2022 | 120 | DEB KUMAR BASU | 6.86 | 0 | 0 | 100
469 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chanda Bila stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1409/JMD | 14/07/2022 | 120 | DEBJYOTI BASU | 6.84 | 0 | 0 | 85
470 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Madhabpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1410/JMD | 14/07/2022 | 120 | SUJOY RANJAN BHOWMICK | 6.86 | 0 | 0 | 95
471 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bankra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1454/JMD | 19/07/2022 | 120 | MONORANJAN DEY | 6.86 | 0 | 0 | 10
472 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1412/JMD | 14/07/2022 | 120 | DEBJYOTI BASU | 6.84 | 0 | 0 | 98
473 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bhadai stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1456/JMD | 19/07/2022 | 120 | P.K. ENGINEERING | 6.86 | 0 | 0 | 100
474 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kumarbandh stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1413/JMD | 14/07/2022 | 120 | BHABANI PRASAD MANNA | 6.86 | 0 | 0 | 95
475 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Tungadhua stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1466/JMD | 19/07/2022 | 120 | T.N. BANERJEE | 6.86 | 0 | 0 | 100
476 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Shutpipal stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1728/JMD | 17/08/2022 | 120 | DEBJYOTI BASU | 6.84 | 0 | 0 | 100
477 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kargonala stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1729/JMD | 17/08/2022 | 120 | ECO ENTERPRISE | 6.87 | 0 | 0 | 100
478 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bag Doba stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1730/JMD | 17/08/2022 | 120 | SHOVAN KUMAR DAS | 6.87 | 0 | 0 | 100
479 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jhaurishol stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1737/JMD | 17/08/2022 | 120 | S.K. ENTERPRISE | 6.85 | 0 | 0 | 100
480 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chilkigar stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1588/JMD | 27/07/2022 | 120 | DIPALI CONSTRUCTION | 6.79 | 0 | 0 | 95
481 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bhurkundi stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1592/JMD | 27/07/2022 | 120 | M/S. SAJAHAN CHOWDHURY | 6.82 | 0 | 0 | 100
482 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jamda Hara stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1736/JMD | 17/08/2022 | 120 | MASSK ENGINEERING WORKS | 6.86 | 0 | 0 | 100
483 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) at Arrah and Malam GP of Nayagram Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | 46/GPSD | 29/08/2022 | 15 | MAKALI ENGG. CORPORATION | 4.8 | 0 | 0 | 100
484 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) for Jhargram & Gopiballavpur-II Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | 355/JSD | 15/07/2022 | 15 | MAKALI ENGG. CORPORATION | 4.8 | 0 | 0 | 100
485 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kalma Pukhuria stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1731/JMD | 17/08/2022 | 120 | S.S. GHORAI | 6.86 | 0 | 0 | 100
486 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bara Khankri stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1732/JMD | 17/08/2022 | 120 | M/S. EMMESS | 6.83 | 0 | 0 | 0
487 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chhota Khankri stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1733/JMD | 17/08/2022 | 120 | A. G. ENTERPRISE | 6.85 | 0 | 0 | 95
488 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Amtalia stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1585/JMD | 27/07/2022 | 120 | MENAKA ENTERPRISE | 6.87 | 0 | 0 | 90
489 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghakhondar stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1586/JMD | 27/07/2022 | 120 | ABHIJIT BASU | 6.86 | 0 | 0 | 90
490 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Jharia T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3625/JMD | 07/12/2022 | 120 | RITESH ENTERPRISE | 5.71 | 0 | 0 | 100
491 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhulaburari T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3324/JMD | 14/11/2022 | 120 | SUJOY RANJAN BHOWMICK | 5.71 | 0 | 0 | 100
492 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Niramishpur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3620/JMD | 07/12/2022 | 120 | BUSR ENGINEERING | 5.7 | 0 | 0 | 100
493 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Koima (Pal) T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3072/JMD | 28/09/2022 | 120 | M/S. EMMESS | 5.71 | 0 | 0 | 100
494 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nuagarh T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3083/JMD | 28/09/2022 | 120 | CHAKRABORTY MINING & ENGINEERING | 5.7 | 0 | 0 | 100
495 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Goal Danga T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3621/JMD | 07/12/2022 | 120 | MAA TARA ENTERPRISE | 5.72 | 0 | 0 | 100
496 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Khankri T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3622/JMD | 07/12/2022 | 120 | PRANAB KUMAR DAS | 5.7 | 0 | 0 | 95
497 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Khankri T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3623/JMD | 07/12/2022 | 120 | BHABANI PRASAD MANNA | 5.72 | 0 | 0 | 100
498 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rajpara T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3097/JMD | 28/09/2022 | 120 | DEB KUMAR BASU | 5.75 | 0 | 0 | 100
499 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jugi Bandh T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3628/JMD | 07/12/2022 | 120 | SUBHAM ENTERPRISE | 5.73 | 0 | 0 | 100
500 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rangamatia T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3079/JMD | 28/09/2022 | 120 | J.K. ENGINEERING CO. | 5.7 | 0 | 0 | 100
501 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpir-I_2_1_C under Jhargram Division in the District of Jhargram. | 346/JHD | 28/09/2022 | 120 | BISHNU PADA NANDI | 22.38 | 0 | 0 | 1
502 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Didiha T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3086/JMD | 28/09/2022 | 120 | BEE GEE CONSTRUCTION | 5.7 | 0 | 0 | 100
503 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jamboni T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3192/JMD | 28/10/2022 | 120 | ARATI ENGINEERING | 5.72 | 0 | 0 | 100
504 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gaida Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4201/JMD | 28/12/2022 | 120 | A.S. ENTERPRISE | 5.78 | 0 | 0 | 100
505 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Degaria Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4196/JMD | 28/12/2022 | 120 | CHATTERJEE CONSTRUCTION | 5.78 | 0 | 0 | 100
506 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Jamboni_1_3 under Jhargram Division in the District of Jhargram. | 318/MD | 17/02/2022 | 180 | ASIS KUMAR SARANGI | 90.24 | 0 | 0 | 40
507 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pathar Chakri T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3084/JMD | 28/09/2022 | 120 | B. P. TRADING CORPORATION | 5.71 | 0 | 0 | 100
508 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chilkigarh Stand Alone piped water supply scheme, tube well no-II of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4206/JMD | 28/12/2022 | 120 | BUSR ENGINEERING | 5.77 | 0 | 0 | 100
509 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Brindabanpur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3088/JMD | 28/09/2022 | 120 | A.S. ENTERPRISE | 5.7 | 0 | 0 | 100
510 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Murakati T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3077/JMD | 28/09/2022 | 120 | A. G. ENTERPRISE | 5.7 | 0 | 0 | 100
511 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Salgaria (Near Club) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3089/JMD | 28/09/2022 | 120 | SAMARPITA ENGINEERING | 5.72 | 0 | 0 | 100
512 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3090/JMD | 28/09/2022 | 120 | SUBHASIS ROY | 5.7 | 0 | 0 | 100
513 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Purba Para) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3094/JMD | 28/09/2022 | 120 | DEB KUMAR BASU | 5.71 | 0 | 0 | 100
514 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluk Chua T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3087/JMD | 28/09/2022 | 120 | S.K. ENTERPRISE | 5.71 | 0 | 0 | 100
515 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_4_A under Jhargram Division in the District of Jhargram. | 347/JHD | 28/09/2022 | 120 | M/S. SANKAR KUMAR NAG | 22.33 | 0 | 0 | 100
516 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3091/JMD | 28/09/2022 | 120 | M/S. SAMRIDDHI ENTERPRISE | 5.71 | 0 | 0 | 100
517 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3092/JMD | 28/09/2022 | 120 | ECO ENTERPRISE | 5.71 | 0 | 0 | 100
518 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Kutisai) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3159/JMD | 19/10/2022 | 120 | ABHIJIT BASU | 5.71 | 0 | 0 | 100
519 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Baradhan Sola T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3166/JMD | 19/10/2022 | 120 | M.D. ENTERPRISE | 5.7 | 0 | 0 | 0
520 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rukhni Mara (Village) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3093/JMD | 28/09/2022 | 120 | CHATTERJEE CONSTRUCTION | 5.71 | 0 | 0 | 100
521 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khanakul T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3085/JMD | 28/09/2022 | 120 | RSA ENTERPRISE | 5.71 | 0 | 0 | 0
522 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Antapati T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3168/JMD | 19/10/2022 | 120 | R.K. ENTERPRISES | 5.7 | 0 | 0 | 0
523 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalinagar T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3169/JMD | 19/10/2022 | 120 | SHIVAM ENTERPRISE | 5.7 | 0 | 0 | 0
524 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Koima (A.W.C.) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3170/JMD | 19/10/2022 | 120 | M/S. EMMESS | 5.7 | 0 | 0 | 100
525 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tukurya Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4199/JMD | 28/12/2022 | 120 | RADHARANI ENTERPRISE | 5.77 | 0 | 0 | 100
526 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kiajharia T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3163/JMD | 19/10/2022 | 120 | M/S. CHANDRANATH MUKHERJEE | 5.71 | 0 | 0 | 95
527 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paika T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3156/JMD | 19/10/2022 | 120 | DEBJYOTI BASU | 5.71 | 0 | 0 | 100
528 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Bardanga) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3194/JMD | 28/10/2022 | 120 | SUJOY RANJAN BHOWMICK | 5.71 | 0 | 0 | 100
529 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_4_B under Jhargram Division in the District of Jhargram. | 320/JHD | 21/09/2022 | 120 | RAMENDRA NATH KAR | 22.3 | 0 | 0 | 100
530 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Murar, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 146/JMD | 19/01/2023 | 120 | MAA BHABOTARINE ENTERPRISE | 5.77 | 0 | 0 | 100
531 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Naharia, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 150/JMD | 19/01/2023 | 120 | SUBHASIS ROY | 5.77 | 0 | 0 | 100
532 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_1 under Jhargram Division in the District of Jhargram. | 195/MD | 28/12/2022 | 180 | KISHORE GHOSH | 133.21 | 0 | 0 | 100
533 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_4 under Jhargram Division in the District of Jhargram. | 876/MD | 10/05/2022 | 180 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 177.59 | 0 | 0 | 100
534 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jamboni Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 259/JMD | 03/02/2023 | 120 | DEB KUMAR BASU | 5.78 | 0 | 0 | 95
535 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Parashia, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 262/JMD | 03/02/2023 | 120 | RSA ENTERPRISE | 5.78 | 0 | 0 | 100
536 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Parashia, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 263/JMD | 03/02/2023 | 120 | RSA ENTERPRISE | 5.78 | 0 | 0 | 100
537 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Hudhudi T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3069/JMD | 28/09/2022 | 120 | RMD TRADING | 5.7 | 0 | 0 | 100
538 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Shibanandapur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3070/JMD | 28/09/2022 | 120 | BALAJI CONSTRUCTION | 5.71 | 0 | 0 | 100
539 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Lakhipara (School) T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3071/JMD | 28/09/2022 | 120 | MONORANJAN DEY | 5.71 | 0 | 0 | 100
540 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Ram Chandra Pur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 144/JMD | 19/01/2023 | 120 | SUJOY RANJAN BHOWMICK | 5.78 | 0 | 0 | 10
541 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sahari Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4203/JMD | 28/12/2022 | 120 | PINTU DEY | 5.78 | 0 | 0 | 100
542 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kandnashol, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 257/JMD | 03/02/2023 | 120 | M/S. EMMESS | 5.78 | 0 | 0 | 100
543 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paika, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 267/JMD | 03/02/2023 | 120 | DEBJYOTI BASU | 5.77 | 0 | 0 | 10
544 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Menia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 256/JMD | 03/02/2023 | 120 | M/S A.D. CONCERN | 5.78 | 0 | 0 | 95
545 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Biriberia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 258/JMD | 03/02/2023 | 120 | MAA TARA ENTERPRISE | 5.78 | 0 | 0 | 100
546 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai, Tube Well no.-IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 266/JMD | 03/02/2023 | 120 | ABHIJIT BASU | 5.78 | 0 | 0 | 100
547 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Naharia, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 136/JMD | 18/01/2023 | 120 | SOUMEN ELECTRIC | 5.78 | 0 | 0 | 0
548 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Harki Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 137/JMD | 18/01/2023 | 120 | PADMA ENGINEERING CO. | 5.78 | 0 | 0 | 100
549 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Madhabpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3431/JMD | 29/11/2022 | 7 | SUJOY RANJAN BHOWMICK | 0.07 | 0 | 0 | 100
550 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chanda Bila stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3443/JMD | 29/11/2022 | 7 | DEBJYOTI BASU | 0.07 | 0 | 0 | 100
551 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhansola Chhota Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 311/JMD | 09/02/2023 | 120 | RADHARANI ENTERPRISE | 5.77 | 0 | 0 | 95
552 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Murar, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 145/JMD | 19/01/2023 | 120 | DEBJYOTI BASU | 5.77 | 0 | 0 | 97
553 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3444/JMD | 29/11/2022 | 7 | SUJOY RANJAN BHOWMICK | 0.07 | 0 | 0 | 100
554 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Narendrapur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 148/JMD | 19/01/2023 | 120 | CHATTERJEE CONSTRUCTION | 5.77 | 0 | 0 | 100
555 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Khankri T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3500/JMD | 29/11/2022 | 7 | PRANAB KUMAR DAS | 0.07 | 0 | 0 | 100
556 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3433/JMD | 29/11/2022 | 7 | DEBJYOTI BASU | 0.07 | 0 | 0 | 100
557 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Maubhandar, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 255/JMD | 03/02/2023 | 120 | DEY ENTERPRISE | 5.78 | 0 | 0 | 100
558 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nargi mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 569/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.77 | 0 | 0 | 100
559 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bihankuria Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 657/JMD | 24/03/2023 | 120 | SHIVAM ENTERPRISE | 5.75 | 0 | 0 | 100
560 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Ningui, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 658/JMD | 24/03/2023 | 120 | DEBJYOTI BASU | 5.77 | 0 | 0 | 95
561 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Totasai, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 662/JMD | 24/03/2023 | 120 | M.D. ENTERPRISE | 5.78 | 0 | 0 | 80
562 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Astia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 664/JMD | 24/03/2023 | 120 | B. P. TRADING CORPORATION | 5.78 | 0 | 0 | 100
563 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Ningui, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 659/JMD | 24/03/2023 | 120 | DEBJYOTI BASU | 5.77 | 0 | 0 | 95
564 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhalia Ghati, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 660/JMD | 24/03/2023 | 120 | P.K. ENGINEERING | 5.78 | 0 | 0 | 95
565 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 957/JMD | 25/04/2023 | 120 | MENAKA ENTERPRISE | 5.78 | 0 | 0 | 95
566 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Deulbar, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 959/JMD | 25/04/2023 | 120 | DEB KUMAR BASU | 5.78 | 0 | 0 | 95
567 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sankarbani Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 953/JMD | 25/04/2023 | 120 | SRI KRISHNA NIRMAN | 5.78 | 0 | 0 | 100
568 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Continuation Work Order For "Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority for the Office of the Executive Engineer, Jhargram Division, PHE Dte. for the period of 2 (Two) Month's, from 01.03.2023 to 30.04.2023. | 146/JSD | 27/02/2023 | 59 | SUNIL DULE | 0.29 | 0 | 0 | 99
569 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Ramkrishnapur, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 967/JMD | 25/04/2023 | 120 | SOUMEN ELECTRIC | 5.78 | 0 | 0 | 100
570 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paira Kuli, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 955/JMD | 25/04/2023 | 120 | A.K. SIKDAR | 5.77 | 0 | 0 | 100
571 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 956/JMD | 25/04/2023 | 120 | P.K. ENGINEERING | 5.78 | 0 | 0 | 95
572 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Nargi mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 570/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 100
573 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority valid for the State of West Bengal not older than 2 years from the date of 1st Registration on daily Hire rate basis for the period from 01.12.2022 to 15.05.2023. for the Movement of Junior Engineer (RWS) under Jhargram Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, fees etc., as applicable. Diesel-12KM/Lit. Mobil-500KM/Lit. | 664 | 28/11/2022 | 166 | TAPAN KUMAR UPADHYAY | 0.93 | 0 | 0 | 80
574 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kadam Diha, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 963/JMD | 25/04/2023 | 120 | M/S. P.P. ELECTRICALS | 5.77 | 0 | 0 | 95
575 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paira Kuli, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 954/JMD | 25/04/2023 | 120 | SINHA ELECTRICALS | 5.62 | 0 | 0 | 95
576 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kandnashol, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1359/JMD | 06/06/2023 | 120 | MONORANJAN DEY | 5.77 | 0 | 0 | 95
577 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jagannathpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1206/JMD | 25/05/2023 | 120 | MASSK ENGINEERING WORKS | 5.78 | 0 | 0 | 95
578 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chandabila, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1207/JMD | 25/05/2023 | 120 | M/S. EMMESS | 5.78 | 0 | 0 | 95
579 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhararu T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 1712/JMD | 13/07/2023 | 120 | SOUMEN ELECTRIC | 5.98 | 0 | 0 | 100
580 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amadubi T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 985/JMD | 26/04/2023 | 180 | ABHIJIT BASU | 6.89 | 0 | 0 | 95
581 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Andharisol, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 987/JMD | 26/04/2023 | 120 | SHOVAN KUMAR DAS | 5.78 | 0 | 0 | 95
582 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pukhuria, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1727/JMD | 14/07/2023 | 120 | SAMARPITA ENGINEERING | 5.78 | 0 | 0 | 95
583 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pukhuria, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1728/JMD | 14/07/2023 | 120 | M/S. SAMRIDDHI ENTERPRISE | 5.78 | 0 | 0 | 100
584 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sanuningui, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1729/JMD | 14/07/2023 | 120 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 5.78 | 0 | 0 | 95
585 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sanuningui, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1730/JMD | 14/07/2023 | 120 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 5.78 | 0 | 0 | 95
586 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kankrajhor T/W no. -III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 986/JMD | 24/04/2023 | 120 | DEB KUMAR BASU | 5.98 | 0 | 0 | 95
587 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rai Gani, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1760/JMD | 19/07/2023 | 120 | ABHIJIT BASU | 5.78 | 0 | 0 | 100
588 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Deulbar, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1771/JMD | 19/07/2023 | 120 | ABHIJIT BASU | 5.78 | 0 | 0 | 100
589 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rangua T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 2021/JMD | 02/08/2023 | 120 | MENAKA ENTERPRISE | 5.78 | 0 | 0 | 100
590 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dingla Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1841/JMD | 24/07/2023 | 120 | A.M.S. ENTERPRISE | 5.75 | 0 | 0 | 100
591 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank and provision of FHTC for drought like situation prone areas at different location under Binpur-II Block location Id Binpur-II_3_2_A under Jhargram Division in the District of Jhargram. | 1205/JHD | 26/07/2023 | 60 | MANISHIKA CONSTRUCTION | 19.86 | 0 | 0 | 100
592 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khatkura Jr. High School Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 2633/JMD | 29/08/2023 | 120 | MOUSUMI BANERJEE | 5.77 | 0 | 0 | 100
593 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Malam mouza , tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 697/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 0 | 0 | 100
594 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 3 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 675/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 0 | 0 | 100
595 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria , tube well no. 4 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 1052/JMD | 01/06/2022 | 5 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.78 | 0 | 0 | 100
596 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Jadabpur mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 664/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0 | 0 | 100
597 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Malam mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 700/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0 | 0 | 100
598 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Tikra Para mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 706/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0 | 0 | 100
599 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Jadabpur mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 663/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 0 | 0 | 100
600 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 4 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 1053/JMD | 01/06/2022 | 5 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0 | 0 | 100
601 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Organizing Inauguration Ceremony of Different Commissioned Piped Water Supply Schemes for IEC Activities in Different Places within Jhargram District under Jhargram Division, PHE Dte. (Location ID_1) | 341/JSD | 11/05/2023 | 45 | NRIPENDRA NATH SINGHA | 0.69 | 0 | 0 | 100
602 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Narda stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1458/JMD | 19/07/2022 | 120 | ECO ENTERPRISE | 6.87 | 0 | 0 | 100
603 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Chilkigar mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 565/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.62 | 0 | 0 | 100
604 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Chilkigar mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 566/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 100
605 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Panisol Primary School under Gopiballavpur-I Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 2984/JMD | 16/10/2023 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.37 | 0 | 0 | 100
606 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Tiyakati mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 647/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 2.6 | 0 | 0 | 100
607 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Tiyakati mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 648/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 0.33 | 0 | 0 | 100
608 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing additional FHTC under Stand Alone PWSS, in Shankarbani Mouza, Jhargram Block under Jhargram Division, PHE Dte. | 1988/JHD | 29/11/2023 | 30 | ASHIS SHEE | 0.87 | 0 | 0 | 100
609 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Extension of distribution pipe line and its allied works at different location under location Id Jhargram_2_2 for 269 Stand alone PWSS under Jhargram Division, PHE Dte. | 3078/JHD | 26/12/2023 | 30 | LALIT BIHARI MAITY | 3.35 | 0 | 0 | 100
610 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Hanri Bhanga stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1464/JMD | 19/07/2022 | 120 | PRANAB KUMAR DAS | 6.86 | 0 | 0 | 100
611 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Installation of Display Bord for JJM works at different piped water supply scheme within Gopiballavpur-I Block under Jhargram Division, PHE dte. (1st Phase) | 53/JHD | 10/01/2024 | 45 | MANOJ KUMAR MAHATA | 0.91 | 0 | 0 | 100
612 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Installation of Display Bord for JJM works at different piped water supply scheme within Binpur-II Block under Jhargram Division, PHE dte. (1st Phase) | 52/JHD | 10/01/2024 | 45 | PRINT PREVIEW | 0.91 | 0 | 0 | 100
613 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply delivery of CIDF S/V , CI Specials, Jiffy Coupler etc. for the work of O & M of Different Water Supply Scheme under Jhargram Sub Division within Jhargram Division, PHE Dte. | 977/JSD | 17/11/2023 | 7 | NRIPENDRA NATH SINGHA | 0.96 | 0 | 0 | 100
614 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khatkhura T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3627/JMD | 07/12/2022 | 120 | SHOVAN KUMAR DAS | 5.72 | 0 | 0 | 10
615 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Installation of Display Bord for JJM works at different piped water supply scheme within Gopiballavpur-II Block under Jhargram Division, PHE dte. (1st Phase) | 54/JHD | 10/01/2024 | 45 | MANOJ KUMAR MAHATA | 0.91 | 0 | 0 | 100
616 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Continuation Work for Uploading, Development upgradation of all collected FHTC data and special features alongwith reorientation of JJM_ IMIS Dashboard. (including all charges i.e. contructor profit etc.) for September-2023 to November-2023 under Jhargram Division, PHE Dte. | 194/JRWS | 29/08/2023 | 90 | GOPAL JANA | 0.83 | 0 | 0 | 100
617 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Installation of Display Bord for JJM works at different piped water supply scheme within Binpur-I Block under Jhargram Division, PHE dte. (1st Phase) | 51/JHD | 10/01/2024 | 45 | PRINT PREVIEW | 0.91 | 0 | 0 | 100
618 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Continuation Work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission from 01.02.2024 to 15.02.2024 under Jhargram Division PHE Dte. | 374/JRWS | 29/01/2024 | 15 | JAGOMOHAN SETUA | 0.63 | 0 | 0 | 100
619 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for December 2023 under Jhargram Division PHE Dte | 285/JRWS | 28/11/2023 | 31 | JAGOMOHAN SETUA | 0.95 | 0 | 0 | 100
620 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional (90 mm) pipeline distribution and associated works for Standalone PWSS at Nuagarh in Bandhgora GP under Jhargram division, Phe Dte. | 1968/JHD | 21/10/2024 | 30 | ASHIS SHEE | 0.49 | 0 | 0 | 100
621 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional (63 mm) pipeline distribution and associated works for Standalone PWSS at Nuagarh in Bandhgora GP under Jhargram division, Phe Dte. | 1969/JHD | 21/10/2024 | 30 | ASHIS SHEE | 0.84 | 0 | 0 | 100
622 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Jharia T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3501/JMD | 29/11/2022 | 7 | M/S B.M. ELECTRICAL | 0.07 | 0 | 0 | 100
623 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Jharia T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3502/JMD | 29/11/2022 | 7 | RITESH ENTERPRISE | 0.07 | 0 | 0 | 100
624 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Arra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3455/JMD | 29/11/2022 | 7 | M/S B.M. ELECTRICAL | 0.07 | 0 | 0 | 100
625 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Continuation work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January 2024 under Jhargram Division PHE Dte. | 338/JRWS | 29/12/2023 | 31 | JAGOMOHAN SETUA | 0.89 | 0 | 0 | 100
626 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well-2 (Location ID Jamboni_4_2) at Mouza- Dumuria in Jamboni Block of Jhargram District under Jhargram Division, PHE Dte. | 1039/JHD | 22/07/2024 | 30 | FIROJ KHAN | 5.32 | 0 | 0 | 100
627 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well-2 (Location ID Jamboni_4_3) at Mouza- Dumuria in Jamboni Block of Jhargram District under Jhargram Division, PHE Dte. | 923/JHD | 09/07/2024 | 30 | BISHNU PADA NANDI | 5.63 | 0 | 0 | 100
628 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Fuel and lubricant bill for Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at different blocks under stand alone piped water supply scheme (SM/09915) of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | BP-2023-24-600 | 30/03/2024 | 0 | SURAJ SERVICE STATION | 0.63 | 0 | 0 | 0
629 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply of 10 nos. DSC - Class 3 Combo - 2 years under Jhargram Division, PHE Dte. | BP-2024-25-297 | 10/12/2024 | 0 | GOPAL JANA | 0.31 | 0 | 0 | 0
630 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Fuel and lubricant bill for Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Khatkura and others mouza of Jamboni and others blocks under stand alone piped water supply scheme (SM/09915) of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | BP-2023-24-524 | 12/03/2024 | 0 | SURAJ SERVICE STATION | 1.62 | 0 | 0 | 0
631 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Charges for periodical filing of various statutory deductions viz. GST, IT, Cess, Revenue, P.Tax etc. under Jhargram Division, PHE Dte. Period | BP-2024-25-296 | 10/12/2024 | 0 | NIGAM CONSULTANCY SERVICES | 0.96 | 0 | 0 | 0
632 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Arra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 1463/JMD | 19/07/2022 | 709 | M/S B.M. ELECTRICAL | 6.86 | 0 | 0 | 100
633 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpir-I_2_1_D under Jhargram Division in the District of Jhargram. | 455/JHD | 11/11/2022 | 120 | ASSOCIATED ENGINEERS & TRADERS | 22.38 | 0 | 0 | 100
634 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_3 under Jhargram Division in the District of Jhargram. | 196/MD | 01/02/2022 | 180 | SUNIL DULE | 134.69 | 0 | 0 | 90
635 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jugi Bandh T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3629/JMD | 07/12/2022 | 480 | COMBINE ENTERPRISES | 5.71 | 0 | 0 | 100
636 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhengbahara Stand Alone piped water supply scheme, tube well no-I of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4202/JMD | 28/12/2022 | 765 | SUBHRA ENTERPRISE | 5.78 | 0 | 0 | 100
637 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Jharia T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3624/JMD | 07/12/2022 | 568 | M/S B.M. ELECTRICAL | 5.7 | 0 | 0 | 100
638 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Muniada T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3626/JMD | 07/12/2022 | 480 | R.N.S. TRADING | 5.73 | 0 | 0 | 100
639 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluka Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4205/JMD | 28/12/2022 | 459 | COMBINE ENTERPRISES | 5.78 | 0 | 0 | 95
640 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_1 under Jhargram Division in the District of Jhargram. | 189/MD | 01/02/2022 | 180 | PROVAT KUMAR DE | 106.64 | 0 | 0 | 100
641 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_3 under Jhargram Division in the District of Jhargram. | 218/MD | 03/02/2022 | 180 | MAHAVIR PUMPS MFG. PVT. LTD. | 177.75 | 0 | 0 | 75
642 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Benachapra Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 149/JMD | 19/01/2023 | 792 | ABHIJIT MUKHERJEE | 5.78 | 0 | 0 | 100
643 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Sol, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 260/JMD | 03/02/2023 | 451 | M/S D.G.B. ENTERPRISE | 5.78 | 0 | 0 | 100
644 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_6 under Jhargram Division in the District of Jhargram. | 1013/MD | 27/05/2022 | 1085 | MONDAL PRECISION PRIVATE LIMITED | 176.7 | 0 | 0 | 82
645 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_7 under Jhargram Division in the District of Jhargram. | 1014/MD | 27/05/2022 | 1034 | MONDAL PRECISION PRIVATE LIMITED | 176.7 | 0 | 0 | 86
646 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_9 under Jhargram Division in the District of Jhargram. | 1015/MD | 27/05/2022 | 1085 | MONDAL PRECISION PRIVATE LIMITED | 177.73 | 0 | 0 | 81
647 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Kutisai) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3491/JMD | 29/11/2022 | 7 | ABHIJIT BASU | 0.07 | 0 | 0 | 0
648 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Narcha stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3432/JMD | 29/11/2022 | 763 | ABHIJIT BASU | 0.07 | 0 | 0 | 100
649 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghakhondar stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 3542/JMD | 29/11/2022 | 7 | ABHIJIT BASU | 0.07 | 0 | 0 | 100
650 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tentulia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 142/JMD | 19/01/2023 | 718 | SOUMEN ELECTRIC | 5.78 | 0 | 0 | 70
651 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_11 under Jhargram Division in the District of Jhargram. | 219/MD | 03/02/2022 | 180 | SANYUKTA ENGINEERING PVT. LTD. | 177.68 | 0 | 0 | 40
652 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Jamboni_3_3 under Jhargram Division in the District of Jhargram. | 199/MD | 01/02/2022 | 180 | FIDERE MARINE SERVICES PVT. LTD. | 161.08 | 0 | 0 | 75
653 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_8 under Jhargram Division in the District of Jhargram. | 194/MD | 01/02/2022 | 1098 | PALCON | 107.05 | 0 | 0 | 50
654 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_12 under Jhargram Division in the District of Jhargram. | 220/MD | 03/02/2022 | 1004 | CARBON SERVICES INDIA | 176.88 | 0 | 0 | 50
655 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-I_3_1 under Jhargram Division in the District of Jhargram. | 303/MD | 15/02/2022 | 1086 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 100.66 | 0 | 0 | 70
656 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Patina, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 958/JMD | 25/04/2023 | 598 | SUJOY RANJAN BHOWMICK | 5.78 | 0 | 0 | 100
657 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_8 under Jhargram Division in the District of Jhargram. | 430/MD | 04/03/2022 | 1440 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 177.59 | 0 | 0 | 45
658 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_1 under Jhargram Division in the District of Jhargram. | 428/MD | 04/03/2022 | 1440 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 177.59 | 0 | 0 | 40
659 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_2 under Jhargram Division in the District of Jhargram. | 429/MD | 04/03/2022 | 1440 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 177.59 | 0 | 0 | 50
660 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Patina, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1770/JMD | 19/07/2023 | 514 | SUJOY RANJAN BHOWMICK | 5.78 | 0 | 0 | 70
661 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Phulbani, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1765/JMD | 19/07/2023 | 651 | M/S D.G.B. ENTERPRISE | 5.78 | 0 | 0 | 70
662 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Taldangra Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1764/JMD | 19/07/2023 | 650 | DAS CONSTRUCTION | 5.78 | 0 | 0 | 100
663 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Muniada T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1967/JMD | 31/07/2023 | 220 | RUBY ENTERPRISE | 5.78 | 0 | 0 | 100
664 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kul Diha, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1828/JMD | 24/07/2023 | 704 | B. P. TRADING CORPORATION | 5.78 | 0 | 0 | 90
665 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kul Diha, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1973/JMD | 31/07/2023 | 598 | SOUMEN ELECTRIC | 5.78 | 0 | 0 | 100
666 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Panchami Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 265/JMD | 03/02/2023 | 331 | BALAJI CONSTRUCTION | 5.78 | 0 | 0 | 100
667 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gorur Ghata Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1796/JMD | 24/07/2023 | 240 | BEE GEE CONSTRUCTION | 5.78 | 0 | 0 | 96
668 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Kati Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1824/JMD | 24/07/2023 | 589 | PRANAB KUMAR DAS | 5.78 | 0 | 0 | 100
669 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Andharisol, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1968/JMD | 31/07/2023 | 306 | BALAJI CONSTRUCTION | 5.78 | 0 | 0 | 100
670 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nagri Pada, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1972/JMD | 31/07/2023 | 773 | S.S. GHORAI | 5.78 | 0 | 0 | 100
671 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria , tube well no. 5 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 1054/JMD | 01/06/2022 | 1096 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.78 | 0 | 0 | 100
672 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Nischintapur mouza, tube well no.1 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 125/JMD | 31/01/2022 | 1125 | DEBJYOTI BASU | 0.71 | 0 | 0 | 100
673 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Lekraanchra mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 107/JMD | 31/01/2022 | 475 | DEBJYOTI BASU | 0.71 | 0 | 0 | 100
674 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Kankrajhor mouza, tube well no.4 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 91/JMD | 31/01/2022 | 608 | DEBJYOTI BASU | 0.71 | 0 | 0 | 100
675 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_2 under Jhargram Division in the District of Jhargram | 190/MD | 01/02/2022 | 180 | SUJATA CONSTRUCTION | 106.99 | 0 | 0 | 70
676 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Nischintapur mouza, tube well no.1 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 126/JMD | 31/01/2022 | 1125 | DEBJYOTI BASU | 0.16 | 0 | 0 | 100
677 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Kankrajhor mouza, tube well no.4 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 92/JMD | 31/01/2022 | 608 | DEBJYOTI BASU | 0.16 | 0 | 0 | 100
678 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Lekraanchra mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 108/JMD | 31/01/2022 | 475 | DEBJYOTI BASU | 0.16 | 0 | 0 | 100
679 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Hiring of 1 (one) no Additional Motor Cab (standard) commercial with Catalatyic Converter attachement with Bharat Stage as per prevalent applicable standard compliant new not older than 30 (Thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Gopiballavpur Sub-Division, PHE Dte. for monitoring of JJM Works (One Year). | 58/GPSD | 06/02/2024 | 366 | SUJOY RANJAN BHOWMICK | 2.05 | 0 | 0 | 0
680 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Hiring of 1 (one) no Additional Motor Cab (standard) commercial with Catalytic Converter Attachment with Bharat Stage as per prevalent applicable standard compliant new not older than 30 (Thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram Sub-Division, PHE Dte. for monitoring of JJM Works (One Year). (4th Call) [Ref: 3rd Call of e-NIQ-01 of AE/JSD of 2024-2025, SL. No.-01] | 1132/JSD | 10/12/2024 | 365 | A.K. SIKDAR | 2.05 | 0 | 0 | 0
681 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under Binpur-II Block location Id Binpur-II_3_2_B under Jhargram Division in the District of Jhargram. 3rd (Ref: 1st Call eNIT_39 of 2022-23, SL No.-5, 2nd Call eNIT_11 of EE/JHD of 2023-24, SL No.-14) | 1276/JHD | 03/09/2024 | 60 | A R CONSTRUCTION | 20.38 | 0 | 0 | 55
682 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Hiring of 1 (one) no Additional Motor Cab (standard) commercial with Catalytic Converter Attachment with Bharat Stage as per prevalent applicable standard compliant new not older than 30 (Thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram Sub-Division, PHE Dte. (Priods from 1.11.2024 to 31.10.2025) | 1008/JSD | 30/10/2024 | 365 | BIDYUT KUMAR SANTRA | 2.05 | 0 | 0 | 0
683 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Installation of Iron Elimination Plant including PCC Concrete Platform at Bamundiha Stand Alone PWSS of Binpir-II Block under Jhargram Division PHE Dte. | 41/JHD | 07/01/2025 | 60 | PALCON | 7.47 | 0 | 0 | 0
684 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority valid for the State of West Bengal not older than 2 years from the date of 1st Registration on daily Hire rate basis for the period from 01.07.2024 to 31.12.2024. for the Movement of Junior Engineer (RWS) under Jhargram Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, fees etc., as applicable. ( For 6 months) | 170/JRWS | 28/06/2024 | 184 | RAHUL DEY | 0.87 | 0 | 0 | 0
685 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_5 under Jhargram Division in the District of Jhargram. | 425/MD | 04/03/2022 | 180 | RELIABLE SANITARY & PLUMBING CO. | 107.26 | 0 | 0 | 60
686 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pathar Chakri T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3521/JMD | 29/11/2022 | 7 | B. P. TRADING CORPORATION | 0.07 | 0 | 0 | 100
687 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | preparation of documents for uploading in Parivesh Portal for clearance of forest land proposed for 269 Stand Alone PWSS under Jhargram Sub-Division, PHE Dte. | 700/JSD | 04/08/2023 | 30 | CARTO | 0.41 | 0 | 0 | 100
688 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Installation of Iron Elimination Plant including PCC Concrete Platform at Charakpahari Stand Alone PWSS of Binpir-II Block under Jhargram Division PHE Dte. | 03/JHD | 02/01/2025 | 180 | NEER UDYOG | 7.47 | 0 | 0 | 0
689 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Hiring of 1 (one) no Motor Cab (standard) commercial with Catalytic Converter Attachment with Bharat Stage as per prevalent applicable standard compliant new not older than 30 (Thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram RWS Sub-Division, PHE Dte. for monitoring of JJM Works (For One Year)(1st August 2024 to 31st July2025) . | 219/JRWS | 22/07/2024 | 365 | JAGOMOHAN SETUA | 2.05 | 0 | 0 | 0
690 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Continuation Order for Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority valid for the State of West Bengal not older than 2 years from the date of 1st Registration on daily Hire rate basis for the period from 01.07.2024 to 31.07.2024. for the Movement of Junior Engineer (RWS) under Jhargram Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, fees etc., as applicable. (For 1 months) | 636/JSD | 28/06/2024 | 31 | JAGOMOHAN SETUA | 0.17 | 0 | 0 | 0
691 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority valid for the State of West Bengal not older than 2 years from the date of 1st Registration on daily Hire rate basis for the period from 01.01.2025 to 30.06.2025. for the Movement of Junior Engineer (RWS) under Jhargram Sub-Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, fees etc., as applicable. (For 6 months) | 547/JRWS | 30/12/2024 | 181 | RAHUL DEY | 0.86 | 0 | 0 | 0
692 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhadka Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4195/JMD | 28/12/2022 | 735 | J.K. ENGINEERING CO. | 5.78 | 0 | 0 | 100
693 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Sankrail_1_1 under Jhargram Division in the District of Jhargram. [Location of Work Site - (1) Mouza - Tungadhua, J.L. - 127, No. of Unit - 1, (2) Mouza - Bhurkundi, J.L. - 128, No. of Unit - 1, (3) Mouza - Bara Kanya Diha, J.L. - 129, No. of Unit - 1 & (4) Mouza - Nischinta, J.L. - 139, No. of Unit - 2, Total = 5 Units] | 172/MD | 01/02/2022 | 180 | DIPAK KUMAR BAKLY | 90.06 | 0 | 0 | 95
694 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kankrajhor T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3066/JMD | 28/09/2022 | 682 | DEBJYOTI BASU | 6.79 | 0 | 0 | 100
695 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpur-II_2_1 under Jhargram Division in the District of Jhargram. | 301/MD | 15/02/2022 | 180 | ASIS KUMAR SARANGI | 135.09 | 0 | 0 | 100
696 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jari Ghati Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1832/JMD | 24/07/2023 | 453 | SUJOY RANJAN BHOWMICK | 5.78 | 0 | 0 | 80
697 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-VI Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1808/JMD | 24/07/2023 | 485 | DEB KUMAR BASU | 5.78 | 0 | 0 | 100
698 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under Jamboni Block location Id Jamboni_4_3 under Jhargram Division in the District of Jhargram. | 1333/JHD | 10/08/2023 | 485 | BISHNU PADA NANDI | 19.81 | 0 | 0 | 100
699 | JHARGRAM | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhengbahara Stand Alone piped water supply scheme, tube well no-II of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4204/JMD | 28/12/2022 | 643 | M/S. NABIN GOPAL SENGUPTA | 5.78 | 0 | 0 | 100
700 | JHARGRAM | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. , SM/09915 | New | Repair of FHTC and others allied works of Bachurkhoyar PWSS (out of 45 Mini PWSS) under Nayagram Block within Jhargram Division,PHE Dte. | 535/GPSD | 20/08/2024 | 21 | TAPAS KUMAR JANA | 4.13 | 0 | 0 | 50
701 | JHARGRAM | Jhargram Mechanical Division | METIAL AND ADJOINING MOUJAS PWSS , SM/12437 | New | new service connection charges for Metal-2 | 182/JMD | 30/03/2024 | 0 | WBSEDCL | 5.04 | 0 | 0 | 0
702 | JHARGRAM | Jhargram Mechanical Division | METIAL AND ADJOINING MOUJAS PWSS , SM/12437 | New | NEW SERVICE CONNECTION CHARGES FOR METAL-1 | 183/JMD | 30/03/2024 | 0 | WBSEDCL | 6.68 | 0 | 0 | 0
703 | JHARGRAM | Central Drilling | METIAL AND ADJOINING MOUJAS PWSS , SM/12437 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
704 | JHARGRAM | Jhargram Division | METIAL AND ADJOINING MOUJAS PWSS , SM/12437 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
705 | JHARGRAM | Jhargram Division | METIAL AND ADJOINING MOUJAS PWSS , SM/12437 | New | Construction of boundary wall and Allied works At Burimol, Rajband, Bhaudi , Metial 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1077/JHD | 25/07/2024 | 211 | M/S MITRA BROTHERS | 48.9 | 0 | 0 | 40
706 | JHARGRAM | Jhargram Mechanical Division | RAMCHANDRAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12332 | New | New service connection charges at Ramchandrapur-I water supply scheme | 193/JMD | 14/06/2024 | 0 | WBSEDCL | 2.85 | 0 | 0 | 0
707 | JHARGRAM | Jhargram Mechanical Division | RAMCHANDRAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12332 | New | New service connection charges at Ramchandrapur-II water supply scheme | 192/JMD | 14/06/2024 | 0 | WBSEDCL | 6.9 | 0 | 0 | 0
708 | JHARGRAM | Central Drilling | RAMCHANDRAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12332 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
709 | JHARGRAM | Jhargram Division | RAMCHANDRAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12332 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
710 | JHARGRAM | Jhargram Mechanical Division | MAHISAMURA & ADJOINING MOUJAS PWSS , SM/12521 | New | New Service connection | 12/JMD | 10/11/2023 | 0 | WBSEDCL | 1.26 | 0 | 0 | 0
711 | JHARGRAM | Jhargram Mechanical Division | MAHISAMURA & ADJOINING MOUJAS PWSS , SM/12521 | New | New Service connection | 1/JMD | 07/09/2023 | 0 | WBSEDCL | 1.38 | 0 | 0 | 0
712 | JHARGRAM | Jhargram Division | MAHISAMURA & ADJOINING MOUJAS PWSS , SM/12521 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Mahismura and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 519/JRWS | 15/03/2024 | 60 | ENVOTECH INFRA SOLUTION | 4.77 | 0 | 0 | 0
713 | JHARGRAM | Jhargram Mechanical Division | MAHISAMURA & ADJOINING MOUJAS PWSS , SM/12521 | New | Additional service connection chargers at Mahishamura-I water supply scheme | 378/JMD | 30/09/2024 | 0 | WBSEDCL | 2.48 | 0 | 0 | 0
714 | JHARGRAM | Jhargram Mechanical Division | MAHISAMURA & ADJOINING MOUJAS PWSS , SM/12521 | New | new service connection charges at Mahisamura tw-II | 386/JMD | 04/10/2024 | 0 | WBSEDCL | 3.56 | 0 | 0 | 0
715 | JHARGRAM | Central Drilling | MAHISAMURA & ADJOINING MOUJAS PWSS , SM/12521 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
716 | JHARGRAM | Jhargram Division | MAHISAMURA & ADJOINING MOUJAS PWSS , SM/12521 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection ( 7683 Nos), etc.including 02(Two) Years Operation & Maintenance For KAMTA , SUSHNI, BAHIR GRAM, KAPGARI, MURAKATI, MAHISAMURA PWSS Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 1954/JHD | 22/11/2023 | 406 | SIBSANKAR CHOWDHURY | 2070.24 | 0 | 0 | 65
717 | JHARGRAM | Jhargram Division | NOAGOAN AND ADJOINING MOUJAS PWSS , SM/12526 | New | Material Requisition To Resource Division | 957/JHD | 22/06/2023 | 0 | Resource Division | 29.05 | 0 | 0 | 0
718 | JHARGRAM | Jhargram Mechanical Division | NOAGOAN AND ADJOINING MOUJAS PWSS , SM/12526 | New | New Service Connection charges. | 31/JMD | 31/10/2023 | 0 | WBSEDCL | 3.37 | 0 | 0 | 0
719 | JHARGRAM | Jhargram Mechanical Division | NOAGOAN AND ADJOINING MOUJAS PWSS , SM/12526 | New | New Service connection | 9/JMD | 10/11/2023 | 0 | WBSEDCL | 4.03 | 0 | 0 | 0
720 | JHARGRAM | Jhargram Mechanical Division | NOAGOAN AND ADJOINING MOUJAS PWSS , SM/12526 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Noagaon & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | 2265/JMD | 09/08/2023 | 180 | ORIENTAL ENGINEERING CO. | 22.08 | 0 | 0 | 94
721 | JHARGRAM | Jhargram Division | NOAGOAN AND ADJOINING MOUJAS PWSS , SM/12526 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of NOAGAON and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 168/GPSD | 05/03/2024 | 30 | PASCHIMANCHAL ADIBASI ENGINEERS CO-OPERATIVE SOCIETY LIMITED. | 4.26 | 0 | 0 | 100
722 | JHARGRAM | Jhargram Division | NOAGOAN AND ADJOINING MOUJAS PWSS , SM/12526 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House , & Providing Functional Household Tap Connection (6745 Nos), etc. For RAGRA, SATKULI CHARAR, NOAGAON, RAMPURA Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 607/JHD | 04/05/2023 | 881 | GOBINDA MAITY | 1886.45 | 0 | 0 | 20
723 | JHARGRAM | Central Drilling | NOAGOAN AND ADJOINING MOUJAS PWSS , SM/12526 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
724 | JHARGRAM | Jhargram Division | NOAGOAN AND ADJOINING MOUJAS PWSS , SM/12526 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Ragra, Rohini GP at Sankrail Block under jhargram Division PHE Dte. (Phase-I) | 653/GPSD | 19/11/2024 | 10 | PRINT PREVIEW | 0.92 | 0 | 0 | 100
725 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Laying of Distribution pipe line, Accommodate FHTC ( 420 nos) under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1313/JHD | 09/08/2023 | 90 | NIRMAL DUTTA | 31.88 | 0 | 0 | 0
726 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Sinking of Tube Well, Laying of Distribution pipe line under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1335/JHD | 10/08/2023 | 60 | NRIPENDRA NATH SINGHA | 19.55 | 0 | 0 | 0
727 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Laying distribution pipe line under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1319/JHD | 10/08/2023 | 90 | RAHIBUDDIN MONDAL | 26.7 | 0 | 0 | 0
728 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Constructions of Pump House under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1336/JHD | 10/08/2023 | 90 | NRIPENDRA NATH SINGHA | 21.92 | 0 | 0 | 0
729 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Laying distribution pipe line under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1337/JHD | 10/08/2023 | 90 | NIRMAL DUTTA | 27.48 | 0 | 0 | 0
730 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Constructions of Pump House, Laying of Distribution pipe line under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1613/JHD | 08/09/2023 | 90 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.72 | 0 | 0 | 0
731 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Constructions of 400 cum OHR, Rising main pipe line, Interconnection pipe line, Installation of display Board, soil investigation, Accommodate FHTC (420 nos) under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23, SL No.-15) | 2019/JHD | 04/12/2023 | 300 | SUBHANKAR BANERJEE | 214.16 | 0 | 0 | 0
732 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Laying of Distribution pipe line, Accommodate FHTC ( 420 nos) under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 2002/JHD | 01/12/2023 | 90 | GOUTAM PARIA | 37.53 | 0 | 0 | 0
733 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Material Requisition To Resource Division | 1590/JHD | 08/09/2023 | 0 | Resource Division | 52.34 | 0 | 0 | 0
734 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Sinking of Tube Well, Laying of Distribution pipe line under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23, SL No.-17) | 245/JHD | 16/02/2024 | 60 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.21 | 0 | 0 | 0
735 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Jirapara and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 527/JRWS | 16/03/2024 | 60 | NIPENDRANATH SINGHA | 4.83 | 0 | 0 | 0
736 | JHARGRAM | Central Drilling | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
737 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Laying of Distribution pipe, Accommodate FHTC ( 420 nos) under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 2003/JHD | 01/12/2023 | 502 | MAHARAJA CONSTRUCTION CO. | 46.39 | 0 | 0 | 0
738 | JHARGRAM | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS , SM/12533 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Chichra GP at Jambani Block under jhargram Division PHE Dte. (Phase-I) | 335/JRWS | 19/09/2024 | 10 | PRINT PREVIEW | 0.5 | 0 | 0 | 100
739 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | Material Requisition To Resource Division | 1509/JHD | 05/09/2023 | 0 | Resource Division | 6.71 | 0 | 0 | 0
740 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Bandhagora at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6760/JMD | 27/08/2024 | 4 | RSA ENTERPRISE | 1.56 | 0 | 0 | 0
741 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | New service connection charge at Harulia | 50/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
742 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | New service connection payment towards WBSEDCL for Mohanpur | 231/JMD | 28/06/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
743 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | PAYMENT FOR NEW SERVICE CONNECTION OF WBSEDCL AT SITE ALAMDANGA ( scheme code SM/11475) | 277/JMD | 31/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
744 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | New service connection at manpur under 179 Scheme.(Scheme code:- SM/11475) | 427/JMD | 28/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
745 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | New service connection charges | 50/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
746 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | PAYMENT FOR NEW SERVICE CONNECTION OF WBSEDCL AT SITE NAMBANSHBER ( scheme code SM/11475) | 279/JMD | 31/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
747 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | New service connection at Dhabani,Andharia GP | 50/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
748 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | New service connection charge at Bagghara,Dharampur GP | 50/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
749 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | WBSEDCL New connection payment for Benakharanga | 85/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
750 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | Payment of New connection of WBSEDCL for Jualbhanga | 87/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
751 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | New service connection at Baita under 179 Scheme.(Scheme code:- SM/11475) | 428/JMD | 28/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
752 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | New service connection payment towards WBSEDCL for Shiyartola | 86/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
753 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | New service connection charge at Padiha | 50/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
754 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | PAYMENT FOR NEW SERVICE CONNECTION OF WBSEDCL AT SITE OF MOHANPUR (scheme code SM/11475 ) | 278/JMD | 31/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
755 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | WBSEDCL New connection payment for Bara Brindabanpur | 232/JMD | 28/06/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
756 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | Payment of New connection of WBSEDCL for Melkharia | 88/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
757 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | New service connection at Chantukasda,Ramgarh GP | 50/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
758 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | 340/JHD | 09/03/2023 | 872 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 0 | 0 | 50
759 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. , SM/11475 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Chunpara at Binpur-I block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6774/JMD | 27/08/2024 | 4 | RSA ENTERPRISE | 3.49 | 0 | 0 | 100
760 | JHARGRAM | Jhargram Mechanical Division | SIMLI AND IT'S ADJOINING MOJAS PWS at Jhargram Block. , SM/12326 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Simli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1241/JMD | 26/05/2023 | 180 | T.N. BANERJEE | 20.82 | 0 | 0 | 0
761 | JHARGRAM | Central Drilling | SIMLI AND IT'S ADJOINING MOJAS PWS at Jhargram Block. , SM/12326 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 91/CDD | 25/04/2024 | 122 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 0 | 0 | 10
762 | JHARGRAM | Jhargram Division | SIMLI AND IT'S ADJOINING MOJAS PWS at Jhargram Block. , SM/12326 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
763 | JHARGRAM | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | Construction of Laying distribution pipe line under JJM with allied work for DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1318/JHD | 10/08/2023 | 90 | SUBHANKAR BANERJEE | 63.09 | 0 | 0 | 0
764 | JHARGRAM | Jhargram Mechanical Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dud Kundi & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1243/JMD | 26/05/2023 | 617 | DEBJYOTI BASU | 21.76 | 0 | 0 | 50
765 | JHARGRAM | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | Laying distribution pipe line, under JJM with allied work for DUDKUNDI AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour, materials with in Jhargram Sub Division under Jhargram Division, PHE Dte. | 868/JHD | 08/06/2023 | 90 | TAPAN KUMAR MANDAL | 52.9 | 0 | 0 | 50
766 | JHARGRAM | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line,Installation of display Board, soil investigation , under JJM with allied work for DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref: 1st Call eNIT_25 of 2022-23 , SL No.-1 and 2nd Call eNIT_07 of 2023-24, SL No.-4 ) | 1833/JHD | 27/10/2023 | 210 | A.K. SIKDAR | 135.79 | 0 | 0 | 70
767 | JHARGRAM | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Dudkundi and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | 2269/JHD | 02/12/2024 | 30 | TAPAN KUMAR MANDAL | 7.92 | 0 | 0 | 0
768 | JHARGRAM | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | Construction of Boundary wall and allied works at 1st. Tube well site of Dudkundi and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 1315/JHD | 05/09/2024 | 30 | SONU SINGH | 3.75 | 0 | 0 | 0
769 | JHARGRAM | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Aguiboni GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | 1837/JHD | 20/09/2024 | 10 | PRINT PREVIEW | 0.92 | 0 | 0 | 100
770 | JHARGRAM | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Bundhgora GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | 1838/JHD | 20/09/2024 | 10 | MANOJ KUMAR MAHATA | 0.84 | 0 | 0 | 100
771 | JHARGRAM | Jhargram Mechanical Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | NEW SERVICE CONNECTION CHARGES AT DUDHKUNDI TW-II PWSS | 321/JMD | 28/08/2024 | 0 | WBSEDCL | 5.26 | 0 | 0 | 0
772 | JHARGRAM | Jhargram Mechanical Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | NEW SERVICE CONNECTION CHARGES AT DUDHKUNDI TW-I PWSS | 320/JMD | 28/08/2024 | 0 | WBSEDCL | 3.18 | 0 | 0 | 0
773 | JHARGRAM | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | Laying distribution pipe line, under JJM with allied work for DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte | 869/JHD | 08/06/2023 | 632 | SUNIL DULE | 47.31 | 0 | 0 | 0
774 | JHARGRAM | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | Laying distribution pipe line, under JJM with allied work for DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 870/JHD | 08/06/2023 | 632 | SUNIL DULE | 62.73 | 0 | 0 | 0
775 | JHARGRAM | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | Accommodate FHTC ( 1326 nos) under JJM with allied work for DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 871/JHD | 08/06/2023 | 722 | SUNIL DULE | 55.4 | 0 | 0 | 0
776 | JHARGRAM | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS , SM/12723 | New | Construction of Boundary wall and allied works at 1st. Tube well site of Dudkundi and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 1301/JHD | 10/06/2025 | 30 | RADHE RADHE ENTERPRISE | 7.67 | 0 | 0 | 0
777 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Rohini PWSS in Sankrail Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 61/JSD | 18/06/2021 | 14 | ROY CHOWDHURY ASSOCIATES | 4.38 | 0 | 0 | 1
778 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Dismantling the existing damaged voltage stabilizer and supply, delivery & installation of newly supplied three phase 15 KVA oil cooled type voltage stabilizer with other allied works at tube well no.II of Rohini water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 525/JMD | 22/03/2022 | 7 | BEE GEE CONSTRUCTION | 2.28 | 0 | 0 | 0
779 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Supply, delivery & installation of submersible pumping machinery and other electro mechanical accessories at tubewell no.II of Rohini water supply scheme in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 523/JMD | 22/03/2022 | 7 | ORIENTAL ENGINEERING CO. | 4.55 | 0 | 0 | 0
780 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Dismantling the existing damaged voltage stabilizer and supply, delivery & installation of newly supplied single phase 20 KVA oil cooled type voltage stabilizer with other allied works at tube well no.-II of Rohini water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 924/JMD | 12/05/2022 | 7 | PRANAB KUMAR DAS | 2.62 | 0 | 0 | 0
781 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Making compound lighting arrangement and allied works at tube well no.I (Head work site) of Rohini water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 526/JMD | 22/03/2022 | 7 | SUBHRA ENTERPRISE | 2.96 | 0 | 0 | 0
782 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Supply, delivery & installation of submersible pumping machinery and other electro mechanical accessories at tube well no.I of Rohini water supply scheme in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 522/JMD | 22/03/2022 | 7 | SWAPAN ENTERPRISE | 4.42 | 0 | 0 | 0
783 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Repairing & Renovation of RCC Over Head Reservoir (Intze type with Coloum ) of capacity 250 cum at Rohini Water Supply Scheme under Jhargram Division within Jhargram Division P.H.E. Dte. | 172/JSD | 22/03/2022 | 30 | ASSOCIATED ENGINEERS & TRADERS | 4.81 | 0 | 0 | 1
784 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Supply , Delivery of multicore copper control cable for actuator connection at tube well no.II of Rohini water supply scheme in Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 2825/JMD | 16/09/2022 | 7 | ORIENTAL ENGINEERING CO. | 0.16 | 0 | 0 | 0
785 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Supply, Delivery of multicore copper control cable for actuator connection at tube well no.I of Rohini water supply scheme in Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 2824/JMD | 16/09/2022 | 7 | SWAPAN ENTERPRISE | 0.08 | 0 | 0 | 0
786 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Construction of Boundary wall for 2nd Tube well site of Rohini W/S Scheme under Jhargram Sub-Division within Jhargram Division, PHE Dte. (B/W Length = 71.00 Mtr.) |  | 02/08/2022 | 0 | ASSOCIATED ENGINEERS & TRADERS | 5.59 | 0 | 0 | 0
787 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Retrofitting of Ground Water Based Water Supply Scheme for Rohini PWSS to Accommodate FHTC in Block - Sankrail under Jhargram Division, PHE Dte. |  | 02/08/2022 | 0 | ASIS KUMAR SARANGI | 14.92 | 0 | 0 | 0
788 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Repairing & Renovation of RCC Over Head Reservoir (Intze type with Coloum ) of capacity 250 cum at Rohini Water Supply Scheme under Jhargram Division within Jhargram Division P.H.E. Dte |  | 30/08/2022 | 0 | ASSOCIATED ENGINEERS & TRADERS | 4.61 | 0 | 0 | 0
789 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Retrofitting of Ground Water Based Water Supply Scheme for Rohini PWSS to Accommodate FHTC in Block - Sankrail under Jhargram Division, PHE Dte. | 1526/MD | 10/09/2021 | 60 | ASIS KUMAR SARANGI | 136.63 | 0 | 0 | 0
790 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Retrofitting of Ground Water Based Water Supply Scheme for Rohini PWSS to Accommodate FHTC in Block - Sankrail under Jhargram Division, PHE Dte. | 1526/MD | 10/09/2021 | 60 | ASIS KUMAR SARANGI | 136.63 | 0 | 0 | 95
791 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08735 | Retrofitting | Construction of Boundary wall for 2nd Tube well site of Rohini W/S Scheme under Jhargram Sub-Division within Jhargram Division, PHE Dte. (B/W Length = 71.00 Mtr.) | 870/MD | 10/05/2022 | 30 | ASSOCIATED ENGINEERS & TRADERS | 5.98 | 0 | 0 | 100
792 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Bankati And It'S Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16703 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Jangalkhas and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2772/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 77.3 | 0 | 0 | 0
793 | JHARGRAM | Jhargram Mechanical Division | Retrofitting(Phase-III) to accomodate FHTC under JJM in Junsola PWSS within Gopiballavpur-II Block, Jhargram District under Jhargram Division, PHE Dte. , SM/18190 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at proposed additional T/Well as part of augmentation of Junsola W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | 2098/JMD | 03/08/2023 | 30 | DAS CONSTRUCTION | 9.41 | 0 | 0 | 0
794 | JHARGRAM | Jhargram Division | Retrofitting(Phase-III) to accomodate FHTC under JJM in Junsola PWSS within Gopiballavpur-II Block, Jhargram District under Jhargram Division, PHE Dte. , SM/18190 | Augmentation | Sinkingof 200 X150mm diaX150 mtr. rig bored tubewell(replacement),interconnection pipeline from propose tubewell to rising main pipeline and construction damged boudary wall of Junsola PWSS within Gopiballavpur-II Block, under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_28 of 2022-23 , SL No.-2 ) | 1464/JHD | 31/08/2023 | 30 | SHREE ENGINEERING | 8.57 | 0 | 0 | 0
795 | JHARGRAM | Jhargram Division | Retrofitting(Phase-III) to accomodate FHTC under JJM in Junsola PWSS within Gopiballavpur-II Block, Jhargram District under Jhargram Division, PHE Dte. , SM/18190 | Augmentation | Replacement rising main & distribution pipe line(part) of Junsola W/S scheme.within Gopiballavpur-II Block, under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_28 of 2022-23 , SL No.-1 ) | 1329/JHD | 10/08/2023 | 30 | ENVOTECH INFRA SOLUTION | 13.14 | 0 | 0 | 100
796 | JHARGRAM | Jhargram Division | Retrofitting(Phase-III) to accomodate FHTC under JJM in Junsola PWSS within Gopiballavpur-II Block, Jhargram District under Jhargram Division, PHE Dte. , SM/18190 | Augmentation | Providing pending FHTC (85 nos)of Junsola W/S scheme at Gopiballavpur-II Block under Jhargram Sub Division within Jhargram Division,PHE Dte | 649/JSD | 14/07/2023 | 30 | S.R. ENTERPRISE | 3.87 | 0 | 0 | 95
797 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Patharnala w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17126 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Patharnala and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2499/JMD | 25/08/2023 | 180 | RSA ENTERPRISE | 75.13 | 0 | 0 | 0
798 | JHARGRAM | Jhargram Division | Retrofitting(Phase-III) to accomodate FHTC under JJM in Balibandh PWSS within Jamboni Block, Jhargram District under Jhargram Division, PHE Dte. , SM/17945 | Augmentation | SINKING OF 250 X 150 mm dia. X 150 Mtr. DEPTH RIG BORED TUBE WELL ( REPLACEMENT) & PIPE LINE FOR RETROFITTING (Phase-III) OF BALIBUNDH WATER SUPPLY SCHEME WITH IN JAMBONI BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. | 648/JHD | 11/05/2023 | 45 | NRIPENDRA NATH SINGHA | 8.12 | 0 | 0 | 70
799 | JHARGRAM | Jhargram Mechanical Division | Retrofitting(Phase-III) to accomodate FHTC under JJM in Balibandh PWSS within Jamboni Block, Jhargram District under Jhargram Division, PHE Dte. , SM/17945 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories for proposed additional T/Well at head work site as part of augmentation of Balibandh W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | 1128/JMD | 18/05/2023 | 120 | SAMARPITA ENGINEERING | 10.42 | 0 | 0 | 100
800 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at DOMAHANI AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17078 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Parihati and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2773/JMD | 05/09/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 77.27 | 0 | 0 | 0
801 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Chingra And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18031 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Chingra and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2776/JMD | 05/09/2023 | 180 | ELECTRO ENTERPRISES | 32.07 | 0 | 0 | 0
802 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Tiakitpur w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17978 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Gohalmara and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2505/JMD | 25/08/2023 | 180 | SUBHASIS ROY | 75.13 | 0 | 0 | 0
803 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Kantabani Villages Having Less than 20 Household at Gopiballavpur-I Block under Jhargram Division, PHE Dte. | 1674/JHD | 21/09/2023 | 30 | SANTOSH GHOSH | 5.79 | 0 | 0 | 0
804 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Nandan Gerya Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. | 1667/JHD | 21/09/2023 | 30 | M/S ANKITA CONSTRUCTION | 5.65 | 0 | 0 | 98
805 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Ranijhor, Hamirpur Villages Having Less than 20 Household at Jamboni Block under Jhargram Division, PHE Dte. | 1853/JHD | 31/10/2023 | 45 | NRIPENDRA NATH SINGHA | 12.06 | 0 | 0 | 20
806 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Dakshin Sol, Tangasoli Villages Having Less than 20 Household at Jamboni Block under Jhargram Division, PHE Dte. | 1845/JHD | 31/10/2023 | 45 | NIRMAL DUTTA | 12.06 | 0 | 0 | 20
807 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Jaygerya Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-21) | 3105/JHD | 29/12/2023 | 30 | DEBDATTA MANNA | 6.11 | 0 | 0 | 95
808 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Bahara Soli Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-32) | 101/JHD | 18/01/2024 | 30 | BHOWMIK CONSTRUCTION | 6.1 | 0 | 0 | 80
809 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Shiarkata Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-1) | 173/JHD | 01/02/2024 | 30 | MA GAYETRI NIRMAN PRIVATE LIMITED | 6.03 | 0 | 0 | 0
810 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Mayurjharna, Telighana, Bandhgora, Palashbani, Bamni, Barsol(khurd), Ukhuldoba, Chakchakli, Jamda, Kunkrakhopi, Salbant Villages Having Less than 20 Household at Binpur-II Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-10) | 913/JHD | 08/07/2024 | 60 | SAIKAT DANDAPAT | 60.08 | 0 | 0 | 0
811 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Bodakata, Jonka Villages Having Less than 20 Household at Jamboni Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-16) | 1132/JHD | 06/08/2024 | 45 | HYDRO TECH ASSOCIATES | 12.02 | 0 | 0 | 0
812 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Basantapur Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-24) | 434/JHD | 14/03/2024 | 30 | M/S. R.K.TRADERS | 6.16 | 0 | 0 | 0
813 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Phul Beria Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-25) | 433/JHD | 14/03/2024 | 30 | KRISHNA CHANDRA DAS | 5.88 | 0 | 0 | 0
814 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Kumar Kata, Mahulbani, Beldanga,Galasia,Kamar Bandi Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-6) | 2189/JHD | 22/11/2024 | 60 | TARUN MAHATA | 30.29 | 0 | 0 | 0
815 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Kismat Debi, Panisol, Shida Danga Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-33) | 2188/JHD | 22/11/2024 | 45 | TAPAS KUMAR JANA | 17.82 | 0 | 0 | 0
816 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Rasiagerya Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. | 1675/JHD | 21/09/2023 | 30 | ASHIS SHEE | 6.15 | 0 | 0 | 100
817 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Additional pipeline of Bankati PWSS (under Below 20 PWSS) under Dharampur GP within Binpur-I Block under Jhargram Sub Division within Jhargram Division, PHE Dte. | 191/JSD | 07/03/2024 | 7 | SAMIR PATRA | 0.74 | 0 | 0 | 100
818 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Kumarkata, Jl no-824 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
819 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Ghoraghata, Jl no-577 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
820 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Gaighata Jl no-624 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
821 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. (Electricity New Connection quotation : Raisageria, Jhargram Block.) | BP-2023-24-468 | 15/02/2024 | 0 | WBSEDCL | 0.04 | 0 | 0 | 0
822 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Kodadanga Jl no-846 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
823 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | WBSCDCL payment for Shiarkata new connection |  | 09/05/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
824 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Karkata Jl no-672 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
825 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground water based mini piped water supply scheme to accommodate FHTC in villages having less then 20 household within Jhargram District under Jhargram Division, PHE Dte. | BP-2024-25-270 | 23/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.29 | 0 | 0 | 0
826 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Choto Brindabanpur, JL no-822 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
827 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Nutandi Jl no-789,Reference ID- 204237368 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
828 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | new service connection charges at Phulberia water supply scheme |  | 27/09/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
829 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Bamaldaha, JL no-809 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
830 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Kamarbandi Jl no-919 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
831 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Galasia Jl no-793 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
832 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Haringanj | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
833 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Phutibaria | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
834 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Bhepua Jl no-630 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
835 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New Service Connection Charges for Sagbandi PWSS |  | 01/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
836 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Asanboni, JL no-573 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
837 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for sitarampur | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
838 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Kamarbandi Jl no-851 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
839 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Kallokal Jl no-820 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
840 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Beldanga Jl no-848 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
841 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Sushna, JL no-684 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
842 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for chakgeriapur | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
843 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New Service Connection Charges for Gunguni PWSS |  | 01/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
844 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | new service connection charges at Mahulbani water supply scheme |  | 27/09/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
845 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Mahulboni, Jl no-677 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
846 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | WBSCDCL payment for Benageria new connection | BP-2024-25-298 | 23/12/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
847 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Keudi, Jl no-838 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
848 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Bamankata Jl no-844 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
849 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Durllabhpur Jl no-650 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
850 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New Service Connection Charges for Bhakut Khulya PWSS |  | 01/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
851 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New Service Connection Charges for Chhoto Kashitoriya PWSS |  | 01/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
852 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New Service Connection Charges for Kismat Debi PWSS |  | 01/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
853 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | 6 nos. Bill for New service connection charges under 'Ground Water Based Mini piped water supply schemes to Accommodate FHTC in villages having less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | BP-2024-25-292 | 21/11/2024 | 0 | WBSEDCL | 0.57 | 0 | 0 | 0
854 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Chhagalpota, Jl no-660 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
855 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Jaypur Jl no-693 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
856 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Bankati Jl no-842 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
857 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Bijli | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
858 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for Jankipur Jl no-827 | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
859 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New connection quotation bill for sauda | BP-2024-25-7 | 03/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
860 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | New Service Connection Charges for Nandan Gerya PWSS |  | 01/10/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
861 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | new service connection charges at TIPASOL water supply scheme |  | 27/09/2024 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
862 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Bhepua, Durllabhpur, Gaighata, Karkata, Phutibaria Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. | 1654/JHD | 15/09/2023 | 60 | ENVOTECH INFRA SOLUTION | 29.49 | 0 | 0 | 100
863 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Mahul Bani Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. | 1673/JHD | 21/09/2023 | 30 | SANTOSH GHOSH | 6.14 | 0 | 0 | 75
864 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Elagerya, Dhunamari Villages Having Less than 20 Household at Jamboni Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-14) | 3054/JHD | 20/12/2023 | 600 | SUBHRANIL DAS | 12.03 | 0 | 0 | 40
865 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Bhakut Khulya Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. | 44/JHD | 09/01/2024 | 30 | M/S MILAN DATTA | 5.69 | 0 | 0 | 75
866 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Bamaldaha Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-3) | 80/JHD | 16/01/2024 | 30 | SAURABH KAR | 5.89 | 0 | 0 | 100
867 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Tipasol Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-27) | 99/JHD | 18/01/2024 | 30 | GANDHI MAHATA | 6.19 | 0 | 0 | 95
868 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Jangal Khas(JL 823) Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-20) | 79/JHD | 16/01/2024 | 30 | UMA PRASAD DATTA | 5.91 | 0 | 0 | 0
869 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Chhota Kashitarya Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-18) | 100/JHD | 18/01/2024 | 30 | DIPAK ENTERPRISE | 6 | 0 | 0 | 75
870 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Gunguni I Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-29) | 81/JHD | 16/01/2024 | 30 | SUBHAMAY DANDAPAT | 5.61 | 0 | 0 | 75
871 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Fuldihi Villages Having Less than 20 Household at Gopiballavpur-I Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-35) | 154/JHD | 30/01/2024 | 30 | KALYAN ADHIKARI | 6.17 | 0 | 0 | 95
872 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Parulia, Baragupta Villages Having Less than 20 Household at jamboni Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL12) | 125/JHD | 24/01/2024 | 429 | MANDAL ENTERPRISE | 11.81 | 0 | 0 | 95
873 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Jamsol, Kendubani(chhota), Tentul Muri, Ausha Pal, Babui Chati Villages Having Less than 20 Household at Nayagram Block under Jhargram Division, PHE Dte. | 124/JHD | 24/01/2024 | 360 | BRAJENDRANATH SENAPATI | 30.42 | 0 | 0 | 30
874 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Sagbandi Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. | 336/JHD | 28/02/2024 | 30 | A R ENTERPRISE | 6.26 | 0 | 0 | 95
875 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Barakala, Beldangri Villages Having Less than 20 Household at Jamboni Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-11) | 40/JHD | 07/01/2025 | 45 | DEBJIT PATRA | 12.05 | 0 | 0 | 0
876 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Chhota Rajgram, Satpati Villages Having Less than 20 Household at Jamboni Block under Jhargram Division, PHE Dte. 3rd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-17, 2nd Call eNIT_20 of EE/JHD of 2023-24, SL No.-11) | 436/JHD | 14/03/2024 | 45 | TAPAS PAL | 11.96 | 0 | 0 | 80
877 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Chhahazari Fulberia Villages Having Less than 20 Household at Gopiballavpur-I Block under Jhargram Division, PHE Dte. 3rd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-34, 2nd Call eNIT_20 of EE/JHD of 2023-24, SL No.-23) | 438/JHD | 14/03/2024 | 30 | S.R. ENTERPRISE | 6.23 | 0 | 0 | 80
878 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Chhota Brindabanpur, Harin Ganj, Jankipur, Kallokal, Keudi Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. 3rd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-5, 2nd Call eNIT_20 of EE/JHD of 2023-24, SL No.-3) | 377/JHD | 05/03/2024 | 317 | TAPAN KUMAR UPADHYAY | 29.4 | 0 | 0 | 20
879 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 12(twelve) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer(HQ), Jhargram Division PHE Dte. | 463/JHD | 16/03/2024 | 365 | SANJIB SARKAR | 2.07 | 0 | 0 | 25
880 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Jangalkhas Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-19) | 1038/JHD | 22/07/2024 | 30 | KOUSIK MUKHERJEE | 5.98 | 0 | 0 | 0
881 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Bankati Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. | 1672/JHD | 21/09/2023 | 30 | SAMIR PATRA | 5.86 | 0 | 0 | 100
882 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Kamar Bandi Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. | 1666/JHD | 21/09/2023 | 30 | SAMIR PATRA | 5.86 | 0 | 0 | 100
883 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. , SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Kodo Danga, Nutandi, Bijli, Chakgariapur, Benageria Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. | 1718/JHD | 29/09/2023 | 60 | SHIBAM ENTERPRIZES | 31.51 | 0 | 0 | 95
884 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Upar Baghuasol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18011 | Solarisation | Providing solarisation of WBSEDCL energised pumping installation at Upar Baghuasol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2775/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 32.21 | 0 | 0 | 0
885 | JHARGRAM | Jhargram Division | Rejuvenation (Phase-II) of Ground Water Based Birkanar PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18012 | Augmentation | Extension of distribution pipeline,providing pending FHTC,construction of boundary walls at 1st tubewell site and 2nd tubewell site,brick masonary drain,ground water recharge structure of Birkarnar w/s scheme at Binpur-I block under Jhargram Sub-division within Jhargram Division,PHE Dte. | 606/JHD | 04/05/2023 | 60 | DHUMKETU ENGINEERING PRIVATE LIMITED | 30.84 | 0 | 0 | 31
886 | JHARGRAM | Jhargram Division | Rejuvenation (Phase-II) of Ground Water Based Birkanar PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18012 | Augmentation | 01 nos I.E.P (size 20 cum/hr) with platfrom, blower with compressor room of Birkarnar W/S Scheme at Binpur-I Dev. Block under Jhargram Sub division within Jhargram Division ,PHE Dte. | 1646/JHD | 14/09/2023 | 684 | KANAN CONSTRUCTION ENTERPRISE | 14.45 | 0 | 0 | 100
887 | JHARGRAM | Jhargram Division | Rejuvenation (Phase-II) of Ground Water Based Birkanar PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18012 | Augmentation | Re-Laying of Rising Main [100 mm DI (K9)] and Distribution Line (Partly) of Birkarnar Piped Water Supply Scheme within Jhargram Sub-Division under Jhargram Division, PHE Dte.; i.c.w. Strengthening of Lalgarh-Ramgarh Road and Construction of Wide Culverts by Replacing Existing Narrow Culverts under Jhargram Highway Division, PW (Roads) Dte. | 46/JSD | 13/01/2025 | 21 | DHUMKETU ENGINEERING PRIVATE LIMITED | 4.01 | 0 | 0 | 0
888 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | Material Requisition To Resource Division | 1562/JHD | 07/09/2023 | 0 | Resource Division | 66.81 | 0 | 0 | 0
889 | JHARGRAM | Central Drilling | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 91/CDD | 25/04/2024 | 122 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 0 | 0 | 10
890 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | NEW METER CONNECTION CHARGES AT GOBINDAPUR T/W-1 WATER SUPPLY SCHEME | 69/JMD | 29/04/2024 | 0 | WBSEDCL | 9.92 | 0 | 0 | 0
891 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | NEW SERVICE CONNECTION CHARGES AT GOBINDAPUR T/W-2 WATER SUPPLY SCHEME | 70/JMD | 29/04/2024 | 0 | WBSEDCL | 4.78 | 0 | 0 | 0
892 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Gobindapur & adjoining moujas piped water supply scheme, Block-Jhargram in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1236/JMD | 26/05/2023 | 890 | DAS CONSTRUCTION | 20.78 | 0 | 0 | 50
893 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | Laying distribution pipe line under JJM with allied work for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_26 of 2022-23 , SL No.-5 ) | 1341/JHD | 10/08/2023 | 90 | RAHIBUDDIN MONDAL | 26.57 | 0 | 0 | 100
894 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | Accommodate FHTC (1339 nos) under JJM with allied work for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3 rd Cali (Ref: 1st Call eNIT_26 of 2022-23, SL No.-6 and 2nd Call eNIT_08 of 2023-24, SL No.- 11) | 1858/JHD | 31/10/2023 | 90 | M/S BLUE BIRD | 54.78 | 0 | 0 | 70
895 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | Sinking of Tube Well , Pump House , 150 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation under JJM with allied work for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref 1st Call eNIT_26 of 2022-23 , SL No.-1, 2nd Call eNIT_07 of 2023-24 , SL No.-5 ) | 97/JHD | 18/01/2024 | 488 | M/S SUPRIYA CHATTERJEE | 127.38 | 0 | 0 | 30
896 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Gobindapur and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | 2296/JHD | 04/12/2024 | 30 | TAPAN KUMAR MANDAL | 7.92 | 0 | 0 | 70
897 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | Construction of boundary wall and Allied works At Gobindapur 1st and 2nd Tube well site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1207/JHD | 29/05/2025 | 30 | GRAVITA ENTERPRISE | 11.71 | 0 | 0 | 0
898 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | Laying distribution pipe line under JJM with allied work for GOBINDAPUR AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour, materials within Jhargram Sub Division under Jhargram Division, PHE Dte. | 872/JHD | 08/06/2023 | 90 | MANISHIKA CONSTRUCTION | 31.73 | 0 | 0 | 85
899 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | Laying distribution pipe line under JJM with allied work for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1089/JHD | 14/07/2023 | 90 | LALIT BIHARI MAITY | 48.39 | 0 | 0 | 75
900 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/17571 | New | Laying distribution pipe line under JJM with allied work for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_26 of 2022-23 , SL No.-3 ) | 1399/JHD | 18/08/2023 | 90 | NIMAI HAZRA | 41.73 | 0 | 0 | 70
901 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS , SM/17925 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Jamirdiha & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 1350/JMD | 06/06/2023 | 40 | SUBHASIS ROY | 22 | 0 | 0 | 30
902 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS , SM/17925 | New | Construction of (125 mm X 115 mm X 200 mtr.) RBTW by DTH/ combination method for providing FHTC at SITAPUR & its adjacent Seventy Three (73) nos. villages under Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 2297/JMD | 11/08/2023 | 148 | MONDAL PRECISION PRIVATE LIMITED | 163.47 | 0 | 0 | 100
903 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS , SM/17925 | New | New Service connection | 44/JMD | 29/12/2023 | 0 | WBSEDCL | 1.26 | 0 | 0 | 0
904 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS , SM/17925 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM. | 134/JMD | 24/05/2024 | 0 | SURAJ SERVICE STATION | 1.01 | 0 | 0 | 0
905 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS , SM/17925 | New | New Service connection charges. | 10/JMD | 01/03/2024 | 0 | WBSEDCL | 0.42 | 0 | 0 | 0
906 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS , SM/17925 | New | New service connection charges | 32/JMD | 19/12/2023 | 0 | WBSEDCL | 1.68 | 0 | 0 | 0
907 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS , SM/17925 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 200 mtr.) RBTW by DTH / Combination method at Sandapara G.P. in place of (Chainbera, Zone-I Darra (SM/17930), Chainbera, Zone-II Jarda (SM/17925) and Chainbera, Zone-III Joypur (SM/18746) w/s schemes under Binpur-II Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 193/JMD | 30/01/2025 | 352 | MONDAL PRECISION PRIVATE LIMITED | 58.26 | 0 | 0 | 20
908 | JHARGRAM | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at PALASHBANI AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17124 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Uttar Barashol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2498/JMD | 25/08/2023 | 180 | AMITAVA CHAKRABORTY | 75.12 | 0 | 0 | 0
909 | JHARGRAM | Jhargram Mechanical Division | Chorchita Adjoining Moujas Piped Water supply Scheme block-Gopiballavpur-II, Dist-Jhargram , SM/12350 | New | Quotation for new service connection at Charchita T/W I water supply scheme. | 79/JMD | 29/04/2024 | 0 | WBSEDCL | 7.46 | 0 | 0 | 0
910 | JHARGRAM | Central Drilling | Chorchita Adjoining Moujas Piped Water supply Scheme block-Gopiballavpur-II, Dist-Jhargram , SM/12350 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
911 | JHARGRAM | Jhargram Division | Chorchita Adjoining Moujas Piped Water supply Scheme block-Gopiballavpur-II, Dist-Jhargram , SM/12350 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
912 | JHARGRAM | Jhargram Division | Chorchita Adjoining Moujas Piped Water supply Scheme block-Gopiballavpur-II, Dist-Jhargram , SM/12350 | New | Field Level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in fferent Pipe Water Supply Scheme (7 nos PWSS of 130 PWSS) within Gopiballavpur-II Block in the District of Jhargram under Jhargram Division. PHE Dte. Location- i) Chingra PWSS, ii) Gohalmara PWSS iii) Kendana PWSS iv) Kulina PWSS v) Sonakinia PWSS Vi) Tentilia PWSS vii) Chorchita PWSS | 368/JSD | 29/04/2025 | 150 | TECHVISION | 3.72 | 0 | 0 | 10
913 | JHARGRAM | Jhargram Division | Chorchita Adjoining Moujas Piped Water supply Scheme block-Gopiballavpur-II, Dist-Jhargram , SM/12350 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Chorchita and its Adjoining Mouzas PWSS , Block Gopiballavpur-II, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | 785/JSD | 09/08/2024 | 30 | KARTIK DUTTA | 4.49 | 0 | 0 | 100
914 | JHARGRAM | Jhargram Division | GAJPATHAR AND ADJOINING MOUJAS PWSS , SM/17590 | New | 62 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-4) | 1835/JHD | 27/10/2023 | 60 | ASIS KUMAR SARANGI | 101.91 | 0 | 0 | 80
915 | JHARGRAM | Jhargram Division | GAJPATHAR AND ADJOINING MOUJAS PWSS , SM/17590 | New | Four numbers (4) of yield test process need to be done at Dulungdiha and Balichua Mouza of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 544/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
916 | JHARGRAM | Jhargram Division | GAJPATHAR AND ADJOINING MOUJAS PWSS , SM/17590 | New | Four numbers (4) of yield test process need to be done at Gajpathar and Mahulbani Mouza of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 542/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
917 | JHARGRAM | Jhargram Division | GAJPATHAR AND ADJOINING MOUJAS PWSS , SM/17590 | New | Four numbers (4) of yield test process need to be done at Kusumdanga and Tulsibani Mouza of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 543/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
918 | JHARGRAM | Jhargram Division | GAJPATHAR AND ADJOINING MOUJAS PWSS , SM/17590 | New | Four numbers (4) of yield test process need to be done at Thakuranpahari and Katuchua Mouza of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 541/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
919 | JHARGRAM | Jhargram Division | GAJPATHAR AND ADJOINING MOUJAS PWSS , SM/17590 | New | New Service Connection Charges for Katuchua Gajpathar & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
920 | JHARGRAM | Jhargram Division | GAJPATHAR AND ADJOINING MOUJAS PWSS , SM/17590 | New | 31 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur II Block under Jhargram Division, PHE Dte. | 1714/JHD | 29/09/2023 | 820 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 848.26 | 0 | 0 | 45
921 | JHARGRAM | Jhargram Division | GAJPATHAR AND ADJOINING MOUJAS PWSS , SM/17590 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | 383/JRWS | 31/01/2024 | 30 | CARTO | 0.82 | 0 | 0 | 100
922 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | 66 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for BHULAVEDA GP (TALPUPUKHURIA, RAGHUNATHPUR, GIDIGHATI, SHIYARBINDA PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-2) | 1834/JHD | 27/10/2023 | 484 | SUNIL DULE | 108.48 | 0 | 0 | 80
923 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | Four numbers (4) of yield test process need to be done at Jamtalgara & Ashri of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 504/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
924 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | Four numbers (4) of yield test process need to be done at Gidighati & Bamandiha of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 503/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
925 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | Four numbers (4) of yield test process need to be done at Jaypur & Kashijora of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 505/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
926 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | Four numbers (4) of yield test process need to be done at Srinathpur urfkuldiha & Khandarbhula of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 502/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
927 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | New Service Connection Charges for Kashijora, Gidighati & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
928 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | New Service Connection Charges for Jamtalgora Gidighati & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
929 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | New Service Connection Charges for Gidhighati ,Gidighati & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
930 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | New Service Connection Charges for Bamandiha Gidighati & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
931 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | New Service Connection Charges for Khandarbhula Gidighati & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
932 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | New Service Connection Charges for Shusnijubi Gidighati & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
933 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | 33 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for BHULAVEDA GP ( TALPUPUKHURIA ,RAGHUNATHPUR ,GIDIGHATI ,SHIYARBINDA PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-2 ) | 1531/JHD | 06/09/2023 | 602 | ASIS KUMAR SARANGI | 910.58 | 0 | 0 | 80
934 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | 345/JRWS | 08/01/2024 | 30 | MESAURE LAND | 0.82 | 0 | 0 | 100
935 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | 343/JRWS | 08/01/2024 | 30 | MESAURE LAND | 0.82 | 0 | 0 | 100
936 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | 378/JRWS | 31/01/2024 | 30 | MESAURE LAND | 0.82 | 0 | 0 | 50
937 | JHARGRAM | Jhargram Division | GIDIGHATI AND ADJOINING MOUJAS PWSS , SM/17926 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | 382/JRWS | 31/01/2024 | 30 | CARTO | 0.82 | 0 | 0 | 100
938 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 1 No. P.W.S.S. within Gopiballavpur - I & 2 Nos. P.W.S.S. within Gopiballavpur-II , SM/06831 | Retrofitting | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN 1NO.PWSS WITHIN GOPIBALLAVPUR-1&2 NOS PWSS WITHIN GOPIBALLAVPUR-II | 844310 | 02/08/2021 | 0 | ASIS KUMAR SARANGI | 0.82 | 0 | 0 | 0
939 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 1 No. P.W.S.S. within Gopiballavpur - I & 2 Nos. P.W.S.S. within Gopiballavpur-II , SM/06831 | Retrofitting | Extension of Distribution pipe line for left out Habitation in Phul Baria Mouza (0264) in connection with FHTC under Alampur W/S Scheme within Gopiballavpur-I Block Under Jhargram Division, PHE Dte. | 844350 | 09/12/2021 | 0 | ASIM KUMAR DEY. | 2.67 | 0 | 0 | 0
940 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 1 No. P.W.S.S. within Gopiballavpur - I & 2 Nos. P.W.S.S. within Gopiballavpur-II , SM/06831 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Naupara PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. | 1412/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 36.77 | 27.31 | 86.59 | 80
941 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 1 No. P.W.S.S. within Gopiballavpur - I & 2 Nos. P.W.S.S. within Gopiballavpur-II , SM/06831 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Alampur PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. | 1398/MD | 26/11/2020 | 180 | ASHIM KUMAR DEY | 50.2 | 50.18 | 100 | 0
942 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Sankrail , SM/06833 | Retrofitting | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN 2NOS.PWSS WITHIN SANKRAIL | 84439 | 02/08/2021 | 0 | ASIS KUMAR SARANGI | 0.8 | 0 | 0 | 0
943 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Sankrail , SM/06833 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Ragra PWSS of Sankrail Block under Jhargram Division, PHE Dte. | 1402/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 60.82 | 46.98 | 100 | 1
944 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Sankrail , SM/06833 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Nakrasuli PWSS of Sankrail Block under Jhargram Division, PHE Dte. | 1419/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 4.81 | 4.36 | 100 | 0
945 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte , SM/08733 | Retrofitting | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Dhamro PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 102/JSD | 13/07/2021 | 14 | M/S R. DUTTA & CO | 1.59 | 0 | 0 | 1
946 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte , SM/08733 | Retrofitting | Extension distribution pipeline in connection with retrofitting to accommodate FHTC in Dhamro PWSS Block - Binpur-I under Jhargram Sub-Division,PHE Dte. | 429/JSD | 05/08/2022 | 21 | PRANOY KUMAR UKIL | 4.67 | 0 | 0 | 1
947 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte , SM/08733 | Retrofitting | Replacement of pipeline by higher diameter pipe at Kanipal Mouza in connection with retrofitting to accommodate FHTC in Dhamro PWSS Block - Binpur-I under Jhargram Sub-Division, PHE Dte. | 428/JSD | 05/08/2022 | 21 | SAMIR PATRA | 2.91 | 0 | 0 | 1
948 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte , SM/08733 | Retrofitting | Retrofitting and allied works to accommodate FHTC under JJM in Dhamro PWSS within Binpur-I Block under Jhargram Division, PHE Dte. | 1690/MD | 30/09/2021 | 15 | SAIKAT DANDAPAT | 33.29 | 0 | 0 | 0
949 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte , SM/08733 | Retrofitting | Transfer to EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. PFMS bank account. | BP-2022-23-690 | 10/03/2023 | 0 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 9.21 | 0 | 0 | 0
950 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte , SM/08733 | Retrofitting | Retrofitting and allied works to accommodate FHTC under JJM in Dhamro PWSS within Binpur-I Block under Jhargram Division, PHE Dte. | 1690/MD | 30/09/2021 | 15 | SAIKAT DANDAPAT | 33.29 | 0 | 0 | 1
951 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Sasarah P.W.S.S. Within Gopiballavpur I Block Under Jhargram Division, P.H.E. , SM/08736 | Retrofitting | Retrofitting and allied works to accommodate FHTC under JJM in Sasarah PWSS within Gopiballavpur-I Block under Jhargram Division, PHE Dte. | 1606/MD | 17/09/2021 | 21 | SUNIL DULE | 44.65 | 32.74 | 73.34 | 1
952 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Sasarah P.W.S.S. Within Gopiballavpur I Block Under Jhargram Division, P.H.E. , SM/08736 | Retrofitting | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Sasarah PWSS in Gopiballavpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | BP-2021-22-370 | 23/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 1.8 | 0 | 0 | 0
953 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Sasarah P.W.S.S. Within Gopiballavpur I Block Under Jhargram Division, P.H.E. , SM/08736 | Retrofitting | Supply, delivery & installation of submersible pumping machinery and other electro mechanical accessories at tubewell no. I of Sasrah water supply scheme in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 3634/JMD | 07/12/2022 | 30 | SUJOY RANJAN BHOWMICK | 6.62 | 0 | 0 | 0
954 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Sasarah P.W.S.S. Within Gopiballavpur I Block Under Jhargram Division, P.H.E. , SM/08736 | Retrofitting | Supply, delivery & installation of submersible pumping machinery and other electro mechanical accessories at tubewell no. II of Sasrah water supply scheme in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 3635/JMD | 07/12/2022 | 30 | SUJOY RANJAN BHOWMICK | 5.78 | 0 | 0 | 0
955 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Baratilaboni PWSS (Phase-II) , SM/09102 | Retrofitting | construction barbed wire fencing(Total Length-42 M, Height 1.8 M) with precast R.C.C piller (size 0.2 M X 0.20 M , 2 M C/C) and a gate (width 4 M) of Baratilaboni w/s scheme. | 992/JSD | 22/10/2024 | 30 | SAIKAT JANA | 1.54 | 0 | 0 | 0
956 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(174 nos.) within Sankrail Block under Jhargram District. , SM/10350 | Anganwadi | Water Supply arrangement for 174 Nos. Anganwadi Centers at Sankrail Block in Jhargram District under Jhargram Division, PHE Dte. | 163/JHD | 07/02/2023 | 687 | ASIS KUMAR SARANGI | 427.57 | 0 | 0 | 90
957 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Acceptance-Cum-Work Order "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_11_20)" | 624/JSD | 23/11/2022 | 30 | BHOWMIK CONSTRUCTION | 3.19 | 0 | 0 | 100
958 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BELATIKRI GP under Binpur-I Block in Jhargram District under Jhargrm Division PHE Dte. (Location ID : AWS_Binpur-I_5_20) | 676/JHD | 13/12/2022 | 45 | NIMAI HAZRA | 57.24 | 0 | 0 | 80
959 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_13_20)" | 626/JSD | 23/11/2022 | 30 | ASHIS SHEE | 3.03 | 0 | 0 | 0
960 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_10_20)" | 623/JSD | 23/11/2022 | 30 | M/S PIJUSH PAL | 3.1 | 0 | 0 | 0
961 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BINPUR GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_2_20) | 624/JHD | 28/11/2022 | 30 | DHUMKETU ENGINEERING PRIVATE LIMITED | 10.99 | 0 | 0 | 0
962 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_9_20)" | 622/JSD | 23/11/2022 | 30 | SAMIR PATRA | 3.06 | 0 | 0 | 100
963 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_14_20)" | 627/JSD | 23/11/2022 | 30 | MANDAL ENTERPRISE | 3.16 | 0 | 0 | 100
964 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_16_20)" | 629/JSD | 23/11/2022 | 30 | S.B.TRADERS | 4.03 | 0 | 0 | 100
965 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At ANDHARIA GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Binpur-I_6_20) | 450/JHD | 11/11/2022 | 45 | SUNIL DULE | 51.83 | 0 | 0 | 25
966 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At LALGARH and SIJUA GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Binpur-I_19_20) | 451/JHD | 11/11/2022 | 45 | SUNIL DULE | 62.36 | 0 | 0 | 80
967 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At BINPUR GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_1_20)" | 619/JSD | 23/11/2022 | 30 | SOURABH KAR | 4.71 | 0 | 0 | 100
968 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Acceptance-Cum-Work Order For Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_7_20) | 620/JSD | 23/11/2022 | 30 | M/S S.R. & COMPANY | 3.18 | 0 | 0 | 100
969 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_8_20)" | 621/JSD | 23/11/2022 | 30 | MAHAVIR SAMPARK PVT. LTD. | 2.96 | 0 | 0 | 100
970 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_12_20)" | 625/JSD | 23/11/2022 | 30 | RAMENDRA NATH KAR | 3.16 | 0 | 0 | 100
971 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers at NEPURA, BAITA and DHARAMPUR GP under Binpur-I Block in Jhargram District under Jhargram Division, PHE Dte. ( Location ID L AWC_Binpur-I_18_20) | 1144/JHD | 21/07/2023 | 45 | SAIKAT DANDAPAT | 75.97 | 0 | 0 | 60
972 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_15_20)" | 628/JSD | 23/11/2022 | 30 | SANKAR KUMAR NAG | 3.68 | 0 | 0 | 100
973 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_17_20)" | 630/JSD | 23/11/2022 | 30 | SAUBHIK KUMAR NAG | 4.52 | 0 | 0 | 100
974 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BINPUR GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Binpur-I_4_20) | 629/JHD | 28/11/2022 | 45 | NIMAI LAL GURIA | 16.92 | 0 | 0 | 100
975 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At RAMGARH GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Binpur-I_20_20) | 452/JHD | 11/11/2022 | 45 | SUNIL DULE | 63.21 | 0 | 0 | 90
976 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BINPUR GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_3_20) | 623/JHD | 28/11/2022 | 45 | BIDYUT KUMAR SANTRA | 16.29 | 0 | 0 | 100
977 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. , SM/10355 | Anganwadi | Arrangement for supporting structureof 1000 Lit PVC water storage tank for 1) Loagaon AWC(19344030210) at Binpur GP & 2)Providing necessary water supply arrangement within Anganwadi Center with PVC pipes (medium duty conforming to ASTMD - 1785) and G.I. pipe, supplying, installation and lowering in position with column pipe of Submersible pumping machineries of 1.0 HP with varying head & discharge of Crompton/ KSB or other renowned make conforming to latest BIS codes with control panel and all necessary electrical connections, supplying & installation of P.V.C. water storage tank of approved quality of 1000 litre capacity (to be installed at roof top of Anganwadi building) and construction of Drains / Pipe, Soak Pit etc all complete for Rathbera AWC (19344030715) at Dahijuri G.P. under Binpur-I Block in Jhargram District under Jhargram Division ,PHE Dte. | 212/JSD | 07/03/2025 | 14 | SAURABH KAR | 1.39 | 0 | 0 | 100
978 | JHARGRAM | Midnapore Division | Rejuvenation of Ground Water Based Ragra PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10489 | Augmentation | Retrofitting to accommodate FHTC under JJM in Ragra PWSS of Sankrail Block under Jhargram Division, PHE Dte. | 1402/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 60.82 | 0 | 0 | 1
979 | JHARGRAM | Midnapore Division | Rejuvenation of Ground Water Based Ragra PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10489 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Rogra PWSS in Sankrail Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | BP-2022-23-96 | 04/06/2022 | 0 | RADIANT | 1.86 | 0 | 0 | 0
980 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Ragra PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10489 | Augmentation | Construction of 200 cum OHR, Interconnection pipe line with allied work for Ragra and its adjoining mouzas PWSS in Sankrail Block under Jhargram Division, PHE Dte. | 1278/JHD | 03/09/2024 | 420 | ASIS KUMAR SARANGI | 76.24 | 0 | 0 | 0
981 | JHARGRAM | Jhargram Mechanical Division | BAGMURI AND ADJOINING MOUJAS PWSS , SM/12523 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bagmuri & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1228/JMD | 26/05/2023 | 180 | ARATI ENGINEERING | 20.76 | 0 | 0 | 0
982 | JHARGRAM | Central Drilling | BAGMURI AND ADJOINING MOUJAS PWSS , SM/12523 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 91/CDD | 25/04/2024 | 122 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 0 | 0 | 10
983 | JHARGRAM | Jhargram Division | BAGMURI AND ADJOINING MOUJAS PWSS , SM/12523 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
984 | JHARGRAM | Jhargram Division | BAGMURI AND ADJOINING MOUJAS PWSS , SM/12523 | New | Construction of boundary wall and Allied works At Dahatmal,Bagmuri,Champasol 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1280/JHD | 03/09/2024 | 30 | PROVAT KUMAR DE | 37.25 | 0 | 0 | 30
985 | JHARGRAM | Jhargram Mechanical Division | MURAKATI AND ADJOINING MOUJAS PWSS , SM/12339 | New | New service connection | 20/AUG | 24/08/2023 | 0 | WBSEDCL | 4.72 | 0 | 0 | 0
986 | JHARGRAM | Jhargram Mechanical Division | MURAKATI AND ADJOINING MOUJAS PWSS , SM/12339 | New | New service connection | 19/AUG | 24/08/2023 | 0 | WBSEDCL | 2.95 | 0 | 0 | 0
987 | JHARGRAM | Jhargram Division | MURAKATI AND ADJOINING MOUJAS PWSS , SM/12339 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Murakati and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 524/JRWS | 15/03/2024 | 60 | VAIDIK CONSTRUCTION | 4.84 | 0 | 0 | 0
988 | JHARGRAM | Central Drilling | MURAKATI AND ADJOINING MOUJAS PWSS , SM/12339 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
989 | JHARGRAM | Jhargram Division | MURAKATI AND ADJOINING MOUJAS PWSS , SM/12339 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection ( 7683 Nos), etc.including 02(Two) Years Operation & Maintenance For KAMTA , SUSHNI, BAHIR GRAM, KAPGARI, MURAKATI, MAHISAMURA PWSS Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 1954/JHD | 22/11/2023 | 406 | SIBSANKAR CHOWDHURY | 2070.24 | 0 | 0 | 65
990 | JHARGRAM | Midnapore Division | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. , SM/09881 | Augmentation | Sinking of 250mm X 150mm dia. & depth 135 Mtr. Rig bore Tube well (Replacement) for Augmentation of Khasjungal W/S Scheme within Binpur-I block under Jhargram Division, PHE Dte. | 613/MD | 04/04/2022 | 15 | TAPAS KUMAR GIRI | 6.13 | 0 | 0 | 1
991 | JHARGRAM | Midnapore Division | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. , SM/09881 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Khasjungle PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | BP-2021-22-409 | 23/02/2022 | 0 | RADIANT | 1.35 | 0 | 0 | 0
992 | JHARGRAM | Jhargram Mechanical Division | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. , SM/09881 | Augmentation | Withdrawing the damaged sub-mersible pumping machinery and installation of same capacity departmentally supplied pump motor set with other allied works at Khasjangle water supply scheme, tube well no.-1 at Binpur-I block in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | 1572/JMD | 26/07/2022 | 5 | M/S. EMMESS | 4.18 | 0 | 0 | 100
993 | JHARGRAM | Jhargram Mechanical Division | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. , SM/09881 | Augmentation | Supply, delivery and laying of additional Cable, pipe & erection of fencing arrangement with other allied accessories at T/W no.-II of Khasjungle W/S Scheme at Binpur-I Block in the district of Jhargram under Jhargram Mechanical Division P.H.E Dte. | 1240/JMD | 02/06/2025 | 90 | SOUMEN ELECTRIC | 3.39 | 0 | 0 | 100
994 | JHARGRAM | Jhargram Mechanical Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. , SM/09882 | Augmentation | Supply delivery & installation of pumping machinery and other electro mechanical accessories for the newly sunk replacement tube well no -II at Chichira w/s scheme to accommodate FHTC at Jamboni block of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3068/JMD | 28/09/2022 | 30 | SHOVAN KUMAR DAS | 9.89 | 0 | 0 | 0
995 | JHARGRAM | Midnapore Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. , SM/09882 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Chichira PWSS in Jamboni Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | BP-2021-22-394 | 22/02/2022 | 0 | RADIANT | 1.38 | 0 | 0 | 0
996 | JHARGRAM | Jhargram Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. , SM/09882 | Augmentation | Sinking of 250mm X 150mm dia. & depth 150 Mtr. Rig bore Tube well for Augmentation of Chichira W/S Scheme under Jhargram Division, PHE Dte. |  | 16/08/2022 | 0 | NIRPENDRA NATH SINGHA | 4.78 | 0 | 0 | 0
997 | JHARGRAM | Midnapore Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. , SM/09882 | Augmentation | Sinking of 250mm X 150mm dia. & depth 150 Mtr. Rig bore Tube well for Augmentation of Chichira W/S Scheme under Jhargram Division, PHE Dte. | 615/MD | 04/04/2022 | 15 | NRIPENDRA NATH SINGHA | 6.58 | 0 | 0 | 0
998 | JHARGRAM | Jhargram Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. , SM/09882 | Augmentation | Sinking of 250mm X 150mm dia. & depth 150 Mtr. Rig bore Tube well for Augmentation of Chichira W/S Scheme under Jhargram Division, PHE Dte. | 615/MD | 04/04/2022 | 15 | NIPENDRANATH SINGHA | 6.58 | 0 | 0 | 1
999 | JHARGRAM | Jhargram Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. , SM/09882 | Augmentation | DISMANTILING OF CONCRETE ROAD & RESTORATION AT CHICHIRA VILLAGE UNDER CHICHIRA W/S SCHEME WITHIN JAMBONI BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. (Phase-I). | 197/JRWS | 12/07/2024 | 30 | SUNIL DULE | 0.97 | 0 | 0 | 0
1000 | JHARGRAM | Jhargram Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. , SM/09882 | Augmentation | DISMANTILING OF CONCRETE ROAD & RESTORATION AT CHICHIRA VILLAGE UNDER CHICHIRA W/S SCHEME WITHIN JAMBONI BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. (Phase-II). | 198/JRWS | 12/07/2024 | 30 | SUNIL DULE | 0.97 | 0 | 0 | 0
1001 | JHARGRAM | Jhargram Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. , SM/09882 | Augmentation | LEFT OUT HABITATION ACCOMODATE FUNCTIONAL HOUSE TAP CONNECTION (F.H.T.C.) AT CHICHIRA MOUZA UNDER CHICHIRA WATER SUPPLY SCHEME WITH IN JAMBONI BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. | 261/JRWS | 07/08/2024 | 60 | SAUBHIK KUMAR NAG | 3.8 | 0 | 0 | 0
1002 | JHARGRAM | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS , SM/12444 | New | Material Requisition To Resource Division | 1545/JHD | 07/09/2023 | 0 | Resource Division | 31.34 | 0 | 0 | 0
1003 | JHARGRAM | Jhargram Mechanical Division | BELIA AND ADJOINING MOUJAS PWSS , SM/12444 | New | New service connection | 25/AUG | 25/08/2023 | 0 | WBSEDCL | 5.64 | 0 | 0 | 0
1004 | JHARGRAM | Jhargram Mechanical Division | BELIA AND ADJOINING MOUJAS PWSS , SM/12444 | New | New service connection | 18/AUG | 24/08/2023 | 0 | WBSEDCL | 2.94 | 0 | 0 | 0
1005 | JHARGRAM | Jhargram Mechanical Division | BELIA AND ADJOINING MOUJAS PWSS , SM/12444 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Belia & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2266/JMD | 09/08/2023 | 180 | CHAKRABORTY MINING & ENGINEERING | 22.09 | 0 | 0 | 65
1006 | JHARGRAM | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS , SM/12444 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation , Accommodate FHTC ( 1424 nos) under JJM with allied work including 02 (Two) Years Operation & Maintenance for BELIA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 789/JHD | 31/05/2023 | 180 | ASIS KUMAR SARANGI | 353.43 | 0 | 0 | 80
1007 | JHARGRAM | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS , SM/12444 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Belia and Chandabila PWSS , Block Jamboni, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 503/JHD | 07/03/2025 | 60 | M/S DURGA ENTERPRISE | 28.11 | 0 | 0 | 0
1008 | JHARGRAM | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS , SM/12444 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Gidhni GP at Jambani Block under jhargram Division PHE Dte. (Phase-I) | 362/JRWS | 01/10/2024 | 10 | GOPAL JANA | 0.92 | 0 | 0 | 100
1009 | JHARGRAM | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS , SM/12444 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Belia and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 516/JRWS | 15/03/2024 | 60 | MANDAL ENTERPRISE | 4.77 | 0 | 0 | 90
1010 | JHARGRAM | Jhargram Mechanical Division | TENTULIA AND ADJOINING MOUJAS PWSS , SM/12341 | New | New Service connection | 2/JMD | 07/09/2023 | 0 | WBSEDCL | 3.1 | 0 | 0 | 0
1011 | JHARGRAM | Jhargram Mechanical Division | TENTULIA AND ADJOINING MOUJAS PWSS , SM/12341 | New | New Service connection | 3/JMD | 07/09/2023 | 0 | WBSEDCL | 4.75 | 0 | 0 | 0
1012 | JHARGRAM | Jhargram Division | TENTULIA AND ADJOINING MOUJAS PWSS , SM/12341 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Tentulia and its Adjoining Mouzas PWSS , Block: - Gopiballavpur-II, District: - Jhargram {TYPE - B} (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 784/JSD | 09/08/2024 | 30 | GOPESH DEY | 4.76 | 0 | 0 | 0
1013 | JHARGRAM | Jhargram Mechanical Division | TENTULIA AND ADJOINING MOUJAS PWSS , SM/12341 | New | Quotation for new service connection at Tentulia tw-II water supply scheme. | 149/JMD | 31/05/2024 | 0 | WBSEDCL | 4.3 | 0 | 0 | 0
1014 | JHARGRAM | Jhargram Mechanical Division | TENTULIA AND ADJOINING MOUJAS PWSS , SM/12341 | New | Quotation for new service connection at Tentulia T/W -I water supply scheme. | 150/JMD | 31/05/2024 | 0 | WBSEDCL | 3.04 | 0 | 0 | 0
1015 | JHARGRAM | Central Drilling | TENTULIA AND ADJOINING MOUJAS PWSS , SM/12341 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1016 | JHARGRAM | Jhargram Division | TENTULIA AND ADJOINING MOUJAS PWSS , SM/12341 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1017 | JHARGRAM | Jhargram Division | TENTULIA AND ADJOINING MOUJAS PWSS , SM/12341 | New | Field Level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in fferent Pipe Water Supply Scheme (7 nos PWSS of 130 PWSS) within Gopiballavpur-II Block in the District of Jhargram under Jhargram Division. PHE Dte. Location- i) Chingra PWSS, ii) Gohalmara PWSS iii) Kendana PWSS iv) Kulina PWSS v) Sonakinia PWSS Vi) Tentilia PWSS vii) Chorchita PWSS | 368/JSD | 29/04/2025 | 150 | TECHVISION | 3.72 | 0 | 0 | 10
1018 | JHARGRAM | Jhargram Mechanical Division | JUNSOLA AND ADJOINING MOUJAS PWSS , SM/12342 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Junsola & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1227/JMD | 26/05/2023 | 180 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD | 20.73 | 0 | 0 | 0
1019 | JHARGRAM | Jhargram Division | JUNSOLA AND ADJOINING MOUJAS PWSS , SM/12342 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 150 cum and staging height 20 mtr. as per approved drawing with allied works of JUNSOLA & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for GOPIBALLAVPUR-II Block, District: - Jhargram. | 2051/JHD | 07/12/2023 | 210 | ABJ ENGINEERING | 71.51 | 0 | 0 | 0
1020 | JHARGRAM | Jhargram Division | JUNSOLA AND ADJOINING MOUJAS PWSS , SM/12342 | New | Material Requisition To Resource Division | 1560/JHD | 07/09/2023 | 0 | Resource Division | 22.19 | 0 | 0 | 0
1021 | JHARGRAM | Central Drilling | JUNSOLA AND ADJOINING MOUJAS PWSS , SM/12342 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 2104/CDD | 09/02/2024 | 182 | JHARGRAM SPV PRIVATE LIMITED | 110.72 | 0 | 0 | 10
1022 | JHARGRAM | Jhargram Division | JUNSOLA AND ADJOINING MOUJAS PWSS , SM/12342 | New | Sinking of Tube Well , Pump House, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board & Accommodate FHTC(6721 nos) including 02(Two) Years Operation & Maintenance under JJM with allied work for DHADANGIRI, GOBINDAPUR, JUNSOLA, PETBINDHI & MAHAPAL PWSS in Gopiballavpur-II Block including supply of all labour & materials within Gopiballavpur Sub-Division under Jhargram Division, PHE Dte. | 1373/JHD | 16/08/2023 | 465 | M/S. EL-CON | 1574.44 | 0 | 0 | 0
1023 | JHARGRAM | Jhargram Mechanical Division | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. , SM/12324 | New | New service connection | 17/AUG | 24/08/2023 | 0 | WBSEDCL | 3.06 | 0 | 0 | 0
1024 | JHARGRAM | Jhargram Division | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. , SM/12324 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Barsol and its adjoining mouzas Pipe Water Supply Scheme within Gopialavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 191/GPSD | 11/03/2024 | 30 | ENVOTECH INFRA SOLUTION | 4.24 | 0 | 0 | 0
1025 | JHARGRAM | Jhargram Division | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. , SM/12324 | New | Material Requisition To Resource Division | 419/JHD | 13/03/2024 | 0 | Resource Division | 15.79 | 0 | 0 | 0
1026 | JHARGRAM | Jhargram Mechanical Division | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. , SM/12324 | New | Quotation for new service connection at Barsole T/W -I water supply scheme. | 230/JMD | 28/06/2024 | 0 | WBSEDCL | 5.37 | 0 | 0 | 0
1027 | JHARGRAM | Central Drilling | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. , SM/12324 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1028 | JHARGRAM | Jhargram Division | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. , SM/12324 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1029 | JHARGRAM | Jhargram Division | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. , SM/12324 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Bhila, Gohalbura and Barasol and its adjoining Mouzas , Block Gopiballavpur-I, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 313/JHD | 12/02/2025 | 60 | ANUSKA ENTERPRISE | 43.87 | 0 | 0 | 0
1030 | JHARGRAM | Jhargram Mechanical Division | KAMTA AND ADJOINING MOUZAS PWSS , SM/12885 | New | New Service connection | 6/JMD | 07/09/2023 | 0 | WBSEDCL | 1.23 | 0 | 0 | 0
1031 | JHARGRAM | Jhargram Mechanical Division | KAMTA AND ADJOINING MOUZAS PWSS , SM/12885 | New | New Service connection | 4/JMD | 07/09/2023 | 0 | WBSEDCL | 3.15 | 0 | 0 | 0
1032 | JHARGRAM | Jhargram Division | KAMTA AND ADJOINING MOUZAS PWSS , SM/12885 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of KAMTA and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 522/JRWS | 15/03/2024 | 60 | JAGOMOHAN SETUA | 4.74 | 0 | 0 | 0
1033 | JHARGRAM | Central Drilling | KAMTA AND ADJOINING MOUZAS PWSS , SM/12885 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1034 | JHARGRAM | Jhargram Division | KAMTA AND ADJOINING MOUZAS PWSS , SM/12885 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection ( 7683 Nos), etc.including 02(Two) Years Operation & Maintenance For KAMTA , SUSHNI, BAHIR GRAM, KAPGARI, MURAKATI, MAHISAMURA PWSS Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 1954/JHD | 22/11/2023 | 406 | SIBSANKAR CHOWDHURY | 2070.24 | 0 | 0 | 65
1035 | JHARGRAM | Jhargram Division | KAMTA AND ADJOINING MOUZAS PWSS , SM/12885 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Parihati GP at Jambani Block under jhargram Division PHE Dte. (Phase-I) | 376/JRWS | 22/10/2024 | 10 | GOPAL JANA | 0.92 | 0 | 0 | 100
1036 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Jakua w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16925 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Rampura and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2777/JMD | 05/09/2023 | 180 | ELECTRO ENTERPRISES | 32.07 | 0 | 0 | 0
1037 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at RAGHUNATHPUR AND ADJOING MOUJUAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16692 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Bandarbani and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2774/JMD | 05/09/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 64.39 | 0 | 0 | 0
1038 | JHARGRAM | Jhargram Division | ANDHARI AND ADJOINING MOUJAS PWSS , SM/16991 | New | Material Requisition To Resource Division | 1503/JHD | 05/09/2023 | 0 | Resource Division | 28.37 | 0 | 0 | 0
1039 | JHARGRAM | Jhargram Mechanical Division | ANDHARI AND ADJOINING MOUJAS PWSS , SM/16991 | New | New Service connection | 25/JMD | 29/11/2023 | 0 | WBSEDCL | 0.05 | 0 | 0 | 0
1040 | JHARGRAM | Jhargram Mechanical Division | ANDHARI AND ADJOINING MOUJAS PWSS , SM/16991 | New | New service connection charges. | 2/JMD/AUG | 17/08/2023 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
1041 | JHARGRAM | Jhargram Mechanical Division | ANDHARI AND ADJOINING MOUJAS PWSS , SM/16991 | New | New Service connection | 18/JMD | 20/11/2023 | 0 | WBSEDCL | 2.9 | 0 | 0 | 0
1042 | JHARGRAM | Jhargram Mechanical Division | ANDHARI AND ADJOINING MOUJAS PWSS , SM/16991 | New | Additional Service Connection Charges for Andhari P.H - II PWSS | 208/JMD | 20/06/2024 | 0 | WBSEDCL | 5.7 | 0 | 0 | 0
1043 | JHARGRAM | Jhargram Division | ANDHARI AND ADJOINING MOUJAS PWSS , SM/16991 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (5510 Nos), etc. For ANANDAPUR, ANDARI, BHAMAL SANKRAIL, DHANSOL Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 567/JHD | 25/04/2023 | 860 | GOBINDA MAITY | 1535.46 | 0 | 0 | 75
1044 | JHARGRAM | Central Drilling | ANDHARI AND ADJOINING MOUJAS PWSS , SM/16991 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1045 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Ramgarh, Zone-I w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16707 | Solarisation | Quotation for meter installation for solar power plant for Ramgarh zone-2 T/W-1. | 400/JMD | 25/10/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
1046 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Ramgarh, Zone-I w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16707 | Solarisation | Quotation for meter installation for solar power plant for Ramgarh zone-1 T/W-1. | 399/JMD | 25/10/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
1047 | JHARGRAM | Jhargram Division | DHADANGIRI AND ADJOINING MOUJAS , SM/16992 | New | Material Requisition To Resource Division | 1594/JHD | 08/09/2023 | 0 | Resource Division | 37.99 | 0 | 0 | 0
1048 | JHARGRAM | Central Drilling | DHADANGIRI AND ADJOINING MOUJAS , SM/16992 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 2104/CDD | 09/02/2024 | 182 | JHARGRAM SPV PRIVATE LIMITED | 110.72 | 0 | 0 | 10
1049 | JHARGRAM | Jhargram Division | DHADANGIRI AND ADJOINING MOUJAS , SM/16992 | New | Soil Investigation and determination of safe bearing capacity and other relevant parameters of soil for construction of Proposed O.H.R. of Petbindhi and Dhadangiri PWSS at Gopiballavpur-II Block under Jhargram Division, P.H.E. Dte. | 1086/JSD | 28/11/2024 | 14 | MOYTEC | 1.34 | 0 | 0 | 0
1050 | JHARGRAM | Jhargram Mechanical Division | DHADANGIRI AND ADJOINING MOUJAS , SM/16992 | New | Quotation for new service connection at Dhadangri T/W-II water supply scheme. | 117/JMD | 13/05/2024 | 0 | WBSEDCL | 3.86 | 0 | 0 | 0
1051 | JHARGRAM | Jhargram Division | DHADANGIRI AND ADJOINING MOUJAS , SM/16992 | New | Sinking of Tube Well , Pump House, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board & Accommodate FHTC(6721 nos) including 02(Two) Years Operation & Maintenance under JJM with allied work for DHADANGIRI, GOBINDAPUR, JUNSOLA, PETBINDHI & MAHAPAL PWSS in Gopiballavpur-II Block including supply of all labour & materials within Gopiballavpur Sub-Division under Jhargram Division, PHE Dte. | 1373/JHD | 16/08/2023 | 465 | M/S. EL-CON | 1574.44 | 0 | 0 | 0
1052 | JHARGRAM | Jhargram Mechanical Division | DHADANGIRI AND ADJOINING MOUJAS , SM/16992 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dhadangiri & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1251/JMD | 26/05/2023 | 885 | BHABANI PRASAD MANNA | 22.08 | 0 | 0 | 90
1053 | JHARGRAM | Jhargram Division | DHADANGIRI AND ADJOINING MOUJAS , SM/16992 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Dhadangiri and its Adjoining Mouzas PWSS , Block Gopiballavpur-II, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | 786/JSD | 09/08/2024 | 150 | DEBABRATA DUTTA | 4.71 | 0 | 0 | 0
1054 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Junsola And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18022 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Chingra and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2776/JMD | 05/09/2023 | 180 | ELECTRO ENTERPRISES | 32.07 | 0 | 0 | 0
1055 | JHARGRAM | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at Gramohan w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17116 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Champasol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2500/JMD | 25/08/2023 | 180 | MEGA SOLAR ENERGY | 75.09 | 0 | 0 | 0
1056 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Pithapura And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18026 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Chingra and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2776/JMD | 05/09/2023 | 180 | ELECTRO ENTERPRISES | 32.07 | 0 | 0 | 0
1057 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Rajband w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17079 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Pindrakuli and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2502/JMD | 25/08/2023 | 180 | SUBHASIS ROY | 31.3 | 0 | 0 | 0
1058 | JHARGRAM | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at Kendana And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17971 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Gohalmara and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2505/JMD | 25/08/2023 | 180 | SUBHASIS ROY | 75.13 | 0 | 0 | 0
1059 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Dalkati w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17058 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Pindrakuli and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2502/JMD | 25/08/2023 | 180 | SUBHASIS ROY | 31.3 | 0 | 0 | 0
1060 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Ramchandrapur w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17068 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Pindrakuli and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2502/JMD | 25/08/2023 | 180 | SUBHASIS ROY | 31.3 | 0 | 0 | 0
1061 | JHARGRAM | Jhargram Division | DHANSOL AND ADJOINING MOUJAS PWSS , SM/17581 | New | Material Requisition To Resource Division | 1506/JHD | 05/09/2023 | 0 | Resource Division | 28.78 | 0 | 0 | 0
1062 | JHARGRAM | Jhargram Mechanical Division | DHANSOL AND ADJOINING MOUJAS PWSS , SM/17581 | New | New service connection charges | 12/JMD/PFMS/JUL | 27/07/2023 | 0 | WBSEDCL | 2.83 | 0 | 0 | 0
1063 | JHARGRAM | Jhargram Mechanical Division | DHANSOL AND ADJOINING MOUJAS PWSS , SM/17581 | New | New service connection charges | 14/JMD/PFMS/APR | 27/07/2023 | 0 | WBSEDCL | 3.3 | 0 | 0 | 0
1064 | JHARGRAM | Jhargram Mechanical Division | DHANSOL AND ADJOINING MOUJAS PWSS , SM/17581 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dhansol & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2262/JMD | 09/08/2023 | 180 | RS ELECTROMECHANICAL CORPORATION | 21.96 | 0 | 0 | 91
1065 | JHARGRAM | Jhargram Division | DHANSOL AND ADJOINING MOUJAS PWSS , SM/17581 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of DHANSOLA and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 174/GPSD | 05/03/2024 | 30 | SANITARY PLANET | 4.18 | 0 | 0 | 100
1066 | JHARGRAM | Jhargram Division | DHANSOL AND ADJOINING MOUJAS PWSS , SM/17581 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (5510 Nos), etc. For ANANDAPUR, ANDARI, BHAMAL SANKRAIL, DHANSOL Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 567/JHD | 25/04/2023 | 860 | GOBINDA MAITY | 1535.46 | 0 | 0 | 75
1067 | JHARGRAM | Jhargram Division | DHANSOL AND ADJOINING MOUJAS PWSS , SM/17581 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Dhansola and its adjoining Mouzas, Block Sankrail, District Jhargram | 446/JHD | 14/03/2024 | 30 | NIKHIL CHANDRA MONDAL | 8.35 | 0 | 0 | 100
1068 | JHARGRAM | Jhargram Division | ANANDAPUR AND ADJOINING MOUJAS PWSS , SM/17583 | New | Material Requisition To Resource Division | 1502/JHD | 05/09/2023 | 0 | Resource Division | 20.38 | 0 | 0 | 0
1069 | JHARGRAM | Jhargram Mechanical Division | ANANDAPUR AND ADJOINING MOUJAS PWSS , SM/17583 | New | New service connection charges | 3/JMD/AUG | 17/08/2023 | 0 | WBSEDCL | 2.83 | 0 | 0 | 0
1070 | JHARGRAM | Jhargram Mechanical Division | ANANDAPUR AND ADJOINING MOUJAS PWSS , SM/17583 | New | New Service Connection charges | 30/JMD | 31/10/2023 | 0 | WBSEDCL | 4.73 | 0 | 0 | 0
1071 | JHARGRAM | Jhargram Mechanical Division | ANANDAPUR AND ADJOINING MOUJAS PWSS , SM/17583 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Anandapur & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2259/JMD | 09/08/2023 | 180 | DAS ENTERPRISE | 20.74 | 0 | 0 | 94
1072 | JHARGRAM | Jhargram Division | ANANDAPUR AND ADJOINING MOUJAS PWSS , SM/17583 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Anandapur and its adjoining Mouzas, Block Sankrail, District Jhargram | 1136/JHD | 06/08/2024 | 30 | KOUSIK MONDAL | 8.02 | 0 | 0 | 0
1073 | JHARGRAM | Jhargram Division | ANANDAPUR AND ADJOINING MOUJAS PWSS , SM/17583 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of ANANDAPUR and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 171/GPSD | 05/03/2024 | 30 | SAMIR PATRA | 4.23 | 0 | 0 | 100
1074 | JHARGRAM | Jhargram Division | ANANDAPUR AND ADJOINING MOUJAS PWSS , SM/17583 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (5510 Nos), etc. For ANANDAPUR, ANDARI, BHAMAL SANKRAIL, DHANSOL Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 567/JHD | 25/04/2023 | 860 | GOBINDA MAITY | 1535.46 | 0 | 0 | 75
1075 | JHARGRAM | Jhargram Division | ANANDAPUR AND ADJOINING MOUJAS PWSS , SM/17583 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection for Anandapur and its adjoining mouzas Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division of Jhargram Division, P.H.E.Dte. | 503/GPSD | 30/07/2024 | 10 | GOBINDA MAITY | 2.4 | 0 | 0 | 100
1076 | JHARGRAM | Jhargram Division | KULIANA AND ADJOINING MOUJAS PWSS , SM/17587 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Kuliana and its Adjoining Mouzas PWSS , Block Gopiballavpur-II, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | 782/JSD | 09/08/2024 | 30 | BINPUR-I A ONE ENGINEERS CO OPERATIVE SOCIETY | 4.82 | 0 | 0 | 0
1077 | JHARGRAM | Jhargram Mechanical Division | KULIANA AND ADJOINING MOUJAS PWSS , SM/17587 | New | Quotation for new service connection at Kuliana T/W-I water supply scheme. | 80/JMD | 29/04/2024 | 0 | WBSEDCL | 3.82 | 0 | 0 | 0
1078 | JHARGRAM | Jhargram Mechanical Division | KULIANA AND ADJOINING MOUJAS PWSS , SM/17587 | New | Quotation for new service connection at Kuliana T/W-II water supply scheme. | 81/JMD | 29/04/2024 | 0 | WBSEDCL | 2.99 | 0 | 0 | 0
1079 | JHARGRAM | Central Drilling | KULIANA AND ADJOINING MOUJAS PWSS , SM/17587 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1080 | JHARGRAM | Jhargram Division | KULIANA AND ADJOINING MOUJAS PWSS , SM/17587 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1081 | JHARGRAM | Jhargram Division | KULIANA AND ADJOINING MOUJAS PWSS , SM/17587 | New | Field Level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in fferent Pipe Water Supply Scheme (7 nos PWSS of 130 PWSS) within Gopiballavpur-II Block in the District of Jhargram under Jhargram Division. PHE Dte. Location- i) Chingra PWSS, ii) Gohalmara PWSS iii) Kendana PWSS iv) Kulina PWSS v) Sonakinia PWSS Vi) Tentilia PWSS vii) Chorchita PWSS | 368/JSD | 29/04/2025 | 150 | TECHVISION | 3.72 | 0 | 0 | 10
1082 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | 62 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-4) | 1835/JHD | 27/10/2023 | 60 | ASIS KUMAR SARANGI | 101.91 | 0 | 0 | 80
1083 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | Four numbers (4) of yield test process need to be done at Patharchakri & Makarbhula of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 533/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
1084 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | Four numbers (4) of yield test process need to be done at Purnapani & Chirugora of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 537/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
1085 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | Four numbers (4) of yield test process need to be done at Shankhabhanga & Kodalbani of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 534/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
1086 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | Four numbers (4) of yield test process need to be done at Majgerya & Birmadal of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 536/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
1087 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | Four numbers (4) of yield test process need to be done at Jamaimari & Jantalberya of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 535/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
1088 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | New Service Connection Charges for Chirugora, Birmadal & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1089 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | New Service Connection Charges for Shankhabhanga, Birmadal & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1090 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | New Service Connection Charges for Purnapani, Birmadal & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1091 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | New Service Connection Charges for Birmadal, Birmadal & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1092 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | New Service Connection Charges for Kodalbani, Birmadal & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1093 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | New Service Connection Charges for Patharchakri, Birmadal & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1094 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | New Service Connection Charges for Jamaimari, Birmadal & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1095 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | 31 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur II Block under Jhargram Division, PHE Dte. | 1714/JHD | 29/09/2023 | 820 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 848.26 | 0 | 0 | 45
1096 | JHARGRAM | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS , SM/17593 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | 384/JRWS | 31/01/2024 | 30 | CARTO | 0.82 | 0 | 0 | 100
1097 | JHARGRAM | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS , SM/17594 | New | Acceptance cum Formal work order for the work of Supply and delivery of different types of Drilling Martials in connection with Jal Jeevan Mission Program at Jhargram under Bankura Mechanical Division P.H.E Dte | 2038/BMD | 01/09/2023 | 60 | CHAKRABORTY MINING & ENGINEERING. | 22.91 | 0 | 0 | 100
1098 | JHARGRAM | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS , SM/17594 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W. in connection to JJM programme in Jhargram District by Rig unit KLR at B.M.S.D (D) under Bankura Mechanical Division PHE Dte. | 948/BMSD(D) | 17/11/2023 | 15 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 0 | 100
1099 | JHARGRAM | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS , SM/17594 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM Programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under B.M.D., P.H.E. Dte. | 984/BMSD(D) | 01/12/2023 | 15 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 0 | 100
1100 | JHARGRAM | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS , SM/17594 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM Programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under B.M.D, P.H.E Dte. | 264/BMSD(D) | 15/03/2024 | 15 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 0 | 100
1101 | JHARGRAM | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS , SM/17594 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under B.M.D., P.H.E. Dte. | 1028/BMSD(D) | 15/12/2023 | 15 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 0 | 100
1102 | JHARGRAM | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS , SM/17594 | New | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling site in Bhelaidiha GP of Binpur-II Block of Jhargram District in Connection to JJM programme under Bankura Mechanical Division P.H.E. Dte. | 20/BMSD(D) | 05/01/2024 | 20 | DEBJYOTI BASU | 0.97 | 0 | 0 | 100
1103 | JHARGRAM | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS , SM/17594 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under Bankura Mechanical Division P.H.E. Dte | 101/BMSD(D) | 31/01/2024 | 15 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 0 | 73
1104 | JHARGRAM | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS , SM/17594 | New | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling pin point place of Banksol, Barasol, Mahulbani, Hijla, Bansgar, Adgari etc site in Bhelaidiha gp, Binpur-II Block of Jhargram District in connection to JJM programme under Bankura Mechanical Division, P.H.E. Dte. | 250/BMSD(D) | 13/03/2024 | 122 | DEBJYOTI BASU | 0.97 | 0 | 0 | 100
1105 | JHARGRAM | Jhargram Mechanical Division | HIJLA AND ADJOINING MOUJAS PWSS , SM/17594 | New | New service connection charges | 11/JMD | 05/01/2024 | 0 | WBSEDCL | 1.05 | 0 | 0 | 0
1106 | JHARGRAM | Jhargram Mechanical Division | HIJLA AND ADJOINING MOUJAS PWSS , SM/17594 | New | New connection bill for Mahulbani in Bheliadiha GP | 76/JMD | 20/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1107 | JHARGRAM | Jhargram Mechanical Division | HIJLA AND ADJOINING MOUJAS PWSS , SM/17594 | New | New connection bill for Jagannathpur in Bheliadiha GP | 75/JMD | 20/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1108 | JHARGRAM | Jhargram Mechanical Division | HIJLA AND ADJOINING MOUJAS PWSS , SM/17594 | New | Erection & commissioning of 22 (twenty two) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Bhelaidiha G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Hijla (TSM/014334) and Banksol (TSM/015563) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 3015/JMD | 20/10/2023 | 794 | CONCORD ENGINEERING | 621.67 | 0 | 0 | 25
1109 | JHARGRAM | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Rohini PWSS to Accommodate FHTC under JJM at Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. , SM/17956 | Augmentation | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. III & IV as part of augmentation of Rohini W/S scheme under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | 2095/JMD | 03/08/2023 | 180 | WEST BENGAL ENGINEERING CO. | 19.76 | 0 | 0 | 0
1110 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Rohini PWSS to Accommodate FHTC under JJM at Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. , SM/17956 | Augmentation | SINKING OF 250 X 150 mm dia. X 150 Mtr. DEPTH RIG BORED TUBE WELL, BOUNDARY WALL & CONSTRUCTION OF SWITCH ROOM FOR REJUVENATION OF ROHINI WATER SUPPLY SCHEME WITH IN SANKRAIL BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. 2nd Call (Ref eNIT_21 of 2022-23 , SL No.-1 ) | 1716/JHD | 29/09/2023 | 662 | ASIS KUMAR SARANGI | 30.87 | 0 | 0 | 90
1111 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Petbindhi And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17967 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Petbindi and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2506/JMD | 25/08/2023 | 180 | SUJOY RANJAN BHOWMICK | 12.52 | 0 | 0 | 0
1112 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Simli w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17050 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Barabari and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2503/JMD | 25/08/2023 | 180 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 31.3 | 0 | 0 | 0
1113 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Panchami w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17057 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Pindrakuli and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2502/JMD | 25/08/2023 | 180 | SUBHASIS ROY | 31.3 | 0 | 0 | 0
1114 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Noharia And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17012 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Gohalmara and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2505/JMD | 25/08/2023 | 180 | SUBHASIS ROY | 75.13 | 0 | 0 | 0
1115 | JHARGRAM | Jhargram Division | RAMPURA AND ADJOINING MOUJAS , SM/12880 | New | Material Requisition To Resource Division | 958/JHD | 22/06/2023 | 0 | Resource Division | 30.92 | 0 | 0 | 0
1116 | JHARGRAM | Jhargram Division | RAMPURA AND ADJOINING MOUJAS , SM/12880 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of RAMPURA and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 164/GPSD | 05/03/2024 | 30 | MAHAVIR SAMPARK PVT. LTD. | 4.11 | 0 | 0 | 100
1117 | JHARGRAM | Jhargram Mechanical Division | RAMPURA AND ADJOINING MOUJAS , SM/12880 | New | New service connection charges for Rampura w/s scheme, t/w no.- II | 123/JMD | 20/05/2024 | 0 | WBSEDCL | 10.17 | 0 | 0 | 0
1118 | JHARGRAM | Jhargram Mechanical Division | RAMPURA AND ADJOINING MOUJAS , SM/12880 | New | New Service Connection Charges for Rampura P.H - I PWSS | 203/JMD | 14/06/2024 | 0 | WBSEDCL | 3.14 | 0 | 0 | 0
1119 | JHARGRAM | Jhargram Division | RAMPURA AND ADJOINING MOUJAS , SM/12880 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House , & Providing Functional Household Tap Connection (6745 Nos), etc. For RAGRA, SATKULI CHARAR, NOAGAON, RAMPURA Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 607/JHD | 04/05/2023 | 881 | GOBINDA MAITY | 1886.45 | 0 | 0 | 20
1120 | JHARGRAM | Central Drilling | RAMPURA AND ADJOINING MOUJAS , SM/12880 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1121 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | Conducting Geophysical investigation of twenty two (22) nos. sites in Bhelaidiha GP in Binpur-2 Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 2288/JMD | 10/08/2023 | 44 | SUBHASIS ROY | 4.12 | 0 | 0 | 97
1122 | JHARGRAM | Jhargram Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | 16 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for SILDA GP ( CHAINBERA ZONE-III JOYPUR PWSS) under Binpur-II Block under Jhargram Division, PHE Dte. | 1406/JHD | 18/08/2023 | 30 | SAIKAT DANDAPAT | 26.27 | 0 | 0 | 50
1123 | JHARGRAM | Jhargram Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | 8 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for SILDA GP ( CHAINBERA ZONE-III JOYPUR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-3 ) | 1951/JHD | 22/11/2023 | 90 | MONDAL PRECISION PRIVATE LIMITED | 194.87 | 0 | 0 | 25
1124 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | Construction of (125 mm X 115 mm X 200 mtr.) RBTW by DTH/ combination method for providing FHTC at SITAPUR & its adjacent Seventy Three (73) nos. villages under Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 2297/JMD | 11/08/2023 | 148 | MONDAL PRECISION PRIVATE LIMITED | 163.47 | 0 | 0 | 100
1125 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | New Service Connection Charges for Jhatiara PWSS | 417/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1126 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | New Service Connection Charges for Pakurasol PWSS.CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | 416/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1127 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM.(scheme code -TSM/015566 ) | 355/JMD | 13/09/2024 | 0 | SURAJ SERVICE STATION | 0.53 | 0 | 0 | 0
1128 | JHARGRAM | Jhargram Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | New Service Connection Charges for Hetyasol Chianbera Zone-III Joypur& Adjoining Moujas PWSS |  | 18/06/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1129 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | New Service connection charges. | 31/JMD | 18/01/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1130 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | New service connection charges | 42/JMD | 29/12/2023 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1131 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | Providing fuel & lubricant for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Jamirdiha & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 16/JMD | 10/01/2024 | 0 | SURAJ SERVICE STATION | 5 | 0 | 0 | 0
1132 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | New Service connection charges. | 9/JMD | 01/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1133 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | New Service Connection Charges for Srinathpur PWSS. CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | 418/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1134 | JHARGRAM | Jhargram Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | New Service Connection Charges for Hizli, Chianbera Zone-III Joypur& Adjoining Moujas PWSS |  | 18/06/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1135 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | New Service Connection Charges for Baramsol PWSS. CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | 415/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1136 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | New service connection | 68/JMD | 12/02/2024 | 0 | WBSEDCL | 0.84 | 0 | 0 | 0
1137 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Srinathpur & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 2790/JMD | 08/09/2023 | 502 | RSA ENTERPRISE | 22 | 0 | 0 | 91
1138 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | Erection & commissioning of 22 (twenty two) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Bhelaidiha G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Hijla (TSM/014334) and Banksol (TSM/015563) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 3015/JMD | 20/10/2023 | 794 | CONCORD ENGINEERING | 621.67 | 0 | 0 | 25
1139 | JHARGRAM | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS , SM/18746 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 200 mtr.) RBTW by DTH / Combination method at Sandapara G.P. in place of (Chainbera, Zone-I Darra (SM/17930), Chainbera, Zone-II Jarda (SM/17925) and Chainbera, Zone-III Joypur (SM/18746) w/s schemes under Binpur-II Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 193/JMD | 30/01/2025 | 352 | MONDAL PRECISION PRIVATE LIMITED | 58.26 | 0 | 0 | 20
1140 | JHARGRAM | Jhargram Division | JANGALKHAS AND ADJOINING MOUJAS PWSS , SM/12775 | New | Material Requisition To Resource Division | 1559/JHD | 07/09/2023 | 0 | Resource Division | 35.89 | 0 | 0 | 0
1141 | JHARGRAM | Jhargram Mechanical Division | JANGALKHAS AND ADJOINING MOUJAS PWSS , SM/12775 | New | Quotation for new service connection at Jangalkhash TW-I water supply scheme. | 140/JMD | 24/05/2024 | 0 | WBSEDCL | 11.72 | 0 | 0 | 0
1142 | JHARGRAM | Jhargram Mechanical Division | JANGALKHAS AND ADJOINING MOUJAS PWSS , SM/12775 | New | New Service connection charges. | 85/JMD | 21/03/2024 | 0 | WBSEDCL | 2.59 | 0 | 0 | 0
1143 | JHARGRAM | Central Drilling | JANGALKHAS AND ADJOINING MOUJAS PWSS , SM/12775 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1144 | JHARGRAM | Jhargram Division | JANGALKHAS AND ADJOINING MOUJAS PWSS , SM/12775 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Jangalkhas and its Adjoining Mouzas PWSS , Block: - Binpur-I, District: - Jhargram {TYPE - B} (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 773/JSD | 09/08/2024 | 153 | S. P. ENTERPRISE | 4.83 | 0 | 0 | 85
1145 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II , SM/06828 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khasjangal / Dhansola PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | 1406/MD | 26/11/2020 | 180 | SAIKAT DANDAPAT | 19.14 | 6.81 | 35.57 | 1
1146 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II , SM/06828 | Retrofitting | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM AT BIRKANAR PWSS OF BINPUR-I BLOCK UNDER JHARGRAM DIVISION ,PHE DTE.. | 8443208 | 26/03/2022 | 0 | DEBABRATA DUTTA | 6.69 | 0 | 0 | 0
1147 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II , SM/06828 | Retrofitting | Extension distribution pipe line to accommodation FHTC under JJM in Lakat PWSS Block-Binpur-I in the District of Jhargram. | 844313 | 06/07/2022 | 0 | S.B. TRADERS | 0.89 | 0 | 0 | 0
1148 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II , SM/06828 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kantapahari PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | 8443205 | 26/03/2022 | 0 | S.T. ENTERPRISE | 4.71 | 0 | 0 | 0
1149 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II , SM/06828 | Retrofitting | Relaying Distribution pipe line (Part) for Netai Water Supply Scheme to accommodate FHTC under Jhargram Sub-Division, PHE Dte. within Jhargram Division, PHE Dte. | 2249/MD | 28/12/2021 | 21 | S.B.TRADERS | 15.45 | 0 | 0 | 1
1150 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II , SM/06828 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kechanda PWSS of Binpur-II Block under Jhargram Division, PHE Dte. [PART - 2/2] (Allotted for near about 50% of the total work) | 1599/MD | 14/12/2020 | 180 | J.S.S. ENTERPRISE | 7.74 | 7.23 | 100 | 0
1151 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II , SM/06828 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kechanda PWSS of Binpur-II Block under Jhargram Division, PHE Dte. [PART - 1/2] (Allotted for near about 50% of the total work) | 1598/MD | 14/12/2020 | 180 | DEBABRATA DUTTA | 7.72 | 7.32 | 100 | 0
1152 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II , SM/06828 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Lakat PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | 1583/MD | 11/12/2020 | 180 | S.B. TRADERS | 8.2 | 5.28 | 100 | 0
1153 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Lalgarh PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 143/JSD | 12/08/2021 | 14 | INDRANIL DUTTA & ASSOCIATES | 4.84 | 0 | 0 | 1
1154 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | Restoration work due to laying of PHE pipe line along Lalgarh Ramgarh Road (MDR ) and KPDL road (MDR) due to augmentation of Lalgarh pipe water supply scheme under Jhargram Division, PHE Dte. | BP-2022-23-38 | 20/10/2022 | 0 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 18.7 | 0 | 0 | 0
1155 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January-2023 and February-2023 under Jhargram Division, PHE Dte. | 29A/JRWS | 28/12/2022 | 60 | PROVAT KUMAR DE | 0.93 | 0 | 0 | 100
1156 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | Supply, delivery, installation & commissioning of electro-mechanical components at T/W no. III of Lalgarh water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1942/JMD | 28/07/2023 | 15 | M/S. CHANDRANATH MUKHERJEE | 9.27 | 0 | 0 | 100
1157 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 300 cum and staging height 20 mtr. with including supply of all labour & materials for Augmentation of Ground based Lalgarh PWSS in Binpur- I Block within Jhargram District under Jhargram Division, PHE Dte. | 875/MD | 10/05/2022 | 180 | DULAL CHANDRA DAS | 329.37 | 0 | 0 | 0
1158 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | Material Requisition To Resource Division | 498/MD | 15/03/2022 | 0 | Resource Division | 18.23 | 0 | 0 | 0
1159 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | Lalgarh-Ramgarh road from 0.00 kmp to 1.50 kmp and KPDL Road from 34.00 kmp to 35.00 kmp with link road 1.05 km,restoration work for laying of pipeline due to augmentation of Lalgarh pipe water supply scheme by PHE Dte. under Jhargram Highway Division in the District of Jhargram. | BP-2023-24-36 | 15/05/2023 | 0 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 31.65 | 0 | 0 | 0
1160 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | Transfer to EE/JSD, PHE Dte. ( Aug. of Lalgarh PWSS) | BP-2022-23-464 | 20/12/2022 | 0 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 98 | 0 | 0 | 0
1161 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | Supply, delivery, installation & commissioning of electro-mechanical components at T/W no. I, II and renovation of existing compound lighting arrangement with other allied works at Lalgarh water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1941/JMD | 28/07/2023 | 30 | M/S. EMMESS | 21.22 | 0 | 0 | 100
1162 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | Meter shifting bill for Lalgarh pwss, P/H/ no.-II | 25/JMD | 15/01/2024 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
1163 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | Supply delivery of Different dia CIDF S/V for the work of ¿ Augmentation of Ground Water Based Water Supply Scheme for Lalgarh to Accommodate FHTC in Block Binpur-I under Jhargram Sub Division within Jhargram Division, PHE Dte. | 434/JSD | 10/08/2022 | 7 | DULAL CHANDRA DAS | 4.42 | 0 | 0 | 100
1164 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | MS STRUCTURAL GANG WAY CUM BRIDGE FOR CROSSING 200 MM HDPE PIPE OF DISTRIBUTION MAIN OF LAGARH P.W.S.S. OVER SAHAR KHAL (LOCAL NAME) IN BETWEEN LALGARH AND CHUNPARA UNDER BINPUR -I DEV. BLOCK WITHIN JHARGRAM SUB-DIVISION UNDER JHARGRAM DIVISION P.H.E.DTE. | 973/JSD | 10/11/2023 | 21 | MAMPI ENTERPRISE | 4.28 | 0 | 0 | 100
1165 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09373 | Augmentation | Laying of Additional Distribution Pipe Line for Augmentation of Ground Water Based Lalgarh PWSS To Accommodate FHTC In Binpur-I Block within Jhargram district under Jhargram Division P.H.E Dte. | 1416/JHD | 22/08/2023 | 45 | MAMPI ENTERPRISE | 10.1 | 0 | 0 | 90
1166 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Supply delivery of Different dia CIDF S/V for the work of ¿ Augmentation of Ground Water Based Water Supply Scheme for Odalchua to Accommodate FHTC in Block Binpur - II under Jhargram Sub Division within Jhargram Division, PHE Dte. | 427/JSD | 05/08/2022 | 7 | SUNIL DULE | 3.44 | 0 | 0 | 1
1167 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Supply, delivery& installation of submersible pumping machinary and other Electro-Mechanical accessories for newly sunk tube well under JJM programme at Odolchua water Supply scheme T/w no-1 (Chirakuti Mouza ,JL No-91) t under Jhargram Mechanical Division P.H.E Dte. in the district of Jhargram. | 3326/JMD | 14/11/2022 | 30 | DEBJYOTI BASU | 5.42 | 0 | 0 | 0
1168 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Payment for new service connection of WBSEDCL. | 20/JMD/PFMS/SEP | 29/09/2022 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1169 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tubwell (Replacement) by DTH Method for Augmentation of Source of Odalchua PWSS under Jhargram Division P.H.E. Dte. | BP-2021-22-473 | 16/03/2022 | 0 | SAIKAT DANDAPAT | 1.77 | 0 | 0 | 0
1170 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Odalchua PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | BP-2021-22-417 | 23/02/2022 | 0 | LEMNISCATE | 2.24 | 0 | 0 | 0
1171 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.96 | 0 | 0 | 0
1172 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Construction of 3.60 M X 3.0 M size Switch Room-Cum-Guard room with Sanitary Arrangement for Odalchua Water Supply Scheme within Jhargram Sub-Division P.H.E. Dte. Under Jhargram Division P.H.E.Dte. | 389/JSD | 27/07/2022 | 45 | SAIKAT DANDAPAT | 4.78 | 0 | 0 | 100
1173 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work for Augmentation of Ground Water Based Odalchua PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | 177/MD | 01/02/2022 | 45 | PROVAT KUMAR DE | 47.08 | 0 | 0 | 1
1174 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Material Requisition To Resource Division | 2160/MD | 17/12/2021 | 0 | Resource Division | 1.36 | 0 | 0 | 0
1175 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | New Service connection | 17/JMD | 10/11/2023 | 0 | WBSEDCL | 0.26 | 0 | 0 | 0
1176 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | New Service connection | 5/JMD | 11/10/2023 | 0 | WBSEDCL | 0.36 | 0 | 0 | 0
1177 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work for Augmentation of Ground Water Based Odalchua PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | 177/MD | 01/02/2022 | 45 | PROVAT KUMAR DE | 47.08 | 0 | 0 | 100
1178 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Providing solarization of WBSEDCL energised pumping installation at tube well no.-I & II of Odalchua w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2985/JMD | 13/03/2024 | 30 | DEBJYOTI BASU | 6.26 | 0 | 0 | 0
1179 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tube well no. II of Odalchua piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 2986/JMD | 16/10/2023 | 120 | DEBJYOTI BASU | 7.08 | 0 | 0 | 100
1180 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | Supply delivery & Installation of on-line booster pumping machinery at Odalchua PWSS of Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 2984/JMD | 13/03/2024 | 15 | DEBJYOTI BASU | 3.12 | 0 | 0 | 100
1181 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | LAFT OUT HOUSEHOLD FOR ACCOMODATE FUNCTIONAL HOUSE TAP CONNECTION (F.H.T.C.), LAYING PIPE LINE CONNECTION AT DHOBAKACHA & CHIRAKUTI MOUZA UNDER AUGMENTATION OF ODALCHUA PWSS WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. | 435/JSD | 08/05/2025 | 7 | MAHAVIR SAMPARK PVT. LTD. | 0.48 | 0 | 0 | 0
1182 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09375 | Augmentation | REPAIRING OF EXISTING F.H.T.C AT MOUZA ODALCHUA UNDER ODALCHUA W/S SCHEME WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE | 1082/JSD | 27/11/2024 | 14 | DEBABRATA DUTTA | 0.97 | 0 | 0 | 100
1183 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09383 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Rantua PWSS in Gopiballavpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 113/JSD | 22/07/2021 | 14 | ROY CHOWDHURY ASSOCIATES | 4.49 | 0 | 0 | 1
1184 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09383 | Augmentation | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.68 | 0 | 0 | 0
1185 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09383 | Augmentation | Purchasing of Materials. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.68 | 0 | 0 | 0
1186 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09383 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Sinking of 250 X 150mm dia. X 120 Mtr. Depth Rig bored Tube well for Augmentation of Ground Based Rantua PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | 137/MD | 27/01/2022 | 60 | SUNIL DULE | 82.58 | 0 | 0 | 1
1187 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09383 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories at T/W no. III & IV as part of augmentation of Rantua W/S scheme under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | 2093/JMD | 03/08/2023 | 180 | RSA ENTERPRISE | 19.73 | 0 | 0 | 0
1188 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09383 | Augmentation | Supply, delivery and Installation of new pumping machinery and other electro mechanical accessories at Rantua T/W no -II water supply scheme at Gopiballavpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1661/JMD | 01/08/2022 | 15 | BUSR ENGINEERING | 4.54 | 0 | 0 | 0
1189 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09383 | Augmentation | Supply, delivery & installation of voltage stabilizer, chlorine machine and other allied works at Rantua tubewell no. 2 water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | 3636/JMD | 07/12/2022 | 30 | BUSR ENGINEERING | 5.67 | 0 | 0 | 0
1190 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09383 | Augmentation | Replacement of pipeline from Bajnaguri Chawk to Bajanaguri Primary School and installation of different dia sluice valves at different position of distribution pipeline network for Rantua PWSS in Gopiballavpur-II block Jhargrm Division, PHE Dte | 215/JHD | 15/02/2023 | 45 | SUNIL DULE | 10.64 | 0 | 0 | 80
1191 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09383 | Augmentation | Material Requisition To Resource Division | 2164/MD | 17/12/2021 | 0 | Resource Division | 8.06 | 0 | 0 | 0
1192 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09383 | Augmentation | Money transfer to EE/JSD. | BP-2022-23-691 | 10/03/2023 | 0 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 3.63 | 0 | 0 | 0
1193 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09383 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Sinking of 250 X 150mm dia. X 120 Mtr. Depth Rig bored Tube well for Augmentation of Ground Based Rantua PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | 137/MD | 27/01/2022 | 60 | SUNIL DULE | 14.43 | 0 | 0 | 100
1194 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Creation of Water Supply System at Different Sourceless school in Binpur-II and Jamboni Block with DTH tubewell within Jhargram District under Jhargram Division, PHE Dte. | 273/JHD | 12/09/2022 | 21 | SAIKAT DANDAPAT | 22.83 | 0 | 0 | 0
1195 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Water Supply System at Different Source less school in Nayagram Block within Jhargram District under Jhargram Division PHE Dte. | 502/JHD | 13/04/2023 | 45 | SUNIL KUMAR MANDAL | 14.43 | 0 | 0 | 100
1196 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Surging, developing, washing & others allied works to rejuvenate the water sources at Manikapara High School to provide safe drinking water under Jhargram Dev. Block within Jhargram Division,PHE Dte. | 385/JSD | 29/05/2023 | 15 | SAURABH KAR | 0.75 | 0 | 0 | 100
1197 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Survey & Collection of Data Through Mobile App Regarding Availability of Drinking Water, Sanitation Facilities & other Parameters in Primary, Upper Primary School, Anganwadi Centers under Jhargram Division PHE Dte. | 176/JHD | 12/08/2022 | 30 | ARUNALOY SCIENTIFIC HOUSE | 4.59 | 0 | 0 | 100
1198 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Water Supply System at Different Sourceless school in Binpur-I Block within Jhargram District under Jhargram Division PHE Dte. | 854/JHD | 08/06/2023 | 45 | RITESH AGARWALL | 22.7 | 0 | 0 | 90
1199 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Water Supply System at Different Sourceless school in Gopiballavpur-II Block within Jhargram District under Jhargram Division PHE Dte. | 856/JHD | 08/06/2023 | 30 | MANNA COMPUTER | 10.58 | 0 | 0 | 100
1200 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Sinking of Tube-wells and water supply arrangement at Ambihat Primary School in Gopiballavpur-II Block under Jhargram Division, PHE Dte. | 743/JSD | 17/08/2023 | 21 | GOPESH DEY | 2.62 | 0 | 0 | 100
1201 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Installation of 150 mm X 100 mm Dia. X 135 Mtr. DepthTube Well with Installation of Pumping Machinery for Jhargram Raj College Hostel at Jhargram Block within Jhargram District under Jhargram Division, P.H.E. Dte. | 965/JSD | 10/11/2023 | 21 | MMS CONSTRUCTIONS PVT.LTD. | 4.53 | 0 | 0 | 100
1202 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Installation of 150 mm X 100 mm Dia. X 135 Mtr. DepthTube Well with Installation of Pumping Machinery for Rani Binod Manjari Govt. Girl's High School at Jhargram Block within Jhargram District under Jhargram Division, P.H.E. Dte. | 964/JSD | 10/11/2023 | 21 | J.S.S. ENTERPRISE | 4.54 | 0 | 0 | 100
1203 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Water Supply System at Different Sourceless school in Gopiballavpur-I Block within Jhargram District under Jhargram Division PHE Dte.(Part-II)) 3 rd Call, (Ref eNIT_14 of 2022-23 2nd Call, SL No.-14) | 1997/JHD | 01/12/2023 | 45 | BISHNU PADA NANDI | 27.7 | 0 | 0 | 100
1204 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | EXTENTION PIPELINE AND STAND POST FOR DIFFERENT NEWLY CONSTRUCTED SUB-HEALTH CENTER UNDER DIFFERENT BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. | 91/JSD | 06/02/2024 | 30 | MAA CONSTRUCTION | 2.09 | 0 | 0 | 60
1205 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Installation of 150 mm X 100 mm Dia. X 135 Mtr. DepthTube Well with Installation of Pumping Machinery of Jhargram Raj College Ladies Hostel at Jhargram District under Jhargram Division, P.H.E. Dte. | 751/JSD | 06/08/2024 | 21 | HONEY CONSTRUCTION | 4.62 | 0 | 0 | 100
1206 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Water Supply System at Different Source less school in Jhargram Block within Jhargram District under Jhargram Division PHE Dte. | 1497/JHD | 02/07/2025 | 45 | PRANTIK DRILLING AGENCY | 22.17 | 0 | 0 | 0
1207 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Water Supply System at Different Sourceless school in Jamboni Block within Jhargram District under Jhargram Division PHE Dte. 4th Call, (1st Call Ref eNIT_09 of 2022-23, SL No.-16, 2nd Call Ref eNIT_14 of 2022-23, SL No.-16, 3rd call Ref eNIT_12 of 2023-24, SL No.-7 ) | 914/JHD | 08/07/2024 | 45 | RAMASISH ENTERPRISE | 30.37 | 0 | 0 | 65
1208 | JHARGRAM | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. , SM/10358 | School | Water Supply System at Different Sourceless school in Gopiballavpur-1 Block within Jhargram District under Jhargram Division PHE Dte. (Part-1) 3rd Call (Ref. eNit No._14 of 2022-23 2nd call SL-13) | 1996/JHD | 01/12/2023 | 45 | AMITAVA CHAKRABORTY | 25.72 | 0 | 0 | 55
1209 | JHARGRAM | Jhargram Mechanical Division | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATION AT ROHINI GROUND WATER BASED PIPED WATER SUPPLY SCHEME UNDER JJM PROGRAMME , SM/10289 | Solarisation | Providing Solarizatin of WBSEDCL Energised Pumping installation at Rohini Ground water Based piped Water supply Scheme under JJM Programme under Jhargram Mechanical Division, PHE Dte. | 339/JMD | 03/03/2022 | 30 | DIPALI CONSTRUCTION | 6.17 | 0 | 0 | 100
1210 | JHARGRAM | Jhargram Mechanical Division | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATION AT ROHINI GROUND WATER BASED PIPED WATER SUPPLY SCHEME UNDER JJM PROGRAMME , SM/10289 | Solarisation | Additional work in connection with providing solarisation of WBSEDCL Energised Pumping installation at Rohini Ground water Based piped Water supply Scheme under JJM Programme under Jhargram Mechanical Division, PHE Dte. | 1962/JMD | 28/07/2023 | 7 | DIPALI CONSTRUCTION | 0.19 | 0 | 0 | 100
1211 | JHARGRAM | Jhargram Mechanical Division | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATION AT ROHINI GROUND WATER BASED PIPED WATER SUPPLY SCHEME UNDER JJM PROGRAMME , SM/10289 | Solarisation | Supply, installation, testing & commissioning of sprinkler system facility for cleaning the installed solar panel with other allied works at Rohini piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | 568/W/MMSD(D) | 04/07/2024 | 7 | RSA ENTERPRISE | 0.5 | 0 | 0 | 100
1212 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10483 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Jhitka PWSS in Binpur-1Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 76/JSD | 25/06/2021 | 14 | RADIANT | 1.89 | 0 | 0 | 1
1213 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10483 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Jhitka PWSS in Binpur-1Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | 02/08/2022 | 0 | RADIANT | 1.71 | 0 | 0 | 0
1214 | JHARGRAM | Midnapore Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10483 | Augmentation | Retrofitting to accommodate FHTC under JJM in Jhitka PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | 1582/MD | 11/12/2020 | 180 | RAMENDRA NATH KAR | 15.06 | 0 | 0 | 80
1215 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10483 | Augmentation | Relaying of distribution pipe line (part)(Phase-I) of Jitka pipe water supply scheme to accommodate FHTC in Binpur-I Block under Jhargram Sub-Division within Jhargram Division P.H.E Dte. | 458/JHD | 11/11/2022 | 60 | RAMENDRA NATH KAR | 7.77 | 0 | 0 | 0
1216 | JHARGRAM | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10483 | Augmentation | New service connection | 26/JMD | 17/10/2023 | 0 | WBSEDCL | 5.63 | 0 | 0 | 0
1217 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10483 | Augmentation | Restoration work for laying pipeline along the Kaiaberia-Pirakata-Dhansole-Lalgarh road for Jhitka Water Supply Scheme under Jhargram Division, PHE Dte. | BP-2022-23-177 | 15/03/2023 | 0 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 1.46 | 0 | 0 | 0
1218 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10483 | Augmentation | Repair, renovation and painting of 2 nos Pump houses and 2 nos boundary walls for Jitka w/s scheme at Binpur-I block under Jhargram Sub-division within Jhargram Division, PHE Dte. . (2nd Call) [Ref. eNIT 03 OF AE/JSD OF 2024-2025, SL No. 01] | 1105/JSD | 04/12/2024 | 14 | SUPRAKASH MONDAL | 4.01 | 0 | 0 | 0
1219 | JHARGRAM | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10483 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories for additional T/Well at head work site as part of augmentation of Jhitka W/S scheme under Jhargram Mechanical Division, PHE. Dte. in the dist. of Jhargram. | 2516/JMD | 25/08/2023 | 30 | SHOVAN KUMAR DAS | 9.41 | 0 | 0 | 80
1220 | JHARGRAM | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10483 | Augmentation | Excess quotation payment for Jhitka-1 ,Binpur-1. | 66/JMD | 12/02/2024 | 0 | WBSEDCL | 0.93 | 0 | 0 | 0
1221 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Interconnection between newly laid distribution pipeline with raising main and P.W.D road crossing work along with restoration for Manikpara PWSS under Jhargram Sub Division within Jhargram Division, P.H.E DTE. | 430/JSD | 05/08/2022 | 45 | SOURABH KAR | 3.46 | 0 | 0 | 1
1222 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Manikpara PWSS in Jhargram Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 74/JSD | 25/06/2021 | 14 | RADIANT | 3.62 | 0 | 0 | 1
1223 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Manikpara PWSS in Jhargram Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | 16/08/2022 | 0 | RADIANT | 3.6 | 0 | 0 | 0
1224 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Day to day operation & maintenance of Rising main & delivery main pipe line (CI/DI/ HDPE/UPVC/AC) with all related structure i.e. OHR etc. of Manikpara within Jhargram Sub Division under Jhargram Division, PHE Dte. from 01.10.2022 to 31.12.2022. | 543/JSD | 23/09/2022 | 91 | SOURABH KAR | 0.4 | 0 | 0 | 100
1225 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Uploading, Development upgradation of all collected FHTC data and special features alongwith reorientation of JJM_ IMIS Dashboard (June-2023 to August-2023). | 117A/JRWS | 31/05/2023 | 90 | GOPAL JANA | 0.93 | 0 | 0 | 100
1226 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Material Requisition To Resource Division | 1706/JHD | 28/09/2023 | 0 | Resource Division | 10.81 | 0 | 0 | 0
1227 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | New service connection charges. | 18/JMD/PFMS/JUL | 31/07/2023 | 0 | WBSEDCL | 3.02 | 0 | 0 | 0
1228 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Laying Of Extention Distribution Pipe Line and Sinking Of T/W For Augmentation of Ground Water Based Manikpara Pwss to Accommodate FHTC In Jhargram Block Within Jhargram District Under Jhargram Division P.H.E Dte. | 1852/JHD | 31/10/2023 | 30 | DIPAK KUMAR BAKLY | 35.03 | 0 | 0 | 100
1229 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Providing additional FHTC under Manikpara W/S Scheme Jhargram Block under Jhargram Division, PHE Dte.( Part- A) | 444/JHD | 14/03/2024 | 15 | KOUSIK MONDAL | 9.67 | 0 | 0 | 95
1230 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Providing additional FHTC under Manikpara W/S Scheme Jhargram Block under Jhargram Division, PHE Dte. (Part-B) | 332/JHD | 28/02/2024 | 15 | DIPAK KUMAR BAKLY | 9.96 | 0 | 0 | 95
1231 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Augmentation of ground water based Manikpara Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work & Sinking of 250 mm x 150 mm x 165 m Tube Well and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Jhargram Dev. Block under Jhargram Division, PHE Dte. | 252/JHD | 06/09/2022 | 180 | DIPAK KUMAR BAKLY | 245.7 | 0 | 0 | 100
1232 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I of Manikpara piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1256/JMD | 26/05/2023 | 180 | K.S.P. ENTERPRISE | 10.81 | 0 | 0 | 95
1233 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Supply, delivery, installation, commissioning of pumping machinery and allied electro-mechanical works for Augmentation of t/w no. II of Manikpara water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | 2123/JMD | 22/02/2024 | 30 | SUBHRA ENTERPRISE | 9.73 | 0 | 0 | 100
1234 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10490 | Augmentation | Laying of rising main with interconnection with 2 nos tubewells and laying distribution pipeline from Manikpara Vivekananda more to propose O.H.R and by pass connection and Pump house for Augmentation of Manikpara PWSS in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | 882/JHD | 08/06/2023 | 481 | DIPAK KUMAR BAKLY | 33.98 | 0 | 0 | 95
1235 | JHARGRAM | Jhargram Division | BHAMAN SANKRAIL AND ADJOINING MOUJAS PWSS , SM/12352 | New | Material Requisition To Resource Division | 1505/JHD | 05/09/2023 | 0 | Resource Division | 46.05 | 0 | 0 | 0
1236 | JHARGRAM | Jhargram Division | BHAMAN SANKRAIL AND ADJOINING MOUJAS PWSS , SM/12352 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of BHAMAL SANKRAIL and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 166/GPSD | 05/03/2024 | 30 | FIROJ KHAN | 4.14 | 0 | 0 | 100
1237 | JHARGRAM | Jhargram Division | BHAMAN SANKRAIL AND ADJOINING MOUJAS PWSS , SM/12352 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (5510 Nos), etc. For ANANDAPUR, ANDARI, BHAMAL SANKRAIL, DHANSOL Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 567/JHD | 25/04/2023 | 860 | GOBINDA MAITY | 1535.46 | 0 | 0 | 75
1238 | JHARGRAM | Central Drilling | BHAMAN SANKRAIL AND ADJOINING MOUJAS PWSS , SM/12352 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1239 | JHARGRAM | Jhargram Division | BALISHIRA AND ADJOINING MOUJAS PWSS , SM/12388 | New | Material Requisition To Resource Division | 1552/JHD | 07/09/2023 | 0 | Resource Division | 31.84 | 0 | 0 | 0
1240 | JHARGRAM | Jhargram Division | BALISHIRA AND ADJOINING MOUJAS PWSS , SM/12388 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Balishira and its Adjoining Mouzas PWSS , Block Binpur-I, District Jhargram TYPE - B Total length 50 mtr,column size 250250mm,3.00 M cc ht.- 2.300mtr from G.L | 770/JSD | 09/08/2024 | 30 | MAA SUSOMA & COMPANY | 4.84 | 0 | 0 | 0
1241 | JHARGRAM | Jhargram Mechanical Division | BALISHIRA AND ADJOINING MOUJAS PWSS , SM/12388 | New | New Service connection charges. | 201/JMD | 14/06/2024 | 0 | WBSEDCL | 13.6 | 0 | 0 | 0
1242 | JHARGRAM | Jhargram Mechanical Division | BALISHIRA AND ADJOINING MOUJAS PWSS , SM/12388 | New | Qutation for new service connection at Balishira T/W -2 WATER SUPPLY SCHEME. | 92/JMD | 22/03/2024 | 0 | WBSEDCL | 2.92 | 0 | 0 | 0
1243 | JHARGRAM | Central Drilling | BALISHIRA AND ADJOINING MOUJAS PWSS , SM/12388 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1244 | JHARGRAM | Jhargram Mechanical Division | BRAHMANDANA AND ADJOINING MOUJAS PWSS , SM/12392 | New | New Service Connection Charges for Brahmandana T/W-II PWSS | 189/JMD | 30/03/2024 | 0 | WBSEDCL | 5.88 | 0 | 0 | 0
1245 | JHARGRAM | Jhargram Mechanical Division | BRAHMANDANA AND ADJOINING MOUJAS PWSS , SM/12392 | New | New Service Connection Charges for Brahmandana T/W - I PWSS | 190/JMD | 30/03/2024 | 0 | WBSEDCL | 4.29 | 0 | 0 | 0
1246 | JHARGRAM | Central Drilling | BRAHMANDANA AND ADJOINING MOUJAS PWSS , SM/12392 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1247 | JHARGRAM | Jhargram Division | BRAHMANDANA AND ADJOINING MOUJAS PWSS , SM/12392 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1248 | JHARGRAM | Jhargram Mechanical Division | KHAS JANGAL AND ADJOINING MOUJAS PWSS , SM/12439 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Khasjangal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1233/JMD | 26/05/2023 | 180 | AVIK KUMAR GHOSH | 20.78 | 0 | 0 | 0
1249 | JHARGRAM | Central Drilling | KHAS JANGAL AND ADJOINING MOUJAS PWSS , SM/12439 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 91/CDD | 25/04/2024 | 122 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 0 | 0 | 10
1250 | JHARGRAM | Jhargram Division | KHAS JANGAL AND ADJOINING MOUJAS PWSS , SM/12439 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1251 | JHARGRAM | Jhargram Division | TENTULIA AND ADJOINING MOUJAS PWSS , SM/12449 | New | Material Requisition To Resource Division | 1589/JHD | 08/09/2023 | 0 | Resource Division | 70.94 | 0 | 0 | 0
1252 | JHARGRAM | Central Drilling | TENTULIA AND ADJOINING MOUJAS PWSS , SM/12449 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1253 | JHARGRAM | Jhargram Division | TENTULIA AND ADJOINING MOUJAS PWSS , SM/12449 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House& Providing Functional Household Tap Connection (2163 Nos), including 02(Two)Years Operation & Maintanance For KHAMARPARA, TENTULIA Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 1207/JHD | 26/07/2023 | 727 | SUNIL DULE | 651.28 | 0 | 0 | 70
1254 | JHARGRAM | Jhargram Division | SIJUA AND ADJOINING MOUJAS PWSS , SM/12519 | New | Material Requisition To Resource Division | 1534/JHD | 06/09/2023 | 0 | Resource Division | 17.07 | 0 | 0 | 0
1255 | JHARGRAM | Jhargram Division | SIJUA AND ADJOINING MOUJAS PWSS , SM/12519 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Sijua and its Adjoining Mouzas PWSS , Block Binpur-I, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | 771/JSD | 09/08/2024 | 30 | M/S S.B. ENTRPRISE | 4.54 | 0 | 0 | 0
1256 | JHARGRAM | Jhargram Mechanical Division | SIJUA AND ADJOINING MOUJAS PWSS , SM/12519 | New | NEW SERVICE CONNECTION CHARGES FOR SIJUA T/W - I PWSS | 50/JMD | 12/03/2024 | 0 | WBSEDCL | 4.98 | 0 | 0 | 0
1257 | JHARGRAM | Jhargram Mechanical Division | SIJUA AND ADJOINING MOUJAS PWSS , SM/12519 | New | NEW SERICE CONNECTION CHARGES FOR SIJUA T/W -II PWSS | 51/JMD | 12/03/2024 | 0 | WBSEDCL | 5.28 | 0 | 0 | 0
1258 | JHARGRAM | Central Drilling | SIJUA AND ADJOINING MOUJAS PWSS , SM/12519 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1259 | JHARGRAM | Jhargram Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. , SM/12325 | New | Material Requisition To Resource Division | 1592/JHD | 08/09/2023 | 0 | Resource Division | 33.72 | 0 | 0 | 0
1260 | JHARGRAM | Jhargram Mechanical Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. , SM/12325 | New | New service connection | 28/AUG | 29/08/2023 | 0 | WBSEDCL | 2.83 | 0 | 0 | 0
1261 | JHARGRAM | Jhargram Mechanical Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. , SM/12325 | New | New service connection | 26/Aug | 29/08/2023 | 0 | WBSEDCL | 11.35 | 0 | 0 | 0
1262 | JHARGRAM | Jhargram Mechanical Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. , SM/12325 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Panchami & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1229/JMD | 26/05/2023 | 180 | JAGANNATH ENTERPRISE | 20.76 | 0 | 0 | 70
1263 | JHARGRAM | Jhargram Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. , SM/12325 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Panchami and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | 2268/JHD | 02/12/2024 | 30 | TAPAN KUMAR MANDAL | 7.92 | 0 | 0 | 0
1264 | JHARGRAM | Jhargram Mechanical Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. , SM/12325 | New | Additional service connection charges of Panchami-1 water supply scheme | 25/JMD | 24/04/2024 | 0 | WBSEDCL | 4.12 | 0 | 0 | 0
1265 | JHARGRAM | Jhargram Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. , SM/12325 | New | Pump House , Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, Accommodate FHTC (336 nos) under JJM with allied work for PANCHAMI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1325/JHD | 10/08/2023 | 90 | DIVINE | 71.48 | 0 | 0 | 100
1266 | JHARGRAM | Jhargram Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. , SM/12325 | New | Construction of 150 cum OHR, Laying distribution pipe line, soil investigation for PANCHAMI AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 5th Call (Ref: 1st Call eNIT_16 of 2022-23, SL No.-1 and 2nd Call eNIT_37 of 2023-24, SL No.-1, 3rd Call eNIT_13 of 2023-24, SL No.-1, 4th Call eNIT_22 of 2023-24, SL No.-2) | 987/JHD | 16/07/2024 | 390 | SRIKANTA MONDAL | 79.97 | 0 | 0 | 45
1267 | JHARGRAM | Jhargram Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. , SM/12325 | New | Trial run for PANCHAMI AND ADJOINING MOUZAS PWSS scheme within Jhargram Block under Jhargram Division, PHE Dte. for 3 months. | 732/JHD | 02/04/2025 | 91 | SUNIL DULE | 0.7 | 0 | 0 | 0
1268 | JHARGRAM | Jhargram Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. , SM/12325 | New | Laying distribution pipe line, Accommodate FHTC (200 nos) for PANCHAMI AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (2nd Call) | 883/JHD | 08/06/2023 | 727 | PALCON | 51.64 | 0 | 0 | 98
1269 | JHARGRAM | Jhargram Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. , SM/12325 | New | Sinking of Tube Well , Laying distribution pipe line, Accommodate FHTC (400 nos) under JJM with allied work for PANCHAMI AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 646/JHD | 11/05/2023 | 90 | SUNIL DULE | 79.43 | 0 | 0 | 90
1270 | JHARGRAM | Jhargram Division | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12328 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Dudkundi GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | 1841/JHD | 20/09/2024 | 10 | MANOJ KUMAR MAHATA | 0.58 | 0 | 0 | 100
1271 | JHARGRAM | Jhargram Division | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12328 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Lodhasuli GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | 1842/JHD | 20/09/2024 | 10 | GOPAL JANA | 0.92 | 0 | 0 | 100
1272 | JHARGRAM | Jhargram Mechanical Division | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12328 | New | new service connection charges at Burimole-2 water supply scheme | 73/JMD | 29/04/2024 | 0 | WBSEDCL | 3.72 | 0 | 0 | 0
1273 | JHARGRAM | Jhargram Mechanical Division | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12328 | New | new service connection charges at Burimol-1 water supply scheme | 74/JMD | 29/04/2024 | 0 | WBSEDCL | 5.38 | 0 | 0 | 0
1274 | JHARGRAM | Central Drilling | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12328 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1275 | JHARGRAM | Jhargram Division | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12328 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1276 | JHARGRAM | Jhargram Division | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12328 | New | Construction of boundary wall and Allied works At Burimol, Rajband, Bhaudi , Metial 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1077/JHD | 25/07/2024 | 211 | M/S MITRA BROTHERS | 48.9 | 0 | 0 | 40
1277 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Noagoan w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16918 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Satkuli Charar and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2501/JMD | 25/08/2023 | 180 | THE BUSINESS ENGINEERS INDIA | 75.12 | 0 | 0 | 0
1278 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at ANKRO AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16690 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Jangalkhas and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2772/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 77.3 | 0 | 0 | 0
1279 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at TILABANI AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16704 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Bandarbani and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2774/JMD | 05/09/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 64.39 | 0 | 0 | 0
1280 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Champasol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17115 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Champasol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2500/JMD | 25/08/2023 | 180 | MEGA SOLAR ENERGY | 75.09 | 0 | 0 | 0
1281 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Metial w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17117 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Patharnala and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2499/JMD | 25/08/2023 | 180 | RSA ENTERPRISE | 75.13 | 0 | 0 | 0
1282 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Rautarapur w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17121 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Patharnala and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2499/JMD | 25/08/2023 | 180 | RSA ENTERPRISE | 75.13 | 0 | 0 | 0
1283 | JHARGRAM | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at Bagmuri w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17041 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Barabari and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2503/JMD | 25/08/2023 | 180 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 31.3 | 0 | 0 | 0
1284 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Barabari w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17044 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Barabari and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2503/JMD | 25/08/2023 | 180 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 31.3 | 0 | 0 | 0
1285 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Mantipa w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17059 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Darukuli and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2632/JMD | 29/08/2023 | 180 | AMITAVA CHAKRABORTY | 31.3 | 0 | 0 | 0
1286 | JHARGRAM | Bankura Mechanical | BANKSOL AND ADJOINING MOUJAS PWSS , SM/17931 | New | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling pin point place of Banksol(T/w-II), Barasol (T/w-II) etc site in Bhelaidiha gp, Binpur-II Block of Jhargram District in Connection to JJM programme under Bankura Mechanical Division, P.H.E. Dte. | 548/BMSD(D) | 19/06/2024 | 183 | DEBJYOTI BASU | 0.97 | 0 | 0 | 0
1287 | JHARGRAM | Bankura Mechanical | BANKSOL AND ADJOINING MOUJAS PWSS , SM/17931 | New | Acceptance cum Formal work order for the work of Supply and delivery of Cutting tools, Lubricants etc for KLR Rig machine in connection with Jal Jeevan Mission programme at Jhargram under Bankura Mechanical Division ,PHE Dte. | 2087/BMD | 12/09/2023 | 120 | SUDIP ENGINEERING CO | 23.85 | 0 | 0 | 100
1288 | JHARGRAM | Bankura Mechanical | BANKSOL AND ADJOINING MOUJAS PWSS , SM/17931 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under Bankura Mechanical Division P.H.E. Dte. | 252/BMSD(D) | 13/03/2024 | 18 | CHAKRABORTY MINING & ENGINEERING. | 0.97 | 0 | 0 | 100
1289 | JHARGRAM | Jhargram Mechanical Division | BANKSOL AND ADJOINING MOUJAS PWSS , SM/17931 | New | New connection bill for Barsole in Bheliadiha GP | 77/JMD | 20/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1290 | JHARGRAM | Jhargram Mechanical Division | BANKSOL AND ADJOINING MOUJAS PWSS , SM/17931 | New | New connection bill for Banksole in Bheliadiha GP | 78/JMD | 20/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1291 | JHARGRAM | Jhargram Mechanical Division | BANKSOL AND ADJOINING MOUJAS PWSS , SM/17931 | New | New service connection charges | 10/JMD | 05/01/2024 | 0 | WBSEDCL | 0.42 | 0 | 0 | 0
1292 | JHARGRAM | Jhargram Mechanical Division | BANKSOL AND ADJOINING MOUJAS PWSS , SM/17931 | New | Erection & commissioning of 22 (twenty two) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Bhelaidiha G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Hijla (TSM/014334) and Banksol (TSM/015563) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 3015/JMD | 20/10/2023 | 794 | CONCORD ENGINEERING | 621.67 | 0 | 0 | 25
1293 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Chhahazari humtia w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17982 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Chhahazari humtia and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2771/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 77.3 | 0 | 0 | 0
1294 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at BELDA AND ADJOINING MOUJAS Piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17083 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Belda and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2504/JMD | 25/08/2023 | 180 | M/S. SAMRIDDHI ENTERPRISE | 31.3 | 0 | 0 | 0
1295 | JHARGRAM | Jhargram Division | TULIBAR AND ADJOINING MOUZAS PWSS , SM/17570 | New | Material Requisition To Resource Division | 1583/JHD | 08/09/2023 | 0 | Resource Division | 25.83 | 0 | 0 | 0
1296 | JHARGRAM | Jhargram Division | TULIBAR AND ADJOINING MOUZAS PWSS , SM/17570 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of TULIBAR and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 520/JRWS | 15/03/2024 | 60 | M/S DURGA ENTERPRISE | 4.3 | 0 | 0 | 5
1297 | JHARGRAM | Jhargram Mechanical Division | TULIBAR AND ADJOINING MOUZAS PWSS , SM/17570 | New | New service connection charges at Dhobakuria TW-I water supply scheme | 229/JMD | 28/06/2024 | 0 | WBSEDCL | 3.06 | 0 | 0 | 0
1298 | JHARGRAM | Jhargram Mechanical Division | TULIBAR AND ADJOINING MOUZAS PWSS , SM/17570 | New | new service connection chargers at Dhobakurya-II water supply scheme | 387/JMD | 04/10/2024 | 0 | WBSEDCL | 7.06 | 0 | 0 | 0
1299 | JHARGRAM | Central Drilling | TULIBAR AND ADJOINING MOUZAS PWSS , SM/17570 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1300 | JHARGRAM | Jhargram Division | TULIBAR AND ADJOINING MOUZAS PWSS , SM/17570 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House,& Providing Functional Household Tap Connection (1685 Nos) including 02(Two) Years Operation & Maintenance For CHANDABILE , TULIBAR Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 1138/JHD | 20/07/2023 | 711 | ASIS KUMAR SARANGI | 629.25 | 0 | 0 | 95
1301 | JHARGRAM | Jhargram Division | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS , SM/17584 | New | Laying of Distribution pipe line (Left-Out) for Sasrah (Z-I) & its adjoining moujas Pipe Water Supply Scheme under Gopiballavpur-I Block within Jhargram Division, PHE Dte. | 878/JHD | 28/06/2024 | 30 | MANISHIKA CONSTRUCTION | 32.4 | 0 | 0 | 0
1302 | JHARGRAM | Jhargram Division | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS , SM/17584 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Sasra( Zone-I) and its adjoining mouzas Pipe Water Supply Scheme within Gopibalavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 195/GPSD | 11/03/2024 | 30 | DEBABRATA DUTTA | 4.3 | 0 | 0 | 0
1303 | JHARGRAM | Jhargram Mechanical Division | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS , SM/17584 | New | NEW SERVICE CONNECTION CHARGES AT SASRA T/W-I WATER SUPPLY SCHEME | 346/JMD | 11/09/2024 | 0 | WBSEDCL | 6.65 | 0 | 0 | 0
1304 | JHARGRAM | Central Drilling | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS , SM/17584 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1305 | JHARGRAM | Jhargram Division | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS , SM/17584 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1306 | JHARGRAM | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at Bhaudi w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17052 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Barabari and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2503/JMD | 25/08/2023 | 180 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 31.3 | 0 | 0 | 0
1307 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at KHAMARPARA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17053 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Parihati and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2773/JMD | 05/09/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 77.27 | 0 | 0 | 0
1308 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Pindrakuli w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17077 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Pindrakuli and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2502/JMD | 25/08/2023 | 180 | SUBHASIS ROY | 31.3 | 0 | 0 | 0
1309 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Sushni And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17081 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Uttar Barashol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2498/JMD | 25/08/2023 | 180 | AMITAVA CHAKRABORTY | 75.12 | 0 | 0 | 0
1310 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS , SM/12455 | New | Material Requisition To Resource Division | 1568/JHD | 07/09/2023 | 0 | Resource Division | 29.22 | 0 | 0 | 0
1311 | JHARGRAM | Jhargram Mechanical Division | PARIHATI AND ADJOINING MOUJAS PWSS , SM/12455 | New | New Service connection | 7/JMD | 07/09/2023 | 0 | WBSEDCL | 3.25 | 0 | 0 | 0
1312 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS , SM/12455 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line,Installation of display Board, soil investigation ,including 02(Two) Years Operation & Maintenance & Accommodate FHTC (1440 nos) under JJM with allied work for Parihati PWSS in Jamboni Block including supply of all labour & materials within Jhargram Sub- Division under Jhargram Division, PHE Dte. | 1202/JHD | 26/07/2023 | 180 | SAIKAT DANDAPAT | 362.99 | 0 | 0 | 5
1313 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS , SM/12455 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Parihati and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 514/JRWS | 15/03/2024 | 60 | SANKAR KUMAR NAG | 4.82 | 0 | 0 | 0
1314 | JHARGRAM | Central Drilling | PARIHATI AND ADJOINING MOUJAS PWSS , SM/12455 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1315 | JHARGRAM | Jhargram Division | BAKRA AND ITS ADJOINING MOUJAS PWSS , SM/12390 | New | Material Requisition To Resource Division | 1496/JHD | 05/09/2023 | 0 | Resource Division | 39.05 | 0 | 0 | 0
1316 | JHARGRAM | Jhargram Mechanical Division | BAKRA AND ITS ADJOINING MOUJAS PWSS , SM/12390 | New | New service connection charges | 17/JMD/PFMS/JUL | 27/07/2023 | 0 | WBSEDCL | 2.02 | 0 | 0 | 0
1317 | JHARGRAM | Jhargram Mechanical Division | BAKRA AND ITS ADJOINING MOUJAS PWSS , SM/12390 | New | New Service connection | 2/JMD | 20/11/2023 | 0 | WBSEDCL | 5.68 | 0 | 0 | 0
1318 | JHARGRAM | Jhargram Mechanical Division | BAKRA AND ITS ADJOINING MOUJAS PWSS , SM/12390 | New | New Service connection | 26/JMD | 29/11/2023 | 0 | WBSEDCL | 0.12 | 0 | 0 | 0
1319 | JHARGRAM | Jhargram Mechanical Division | BAKRA AND ITS ADJOINING MOUJAS PWSS , SM/12390 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bakra & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2263/JMD | 09/08/2023 | 180 | DEY ENTERPRISE | 22.09 | 0 | 0 | 92
1320 | JHARGRAM | Jhargram Division | BAKRA AND ITS ADJOINING MOUJAS PWSS , SM/12390 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of BAKRA and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 169/GPSD | 05/03/2024 | 30 | M/S. R.K.TRADERS | 4.26 | 0 | 0 | 100
1321 | JHARGRAM | Jhargram Division | BAKRA AND ITS ADJOINING MOUJAS PWSS , SM/12390 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system ,Pump House ,& Providing Functional Household Tap Connection (7650 Nos), etc. For BAKRA, GOBINDAPUR, HARIPURBIRUA, KARKATASOL, Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 443/JHD | 23/03/2023 | 923 | GOBINDA MAITY | 2154.34 | 0 | 0 | 70
1322 | JHARGRAM | Central Drilling | BAKRA AND ITS ADJOINING MOUJAS PWSS , SM/12390 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1323 | JHARGRAM | Jhargram Division | BAKRA AND ITS ADJOINING MOUJAS PWSS , SM/12390 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Pahra GP at Sankrail Block under jhargram Division PHE Dte. (Phase-I) | 652/GPSD | 19/11/2024 | 10 | MANOJ KUMAR MAHATA | 0.84 | 0 | 0 | 100
1324 | JHARGRAM | Jhargram Division | BAKRA AND ITS ADJOINING MOUJAS PWSS , SM/12390 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Bakra and its adjoining Mouzas, Block Sankrail, District Jhargram | 443/JHD | 14/03/2024 | 30 | NIKHIL CHANDRA MONDAL | 8.35 | 0 | 0 | 100
1325 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09372 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Chandalbandh PWSS in Nayagram Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | BP-2021-22-395 | 22/02/2022 | 0 | RADIANT | 3.78 | 0 | 0 | 0
1326 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09372 | Augmentation | Rendering Consultancy Service for Geotechnical Investigation and Report preparation for OHR under Chandalbund Water Supply Scheme, Nayagram block of Jhargram District. | 1385/JHD | 17/08/2023 | 30 | JADAVPUR UNIVERSITY | 2.34 | 0 | 0 | 0
1327 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09372 | Augmentation | Material Requisition To Resource Division | 2165/MD | 17/12/2021 | 0 | Resource Division | 0.05 | 0 | 0 | 0
1328 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09372 | Augmentation | Material Requisition To Resource Division | 498/MD | 15/03/2022 | 0 | Resource Division | 15.18 | 0 | 0 | 0
1329 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09372 | Augmentation | Proforma bill of Soil Testing for Constriction of 150 cum capaicty OHR at CHANDALBANDH for Augmentation of CHANDALBANDH PWSS in Nayagram Block under Jhargram Division, PHE Dte. | BP-2023-24-300 | 24/11/2023 | 0 | JADAVPUR UNIVERSITY | 1.17 | 0 | 0 | 0
1330 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09372 | Augmentation | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 cum and staging height 20 mtr as per approved drawing (No:- PC-1/OHR/15/2012) including supply of all labour & materials for Augmentation of Chandal Bandh W/S Scheme within Jhargram Sub-Division under Jhargram Division P.H.E Dte. | 769/JHD | 30/12/2022 | 180 | CHAKRABORTTI ENTERPRISE | 55.3 | 0 | 0 | 95
1331 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09372 | Augmentation | Quotation payment for Chandalbandh-III. | 23/JMD | 24/04/2024 | 0 | WBSEDCL | 3.17 | 0 | 0 | 0
1332 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09372 | Augmentation | Rendering Consultancy Service for Geological Investigation & Report Preparation for OHR under Chandalbund Water Supply Scheme, Nayagram block of Jhargram District. | BP-2024-25-204 | 20/09/2024 | 0 | JADAVPUR UNIVERSITY | 1.17 | 0 | 0 | 0
1333 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09372 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at proposed additional T/Well as a part of augmentation of Chandalbandh W/S scheme under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | 2092/JMD | 03/08/2023 | 837 | BUSR ENGINEERING | 12.08 | 0 | 0 | 100
1334 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09372 | Augmentation | Laying Rising Main including Interconnection of Proposed Augmentation Chandalbundh & Its adjoining mouzas PWSS, Block: - Nayagram, District: - Jhargram. | 712/GPSD | 17/12/2024 | 21 | DHUMKETU ENGINEERING PRIVATE LIMITED | 1.3 | 0 | 0 | 50
1335 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09372 | Augmentation | Supply & Delivery of CI&DI Specials Sluice valves etc. for laying of Rising Main , distribution main, including interconnection between Tube Well and Raising Main and OHR with by-pass arrangement for augmentation Chandalbundh and its adjoining mouzas Water Supply Scheme within Nayagram Block under Gopiballavpur Sub Division of Jhargram Division, P.H.E.Dte. | 362/GPSD | 22/07/2025 | 21 | DHUMKETU ENGINEERING PRIVATE LIMITED | 1.82 | 0 | 0 | 0
1336 | JHARGRAM | Midnapore Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR / CWR locations of different proposed piped water supply scheme at Jhargram district under Drinking Water Mitigation Master Plan. [Name of proposed Scheme - Sankrail, Bakra, Ragra (Zone-I & Zone-II) & Nakrasuli of Sankrail Block, Pithapura, Chorchita, Mahapal, Dhadangiri, Kendana, Tentulia, Gohal Mara & Kuliana of Gopiballavpur-II Block, Sijua, Shaluka & Bandarboni of Binpur-I Block, Naharia of Jamboni Block in Jhargram district.] | 53/MD | 13/01/2022 | 60 | DR. GOKUL MONDAL (PHD, PROFESSOR), | 81.24 | 0 | 0 | 0
1337 | JHARGRAM | Midnapore Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR / CWR locations of different proposed piped water supply scheme at Jhargram district under Drinking Water Mitigation Master Plan. [Name of proposed Scheme - Sankrail, Bakra, Ragra (Zone-I & Zone-II) & Nakrasuli of Sankrail Block, Pithapura, Chorchita, Mahapal, Dhadangiri, Kendana, Tentulia, Gohal Mara & Kuliana of Gopiballavpur-II Block, Sijua, Shaluka & Bandarboni of Binpur-I Block, Naharia of Jamboni Block in Jhargram district.] | BP-2021-22-553 | 04/04/2022 | 0 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0 | 0
1338 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Netai PWSS in Binpur-1Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | : 75/JSD | 25/06/2021 | 14 | RADIANT | 1.91 | 0 | 0 | 0
1339 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Belpahari PWSS (Zone-II) in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 149/JSD | 12/08/2021 | 14 | LEMNISCATE | 4.59 | 0 | 0 | 0
1340 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Belpahari PWSS (Zone -I) in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | : 148/JSD | 12/08/2021 | 14 | LEMNISCATE | 4.36 | 0 | 0 | 0
1341 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Silda Pond Based PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 155/JSD | 12/08/2021 | 14 | LEMNISCATE | 2.35 | 0 | 0 | 0
1342 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Belpahari PWSS (Zone-III) in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 150/ JSD | 12/08/2021 | 14 | LEMNISCATE | 4.31 | 0 | 0 | 0
1343 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Consultancy Service for Geotechnical Investigation and Report preparation for OHR location of different PWSS in Jhargram District through Jadavpur University | 82/JHD | 16/01/2024 | 30 | JADAVPUR UNIVERSITY | 43.29 | 0 | 0 | 0
1344 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Jamboni Block and Others Block under Jhargram Division, PHE dte. (4th Phase) | 240/GPSD | 12/03/2024 | 10 | KARNAJORA AGNIBINA SEVA SAMITY | 0.97 | 0 | 0 | 100
1345 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Sankrail Block and Others Block under Jhargram Division ,PHE dte.(2nd Phase) | 211/GPSD | 12/03/2024 | 10 | MANDAL ENTERPRISE | 0.97 | 0 | 0 | 100
1346 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-I Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | 213/GPSD | 12/03/2024 | 10 | ASHIS SHEE | 0.97 | 0 | 0 | 100
1347 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Sankrail Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | 235/GPSD | 12/03/2024 | 10 | MANDAL ENTERPRISE | 0.97 | 0 | 0 | 100
1348 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Jhargram Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | 217/GPSD | 12/03/2024 | 10 | MANDAL ENTERPRISE | 0.97 | 0 | 0 | 100
1349 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Sankrail Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | 219/GPSD | 12/03/2024 | 10 | MANDAL ENTERPRISE | 0.97 | 0 | 0 | 100
1350 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-II Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | 224/GPSD | 12/03/2024 | 10 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0 | 0 | 100
1351 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-II Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | 230/GPSD | 12/03/2024 | 10 | ASHIS SHEE | 0.97 | 0 | 0 | 100
1352 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-II Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | 232/GPSD | 12/03/2024 | 10 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0 | 0 | 100
1353 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Jhargram Block and Others Block under Jhargram Division ,PHE dte.(2nd Phase) | 209/GPSD | 12/03/2024 | 10 | MANDAL ENTERPRISE | 0.97 | 0 | 0 | 100
1354 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-I Block and Others Block under Jhargram Division ,PHE dte.(2nd Phase) | 205/GPSD | 12/03/2024 | 10 | ASHIS SHEE | 0.97 | 0 | 0 | 100
1355 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-I Block and Others Block under Jhargram Division ,PHE dte.(2nd Phase) | 207/GPSD | 12/03/2024 | 10 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0 | 0 | 100
1356 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-II Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | 214/GPSD | 12/03/2024 | 10 | ASHIS SHEE | 0.97 | 0 | 0 | 100
1357 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-I Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | 215/GPSD | 12/03/2024 | 10 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0 | 0 | 100
1358 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Preparation of documents for uploading in Parivesh Portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | 447/JHD | 14/03/2024 | 30 | CARTO | 4.83 | 0 | 0 | 100
1359 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-II Block and Others Block under Jhargram Division,PHE dte. (2nd Phase) | 206/GPSD | 12/03/2024 | 10 | ASHIS SHEE | 0.97 | 0 | 0 | 100
1360 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-I Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | 231/GPSD | 12/03/2024 | 10 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0 | 0 | 100
1361 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Nayagram Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | 236/GPSD | 12/03/2024 | 10 | ASHIS SHEE | 0.97 | 0 | 0 | 100
1362 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Nayagram Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | 220/GPSD | 12/03/2024 | 10 | ASHIS SHEE | 0.97 | 0 | 0 | 100
1363 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-II Block and Others Block under Jhargram Division ,PHE dte.(2nd Phase) | 208/GPSD | 12/03/2024 | 10 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0 | 0 | 100
1364 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Nayagram Block and Others Block under Jhargram Division ,PHE dte.(2nd Phase) | 212/GPSD | 12/03/2024 | 10 | ASHIS SHEE | 0.97 | 0 | 0 | 100
1365 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-II Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | 216/GPSD | 12/03/2024 | 10 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0 | 0 | 100
1366 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-I Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | 221/GPSD | 12/03/2024 | 10 | ASHIS SHEE | 0.97 | 0 | 0 | 100
1367 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-II Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | 222/GPSD | 12/03/2024 | 10 | ASHIS SHEE | 0.97 | 0 | 0 | 100
1368 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-I Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | 223/GPSD | 12/03/2024 | 10 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0 | 0 | 100
1369 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Jhargram Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | 225/GPSD | 12/03/2024 | 10 | MANDAL ENTERPRISE | 0.97 | 0 | 0 | 100
1370 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Sankrail Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | 227/GPSD | 12/03/2024 | 10 | MANDAL ENTERPRISE | 0.97 | 0 | 0 | 100
1371 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Nayagram Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | 228/GPSD | 12/03/2024 | 10 | ASHIS SHEE | 0.97 | 0 | 0 | 100
1372 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-I Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | 229/GPSD | 12/03/2024 | 10 | ASHIS SHEE | 0.97 | 0 | 0 | 100
1373 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Jhargram Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | 233/GPSD | 12/03/2024 | 10 | MANDAL ENTERPRISE | 0.97 | 0 | 0 | 100
1374 | JHARGRAM | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. , SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Jamboni Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | 234/GPSD | 12/03/2024 | 10 | MANDAL ENTERPRISE | 0.97 | 0 | 0 | 100
1375 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II , SM/06829 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Netai PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | 1584/MD | 11/12/2020 | 180 | BIDYUT KUMAR SANTRA | 40.78 | 19.54 | 47.9 | 1
1376 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II , SM/06829 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khasjungle PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | 8443122 | 25/02/2022 | 0 | M/S. SOMNATH | 7.01 | 0 | 0 | 0
1377 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II , SM/06829 | Retrofitting | Extension distribution pipe line to accomodate FHTC under JJM in Lakat PWSS Block - Binpur-I in the District of Jhargram | 33/JSD | 01/02/2022 | 15 | S.B.TRADERS | 2.64 | 0 | 0 | 1
1378 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II , SM/06829 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Aulia PWSS of Binpur-II Block under Jhargram Division, PHE Dte. | 1410/MD | 26/11/2020 | 180 | GOUTAM PARIA | 14.09 | 12.14 | 100 | 0
1379 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II , SM/06829 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Simulpal PWSS of Binpur-II Block under Jhargram Division, PHE Dte. | 1408/MD | 26/11/2020 | 180 | GOUTAM RAY | 14.62 | 12.54 | 100 | 0
1380 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Baratilaboni PWSS (Phase-II) Block - Binpur-I in the District of Jhargram | 348/JSD | 23/11/2021 | 7 | J.S.S. ENTERPRISE | 2.59 | 0 | 0 | 1
1381 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pitanow PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. | 869/MD | 10/05/2022 | 15 | AJITESH ACHARJEE | 6 | 0 | 0 | 0
1382 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Domsole PWSS of Binpur-II Block under Jhargram Division, PHE Dte. | 382/MD | 25/02/2021 | 15 | S.B. TRADERS | 5.24 | 3.95 | 75.46 | 1
1383 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Sinking of 200 mm x 150 mm dia and depth 110 mtr. Rig bore Tubewell (Replacement) for Pathardhara W/S Scheme i.c.w providing F.H.T.C. under Jhargram Sub Division within Jhargram Division, PHE Dte. | 238/JSD | 24/09/2021 | 14 | DHUMKETU ENGINEERING PRIVATE LIMITED | 4.67 | 0 | 0 | 1
1384 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhera PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. | BP-2021-22-393 | 22/02/2022 | 0 | NIRMAL DUTTA | 1.43 | 0 | 0 | 0
1385 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Pitanaw PWSS water supply scheme. | BP-2022-23-518 | 01/02/2023 | 0 | AJITESH ACHARJEE | 0.52 | 0 | 0 | 0
1386 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pitanow PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. | 869/MD | 10/05/2022 | 15 | AJITESH ACHARJEE | 6 | 0 | 0 | 100
1387 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS of Nayagram Block under Jhargram Division, PHE Dte. | 588/JSD | 01/02/2021 | 15 | DHUMKETU ENGINEERING PRIVATE LIMITED | 2.53 | 2.38 | 100 | 0
1388 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Logan PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | 582/JSD | 01/02/2021 | 30 | J.S.S. ENTERPRISE | 4.38 | 0 | 0 | 0
1389 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barabaria PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. | 587/JSD | 01/02/2021 | 15 | BISHNU PADA NANDI | 2.27 | 2.02 | 100 | 0
1390 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhangabandh PWSS of Binpur-II Block under Jhargram Division, PHE Dte. | 381/MD | 25/02/2021 | 15 | SAIKAT DANDAPAT | 7.78 | 7.95 | 100 | 0
1391 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bartilaboni PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | 580/JSD | 01/02/2021 | 10 | J.S.S. ENTERPRISE | 0.71 | 0 | 0 | 0
1392 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo , SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sankrail PWSS of Sankrail Block under Jhargram Division, PHE Dte. | 878/MD | 08/06/2021 | 15 | PULLOCK KUMAR GHOSH | 5.5 | 5.15 | 100 | 0
1393 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08734 | Retrofitting | Retrofitting and allied works to accommodate FHTC under JJM in Laudaha PWSS within Sankrail Block under Jhargram Division, PHE Dte. | 1535/MD | 13/09/2021 | 15 | S.T. ENTERPRISE | 29.73 | 18.15 | 61.06 | 1
1394 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08734 | Retrofitting | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Sasarah PWSS in Gopiballavpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | BP-2021-22-403 | 23/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 1.67 | 0 | 0 | 0
1395 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08734 | Retrofitting | Payment for new service connection of WBSEDCL. | 24/JMD/PFMS/SEP | 14/09/2022 | 0 | WBSEDCL | 0.35 | 0 | 0 | 0
1396 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08734 | Retrofitting | Repairing & rejuvenation of various installed electro mechanical accessories for augmentation of ground water based water supply scheme for Laudaha Pump house no. II to accommodate FHTC at Sankrail block in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1126/JMD | 10/06/2022 | 30 | MENAKA ENTERPRISE | 8.33 | 0 | 0 | 0
1397 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08734 | Retrofitting | Supply & delivery of stand by submersible pumping machinery at pump house no. II of Laudaha ground water based water supply scheme of Sankrail block of Jhargram Dist. under Jhargram Mechanical Division, P.H.E Dte. | 163/JMD | 27/01/2023 | 7 | MENAKA ENTERPRISE | 0.5 | 0 | 0 | 0
1398 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. , SM/08734 | Retrofitting | Supply, delivery, installation of various electro-mechanical accessories for Laudaha W/S scheme, T/W no. I to accommodate FHTC at Sankrail block in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | 2099/JMD | 03/08/2023 | 30 | P.K. ENGINEERING | 2.37 | 0 | 0 | 100
1399 | JHARGRAM | Jhargram Division | KHAMARPARA AND ADJOINING MOUJAS PWSS , SM/12446 | New | Material Requisition To Resource Division | 1569/JHD | 07/09/2023 | 0 | Resource Division | 40.31 | 0 | 0 | 0
1400 | JHARGRAM | Jhargram Mechanical Division | KHAMARPARA AND ADJOINING MOUJAS PWSS , SM/12446 | New | New Service connection | 9/JMD | 28/09/2023 | 0 | WBSEDCL | 6.52 | 0 | 0 | 0
1401 | JHARGRAM | Jhargram Mechanical Division | KHAMARPARA AND ADJOINING MOUJAS PWSS , SM/12446 | New | New Service connection | 14/JMD | 28/09/2023 | 0 | WBSEDCL | 3.98 | 0 | 0 | 0
1402 | JHARGRAM | Jhargram Division | KHAMARPARA AND ADJOINING MOUJAS PWSS , SM/12446 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Khamarpara and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 523/JRWS | 15/03/2024 | 60 | SUNIL DULE | 4.84 | 0 | 0 | 90
1403 | JHARGRAM | Central Drilling | KHAMARPARA AND ADJOINING MOUJAS PWSS , SM/12446 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1404 | JHARGRAM | Jhargram Division | KHAMARPARA AND ADJOINING MOUJAS PWSS , SM/12446 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House& Providing Functional Household Tap Connection (2163 Nos), including 02(Two)Years Operation & Maintanance For KHAMARPARA, TENTULIA Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 1207/JHD | 26/07/2023 | 727 | SUNIL DULE | 651.28 | 0 | 0 | 70
1405 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Constructions of 150 cum OHR, soil investigation under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1455/JHD | 30/08/2023 | 240 | ABJ ENGINEERING | 72.41 | 0 | 0 | 0
1406 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Accommodate FHTC (382 nos) under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23, SL No.-10) | 2001/JHD | 01/12/2023 | 90 | MAHAPRABHU ENTERPRISE | 16.13 | 0 | 0 | 0
1407 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Material Requisition To Resource Division | 1570/JHD | 07/09/2023 | 0 | Resource Division | 57.74 | 0 | 0 | 0
1408 | JHARGRAM | Jhargram Mechanical Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dalkati & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1239/JMD | 26/05/2023 | 180 | CHATTERJEE CONSTRUCTION | 20.81 | 0 | 0 | 60
1409 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Laying distribution pipe line, Accommodate FHTC (383 nos) under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1394/JHD | 18/08/2023 | 90 | GOUTAM RAY | 79.26 | 0 | 0 | 90
1410 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Dalkati and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | 2292/JHD | 04/12/2024 | 30 | TAPAS KUMAR HAZRA | 7.93 | 0 | 0 | 0
1411 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Accommodate FHTC (383 nos) under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref: 1st Call eNIT_35 of EE/JHD of 2022-23, SL No.-9, 2nd Call eNIT_11 of EE/JHD of 2023-24, SL No.-8) | 1134/JHD | 06/08/2024 | 90 | RUPKUMAR KARMAKAR | 15.67 | 0 | 0 | 0
1412 | JHARGRAM | Jhargram Mechanical Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | new meter connection charges of Dalkati-I water supply scheme | 16/JMD | 15/04/2024 | 0 | WBSEDCL | 3.03 | 0 | 0 | 0
1413 | JHARGRAM | Jhargram Mechanical Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | new meter connection charges of Dalkati T/W-II water supply scheme | 17/JMD | 15/04/2024 | 0 | WBSEDCL | 9.97 | 0 | 0 | 0
1414 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23, SL No.-7) | 3077/JHD | 26/12/2023 | 90 | APEX ENGINEERING | 15.83 | 0 | 0 | 95
1415 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Laying of distribution pipe line for Dalkati and its adjoining moujas pwss in Jhargram block within Jhargram district under jhargram division P.H.E Dte. | 1213/JHD | 27/08/2024 | 45 | RAMENDRA NATH KAR | 22.88 | 0 | 0 | 87
1416 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Trial run for DALKATI AND ADJOINING MOUZAS PWSS scheme within Jhargram Block under Jhargram Division, PHE Dte. for 3 months. (The date of starting of trial run will be effective after consultation with departmental officials) | 736/JHD | 02/04/2025 | 91 | DHUMKETU ENGINEERING PRIVATE LIMITED | 1.01 | 0 | 0 | 0
1417 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Laying distribution pipe line under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1312/JHD | 09/08/2023 | 90 | DHUMKETU ENGINEERING PRIVATE LIMITED | 20.97 | 0 | 0 | 90
1418 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Sinking of Tube Well, Switch Room under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23,SL No.-8) | 1856/JHD | 31/10/2023 | 90 | SHEFALI CONSTRUCTION | 29.03 | 0 | 0 | 95
1419 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Laying distribution pipe line under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022- 23, SL No.-12) | 1998/JHD | 01/12/2023 | 90 | SAUBHIK KUMAR NAG | 11.84 | 0 | 0 | 90
1420 | JHARGRAM | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS , SM/12357 | New | Laying of extention distribution pipe line for dalkati and adjoining moujas pwss in jhargram block within jhargram district under jhargram division P.H.E Dte. (Part-B) | 1215/JHD | 27/08/2024 | 45 | SAMIR PATRA | 5.75 | 0 | 0 | 95
1421 | JHARGRAM | Jhargram Division | JAKUA AND ADJOINING MOUJAS PWSS , SM/12344 | New | Material Requisition To Resource Division | 1507/JHD | 05/09/2023 | 0 | Resource Division | 29.73 | 0 | 0 | 0
1422 | JHARGRAM | Jhargram Mechanical Division | JAKUA AND ADJOINING MOUJAS PWSS , SM/12344 | New | New Service connection | 20/JMD | 20/11/2023 | 0 | WBSEDCL | 3.13 | 0 | 0 | 0
1423 | JHARGRAM | Jhargram Mechanical Division | JAKUA AND ADJOINING MOUJAS PWSS , SM/12344 | New | New service connection charges | 11/JMD/PFMS/JUL | 27/07/2023 | 0 | WBSEDCL | 2.31 | 0 | 0 | 0
1424 | JHARGRAM | Jhargram Mechanical Division | JAKUA AND ADJOINING MOUJAS PWSS , SM/12344 | New | New Service connection | 28/JMD | 29/11/2023 | 0 | WBSEDCL | 0.05 | 0 | 0 | 0
1425 | JHARGRAM | Jhargram Division | JAKUA AND ADJOINING MOUJAS PWSS , SM/12344 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Jaqua-I and its adjoining Mouzas, Block Sankrail, District Jhargram. | 1135/JHD | 06/08/2024 | 30 | S.R. ENTERPRISE | 8.15 | 0 | 0 | 80
1426 | JHARGRAM | Jhargram Division | JAKUA AND ADJOINING MOUJAS PWSS , SM/12344 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of JAQUA and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 170/GPSD | 05/03/2024 | 30 | ASHIS SHEE | 4.23 | 0 | 0 | 100
1427 | JHARGRAM | Jhargram Division | JAKUA AND ADJOINING MOUJAS PWSS , SM/12344 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House , & Providing Functional Household Tap Connection (2568 Nos), etc. For DUMRI NAKRASULI, JAKUA Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 444/JHD | 23/03/2023 | 923 | MASUM ALI KHAN | 772.82 | 0 | 0 | 65
1428 | JHARGRAM | Central Drilling | JAKUA AND ADJOINING MOUJAS PWSS , SM/12344 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1429 | JHARGRAM | Jhargram Mechanical Division | CHAMPASOL AND ADJOINING MOUJAS PWSS , SM/12387 | New | New service connection charges at Champasole water supply scheme | 191/JMD | 14/06/2024 | 0 | WBSEDCL | 11.57 | 0 | 0 | 0
1430 | JHARGRAM | Central Drilling | CHAMPASOL AND ADJOINING MOUJAS PWSS , SM/12387 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1431 | JHARGRAM | Jhargram Division | CHAMPASOL AND ADJOINING MOUJAS PWSS , SM/12387 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1432 | JHARGRAM | Jhargram Division | CHAMPASOL AND ADJOINING MOUJAS PWSS , SM/12387 | New | Construction of boundary wall and Allied works At Dahatmal,Bagmuri,Champasol 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1280/JHD | 03/09/2024 | 30 | PROVAT KUMAR DE | 37.25 | 0 | 0 | 30
1433 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. , SM/11476 | New | Material Requisition To Resource Division | 1512/JHD | 05/09/2023 | 0 | Resource Division | 7.32 | 0 | 0 | 0
1434 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. , SM/11476 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Jabarpur at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6758/JMD | 27/08/2024 | 127 | RSA ENTERPRISE | 1.56 | 0 | 0 | 100
1435 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. , SM/11476 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Ergoda at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6759/JMD | 27/08/2024 | 4 | RSA ENTERPRISE | 1.56 | 0 | 0 | 0
1436 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. , SM/11476 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Mujrakanali at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6761/JMD | 27/08/2024 | 4 | RSA ENTERPRISE | 1.56 | 0 | 0 | 0
1437 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. , SM/11476 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Baharabani at Binpur-I block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6773/JMD | 27/08/2024 | 127 | RSA ENTERPRISE | 3.49 | 0 | 0 | 100
1438 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. , SM/11476 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Dhobajan at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6757/JMD | 27/08/2024 | 127 | RSA ENTERPRISE | 1.56 | 0 | 0 | 100
1439 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. , SM/11476 | New | New service connection charge at Dubrajpur. | 48/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1440 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. , SM/11476 | New | New Service connection charges. | 33/JMD | 18/01/2024 | 0 | WBSEDCL | 2.1 | 0 | 0 | 0
1441 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. , SM/11476 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM.(scheme code.- SM/11476) | 356/JMD | 13/09/2024 | 0 | SURAJ SERVICE STATION | 1.04 | 0 | 0 | 0
1442 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. , SM/11476 | New | New service connection payment towards WBSEDCL for Sankhuliya | 89/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1443 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. , SM/11476 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | 340/JHD | 09/03/2023 | 872 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 0 | 0 | 50
1444 | JHARGRAM | Jhargram Division | THAKURPARA AND ADJOINING MOUJAS PWSS , SM/12453 | New | Material Requisition To Resource Division | 1561/JHD | 07/09/2023 | 0 | Resource Division | 64.65 | 0 | 0 | 0
1445 | JHARGRAM | Jhargram Division | THAKURPARA AND ADJOINING MOUJAS PWSS , SM/12453 | New | Continuation Work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for April-2024 under Jhargram Division PHE Dte. | 572/JRWS | 28/03/2024 | 30 | JAGOMOHAN SETUA | 0.53 | 0 | 0 | 100
1446 | JHARGRAM | Jhargram Mechanical Division | THAKURPARA AND ADJOINING MOUJAS PWSS , SM/12453 | New | New service connection charges | 49/JMD | 29/12/2023 | 0 | WBSEDCL | 4.78 | 0 | 0 | 0
1447 | JHARGRAM | Jhargram Mechanical Division | THAKURPARA AND ADJOINING MOUJAS PWSS , SM/12453 | New | New Service connection charges. | 84/JMD | 21/03/2024 | 0 | WBSEDCL | 5.52 | 0 | 0 | 0
1448 | JHARGRAM | Jhargram Mechanical Division | THAKURPARA AND ADJOINING MOUJAS PWSS , SM/12453 | New | Quotation for new service connection at Thakurpara TW-III water supply scheme. | 186/JMD | 11/06/2024 | 0 | WBSEDCL | 6.61 | 0 | 0 | 0
1449 | JHARGRAM | Central Drilling | THAKURPARA AND ADJOINING MOUJAS PWSS , SM/12453 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1450 | JHARGRAM | Jhargram Division | THAKURPARA AND ADJOINING MOUJAS PWSS , SM/12453 | New | Construction of Boundary wall & allied works at 3rd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Thakurpara and its Adjoining Mouzas PWSS , Block: - Binpur-I, District: - Jhargram {TYPE - B} (Total length 50 mtr, column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) (2nd Call) [Ref. eNIT 20 OF AE/JSD OF 2023-2024, SL No. 15] | 970/JSD | 01/10/2024 | 150 | ASHIS SHEE | 4.51 | 0 | 0 | 100
1451 | JHARGRAM | Jhargram Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS , SM/12409 | New | Material Requisition To Resource Division | 1500/JHD | 05/09/2023 | 0 | Resource Division | 104.12 | 0 | 0 | 0
1452 | JHARGRAM | Jhargram Mechanical Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS , SM/12409 | New | New Service connection | 8/JMD | 08/11/2023 | 0 | WBSEDCL | 2.97 | 0 | 0 | 0
1453 | JHARGRAM | Jhargram Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS , SM/12409 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of HARIPURBIRUA and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 165/GPSD | 05/03/2024 | 30 | FIROJ KHAN | 4.14 | 0 | 0 | 100
1454 | JHARGRAM | Jhargram Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS , SM/12409 | New | Continuation work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for 16th March 2024 to 31st March 2024 under Jhargram Division PHE Dte. | 473/JRWS | 13/03/2024 | 16 | JAGOMOHAN SETUA | 0.53 | 0 | 0 | 100
1455 | JHARGRAM | Jhargram Mechanical Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS , SM/12409 | New | New service connection charges for Haripurbirua, t/w no.II pwss | 32/JMD | 11/03/2024 | 0 | WBSEDCL | 3.1 | 0 | 0 | 0
1456 | JHARGRAM | Jhargram Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS , SM/12409 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system ,Pump House ,& Providing Functional Household Tap Connection (7650 Nos), etc. For BAKRA, GOBINDAPUR, HARIPURBIRUA, KARKATASOL, Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 443/JHD | 23/03/2023 | 923 | GOBINDA MAITY | 2154.34 | 0 | 0 | 70
1457 | JHARGRAM | Central Drilling | HARIPURBIRUA AND AJOINING MOUJAS PWSS , SM/12409 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1458 | JHARGRAM | Jhargram Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS , SM/12409 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection with By-Pass arrangement for Haripurbirua and its adjoining mouzas Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division of Jhargram Division, P.H.E.Dte. | 133/GPSD | 18/03/2025 | 21 | GOBINDA MAITY | 2.2 | 0 | 0 | 100
1459 | JHARGRAM | Jhargram Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS , SM/12409 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Chandabila GP at Nayagram Block under jhargram Division PHE Dte. (Phase-I) | 643/GPSD | 19/11/2024 | 10 | GOPAL JANA | 0.92 | 0 | 0 | 100
1460 | JHARGRAM | Jhargram Division | KARKATASOL AND IT'S ADJOINING MOUJAS PWSS , SM/12524 | New | Material Requisition To Resource Division | 1501/JHD | 05/09/2023 | 0 | Resource Division | 60.45 | 0 | 0 | 0
1461 | JHARGRAM | Jhargram Mechanical Division | KARKATASOL AND IT'S ADJOINING MOUJAS PWSS , SM/12524 | New | New service connection charges | 4/JMD/AUG | 17/08/2023 | 0 | WBSEDCL | 2.93 | 0 | 0 | 0
1462 | JHARGRAM | Jhargram Mechanical Division | KARKATASOL AND IT'S ADJOINING MOUJAS PWSS , SM/12524 | New | New service connection charges | 13/JMD/PFMS/JUL | 27/07/2023 | 0 | WBSEDCL | 10.44 | 0 | 0 | 0
1463 | JHARGRAM | Jhargram Mechanical Division | KARKATASOL AND IT'S ADJOINING MOUJAS PWSS , SM/12524 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Karkatasol & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2260/JMD | 09/08/2023 | 180 | DAS ENTERPRISE | 20.74 | 0 | 0 | 94
1464 | JHARGRAM | Jhargram Division | KARKATASOL AND IT'S ADJOINING MOUJAS PWSS , SM/12524 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of KARKATASOL and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 172/GPSD | 05/03/2024 | 30 | M/S MAA KAMALA TRADERS | 4.05 | 0 | 0 | 100
1465 | JHARGRAM | Jhargram Mechanical Division | KARKATASOL AND IT'S ADJOINING MOUJAS PWSS , SM/12524 | New | Additional Service Connection Charges for Karkatasola P.H - I PWSS | 209/JMD | 20/06/2024 | 0 | WBSEDCL | 8.66 | 0 | 0 | 0
1466 | JHARGRAM | Jhargram Division | KARKATASOL AND IT'S ADJOINING MOUJAS PWSS , SM/12524 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system ,Pump House ,& Providing Functional Household Tap Connection (7650 Nos), etc. For BAKRA, GOBINDAPUR, HARIPURBIRUA, KARKATASOL, Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 443/JHD | 23/03/2023 | 923 | GOBINDA MAITY | 2154.34 | 0 | 0 | 70
1467 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. , SM/11480 | New | Material Requisition To Resource Division | 1514/JHD | 05/09/2023 | 0 | Resource Division | 7.5 | 0 | 0 | 0
1468 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. , SM/11480 | New | New service connection charges for Darkhuli | 7/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1469 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. , SM/11480 | New | New Service connection charges. | 47/JMD | 06/02/2024 | 0 | WBSEDCL | 2.1 | 0 | 0 | 0
1470 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. , SM/11480 | New | New service connection charges for Bhaliadiha. | 8/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1471 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. , SM/11480 | New | new service connection charges at Krishnanagar water supply scheme | 104/JMD | 08/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1472 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. , SM/11480 | New | New service connection charges for Jangal Khas | 9/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1473 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. , SM/11480 | New | New service connection charges for Salgeria PWSS | 269/JMD | 26/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1474 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. , SM/11480 | New | New Service connection charges | 13/JMD | 09/01/2024 | 0 | WBSEDCL | 1.47 | 0 | 0 | 0
1475 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. , SM/11480 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | 340/JHD | 09/03/2023 | 872 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 0 | 0 | 50
1476 | JHARGRAM | Jhargram Mechanical Division | PINDRAKULI AND ADJOINING MOUJAS PWSS , SM/12450 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Pindra Kuli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1230/JMD | 26/05/2023 | 180 | RSA ENTERPRISE | 20.71 | 0 | 0 | 0
1477 | JHARGRAM | Central Drilling | PINDRAKULI AND ADJOINING MOUJAS PWSS , SM/12450 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 91/CDD | 25/04/2024 | 122 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 0 | 0 | 10
1478 | JHARGRAM | Jhargram Division | PINDRAKULI AND ADJOINING MOUJAS PWSS , SM/12450 | New | Construction of Pump House , 100 cum OHR & 250 Cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, Soil investigation & Accommodate FHTC (3051 nos) under JJM with allied work including 02(Two) Years Operation & Maintanance for RAJBAND, PINDRAKULI & RAJABASA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 667/JHD | 26/03/2025 | 180 | ASIS KUMAR SARANGI | 813.53 | 0 | 0 | 0
1479 | JHARGRAM | Jhargram Division | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/12725 | New | Material Requisition To Resource Division | 1555 | 07/09/2023 | 0 | Resource Division | 27.06 | 0 | 0 | 0
1480 | JHARGRAM | Jhargram Mechanical Division | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/12725 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Gramohan & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1244/JMD | 26/05/2023 | 180 | MAA BHABOTARINE ENTERPRISE | 21.76 | 0 | 0 | 65
1481 | JHARGRAM | Jhargram Mechanical Division | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/12725 | New | New service connection charges. | 21/JMD | 08/12/2023 | 0 | WBSEDCL | 8.86 | 0 | 0 | 0
1482 | JHARGRAM | Jhargram Mechanical Division | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/12725 | New | New Service connection charges. | 104/JMD | 27/02/2024 | 0 | WBSEDCL | 4.52 | 0 | 0 | 0
1483 | JHARGRAM | Jhargram Division | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/12725 | New | Sinking of Tube Well , Pump House , 150 cum GLR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Boundary wall, Installation of display Board, Operation and Maintenance and Accommodate FHTC (1289 nos) under JJM with allied work for GRAMOHAN AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1130/JHD | 20/07/2023 | 711 | ASIS KUMAR SARANGI | 396.08 | 0 | 0 | 95
1484 | JHARGRAM | Jhargram Division | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/12725 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 200 cum and staging height 20 mtr. as per approved drawing with allied works of GARMOHAN & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for JHARGRAM Block, District: - Jhargram. | 2055/JHD | 07/12/2023 | 631 | ASIS KUMAR SARANGI | 73.72 | 0 | 0 | 5
1485 | JHARGRAM | Jhargram Division | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/12725 | New | Construction of boundary wall and Allied works At Chandri, Barabari, Gramohan 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1282/JHD | 03/09/2024 | 120 | ASIS KUMAR SARANGI | 37.46 | 0 | 0 | 55
1486 | JHARGRAM | Jhargram Division | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/12725 | New | Accommodate FHTC (200 nos) under JJM with allied work for GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-1) | 367/JHD | 20/02/2025 | 90 | ASSOCIATED ENGINEERS & TRADERS | 8.34 | 0 | 0 | 0
1487 | JHARGRAM | Jhargram Division | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS , SM/12725 | New | Accommodate FHTC (200 nos) under JJM with allied work for GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-1) | 1315/JHD | 11/06/2025 | 90 | ASSOCIATED ENGINEERS & TRADERS | 8.34 | 0 | 0 | 0
1488 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at HARDA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16686 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Gohalmara and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2505/JMD | 25/08/2023 | 180 | SUBHASIS ROY | 75.13 | 0 | 0 | 0
1489 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Gobindapur w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16926 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Rampura and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2777/JMD | 05/09/2023 | 180 | ELECTRO ENTERPRISES | 32.07 | 0 | 0 | 0
1490 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS , SM/16982 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dharampur zone-VII, Damsole & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2284/JMD | 10/08/2023 | 180 | SUBHASIS ROY | 21.03 | 0 | 0 | 0
1491 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS , SM/16982 | New | Material Requisition To Resource Division | 1588/JHD | 08/09/2023 | 0 | Resource Division | 29.81 | 0 | 0 | 0
1492 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS , SM/16982 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection for Dharampur(Zone-VII) Santal Sirshi and its adjoining mouzas Water Supply Scheme within Binpur-II Block under Jhargram Sub Division of Jhargram Division, P.H.E.Dte. | 1158/JSD | 16/12/2024 | 14 | SUNIL DULE | 1.56 | 0 | 0 | 0
1493 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS , SM/16982 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (2294 Nos), etc.including 02(Two) Years Operation & Maintenance For DHARAMPUR ZONE-I , DHARAMPUR ZONE-VII Pipe water supply Scheme within Binpur-II Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1209/JHD | 26/07/2023 | 615 | SUNIL DULE | 761.33 | 0 | 0 | 70
1494 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS , SM/16982 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at replacement T/W no. II of Domsol water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1652/JMD | 08/02/2024 | 120 | MAA BHABOTARINE ENTERPRISE | 9.42 | 0 | 0 | 100
1495 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at NEPURA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16689 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Jangalkhas and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2772/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 77.3 | 0 | 0 | 0
1496 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Damro w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16681 | Solarisation | QUOTATION FOR METER INSTALLATION FOR SOLAR POWER PLANT DHAMRO-1 | 402/JMD | 25/10/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
1497 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Radhanagar w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17122 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Patharnala and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2499/JMD | 25/08/2023 | 180 | RSA ENTERPRISE | 75.13 | 0 | 0 | 0
1498 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Bhila w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18000 | Solarisation | Providing solarisation of WBSEDCL energised pumping installation at Upar Baghuasol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2775/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 32.21 | 0 | 0 | 0
1499 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Tentulia And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18033 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Chhahazari humtia and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2771/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 77.3 | 0 | 0 | 0
1500 | JHARGRAM | Midnapore Division | Rejuvenation (Phase-II) of Ground Water Based Jhitka PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18008 | Augmentation | Retrofitting to accommodate FHTC under JJM in Jhitka PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | 1582/MD | 11/12/2020 | 180 | RAMENDRA NATH KAR | 15.06 | 0 | 0 | 80
1501 | JHARGRAM | Jhargram Division | Rejuvenation (Phase-II) of Ground Water Based Jhitka PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18008 | Augmentation | Sinking of 200X150mm diaX150 mtr rig bored tubewell,replacement of distribution pipeline(part),cons. brick masonary drain,cons. boundary wall of Jitka w/s scheme at Binpur-I block under Jhargram Sub-division within Jhargram Division,PHE Dte. | 725/JHD | 18/05/2023 | 45 | RAMENDRA NATH KAR | 23.71 | 0 | 0 | 100
1502 | JHARGRAM | Jhargram Division | Rejuvenation (Phase-II) of Ground Water Based Jhitka PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18008 | Augmentation | 01 nos I.E.P (size 20 cum/hr) with platfrom, blower with compressor room of Jitka W/S Scheme at Binpur-I Dev. Block under Jhargram Sub division within Jhargram Division ,PHE Dte. | 1647/JHD | 14/09/2023 | 684 | KANAN CONSTRUCTION ENTERPRISE | 14.45 | 0 | 0 | 100
1503 | JHARGRAM | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Naupara PWSS and Installation of IEP & related works to Accommodate FHTC at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18010 | Augmentation | Providing pending FHTC (120nos) of Naupara W/S scheme under Jhargram Sub Division within Jhargram Division,PHE Dte | 880/JHD | 08/06/2023 | 30 | KRISHNA CHANDRA DAS | 5.86 | 0 | 0 | 0
1504 | JHARGRAM | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Naupara PWSS and Installation of IEP & related works to Accommodate FHTC at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18010 | Augmentation | 01 nos I.E.Ps[size 30 cum/hr.(at head work site)] with platfrom,blower with compressor room etc. of Naupara w/s scheme under Gopiballavpur Dev. Block with Jhargram Sub Division ,PHE Dte | 881/JHD | 08/06/2023 | 45 | MONDAL PRECISION PRIVATE LIMITED | 16.44 | 0 | 0 | 55
1505 | JHARGRAM | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Naupara PWSS and Installation of IEP & related works to Accommodate FHTC at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18010 | Augmentation | Sinking of 250 X 150 mm dia. X 150 mtr.rig bored tubewell (replacement)with inter connection with Raising main at head work site of Naupara w/s scheme.within Gopiballavpur-II Block, within Jhargram Sub Division, PHE Dte. 2nd Call (Ref eNIT_28 of 2022-23 , SL No.-3 ) | 1414/JHD | 22/08/2023 | 30 | KARTIK DUTTA | 7.05 | 0 | 0 | 100
1506 | JHARGRAM | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Naupara PWSS and Installation of IEP & related works to Accommodate FHTC at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18010 | Augmentation | replacement of distribution pipe line(part) and Construction boundary wall ( Length 160 mtr. ,Height-2.45,including 4 mtr width gate) at head work site of Naupara w/s scheme under Gopiballavpur-II Dev. Block within Jhargram Sub Division ,PHE Dte. | 1393/JHD | 18/08/2023 | 90 | SUNIL DULE | 33.6 | 0 | 0 | 100
1507 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Burimol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17071 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Champasol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2500/JMD | 25/08/2023 | 180 | MEGA SOLAR ENERGY | 75.09 | 0 | 0 | 0
1508 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at BELIA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17076 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Parihati and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2773/JMD | 05/09/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 77.27 | 0 | 0 | 0
1509 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at BELIA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17076 | Solarisation | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Belia and adjacent water supply schemes for ongoing Solarisation works for the purpose of Geotagging in JJM under Jhargram Mechanical Division, P.H.E. Dte. | 3062/JMD | 14/03/2024 | 10 | MUKHERJEE ART CENTRE | 5.28 | 0 | 0 | 100
1510 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Material Requisition To Resource Division | 1578/JHD | 08/09/2023 | 0 | Resource Division | 40.51 | 0 | 0 | 0
1511 | JHARGRAM | Jhargram Mechanical Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | New Service connection |  | 09/11/2023 | 0 | WBSEDCL | 0.16 | 0 | 0 | 0
1512 | JHARGRAM | Jhargram Mechanical Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | New service connection | 23/JMD | 24/11/2023 | 0 | WBSEDCL | 1.43 | 0 | 0 | 0
1513 | JHARGRAM | Jhargram Mechanical Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | New Service connection | 1/JMD | 20/11/2023 | 0 | WBSEDCL | 5.34 | 0 | 0 | 0
1514 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-I) | 1375/JHD | 16/08/2023 | 90 | SUJOY RANJAN BHOWMICK | 11.86 | 0 | 0 | 92
1515 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-L) | 1435/JHD | 24/08/2023 | 90 | TAPAS KUMAR JANA | 10.64 | 0 | 0 | 82
1516 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-E) | 1719/JHD | 29/09/2023 | 90 | AJITESH ACHARJEE | 9.35 | 0 | 0 | 95
1517 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-J) | 1320/JHD | 10/08/2023 | 90 | HYDRO TECH ASSOCIATES | 12.1 | 0 | 0 | 77
1518 | JHARGRAM | Jhargram Mechanical Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Saftaldiha & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1237/JMD | 26/05/2023 | 180 | MAA BHABOTARINE ENTERPRISE | 20.78 | 0 | 0 | 86
1519 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Accommodate FHTC ( 499 nos) under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-1) | 1321/JHD | 10/08/2023 | 90 | DHUMKETU ENGINEERING PRIVATE LIMITED | 21.08 | 0 | 0 | 95
1520 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Field Level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme In different Block in the District of Jhargram under Jhargram Division, PHE Dte. | 323/JHD | 23/02/2024 | 90 | TECHVISION | 0.6 | 0 | 0 | 95
1521 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Construction of boundary wall and Allied works At Saftaldiha 1st and 2nd Tube well site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1206/JHD | 29/05/2025 | 30 | GRAVITA ENTERPRISE | 11.71 | 0 | 0 | 0
1522 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation, under JJM with allied work for SAFTALDIHA AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour, materials within Jhargram Sub Division under Jhargram Division, PHE Dte. (2nd Call) | 1088/JHD | 14/07/2023 | 568 | PALCON | 156.73 | 0 | 0 | 60
1523 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Accommodate FHTC ( 499 nos) under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-2) | 1111/JHD | 18/07/2023 | 90 | A.R. ENTERPRISE | 21.08 | 0 | 0 | 90
1524 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-H) | 1098/JHD | 14/07/2023 | 90 | M/S GRAVITA ENTERPRISE | 10.24 | 0 | 0 | 91
1525 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Accommodate FHTC ( 499 nos) under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-3) | 1110/JHD | 18/07/2023 | 90 | M/S BLUE BIRD | 21.08 | 0 | 0 | 95
1526 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour, materials within Jhargram Sub Division under Jhargram Division, PHE Dte. (Part-N) | 1204/JHD | 26/07/2023 | 90 | J.S.S. ENTERPRISE | 20.8 | 0 | 0 | 100
1527 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour, materials within Jhargram Sub Division under Jhargram Division, PHE Dte. ( Part-D ) | 1206/JHD | 26/07/2023 | 90 | ENVOTECH INFRA SOLUTION | 11.5 | 0 | 0 | 100
1528 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour, materials within Jhargram Sub Division under Jhargram Division, PHE Dte. (Part-c) | 1203/JHD | 26/07/2023 | 90 | J.S.S. ENTERPRISE | 15.41 | 0 | 0 | 100
1529 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-F) | 1395/JHD | 18/08/2023 | 90 | MAHAVIR SAMPARK PVT. LTD. | 10.27 | 0 | 0 | 90
1530 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte.(Part-K) | 1391/JHD | 18/08/2023 | 90 | DEBABRATA DUTTA | 12.37 | 0 | 0 | 95
1531 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-M) | 1392/JHD | 18/08/2023 | 90 | DEBABRATA DUTTA | 20.1 | 0 | 0 | 95
1532 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-B) | 1644/JHD | 14/09/2023 | 90 | NEER UDYOG | 14.03 | 0 | 0 | 100
1533 | JHARGRAM | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS , SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-G) | 1566/JHD | 07/09/2023 | 90 | M/S. SANKAR KUMAR NAG | 24.23 | 0 | 0 | 100
1534 | JHARGRAM | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS , SM/17927 | New | 62 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-4) | 1835/JHD | 27/10/2023 | 60 | ASIS KUMAR SARANGI | 101.91 | 0 | 0 | 80
1535 | JHARGRAM | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS , SM/17927 | New | Four numbers (4) of yield test process need to be done at Bodadihi & Machhkandna of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 540/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
1536 | JHARGRAM | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS , SM/17927 | New | Four numbers (4) of yield test process need to be done at Dakai & Kankrijharna of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 538/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
1537 | JHARGRAM | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS , SM/17927 | New | Four numbers (4) of yield test process need to be done at Jarma & Labani of Sumulpal GP of Simulpal Block, under Jhargram division, PHE Dte. | 539/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
1538 | JHARGRAM | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS , SM/17927 | New | New Service Connection Charges for Labani, Dakai & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1539 | JHARGRAM | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS , SM/17927 | New | New Service Connection Charges for Kankrijharna, Dakai & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1540 | JHARGRAM | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS , SM/17927 | New | New Service Connection Charges for Dakai, Dakai & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1541 | JHARGRAM | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS , SM/17927 | New | New Service Connection Charges for Bodadihi Dakai & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1542 | JHARGRAM | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS , SM/17927 | New | 31 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur II Block under Jhargram Division, PHE Dte. | 1714/JHD | 29/09/2023 | 820 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 848.26 | 0 | 0 | 45
1543 | JHARGRAM | Jhargram Division | SHIYARBINDA AND ADJOINING MOUJAS PWSS , SM/17591 | New | 66 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for BHULAVEDA GP (TALPUPUKHURIA, RAGHUNATHPUR, GIDIGHATI, SHIYARBINDA PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-2) | 1834/JHD | 27/10/2023 | 484 | SUNIL DULE | 108.48 | 0 | 0 | 80
1544 | JHARGRAM | Jhargram Division | SHIYARBINDA AND ADJOINING MOUJAS PWSS , SM/17591 | New | Four numbers (4) of yield test process need to be done at Shushnijubi & Lagadari of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 506/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
1545 | JHARGRAM | Jhargram Division | SHIYARBINDA AND ADJOINING MOUJAS PWSS , SM/17591 | New | Two numbers (2) of yield test process need to be done at Pataghar of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 510/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.36 | 0 | 0 | 0
1546 | JHARGRAM | Jhargram Division | SHIYARBINDA AND ADJOINING MOUJAS PWSS , SM/17591 | New | Four numbers (4) of yield test process need to be done at Shiyarbinda & Girulia of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 507/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
1547 | JHARGRAM | Jhargram Division | SHIYARBINDA AND ADJOINING MOUJAS PWSS , SM/17591 | New | Four numbers (4) of yield test process need to be done at Joram & Laljol of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 508/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
1548 | JHARGRAM | Jhargram Division | SHIYARBINDA AND ADJOINING MOUJAS PWSS , SM/17591 | New | New Service Connection Charges for Lagadari Shiyarbinda & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1549 | JHARGRAM | Jhargram Division | SHIYARBINDA AND ADJOINING MOUJAS PWSS , SM/17591 | New | New Service Connection Charges for Shiyarbinda, Shiyarbinda & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1550 | JHARGRAM | Jhargram Division | SHIYARBINDA AND ADJOINING MOUJAS PWSS , SM/17591 | New | New Service Connection Charges for Laljal ,Shiyarbinda & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1551 | JHARGRAM | Jhargram Division | SHIYARBINDA AND ADJOINING MOUJAS PWSS , SM/17591 | New | New Service Connection Charges for Pataghar Shiyarbinda & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1552 | JHARGRAM | Jhargram Division | SHIYARBINDA AND ADJOINING MOUJAS PWSS , SM/17591 | New | 33 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for BHULAVEDA GP ( TALPUPUKHURIA ,RAGHUNATHPUR ,GIDIGHATI ,SHIYARBINDA PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-2 ) | 1531/JHD | 06/09/2023 | 602 | ASIS KUMAR SARANGI | 910.58 | 0 | 0 | 80
1553 | JHARGRAM | Jhargram Division | SHIYARBINDA AND ADJOINING MOUJAS PWSS , SM/17591 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | 344/JRWS | 08/01/2024 | 30 | MESAURE LAND | 0.82 | 0 | 0 | 100
1554 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Khas Jangal w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17054 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Darukuli and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2632/JMD | 29/08/2023 | 180 | AMITAVA CHAKRABORTY | 31.3 | 0 | 0 | 0
1555 | JHARGRAM | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at Mahisamura & Adjoining Moujas Piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17060 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Belda and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2504/JMD | 25/08/2023 | 180 | M/S. SAMRIDDHI ENTERPRISE | 31.3 | 0 | 0 | 0
1556 | JHARGRAM | Jhargram Mechanical Division | BHAMAL AND ADOINING MOUJAS PWSS , SM/17417 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bhamal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1242/JMD | 26/05/2023 | 180 | M/S A.D. CONCERN | 21.75 | 0 | 0 | 0
1557 | JHARGRAM | Jhargram Division | BHAMAL AND ADOINING MOUJAS PWSS , SM/17417 | New | Sinking of Tube Well, Pump House, Rising main pipe line, Interconnection pipe line, Installation of display Board, under JJM with allied work for BHAMAL AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1120/JHD | 19/07/2023 | 90 | ASIS KUMAR SARANGI | 38.26 | 0 | 0 | 0
1558 | JHARGRAM | Jhargram Division | BHAMAL AND ADOINING MOUJAS PWSS , SM/17417 | New | Laying distribution pipe line, Accommodate FHTC (1009 nos) under JJM with allied work for BHAMAL AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1517/JHD | 05/09/2023 | 180 | SUDHAMAY MAJUMDAR | 131.09 | 0 | 0 | 0
1559 | JHARGRAM | Jhargram Division | BHAMAL AND ADOINING MOUJAS PWSS , SM/17417 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 150 cum and staging height 20 mtr. as per approved drawing with allied works of BHAMAL & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for GOPIBALLAVPUR-II Block, District: - Jhargram. | 2045/JHD | 07/12/2023 | 210 | ABJ ENGINEERING | 71.49 | 0 | 0 | 0
1560 | JHARGRAM | Jhargram Division | BHAMAL AND ADOINING MOUJAS PWSS , SM/17417 | New | Material Requisition To Resource Division | 1581/JHD | 08/09/2023 | 0 | Resource Division | 30.99 | 0 | 0 | 0
1561 | JHARGRAM | Jhargram Mechanical Division | BHAMAL AND ADOINING MOUJAS PWSS , SM/17417 | New | New Service connection | 7/JMD | 08/11/2023 | 0 | WBSEDCL | 2.85 | 0 | 0 | 0
1562 | JHARGRAM | Jhargram Division | BHAMAL AND ADOINING MOUJAS PWSS , SM/17417 | New | Soil Investigation and determination of safe bearing capacity and other relevant parameters of soil for construction of Proposed O.H.R. of Gobindapur and Bhamal PWSS at Gopiballavpur-II Block under Jhargram Division, P.H.E. Dte. | 1085/JSD | 28/11/2024 | 14 | MOYTEC | 1.34 | 0 | 0 | 0
1563 | JHARGRAM | Jhargram Division | BHAMAL AND ADOINING MOUJAS PWSS , SM/17417 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Bhamal and its Adjoining Mouzas PWSS , Block Gopiballavpur-II, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | 791/JSD | 09/08/2024 | 30 | S.R. ENTERPRISE | 4.79 | 0 | 0 | 0
1564 | JHARGRAM | Jhargram Mechanical Division | BHAMAL AND ADOINING MOUJAS PWSS , SM/17417 | New | New Service Connection Charges for Bhamal P.H -II PWSS | 202/JMD | 14/06/2024 | 0 | WBSEDCL | 3.43 | 0 | 0 | 0
1565 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at PARIHATI AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17650 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Parihati and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2773/JMD | 05/09/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 77.27 | 0 | 0 | 0
1566 | JHARGRAM | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at Chandri w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17011 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Gohalmara and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2505/JMD | 25/08/2023 | 180 | SUBHASIS ROY | 75.13 | 0 | 0 | 0
1567 | JHARGRAM | Jhargram Division | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS , SM/12535 | New | Material Requisition To Resource Division | 1300/JHD | 08/08/2023 | 0 | Resource Division | 68.87 | 0 | 0 | 0
1568 | JHARGRAM | Jhargram Mechanical Division | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS , SM/12535 | New | New Service connection | 13/JMD | 28/09/2023 | 0 | WBSEDCL | 5.08 | 0 | 0 | 0
1569 | JHARGRAM | Jhargram Mechanical Division | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS , SM/12535 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uttar Barashol & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2269/JMD | 09/08/2023 | 180 | M/S B.M. ELECTRICAL | 22.53 | 0 | 0 | 80
1570 | JHARGRAM | Jhargram Division | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS , SM/12535 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection for Uttar Barsol and its adjoining mouzas Water Supply Scheme within Jamboni Block under Jhargram RWS Sub Division of Jhargram Division, P.H.E.Dte | 545/JRWS | 30/12/2024 | 15 | SUNIL DULE | 2.95 | 0 | 0 | 0
1571 | JHARGRAM | Jhargram Division | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS , SM/12535 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation , Accommodate FHTC ( 1191 nos) under JJM with allied work including 02 (Two) Years Operation & Maintenance for UTTAR BARASHOL AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub- Division under Jhargram Division, PHE Dte. | 372/JHD | 14/03/2023 | 671 | SUNIL DULE | 466.4 | 0 | 0 | 90
1572 | JHARGRAM | Jhargram Division | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS , SM/12535 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Uttar Barsole and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 515/JRWS | 15/03/2024 | 60 | SUNIL DULE | 4.84 | 0 | 0 | 90
1573 | JHARGRAM | Jhargram Division | KALADABAR AND ADJOINING MOUJAS PWSS , SM/17597 | New | 17 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for BANASPAHARI GP ( CHAKADOBA, KHARIYARATA, KALADABAR PWSS ) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-1 ) | 1657/JHD | 19/09/2023 | 665 | MONDAL PRECISION PRIVATE LIMITED | 508.47 | 0 | 0 | 41
1574 | JHARGRAM | Jhargram Division | KALADABAR AND ADJOINING MOUJAS PWSS , SM/17597 | New | New Service Connection Charges for Kaladabar PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1575 | JHARGRAM | Jhargram Division | KALADABAR AND ADJOINING MOUJAS PWSS , SM/17597 | New | 34 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for BANASPAHARI GP (CHAKADOBA, KHARIYARATA,KALADABAR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_38 of 2022-23, SL No.-1) | 1668/JHD | 21/09/2023 | 543 | NEER UDYOG | 55.86 | 0 | 0 | 60
1576 | JHARGRAM | Jhargram Division | KALADABAR AND ADJOINING MOUJAS PWSS , SM/17597 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | 391/JRWS | 02/02/2024 | 30 | MESAURE LAND | 0.82 | 0 | 0 | 100
1577 | JHARGRAM | Jhargram Mechanical Division | KAPGARI AND IT'S ADJOINING MOUJAS PWSS , SM/12454 | New | New Service connection | 15/JMD | 10/11/2023 | 0 | WBSEDCL | 2.99 | 0 | 0 | 0
1578 | JHARGRAM | Jhargram Division | KAPGARI AND IT'S ADJOINING MOUJAS PWSS , SM/12454 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Kapgari and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 513/JRWS | 15/03/2024 | 60 | SAUBHIK KUMAR NAG | 4.82 | 0 | 0 | 0
1579 | JHARGRAM | Central Drilling | KAPGARI AND IT'S ADJOINING MOUJAS PWSS , SM/12454 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1580 | JHARGRAM | Jhargram Division | KAPGARI AND IT'S ADJOINING MOUJAS PWSS , SM/12454 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection ( 7683 Nos), etc.including 02(Two) Years Operation & Maintenance For KAMTA , SUSHNI, BAHIR GRAM, KAPGARI, MURAKATI, MAHISAMURA PWSS Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 1954/JHD | 22/11/2023 | 406 | SIBSANKAR CHOWDHURY | 2070.24 | 0 | 0 | 65
1581 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Hatikadua Mini PWSS (Out of 45 Nos. Mini PWSS) at Jamboni Block under Jhargram Division, PHE Dte. | 1224/MD | 29/07/2021 | 15 | NIRMAL DUTTA | 5.99 | 0 | 0 | 0
1582 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Dakaisol SSK Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. | 387/MD | 25/02/2021 | 15 | SAIKAT DANDAPAT | 5.78 | 0 | 0 | 0
1583 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Ruknimara Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | 1055/MD | 02/07/2021 | 15 | ASIS KUMAR SARANGI | 5.82 | 0 | 0 | 1
1584 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nuasai Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | 1287/MD | 09/08/2021 | 15 | GOUTAM PARIA | 4.92 | 0 | 0 | 1
1585 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Telidanga Jr. High School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. | 1377/MD | 25/08/2021 | 15 | SAIKAT DANDAPAT | 7.42 | 0 | 0 | 0
1586 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Sankhara Primary School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | 385/MD | 25/02/2021 | 15 | SUNIL DULE | 5.37 | 4.92 | 100 | 1
1587 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Jashpur Primary School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | 384/MD | 25/02/2021 | 15 | SUNIL DULE | 6.16 | 6.16 | 100 | 1
1588 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Kashafulia Mini PWSS (Out of 45 Nos. Mini PWSS) at Jamboni Block under Jhargram Division, PHE Dte. | 452/MD | 26/02/2021 | 15 | NIRMAL DUTTA | 5.99 | 0 | 0 | 0
1589 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Kaluasarn SSK Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | 824/MD | 03/06/2021 | 15 | PROVAT KUMAR DE | 7.43 | 0 | 0 | 0
1590 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Junsola PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. (Phase-II) | 817/MD | 03/06/2021 | 15 | SATYA RANJAN DAS | 4.96 | 0 | 0 | 1
1591 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nayabasan, Khunti Village Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-I Block under Jhargram Division, PHE Dte. | 1058/MD | 02/07/2021 | 15 | BISHNU PADA NANDI | 7.83 | 5.19 | 100 | 1
1592 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Bachurkhur Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | 1064/MD | 02/07/2021 | 15 | NIMAI LAL GURIA | 7.76 | 7.64 | 100 | 1
1593 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Baharuna Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. | 826/MD | 03/06/2021 | 15 | SATYA RANJAN DAS | 8.01 | 0 | 0 | 1
1594 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at DEHAGANJE Mini PWSS (Out of 45 Nos. Mini PWSS) at SANKRAIL Block under Jhargram Division, PHE Dte. | 626/JSD | 22/02/2021 | 30 | ASSOCIATED ENGINEERS & TRADERS | 4.55 | 0 | 0 | 1
1595 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at RANDEBPUR Mini PWSS (Out of 45 Nos. Mini PWSS) at SANKRAIL Block under Jhargram Division, PHE Dte. | 628/JSD | 22/02/2021 | 30 | ASSOCIATED ENGINEERS & TRADERS | 2.74 | 0 | 0 | 1
1596 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Salpatra SSK Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. | 389/MD | 25/02/2021 | 15 | J.S.S. ENTERPRISE | 5.24 | 0 | 0 | 1
1597 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Kalmapukuria, Dakshin Sadar Para Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | 390/MD | 25/02/2021 | 15 | PROVAT KUMAR DE | 5.99 | 5.99 | 75.03 | 1
1598 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Bhalaidiha Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. | 388/MD | 25/02/2021 | 15 | DEBABRATA DUTTA | 6.07 | 0 | 0 | 1
1599 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Chirakuti Mini PWSS (Out of 45 Nos. Mini PWSS) at Sankrail Block under Jhargram Division, PHE Dte. | 1056/MD | 02/07/2021 | 15 | ASIS KUMAR SARANGI | 8.95 | 0 | 0 | 1
1600 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Balarampur Primary School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | 386/MD | 25/02/2021 | 15 | SUNIL DULE | 4.96 | 0 | 0 | 1
1601 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Gokhurpal Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | 825/MD | 03/06/2021 | 15 | PROVAT KUMAR DE | 9.07 | 0 | 0 | 1
1602 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Bansketia Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. | 1376/MD | 25/08/2021 | 15 | SAIKAT DANDAPAT | 6.19 | 0 | 0 | 1
1603 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Tapsia Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. | 1211/MD | 28/07/2021 | 15 | MAMPI ENTERPRISE | 7.42 | 0 | 0 | 1
1604 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nischintapur Mini PWSS (Out of 45 Nos. Mini PWSS) at Jhargram Block under Jhargram Division, PHE Dte. (3rd Call) | 1375/MD | 25/08/2021 | 15 | A R ENTERPRISE | 4.95 | 4.58 | 100 | 1
1605 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nepura Village Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | 1286/MD | 09/08/2021 | 15 | SUNIL DULE | 6.4 | 0 | 0 | 1
1606 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Hatipada Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. | 1378/MD | 25/08/2021 | 15 | S.B. TRADERS | 6.19 | 0 | 0 | 1
1607 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Pasro Primary School Mini PWSS (Out of 45 Nos. Mini PWSS) at Jhargram Block under Jhargram Division, PHE Dte. (3rd Call) | 1939/MD | 24/11/2021 | 15 | DHUMKETU ENGINEERING PRIVATE LIMITED | 6.24 | 0 | 0 | 1
1608 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Jamunasole Mini PWSS (Out of 45 Nos. Mini PWSS) at Jamboni Block under Jhargram Division, PHE Dte. | 453/MD | 26/02/2021 | 15 | NRIPENDRA NATH SINGHA | 5.99 | 0 | 0 | 1
1609 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Bihankuria JR. High School Mini PWSS (Out of 45 Nos. Mini PWSS) at NAYAGRAM Block under Jhargram Division, PHE Dte. | 624/JSD | 22/02/2021 | 30 | ASSOCIATED ENGINEERS & TRADERS | 3.93 | 0 | 0 | 1
1610 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting with extension of distribution pipeline to accommodate FHTC under JJM in Barjharia Mini PWSS (out of 45 nos Mini pwss)(Phase-II) Block - Nayagram in the District of Jhargram | 34/JSD | 01/02/2022 | 15 | PROVAT KUMAR DE | 3.07 | 0 | 0 | 1
1611 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Sinking of 200 X 150 mm dia. X 165 mtr. rig bored replacement tubewell for Rukhnimara Mini W/S Scheme in connection with Retrofitting to Accommodate FHTC under JJM in 45nos. Mini PWSS at Nayagram Block under Jhargram Division, P.H.E. Dte. (As per ANNEXURE-III) | 585/JHD | 18/11/2022 | 21 | BIDYUT KUMAR SANTRA | 6.56 | 0 | 0 | 1
1612 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at AUSHPAL ADIBASHI PARA Mini PWSS (Out of 45 Nos. Mini PWSS) at JHARGRAM Block under Jhargram Division, PHE Dte. | BP-2021-22-490 | 16/03/2022 | 0 | S.B. TRADERS | 0.77 | 0 | 0 | 0
1613 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | FHTC of 45 Drought. | BP-2021-22-103 | 03/03/2022 | 0 | BISHNU PADA NANDI | 0.03 | 0 | 0 | 0
1614 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Kui (Yartri Patikashaloy) Mini PWSS ( out of 45 nos. Mini PWSS) at Binpur-I Block under Jhargram division, PHE Dte. |  | 26/09/2022 | 0 | RAMENDRA NATH KAR | 3.6 | 0 | 0 | 0
1615 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Bhaliaghati Mini PWSS (Out of 45 Nos. Mini PWSS) at NAYAGRAM Block under Jhargram Division, PHE Dte. | BP-2021-22-425 | 02/03/2022 | 0 | BISHNU PADA NANDI | 3.38 | 0 | 0 | 0
1616 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC with extension of pipeline under JJM in Kui mini PWSS ( out of 45 mini PWSS ) ( Phase-II) Block : Binpur-I in district of Jhargram |  | 26/09/2022 | 0 | RAMENDRA NATH KAR | 5.56 | 0 | 0 | 0
1617 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nuasi Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | BP-2021-22-455 | 11/03/2022 | 0 | GOUTAM PARIA | 4.91 | 0 | 0 | 0
1618 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Naupara PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. | 1412/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 36.77 | 0 | 0 | 80
1619 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Jhitka PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | 1582/MD | 11/12/2020 | 180 | RAMENDRA NATH KAR | 15.06 | 0 | 0 | 80
1620 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Continuation Work Order For "Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority for the Office of the Executive Engineer, Jhargram Division, PHE Dte. for the period of 6 (six) Month's, from 01.09.2022 to 28.02.2023. | 474/JSD | 29/08/2022 | 183 | SUNIL DULE | 0.86 | 0 | 0 | 90
1621 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Manikpara High School Mini PWSS (Out of 45 Nos. Mini PWSS) at Jhargram Block under Jhargram Division, PHE Dte. | 1212/MD | 28/07/2021 | 15 | MAMPI ENTERPRISE | 7.01 | 0 | 0 | 1
1622 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Executive Engineer, Jhargram Division PHE Dte. (Period from 01.09.2021 to 31.08.2022) | 186/JSD | 26/08/2021 | 365 | SUNIL DULE | 1.52 | 0 | 0 | 100
1623 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Book Binding and photo copy of Tender Documents of different works and official paper for the JJM works and others establishment works under office of the Engineer, Jhargram Division, PHE Dte. (Period from 15.01.2023 to 14.07.2023) | 33A/JRWS | 17/01/2023 | 180 | PRINT PREVIEW | 0.96 | 0 | 0 | 80
1624 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at BHURURDIHI Mini PWSS (Out of 45 Nos. Mini PWSS) at GOPIBALLAVPUR-I Block under Jhargram Division, PHE Dte. | 619/JSD | 22/02/2021 | 30 | SRIMANTA KUMAR DE | 4.29 | 4.22 | 100 | 0
1625 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Providing FHTC at Nuasai village (45 mini scheme) under JJM in the District of Jhargram under Jhargram Division. P.H.E Dte. | 507/JSD | 13/09/2022 | 21 | MANDAL ENTERPRISE | 1.75 | 0 | 0 | 1
1626 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Hatikadua Mini PWSS (Out of 45 Nos. Mini PWSS) at Jamboni Block under Jhargram Division, PHE Dte | 1224/MD | 29/07/2021 | 15 | NIRMAL DUTTA | 5.99 | 0 | 0 | 1
1627 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Raipal mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. | 1057/MD | 02/07/2021 | 15 | ASIS KUMAR SARANGI | 8.25 | 0 | 0 | 100
1628 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Ruknimara Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | 1055/MD | 02/07/2021 | 15 | ASIS KUMAR SARANGI | 5.82 | 0 | 0 | 100
1629 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Extention Distribution pipe line for smooth functioning of Ghokurpal water (Out of 45 nos Mini PWSS) at Nayagram Block and providing due FHTC with extension pipeline of Banisole scheme (Out of 45 nos Mini PWSS) at Nayagram Block Within Jhargram Division, PHE dte. | 376/GPSD | 03/10/2023 | 20 | ASHIS SHEE | 3.96 | 0 | 0 | 100
1630 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Jhitka PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | 1582/MD | 11/12/2020 | 15 | RAMENDRA NATH KAR | 5.71 | 0 | 0 | 90
1631 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC with extension of pipeline under JJM in Kui Mini PWSS (out of 45 Nos. Mini PWSS) (Phase-II) Block - Binpur-I in the district of Jhargram. | 535/MD | 22/03/2022 | 15 | RAMENDRA NATH KAR | 5.62 | 0 | 0 | 1
1632 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Kui (Yatri Patikshaloy) Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | 1223/MD | 29/07/2021 | 15 | RAMENDRA NATH KAR | 9.07 | 0 | 0 | 1
1633 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Transfer money to EE/JSD PFMS bank account. | BP-2022-23-692 | 10/03/2023 | 0 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 8.33 | 0 | 0 | 0
1634 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Gopiballavpur Sub-Division PHE Dte. | 329/JSD | 30/06/2022 | 365 | SAIKAT DANDAPAT | 1.7 | 0 | 0 | 100
1635 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Kui (Yatri Patikshaloy) Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | 1223/MD | 29/07/2021 | 15 | RAMENDRA NATH KAR | 9.07 | 0 | 0 | 100
1636 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC with extension of pipeline under JJM in Kui Mini PWSS (out of 45 Nos. Mini PWSS) (Phase-II) Block - Binpur-I in the district of Jhargram. | 535/MD | 22/03/2022 | 15 | RAMENDRA NATH KAR | 5.62 | 0 | 0 | 100
1637 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty)months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram H.Q./RWS/Gopiballavpur Sub-Division PHE Dte. | 408/JSD | 29/07/2022 | 365 | JAGOMOHAN SETUA | 1.7 | 0 | 0 | 80
1638 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new not older than 30 thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram Sub-Division PHE Dte. | 775/JSD | 31/08/2023 | 336 | BIDYUT KUMAR SANTRA | 1.88 | 0 | 0 | 100
1639 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Balance Replacement of distribution pipe line (part) for Ramgarh water supply scheme (Zone-I & Zone-II). | 972/JSD | 10/11/2023 | 21 | ASHIS SHEE | 4.77 | 0 | 0 | 80
1640 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Naupara PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. | 1412/MD | 26/11/2020 | 15 | ASIS KUMAR SARANGI | 5.24 | 0 | 0 | 100
1641 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Installation of Display Bord for JJM works at different piped water supply scheme within Nayagram Block under Jhargram Division, PHE dte. (1st Phase) | 58/JHD | 10/01/2024 | 45 | PRINT PREVIEW | 0.91 | 0 | 0 | 0
1642 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Continuation of Work Order "Hire charges of Bharat Stage-11/III Diesel Motor Cabs (Luxury Taxi)/Maruti Omni (Standard - Non - Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority for the Office of the Executive Engineer. Jhargram Division, PHE Dte. For the period of 2 (TWO) Month's from 01.07.2023 to 31.07.2023." | 542/JSD | 30/06/2023 | 31 | SUNIL DULE | 0.15 | 0 | 0 | 100
1643 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at KADAMDIHA Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | 603/JSD | 09/02/2021 | 30 | PROVAT KUMAR DE | 3.44 | 3.42 | 100 | 0
1644 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at AUSHPAL ADIBASHI PARA Mini PWSS (Out of 45 Nos. Mini PWSS) at JHARGRAM Block under Jhargram Division, PHE Dte. | 621/JSD | 22/02/2021 | 30 | S.B. TRADERS | 4.55 | 3.37 | 100 | 0
1645 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at BARJHARIA ICDS Mini PWSS (Out of 45 Nos. Mini PWSS) at NAYAGRAM Block under Jhargram Division, PHE Dte. | 622/JSD | 22/02/2021 | 30 | DHUMKETU ENGINEERING PRIVATE LIMITED | 2.66 | 2.43 | 57.31 | 0
1646 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at BANKATI Mini PWSS (Out of 45 Nos. Mini PWSS) at SANKRAIL Block under Jhargram Division, PHE Dte. | 627/JSD | 22/02/2021 | 30 | ASSOCIATED ENGINEERS & TRADERS | 4.38 | 0 | 0 | 0
1647 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Sijua Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-I Block under Jhargram Division, PHE Dte. | 451/MD | 26/02/2021 | 15 | BISHNU PADA NANDI | 5.98 | 5.45 | 100 | 0
1648 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at CHULBATA Mini PWSS (Out of 45 Nos. Mini PWSS) at GOPIBALLAVPUR-I Block under Jhargram Division, PHE Dte. | 617/JSD | 22/02/2021 | 30 | SRIMANTA KUMAR DE | 4.29 | 3.95 | 100 | 0
1649 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at GARHDOAR Mini PWSS (Out of 45 Nos. Mini PWSS) at GOPIBALLAVPUR-I Block under Jhargram Division, PHE Dte. | 618/JSD | 22/02/2021 | 30 | SRIMANTA KUMAR DE | 4.75 | 4.29 | 100 | 0
1650 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Chandabila Pry. School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | 620/JSD | 22/02/2021 | 30 | SUNIL DULE | 4.75 | 0 | 0 | 0
1651 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at BHURKUNDI Mini PWSS (Out of 45 Nos. Mini PWSS) at SANKRAIL Block under Jhargram Division, PHE Dte. | 625/JSD | 22/02/2021 | 30 | THE TILES | 3.4 | 0 | 0 | 0
1652 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at BANISOLE Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | 602/JSD | 09/02/2021 | 30 | PROVAT KUMAR DE | 3.31 | 3.04 | 100 | 0
1653 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Book binding and photocopy of Tender Documents of different works and official paper for the JJM works and others establishment works under office of the Superintending Engineer, Western Circle, P.H.E. Dte. (period from 01.01.2023 to 30.06.2023) | 29B/JRWS | 28/12/2022 | 181 | M/S PIJUSH PAL | 0.97 | 0 | 0 | 100
1654 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kui Mini PWSS (Out of 45 nos Mini PWSS) (Phase-III) Block - Binpur-I in the District of Jhargram. | 939/JSD | 02/11/2023 | 21 | SAURABH KAR | 1.28 | 0 | 0 | 100
1655 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Sinking of 250 X 150 mm dia. X 150 mtr.rig bored tubewell for Augmentation of Ramgarh W/S Scheme in Binpur-I Block within Jhargram District under Jhargram Division, P.H.E.Dte. | 2099/JHD | 12/12/2023 | 15 | SAURABH KAR | 7.03 | 0 | 0 | 100
1656 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Installation of Display Bord for JJM works at different piped water supply scheme within Sankrail Block under Jhargram Division, PHE dte. (1st Phase) | 57/JHD | 10/01/2024 | 45 | PRINT PREVIEW | 0.91 | 0 | 0 | 100
1657 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Installation of Display Bord for JJM works at different piped water supply scheme within JhargramBlock under Jhargram Division, PHE dte. (1st Phase) | 55/JHD | 10/01/2024 | 45 | GOPAL JANA | 0.91 | 0 | 0 | 100
1658 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Installation of Display Bord for JJM works at different piped water supply scheme within Jamboni Block under Jhargram Division, PHE dte. (1st Phase) | 56/JHD | 10/01/2024 | 45 | GOPAL JANA | 0.91 | 0 | 0 | 100
1659 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Continuation work for book binding and photocopy of Tender Documents of different works and official paper for the J.J.M. works and others establishment works under office of the Superintending Engineer, Western Circle, P.H.E. Dte. (Period from 15.07.2023 to 14.01.2024) | 151/JRWS | 12/07/2023 | 184 | PRINT PREVIEW | 0.96 | 0 | 0 | 100
1660 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Raipal Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. | 1057/MD | 02/07/2021 | 15 | ASIS KUMAR SARANGI | 8.25 | 0 | 0 | 1
1661 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Continuation work for Hiring charges of Bharat Stage-III Diesel Indigo ECS Car / Motor Cabs (Luxury Taxi) having contract Carriage permit from the Regional Transport Authority valid for the State of West Bengal not older than 30 month from the date of 1st Registration on monthly hire rate basis for the period from 01.07.2023 to 30.06.2024 (12 months)) for the office of the Assistant Engineer, Gopiballavpur Sub-Division, P.H.E. Dte. The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, fees etc. | 275/GPSD | 01/07/2023 | 366 | SAIKAT DANDAPAT | 1.79 | 0 | 0 | 100
1662 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty)months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Executive Engineer, Jhargram Division PHE Dte. ( For 12 months) | 1228/JHD | 28/07/2023 | 366 | SUNIL DULE | 2.05 | 0 | 0 | 100
1663 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Hatipada Mini PWSS (Out of 45 nos Mini PWSS) (Phase-II) Block - Gopiballavpur-II in the District of Jhargram. | 938/JSD | 02/11/2023 | 21 | MAA LAXMI ENTERPRISE | 1.51 | 0 | 0 | 100
1664 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Hiring of 1 (one) no Motor Cab (standard) commercial with Catalatyic Converter attachement with Bharat Stage as per prevalent applicable standard compliant new not older than 30 (Thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Gopiballavpur Sub-Division, PHE Dte. from 01.07.2024 to 30.06.2025). | 461/GPSD | 28/06/2024 | 365 | SAIKAT DANDAPAT | 2.05 | 0 | 0 | 0
1665 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. , SM/08029 | Retrofitting | Continuation Order for Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty)months from the date of 1st registration on daily hire rate basis for 5 (Five) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Executive Engineer, Jhargram Division PHE Dte. ( For 5 months) | 1108/JHD | 01/08/2024 | 150 | SUNIL DULE | 0.71 | 0 | 0 | 100
1666 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09381 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tubwell (Replacement) by DTH Method for Augmentation of Source of Banspahari PWSS under Jhargram Division P.H.E. Dte. | BP-2021-22-472 | 16/03/2022 | 0 | SUNIL DULE | 3.36 | 0 | 0 | 0
1667 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09381 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Banspahari PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | BP-2021-22-401 | 23/02/2022 | 0 | RADIANT | 1.8 | 0 | 0 | 0
1668 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09381 | Augmentation | Extension of Distribution pipe line and FHTC work for Augmentation of Ground based Banspahari PWSS to Accommodate FHTC in Binpur -II Block within Jhargram District under Jhargram Division, PHE Dte. |  | 23/08/2022 | 0 | SUNIL DULE | 14.12 | 0 | 0 | 0
1669 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09381 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Replacement Tube Well no. II of Banspahari piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1940/JMD | 28/07/2023 | 30 | ECO ENTERPRISE | 8.35 | 0 | 0 | 98
1670 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09381 | Augmentation | Health Assessment (Conducting Non Destructive Test) of Existing RCC O.H.R (Zone-I) of capacity 50000 gallon with staging height of 20 mtr. of Ramgarh Piped Water Supply Scheme at Binpur-I Block under Jhargram Sub Division within Jhargram Division, PHE Dte. | 426/JSD | 05/08/2022 | 15 | SIRCON ENGINEERING SERVICES | 4.4 | 0 | 0 | 1
1671 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09381 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tube-well (Replacement) 2 Nd T/W site by D.T.H. Method, Construction of Boundary Wall ( Length 34.00 mtr. ) 2Nd T/W & Interconnection of 2 Nos. Newly Sunk T/W at Banspahari Water Supply Scheme within Jhargram Sub-Division Under Jhargram Division P.H.E.Dte. | 569/JHD | 25/04/2023 | 45 | SUNIL DULE | 8.03 | 0 | 0 | 100
1672 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09381 | Augmentation | Extension of Distribution pipe line and FHTC work for Augmentation of Ground based Banspahari PWSS to Accommodate FHTC in Binpur -II Block within Jhargram District under Jhargram Division, PHE Dte. | 616/MD | 04/04/2022 | 21 | SUNIL DULE | 14.28 | 0 | 0 | 1
1673 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09381 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Belpahari PWSS (Zone-III) in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 150/JSD | 12/08/2021 | 14 | LEMNISCATE | 4.31 | 0 | 0 | 100
1674 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09381 | Augmentation | Extension of Distribution pipe line and FHTC work for Augmentation of Ground based Banspahari PWSS to Accommodate FHTC in Binpur -II Block within Jhargram District under Jhargram Division, PHE Dte. | 616/MD | 04/04/2022 | 21 | SUNIL DULE | 14.28 | 0 | 0 | 100
1675 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At DUBRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_16_32) | 616/JHD | 24/11/2022 | 30 | MASUM CONSTRUCTION | 10.01 | 0 | 0 | 0
1676 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_9_32)" | 639/JSD | 23/11/2022 | 30 | TAPAS KUMAR JANA | 3.69 | 0 | 0 | 0
1677 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PARIHATI GP under Jamboni Block in Jhargram District under Jhargram Division P.H.E Dte. ( Location ID : AWC_Jamboni_32_32) | 678/JHD | 13/12/2022 | 30 | SUNIL KUMAR MANDAL | 15.88 | 0 | 0 | 0
1678 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_8_32)" | 638/JSD | 23/11/2022 | 30 | KARTIK DUTTA | 3.18 | 0 | 0 | 0
1679 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At KAPGARI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Jamboni_20_32) | 703/JHD | 15/12/2022 | 45 | SUJOY RANJAN BHOWMICK | 25.93 | 0 | 0 | 0
1680 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHICHIRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_2_32)" | 632/JSD | 23/11/2022 | 30 | SUBHAMAY DANDAPAT | 3.59 | 0 | 0 | 0
1681 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHICHIRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_1_32)" | 631/JSD | 23/11/2022 | 30 | IMRAN KHAN | 3.89 | 0 | 0 | 0
1682 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHICHIRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_3_32)" | 633/JSD | 23/11/2022 | 30 | S.R. ENTERPRISE | 3.77 | 0 | 0 | 0
1683 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At DHARSA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWS_Jamboni_13_32) | 674/JHD | 13/12/2022 | 45 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.41 | 0 | 0 | 90
1684 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_22_32)" | 641/JSD | 23/11/2022 | 30 | M/S ANKITA CONSTRUCTION | 2.37 | 0 | 0 | 0
1685 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_23_32)" | 642/JSD | 23/11/2022 | 30 | TAPAS PAL | 2.98 | 0 | 0 | 0
1686 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Jamboni_27_32) | 454/JHD | 11/11/2022 | 30 | A.R. ENTERPRISE | 5 | 0 | 0 | 0
1687 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At DUBRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_17_32) | 626/JHD | 28/11/2022 | 30 | M/S BAKLY CONSTRUCTION | 5.69 | 0 | 0 | 0
1688 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHICHIRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_4_32)" | 634/JSD | 23/11/2022 | 30 | ENVOTECH INFRA SOLUTION | 4.38 | 0 | 0 | 0
1689 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_6_32)" | 636/JSD | 23/11/2022 | 30 | M/S MILAN DATTA | 3.19 | 0 | 0 | 0
1690 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At KAPGARI GP under Jamboni block in Jhargram Division PHE Dte. (Location ID : AWC_jamboni_21_32) | 675/JHD | 13/12/2022 | 45 | TAPAN KUMAR MANDAL | 22.57 | 0 | 0 | 0
1691 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_7_32)" | 637/JSD | 23/11/2022 | 30 | ARUSHI CONSTRUCTION | 3.09 | 0 | 0 | 100
1692 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At KENDANGRI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Jamboni_29_32) | 702/JHD | 15/12/2022 | 45 | JYOTY SOLAR POWER | 18.01 | 0 | 0 | 0
1693 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Jamboni_11_32) | 453/JHD | 11/11/2022 | 30 | ENVOTECH INFRA SOLUTION | 5.7 | 0 | 0 | 0
1694 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_5_32)" | 635/JSD | 23/11/2022 | 30 | M/S TARUN MAHATA | 3.19 | 0 | 0 | 0
1695 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_12_32) | 630/JHD | 28/11/2022 | 30 | DEBASISH DOGRA | 6.19 | 0 | 0 | 0
1696 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At KENDANGRI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_30_32) | 631/JHD | 28/11/2022 | 45 | MANISHIKA CONSTRUCTION | 33.51 | 0 | 0 | 100
1697 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_26_32)" | 645/JSD | 23/11/2022 | 30 | DEBABRATA DUTTA | 3.18 | 0 | 0 | 100
1698 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_24_32)" | 643/JSD | 23/11/2022 | 30 | SUTANU DE | 2.99 | 0 | 0 | 100
1699 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_25_32)" | 644/JSD | 23/11/2022 | 30 | HRITWIK DUTTA | 3.09 | 0 | 0 | 80
1700 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At GIDHNI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Jamboni_19_32) | .625/JHD | 28/11/2022 | 45 | BISHNU PADA NANDI | 27.91 | 0 | 0 | 95
1701 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DUBRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_14_32)" | 640/JSD | 23/11/2022 | 30 | M/S R.K. CONTRACTORY | 3.67 | 0 | 0 | 50
1702 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PARIHATI GP under Jamboni block in Jhargram Division PHE Dte. (Location ID : AWC_jamboni_31_32) | 677/JHD | 13/12/2022 | 30 | J.S.S. ENTERPRISE | 13.49 | 0 | 0 | 100
1703 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At DURBA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte (Location : AWC_Jamboni_18_32) | 628/JHD | 28/11/2022 | 45 | BIDYUT KUMAR SANTRA | 17.28 | 0 | 0 | 100
1704 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi centers At LALBANDH GP under jamboni Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Jamboni_15_32) | 768/JHD | 30/12/2022 | 30 | NIRMAL DUTTA | 20.13 | 0 | 0 | 100
1705 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. , SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers at JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. | 767/JHD | 30/12/2022 | 45 | NRIPENDRA NATH SINGHA | 21.73 | 0 | 0 | 100
1706 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(176 nos.) within Jhargram Block under Jhargram District. , SM/10354 | Anganwadi | Water Supply Arrangement for 176 Nos. Anganwadi Centers At Jhargram Block in Jhargram District under Jhargram Division, PHE Dte. | 382/JHD | 21/10/2022 | 90 | M/S. D.K.H.CONSTRUCTION | 293.08 | 0 | 0 | 70
1707 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Ramgarh ( Zone-I & II) PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10485 | Augmentation | Health Assessment (Conducting Non Destructive Test) of Existing RCC O.H.R (Zone-I) of capacity 50000 gallon with staging height of 20 mtr. of Ramgarh Piped Water Supply Scheme at Binpur-I Block under Jhargram Sub Division within Jhargram Division, PHE Dte. | 426/JSD | 05/08/2022 | 15 | SIRCON ENGINEERING SERVICES | 4.4 | 0 | 0 | 1
1708 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Ramgarh ( Zone-I & II) PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10485 | Augmentation | Replacement of distribution pipe line from Dasbundh to Sarasbedia pond for Ramgarh water supply Scheme (Zone-I). | 971/JSD | 10/11/2023 | 21 | KALI GANGA ENTERPRISE | 4.81 | 0 | 0 | 100
1709 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Netai PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/10488 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Netai PWSS in Binpur-1Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | 02/08/2022 | 0 | RADIANT | 1.8 | 0 | 0 | 0
1710 | JHARGRAM | Jhargram Mechanical Division | DAHATMAL AND IT'S ADJOINING MOUJAS PWSS , SM/12532 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dahatmal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1232/JMD | 26/05/2023 | 546 | M/S. NABIN GOPAL SENGUPTA | 20.79 | 0 | 0 | 75
1711 | JHARGRAM | Jhargram Division | DAHATMAL AND IT'S ADJOINING MOUJAS PWSS , SM/12532 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1712 | JHARGRAM | Jhargram Division | DAHATMAL AND IT'S ADJOINING MOUJAS PWSS , SM/12532 | New | Construction of boundary wall and Allied works At Dahatmal,Bagmuri,Champasol 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1280/JHD | 03/09/2024 | 30 | PROVAT KUMAR DE | 37.25 | 0 | 0 | 30
1713 | JHARGRAM | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS , SM/12355 | New | Constructions of 150 cum OHR, Installation of display Board, soil investigationunder JJM with allied work for PITHAPURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1456/JHD | 30/08/2023 | 240 | ABJ ENGINEERING | 73.26 | 0 | 0 | 0
1714 | JHARGRAM | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS , SM/12355 | New | Material Requisition To Resource Division | 1554/JHD | 07/09/2023 | 0 | Resource Division | 37.24 | 0 | 0 | 0
1715 | JHARGRAM | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS , SM/12355 | New | Laying distribution pipe line under JJM with allied work for PITHAPURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1516/JHD | 05/09/2023 | 550 | I R CONSTRUCTION | 87.13 | 0 | 0 | 85
1716 | JHARGRAM | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS , SM/12355 | New | Sinking of Tube Well under JJM with allied work for PITHAPURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1612/JHD | 08/09/2023 | 30 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.75 | 0 | 0 | 100
1717 | JHARGRAM | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS , SM/12355 | New | Rising main pipe line, Interconnection pipe line, Accommodate FHTC ( 927 nos) under JJM with allied work for PITHAPURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1564/JHD | 07/09/2023 | 637 | I R CONSTRUCTION | 48.13 | 0 | 0 | 90
1718 | JHARGRAM | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS , SM/12355 | New | Construction of Pump House under JJM with allied work for PITHAPURA AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour and & materials within Jhargram Sub-Division. | 1864/JHD | 01/11/2023 | 90 | GANGULY ENTERPRISE | 12.24 | 0 | 0 | 100
1719 | JHARGRAM | Jhargram Mechanical Division | PITHAPURA AND ADJOINING MOUJAS PWSS , SM/12355 | New | New service connection charges | 47/JMD | 29/12/2023 | 0 | WBSEDCL | 5.49 | 0 | 0 | 0
1720 | JHARGRAM | Jhargram Mechanical Division | PITHAPURA AND ADJOINING MOUJAS PWSS , SM/12355 | New | Quotation for new servcie connection at PITHAPURA TW-II water supply scheme. | 95/JMD | 08/05/2024 | 0 | WBSEDCL | 8.22 | 0 | 0 | 0
1721 | JHARGRAM | Central Drilling | PITHAPURA AND ADJOINING MOUJAS PWSS , SM/12355 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1722 | JHARGRAM | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS , SM/12355 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Kuliana GP at Gopiballavpur-II Block under jhargram Division PHE Dte. (Phase-I) | 1034/JSD | 13/11/2024 | 10 | PRINT PREVIEW | 0.84 | 0 | 0 | 0
1723 | JHARGRAM | Jhargram Mechanical Division | BAHIR GRAM AND ADJOINING MOUJAS PWSS , SM/12441 | New | New Service Connection | 23/AUG | 25/08/2023 | 0 | WBSEDCL | 7.91 | 0 | 0 | 0
1724 | JHARGRAM | Jhargram Mechanical Division | BAHIR GRAM AND ADJOINING MOUJAS PWSS , SM/12441 | New | New service connection | 24/AUG | 25/08/2023 | 0 | WBSEDCL | 2.81 | 0 | 0 | 0
1725 | JHARGRAM | Central Drilling | BAHIR GRAM AND ADJOINING MOUJAS PWSS , SM/12441 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1726 | JHARGRAM | Jhargram Division | BAHIR GRAM AND ADJOINING MOUJAS PWSS , SM/12441 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection ( 7683 Nos), etc.including 02(Two) Years Operation & Maintenance For KAMTA , SUSHNI, BAHIR GRAM, KAPGARI, MURAKATI, MAHISAMURA PWSS Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 1954/JHD | 22/11/2023 | 406 | SIBSANKAR CHOWDHURY | 2070.24 | 0 | 0 | 65
1727 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11478 | New | Material Requisition To Resource Division | 1511/JHD | 05/09/2023 | 0 | Resource Division | 7.87 | 0 | 0 | 0
1728 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11478 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Balidiha at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6768/JMD | 27/08/2024 | 34 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 100
1729 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11478 | New | new service connection for Kaliam water supply scheme | 01/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1730 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11478 | New | Fuel & lubricant charges which is used at Rig unit HALCO for boring purpose at the site of Balidiha under 179 scheme(SM/11478) under Jamboni block | 424/JMD | 27/11/2024 | 0 | SURAJ SERVICE STATION | 0.53 | 0 | 0 | 0
1731 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11478 | New | New Service Connection Charges for Chirkundihi PWSS | 83/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1732 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11478 | New | New Service Connection Charges for Bhalukhuliya PWSS | 84/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1733 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11478 | New | New Service Connection Charges for Kapashi PWSS | 82/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1734 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11478 | New | new service connection charges at Juasole,Parsuli water supply scheme | 02/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1735 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11478 | New | New service connection | 65/JMD | 12/02/2024 | 0 | WBSEDCL | 0.84 | 0 | 0 | 0
1736 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11478 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | 340/JHD | 09/03/2023 | 872 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 0 | 0 | 50
1737 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11478 | New | Supply , Delivery of Hydraulic pump for rotation motor of Halco / 238 / V-596 Rig unit under Jhargram Mechanical Division P.H.E Dte. | 16/W/MMSD(D) | 13/01/2025 | 10 | CHAKRABORTY MINING & ENGINEERING | 0.97 | 0 | 0 | 100
1738 | JHARGRAM | Jhargram Division | TIAKITPUR ANAD AJOINING MOUJAS PWSS , SM/12349 | New | Material Requisition To Resource Division | 422/JHD | 13/03/2024 | 0 | Resource Division | 33.76 | 0 | 0 | 0
1739 | JHARGRAM | Jhargram Mechanical Division | TIAKITPUR ANAD AJOINING MOUJAS PWSS , SM/12349 | New | Quotation for new service connection at Tikayetpur T/W-I water supply scheme. | 259/JMD | 15/07/2024 | 0 | WBSEDCL | 6.86 | 0 | 0 | 0
1740 | JHARGRAM | Jhargram Mechanical Division | TIAKITPUR ANAD AJOINING MOUJAS PWSS , SM/12349 | New | New Service Connection Charges for Tikayetpur tw-I pwss | 41/JMD | 01/02/2024 | 0 | WBSEDCL | 2.88 | 0 | 0 | 0
1741 | JHARGRAM | Central Drilling | TIAKITPUR ANAD AJOINING MOUJAS PWSS , SM/12349 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1742 | JHARGRAM | Jhargram Division | TIAKITPUR ANAD AJOINING MOUJAS PWSS , SM/12349 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1743 | JHARGRAM | Jhargram Division | TIAKITPUR ANAD AJOINING MOUJAS PWSS , SM/12349 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Tiakitpur and its adjoining mouzas Pipe Water Supply Scheme within Gopiballavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 200/GPSD | 11/03/2024 | 30 | DEBABRATA DUTTA | 4.3 | 0 | 0 | 5
1744 | JHARGRAM | Jhargram Division | BELDA AND ADJOINING MOUJAS PWSS , SM/12451 | New | Material Requisition To Resource Division | 1577/JHD | 08/09/2023 | 0 | Resource Division | 54.42 | 0 | 0 | 0
1745 | JHARGRAM | Jhargram Mechanical Division | BELDA AND ADJOINING MOUJAS PWSS , SM/12451 | New | New service connection | 21/AUG | 24/08/2023 | 0 | WBSEDCL | 4.82 | 0 | 0 | 0
1746 | JHARGRAM | Jhargram Mechanical Division | BELDA AND ADJOINING MOUJAS PWSS , SM/12451 | New | New service connection | 16/AUG | 24/08/2023 | 0 | WBSEDCL | 2.83 | 0 | 0 | 0
1747 | JHARGRAM | Jhargram Mechanical Division | BELDA AND ADJOINING MOUJAS PWSS , SM/12451 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Belda & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2258/JMD | 09/08/2023 | 180 | AMIT DAS | 20.75 | 0 | 0 | 75
1748 | JHARGRAM | Jhargram Division | BELDA AND ADJOINING MOUJAS PWSS , SM/12451 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection for Belda and its adjoining mouzas Water Supply Scheme within Jamboni Block under R.W.S.Jhargram Sub Division of Jhargram Division, P.H.E.Dte. | 546/JRWS | 30/12/2024 | 15 | M/S. D.K.H.CONSTRUCTION | 2.46 | 0 | 0 | 0
1749 | JHARGRAM | Jhargram Division | BELDA AND ADJOINING MOUJAS PWSS , SM/12451 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Belda and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 517/JRWS | 15/03/2024 | 60 | M/S DURGA ENTERPRISE | 4.2 | 0 | 0 | 5
1750 | JHARGRAM | Jhargram Division | BELDA AND ADJOINING MOUJAS PWSS , SM/12451 | New | Sinking of Tube Well , Pump House , 100 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation ,including 02(Two) Years Operation & Maintenance & Accommodate FHTC (933 nos) under JJM with allied work for Belda PWSS in Jamboni Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 368/JHD | 14/03/2023 | 180 | M/S. D.K.H.CONSTRUCTION | 323.71 | 0 | 0 | 95
1751 | JHARGRAM | Jhargram Division | BELDA AND ADJOINING MOUJAS PWSS , SM/12451 | New | Installation of display board for JJM works at different piped water supply scheme within Jamboni Block and Others Block under Jhargram Division, PHE dte. (2nd Phase) | 238/GPSD | 12/03/2024 | 10 | KARNAJORA AGNIBINA SEVA SAMITY | 0.97 | 0 | 0 | 100
1752 | JHARGRAM | Jhargram Division | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. , SM/12330 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 150 cum and staging height 20 mtr. as per approved drawing with allied works of KANKRIDAHI & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for GOPIBALLAVPUR-I Block, District: - Jhargram. | 2058/JHD | 07/12/2023 | 210 | ASIS KUMAR SARANGI | 73.5 | 0 | 0 | 0
1753 | JHARGRAM | Jhargram Division | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. , SM/12330 | New | Material Requisition To Resource Division | 1582/JHD | 08/09/2023 | 0 | Resource Division | 83.7 | 0 | 0 | 0
1754 | JHARGRAM | Jhargram Division | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. , SM/12330 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Kankridahi and its adjoining mouzas Pipe Water Supply Scheme within Gopaballavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 199/GPSD | 11/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 4.3 | 0 | 0 | 0
1755 | JHARGRAM | Jhargram Mechanical Division | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. , SM/12330 | New | New Service Connection Charges for Kakridahi t/w-II pwss | 35/JMD | 01/02/2024 | 0 | WBSEDCL | 2.67 | 0 | 0 | 0
1756 | JHARGRAM | Jhargram Mechanical Division | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. , SM/12330 | New | New Service Connection Charges for Kakridahi tw-I pwss | 36/JMD | 01/02/2024 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
1757 | JHARGRAM | Central Drilling | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. , SM/12330 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1758 | JHARGRAM | Jhargram Division | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. , SM/12330 | New | Sinking of Tube Well , Pump House , 100 cum GLR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, Operation and Maintenance and Accommodate FHTC ( 1288 nos) under JJM with allied work for KANKRIDAHI AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1129/JHD | 20/07/2023 | 720 | ASIS KUMAR SARANGI | 308.99 | 0 | 0 | 95
1759 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Material Requisition To Resource Division | 1591/JHD | 08/09/2023 | 0 | Resource Division | 60.65 | 0 | 0 | 0
1760 | JHARGRAM | Jhargram Mechanical Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | New Service connection | 16/JMD | 10/11/2023 | 0 | WBSEDCL | 6.88 | 0 | 0 | 0
1761 | JHARGRAM | Jhargram Mechanical Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | New service connection | 27/AUG | 29/08/2023 | 0 | WBSEDCL | 6.24 | 0 | 0 | 0
1762 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Accommodate FHTC ( 1591 nos) under JJM with allied work for RADHANAGAR AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 858/JHD | 08/06/2023 | 90 | SUNIL DULE | 67.72 | 0 | 0 | 90
1763 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Radhanagar and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | 2266/JHD | 02/12/2024 | 30 | TAPAN KUMAR MANDAL | 8.01 | 0 | 0 | 0
1764 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Sinking of Tube Well , Interconnection pipe line, Laying distribution pipe line, under JJM with allied work for RADHANAGAR AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 649/JHD | 11/05/2023 | 90 | R. CONSTRUCTION | 47.91 | 0 | 0 | 95
1765 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Construction of Pump House , Laying distribution pipe line, Boundary wall, Installation of display Board under JJM with allied work for RADHANAGAR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (2nd Call Ref eNIT_17 of 2022-23 , SL No.-3 ) | 1322/JHD | 10/08/2023 | 90 | R. CONSTRUCTION | 96.19 | 0 | 0 | 100
1766 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Nedabahara GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | 1844/JHD | 20/09/2024 | 10 | PRINT PREVIEW | 0.92 | 0 | 0 | 100
1767 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Patashimul, Salboni GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | 1845/JHD | 20/09/2024 | 10 | MANOJ KUMAR MAHATA | 0.84 | 0 | 0 | 100
1768 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Stagging of GI Pipe at Bindukata under Radhanagar PWSS under Jhargram Block under Jhargram District. | 341/JHD | 29/02/2024 | 30 | A R CONSTRUCTION | 0.96 | 0 | 0 | 100
1769 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Stagging of GI Pipe at Murgidihi, Kanyaduba under Radhanagar PWSS under Jhargram Block under Jhargram District. | 342/JHD | 29/02/2024 | 30 | A R CONSTRUCTION | 0.91 | 0 | 0 | 100
1770 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Manik-para GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | 1843/JHD | 20/09/2024 | 10 | MANOJ KUMAR MAHATA | 0.84 | 0 | 0 | 100
1771 | JHARGRAM | Jhargram Mechanical Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | New service connection | 125/JMD | 29/03/2024 | 0 | WBSEDCL | 0.82 | 0 | 0 | 0
1772 | JHARGRAM | Jhargram Mechanical Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Radhanagar & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1248/JMD | 26/05/2023 | 180 | BEE GEE CONSTRUCTION | 21.86 | 0 | 0 | 100
1773 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Construction of Laying distribution pipe line under JJM with allied work for RADHANAGAR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 815/JHD | 02/06/2023 | 90 | SUNIL DULE | 94.39 | 0 | 0 | 100
1774 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Construction of 250 cum OHR, Rising main pipe line, Laying distribution pipe line, soil investigation under JJM with allied work for RADHANAGAR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref: 1 st Call eNIT_17 of 2022-23, SL No.-1 and 2nd Call eNIT_03 of 2023-24, SL No.-1) | 1717/JHD | 29/09/2023 | 783 | PARTHA PROTIM PRADHAN | 94.29 | 0 | 0 | 60
1775 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Balance work for Laying DI Rising Main Work for Radhanagar Water Supply Scheme within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1177/JHD | 27/05/2025 | 60 | SUNIL DULE | 2.02 | 0 | 0 | 0
1776 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Trial run for RADHANGAR AND ADJOINING MOUZAS PWSS scheme within Jhargram Block under Jhargram Division, PHE Dte. for 3 months. | 733/JHD | 02/04/2025 | 91 | SUNIL DULE | 1.04 | 0 | 0 | 0
1777 | JHARGRAM | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS , SM/12777 | New | Construction of boundary wall and Allied works At Radhanagar 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1356/JHD | 16/06/2025 | 30 | SUNIL DULE | 11.42 | 0 | 0 | 0
1778 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS , SM/12713 | New | Material Requisition To Resource Division | 1539/JHD | 06/09/2023 | 0 | Resource Division | 60.72 | 0 | 0 | 0
1779 | JHARGRAM | Jhargram Mechanical Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS , SM/12713 | New | Quotation for new service connection atRaghunathpur water supply scheme T/W -1 | 26/JMD | 22/04/2024 | 0 | WBSEDCL | 3.06 | 0 | 0 | 0
1780 | JHARGRAM | Jhargram Mechanical Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS , SM/12713 | New | New service connection charges for Belatikri, t/w no.-II | 54/JMD | 12/03/2024 | 0 | WBSEDCL | 3.34 | 0 | 0 | 0
1781 | JHARGRAM | Central Drilling | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS , SM/12713 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1782 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS , SM/12713 | New | Laying Distribution pipe line (140 mm) at Raghunathpur PWSS within Binpur-I Block under Jhargram Sub Division under Jhargram Division PHE Dte. | 416/JHD | 25/02/2025 | 90 | ENVOTECH INFRA SOLUTION | 21.29 | 0 | 0 | 0
1783 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS , SM/12713 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Ramgarh GP at Binpur-I Block under jhargram Division PHE Dte. (Phase-I) | 996/JSD | 23/10/2024 | 10 | PRINT PREVIEW | 0.75 | 0 | 0 | 0
1784 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS , SM/12713 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Sijua GP at Binpur-I Block under jhargram Division PHE Dte. (Phase-I) | 997/JSD | 23/10/2024 | 10 | MANOJ KUMAR MAHATA | 0.92 | 0 | 0 | 0
1785 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS , SM/12713 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Raghunathpur and its Adjoining Mouzas PWSS , Block Binpur-I, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht 2.300mtr from G.L | 767/JSD | 09/08/2024 | 30 | ASHOK CHATTARAJ | 4.61 | 0 | 0 | 100
1786 | JHARGRAM | Jhargram Division | BARABARI AND ADJOINING MOUJAS PWSS , SM/12722 | New | Material Requisition To Resource Division | 1602/JHD | 08/09/2023 | 0 | Resource Division | 28.74 | 0 | 0 | 0
1787 | JHARGRAM | Jhargram Division | BARABARI AND ADJOINING MOUJAS PWSS , SM/12722 | New | Supply and Delivery of DI Specials for laying of Distribution Main including interconnection for Barabari and its adjoining mouzas Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte. | 2369/JHD | 09/12/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 3.42 | 0 | 0 | 0
1788 | JHARGRAM | Jhargram Mechanical Division | BARABARI AND ADJOINING MOUJAS PWSS , SM/12722 | New | New service connection charges. | 20/JMD | 08/12/2023 | 0 | WBSEDCL | 9.92 | 0 | 0 | 0
1789 | JHARGRAM | Jhargram Mechanical Division | BARABARI AND ADJOINING MOUJAS PWSS , SM/12722 | New | New Service connection charges. | 24/JMD | 04/03/2024 | 0 | WBSEDCL | 3 | 0 | 0 | 0
1790 | JHARGRAM | Jhargram Mechanical Division | BARABARI AND ADJOINING MOUJAS PWSS , SM/12722 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Barabari & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1231/JMD | 26/05/2023 | 180 | KAMAKHYA ENTERPRISE | 20.79 | 0 | 0 | 87
1791 | JHARGRAM | Jhargram Division | BARABARI AND ADJOINING MOUJAS PWSS , SM/12722 | New | Sinking of Tube Well , Pump House , 100 cum OHR, & 100 cum GLR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation & Accommodate FHTC (883 nos) under JJM with allied work including 02(Two) Years Operation & Maintenanace for BARABARI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 851/JHD | 08/06/2023 | 724 | ASIS KUMAR SARANGI | 408.94 | 0 | 0 | 70
1792 | JHARGRAM | Jhargram Division | BARABARI AND ADJOINING MOUJAS PWSS , SM/12722 | New | Construction of boundary wall and Allied works At Chandri, Barabari, Gramohan 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1282/JHD | 03/09/2024 | 120 | ASIS KUMAR SARANGI | 37.46 | 0 | 0 | 55
1793 | JHARGRAM | Jhargram Mechanical Division | BARABARI AND ADJOINING MOUJAS PWSS , SM/12722 | New | Supply delivery & Installation of actuator operated double flanged type Sluice Valve at three different locations in the delivery pipeline with other allied works at Barabari PWSS of Jhargram block of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 1115/JMD | 27/05/2025 | 60 | DEBJYOTI BASU | 11.06 | 0 | 0 | 0
1794 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Satkuli Charar w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16917 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Satkuli Charar and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2501/JMD | 25/08/2023 | 180 | THE BUSINESS ENGINEERS INDIA | 75.12 | 0 | 0 | 0
1795 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at GOBINDAPUR AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16687 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Jangalkhas and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2772/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 77.3 | 0 | 0 | 0
1796 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS , SM/16934 | New | Material Requisition To Resource Division | 1584/JHD | 08/09/2023 | 0 | Resource Division | 38.98 | 0 | 0 | 0
1797 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS , SM/16934 | New | New Service Connection Charges for Amlatora T/W - II PWSS | 368/JMD | 24/09/2024 | 0 | WBSEDCL | 6.51 | 0 | 0 | 0
1798 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS , SM/16934 | New | New Service Connection Charges for Amlatora T/W-I PWSS | 353/JMD | 13/09/2024 | 0 | WBSEDCL | 3.56 | 0 | 0 | 0
1799 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS , SM/16934 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (2294 Nos), etc.including 02(Two) Years Operation & Maintenance For DHARAMPUR ZONE-I , DHARAMPUR ZONE-VII Pipe water supply Scheme within Binpur-II Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1209/JHD | 26/07/2023 | 615 | SUNIL DULE | 761.33 | 0 | 0 | 70
1800 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS , SM/16934 | New | Supply & Delivery of CI&DI Specials for laying of Rising Main including interconnection between Tube Well and Raising Main and OHR for Dharampur (Zone-I) Amratora and its adjoining mouzas Water Supply Scheme within Binpur-I Block under Jhargram Sub Division of Jhargram Division, P.H.E.Dte. (2nd Call) [Ref: 1st Call of e-NIQ-02 of AE/JSD of 2024-2025, SL. No.-01] | 366/JSD | 29/04/2025 | 14 | SUNIL DULE | 2.13 | 0 | 0 | 0
1801 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS , SM/16934 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dharampur zone-I, Amlatora & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2281/JMD | 10/08/2023 | 360 | ABHIJIT BASU | 22.11 | 0 | 0 | 91
1802 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS , SM/16993 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dharampur zone-V, Bashajuri & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2283/JMD | 10/08/2023 | 180 | SUJOY RANJAN BHOWMICK | 21.04 | 0 | 0 | 0
1803 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS , SM/16993 | New | Material Requisition To Resource Division | 1597/JHD | 08/09/2023 | 0 | Resource Division | 94.68 | 0 | 0 | 0
1804 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS , SM/16993 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (3149 Nos), etc. including 02(Two) Years Operation & Maintenance For DHARAMPUR ZONE-V , DHARAMPUR ZONE-VI Pipe water supply Scheme within Binpur-II Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1396/JHD | 18/08/2023 | 772 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 977.25 | 0 | 0 | 20
1805 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS , SM/16993 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Kanke GP at Binpur-II Block under jhargram Division PHE Dte. (Phase-I) | 1012/JSD | 05/11/2024 | 10 | PRINT PREVIEW | 0.84 | 0 | 0 | 0
1806 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS , SM/16993 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Ergoda GP at Binpur-II Block under jhargram Division PHE Dte. (Phase-I) | 1011/JSD | 05/11/2024 | 10 | GOPAL JANA | 0.75 | 0 | 0 | 0
1807 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Ghora Pincha w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18024 | Solarisation | Providing solarisation of WBSEDCL energised pumping installation at Upar Baghuasol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2775/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 32.21 | 0 | 0 | 0
1808 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Murakati And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17119 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Uttar Barashol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2498/JMD | 25/08/2023 | 180 | AMITAVA CHAKRABORTY | 75.12 | 0 | 0 | 0
1809 | JHARGRAM | Jhargram Division | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte , SM/17964 | Augmentation | Providing pending FHTC (200 nos)of Rantua W/S scheme at Gopiballavpur-II block under Jhargram Sub Division within Jhargram Division,PHE Dte | 879/JHD | 08/06/2023 | 30 | TAPAS KUMAR JANA | 8.7 | 0 | 0 | 0
1810 | JHARGRAM | Jhargram Division | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte , SM/17964 | Augmentation | 03 nos I.E.Ps [2 nos of size 20 cum/hr.(at proposed sites),35 cum/hr.(at head work site)] with platfroms, blower with compressor rooms, Pump house with blower, compressor room of Rantua w/s scheme. | 878/JHD | 08/06/2023 | 60 | MONDAL PRECISION PRIVATE LIMITED | 39.84 | 0 | 0 | 25
1811 | JHARGRAM | Jhargram Division | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte , SM/17964 | Augmentation | 02 nos Sinking of 250x150 mm dia x 150 mtr.rig bored tubewell at prposed sites (Jarakusum Mouza & Askola Mouza), replacement of distribution pipe line(part)and extension of distribution pipeline, construction chain link fencing at 3 nos sites for Rantua w/s scheme at Gopiballavpur-II block under Jhargram Sub-division within Jhargram Division, PHE Dte. 3rd Call (Ref: 1st Call eNIT_28 of EE/JHD of 2022-23, SL No.-9, 2nd Call eNIT_11 of EE/JHD of 2023-24, SL No.-1) | 448/JHD | 14/03/2024 | 383 | DEBASISH DOGRA | 57.49 | 0 | 0 | 50
1812 | JHARGRAM | Jhargram Division | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte , SM/17964 | Augmentation | Construction of Pump house (inner size 3.6m x 3.00m width) at proposed tube-well site at Askola mouza & Jarakusum mouza with chain link fencing 60.00mtr each site of Rantua W/S Scheme at Gopiballavpur-II Block under Jhargram sub-division, PHE Dte. 2nd Call (Ref eNIT_28 of 2022-23 , SL No.-8 ) | 1402/JHD | 18/08/2023 | 60 | TAPAS PAL | 15.78 | 0 | 0 | 15
1813 | JHARGRAM | Jhargram Division | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte , SM/17964 | Augmentation | Repair and renovation of Pump house no 2 at Rantua w/s Scheme within Jhargram Sub Division, PHE Dte. . (3rd Call) [Ref. eNIT 07 OF AE/JSD OF 2024-2025, SL No. 02] | 1068/JSD | 26/11/2024 | 14 | S.R. ENTERPRISE | 2.23 | 0 | 0 | 85
1814 | JHARGRAM | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at Shona Konia And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17962 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Petbindi and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2506/JMD | 25/08/2023 | 180 | SUJOY RANJAN BHOWMICK | 12.52 | 0 | 0 | 0
1815 | JHARGRAM | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at Mahulbani w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17981 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Chhahazari humtia and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2771/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 77.3 | 0 | 0 | 0
1816 | JHARGRAM | Jhargram Division | Augmentation of Pond Water Based Silda Pipe Water Supply Scheme under Jhargram Division, Block : Binpur-II, District : Jhargram , SM/17953 | Augmentation | Construction of 50 Cum/Hr Capacity WTP,Installation of MS Structural Intake Jetty(Floating Type including Intake pipe carriage way) , Laying of Distribution System,to Accommodate FHTC (1880 Nos) For Augmentation of Silda Pond Based PWSS Under Binpur-II Block under Jhargram Division, P.H.E. Dte. | 45/JHD | 09/01/2024 | 580 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 369 | 0 | 0 | 60
1817 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Pond Water Based Silda Pipe Water Supply Scheme under Jhargram Division, Block : Binpur-II, District : Jhargram , SM/17953 | Augmentation | Supply, delivery and installation of pumping machineries and allied electro-mechanical accessories for Low lift and High lift pumping operations for augmentation of pond based Silda and its adjoining moujas surface water based piped water supply scheme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 480/JMD | 20/03/2025 | 150 | B. T. PROJECTS PVT. LTD. | 86.7 | 0 | 0 | 0
1818 | JHARGRAM | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at Darukuli w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18121 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Darukuli and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2632/JMD | 29/08/2023 | 180 | AMITAVA CHAKRABORTY | 31.3 | 0 | 0 | 0
1819 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Chenchur gerya w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17062 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Champasol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2500/JMD | 25/08/2023 | 180 | MEGA SOLAR ENERGY | 75.09 | 0 | 0 | 0
1820 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at CHANDABILA AND ADJOINING MOPUJAS Pwss under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17066 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Belda and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2504/JMD | 25/08/2023 | 180 | M/S. SAMRIDDHI ENTERPRISE | 31.3 | 0 | 0 | 0
1821 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at UTTAR BARASHOL AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17073 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Uttar Barashol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2498/JMD | 25/08/2023 | 180 | AMITAVA CHAKRABORTY | 75.12 | 0 | 0 | 0
1822 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-VI CHANDPARA AND ADJOINING MOUJAS PWSS , SM/16994 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I, II & III and making compound lighting arrangement at T/W no. I of Dharampur zone-VI, Chandpara & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2282/JMD | 10/08/2023 | 180 | DEBJYOTI BASU | 30.67 | 0 | 0 | 0
1823 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-VI CHANDPARA AND ADJOINING MOUJAS PWSS , SM/16994 | New | Material Requisition To Resource Division | 1598/JHD | 08/09/2023 | 0 | Resource Division | 55.79 | 0 | 0 | 0
1824 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-VI CHANDPARA AND ADJOINING MOUJAS PWSS , SM/16994 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (3149 Nos), etc. including 02(Two) Years Operation & Maintenance For DHARAMPUR ZONE-V , DHARAMPUR ZONE-VI Pipe water supply Scheme within Binpur-II Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1396/JHD | 18/08/2023 | 772 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 977.25 | 0 | 0 | 20
1825 | JHARGRAM | Jhargram Division | GOHALMARA AND ADJOINING MOUJAS PWSS , SM/12340 | New | Material Requisition To Resource Division | 1550/JHD | 07/09/2023 | 0 | Resource Division | 33.8 | 0 | 0 | 0
1826 | JHARGRAM | Jhargram Mechanical Division | GOHALMARA AND ADJOINING MOUJAS PWSS , SM/12340 | New | Quotation for new service connection at Gohalmara water supply scheme T/W - I | 21/JMD | 19/04/2024 | 0 | WBSEDCL | 3.41 | 0 | 0 | 0
1827 | JHARGRAM | Jhargram Mechanical Division | GOHALMARA AND ADJOINING MOUJAS PWSS , SM/12340 | New | Quotation for new service connection at Gohalmara water supply scheme T/W-II | 22/JMD | 19/04/2024 | 0 | WBSEDCL | 4 | 0 | 0 | 0
1828 | JHARGRAM | Central Drilling | GOHALMARA AND ADJOINING MOUJAS PWSS , SM/12340 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1829 | JHARGRAM | Jhargram Division | GOHALMARA AND ADJOINING MOUJAS PWSS , SM/12340 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1830 | JHARGRAM | Jhargram Division | GOHALMARA AND ADJOINING MOUJAS PWSS , SM/12340 | New | Field Level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in fferent Pipe Water Supply Scheme (7 nos PWSS of 130 PWSS) within Gopiballavpur-II Block in the District of Jhargram under Jhargram Division. PHE Dte. Location- i) Chingra PWSS, ii) Gohalmara PWSS iii) Kendana PWSS iv) Kulina PWSS v) Sonakinia PWSS Vi) Tentilia PWSS vii) Chorchita PWSS | 368/JSD | 29/04/2025 | 150 | TECHVISION | 3.72 | 0 | 0 | 10
1831 | JHARGRAM | Jhargram Division | GOHALMARA AND ADJOINING MOUJAS PWSS , SM/12340 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Ghohalmara and its Adjoining Mouzas PWSS , Block Gopiballavpur-II, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | 780/JSD | 09/08/2024 | 30 | MAA RAJBALLABHI ENTERPRISE | 4.69 | 0 | 0 | 100
1832 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(306 nos) within Binpur-II Block under Jhargram District. , SM/10356 | Anganwadi | Water Supply Arrangement for 163 Nos. Anganwadi Centers at GP Bhulaveda, Ergoda, Belpahari, Harda, Simulpal under Binpur-II Block in Jhargram District under Jhargram Division, PHE Dte. | 344/JHD | 28/09/2022 | 916 | SUNIL DULE | 225.19 | 0 | 0 | 90
1833 | JHARGRAM | Jhargram Division | CHAKKUA AND ADJOINING MOUJAS PWSS , SM/12356 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 150 cum and staging height 20 mtr. as per approved drawing with allied works of CHAKUA & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for JHARGRAM Block, District: - Jhargram. | 2054/JHD | 07/12/2023 | 210 | SATYABRATA BHAUMIK | 71.15 | 0 | 0 | 0
1834 | JHARGRAM | Jhargram Division | CHAKKUA AND ADJOINING MOUJAS PWSS , SM/12356 | New | Material Requisition To Resource Division | 1563/JHD | 07/09/2023 | 0 | Resource Division | 32.14 | 0 | 0 | 0
1835 | JHARGRAM | Jhargram Mechanical Division | CHAKKUA AND ADJOINING MOUJAS PWSS , SM/12356 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chakkua & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1238/JMD | 26/05/2023 | 180 | DEB KUMAR BASU | 20.83 | 0 | 0 | 50
1836 | JHARGRAM | Jhargram Division | CHAKKUA AND ADJOINING MOUJAS PWSS , SM/12356 | New | Laying distribution pipe line under JJM with allied work for CHAKKUA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1108/JHD | 18/07/2023 | 711 | SUNIL DULE | 168.97 | 0 | 0 | 90
1837 | JHARGRAM | Jhargram Division | CHAKKUA AND ADJOINING MOUJAS PWSS , SM/12356 | New | Construction of boundary wall and Allied works At Chakua, Uransol, Patharnala 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1281/JHD | 03/09/2024 | 30 | SUNIL DULE | 37.46 | 0 | 0 | 0
1838 | JHARGRAM | Jhargram Mechanical Division | CHAKKUA AND ADJOINING MOUJAS PWSS , SM/12356 | New | new service connection charges at Chakua water supply scheme | 19/JMD | 15/04/2024 | 0 | WBSEDCL | 5.29 | 0 | 0 | 0
1839 | JHARGRAM | Jhargram Mechanical Division | CHAKKUA AND ADJOINING MOUJAS PWSS , SM/12356 | New | New meter connection charges of Chakua-2 water supply scheme | 24/JMD | 22/04/2024 | 0 | WBSEDCL | 9.92 | 0 | 0 | 0
1840 | JHARGRAM | Jhargram Division | CHAKKUA AND ADJOINING MOUJAS PWSS , SM/12356 | New | Sinking of Tube Well , Pump House , 100 cum CWR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Boundary wall, Installation of display Board, Operation and Maintenance and Accommodate FHTC ( 1104 nos) under JJM with allied work for CHAKKUA AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub Division under Jhargram Division, PHE Dte. | 1109/JHD | 18/07/2023 | 711 | SUNIL DULE | 161.02 | 0 | 0 | 75
1841 | JHARGRAM | Jhargram Division | CHAKKUA AND ADJOINING MOUJAS PWSS , SM/12356 | New | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of Propose O.H.R. for Chakkua, Uransol PWSS in Jhargram Block within Jhargram District under Jhargram Division, P.H.E.Dte. | 366/JHD | 20/03/2025 | 30 | M/S. M.D. ENGINEERING & SURVEYS | 1.59 | 0 | 0 | 0
1842 | JHARGRAM | Jhargram Mechanical Division | SHONA KONIA AND ADJOINING MOUJAS PWSS , SM/12345 | New | Quotation for new service connection atSONAKUNIA TW-I water supply scheme. | 100/JMD | 08/05/2024 | 0 | WBSEDCL | 5.02 | 0 | 0 | 0
1843 | JHARGRAM | Jhargram Mechanical Division | SHONA KONIA AND ADJOINING MOUJAS PWSS , SM/12345 | New | Qutation for new service connection at Sonakunia T/W-II water supply scheme. | 153/JMD | 31/05/2024 | 0 | WBSEDCL | 7.11 | 0 | 0 | 0
1844 | JHARGRAM | Central Drilling | SHONA KONIA AND ADJOINING MOUJAS PWSS , SM/12345 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1845 | JHARGRAM | Jhargram Division | SHONA KONIA AND ADJOINING MOUJAS PWSS , SM/12345 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1846 | JHARGRAM | Jhargram Division | SHONA KONIA AND ADJOINING MOUJAS PWSS , SM/12345 | New | Field Level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in fferent Pipe Water Supply Scheme (7 nos PWSS of 130 PWSS) within Gopiballavpur-II Block in the District of Jhargram under Jhargram Division. PHE Dte. Location- i) Chingra PWSS, ii) Gohalmara PWSS iii) Kendana PWSS iv) Kulina PWSS v) Sonakinia PWSS Vi) Tentilia PWSS vii) Chorchita PWSS | 368/JSD | 29/04/2025 | 150 | TECHVISION | 3.72 | 0 | 0 | 10
1847 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni , SM/06830 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443106 | 12/02/2021 | 0 | SANDIP MANNA | 0.15 | 0 | 0 | 0
1848 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni , SM/06830 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443106 | 12/02/2021 | 0 | SOVANDEB MANNA | 0.03 | 0 | 0 | 0
1849 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni , SM/06830 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443106 | 12/02/2021 | 0 | ANIRBAN CHAKRABORTY | 0.18 | 0 | 0 | 0
1850 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni , SM/06830 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443106 | 12/02/2021 | 0 | ARUP KR ADAK | 0.07 | 0 | 0 | 0
1851 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni , SM/06830 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chhatinasole PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. | 8443115 | 23/03/2022 | 0 | CHAKRABORTTI ENTERPRISE | 23.06 | 0 | 0 | 0
1852 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni , SM/06830 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chichira PWSS of Jamboni Block under Jhargram Division, PHE Dte. | 1581/MD | 11/12/2020 | 180 | SUNIL DULE | 31 | 12.55 | 40.47 | 0
1853 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni , SM/06830 | Retrofitting | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | 844368 | 30/11/2022 | 0 | SUNIL DULE | 2.35 | 0 | 0 | 0
1854 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni , SM/06830 | Retrofitting | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | 844368 | 30/11/2022 | 0 | SUNIL DULE | 13 | 0 | 0 | 0
1855 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni , SM/06830 | Retrofitting | Alied Works (specialy Valve Chember) under Chatinasole W/S Scheme within Jhargram Sub Division unde Jhargram Division, PHE Dte. | 31/GPSD | 18/07/2022 | 21 | DIPAK KUMAR BAKLY | 1.29 | 0 | 0 | 100
1856 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni , SM/06830 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chichira PWSS of Jamboni Block under Jhargram Division, PHE Dte. | 1581/MD | 11/12/2020 | 180 | SUNIL DULE | 31 | 0 | 0 | 90
1857 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni , SM/06830 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Banshia PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. | 1411/MD | 26/11/2020 | 180 | BISHNU PADA NANDI | 3.52 | 3.22 | 50 | 0
1858 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram , SM/06832 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chhenpara PWSS of Jhargram Block under Jhargram Division, PHE Dte. | 844331 | 28/04/2021 | 0 | NIPENDRANATH SINGHA | 0.42 | 0 | 0 | 0
1859 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram , SM/06832 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chhenpara PWSS of Jhargram block under Jhargram Division, PHE Dte. | 8443377 | 24/03/2021 | 0 | NRIPENDRA NATH SINGHA | 3.84 | 0 | 0 | 0
1860 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram , SM/06832 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandalbandh PWSS of Nayagram Block under Jhargram Division, PHE Dte. | 844353 | 17/01/2022 | 0 | PROVAT KUMAR DE | 7.38 | 0 | 0 | 0
1861 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram , SM/06832 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chhenpara PWSS of Jhargram Block under Jhargram Division, PHE Dte. | 8443154 | 24/03/2022 | 0 | NRIPENDRA NATH SINGHA | 0.55 | 0 | 0 | 0
1862 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram , SM/06832 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Lohamelya PWSS of Jhargram Block under Jhargram Division, PHE Dte. (Phase-II) | 1059/MD | 02/07/2021 | 15 | NIMAI LAL GURIA | 7.53 | 6.88 | 100 | 1
1863 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram , SM/06832 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Balibandh PWSS of Jamboni Block under Jhargram Division, PHE Dte. | 1589/MD | 11/12/2020 | 180 | NIRMAL DUTTA | 8.06 | 7.48 | 100 | 0
1864 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram , SM/06832 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barajharia PWSS of Nayagram Block under Jhargram Division, PHE Dte. | 1417/MD | 26/11/2020 | 180 | PROVAT KUMAR DE | 6.04 | 5.3 | 50 | 0
1865 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram , SM/06832 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Lohamelya PWSS of Jhargram Block under Jhargram Division, PHE Dte. | 1414/MD | 26/11/2020 | 180 | NIMAI LAL GURIA | 7.76 | 6.84 | 50 | 0
1866 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram , SM/06832 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Jamboni PWSS of Nayagram Block under Jhargram Division, PHE Dte. | 1418/MD | 26/11/2020 | 180 | K & KABERI ENTERPRISE (PROP. GOUTAM MAITY) | 4.47 | 3.11 | 79.59 | 0
1867 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Purchasing of Materials. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.58 | 0 | 0 | 0
1868 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.58 | 0 | 0 | 0
1869 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January-2023 and February-2023 under Jhargram Division, PHE Dte. | 29A/JRWS | 28/12/2022 | 60 | PROVAT KUMAR DE | 0.93 | 0 | 0 | 100
1870 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Material Requisition To Resource Division | 2162/MD | 17/12/2021 | 0 | Resource Division | 5.58 | 0 | 0 | 0
1871 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Material Requisition To Resource Division | 305/JHD | 28/02/2023 | 0 | Resource Division | 61.6 | 0 | 0 | 0
1872 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for newly sunk tubewell for augmentation of Gidhni (Zone-I) water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 308/JMD | 09/02/2023 | 120 | SUBHASIS ROY | 7.27 | 0 | 0 | 75
1873 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Construction of boundary wall, switch room & interconnection of T/Well for augmentation of Gidhni water supply scheme with in Jamboni block under Jhargram division, P.H.E. DTE. | 1138/JHD | 06/08/2024 | 30 | NRIPENDRA NATH SINGHA | 16.16 | 0 | 0 | 95
1874 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Charichaka ICDS water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 3081/JMD | 14/03/2024 | 120 | DAS CONSTRUCTION | 5.82 | 0 | 0 | 0
1875 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Gidhni PWSS Part-II) in Jamboni Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 273/JSD | 07/10/2021 | 15 | M/S R. DUTTA & CO | 3.95 | 0 | 0 | 100
1876 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Gidhni PWSS (Part-I) in Jamboni Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 240/JSD | 24/09/2021 | 15 | M/S R. DUTTA & CO | 3.92 | 0 | 0 | 100
1877 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Construction of 3.60 M X 3.0 M size Switch Room-Cum-Guard room with Sanitary Arrangement & Construction of Boundary Wall (Length 34.00 mtr. ) for Gidhni (Zone-I) Water Supply Scheme within Jhargram Sub-Division Under Jhargram Division P.H.E. Dte. (2nd Call) | 1326/JHD | 10/08/2023 | 45 | NRIPENDRA NATH SINGHA | 9.36 | 0 | 0 | 100
1878 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Supply delivery of CIDF S/V for the work Augmentation Gidhni Water Supply Scheme under Jhargram Sub Division within Jhargram Division, PHE Dte. | 979/JSD | 17/11/2023 | 7 | NIRMAL DUTTA | 0.93 | 0 | 0 | 100
1879 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | New service connection charges | 30/JMD | 19/12/2023 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1880 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | new service connection charges at Gidhni water supply scheme | 136/JMD | 24/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1881 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Providing fuel and lubricant for rig unit 238/AR/HALCO for boring purpose, augmentation of Ground water based water supply scheme for Gidhni (SM/09374) of two sites in Jamboni Block under Jhargram Division PHE Dte | 274/JMD | 26/07/2024 | 0 | SURAJ SERVICE STATION | 1.01 | 0 | 0 | 0
1882 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Laying of Clear Water Rising main / Distribution pipe line and FHTC work for Augmentation of Ground based Gidhni PWSS (Zone-I to IV) to Accommodate FHTC in Jamboni Block within Jhargram District under Jhargram Division, PHE Dte. | 432/MD | 04/03/2022 | 1124 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 321.65 | 0 | 0 | 60
1883 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. , SM/09374 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gidhni ICDS water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 3080/JMD | 14/03/2024 | 293 | M/S. CHANDRANATH MUKHERJEE | 5.82 | 0 | 0 | 100
1884 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Pukuria PWSS in Jhargram Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 147/JSD | 12/08/2021 | 14 | INDRANIL DUTTA & ASSOCIATES | 2.94 | 0 | 0 | 1
1885 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Sinking of 250mm X 150mm dia. & depth 150 Mtr. Rig bore Tube well - II for Augmentation of Pakuria W/S Scheme within Jhargram block under Jhargram Division, PHE Dte. | 614/MD | 04/04/2022 | 15 | TAPAS KUMAR GIRI | 6.58 | 0 | 0 | 1
1886 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.21 | 0 | 0 | 0
1887 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Purchasing of Materials. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.21 | 0 | 0 | 0
1888 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Sinking of 250mm X 150mm dia. & 150 Mtr. Depth Rig bored Tube well for Augmentation of Ground Water Based Pukuria PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | 179/MD | 01/02/2022 | 60 | ASHIM KUMAR DEY | 96.77 | 0 | 0 | 95
1889 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Construction of 3.60 M X 3.0 M size Switch Room-Cum-Guard room with Sanitary Arrangement for Pukuria Water Supply Scheme within Jhargram Sub-Division P.H.E. Dte. Under Jhargram Division P.H.E.Dte. | 390/JSD | 27/07/2022 | 45 | HRITWIK DUTTA | 4.72 | 0 | 0 | 1
1890 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Supply delivery of Different dia CIDF S/V for the work of ¿ Augmentation of Ground Water Based Water Supply Scheme for Pukuria to Accommodate FHTC in Block Jhargram under Jhargram Sub Division within Jhargram Division, PHE Dte. | 366/JSD | 21/07/2022 | 7 | ASHIM KUMAR DEY | 1.79 | 0 | 0 | 100
1891 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Construction of Boundary Wall for 2nd tubewell site for augmentation of ground water based Pukuria PWSS to accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division P.H.E.Dte. (Length-122mtr,height- 2.3 mtr above G.L. ) | 457/JHD | 11/11/2022 | 60 | TAPAS KUMAR JANA | 9.03 | 0 | 0 | 1
1892 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Supply, delivery, installation, commissioning & trial run of pumping machinery and other electro mechanical accessories at newly sunk replacement tubwell no.II (Near Primary School) of Pukuria W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | 305/JMD | 09/02/2023 | 120 | RSA ENTERPRISE | 9.76 | 0 | 0 | 0
1893 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Laying of rising main & distribution main(part) including interconnection between tube wells of augmentation of ground water based water supply scheme for Pukuria to accommodate FHTC within Jhargram Block Under Jhargram Sub- Division within Jhargram Division, P.H.E. Dte. | 344/JHD | 10/03/2023 | 60 | ASHIM KUMAR DEY | 6.78 | 0 | 0 | 100
1894 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Sinking of 250mm X 150mm dia. & 150 Mtr. Depth Rig bored Tube well for Augmentation of Ground Water Based Pukuria PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | 179/MD | 01/02/2022 | 60 | ASHIM KUMAR DEY | 96.77 | 0 | 0 | 1
1895 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Material Requisition To Resource Division | 2163/MD | 17/12/2021 | 0 | Resource Division | 1.81 | 0 | 0 | 0
1896 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Material Requisition To Resource Division | 2164/MD | 21/10/2022 | 0 | Resource Division | 5.12 | 0 | 0 | 0
1897 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | WBSEDCL new service connection. | 8/JMD/PFMS/DEC | 07/12/2022 | 0 | WBSEDCL | 0.34 | 0 | 0 | 0
1898 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District , SM/09377 | Augmentation | Supply, delivery, installation & commisioning of pumping machinery and other electro mechanical accessories at newly sunk replacement tubwell no.I at Pukuria W/S scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3195/JMD | 28/10/2022 | 30 | DEBJYOTI BASU | 10.07 | 0 | 0 | 95
1899 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09380 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Kechenda PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | BP-2021-22-402 | 23/02/2022 | 0 | RADIANT | 1.36 | 0 | 0 | 0
1900 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09380 | Augmentation | Extension of Distribution pipe line and FHTC work for Augmentation of Ground based Kechenda PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | 424/JSD | 30/12/2021 | 30 | J.S.S. ENTERPRISE | 4.68 | 0 | 0 | 1
1901 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09380 | Augmentation | Balance Work of Augmentation Work of Kechanda Water Supply Scheme within Binpur-II Block under Jhargram Division, P.H.E. Dte. | 740/JSD | 16/08/2023 | 7 | M/S MA LAXMI ENTERPRISE | 0.71 | 0 | 0 | 100
1902 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09380 | Augmentation | Sinking tubewell (200 mm X 165 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works near Kechenda PWSS at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 3079/JMD | 14/03/2024 | 5 | SUJOY RANJAN BHOWMICK | 3.32 | 0 | 0 | 100
1903 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09380 | Augmentation | New Service Connection Charges for Kechanda T/W - III PWSS | 369/JMD | 24/09/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1904 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09380 | Augmentation | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM for scheme (SM/09380) KECHENDA PWSS | 329/JMD | 29/08/2024 | 0 | SURAJ SERVICE STATION | 0.93 | 0 | 0 | 0
1905 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09380 | Augmentation | Supply, delivery, installation, commissioning of submersible pumping machinery and other Electro Mechanical accessories at newly sunk tube well at Kechenda of Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 7305/JMD | 13/11/2024 | 30 | M/S. NABIN GOPAL SENGUPTA | 2.12 | 0 | 0 | 100
1906 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09380 | Augmentation | Dismantling the existing damaged voltage stabilizer & supply, delivery & installation of newly supplied single phase 10 KVA oil cooled type voltage stabilizer with other allied works at tube well no.-I of Kechenda water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 3096/JMD | 15/03/2024 | 30 | M/S. NABIN GOPAL SENGUPTA | 1.79 | 0 | 0 | 100
1907 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Balibandh PWSS (Phase - II) under Jamboni Block. , SM/09385 | Retrofitting | Retrofitting of Ground Water Based W/S Scheme for Baliband PWSS to accommodate FHTC in Block Jamboni under Jhargram Division P.H.E. Dte. (Phase-II) | 288/MD | 15/02/2022 | 45 | NRIPENDRA NATH SINGHA | 6.24 | 0 | 0 | 1
1908 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Balibandh PWSS (Phase - II) under Jamboni Block. , SM/09385 | Retrofitting | Material Requisition To Resource Division | 2166/MD | 17/12/2021 | 0 | Resource Division | 0.32 | 0 | 0 | 0
1909 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers (137 nos.) within Gopiballavpur-II Block under Jhargram District. , SM/10352 | Anganwadi | Water Supply Arrangement for 137 Nos Anganwadi Centers At Gopiballavpur-II Block in Jhargram District under Jhargarm Division, PHE Dte. | 432/JHD | 04/11/2022 | 90 | CHAKRABORTTI ENTERPRISE | 186.54 | 0 | 0 | 100
1910 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. , SM/11481 | New | Material Requisition To Resource Division | 1513/JHD | 05/09/2023 | 0 | Resource Division | 4.05 | 0 | 0 | 0
1911 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. , SM/11481 | New | NEW SERVICE CONNECTION CHARGES FOR SHIYALIA PWSS | 47/JMD | 11/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1912 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. , SM/11481 | New | NEW SERVICE CONNECTION CHARGES FOR CHOTOKANYADIHA PWSS | 48/JMD | 11/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1913 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. , SM/11481 | New | New Service connection charges. | 46/JMD | 06/02/2024 | 0 | WBSEDCL | 1.26 | 0 | 0 | 0
1914 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. , SM/11481 | New | New service connection charges for Ichhapura | 03/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1915 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. , SM/11481 | New | New service connection charges for Rangamatia | 10/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
1916 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. , SM/11481 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | 340/JHD | 09/03/2023 | 872 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 0 | 0 | 50
1917 | JHARGRAM | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | Material Requisition To Resource Division | 1551/JHD | 07/09/2023 | 0 | Resource Division | 29.71 | 0 | 0 | 0
1918 | JHARGRAM | Jhargram Mechanical Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | New Service connection | 11/JMD | 10/11/2023 | 0 | WBSEDCL | 3.25 | 0 | 0 | 0
1919 | JHARGRAM | Jhargram Mechanical Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | New Service connection | 10/JMD | 10/11/2023 | 0 | WBSEDCL | 3.12 | 0 | 0 | 0
1920 | JHARGRAM | Jhargram Mechanical Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Murabani & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1240/JMD | 26/05/2023 | 180 | R.K. ENTERPRISES | 20.82 | 0 | 0 | 60
1921 | JHARGRAM | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | Laying of Distribution pipe line for MURABANI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block under Jhargram Division, PHE Dte. | 1094/JHD | 14/07/2023 | 90 | SAIKAT DANDAPAT | 61.33 | 0 | 0 | 30
1922 | JHARGRAM | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | Accommodate FHTC ( 1316 nos) under JJM with allied work for MURABANI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1095/JHD | 14/07/2023 | 90 | SAIKAT DANDAPAT | 55.48 | 0 | 0 | 20
1923 | JHARGRAM | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | Construction of Boundary wall and allied works at 1st. Tube well site of Murabani and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 1314/JHD | 05/09/2024 | 30 | HONEY CONSTRUCTION | 3.71 | 0 | 0 | 0
1924 | JHARGRAM | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | Schedule for Construction of Boundary wall and allied works at 1st. Tube well site of Murabani and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 2193/JHD | 22/11/2024 | 30 | MANDAL ENTERPRISE | 8.07 | 0 | 0 | 0
1925 | JHARGRAM | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | Switch room cum chlorine room at different pipe water supply scheme for MURABONI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block under Jhargrm Division, PHE Dte. | 437/JHD | 14/03/2024 | 45 | MANDAL ENTERPRISE | 6.02 | 0 | 0 | 100
1926 | JHARGRAM | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | Sinking of Tube Well , Laying distribution pipe line, under JJM with allied work for MURABANI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_15 of 2022-23 , SL No.-2 ) | 1340/JHD | 10/08/2023 | 90 | BIDYUT KUMAR SANTRA | 93.89 | 0 | 0 | 90
1927 | JHARGRAM | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | Construction of Pump House , 150 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation , under JJM with allied work for MURABANI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_15 of 2022-23 , SL No.-1 ) | 1424/JHD | 23/08/2023 | 210 | SUBRATA DAS | 90.46 | 0 | 0 | 60
1928 | JHARGRAM | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | Trial run for MURABANI AND ADJOINING MOUZAS PWSS scheme within Jhargram Block under Jhargram Division, PHE Dte. for 3 months. | 730/JHD | 02/04/2025 | 91 | DHUMKETU ENGINEERING PRIVATE LIMITED | 1.09 | 0 | 0 | 0
1929 | JHARGRAM | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS , SM/12440 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Murabani and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | 2191/JHD | 22/11/2024 | 30 | S.B.TRADERS | 8.31 | 0 | 0 | 90
1930 | JHARGRAM | Jhargram Division | BANDARBANI AND ADJONING MOUJAS PWSS , SM/12442 | New | Material Requisition To Resource Division | 1537/JHD | 06/09/2023 | 0 | Resource Division | 67.58 | 0 | 0 | 0
1931 | JHARGRAM | Jhargram Mechanical Division | BANDARBANI AND ADJONING MOUJAS PWSS , SM/12442 | New | Qutation for new service connection at Bandarboni T/W-1 water supply scheme. | 89/JMD | 22/03/2024 | 0 | WBSEDCL | 2.87 | 0 | 0 | 0
1932 | JHARGRAM | Jhargram Mechanical Division | BANDARBANI AND ADJONING MOUJAS PWSS , SM/12442 | New | Quotation for new service connection for Bandarboni T/W-2 water supply scheme. | 78/JMD | 29/04/2024 | 0 | WBSEDCL | 2.72 | 0 | 0 | 0
1933 | JHARGRAM | Central Drilling | BANDARBANI AND ADJONING MOUJAS PWSS , SM/12442 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1934 | JHARGRAM | Jhargram Division | BANDARBANI AND ADJONING MOUJAS PWSS , SM/12442 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Bandarbani and its Adjoining Mouzas PWSS , BlockBinpur-I, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | 772/JSD | 09/08/2024 | 89 | SUBHAMAY DANDAPAT | 4.5 | 0 | 0 | 90
1935 | JHARGRAM | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | Material Requisition To Resource Division | 1601/JHD | 08/09/2023 | 0 | Resource Division | 37.58 | 0 | 0 | 0
1936 | JHARGRAM | Jhargram Mechanical Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chandri & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1250/JMD | 26/05/2023 | 180 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.95 | 0 | 0 | 50
1937 | JHARGRAM | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | Accommodate FHTC (2066 nos) under JJM with allied work for CHANDRI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 861/JHD | 08/06/2023 | 726 | ASIS KUMAR SARANGI | 88.73 | 0 | 0 | 85
1938 | JHARGRAM | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Chandri and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | 2267/JHD | 02/12/2024 | 30 | TAPAN KUMAR MANDAL | 7.93 | 0 | 0 | 0
1939 | JHARGRAM | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 3(three) months from the date of 1st registration on daily hire rate basis for 3 (Three) months only (From 01.01.2024 to 31.03.2024) having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer(HQ), Jhargram Division PHE Dte. | 3112/JHD | 30/12/2023 | 91 | TAPAN KUMAR UPADHYAY | 0.51 | 0 | 0 | 100
1940 | JHARGRAM | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | Continuation Work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for May 2024 under Jhargram Division PHE Dte. | 40/JRWS | 30/04/2024 | 31 | JAGOMOHAN SETUA | 0.58 | 0 | 0 | 100
1941 | JHARGRAM | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | Continuation Work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for June 2024 under Jhargram Division PHE Dte. | 103/JRWS | 29/05/2024 | 30 | JAGOMOHAN SETUA | 0.89 | 0 | 0 | 100
1942 | JHARGRAM | Jhargram Mechanical Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | new service connection charges at Chandri T/W-1,water supply scheme | 75/JMD | 29/04/2024 | 0 | WBSEDCL | 9.35 | 0 | 0 | 0
1943 | JHARGRAM | Jhargram Mechanical Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | new service connection charges at Chandri-II water supply scheme | 360/JMD | 20/09/2024 | 0 | WBSEDCL | 5.33 | 0 | 0 | 0
1944 | JHARGRAM | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | Sinking of Tube Well , Pump House , 250 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation under JJM with allied work for CHANDRI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref: 1st Call eNIT_20 of 2022-23 , SL No.-1 and 2nd Call eNIT_07 of 2023-24, SL No.-2 ) | 1832/JHD | 27/10/2023 | 428 | ASIS KUMAR SARANGI | 145.7 | 0 | 0 | 50
1945 | JHARGRAM | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | Construction of boundary wall and Allied works At Chandri, Barabari, Gramohan 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1282/JHD | 03/09/2024 | 120 | ASIS KUMAR SARANGI | 37.46 | 0 | 0 | 55
1946 | JHARGRAM | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | Construction of Pump House , Laying distribution pipe line, Boundary wall, Installation of display Board under JJM with allied work for CHANDRI AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 863/JHD | 08/06/2023 | 457 | ASIS KUMAR SARANGI | 82.54 | 0 | 0 | 80
1947 | JHARGRAM | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS , SM/12715 | New | Laying distribution pipe line under JJM with I allied work for CHANDRI AND IT'S ADJOINING MOUJAS PWSS in I JHARGRAM Block including supply of all labour & materials within! I Jhargram Sub-Division under Jhargram Division, PHE Dte. | 862/JHD | 08/06/2023 | 638 | ASIS KUMAR SARANGI | 71.81 | 0 | 0 | 95
1948 | JHARGRAM | Jhargram Division | NEPURA AND ADJOINING MOUJAS PWSS , SM/12776 | New | Material Requisition To Resource Division | 1546/JHD | 07/09/2023 | 0 | Resource Division | 30.66 | 0 | 0 | 0
1949 | JHARGRAM | Jhargram Division | NEPURA AND ADJOINING MOUJAS PWSS , SM/12776 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Nepura and its Adjoining Mouzas PWSS , Block: - Binpur-I, District: - Jhargram {TYPE - B} (Total length 50 mtr, column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) (2nd Call) [Ref. eNIT 20 OF AE/JSD OF 2023-2024, SL No. 10] | 1087/JSD | 28/11/2024 | 30 | M/S. PRATIMA CONSTRUCTION | 4.05 | 0 | 0 | 0
1950 | JHARGRAM | Jhargram Mechanical Division | NEPURA AND ADJOINING MOUJAS PWSS , SM/12776 | New | Quotation for new sevice connection at Nepura tw-I water supply scheme. | 141/JMD | 24/05/2024 | 0 | WBSEDCL | 9.91 | 0 | 0 | 0
1951 | JHARGRAM | Central Drilling | NEPURA AND ADJOINING MOUJAS PWSS , SM/12776 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1952 | JHARGRAM | Jhargram Division | NEPURA AND ADJOINING MOUJAS PWSS , SM/12776 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Lalgarh GP at Binpur-I Block under jhargram Division PHE Dte. (Phase-I) | 988/JSD | 04/10/2024 | 10 | MANOJ KUMAR MAHATA | 0.92 | 0 | 0 | 0
1953 | JHARGRAM | Jhargram Division | NEPURA AND ADJOINING MOUJAS PWSS , SM/12776 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Nepura GP at Binpur-I Block under jhargram Division PHE Dte. (Phase-I) | 989/JSD | 04/10/2024 | 10 | GOPAL JANA | 0.92 | 0 | 0 | 0
1954 | JHARGRAM | Jhargram Division | UPAR BAGHUASOL AND IT'S ADJOINING MOJAS PWSS , SM/12845 | New | Material Requisition To Resource Division | 1557/JHD | 07/09/2023 | 0 | Resource Division | 44.79 | 0 | 0 | 0
1955 | JHARGRAM | Jhargram Division | UPAR BAGHUASOL AND IT'S ADJOINING MOJAS PWSS , SM/12845 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Upar Baghuasol and its adjoining mouzas Pipe Water Supply Scheme within Gopibalavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 196/GPSD | 11/03/2024 | 30 | DHUMKETU ENGINEERING PRIVATE LIMITED | 4.3 | 0 | 0 | 40
1956 | JHARGRAM | Jhargram Mechanical Division | UPAR BAGHUASOL AND IT'S ADJOINING MOJAS PWSS , SM/12845 | New | Quotation for new service connection at BAGHUASOLE T/W-I water supply scheme. | 11/JMD | 05/04/2024 | 0 | WBSEDCL | 2.7 | 0 | 0 | 0
1957 | JHARGRAM | Jhargram Mechanical Division | UPAR BAGHUASOL AND IT'S ADJOINING MOJAS PWSS , SM/12845 | New | Quotation for new service connection at BAGHUASOLE T/W-II water supply scheme. | 12/JMD | 05/04/2024 | 0 | WBSEDCL | 4.3 | 0 | 0 | 0
1958 | JHARGRAM | Central Drilling | UPAR BAGHUASOL AND IT'S ADJOINING MOJAS PWSS , SM/12845 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1959 | JHARGRAM | Jhargram Division | UPAR BAGHUASOL AND IT'S ADJOINING MOJAS PWSS , SM/12845 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
1960 | JHARGRAM | Jhargram Mechanical Division | KHARBANDI AND ADJOINING MOUZAS PWSS , SM/14133 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I, II & III and making compound lighting arrangement at T/W no. I of Barbaria & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1253/JMD | 26/05/2023 | 180 | SAMARPITA ENGINEERING | 31.73 | 0 | 0 | 0
1961 | JHARGRAM | Jhargram Division | KHARBANDI AND ADJOINING MOUZAS PWSS , SM/14133 | New | Material Requisition To Resource Division | 1558/JHD | 07/09/2023 | 0 | Resource Division | 229.2 | 0 | 0 | 0
1962 | JHARGRAM | Jhargram Division | KHARBANDI AND ADJOINING MOUZAS PWSS , SM/14133 | New | Sinking of Tube Well , Pump House , 350 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation & Accommodate FHTC ( 2994 nos) under JJM with allied work including 02(Two) Years Operation & Maintenanace for KHARBANDI AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1218/JHD | 27/07/2023 | 180 | SIBSANKAR CHOWDHURY | 820.21 | 0 | 0 | 10
1963 | JHARGRAM | Jhargram Mechanical Division | RAJABASA AND ADJOINING MOUJAS PWSS , SM/14184 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I, II, III & IV and making compound lighting arrangement at T/W no. I of Rajabasa & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1255/JMD | 26/05/2023 | 180 | DEBJYOTI BASU | 43.9 | 0 | 0 | 0
1964 | JHARGRAM | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS , SM/14184 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Radhanagar GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | 1846/JHD | 20/09/2024 | 10 | PRINT PREVIEW | 0.92 | 0 | 0 | 100
1965 | JHARGRAM | Central Drilling | RAJABASA AND ADJOINING MOUJAS PWSS , SM/14184 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 91/CDD | 25/04/2024 | 122 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 0 | 0 | 10
1966 | JHARGRAM | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS , SM/14184 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Sapdhara GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | 1847/JHD | 20/09/2024 | 10 | GOPAL JANA | 0.84 | 0 | 0 | 100
1967 | JHARGRAM | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS , SM/14184 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Sardiha GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | 1848/JHD | 20/09/2024 | 10 | MANOJ KUMAR MAHATA | 0.5 | 0 | 0 | 100
1968 | JHARGRAM | Jhargram Mechanical Division | RAJABASA AND ADJOINING MOUJAS PWSS , SM/14184 | New | NEW SERVICE CONNECTION CHARGES AT RAJABASA TW-II PWSS | 322/JMD | 28/08/2024 | 0 | WBSEDCL | 4.04 | 0 | 0 | 0
1969 | JHARGRAM | Jhargram Mechanical Division | RAJABASA AND ADJOINING MOUJAS PWSS , SM/14184 | New | new service connection charges at Rajabasa-I water supply scheme | 361/JMD | 20/09/2024 | 0 | WBSEDCL | 3.37 | 0 | 0 | 0
1970 | JHARGRAM | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS , SM/14184 | New | Construction of Pump House , 100 cum OHR & 250 Cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, Soil investigation & Accommodate FHTC (3051 nos) under JJM with allied work including 02(Two) Years Operation & Maintanance for RAJBAND, PINDRAKULI & RAJABASA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 667/JHD | 26/03/2025 | 180 | ASIS KUMAR SARANGI | 813.53 | 0 | 0 | 0
1971 | JHARGRAM | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS , SM/14184 | New | Laying of extention distribution pipe line for under Rajabasa PWSS in Jhargram block within Jhargram district under Jhargram division P.H.E dte. | 369/JHD | 20/02/2025 | 45 | KOUSIK MONDAL | 4.76 | 0 | 0 | 0
1972 | JHARGRAM | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS , SM/14184 | New | Laying of extention distribution pipe line for Manikpara under Rajabasa PWSS in Jhargram block within Jhargram district under Jhargram Division, PHE Dte. (phase- II) | 370/JHD | 20/02/2025 | 45 | KOUSIK MONDAL | 4.79 | 0 | 0 | 100
1973 | JHARGRAM | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS , SM/14184 | New | Laying of extension distribution pipe line for Manikpara under Rajabasa PWSS in Jhargram block within Jhargram district under Jhargram Division, PHE Dte. (phase- III) | 371/JHD | 20/02/2025 | 45 | KOUSIK MONDAL | 4.76 | 0 | 0 | 100
1974 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Bakra w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16921 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Satkuli Charar and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2501/JMD | 25/08/2023 | 180 | THE BUSINESS ENGINEERS INDIA | 75.12 | 0 | 0 | 0
1975 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Karkatasol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16924 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Rampura and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2777/JMD | 05/09/2023 | 180 | ELECTRO ENTERPRISES | 32.07 | 0 | 0 | 0
1976 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at THAKURPARA AND ADJOINING MOUJA piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16693 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Jangalkhas and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2772/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 77.3 | 0 | 0 | 0
1977 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Simladanga And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16710 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Bandarbani and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2774/JMD | 05/09/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 64.39 | 0 | 0 | 0
1978 | JHARGRAM | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at PARSHULI AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17125 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Uttar Barashol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2498/JMD | 25/08/2023 | 180 | AMITAVA CHAKRABORTY | 75.12 | 0 | 0 | 0
1979 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Uransaol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17127 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Patharnala and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2499/JMD | 25/08/2023 | 180 | RSA ENTERPRISE | 75.13 | 0 | 0 | 0
1980 | JHARGRAM | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram , SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Amlagura W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | 2101/JMD | 03/08/2023 | 90 | MONORANJAN DEY | 1.23 | 0 | 0 | 0
1981 | JHARGRAM | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram , SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no. II under JJM programme at Telidanga W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | 2100/JMD | 03/08/2023 | 90 | JAGANNATH ENTERPRISE | 1.23 | 0 | 0 | 0
1982 | JHARGRAM | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram , SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Natundihi W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | 2096/JMD | 03/08/2023 | 90 | RMD TRADING | 1.23 | 0 | 0 | 0
1983 | JHARGRAM | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram , SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Bhaliadiha W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | 2102/JMD | 03/08/2023 | 90 | DEBJYOTI BASU | 1.23 | 0 | 0 | 0
1984 | JHARGRAM | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram , SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Dakisole SSK W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | 2640/JMD | 29/08/2023 | 90 | BHABANI PRASAD MANNA | 1.23 | 0 | 0 | 0
1985 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram , SM/17950 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tube-well (Replacement) by D.T.H. Method for Augmentation of Source of Dakaisole PWSS under 45 Mini PWSS at Binpur-II Block under Jhargram Sub-Division within Jhargram Division, P.H.E. Dte. | 738JSD | 02/08/2024 | 21 | BIDYUT KUMAR SANTRA | 4.05 | 0 | 0 | 0
1986 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram , SM/17950 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tube-well (Replacement) by D.T.H. Method for Augmentation of Source of Telidanga PWSS under 45 Mini PWSS at Binpur-II Block under Jhargram Sub-Division within Jhargram Division, P.H.E. Dte. | 737/JSD | 02/08/2024 | 21 | BIDYUT KUMAR SANTRA | 4.05 | 0 | 0 | 100
1987 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram , SM/17950 | Augmentation | 01 nos I.E.P (size 10 cum/hr) with platfrom, with masonary drain of Chandabila W/S Scheme(under 45 nos Mini scheme) at Binpur-I Dev. Block under Jhargram Sub division within Jhargram Division ,PHE Dte. | 1091/JHD | 14/07/2023 | 580 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 9.9 | 0 | 0 | 95
1988 | JHARGRAM | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram , SM/17950 | Augmentation | Providing different manpower for construction of (125 mm X 115 mm X 200 mtr) RBTW by DTH Method by departmental rig unit under JJM programme at Dakisole SSK ( T/W-2) water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E Dte. | 81/JMD | 03/01/2023 | 3 | DEBJYOTI BASU | 0.15 | 0 | 0 | 100
1989 | JHARGRAM | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram , SM/17950 | Augmentation | Providing UPVC materials including other drilling related works for construction of (125 mm X 115 mm X 200 mtr) RBTW by DTH Method by departmental rig unit under JJM programme at Dakisole SSK ( T/W-2) water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E Dte. | 80/JMD | 03/01/2023 | 3 | DEBJYOTI BASU | 0.75 | 0 | 0 | 100
1990 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram , SM/17950 | Augmentation | EXTENSION OF PIPELINE INCLUDING LEFTOUT FHTC UNDER JJM IN KUI MINI PWSS(OUT OF 45 NOS MINI PWSS) BLOCK - BINPUR-I WITHIN JHARGRAM SUB DIVISION UNDER JHARGRAM DIVISION PHE DTE. | 473/JSD | 16/05/2025 | 7 | SAURABH KAR | 0.97 | 0 | 0 | 0
1991 | JHARGRAM | Jhargram Division | Retrofitting incl. Augmentation of Source (Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground Water based Lakat Water Supply Scheme at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/17965 | Augmentation | Replacement of distribution pipe line(part) of Lakat w/s scheme at Binpur-I Dev. Block under Jhargram Sub division within Jhargram Division ,PHE Dte. | 875/JHD | 08/06/2023 | 30 | MAA LAXMI ENTERPRISE | 7.96 | 0 | 0 | 0
1992 | JHARGRAM | Jhargram Division | Retrofitting incl. Augmentation of Source (Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground Water based Lakat Water Supply Scheme at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/17965 | Augmentation | 01 nos I.E.P (size 10 cum/hr) with platfrom, blower with compressor room of Lakat W/S Scheme at Binpur-I Dev. Block under Jhargram Sub division within Jhargram Division ,PHE Dte. | 874/JHD | 08/06/2023 | 45 | NEER UDYOG | 12.58 | 0 | 0 | 60
1993 | JHARGRAM | Jhargram Mechanical Division | Retrofitting incl. Augmentation of Source (Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground Water based Lakat Water Supply Scheme at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/17965 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at replacement T/W no. II of Lakat W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | 2107/JMD | 03/08/2023 | 30 | DEBJYOTI BASU | 9.62 | 0 | 0 | 100
1994 | JHARGRAM | Jhargram Division | Retrofitting incl. Augmentation of Source (Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground Water based Lakat Water Supply Scheme at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/17965 | Augmentation | Sinking of 200 X150mm diaX150 mtr. rig bored tubewell(replacement) and interconnection pipeline from propose tubewell to rising main pipeline and construction damaged boudary wall (length-7.5) and colour painting total length boundary wall of Lakat PWSS within Binpur-1 Block, under Jhargram Division, PHE Dte. 2 nd Call (Ref eNIT_28 of 2022-23, SL No.-14) | 1669/JHD | 21/09/2023 | 45 | M/S ANKITA CONSTRUCTION | 7.88 | 0 | 0 | 100
1995 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Sumitrapur w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18025 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Chhahazari humtia and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2771/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 77.3 | 0 | 0 | 0
1996 | JHARGRAM | Jhargram Mechanical Division | Design, development, supply and installation of smart water supply measurement & Monitoring system of Gobindapur w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. , SM/17998 | IOT | Supply & delivery of suitable size of Banner displaying the scheme details of JJM work under Jhargram Mechanical Division, P.H.E. Dte. | 107/W/MMSD(D) | 05/03/2024 | 14 | PRINT PREVIEW | 0.88 | 0 | 0 | 100
1997 | JHARGRAM | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Chandal Bandh PWSS and Installation of IEP & related works to Accommodate FHTC at Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/17966 | Augmentation | Sinking of 250x150mm dia x150mtr rig bored tubewell,const.of pumhouse,const. of brick masonary drain and cons. ground water recharge structure of Chandalbundh W/s schme in Nayagram block under Jhargram District within Jhargram Division,PHE Dte. | 1331/JHD | 10/08/2023 | 45 | BRAJENDRANATH SENAPATI | 17.37 | 0 | 0 | 80
1998 | JHARGRAM | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Chandal Bandh PWSS and Installation of IEP & related works to Accommodate FHTC at Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. , SM/17966 | Augmentation | 01 nos I.E.Ps[size 30 cum/hr] with platfroms,blower with compressor rooms etc. of Chandalbundh w/s scheme. | 1645/JHD | 14/09/2023 | 45 | KANAN CONSTRUCTION ENTERPRISE | 16.58 | 0 | 0 | 10
1999 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Mahapal And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18034 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Chingra and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2776/JMD | 05/09/2023 | 180 | ELECTRO ENTERPRISES | 32.07 | 0 | 0 | 0
2000 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Chorchita piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18035 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Chhahazari humtia and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2771/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 77.3 | 0 | 0 | 0
2001 | JHARGRAM | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18014 | Augmentation | Providing FHTCs (250 nos)in the uncovered pocktes of of Ramagarh W/S scheme(Zone-I & II) under Jhargram Sub Division within Jhargram Division, PHE Dte | 876/JHD | 08/06/2023 | 45 | TAPAS KUMAR JANA | 11.11 | 0 | 0 | 0
2002 | JHARGRAM | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18014 | Augmentation | 03 nos I.E.Ps[size 15 cum/hr.(at propose site under Zone-I),25 cum/hr.(at head work site of Zone-I),30 cum/hr.(at head work site of Zone-II)] with platfroms,blower with compressor rooms,Pump house with blower,compressor room of Ramgarh w/s(Zone-I & II) scheme. | 877/JHD | 08/06/2023 | 60 | MONDAL PRECISION PRIVATE LIMITED | 46.94 | 0 | 0 | 40
2003 | JHARGRAM | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18014 | Augmentation | Repair and renovation of RCC O.H.R (Zone-I)of capacity 50000 gallon with staging height of 20 mtr.with allied works of Ramgarh Piped water supply Scheme at Binpur-I block under Jhargram Sub Division within Jhargram Division. | 570/JHD | 25/04/2023 | 60 | SUNIL DULE | 14.91 | 0 | 0 | 100
2004 | JHARGRAM | Jhargram Mechanical Division | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18014 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at replacement T/W no. I (Zone-II) of Ramgarh W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | 2104/JMD | 03/08/2023 | 30 | A.K. INDUSTRIES | 9.61 | 0 | 0 | 100
2005 | JHARGRAM | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18014 | Augmentation | Sinking of 2 nos of 250 X 150 mm dia. X 150 mtr.rig bored tubewells(1 nos at proposed tubewell site & 1 nos replacement tube well at head work site of Zone-II ), Construction of brick masonry drain of 300 mm X 250 mm inner section (length-20 m),laying of drainage pipe line for backwash water from 3nos IEPs,replacement of distribution pipe line(part), extension of distribution pipeline and providing 50 nos of pending FHTC of Ramgarh W/S(Zone-I & II) scheme at Binpur-I Block under Jhargram Sub Division within Jhargram Division, PHE Dte. | 647/JHD | 11/05/2023 | 90 | SUNIL DULE | 77.74 | 0 | 0 | 60
2006 | JHARGRAM | Jhargram Mechanical Division | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18014 | Augmentation | Supply, delivery, installation of pumping machinery and other electro-mechanical components at replacement T/W no. I of Zone-1 at Ramgarh water supply scheme in Binpur-1 Block under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | 925/JMD | 13/05/2025 | 111 | M/S. CHANDRANATH MUKHERJEE | 3.27 | 0 | 0 | 100
2007 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | 66 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for BHULAVEDA GP (TALPUPUKHURIA, RAGHUNATHPUR, GIDIGHATI, SHIYARBINDA PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-2) | 1834/JHD | 27/10/2023 | 484 | SUNIL DULE | 108.48 | 0 | 0 | 80
2008 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | Four numbers (4) of yield test process need to be done at Chirugara urf Kuilapal & Chandbila of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 498/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
2009 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | Four numbers (4) of yield test process need to be done at Baksol and Madhupur Mouza of Bhulaveda GP of Binpur II Block, under Jhargram division, PHE Dt | 494/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
2010 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | Four numbers (4) of yield test process need to be done at Talpukuhuria and Pukhuria Mouza of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 496/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
2011 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | Four numbers (4) of yield test process need to be done at Charak pahari and Murgadabar Mouza of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 495/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
2012 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | Four numbers (4) of yield test process need to be done at Kusbhula & Majugara of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte | 499/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
2013 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | Four numbers (4) of yield test process need to be done at Bhula dhara and Gochgiri Mouza of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 497/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
2014 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | New Service Connection Charges for Chirugara Talpupukhuria & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2015 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | New Service Connection Charges for Charakpahari Talpupukhuria & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2016 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | New Service Connection Charges for Madhupur, Talpupukhuria & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2017 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | New Service Connection Charges for Chandabila, Talpupukhuria & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2018 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | New Service Connection Charges for Baksol, Talpupukhuria & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2019 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | New Service Connection Charges for Talpukhuria, Talpupukhuria & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2020 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | New Service Connection Charges for Gochgiri, Talpupukhuria & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2021 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | New Service Connection Charges for Kushbhula Talpupukhuria & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2022 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | 33 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for BHULAVEDA GP ( TALPUPUKHURIA ,RAGHUNATHPUR ,GIDIGHATI ,SHIYARBINDA PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-2 ) | 1531/JHD | 06/09/2023 | 602 | ASIS KUMAR SARANGI | 910.58 | 0 | 0 | 80
2023 | JHARGRAM | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS , SM/17932 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | 378/JRWS | 31/01/2024 | 30 | MESAURE LAND | 0.82 | 0 | 0 | 50
2024 | JHARGRAM | Jhargram Division | CHAKADOBA AND ADJOINING MOUJAS PWSS , SM/17596 | New | 17 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for BANASPAHARI GP ( CHAKADOBA, KHARIYARATA, KALADABAR PWSS ) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-1 ) | 1657/JHD | 19/09/2023 | 665 | MONDAL PRECISION PRIVATE LIMITED | 508.47 | 0 | 0 | 41
2025 | JHARGRAM | Jhargram Division | CHAKADOBA AND ADJOINING MOUJAS PWSS , SM/17596 | New | New Service Connection Charges for Chakadoba PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2026 | JHARGRAM | Jhargram Division | CHAKADOBA AND ADJOINING MOUJAS PWSS , SM/17596 | New | 34 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for BANASPAHARI GP (CHAKADOBA, KHARIYARATA,KALADABAR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_38 of 2022-23, SL No.-1) | 1668/JHD | 21/09/2023 | 543 | NEER UDYOG | 55.86 | 0 | 0 | 60
2027 | JHARGRAM | Jhargram Division | CHAKADOBA AND ADJOINING MOUJAS PWSS , SM/17596 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | 381/JRWS | 31/01/2024 | 30 | CARTO | 0.82 | 0 | 0 | 100
2028 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Dhamro Water Supply Scheme to Accommodate FHTC under JJM at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/17959 | Augmentation | Extension of distribution pipeline and providing the pending FHTCs at Binpur-I block under Dhamro PWSS under Jhargram Sub-division within Jhargram Division,PHE Dte. | 1096/JHD | 14/07/2023 | 45 | SAIKAT DANDAPAT | 23.97 | 0 | 0 | 80
2029 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Dhamro Water Supply Scheme to Accommodate FHTC under JJM at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/17959 | Augmentation | construction of boundary wall of 1st tubewell site,repairing boundary wall of 2nd tubewell site at Binpur-I block under Dhamro PWSS under Jhargram Sub-division within Jhargram Division,PHE Dte. | 1397/JHD | 18/08/2023 | 45 | RABINDRANATH MANDAL | 11.03 | 0 | 0 | 90
2030 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Dahatmal w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17051 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Darukuli and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2632/JMD | 29/08/2023 | 180 | AMITAVA CHAKRABORTY | 31.3 | 0 | 0 | 0
2031 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at KAPGARI AND IT'S ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17056 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Parihati and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2773/JMD | 05/09/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 77.27 | 0 | 0 | 0
2032 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Brahmandana w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17064 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Champasol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2500/JMD | 25/08/2023 | 180 | MEGA SOLAR ENERGY | 75.09 | 0 | 0 | 0
2033 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | Construction of OHR(200 Cum) and Soil Investigation for augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | 1344/JHD | 10/08/2023 | 270 | M.RAHAMAN CONSTRUCTION | 81.74 | 0 | 0 | 0
2034 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | Connection to Tail End Habitation from Clear Water Rising Main of Bamundiha Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram District under Jhargram Division, P.H.E. Dte. | 969/JSD | 10/11/2023 | 21 | SUNIL DULE | 3.79 | 0 | 0 | 100
2035 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | Laying of Distribution pipe line for Augmentation of Ground based Barasukjora Pond Based PWSS in Binpur-II with in Jhargram District under Jhargram Division, PHE Dte. | 1143/JHD | 21/07/2023 | 30 | SAIKAT DANDAPAT | 18.31 | 0 | 0 | 100
2036 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | REPAIRING OF EXISTING F.H.T.C AT MOUZA SHYAMPUR UNDER BARASUKJORA W/S SCHEME (ZONE-II) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE (PHASE-II) | 1081/JSD | 27/11/2024 | 14 | SAIKAT DANDAPAT | 0.96 | 0 | 0 | 0
2037 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | REPAIRING OF EXISTING F.H.T.C AT MOUZA SHYAMPUR UNDER BARASUKJORA W/S SCHEME (ZONE-II) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE (PHASE-I) | 1080/JSD | 27/11/2024 | 14 | SAIKAT DANDAPAT | 0.96 | 0 | 0 | 0
2038 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | Re-Laying of Distribution Line Orgonda to Biridanga Village (Orgonda Mouza) under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-II) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. | 149/JHD | 29/01/2024 | 15 | SAIKAT DANDAPAT | 4.76 | 0 | 0 | 100
2039 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | Uncovered Habitation of Barasukjora Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Phase - I) | 739/JSD | 02/08/2024 | 21 | ASSOCIATED ENGINEERS & TRADERS | 4.7 | 0 | 0 | 100
2040 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | Uncovered Habitation of Barasukjora Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Phase - II) | 740/JSD | 02/08/2024 | 21 | ASSOCIATED ENGINEERS & TRADERS | 4.82 | 0 | 0 | 100
2041 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | Uncovered Habitation of Barasukjora Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Phase - IV) | 742/JSD | 02/08/2024 | 21 | ASSOCIATED ENGINEERS & TRADERS | 4.67 | 0 | 0 | 100
2042 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | Uncovered Habitation of Barasukjora Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Phase - III) | 741/JSD | 02/08/2024 | 21 | ASSOCIATED ENGINEERS & TRADERS | 1.73 | 0 | 0 | 100
2043 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | Repair, Renewing of existing water storage pond, Approach Road towards WTP also inspection Road round the pond embankment & Construction of Boundary wall on periphery of down stream toe wall cum guard wall of existing water storage pond under Augmentation of Barasukjora Surface water based P.W.S.S, Block: - Binpur - II, District: - Jhargram, under Jhargram Division, P.H.E. Dte. | 2009/JHD | 01/12/2023 | 425 | GEE BEE NIRMAN CO. PRIVATE LIMITED | 1590.58 | 0 | 0 | 40
2044 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | Laying Left Out Habitation pipeline of Bamundiha (Mahuldanga) Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Part:I) | 275/JSD | 21/03/2025 | 14 | SAIKAT DANDAPAT | 3.8 | 0 | 0 | 0
2045 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | REPAIRING OF EXISTING F.H.T.C. AT BAMUNDIHA VILLAGE UNDER BARASUKJORA W/S SCHEME (ZONE-I) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE (Phase: I) | 248/JSD | 17/03/2025 | 14 | SAIKAT DANDAPAT | 3.96 | 0 | 0 | 0
2046 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | LAFT OUT HOUSEHOLD FOR ACCOMODATE FUNCTIONAL HOUSE TAP CONNECTION (F.H.T.C.) & REPAIRING OF EXISTING F.H.T.C. AT BARASUKJORA VILLAGE UNDER BARASUKJORA W/S SCHEME (ZONE-I) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE (Phase: I) | 233/JSD | 12/03/2025 | 14 | SAIKAT DANDAPAT | 4.4 | 0 | 0 | 0
2047 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | Laying Damage pipeline of Barasukjora; & Kharpal Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. | 274/JSD | 21/03/2025 | 14 | SAIKAT DANDAPAT | 4.23 | 0 | 0 | 0
2048 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | REPAIRING OF EXISTING F.H.T.C. AT BARASUKJORA VILLAGE UNDER BARASUKJORA W/S SCHEME (ZONE-I) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE (Phase: II) | 234/JSD | 12/03/2025 | 14 | SAIKAT DANDAPAT | 2 | 0 | 0 | 0
2049 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. , SM/18435 | Augmentation | Laying Left Out Habitation pipeline of Bamundiha (Mahuldanga) Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Part:II) | 276/JSD | 21/03/2025 | 14 | SAIKAT DANDAPAT | 3.5 | 0 | 0 | 0
2050 | JHARGRAM | Jhargram Division | SHALUKA AND ADJOINING MOUJAS PWSS , SM/12520 | New | Material Requisition To Resource Division | 1549/JHD | 07/09/2023 | 0 | Resource Division | 33.68 | 0 | 0 | 0
2051 | JHARGRAM | Jhargram Division | SHALUKA AND ADJOINING MOUJAS PWSS , SM/12520 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Shaluka and its Adjoining Mouzas PWSS , Block: - Binpur-I, District: - Jhargram {TYPE - B} (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 775/JSD | 09/08/2024 | 30 | CONSTRUCTURE | 4.81 | 0 | 0 | 0
2052 | JHARGRAM | Jhargram Mechanical Division | SHALUKA AND ADJOINING MOUJAS PWSS , SM/12520 | New | Quotation for new service connection at Shaluka TW-I water supply scheme. | 184/JMD | 11/06/2024 | 0 | WBSEDCL | 2.92 | 0 | 0 | 0
2053 | JHARGRAM | Central Drilling | SHALUKA AND ADJOINING MOUJAS PWSS , SM/12520 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2054 | JHARGRAM | Jhargram Division | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS , SM/12359 | New | Material Requisition To Resource Division | 1504/JHD | 05/09/2023 | 0 | Resource Division | 34.35 | 0 | 0 | 0
2055 | JHARGRAM | Jhargram Mechanical Division | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS , SM/12359 | New | New service connection charges | 15/JMD/PFMS/APR | 27/07/2023 | 0 | WBSEDCL | 2.89 | 0 | 0 | 0
2056 | JHARGRAM | Jhargram Mechanical Division | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS , SM/12359 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dumri Nakrasuli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2264/JMD | 09/08/2023 | 180 | ORIENTAL ENGINEERING CO. | 22.08 | 0 | 0 | 55
2057 | JHARGRAM | Jhargram Division | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS , SM/12359 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House , & Providing Functional Household Tap Connection (2568 Nos), etc. For DUMRI NAKRASULI, JAKUA Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 444/JHD | 23/03/2023 | 923 | MASUM ALI KHAN | 772.82 | 0 | 0 | 65
2058 | JHARGRAM | Central Drilling | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS , SM/12359 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2059 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Kuldiha PWSS under Nayagram Block. , SM/09386 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Kuldiha Water Supply Scheme Block -Nayagram in the District of Jhargram. | 225/JHD | 16/02/2023 | 45 | GOBINDA MAITY | 20.73 | 0 | 0 | 1
2060 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Kuldiha PWSS under Nayagram Block. , SM/09386 | Retrofitting | New service connection charges | BP-2022-23-156 | 01/03/2023 | 0 | WBSEDCL | 1.12 | 0 | 0 | 0
2061 | JHARGRAM | Jhargram Division | MAHULBANI AND ADJOINING MOUJAS PWSS , SM/12534 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Mahulboni and its adjoining mouzas Pipe Water Supply Scheme within Gopibalavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 194/GPSD | 11/03/2024 | 30 | MMS CONSTRUCTIONS PVT.LTD. | 4.24 | 0 | 0 | 100
2062 | JHARGRAM | Jhargram Division | MAHULBANI AND ADJOINING MOUJAS PWSS , SM/12534 | New | Material Requisition To Resource Division | 423/JHD | 13/03/2024 | 0 | Resource Division | 47.81 | 0 | 0 | 0
2063 | JHARGRAM | Jhargram Mechanical Division | MAHULBANI AND ADJOINING MOUJAS PWSS , SM/12534 | New | Qutation for new service connection at MAHULBONI TW-II water supply scheme. | 96/JMD | 08/05/2024 | 0 | WBSEDCL | 10.75 | 0 | 0 | 0
2064 | JHARGRAM | Jhargram Mechanical Division | MAHULBANI AND ADJOINING MOUJAS PWSS , SM/12534 | New | Quotation for Mahulboni T/W - I water supply scheme. | 72/JMD | 15/03/2024 | 0 | WBSEDCL | 4.3 | 0 | 0 | 0
2065 | JHARGRAM | Central Drilling | MAHULBANI AND ADJOINING MOUJAS PWSS , SM/12534 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2066 | JHARGRAM | Jhargram Division | MAHULBANI AND ADJOINING MOUJAS PWSS , SM/12534 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
2067 | JHARGRAM | Jhargram Division | MAHULBANI AND ADJOINING MOUJAS PWSS , SM/12534 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Kharikamathani GP at Nayagram Block under jhargram Division PHE Dte. (Phase-I) | 644/GPSD | 19/11/2024 | 10 | PRINT PREVIEW | 0.67 | 0 | 0 | 100
2068 | JHARGRAM | Jhargram Division | MAHULBANI AND ADJOINING MOUJAS PWSS , SM/12534 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Malam GP at Nayagram Block under jhargram Division PHE Dte. (Phase-I) | 645/GPSD | 19/11/2024 | 10 | GOPAL JANA | 0.92 | 0 | 0 | 100
2069 | JHARGRAM | Jhargram Division | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS , SM/12448 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Chhahazari Humtia and its adjoining mouzas Pipe Water Supply Scheme within Gopibalavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 193/GPSD | 11/03/2024 | 30 | BISHNU PADA NANDI | 4.28 | 0 | 0 | 95
2070 | JHARGRAM | Jhargram Division | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS , SM/12448 | New | Material Requisition To Resource Division | 418/JHD | 13/03/2024 | 0 | Resource Division | 20.5 | 0 | 0 | 0
2071 | JHARGRAM | Jhargram Mechanical Division | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS , SM/12448 | New | New Service Connection Charges for Chhayhazari Humita tw-I PWSS | 37/JMD | 01/02/2024 | 0 | WBSEDCL | 4.24 | 0 | 0 | 0
2072 | JHARGRAM | Central Drilling | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS , SM/12448 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2073 | JHARGRAM | Jhargram Division | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS , SM/12448 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
2074 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12347 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Gobindapur & adjoining moujas piped water supply scheme, Block- Gopiballavpur-II in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1234/JMD | 26/05/2023 | 180 | GOENKA ENTERPRISE | 20.77 | 0 | 0 | 0
2075 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12347 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 150 cum and staging height 20 mtr. as per approved drawing with allied works of GOBINDAPUR & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for GOPIBALLAVPUR-II Block, District: - Jhargram. | 2050/JHD | 07/12/2023 | 210 | ABJ ENGINEERING | 71.52 | 0 | 0 | 0
2076 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12347 | New | Material Requisition To Resource Division | 1548/JHD | 07/09/2023 | 0 | Resource Division | 36.36 | 0 | 0 | 0
2077 | JHARGRAM | Central Drilling | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12347 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 2104/CDD | 09/02/2024 | 182 | JHARGRAM SPV PRIVATE LIMITED | 110.72 | 0 | 0 | 10
2078 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12347 | New | Soil Investigation and determination of safe bearing capacity and other relevant parameters of soil for construction of Proposed O.H.R. of Gobindapur and Bhamal PWSS at Gopiballavpur-II Block under Jhargram Division, P.H.E. Dte. | 1085/JSD | 28/11/2024 | 14 | MOYTEC | 1.34 | 0 | 0 | 0
2079 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12347 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Gobindapur and its Adjoining Mouzas PWSS , Block Gopiballavpur-II, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | 787/JSD | 09/08/2024 | 30 | SUJOY RANJAN BHOWMICK | 4.81 | 0 | 0 | 0
2080 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12347 | New | Quotation for new service connection at GOBINDAPUR T/W -I water supply scheme. | 99/JMD | 08/05/2024 | 0 | WBSEDCL | 3.29 | 0 | 0 | 0
2081 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12347 | New | Quotation for new service connection at GOBINDDPUR TW-II water supply scheme. | 98/JMD | 08/05/2024 | 0 | WBSEDCL | 2.73 | 0 | 0 | 0
2082 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12347 | New | Sinking of Tube Well , Pump House, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board & Accommodate FHTC(6721 nos) including 02(Two) Years Operation & Maintenance under JJM with allied work for DHADANGIRI, GOBINDAPUR, JUNSOLA, PETBINDHI & MAHAPAL PWSS in Gopiballavpur-II Block including supply of all labour & materials within Gopiballavpur Sub-Division under Jhargram Division, PHE Dte. | 1373/JHD | 16/08/2023 | 465 | M/S. EL-CON | 1574.44 | 0 | 0 | 0
2083 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09378 | Augmentation | Purchasing of materials for the Retrofitting to Accommodate FHTC incl. Augmentation of Source under UM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-1I Block within Jhargram District under Jhargram Division. PHE Dte. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.05 | 0 | 0 | 0
2084 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09378 | Augmentation | Purchasing of Materials. | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.05 | 0 | 0 | 0
2085 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09378 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tubwell (Replacement) by DTH Method for Augmentation of Source of Tamajuri PWSS under Jhargram Division P.H.E. Dte. | BP-2021-22-471 | 16/03/2022 | 0 | BIDYUT KUMAR SANTRA | 3.62 | 0 | 0 | 0
2086 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09378 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Tamajuri PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | BP-2021-22-408 | 23/02/2022 | 0 | LEMNISCATE | 2.28 | 0 | 0 | 0
2087 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09378 | Augmentation | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.05 | 0 | 0 | 0
2088 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09378 | Augmentation | Material Requisition To Resource Division | 2161/MD | 17/12/2021 | 0 | Resource Division | 1.44 | 0 | 0 | 0
2089 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09378 | Augmentation | Sinking tubewell (125 mm X 115 mm X 200 mtr) by DTH / Combination Method with supply and delivery of UPVC consumables with drilling related works at Tamajuri at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 3078/JMD | 14/03/2024 | 2 | SUJOY RANJAN BHOWMICK | 1.27 | 0 | 0 | 100
2090 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09378 | Augmentation | Supply of Fuel and lubricants for KLR/DR/DTH-500 for the month of March 2023 during construction of RBT works under JMD,PHE dte | 135/JMD | 24/05/2024 | 0 | SURAJ SERVICE STATION | 0.43 | 0 | 0 | 0
2091 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. , SM/09378 | Augmentation | Extension of Distribution pipe line and FHTC work for Augmentation of Ground based Tamajuri PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | 178/MD | 01/02/2022 | 1259 | WATER LINK | 48.15 | 0 | 0 | 50
2092 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09379 | Augmentation | Material Requisition To Resource Division | 2395/MD | 24/11/2022 | 0 | Resource Division | 36.34 | 0 | 0 | 0
2093 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09379 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Belaberia PWSS in Gopi-IIBlock for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | BP-2021-22-458 | 11/03/2022 | 0 | LEMNISCATE | 3.01 | 0 | 0 | 0
2094 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09379 | Augmentation | Material Requisition To Resource Division | 498/MD | 15/03/2022 | 0 | Resource Division | 15.18 | 0 | 0 | 0
2095 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09379 | Augmentation | Supply delivery of Different dia CIDF S/V for the work of ¿Augmentation of Ground Water Based Water Supply Scheme for Beliabera to Accommodate FHTC in Block Gopiballavpur - II under Jhargram Sub Division within Jhargram Division, PHE Dte. | 57/GPSD | 16/09/2022 | 15 | PROVAT KUMAR DE | 2.63 | 0 | 0 | 100
2096 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09379 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft ) of capacity 150 cum and staging height 20 mtr. as per approved drawing (No:- PC-I /OHR /10/2012) including supply of all labour & materials for Augmentation of Ground Based Belaberya PWSS in Gopiballavpur -II Block within Jhargram District under Jhargram Division, PHE Dte. | 874/MD | 10/05/2022 | 180 | SUBRATA DAS | 188.22 | 0 | 0 | 77
2097 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09379 | Augmentation | Supply, delivery, installation, commissioning electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Beliaberya W/S scheme under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | 2094/JMD | 03/08/2023 | 30 | S.S. GHORAI | 13.82 | 0 | 0 | 90
2098 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09379 | Augmentation | Repairing approach road from headwork side of Beliabera PWSS to main road under Gopiballavpur-II block within Jhargram Sub-Division of Jhargram Division, PHE DTE. (Lenght-220 m) . (2nd Call) [Ref. eNIT 04 OF AE/JSD OF 2024-2025, SL No. 03] | 1070/JSD | 26/11/2024 | 14 | SUBRATA DAS | 3.11 | 0 | 0 | 0
2099 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09379 | Augmentation | laying of raising main with interconnection with tube wells ,bypass connection ,road crosssing work & pending distribution main[Node 1 to Node 3,Node 5 to Node 10,Node 3 to Node 8(part)] of augmentation of ground water based water Beliabera PWSS under Gopiballavpur-II Block within Jhargram Division,P.H.E. Dte. | 884/JHD | 08/06/2023 | 30 | SUBRATA DAS | 16.48 | 0 | 0 | 100
2100 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09379 | Augmentation | Sinking of 250 x 150 mm dia. x 150 mtr.rig bored tubewell at Head worksite for Augmentation of Beliabera W/S Scheme in Gopiballavpur-II Block within Jhargram District under Jhargram Division, P.H.E. Dte. | 1949/JHD | 22/11/2023 | 15 | S.R. ENTERPRISE | 7.01 | 0 | 0 | 100
2101 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09379 | Augmentation | Supply, delivery, installation of electro-mechanical components for tube well no. II of Beliabera water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | 113/W/MMSD(D) | 12/03/2024 | 30 | S.S. GHORAI | 1.39 | 0 | 0 | 100
2102 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09379 | Augmentation | Supply, delivery & installation of various electro-mechanical accessories at tube well no.-I of Beliabera w/s scheme in the dist. of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 2989/JMD | 13/03/2024 | 30 | S.S. GHORAI | 1.39 | 0 | 0 | 100
2103 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09382 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Khamar PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | BP-2021-22-406 | 23/02/2022 | 0 | M/S R. DUTTA & CO | 1.34 | 0 | 0 | 0
2104 | JHARGRAM | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09382 | Augmentation | Extension of distribution pipe line and FHTC work for Augmentation of Ground Based Khamar PWSS to accommodate FHTC in Binpur-II block within Jhargram district under Jhargram Division, PHE Dte. | 612/MD | 04/04/2022 | 21 | M/S. SANKAR KUMAR NAG | 10.11 | 0 | 0 | 0
2105 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09382 | Augmentation | Supply, delivery, installation, commissioning of submersible pumping machinery and other Electro Mechanical accessories for two (02) nos. newly sunk Rig bore Tube well at Khamar piped water supply scheme at Binpur -II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 4212/JMD | 28/12/2022 | 30 | AMIT DAS | 7.38 | 0 | 0 | 0
2106 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09382 | Augmentation | Sinking of (200 mmX 165 mm) RBTW by DTH Method at Khamar PWSS, tube well no.-1 of Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 593/JMD | 23/12/2021 | 4 | SUJOY RANJAN BHOWMICK | 0.62 | 0 | 0 | 0
2107 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09382 | Augmentation | Extension of distribution pipe line and FHTC work for Augmentation of Ground Based Khamar PWSS to accommodate FHTC in Binpur-II block within Jhargram district under Jhargram Division, PHE Dte. | 612/MD | 04/04/2022 | 21 | M/S. SANKAR KUMAR NAG | 10.11 | 0 | 0 | 1
2108 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09382 | Augmentation | Balance Work of Augmentation of Khamar Piped Water Supply Scheme in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. | 648/JSD | 13/07/2023 | 30 | SAUBHIK KUMAR NAG | 4.84 | 0 | 0 | 100
2109 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09382 | Augmentation | New service connection charges | 17/JMD/PFMS/MAR | 06/03/2023 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2110 | JHARGRAM | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09382 | Augmentation | SWITCH ROOM SIZE (3.6 MTRX3.00 MTR) WITHOUT SANITATION AT KHAMAR W/S SCHEME UNDER BINPUR-II BLOCK WITHIN JHARGRAM DIVISION, P.H.E. DTE. | 737/JSD | 16/08/2023 | 30 | ANJAN KUMAR MAHATA | 2.91 | 0 | 0 | 100
2111 | JHARGRAM | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/09382 | Augmentation | Supply, delivery, installation, commissioning of Electro Mechanical accessories for newly constructed Pump house for newly sunk Rig bore T/W at Khamar piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 2110/JMD | 03/08/2023 | 60 | DEBJYOTI BASU | 4.46 | 0 | 0 | 100
2112 | JHARGRAM | Jhargram Division | Water Supply System at Anganwadi Centers(220 nos.) within Gopiballavpur-I Block under Jhargram District. , SM/10351 | Anganwadi | Water Supply Arrangement for 220 Nos. Anganwadi Centers At Gopiballavpur-I Block in Jhargram District under Jhargram Division PHE Dte. | 589/JHD | 02/05/2023 | 618 | M/S A.R ENTERPRISE | 585.77 | 0 | 0 | 20
2113 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) in Nayagram Block under Jhargram district. , SM/10439 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) Block - Nayagram in the District of Jhargram | 201/JSD | 04/04/2022 | 21 | DHUMKETU ENGINEERING PRIVATE LIMITED | 4.05 | 0 | 0 | 0
2114 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) in Nayagram Block under Jhargram district. , SM/10439 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) Block - Nayagram in the District of Jhargram | 201/JSD | 04/04/2022 | 21 | DHUMKETU ENGINEERING PRIVATE LIMITED | 4.05 | 0 | 0 | 100
2115 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District , SM/10492 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Dohijuri PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 78/JSD | 25/06/2021 | 14 | INDRANIL DUTTA & ASSOCIATES | 3.31 | 0 | 0 | 1
2116 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District , SM/10492 | Augmentation | Restoration work for laying of pipeline along Dahijuri Binpur Silda Hatiari Road & Dahijuri-Lalgarh Road due to distribution pipeline of ground wter based Dahijuri PWSS under Jhargram Division ,PHE Dte | BP-2023-24-35 | 15/05/2023 | 0 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 8.6 | 0 | 0 | 0
2117 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District , SM/10492 | Augmentation | Supply, delivery & installation of various electro-mechanical accessories for repairing & rejuvenation of pump house no.-II of Dahijuri w/s scheme in the dist. of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 2988/JMD | 13/03/2024 | 30 | SUJOY RANJAN BHOWMICK | 9.57 | 0 | 0 | 50
2118 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District , SM/10492 | Augmentation | Laying of additional distribution pipe line for augmentation of ground water based Dahijuri PWSS to accommodate FHTC in Binpur-I Block within Jhargram district under Jhargram Division, PHE Dte. | 744/JSD | 17/08/2023 | 45 | JMC, PRO. CHIRANJIT NANDI | 2.36 | 0 | 0 | 100
2119 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District , SM/10492 | Augmentation | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Dahijuri and adjacent water supply schemes for ongoing Solarisation works for the purpose of Geotagging under Jhargram Mechanical Division, P.H.E. Dte. | 3061/JMD | 14/03/2024 | 15 | MUKHERJEE ART CENTRE | 9.68 | 0 | 0 | 100
2120 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District , SM/10492 | Augmentation | Restoration work for laing pipeline along with Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District | BP-2023-24-389 | 10/01/2024 | 0 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 8.6 | 0 | 0 | 0
2121 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District , SM/10492 | Augmentation | Laying of Distribution pipe line and FHTC work for Augmentation of Ground water based Water Supply for Dahijuri to accommodate FHTC under Binpur-I Block within Jhargram District under Jhargram Division, PHE De. | 619/JHD | 25/11/2022 | 829 | UTTAM KUMAR DAS | 128.45 | 0 | 0 | 80
2122 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District , SM/10492 | Augmentation | SPECIAL REPAIR AND RENOVATION OF PUMP HOUSE NO I & II FOR DAHIJURI PWSS WITHIN JHARGRAM SUB DIVISION UNDER JHARGRAM DIVISION, PHE DTE. | 434/JSD | 08/05/2025 | 7 | J.S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
2123 | JHARGRAM | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Sinking of Tube Well under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23, SL No.-1) | 1137/JHD | 06/08/2024 | 30 | PALASH MANDAL | 16.67 | 0 | 0 | 0
2124 | JHARGRAM | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Constructions of Pump House under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref: 1st Call eNIT_35 of EE/JHD of 2022-23, SL No.-2, 2nd Call eNIT_11 of EE/JHD of 2023-24, SL No.-3) | 435/JHD | 14/03/2024 | 90 | MILON MAITY | 12.39 | 0 | 0 | 10
2125 | JHARGRAM | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Supply & Delivery of CI&DI Specials for laying of Rising Main including interconnection between Tube Well and Raising Main and OHR for Bhila and its adjoining mouzas Water Supply Scheme within Gopiballavpur-I Block under Gopiballavpur Sub Division of Jhargram Division, P.H.E.Dte. | 685/GPSD | 02/12/2024 | 21 | A R CONSTRUCTION | 2.31 | 0 | 0 | 95
2126 | JHARGRAM | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Material Requisition To Resource Division | 426/JHD | 13/03/2024 | 0 | Resource Division | 20.49 | 0 | 0 | 0
2127 | JHARGRAM | Jhargram Mechanical Division | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Quotation for Bhila T/W - I water supply scheme. | 73/JMD | 15/03/2024 | 0 | WBSEDCL | 2.86 | 0 | 0 | 0
2128 | JHARGRAM | Jhargram Mechanical Division | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Quotation for Bhila T/W - 2 water supply scheme. | 74/JMD | 15/03/2024 | 0 | WBSEDCL | 3.96 | 0 | 0 | 0
2129 | JHARGRAM | Central Drilling | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2130 | JHARGRAM | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Laying distribution pipe line under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1857/JHD | 31/10/2023 | 180 | ONKAR ENTERPRISE | 174.38 | 0 | 0 | 95
2131 | JHARGRAM | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Rising main pipe line, Interconnection pipe line, Laying of Distribution pipe line, Installation of display Board, FHTC I 497 under JJM with allied work for BHILA AND IT'S ADJOINING I MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT 35 of 2022-23, SL No.-4) | 1865/JHD | 01/11/2023 | 90 | R.CONSTRUCTION | 59.84 | 0 | 0 | 95
2132 | JHARGRAM | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Supplying and Delivery of Different dia CIDF Sluice Valve, including Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Bhila & its Adjoining Mouzas PWSS in Gopiballavpur-I Block under Jhargram Division PHE Dte. | 42/JHD | 07/01/2025 | 45 | ONKAR ENTERPRISE | 8.34 | 0 | 0 | 45
2133 | JHARGRAM | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Bhila, Gohalbura and Barasol and its adjoining Mouzas , Block Gopiballavpur-I, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 313/JHD | 12/02/2025 | 60 | ANUSKA ENTERPRISE | 43.87 | 0 | 0 | 0
2134 | JHARGRAM | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Constructions of 150 cum OHR, soil investigation under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1653/JHD | 15/09/2023 | 240 | KANAN CONSTRUCTION ENTERPRISE | 73.16 | 0 | 0 | 95
2135 | JHARGRAM | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS , SM/12452 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Bhila and its adjoining mouzas Pipe Water Supply Scheme within Gopiballavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 201/GPSD | 11/03/2024 | 30 | J.S.S. ENTERPRISE | 4.3 | 0 | 0 | 10
2136 | JHARGRAM | Jhargram Division | TILABANI AND ADJOINING MOUJAS PWSS , SM/12530 | New | Material Requisition To Resource Division | 1540/JHD | 06/09/2023 | 0 | Resource Division | 45.04 | 0 | 0 | 0
2137 | JHARGRAM | Jhargram Mechanical Division | TILABANI AND ADJOINING MOUJAS PWSS , SM/12530 | New | New service connection | 84/JMD | 12/02/2024 | 0 | WBSEDCL | 3.14 | 0 | 0 | 0
2138 | JHARGRAM | Jhargram Mechanical Division | TILABANI AND ADJOINING MOUJAS PWSS , SM/12530 | New | New service connection | 85/JMD | 12/02/2024 | 0 | WBSEDCL | 3.68 | 0 | 0 | 0
2139 | JHARGRAM | Jhargram Mechanical Division | TILABANI AND ADJOINING MOUJAS PWSS , SM/12530 | New | Quotation for new service connection at Tilaboni TW-III water supply scheme. | 187/JMD | 11/06/2024 | 0 | WBSEDCL | 4.43 | 0 | 0 | 0
2140 | JHARGRAM | Central Drilling | TILABANI AND ADJOINING MOUJAS PWSS , SM/12530 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2141 | JHARGRAM | Jhargram Division | PARSHULI AND ADJOINING MOUJAS PWSS , SM/12531 | New | Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpir-I_2_1_C under Jhargram Division in the District of Jhargram. | 346/JHD | 28/09/2022 | 120 | BISHNU PADA NANDI | 22.38 | 0 | 0 | 1
2142 | JHARGRAM | Jhargram Division | PARSHULI AND ADJOINING MOUJAS PWSS , SM/12531 | New | Material Requisition To Resource Division | 1533/jhd | 06/09/2023 | 0 | Resource Division | 27.63 | 0 | 0 | 0
2143 | JHARGRAM | Jhargram Mechanical Division | PARSHULI AND ADJOINING MOUJAS PWSS , SM/12531 | New | New Service connection | 11/JMD | 28/09/2023 | 0 | WBSEDCL | 2.96 | 0 | 0 | 0
2144 | JHARGRAM | Jhargram Mechanical Division | PARSHULI AND ADJOINING MOUJAS PWSS , SM/12531 | New | New Service connection | 12/JMD | 28/09/2023 | 0 | WBSEDCL | 4.71 | 0 | 0 | 0
2145 | JHARGRAM | Jhargram Division | PARSHULI AND ADJOINING MOUJAS PWSS , SM/12531 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line,Installation of display Board, soil investigation ,including 02(Two) Years Operation & Maintenance & Accommodate FHTC (1226 nos) under JJM with allied work for Parshuli PWSS in Jamboni Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHEDte. | 346/JHD | 10/03/2023 | 724 | ASIS KUMAR SARANGI | 337.12 | 0 | 0 | 90
2146 | JHARGRAM | Jhargram Division | PARSHULI AND ADJOINING MOUJAS PWSS , SM/12531 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Parshuli and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 521/JRWS | 15/03/2024 | 60 | TAPAS KUMAR JANA | 4.58 | 0 | 0 | 0
2147 | JHARGRAM | Jhargram Mechanical Division | PARSHULI AND ADJOINING MOUJAS PWSS , SM/12531 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Par Shuli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2268/JMD | 09/08/2023 | 360 | JIBON GHOSH | 22.53 | 0 | 0 | 80
2148 | JHARGRAM | Jhargram Division | PARSHULI AND ADJOINING MOUJAS PWSS , SM/12531 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Kenddangri GP at Jambani Block under jhargram Division PHE Dte. (Phase-I) | 371/JRWS | 04/10/2024 | 10 | GOPAL JANA | 0.75 | 0 | 0 | 100
2149 | JHARGRAM | Jhargram Division | BANKATI AND IT'S ADJOINING MOUJAS , SM/12351 | New | Material Requisition To Resource Division | 1535/JHD | 06/09/2023 | 0 | Resource Division | 70.86 | 0 | 0 | 0
2150 | JHARGRAM | Jhargram Mechanical Division | BANKATI AND IT'S ADJOINING MOUJAS , SM/12351 | New | NEW SERVICE CONNECTION CHARGES FOR BANKATI T/W - II PWSS | 53/JMD | 12/03/2024 | 0 | WBSEDCL | 5.32 | 0 | 0 | 0
2151 | JHARGRAM | Jhargram Mechanical Division | BANKATI AND IT'S ADJOINING MOUJAS , SM/12351 | New | NEW SERVICE CONNECTION CHARGRES FOR BANKATI T/W -I PWSS | 52/JMD | 12/03/2024 | 0 | WBSEDCL | 11.31 | 0 | 0 | 0
2152 | JHARGRAM | Central Drilling | BANKATI AND IT'S ADJOINING MOUJAS , SM/12351 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2153 | JHARGRAM | Jhargram Division | BANKATI AND IT'S ADJOINING MOUJAS , SM/12351 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Bankati and its Adjoining Mouzas PWSS , Block: - Binpur-I, District: - Jhargram {TYPE - B} (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 852/JSD | 03/09/2024 | 212 | NAYAN CONSTRUCTION | 4.82 | 0 | 0 | 100
2154 | JHARGRAM | Jhargram Division | Chingra And Adjoining Moujas PWSS , SM/12385 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Chingra and its Adjoining Mouzas PWSS , Block Gopiballavpur-II, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | 779/JSD | 09/08/2024 | 30 | MAA RAJBALLABHI ENTERPRISE | 4.69 | 0 | 0 | 0
2155 | JHARGRAM | Jhargram Mechanical Division | Chingra And Adjoining Moujas PWSS , SM/12385 | New | New service connection charges | 46/JMD | 29/12/2023 | 0 | WBSEDCL | 2.73 | 0 | 0 | 0
2156 | JHARGRAM | Jhargram Mechanical Division | Chingra And Adjoining Moujas PWSS , SM/12385 | New | New service connection charges | 45/JMD | 29/12/2023 | 0 | WBSEDCL | 3.44 | 0 | 0 | 0
2157 | JHARGRAM | Central Drilling | Chingra And Adjoining Moujas PWSS , SM/12385 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2158 | JHARGRAM | Jhargram Division | Chingra And Adjoining Moujas PWSS , SM/12385 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
2159 | JHARGRAM | Jhargram Division | Chingra And Adjoining Moujas PWSS , SM/12385 | New | Field Level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in fferent Pipe Water Supply Scheme (7 nos PWSS of 130 PWSS) within Gopiballavpur-II Block in the District of Jhargram under Jhargram Division. PHE Dte. Location- i) Chingra PWSS, ii) Gohalmara PWSS iii) Kendana PWSS iv) Kulina PWSS v) Sonakinia PWSS Vi) Tentilia PWSS vii) Chorchita PWSS | 368/JSD | 29/04/2025 | 150 | TECHVISION | 3.72 | 0 | 0 | 10
2160 | JHARGRAM | Jhargram Division | Chingra And Adjoining Moujas PWSS , SM/12385 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Nota, Tapsia GP at Gopiballavpur-II Block under jhargram Division PHE Dte. (Phase-I) | 1037/JSD | 14/11/2024 | 10 | MANOJ KUMAR MAHATA | 0.84 | 0 | 0 | 0
2161 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Material Requisition To Resource Division | 1511/JHD | 05/09/2023 | 0 | Resource Division | 8.21 | 0 | 0 | 0
2162 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Matihana at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6762/JMD | 27/08/2024 | 4 | RSA ENTERPRISE | 1.56 | 0 | 0 | 0
2163 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Dahi at Gopiballavpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6764/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
2164 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Ranjia at Gopiballavpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6765/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
2165 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Chaqua at Gopiballavpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6766/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
2166 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Madhabpur at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6775/JMD | 27/08/2024 | 127 | RSA ENTERPRISE | 3.49 | 0 | 0 | 100
2167 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Kachmabila at Gopiballavpur-I block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6763/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
2168 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Jamdahari at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6769/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
2169 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Mahupal at Gopiballavpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6767/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
2170 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Kamarbandi at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6756/JMD | 27/08/2024 | 4 | RSA ENTERPRISE | 1.56 | 0 | 0 | 0
2171 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | New Service connection charges. | 32/JMD | 18/01/2024 | 0 | WBSEDCL | 0.42 | 0 | 0 | 0
2172 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM. (scheme code:- SM/11477) | 423/JMD | 27/11/2024 | 0 | SURAJ SERVICE STATION | 0.12 | 0 | 0 | 0
2173 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | New service connection charges for Phulakendu mini pwss | 15/JMD | 18/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2174 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | New Service connection charges. | 19/JMD | 11/01/2024 | 0 | WBSEDCL | 0.42 | 0 | 0 | 0
2175 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | New Service connection charges for Muchinala mini pwss | 72/JMD | 29/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2176 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | 340/JHD | 09/03/2023 | 872 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 0 | 0 | 50
2177 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Panchberia at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6770/JMD | 27/08/2024 | 127 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 100
2178 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. , SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Banbhum at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6771/JMD | 27/08/2024 | 127 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 100
2179 | JHARGRAM | Jhargram Mechanical Division | CHANDABILA AND ADJOINING MOPUJAS PWSS , SM/12435 | New | New Service connection | 14/JMD | 10/11/2023 | 0 | WBSEDCL | 3.16 | 0 | 0 | 0
2180 | JHARGRAM | Jhargram Mechanical Division | CHANDABILA AND ADJOINING MOPUJAS PWSS , SM/12435 | New | New Service connection | 5/JMD | 07/09/2023 | 0 | WBSEDCL | 3.32 | 0 | 0 | 0
2181 | JHARGRAM | Jhargram Division | CHANDABILA AND ADJOINING MOPUJAS PWSS , SM/12435 | New | Material Requisition To Resource Division | 427/JHD | 13/03/2024 | 0 | Resource Division | 7.15 | 0 | 0 | 0
2182 | JHARGRAM | Central Drilling | CHANDABILA AND ADJOINING MOPUJAS PWSS , SM/12435 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2183 | JHARGRAM | Jhargram Division | CHANDABILA AND ADJOINING MOPUJAS PWSS , SM/12435 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House,& Providing Functional Household Tap Connection (1685 Nos) including 02(Two) Years Operation & Maintenance For CHANDABILE , TULIBAR Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 1138/JHD | 20/07/2023 | 711 | ASIS KUMAR SARANGI | 629.25 | 0 | 0 | 95
2184 | JHARGRAM | Jhargram Division | CHANDABILA AND ADJOINING MOPUJAS PWSS , SM/12435 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Belia and Chandabila PWSS , Block Jamboni, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 503/JHD | 07/03/2025 | 60 | M/S DURGA ENTERPRISE | 28.11 | 0 | 0 | 0
2185 | JHARGRAM | Central Drilling | CHANDABILA AND ADJOINING MOPUJAS PWSS , SM/12435 | New | Continuation for Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for office of the Store & Workshop Sub Division, Central Drilling Division, PHE Dte. | 23/S&WSD | 29/01/2025 | 184 | SULEKHA GHOSH | 0.87 | 0 | 0 | 0
2186 | JHARGRAM | Central Drilling | CHANDABILA AND ADJOINING MOPUJAS PWSS , SM/12435 | New | Continuation for Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for office of the Store & Workshop Sub Division, Central Drilling Division, PHE Dte. | 154/S&WSD | 29/07/2025 | 184 | SULEKHA GHOSH | 0.87 | 0 | 0 | 0
2187 | JHARGRAM | Jhargram Division | CHANDABILA AND ADJOINING MOPUJAS PWSS , SM/12435 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Chandabila and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 528/JRWS | 16/03/2024 | 60 | ASSOCIATED ENGINEERS & TRADERS | 4.84 | 0 | 0 | 70
2188 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Material Requisition To Resource Division | 1596/JHD | 08/09/2023 | 0 | Resource Division | 57.15 | 0 | 0 | 0
2189 | JHARGRAM | Jhargram Mechanical Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Rautarapur & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1249/JMD | 26/05/2023 | 180 | MAA BHABOTARINE ENTERPRISE | 21.88 | 0 | 0 | 50
2190 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub Division under Jhargram Division, PHE Dte. | 873/JHD | 08/06/2023 | 90 | TAPAN KUMAR UPADHYAY | 25.78 | 0 | 0 | 80
2191 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1374/JHD | 16/08/2023 | 90 | LAKSHMI IRON | 33.9 | 0 | 0 | 95
2192 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_27 of 2022-23 , SL No.-9 ) | 1580/JHD | 08/09/2023 | 90 | GANGULY ENTERPRISE | 14.67 | 0 | 0 | 95
2193 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Accommodate FHTC ( 1531 nos) under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1499/JHD | 05/09/2023 | 360 | MONDAL ENTERPRISE | 64.5 | 0 | 0 | 70
2194 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3 rd Call (Ref: 1st Call eNIT_27 of 2022-23, SL No.-3 and 2nd Call eNIT_08 of 2023-24, SL No.-12) | 1950/JHD | 22/11/2023 | 90 | MASUM CONSTRUCTION | 17.09 | 0 | 0 | 100
2195 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Rautarapur and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | 2294/JHD | 04/12/2024 | 30 | BIKASH MANDAL | 7.92 | 0 | 0 | 0
2196 | JHARGRAM | Jhargram Mechanical Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | new service connection charges at Rautarapur, T/W-1 water supply scheme | 77/JMD | 29/04/2024 | 0 | WBSEDCL | 9.06 | 0 | 0 | 0
2197 | JHARGRAM | Jhargram Mechanical Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | new service connection charges at Rautrapur t/w-2 water supply scheme | 76/JMD | 29/04/2024 | 0 | WBSEDCL | 6.82 | 0 | 0 | 0
2198 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_27 of 2022-23 , SL No.-4 ) | 3090/JHD | 28/12/2023 | 90 | TARUN MAHATA | 23.06 | 0 | 0 | 95
2199 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Construction of Boundary wall and allied works at 1st. Tube well site of Rautarapur and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 75/JHD | 10/01/2025 | 30 | ENVOTECH INFRA SOLUTION | 8.39 | 0 | 0 | 0
2200 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Construction of Boundary wall and allied works at 2nd. Tube well site of Rautarapur and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 50 mtr, column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 1318/JHD | 23/09/2024 | 30 | BISWANATH PANIGRAHI | 3.67 | 0 | 0 | 100
2201 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Additional Laying of Distribution pipe line for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in Jhargram Block under Jhargram Division, PHE Dte. | 372/JHD | 20/02/2025 | 45 | MASUM CONSTRUCTION | 5.78 | 0 | 0 | 0
2202 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Trial run for RAUTARAPUR AND ADJOINING MOUZAS PWSS scheme within Jhargram Block under Jhargram Division, PHE Dte. for 3 months. | 731/JHD | 02/04/2025 | 91 | ENVOTECH INFRA SOLUTION | 1.29 | 0 | 0 | 0
2203 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1093/JHD | 14/07/2023 | 90 | ASSOCIATED ENGINEERS & TRADERS | 23.96 | 0 | 0 | 90
2204 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_27 of 2022-23 , SL No.-8 ) | 1342/JHD | 10/08/2023 | 90 | SANDIP GURIA | 14.78 | 0 | 0 | 95
2205 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1615/JHD | 08/09/2023 | 90 | A.K. SIKDAR | 31.62 | 0 | 0 | 100
2206 | JHARGRAM | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12333 | New | Laying of extention distribution pipe line for rautarapur and adjoining moujas pwss in jhargram block within jhargram district under jhargram division P.H.E Dte. | 1243/JHD | 30/08/2024 | 45 | MMS CONSTRUCTIONS PVT.LTD. | 15.05 | 0 | 0 | 100
2207 | JHARGRAM | Jhargram Division | SUMITRAPUR AND ADJOINING MOJAS PWSS , SM/12528 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Sumitrapur and its adjoining mouzas Pipe Water Supply Scheme within Gopaballavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 190/GPSD | 11/03/2024 | 30 | S.R. ENTERPRISE | 4.25 | 0 | 0 | 100
2208 | JHARGRAM | Jhargram Division | SUMITRAPUR AND ADJOINING MOJAS PWSS , SM/12528 | New | Material Requisition To Resource Division | 421/JHD | 13/03/2024 | 0 | Resource Division | 30.74 | 0 | 0 | 0
2209 | JHARGRAM | Jhargram Mechanical Division | SUMITRAPUR AND ADJOINING MOJAS PWSS , SM/12528 | New | New Service Connection charges for Sumitrapur tw-II pwss | 38/JMD | 01/02/2024 | 0 | WBSEDCL | 3.83 | 0 | 0 | 0
2210 | JHARGRAM | Jhargram Mechanical Division | SUMITRAPUR AND ADJOINING MOJAS PWSS , SM/12528 | New | New Service Connection charges for Sumitrapur, Tw-I pwss | 39/JMD | 01/02/2024 | 0 | WBSEDCL | 4.28 | 0 | 0 | 0
2211 | JHARGRAM | Central Drilling | SUMITRAPUR AND ADJOINING MOJAS PWSS , SM/12528 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2212 | JHARGRAM | Jhargram Division | SUMITRAPUR AND ADJOINING MOJAS PWSS , SM/12528 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
2213 | JHARGRAM | Jhargram Division | SUMITRAPUR AND ADJOINING MOJAS PWSS , SM/12528 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Sumitrapur and Amarda and its adjoining Mouzas , Block Gopiballavpur-I, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 468/JHD | 04/03/2025 | 60 | RITESH AGARWALL | 27.15 | 0 | 0 | 0
2214 | JHARGRAM | Jhargram Division | HARDA AND ADJOINING MOUJAS PWSS , SM/12436 | New | Material Requisition To Resource Division | 1538/JHD | 06/09/2023 | 0 | Resource Division | 63.14 | 0 | 0 | 0
2215 | JHARGRAM | Jhargram Mechanical Division | HARDA AND ADJOINING MOUJAS PWSS , SM/12436 | New | Quotation for new cesvice connection at Harda tw-1 water supply scheme. | 93/JMD | 22/03/2024 | 0 | WBSEDCL | 11.49 | 0 | 0 | 0
2216 | JHARGRAM | Jhargram Mechanical Division | HARDA AND ADJOINING MOUJAS PWSS , SM/12436 | New | New service connection charges | 48/JMD | 29/12/2023 | 0 | WBSEDCL | 3.67 | 0 | 0 | 0
2217 | JHARGRAM | Central Drilling | HARDA AND ADJOINING MOUJAS PWSS , SM/12436 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2218 | JHARGRAM | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS , SM/12343 | New | Material Requisition To Resource Division | 1553/JHD | 07/09/2023 | 0 | Resource Division | 181.8 | 0 | 0 | 0
2219 | JHARGRAM | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS , SM/12343 | New | Construction of Boundary wall allied works at 3rd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Simladanga and its Adjoining Mouzas PWSS , Block Binpur-I, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | 778/JSD | 09/08/2024 | 30 | ARUP KUMAR MAITI | 4.39 | 0 | 0 | 0
2220 | JHARGRAM | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS , SM/12343 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Simladanga and its Adjoining Mouzas PWSS , Block: - Binpur-I, District: - Jhargram {TYPE - B} (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 776/JSD | 09/08/2024 | 30 | CONSTRUCTURE | 4.81 | 0 | 0 | 0
2221 | JHARGRAM | Jhargram Mechanical Division | SIMLADANGA AND ADJOINING MOUJAS PWSS , SM/12343 | New | Quotation for new service connection at Simladanga tw-III water supply scheme. | 185/JMD | 11/06/2024 | 0 | WBSEDCL | 5.94 | 0 | 0 | 0
2222 | JHARGRAM | Central Drilling | SIMLADANGA AND ADJOINING MOUJAS PWSS , SM/12343 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2223 | JHARGRAM | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS , SM/12343 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Belatikri GP at Binpur-I Block under jhargram Division PHE Dte. (Phase-I) | 965/JSD | 30/09/2024 | 10 | GOPAL JANA | 0.92 | 0 | 0 | 0
2224 | JHARGRAM | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS , SM/12343 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Dharampur GP at Binpur-I Block under jhargram Division PHE Dte. (Phase-I) | 966/JSD | 30/09/2024 | 10 | PRINT PREVIEW | 0.84 | 0 | 0 | 0
2225 | JHARGRAM | Jhargram Division | PALASHBANI AND ADJOINING MOUJAS PWSS , SM/12711 | New | Material Requisition To Resource Division | 1495/JHD | 05/09/2023 | 0 | Resource Division | 19.45 | 0 | 0 | 0
2226 | JHARGRAM | Jhargram Mechanical Division | PALASHBANI AND ADJOINING MOUJAS PWSS , SM/12711 | New | New Service connection | 13/JMD | 10/11/2023 | 0 | WBSEDCL | 8.33 | 0 | 0 | 0
2227 | JHARGRAM | Jhargram Mechanical Division | PALASHBANI AND ADJOINING MOUJAS PWSS , SM/12711 | New | New Service connection | 22/JMD | 20/11/2023 | 0 | WBSEDCL | 2.64 | 0 | 0 | 0
2228 | JHARGRAM | Jhargram Mechanical Division | PALASHBANI AND ADJOINING MOUJAS PWSS , SM/12711 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Palasbani & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2267/JMD | 09/08/2023 | 180 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 22.55 | 0 | 0 | 85
2229 | JHARGRAM | Jhargram Division | PALASHBANI AND ADJOINING MOUJAS PWSS , SM/12711 | New | Installation of display board for JJM works at different piped water supply scheme within Jamboni Block and Others Block under Jhargram Division, PHE dte. (3rd Phase) | 239/GPSD | 12/03/2024 | 10 | KARNAJORA AGNIBINA SEVA SAMITY | 0.97 | 0 | 0 | 100
2230 | JHARGRAM | Jhargram Division | PALASHBANI AND ADJOINING MOUJAS PWSS , SM/12711 | New | Sinking of Tube Well , Pump House , 100 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation ,including 02(Two) Years Operation & Maintenance & Accommodate FHTC (841 nos) under JJM with allied work for Palashbani PWSS in Jamboni Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. . | 240/JHD | 17/02/2023 | 774 | SUNIL DULE | 353.65 | 0 | 0 | 90
2231 | JHARGRAM | Jhargram Division | PALASHBANI AND ADJOINING MOUJAS PWSS , SM/12711 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Lalbundh GP at Jambani Block under jhargram Division PHE Dte. (Phase-I) | 372/JRWS | 04/10/2024 | 10 | MANOJ KUMAR MAHATA | 0.84 | 0 | 0 | 100
2232 | JHARGRAM | Jhargram Division | PALASHBANI AND ADJOINING MOUJAS PWSS , SM/12711 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Palashboni and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 518/JRWS | 15/03/2024 | 60 | SUNIL DULE | 4.84 | 0 | 0 | 90
2233 | JHARGRAM | Jhargram Division | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. , SM/09434 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Birkarnar PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 97/JSD | 08/07/2021 | 14 | RADIANT | 1.8 | 0 | 0 | 1
2234 | JHARGRAM | Jhargram Division | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. , SM/09434 | Augmentation | Retrofitting with relaying of distribution pipeline to accommodate FHTC under JJM of Rejuvenation of Birkarnar water supply scheme at Block - Binpur-I in the District of Jhargram | 202/JSD | 04/04/2022 | 21 | DEBASIS DATTA | 4.69 | 0 | 0 | 1
2235 | JHARGRAM | Jhargram Division | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. , SM/09434 | Augmentation | Retrofitting with relaying of distribution pipeline to accommodate FHTC under JJM of Rejuvenation of Birkarnar water supply scheme at Block - Binpur-I in the District of Jhargram |  | 12/08/2022 | 0 | DEBASIS DATTA | 4.5 | 0 | 0 | 0
2236 | JHARGRAM | Jhargram Division | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. , SM/09434 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Birkarnar PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | 02/08/2022 | 0 | RADIANT | 1.79 | 0 | 0 | 0
2237 | JHARGRAM | Jhargram Division | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. , SM/09434 | Augmentation | Retrofitting with relaying of distribution pipeline to accommodate FHTC under JJM of rejuvenation of Birkarnar Water Supply Scheme at Block Binpur-I in the district of Jhargram. (Adintariam Bill) |  | 01/09/2022 | 0 | DEBASIS DATTA | 0.05 | 0 | 0 | 0
2238 | JHARGRAM | Jhargram Division | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. , SM/09434 | Augmentation | Restoration work for laying pipeline along the Lalgarh-Ramgarh Road (near 3rd kmp) due to Augmentation of Birkarner Piped W/S Scheme under Jhargram Divison | BP-2023-24-137 | 03/08/2023 | 0 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 1.83 | 0 | 0 | 0
2239 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12724 | New | Material Requisition To Resource Division | 1556/JHD | 07/09/2023 | 0 | Resource Division | 29.57 | 0 | 0 | 0
2240 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12724 | New | Qutation for new service connection at Gobindapur T/W-1 water supply scheme. | 91/JMD | 22/03/2024 | 0 | WBSEDCL | 4.74 | 0 | 0 | 0
2241 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12724 | New | Quotation for new service connection at Gobindapur T/W -2 water supply scheme. | 90/JMD | 22/03/2024 | 0 | WBSEDCL | 4.53 | 0 | 0 | 0
2242 | JHARGRAM | Central Drilling | GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/12724 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2243 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Dumri-Nakrasuli w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16919 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Satkuli Charar and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2501/JMD | 25/08/2023 | 180 | THE BUSINESS ENGINEERS INDIA | 75.12 | 0 | 0 | 0
2244 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Haripurbirua w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16922 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Satkuli Charar and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2501/JMD | 25/08/2023 | 180 | THE BUSINESS ENGINEERS INDIA | 75.12 | 0 | 0 | 0
2245 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Rampura w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16923 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Rampura and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2777/JMD | 05/09/2023 | 180 | ELECTRO ENTERPRISES | 32.07 | 0 | 0 | 0
2246 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at JANGALKHAS AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16688 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Jangalkhas and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2772/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 77.3 | 0 | 0 | 0
2247 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Dahijuri w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16682 | Solarisation | Quotation for solar power meter application for site Dahijuri-1 | 401/JMD | 25/10/2024 | 0 | WBSEDCL | 0.01 | 0 | 0 | 0
2248 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-IV (MADHABPUR) AND IT'S ADJOINING MOUJAS PWSS , SM/16675 | New | Supply, delivery and installation of horizontal split casing type centrifugal pumping machineries with suitable rated horizontal foot mounted Induction motor sets and allied electro-mechanical accessories for low lift and high lift pumping operations at Dharampur Zone-IV (Madhabpur) and its adjoining moujas surface water based piped water supply scheme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2009/JMD | 02/08/2023 | 180 | M/S. EMMESS | 50.21 | 0 | 0 | 0
2249 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-IV (MADHABPUR) AND IT'S ADJOINING MOUJAS PWSS , SM/16675 | New | Surveying, planning, designing ,delivery, erection, construction, commissioning and completion in all respect of all Civil, Electrical and Mechanical Works including all allied, related and enabling works for the proposed DHARAMPUR ZONE -IV (MADHABPUR) Piped water supply Scheme based on surface water of Open Cast Stone Mine /pond at DHARAMPUR, Block Binpur-II district of Jhargram | 1831/JHD | 27/10/2023 | 882 | MONDAL PRECISION PRIVATE LIMITED | 502 | 0 | 0 | 6
2250 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Sijua And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16708 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Belda and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2504/JMD | 25/08/2023 | 180 | M/S. SAMRIDDHI ENTERPRISE | 31.3 | 0 | 0 | 0
2251 | JHARGRAM | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at Balishira And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram , SM/16709 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Bandarbani and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2774/JMD | 05/09/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 64.39 | 0 | 0 | 0
2252 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Murabani w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17118 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Patharnala and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2499/JMD | 25/08/2023 | 180 | RSA ENTERPRISE | 75.13 | 0 | 0 | 0
2253 | JHARGRAM | Jhargram Division | Installation of Iron Elemination Plant(IEP) and related works in different schemes(Barajharia PWSS, Lalgarh PWSS, Baratilaboni PWSS) within Nayagram and Binpur-I Blocks in Jhargram District under Jhargram Division, PHE Dte. , SM/17948 | Augmentation | 03 nos I.E.Ps[ 30 cum/hr for Lalgarh pwss at Bipur-I block,10 cum/hr for Baratilaboni at Binpur-I block,10 cum for Barajharia at Nayagram block] with blower with compressor room ,platfroms,ground water recharge structure, const. of brick masonary drains and laying drainage pipe lines | 1090/JHD | 14/07/2023 | 90 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 54.17 | 0 | 0 | 95
2254 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Amlachati w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17042 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Barabari and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2503/JMD | 25/08/2023 | 180 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 31.3 | 0 | 0 | 0
2255 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS , SM/17929 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under ¿Kanko¿ G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 1126/JMD | 18/05/2023 | 613 | RSA ENTERPRISE | 27 | 0 | 0 | 85
2256 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS , SM/17929 | New | Material Requisition To Resource Division | 2867/JMD | 07/03/2024 | 0 | Resource Division | 4.8 | 0 | 0 | 0
2257 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS , SM/17929 | New | New service connection charges for Jadabpur, Kanko GP ,Jhargram | 67/JMD | 12/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2258 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS , SM/17929 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Kanko G.P. in place of {Dharampur Zone-III Kanko } w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 12/JMD | 01/03/2024 | 0 | SURAJ SERVICE STATION | 1.23 | 0 | 0 | 0
2259 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS , SM/17929 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under Kanko G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 17/JMD | 10/01/2024 | 0 | SURAJ SERVICE STATION | 0.89 | 0 | 0 | 0
2260 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS , SM/17929 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under Kanko G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 91/JMD | 16/02/2024 | 0 | SURAJ SERVICE STATION | 1.25 | 0 | 0 | 0
2261 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS , SM/17929 | New | New service connection charge in Nachna, Kanko GP, Binpur-1 | 44/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2262 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS , SM/17929 | New | New service connection charges for Bankrasol, Kanko GP ,Jhargram | 67/JMD | 12/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2263 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS , SM/17929 | New | New service connection charge in Salpatra, Kanko GP, Binpur-1 | 44/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2264 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS , SM/17929 | New | New Service connection charges. | 21/JMD | 11/01/2024 | 0 | WBSEDCL | 1.47 | 0 | 0 | 0
2265 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS , SM/17929 | New | Payment for new service connection at Korkora laldanga school(H.S),Kanko under 130 PWSS scheme. |  | 18/12/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2266 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS , SM/17929 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Bankrasol & adjacent eight (08) nos. villages under ¿Kanko¿ G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 1127/JMD | 18/05/2023 | 611 | RSA ENTERPRISE | 30.38 | 0 | 0 | 83
2267 | JHARGRAM | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS , SM/17930 | New | Construction of (125 mm X 115 mm X 200 mtr.) RBTW by DTH/ combination method for providing FHTC at SITAPUR & its adjacent Seventy Three (73) nos. villages under Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 2297/JMD | 11/08/2023 | 148 | MONDAL PRECISION PRIVATE LIMITED | 163.47 | 0 | 0 | 100
2268 | JHARGRAM | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS , SM/17930 | New | New service connection charges | 31/JMD | 19/12/2023 | 0 | WBSEDCL | 0.84 | 0 | 0 | 0
2269 | JHARGRAM | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS , SM/17930 | New | New Service connection | 43/JMD | 29/12/2023 | 0 | WBSEDCL | 0.42 | 0 | 0 | 0
2270 | JHARGRAM | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS , SM/17930 | New | New Service connection charges. | 11/JMD | 01/03/2024 | 0 | WBSEDCL | 0.63 | 0 | 0 | 0
2271 | JHARGRAM | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS , SM/17930 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 200 mtr.) RBTW by DTH / Combination method at Sandapara G.P. in place of (Chainbera, Zone-I Darra (SM/17930), Chainbera, Zone-II Jarda (SM/17925) and Chainbera, Zone-III Joypur (SM/18746) w/s schemes under Binpur-II Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 193/JMD | 30/01/2025 | 352 | MONDAL PRECISION PRIVATE LIMITED | 58.26 | 0 | 0 | 20
2272 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Chakkua w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17048 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Darukuli and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2632/JMD | 29/08/2023 | 180 | AMITAVA CHAKRABORTY | 31.3 | 0 | 0 | 0
2273 | JHARGRAM | Jhargram Division | AMARDA AND ADJOINING MOUJAS PWSS , SM/17586 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Amarda and its adjoining mouzas Pipe Water Supply Scheme within Gopiballavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 198/GPSD | 11/03/2024 | 30 | M/S S.R. & COMPANY | 4.28 | 0 | 0 | 0
2274 | JHARGRAM | Jhargram Division | AMARDA AND ADJOINING MOUJAS PWSS , SM/17586 | New | Material Requisition To Resource Division | 425/JHD | 13/03/2024 | 0 | Resource Division | 35.66 | 0 | 0 | 0
2275 | JHARGRAM | Jhargram Mechanical Division | AMARDA AND ADJOINING MOUJAS PWSS , SM/17586 | New | Quotation for new service connection at Amarda T/W-I water supply scheme. | 347/JMD | 11/09/2024 | 0 | WBSEDCL | 3.77 | 0 | 0 | 0
2276 | JHARGRAM | Central Drilling | AMARDA AND ADJOINING MOUJAS PWSS , SM/17586 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2277 | JHARGRAM | Jhargram Division | AMARDA AND ADJOINING MOUJAS PWSS , SM/17586 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
2278 | JHARGRAM | Jhargram Division | AMARDA AND ADJOINING MOUJAS PWSS , SM/17586 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Sumitrapur and Amarda and its adjoining Mouzas , Block Gopiballavpur-I, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 468/JHD | 04/03/2025 | 60 | RITESH AGARWALL | 27.15 | 0 | 0 | 0
2279 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at JIRAPARA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17080 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Uttar Barashol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2498/JMD | 25/08/2023 | 180 | AMITAVA CHAKRABORTY | 75.12 | 0 | 0 | 0
2280 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at TENTULIA AND ADJOINING MOUJAS Piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17082 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Belda and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2504/JMD | 25/08/2023 | 180 | M/S. SAMRIDDHI ENTERPRISE | 31.3 | 0 | 0 | 0
2281 | JHARGRAM | Jhargram Division | RAGRA AND ADJOINING MOUJAS PWSS , SM/17174 | New | Material Requisition To Resource Division | 955/JHD | 22/06/2023 | 0 | Resource Division | 34.48 | 0 | 0 | 0
2282 | JHARGRAM | Jhargram Division | RAGRA AND ADJOINING MOUJAS PWSS , SM/17174 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of ROGRA and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 173/GPSD | 05/03/2024 | 30 | SAUBHIK KUMAR NAG | 4.25 | 0 | 0 | 100
2283 | JHARGRAM | Jhargram Division | RAGRA AND ADJOINING MOUJAS PWSS , SM/17174 | New | Continuation work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission from 16.02.2024 to 29.02.2024 under Jhargram Division PHE Dte. | 420/JRWS | 15/02/2024 | 14 | JAGOMOHAN SETUA | 0.53 | 0 | 0 | 100
2284 | JHARGRAM | Jhargram Mechanical Division | RAGRA AND ADJOINING MOUJAS PWSS , SM/17174 | New | Service Connection Charges for Ragra tw-I pwss | 40/JMD | 01/02/2024 | 0 | WBSEDCL | 5.66 | 0 | 0 | 0
2285 | JHARGRAM | Jhargram Mechanical Division | RAGRA AND ADJOINING MOUJAS PWSS , SM/17174 | New | New service connection charges for Ragra w/s scheme, t/w no.II | 31/JMD | 11/03/2024 | 0 | WBSEDCL | 10.96 | 0 | 0 | 0
2286 | JHARGRAM | Jhargram Division | RAGRA AND ADJOINING MOUJAS PWSS , SM/17174 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House , & Providing Functional Household Tap Connection (6745 Nos), etc. For RAGRA, SATKULI CHARAR, NOAGAON, RAMPURA Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 607/JHD | 04/05/2023 | 881 | GOBINDA MAITY | 1886.45 | 0 | 0 | 20
2287 | JHARGRAM | Central Drilling | RAGRA AND ADJOINING MOUJAS PWSS , SM/17174 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2288 | JHARGRAM | Central Drilling | RAGRA AND ADJOINING MOUJAS PWSS , SM/17174 | New | Hiring of Diesel Driven Motor Cab (BS-III & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub-Divn-I (D), CDD, P.H.E. Dte. | 33/CMSD-I | 11/02/2025 | 197 | BINDU PRASAD DEVI | 0.94 | 0 | 0 | 0
2289 | JHARGRAM | Jhargram Division | RAGRA AND ADJOINING MOUJAS PWSS , SM/17174 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Rogra and its adjoining Mouzas, Block Sankrail, District Jhargram | 1037/JHD | 22/07/2024 | 30 | TAPAS PAL | 8.35 | 0 | 0 | 40
2290 | JHARGRAM | Jhargram Division | RAGRA AND ADJOINING MOUJAS PWSS , SM/17174 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection for Ragra and its adjoining mouzas Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division of Jhargram Division, P.H.E.Dte. | 130/GPSD | 18/03/2025 | 21 | GOBINDA MAITY | 2.15 | 0 | 0 | 100
2291 | JHARGRAM | Jhargram Mechanical Division | DARUKULI AND ADJOINING MOUJAS PWSS , SM/12358 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Darkuli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2111/JMD | 03/08/2023 | 180 | S.K. ENTERPRISE | 15.64 | 0 | 0 | 0
2292 | JHARGRAM | Central Drilling | DARUKULI AND ADJOINING MOUJAS PWSS , SM/12358 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 91/CDD | 25/04/2024 | 122 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 0 | 0 | 10
2293 | JHARGRAM | Jhargram Division | DARUKULI AND ADJOINING MOUJAS PWSS , SM/12358 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
2294 | JHARGRAM | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS , SM/12408 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 150 cum and staging height 20 mtr. as per approved drawing with allied works of GHORA PINCHA & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for GOPIBALLAVPUR-I Block, District: - Jhargram. | 2056/JHD | 07/12/2023 | 210 | ASIS KUMAR SARANGI | 73.5 | 0 | 0 | 0
2295 | JHARGRAM | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS , SM/12408 | New | Material Requisition To Resource Division | 1579/JHD | 08/09/2023 | 0 | Resource Division | 25.64 | 0 | 0 | 0
2296 | JHARGRAM | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS , SM/12408 | New | Pump House, 100 cum GLR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, Accommodate FHTC (929 nos) under JJM with allied work for GHORAPINCHA AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1097/JHD | 14/07/2023 | 180 | ASIS KUMAR SARANGI | 87.33 | 0 | 0 | 90
2297 | JHARGRAM | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS , SM/12408 | New | Sinking of Tube Well, Pump House under JJM with allied work for GHORAPINCHA AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour and materials within Jhargram Sub Division under Jhargram Division, PHE Dte. | 1119/JHD | 19/07/2023 | 90 | ASIS KUMAR SARANGI | 29.33 | 0 | 0 | 95
2298 | JHARGRAM | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS , SM/12408 | New | Laying distribution pipe line under JJM with allied work for GHORAPINCHA AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1327/JHD | 10/08/2023 | 495 | ASIS KUMAR SARANGI | 123.65 | 0 | 0 | 96
2299 | JHARGRAM | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS , SM/12408 | New | Supplying and Delivery of Different dia CIDF Sluice Valve,CIDF Pipes & Specials etc for Laying distribution of HDPE Pipe Line and Inter Connection between Tube Well and Rising main & OHR including By-Pass arrangement etc. For Ghorapincha & its Adjoining Mouzas PWSS in Gopiballavpur-I Block under Jhargram Division PHE Dte. | 684/GPSD | 02/12/2024 | 21 | ASSOCIATED ENGINEERS & TRADERS | 3.57 | 0 | 0 | 0
2300 | JHARGRAM | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS , SM/12408 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Ghorapincha and its adjoining mouzas Pipe Water Supply Scheme within Gopiballavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 197/GPSD | 11/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 4.3 | 0 | 0 | 100
2301 | JHARGRAM | Jhargram Mechanical Division | GHORA PINCHA AND ADJOINING MOJAS PWSS , SM/12408 | New | Quotation for new service connection at Ghorapitcha T/W-II water supply scheme. | 236/JMD | 09/07/2024 | 0 | WBSEDCL | 3.04 | 0 | 0 | 0
2302 | JHARGRAM | Jhargram Mechanical Division | GHORA PINCHA AND ADJOINING MOJAS PWSS , SM/12408 | New | Quotation for new service connection at Ghorapitcha T/W-I water supply scheme. | 235/JMD | 09/07/2024 | 0 | WBSEDCL | 7.07 | 0 | 0 | 0
2303 | JHARGRAM | Central Drilling | GHORA PINCHA AND ADJOINING MOJAS PWSS , SM/12408 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2304 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | Laying of Pipe Line for uncovered habitation of Muransole Mouza under Belpahari WS Scheme within Binpur-II Block under Jhargram Division, P.H.E. Dte | 967/JSD | 10/11/2023 | 21 | SUNIL DULE | 3.07 | 0 | 0 | 100
2305 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | Installation of 1000 Litres capacity PVC Water Tank and allied construction at Different Places under Belpahari W/S Scheme within Jhargram Sub-Division under Jhargram Division P.H.E.Dte. | 966/JSD | 10/11/2023 | 21 | SAIKAT DANDAPAT | 1.15 | 0 | 0 | 100
2306 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | Laying of Distribution Pipe Line due to damage in existing pipeline during Construction of Concrete Road from Merasuli to Sahari Rana Para & Adibasipara under Belpahari Water Supply Scheme. | 148/JHD | 29/01/2024 | 15 | SAIKAT DANDAPAT | 5.78 | 0 | 0 | 100
2307 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | Continuation Work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for 1st March 2024 to 15th March 2024 under Jhargram Division PHE Dte. | 451/JRWS | 27/02/2024 | 15 | JAGOMOHAN SETUA | 0.63 | 0 | 0 | 100
2308 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | Material Requisition To Resource Division | 279/JHD | 20/02/2024 | 0 | Resource Division | 3.98 | 0 | 0 | 0
2309 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | Material Requisition To Resource Division | 2236/JHD | 29/11/2024 | 0 | Resource Division | 44.92 | 0 | 0 | 0
2310 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | Material Requisition To Resource Division | 1094/JHD | 30/07/2024 | 0 | Resource Division | 184.4 | 0 | 0 | 0
2311 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | Construction of 600 Cum OHR(Intze type solid raft) ,Laying of Distribution ,clear Water & Raw Water Raising main to accommodate FHTC (7292 Nos) for Augmentation of Belpahari Water Supply Scheme within Binpur-II Block under Jhargram District under Jhargram Division, P.H.E. Dte. | 1463/JHD | 31/08/2023 | 660 | M/S A.R ENTERPRISE | 929.37 | 0 | 0 | 70
2312 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | Repairing of Existing OHR of Capacity 90 Cum at WTP Site and Painting work of existing Boundary Wall including Minor Repairing work of PH & Boundary Wall of Belpahari PWSS situated at Naynagora within Binpur Il Block under Jhargram Sub Division under Jhargram Division, PHE Dte. | 72/JHD | 10/01/2025 | 45 | RAMENDRA NATH KAR | 6.59 | 0 | 0 | 95
2313 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | Supply of CIDF Sluice Valve for Belpahari PWSS within Augmentation of Belpaharai W/S Scheme under Jhargram Sub Division under Jhargram Division P.H.E. Dte. . (2nd Call) [Ref: 1st Call of e-NIQ-03 of AE/JSD of 2024-2025, SL. No.-01] | 1101/JSD | 03/12/2024 | 14 | M/S A.R ENTERPRISE | 3.23 | 0 | 0 | 100
2314 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | Repairing of Existing OHR of Capacity 450 Cum at Head Work Site of Belpahari PWSS situated at Hodra within Binpur II Block under Jhargram Sub Division under Midnapore Division, PHE Dte. | 415/JHD | 25/02/2025 | 120 | ANKITA ENTERPRISE | 20 | 0 | 0 | 0
2315 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | Special Repair and Renovation of Pump House at Tarafeni intake pond for Augmentation of Belpahari Water Supply Scheme, Block: - Binpur II within Jhargram Sub Division under Jhargram Division, PHE Dte. ) [Ref. eNIT 05 OF AE/JSD OF 2024-2025, SL No. 04] | 45/JSD | 13/01/2025 | 14 | SAURABH KAR | 1.72 | 0 | 0 | 0
2316 | JHARGRAM | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. , SM/18428 | Augmentation | CLEANING COMPOUND PREMISES OF TARAFENI INTAKE POND WITHIN BELPAHARI PWSS UNDER JHARGRAM SUB DIVISION UNDER JHARGRAM DIVISION P.H.E. DTE. | 975/JSD | 03/10/2024 | 14 | RAMENDRA NATH KAR | 0.94 | 0 | 0 | 100
2317 | JHARGRAM | Jhargram Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. , SM/12327 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 200 cum and staging height 20 mtr. as per approved drawing with allied works of URANSOL & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for JHARGRAM Block, District: - Jhargram. | 2053/JHD | 07/12/2023 | 210 | SATYABRATA BHAUMIK | 71.95 | 0 | 0 | 0
2318 | JHARGRAM | Jhargram Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. , SM/12327 | New | Construction of boundary wall and Allied works At Chakua, Uransol, Patharnala 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1281/JHD | 03/09/2024 | 30 | SUNIL DULE | 37.46 | 0 | 0 | 0
2319 | JHARGRAM | Jhargram Mechanical Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. , SM/12327 | New | new service connection charge for Uransole water supply scheme | 18/JMD | 18/04/2024 | 0 | WBSEDCL | 7.1 | 0 | 0 | 0
2320 | JHARGRAM | Jhargram Mechanical Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. , SM/12327 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uransoal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1245/JMD | 26/05/2023 | 705 | MANAS KUMAR SAHA | 21.75 | 0 | 0 | 40
2321 | JHARGRAM | Jhargram Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. , SM/12327 | New | Laying distribution pipe line under JJM with allied work for URNASAOL AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1107/JHD | 18/07/2023 | 651 | SUNIL DULE | 143.61 | 0 | 0 | 91
2322 | JHARGRAM | Jhargram Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. , SM/12327 | New | Sinking of Tube Well, Pump House, 100 cum GLR, Rising main pipe line, Interconnection pipe line, Installation of display Board, Accommodate FHTC (1451 nos) under JJM with allied work for URNASAOL AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_31 of 2022-23, SL No.-3) | 1836/JHD | 27/10/2023 | 792 | SUNIL DULE | 160.92 | 0 | 0 | 60
2323 | JHARGRAM | Jhargram Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. , SM/12327 | New | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of Propose O.H.R. for Chakkua, Uransol PWSS in Jhargram Block within Jhargram District under Jhargram Division, P.H.E.Dte. | 366/JHD | 20/03/2025 | 30 | M/S. M.D. ENGINEERING & SURVEYS | 1.59 | 0 | 0 | 0
2324 | JHARGRAM | Jhargram Mechanical Division | CHIANBERA ZONE-IV (MALABATI) AND IT'S ADJOINING MOUJAS PWSS , SM/18604 | New | Supply, delivery and installation of horizontal split casing type centrifugal pumping machineries with suitable rated horizontal foot mounted Induction motor sets and allied electro-mechanical accessories for low lift and high lift pumping operations at Chianbera Zone-IV (Malabati) and its adjoining moujas surface water based piped water supply scheme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2280/JMD | 10/08/2023 | 180 | DIPALI CONSTRUCTION | 62.3 | 0 | 0 | 0
2325 | JHARGRAM | Jhargram Division | CHIANBERA ZONE-IV (MALABATI) AND IT'S ADJOINING MOUJAS PWSS , SM/18604 | New | Surveying, planning, designing ,delivery, erection, construction, commissioning and completion in all respect of all Civil, Electrical and Mechanical Works including all allied, related and enabling works for the proposed Chianbera (Malabati) Zone-IV Piped water supply Scheme based on surface water of Open Cast Stone Mine /pond at Chianbera, Block -Binpur-II district of Jhargram | 1830/JHD | 27/10/2023 | 260 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 789.8 | 0 | 0 | 0
2326 | JHARGRAM | Jhargram Division | CHIANBERA ZONE-IV (MALABATI) AND IT'S ADJOINING MOUJAS PWSS , SM/18604 | New | Laying of Distribution pipe line , Community Water Tank, Street Stand post & Inter Connection at Malaboti Village in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | 940/JSD | 02/11/2023 | 21 | SAIKAT DANDAPAT | 2.52 | 0 | 0 | 100
2327 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Bahadurpur P.W.S.S. (Phase-II) within Binpur-I Block , SM/08173 | Retrofitting | Retrofitting to accommodate FHTC under JJM in BAHADURPUR PWSS of Binpur-I Block under Jhargram Division, PHE Dte. ( PHASE - II) | 629/JSD | 22/02/2021 | 30 | MA LAXMI ENTERPRISE | 4.53 | 3.73 | 50 | 0
2328 | JHARGRAM | Midnapore Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. , SM/09376 | Augmentation | Laying of clear water rising main / distribution pipe line with FHTC work, Sinking of 250mm X 150mm dia. Rig bore Tube well, Construction & Commissioning of 150 CuM RCC OHR etc. for Rejuvenation of Ground Based Naupara PWSS to accommodate FHTC in Gopiballavpur-II block within Jhargram district under Jhargram Division, PHE Dte. | 499/MD | 15/03/2022 | 180 | GHOSH ENTERPRISE | 77.25 | 0 | 0 | 0
2329 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. , SM/09376 | Augmentation | Non Destructive Test of OHR for Naopara W/S at Gopiballavpur-II Block under Gopiballavpur Sub Division in Jhargram Division, PHE Dte. | 555/JSD | 27/09/2022 | 15 | SIRCON ENGINEERING SERVICES | 1.71 | 0 | 0 | 1
2330 | JHARGRAM | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. , SM/09376 | Augmentation | Supply, delivery and Installation of new pumping machinery and other electro mechanical accessories at Naupara T/W no -II water supply scheme at Gopiballavpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 1653/JMD | 01/08/2022 | 15 | SHOVAN KUMAR DAS | 4.59 | 0 | 0 | 0
2331 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. , SM/09376 | Augmentation | Laying of clear water rising main / distribution pipe line with FHTC work, Sinking of 250mm X 150mm dia. Rig bore Tube well, Construction & Commissioning of 150 CuM RCC OHR etc. for Rejuvenation of Ground Based Naupara PWSS to accommodate FHTC in Gopiballavpur-II block within Jhargram district under Jhargram Division, PHE Dte |  | 30/08/2022 | 0 | GHOSH ENTERPRISE | 19.8 | 0 | 0 | 0
2332 | JHARGRAM | Midnapore Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. , SM/09376 | Augmentation | Retrofitting to accommodate FHTC under JJM in Naupara PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. | 1412/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 36.77 | 0 | 0 | 80
2333 | JHARGRAM | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. , SM/09376 | Augmentation | Supply, delivery & installation of voltage stabilizer and other allied works at Naupara tubewell no.1 water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | 3638/JMD | 07/12/2022 | 30 | SOUMEN ELECTRIC | 4.41 | 0 | 0 | 0
2334 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. , SM/09376 | Augmentation | Laying of clear water rising main / distribution pipe line with FHTC work, Sinking of 250mm X 150mm dia. Rig bore Tube well, Construction & Commissioning of 150 CuM RCC OHR etc. for Rejuvenation of Ground Based Naupara PWSS to accommodate FHTC in Gopiballavpur-II block within Jhargram district under Jhargram Division, PHE Dte. | 499/MD | 15/03/2022 | 180 | GHOSH ENTERPRISE | 77.25 | 0 | 0 | 90
2335 | JHARGRAM | Midnapore Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. , SM/09376 | Augmentation | Material Requisition To Resource Division | 498/MD | 15/03/2022 | 0 | Resource Division | 15.18 | 0 | 0 | 0
2336 | JHARGRAM | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. , SM/09376 | Augmentation | Supply, delivery, installation of pumping machinery and allied electro-mechanical accessories within newly sunk replacement tube well at P/H no. I of Naupara water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | 2122/JMD | 22/02/2024 | 183 | JAGANNATH ENTERPRISE | 5.13 | 0 | 0 | 100
2337 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. , SM/09384 | Retrofitting | Retrofitting to Accommodate FHTC for Sub-Surface Water Based Piped Water Supply Scheme in Nayagram Block (Part) under JJM under Jhargram Division P.H.E. Dte. |  | 19/07/2022 | 0 | GOBINDA MAITY | 73.78 | 0 | 0 | 0
2338 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. , SM/09384 | Retrofitting | Retrofitting to Accommodate FHTC for Sub-Surface Water Based Piped Water Supply Scheme in Nayagram Block (Part) under JJM under Jhargram Division P.H.E. Dte. |  | 12/08/2022 | 0 | GOBINDA MAITY | 60 | 0 | 0 | 0
2339 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. , SM/09384 | Retrofitting | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 04 (Four) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram Sub-Division PHE Dte.(from 01.01.2023 to 30.04.2023) | 761/JSD | 30/12/2022 | 121 | BIDYUT KUMAR SANTRA | 0.67 | 0 | 0 | 99
2340 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. , SM/09384 | Retrofitting | Lay Left Out Different Dia Pipe with Balace F.H.T.C (700 Nos), Of Nayagram (part) Sub-Surface based pipe water supply scheme under Nayagram Dev. Block under Gopiballavpur Sub-Division of Jhargram Division PHE Dte. the District of Jhargram. | 1871/JHD | 01/11/2023 | 45 | GOBINDA MAITY | 101.65 | 0 | 0 | 36
2341 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. , SM/09384 | Retrofitting | Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January-2023 and February-2023 under Jhargram Division, PHE Dte. | 29A/JRWS | 28/12/2022 | 60 | PROVAT KUMAR DE | 0.93 | 0 | 0 | 100
2342 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. , SM/09384 | Retrofitting | Erection of scaffolding with necessary cross bracing and fixtures and removal after condition assesment for the OHR of Zone-IX of Nayagram (Part) W/S Scheme within Nayagram Dev. Block of Jhargram Division P.H.E Dte. | 663/JSD | 21/07/2023 | 21 | SUNIL DULE | 2.29 | 0 | 0 | 100
2343 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. , SM/09384 | Retrofitting | Material Requisition To Resource Division | 355 | 29/09/2022 | 0 | Resource Division | 0.22 | 0 | 0 | 0
2344 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. , SM/09384 | Retrofitting | Construction of Neutralization Pit at Khanamuri, under Nayagram block (part) sub-surface base water supply scheme under Jhargram Division P.H.E.Dte. (Part-A) & Construction of Neutralization Pit at Barasukjora under Jhargram Division P.H.E.Dte. (Part-B) | 541/JSD | 23/09/2022 | 30 | MAHAVIR SAMPARK PVT. LTD. | 0.29 | 0 | 0 | 100
2345 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. , SM/09384 | Retrofitting | Continuation Order for the Work of "Retrofitting to Accommodate FHTC for Sub-Surface Water Based Piped Water Supply Scheme in Nayagram Block (Part) under JJM under Jhargram Division P.H.E. Dte. (For Zone VIII-B)" | 337/JHD | 26/09/2022 | 60 | GOBINDA MAITY | 95.26 | 0 | 0 | 1
2346 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. , SM/09384 | Retrofitting | Supply delivery of DI Specials, for the work of Nayagram Block (Part) Sub Surface Based Water Supply Scheme under Gopiballavpur Sub Division of Jhargram Division, PHE Dte. | 464/GPSD | 12/12/2023 | 15 | S.B.TRADERS | 3.44 | 0 | 0 | 100
2347 | JHARGRAM | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. , SM/09384 | Retrofitting | Retrofitting to Accommodate FHTC for Sub-Surface Water Based Piped Water Supply Scheme in Nayagram Block (Part) under JJM under Jhargram Division P.H.E. Dte. | 805/MD | 28/04/2022 | 1371 | GOBINDA MAITY | 659.49 | 0 | 0 | 100
2348 | JHARGRAM | Jhargram Mechanical Division | PETBINDHI AND ADJOINING MOUJAS PWSS , SM/12354 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Petbindhi & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1252/JMD | 26/05/2023 | 180 | M/S B.M. ELECTRICAL | 22.09 | 0 | 0 | 0
2349 | JHARGRAM | Jhargram Division | PETBINDHI AND ADJOINING MOUJAS PWSS , SM/12354 | New | Material Requisition To Resource Division | 1595/JHD | 08/09/2023 | 0 | Resource Division | 42.7 | 0 | 0 | 0
2350 | JHARGRAM | Central Drilling | PETBINDHI AND ADJOINING MOUJAS PWSS , SM/12354 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 2104/CDD | 09/02/2024 | 182 | JHARGRAM SPV PRIVATE LIMITED | 110.72 | 0 | 0 | 10
2351 | JHARGRAM | Jhargram Division | PETBINDHI AND ADJOINING MOUJAS PWSS , SM/12354 | New | Soil Investigation and determination of safe bearing capacity and other relevant parameters of soil for construction of Proposed O.H.R. of Petbindhi and Dhadangiri PWSS at Gopiballavpur-II Block under Jhargram Division, P.H.E. Dte. | 1086/JSD | 28/11/2024 | 14 | MOYTEC | 1.34 | 0 | 0 | 0
2352 | JHARGRAM | Jhargram Mechanical Division | PETBINDHI AND ADJOINING MOUJAS PWSS , SM/12354 | New | Quotation for new service connection at PETBINDHI TW-II watyer supply scheme. | 97/JMD | 08/05/2024 | 0 | WBSEDCL | 5.02 | 0 | 0 | 0
2353 | JHARGRAM | Jhargram Mechanical Division | PETBINDHI AND ADJOINING MOUJAS PWSS , SM/12354 | New | Quotation for new service connection at Petbindhi tw-I water supply scheme. | 103/JMD | 08/05/2024 | 0 | WBSEDCL | 3.24 | 0 | 0 | 0
2354 | JHARGRAM | Jhargram Division | PETBINDHI AND ADJOINING MOUJAS PWSS , SM/12354 | New | Sinking of Tube Well , Pump House, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board & Accommodate FHTC(6721 nos) including 02(Two) Years Operation & Maintenance under JJM with allied work for DHADANGIRI, GOBINDAPUR, JUNSOLA, PETBINDHI & MAHAPAL PWSS in Gopiballavpur-II Block including supply of all labour & materials within Gopiballavpur Sub-Division under Jhargram Division, PHE Dte. | 1373/JHD | 16/08/2023 | 465 | M/S. EL-CON | 1574.44 | 0 | 0 | 0
2355 | JHARGRAM | Jhargram Division | PETBINDHI AND ADJOINING MOUJAS PWSS , SM/12354 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Petbindhi and its Adjoining Mouzas PWSS , Block: - Gopiballavpur-II, District: - Jhargram {TYPE - B} (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 857/JSD | 03/09/2024 | 30 | MANAS DATTA | 4.79 | 0 | 0 | 100
2356 | JHARGRAM | Jhargram Division | PETBINDHI AND ADJOINING MOUJAS PWSS , SM/12354 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Pet Bindhi GP at Gopiballavpur-II Block under jhargram Division PHE Dte. (Phase-I) | 1057/JSD | 22/11/2024 | 10 | GOPAL JANA | 0.92 | 0 | 0 | 0
2357 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11479 | New | Material Requisition To Resource Division | 1510/JHD | 05/09/2023 | 0 | Resource Division | 6.73 | 0 | 0 | 0
2358 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11479 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Kismat Balibhasa at Jhargram block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6772/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
2359 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11479 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Parihati at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | 6717/JMD | 23/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 100
2360 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11479 | New | new service connection charges at Chhota Ektal water supply scheme | 71/JMD | 29/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2361 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11479 | New | new service connection charges at Kasitoria water supply scheme | 119/JMD | 13/05/2024 | 0 | WBSEDCL | 2.44 | 0 | 0 | 0
2362 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11479 | New | new service connection for Ashanbani water supply scheme | 4/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2363 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11479 | New | New Service connection charges | 12/JMD | 09/01/2024 | 0 | WBSEDCL | 3.36 | 0 | 0 | 0
2364 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11479 | New | new service connection charges at Kumari water supply scheme | 2/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2365 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11479 | New | NEW SERVICE CONNECTION CHARGES AT KISMAT BAGJHAPA WATER SUPPLY SCHEME | 118/JMD | 13/05/2024 | 0 | WBSEDCL | 2.98 | 0 | 0 | 0
2366 | JHARGRAM | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11479 | New | Fuel & lubricant charges which is used at Rig unit HALCO for boring purpose at the site of Parihati under 179 scheme(SM/11479) under Jamboni block | 422/JMD | 27/11/2024 | 0 | SURAJ SERVICE STATION | 0.54 | 0 | 0 | 0
2367 | JHARGRAM | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. , SM/11479 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | 340/JHD | 09/03/2023 | 872 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 0 | 0 | 50
2368 | JHARGRAM | Jhargram Mechanical Division | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram , SM/12386 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Mahapal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1254/JMD | 26/05/2023 | 180 | SUBHASIS ROY | 22.71 | 0 | 0 | 0
2369 | JHARGRAM | Jhargram Division | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram , SM/12386 | New | Material Requisition To Resource Division | 1547/JHD | 07/09/2023 | 0 | Resource Division | 18.97 | 0 | 0 | 0
2370 | JHARGRAM | Central Drilling | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram , SM/12386 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 2104/CDD | 09/02/2024 | 182 | JHARGRAM SPV PRIVATE LIMITED | 110.72 | 0 | 0 | 10
2371 | JHARGRAM | Jhargram Mechanical Division | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram , SM/12386 | New | Quotation for new service connection at Mahapal tw-I water supply scheme. | 152/JMD | 31/05/2024 | 0 | WBSEDCL | 3.42 | 0 | 0 | 0
2372 | JHARGRAM | Jhargram Mechanical Division | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram , SM/12386 | New | Quotation for new service connection at Mahapal tw-II water supply scheme. | 151/JMD | 31/05/2024 | 0 | WBSEDCL | 3.6 | 0 | 0 | 0
2373 | JHARGRAM | Jhargram Division | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram , SM/12386 | New | Sinking of Tube Well , Pump House, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board & Accommodate FHTC(6721 nos) including 02(Two) Years Operation & Maintenance under JJM with allied work for DHADANGIRI, GOBINDAPUR, JUNSOLA, PETBINDHI & MAHAPAL PWSS in Gopiballavpur-II Block including supply of all labour & materials within Gopiballavpur Sub-Division under Jhargram Division, PHE Dte. | 1373/JHD | 16/08/2023 | 465 | M/S. EL-CON | 1574.44 | 0 | 0 | 0
2374 | JHARGRAM | Jhargram Division | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram , SM/12386 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Mahapal and its Adjoining Mouzas PWSS , Block Gopiballavpur-II, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | 790/JSD | 09/08/2024 | 30 | DEEPSHIKHA ENTERPRISE | 4.68 | 0 | 0 | 90
2375 | JHARGRAM | Jhargram Mechanical Division | SUSHNI AND ADJOINING MOUJAS PWSS , SM/12389 | New | New Service connection |  | 09/11/2023 | 0 | WBSEDCL | 13.78 | 0 | 0 | 0
2376 | JHARGRAM | Jhargram Mechanical Division | SUSHNI AND ADJOINING MOUJAS PWSS , SM/12389 | New | New service connection | 15/Aug | 24/08/2023 | 0 | WBSEDCL | 3.04 | 0 | 0 | 0
2377 | JHARGRAM | Jhargram Division | SUSHNI AND ADJOINING MOUJAS PWSS , SM/12389 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Shushni and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | 526/JRWS | 15/03/2024 | 60 | SWASTIK ENTERPRISE | 4.79 | 0 | 0 | 0
2378 | JHARGRAM | Central Drilling | SUSHNI AND ADJOINING MOUJAS PWSS , SM/12389 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2379 | JHARGRAM | Jhargram Division | SUSHNI AND ADJOINING MOUJAS PWSS , SM/12389 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection ( 7683 Nos), etc.including 02(Two) Years Operation & Maintenance For KAMTA , SUSHNI, BAHIR GRAM, KAPGARI, MURAKATI, MAHISAMURA PWSS Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 1954/JHD | 22/11/2023 | 406 | SIBSANKAR CHOWDHURY | 2070.24 | 0 | 0 | 65
2380 | JHARGRAM | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS , SM/12391 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Bhalukasol and its adjoining mouzas Pipe Water Supply Scheme within Gopibalavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 192/GPSD | 11/03/2024 | 30 | GOPESH DEY | 4.03 | 0 | 0 | 98
2381 | JHARGRAM | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS , SM/12391 | New | Material Requisition To Resource Division | 424/JHD | 13/03/2024 | 0 | Resource Division | 45.06 | 0 | 0 | 0
2382 | JHARGRAM | Jhargram Mechanical Division | BHALUKASOL AND ADJOINING MOUJAS PWSS , SM/12391 | New | Quotation for new service connection at BHALUKASOLE T/W-II water supply scheme. | 13/JMD | 05/04/2024 | 0 | WBSEDCL | 2.56 | 0 | 0 | 0
2383 | JHARGRAM | Jhargram Mechanical Division | BHALUKASOL AND ADJOINING MOUJAS PWSS , SM/12391 | New | New Service connection charges | 34/JMD | 01/02/2024 | 0 | WBSEDCL | 4.62 | 0 | 0 | 0
2384 | JHARGRAM | Central Drilling | BHALUKASOL AND ADJOINING MOUJAS PWSS , SM/12391 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2385 | JHARGRAM | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS , SM/12391 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
2386 | JHARGRAM | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS , SM/12391 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Patina GP at Nayagram Block under jhargram Division PHE Dte. (Phase-I) | 647/GPSD | 19/11/2024 | 10 | PRINT PREVIEW | 0.92 | 0 | 0 | 100
2387 | JHARGRAM | Jhargram Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12334 | New | Material Requisition To Resource Division | 956/JHD | 22/06/2023 | 0 | Resource Division | 33.32 | 0 | 0 | 0
2388 | JHARGRAM | Jhargram Mechanical Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12334 | New | New Service connection | 29/JMD | 29/11/2023 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
2389 | JHARGRAM | Jhargram Mechanical Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12334 | New | New Service connection | 21/JMD | 20/11/2023 | 0 | WBSEDCL | 5.65 | 0 | 0 | 0
2390 | JHARGRAM | Jhargram Mechanical Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12334 | New | New Service Connection Charges for Satkuli P.H - II PWSS | 256/JMD | 10/07/2024 | 0 | WBSEDCL | 6.79 | 0 | 0 | 0
2391 | JHARGRAM | Jhargram Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12334 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House , & Providing Functional Household Tap Connection (6745 Nos), etc. For RAGRA, SATKULI CHARAR, NOAGAON, RAMPURA Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 607/JHD | 04/05/2023 | 881 | GOBINDA MAITY | 1886.45 | 0 | 0 | 20
2392 | JHARGRAM | Central Drilling | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12334 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2393 | JHARGRAM | Jhargram Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12334 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Chhatri, Dhanghori GP at Sankrail Block under jhargram Division PHE Dte. (Phase-I) | 649/GPSD | 19/11/2024 | 10 | MANOJ KUMAR MAHATA | 0.84 | 0 | 0 | 100
2394 | JHARGRAM | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12336 | New | Material Requisition To Resource Division | 1593/JHD | 08/09/2023 | 0 | Resource Division | 30.87 | 0 | 0 | 0
2395 | JHARGRAM | Jhargram Mechanical Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12336 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Amlachati & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1235/JMD | 26/05/2023 | 180 | S.S. GHORAI | 20.79 | 0 | 0 | 70
2396 | JHARGRAM | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12336 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Boundary wall, Installation of display Board, soil investigation under JJM with allied work for AMLACHATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (2nd Call Ref eNIT_18 of 2022-23 , SL No.-1 ) | 1334/JHD | 10/08/2023 | 210 | SUBHANKAR BANERJEE | 199.53 | 0 | 0 | 95
2397 | JHARGRAM | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12336 | New | Sinking of Tube Well , Interconnection pipe line, Laying distribution pipe line, under JJM with allied work for AMLACHATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1324/JHD | 10/08/2023 | 90 | BISHNU PADA NANDI | 23.33 | 0 | 0 | 100
2398 | JHARGRAM | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12336 | New | Construction of Laying distribution pipe line under JJM with allied work for AMLACHATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1323/JHD | 10/08/2023 | 90 | RAMENDRA NATH KAR | 50.31 | 0 | 0 | 95
2399 | JHARGRAM | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12336 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Amlachati and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | 2293/JHD | 04/12/2024 | 30 | TAPAS KUMAR HAZRA | 7.92 | 0 | 0 | 0
2400 | JHARGRAM | Jhargram Mechanical Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12336 | New | New Service connection | 13/JMD | 07/12/2023 | 0 | WBSEDCL | 2.82 | 0 | 0 | 0
2401 | JHARGRAM | Jhargram Mechanical Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12336 | New | New Service connection | 14/JMD | 07/12/2023 | 0 | WBSEDCL | 6.12 | 0 | 0 | 0
2402 | JHARGRAM | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12336 | New | Laying distribution pipe line under JJM with allied work for AMLACHATI AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 650/JHD | 11/05/2023 | 90 | R. CONSTRUCTION | 39.7 | 0 | 0 | 100
2403 | JHARGRAM | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12336 | New | Accommodate FHTC ( 1414 nos) under JJM with allied work for AMLACHATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1415/JHD | 22/08/2023 | 631 | M/S. D.K.H.CONSTRUCTION | 59.36 | 0 | 0 | 30
2404 | JHARGRAM | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12336 | New | Extention distribution pipe line for amlachati and adjoining moujas pwss in jhargram block within jhargram district under jhargram division P.H.E Dte. | 1214/JHD | 27/08/2024 | 45 | SAURABH KAR | 7.97 | 0 | 0 | 90
2405 | JHARGRAM | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. , SM/12336 | New | Construction of boundary wall and Allied works At Amlachati 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 2195/JHD | 22/11/2024 | 30 | RAMENDRA NATH KAR | 12.07 | 0 | 0 | 100
2406 | JHARGRAM | Jhargram Mechanical Division | BHAUDI AND ADJOINING MOUJAS PWSS , SM/12353 | New | New service connection charges for Bhaudit-1 | 186/JMD | 30/03/2024 | 0 | WBSEDCL | 7.55 | 0 | 0 | 0
2407 | JHARGRAM | Central Drilling | BHAUDI AND ADJOINING MOUJAS PWSS , SM/12353 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2408 | JHARGRAM | Jhargram Division | BHAUDI AND ADJOINING MOUJAS PWSS , SM/12353 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
2409 | JHARGRAM | Jhargram Division | BHAUDI AND ADJOINING MOUJAS PWSS , SM/12353 | New | Construction of boundary wall and Allied works At Burimol, Rajband, Bhaudi , Metial 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1077/JHD | 25/07/2024 | 211 | M/S MITRA BROTHERS | 48.9 | 0 | 0 | 40
2410 | JHARGRAM | Jhargram Mechanical Division | MANTIPA & IT'S ADJOINING MOJAS PWSS , SM/12525 | New | NEW SERVICE CONNECTION CHARGES AT MANTIPA-II WATER SUPPLY SCHEME | 155/JMD | 31/05/2024 | 0 | WBSEDCL | 3.5 | 0 | 0 | 0
2411 | JHARGRAM | Jhargram Mechanical Division | MANTIPA & IT'S ADJOINING MOJAS PWSS , SM/12525 | New | NEW SERVICE CONNECTION CHARGES AT MANTIPA-1 WATER SUPPLY SCHEME | 154/JMD | 31/05/2024 | 0 | WBSEDCL | 7.08 | 0 | 0 | 0
2412 | JHARGRAM | Central Drilling | MANTIPA & IT'S ADJOINING MOJAS PWSS , SM/12525 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2413 | JHARGRAM | Jhargram Division | MANTIPA & IT'S ADJOINING MOJAS PWSS , SM/12525 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
2414 | JHARGRAM | Jhargram Division | PATHARNALA AND ADJOINING MOUJAS PWSS , SM/12527 | New | Material Requisition To Resource Division | 1603/JHD | 08/09/2023 | 0 | Resource Division | 37.39 | 0 | 0 | 0
2415 | JHARGRAM | Jhargram Mechanical Division | PATHARNALA AND ADJOINING MOUJAS PWSS , SM/12527 | New | New service connection | 29/AUG | 29/08/2023 | 0 | WBSEDCL | 3.49 | 0 | 0 | 0
2416 | JHARGRAM | Jhargram Mechanical Division | PATHARNALA AND ADJOINING MOUJAS PWSS , SM/12527 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Pathar Nala & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 1247/JMD | 26/05/2023 | 180 | DEY ENTERPRISE | 21.88 | 0 | 0 | 55
2417 | JHARGRAM | Jhargram Division | PATHARNALA AND ADJOINING MOUJAS PWSS , SM/12527 | New | Construction of boundary wall and Allied works At Chakua, Uransol, Patharnala 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1281/JHD | 03/09/2024 | 30 | SUNIL DULE | 37.46 | 0 | 0 | 0
2418 | JHARGRAM | Jhargram Division | PATHARNALA AND ADJOINING MOUJAS PWSS , SM/12527 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation , Accommodate FHTC ( 1700 nos) under JJM with allied work including 02 (Two) Years Operation & Maintenance for PATHARNALA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 371/JHD | 14/03/2023 | 749 | SUNIL DULE | 485.06 | 0 | 0 | 75
2419 | JHARGRAM | Central Drilling | RAJBAND AND ADJOINING MOUJAS PWSS , SM/12842 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2420 | JHARGRAM | Jhargram Division | RAJBAND AND ADJOINING MOUJAS PWSS , SM/12842 | New | Construction of boundary wall and Allied works At Burimol, Rajband, Bhaudi , Metial 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | 1077/JHD | 25/07/2024 | 211 | M/S MITRA BROTHERS | 48.9 | 0 | 0 | 40
2421 | JHARGRAM | Jhargram Division | RAJBAND AND ADJOINING MOUJAS PWSS , SM/12842 | New | Construction of Pump House , 100 cum OHR & 250 Cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, Soil investigation & Accommodate FHTC (3051 nos) under JJM with allied work including 02(Two) Years Operation & Maintanance for RAJBAND, PINDRAKULI & RAJABASA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 667/JHD | 26/03/2025 | 180 | ASIS KUMAR SARANGI | 813.53 | 0 | 0 | 0
2422 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12329 | New | Material Requisition To Resource Division | 1497/JHD | 05/09/2023 | 0 | Resource Division | 37.5 | 0 | 0 | 0
2423 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12329 | New | New Service connection | 27/JMD | 29/11/2023 | 0 | WBSEDCL | 0.12 | 0 | 0 | 0
2424 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12329 | New | New service connection charges | 16/JMD/PFMS/APR | 27/07/2023 | 0 | WBSEDCL | 6.48 | 0 | 0 | 0
2425 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12329 | New | Revused Quotation for New service connection | 30/AUG | 29/08/2023 | 0 | WBSEDCL | 0 | 0 | 0 | 0
2426 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12329 | New | New Service connection | 19/JMD | 20/11/2023 | 0 | WBSEDCL | 5.55 | 0 | 0 | 0
2427 | JHARGRAM | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12329 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Gobindapur & adjoining moujas piped water supply scheme, Block- Sankrail in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | 2261/JMD | 09/08/2023 | 180 | M/S. EMMESS | 21.77 | 0 | 0 | 90
2428 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12329 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of GOBINDAPUR and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 167/GPSD | 05/03/2024 | 30 | SAURABH KAR | 4.26 | 0 | 0 | 100
2429 | JHARGRAM | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12329 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system ,Pump House ,& Providing Functional Household Tap Connection (7650 Nos), etc. For BAKRA, GOBINDAPUR, HARIPURBIRUA, KARKATASOL, Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | 443/JHD | 23/03/2023 | 923 | GOBINDA MAITY | 2154.34 | 0 | 0 | 70
2430 | JHARGRAM | Central Drilling | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. , SM/12329 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2431 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/13678 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Domsole PWSS in Binpur-1I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 153/JSD | 12/08/2021 | 14 | RADIANT | 1.7 | 0 | 0 | 1
2432 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/13678 | Augmentation | Sinking of 1 (One) No. Replacement tube Well with Augmentation & Retrofitting works for Domsole PWSS to accommodate FHTC (Phase-II) in Binpur-II Block under Jhargram Division, PHE Dte. | 647/JHD | 01/12/2022 | 21 | DEBASISH DOGRA | 14.91 | 0 | 0 | 100
2433 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/13678 | Augmentation | Balance Work of Augmentation of Domsole Piped Water Supply Scheme within Binpur-II Block under Jhargram Division P.H.E. Dte. | 970/JSD | 10/11/2023 | 21 | DEBASISH DOGRA | 3.83 | 0 | 0 | 100
2434 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/13678 | Augmentation | Construction of boundary wall, switch room & interconnection of T/Well for augmentation of Domsole water supply scheme with in Binpur-ii block under Jhargram division, P.H.E Dte. | 1398/JHD | 18/08/2023 | 45 | ASOKE KUMAR MAHATA | 8.57 | 0 | 0 | 100
2435 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/13678 | Augmentation | New Service connection charges. | 37/JMD | 23/01/2024 | 0 | WBSEDCL | 3 | 0 | 0 | 0
2436 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/13678 | Augmentation | New Service Connection Charges for Domsole T/W-I PWSS | 324/JMD | 28/08/2024 | 0 | WBSEDCL | 3.7 | 0 | 0 | 0
2437 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/13678 | Augmentation | New Service Connection Charges for Domsole-II PWSS | 323/JMD | 28/08/2024 | 0 | WBSEDCL | 3.7 | 0 | 0 | 0
2438 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. , SM/13678 | Augmentation | REPAIRING OF EXISTING F.H.T.C AT MOUZA DAMSOLE UNDER DAMSOLE W/S SCHEME WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE | 1078/JSD | 27/11/2024 | 14 | SUNIL DULE | 0.97 | 0 | 0 | 0
2439 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | DATA ENTRY FOR FHTC | 8443209 | 27/09/2021 | 0 | GANESH CH NANDY | 0.22 | 0 | 0 | 0
2440 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443457 | 26/03/2021 | 0 | SIDDHESWAR BAG | 0.2 | 0 | 0 | 0
2441 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | DATA ENTRY FOR FHTC | 8443209 | 27/09/2021 | 0 | SOVANDEB MANNA | 0.03 | 0 | 0 | 0
2442 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443117 | 31/05/2021 | 0 | PARTHA PRATIM PAL | 0.06 | 0 | 0 | 0
2443 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443117 | 31/05/2021 | 0 | SANDIP MANNA | 0.04 | 0 | 0 | 0
2444 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | DATA ENTRY FOR FHTC | 8443209 | 27/09/2021 | 0 | ANIRBAN CHAKRABORTY | 0.12 | 0 | 0 | 0
2445 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443117 | 31/05/2021 | 0 | NABOGOPAL ADHIKARI | 0.06 | 0 | 0 | 0
2446 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | 8443117 | 31/05/2021 | 0 | RINTU SAMANTA | 0.11 | 0 | 0 | 0
2447 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443357 | 26/03/2021 | 0 | NABOGOPAL ADHIKARI | 0.12 | 0 | 0 | 0
2448 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN RAMGARH (ZONE-I/II)PWSS | 844311 | 02/08/2021 | 0 | ASIS KUMAR SARANGI | 1.79 | 0 | 0 | 0
2449 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | 8443457 | 26/03/2021 | 0 | SOVANDEB MANNA | 0.17 | 0 | 0 | 0
2450 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I & II) PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | 1403/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 76.93 | 46.49 | 60.44 | 1
2451 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | FHTC imis data entry. | 8443206 | 26/03/2022 | 0 | SHRABONTI BERA | 0.14 | 0 | 0 | 0
2452 | JHARGRAM | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. , SM/06827 | Retrofitting | FHTC imis data entry. | 8443206 | 26/03/2022 | 0 | ANIRBAN CHAKRABORTY | 0.15 | 0 | 0 | 0
2453 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Bhaman Sankrail w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16920 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Satkuli Charar and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2501/JMD | 25/08/2023 | 180 | THE BUSINESS ENGINEERS INDIA | 75.12 | 0 | 0 | 0
2454 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at BANDARBANI AND ADJONING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16691 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Bandarbani and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2774/JMD | 05/09/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 64.39 | 0 | 0 | 0
2455 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Shaluka And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/16699 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Rampura and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2777/JMD | 05/09/2023 | 180 | ELECTRO ENTERPRISES | 32.07 | 0 | 0 | 0
2456 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Gohalmara And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17968 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Gohalmara and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2505/JMD | 25/08/2023 | 180 | SUBHASIS ROY | 75.13 | 0 | 0 | 0
2457 | JHARGRAM | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18002 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at replacement T/W no. I of Kantapahari W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | 2106/JMD | 03/08/2023 | 30 | SUBHASIS ROY | 9.62 | 0 | 0 | 100
2458 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18002 | Augmentation | Sinking of 250x150 mm dai x 150 mtr. Rig bored tubewell(replacement), laying of drainage pipeline for I I backwash water from IEP, construction brick masonary drain, I I replacement of distribution pipe line(partly)and extension of I I distribution pipeline for Kantapahari w/s scheme at Binpur-1 block I I under Jhargram Sub-division within Jhargram Division, PHE Dte. I 13 rd Call (Ref: 1st Call eNIT 21 of 2022-23, 2022-23, SL No.-8, and 2nd I I Call eNIT 08 of 2023-24, SL No.- 5) | 1884/JHD | 03/11/2023 | 60 | SUJOY RANJAN BHOWMICK | 31.11 | 0 | 0 | 90
2459 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18002 | Augmentation | replacement of Distribution pipe line(part) of Kantapahari w/s scheme at Binpur-I Block under Jhargram Sub Division within Jhargram Division,PHE Dte. | 194/JSD | 11/03/2024 | 7 | SAMIR PATRA | 0.96 | 0 | 0 | 100
2460 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18002 | Augmentation | Providing FHTCs (80 nos) in the uncovered pocktes of Kantapahari W/S scheme under Jhargram Sub Division within Jhargram Division,PHE Dte | 652/JSD | 18/07/2023 | 30 | SAMIR PATRA | 4.13 | 0 | 0 | 100
2461 | JHARGRAM | Jhargram Division | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18002 | Augmentation | Providing pending FHTC (70 nos) of Kantapahari W/S scheme under Jhargram Sub Division within Jhargram Division, PHE Dte. | 671/JSD | 25/07/2023 | 30 | GOURMOHAN DAS | 3.39 | 0 | 0 | 95
2462 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Kankridahi w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18003 | Solarisation | Providing solarisation of WBSEDCL energised pumping installation at Upar Baghuasol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2775/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 32.21 | 0 | 0 | 0
2463 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Gobindapur And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18030 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Chingra and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2776/JMD | 05/09/2023 | 180 | ELECTRO ENTERPRISES | 32.07 | 0 | 0 | 0
2464 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Dudkundi w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17114 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Champasol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2500/JMD | 25/08/2023 | 180 | MEGA SOLAR ENERGY | 75.09 | 0 | 0 | 0
2465 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Barasol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18006 | Solarisation | Providing solarisation of WBSEDCL energised pumping installation at Upar Baghuasol and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2775/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 32.21 | 0 | 0 | 0
2466 | JHARGRAM | Jhargram Mechanical Division | Rejuvenation (Phase-II) of Ground Water Based Netai PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18007 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at replacement T/W no. II of Netai W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | 2105/JMD | 03/08/2023 | 30 | P.K. ENGINEERING | 9.62 | 0 | 0 | 17
2467 | JHARGRAM | Jhargram Division | Rejuvenation (Phase-II) of Ground Water Based Netai PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. , SM/18007 | Augmentation | Sinking of 250x150mm dia x150mtr rig bored tubewell,providing pending FHTCs, 2nos IEPs with platforms and Blower with compressor Rooms,Extention distribution pipeline,const.boundary walls at 3 nos t/w site,cons. pumhouse,cons. ground water recharge structure and cons.brick masonary drain of Netai W/s schme in Binpur-I block under Jhargram Sub-division within Jhargram Division,PHE Dte. 2nd Call (Ref eNIT_22 of 2022-23 , SL No.-1 ) | 1614/JHD | 08/09/2023 | 511 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 90.75 | 0 | 0 | 80
2468 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Bhalukasol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/18015 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Chhahazari humtia and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2771/JMD | 05/09/2023 | 180 | A.K. INDUSTRIES | 77.3 | 0 | 0 | 0
2469 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Pusda & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566), Dharampur Zone-II Barbasuli (TSM/015892)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 1351/JMD | 06/06/2023 | 40 | CHAKRABORTY MINING & ENGINEERING | 21.95 | 0 | 0 | 30
2470 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Providing additional man power & driver for Dept. rig unit with supply & delivery of UPVC consumable items with other drilling related allied works for Sinking of (125 mmX 115 mmX 200mtr) RBTW by Rotary/Combination Method at Jamirdiha & its adjacent nine (09) nos villages under Ergoda G.P. in place of (Chinbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 4295/JMD | 24/07/2024 | 40 | SUBHASIS ROY | 15.61 | 0 | 0 | 0
2471 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Sinking tubewell (150 mm X 100 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works at Parulia & its adjacent 2 (two) nos. village under Ergoda G.P. at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 2970/JMD | 12/03/2024 | 12 | CHAKRABORTY MINING & ENGINEERING | 9.06 | 0 | 0 | 65
2472 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Sinking tubewell (150 mm X 100 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works at Kishda & its adjacent 2 (two) nos. village under Ergoda G.P. at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 2968/JMD | 12/03/2024 | 12 | CHAKRABORTY MINING & ENGINEERING | 9.06 | 0 | 0 | 65
2473 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Additional work for Washing and development including determination of yield of Rig Bored Tube Wells at different locations in Ergoda GP under MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | 3490/JMD | 21/06/2024 | 120 | RSA ENTERPRISE | 6.83 | 0 | 0 | 25
2474 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Providing additional man power & driver for Dept. rig unit with supply & delivery of UPVC consumable items with other drilling related allied works for Sinking of (125 mmX 115 mmX 200mtr) RBTW by Rotary/Combination Method at Ergoda G.P. in place of (Chinbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 3871/JMD | 22/07/2024 | 406 | RSA ENTERPRISE | 8.14 | 0 | 0 | 40
2475 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Sinking tubewell (150 mm X 100 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works at Siarkatia & its adjacent 2 (two) nos. village under Ergoda G.P. at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 2969/JMD | 12/03/2024 | 12 | CHAKRABORTY MINING & ENGINEERING | 9.06 | 0 | 0 | 100
2476 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Supply & delivery of different spare parts for LMP-500 and other departmental Rig unit at MMSD(D) store under Jhargram Mechanical Division P.H.E Dte. | 572/W/MMSD(D) | 04/07/2024 | 7 | B. P. TRADING CORPORATION | 0.97 | 0 | 0 | 100
2477 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Supply & delivery of Mud Rotary Drilling tools at MMSD(D) store of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | 576/W/MMSD(D) | 04/07/2024 | 7 | B. P. TRADING CORPORATION | 0.77 | 0 | 0 | 100
2478 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Supply and Delivery of Bucket Holder for mud pump of Halco / 238 / V-596 Rig unit under Jhargram Mechanical Division P.H.E Dte. | 119/W/MMSD(D) | 15/03/2024 | 7 | CHAKRABORTY MINING & ENGINEERING | 0.96 | 0 | 0 | 100
2479 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Supply & delivery of Hydraulic house and other essential spare parts at MMSD(D) store under Jhargram Mechanical Division P.H.E Dte. | 573/W/MMSD(D) | 04/07/2024 | 7 | B. P. TRADING CORPORATION | 0.97 | 0 | 0 | 100
2480 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Supply & delivery of essential drilling tools and Mud pump spare parts for 21D/ LT-500 and KLR/DR/DTH-500 under Jhargram Mechanical Division P.H.E Dte. | 574/W/MMSD(D) | 04/07/2024 | 7 | B. P. TRADING CORPORATION | 0.99 | 0 | 0 | 100
2481 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Supply and Delivery of Piston Rod for mud pump of Halco / 238 / V-596 Rig unit under Jhargram Mechanical Division P.H.E Dte. | 120/W/MMSD(D) | 15/03/2024 | 7 | CHAKRABORTY MINING & ENGINEERING | 0.96 | 0 | 0 | 100
2482 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Supply & delivery of pneumatically air hammer & 165 mm dia Button Bit at MMSD (D) store for DTH drilling works under Midnapore Mechanical Sub-Division (D) in the district of Jhargram. | 551/W/MMSD(D) | 21/06/2024 | 30 | SUDIP ENGINEERING CO. | 6.06 | 0 | 0 | 100
2483 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Material Requisition To Resource Division | 2868/JMD | 07/03/2024 | 0 | Resource Division | 2.16 | 0 | 0 | 0
2484 | JHARGRAM | Jhargram Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under Kanko G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | BP-2023-24-354 | 26/12/2023 | 0 | SURAJ SERVICE STATION | 2.2 | 0 | 0 | 0
2485 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | New Service connection charges. | 8/JMD | 01/03/2024 | 0 | WBSEDCL | 0.42 | 0 | 0 | 0
2486 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Providing fuel and lubricant for rig unit-238/AR/HALCO for boring purpose under Dharampur Zone-II Barbasuli and Adjoining Mouzas PWSS(Amakuli),(SM/17924) for Binpur-II Block of Jhargram District under Jhargram Mechanical Division,PHE Dte | 273/JMD | 26/07/2024 | 0 | SURAJ SERVICE STATION | 0.54 | 0 | 0 | 0
2487 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ergoda G.P. in place of {Dharampur Zone-II Barbasuli} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 28/JMD | 26/04/2024 | 0 | SURAJ SERVICE STATION | 1.04 | 0 | 0 | 0
2488 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Providing fuel and lubricant for rig unit-238/AR/HALCO for boring purpose under Dharampur Zone-II Barbasuli and Adjoining Mouzas PWSS(Siarkatia & Beniadihi),(SM/17924) for Binpur-II Block of Jhargram District under Jhargram Mechanical Division,PHE Dte. upto 21.03.2024 | 126/JMD | 20/05/2024 | 0 | SURAJ SERVICE STATION | 1.04 | 0 | 0 | 0
2489 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | New Service connection charges. | 20/JMD | 11/01/2024 | 0 | WBSEDCL | 0.63 | 0 | 0 | 0
2490 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ergoda G.P. in place of {Dharampur Zone-II Barbasuli} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 13/JMD | 01/03/2024 | 0 | SURAJ SERVICE STATION | 1.68 | 0 | 0 | 0
2491 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ergoda G.P. in place of {Dharampur Zone-II Barbasuli} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 126/JMD | 29/03/2024 | 0 | SURAJ SERVICE STATION | 1.1 | 0 | 0 | 0
2492 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Providing fuel & lubricant for rig unit 238/AR/HALCO for boring purpose under Dharampur Zone-II Barbasuli and Adjoining Mouzas PWSS(Birgeria)(SM/17924) for Binpur-II Block of Jhargram District under Jhargram Mechanical Division PHE Dte. upto 05.04.2024 | 133/JMD | 24/05/2024 | 0 | SURAJ SERVICE STATION | 0.54 | 0 | 0 | 0
2493 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM. Dharampur zone-II Barbasuli and adjoining moujas PWSS (SM/17924). | 266/JMD | 26/07/2024 | 0 | SURAJ SERVICE STATION | 0.82 | 0 | 0 | 0
2494 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | New Service Connection Charges for Birgeria PWSS. DHARAMPUR ZONE-II (BARBASULI) AND ADJOINING MOUJAS PWSS | 419/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2495 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | New Service Connection Charges for Kharipahari PWSS. DHARAMPUR ZONE-II (BARBASULI) AND ADJOINING MOUJAS PWSS | 420/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2496 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | New service connection charge in Ratanpur, Kanko GP, Binpur-1 | 45/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2497 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | New Service Connection Charges for Beniadihi PWSS | 421/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2498 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM for Scheme(SM/17924) Bibarda & Baramsol in Ergoda GP, Binpur -2 | 330/JMD | 29/08/2024 | 0 | SURAJ SERVICE STATION | 1.12 | 0 | 0 | 0
2499 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Supply, delivery of batteries for Rig unit Halco/238/V-596 under Jhargram Mechanical Division P.H.E Dte. | 705/W/MMSD(D) | 13/12/2024 | 7 | CHAKRABORTY MINING & ENGINEERING | 0.47 | 0 | 0 | 100
2500 | JHARGRAM | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS , SM/17924 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ratanpur & adjacent 5 nos. villages under ¿Kanko¿ G.P. in place of {Dharampur Zone-II Barbasuli (TSM/015892)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | 1900/JMD | 27/07/2023 | 543 | RSA ENTERPRISE | 20.25 | 0 | 0 | 100
2501 | JHARGRAM | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS , SM/17928 | New | 62 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-4) | 1835/JHD | 27/10/2023 | 60 | ASIS KUMAR SARANGI | 101.91 | 0 | 0 | 80
2502 | JHARGRAM | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS , SM/17928 | New | Four numbers (4) of yield test process need to be done at Kadamdiha & Pirragerya of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 532/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
2503 | JHARGRAM | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS , SM/17928 | New | Two numbers (2) of yield test process need to be done at Dhangikusum of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 529/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.36 | 0 | 0 | 100
2504 | JHARGRAM | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS , SM/17928 | New | Four numbers (4) of yield test process need to be done at Shushnijubi & Banspahari of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | 530/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
2505 | JHARGRAM | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS , SM/17928 | New | Four numbers (4) of yield test process need to be done at Burijhor & Singaduba of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte | 531/JRWS | 16/03/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
2506 | JHARGRAM | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS , SM/17928 | New | New Service Connection Charges for kodamdiha Burijhor & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2507 | JHARGRAM | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS , SM/17928 | New | New Service Connection Charges for Dhangikusum, Burijhor & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2508 | JHARGRAM | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS , SM/17928 | New | New Service Connection Charges for Burijhor, Burijhor & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2509 | JHARGRAM | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS , SM/17928 | New | New Service Connection Charges for Shusnijubi, Burijhor & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2510 | JHARGRAM | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS , SM/17928 | New | New Service Connection Charges for Pirragerya, Burijhor & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2511 | JHARGRAM | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS , SM/17928 | New | New Service Connection Charges for Singaduba, Burijhor & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2512 | JHARGRAM | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS , SM/17928 | New | 31 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur II Block under Jhargram Division, PHE Dte. | 1714/JHD | 29/09/2023 | 820 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 848.26 | 0 | 0 | 45
2513 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at BAHIR GRAM AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17069 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Parihati and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2773/JMD | 05/09/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD | 77.27 | 0 | 0 | 0
2514 | JHARGRAM | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at BAHIR GRAM AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. , SM/17069 | Solarisation | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Bahirgram and adjacent water supply schemes for ongoing Solarisation works for the purpose of Geotagging in JJM under Jhargram Mechanical Division, P.H.E. Dte. | 3063/JMD | 14/03/2024 | 10 | MUKHERJEE ART CENTRE | 5.28 | 0 | 0 | 100
2515 | JHARGRAM | Jhargram Division | BHATAN DIA AND ADJOINING MOUJAS PWSS , SM/17582 | New | Material Requisition To Resource Division | 420/JHD | 13/03/2024 | 0 | Resource Division | 30.76 | 0 | 0 | 0
2516 | JHARGRAM | Central Drilling | BHATAN DIA AND ADJOINING MOUJAS PWSS , SM/17582 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2517 | JHARGRAM | Jhargram Division | BHATAN DIA AND ADJOINING MOUJAS PWSS , SM/17582 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | 1727/JHD | 30/09/2023 | 459 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
2518 | JHARGRAM | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Material Requisition To Resource Division | 1599/JHD | 08/09/2023 | 0 | Resource Division | 40.95 | 0 | 0 | 0
2519 | JHARGRAM | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Construction of Laying distribution pipe line under JJM with allied work for GOHAL BURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_24 of 2022-23 , SL No.-2 ) | 1400/JHD | 18/08/2023 | 90 | SRIMANTA KUMAR DE | 45.02 | 0 | 0 | 96
2520 | JHARGRAM | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Accommodate FHTC ( 1558 nos) under JJM with allied work for GOHAL BURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 1401/JHD | 18/08/2023 | 90 | M/S. D.K.H.CONSTRUCTION | 64.91 | 0 | 0 | 60
2521 | JHARGRAM | Jhargram Mechanical Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | New Service connection charges. | 95/JMD | 22/02/2024 | 0 | WBSEDCL | 2.86 | 0 | 0 | 0
2522 | JHARGRAM | Jhargram Mechanical Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | ADDITIONAL Quotation for new service connection at GOHALBURA T/W-II water supply scheme. | 101/JMD | 08/05/2024 | 0 | WBSEDCL | 3.32 | 0 | 0 | 0
2523 | JHARGRAM | Jhargram Mechanical Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | New Service connection charges. | 96/JMD | 22/02/2024 | 0 | WBSEDCL | 5.85 | 0 | 0 | 0
2524 | JHARGRAM | Jhargram Mechanical Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM ( scheme code SM/17585 ) | 357/JMD | 13/09/2024 | 0 | SURAJ SERVICE STATION | 0.8 | 0 | 0 | 0
2525 | JHARGRAM | Central Drilling | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2526 | JHARGRAM | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation under JJM with allied work for GOHAL BURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref 1st Call eNIT_24 of 2022-23 , SL No.-1, 2nd Call eNIT_07 of 2023-24 , SL No.-3 ) | 86/JHD | 17/01/2024 | 336 | ANUSKA ENTERPRISE | 131.4 | 0 | 0 | 70
2527 | JHARGRAM | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Supplying and Delivery of Different dia CIDF Sluice Valve, CIDF Pipes & Speci including Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line and Inter Connection between Tube Well and Rising main For Gohal Bura & its Adjoining Mouzas PWSS in Gopiballavpur-I Block under Jhargram Division PHE Dte. | 2190/JHD | 22/11/2024 | 30 | ASSOCIATED ENGINEERS & TRADERS | 9.46 | 0 | 0 | 45
2528 | JHARGRAM | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Chorchita, Kharbandhi GP at Gopiballavpur-II Block under jhargram Division PHE Dte. (Phase-I) | 1031/JSD | 12/11/2024 | 10 | GOPAL JANA | 0.92 | 0 | 0 | 0
2529 | JHARGRAM | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Bhila, Gohalbura and Barasol and its adjoining Mouzas , Block Gopiballavpur-I, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | 313/JHD | 12/02/2025 | 60 | ANUSKA ENTERPRISE | 43.87 | 0 | 0 | 0
2530 | JHARGRAM | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Beliabera GP at Gopiballavpur-II Block under jhargram Division PHE Dte. (Phase-I) | 1030/JSD | 12/11/2024 | 10 | MANOJ KUMAR MAHATA | 0.84 | 0 | 0 | 0
2531 | JHARGRAM | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Construction of Laying distribution pipe line under JJM with allied work for GOHAL BURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-D) | 867/JHD | 08/06/2023 | 455 | ASIS KUMAR SARANGI | 61.58 | 0 | 0 | 95
2532 | JHARGRAM | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Construction of Laying distribution pipe line under JJM with allied work for GOHAL BURA AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-B) | 865/JHD | 08/06/2023 | 455 | ASIS KUMAR SARANGI | 30.88 | 0 | 0 | 90
2533 | JHARGRAM | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS , SM/17585 | New | Construction of Laying distribution pipe line under JJM with allied work for GOHAL BURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-C) | 866/JHD | 08/06/2023 | 455 | ASIS KUMAR SARANGI | 66.32 | 0 | 0 | 95
2534 | JHARGRAM | Jhargram Division | KHARIYARATA AND ADJOINING MOUJAS PWSS , SM/17592 | New | 17 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for BANASPAHARI GP ( CHAKADOBA, KHARIYARATA, KALADABAR PWSS ) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-1 ) | 1657/JHD | 19/09/2023 | 665 | MONDAL PRECISION PRIVATE LIMITED | 508.47 | 0 | 0 | 41
2535 | JHARGRAM | Jhargram Division | KHARIYARATA AND ADJOINING MOUJAS PWSS , SM/17592 | New | New Service Connection Charges for Khariyarata PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2536 | JHARGRAM | Jhargram Division | KHARIYARATA AND ADJOINING MOUJAS PWSS , SM/17592 | New | 34 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for BANASPAHARI GP (CHAKADOBA, KHARIYARATA,KALADABAR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_38 of 2022-23, SL No.-1) | 1668/JHD | 21/09/2023 | 543 | NEER UDYOG | 55.86 | 0 | 0 | 60
2537 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS , SM/17595 | New | 66 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for BHULAVEDA GP (TALPUPUKHURIA, RAGHUNATHPUR, GIDIGHATI, SHIYARBINDA PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-2) | 1834/JHD | 27/10/2023 | 484 | SUNIL DULE | 108.48 | 0 | 0 | 80
2538 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS , SM/17595 | New | Four numbers (4) of yield test process need to be done at Jamjurki & Phulgeria of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 500/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
2539 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS , SM/17595 | New | Four numbers (4) of yield test process need to be done at Dangardiha & Birgi of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 501/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
2540 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS , SM/17595 | New | Four numbers (4) of yield test process need to be done at Raghunathpur & Adargeria of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | 509/JRWS | 15/03/2024 | 30 | SUNIL DULE | 0.72 | 0 | 0 | 0
2541 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS , SM/17595 | New | New Service Connection Charges for Raghunathpur, Raghunatpur & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2542 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS , SM/17595 | New | New Service Connection Charges for Phulgeria, Raghunatpur & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2543 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS , SM/17595 | New | New Service Connection Charges for Dangardiha, Raghunatpur & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2544 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS , SM/17595 | New | New Service Connection Charges for Jamjurki, Raghunatpur & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2545 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS , SM/17595 | New | New Service Connection Charges for Adargeria, Raghunatpur & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2546 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS , SM/17595 | New | New Service Connection Charges for Majugora, Raghunatpur & Adjoining Moujas PWSS | BP-2024-25-111 | 10/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0 | 0
2547 | JHARGRAM | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS , SM/17595 | New | 33 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for BHULAVEDA GP ( TALPUPUKHURIA ,RAGHUNATHPUR ,GIDIGHATI ,SHIYARBINDA PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-2 ) | 1531/JHD | 06/09/2023 | 602 | ASIS KUMAR SARANGI | 910.58 | 0 | 0 | 80
2548 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Material Requisition To Resource Division | 2472/MD | 06/12/2022 | 0 | Resource Division | 61.6 | 0 | 0 | 0
2549 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Laying distribution pipe line, Providing FHTC, soil test & construction of RCC OHR of capacity 600 cum and staging height 20.00 mtr. with allied work for Augmentation of Gopiballavpur PWSS within Gopiballavpur-I Block under Jhargram Division, PHE Dte. |  | 26/08/2022 | 0 | GOBINDA MAITY | 26.65 | 0 | 0 | 0
2550 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Payment for new service connection of WBSEDCL. | 21/JMD/PFMS/SEP | 29/09/2022 | 0 | WBSEDCL | 1.63 | 0 | 0 | 0
2551 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Laying distribution pipe line,Providing FHTC, soil test & construction of R.C.C. Over Head Reservoir of capacity 600 Cum and staging height 20.00 mtr. with allied work For Augmentation of Gopiballavpur PWSS within Gopiballavpur-I Block Under Jhargram Division, P.H.E. Dte. |  | 12/08/2022 | 0 | GOBINDA MAITY | 57 | 0 | 0 | 0
2552 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Laying distribution pipe line,Providing FHTC, soil test & construction of R.C.C. Over Head Reservoir of capacity 600 Cum and staging height 20.00 mtr. with allied work For Augmentation of Gopiballavpur PWSS within Gopiballavpur-I Block Under Jhargram Division, P.H.E. Dte. |  | 03/08/2022 | 0 | GOBINDA MAITY | 172.34 | 0 | 0 | 0
2553 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January-2023 and February-2023 under Jhargram Division, PHE Dte. | 29A/JRWS | 28/12/2022 | 60 | PROVAT KUMAR DE | 0.93 | 0 | 0 | 100
2554 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Material Requisition To Resource Division | 1044/MD | 01/06/2022 | 0 | Resource Division | 157.59 | 0 | 0 | 0
2555 | JHARGRAM | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Material Requisition To Resource Division | 498/MD | 15/03/2022 | 0 | Resource Division | 30.36 | 0 | 0 | 0
2556 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Restoration work due to laying pipeline along the road providing by PHE Jhargram Division under Jhargram Highway Division in the district of Jhargram. | BP-2023-24-346 | 22/12/2023 | 0 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 52.47 | 0 | 0 | 0
2557 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Restoration work for laying pipeline along the roads provided by PHE Jhargram under Jhargram Highway Division in the district of Jhargram | BP-2022-23-91 | 30/12/2022 | 0 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 30 | 0 | 0 | 0
2558 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Supply delivery of Different dia CIDF S/V for the work of ¿ Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block Gopiballavpur - I under Gopiballavpur Sub Division within Jhargram Division, PHE Dte. | 60/GPSD | 22/09/2022 | 15 | GOBINDA MAITY | 4.79 | 0 | 0 | 100
2559 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Continuation work order for Hiring of Diesel driven Commercial Covered four wheeler vehicle on daily basis along with LMV licensed driver for official purpose of Executive Engineer, Jhargram Mechanical Division, PHE Dte. | 641/JMD | 22/03/2023 | 366 | SUJOY RANJAN BHOWMICK | 1.74 | 0 | 0 | 100
2560 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Laying Additional Distribution Pipe line for Augmentation of Gopiballavpur PWSS to accommodate FHTC in Gopiballavpur -I Block within Jhargram District under Jhargram Division, PHE Dte. (Total Length 9615.00 Mtr. ) | 1332/JHD | 10/08/2023 | 60 | GOBINDA MAITY | 41.57 | 0 | 0 | 42
2561 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Providing solarization of WBSEDCL energised pumping installation at Gopiballavpur w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | 2986/JMD | 13/03/2024 | 30 | SAMARPITA ENGINEERING | 6.26 | 0 | 0 | 0
2562 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro mechanical accessories at newly sunk tube well no. I as part of augmentation of Gopiballavpur w/s scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3322/JMD | 14/11/2022 | 120 | ORIENTAL ENGINEERING CO. | 11.03 | 0 | 0 | 100
2563 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro mechanical accessories at newly sunk tube well no. II as part of augmentation of Gopiballavpur w/s scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | 3323/JMD | 14/11/2022 | 120 | DEBJYOTI BASU | 11.04 | 0 | 0 | 100
2564 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Gopiballavpur PWSS (Part-II) in Gopiballavpur Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 275/JSD | 07/10/2021 | 15 | M/S R. DUTTA & CO | 4.52 | 0 | 0 | 100
2565 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Gopiballavpur PWSS (Part-I) in Gopiballavpur Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | 274/JSD | 07/10/2021 | 15 | M/S R. DUTTA & CO | 4.44 | 0 | 0 | 100
2566 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Supply, delivery & installation of various electro-mechanical accessories for repairing & rejuvenation of pump house no.-I of Gopiballavpur w/s scheme in the dist. of Jhargram under Jhargram Mechanical Division P.H.E Dte. | 3058/JMD | 14/03/2024 | 30 | S.S. GHORAI | 8.81 | 0 | 0 | 100
2567 | JHARGRAM | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Supply, delivery & installation of various electro-mechanical accessories for repairing & rejuvenation of pump house no.-II of Gopiballavpur w/s scheme in the dist. of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | 2987/JMD | 13/03/2024 | 30 | SOUMEN ELECTRIC | 8.81 | 0 | 0 | 100
2568 | JHARGRAM | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram , SM/10064 | Augmentation | Laying distribution pipe line,Providing FHTC, soil test & construction of R.C.C. Over Head Reservoir of capacity 600 Cum and staging height 20.00 mtr. with allied work For Augmentation of Gopiballavpur PWSS within Gopiballavpur-I Block Under Jhargram Division, P.H.E. Dte. | 818/MD | 29/04/2022 | 1370 | GOBINDA MAITY | 732.35 | 0 | 0 | 100
2569 | JHARGRAM | Jhargram Division | DOMAHANI AND ADJOINING MOUJAS PWSS , SM/12438 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line,Installation of display Board, soil investigation ,including 02(Two) Years Operation & Maintenance & Accommodate FHTC (1160 nos) under JJM with allied work for Domahani PWSS in Jamboni Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | 347/JHD | 10/03/2023 | 180 | ASIS KUMAR SARANGI | 387.03 | 0 | 0 | 0
2570 | JHARGRAM | Jhargram Division | DOMAHANI AND ADJOINING MOUJAS PWSS , SM/12438 | New | Material Requisition To Resource Division | 1604/JHD | 08/09/2023 | 0 | Resource Division | 13.75 | 0 | 0 | 0
2571 | JHARGRAM | Jhargram Division | DOMAHANI AND ADJOINING MOUJAS PWSS , SM/12438 | New | Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_4_A under Jhargram Division in the District of Jhargram. | 347/JHD | 28/09/2022 | 120 | M/S. SANKAR KUMAR NAG | 22.33 | 0 | 0 | 100
2572 | JHARGRAM | Central Drilling | DOMAHANI AND ADJOINING MOUJAS PWSS , SM/12438 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2573 | JHARGRAM | Jhargram Division | DOMAHANI AND ADJOINING MOUJAS PWSS , SM/12438 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Kapgari GP at Jambani Block under jhargram Division PHE Dte. (Phase-I) | 370/JRWS | 04/10/2024 | 10 | MANOJ KUMAR MAHATA | 0.67 | 0 | 0 | 100
2574 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | HP Intel core i5 12500 16GB/0GB HDD/ Windows 10 professional | BP-2023-24-105 | 28/06/2023 | 0 | IONET | 4.97 | 0 | 0 | 0
2575 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply of Printer Device and Almirah for Jhargram Division office. | BP-2023-24-113 | 06/07/2023 | 0 | IONET | 0.44 | 0 | 0 | 0
2576 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | SUPPLYOFMICROTECLINEINTERACTIVEUPSFORJHARGRAMDIVISIONPHEDTE | BP-2023-24-253 | 13/10/2023 | 0 | IONET | 0.25 | 0 | 0 | 0
2577 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | LLOYD 2 ton, 3 Star AC | BP-2023-24-106 | 28/06/2023 | 0 | NEXUS ENTERPRISE | 1.48 | 0 | 0 | 0
2578 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | BP-2023-24-256 | 18/10/2023 | 0 | SPARSH COOL WAVES | 0.15 | 0 | 0 | 0
2579 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | BP-2023-24-252 | 13/10/2023 | 0 | EASY DAY ENTERPRISE | 3.69 | 0 | 0 | 0
2580 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | BP-2023-24-255 | 18/10/2023 | 0 | NEXUS ENTERPRISE | 0.96 | 0 | 0 | 0
2581 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply of office Chair for the use of Executive Engineer, Jhargram Division, PHE Dte. | BP-2023-24-305 | 29/11/2023 | 0 | RVS ENTERPRISE | 0.12 | 0 | 0 | 0
2582 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | BP-2023-24-370 | 04/01/2024 | 0 | IONET | 3.86 | 0 | 0 | 0
2583 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | BP-2023-24-372 | 04/01/2024 | 0 | IONET | 5 | 0 | 0 | 0
2584 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | BP-2023-24-371 | 04/01/2024 | 0 | EASY DAY ENTERPRISE | 2 | 0 | 0 | 0
2585 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | 23-24-372 | 03/07/2024 | 0 | IONET | 0.25 | 0 | 0 | 0
2586 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | BP-2024-25-167 | 09/08/2024 | 0 | EASY DAY ENTERPRISE | 4.98 | 0 | 0 | 0
2587 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | BP-2024-25-166 | 09/08/2024 | 0 | IONET | 3.92 | 0 | 0 | 0
2588 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | BP-2024-25-193 | 09/09/2024 | 0 | ARDIGITRONICS | 0.12 | 0 | 0 | 0
2589 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | BP-2023-24-361 | 02/01/2024 | 0 | SEATING SOLUTION ENTERPRISE | 0.73 | 0 | 0 | 0
2590 | JHARGRAM | Jhargram Division | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. , SM/16630 | Support-MIS | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | BP-2023-24-373 | 04/01/2024 | 0 | NEXUS ENTERPRISE | 0.99 | 0 | 0 | 0
2591 | JHARGRAM | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. , SM/16680 | Support-WQMSP | Construction of District Water Testing Laboratory under Jhargram Division, PHE Dte. | 1843/JHD | 31/10/2023 | 608 | SAIKAT DANDAPAT | 45.24 | 0 | 0 | 33
2592 | JHARGRAM | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. , SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | 2203/JHD | 14/10/2025 | 60 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 13.3 | 0 | 0 | 0
2593 | JHARGRAM | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. , SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | 2204/JHD | 14/10/2025 | 60 | UTSAV AGENCY | 2.36 | 0 | 0 | 0
2594 | JHARGRAM | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. , SM/16680 | Support-WQMSP | Engagement of 04(Four) nos. Laboratory Personnel ( One Chemist , One Bacteriologist, One Laboratory Assistant, Sampling Assistant) for regular analysis, testing and monitoring of water samples for District Laboratory of Jhargram under Jhargram Division, P.H.E. Dte. (From 01/11/2025 to 31/10/2026) | 2208/JHD | 14/10/2025 | 365 | GOBINDA MAITY | 5.99 | 0 | 0 | 0
2595 | JHARGRAM | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. , SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | 2205/JHD | 14/10/2025 | 60 | SCIENTIFIC VENTURES | 1 | 0 | 0 | 0
2596 | JHARGRAM | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. , SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | 2207/JHD | 14/10/2025 | 60 | SAKTI ENTERPRISE | 0 | 0 | 0 | 0
2597 | JHARGRAM | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. , SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | 2206/JHD | 14/10/2025 | 60 | LAB SOLUTION | 1.4 | 0 | 0 | 0
2598 | JHARGRAM | Jhargram Mechanical Division | Supply, delivery of Computer and other allied accessories (through GeM portal) for Office of the Executive Engineer, Jhargram Mechanical Division, PHE Dte. in the district of Jhargram , SM/18717 | Support-MIS | Supply, delivery of Computer and other allied accessories (through GeM portal) for Office of the Executive Engineer, Jhargram Mechanical Division, PHE Dte. in the district of Jhargram | 42/JMD | 24/01/2024 | 0 | IONET | 3.64 | 0 | 0 | 0
2599 | JHARGRAM | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Jhargram District. , SM/08978 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District. | 4724/RS | 18/08/2022 | 365 | KARNAJORA AGNIBINA SEVA SAMITY | 174.96 | 0 | 0 | 96
2600 | JHARGRAM | Jhargram Division | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM , SM/16656 | Support-WQMSP | Enhancement of monthly remuneration of NGO lab personnel for the month of June,23 to August'2023 | BP-2023-24-206 | 27/09/2023 | 0 | JHARGRAM MAHAKUMA JANASIKSHA PRASAR SAMITY | 1.35 | 0 | 0 | 0
2601 | JHARGRAM | Jhargram Division | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM , SM/16656 | Support-WQMSP | Remuneration Bill to the Laboratory Personnel's of NGO managed Laboratories. | BP-2023-24-55 | 29/05/2023 | 0 | JHARGRAM MAHAKUMA JANASIKSHA PRASAR SAMITY | 2.31 | 0 | 0 | 0
2602 | JHARGRAM | Jhargram Division | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM , SM/16656 | Support-WQMSP | Bill for remuneration of Lab Personnel for the months of Jan'23, Feb'23, Mar'23, Apr'23, May'23 | BP-2023-24-111 | 04/07/2023 | 0 | JHARGRAM MAHAKUMA JANASIKSHA PRASAR SAMITY | 2.25 | 0 | 0 | 0
2603 | JHARGRAM | Jhargram Division | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM , SM/16656 | Support-WQMSP | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM | BP-2023-24-535 | 19/03/2024 | 0 | JHARGRAM MAHAKUMA JANASIKSHA PRASAR SAMITY | 1.35 | 0 | 0 | 0
2604 | JHARGRAM | Jhargram Division | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM , SM/16656 | Support-WQMSP | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM | BP-2024-25-294 | 27/11/2024 | 0 | JHARGRAM MAHAKUMA JANASIKSHA PRASAR SAMITY | 1.53 | 0 | 0 | 0
2605 | JHARGRAM | Jhargram Division | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM , SM/16656 | Support-WQMSP | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM | BP-2024-25-113 | 15/07/2024 | 0 | JHARGRAM MAHAKUMA JANASIKSHA PRASAR SAMITY | 1.35 | 0 | 0 | 0
2606 | JHARGRAM | Jhargram Division | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM , SM/16656 | Support-WQMSP | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM | BP-2023-24-385 | 10/01/2024 | 0 | JHARGRAM MAHAKUMA JANASIKSHA PRASAR SAMITY | 1.51 | 0 | 0 | 0
2607 | JHARGRAM | Jhargram Division | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM , SM/16656 | Support-WQMSP | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM | BP-2023-24-386 | 10/01/2024 | 0 | JHARGRAM MAHAKUMA JANASIKSHA PRASAR SAMITY | 0.4 | 0 | 0 | 0
2608 | JHARGRAM | Jhargram Division | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission , SM/18228 | Support-WQMSP | Procurement of 1 no. of Mobile Laboratory Van (MLV) complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with Chemicals, equipment etc. for onsite testing, smart phone with preloaded water quality app synchronized with PHED water quality dashboard and safety gear for resource personnel for water quality testing in remote areas including external designing and painting for IEC propaganda complete with IEC audio visual aids as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. | 1908/JHD | 27/09/2024 | 365 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 75.86 | 0 | 0 | 60
2609 | JHARGRAM | Resource | Design Development and Installation of web and mobile application based Monitoring system for Duel use Solar PWSS at different pin point location district Jhargram , SM/08059 | Support-MIS | Upkeepment and Hosting of WhatsApp bot Platform to Optimize Data Accessibility, Enhanced Service Delivery and Operational Efficiency ,Public Health Engineering Department (PHED), Govt. of West Bengal. | 1439/RS | 03/07/2025 | 365 | HORIZEN | 48.1 | 0 | 0 | 26
Total | [9 empty] | 1968350.25 | 432.29 | 0.02