## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Formal order for the work of Supplying laying of 90 mm dia UPVC pipe bypass connection for Amlouka gram from Banguri more of Improvement of Jamgora-Jagannathpur W/s Scheme under DWSD ,PHE Dte (SL-02) | 135/DWSD | 02/02/2022 | 15 | MD JAWED KHAN | 6.6 | 0 | 0 | 50
2 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Continuation order for the work of Providing functional house hold tap connection in connection with JJM at Shyamsundarpur Mouza(JL-07) ,block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte. | 245/DWSD | 28/02/2022 | 15 | PRAVAT SARKAR | 4.97 | 0 | 0 | 50
3 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at Hazra para ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte | 312/DWSD | 20/02/2023 | 15 | GHOSH ENTERPRISE | 6.92 | 6.92 | 100 | 0
4 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Acceptance cum formal order for the work of water supply arrangement at Muslim Para ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students),Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte | 313/DWSD | 20/02/2023 | 15 | RUBY CONSTRUCTION | 6.96 | 6.96 | 100 | 0
5 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at Akandara Adibasipara ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte | 314/DWSD | 20/02/2023 | 15 | JUBILEE CONSTRUCTION | 6.95 | 6.95 | 100 | 0
6 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement 1(One) No ICDS Centre at Shyambazar for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte | 315/DWSD | 20/02/2023 | 15 | KIRON ENTERPRISE | 12.15 | 11.92 | 98.13 | 0
7 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Acceptance cum formal order for the work of water supply arrangement at Jatgoria Junior High School ICDS Centre having no Electricity power supply to provide solar power connection (For 350 Nos Students),Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte | 316/DWSD | 20/02/2023 | 15 | BASANTI TRADERS | 6.95 | 6.95 | 100 | 0
8 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Formal order for the work of Laying of branch pipe line at Basudevpur ,Binodpur and Sashipur mouza with its adjoining area UPVC pipe of Kanchanpur W/s Scheme under DWSD, PHE Dte (SL-08) | 834/DWSD | 24/05/2021 | 15 | T.M.CONCRETE CREATION PVT LTD | 10.76 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road at Madhammath Subashpally sher para of Kanksa mouza Zone-II Ph-II W/s Scheme under DWSD ,PHE Dte (SL-05) | 1407/DWSD | 29/09/2021 | 15 | SWATI CORPORATION | 4.56 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Acceptance cum formal order for the work of Connection provide to different Govt offices ,Schools,(Kanksa Thana,Kanksa Girls high Schools,Kanksa GP,TC Pur GP & 6 Nos ICDS at Kanksa mouza under DWSD,PHE Dte (SL-01) | 1403/DWSD | 23/09/2021 | 15 | SWATI CORPORATION | 3.03 | 0 | 0 | 0
11 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Acceptance cum formal order for the work of Dismantling of concre road and reconcreting the same at poral para,Khadrapara ,near Kanksa Police Station under pass to towards kanksa PS and Sher para under command areaof Kanksa zone-II W/s Scheme for providing of FHTC under DWSD,PHE Dte (SL-04) | 1406/DWSD | 23/09/2021 | 15 | SWATI CORPORATION | 4.56 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at Ruidas para ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte | 310/DWSD | 20/02/2023 | 15 | QUICK PAL SUPPLIERS | 6.96 | 6.96 | 100 | 100
13 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at Akandara Bouri para ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte | 311/DWSD | 20/02/2023 | 15 | M/S MONDAL ENTERPRISE | 6.94 | 6.87 | 100 | 0
14 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at Borobigha Adibasi para ICDS Centre of Domra Bagdipara ICDS, Domra Bagdipara,Satkahania billpara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte | 263/DWSD | 15/02/2023 | 25 | BISHAL ENTERPRISE | 21.24 | 21.24 | 100 | 0
15 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block at Basudevpur village, Kanchanpur (N),Talbahari under Augmentation of Kanchanpur piped W/s Scheme (Part- A) | 1296/DWSD | 07/08/2023 | 15 | M/S MANDAL ENTERPRISE | 5.87 | 5.87 | 100 | 100
16 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block at Kanchanpur under Augmentation of Kanchanpur piped W/s Scheme (Part- B) | 1298/DWSD | 07/08/2023 | 15 | M/S BANERJEE CONSTRUCTION | 7.05 | 7.05 | 100 | 100
17 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07518 | Retrofitting | Continuation order for Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block at Basudevpur village, Kanchanpur (N),Talbahari under Retrofitting of ARRAH piped W/s Scheme (Part- A) | 1376/DWSD | 14/08/2023 | 7 | M/S MANDAL ENTERPRISE | 1.72 | 1.72 | 100 | 100
18 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07561 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-IV), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | 963/RCD-I | 07/06/2021 | 30 | DAS & CHAKRABORTY | 45.92 | 10.12 | 100 | 0
19 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07561 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-IV), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | 962/RCD-I | 07/06/2021 | 30 | ASHA CONSTRUCTION | 45.95 | 83.29 | 172.33 | 0
20 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07561 | Retrofitting | Supplying, aligning and laying of HDPE line (parallel to main distribution) at Ghidoba, Kushum Danali and extension of pipe line at Ghiadoba village for providing FHTC under Chotkara Kanskuli water supply scheme under RCFA Division-I PHE Dte.(Sl no 07) | 636/RCD 1 | 09/03/2022 | 15 | DAS & CHAKRABORTY | 3.01 | 2.45 | 100 | 0
21 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07561 | Retrofitting | Supplying, aligning and laying of UPVC line (parallel to main distribution) at Malladihi Hospital para towards Chayanpur for providing FHTC work under Chotkara Kanskuli water supply scheme under RCFA Division-I PHE Dte. (Sl no 09) | 638/RCD 1 | 09/03/2022 | 15 | MD AAMIR KHAN | 2.82 | 0 | 0 | 0
22 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07561 | Retrofitting | Additional work for laying of different dia DI (K7) & HDPE pipe line with other allied work from Dabor OHR Zone-II (Lohat, Phulberiya, Patal, Sadhana, Madhaichak, Shyamdihi etc.) distribution Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) (Sl No. 08) | 251/RCD-I | 01/02/2022 | 15 | ASHA CONSTRUCTION | 2.18 | 1.96 | 89.76 | 0
23 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07561 | Retrofitting | Supplying, aligning and laying of HDPE line (Parallel to main distribution) for Ghidoba village & Kushum Danali West side for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 09) | 252/RCD-I | 01/02/2022 | 20 | GITA CONSTRUCTION | 4.98 | 4.71 | 100 | 0
24 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07561 | Retrofitting | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kushum Danali more towords Ghidoba West side for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 10) | 253/RCD-I | 01/02/2022 | 20 | GITA CONSTRUCTION | 4.99 | 4.71 | 100 | 0
25 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07561 | Retrofitting | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kushum Danali more towords Ghidoba East side under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 15) | 257/RCD-I | 01/02/2022 | 20 | B.T.M CONCERN | 4.98 | 4.75 | 100 | 0
26 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07561 | Retrofitting | Extension of UPVC Pipe line at Uttarrampur and Part of Kalisanko including connection to different ICDS & FP Schools for providing FHTC under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl no 01) | 630/ RCD I | 09/03/2022 | 15 | KHEPI MAA TRADERS | 4.18 | 2.74 | 100 | 0
27 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07561 | Retrofitting | Additional work of supplying, aligning and laying of 160 mm dia HDPE pipe line for distribution line at Bolkundi village under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | 250/RCD-I | 01/02/2022 | 15 | DAS & CHAKRABORTY | 2.05 | 2.05 | 100 | 0
28 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07561 | Retrofitting | Sinking of 4 (Four) nos river bed tube wells including collecting main at Runakuraghat for Flood damaged at river Ajoy under Chotkara Kanskuli water supply scheme under RCFA Division-I PHE Dte. (Sl No. 14) | 1093/RCD I | 13/05/2022 | 30 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 4.99 | 4.73 | 94.9 | 100
29 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Improvement of Babani Zone PWSS for Providing FHTC Within Barabani Block of Paschim Bardhaman District , SM/07562 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Barabani Zone PWSS, Block- Barabani of Improvement of Barabani Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | 951/RCD-I | 07/06/2021 | 30 | TARAPRASAD SARKAR | 30.12 | 24.47 | 100 | 0
30 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Improvement of Babani Zone PWSS for Providing FHTC Within Barabani Block of Paschim Bardhaman District , SM/07562 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Barabani Zone PWSS, Block- Barabani of Improvement of Barabani Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | 950/RCD-I | 07/06/2021 | 30 | UMA ENTERPRISE | 30.02 | 30.7 | 88.13 | 0
31 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Improvement of Babani Zone PWSS for Providing FHTC Within Barabani Block of Paschim Bardhaman District , SM/07562 | Retrofitting | Block Level Orientation Programme involving PRI functionaries on Jal Jeevan Mission and its components at Barabani, Salanpur, Jamuria, Pandabeswar, Raniganj, Andal, Kansha & Durgapur Faridpur Block in the Districts of Paschim Bardhaman under RCFA Division-I PHE Dte. | Camp_02_8_Nos_Block_AE_II | 26/09/2023 | 30 | MUKHERJEE TRADERS | 3.79 | 3.79 | 100 | 100
32 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Suri Para, Bisakhalakhi Tala (Sansad-VI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1870/RCD-I | 28/10/2021 | 30 | JAYANTA DATTA | 18.06 | 18.06 | 100 | 0
33 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Subhas Para & Chunari Para (Sansad-III) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1867/RCD-I | 28/10/2021 | 30 | DAS & CHAKRABORTY | 18.1 | 18.09 | 100 | 0
34 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Puratan Mushlim Para & Dhibarpara (Sansad-VII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1871/RCD-I | 28/10/2021 | 30 | RUBY CONSTRUCTION | 15.67 | 15.67 | 100 | 0
35 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Kankardanga (Sansad-VIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1872/RCD-I | 28/10/2021 | 30 | MS KALYAN ENTERPRISE | 10.6 | 10.6 | 100 | 0
36 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dangal Para (Sansad-XI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1873/RCD-I | 28/10/2021 | 30 | SNEHA ELECTRIC | 13.31 | 13.3 | 100 | 0
37 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Sukho Para (Sansad-XX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1879/RCD-I | 28/10/2021 | 30 | SOMNATH SAMANTA | 15.63 | 15.63 | 100 | 0
38 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Asthalpara (Sansad-XIV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1875/RCD-I | 28/10/2021 | 30 | UNITED CONSTRUCTION | 13.32 | 13.32 | 100 | 0
39 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Mulimpara & Ruidaspara (Sansad-XIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1874/RCD-I | 28/10/2021 | 30 | MD. JAWED KHAN | 18.16 | 18.15 | 100 | 0
40 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Mukherjeepara & Khad Para (Sansad-XVII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1877/RCD-I | 28/10/2021 | 30 | SIMA ENTERPRISE | 15.72 | 15.71 | 100 | 0
41 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Pathakpara (Sansad-XV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1876/RCD-I | 28/10/2021 | 30 | B.T.M CONCERN | 15.25 | 15.25 | 100 | 0
42 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order Laying of different dia distribution pipe line at Sukopara (Part), Bauripara (Part) etc adjacent area at Ukhra Gram Panchayet (Sansad-XX) Augmentation of RCFA Part-II (Zone-2A) W/S Scheme under RCFA Division-I PHE Dte. | 1275/RCD-I | 27/03/2023 | 15 | SOMNATH SAMANTA | 3.25 | 2.95 | 90.55 | 0
43 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Bazar Area (Sansad-V) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1869/RCD-I | 28/10/2021 | 30 | UMA ENTERPRISE | 21.3 | 6.08 | 100 | 0
44 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Teli Para (Sansad-XVIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1878/RCD-I | 28/10/2021 | 30 | M/S K & KONAR CONSTRUCTION | 17.13 | 11.64 | 100 | 0
45 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Hanuman Danga & Saradapally (Sansad-IV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1868/RCD-I | 28/10/2021 | 30 | DAWN CONSTRUCTION | 26.54 | 20.57 | 100 | 0
46 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | hire charges & fuel bill of Ranajit Auto | 220/23-24 | 22/08/2023 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0 | 0
47 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Spiral Binding | 185/23-24 | 10/08/2023 | 0 | MUKHERJEE TRADERS | 0.68 | 0 | 0 | 0
48 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Hire charge and fuel bill for the month o June 2023 to August 2023 | 323/23-24 | 17/10/2023 | 0 | KHEPI MAA TRADERS | 1.19 | 0 | 0 | 0
49 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Submissin of quarterly revised return for non salary return Bill no 7236 to 7339 | 367/23-24 | 10/11/2023 | 0 | SHRESTHA & ASSOCIATES | 0.36 | 0 | 0 | 0
50 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Transporting loading and unloading of jackets Banners etc for pump operator and valve operation at sites under JJM | 179/23-24 | 08/08/2023 | 0 | SHARMA ENGINEERING WORKS | 0.18 | 0 | 0 | 0
51 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | fuel bill shyamal maji jyly 2023 | 220/23-24 | 24/08/2023 | 0 | RANAJIT AUTO | 0.16 | 0 | 0 | 0
52 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Fuel bill for WB 37 D 0482 for Oct 23 and Nov 23 | 430/23-24 | 20/12/2023 | 0 | RANAJIT AUTO | 0.29 | 0 | 0 | 0
53 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Fuel and vehicle bill for Feb 2023 to June 23 | 234/23-24 | 04/09/2023 | 0 | NIRMALA TRADERS | 1.19 | 0 | 0 | 0
54 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Khepi Maa Traders | 215/23-24 | 22/08/2023 | 0 | KHEPI MAA TRADERS | 1.16 | 0 | 0 | 0
55 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Vehicle bill for 37 D 0482 Oct 2023 and nov 2023 | 429/23-24 | 20/12/2023 | 0 | SHYAMAL MAJI | 0.3 | 0 | 0 | 0
56 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Supply of it periphersls under sub district laboratory | 92/24-25 | 13/06/2024 | 0 | SHARMA ENGINEERING WORKS | 0.02 | 0 | 0 | 0
57 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order Laying of different dia HDPE pipe line and allied works at Kankardanga Part (Sansad-VIII) at Ukhra area under Augmentation of RCFA Part-II (Zone-2A) PWSS under RCFA Division-I PHE Dte. (Sl No. 18) | 1162/RCD-I | 24/03/2023 | 15 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 1.42 | 1.29 | 90.79 | 100
58 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-E) | 2333/RCD-I | 17/12/2021 | 30 | TARAPRASAD SARKAR | 14.37 | 2.26 | 100 | 100
59 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Construction of 150 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Augmentation of Jamuria Rural (Zone-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (2nd Call) | 1631/RCD-I | 26/04/2023 | 366 | UNITED CONSTRUCTION | 69.15 | 20.75 | 100 | 100
60 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) , SM/09059 | Retrofitting | Acceptance cum work order for Sinking of 02 (Two) nos. river bed tube wells including collecting main and other allied works at Narayankuri H/W site at Damodar river under Narayankuri Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | 2242/RCD-I | 17/07/2023 | 30 | MS KALYAN ENTERPRISE | 12.81 | 11.11 | 100 | 100
61 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of Construction of Pump house cum chlorine room and switch room at Molandighi (Tube well no ¿III) sites under Bistupur piped W/S scheme under DWSD,PHE Dte (SL-21) | 1810/DWSD | 29/12/2021 | 45 | DARPAN DAS & CO. | 4.67 | 3.59 | 76.91 | 0
62 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Formal order for the work of Sinking of 1 No (300X200 mm) dia tube well 120 mtr deep by DR rig method using PVC pipe and fiber glass reinforced epoxy resin slotted at Tube well no 3 site of Bistupur piped W/s Scheme under Durgapur W/s Division, PHE Dte (SL-02) | 1679/DWSD | 01/12/2021 | 25 | SK. ALIM | 9.32 | 6.7 | 71.96 | 0
63 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Fomal order for the work of Supplying laying and alinging of UPVC distribution pipe line (distribution system Part-B) and allied works including FHTC and connecrtion provided to Kuldiha,Pathardihi,Keshabpur moluzas under command area of Bistupur piped W/s Scheme under Durgapur W/s Division, PHE Dte | 148/DWSD | 07/02/2022 | 30 | TARA CONSTRUCTION | 147.47 | 139.68 | 94.72 | 0
64 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of Construction of Pump house cum chlorine room and switch room at Molandighi (Tube well no ¿II) sites under Bistupur piped W/S scheme under DWSD,PHE Dte | 1808/DWSD | 29/12/2021 | 45 | CHATTERJEE CONSTRUCTION | 4.67 | 3.59 | 76.9 | 0
65 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Formal order for the work of Laying and aligning of DI K9 Rising main pipe line supplying of DI Specials and valves and other allied works under Command area of Bistupur piped W/s Scheme under DWSD PHE Dte (SL-12) | 749/DWSD | 10/05/2022 | 20 | MAK CONSTRUCTION CO. | 17.52 | 14.97 | 85.47 | 0
66 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of Supplying laying and aligning of UPVC distributing pipe line and allied works including FHTC and connection providing Kuldiha(JL-53),Pathardiha(JL-52) ,Keshbpur(JL-66) Mouzas under command area of Bistupur distribution system (Part-B) of Bistupur piped W/S Scheme under DWSD,PHE Dte. (SL-03) | 815/DWSD | 21/05/2022 | 25 | TARA CONSTRUCTION | 54.66 | 42.36 | 77.49 | 0
67 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works at Molandighi H/W site Pump house No-3 Tube well No-03 for Bistupur pipe W/S Scheme under DWSD,PHE Dte (SL-06) | 1061/DWSD | 08/07/2022 | 25 | DARPAN DAS & CO. | 4.82 | 3.02 | 62.62 | 0
68 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of supplying and laying of 150 mm dia MS water carrying pipe with making necessary bend and others allied works at node point -414,323 and 540 near Kuldiha boys club ,Kuldiha More bus stand and Kuldiha bordoba More, Kanksa Block under Bistupur piped W/S Scheme under DWSD,PHE Dte. (SL-04) | 1577/DWSD | 02/11/2022 | 15 | TARA CONSTRUCTION | 37.4 | 33.92 | 90.68 | 0
69 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of Construction of Pump house cum chlorine room and switch room at Bistupur Head work sites (Tube well no ¿I) under Bistupur piped W/S scheme under DWSD,PHE Dte (SL-18) | 1805/DWSD | 28/12/2021 | 45 | BABA LOKENATH ENTERPRISE | 4.87 | 4.2 | 100 | 0
70 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Continuation order for the work of soil investigation for determining the safe bearing capacity and other relevant parameters of soil for the work of construction of RCC Elevated At Molandighi Reservoir site of Bistupur W/s Scheme under DWSD,PHE Dte | 303/DWSD | 10/03/2022 | 25 | MABCO CONSULTANT | 1.2 | 1.2 | 100 | 0
71 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of Additional work for laying and aligning of DI K9 rising main pipe line and supplying DI specials ,valves & allied works under command area of Bistupur piped W/S Scheme under DWSD ,PHE Dte (Sl-06) | 820/DWSD | 23/05/2022 | 15 | MAK CONSTRUCTION CO. | 39.46 | 39.53 | 100 | 0
72 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of Additional work for supplying laying and aligning of UPVC distribution pipe line and allied works including FHTC and connection providing to Akandara (JL-47) ,Molandighi (JL-48),Kandarakona (JL-51),Rakhitpur (JL-42) ,Chua(JL-43),Bhagaabanpur (JL-45),Hariki(JL-50) Mouzas under command area of Bistupur distributin system (Part-A) of Bistupur piped W/s Scheme under DWSD,PHE Dte (SL-02) | 814/DWSD | 21/05/2022 | 25 | MRITYUNJOY MUKHERJEE AND CO | 71.11 | 44.6 | 100 | 0
73 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of Construction of temporary approach road at Molandighi H/W site of Bistupur piped W/s Scheme under DWSD ,PHE Dte (SL-05) | 962/DWSD | 17/06/2022 | 10 | MACHINO TECHNO | 4.11 | 4.09 | 100 | 0
74 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of Land development at Molandighi H/W site & back filling of Bistupur H/W site of Bistupur piped W/s Scheme under DWSD ,PHE Dte (SL-06) | 963/DWSD | 17/06/2022 | 10 | MRITYUNJOY MUKHERJEE AND CO | 4.15 | 4.17 | 100 | 0
75 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Formal order for the work of 2 Nos road crossing of distribution pipe line under Bistupur distribution main (Part-C) by modern trenchless technology through Jack pushing method at node point of Bistupur piped W/s Scheme under DWSD, PHE Dte (SL-09) | 1123/DWSD | 22/07/2022 | 25 | SK. ALIM | 12.44 | 12.44 | 100 | 0
76 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Formal order for the work of 3 Nos road crossing of distribution pipe line under Bistupur distribution main (Part-A) by modern trenchless technology through Jack pushing method at node point1 to 2 & 64 of Bistupur piped W/s Scheme under DWSD, PHE Dte (SL-10) | 1110/DWSD | 19/07/2022 | 25 | MACHINO TECHNO | 18.64 | 18.64 | 100 | 0
77 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Formal order for the work of 2 Nos road crossing of distribution pipe line under Bistupur distribution main (Part-B) by modern trenchless technology through Jack pushing method at node point-414 to 402 of Bistupur piped W/s Scheme under DWSD, PHE Dte (SL-11) | 1164/DWSD | 01/08/2022 | 25 | TARA CONSTRUCTION | 12.43 | 12.43 | 100 | 0
78 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Formal order for the work of 1 No road crossing of distribution pipe line under Bistupur distribution main (Part-B) by modern trenchless technology through Jack Pushing method at node point 540 of Bistupur piped W/S Scheme under DWSD,PHE Dte.(SL-01) | 1163/DWSD | 01/08/2022 | 25 | TARA CONSTRUCTION | 6.21 | 6.21 | 100 | 0
79 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Quotation for Bistupur Pump house no -03 | BP-2022-23-96 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.62 | 0 | 0 | 0
80 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Quatation for Bistupur Pump house no -02 | BP-2022-23-95 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.76 | 0 | 0 | 0
81 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Quotation for Bistupur Pamp House No 1 | BP-2021-22-207 | 15/03/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.76 | 0 | 0 | 0
82 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Formal order for the work of Supplying, laying and aligning of UPVC distribution pipe line (Distribution system( Part-B) and allied works including functional house holds tap connection (FHTC) and connection providing to Saraswatiganj (JL No-49) ,Bistupur (JL No-44) Mouzas under command area of Bistupur piped W/s Scheme under DWSD,PHE Dte (SL-03) | 150/DWSD | 07/02/2022 | 30 | SK. ALIM | 188.51 | 186.94 | 99.17 | 0
83 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of Additional work for supplying laying and aligning of UPVC distribution pipe line and allied works including FHTC and connecting providing to Saraswatiganj (JL-49) ,Bistupur(JL-44) Mouzas under command area of Bistupur distribution system (Part-B) under Bistupur W/s Scheme (SL-01) | 813/DWSD | 21/05/2022 | 25 | SK. ABDUL HALIM | 76.67 | 72.69 | 94.81 | 0
84 | PASCHIM BARDHAMAN | Central Mechanical | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 2 of Bistupur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 734/CMD | 29/04/2022 | 30 | MAHADEV ENTERPRISE | 9.95 | 9.73 | 97.77 | 0
85 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of Construction of boundary wall at Madhabmat H/W site (PH No-2,TW No-2) site under Bistupur piped W/s Scheme under DWSD ,PHE Dte | 336/DWSD | 20/02/2023 | 20 | GHOSH & ROY ENTERPRISE | 18.36 | 15.74 | 85.7 | 0
86 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of Construction of boundary wall at Ghatakdanga H/W site (PH No-3,TW No-3) site under Bistupur piped W/s Scheme under DWSD ,PHE Dte | 286/A/DWSD | 16/02/2023 | 30 | DARPAN DAS & CO. | 12.08 | 0 | 0 | 0
87 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work of rising main & distribution system of Gopalpur Piped W/s Scheme under DWSD, PHE Dte | 66/DWSD | 19/01/2022 | 15 | EXECUTIVE ENGINEER , RESOURCES DIVISION, PHE DTE. | 8.89 | 80.89 | 100 | 0
88 | PASCHIM BARDHAMAN | Central Mechanical | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Supply & Installation of Submersible Pumping Machinery , Voltage stabilizer , Chlorinator and Internal House wiring for Tube well No. 1 of Bistupur Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim Bardhaman. | 478/CMD | 28/03/2022 | 30 | C.M. ENTERPRISE | 9.74 | 9.56 | 100 | 0
89 | PASCHIM BARDHAMAN | Central Mechanical | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Supply & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorination Sistem and Internal House wiring for Tube well No. 3 at Bistupur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 913/CMD | 31/05/2022 | 30 | ASHUTOSH DAS & CO. | 9.96 | 9.69 | 100 | 0
90 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Material Requisition To Resource Division | 1816/DWSD | 30/12/2021 | 0 | Resource Division | 20.35 | 0 | 0 | 0
91 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Material Requisition To Resource Division | 66/DWSD | 19/01/2022 | 0 | Resource Division | 80.94 | 0 | 0 | 0
92 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Material Requisition To Resource Division | 1752/DWSD | 16/12/2021 | 0 | Resource Division | 1.27 | 0 | 0 | 0
93 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Formal order for the work of Sinking of 2 Nos (300X200 mm) dia tube well 120 mtr deep by DR rig method using PVC pipe and fiber glass reinforced epoxy resin slotted at tube well No-01 & 02) Molandighi of Bistupur piped W/s Scheme under Durgapur W/s Division, PHE Dte (SL-03) | 1676/DWSD | 30/11/2021 | 35 | M/S. D. PALIT & CO. | 18.62 | 11.91 | 100 | 100
94 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Formal order for the work of Supplying, laying & aligning of UPVC distribution pipe line (Distribution system Part-A) and allied works including functional house holds tap connection (FHTC) and connection providing to Akandara(JL No-47) ,Molandighi(JL No-48),Kandarakona (JL_51),Rakhitpur(JL-42,Chua(JL-43),Bhagaabanpur(JL-45),Hariki(JL No-50) Mouzas under command area of Bistupur piped W/s Scheme under DWSD,PHE Dte (SL-01) | 149/DWSD | 07/02/2022 | 65 | MACHINO TECHNO | 377.24 | 232.69 | 100 | 100
95 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. , SM/08877 | New | Acceptance cum formal order for the work-Construction of boundary wall at Saraswatiganj H/W site (PH No-2,TW No-2) site under Bistupur piped W/s Scheme under DWSD ,PHE Dte | 337/DWSD | 20/02/2023 | 30 | CHATTERJEE CONSTRUCTION | 10.68 | 6.07 | 100 | 100
96 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Detailed Route Survey, Design Drawing & DPR Preparation for Ondal (Phase-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | 501/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.91 | 3.91 | 100 | 0
97 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Material Requisition To Resource Division | 3132 | 09/12/2022 | 0 | Resource Division | 40.44 | 0 | 0 | 0
98 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order for Sinking of 5 (five) nos. 200 mm dia river bed tube well in river Damodar including laying of collecting main (HDPE & MS) of Augmentation of Ondal (Phase-I & Phase-II) piped Water Supply Scheme under RCFA Division-I PHE Dte.(SL NO 6) | 1287/RCD I | 03/06/2022 | 30 | DAS & CHAKRABORTY | 75.11 | 36.68 | 48.83 | 100
99 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order for additional work cutting hard rock,boulder concrete and others work including filling earth, removal rubbish of Augmentation of Ondal Phase-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2382/RCD-I | 07/08/2023 | 30 | M/S UNIT CONSTRUCTION | 89.75 | 81.28 | 100 | 100
100 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Supply fitting fixing different dia valve and allied works in connection with laying distribution system including FHTC of Ondal Phase-I Water Supply Scheme (Part-B) under RCFA Division-I PHE Dte. | 2465/RCD-I | 18/08/2023 | 30 | AMAR CONSTRUCTION | 0.62 | 0.62 | 100 | 100
101 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Material Requisition To Resource Division | 2346/RCD-I | 28/09/2022 | 0 | Resource Division | 30.8 | 0 | 0 | 0
102 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Distribution Network for Augmentation of Ondal Phase-1 Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-C) | 2452/RCD-I | 13/10/2022 | 180 | M/S PIONEER CONSTRUCTION | 307.62 | 304.88 | 69.14 | 100
103 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-I) Piped Water Supply Scheme (Part-C) Block Andal, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | 2215/RCD-I | 17/07/2023 | 30 | M/S UNIT CONSTRUCTION | 30.8 | 30.73 | 100 | 100
104 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Lowering of Submersible Pumping machineries in the Newly sunk River Bed Tube Well No-11,12,13,14 & 15 and other allied works at Ramprasadpur HeadWorks Site under Andal Water Supply Scheme. | 554/AMD | 14/03/2024 | 30 | EASTERN INDIA SALES AND SERVICE | 6.62 | 6.58 | 100 | 100
105 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-A) | 1608/RCD-I | 06/07/2022 | 1057 | AMAR CONSTRUCTION | 53.68 | 31.3 | 58.3 | 100
106 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order for Emergency repairing and maintenance work of damaged RCC Elevated Reservoir including of capacity 700cum at Ramprasadpur of Augmentation of Ondal Phase-I W/S Scheme under RCFA Division-I PHE Dte. | 390/RCD I | 30/01/2023 | 60 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 12.78 | 12.62 | 98.73 | 100
107 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-B) | 1609/RCD-I | 06/07/2022 | 90 | UMA ENTERPRISE | 67.49 | 65.53 | 100 | 100
108 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order for Special repair and renovation of existing high lift Pump house, boundary Walls, Guard rooms, CWR, Switch Room etc, and allied works at H/W site of Ondal Phase-I Piped water Supply Scheme under RCFA Division-I PHE Dte. (Sl No 03) | 1404 RCD I | 12/04/2023 | 60 | NATIONAL CONSTRUCTION | 13.75 | 12.12 | 100 | 100
109 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order Additional for Distribution Network for Augmentation of Ondal (Phase-I) Piped Water Supply Scheme (Part-A) Block Andal, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | 2222/RCD-I | 17/07/2023 | 30 | M/S SUBHRADEEP | 16.33 | 15.89 | 100 | 100
110 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order for Emergency Repairing of 50 sqmm x 4 core Al Armoured damaged cable line provided of FHTC Pipe line near Dignala OHR Site under Andal W/S Scheme under RCFA Div-I, PHE Dte. | 2887/RCD-I | 06/10/2023 | 15 | T R ENTERPRISE | 3.72 | 3.72 | 100 | 100
111 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order for Additional for supplying, aligning and laying HDPE pipe, dismantling & concerting, supplying sluice valve and other allied works for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-B) | 3424/RCD-1 | 24/11/2023 | 30 | M/S SUBHRADEEP | 34.89 | 34.51 | 100 | 100
112 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied works at Ramprasadpur Head Works Site under Andal Water Supply Scheme, Dist.- Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | 2117/AMD | 16/12/2024 | 30 | M/S JIT ENTERPRISE | 4.16 | 0 | 0 | 100
113 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order for Allied work for collecting main of River bed tube well in Damodar River for Augmentation of Ondal (Phase-I) Water Supply Scheme under JJM at Andal H/W Site under Andal Block under RCFA Division-I, PHE Dte. | 2543/RCD-I | 29/10/2024 | 30 | MAA ENTERPRISE | 10.75 | 9.73 | 100 | 100
114 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Lowering of Submersible Pumping machineries in the Newly sunk River Bed Tube Well No-16, 17 & 18 and other allied works at Ramprasadpur Head Works Site under Andal Water Supply Scheme. | 1674/AMD | 04/10/2024 | 213 | EASTERN INDIA SALES AND SERVICE | 31.75 | 0 | 0 | 100
115 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order for Construction additional length of Boundary wall including land development and Pathway at Khas Kajora OHR site at Andal Block for Augmentation of Ondal (Phase-I) Water Supply Scheme under RCFA Division-I, PHE Dte. | 2467/RCD-I | 01/10/2024 | 45 | M/S UNIT CONSTRUCTION | 21.86 | 17.76 | 44.82 | 100
116 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme , SM/10641 | Augmentation | Acceptance cum work order for Laying of rising main for Augmentation of Andal Phase-I (Dignala OHR) from Andal H/W Site under RCFA Div-I PHE Dte. | 131/RCD-I | 08/01/2025 | 45 | UNITED CONSTRUCTION | 16.84 | 0 | 0 | 100
117 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . , SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Nuni village within Nuni and Adjoining Mouzas and Panchgachia Zone Piped Water Supply Scheme. | 149/AMD | 11/02/2022 | 7 | HINDUSTHAN CONSULTANT FIRM | 1.29 | 0 | 0 | 0
118 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . , SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Kanyapur (near Durgamandir) under Nuni Panchgachia Zone Piped Water Supply Scheme. | 145/AMD | 11/02/2022 | 7 | M/S SWAPAN BANERJEE | 2.46 | 2.45 | 100 | 0
119 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . , SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Kapatiya Village & Saroda Pally within Panchgachia Zone Piped Water Supply Scheme. | 146/AMD | 11/02/2022 | 7 | UNIQUE ENTERPRISE | 3.25 | 3.22 | 100 | 0
120 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . , SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Choto Nuni (Majhi Para) and Upadhya Para withih Panchgachia Zone Piped Water Supply Scheme. | 147/AMD | 11/02/2022 | 7 | ANANYA CONSTRUCTION | 3.72 | 3.7 | 100 | 0
121 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . , SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Sen-Raliegh B. Block within Panchgachia Zone Piped Water Supply Scheme. | 148/AMD | 11/02/2022 | 7 | VIKING TRADERS | 1.3 | 1.29 | 100 | 0
122 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . , SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Nuni Namo Para within Nuni and Adjoining Mouzas and Panchgachia Zone Piped Water Supply Scheme. | 150/AMD | 11/02/2022 | 7 | PESTCO INDIA | 3.74 | 3.72 | 100 | 0
123 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . , SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Nadiha Market (Gandhinagar) under Panchgachia Zone Piped Water Supply Scheme. | 151/AMD | 11/02/2022 | 7 | M/S SWAPAN BANERJEE | 3.22 | 3.2 | 100 | 0
124 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . , SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Nayabasti (Gandhinagar) under Panchgachia Zone Piped Water Supply Scheme. | 152/AMD | 11/02/2022 | 7 | M/S JIT ENTERPRISE | 4.56 | 4.54 | 100 | 0
125 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . , SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Monoharbohal Village under Panchgachia Zone Piped Water Supply Scheme. | 153/AMD | 11/02/2022 | 7 | PESTCO INDIA | 2.93 | 2.91 | 100 | 0
126 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Material Requisition To Resource Division | 2927/RCD-I | 17/11/2022 | 0 | Resource Division | 85.11 | 0 | 0 | 0
127 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Material Requisition To Resource Division | 3125 | 09/12/2022 | 0 | Resource Division | 220.25 | 0 | 0 | 0
128 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Material Requisition To Resource Division | 2206/RCD-I | 17/07/2023 | 0 | Resource Division | 24.19 | 0 | 0 | 0
129 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Acceptance cum Work Order for Construction of Guard room with toilet under Ondal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | 1150/RCD-1 | 24/03/2023 | 60 | SUBHADEEP DAS | 5.64 | 5.53 | 100 | 100
130 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Acceptance cum work order for Allied work of 600 mm Dia RCC pipe road crossing trenchless method jack pushing under NH-19 at Railway Kajora more to Andal Police station under OCP based KAJORA of Augmentation sub surface water supply scheme Ondal Phase-II/B under RCFA Division-I PHE, Dte | 2431/RCD-I | 26/09/2024 | 60 | T M CONCRETE CREATION PVT.LTD | 73.64 | 73.64 | 100 | 100
131 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Distribution network for Augmentation of Ondal (Phase-II/B) Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-1) | 2836/RCDI | 28/10/2022 | 885 | M/S KALYANI ENTERPRISE | 88.58 | 24.33 | 27.47 | 60
132 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Acceptance cum work order for laying of 200 mm dia rising main from Dignala OHR ste to proposed OHR site at Andal BL & LRO office for the proposed Augmentation work of Andal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 343/RCDI | 30/01/2023 | 822 | D.S.C. CONCERN | 7.65 | 4.3 | 56.2 | 65
133 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Formal work order for distribution network for augmentation of Ondal (Phase-II/B) piped Water Supply Scheme including FHTC & allied works within Ondal Block under RCFA Div-I, PHE Dte.(Part-3) | 15/RCDI | 05/01/2023 | 30 | DAS & CHAKRABORTY | 178.26 | 60.64 | 34.02 | 85
134 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Formal order for distribution network for augmentation of Ondal (Phase -II/B) piped Water Supply scheme including FHTC & allied work within ondal block under RCFA Div-I, PHE Dte. | 819/RCDI | 10/03/2023 | 30 | M/S MONI TRADERS | 108.27 | 34.49 | 31.85 | 60
135 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Supply & erection of Swajal Village Boards (102 nos) having M.S. Channel/Angle Posts & 1.5 mm thick M.S. synthetic enamel paint over a coat of red oxied primer including lettering complete at different places under Augmentation of sub surface water based for PWSS Ondal Phase-II/B under RCFA Division-I PHE Dte. | Camp-02_Swajal/AE/24-25 | 03/10/2024 | 120 | SHARMA ENGINEERING WORKS | 20.55 | 0 | 0 | 50
136 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Formal work order for construction of 450 cum capacity 20 mtr staging height RCC over head reservoir pipe connection and cost of pipes, specials at Andal village for Augmentation of Ondal Phase-II/B piped water supply scheme under RCFA Div-I, PHE Dte. in the District of Paschim Bardhaman. | 18 /RCD I | 05/01/2023 | 9 | AMAR CONSTRUCTION | 129.3 | 129.3 | 100 | 100
137 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Acceptance cum Work Order for Construction of Chlorine Room (Size 4.1 m x 3.5 m out to out) at OHR Site for Augmentation of Ondal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte.(Sl No. 34) | 1177/RCD-1 | 24/03/2023 | 90 | SUBHADEEP DAS | 4.61 | 3.91 | 100 | 100
138 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Acceptance cum work order forConstruction of Boundary Wall with Gate at OHR Site (Length-160 mtrs) at Ondal Block for Augmentation of Ondal Phase- II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 1126/ RCD I | 24/03/2023 | 30 | AMAR CONSTRUCTION | 13.43 | 13.27 | 100 | 100
139 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Acceptance cum Work Order for Land development with approach road including internal drain at Head Works Site for Augmentation of Ondal Phase II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 04) | 1148/RCD-1 | 24/03/2023 | 30 | AMAR CONSTRUCTION | 6.5 | 6.09 | 100 | 100
140 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Acceptance cum work order for Carriage DI pipe & specials from Searsole to Andal for rising main pipeline work at Andal block of Augmentation of sub surface water supply scheme for Andal Phase-II/B RCFA Division-I ,PHE Dte | 2428/RCD-I | 26/09/2024 | 15 | MRITYUNJOY MUKHERJEE & CO. | 5.04 | 0 | 0 | 10
141 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Acceptance cum work order for Balance work of the pushing 300 mm Dia MS rising main through 600 mm Dia pipe under Hinglow River for the work Of OCP based Kajora site of Augmentation of sub surface water supply scheme for Ondal Phase-II/B Under RCFA Division-I PHE, Dte | 2430/RCD-I | 26/09/2024 | 60 | T M CONCRETE CREATION PVT.LTD | 48.99 | 16.1 | 24.74 | 100
142 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC , SM/11576 | Augmentation | Acceptance cum work order for Additional work for cutting hard rock at Kajora OHR Site for Ghanashyampur abandoned Kajora of Augmentation of sub surface water based PWSS for Andal Phase-II/B under RCFA Division-I PHE Dte | 2426/RCD-I | 26/09/2024 | 45 | MACHINO TECHNO | 14.71 | 0 | 0 | 100
143 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Material Requisition To Resource Division | 2944/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
144 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Acceptance cum work order for Construction of Guard Room with toilet under Mangalpur Water Supply Scheme under RCFA Division-I PHE Dte. | 300/RCD-I | 07/02/2024 | 15 | M/S SUBHRADEEP | 5.63 | 0 | 0 | 0
145 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Acceptance cum work order for Repairing of Boundary Wall at Khandra Bisswari OHR Site under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | 299/RCD-I | 07/02/2024 | 45 | NATIONAL CONSTRUCTION | 11.15 | 6.65 | 59.65 | 100
146 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Charanpur Bus Stand and Faridpur of Barabani Block under Improvement of RCFA Part-I (Zone-11, Part-9) PWSS under RCFA Division-I PHE Dte. | 2231/RCD-I | 17/07/2023 | 30 | SOMNATH SAMANTA | 14.44 | 14.39 | 100 | 100
147 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Acceptance cum work order for Construction of Boundary Wall with gate (length 200 mtr.) land development with approach road including internal drain at H/W site & construction of guard room with toilet at Baliapur under Barabani Block in Improvement of RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | 2330/RCD-I | 01/08/2023 | 90 | AMAR CONSTRUCTION | 31.48 | 30.67 | 100 | 100
148 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Acceptance cum work order for Supply and delivery of Centrifugal Pump Motor Set for Nimsha Village (High Lift) at Shemalya under AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) Block - Jamuria, Dist - Paschim Bardhaman | 3502/RCD-1 | 30/11/2023 | 10 | M/S SWAPAN BANERJEE | 21.05 | 21.05 | 100 | 100
149 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-93 at sonachara under Augmentation of RCFA Part-II (Zone-13) under RCFA Division-I PHE Dte | 51/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 4.9 | 0 | 0 | 0
150 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-95 at Sonachara under Augmentation of RCFA Part-II (Zone-13) under RCFA Division-I PHE Dte | 50/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 4.58 | 0 | 0 | 0
151 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (zone-13) with Construction of 400 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain ad internal pathway at OHR site under Jamuria Block, District- Paschim Bardhaman. | 1844/RCD-I | 31/05/2023 | 365 | JAYANTA DATTA | 129.69 | 99.19 | 76.49 | 65
152 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 150 cum & allied works at Churulia under Augmentation of Churulia Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 3501/RCD-1 | 30/11/2023 | 90 | SIMA ENTERPRISE | 23.68 | 22.16 | 93.61 | 100
153 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Sub Soil Investigation for 400 cum capacity RCC Over Head Reservoir at (Zone-13) of Pandabeswar Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3347/RCDI | 23/12/2022 | 782 | MOYTEC | 0.46 | 0 | 0 | 100
154 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Acceptance cum work order Sinking of 6 (Six) nos 200 mm dia river bed tube wells including collecting main for river Damodar at Kalajharia of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2482/RCD-I | 23/08/2023 | 30 | A. CONSTRUCTION CO. | 13.15 | 11.12 | 100 | 100
155 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Churulia (200 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3019/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.92 | 4.92 | 100 | 100
156 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Kendra (750Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3027/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.92 | 4.92 | 100 | 100
157 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Acceptance cum work order for Sinking of 5 (Five) nos 200 mm dia river bed tube well in the river of Damodar at Kalajharia H/W site for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2884/RCD-1 | 06/10/2023 | 45 | A CONSTRUCTION CO | 9.8 | 9.62 | 100 | 100
158 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Acceptance cum work order for Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (length-160 mtr) at Churulia OHR site of AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) under RCFA Division-I PHE Dte. | 3500/RCD-1 | 30/11/2023 | 30 | ASHA CONSTRUCTION | 28.18 | 5.99 | 20.94 | 100
159 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. , SM/12032 | Augmentation | Acceptance cum work order for Additional work for distribution network & allied work at Ondal Block of RCFA Part-II (Zone-II) PWSS under RCFA Division-I PHE Dte. | 717/RCD-I | 01/03/2024 | 30 | M/S UNIT CONSTRUCTION | 92.71 | 92.67 | 100 | 100
160 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. , SM/12033 | Augmentation | Acceptance cum work order for Additional work for laying MS pipe and allied works including adopting trench less technology (e.g. Jack Pushing Method etc) at Amnala irrigation Damp within command area of Zone-IX Part-I distribution system under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | 3439/RCD-1 | 24/11/2023 | 15 | KHEPI MAA TRADERS | 22.98 | 22.91 | 100 | 100
161 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. , SM/12033 | Augmentation | Material Requisition To Resource Division | 2943/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
162 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. , SM/12033 | Augmentation | Restoration and repairing work form Ch. 6.889 km to Ch 12.7 mm km of Chinchuria-Bhuri road under Asansol Division, PWD for laying pipe line under JJM | 236/23-24 | 29/08/2023 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 68.17 | 0 | 0 | 0
163 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. , SM/12033 | Augmentation | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-14A) | 1617/RCD I | 25/04/2023 | 180 | KONAR CONSTRUCTION | 365.88 | 115.24 | 31.5 | 35
164 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. , SM/12033 | Augmentation | Sub Soil Investigation for 1250 cum capacity RCC Over Head Reservoir at (Zone-14A) of Pandabeswar Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3348/RCDI | 23/12/2022 | 782 | G. MITRA & ASSOCIATES | 0.5 | 0 | 0 | 100
165 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. , SM/12033 | Augmentation | Acceptance cum work order for Laying of different dia MS & HDPE Pipe line and mending works at Chanchani (Sansad-XII) of Ukhra area under Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-D) | 397/RCDI | 30/01/2023 | 30 | M/S B.K. CONSTRUCTION | 11.94 | 10.71 | 100 | 100
166 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. , SM/12033 | Augmentation | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-14A) with Construction of 1250 cum capacity RCC OHR with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District Paschim Bardhaman. | 1842/RCD-I | 31/05/2023 | 365 | A. CONSTRUCTION CO. | 277.09 | 214.82 | 77.53 | 40
167 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. , SM/12033 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Majiara (250 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3020/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.92 | 4.92 | 100 | 100
168 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. , SM/12033 | Augmentation | Acceptance cum work order for Balance work of in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS & FHTC work | 3427/RCD-1 | 24/11/2023 | 160 | MACHINO TECHNO | 58.12 | 47.13 | 82.91 | 100
169 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. , SM/12040 | Augmentation | Material Requisition To Resource Division | 2941/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
170 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. , SM/12040 | Augmentation | Acceptance cum work order for Additional work supplying, laying and pushing of 600 mm dia MS cashing pipe for Railway crossing by Jack Pushing method with 150 mm dia MS water carrier pipe in Rupnarayanpur in between 232/16-18 (SLS-RNPR) in Asansol Division under distribution network Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII (Part-E) under RCFA Division-I PHE Dte. | 3430/RCD-1 | 24/11/2023 | 45 | TARA CONSTRUCTION | 55.01 | 50.99 | 100 | 100
171 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. , SM/12040 | Augmentation | Continuation work order for Supplying, fitting, fixing and fabrication of sign board including printing and carriage to different area with necessary allied works in connection with Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2382_A_RCD_I | 07/08/2023 | 20 | UNITED CONSTRUCTION | 17.51 | 17.08 | 100 | 100
172 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. , SM/12040 | Augmentation | Acceptance cum work order for Balance Work of Road Restoration In Connection With Improvement of RCFA _Part-I Water Supply Scheme for Amritnagar Zone-II of Augmentation PWSS of RCFA Part-II (Zone-14C) under RCFA Division PHE Dte. | 2130/RCD-I | 27/08/2024 | 30 | T M CONCRETE CREATION PVT.LTD | 48.27 | 47.82 | 100 | 100
173 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. , SM/12040 | Augmentation | Acceptance cum work order for Construction of Additional works of Pump House and other allied works at Damalia H/W Site for Augmentation PWSS of RCFA Part-II (Zone-14C) under RCFA, Division-I, PHE Dte. | 2128/RCD-I | 27/08/2024 | 45 | B.T.M. CONCERN | 15.28 | 15.12 | 100 | 100
174 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. , SM/12040 | Augmentation | Continuation work order for Supplying, fitting, fixing and fabrication of sign board including printing and carriage to different area with necessary allied works in connection with Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2263/RCD-I | 19/07/2023 | 20 | UNITED CONSTRUCTION | 17.51 | 10.12 | 57.78 | 60
175 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. , SM/12040 | Augmentation | Acceptance cum Work Order for Additional work along with Construction of Guard room with Toilet for Construction of 150 cum capacity RCC OHR with 20 Mtr staging height RCC Over Head Reservoir Piped connection and cost of pipes, specials at Augmentation of PWSS of RCFA Part-II (Zone-14C) Piped Water Supply Scheme under RCFA Division-I PHE Dte | 1744/RCD-I | 18/07/2024 | 256 | NATIONAL CONSTRUCTION | 12.73 | 2.98 | 23.42 | 85
176 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. , SM/12040 | Augmentation | Acceptance cum work order for Balance work of dismantling of concrete, restoration of road including pipe crossing by adopting trenchless technologies (e.g. Jack Pushing Method etc.) 03 nos. location at Haripur (Zone-14C) within Pandabeswar Block of Augmentation of PWSS RCFA Part-II (Zone-14C) under RCFA Division-I PHE Dte. | 140/RCD-I | 08/01/2025 | 90 | MD AAMIR KHAN | 85.12 | 0 | 0 | 60
177 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. , SM/12040 | Augmentation | Formal work order for Distribution Network for RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-14C) | 38/RCD-I | 11/01/2023 | 90 | PRADIP KUMAR DEB | 378.29 | 291.68 | 100 | 100
178 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. , SM/12040 | Augmentation | Acceptence cum work order for Supplying aligning & laying 90 mm dia HDPE pipe line bye pass at Kallya, Dharashpur & Pahargara under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte. | 2583/RCD-I | 07/09/2023 | 15 | ASHA CONSTRUCTION | 8.67 | 8.54 | 100 | 100
179 | PASCHIM BARDHAMAN | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME , SM/11937 | New | Acceptance cum formal order for the work of Route survey and preparation of DPR for Augmentation of Amlajora, Birudiha piped W/s Scheme and Kataberia PWSS under DWSD, PHE Dte | 528/DWSD | 29/03/2023 | 15 | MEASURE LAND | 7.53 | 7.53 | 100 | 0
180 | PASCHIM BARDHAMAN | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME , SM/11937 | New | Acceptance cum formal order for the work of sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Amlajora piped W/s Scheme under DWSD ,PHE Dte (SL-02) | 1234/DWSD | 17/08/2022 | 15 | JOY GURU ENTERPRISE | 14.68 | 14.14 | 100 | 0
181 | PASCHIM BARDHAMAN | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME , SM/11937 | New | Material Requisition To Resource Division | 255/F/DWSD | 15/02/2023 | 0 | Resource Division | 10.47 | 0 | 0 | 0
182 | PASCHIM BARDHAMAN | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME , SM/11937 | New | Material Requisition To Resource Division | 787/DWSD | 25/05/2023 | 0 | Resource Division | 25.85 | 0 | 0 | 0
183 | PASCHIM BARDHAMAN | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME , SM/11937 | New | Electricity service connection for Amlajora H/W site under Amlajora piped W/s Scheme | BP-2023-24-97 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
184 | PASCHIM BARDHAMAN | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME , SM/11937 | New | Electricity service connection charges for Amlajora H/W Site TW-II under Amlajora Piped W/s Scheme | BP-2023-24-98 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.52 | 0 | 0 | 0
185 | PASCHIM BARDHAMAN | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME , SM/11937 | New | Formal order for the work of laying distribution system rising main construction of 250 M3 Over Head Reservoir with 20 Mtr staging height including soil investigation ,construction of Pump House (5.4X3.6mtr) with FHTC for Amlajora piped W/s Scheme under DWSD,PHE Dte ,Dist-Paschim Bardhaman. | 1175/DWSD | 02/08/2022 | 12 | RANADHIR SINHA | 426.89 | 287.14 | 68.2 | 100
186 | PASCHIM BARDHAMAN | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME , SM/11937 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle) of Assistant Engineer for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.09.2023 to 29.02.2024). (Sl-01) | 1397/DWSD | 17/08/2023 | 184 | BIPLAB BANERJEE | 0.82 | 1.58 | 100 | 30
187 | PASCHIM BARDHAMAN | Asansol Mechanical | AMLAJORA PIPED WATER SUPPLY SCHEME , SM/11937 | New | Supply & installation of Submersible Pumping Machineries, Voltage Stabilizer, Chlorination System and internal House wiring for Tube Well No-II at Amlajora Water Supply Scheme, under Asansol Mechanical Division, P.H.E Dte. | 531/AMD | 12/03/2024 | 90 | M/S SAJAHAN CHOWDHURY | 11.46 | 11.46 | 100 | 100
188 | PASCHIM BARDHAMAN | Asansol Mechanical | AMLAJORA PIPED WATER SUPPLY SCHEME , SM/11937 | New | Supply & installation of Submersible Pumping Machineries, Voltage Stabilizer, Chlorination System and internal House wiring for Tube Well No-I at Amlajora Water Supply Scheme, under Asansol Mechanical Division, P.H.E Dte. | 530/AMD | 12/03/2024 | 90 | P.K.ENGINEERING | 11.43 | 11.15 | 100 | 100
189 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of construction of boundary wall at TETIKHOLA pump house site No-2 under Tetikhola piped W/s Scheme under DWSD ,PHE Dte | 321/DWSD | 20/02/2023 | 30 | CHATTERJEE CONSTRUCTION | 15.35 | 0 | 0 | 0
190 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of Construction of boundary wall at TETIKHOLA pump house site No-3 under Tetikhola piped W/s Scheme under DWSD ,PHE Dte | 322/DWSD | 20/02/2023 | 30 | BABA LOKENATH ENTERPRISE | 15.35 | 0 | 0 | 0
191 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of Construction of 5.40 X3.60 mtr switch room with plinth height (600X 2000 mm) with sanitary and water supply arrangement at TW No-2 site at Tetikhola H/W site under Tetikhola piped W/S Scheme under DWSD ,PHE Dte | 324/DWSD | 20/02/2023 | 35 | MUKHERJEE ENTERPRISE | 13.83 | 0 | 0 | 0
192 | PASCHIM BARDHAMAN | Asansol Mechanical | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Supply, delivery & installation of Submersible Pumping Machineries, Voltage Stabilizer, Chlorination System and internal House wiring for Tube Well No-I,II and III under Tetikhola Piped Water Supply Scheme, Block- Faridpur-Durgapur, District-Paschim Bardhaman. | 1022/AMD | 19/04/2023 | 90 | M/S SWAPAN BANERJEE | 34.29 | 0 | 0 | 0
193 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of Construction of boundary wall at Tetikhola H/W site (OHR ) site ,land development ,approach road and others allied works of Augmentation of Tetikhola piped W/s Scheme under DWSD ,PHE Dte | 330/DWSD | 20/02/2023 | 30 | BISHAL ENTERPRISE | 34.05 | 0 | 0 | 0
194 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of Laying ,aligning of DI K9 R/M pipe and interconnection between 3 Nos Tube well with OHR and other allied works of Tetikhola piped W/s Scheme under DWSD ,PHE Dte | 504/DWSD | 28/03/2023 | 25 | BISHAL ENTERPRISE | 48.29 | 0 | 0 | 50
195 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-C) under Tetikhola piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-14) | 759/DWSD | 19/05/2023 | 35 | ANWESHA CONSTRUCTION | 98.7 | 49.22 | 49.87 | 65
196 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-A) under Tetikhola piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-18) | 810/DWSD | 29/05/2023 | 35 | BASANTI TRADERS | 99.25 | 78.14 | 78.73 | 70
197 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE/CI/DI distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-B) under Tetikhola piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-13) | 762/DWSD | 22/05/2023 | 35 | JOY GURU ENTERPRISE | 94.09 | 65.76 | 69.89 | 85
198 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-F) under Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman | 811/DWSD | 29/05/2023 | 35 | CHATTERJEE CONSTRUCTION | 87.79 | 60.58 | 69 | 75
199 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of Drawing design and surveying work for proposed piped W/S Scheme of Tetikhola Piped W/s Scheme under DWSD ,PHE Dte (SL-14) | 1035/DWSD | 04/07/2022 | 15 | APEX ENGINEERING | 3.9 | 3.9 | 100 | 0
200 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Material Requisition To Resource Division | 788/DWSD | 25/05/2023 | 0 | Resource Division | 26.4 | 0 | 0 | 0
201 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-D) under Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman | 763/DWSD | 22/05/2023 | 35 | PRAVAT SARKAR | 98.69 | 33.51 | 33.95 | 40
202 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-E) under Tetikhola piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman | 761/DWSD | 22/05/2023 | 35 | SWATI CORPORATION | 95.42 | 81.27 | 85.17 | 45
203 | PASCHIM BARDHAMAN | Asansol Mechanical | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | SUPPLY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-4 &5 AT TETIKHOLA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE., BOLCK- DURGAPUR-FARIDPUR, DIST- PASCHIM BARDHAMAN. | 1925/AMD | 19/11/2024 | 165 | PESTCO INDIA | 22.69 | 0 | 0 | 0
204 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of Construction of 5.40 X3.60 mtr switch room with plinth height (600X 2000 mm) with sanitary and water supply arrangemnt at TW No-3 site at Tetikhola under Tetikhola piped W/S Scheme under DWSD ,PHE Dte | 335/DWSD | 20/02/2023 | 25 | M/S BANERJEE CONSTRUCTION | 6.88 | 6.88 | 100 | 100
205 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum formal order for the work of Sinking of 03 Nos 300X200 mm dia Tube well with 210 mtr deapth by DR rig method using UPVC pipe (CD and UPVC deep well screen (RDS) at TETIKHOLA H/W site & TW-II site of Durgapur-Faridpur Block under TETIKHOLA piped W/s Scheme under DWSD ,PHE Dte | 309/DWSD | 20/02/2023 | 681 | M/S. D. PALIT & CO. | 47.15 | 0 | 0 | 100
206 | PASCHIM BARDHAMAN | RCFA Division -I | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. , SM/15666 | New | Acceptance cum Work Order for Laying & pushing of 600 mm dia RCC hume pipe (NP3) by adopting trench less technology (e.g. Jack Pushing Method) MS water carrier pipe and other allied works under command area of Tetikhola (Part-E) under Tetikhola Piped Water Supply Scheme, Block Durgapur-Faridpur, Dist-Paschim Bardhaman | 940/RCD-I | 15/03/2024 | 15 | TARA CONSTRUCTION | 9.51 | 4.74 | 36.59 | 100
207 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18825 | Augmentation | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 AT AUGMENTATION OF JATGORIA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | 2181/AMD | 26/12/2024 | 30 | SAIKET SINHA | 11.61 | 0 | 0 | 0
208 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18825 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of JATGARIA (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -09) | 1192/DWSD | 25/07/2023 | 7 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
209 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18825 | Augmentation | Acceptance cum Work Order for balance work for Construction of site office at Panagarh of RCFA Division-I PHE Dte. under Augmentation of Jatgoria W/S Scheme JJm Fund. | 211/RCD-I | 29/01/2024 | 60 | BASANTI TRADERS | 32.98 | 32.76 | 100 | 100
210 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18825 | Augmentation | Acceptance cum work order for Additional works for distribution main pipe line including Road Restoration under Augmentation of Jatgoria Water Supply Scheme Distribution System of Jatgoria W/S Scheme under RCFA Division-I PHE Dte. | 2607/RCD-I | 12/11/2024 | 90 | SUPERSKILL | 84.46 | 0 | 0 | 0
211 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18825 | Augmentation | Acceptance cum work order for Construction of Guard Room at Jatgoria Head Works Site under Augmentation of Jatgoria Water Supply Distribution System of Jatgoria W/S Scheme under RCFA Division-I PHE Dte. | 2730/RCD-I | 26/11/2024 | 90 | IMPULSE INTERNATIONAL | 5.53 | 0 | 0 | 40
212 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18825 | Augmentation | Formal order for the work of balance work of supplying and laying of HDPE distribution system with construction 02 Nos pump house construction of 150 M3 OHR of 20 Mtr staging height as per Deptt drawing laying aligning of rising main and providing FHTC connection of all mouzas under Command area of Augmentation Jatgoria piped W/s Scheme udner DWSD, PHE Dte | 1579/DWSD | 21/09/2023 | 558 | SUPER SKILL | 145.14 | 32.51 | 20.12 | 100
213 | PASCHIM BARDHAMAN | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. , SM/11282 | New | Acceptance cum formal order for the work Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Dandeswar piped W/s Scheme under DWSD ,PHE Dte (SL-03) | 1240/DWSD | 18/08/2022 | 15 | M/S BADAL GHOSH | 14.75 | 13.3 | 100 | 0
214 | PASCHIM BARDHAMAN | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. , SM/11282 | New | Formal order for the work of laying distribution system rising main construction of 150 M3 reservoir with 20 mtrs staging height including soil investigation construction of Pump house (5.4 m X 3.60 m) with sanitary and water supply arrangement and construction of pump house(3.60 X 3.00 m) with FHTC for Dandeswar water Supply schme under DWSD ,PHE Dte (NS) | 1614/DWSD | 21/11/2022 | 365 | POWER TOOLS AND ENGINEERING | 164.79 | 139.27 | 84.52 | 80
215 | PASCHIM BARDHAMAN | Central Mechanical | DANDESHWAR PIPED WATER SUPPLY SCHEME. , SM/11282 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Dandeshwar Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | 1654/CMD | 06/04/2023 | 30 | P.K. ENGINEERING | 21.21 | 20.57 | 100 | 80
216 | PASCHIM BARDHAMAN | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. , SM/11282 | New | 1 (One) No Trial bore by DR method using rig machine at Dwandeswar ,Block-Kanksa under Augmentation of Dandeswar PWSS under DWSD,PHE Dte | 1446/DWSD | 25/08/2023 | 15 | M/S BADAL GHOSH | 1 | 1 | 100 | 100
217 | PASCHIM BARDHAMAN | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. , SM/11282 | New | Material Requisition To Resource Division | 255/B/DWSD | 15/02/2023 | 0 | Resource Division | 4.24 | 0 | 0 | 0
218 | PASCHIM BARDHAMAN | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. , SM/11282 | New | Electricity service charges for Dandeswar TW-II under Dandeswar piped W/s Scheme | BP-2023-24-100 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.83 | 0 | 0 | 0
219 | PASCHIM BARDHAMAN | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. , SM/11282 | New | New service connection charges for Dandeswar piped Water supply scheme TW-I | BP-2023-24-37 | 01/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.62 | 0 | 0 | 0
220 | PASCHIM BARDHAMAN | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. , SM/11282 | New | Electricity service charges for Kanchanpur TW-III under Kanksa block of Dandeswar piped W/s Scheme | BP-2023-24-99 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.67 | 0 | 0 | 0
221 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Material Requisition To Resource Division | 3127 | 09/12/2022 | 0 | Resource Division | 178.46 | 0 | 0 | 0
222 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Acceptance cum work order for Sinking of 2 (Two) no. 200 mm dia river bed tube well in the river Ajoy of Augmentation of Churulia and its Adjoining Mouzas PWSS under RCFA Division-I PHE Dte.(SL NO 09) | 1283/RCD I | 02/06/2022 | 30 | R B ENTERPRISE | 13 | 8.2 | 63.07 | 80
223 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Material Requisition To Resource Division | 106/RCD-I | 20/01/2023 | 0 | Resource Division | 159.09 | 0 | 0 | 0
224 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Material Requisition To Resource Division | 1639/RCD-I | 27/04/2023 | 0 | Resource Division | 45.72 | 0 | 0 | 0
225 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Quotation for New Connection at Churulia. | BP-2023-24-6 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.94 | 0 | 0 | 0
226 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Acceptance cum work order for Distribution Network including providing FHTC Work under Augmentation of Churulia and its adjoining mouzas (Zone-II) PWSS Block- Jamuira, Dist- Paschim Bardhaman under RCFA Div-I Phe,Dte. | 1276/RCD-I | 02/06/2022 | 90 | MD AAMIR KHAN | 70.29 | 48.29 | 68.71 | 100
227 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Formal Work Order for Augmentation of Churulia and its adjoining mouzas (Zone-I) PWSS by construction of OHR of capacity 100 cum with 20 mtr staging height LDS with necessary interconnection & FHTC work Block-Jamuria, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | 1372/RCD-I | 16/06/2022 | 1172 | ASHA CONSTRUCTION | 306.57 | 156.81 | 51.15 | 100
228 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Acceptance cum work order for laying of 150 mm and 200 mm dia rising main for the proposed augmentation work of Churulia and its adjoining mouzas piped water supply scheme under RCFA Div-I, PHE Dte | 3273/RCD I | 20/12/2022 | 621 | T.R. ENTERPRISE | 21.17 | 10.65 | 50.3 | 70
229 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Supply,delivery & installation of Electro-Mechanical equipment and other allied works at Ajoyghat Head Works Site in the basis of "Augmentation of Churulia & Its Adjoining Mouzas"Piped Water Supply Scheme under Asansol Mechanical Division,P.H.E Dte. Block-Jamuria, District-Paschim Bardhaman. | 747/AMD | 16/03/2023 | 1346 | BENGAL CONSTRUCTION | 116.52 | 60.15 | 51.62 | 100
230 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Acceptance cum work Order for Repairing, Renovation, renewing & oversauling & obsolete i) for 2 nos. Iron Removal Plant (Pressure type) each capacity 45 cum/Hr at Churulia Head Work Site for Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. (Part-A) ii) for 3 nos. Iron Removal Plant (Pressure type of capacity 50 cum/hr 1no. & 75 cum/hr-2nos) at Madantore Head Works site for Madantore W/S Scheme under RCFA Division-I PHE Dte (Part-B) iii) for 4 nos. iron removal Plant (Pressure type) each capacity 20 cum /hr at Pandabeswar Head Works Site for Pandabeswar W/S Scheme under RCFA Division-I PHE Dte. (Part-C) iv) for 2 nos. iron Removal Plant (Pressure type) each capacity 50 cum/hr at Madanpur Head Work Site under RCFA Division-I PHE Dte. (Part-D). | 1391/RCD I | 11/04/2023 | 356 | TARAPRASAD SARKAR | 97.93 | 45.74 | 46.71 | 100
231 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Acceptance cum work order Construction of Concrete retaining wall with land development Churulia Ajoy River Bed Site under Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. | 1088/RCD-I | 23/03/2023 | 90 | S. CHAKRABORTY & CO. | 44.66 | 40.55 | 90.8 | 100
232 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Acceptance cum work order for construction of 200 cum capacity 20 mtr staging height RCC over Head Reservoir, pipe connection and cost of pipes specials of Churulia piped Water Supply Scheme under RCFA Div-I PHE Dte in the District of Paschim Bardhaman. Ref PC-I/OHR/09/2021 | 3245/RCD I | 20/12/2022 | 274 | ASHA CONSTRUCTION | 71.55 | 71.55 | 100 | 100
233 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Acceptance cum work order for Sinking of 6 (Six) nos 200 mm dia river bed tube well in river Ajoy of Augmentation of Churulia PWSS under RCFA Division-I PHE Dte. | 388/RCDI | 30/01/2023 | 45 | ASHA CONSTRUCTION | 41.46 | 40.95 | 100 | 100
234 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. , SM/11205 | Augmentation | Acceptance come work order for Balance work for distribution network of Churulia Madhudanga and its adjoining mouzas (Zone-II) under Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 20) | 1087/RCD-I | 23/03/2023 | 90 | MD AAMIR KHAN | 16.38 | 16.32 | 100 | 100
235 | PASCHIM BARDHAMAN | Durgapur W/S Division | BANAGRAM PIPED WATER SUPPLY SCHEME , SM/11223 | New | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distributing pipe line and providing FHTC at BONAGRAM Mouza of Bonagaram piped W/s Scheme under DWSD, PHE Dte(Part-A ,B & C)(SL-04) | 789/DWSD | 18/05/2022 | 45 | BISHAL ENTERPRISE | 22.78 | 22.89 | 100 | 100
236 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Acceptance cum Work Order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-18) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. (Sl No. 32) | 1176/RCD-1 | 24/03/2023 | 90 | GOPAL CONSTRUCTION | 4.61 | 0 | 0 | 0
237 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Acceptance cum work order for Additional works of extra cutting Laterate/sand stone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-18) | 2872/RCD-1 | 06/10/2023 | 90 | SWATI CORPORATION | 21.83 | 21.48 | 100 | 100
238 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Material Requisition To Resource Division | 2937/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
239 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-18) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3351/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0.49 | 100 | 100
240 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Acceptance cum work order for Additional works of concrete dismantling & re concreting with other allied works at distribution networks including additional laying of pipe line for RCFA Part-II Piped Water Supply Scheme under RCFA Div-I PHE Dte. (Zone-18) | 2885/RCD-1 | 06/10/2023 | 30 | SWATI CORPORATION | 73.24 | 60.8 | 100 | 100
241 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Acceptance cum work order for Construction of Godown for stacking of Cholorine at Searsole Head Work site of Augmentation PWSS Of RCFA Part-II (Zone-18) under RCFA Division-I PHE Dte. | 466/RCD-1 | 12/02/2024 | 90 | M/S MONDAL ENTERPRISE | 9.5 | 9.27 | 100 | 100
242 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Formal work order for distribution network for RCFA Part-II Piped water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-18) | 998/RCDI | 22/03/2023 | 1016 | SWATI CORPORATION | 454.37 | 284.71 | 62.66 | 100
243 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Formal work order for Construction of 450 cum capacity 20 mtr. staging height RCC Over Head Reservoir (Pipe connection and cost of pipes. specials at Raniganj Block (Zone-18) for Augmentation of RCFA Part-II piped Water Supply Scheme under RCFA Division-I PHe Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/04/2022 (Sheet No. 1 & 2) | 1901/RCD-I | 09/06/2023 | 366 | SRI KRISHNA ENTERPRISE | 130.86 | 39.26 | 30 | 20
244 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir at (Zone-VII) of Salanpur Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 2553/RCD-I | 31/08/2023 | 7 | SINGHA ROY & CO. | 0.98 | 0.98 | 100 | 100
245 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Acceptance cum work order for Laying & pushing of 600 mm dia RCC Hume pipe (NP3) by adopting trench less technology (e.g. Jack pushing method), MS water carrier pipe and other allied works at distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-18) | 2862/RCD-I | 06/10/2023 | 544 | SWATI CORPORATION | 44.91 | 39.27 | 93.46 | 100
246 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Acceptance cum work order for Additional work related to Rising Main Part-A for concrete cutting and road restoration at Ethora village including interconnection and Barabani OHR including Bituminous road cutting etc allied works under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | 465/RCD-1 | 12/02/2024 | 30 | M/S MONDAL ENTERPRISE | 25.64 | 24.96 | 100 | 100
247 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Acceptance cum work order for Carring, stacking of different dia (80 mm to 700 mm dia) C.I./D.I. specials, valves grannual chlorine etc including surface dressing, road base at Searsole Stack yard under RCFA Division-I PHE Dte. | 463/RCD-1 | 12/02/2024 | 20 | M/S MONDAL ENTERPRISE | 10.95 | 10.91 | 100 | 100
248 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Formal work order for Acceptance order for Construction of 700 cum capacity 20 mtr staging height RCC Over Head Reservior (pipe connection and cost of pipes, specials and land devlopment with approached road including internal drain at Mohishila OHR within Asansol Municipal Corporation area under RCFA Division-I PHE Dte. | 805/RCD-I | 13/03/2024 | 180 | GITA CONSTRUCTION | 180.36 | 95.61 | 53.78 | 82
249 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. , SM/12220 | Augmentation | Acceptance cum Work Order for Additional works of extra cutting laterate / sandstone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Div-I PHE Dte. (Zone-18) | 489/RCD-I | 12/02/2024 | 45 | TARA CONSTRUCTION | 9.36 | 9.32 | 100 | 100
250 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Safique Nagar (Sansad-XXII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1881/RCD-I | 28/10/2021 | 30 | A. CONSTRUCTION CO. | 18.11 | 18.11 | 100 | 0
251 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Huchukpara (Sansad-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 2324/RCD-I | 16/12/2021 | 30 | A. CONSTRUCTION CO. | 15.53 | 15.53 | 100 | 0
252 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Asthana (Sansad-IX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. 2nd Call | 198/RCD-I | 28/01/2022 | 30 | B M SARKAR | 13.04 | 10.18 | 78.07 | 0
253 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Sanyasi Kalitala (Sansad-XVI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 2491/RCD-I | 31/12/2021 | 30 | TARA CONSTRUCTION | 11.24 | 10.92 | 97.15 | 0
254 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Guzarbagh (Sansad-XXI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1880/RCD-I | 28/10/2021 | 30 | R B ENTERPRISE | 13.3 | 13.3 | 100 | 0
255 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Bibirbandh Para and Santipara (Sansad-I) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 2323/RCD-I | 16/12/2021 | 30 | GITASHREE FABRICATION | 18.16 | 18.16 | 100 | 0
256 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Das Para (Sansad-XIX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 2325/RCD-I | 16/12/2021 | 30 | JYOGOMAYA ENTERPRISE | 12.46 | 10.43 | 100 | 0
257 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chanchani (Sansad-X) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 2327/RCD-I | 16/12/2021 | 30 | ASHA CONSTRUCTION | 27.72 | 18.23 | 65.78 | 0
258 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Bazar Area (Sansad-V) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1869/RCD-I | 28/10/2021 | 30 | UMA ENTERPRISE | 21.3 | 15.22 | 100 | 0
259 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Teli Para (Sansad-XVIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1878/RCD-I | 28/10/2021 | 30 | M/S K & KONAR CONSTRUCTION | 17.13 | 5.48 | 50 | 0
260 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-C) 2nd Call | 120/RCD-I | 20/01/2022 | 30 | GLOBAL CONSTRUCTION | 14.23 | 13.36 | 100 | 0
261 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | 2328/RCD-I | 16/12/2021 | 30 | MD AAMIR KHAN | 14.42 | 14.42 | 100 | 0
262 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Supply of 10 mm into female 15 mm outer male reducer Brass Bush at Searsole Store to provide interconnection work in between maniflod and ferrule under Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | 1909/RCD-I | 12/08/2022 | 7 | SNEHA ELECTRIC | 4.69 | 4.69 | 100 | 0
263 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-D) | 2332/RCD-1 | 17/12/2021 | 30 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 14.44 | 4.03 | 100 | 0
264 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Hanuman Danga & Saradapally (Sansad-IV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 1868/RCD-I | 28/10/2021 | 30 | DAWN CONSTRUCTION | 26.54 | 5.97 | 100 | 0
265 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | hirting of maxi cab for date 27.7.2023 to 28.07.2023 us of AE RCFA Div WB37D 9526 | 256/23-24 | 11/09/2023 | 0 | NIRMALA TRADERS | 0.06 | 0 | 0 | 0
266 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Laying of 110 mm dia HDPE Pipe line including concrete cutting mending etc allied works towards Pathakpara (Sansad-XV) Block Andal & Pandabeswar of Improvement of Ukhra Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 372/23-24 | 21/11/2023 | 0 | B.T.M. CONCERN | 2.14 | 0 | 0 | 0
267 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Supply of chair for SE/RCFA Circle | 151/23-24 | 25/07/2023 | 0 | GLOBAL LOGISTIC CO | 0.23 | 0 | 0 | 0
268 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | 2329/RCD-I | 16/12/2021 | 30 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 14.4 | 10.71 | 100 | 0
269 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Suuply of UPS laboratory antivirus toner 12 for Asansol Laboratory | 91/24-25 | 13/06/2024 | 0 | SHARMA ENGINEERING WORKS | 0.08 | 0 | 0 | 0
270 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-E) | 2333/RCD-I | 17/12/2021 | 30 | TARAPRASAD SARKAR | 14.37 | 10.48 | 100 | 100
271 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-D) | 2332/RCD-I | 17/12/2021 | 30 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 14.44 | 7.14 | 100 | 0
272 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chanchani (Sansad-XII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | 2326/RCD-I | 16/12/2021 | 30 | M/S B.K. CONSTRUCTION | 25.7 | 17.19 | 100 | 100
273 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) , SM/09060 | Retrofitting | Acceptance cum work order for Sinking of 02 (Two) nos. river bed tube wells including collecting main and other allied works at Narayankuri H/W site at Damodar river under Narayankuri Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | 2243/RCD-1 | 17/07/2023 | 30 | MS KALYAN ENTERPRISE | 13.23 | 11.39 | 100 | 100
274 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 12 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 271/DWSD | 16/02/2023 | 45 | SHWET BARANI | 32.57 | 14.8 | 45.43 | 100
275 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A(From New. OHR Ramnagar )(Part - 6 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 45/DWSD | 11/01/2023 | 45 | RANJIB GHATAK | 21.38 | 16.28 | 76.12 | 85
276 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From Ext. OHR Ramnagar ) (Part - 1B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte.(DL-02) | 272/DWSD | 16/02/2023 | 45 | GHOSH ENTERPRISE | 31.84 | 15.06 | 47.31 | 100
277 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From New OHR Ramnagar) (Part - 6 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1696/DWSD | 09/12/2022 | 45 | HIRANMAY GHOSH | 30.39 | 29.96 | 98.59 | 68
278 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 13 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 29/DWSD | 09/01/2023 | 45 | PRAVAT SARKAR | 28.7 | 16.11 | 56.14 | 0
279 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 16 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 28/DWSD | 09/01/2023 | 45 | M/S MONDAL ENTERPRISE | 23.8 | 21.49 | 90.27 | 90
280 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 17 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 27/DWSD | 09/01/2023 | 45 | M/S BADAL GHOSH | 38.49 | 18.77 | 48.78 | 0
281 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II B (From Mahal OHR) (Part - 14 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1710/DWSD | 09/12/2022 | 45 | CHATTERJEE CONSTRUCTION | 20.6 | 19.56 | 94.94 | 85
282 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 14 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1711/DWSD | 09/12/2022 | 45 | SAIKAT RAY | 21.33 | 14.24 | 66.79 | 85
283 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From New OHR Ramnagar) (Part - 7 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1697/DWSD | 09/12/2022 | 45 | JAYANTA DATTA | 51.74 | 38.7 | 74.8 | 65
284 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From Ext. OHR Ramnagar )(Part - 4 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte | 46/DWSD | 11/01/2023 | 45 | RANJIB GHATAK | 36.4 | 29.81 | 81.91 | 0
285 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 15 B) Under Augmentation of RCFA Pt - III, Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 73/DWSD | 18/01/2023 | 45 | SARKAR AGENCY | 24.19 | 0 | 0 | 0
286 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From Ext. OHR Ramnagar )(Part - 3 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte.. | 26/DWSD | 09/01/2023 | 45 | KIRON ENTERPRISE | 39.5 | 26.2 | 66.34 | 100
287 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From Ext. OHR Ramnagar )(Part - 2 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme(JJM) under Durgapur Water Supply Division, PHE Dte.(Sl-4) | 427/DWSD | 13/03/2023 | 45 | TARA PRASAD SARKAR | 34.36 | 22.91 | 66.67 | 100
288 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From Ext. OHR Ramnagar )(Part - 4 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1690/DWSD | 09/12/2022 | 45 | RANJIB GHATAK | 52.17 | 47.46 | 90.97 | 70
289 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From New. OHR Ramnagar )(Part - 7 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 426/DWSD | 13/03/2023 | 45 | DIP CONSTRUCTION | 34.53 | 14.98 | 43.39 | 65
290 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From Ext. OHR Ramnagar )(Part - 5 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte | 270/DWSD | 16/02/2023 | 45 | D. S. ENTERPRISE | 27.65 | 12.83 | 46.39 | 100
291 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From New OHR Ramnagar) (Part - 10 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1701/DWSD | 09/12/2022 | 45 | BABA LOKENATH ENTERPRISE | 58.48 | 50.06 | 85.6 | 75
292 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From Ext. OHR Ramnagar )(Part - 2 A) Under Augmentation of RCFA Pt - III Zone - II W/S (JJM) Scheme under Durgapur Water Supply Division, PHE Dte.(S-3) | 1686/DWSD | 09/12/2022 | 45 | AMAR CONSTRUCTION | 45.34 | 42.47 | 93.66 | 80
293 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A(From New. OHR Ramnagar )(Part - 10 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 391/DWSD | 01/03/2023 | 45 | BISHAL ENTERPRISE | 38.7 | 0 | 0 | 0
294 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 11 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1704/DWSD | 09/12/2022 | 45 | AMARANJALI CONSTRUCTION | 37.9 | 31.57 | 83.3 | 65
295 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 16 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1715/DWSD | 09/12/2022 | 45 | M/S MONDAL ENTERPRISE | 29.3 | 28.85 | 98.46 | 100
296 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 12 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1706/DWSD | 09/12/2022 | 45 | SUJAY KUMAR RAY | 50.44 | 45.54 | 90.28 | 85
297 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From New. OHR Ramnagar )(Part - 8 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1698/DWSD | 09/12/2022 | 45 | ASHA CONSTRUCTION | 35.77 | 23.48 | 65.65 | 85
298 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From New OHR Ramnagar) (Part - 9 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1699/DWSD | 09/12/2022 | 45 | JOY GURU ENTERPRISE | 49.65 | 43.58 | 87.77 | 90
299 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From New. OHR Ramnagar )(Part - 9 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte | 387/DWSD | 01/03/2023 | 45 | JOY GURU ENTERPRISE | 26.58 | 17.48 | 65.79 | 100
300 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 15 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme under Durgapur Water Supply Division, PHE Dte. | 1712/DWSD | 09/12/2022 | 45 | MAITO MAA ENTERPRISE | 33.13 | 28.92 | 87.29 | 100
301 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 11 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 428/DWSD | 13/03/2023 | 45 | AMARANJALI CONSTRUCTION | 31.13 | 12.76 | 41.01 | 80
302 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 13 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1708/DWSD | 09/12/2022 | 45 | B.M. SARKAR | 40.19 | 27.41 | 68.2 | 0
303 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II B (From Mahal OHR) (Part - 17 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1714/DWSD | 09/12/2022 | 45 | M/S BADAL GHOSH | 58.47 | 54.83 | 93.78 | 85
304 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Supply, delivery and installation of Electro-Mechanical equipment at Mahal & ECL Head Works site in the basis for ''Augmentation of Ramnagar Head Works site under R.C.F.A.-III(Zone-II) water supply scheme" under Asansol Mechanical Division, P.H.E. Dte., Block-Pandabeswar, District-Paschim Bardhaman. | 362/AMD | 09/02/2023 | 90 | R.N.S TRADING | 83.82 | 52.68 | 62.85 | 62
305 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Additional work at RCC Over Head Reservoir (OHR) Site at Ramnagar H/W Site under Augmentation 0f RCFA, Pt- III , Zone- II Water Supply Scheme (JJM) under Durgapur Water Supply Division, P.H.E. Dte. (Sl- 01) | 839/DWSD | 05/06/2023 | 15 | RANJIB GHATAK | 0.95 | 0 | 0 | 0
306 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Additional work for connection of OHR to distribution main and supplying and laying of UPVC pipe line and laying of 600 mm dia RCC NP3 hume pipe modern hydraulic Jack pushing method including laying of 250 mm dia MS pipe with necessary allied works at Mohal OHR to Gobindapur under Augmentation of RCFA Part-III (Zone-II) Piped W/s Scheme under DWSD,PHE Dte | 1448/DWSD | 25/08/2023 | 30 | SAIKAT RAY | 11.66 | 0 | 0 | 0
307 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Repairing and road restoration side drainage system and other allied FHTC related works at Patseura village under Augmentation of RCFA Part-III W/s Scheme (Zone-II) under DWSD. | 1564/DWSD | 20/09/2023 | 15 | SHWET BARANI | 3.66 | 0 | 0 | 0
308 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From Ext. OHR Ramnagar) (Part - 1A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1684/DWSD | 09/12/2022 | 45 | M/S KALYANI ENTERPRISE | 43.17 | 41.37 | 95.83 | 100
309 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works for shifting of existing line due to ROB at Pandabeswar under RCFA Pt-III (Zone-II) W/s Scheme under DWSD,PHE Dte. (SL-6) | 1571/DWSD | 27/10/2021 | 20 | RANJIB GHATAK | 3.59 | 3.59 | 100 | 0
310 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of demarcation of new land for mahal OHR site and repairing of UPVC pipe line and allied works at Konda ,Gobindapur village under Modified RCFA Part-III W/s Scheme under DWSD,PHE Dte (SL-01) | 952/DWSD | 16/06/2022 | 10 | RANJIB GHATAK | 3.19 | 3.19 | 100 | 0
311 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of Laying of 600 mm dia RCC (NP3) Hume pipe by modern Hydraulic Jack pushing method including laying 150 mm dia MS pipe line at DVC More over Suri road (NH-60) for ROB under Augmentation of RCFA Part-III W/s Scheme (Zone-II) under DWSD, PHE Dte (SL_12) | 872/DWSD | 26/05/2022 | 15 | RANJIB GHATAK | 13.63 | 13.49 | 100 | 100
312 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | formal order for the work of Repairing ,shifting and replacing of UPVC pipe line and allied works at Fulbagan More to WBSEDCL office under Augmentation of RCFA Part-III (Zone-II) piped W/S Scheme under DWSD ,PHE Dte | 388/DWSD | 01/03/2023 | 20 | RANJIB GHATAK | 6.59 | 6.58 | 100 | 0
313 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 1,2,3 Ext) to combat drought like situation at Ramnagar head work site under Augmentation of RCFA,Part-III (Zone-II) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-01) | 10/SPOT/DWSD | 16/06/2023 | 4 | RANJIB GHATAK | 0.99 | 0.99 | 100 | 100
314 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 4,5 ,6 Ext ) to combat drought like situation at Ramnagari head work site under Augmentation of RCFA,Part-III (Zone-II) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-02) | 05/SPOT/DWSD | 16/06/2023 | 4 | RANJIB GHATAK | 0.99 | 0.99 | 100 | 100
315 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 12,14,15 Ext ) to combat drought like situation at Ramnagari head work site under Augmentation of RCFA,Part-III (Zone-II) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-04) | 07/SPOT/DWSD | 16/06/2023 | 4 | RANJIB GHATAK | 0.99 | 0.99 | 100 | 100
316 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Repairing of existing concrete road restoration and other allied works at Konda ,Gobindapur mouza under Augmentation of RCFA Part-III (Zone-I) piped W/s Scheme under DWSD,PHE Dte (Part-A) | 1299/DWSD | 07/08/2023 | 15 | SAIKAT RAY | 9.62 | 9.62 | 100 | 100
317 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Additional work supplying and laying of UPVC pipe le and laying with necessary allied works at Mohal ,Gobindapur under Augmentation of RCFA Part-III (Zone-II) (Part-B) Piped W/s Scheme under DWSD,PHE Dte | 1452/DWSD | 25/08/2023 | 25 | M/S BADAL GHOSH | 9.78 | 9.72 | 100 | 100
318 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Continuation order for the work of ''Laying of 600 mm dia RCC (NP3) Hume pipe by modern Hydraulic Jack pushing method including laying 150 mm dia MS pipe line at DVC More over Suri road (NH-60) for ROB under Augmentation of RCFA Part-III W/s Scheme (Zone-II) under DWSD, PHE Dte (SL_12)'' | 748/DWSD | 18/05/2023 | 15 | RANJIB GHATAK | 1.51 | 1.5 | 100 | 100
319 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of RCFA Part - III Zone - II (PART - B) under Durgapur Faridpur Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No-04) | 1235/DWSD | 31/07/2023 | 7 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
320 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Additional work at Danya under Augmentation of RCFA Part-III (Zone-II) W/S Scheme (JJM) under DWSD,PHE Dte | 1562/DWSD | 20/09/2023 | 15 | MAITO MAA ENTERPRISE | 2.99 | 2.99 | 100 | 100
321 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Material Requisition To Resource Division | 402/DWSD | 03/03/2023 | 0 | Resource Division | 271.47 | 0 | 0 | 0
322 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Material Requisition To Resource Division | 786/DWSD | 25/05/2023 | 0 | Resource Division | 172.1 | 0 | 0 | 0
323 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From Ext. OHR Ramnagar )(Part - 5 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1692/DWSD | 09/12/2022 | 45 | BASANTI TRADERS | 32.47 | 23.73 | 73.09 | 1
324 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Repairing of existing concrete road restoration and other allied works at Baidhayanathpur mouza under Augmentation of RCFA Part-III (Zone-II) piped W/s Scheme under DWSD,PHE Dte (Part-B) | 1300/DWSD | 07/08/2023 | 25 | BASANTI TRADERS | 8.92 | 6.9 | 77.37 | 70
325 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Hiring of Maxi Cab (Non Air Conditional ) Bharat Stage-iii/BS-ii purchased on or after 01.05.2008 with Diesel /LPG /CNG Engine for the supervision work of Durgapur W/S Division for office use of Assitant Engineer, RCFA Division-I Public Helth Engineering Directorate, Govt of West Bengal ( w.e.f 01.12.2023. to 31.05.2024) Consumption of Diesel,12 km per litre, Mobil 05 litre per 2500 km. | 3514/RCD-I | 30/11/2023 | 182 | SUBHA TOUR & TRAVELS | 0.89 | 1.6 | 267.73 | 35
326 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance order for the work of Supply ,Installation and fabrication of 5 Nos 50 cum./Hr capacity pressure type Iron Elimination Plant which consist of one filter chamber ( dia- 3 m,height -1.5 mtr ) and one oxidation chamber ( dia -1.00 m height -1.2 m) each and Construction of Blower Room (6.50m X 4.00m) With I.E.P. Platform, Plinth, Roof Top Treatment, Plinth Protection and Side Drain at Ramnagar H/W site under Augmentation 0f RCFA, Pt- III (Zone- II) W/S Scheme (JJM) under D.W.S.D., P.H.E. Dte. | 1718/DWSD | 09/12/2022 | 45 | ALOK ENTERPRISE | 86.64 | 85.97 | 100 | 100
327 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of Sinking of 5 Nos 200 mm dia river bed tube wells with collecting main with manifold in river Ajoy at Ramnagar H/W site (Part-A) under Augmentation of RCFA Part-III (Zone-II/JJM) piped W/S Scheme under DWSD,PHE Dte. | 389/DWSD | 01/03/2023 | 15 | RANJIB GHATAK | 35.85 | 35.6 | 100 | 100
328 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Formal order for the work of Sinking of 6 Nos 200 mm dia river bed tube wells with collecting main with manifold in river Ajoy at Ramnagar H/W site (Part-B) under Augmentation of RCFA Part-III (Zone-II/JJM) piped W/S Scheme under DWSD,PHE Dte. | 390/DWSD | 01/03/2023 | 20 | RANJIB GHATAK | 42.39 | 42.33 | 100 | 100
329 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Emergent Road restoration dismanttled road of Paranganj mouza of Jemua Piped Water supply scheme under DWSD ,PHE Dte | 1197/DWSD | 27/07/2023 | 35 | MAK CONSTRUCTION CO. | 14.52 | 14.4 | 100 | 100
330 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangement at Kanksa of Kanksa Block under Augmentation of Kanksa (Zone-II) (Part-C) piped W/S Scheme under DWSD,PHE Dte | 1287/DWSD | 07/08/2023 | 45 | MOTIONMASS TECHNO (OPC) PVT LTD | 6.75 | 6.58 | 100 | 100
331 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Repairing of existing concrete road restoration and other allied works at Dalubandh mouza under Augmentation of RCFA Part-III (Zone-II) piped W/s Scheme under DWSD,PHE Dte (Part-D) | 1289/DWSD | 07/08/2023 | 25 | PRAKRITI CONSTRUCTION | 7.82 | 7.81 | 100 | 80
332 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Additional work for UPVC pipe line and laying with necessary allied works at Ramnagar (existing OHR Part-2A) under Augmentation of RCFA Part-III (Zone-II) Piped W/s Scheme under DWSD,PHE Dte | 1447/DWSD | 25/08/2023 | 25 | RANJIB GHATAK | 9.61 | 9.6 | 100 | 100
333 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Additional work for collecting main with manifold for IEP at Ramnagar H/W site and DI distribution line at ROB new culvert portion under Augmentation of RCFA Part-III (Zone-II) Piped W/s Scheme under DWSD,PHE Dte | 1499/DWSD | 04/09/2023 | 15 | RANJIB GHATAK | 19.4 | 17.6 | 100 | 100
334 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Quotation for new connection at Natundanga OHR under RCFA Part-III(Zone-II) water supply scheme. | BP-2024-25-20 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.09 | 0 | 0 | 0
335 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Road restoration of work 03 nes location (Reghunathpur Kantaberia via Molandihi, Muchipara Shibpur, Reghunathpur Kantaberna via Molandihi) | 275/24-25 | 06/09/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, PW (ROADS) DIRECTT. | 26.8 | 0 | 0 | 0
336 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum work order for Laying and pushing by adopting trenchless technology (jack pushing method) additional for distribution network for Augmentation of RCFA part-III (Zone-II) PWSS including FHTC and allied works under RCFA Division-I, PHE Dte. | 2779/RCD-I | 28/11/2024 | 180 | MAK CONSTRUCTION CO | 35.16 | 0 | 0 | 68
337 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum work order for Additional work for Jemua Water Supply Scheme at Gopalpur within Durgapur Faridpur Block for Augmentation of RCFA Part-III (Zone-II) PWSS under RCFA Division-I PHE Dte. | 1522/RCD-I | 14/06/2024 | 292 | ASHA CONSTRUCTION | 22.23 | 0 | 0 | 100
338 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum work order for Supplying laying HDPE distribution pipe line at JhanjraPurbapara at Durgapur Faridpur Block under Augmentation of RCFA Part-III Zone-II under RCFA Division-I PHE Dte. | 1509/RCD-I | 20/05/2025 | 73 | DAWN CONSTRUCTION | 23.41 | 0 | 0 | 40
339 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From New OHR Ramnagar) (Part - 8A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1695/DWSD | 09/12/2022 | 1056 | RUBY CONSTRUCTION | 51.35 | 33.7 | 65.77 | 70
340 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From Ext. OHR Ramnagar )(Part - 3 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1688/DWSD | 09/12/2022 | 966 | MAK CONSTRUCTION CO. | 75.68 | 62.05 | 82.23 | 100
341 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Supply, delivery and installation of Electro-Mechanical equipments in existing Ramnagar Pump House in the basis of "Augmentation of Ramnagar Head works Site under R.C.F.A.-III(Zone-II)" Water Supply Scheme under Asansol Mechnical Division,P.H.E. Dte. | 361/AMD | 09/02/2023 | 811 | SUNRISE ENGINEERING CORPORATION | 65.77 | 51.13 | 77.83 | 100
342 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Additional work supplying and laying of alternative rute for extra rising main of 250 mm dia DI (K9) and 200 mm dia HDPE pipe line with necessary allied works from Ramnagar H/W site to Mohal OHR under Augmentation of RCFA Part-III (Zone-II) Piped W/s Scheme under DWSD,PHE Dte | 1449/DWSD | 25/08/2023 | 305 | RANJIB GHATAK | 67.61 | 0 | 0 | 100
343 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum work order for Detailed study of Households/Habitations of Barabani, Faridpur-Durgapur, Jamuria, Kanksa, Ondal, Pandabeswar, Raniganj and Salanpur blocks under Paschim Barddhaman District under the jurisdiction of RCFA Division-I, PHE Dte. | 803/RCD-I | 13/03/2024 | 2224 | HORIZEN | 67.79 | 48.15 | 84.56 | 80
344 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . , SM/12726 | Augmentation | Acceptance cum work order for Balance work of dismantling of concrete, restoration of road including pipe crossing by adopting trenchless technologies (e.g Jack Pushing Method etc.) 03 nos. location at Bahula(Zone-9) within Pandabeswar Block for Augmentation of RCFA Part-III (Zone-II) PWSS under RCFA Division-I PHE Dte. | 139/RCD-I | 08/01/2025 | 45 | MD AAMIR KHAN | 40.95 | 0 | 0 | 100
345 | PASCHIM BARDHAMAN | Asansol Mechanical | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN , SM/14888 | Augmentation | Quotation Money for New Connection at Kajora | BP-2023-24-16 | 23/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.31 | 0 | 0 | 0
346 | PASCHIM BARDHAMAN | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN , SM/14888 | Augmentation | Acceptance cum Work Order for Construction of Pump House under at Kajora under Kajora OCP based PWSS under RCFA Division-I PHE Dte. | 928/RCD-I | 15/03/2024 | 90 | MACHINO TECHNO | 35.86 | 35.85 | 100 | 100
347 | PASCHIM BARDHAMAN | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN , SM/14888 | Augmentation | Acceptance cum work order for Additional work for Laying 300 mm dia Raising Main through 600 mm dia MS pipe by trenchless technique under railway / NH / SH for the OCP base PWSS of Kajora (Ghanashampur OCP) of OCP Kajora PWSS under RCFA Division -1 PHE Dte. . | 2121/RCD-I | 27/08/2024 | 45 | T M CONCRETE CREATION PVT.LTD | 57.67 | 45.88 | 100 | 100
348 | PASCHIM BARDHAMAN | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN , SM/14888 | Augmentation | Formal work order for Source Augmentation of OCP based PWSS of Kajora (Ghanashampur OCP) including, Intake Arrangement, Construction of Steel Truss Bridge, Guardroom, CWR, Boundary Wall, Laying of Rising Main, Land Development etc. & other allied works of OCP Kajora PWSS under RCFA Division-I PHE Dte. | 2148/RCD-I | 12/07/2023 | 275 | MRITYUNJOY MUKHERJEE & CO. | 120.71 | 119.78 | 99.23 | 16
349 | PASCHIM BARDHAMAN | Asansol Mechanical | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN , SM/14888 | Augmentation | Supply, delivery & installation of Electro-Mechanical equipment and other allied works at Kajora Piped Water Supply Scheme under Asansol Mechanical Division, P.H.E Dte. Block-Andal, District-Paschim Bardhaman. | 483/AMD | 22/02/2023 | 867 | ORIENTAL ENGINEERING CO. | 393.09 | 286.06 | 73.19 | 100
350 | PASCHIM BARDHAMAN | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN , SM/14888 | Augmentation | Acceptance cum work order for Route Survey & Preparation of DPR for Augmentation of Kajora Piped Water Supply Scheme. Augmentation of Kajora Piped Water Supply Scheme including Providing FHTC Block : Andal District- Paschim Bardhaman. | 3381/RCD-I | 21/11/2023 | 15 | APEX ENGINEERING | 2.54 | 2.54 | 100 | 100
351 | PASCHIM BARDHAMAN | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN , SM/14888 | Augmentation | Acceptance cum work order for Additional Work For Concrete , MS Girder In connection With source Augmentation of OCP Based PWSS of Kajora (Ghanashampur OCP ) including intake arrangement construction of steel Truss Bridge , Guard room ,CWR, Boundary wall, Laying of raising main, Land development etc, and other allied works of OCP Kajora PWSS under RCFA Division 1 PHE Dte. | 2118/RCD-I | 27/08/2024 | 445 | MACHINO TECHNO | 82.14 | 0 | 0 | 100
352 | PASCHIM BARDHAMAN | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN , SM/14888 | Augmentation | Acceptance cum work order for Crossing 250 mm Dia MS pipe under the canal in connection with source Augmentation of OCP based PWSS of Kajora (Ghanashampur OCP) including intake arrangement construction of Steel Truss Bridge, Guard Room, CWR Boundary wall, Laying of rising main, land Development etc. and other allied works of OCP Kajora PWSS under RCFA Division-I PHE, Dte. | 2760/RCD-I | 28/11/2024 | 260 | MRITYUNJOY MUKHERJEE & CO. | 14.7 | 0 | 0 | 100
353 | PASCHIM BARDHAMAN | Asansol Mechanical | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN , SM/14888 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard & Bridge lighting arrangement and other allied works at Kajora Pump House under Kajora Piped Water Supply Scheme. | 1679/AMD | 04/10/2024 | 227 | PESTCO INDIA | 23.43 | 0 | 0 | 100
354 | PASCHIM BARDHAMAN | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN , SM/14888 | Augmentation | Acceptance cum work order for Additional work for laying 300 mm Dia rising main through 600 mm Dia Ms pipe by trenchless technique under railway /NH/SH FOR THE OCP base PWSS OF Kajora (Ghanashyampur OCP) of OCP Kajora PWSS under RCFA Division-I PHE, Dte | 2429/RCD-I | 26/09/2024 | 60 | MRITYUNJOY MUKHERJEE & CO. | 54.06 | 0 | 0 | 100
355 | PASCHIM BARDHAMAN | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN , SM/14888 | Augmentation | Acceptance cum work order for Balance work for retaining wall construction and with allied work for Augmentation of OCP Based PWSS of Kajora (Ghanashampur OCP) including intake arrangement construction of steel Truss Bridge, Guard room, CWR, Boundary wall, Laying of raising main, Land development Etc, and other allied works of OCP Kajora PWSS under RCFA Division 1 PHE Dte. | 2116/RCD-I | 27/08/2024 | 353 | MRITYUNJOY MUKHERJEE & CO. | 46.19 | 0 | 0 | 100
356 | PASCHIM BARDHAMAN | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN , SM/14888 | Augmentation | Acceptance cum Work Order for Construction of Boundary Wall at OCP Based Treatment Plant at Kajora under RCFA Division-I PHE Dte. | 1591/RCD-I | 27/06/2024 | 414 | MACHINO TECHNO | 25.99 | 0 | 0 | 100
357 | PASCHIM BARDHAMAN | Asansol Mechanical | Providing and Installation of Sub-Station equipments and other accessories ar Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block: Raniganj, Dist: Paschim Bardhaman. , SM/16777 | Augmentation | New Power Connection at Damalia Pumping Station. | BP-2023-24-12 | 19/05/2023 | 0 | INDIA POWER CORPN. LTD. | 24.34 | 0 | 0 | 0
358 | PASCHIM BARDHAMAN | Asansol Mechanical | Providing and Installation of Sub-Station equipments and other accessories ar Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block: Raniganj, Dist: Paschim Bardhaman. , SM/16777 | Augmentation | Allied Works Corresponding to "Providing and Installation of Sub-Station Equipments and other accessories at Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block : Raniganj, Dist -Paschim Bardhaman. | 1205/AMD | 07/08/2024 | 45 | EASTERN INDIA SALES AND SERVICE | 12.75 | 0 | 0 | 100
359 | PASCHIM BARDHAMAN | Asansol Mechanical | Providing and Installation of Sub-Station equipments and other accessories ar Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block: Raniganj, Dist: Paschim Bardhaman. , SM/16777 | Augmentation | Providing and Installation of Sub-Station Equipments and other accessories at Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block : Raniganj, Dist -Paschim Bardhaman. | 872/AMD | 04/04/2023 | 366 | EASTERN INDIA SALES AND SERVICE | 166.24 | 121.25 | 73.74 | 100
360 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Acceptance cum work order for Additional work laying of different dia HDPE & MS pipe including installation of sluice valve and chamber in different location of Dakshin Khanda & Khandra GP under Ondal Block under RCFA Division-I PHE Dte. | 2860/RCD-I | 06/10/2023 | 30 | UNITED CONSTRUCTION | 25.34 | 22.45 | 88.61 | 90
361 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Laying of different dia distribution pipe line at Ghosalpara, Dharmarajtala, Sabarpara, Dagalpara, Ghosalpara, Kamarpara, MajhiPara etc area of Dakshin Khanda area under Augmentation of RCFA Part-II (Zone-1A) PWSS under RCFA Division-I PHE Dte. | 3294/RCD I | 20/12/2022 | 45 | UNITED CONSTRUCTION | 52.8 | 52.4 | 100 | 0
362 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Material Requisition To Resource Division | 2936/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
363 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Survey Charges for Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-66 dt 22.11.2023 in Indian railway from Andal to Andal Junction Cabin under Augmentation of RCFA Pt-II (Zone-1A) under RCFA Division-I, PHE Dte. | test | 30/11/2023 | 0 | EASTERN RAILWAY | 0.24 | 0 | 0 | 0
364 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Survey Charges for Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-65 dt 22.11.2023 in Indian railway from Andal to Bhaktarnagar under Augmentation of RCFA Pt-II (Zone-1A) under RCFA Division-I, PHE Dte. | 390/23-24 | 29/11/2023 | 0 | EASTERN RAILWAY | 0.25 | 0 | 0 | 0
365 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Acceptance cum Work Order for Additional work line concrete cutting and allied works for Augmentation of Nutondanga RCFA Part-II (Zone-1A) piped W/S Scheme of durgapur sub-Division under RCFA division-I PHE dte. | 214/RCD-I | 29/01/2024 | 30 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 35.52 | 35.52 | 100 | 70
366 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Acceptance cum Work Order for Sinking of 3 (Three) nos river bed tube wells including collecting main manifold sluice valve chamber reinforcement and other allied works at Damalia H/W under RCFA Part-II at Damodar river under Augmentation of Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | 486/RCD-I | 12/02/2024 | 25 | M/S KALYAN ENTERPRISE | 10.68 | 10.57 | 100 | 100
367 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Acceptance cum Work Order for Additional work for Electrical wiring of C and D type quarter building, PHE Housing Complex and Installation of street including arrangement and fedar box and other allied works under RCFA Division-I PHE Dte. | 484/RCD-I | 12/02/2024 | 15 | T R ENTERPRISE | 13.35 | 13.32 | 100 | 100
368 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Acceptance cum work order for Construction of FHTC Platform in different household at Dakshin Khanda (Jl No. 36) Block ¿ Andal under Augmentation of RCFA Part-II (Zone-1A) PWSS under RCFA Division-I PHE Dte. | 385/RCD I | 30/01/2023 | 45 | UNITED CONSTRUCTION | 34.42 | 28.04 | 81.46 | 100
369 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Formal work order for distribution network for RCFA Part-II piped water supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte (Zone-1A) (Ukhra) | 818/RCDI | 10/03/2023 | 905 | ASHA CONSTRUCTION | 249.09 | 53.6 | 21.52 | 70
370 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Acceptance cum work order Laying 160 mm dia HDPE pipe line along Domahani Jamuria Road under RCFA Division-I PHE Dte. | 1254/RCD-I | 27/03/2023 | 15 | NATIONAL CONSTRUCTION | 3.85 | 3.84 | 100 | 100
371 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Acceptance cum work order for Additional work 300 mm dia MS pipe line for Singharani Bridge crossing and Kajora at Madanpur under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | 3418/RCD-1 | 24/11/2023 | 30 | MD. JAWED KHAN | 11.59 | 11.05 | 100 | 100
372 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Acceptance cum work order for Balance work for distribution network for Augmentation of Ondal Phase-II/A Piped Water Supply Scheme including FHTC and allied works within Ondal Block under RCFA Division-I PHE Dte. (Part-I) | 470/RCD-1 | 12/02/2024 | 30 | SIMA ENTERPRISE | 5.59 | 4.39 | 100 | 100
373 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Allied work of laying distribution system of Balance Work of laying distribution system to Accommodate FHTC and providing FHTC including supplying laying fittings fixing of 15 NB PVC pipe with all necessary work specials saddle piece etc. all complete for Augmentation of sub-surface water based PWSS for Amritnagar Zone-II under RCFA Division-I PHE Dte. | 497/RCD-I | 12/02/2024 | 45 | MACHINO TECHNO | 73.78 | 72.39 | 100 | 100
374 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman , SM/12227 | Augmentation | Acceptance cum work order for Laying of 90 mm HDPE pipe line inter connection stand post and other allied works at Dakshin Khanda, Moira and adjacent area under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | 471/RCD-1 | 12/02/2024 | 30 | UNITED CONSTRUCTION | 9.57 | 9.43 | 100 | 100
375 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18824 | Augmentation | Acceptance cum Work Order for Balance work of distribution pipe line of Kanska Zone-II (Part-B)from OHR to Pathanpara under Augmentation of Birudiha W/S Scheme under RCFA Division-I PHE Dte. | 1019/RCD-I | 16/03/2024 | 45 | MD AAMIR KHAN | 35.4 | 35.37 | 100 | 100
376 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18824 | Augmentation | Material Requisition To Resource Division | 134/RCD-I | 18/01/2024 | 0 | Resource Division | 130.63 | 0 | 0 | 0
377 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18824 | Augmentation | Quotation payment as per WBSEDCL Procedure-A (2010) for Pump House No 5, under Augmentation of Birudiha Water Supply Scheme, Block- Kanksa, Paschim Bardhaman. | BP-2024-25-73 | 03/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.76 | 0 | 0 | 0
378 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18824 | Augmentation | Quotation payment as per WBSEDCL Procedure-A (2010) for Pump House No 3, under Augmentation of Birudiha Water Supply Scheme, Block- Kanksa, Paschim Bardhaman. | BP-2024-25-72 | 03/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.94 | 0 | 0 | 0
379 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18824 | Augmentation | Acceptance cum formal order for the work of creating a separate zone for BIRUDIHA of Birudiha piped W/S Scheme with construction of Pump house /Chlorine room Sin king of 1500 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Birudiha, Manikara Mouza under Augmentation of BIRUDIHA piped W/s Scheme under DWSD, PHE Dte | 1136/DWSD | 20/07/2023 | 712 | M/S K.B.CONSTRUCTION | 98.43 | 70.96 | 72.25 | 100
380 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18824 | Augmentation | Balance work of supplying and laying of HDPE distribution system with construction 02 Nos pump house construction of 150 M3 OHR of 20 Mtr staging height as per Deptt drawing laying aligning of rising main and providing FHTC connection of all mouzas under Command area of Augmentation Birudiha piped W/s Scheme under DWSD, PHE Dte | 1551/DWSD | 19/09/2023 | 398 | KHAN ENTERPRISE | 291.36 | 0 | 0 | 90
381 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07558 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | 952/RCD-I | 07/06/2021 | 30 | DIP CONSTRUCTION | 23.01 | 4.1 | 100 | 0
382 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07558 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-D] | 955/RCD-I | 07/06/2021 | 30 | MD AAMIR KHAN | 22.98 | 45.44 | 187.3 | 0
383 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07558 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | 953/RCD-I | 07/06/2021 | 30 | TARA MA ENTERPRISE | 23.02 | 45.17 | 185.9 | 0
384 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07558 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-C] | 954/RCD-I | 07/06/2021 | 30 | PINKI ENTERPRISE | 23.02 | 39.98 | 162.9 | 0
385 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07558 | Retrofitting | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kalya (part) and Siakulberia and Chotkara (Part) village for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl 12) | 255/RCD-I | 01/02/2022 | 20 | JAYANTA DATTA | 4.99 | 4.64 | 100 | 0
386 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07558 | Retrofitting | Extension of HDPE pipe line (Parallel to main distribution) at village Kirtansala and Dharaspur village (Part) for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 18) | 260/RCD-I | 01/02/2022 | 20 | DIP CONSTRUCTION | 4.98 | 4.64 | 100 | 0
387 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07558 | Retrofitting | Supplying, aligning & Laying of different dia HDPE pipe line for providing FHTC to Manahora, Kanskuli (Part) and Kalisanko villages under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | 1433/RCD I | 27/06/2022 | 45 | GITASREE FABRICATION | 1.97 | 1.76 | 100 | 0
388 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07558 | Retrofitting | Extension of UPVC pipe line (Parallel to main distribution) at village Ghiadoba and Kusumdanali West side for providing FHTC under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 20) | 262/RCD-I | 01/02/2022 | 20 | GITA CONSTRUCTION | 3.58 | 2.79 | 100 | 0
389 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Pandabeswar of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C2) | 2133/RCD-I | 29/11/2021 | 30 | MRITYUNJOY MUKHERJEE & CO. | 18.7 | 12.53 | 67 | 0
390 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ B2) | 2131/RCD-I | 29/11/2021 | 30 | M/S B.K. CONSTRUCTION | 18.13 | 18.13 | 100 | 0
391 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Supply, fitting fixing of street stand posts and crossing of distribution water branch main through Khandra main road and etc. including interconnection work under Khandra Zone under RCFA Part-II W/S Scheme. (Sl No. 11) | 223/RCD I | 01/02/2022 | 12 | UNITED CONSTRUCTION | 2.61 | 2.61 | 100 | 0
392 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Laying of different dia HDPE pipe line including repairing work of UPVC pipe line and etc. allied works under Khandra Zone distribution pipe line under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 10) | 222/RCD I | 01/02/2022 | 15 | UNITED CONSTRUCTION | 4.79 | 4.79 | 100 | 0
393 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Maira area Dakshin Khnada (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | 2212/RCD-I | 14/09/2022 | 30 | UNITED CONSTRUCTION | 44.65 | 9.74 | 21.81 | 0
394 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ B1) | 2130/RCD-I | 29/11/2021 | 30 | D.S. ENTERPRISE | 18.12 | 12.86 | 100 | 0
395 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C1) | 2132/RCD-I | 29/11/2021 | 30 | KHEPI MAA TRADERS | 17.52 | 17.52 | 100 | 0
396 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Acceptance cum work order for Laying of different dia HDPE pipe line towards Bisserari, Anandapally and etc. adjacent area under Khandra area Block Andal & Pandabeswar of Improvement of RCFA Part-II Water Supply scheme under RCFA Division-I PHE Dte. | 372/RCD I | 30/01/2023 | 15 | M/S B.K. CONSTRUCTION | 6.87 | 1.11 | 100 | 100
397 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Acceptance cum work order Interconnection work of 200 distribution main at Ukhra Zone and emergency repairing of 400 mm dia rising main at Khandra Zone under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | 1285/ RCD I | 27/03/2023 | 15 | RANJIB GHATAK | 4.28 | 4.26 | 100 | 100
398 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Material Requisition To Resource Division | 2283 | 12/12/2021 | 0 | Resource Division | 18.59 | 0 | 0 | 0
399 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Fuel bill of WB 37D 0482 | 263/23-24 | 27/09/2023 | 0 | RANAJIT AUTO | 0.22 | 0 | 0 | 0
400 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Hire charges and fuel bill 16.05.2023 to 15.08.2023 | 264/23-24 | 27/09/2023 | 0 | PRAMIT CHATTERJEE | 1.2 | 0 | 0 | 0
401 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Hire charges for the month of August 2023 | 262/23-24 | 27/09/2023 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0 | 0
402 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Bill for GST Return Oct 2023 to Feb 2024 24 Q 1 & Q 2 2023-2024 and 16 A 26 Q 23-24 | 172/24-25 | 25/07/2024 | 0 | SHRESTHA & ASSOCIATES | 0.44 | 0 | 0 | 0
403 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Color Xerox repairing and supply of color xerox toner | 131/24-25 | 11/07/2024 | 0 | MUKHERJEE TRADERS | 0.17 | 0 | 0 | 0
404 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Arrangement of Stationary items , Flex and Tea snacks for Krmashree meeting held on 12.07.2024 at RTC Hall Asansol | 171/24-25 | 26/07/2024 | 0 | BLESSING ENTERPRISE | 0.14 | 0 | 0 | 0
405 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Acceptance cum work order Laying of different dia HDPE pipe line towards Ruidas Para and Baouripara under Dakshin Khanda (Jl No. 36) area Block - Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | 1272/ RCD I | 27/03/2023 | 15 | DURGADAS MONDAL | 3.71 | 3.68 | 99.22 | 0
406 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Acceptance cum work order Laying of different 140 mm dia HDPE pipe line including interconnection and fitting, fixing sluice valves and etc allied works at Maira Dipu area under Khandra Zone under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | 1259/ RCD I | 27/03/2023 | 15 | TARA CONSTRUCTION | 2.32 | 2.16 | 93.23 | 0
407 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Formal work order for Providing FHTC through Retrofitting at Khandra (CT) (JL no. 32, Block - Andal) of RCFA Pt-II W/S Scheme under RCFA Division-I, PHE Dte. (Part-A) | 2145/RCD-I | 29/11/2021 | 488 | DAS & CHAKRABORTY | 78.91 | 68.92 | 74.84 | 100
408 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09387 | Retrofitting | Acceptance cum work order for laying of different dia distribution pipe line and allied works etc at Bisseswari Muslimpara and adjacent area of Khandra area under Improvement of RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | 334/RCD I | 30/01/2023 | 15 | M/S B.K. CONSTRUCTION | 7.68 | 0.73 | 100 | 100
409 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Detailed Route Survey, Design Drawing & DPR Preparation for Madantor Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 4) | 503/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.04 | 4.04 | 100 | 0
410 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Material Requisition To Resource Division | 3130 | 09/12/2022 | 0 | Resource Division | 12.9 | 0 | 0 | 0
411 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Acceptance cum work order for repair and renovation works of GLR of capacity 90 cum for Augmentation of Madantor Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 23) | 1166/RCD I | 24/03/2023 | 180 | A.K.CONSTRUCTION | 6.48 | 0 | 0 | 5
412 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Acceptance cum work order Repairing & shifting work of DI pipes and allied repairing at Madanpur under Madanpur W/S Scheme under RCFA Division-I PHE Dte. | 1261/ RCD I | 27/03/2023 | 15 | MAK CONSTRUCTION CO. | 3.22 | 3.21 | 100 | 100
413 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Material Requisition To Resource Division | 2351/RCD-I | 28/09/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
414 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Acceptance cum work order for Repair and renovation works of Clear Water Reservoir of Capacity 150 cum for Augmentation of Madantore Piped water Supply scheme under RCFA division-I PHE dte. | 3187/RCD-I | 01/11/2023 | 180 | A.K.CONSTRUCTION | 10.86 | 0 | 0 | 0
415 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Acceptance cum Work Order for Additional works of Dismantling and concrete works supplying aligning and laying HDPE pipe and other allied works at distribution system network for Bagdiha (Part-D) Augmentation of Madantor Water Supply Scheme under RCFA Division-I PHE Dte. | 491/RCD-I | 12/02/2024 | 45 | TARA MA ENTERPRISE | 18.79 | 11.87 | 63.17 | 75
416 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Acceptance cum work order for Repair and renovation works of One no. RCC Elevated Reservoir of Capacity 250 cum at Madantore under Augmentation of Madantore Piped water Supply scheme under RCFA division-I PHE dte. | 3186/RCD-I | 01/11/2023 | 270 | A.K.CONSTRUCTION | 10.95 | 8.9 | 100 | 100
417 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Acceptance cum work order for Supply & Delivery of GI pipe including loading, unloading and carriage to Searsole Store under RCFA Part-II PWSS under RCFA Division-I PHE Dte. | 713/RCD-I | 29/02/2024 | 20 | NEZONE TUBES LIMITED | 95.53 | 95.49 | 100 | 100
418 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Acceptance cum work order for Additional supplying laying and aligning of distribution system including FHTC for Shyamla in Chatrisganda Mouza, Block Jamuria Paschim Bardhaman under Augmentation of Madantore PWSS under RCFA Division-I PHE Dte. | 2137/RCD-I | 27/08/2024 | 45 | DAWN CONSTRUCTION | 38 | 33.69 | 100 | 100
419 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Laying of distribution system including FHTC work for Augmentation of Madantore Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2450/RCD-I | 13/10/2022 | 180 | JOY HIND TUBEWELLS | 246.41 | 70.1 | 28.45 | 100
420 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-4 Segment) for Augmentation of Madantore Piped Water Supply Scheme under RCFA Division-I PHE Dte | 1708/RCD-I | 15/07/2022 | 881 | DAWN CONSTRUCTION | 48.67 | 32.88 | 77.48 | 100
421 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Construction of Pump House at Churulia under Madantore Water Supply Scheme under RCFA Division-I PHE Dte. | 3281/RCDI | 20/12/2022 | 90 | M/S MONDAL ENTERPRISE | 30.24 | 30.24 | 100 | 100
422 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Acceptance work order for Construction of Chlorine Room of Size (4.50 x 3.50 m) at Churulia for Augmentation of Madantore Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman | 342/RCDI | 30/01/2023 | 15 | ANAMIKA CONSTRUCTION | 4.6 | 4.42 | 100 | 100
423 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Supply, delivery & installation of Pump Motor Set in the basis of "Augmentation of Madantor & Its Adjoining Mouzas "Piped Water Supply Scheme under Asansol Mechanical Division, P.H.E Dte. Block-Jamuria, District-Paschim Bardhaman. | 607/AMD | 03/03/2023 | 580 | M/S. SOMA ENTERPRISE | 14.44 | 11.82 | 81.82 | 100
424 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Acceptance cum work order for Sinking of 1 (One) no. 200 mm dia river bed tube well in the river Ajoy including 01 (One) no collecting main of Augmentation of Madantor Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 22) | 1165/RCD I | 24/03/2023 | 60 | R B ENTERPRISE | 5.77 | 5.68 | 100 | 0
425 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Madantor Water Supply Scheme , SM/10845 | Augmentation | Providing and installation of Gaseous chlorination system at Churulia High lift pump house under Madantore W/S scheme. | 1322/AMD | 21/08/2024 | 197 | M/S. SOMA ENTERPRISE | 28.71 | 0 | 0 | 100
426 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI specials ,valves and other allied works under Telipara piped W/s Scheme of DWSD,PHE Dte (SL-06) | 786/DWSD | 18/05/2022 | 10 | M/S MONDAL ENTERPRISE | 14.09 | 12.59 | 89.37 | 0
427 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Acceptance cum formal order for the work of Sinking of 2 No Tube well 250 mm X 150 mm big dia Tube well 210 mtr depth direct rotary rig method using PVC pipe & Pre packed resin bonded gravels filter for Telipara piped W/s Scheme under DWSD, PHE Dte (SL-10) | 739/DWSD | 06/04/2022 | 10 | M/S. D. PALIT & CO. | 22.86 | 18.07 | 100 | 0
428 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Formal order for the work of Supplying & aligning of HDPE distribution pipe line and allied works including Functional House Holds Tap connecting (FHTC ) and connection providing to Raghunathpur Mouza-39 and Paschim Gangarampur Mouza- JL-92 of Telipara block -Kanksa under TELIPARA piped W/s Scheme under DWSD, PHE Dte (Part-A) | 642/DWSD | 21/04/2022 | 25 | M/S PROCHESTA ENTERPRISE | 98.21 | 98.21 | 100 | 85
429 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Acceptance for the work of Supplying & aligning of HDPE distribution pipe line and allied works including Functional House Holds Tap connecting (FHTC ) and connection providing to Jamdoba Mouza-40 and Telipara Mouza- JL-41 of Telipara block -Kanksa under TELIPARA piped W/s Scheme under DWSD, PHE Dte (SL-03) | 554/DWSD | 11/04/2022 | 25 | M/S SANTANU PALIT & CO. | 127.01 | 0 | 0 | 0
430 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Formal order for the work of Construction of Pump house cum Chlorine Room with Sanitary Plumbing arrangement at Jamdoba tube well No-2 or H/W Site of Telepara piped W/S Scheme under DWSD, PHE Dte (SL-06) | 641/DWSD | 21/04/2022 | 45 | MUKHERJEE ENTERPRISE | 6.15 | 6.06 | 100 | 0
431 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Formal order for the work of Construction of Pump house cum Chlorine Room with Sanitary Plumbing arrangement at Jamdoba tube well No-1 or H/W Site of Telipara piped W/S Scheme under DWSD, PHE Dte (SL-05) | 576/DWSD | 13/04/2022 | 45 | M/S KALYANI ENTERPRISE | 6.21 | 6.21 | 100 | 100
432 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex,Banskopa,DGP-12 (w.e.f 18.02.2023 to 17.08.2023). (SL-02) | 133/DWSD | 31/01/2023 | 181 | PRAMIT CHATTERJEE | 0.82 | 2.39 | 100 | 80
433 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Acceptance cum formal order for the work of Construction of boundary wall at Jamdoba of Telipara W/s Scheme pump house No-II under DWSD ,PHE Dte | 481/DWSD | 22/03/2023 | 45 | MUKHERJEE ENTERPRISE | 14.92 | 12.84 | 100 | 100
434 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Water supply arrangement to 6(Six) Nos AWC without electricity at Jamdoba,Telipara, Nabagram Majhiara & other allied works under Telipara Piped Water Supply Scheme.(TSM/004035) under DWSD,PHE Dte | 625/A/DWSD | 21/04/2022 | 20 | B. T. M. CONCERN | 34.06 | 32.79 | 100 | 100
435 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Material Requisition To Resource Division | 330/DWSD | 15/03/2022 | 0 | Resource Division | 37.85 | 0 | 0 | 0
436 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Quotation for Telipara W/S Scheme , Pump House No- 02 , Panagarh CCC | BP-2022-23-338 | 17/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.13 | 0 | 0 | 0
437 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Quotation for Telipara W/S Scheme , Pump House No- 01 , Panagarh CCC | BP-2022-23-337 | 17/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.45 | 0 | 0 | 0
438 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Acceptance cum formal order for the work Balance work for construction of pump house with approach road and others allied works at Jamdoba pump house No-II Telipara piped W/s Scheme under DWSD ,PHE Dte. | 579/DWSD | 10/03/2023 | 20 | MUKHERJEE ENTERPRISE | 5.68 | 5.68 | 100 | 100
439 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex, Banskopa,DGP-12 (w.e.f 18.08.2023 to 17.02.2024). (SL-02) | 1364/DWSD | 11/08/2023 | 184 | PRAMIT CHATTERJEE | 0.82 | 2.38 | 149.91 | 100
440 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. , SM/10311 | New | Formal order for the work of Construction of 200 M3 capacity , 20 mtr staging height RCC Over head Reservoir (OHR) at Jamdoba of Telipara piped W/s Scheme under Durgapur W/S Division, PHE Dte (SL-07) | 575/DWSD | 13/04/2022 | 1506 | M/S KALYANI ENTERPRISE | 62.35 | 19.72 | 31.63 | 100
441 | PASCHIM BARDHAMAN | Durgapur W/S Division | GARKILLA KHEROBARI PIPED WATER SUPPLY SCHEME. , SM/10998 | New | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at Garkilla-Kherobari,Gourangapur(28) mouzas of Garkilla-Kherobari piped W/s Scheme under DWSD, PHE Dte under DWSD, PHE Dte (Part-A ,B & C) (SL-5) | 764/DWSD | 13/05/2022 | 45 | BABA LOKENATH ENTERPRISE | 28.84 | 24.12 | 100 | 100
442 | PASCHIM BARDHAMAN | Durgapur W/S Division | GARKILLA KHEROBARI PIPED WATER SUPPLY SCHEME. , SM/10998 | New | Quotation for Garkilla Kherobari W/S Scheme, P.H. No - 01, Gopalpur CCC | BP-2022-23-332 | 15/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.8 | 0 | 0 | 0
443 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Acceptance cum work order for Supplying aligning & laying 225 mm dia HDPE pipe line in related to distribution Network for Augmentation of Sarisatali Piped W/S Scheme under RCFA Division-I PHE Dte. ( Sl No. 18) | 1085/RCD I | 23/03/2023 | 90 | JAYANTA DATTA | 19.21 | 18.02 | 93.81 | 100
444 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Preparation of DPR for Augumentation of Sarshatali Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte.(Sl No 04) | 2348/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 2.88 | 2.88 | 100 | 0
445 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Acceptance cum work order for Sinking of 2 (Two) no. 200 mm dia river bed tube well in the river Ajoy of Augmentation of Sarisatali Piped Water Supply Scheme under RCFA Division-I PHE Dte.(Sl No 07) | 1281/RCD I | 02/06/2022 | 30 | MAA ENTERPRISE. | 11.06 | 10.81 | 100 | 0
446 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Providing & Installation of Low Lift Pumping Machineries at newly sunk Tube Wells at Kharabar river bed under Sarshatali Piped Water Supply scheme, Block : Baraboni, Dist : Paschim Bardhaman. | 1024/AMD | 19/04/2023 | 90 | M/S. SOMA ENTERPRISE | 13.7 | 13.68 | 100 | 100
447 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Formal work order for Distribution network for augmentation of Sarisathali piped Water Supply scheme including FHTC work, Block-Baraboni, Dist-Paschim Bardhaman under RCFA Div-I, PHE Dte (Part-D) | 3231//RCDI | 19/12/2022 | 987 | SRI KRISHNA ENTERPRISE | 133.36 | 14.98 | 11.23 | 100
448 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Acceptance cum work order Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (Length-160 mtr) at Sarisathali OHR site of Augmentation of Sarsathali Piped Water Supply Scheme under Barabani Block under RCFA Division-I PHE Dte. | 2219/RCD-I | 17/07/2023 | 30 | M/S CHANDI CHARAN ROY | 29.79 | 18.72 | 62.85 | 65
449 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Acceptance cum work order for Laying rising main including Guard room with Toilet including 12 (Twelve) nos Tube Well and Collecting main at River Ajoy under due to open cast mining activity of ECL Salanpur area for Sarisatali and Majiara Water Supply Scheme under RCFA Division-I PHE Dte. | 2339/RCD-I | 01/08/2023 | 90 | MRITYUNJOY MUKHERJEE & CO. | 87.93 | 13.26 | 15.08 | 20
450 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Sarisatali Piped Water Supply Scheme including FHTC Work Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte.(Part-C) | 1279/RCD I | 02/06/2022 | 90 | M/S B.K. CONSTRUCTION | 59.35 | 38.85 | 65.46 | 80
451 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Providing and installation of vertical Pumping Machineries under Sarisathali Water Supply Scheme. | 1112/AMD | 16/06/2025 | 30 | M/S. SOMA ENTERPRISE | 11.05 | 0 | 0 | 0
452 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Repairing and renovation of staff quarter (Group A Type) and other allied works at Kalyaneswari Township under RCFA Division-I PHE Dte. (Sl No. 02) | 1078/RCDI | 13/05/2022 | 30 | R B ENTERPRISE | 4.86 | 4.72 | 100 | 100
453 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Sarisatali Piped Water Supply Scheme including FHTC work Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-B) | 1278/RCD-I | 02/06/2022 | 90 | MD. JAWED KHAN | 38.01 | 29.87 | 100 | 0
454 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Sarisatali Piped Water Supply Scheme including FHTC Work Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-A) | 1277/RCD-I | 02/06/2022 | 579 | JAYANTA DATTA | 32.82 | 24.1 | 79.38 | 85
455 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Acceptance cum Work Order for Construction of OHR (Capacity 300 cum, staging Height 20 mtrs) for Augmentation of Sarisathali Piped Water Supply Scheme under RCFA Division-I PHE Dte. Block-Barabani, Dist - Paschim Bardhaman. | 2933/RCD-I | 17/11/2022 | 12 | M/S CHANDI CHARAN ROY | 85.83 | 85.83 | 100 | 100
456 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Acceptance cum work order Additional work for laying of distribution system including adopting trench less technology for one location near Khosnagar Health Centre and allied works under Augmentation of Sarishatali PWSS under RCFA Division-I PHE Dte. | 2334/RCD-I | 01/08/2023 | 15 | M/S B.K. CONSTRUCTION | 11.2 | 9.4 | 100 | 100
457 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Emergent sinking of one no 200 X 165 mm dia rig bore tube well at District Magistrate bungalow, Asansole, Paschim Bardhaman under RCFA Division-I PHE Dte. | Camp_2_DM_Office_AE_II_20 | 01/09/2023 | 3 | M/S CHANDI CHARAN ROY | 7.87 | 7.74 | 100 | 100
458 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Acceptance cum work order for Sinking of 2 (Two) nos 200 mm dia river bed tube well including collecting main in the river of Ajoy for Sarisatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2859/RCD-I | 06/10/2023 | 15 | MAA ENTERPRISE | 7.67 | 7.16 | 100 | 100
459 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Acceptance cum Work Order for Additional work for laying Rising Main of Augmentation of Sarshatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1745/RCD-I | 18/07/2024 | 260 | M/S MONDAL ENTERPRISE | 28.19 | 4.69 | 16.38 | 60
460 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Acceptance cum Work Order for Construction of Chlorine room of size 4 mtr x 4 mtr x3.5 mtr (Ht) at Sarsatali under Augmentation of Sarsatali PWSS under RCFA Division-I PHE Dte. | 875/RCD-I | 15/03/2024 | 60 | JAI MAHARAJ ENTERPRISE | 3.99 | 3.99 | 100 | 100
461 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Balance work of Supplying,laying and aligning of Distribution system includind FHTC for Shyamla W/S Scheme in Shyamla and Bhuri Mouza, Block jamuria, Dist-Paschim Bardhaman under Augmentation of Sarshatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Camp-02_Shyamla_AE-II/24- | 06/08/2024 | 30 | TARA CONSTRUCTION | 12.5 | 12.41 | 100 | 100
462 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME , SM/10605 | Augmentation | Interconnection at Nimcha OHR site and allied works at Nimcha village for Amritnagar -II under Augmentation of Sarshathali PWSS under RCFA Division-I PHE Dte. | Camp-02_Nimcha/AE-II/24-2 | 18/02/2025 | 20 | MD. JAWED KHAN | 8.06 | 0 | 0 | 100
463 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Preparation of DPR for Augmentation of Panuria Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. | 2345/RCD-I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 3.02 | 3.02 | 100 | 0
464 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Formal Work Order for Distribution System at Katapahari, Alipur, Baradanga village and surrounding area (Part-B) under Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 598/RCD-I | 07/03/2022 | 60 | GITA CONSTRUCTION | 78.27 | 70.11 | 89.57 | 91
465 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Acceptance cum work order for new pipe line of 200 mm, 90 mm and 75 mm dia at Panuria Bazar under Panuria GP under Augmentation of Panuria Water Supply Scheme under RCFA Division-I PHE Dte. | 3285/RCD I | 20/12/2022 | 60 | SRI KRISHNA ENTERPRISE | 12.15 | 12.08 | 100 | 0
466 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Material Requisition To Resource Division | 696/RCD-I | 23/03/2022 | 0 | Resource Division | 92.44 | 0 | 0 | 0
467 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Material Requisition To Resource Division | 2347/RCD-I | 28/09/2022 | 0 | Resource Division | 21.56 | 0 | 0 | 0
468 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | QUOTATION MONEY FOR NEW CONNECTION AT PANURIA | BP-2023-24-7 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.17 | 0 | 0 | 0
469 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Acceptance cum work order for Providing FHTC work at Baradanga, Alipur and Kanta Pahari Villages under Augmentation of Panuria Water Supply Scheme under RCFA Division-I PHE Dte. | 2015/RCD-I | 26/08/2022 | 45 | GITA CONSTRUCTION | 44.01 | 24.63 | 55.96 | 40
470 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Providing and Installation of Electro-Mechanical Equipments and Allied Works at Panuria under Augmentation of Panuria Itapara Water Supply Scheme, Block-Baraboni, Dist.-Paschim Bardhaman. | 488/AMD | 22/02/2023 | 365 | BENGAL CONSTRUCTION | 180 | 60.38 | 75.48 | 68
471 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Formal Work Order for Distribution System at Panuria village at surrounding area (Part-C) under Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 599/RCD-I | 07/03/2022 | 60 | A. CONSTRUCTION CO. | 76.15 | 76.13 | 100 | 100
472 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Acceptance cum work order Proposed Pump House including Toilet of Augmentation Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1064/RCD-I | 23/03/2023 | 180 | RUBY CONSTRUCTION | 31.13 | 31.12 | 100 | 100
473 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Acceptance cum Work Order for Construction of road at Runakuraghat H/W site including earth filling,treeguard making including repairing and restoration of rising main including collecting main under Augmentation of Panuria PWSS under RCFA Division-I PHE Dte. | 1432/RCD-I | 06/06/2024 | 45 | SRI KRISHNA ENTERPRISE | 58.57 | 57.74 | 100 | 100
474 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Material Requisition To Resource Division | 1179/RCD-I | 03/04/2024 | 0 | Resource Division | 37.47 | 0 | 0 | 0
475 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - A) | 1038/RCD-I | 10/05/2022 | 1179 | ASHA CONSTRUCTION | 147.65 | 26.38 | 100 | 100
476 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-B) | 1611/RCD-I | 06/07/2022 | 1365 | UNITED CONSTRUCTION | 55.84 | 10.08 | 25.54 | 75
477 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Bhtas more, ardanga more on Asansol Runakuraghat Road, including supply of MS pipe and left out laying of HDPE pipe at Gourandi Bazar and allied works under Augmentation of Panuria PWSS under RCFA Division-I PHE Dte. | 2227/RCD-I | 17/07/2023 | 30 | GITA CONSTRUCTION | 43.42 | 39.5 | 90.99 | 91
478 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Plumbing works, sanitary fitting, flooring and other allied works of staff Quarter (Group A Type) and other allied works at Kalyaneswari township under RCFA Division-I PHE Dte.(Sl no 03) | 1077/RCDI | 13/05/2022 | 30 | R B ENTERPRISE | 3.89 | 3.82 | 100 | 100
479 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Acceptance cum work order for Distribution System surrounding OHR near Panuria under Agumentation of Panuria PWSS under RCFA Division-I PHE Dte. | 2151/RCD-I | 02/09/2022 | 30 | A. CONSTRUCTION CO. | 28.88 | 26.24 | 100 | 100
480 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Acceptance cum work order Providing FHTC work at Panuria (Part) and adjacent Habitation under Augmentation of Panuria Water Supply Scheme under RCFA Div-I, PHE Dte. | 2468/RCDI | 14/10/2022 | 45 | A. CONSTRUCTION CO. | 69.99 | 65.36 | 100 | 100
481 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Acceptance cum work order for construction of C.W.R. (Clear water Reservoir) of capacity 200 Cu.m & allied Work at Panuria under Augmentation of Panuria Piped Water Supply Scheme under RCFA Divn.-I. P.H.E. Dte. | 3276/RCDI | 20/12/2022 | 90 | SAMIR KUMAR ROY CHOWDHURY | 22.05 | 20.65 | 100 | 70
482 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Formal work order for construction of 350 cum capacity 20 mtr staging height RCC over Head Reservoir (Piped connection and cost of pipes, specials at Gourandi H/W site for Augmentation of Panuria Piped Water Supply Scheme under RCFA Div-I, PHE dte in the District of Pachim Bardhaman. | 102/RCD I | 20/01/2023 | 212 | A. CONSTRUCTION CO. | 115.99 | 115.99 | 100 | 100
483 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Acceptance cum work order for Repairing and renovation of existing culvert, Pump House, Staff Quarter under Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 24) | 1167/RCD I | 24/03/2023 | 90 | R B ENTERPRISE | 5.94 | 5.88 | 100 | 0
484 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Tematha Panuria Bazar, Gourandi Bazar, Aliganj Road including supply of MS pipe and left out laying of HDPE pipe at Gourandi Bazar and allied works under Augmentation of Panuria PWSS under RCFA Division-I PHE Dte. | 2226/RCD-I | 17/07/2023 | 30 | A. CONSTRUCTION CO. | 30.14 | 29.86 | 100 | 100
485 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME , SM/10165 | Augmentation | Acceptence cum work order for Laying of different dia distribution pipe line and etc. work at Tanti para, Camp para, Sasan para etc. under Khandra area under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | 2587/RCD-I | 07/09/2023 | 15 | D.S.ENTERPRISE | 7.48 | 7.42 | 100 | 100
486 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Metaldhaora, Booth No. 05, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | 1159/RCD I | 23/12/2020 | 20 | VISUVIOUS | 4.47 | 6.17 | 172.92 | 0
487 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Salanpur Mouza, Vill-Salanpur, Block-Salanpur of Salanpur Water Supply Scheme under RCFA Division-I PHE Dte. | 432 /RCD-I | 04/03/2021 | 45 | GITA CONSTRUCTION | 46.13 | 75.61 | 167.59 | 0
488 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Metaldhaora, Booth No. 05, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | 1158/RCD I | 23/12/2020 | 20 | M/S MONDAL CONSTRUCTION | 4.44 | 6.17 | 174.68 | 0
489 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Chatadhawra, Booth No. 02, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-C) | 1157/RCD I | 23/12/2020 | 20 | DHRUBA ENTERPRISE | 4.45 | 6.13 | 137.48 | 0
490 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Chatadhawra, Booth No. 02, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | 1155/RCD I | 23/12/2020 | 20 | ZEROTH CONTROL SYSTEM | 4.4 | 5.68 | 164.56 | 0
491 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Metaldhaora, Booth No. 05, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-C) | 1160/RCD I | 23/12/2020 | 20 | MS KALYAN ENTERPRISE | 4.45 | 6.37 | 179.77 | 0
492 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Chatadhawra, Booth No. 02, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | 1156 /RCD I | 23/12/2020 | 20 | A.K.CONSTRUCTION | 4.43 | 6.18 | 176.28 | 0
493 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Providing FHTC through retrofitting at Dhandardihi Mouza, vill-Madanpur, Block -Andal of Dhandadihi Water supply scheme under RCFA Div-I PHE Dte. | 45/21-22 | 15/07/2021 | 0 | MACHINO TECHNO | 25.79 | 0 | 0 | 0
494 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Continuation work order for Providing FHTC through Retrofitting at Salanpur Mouza, Vill-Salanpur, Block-Salanpur of Salanpur Water Supply Scheme under RCFA Division-I PHE Dte. | 816/RCD-I | 19/04/2021 | 45 | GITA CONSTRUCTION | 11.84 | 9.17 | 77.44 | 0
495 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Laying of different dia UPVC/HDPE pipe line for extension of distribution system regarding FHTC work at Kumardiha mouza of Ratibati water supply scheme under RCFA Div-I PHE Dte. | 1585/RCD-I | 07/09/2021 | 30 | M/S B.K. CONSTRUCTION | 14.42 | 13.73 | 100 | 0
496 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Sinking of 3 (Three) nos 200 mm dia River Bed Tube Wells including repairing work of 100 mm dia Collecting Mains which were damaged due to flood in the month of July - August & etc. allied works at River Damodar under Ratibati Water Supply Scheme under RCFA Div-I PHE Dte. (sl no 05) | 1937/RCD I | 09/11/2021 | 20 | M/S PIONEER CONSTRUCTION | 3.17 | 2.92 | 100 | 0
497 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Hard rock cutting, laying of different dia UPVC pipe line for extension of distribution system regarding FHTC work at Chelod mouza of Ratibati W/S Scheme under RCFA Div-I PHE Dte.(Sl no 10) | 2467/RCD I | 31/12/2021 | 15 | MACHINO TECHNO | 3.06 | 2.82 | 100 | 0
498 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Laying of different dia UPVC pipeline for extension system regarding FHTC work at Chelod village of Ratibati W/S Scheme under RCFA Div-I PHE Dte. | 2464/RCD-I | 31/12/2021 | 15 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 4.81 | 2.35 | 100 | 0
499 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Providing FHTC through retrofitting at Kumardiha village area of Chold mouza, GP -Ratibati Block Raniganj of Ratibati water supply scheme under RCFA Division-I PHE Dte.(Sl no 08) | 2465/RCD I | 31/12/2021 | 7 | D.S.C. CONCERN | 4.81 | 4.81 | 100 | 0
500 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Laying UPVC pipeline for FHTC work for Dhandadihi W/S Scheme under RCFA Div-I, PHE Dte.(Sl no 01) | 2458/RCD I | 31/12/2021 | 10 | MACHINO TECHNO | 3.83 | 3.82 | 100 | 0
501 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Laying of 50 mm dia PVC pipe line and construction of different dia valve chamber, FHTC work and etc. allied works at Kendra area under RCFA Division-I PHE Dte. (Sl No. 03) | 2175/RCD I | 06/12/2021 | 10 | MS KALYAN ENTERPRISE | 4.57 | 4.47 | 100 | 0
502 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Laying of different dia PVC/HDPE pipe line for extension of distribution system regarding FHTC work at Ratibati Mouza of Ratibati Water Supply Scheme under RCFA Div-I PHE Dte. | 581/RCD-I | 02/03/2022 | 15 | SOMNATH SAMANTA | 9.58 | 9.55 | 100 | 0
503 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Supplying, aligning and laying of HDPE pipe line for byepass water supply arrangement to Chapui village under Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A)(Sl no 02) | 631/RCD-1 | 09/03/2022 | 15 | SWATI CORPORATION | 4.75 | 4.75 | 100 | 0
504 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Emergency supplying aligning and laying of different dia HDPE pipe line for by pass water supply arrangement to Roypara, Singhapara and adjacent areas under Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. | 937/RCD-I | 26/04/2022 | 30 | M/S MONDAL ENTERPRISE | 24.23 | 24.17 | 100 | 0
505 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Emergency supplying. Aligning and laying of HDPE pipe line for bypass water supply arrangement to Chapui village under Ratibati water supply scheme under RCFA Division-I PHE Dte. (Part-C)(Sl no 04) | 633/RCD 1 | 09/03/2022 | 15 | SWATI CORPORATION | 4.84 | 4.82 | 100 | 0
506 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Emergency supplying. Aligning and laying of HDPE pipe line for bypass water supply arrangement to Chapui village under Ratibati water supply scheme under RCFA Division-I PHE Dte. (Part-B)(Sl no 3) | 632/RCD 1 | 09/03/2022 | 15 | SWATI CORPORATION | 4.76 | 4.72 | 100 | 0
507 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Laying of Different dia UPVC /PVC pipeline for extention of distribution system regarding FHTC work at Saora Mouza of Ratibati Water supply Scheme under RCFA Div-I PHE Dte. (Sl No 17) | 280/RCD-I | 01/02/2022 | 30 | A. CONSTRUCTION CO. | 4.81 | 4.81 | 100 | 0
508 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Laying of HDPE pipe line and other repairing work of distribution at Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 15) | 1446/RCD I | 27/06/2022 | 45 | M/S MONDAL ENTERPRISE | 2.54 | 2.49 | 100 | 0
509 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Additional laying of different dia UPVC pipeline for extension of distribution system regarding FHTC work at Chelod mouza of Ratibati W/S Scheme under RCFA Div-I PHE Dte.(Sl no 09) | 2466/RCD I | 31/12/2021 | 15 | MACHINO TECHNO | 4.78 | 4.55 | 100 | 0
510 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Repairing of 6 (Six) nos panel board, panel board wiring, Supply and installation of 10 HP submersible pump & motor & cable laying & other allied works at Ratibati river bed pump house site of Ratibati W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | 172/22-23 | 13/06/2022 | 0 | M/S PIONEER CONSTRUCTION | 4.67 | 0 | 0 | 0
511 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dhandardihi Mouza, Vill-Madanpur, Block-Andal of Dhandardihi Water Supply Scheme under RCFA Division-I PHE Dte. | 1032/RCD-I | 05/11/2020 | 30 | MACHINO TECHNO | 43.84 | 13.66 | 76.43 | 0
512 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at ECL 3 Nos Colliery area, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 05) | 1193/RCD-I | 24/12/2020 | 30 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 16.09 | 22.19 | 173.25 | 0
513 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order Providing FHTC of retrofitting at Kumardihi village (Left out portion) of kumardiha Mouza, GP-Ratibati, Block Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 12) | 1742/RCD I | 11/05/2023 | 15 | D.S.C. CONCERN | 7.9 | 7.51 | 95.03 | 0
514 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chapui (CT) Mouza, G.P.-Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | 1185/RCD-I | 24/12/2020 | 30 | SWATI CORPORATION | 39.19 | 58.25 | 178.17 | 0
515 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum Work Order for Providing FHTC through Retrofitting at Kumardiha Mouza, G.P.-Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | 1186/RCD-I | 24/12/2020 | 30 | M/S B.K. CONSTRUCTION | 19.63 | 35.64 | 181.76 | 0
516 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Seora Mouza, G.P.- Ratibati, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte. (Sl No. 05) | 1187/RCD-I | 24/12/2020 | 30 | A. CONSTRUCTION CO. | 20.48 | 39.53 | 187.76 | 0
517 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum Work Order for Providing FHTC through Retrofitting at Chelod Mouza, G.P.-Tirat, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 01) | 1167/RCD-I | 23/12/2020 | 30 | MRITYUNJOY MUKHERJEE & CO. | 37.97 | 31.34 | 189.59 | 0
518 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Kendra Mouza, Booth No. 1 (Kendra Gram), Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) (Sl No. 06) | 1194/RCD-I | 24/12/2020 | 30 | DURGADAS MONDAL | 9.08 | 10.62 | 149.1 | 0
519 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Mines Quarter Booth No. 3, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | 1190/RCD-I | 24/12/2020 | 30 | SIMA ENTERPRISE | 9.93 | 12.38 | 77.42 | 0
520 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Khottamdih Village, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 04) | 1192/RCD-I | 24/12/2020 | 30 | M/S MONI TRADERS | 14.1 | 19.45 | 135.19 | 0
521 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Kendra Mouza, Booth No. 1 (Kendra Gram), Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) (Sl No. 07) | 1195/RCD-I | 24/12/2020 | 30 | UNITED CONSTRUCTION | 9.15 | 13.54 | 183.99 | 0
522 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ratibati (Part-II), G.P.- Ratibati, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte. (Sl No. 06) | 1188/RCD-I | 24/12/2020 | 30 | SOMNATH SAMANTA | 22.88 | 40 | 173.68 | 0
523 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Supplying, aligning and laying of DI & HDPE pipe line for water supply arrangement to Kumardiha village under Ratibati W/S Scheme under RCFA Division-I PHE Dte. | 1584/RCD-I | 07/09/2021 | 30 | M/S MONDAL ENTERPRISE | 20.03 | 19.9 | 100 | 0
524 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Supplying, Aligning and laying of HDPE pipe line for FHTC work at Chapui mouzas of Ratibati W/S Scheme under RCFA Division-I PHE Dte. | 1587/RCD-I | 07/09/2021 | 30 | SWATI CORPORATION | 25.46 | 17.1 | 73.02 | 0
525 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Supply and laying of 16 sqmm x 4 core Al armored PVC power cable and 10 HP Submersible Pump at Ratibati river bed pump house site damaged due to spreading of fire of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. | 2030/RCD-I | 24/11/2021 | 10 | M/S PIONEER CONSTRUCTION | 11.72 | 11.72 | 100 | 0
526 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Supplying, laying and aligning distribution branch main from distribution main including providing FHTC work at Bilpahari General Para (Re-habilitated village) under Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | 2027/RCD-I | 24/11/2021 | 30 | SWATI CORPORATION | 39.08 | 31.16 | 100 | 0
527 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Supplying, laying and aligning distribution branch main from distribution main including providing FHTC work at Bilpahari Bauri Para (Re-habilitated village) under Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | 2026/RCD-I | 24/11/2021 | 30 | RANJIB GHATAK | 26.95 | 22.7 | 95.1 | 0
528 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Providing FHTC through retrofitting at Damra rural and adjacent area of Chelod mouza, G.P, Tirat , GP Block Raniganj of Ratibati water supply scheme under RCFA Division-I PHE Dte.(Sl no 11) | 2468/RCD I | 31/12/2021 | 10 | GOPAL CONSTRUCTION | 4.68 | 4.68 | 100 | 0
529 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Supply, fitting fixing railling, grill, painting of pump house, CWR, chlorine room etc and allied works at Ratibati H/W and Tirat Colliery H/W site under RCFA Division-I PHE Dte. (Sl No. 03) | 2203/RCD I | 06/12/2021 | 21 | SOMNATH SAMANTA | 3.53 | 2.97 | 100 | 0
530 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Providing FHTC through retrofitting at Chelod village area (Part-A) of Chelod mouza, GP Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 15) | 278/RCD-I | 01/02/2022 | 30 | M/S MONDAL CONSTRUCTION | 4.84 | 4.55 | 100 | 0
531 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at ECL 2 Nos Colliery area, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 01) | 1189/RCD-I | 24/12/2020 | 30 | GITASHREE FABRICATION | 12.68 | 19.38 | 157.12 | 0
532 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Material Requisition To Resource Division | 439/RCD-I | 21/02/2022 | 0 | Resource Division | 11 | 0 | 0 | 0
533 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Hiring of Maxi Cab (Non Air- conditioned ) bharatstage - III/BS-III purchased on after 01.05.2008 with Diesel / LPG/CNG Engine. as when required basis for supervision of FHTC related works under JJM) of RCFA Div-I, PHE Dte Govt, of West Bengal ( w.e.f 16.08.2023 to 15.02.2024) | 2420/RCD-I | 11/08/2023 | 184 | PRAMIT CHATTERJEE | 0.9 | 2.37 | 263.55 | 100
534 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dom Para Both No. 4, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | 1191/RCD-I | 24/12/2020 | 30 | DAWN CONSTRUCTION | 18.7 | 7.57 | 50.32 | 0
535 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Supply of 10 mm NB Gun-metal ferrule for Providing FHTC through Retrofitting at Chapui (CT) Mouza, G.P.- Ratibati, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte. (Sl No 17) | 363/RCD I | 26/02/2021 | 7 | SWATI CORPORATION | 4.68 | 9.36 | 200 | 0
536 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Supply of 10 mm NB Gun-metal ferrule for Providing FHTC through Retrofitting at Chelod Mouza, G.P.- Tirat, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte.(SL NO 18) | 364/RCD I | 26/02/2021 | 7 | MRITYUNJOY MUKHERJEE & CO. | 4.66 | 9.33 | 200 | 0
537 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Annual Maintenance Contract (AMC) for Computers, Prnters, UPS & other related peripherals installed at office chamber of the Assistant Engineer, Junior Engineers, DPMU, IEC under of the Executive Engineer, RCFA Division-I PHE Dte. (Period from 01.07.2023 to 31.12.2023) | 2039/RCD-I | 30/06/2023 | 184 | SHARMA ENGINEERING WORKS | 0.9 | 0.9 | 100 | 100
538 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Arrangement of breakfast and lunch box for DWSM meeting held on 13.01.2024 at ADDA Conference hall | 494/23-24 | 25/01/2024 | 0 | SHARMA ENGINEERING WORKS | 0.1 | 0 | 0 | 0
539 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Supply of it peripherals | 497/23-24 | 25/01/2024 | 0 | MUKHERJEE TRADERS | 0.43 | 0 | 0 | 0
540 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Hiring charge of Maxi cab (non conditioned) stage II / BS III for ofice use Veh WB 37 D 9526 | 553/23-24 | 27/02/2024 | 0 | NIRMALA TRADERS | 0.06 | 0 | 0 | 0
541 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Arrangemen of breakfast and lunch box for DWSM meeting held on 13.01.2024 at ADDA Conferenc hall | 495/23-24 | 25/01/2024 | 0 | SHARMA ENGINEERING WORKS | 0.09 | 0 | 0 | 0
542 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Supply of computer desktop | 498/23-24 | 25/01/2024 | 0 | MUKHERJEE TRADERS | 0.42 | 0 | 0 | 0
543 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Hirig of maxi cab state II/BS III for the office use of the Assistant Engineer | 554/23-24 | 27/02/2024 | 0 | NIRMALA TRADERS | 0.06 | 0 | 0 | 0
544 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Vehicle bill for the month of Dec 2023 | 529/23-24 | 06/02/2024 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0 | 0
545 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Repair & maintenance on contract basis of computers and local area network under SERCFA Div-I PHE Dte. | 499/23-24 | 01/02/2024 | 0 | KALPANA ENTERPRISE | 0.46 | 0 | 0 | 0
546 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Fuel bill of Ranajit Auto vehicle no WB 37 D 0482 | 571/23-24 | 27/02/2024 | 0 | RANAJIT AUTO | 0.19 | 0 | 0 | 0
547 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Hire charges bill for vehicle no WB 37 D0482 for the month of January | 570/23-24 | 27/02/2024 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0 | 0
548 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | AMC for xerox machine | 455/23-24 | 04/01/2024 | 0 | WORK CHARGE BILL | 0.21 | 0 | 0 | 0
549 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Fuel bill for shyamal Maji for the month of Dec 23 | 530/23-24 | 08/02/2024 | 0 | RANAJIT AUTO | 0.17 | 0 | 0 | 0
550 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through retrofitting at Saheb Bangla & allied areas at Khottamdihi Block Pandabeswar of Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | 978/RCD-I | 17/06/2021 | 1550 | A.K. SIKDAR | 19.13 | 26.36 | 137.79 | 100
551 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order for Interconnection work including Augurboring, supply of value, construction of valve, construction of valve chamber within command under Dabor OHR under Retrofitting of 4 Nos. PWSS for providing FHTC under RCFA Division-I PHE Dte (sl. no-6). | 804/RCD-I | 06/03/2023 | 10 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 12.51 | 12.28 | 98.14 | 0
552 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order Supplying Laying 90 mm dia HDPE pipe line, sluice valve chamber, Street Stand Post and other allied works within Amritnagar Rising Main & Distribution of Tirat Colliery W/S Scheme Zone under Improvement Part-II W/S Scheme under RCFA Division-I PHE Dte. | 1279/RCD-I | 27/03/2023 | 15 | MS KALYAN ENTERPRISE | 4.81 | 4.8 | 99.83 | 0
553 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order Additional work for sinking 3 nos 200 mm dia river bed tube wells and allied repairing work in river Damodar including surging of tube wells at Damalia H/W site under Tirat Mouza W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 11) | 1387/RCD-I | 11/04/2023 | 12 | D.S.C. CONCERN | 6.88 | 6.87 | 99.92 | 0
554 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order Construction of Street Stand Post, Sluice Valve Chamber and Aligning Laying HDPE pipe in different places (Nimcha, Damra, Chelod Bouripara, Tirat Hospital Etc.) under Tirat Colliery W/S Scheme under RCFA Division-I PHE Dte. | 1281/RCD-I | 27/03/2023 | 15 | MS KALYAN ENTERPRISE | 4.57 | 4.57 | 99.97 | 80
555 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order Emergency repairing of damaged collecting main in river Damodar and allied works at Surjanagar H/W site of Surjanagar W/S Scheme under RCFA Division-I PHE Dte. | 1257/RCD-I | 27/03/2023 | 15 | MD. JAWED KHAN | 4.31 | 4.15 | 96.2 | 0
556 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Providing FHTC through retrofitting at Chelod village area (Part-B) of Chelod mouza, GP Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 16) | 279/RCD-I | 01/02/2022 | 30 | M/S U.G. ENTERPRISE | 4.84 | 4.84 | 100 | 100
557 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district , SM/07392 | Retrofitting | Acceptance cum work order 300 mm dia MS Bye pass line and interconnection work at Khandra OHR site and allied works of Dakhin Khandra and Mahira adjacent area under Retrofitting of 4 Nos. Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1056/RCD-I | 23/03/2023 | 15 | UNITED CONSTRUCTION | 15.47 | 15.47 | 100 | 0
558 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Repairing and renovation of Rupnarayanpur OHR of Capacity 1135 cum staging height 20 mtr under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | 1588/RCD-I | 07/09/2021 | 30 | BKB INFRA PROJECTS PVT LTD | 37.48 | 37.45 | 100 | 0
559 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Supply of Computer and accessories for Office use under RCFA Division-I PHE Dte. District - Paschim Bardhaman (Sl No. 01) | 1908/RCD-I | 12/08/2022 | 7 | SHARMA ENGINEERING WORKS | 1.3 | 1.3 | 100 | 0
560 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Material Requisition To Resource Division | 2626/RCD-I | 17/11/2022 | 0 | Resource Division | 27.66 | 0 | 0 | 0
561 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Submission of Quarterly regular return for non-salary 26Q3 & 26Q4 Regular Return for Salary 24Q3 & 24Q4 for the F.Y 2021-2022 and creation of Form 16 Part A & B 26Q2 for the F.Y 202021-22 Revised return for non salary return for the quarter 26Q3 & 26Q4 for the financial 2021-22 includes GST return for the month of April 2021 to March 2022 and April 2022 to May 2022 | 383/22-23 | 17/08/2022 | 0 | SHRESTHA & ASSOCIATES | 0.58 | 0 | 0 | 0
562 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Hire charges bill for vehicle no WB 37 D 0482 for the month of March 2022 | 518/22-23 | 29/09/2022 | 0 | SHYAMAL MAJI | 0.19 | 0 | 0 | 0
563 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Hiring of maxi cab (Non-airconditioned)Bharat stage-II/BS-II purchased on or after 01.05.2008 with diesel/LPG/CNG engine for the office use of the Assistant Engineer, RCFA Div-I, PHE dte, Govt of West Bengal (w.e.f 01.09.2021 to 31.08.2022) | 1541/RCD I | 31/08/2021 | 365 | KHEPI MAA TRADERS | 1.73 | 1.14 | 81.04 | 0
564 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-8 Distribution Segment) under RCFA Division-I PHE Dte. | 498/RCD-I | 24/02/2022 | 90 | SIMA ENTERPRISE | 30.98 | 29.26 | 94.45 | 81
565 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-IX under RCFA Division-I PHE Dte. (Part-A) | 934/RCD-I | 26/04/2022 | 90 | SRI KRISHNA ENTERPRISE | 86.98 | 30.45 | 35 | 65
566 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-IX under RCFA Division-I PHE Dte. (Part-B) | 935/RCD-I | 26/04/2022 | 90 | KHEPI MAA TRADERS | 71.89 | 67.45 | 93.82 | 75
567 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-A) | 936/RCD-I | 26/04/2022 | 90 | M/S MONI TRADERS | 75.17 | 40.2 | 53.47 | 70
568 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-B) (2nd Call) | 1006/RCD-I | 05/05/2022 | 60 | M/S SANTANU PALIT & CO. | 93.2 | 0 | 0 | 70
569 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-C) | 1612/RCD-I | 06/07/2022 | 90 | PINKI ENTERPRISE | 60.85 | 21.88 | 35.96 | 65
570 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-E) | 1614/RCD-I | 06/07/2022 | 90 | TARA CONSTRUCTION | 88.3 | 43.84 | 49.64 | 70
571 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Construction of 250 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone-VI) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 1874/RCD-I | 04/08/2022 | 12 | KAMIRUL SK & CO | 76.6 | 68.94 | 90 | 100
572 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-8 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | 1712/RCD-I | 15/07/2022 | 45 | SIMA ENTERPRISE | 24.13 | 0 | 0 | 5
573 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir (Zone-XI) of Barabani Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3143/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 0 | 100
574 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-VI/BS-VI purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. For the office Use of the Executive Engineer, RCFA Div-I, PHE Dte Govt. of West Bengal (w.e.f 01.06.2022 to 30.11.2022) | Spot/NIQ/Camp-02/Office/A | 31/05/2022 | 6 | PRASENJIT DEY | 0.9 | 0 | 0 | 0
575 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-VI/BS-VI purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. For the office Use of the Executive Engineer, RCFA Div-I, PHE Dte Govt. of West Bengal (w.e.f 01.06.2022 to 30.11.2022) | SpotNIQ.Camp-02/Office/AE | 31/05/2022 | 183 | PRASENJIT DEY | 0.9 | 0 | 0 | 0
576 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Different dia HDPE pipe line including extra cutting Laterate /sandstone and concrete cutting of distribution of pipe line Zone-I (Part-B) at Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | 370/RCD I | 30/01/2023 | 15 | SWATI CORPORATION | 25.76 | 11.14 | 43.25 | 95
577 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Continuation work order for Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-VI/BS-VI purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine, for the office Use of the Executive Engineer, RCFA Division-I PHE Dte. (w.e.f. 01.12.2022 to 31.05.2023) | 3057/RCD-I | 30/11/2022 | 182 | PRASENJIT DEY | 0.9 | 0 | 0 | 0
578 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Construction of drain at Dabor mouzas under RCFA Part-I W/S Scheme within command area of Zone-VII (Part-E) under RCFA Division-I PHE Dte. | 1865/RCD-1 | 01/06/2023 | 60 | TARA CONSTRUCTION | 10.11 | 10 | 98.88 | 85
579 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-D) | 1613/RCD-I | 06/07/2022 | 90 | KONAR CONSTRUCTION | 64.73 | 23.94 | 36.98 | 75
580 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Repalcing of old and damaged C.I. spiral stairs and other allied minor repairing works at Panchgachia OHR (Capacity 55000 gallon staging height 10 mtr under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte.(Sl no 06) | 635/RCD 1 | 09/03/2022 | 15 | RUBY CONSTRUCTION | 3.87 | 3.83 | 99.02 | 0
581 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Laying of Rising Main (Part-B) at Mohismura Culvat crossing by constructing concrete piller, MS work and allied works under Improvement of RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | 3289/RCD I | 20/12/2022 | 17 | M/S MONDAL ENTERPRISE | 10.26 | 8.52 | 83.02 | 100
582 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-9 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | 1703/RCD-I | 14/07/2022 | 45 | SOMNATH SAMANTA | 28.67 | 0 | 0 | 5
583 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Urgent basis repairing work of Churulia OHR of capacity 100000 gallons and 20 mtr staging height under Churulia Water Supply Scheme under RCFA Division-I PHE Dte. | 2025/RCD-I | 24/11/2021 | 30 | ASHA CONSTRUCTION | 15.47 | 15.33 | 100 | 0
584 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Engagement of 01 (One) person under control of 02 (Two) nos Assistant Engineers of RCFA Division-I for day to day report and return of FHTC as per scheme wise, Panchayet wise and updation of JJM and verification of FHTC connection of School Aganawadi and Heath Centre and monitoring of report return of training of Asha Karmi under Health Department as per direction of EIC. under RCFA Division-I PHE Dte. (w.e.f. 01.01.2022 to 31.12.2022) (Sl no 03) | 2456/RCD I | 31/12/2021 | 365 | MUKHERJEE TRADERS | 1.73 | 0.87 | 100 | 0
585 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Urgent basis repairing work of D P Colony (OHR) at D P Colony W/S Scheme under RCFA Division-I PHE Dte. | 712/RCD-I | 24/03/2022 | 30 | RUBY CONSTRUCTION | 15.72 | 15.13 | 100 | 0
586 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Extension of different dia HDPE pipe line for providing FHTC at Putulia (Part), Kharboni, Jamjuri and allied villages under Gourbazar W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | 1437/RCD I | 27/06/2022 | 45 | VISUVIOUS | 2.75 | 2.35 | 100 | 0
587 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Construction of 450 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at Barabani (Zone-XIII) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman [Rf Drwaing no. PC-I/OHR/04/2012(Sheet 1& 2) under RCFA Division-I PHE Dte. | 2448/RCD-I | 13/10/2022 | 365 | JOY HIND TUBEWELLS | 122.44 | 122.44 | 100 | 0
588 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for dedicated bypass line from Prantapally Durga Mandir to Kalyan Gram under Jitpur Uttarrampur GP under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | 3292/RCD I | 20/12/2022 | 15 | ASHA CONSTRUCTION | 11.77 | 11.48 | 100 | 0
589 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc.) of Water Pipe Lines including supplying and laying of 400 mm dia MS Pipe line at Alladi More on Sitarampur Chittaranjan Road in connection to rising main (Part-A) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | 3288/RCD I | 20/12/2022 | 15 | MAK CONSTRUCTION CO. | 16.45 | 16.38 | 100 | 0
590 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines including supplying and laying of 450 mm dia MS Pipe Line at Hunuman Mandir on Mohismura Ethora Road near Ethora OHR inconnection to rising main (Part-B) under Augmentation of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | 360/RCD I | 30/01/2023 | 15 | M/S MONDAL ENTERPRISE | 11.17 | 11.09 | 100 | 0
591 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Engagement of 01 (One) person under control of 02 (Two) nos Assistant Engineers of RCFA Division-I for day to day report and return of FHTC as per scheme wise, Panchayet wise and updation of JJM and verification of FHTC connection of School Aganawadi and Heath Centre and monitoring of report return of training of Asha Karmi under Health Department as per direction of EIC. under RCFA Division-I PHE Dte. (w.e.f. 01.01.2022 to 31.12.2022)(Sl no 03) | 2456/RCD- 1 | 31/12/2021 | 365 | MUKHERJEE TRADERS | 1.73 | 0.87 | 100 | 0
592 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of water pipe lines including supplying and laying of 450 mm dia MS pipe line at Mohismura More on NH Madhaichak Road in connection to rising main (Part-B) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | 341/RCD I | 30/01/2023 | 15 | M/S MONDAL ENTERPRISE | 8.69 | 8.51 | 100 | 0
593 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Supply and delivery of CI sluice valve and C.I/D.I specials under improvement of RCFA part-I piped water supply scheme under RCFA div-I, PHE Dte. | 613/RCD I | 23/02/2023 | 10 | MAKALI ENGINEERING CORPORATION | 28.49 | 28.49 | 100 | 0
594 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Additional extra cutting Laterate/sandstone of distribution of pipe line at Improvement of RCFA Part-I W/S Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | 374/RCD I | 30/01/2023 | 15 | SWATI CORPORATION | 3.75 | 3.69 | 100 | 0
595 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Additional extra cutting Laterate/sandstone of distribution of pipe line at Improvement of RCFA Part-I W/S Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | 375/RCD I | 30/01/2023 | 15 | SWATI CORPORATION | 3.12 | 3.07 | 100 | 0
596 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Additional extra cutting laterate/sandstone of distribution network for improvement of Part-I W/S Scheme within command area of Zone VII under RCFA Div-I, PHE Dte(Part-E) | 695/RCD I | 02/03/2023 | 7 | TARA CONSTRUCTION | 0.83 | 0.79 | 100 | 0
597 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Supplying aligning and laying of HDPE Pipe line for restoration of pipe line towards MSPL at Kalyaneswari Dendua Road and supplying CI/DI specials in connection to aligning of rising main Part-A for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | 389/RCD I | 30/01/2023 | 10 | MD AAMIR KHAN | 21.01 | 20.7 | 100 | 0
598 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines including supplying and laying of 500 mm dia and 150 mm dia MS pipe line at different location on Asansol Chittaranjan Road within command area of Zone-I (Dendua OHR) Distribution system (Part-B) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | 1095/RCD-I | 23/03/2023 | 30 | SWATI CORPORATION | 25.75 | 25.59 | 100 | 0
599 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Material Requisition To Resource Division | 677/RCD-I | 21/03/2022 | 0 | Resource Division | 57.29 | 0 | 0 | 0
600 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Material Requisition To Resource Division | 301/RCD-I | 02/02/2022 | 0 | Resource Division | 676.57 | 0 | 0 | 0
601 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Material Requisition To Resource Division | 392/RCD-I | 16/02/2022 | 0 | Resource Division | 2340.25 | 0 | 0 | 0
602 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Material Requisition To Resource Division | 19/RCD-I | 05/01/2023 | 0 | Resource Division | 121.92 | 0 | 0 | 0
603 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Material Requisition To Resource Division | 2352/RCD-I | 28/09/2022 | 0 | Resource Division | 92.4 | 0 | 0 | 0
604 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Material Requisition To Resource Division | 54/RCD-I | 11/01/2023 | 0 | Resource Division | 180.92 | 0 | 0 | 0
605 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Material Requisition To Resource Division | 2644/RCD-I | 28/10/2022 | 0 | Resource Division | 64.5 | 0 | 0 | 0
606 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Material Requisition To Resource Division | 1637/RCD-I | 27/04/2023 | 0 | Resource Division | 127.23 | 0 | 0 | 0
607 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Payment for sample PT test bill no 376/21-22 dt. 25.06.2021 | 545/22-23 | 01/11/2022 | 0 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
608 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Deposition of way leave fee for pipeline crossing of Railway track in between Jamuria (JMA) and Barabani stan (BBI) km post 25/02-25/03 of Asansol Division | 65/23-24 | 25/05/2023 | 0 | EASTERN RAILWAY | 4.63 | 0 | 0 | 0
609 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Quotation Money for New Connection of Load at Tabadi (Adibasi Para) | BP-2023-24-9 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.34 | 0 | 0 | 0
610 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Quotation for Earnest money deposit for Bulk Power Supply at Ethora boosting Station Under Improvement of RCFA Part I WS Scheme. | BP-2023-24-31 | 13/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
611 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Deposition of way leave Fees for Railway crossing for pipeline. | 946/22-23 | 09/03/2023 | 0 | EASTERN RAILWAY | 6.08 | 0 | 0 | 0
612 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Deposition of way leave fee for pipeline crossing of Railway track in between Jamuria (JMA) and barabani (BBI) station of Asansol Division, Eastern Railway | 30/23-24 | 03/05/2023 | 0 | EASTERN RAILWAY | 0.53 | 0 | 0 | 0
613 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Quotation Money for New Connection of Load at Dhonudi. | BP-2023-24-10 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.34 | 0 | 0 | 0
614 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Quotation Money for New Connection of Load at Lalganj | BP-2023-24-11 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.48 | 0 | 0 | 0
615 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Vehicle bill | 1166/22-23 | 31/03/2023 | 0 | KHEPI MAA TRADERS | 2.21 | 0 | 0 | 0
616 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Payment for furniture | 433/22-23 | 21/09/2022 | 0 | VYAS & CO. | 2.35 | 0 | 0 | 0
617 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Desposition of way leave Fees for Railway crossing for pipeline. | 947/22-23 | 09/03/2023 | 0 | EASTERN RAILWAY | 5.04 | 0 | 0 | 0
618 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | fuel bill For WB 37D 0482 Nov 2022 | 821/22-23 | 20/01/2023 | 0 | RANAJIT AUTO | 0.27 | 0 | 0 | 0
619 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Quotation Money for Enhanacement of Load at Dendua. | BP-2023-24-9 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.88 | 0 | 0 | 0
620 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Deposition of way leave fee for pipeline crossing of Railway track in between Salanpur (SLS) and Rupnarayanpur (RNPR) km post 23/15-17 to 231/16-18 of Asansol Division, Eastern Railway | 64/23-24 | 25/05/2023 | 0 | EASTERN RAILWAY | 5.12 | 0 | 0 | 0
621 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | ER-ASN-2023-WL-28 (Salanpur SLS to Rupnarayanpur RNPR) | 130/23-24 | 10/07/2023 | 0 | EASTERN RAILWAY | 5.7 | 0 | 0 | 0
622 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Supply of computer for Assistant Enginner-II | 944/22-23 | 30/03/2023 | 0 | MUKHERJEE TRADERS | 0.42 | 0 | 0 | 0
623 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | VEHICLE BILL | 1165/22-23 | 30/03/2023 | 0 | PRAMIT CHATTERJEE | 1.2 | 0 | 0 | 0
624 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Engagement of 01 (One) no person under control of 2 (Two) nos AE/RCFA Div-I day to day report and return of FHTC as per scheme wise panchayet wise and updation of JJm | 320/23-24 | 16/10/2023 | 0 | MUKHERJEE TRADERS | 0.49 | 0 | 0 | 0
625 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Restoration amount for unauthorised execavation and damaged at Ethora Nuni Road [Road connecting FR 10 and FR 19 (FR 13) under Asansol highwa | Asn-Highway-PWD | 11/01/2023 | 0 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, PW (ROADS) DIRECTT. | 10.45 | 0 | 0 | 0
626 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | VEHICLE BILL | 1113/22-23 | 30/03/2023 | 0 | SHYAMAL MAJI | 0.19 | 0 | 0 | 0
627 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | IT GST FILLING | 1206/22-23 | 30/03/2023 | 0 | SHRESTHA & ASSOCIATES | 0.5 | 0 | 0 | 0
628 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Meter Shifting Charge of Ethora Water tank under Improvement of RCFA (Part-I) Piped Water Supply Scheme | BP-2023-24-53 | 29/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
629 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | DEPOSITION OF WAY LEAVE FEE (ER-ASN-2023-WL-17) | 41/23-24 | 10/05/2023 | 0 | EASTERN RAILWAY | 5.37 | 0 | 0 | 0
630 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | June 2022 to Novemeber & December 2022 to Feburary 2023 | 19/23-24 | 18/04/2023 | 0 | PRASENJIT DEY | 3.6 | 0 | 0 | 0
631 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Hiring of Maxi Cab (Non Air-conditioned) Bharat Stage-II/BS-III purchased on or after 01.05.2008 with Diesel/LPG/CNG Engine. for the Office use of the Assistant Engineer, RCFA Division-I, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.07.2022 to 30.06.2023)(sl no 01) | 1210/22-23 | 31/03/2023 | 0 | NIRMALA TRADERS | 2.8 | 0 | 0 | 0
632 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Construction of CWR (90 cum) at Surjanagar Head Works Site to replace existing damaged CWR under Improvement of RCFA (Part-I) Piped Water Supply Scheme. | 376_RCD_I | 15/02/2022 | 30 | MD AAMIR KHAN | 0 | 0 | 0 | 0
633 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal Work Order for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-VIII with LDS & FHTC Work | 1329/RCD-I | 09/06/2022 | 180 | SWATI CORPORATION | 399.2 | 327.2 | 81.97 | 100
634 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal Work Order for Construction of 350 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone-IX) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (2nd Call) | 2403/RCD-I | 30/09/2022 | 365 | MALLICK ENTERPRISE | 107.64 | 107.64 | 100 | 95
635 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for construction of Chlorine Room of Size (4.50 x 3.50 m) at (Zone-VI) of Salanpur Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman | 357/RCDI | 30/01/2023 | 15 | DAS & SARKAR ENTERPRISE | 4.6 | 3.75 | 100 | 100
636 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for the additional work for the laying of different dia (315 mm , 280 mm, 225 mm ) dia HDPE pipe instead of different dia (300 mm , 250 mm, 200 mm) dia DJ pipe of distribution network for improvement RCA Part-I Water Supply Scheme within command area of Zone VI under RCFA Div-I, PHE Dte (Part-A) | 1051/RCD I | 23/03/2023 | 30 | DIP CONSTRUCTION | 98.08 | 89.82 | 94.24 | 100
637 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Samdi and surrounding villages within Samdi Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte. | 3450/RCD-I | 24/11/2023 | 15 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 3.39 | 3.35 | 100 | 100
638 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. on smooth durable wall surface preferably of Govt. premises boundary wall under RCFA Division-I PHE Dte. | Camp-02-Wall-Writing-AE-I | 18/01/2024 | 30 | MUKHERJEE TRADERS | 6.61 | 6.59 | 100 | 100
639 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Construction of RCC column and M.S Structural Bridge for laying of 200 m dia MS pipe and other allied work for distribution network for Improvement of RCFA Part-I water supply scheme within command area of Zone-VII under RCFA Division ¿I PHE Dte | 1012/RCD-I | 16/03/2024 | 30 | UNITED CONSTRUCTION | 6.54 | 6.47 | 100 | 100
640 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Shifting of High Tension Line and Street Light from the Proposed WTP plant area in Kalyaneswari Campus under Improvement of RCFA I Water Supply Scheme | BP-2023-24-59 | 26/12/2023 | 0 | CHIEF ACCOUNTS OFFICER, DAMODAR VALLEY CORPORATION | 0.24 | 0 | 0 | 0
641 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Service connection and Security Deposit charge at Ethora Boosting Station under Improvement of RCFA Part-I W/S Scheme. | BP-2023-24-67 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 25.69 | 0 | 0 | 0
642 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Construction of CWR (90 cum) at Surjanagar Head Works Site to replace existing damaged CWR under Improvement of RCFA (Part-I) Piped Water Supply Scheme. | 376/RCD-I | 15/02/2022 | 30 | MD AAMIR KHAN | 22.72 | 10.42 | 45.84 | 100
643 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-6 Distribution Segment) under RCFA Division-I PHE Dte. | 496/RCD-I | 24/02/2022 | 1087 | UMA ENTERPRISE | 63.83 | 50.69 | 100 | 70
644 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-2 Distribution Segment) under RCFA Division-I PHE Dte. | 492/RCD-I | 24/02/2022 | 90 | SNEHA ELECTRIC | 25.78 | 25.39 | 98.48 | 75
645 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-7 Distribution Segment) under RCFA Division-I PHE Dte. | 497/RCD-I | 24/02/2022 | 90 | UNITED CONSTRUCTION | 23.75 | 23.72 | 99.88 | 80
646 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-9 Distribution Segment) under RCFA Division-I PHE Dte. | 499/RCD-I | 24/02/2022 | 90 | SOMNATH SAMANTA | 39.28 | 38.73 | 98.61 | 98
647 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-3 Distribution Segment) under RCFA Division-I PHE Dte. | 493/RCD-I | 24/02/2022 | 401 | VISUVIOUS | 25.41 | 23.7 | 93.28 | 100
648 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-5 Distribution Segment) under RCFA Division-I PHE Dte. | 495/RCD-I | 24/02/2022 | 1101 | M/S B.K. CONSTRUCTION | 44.11 | 37.17 | 84.27 | 100
649 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VI under RCFA Division-I PHE Dte. (Part-A) | 932/RCD-I | 26/04/2022 | 615 | DIP CONSTRUCTION | 61.83 | 51.53 | 83.35 | 100
650 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VI under RCFA Division-I PHE Dte. (Part-B) | 933/RCD-I | 26/04/2022 | 90 | M/S K & KONAR CONSTRUCTION | 75.35 | 69.5 | 92.23 | 90
651 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - A) | 1038/RCD-I | 10/05/2022 | 1179 | ASHA CONSTRUCTION | 147.65 | 58.28 | 48.06 | 100
652 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-D) (2nd Call) | 1007/RCD-I | 05/05/2022 | 90 | GITASREE FABRICATION | 77.41 | 66.72 | 86.18 | 85
653 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply within command area of Zone-VI under RCFA Division-I PHE Dte. (Part ¿ C) | 1214/RCD-I | 30/05/2022 | 90 | RANJIB GHATAK | 100.72 | 90.61 | 89.96 | 90
654 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Rising Main for Improvement RCFA Part-I Water Supply Scheme for Salanpur and Barabani Block under RCFA Div-I PHE Dte. (Part B) | 931/RCD-I | 26/04/2022 | 736 | M/S MONDAL ENTERPRISE | 82.94 | 61.98 | 74.73 | 100
655 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply within command area of Zone-IX under RCFA Division-I PHE Dte. (Part C) | 1213/RCD-I | 30/05/2022 | 1281 | T M CONCRETE CREATION PRIVATE LIMITED | 131.44 | 108.9 | 82.85 | 65
656 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-C) | 1605/RCD-I | 06/07/2022 | 90 | PINKI ENTERPRISE | 78.73 | 37.76 | 47.96 | 80
657 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-B) | 1611/RCD-I | 06/07/2022 | 1365 | UNITED CONSTRUCTION | 55.84 | 16.36 | 100 | 75
658 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-7 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | 1702/RCD-I | 14/07/2022 | 45 | UNITED CONSTRUCTION | 20.25 | 19.99 | 98.73 | 5
659 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-5 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | 1707/RCD-I | 14/07/2022 | 45 | M/S B.K. CONSTRUCTION | 32.05 | 20.27 | 63.25 | 100
660 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Distribution Network for Improvement of RCFA Part-II Water Supply Scheme Under RCFA Division-I PHE Dte. | 2451/RCD-I | 13/10/2022 | 180 | SINGHA ROY & CO. | 270.57 | 65.85 | 24.34 | 0
661 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal Work Oder for Construction of 900 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone-XI) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 2005/RCD-I | 25/08/2022 | 365 | AMAR CONSTRUCTION | 181 | 162.9 | 90 | 100
662 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order of Construction of CWR (Clear Water Reservoir) of Capacity 500 cum and allied work at Dendua under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | 2484/RCD I | 18/10/2022 | 120 | D.S. ENTERPRISE | 61.78 | 43.72 | 70.77 | 96
663 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-F) | 2404/RCD-I | 30/09/2022 | 180 | GITA CONSTRUCTION | 201.57 | 131.66 | 65.32 | 67
664 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Providing and installation of Gaseous Chlorination system at OHR Site under Zone-XIII under Augmentation of RCFA Part-I water Supply Scheme, Dist.- Paschim Bardhaman. (2nd Call). | 608/AMD | 03/03/2023 | 1036 | M/S SAJAHAN CHOWDHURY | 20.86 | 18.56 | 88.96 | 100
665 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Repairing and renovation of Panchagachia OHR of Capacity 1000 cum staging height 15 mtr under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | 399/RCD I | 30/01/2023 | 90 | RUBY CONSTRUCTION | 20.33 | 11.62 | 57.14 | 100
666 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Accepatance cum work order for construction of chlorine room of size (4.50 X 3.50m) at (Zone-IX) of Baraboni Block for Improvement of RCFA Part-I piped water supply scheme under RCFA Div-I, PHE Dte., in the District Paschim Bardhaman. | 676/RCDI | 24/02/2023 | 15 | ZEROTH CONTROL SYSTEM | 4.61 | 2.91 | 63.24 | 100
667 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Laying & Pushing of 500 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of water pipe lines including supplying and laying of 200 mm dia 250 mm dia MS pipe line at different location on Asansol Chittanrajan Road, Kalyaneswari Dendua road within command area of rising main (Part-A) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | 1060/RCD-I | 23/03/2023 | 15 | MAK CONSTRUCTION CO. | 40.5 | 39.62 | 97.83 | 100
668 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Dismanting of existing Drain and reconstruction the same, Construction of RCC pipe carring structur and other allied work at Alladih more and Rupnarayanpur Railway Station Site of improvement of RCFA Part -I in Connection of Rising main Part-A under RCFA Division-I PHE Dte.(Sl No. 06) | 1066/RCD I | 23/03/2023 | 30 | MAK CONSTRUCTION CO. | 31.64 | 29.75 | 94.03 | 100
669 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-7 Distribution Segment) under RCFA Division-I PHE Dte. | 1138/RCD-I | 24/03/2023 | 30 | UNITED CONSTRUCTION | 24.64 | 17.12 | 69.46 | 90
670 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Pipe line crossing by adopting trench less technology (e.g. Jack Pushing Method etc) at 7 nos location at Zone-V area Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1065/RCD-I | 23/03/2023 | 30 | MRITYUNJOY MUKHERJEE & CO. | 45.79 | 45.79 | 100 | 50
671 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VI under RCAF Division-I PHE Dte. (Part-C) (Sl. No. 17) | 1143/ RCD I | 24/03/2023 | 30 | RANJIB GHATAK | 26.19 | 12.65 | 48.29 | 90
672 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Road crossing by open cut near to Nuni more including construction of drain, laterite cutting, concrete and bitumen road cutting and allied works at Ethora and adjacent area for laying of Rising Main (Part-B) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 08) | 1152/RCD-1 | 24/03/2023 | 15 | M/S MONDAL ENTERPRISE | 5.09 | 4.7 | 92.33 | 100
673 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for additional work for laying of distribution network for Improvement RCFA Part-I Piped Water Supply Scheme within command area of Zone-XI (Part-9 Distribution Segment) under RCFA Div-I, PHE Dte. | 1035/RCDI | 23/03/2023 | 376 | SOMNATH SAMANTA | 42.19 | 20.02 | 47.46 | 100
674 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-4 Distribution Segment) under RCFA Division-I PHE Dte. | 1136/RCD-I | 24/03/2023 | 30 | DAWN CONSTRUCTION | 56.15 | 31.27 | 55.7 | 90
675 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal work order for Supplying aligning and laying of different dia HDPE pipe line instead of DI pipe line within distribution network within command are of Zone-I (Dendua OHR Site) of Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1610/RCD I | 25/04/2023 | 90 | SWATI CORPORATION | 114.21 | 98.16 | 85.94 | 86
676 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal work order for 200 mm, 160 mm & 90 mm dia HDPE PE-80 distribution network of RCFA Part-I Water Supply Scheme command area of Zone-IX under RCFA Div-I PHE Dte. | 1612/RCD I | 25/04/2023 | 90 | KHEPI MAA TRADERS | 149.55 | 53.69 | 35.9 | 90
677 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - B) | 1020/RCD-I | 06/05/2022 | 180 | SWATI CORPORATION | 149.9 | 63.87 | 42.61 | 85
678 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-4 Distribution Segment) under RCFA Division-I PHE Dte. | 494/RCD-I | 24/02/2022 | 1042 | DAWN CONSTRUCTION | 68.87 | 65.56 | 95.19 | 100
679 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Continuation work order for Pipe line crossing by adopting trench less technology (e.g. Jack Pushing Method etc) at 7 Nos. location at Zone-V area Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1911/RCD-I | 14/06/2023 | 30 | MRITYUNJOY MUKHERJEE & CO. | 19.62 | 15.26 | 77.78 | 80
680 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Continuation work order for Laying & Pushing of 600 mm dia MS Water Carrier pipe and road Crossing by adopting trench less technology at Dendua more to Kalyaneswari road of Improvement of RCFA Part-I in connection of rising main (Part-A) under RCFA Division-I PHE Dte. | 1883/1/RCD-I | 07/06/2023 | 15 | MD AAMIR KHAN | 66.19 | 66.19 | 99.99 | 0
681 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Additional work laying of 180 mm dia HDPE pipe line at Alladi More to Jemnari Bus Stand and Railway crossing at Rupnarayanpur village in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of (Zone-V) with LDS & FHTC work under RCFA Division-I PHE Dte. | 2212/RCD-I | 17/07/2023 | 30 | MACHINO TECHNO | 54.74 | 10.58 | 19.32 | 100
682 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Balance work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS & FHTC work under RCFA Division-I PHE Dte. | 2239/RCD-I | 17/07/2023 | 259 | MRITYUNJOY MUKHERJEE & CO. | 88.68 | 0 | 0 | 100
683 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Kelejhora Health Centre More under Improvement of RCFA Part-I (Zone-11) PWSS under RCFA Division-I PHE Dte. | 2233/RCD-I | 17/07/2023 | 30 | SNEHA ELECTRIC | 29.11 | 16.38 | 56.27 | 55
684 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Additional works of Dismantling & concrete works & extra cutting Laterate/sandstone at distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | 2248/RCD-1 | 17/07/2023 | 30 | SWATI CORPORATION | 12.73 | 9.93 | 77.96 | 80
685 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 3 (Three) nos. location at Lalganj Domohani Road under Improvement of RCFA Part-I (Zone-11) PWSS under RCFA Division-I PHE Dte. | 2230/RCD-I | 17/07/2023 | 30 | R B ENTERPRISE | 42.66 | 26.2 | 61.41 | 65
686 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Balance work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V under RCFA Division-I PHE Dte. | 2211/RCD-I | 17/07/2023 | 30 | MACHINO TECHNO | 19.71 | 11.22 | 56.9 | 60
687 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-1 Distribution Segment) under RCFA Division-I PHE Dte. | 491/RCD-I | 24/02/2022 | 90 | R B ENTERPRISE | 27.59 | 26.92 | 97.56 | 85
688 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Additional work for the laying of DI pipe, MS work, making valve chamber and other allied works for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-2 Distribution Segment) under RCFA Division-I PHE Dte. | 2366/RCD-I | 04/08/2023 | 30 | SNEHA ELECTRIC | 51.75 | 50.2 | 97.01 | 98
689 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - C) | 1039/RCD-I | 10/05/2022 | 1179 | DAS & CHAKRABORTY | 130.86 | 56.55 | 43.21 | 100
690 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (Length-160 mtr) at Malbahal OHR site of Improvement of RCFA Part-I Piped Water Supply Scheme under Salanpur Block under RCFA Division-I PHE Dte. | 2662/RCD-I | 26/09/2023 | 583 | AMAR CONSTRUCTION | 35.5 | 0 | 0 | 100
691 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal Work Order for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS & FHTC work | 1379/RCD-I | 17/06/2022 | 180 | MRITYUNJOY MUKHERJEE & CO. | 466.46 | 346.89 | 74.37 | 80
692 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-A) | 1610/RCD-I | 06/07/2022 | 990 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 64.62 | 18.73 | 28.99 | 100
693 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Construction of 1 (One) no. Chlorine Room including Plinth protection, drain for 900 cum and 250 cum OHR at Baliapur under Improvement of RCFA (Part-I) Piped Water Supply Scheme. under RCFA Division-I PHE Dte. | 2138/RCD-I | 27/08/2024 | 60 | AMAR CONSTRUCTION | 9.01 | 0 | 0 | 100
694 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Allied Works Corresponding to "Providing And Installation of Electro-Mechanical Equipments and Sub-Stations Equipments at Ethora Boosting Station under Improvement of RCFA Part-I Block:- Salanpur, Dist -Paschim Bardhaman. | 2121/AMD | 16/12/2024 | 142 | NEW ALIGNMENT | 8.12 | 0 | 0 | 70
695 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Installation of yard lighting arrangement, electrical wiring of chlorine room with lighting luminaries of Tabadi O.H.R. premises under Improvement of RCFA Part-I W/S Scheme. | 954/AMD | 16/05/2025 | 202 | P.K.ENGINEERING | 4.23 | 0 | 0 | 100
696 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Providing and installation of Gaseous chlorination system at Malladi OHR Site under Augmentation of RCFA Part-I Water Supply Scheme. | 992/AMD | 23/05/2025 | 30 | P.K.ENGINEERING | 28.7 | 0 | 0 | 0
697 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Formal Work order for Rising Main for Improvement RCFA Part-I Water Supply Scheme for Salanpur and Barabani Block under RCFA Division-I PHE Dte. (Part ¿ A) | 1073/RCD-I | 13/05/2022 | 719 | MD AAMIR KHAN | 115.25 | 75.01 | 73.7 | 90
698 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Construction of 900 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone VII) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (2nd Call) | 2453/RCD-I | 13/10/2022 | 365 | SINGHA ROY & CO. | 181.16 | 181.16 | 100 | 100
699 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Providing and installation of Gaseous Chlorination system at OHR Site under Zone-IX under Augmentation of RCFA Part-I water Supply Scheme, Block-Salanpur, Dist.- Paschim Bardhaman. | 366/AMD | 09/02/2023 | 919 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 20.85 | 18.55 | 89 | 100
700 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Providing and installation of Gaseous Chlorination system at OHR Site at under Zone-VI under Augmentation of RCFA Part-I Water Supply Scheme, Dist.- Paschim Bardhaman. | 364/AMD | 09/02/2023 | 930 | MAHADEV ENTERPRISE | 20.86 | 18.56 | 88.97 | 100
701 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Providing and installation of Gaseous Chlorination system at OHR Site under Zone-VII under Augmentation of RCFA Part-I water Supply Scheme, Block-Salanpur, Dist.- Paschim Bardhaman. | 365/AMD | 09/02/2023 | 1676 | ORIENTAL ENGINEERING CO. | 20.75 | 18.34 | 88.39 | 80
702 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Providing and installation of Gaseous Chlorination system at Dendua Boosting Station under Augmentation of RCFA Part-I water Supply Scheme, Block-Salanpur, Dist.- Paschim Bardhaman. | 363/AMD | 09/02/2023 | 729 | EASTERN INDIA SALES AND SERVICE | 20.86 | 18.44 | 88.43 | 100
703 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Providing and installation of Gaseous Chlorination system at OHR Site under Zone-XI under Augmentation of RCFA Part-I water Supply Scheme, Dist.- Paschim Bardhaman. | 418/AMD | 16/02/2023 | 919 | MACHINE SUPPLIERS SYNDICATE(P) LTD. | 20.56 | 18.28 | 88.95 | 100
704 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Providing And Installation of Electro-Mechanical Equipments and Allied Works at Dendua Boosting Station under Augmentation of RCFA Part-I Water Supply Scheme, Block-Salanpur, Dist.-Paschim Bardhaman. | 1951/AMD | 22/12/2022 | 771 | EASTERN INDIA SALES AND SERVICE | 129.01 | 72.34 | 56.08 | 100
705 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply within command area of Zone-VI under RCFA Division-I PHE Dte. (Part-B) | 1134/RCD-I | 24/03/2023 | 30 | M/S K & KONAR CONSTRUCTION | 30.49 | 19 | 100 | 100
706 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc.) at Lalganj more and Nuni more in related to laying of rising main (Part-B) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | 1127/ RCD I | 24/03/2023 | 15 | M/S MONDAL ENTERPRISE | 23.75 | 23.62 | 100 | 0
707 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Construction of drain at Ethora and its adjoining mouzas under Improvement of RCFA Part-I W/S Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | 1086/RCD-I | 23/03/2023 | 60 | SWATI CORPORATION | 23.95 | 23.94 | 100 | 0
708 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Laying & Pushing of 400 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of water pipe lines at Sandi More (Node point 137) Sandi Masimura More (Node point 85) and Lalganj Domhani Road (Node point 5-26) under Augmentation of RCFA Part-I PWSS within command area of Zone-VIII under RCFA Division-I PHE Dte. | 1093/RCD-I | 23/03/2023 | 30 | SWATI CORPORATION | 19.65 | 19.65 | 100 | 0
709 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-6 Distribution Segment) under RCAF Division-I PHE Dte. (SL No. 16) | 1142/ RCD I | 24/03/2023 | 283 | UMA ENTERPRISE | 76.17 | 32.7 | 73.64 | 100
710 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Laying & Pushing of 400 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. jack Pushing Method etc) of Water Pipe Lines at Dabor More (Node point 334) Youth club (Node point 398) and Jaya hotel (Node point 228) Augmentation of RCFA Part-I PWSS within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-E) (Sl No. 28) | 1094 / RCD-I | 23/03/2023 | 30 | TARA CONSTRUCTION | 23.59 | 23.59 | 100 | 0
711 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for additional dedicated line to Sen Raleigh (Block-B) under Panchgachiya Distribution zone including laying of UPVC pipe line and allied works under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Div-I, PHE Dte. | 1054/RCD I | 23/03/2023 | 15 | RUBY CONSTRUCTION | 11.13 | 11.11 | 100 | 0
712 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Laying & Pushing of 600mm dia ms water Carrer pipe and road Crossing by adopting trenchless technology at Dendua more to Kalyaneswri road of improvement of RCFA Part-I in connection of rasing main (part-A) under RCFA Division-I PHE Dte.(Sl No. 07) | 1405/RCD-1 | 12/04/2023 | 357 | MD AAMIR KHAN | 90.31 | 68.18 | 75.59 | 100
713 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum Work Order for Dismantling of existing guard room and store room for construction of 500 cum CWR at Dendua Boosting station of Improvement of RCFA Part-I under RCFA Division-I PHE Dte. (Sl No. 09) | 1153/RCD-1 | 24/03/2023 | 10 | D.S. ENTERPRISE | 1.02 | 1.02 | 100 | 0
714 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Additional work for laying of 200 mm dia Rising Main under Lalganj Bridge by concrete conduit and allied MS work including adopting trench less technology (e.g. Jack Pushing Method etc) of 04 (Four) nos. location at Barabani & near Kelejora Health Centre in connection to rising main (Part-B) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2235/RCD-I | 17/07/2023 | 30 | M/S MONDAL ENTERPRISE | 50.86 | 50.09 | 100 | 100
715 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Additional Laying & Pushing of 400 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines and Supplying Aligning Laying MS pipe (including carring loading & unloading at work site) Head Works Site (node point R1-1) and Lalganj Hat of Improvement RCFA Part-I PWSS within command area of Zone-VIII under RCFA Division-I PHE Dte. | 2246/RCD-1 | 17/07/2023 | 30 | TARA CONSTRUCTION | 17.17 | 15.58 | 100 | 100
716 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Dabor More (250 mm dia Water Carrier 02 nos) and Dendua road to Chittaranjan road 01 no 450 mm dia Water Carrier and 02 nos 450 mm dia Water Carrier Pipe on Bonjemary Road of Salanpur Block under Improvement of RCFA Part-I (Part-A Rising Main) PWSS under RCFA Division-I PHE Dte. | 2236/RCD-I | 17/07/2023 | 30 | MD AAMIR KHAN | 51.47 | 51.44 | 100 | 100
717 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-8 Distribution Segment) under RCFA Division-I PHE Dte. | 2216/RCD-I | 17/07/2023 | 30 | SIMA ENTERPRISE | 16.68 | 15.96 | 100 | 100
718 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-5 Distribution Segment) under RCFA Division-I PHE Dte. | 2238/RCD-I | 17/07/2023 | 30 | M/S B.K. CONSTRUCTION | 39.57 | 24.47 | 100 | 100
719 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Gowalabathan More towards Jamuria Road, Gowala para more towards Domohani Village, Goshala More towards Domohani village under Improvement of RCFA Part-I (Zone-11, Part-5) PWSS under RCFA Division-I PHE Dte. | 2232/RCD-I | 17/07/2023 | 30 | M/S B.K. CONSTRUCTION | 19.77 | 19.76 | 100 | 100
720 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Additional work for the laying of distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-5 Distribution Segment) under RCFA Division-I PHE Dte. (Part-B) | 2208/RCD-I | 17/07/2023 | 30 | M/S B.K. CONSTRUCTION | 12.78 | 11.55 | 100 | 100
721 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptation cum work order for Additional work for allied work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS and FHTC work under RCFA Division-I PHE Dte. | 2254/RCD-I | 17/07/2023 | 30 | MACHINO TECHNO | 99.31 | 71.44 | 90.29 | 100
722 | PASCHIM BARDHAMAN | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Acceptance cum work order for Additional works of Dismantling & concrete works & extra cutting Laterate/sandstone at distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-E) | 2247/RCD-1 | 17/07/2023 | 30 | TARA CONSTRUCTION | 10.06 | 9.8 | 100 | 100
723 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house & Substation Buliding with Yard lighting arrangement and other allied works at Ethora Boosting Station under " improvement of RCFA Part-I" Water Supply Scheme. | 2095/AMD | 12/12/2024 | 387 | PREMNATH MITRA | 23.48 | 0 | 0 | 100
724 | PASCHIM BARDHAMAN | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. , SM/09916 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at Dendua Pump House under Improvement R.C.F.A. PART-I Water Supply Scheme. | 1198/AMD | 07/08/2024 | 45 | EASTERN INDIA SALES AND SERVICE | 5.46 | 0 | 0 | 100
725 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-11) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 1755/RCD-I | 12/05/2023 | 90 | MAA DURGA ENTERPRISE | 4.6 | 0 | 0 | 0
726 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Amnala more to towards Amnala village surrounding area (Zone-IX) under Improvement of RCFA Part-I (Zone-11) PWSS under RCFA Division-I PHE Dte. | 2228/RCD-I | 17/07/2023 | 30 | KHEPI MAA TRADERS | 13.09 | 13.09 | 100 | 100
727 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Material Requisition To Resource Division | 2947/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
728 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Formal work order for distribution network for RCFA Part-II Piped Water Supply including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-11) | 1390/RCD I | 11/04/2023 | 90 | M/S SRI MAHADEO ENTERPRISES | 294.95 | 247.45 | 83.9 | 85
729 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order for Trial Run for Barabani Kashidanga under Improvement of RCFA Part-I (Zone-XI) Piped W/S Scheme under RCFA Division-I PHE Dte. (180 days) | 3455/RCD-I | 24/11/2023 | 180 | UNITED CONSTRUCTION | 1.08 | 0 | 0 | 0
730 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptence cum work order for Additional work repairing old plaster surface, color washing, painting and R.B.T. (Reinforced Barbed Tape) Concertina fencing on wall and allied works at Kalyaneswari Inspection Bungalow under RCFA Division-I PHE Dte | 2581/RCD-I | 07/09/2023 | 15 | JYOGOMAYA ENTERPRISE | 5.71 | 5.14 | 100 | 100
731 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Ethora (779 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3016/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.93 | 4.93 | 100 | 100
732 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Pariharpur (900 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3023/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.95 | 4.95 | 100 | 100
733 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Amritnagar (1135 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3026/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100 | 100
734 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order for Additional work for laying distribution main over concrete pillar including supply of rubber gusket within Zone-XI Part-I under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | 3475/RCD-I | 28/11/2023 | 15 | R B ENTERPRISE | 4.89 | 1.86 | 100 | 100
735 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order for Additional supplying, aligning, laying HDPE & PVC pipe line, construction of sluice valve chamber and other allied works under Tirat Mouza (Taldanga, Pathan Dhaora & Shyamdanga) W/S Scheme under RCFA Division-I PHE Dte. | 3425/RCD-1 | 24/11/2023 | 30 | RUBY CONSTRUCTION | 6.78 | 6.65 | 100 | 100
736 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order for Sinking of 3 (Three) nos 200 mm dia river bed tube well including collecting main in the river of Damodar at D.P Colony H/W Site for D P Colony Water Supply Scheme under RCFA Division-I PHE Dte. | 3423/RCD-1 | 24/11/2023 | 15 | DURGA DAS MONDAL | 9.53 | 9.49 | 100 | 100
737 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order for Additional works of Dismantling & concrete works, Supplying, Aligning & Laying HDPE Pipe and other allied works at distribution system Network for Shyamlya in Chatrisganda Mouza under Shyamlya Gram Panchayat under Jamuria Block under RCFA Division-I PHE Dte. (Part-B) | 3499/RCD-1 | 30/11/2023 | 30 | DAWN CONSTRUCTION | 45.48 | 45.02 | 100 | 100
738 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order for Additional work for laying collecting and other allied works at DP Colony PWSS under RCFA Division-I PHE Dte. Augmentation PWSS of RCFA Part-II (Zone-11) | 505/RCD-I | 12/02/2024 | 30 | DURGA DAS MONDAL | 7.01 | 6.9 | 100 | 100
739 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum Work Order for Extension of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-8 Distribution Segment) under RCFA Division-I PHE Dte. | 926/RCD-I | 15/03/2024 | 20 | SIMA ENTERPRISE | 7.02 | 6.79 | 100 | 100
740 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area Zone-VII of Augmentation of RCFA Part-II (Zone-11) PWSS under RCFA Division-I PHE Dte. (Part-D) | 935_RCD_I | 15/03/2024 | 15 | KONAR CONSTRUCTION | 23.57 | 23.52 | 100 | 100
741 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-91 at Pandabeswar under Augmentation of RCFA Part-II (Zone-11) under RCFA Division-I PHE Dte | 47/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 5.45 | 0 | 0 | 0
742 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Way leave track crossing proposal with application ID - ER-ASN-2024-WL-56 Payment of wayleave facility charges. | 272/24-25 | 05/09/2024 | 0 | EASTERN RAILWAY | 6.27 | 0 | 0 | 0
743 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-90 at Pandabeswar under Augmentation of RCFA Part-II (Zone-11) under RCFA Division-I PHE Dte | 49/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 5.45 | 0 | 0 | 0
744 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-18 under Augmentation of RCFA Part-II (Zone-11) under RCFA Division-I PHE Dte | 69/24-25 | 30/05/2024 | 0 | EASTERN RAILWAY | 14.3 | 0 | 0 | 0
745 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir at (Zone-11) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3350/RCDI | 23/12/2022 | 770 | MOYTEC | 0.49 | 0.49 | 100 | 100
746 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr. staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Raniganj Block (Zone-11) for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman. Ref Drawing No. PC-I/OHR/2012 (Sheet No. 1 & 2) | 1841/RCD-I | 31/05/2023 | 366 | DAS & CHAKRABORTY | 115.95 | 104.36 | 90 | 90
747 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum Work Order for Balance work for Enamel paint, painting, weather coat at treatment plant, bridge, CWR and other places for Amritnagar Zone-I under Augmentation of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | 507/RCD-I | 12/02/2024 | 30 | MRITYUNJOY MUKHERJEE & CO. | 16.92 | 16.1 | 100 | 100
748 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. , SM/12210 | Augmentation | Acceptance cum work order for Additional work concrete cutting, restoration of road and allied works within command area of Zone-11 (Part-6 Distribution Segment) of under RCFA Division-I PHE Dte. | 467/RCD-1 | 12/02/2024 | 20 | M/S SUBHRADEEP | 17.08 | 16.96 | 100 | 100
749 | PASCHIM BARDHAMAN | Durgapur W/S Division | BIRUDIHA PIPED WATER SUPPLY SCHEME , SM/11224 | New | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Birudiha piped W/s Scheme under DWSD ,PHE Dte (SL-04) | 1241/DWSD | 18/08/2022 | 15 | MD AAMIR KHAN | 14.75 | 14.3 | 100 | 0
750 | PASCHIM BARDHAMAN | Central Mechanical | BIRUDIHA PIPED WATER SUPPLY SCHEME , SM/11224 | New | Supply & Installation of Submersible Pumping Machinery, Voltages Stabilizer , Chlorination system and internal House wiring for Tube well for Tube well no:- 1 & 2 at Birudiha water supply scheme under CMD PHE Dte, Dist: Paschim Bardhaman. | 1657/CMD | 06/04/2023 | 30 | MAA TARA ENTERPRISE | 21.19 | 20.56 | 100 | 100
751 | PASCHIM BARDHAMAN | Durgapur W/S Division | BIRUDIHA PIPED WATER SUPPLY SCHEME , SM/11224 | New | New service connection charges for birudiha Water Supply scheme (TW-2) | BP-2023-24-89 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.27 | 0 | 0 | 0
752 | PASCHIM BARDHAMAN | Durgapur W/S Division | BIRUDIHA PIPED WATER SUPPLY SCHEME , SM/11224 | New | Quotation money for new electric service connection at Birudiha under Birudiha piped W/s Scheme. | BP-2023-24-38 | 01/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.29 | 0 | 0 | 0
753 | PASCHIM BARDHAMAN | Durgapur W/S Division | BIRUDIHA PIPED WATER SUPPLY SCHEME , SM/11224 | New | Dismantling of concrete road and bituminiou road and land development for constrution of 250 M3 OHR of 20 mtr staging height as per Deptt drawing ,laying alingining of rising main and provding FHTC connection of all mouzas under command area of Birudiha piped W/s Scheme under DWSD ,PHE Dte | 722/DWSD | 11/05/2023 | 25 | M/S K.B.CONSTRUCTION | 30.05 | 29.88 | 99.41 | 100
754 | PASCHIM BARDHAMAN | Durgapur W/S Division | BIRUDIHA PIPED WATER SUPPLY SCHEME , SM/11224 | New | Formal order for the work of laying distribution system ,Rising main ,constrcution of 250 M3 Reservoir with 20 mtr staing height including soil inverstigation ,construction of Pump house (5.4X3.60) with sanitary and Water supply arrangement and construction of Pump house (3.60 X 3.00 m) wiht FHTC for Birudiha piped W/s Scheme under DWSD ,PHE Dte (New Scheme). | 1437/DWSD | 13/10/2022 | 365 | KHAN ENTERPRISE | 524.96 | 477.66 | 90.99 | 100
755 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Material Requisition To Resource Division | 2958/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
756 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Acceptance cum work order for Balance work for laying MS pipe and allied works including Adopting trench less technology (e.g. Jack Pushing Method etc) for crossing of important roads (2 nos location at zone-4A) of Augmentation PWSS of RCFA Part-II (Zone-2) under RCFA Division-I, P.H.E. Dte. | 2132/RCD-I | 27/08/2024 | 30 | UNITED CONSTRUCTION | 39.74 | 32.91 | 82.83 | 100
757 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir at (Zone-2) of Ondal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3358/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0.48 | 100 | 100
758 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Acceptance cum work order for Providing FHTC through Retrofitting at Pathakpara Block Anda & Pandabeswar of Ukhra under Augmentation of RCFA Part-II (Zone-2) PWSS under RCFA Division-I PHE Dte. (Part-C) | 367/RCDI | 30/01/2023 | 30 | JAI MAHARAJ ENTERPRISE | 5.62 | 5.2 | 100 | 100
759 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Acceptance cum work order for Repairing of damaged collecting main in river Damodar rising main to D.P Colony OHR and allied works of DP colony W/S scheme under RCFA Division -I PHE Dte. | 3370/RCD-1 | 21/11/2023 | 15 | DURGA DAS MONDAL | 4.98 | 4.42 | 100 | 100
760 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Acceptance cum work order for Laying of different dia HDPE pipe line towards Teli Para (Sansad -XIV) under Ukhra area Block- Andal & Pandabswar of Augmentation of RCFA Part-II (Zone-2) Water Supply Scheme under RCFA Division-I PHE Dte. | 3188/RCD-I | 01/11/2023 | 15 | NILIMA CONSTRUCTION | 2.49 | 2.3 | 100 | 100
761 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Acceptance cum work order for Additional for supplying & laying M.S pipe, Supplying specials for Interconnection work for Improvement of RCFA Part-I for Augmentation of RCFA Part-II (Zone-2) PWSS within command area of Zone-VIII under RCFA Div-I, PHE Dte. | 2110/RCD-I | 27/08/2024 | 25 | TARA CONSTRUCTION | 13.73 | 13.21 | 100 | 100
762 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Payment of Way leave Plan & Survey charges for track crossing proposal with Application ID ER-ASN2024-WL-18 dt 15.04.2024 | 11/24-25 | 24/04/2024 | 0 | EASTERN RAILWAY | 0.25 | 0 | 0 | 0
763 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | PAYMENT OF WALEAVE PLAN & SURVEY CHARGES ER-ASN-2024-WL-10 | 03/24-25 | 18/04/2024 | 0 | EASTERN RAILWAY | 0.08 | 0 | 0 | 0
764 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Formal work order for Construction of 900 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I, PHE Dte. in the District of Paschim Bardhaman. | 1902/RCD-I | 09/06/2023 | 245 | M/S SANTANU PALIT & CO. | 182.7 | 54.81 | 100 | 70
765 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Formal Work Order for Additional supplying laying 280 mm & 225 mm dia HDPE pipe line for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | 2384/RCD-I | 07/08/2023 | 60 | SWATI CORPORATION | 124.64 | 97.3 | 78.07 | 80
766 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Acceptance cum work order for Distribution of pipe line from Alinagar OHR to Khattardihi Village via Minsa Das Para including Laying & Pushing by adopting trench less technology (e.g, Jack Pushing Method etc) & other allied work under Shyamla GP under Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. | 115/RCD-I | 08/01/2025 | 45 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 47.67 | 9.81 | 20.57 | 80
767 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Acceptance cum work order for Laying of different dia HDPE Pipe Line including concrete cutting, mending etc allied works towards Pathakpara (Sansad-XV) Block Andal & Pandabeswar of Ukhra under Additional works under Ukhra & its adjoining mouzas water supply scheme under RCFA Division-I PHE Dte. | 382/RCD I | 30/01/2023 | 15 | B.T.M CONCERN | 20.71 | 20.34 | 100 | 100
768 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Formal work order for Distribution Network & allied work at Ondal Block of RCFA Part-II (Zone-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1618/RCD I | 25/04/2023 | 372 | M/S UNIT CONSTRUCTION | 231.44 | 209.84 | 89.5 | 100
769 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 01 (One) location on Salanpur ¿ Khuidica road and supplying and laying MS pipe near culvert and gas line including ancillary work within command area of Zone-I (Dendua OHR Site) Part-C under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | 2225/RCD-I | 17/07/2023 | 259 | DAS & CHAKRABORTY | 15.47 | 12.05 | 83.13 | 100
770 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Formal Work order for construction of 900 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connection and cost of pipes, specials at Ondal Block (Zone-2) for Augmentation of RCFA Part-II Piped Water Supply Scheme including Soil Investigation and chlorine Room (4.50 x 3.50) under RCFA Division-I PHE Dte. In District Paschim Bardhaman. | 1846/RCD-I | 31/05/2023 | 366 | M/S CHANDI CHARAN ROY | 199.25 | 199.25 | 100 | 90
771 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Acceptance cum work order for Supplying, aligning & Laying of different dia HDPE pipe line and allied works for dedicated line to Chotkara village and Satta under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte. | 2989-RCD-I | 12/10/2023 | 15 | SHREE DURGA ENTERPRISE | 5.85 | 5.83 | 100 | 100
772 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman , SM/12223 | Augmentation | Acceptance cum work order for Additional works for Laying & pushing of 600mm dia RCC hume pipe (NP3) by adopting trench less technology (e.g Jack pushing method) , MS water carrier pipe and other allied works at different location (Node point:- 226-232, 289-292, 441-442, 69-76, 63-64, 256-272 ) of distribution network for Augmentation PWSS of RCFA Part-II (Zone-2) under RCFA Div-I, PHE Dte. | 2114/RCD-I | 27/08/2024 | 60 | SWATI CORPORATION | 35.82 | 0 | 0 | 100
773 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Urgent Basis rapairing of 50 sqmm x 4 core Al Armoured Damaged cable line street Light Providing of FHTC Pipe line near Andal More to Culvert (Bridge) under Dignala OHR dite under Andal W/s scheme under RCFA Division-I, PHE Dte. | SpotNit_Camp_02/AndalMore | 09/10/2023 | 10 | T R ENTERPRISE | 6.17 | 6.16 | 100 | 100
774 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Material Requisition To Resource Division | 2935/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
775 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Formal work order for Distribution Network including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-I) Pipe Water Supply Scheme under RCFA Division-I PHE Dte. | 1609/RCD I | 25/04/2023 | 90 | GITA CONSTRUCTION | 245.36 | 156.7 | 63.87 | 65
776 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Acceptance cum Work Order for Additional work for concrete cutting and concreting and distribution network for RCFA Part-II PWSS including FHTC and allied work under RCFA Division-I PHE Dte. Zone-12B (Segement 2) | 1009/RCD-I | 16/03/2024 | 15 | M/S SINGH & KONAR CONSTRUCTION | 31.75 | 0 | 0 | 0
777 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Acceptance cum work order for Construction of Guard Wall arrangement to project 450 mm dia the Rising Main at Jagrdih, Gopal area ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | 3283/RCD-I | 08/11/2023 | 15 | SIMA ENTERPRISE | 6.12 | 6.11 | 100 | 100
778 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Acceptance cum Work Order for Additional work for Shifting of 450 mm dia Rising main for ECL Railway siding near Dalmia OCP for extension of Bonjemari Colliery under Improvement of RCFA Part-II Zone-8 under RCFA Division-I PHE Dte. | 913/RCD-I | 15/03/2024 | 45 | MD AAMIR KHAN | 43.51 | 42.65 | 100 | 100
779 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Acceptance cum Work Order for Additional work for concrete cutting, restoration of road and allied works Dakshin Khanda area under RCFA Part-II W/S Scheme PHE Dte. [Zone-1A] | 917/RCD-I | 15/03/2024 | 30 | UNITED CONSTRUCTION | 17.04 | 16.94 | 100 | 100
780 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Acceptance cum Work Order for Additional work for Construction of pillar, MS pipe, specials, GI Pipe and allied works within Zone-I near Dendua under Augmentation PWSS of RCFA Part-II (Zone-I) under RCFA Division-I PHE Dte | 924/RCD-I | 15/03/2024 | 45 | SWATI CORPORATION | 25.03 | 24.35 | 100 | 100
781 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Acceptance cum Work Order for Additional work for Laying of Rising main including allied works of for extension of Bonjemary Colliery and ECL Railway siding under Improvement of RCFA Part-II Zone-8 under RCFA Division-I PHE Dte. | 914/RCD-I | 15/03/2024 | 45 | MD AAMIR KHAN | 38.46 | 38.42 | 100 | 100
782 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Acceptance cum Work Order for Additional work Distribution Network for Augmentation of RCFA Part-II (Zone-1) Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Part-C) | 929/RCD-I | 15/03/2024 | 45 | UNITED CONSTRUCTION | 32.03 | 24.47 | 100 | 100
783 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Formal Work Order for Construction of Sub-station, CWR and Pump House including toilet at Ethora under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2009/RCD-I | 26/06/2023 | 120 | D.S. ENTERPRISE | 122.25 | 43.74 | 35.78 | 40
784 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) 02 (Two) Nos. Near Dakshin Khanda Dharmaraj Tala and Khandra BPHC under Ondal Block under RCFA Division-I PHE Dte. | 3428/RCD-1 | 24/11/2023 | 15 | UNITED CONSTRUCTION | 18.39 | 17.65 | 100 | 100
785 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Acceptance cum Work Order for Additional supplying laying 90 mm dia, HDPE pipe line at Tentul Tala and Damalia Village including repairing different dia pipe line in different places in Tirat Mouza within Amritnagar Distribution Zone under Augmentation Part-II W/S Scheme under RCFA Division-I PHE Dte. | 937/RCD-I | 15/03/2024 | 15 | RUBY CONSTRUCTION | 6.88 | 6.85 | 100 | 100
786 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Acceptance cum Work Order for Dedicated pipe line beyond Patal Lakhi Mandir including FHTC connections and allied works for Augmentation PWSS of RCFA Part-II (Zone-I) under RCFA Division - I PHE Dte. | 916/RCD-I | 15/03/2024 | 30 | RAJAT BARAN CHAND | 17.3 | 17.12 | 100 | 100
787 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Acceptance cum work order for Additional work of laying of rising main at Surjanagar Head Work Site to High lift site and interconnection of collecting main to CWR in the river of Damodar under Augmentation of RCFA Part-II (Zone-I) PWSS under RCFA Division-I. PHE Dte. | 1014/RCD-I | 16/03/2024 | 45 | MAK CONSTRUCTION CO | 40.81 | 10.39 | 20.94 | 100
788 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman , SM/12224 | Augmentation | Acceptance cum Work Order for Additional work for laying pipeline and allied works from Kelejora Health Centre Crossing towards Barabani Village (ICML Road) withthin Zone XIII of Augmentation RCFA Part-II (Zone-I) PWSS under RCFA Division-I PHE Dte | 1011/RCD-I | 16/03/2024 | 168 | PINKI ENTERPRISE | 31.63 | 0 | 0 | 100
789 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Material Requisition To Resource Division | 2950/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
790 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-2 | 1100/RCD I | 23/03/2023 | 90 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 89.86 | 37.08 | 41.26 | 50
791 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-4 | 1104/RCD I | 23/03/2023 | 90 | M/S MONI TRADERS | 93.11 | 39.26 | 42.17 | 45
792 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-1 | 1098/ RCD-I | 23/03/2023 | 90 | MAK CONSTRUCTION CO. | 97.63 | 13.69 | 14.02 | 15
793 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Additional extra cutting Laterrate / sandstone of distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Div-I PHE Dte. (Part-E) | 2694/RCD-I | 27/09/2023 | 15 | TARA CONSTRUCTION | 0.94 | 0.84 | 100 | 100
794 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Acceptance cum work order for Additional supplying, Laying & Aligning of HDPE pipe, including providing FHTC retrofitting (left out portion) at Ratibati village under Augmentation PWSS of RCFA Part-II (Zone-7) under RCFA Division-I PHE Dte. | 622/RCD-I | 27/02/2024 | 15 | M/S KALYAN ENTERPRISE | 4.09 | 4.09 | 100 | 100
795 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Way leave permission of 250 mm dia waer pipeline (Jal Jeevan Mision) near LC Gate No. 9/Spl/T near Pandabeswar Station in Asansol Divison of Eastern Railway by RCFA Division-I PHE Dte | 415/24-25 | 05/12/2024 | 0 | EASTERN RAILWAY | 68.95 | 0 | 0 | 0
796 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Acceptance cum work order for distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-5 | 1106/RCD I | 23/03/2023 | 90 | B.T.M CONCERN | 94.6 | 60.02 | 63.45 | 65
797 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-3 (Sl No. 03) | 1102/RCD I | 23/03/2023 | 90 | RUBY CONSTRUCTION | 94.47 | 48.98 | 51.85 | 70
798 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Formal work order for Augmentation of RCFA part-II Piped Water Supply Scheme (Zone-7) with Construction of 450 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District Paschim Bardhaman. | 1900/RCD-I | 09/06/2023 | 365 | TARAPRASAD SARKAR | 150.41 | 21.85 | 14.53 | 25
799 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-7) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3354/RCDI | 23/12/2022 | 782 | MOYTEC | 0.49 | 0 | 0 | 100
800 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Acceptance Cum work order for Additional work for distribution network for Improvement of RCFA Part-II Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-B) | 358/RCD I | 30/01/2023 | 336 | UNITED CONSTRUCTION | 62.01 | 5.82 | 100 | 100
801 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. , SM/12027 | Augmentation | Formal work order for Supplying aligning and laying of different dia HDPE pipe line instead of DI pipe line and extension of HDPE pipe to adjacent village of Dendua for distribution system within command area of Zone-I (Dendua OHR Site) of Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1615/RCD I | 25/04/2023 | 90 | DAS & CHAKRABORTY | 115.96 | 107.47 | 100 | 100
802 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. , SM/12025 | Augmentation | Material Requisition To Resource Division | 2954/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
803 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. , SM/12025 | Augmentation | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-5) of Ondal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3359/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0.49 | 100 | 100
804 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. , SM/12025 | Augmentation | Acceptance cum work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in Salanpur at KM SLS/1136 and SLS/1138 on Bemjomary siding Railway line in Asansol Division under JJM under RCFA Division-I PHE Dte. | 2620/RCD-I | 13/09/2023 | 15 | MD AAMIR KHAN | 38.07 | 32.09 | 100 | 100
805 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. , SM/12025 | Augmentation | Acceptance cum work order for Construction of new boundary wall, Land developing and Pathway and other allied works at Nimsa mouza RCC over Head Site at Shyamla under Augmentation of RCFA Part-II (Zone-5) under RCFA Division-I PHE Dte. (Length 188 Mtr) | 2873/RCD-I | 06/10/2023 | 90 | M/S CHANDI CHARAN ROY | 21.97 | 13.21 | 100 | 100
806 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. , SM/12025 | Augmentation | Acceptance cum work order for Additional Supplying. Aligning and laying MS pipe (Node no. 45-47, 61-62, 5-16, 44-45) construction of Guard wall, concrete dismantling with re concreting and other allied works for Shyamla & Bhuri Mouzas, Block-Jamuria, Dist-Paschim Bardhaman under Augmentation of RCFA Part-II (Zone-5) under RCFA Division-I PHE Dte. (Part-C) | 2882/RCD-I | 06/10/2023 | 30 | TARA CONSTRUCTION | 13.8 | 10.84 | 100 | 100
807 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. , SM/12025 | Augmentation | Formal work order for distribution network including FHTC & allied work at Ondal Block of RCFA Part-II(zone -5) pipe water supply under RCFA Div-I, PHE Dte. | 954/RCDI | 20/03/2023 | 926 | M/S PIONEER CONSTRUCTION | 475.88 | 209.15 | 43.95 | 80
808 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. , SM/12025 | Augmentation | Formal work order for Supplying laying different HDPE Pipe line for Improvement of RCFA Part-I Water Supply Scheme within Command area of Zone-VIII with LDS work under RCFA Division-I PHE Dte. | 1614/RCD I | 25/04/2023 | 90 | SWATI CORPORATION | 128.33 | 22.19 | 17.29 | 80
809 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. , SM/12025 | Augmentation | Formal work order for Construction of 450 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connection and cost of pipes, specials at Ondal Block (Zone-5) for Augmentation of RCFA Part-II Piped Water Supply Scheme including Soil Investigation and chlorine Room (4.50 x 3.50 m) under RCFA Division-I PHE Dte. In District Paschim Bardhaman. | 1608/RCD I | 25/04/2023 | 366 | HIRANMAY GHOSH | 137.5 | 137.5 | 100 | 50
810 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. , SM/12025 | Augmentation | Acceptance cum work order for Allied work for bridge with foundation at Chalbalpur under Amritnagar Zone-II for Augmentation of RCFA Part-II (Zone-5) under RCFA Division-I PHE Dte. | 2864/RCD-I | 06/10/2023 | 90 | MRITYUNJOY MUKHERJEE & CO. | 87.54 | 87.26 | 100 | 100
811 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. , SM/12025 | Augmentation | Acceptance cum work order for Laying and pushing MS pipe through RCC pipe in different dia and different including cutting welding for barricading jointing for Augmentation of RCFA Part-II (Zone-5) PWSS under Division-I PHE Dte. | 2881/RCD-I | 06/10/2023 | 178 | MRITYUNJOY MUKHERJEE & CO. | 16.98 | 0 | 0 | 100
812 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for BAHADURPUR Water Supply Scheme for Implementation of JJM at Jamuria Block under RCFA DIVISION-I, P.H.E. Dte. | 2970/RCD-I | 11/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100 | 100
813 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for HARIPUR Water Supply Scheme for Implementation of JJM at Pandabeswar Block under RCFA DIVISION-I, P.H.E. Dte. | 2971/RCD-I | 11/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100 | 100
814 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Material Requisition To Resource Division | 2933/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
815 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-68 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | 381/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0 | 0
816 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-72 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | 382/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0 | 0
817 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-69 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | 380/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0 | 0
818 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-71 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | 378/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.11 | 0 | 0 | 0
819 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-70 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | 379/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.11 | 0 | 0 | 0
820 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-67 for Nimcha - Kalipahari under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | 383/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.14 | 0 | 0 | 0
821 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum Work Order for Replacing existing UPVC pipe line with HDPE at Marickkota and different village under Salanpur Block under RCFA Part-I PWSS under RCFA Division-I PHE Dte | 509/RCD-I | 12/02/2024 | 45 | SUKHENDU MAJUMDAR | 6.37 | 0 | 0 | 0
822 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Additional providing FHTC of retrofitting at kumardiha Village (left out portion) of Kumardiha Mouza, GP-Ratibati Block Raniganj of Ratibati Water supply scheme under RCFA Division-I PHE Dte. | 1023/RCD-I | 16/03/2024 | 30 | SAYAN CONSTRUCTION | 5.65 | 0 | 0 | 0
823 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in between KM 227/27-29 and between Salanpur (SLS) Rupnarayanpur (RNPR) in Asansol Division under JJM under RCFA Division-I PHE Dte | 2621/RCD-I | 13/09/2023 | 15 | MAK CONSTRUCTION CO. | 62.81 | 62.23 | 100 | 100
824 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for 2nos of Emergency repairing work of 450 mm dia rising main at Upper Jamdoba and Nichu Para under RCFA Part-II W7S scheme under RCFA Div-I, PHE Dte. | 2890/RCD-I | 06/10/2023 | 15 | KHEPI MAA TRADERS | 2.29 | 2.29 | 49.94 | 100
825 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in Salanpur in between KM 227/31-33 and Salanpur (SLS) ¿ Rupnarayanpur (RNPR) Station in Asansol Division of JJM under Augmentation of RCFA Part-II (Zone-3) under RCFA Division-I PHE Dte. | 2870/RCD-I | 06/10/2023 | 30 | SWATI CORPORATION | 67.3 | 60.1 | 100 | 100
826 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Emergency work for Withdrawing and Relaying of collecting main and other allied works at Damalia H/W under RCFA part II at Damodar river under Amritnagar water supply scheme under RCFA Division -I PHE Dte. | 3368/RCD-1 | 21/11/2023 | 15 | M/S KALYAN ENTERPRISE | 2.78 | 2.78 | 100 | 100
827 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Laying of 90mm dia HDPE pipe and allied works at Bauri para of Khandra area of Block-Ondal under RCFA Part-II water supply scheme under RCFA Div-I, PHE Dte. | 2893/RCD-I | 06/10/2023 | 15 | KHEPI MAA TRADERS | 2.33 | 2.33 | 100 | 100
828 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Emergency repairing of damaged collecting main in river Damodar and allied works at Surjanagar H/W site of Surjanagar W/S Scheme under RCFA Division -I PHE Dte. | 3383/RCD-I | 21/11/2023 | 15 | MD. JAWED KHAN | 4.27 | 4.27 | 49.97 | 100
829 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Supplying aligning, Laying of PVC pipe, HDPE pipe sluice valve, Sluice valve chamber and other allied works at Oriapara, Chapui Vaskadaora 7 nos pit to Rangadanga Talbagan under Ratibati Gram Panchayet under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | 3419/RCD-1 | 24/11/2023 | 30 | M/S KALYAN ENTERPRISE | 7.78 | 7.78 | 100 | 100
830 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Withdrawing, supplying, aligning Relaying of 80 mm dia PVC pipe line, repairing of street stand post and other allied works at Goylapara under Tirat Gram Panchyat under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | 3420/RCD-1 | 24/11/2023 | 30 | M/S KALYAN ENTERPRISE | 6.24 | 0 | 0 | 100
831 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Emergent Sinking of one no.200 x 165 mm Rig box tubewell at ADM Bunglow, Asansol, Paschim Bardhaman, Under R.C.F.A Div-I, PHE Dte. | SpotNITCamp-02/ADMBunglow | 09/01/2024 | 7 | M/S CHANDI CHARAN ROY | 7.5 | 7.44 | 100 | 100
832 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Continuation work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Improvement of Collector well by infiltration gallery at Kalajharia Part-II W/S Scheme | 3523-B/RCD-I | 04/12/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100 | 100
833 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum Work Order for Laying MS pipe over bridge / culvert including adopting trench less technology (e.g. Jack Pushing Method etc) at 4 (Four) nos location within laying distribution system of Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | 483/RCD-I | 12/02/2024 | 45 | TARAPRASAD SARKAR | 25.18 | 24.97 | 100 | 100
834 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Continuation of work order for Conducting route survey, design rising main network and preparation & submission of source Augmentation DPR for Ukhra OHR of RCFA (Part-I) PWSS. | 3523-A/RCD-I | 04/12/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100 | 100
835 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Continuation work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Madanpur OHR of RCFA (Part-I) PWSS under RCFA DIVISION-I , P.H.E Dte. | 3523-C/RCD-I | 04/12/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100 | 100
836 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Formal work order for distribution network for RCFA Part-II Piped water Supply Scheme including FHTC & allied works under RCFA Div-I, PHE Dte. (Zone-3)(Ukhra) | 1002/RCDI | 22/03/2023 | 120 | SINGHA ROY & CO. | 392.43 | 361.61 | 92.15 | 86
837 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Parasia Water Supply Scheme for Implementation of JJM at Jamuria Block under RCFA DIVISION-I, P.H.E. Dte. | 2969/RCD-I | 11/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100 | 100
838 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Supplying, Aligning, laying HDPE pipe & Supply Sluice Valve & construction of sluice valve chamber including providing FHTC and other allied works at Ratibati village Ratibati W/S Scheme under RCFA Division-I PHE Dte. | 2874/RCD-1 | 06/10/2023 | 30 | NIYATI CONSTRUCTION | 7.87 | 7.86 | 100 | 100
839 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Panchgachia & Majiara Water Supply Scheme for Implementation of JJM at Barabani Block under RCFA DIVISION-I, P.H.E. Dte. | 2974/RCD-I | 11/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100 | 100
840 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for RATIBATI Water Supply Scheme for Implementation of JJM at Jamuria Block under RCFA DIVISION-I, P.H.E. Dte. | 2972/RCD-I | 11/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100 | 100
841 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for BAHULA Water Supply Scheme for Implementation of JJM at Pandabeswar Block under RCFA DIVISION-I, P.H.E. Dte. | 2973/RCD-I | 11/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100 | 100
842 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum Work Order for Additional work for Road Crossing by adopting trenchless technology at 3 (Three) nos locations near ECL stack yard including restoration of road from Dabor more to Amdanga more in connection to rising main Part-A under Improvement of RCFA Part-I in Connection of Rising Main (Part-A) under RCFA Division-I PHE Dte | 482/RCD-I | 12/02/2024 | 45 | MD AAMIR KHAN | 44.01 | 43.95 | 100 | 100
843 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum Work Order for Additional work of 50 cum/hr capacity I.E. Plant at Churulia and Madanpur Head Works Site Augmentation of RCFA Part-II (Zone-3) under RCFA Division-I PHE Dte. | 475/RCD-I | 12/02/2024 | 120 | TARAPRASAD SARKAR | 31.29 | 23.47 | 75 | 100
844 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum Work Order for Additional works of dismantling & concrete works, laterite and sand filling at distribution system network for RCFA Part-II (Zone-3) PWSS including FHTC & allied works under RCFA Division-I PHE Dte. | 493/RCD-I | 12/02/2024 | 35 | SINGHA ROY & CO. | 77.52 | 74.45 | 100 | 100
845 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Additional Supplying Aligning & laying HDPE pipe supplying sluice valve and others allied works of different places under Nutun Egara under Narayankuri W/S Scheme under RCFA Division-I PHE Dte. | 496/RCD-1 | 12/02/2024 | 45 | DIP CONSTRUCTION | 8.67 | 8.67 | 100 | 100
846 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum Work Order for Additional works of sinking of 3 (Three) nos. 200 mm dia river bed tube well including collecting main in the river Damodar at Gourbazar H/W Site for Hourbazar Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 510/RCD-I | 12/02/2024 | 25 | R B ENTERPRISE | 12.96 | 12.52 | 100 | 100
847 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum Work Order for Additional repairing and maintenance work of RCC Elevated reservoir, Boundary Wall and other allied works at Mangalpur of 25000 gallon capacity under Augmentation of RCFA Part-II (Zone-3) Water Supply Scheme under RCFA Division-I PHE Dte | 938/RCD-I | 15/03/2024 | 15 | M/S SUBHRADEEP | 16.89 | 16.53 | 100 | 100
848 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Acceptance cum work order for Additional work of HDPE pipeline and MS work and interconnection of Raniganj Chati,Baliapur and adjacent area of Zone-IX for Augmentation of PWSS of RCFA Part-II (Zone-3) under RCFA Div-I PHE Dte. | 126/RCD-I | 08/01/2025 | 30 | DAWN CONSTRUCTION | 16.98 | 0 | 0 | 100
849 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE , SM/12215 | Augmentation | Balance work of Laying of 200 mm dia HDPE pipe line and road restoration at Raghunathchak, Raniganj Chati, Baliapur and adjacent area within Zone-IX of Augmentation PWSS of RCFA Part-II (Zone-3) under RCFA Division-I PHE Dte | Camp_02_Raghunathchak_AE- | 09/12/2024 | 15 | DAWN CONSTRUCTION | 13.12 | 0 | 0 | 100
850 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16903 | Augmentation | Quotation money for new electric connection for Augmentation of ground water based water supply scheme for Banagarm part under Durgapur W/s Division, PHE Dte,Block -Kanksa,Dist-Paschim Bardhaman. | BP-2023-24-25 | 18/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.87 | 0 | 0 | 0
851 | PASCHIM BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16903 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Banagram Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | 1309/CMD | 22/03/2023 | 30 | K.S.P. ENTERPRISE | 9.99 | 8.45 | 84.61 | 70
852 | PASCHIM BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16903 | Augmentation | Supply & Delivery of Pump Motor Set at TW No: 01 of Banagram water supply scheme under CMD, PHE, Dte. | 111/DIC/BMSD(D) | 04/10/2023 | 15 | K.S.P. ENTERPRISE | 0.52 | 0 | 0 | 100
853 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16903 | Augmentation | Balance work for construction of Pump house /Chlorine room sinking of 150 X80X120 mtr depth TW ,supplying laying of HDPE distribution pipe line and providing FHTC at Banagram mouza of Augmentation of Banagram piped W/s Scheme under DWSD,PHE Dte.(SM/16903) | 1606/DWSD | 21/08/2023 | 865 | BISHAL ENTERPRISE | 47.01 | 0 | 0 | 100
854 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. , SM/09065 | Retrofitting | Acceptance cum Work Order for Laying 200 mm dia MS water pipe line with 600 mm dia MS casing pipe for railway crossing in between Jamuria (JMA) and Barabani (BBI) at KM 25/2-3 in Asansol Division under JJM of Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block under RCFA Division-I PHE Dte. | 931/RCD-I | 15/03/2024 | 30 | SOMNATH SAMANTA | 23.15 | 22.61 | 100 | 100
855 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. , SM/09065 | Retrofitting | acceptance cum work order Repairing of 450 mm dia DI pipe line at Baidyanathpur, Barachak, Jagaridih area of ASTA rising main of ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | 1282/RCD-I | 27/03/2023 | 15 | SIMA ENTERPRISE | 2.66 | 2.66 | 100 | 0
856 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. , SM/09065 | Retrofitting | Continuation work order for Hiring of SUV (A.C) (Non Airconditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. for the Office Use of the Deputy Superintending Engineer, RCFA W/S Circle, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.09.2024 to 28.02.2025) (Sl No. 02) | 2164_RCD-I | 30/08/2024 | 182 | SHYAMAL MAJI | 0.9 | 0.33 | 44.08 | 33
857 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. , SM/09065 | Retrofitting | Acceptance cum Providing FHTC of retrofitting at Kumardihi village (left out portion) of kumardihi Mouza, GP Ratibati, Block-Raniganj of Ratibati Water Supply Sceme under RCFA Division -I PHE Dte. | 806/RCD-I | 06/03/2023 | 20 | M/S MONDAL CONSTRUCTION | 13.78 | 12.41 | 100 | 100
858 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. , SM/09065 | Retrofitting | Acceptance cum work order for Additional work for Supply and laying MS water carrier pipe and allied works of Improvement of RCFA Part-I in connection of Rising Main (Part-A) under RCFA Division-I PHE Dte. | 2209/RCD-I | 17/07/2023 | 30 | MD AAMIR KHAN | 37.26 | 36.13 | 100 | 100
859 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18886 | Augmentation | Acceptance cum formal order for the work of Emergency repairing and etc allied works at different places within Basudha area,Domra area ,Tilakchandrapur area ,Krikrishnapur and Roopganj area under DWSD,PHE Dte | 1562/A/DWSD | 20/09/2023 | 15 | GHOSH ENTERPRISE | 3.29 | 3.28 | 100 | 100
860 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18886 | Augmentation | Quotation as per WBSEDCL Procedure-A (2010) ON Turn key/ Full deposit basis for the site of Trilockchandrapur Pump House no-4, Trilockchandrapur under Kanksa Block under Panagarh CCC supply office. | BP-2024-25-12 | 17/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.48 | 0 | 0 | 0
861 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18886 | Augmentation | Quotation Payment for Trilockchandrapur T/W No-3, under Kanksa Block, Paschim Bardhaman as per WBSEDCL Procedure-A(2010) on Turn-Key/Full Deposit Basis. | BP-2024-25-11 | 06/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.79 | 0 | 0 | 0
862 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18886 | Augmentation | Formal order for the work of Sinking of 2(Two) Nos TW,FHTC,laying Rising main and laying distribution system (LDS) ,construction of boundary wall ,Pump House and restoration of road another allied works for Augmentation of ground water based W/s Scheme for Trilakchandrapur under DWSD,Block-Kanksa,Dist-Paschim Bardhhaman | 1826/DWSD | 05/12/2023 | 728 | SHWET BARANI | 243.78 | 111.4 | 45.7 | 100
863 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18886 | Augmentation | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND YARD LIGHTING INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 & TUBE WELL NO-4 AT AUGMENTATION OF TILAKCHANDRAPUR PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | 1820/AMD | 29/10/2024 | 115 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 26.65 | 0 | 0 | 93
864 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18886 | Augmentation | Separate connection for Hazrabera under Prayagpur OHR Kanksa Zone-II (Part-B) under Augmentation of Tilakchandrapur W/S Scheme under RCFA Division-I PHE Dte. | 707/RCD-I | 29/02/2024 | 15 | MALLICK CONSTRUCTION | 0.91 | 0.89 | 100 | 100
865 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of SARPI PWSS under DURGAPUR-FARIDPUR Development Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -06) | 924/DWSD | 23/06/2023 | 7 | CARTO | 0.78 | 0 | 0 | 0
866 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Acceptance cum formal order for the work of Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission for Pratabpur Mouza (JL-48) under retrofitting of Jemua Piped Water Supply Scheme under Durgapur Faridpur Block under DWSD PHE Dte.(Sl-04) | 1394/DWSD | 16/08/2023 | 10 | GHOSH & ROY ENTERPRISE | 0.96 | 0.96 | 100 | 100
867 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Material Requisition To Resource Division | 1833/DWSD | 06/12/2023 | 0 | Resource Division | 236.81 | 0 | 0 | 0
868 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Material Requisition To Resource Division | 1665/DWSD | 12/10/2023 | 0 | Resource Division | 922.9 | 0 | 0 | 0
869 | PASCHIM BARDHAMAN | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Quotation Money for New Connection under Sharpi Water Supply Scheme. | BP-2023-24-44 | 03/11/2023 | 0 | WEST BENGAL ENGINEERING CO. | 3.65 | 0 | 0 | 0
870 | PASCHIM BARDHAMAN | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Quotation Money for new connection under Sharpi Water Supply Scheme. | BP-2023-24-45 | 03/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.03 | 0 | 0 | 0
871 | PASCHIM BARDHAMAN | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Supply,delivery & installation of Electro-Mechanical equipment and other allied works at New Bhaburia Head Works Site and Madhaiganj Boosting Station under Sharpi Piped Water Supply Scheme under Asansol Mechanical Division,P.H.E Dte. Block-Durgapur-Faridpur, District-Paschim Bardhaman. | 1402/AMD | 19/07/2023 | 366 | MACHINE SUPPLIERS SYNDICATE(P) LTD. | 338.11 | 202.91 | 60.01 | 60
872 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Sinking of 2Nos 200 mm dia River bed tube well with collecting main with manifold in river "AJOY" at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-A) | 1095/DWSD | 14/07/2023 | 30 | CHANDAN HAZRA | 18.32 | 14.9 | 81.32 | 82
873 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Supplying,laying and alingining of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman.(Part-F). | 1099/DWSD | 14/07/2023 | 30 | M/S BADAL GHOSH | 99.72 | 65.25 | 65.43 | 100
874 | PASCHIM BARDHAMAN | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at Madhaiganj Boosting Station under Sharpi & adjoining mouzs Piped Water Supply Scheme. | 2099/AMD | 12/12/2024 | 30 | M/S SWAPAN BANERJEE | 19.61 | 0 | 0 | 0
875 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Continuation order for the work of additional number of FHTC in connection with JJM Ichhapur(Mouza-91) with extension of branch pipe line of command area of Gourbazar-Ichhapur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte | 180/DWSD | 11/02/2022 | 15 | SHWET BARANI | 4.12 | 0 | 0 | 100
876 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Sinking of 3 Nos 200 mm dia River bed tube well with collecting main with manifold in river "AJOY" at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-A) | 1105/DWSD | 14/07/2023 | 35 | BISHAL ENTERPRISE | 27.47 | 23.76 | 100 | 90
877 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Construction of 100 M3 capacity Clear Water Reservoir (CWR) at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | 1094/DWSD | 14/07/2023 | 60 | KALPANA BUILDERS | 32.52 | 32.1 | 100 | 100
878 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Sinking of 3 Nos 200 mm dia River bed tube well with collecting main with manifold in river "AJOY" at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-B) | 1103/DWSD | 14/07/2023 | 35 | MAK CONSTRUCTION CO. | 27.48 | 27.44 | 100 | 100
879 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Sinking of 2Nos 200 mm dia River bed tube well with collecting main with manifold in river AJOY at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-C) | 1104/DWSD | 14/07/2023 | 30 | MAITO MAA ENTERPRISE | 18.32 | 10.96 | 100 | 100
880 | PASCHIM BARDHAMAN | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Load Enhancement for Natundanga Zone under Sharpi PWSS | BP-2024-25-59 | 26/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 21.33 | 0 | 0 | 0
881 | PASCHIM BARDHAMAN | RCFA Division -I | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Restoration of damaged road surface due to the cause of earthwork in connection with placement of under ground water pipe line in stretches at Pandabeswar-Natundanga Road from Chainage 0.000 km to 2.00 Km 2.500 to 3.000 Km 5.500 to 5.800 km, 7.900 km to 8.141 km in the district of Paschim Bardhaman under Asansol Division PWD | 629/23-24 | 15/03/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 33.26 | 0 | 0 | 0
882 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Supplying, laying and aligning of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-E). | 1101/DWSD | 14/07/2023 | 658 | KALPANA BUILDERS | 99.89 | 0 | 0 | 65
883 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Supplying, laying and aligning of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-G). | 1102/DWSD | 14/07/2023 | 840 | HIRANMAY GHOSH | 97.54 | 43.97 | 45.08 | 80
884 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Supplying,laying and alingining of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman.(Part-C). | 1096/DWSD | 14/07/2023 | 749 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 93.43 | 23.12 | 24.75 | 70
885 | PASCHIM BARDHAMAN | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Supply delivery and installation of submersible pumping machinery in the newly sunk ground bored tubewell, lighting arrangement at new Bhaburia headworks site and corresponding sharpi O.H.R under RBTW water based water supply scheme for sharpi and adjoining areas under Asansol Mechanical Division, PHE Dte. | 943/AMD | 16/05/2025 | 30 | M/S JIT ENTERPRISE | 14.96 | 0 | 0 | 0
886 | PASCHIM BARDHAMAN | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. , SM/18417 | New | Providing & Installation of Centrifugal Pumping Machineries(No-04) at Amdahi Boosting Station under Augmentation of Sharpi Water Supply Scheme. | 1110/AMD | 16/06/2025 | 30 | WEST BENGAL ENGINEERING CO. | 32.17 | 0 | 0 | 0
887 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Supply and delivery of GI pipe including loading, unloading and carriage to Searsole Store under RCFA Part-II PWSS under RCFA Division-I PHE Dte | 3044/RCD-I | 17/10/2023 | 20 | INDIA PIPE FITTING CO | 94.09 | 93.19 | 100 | 100
888 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Material Requisition To Resource Division | 2980/RCD-I | 12/10/2023 | 0 | Resource Division | 5756.61 | 0 | 0 | 0
889 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Material Requisition To Resource Division | 3662/RCD-I | 28/12/2023 | 0 | Resource Division | 35.15 | 0 | 0 | 0
890 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Execution of agreement with Damodar Valley Corporation for drawl of 15.757 (Fifteen point seven five seven) MGD raw water for RCFA Part-II piped water supply scheme under RCFA Public Health Engineering Directorate, Asansol from Maithon Reservoir | 371/23-24 | 21/11/2023 | 0 | DAMODAR VALLEY CORPORATION | 13.08 | 0 | 0 | 0
891 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-61 for Baktarnagar - Raniganj under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | 409/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 9.91 | 0 | 0 | 0
892 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-55 for Asansol East Cabin - Asansol East Hump under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | 404/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 149.35 | 0 | 0 | 0
893 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-54 for Chinchuria - Sitarampur under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | 406/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 4.78 | 0 | 0 | 0
894 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-59 for Pandabeswar - Ukhra under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | 408/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 8.26 | 0 | 0 | 0
895 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-53 for Salanpur - Sitarampur link Cabin under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | 403/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 15.82 | 0 | 0 | 0
896 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-52 for Damagoria under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | 407/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 15.2 | 0 | 0 | 0
897 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-58 for Sonachara - Topsi under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | 412/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 10.27 | 0 | 0 | 0
898 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-60 for Topsi - Sripur under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | 411/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 4.67 | 0 | 0 | 0
899 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-57 for Kalipahari - Nimcha under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | 410/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 5.28 | 0 | 0 | 0
900 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-56 for Damodar under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | 405/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 19.69 | 0 | 0 | 0
901 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Providing & Installation of Electrical Equipments For Sub-Station at Intake and Water Treatment Plant under Augmentation of RCFA Part-II Piped Water Supply Scheme. | 1687/AMD | 07/09/2023 | 366 | WEST BENGAL ENGINEERING CO. | 1704.7 | 1206.59 | 70.78 | 70
902 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum Work Order for Laying & Pushing by adopting trench less technology (e.g. jack Pushing Method etc) additional for Distribution Network of Augmentation of RCFA Part-II PWSS within command area of Vol-I (Segment-V) under RCFA Division-I PHE Dte. | 1581/RCD-I | 27/06/2024 | 30 | DIP CONSTRUCTION | 37.13 | 0 | 0 | 0
903 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Supplying E.R.M.S. Black pipe of approved quality including carring, stacking at works for crossing of 12 nos culvert/cannel of by the side of PWD road under Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | 3426/RCD-1 | 24/11/2023 | 20 | SWATI CORPORATION | 7.09 | 4.21 | 100 | 100
904 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Bolkunda and surrounding villages within Filberia-Bolkunda Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte | 3449/RCD-I | 24/11/2023 | 15 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 3.52 | 3.5 | 100 | 100
905 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum Work Order for Additional work for concrete dismantling restoration of concrete for 350 mm D.I. and 315 mm HDPE pipe line repair damaged PVC and GI pipe line and other allied works for Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I within command area of Zone-VIII under RCFA Division-I PHE Dte | 490/RCD-I | 12/02/2024 | 30 | TARA CONSTRUCTION | 11.01 | 9.48 | 100 | 100
906 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Supply & Erection of 33 KV, S/C, Electrical Equipments & accessories related to the diversion of 33KV transmission line at Kalyaneswari W.T.P under Asansol Mechanical Division. P.H.E. Dte. | 1087/AMD | 25/07/2024 | 160 | OHMS ELECTRICAL AND CO | 23.95 | 16.82 | 70.23 | 80
907 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Supply & erection of Govt. Land Boards ( 102 nos) having M.S. Channel/Angle posts& 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Jamuria Block for Augmentation of RCFA Part II Piped Water Supply Scheme Volume-I under RCFA Division-I PHE Dte. | Camp-02-Jamuria-AE/2024-2 | 20/08/2024 | 15 | UNITED CONSTRUCTION | 20.45 | 19.85 | 100 | 100
908 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum Work Order for Construction of CWR 150 cum at Shyamla for Kendra Khottamdihi of Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | 1587/RCD-I | 27/06/2024 | 90 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 28.76 | 21.95 | 100 | 90
909 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum Work Order for Balance work of Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block including FHTC & allied work Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. (Part-A) | 1588/RCD-I | 27/06/2024 | 45 | SIMA ENTERPRISE | 27.22 | 26.18 | 100 | 100
910 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Protecting and regulating apparatus for distribution system and rising main under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte | 2232/RCD-i | 10/09/2024 | 30 | MAKALI ENGINEERING CORPORATION | 94.06 | 93.98 | 100 | 100
911 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Laying and Pushing by adopting trench less technology(e.g.Jack Pushing Method etc), additional for Rising main and culvert crossing near Semlya Head Work Site under Jamuria Block under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division I PHE Dte. | 1010/RCD-I | 16/03/2024 | 15 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 12.72 | 12.23 | 100 | 100
912 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum Work Order for Construction of Stack Yard (including filling of low land), Jungle cutting, Surface dressing, Dismantling related to RCFA Part-II WTP Site at Kalyaneswari Town ship under RCFA Division-I PHE Dte. Improvement of RCFA Part-II Vol-I | 1582/RCD-I | 27/06/2024 | 45 | UNITED CONSTRUCTION | 18.67 | 18.18 | 100 | 100
913 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Additional laying of different dia HDPE pipe line at Madhudanga village and adjacent area within Jamuria Block under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | 1524/RCD-I | 14/06/2024 | 45 | MD AAMIR KHAN | 20.3 | 17.53 | 100 | 100
914 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Supply & erection on Information Boards (51 nos) having M.S. Channel/Angle posts & 1.5 mm thick M.S Synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Salanpur, Barabani & Jamuria Block for Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | 2231/RCD-¦ | 10/09/2024 | 15 | SHARMA ENGINEERING WORKS | 9.9 | 9.86 | 100 | 100
915 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum Work Order for Providing of different dia water regulating apparatus (cast iron and Ductile iron) of Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | 1938/RCD-I | 07/08/2024 | 15 | MAKALI ENGINEERING CORPORATION | 96.16 | 96.16 | 100 | 100
916 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Material Requisition To Resource Division | 106/RCD-I | 10/01/2024 | 0 | Resource Division | 308 | 0 | 0 | 0
917 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Restoration work of damaged road flank caused by PHE for laying water pipe line at kajora Haripur from 0.00 km to 10.74 km at Ukhra Madhaigand road rom 0.00 to 12.13 km at Galigram - Kutruki - Chandipur road between 9 km to 12 km , Raghunathpur - Kantaberia road at 19th km near kantabaria Raghunathpur Kantaberia road from 0.00 kmp to 3.50 near Jamdoba village under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | 544/23-24 | 08/02/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, PW (ROADS) DIRECTT. | 32.25 | 0 | 0 | 0
918 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Damage of "PMGSY" and "Pathashree" Roads due to laying of PHED pipeline and tentative estimates for restoration | 549/23-24 | 12/02/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 46.78 | 0 | 0 | 0
919 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Permission for laying of water pipeline along NH-02 from Duburdih (km. 441+780) to Kalla More (Km. 462+080) and 1 no. crossing acros NH-2 in the state of West Bengal unde RCFA Divn-I PHE Dte - Submission of Bank Guarantee reg. | 268/24-25 | 05/09/2024 | 0 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 104.25 | 0 | 0 | 0
920 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Restoreation and repairing work from Ch. 13415 to 14300 of Neamatpur - Rupnarayanpur Road (FR-10) under Asansol Division, PWD for laying of distribution system of Zone - VII under JJM work in the district of Paschim Bardhaman during the year 2024-2025 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte | 168/24-25 | 23/07/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 14.85 | 0 | 0 | 0
921 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Bulk power supply at 33kv to premises PHE DTE ,kalyaneswari WTP ,JL-01,plot-313,KALYANESWARI wtp area,paschim burdwan-713369 for an ultimate contract demand 2246kva | BP-2024-25-19 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 103.61 | 0 | 0 | 0
922 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Permission for laying of water pipeline along NH-02 from Duburdih (km 441.780) to Kalla More (k. 462.080) and 1 no crossing across NH-2 in th state of West Bengal under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. RCFA Division-I, PHE Dte. | 545/23-24 | 08/02/2024 | 0 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 169.62 | 0 | 0 | 0
923 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Construction of Boundary wall including land development, approach road (Length-70 mtr) and drain (Length-160 mtr) at Bansketia OHR site of Augmentation of RCFA Part II Piped Water Supply Scheme Volume-I under Salanpur Block under RCFA Division-I PHE Dte. | 2663/RCD-I | 26/09/2023 | 30 | AMAR CONSTRUCTION | 39.04 | 23.76 | 60.85 | 100
924 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Providing 33KV, 25KA, 1250A, 2 Panel VCB & 33KV Metering Arrangement & Relay Panel for Substation at Water Treatment Plant under Augmentation of RCFA Par-Il Piped W/S Scheme. | 148/AMD | 05/02/2025 | 30 | WEST BENGAL ENGINEERING CO. | 44.4 | 0 | 0 | 0
925 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Different Electro-mechanical works in connection with the execution of Electrical Sub-station and other works at Intake under Augmentation of RCFA Part-II Piped Water Supply Scheme. | 617/AMD | 13/03/2025 | 90 | WEST BENGAL ENGINEERING CO. | 119.63 | 0 | 0 | 0
926 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Balanced work at Shyamsundarpur Zone-13 of Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte | 2802_RCD-1 | 29/11/2024 | 244 | MD AAMIR KHAN | 95.62 | 0 | 0 | 100
927 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Laying 200 mm dia MS water pipe line with 600 mm dia MS casing pipe for Railway crossing between Chinchuria (CCR) and Sitarampur (STN) at KM 34/8-9 (Sitarampur end of LC No. 12/A/E) in Asansol Division under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | 2622/RCD-I | 13/09/2023 | 15 | M/S MONDAL ENTERPRISE | 31.21 | 29.86 | 100 | 100
928 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Additional Supplying E.R.M.S Black pipe of approved quality including carring, stacking at works site and other allied works for Improvement RCFA Part-I Zone VII (Part E) water Supply scheme within command area of Zone VII under RCFA Div-I PHE Dte. | 3444/RCD-I | 24/11/2023 | 557 | TARA CONSTRUCTION | 2.64 | 0 | 0 | 100
929 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Additional work for Supply and laying of MS water Carrier pipe of dia 600 mm, 450 mm, 350 mm, 250 mm and allied works in connection of Rising Main (Part-A) to Improvement of RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | 3417/RCD-1 | 24/11/2023 | 30 | MD AAMIR KHAN | 70.38 | 68.02 | 100 | 100
930 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Interconnection at Kalyaneswari WTP Site, Banskatia OHR and bypass line, Kadvita More branch line, Dendua OHR, Rupnarayanpur OHR and construction of valve chamber etc under RCFA Part-II Vol-I PWSS under RCFA Division-I PHE Dte. | 118/RCD-I | 08/01/2025 | 45 | MAK CONSTRUCTION CO | 46.44 | 0 | 0 | 100
931 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum Work Order for Additional work for providing FHTC within command area of Zone-I (Dendua OHR Site) Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte.(Part-B) | 1742/RCD-I | 18/07/2024 | 355 | TARA CONSTRUCTION | 66.88 | 26.1 | 45.73 | 100
932 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Protecting apparatus of collecting main including other allied works under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | 1517/RCD-I | 14/06/2024 | 15 | INDIA PIPE FITTING CO | 96.97 | 96.86 | 100 | 100
933 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Supply & erection of Govt. Land Boards (51 nos) having M.S. Channel/Angle posts& 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Raniganj, Andal, Pandabeswar, Kanksa & Durgapur-Faridpur Block of Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Camp-02-Raniganj/AE/2024- | 20/08/2024 | 15 | MUKHERJEE TRADERS | 9.91 | 0 | 0 | 100
934 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum Work Order for Additional work for laying pipe line and allied works from Kelejora Health Center towards Domohani Bazar within Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | 1589/RCD-I | 27/06/2024 | 45 | R B ENTERPRISE | 34.16 | 32.87 | 100 | 100
935 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Formal work order for Distribution Network for Laying distribution system including FHTC for 5 (Two) nos uncoverd village viz. Namokeshia and Jorbari within Salanpur Block under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | 807/RCD-I | 14/03/2024 | 505 | UMA ENTERPRISE | 107.86 | 59.72 | 70.21 | 30
936 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum Work Order for Additional work for Shifting of Rising main for extension of Bonjemary Colliery and ECL Railway siding near Dalmia OCP under ECL Deposite Scheme under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | 1013/RCD-I | 16/03/2024 | 15 | R B ENTERPRISE | 30.24 | 30.2 | 100 | 100
937 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for 450 mm dia pipe crossing by adopting trenchless technologies (e.g. Jack Pushing Method etc) Ch. 222.05 near Damlia OCP for IOCL crossing of rising main (Part-A) under RCFA Part-II Vol-I PWSS under RCFA Division-I PHE Dte. | 117/RCD-I | 08/01/2025 | 236 | MD AAMIR KHAN | 29.48 | 0 | 0 | 100
938 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Laying pipe line for Chapui, Kumardihi village under Ratibati Gram Panchayet, Raniganj Block under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-I under RCFA Division-I PHE Dte. | 1520/RCD-I | 14/06/2024 | 45 | M/S U.G. ENTERPRISE | 11.77 | 11.05 | 100 | 100
939 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum Work Order for Providing of different dia water regulating apparatus (cast iron and Ductile iron) of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte | 1937/RCD-I | 07/08/2024 | 15 | MAKALI ENGINEERING CORPORATION | 92.83 | 92.83 | 100 | 100
940 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Additional works for Laying & pushing of 600 mm dia RCC Hume pipe (NP3) by adopting trench less technology (e.g Jack pushing method) and MS water carrier pipe under I.O.C.L pipe line at Basudevpur village of distribution network for RCFA Part-I within command area of Zone-I (Part B) Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Div-I, PHE Dte. | Camp-02_Basudebpur/AE/23- | 15/03/2024 | 30 | SWATI CORPORATION | 10.13 | 10.11 | 100 | 100
941 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Extension and renovation work of Annex Building including other allied works inside the premises of RCFA Division-I Office Campus under Augmentation of RCFA Part-II, Volume-I PWSS under RCFA Division-I PHE Dte | 1698/RCD-I | 11/07/2024 | 180 | M/S KALYANI ENTERPRISE | 28.95 | 13.56 | 47.02 | 100
942 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Providing of lighting luminaries, electrical wiring of chlorine room with yard lighting arrangement of Dhanudi O.H.R. premises under Improvement of RCFA Part-I W/S Scheme. | 1130/AMD | 30/07/2024 | 156 | CIEMENICS | 5.7 | 0 | 0 | 100
943 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. , SM/18769 | Augmentation | Acceptance cum work order for Balance work for laying of HDPE and MS pipeline restoration of drain,road and culvert and allied works at Zone-XI(Segment-5) Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I.PHE Dte. | 1431/RCD-I | 06/06/2024 | 15 | M/S B.K. CONSTRUCTION | 11.57 | 9.26 | 84.23 | 100
944 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Construction of Pumping Station at Itapara new H/W Site of Itapara Water Supply Scheme under RCFA Division-I PHE Dte.(Sl no 01) | 14 / RCD I | 08/01/2021 | 45 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 2.75 | 0 | 0 | 0
945 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Preparation of DPR for Augumentation of Itapara Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 02) | 2346/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 2.82 | 2.82 | 100 | 0
946 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Material Requisition To Resource Division | 121/RCD-I | 24/01/2023 | 0 | Resource Division | 222.41 | 0 | 0 | 0
947 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Material Requisition To Resource Division | 28/RCD-I | 10/01/2023 | 0 | Resource Division | 92.01 | 0 | 0 | 0
948 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Material Requisition To Resource Division | 2207/RCD-I | 17/07/2023 | 0 | Resource Division | 160.38 | 0 | 0 | 0
949 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Providing and Installation of Electro-Mechanical Equipments and Allied Works at Panuria under Augmentation of Panuria Itapara Water Supply Scheme, Block-Baraboni, Dist.-Paschim Bardhaman. | 488/AMD | 22/02/2023 | 365 | BENGAL CONSTRUCTION | 180 | 62.07 | 73.26 | 68
950 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Acceptance cum work order for Construction of Guard Room with toilet at Dabor OHR site under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | 460/RCD-1 | 12/02/2024 | 90 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 5.97 | 0 | 0 | 0
951 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Continuation work order for Renovation of filter bed, changing of Media and allied works at Salanpur Dalmia OCP Project under RCFA Division-I PHE Dte. | 101_A_RCD-I | 09/01/2024 | 15 | R B ENTERPRISE | 7.46 | 0 | 0 | 0
952 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Acceptance cum Work Order for Additional work for raising height of tube well to encounter flood including surging of tube well, repairing work of collecting main at river Ajoy at Churulia under Augmentation of Itapara Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 876/RCD-I | 15/03/2024 | 15 | MD AAMIR KHAN | 4.09 | 0 | 0 | 100
953 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Acceptance cum work order for Construction of Guard Room with toilet at Malladihi OHR site under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | 717-A/RCD-I | 01/03/2024 | 90 | PINKI ENTERPRISE | 5.97 | 0 | 0 | 0
954 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Continuation of work order for Conducting route survey , design rising main network and preparation & submission of source augmentation DPR for Itapara PWSS for Impementation of JJM at Barabani block under RCFA DIVISION-I P.H.E. Dte. | 74/A/RCD-I | 02/01/2024 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100 | 100
955 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Acceptance cum work order for Construction of spout, repairing and restoration of pipe line, FHTC connection and allied land development works within distribution system under Malladihi OHR under Augmentation of Itapara PWSS under RCFA Division-I PHE Dte. | 469/RCD-1 | 12/02/2024 | 15 | ASHA CONSTRUCTION | 7.18 | 6.99 | 100 | 100
956 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Acceptance cum work order for Supply of valves, construction of valve chamber, supplying laying HDPE/UPVC/GI pipe line and allied works at Putulia, Hosenpur and adjacent area under Augmentation of Itapara W/S Scheme under RCFA Division-I PHE Dte. | 461/RCD-1 | 12/02/2024 | 30 | R B ENTERPRISE | 7.72 | 7.67 | 100 | 100
957 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-6 Segment) for augmentation of Itapara piped Water Supply Scheme under RCFA Division-I PHE Dte | 1699/RCD-I | 13/07/2022 | 923 | UMA ENTERPRISE | 44.47 | 16.76 | 37.69 | 45
958 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Rising Main for Augmentation of Itapara Piped Water Supply Scheme at Baraboni Block Under RCFA - Div - I PHE Dte. | 3277/RCD I | 20/12/2022 | 529 | DURGADAS MONDAL | 34.74 | 19.21 | 55.3 | 80
959 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME , SM/10844 | Augmentation | Acceptance cum work order for Construction of approach road, land development, CWR painting, Cable trench slab, drainage system at Runakuraghat H/W campus under Augmentation of Itapara Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 24) | 1090/RCD-I | 23/03/2023 | 60 | SRI KRISHNA ENTERPRISE | 37.83 | 35.84 | 100 | 100
960 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Acceptance cum formal order for the work of Construction of Pump house cum Chlorine room at Madhabmat Pump house No-I tube well no-1 for Augmentation of Kanksa (Zone-II/Part-A) piped W/S Scheme under DWSD, PHE Dte (SL-04) | 379/DWSD | 24/03/2022 | 45 | MUKHERJEE ENTERPRISE | 4.89 | 4.7 | 96.15 | 0
961 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Formal order for the work of Supplying and laying of 90/75 mm dia HDPE pipe and 63/50 mm dia UPVC pipe line with necessary allied work at Sundiara and Tilakchnadrapur mouza JL-63/67) under Augmentation of Kanksa (Zone-II/Part-A) piped W/s Schme for providing FHTC under DWSD ,PHE Dte (SL-02) | 312/DWSD | 11/03/2022 | 15 | SK. ABDUL HALIM | 9.12 | 9.11 | 100 | 0
962 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Formal order for the work of Additional work for providing FHTC tap connection with jjm at Ijjatganj mouza(JL-71) and laying 125 mm dia HDPE and 63/50 mm dia UPVC pipe under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Schme for providing FHTC under DWSD ,PHE Dte | 333/DWSD | 15/03/2022 | 15 | RANJIB GHATAK | 29.48 | 29.65 | 100 | 0
963 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Formal order for the work of Sinking of 1 No 300X200 mm dia tube well ,210 mtr of depth by Direct Rotary method using PVC Pipe and Fiber Strainer reinforced epoxy slotted at Madhabmat Pump House No-1 under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme under DWSD, PHE Dte.(SL-02) | 660/DWSD | 22/04/2022 | 10 | RANJIB GHATAK | 14.01 | 12.95 | 100 | 0
964 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Formal order for the work of Sinking of 1 No 300X200 mm dia tube well ,210 mtr of depth by Direct Rotary method using PVC Pipe and Fiber Strainer reinforced epoxy slotted at Madhabmat Pump House No-2 under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme under DWSD, PHE Dte. | 653/DWSD | 22/04/2022 | 10 | JOY GURU ENTERPRISE | 14 | 11.75 | 100 | 0
965 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Formal order for the work of Sinking of 1 No 300X200 mm dia tube well ,210 mtr of depth by Direct Rotary method using PVC Pipe and Fiber Strainer reinforced epoxy slotted at Madhabmat Pump House No-2 under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme under DWSD, PHE Dte.(SL-04) | 548/DWSD | 08/04/2022 | 10 | AHS R INFRA PRIVATE LIMITED | 14.04 | 13.02 | 100 | 0
966 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Continuation order for the work of soil investigation for determing the safe bearing capacity and other relevant parameters of soil for the work of construction of RCC elevated at Madhabmath Reservoir site of Augmentation of Kanksa (Zone-II/A) piped W.S Scheme under DWSD ,PHE DTe. | 354/DWSD | 21/03/2022 | 25 | MABCO CONSULTANT | 1.2 | 1.2 | 100 | 0
967 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Acceptance cum formal order for the work of Construction of Pump house cum Chlorine room at Madhabmat Pump house No-III tube well no-3 for Augmentation of Kanksa (Zone-II/Part-A) piped W/S Scheme under DWSD, PHE Dte (SL-06) | 385/DWSD | 25/03/2022 | 45 | A.K.D. ENTERPRISE | 4.89 | 4.7 | 100 | 0
968 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Acceptance cum formal order for the work of Construction of Pump house cum Chlorine room at Madhabmat Pump house No-II tube well no-2 for Augmentation of Kanksa (Zone-II/Part-A) piped W/S Scheme under DWSD, PHE Dte(SL-05) | 583/DWSD | 25/03/2022 | 45 | GHOSH & ROY ENTERPRISE | 4.89 | 4.69 | 100 | 0
969 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI Specials valves and other allied works at Madhabmat under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme under DWSD, PHE Dte.(SL-01) | 659/DWSD | 22/04/2022 | 10 | BASANTI TRADERS | 10.58 | 8.45 | 79.84 | 100
970 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Formal order for the work of supplying ,laying of distribution system and providing functional house hold tap connection (FHTC) including reconnection of existing FHTC from AC pipe line to newly laid different dia HDPE pie line for Kanksa (zone-II/A) piped W/s Scheme under DWSD,PHE Dte (Augmentation Scheme) Dist.-Paschim Bardhhaman. | 1361/DWSD | 20/09/2022 | 122 | SAIKAT RAY | 236.37 | 239.55 | 100 | 0
971 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Acceptance cum formal order for the work of Construction of boundary wall at Madhabmat H/W site (PH No-3,TW No-3) site under Augmentation of Kanksa Zone-II/Part-A piped W/s Scheme under DWSD ,PHE Dte | 297/A/DWSD | 17/02/2023 | 30 | A.K.D. ENTERPRISE | 11.08 | 9.88 | 89.2 | 0
972 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Formal order for the work of Construction of 500 M3 capacity, 20 mtr staging height Over Head Reservoir at Madhabmat Tube well No-1 Kanksa (Zone-II/Part-A) piped W/S Scheme under DWSD , PHE Dte (SL-05) | 571/DWSD | 12/04/2022 | 184 | SAIKAT RAY | 99.22 | 95.07 | 100 | 100
973 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Continuation order for the work of supplying fitting fixing and installation of Sluice Valve for O & Mtc of Kanksa (Zone-II/II) piped W/s Scheme of command areas of Panaghar ,Prayagpur mouza under DWSD, PHE Dte | 682/DWSD | 27/04/2022 | 15 | TARA CONSTRUCTION | 4.94 | 0 | 0 | 0
974 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Acceptance cum formal order for the work of Additional work for providing FHTC tap connection with JJN at Debipur mouza -87 and its adjoining area under command area of Augmentation of Kanksa (Zone-II/A ) piped W/s Scheme at Kanksa block under DWSD, PHE Dte (SL-12) | 1032/DWSD | 04/07/2022 | 10 | QUICK PAL SUPPLIERS | 4.99 | 4.99 | 100 | 0
975 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Acceptance cum Formal work-Order for the work of ---Sanitary arrangement and plumbing works at Madhabmat Pump house No-1 Tube well No-01(OHR Site) for Augmentation of Kanksa (Zone-II/A) pipe W/S Scheme under DWSD,PHE Dte (SL-02) | 1055/DWSD | 07/07/2022 | 25 | MUKHERJEE ENTERPRISE | 4.82 | 4.44 | 100 | 100
976 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Acceptance cum Formal work-Order for the work of ---Sanitary arrangement and plumbing works at Madhabmat Pump house No-2 Tube well No-02 for Augmentation of Kanksa (Zone-II/A) pipe W/S Scheme under DWSD,PHE Dte (SL-03) | 1056/DWSD | 07/07/2022 | 25 | GHOSH & ROY ENTERPRISE | 4.82 | 4.44 | 100 | 100
977 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works at Madhabmat Pump house No-3 Tube well No-03 for Augmentation of Kanksa (Zone-II/A) pipe W/S Scheme under DWSD,PHE Dte (SL-01) | 1063/DWSD | 08/07/2022 | 25 | A.K.D. ENTERPRISE | 4.82 | 4.42 | 100 | 100
978 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Formal order for the work of balance work of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme with construction of boundary wall ,approach road,canal crossing ,leftout LDS,FHTC reconnection of FHTC at Kansa(Part),Debipur(Part),Panagarh(Part),Ijjatganj(Part), mouzas of JL-86,88,87,85 of Kanksa block under DWSD ,PHE Dte (SL-03) | 225/DWSD | 06/02/2023 | 90 | SAIKAT RAY | 197.71 | 163.93 | 100 | 100
979 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Acceptance order for the work of Laying and aligning of distribution pipe line from zero point and allied works under Augmentation of Kanksa Zone-II/Part-A) piped W/s Scheme under DWSD ,PHE Dte. | 104/DWSD | 24/01/2023 | 20 | PAYAL CONSTRUCTION | 8.6 | 8.59 | 100 | 0
980 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Acceptance cum formal order for the work of Balance work of Augmentation of Kanksa Zone-ii/C piped W/s Scheme with construction of boundary wall renovation of all existing structure repairing of all water retaining structure left out LDS FHTC reconnection of FHTC at Kanksa (Part) ,Debipur (Part), Paragraph (Part), Prayagpur(Part) mouzas of JL-86,88,87 of Kanksa block under DWSD ,PHE Dte | 490/DWSD | 23/03/2023 | 45 | BRINDABAN KONAR | 94.94 | 3.85 | 100 | 100
981 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Approach road & others necessary allied works at Madhabmat 2nd Pump house to 3rd Pump House ,Kanksa for Kanksa Zone-II/A W/s Scheme under DWSD ,PHE Dte | 1057/DWSD | 20/07/2023 | 30 | A.K.D. ENTERPRISE | 25.4 | 25.36 | 100 | 100
982 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Material Requisition To Resource Division | 307/DWSD | 15/03/2022 | 0 | Resource Division | 45.42 | 0 | 0 | 0
983 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Electricity service connection charges for Kanksa Zone-II Part-A TW-1 | BP-2023-24-104 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.04 | 0 | 0 | 0
984 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Road restoration at Panagarh Silampur Road (ch 2.5 KM to 3.5 KM) to be executed by Executive Engineer, Asansol Highway Division, PWD Roads directorate for the work of repairing of damaged at Panagarh Silampur | BP-2023-24-221 | 21/09/2023 | 0 | EXECUTIVE ENGINEER , ASANSOL HIGHWAY DIVISION, PWD ROADS | 17.96 | 0 | 0 | 0
985 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Quotation money for service connection Kanksa Zone-II Part-A TW-III | BP-2023-24-106 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.99 | 0 | 0 | 0
986 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Electricity charges for installation of service connection for Kanksa Zone-II Part-A TW-II | BP-2023-24-105 | 25/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.87 | 0 | 0 | 0
987 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Hiring of Maxi Cab (Non Air Conditional ) Bharat Stage-iii/BS-ii purchased on or after 01.05.2008 with Diesel /LPG /CNG Engine for the supervision work of Durgapur W/S Division for office use of Assitant Engineer, RCFA Division-I Public Helth Engineering Directorate, Govt of West Bengal ( w.e.f 01.12.2023. to 31.05.2024) Consumption of Diesel,12 km per litre, Mobil 05 litre per 2500 km. | 3514/RCD-I | 30/11/2023 | 182 | SUBHA TOUR & TRAVELS | 0.89 | 0.8 | 268.01 | 35
988 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1, 2 & 3 at Augmentation of Kanksa Zone - II/A Water Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | 2571/CMD | 06/06/2023 | 580 | M/S. SWAPAN BANERJEE | 29.92 | 9.58 | 33.14 | 31
989 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Acceptance cum formal order for the work of 1(One) No PWD road crossing SH-34 at Railpar Sarada Pally near DVC Canal under command area of Kanksa Zone-II/Pt-A distribution main by modern trenches less technology through JACK Pushing method under Augmentation of RCFA part III Zone I piped W/s Scheme under DWSD ,PHE Dte | 1272/DWSD | 07/08/2023 | 620 | SAIKAT RAY | 8.56 | 0 | 0 | 100
990 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) , SM/10211 | Augmentation | Acceptance cum Work Order for Additional work for laying DI pipe at Shilampur under Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC of Gopalpur PWSS under RCFA Division-I PHE Dte | 1794/RCD-I | 24/07/2024 | 161 | MD AAMIR KHAN | 8.7 | 6.99 | 45.35 | 100
991 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI specials ,valves and allied works at Akandara covering Jemua and Paranganj area under Augmentation of Kanksa (Zone-II/Part-B) piped W/s Scheme under DWSD, PHE Dte (SL-02) | 765/DWSD | 13/05/2022 | 15 | AMAR CONSTRUCTION | 70.22 | 66.5 | 94.7 | 0
992 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Acceptance cum formal order for the work of Emergent supply fitting fixing of Sluice Valve for repairing and maintenance of pipe line under Kanksa (Zone-II) W/S Scheme under DWSD ,PHE Dte.(SL-06) | 413/DWSD | 30/03/2022 | 10 | SWATI CORPORATION | 2 | 1.94 | 100 | 0
993 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Acceptance cum formal order for the work of Replacement of pipe line from existing pipe line of Kanksa (Zone-II) W/s Scheme at Madhabmat and near under bypass in Kanksa Block under DWSD, PHE Dte (Sl-4) | 411/DWSD | 30/03/2022 | 7 | SWATI CORPORATION | 3.13 | 3.14 | 100 | 0
994 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Acceptance cum formal order for the work of additional work for providing FHTC tap connecting with JJM at Prayagpur mouza -88 and its adjoining area under command area of Augmentation of Kanksa (Zoe-II/B_) piped W/S Scheme block Kanksa under DWSD,PHE Dte (SL-05) | 1025/DWSD | 04/07/2022 | 10 | QUICK PAL SUPPLIERS | 4.98 | 5.03 | 100 | 0
995 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Formal order for the work of Laying distribution system and providing functional house hold tap connection (FHTC) including reconnection of exiting FHTC form AC pipe line to newly laid different dia pipe line for Kanksa (Zone-II/Part-B) under DWSD ,PHE Dte (Augmentation Scheme) | 1449/DWSD | 17/10/2022 | 123 | MD AAMIR KHAN | 217.39 | 222.62 | 100 | 0
996 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Acceptance cum formal order for the work of Trail bore for sinking of 3(Three) Nos (300X200 mm dia ) big tube well of 210 mtr depth by DR method using UPVC pipe and UPVC deep well screen RDS at Kanksa (Zone-II) tube well site of Augmentation of Kanksa Zone-II/Part-B &C) piped W/S Scheme under DWSD,PHE Dte | 771/DWSD | 22/05/2023 | 15 | JOY GURU ENTERPRISE | 4.81 | 4.81 | 100 | 0
997 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Special repair and renovation of 1(One) No 450 M3 capacity RCC Elevated Reservoir (OHR) at OHR site boundary wall and 2 (Two) Nos Pump house at Kanksa (Zone-II/Part-B) under Augmentation of Kanksa (Zone-II/Part-B) piped W/s Scheme under DWSD, PHE Dte | 1138/DWSD | 20/07/2023 | 30 | MAK CONSTRUCTION CO. | 35.76 | 9.09 | 25.43 | 80
998 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road for extension of pipe line from existing pipe line of Kanksa (Z-II)(Ph-II) W/s Scheme to laying branch pipe line in kanksa block for providing FHTC at PanagarhJL_85) at Palpara ,Hazra Para ,Kumanrpara near TC pur Panchayat ,Panagarh bypass under DWSD PHE Dte (Sl-04) | 78/DWSD | 24/01/2022 | 15 | GITA CONSTRUCTION | 3.46 | 0 | 0 | 0
999 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Formal order for the work of extensioin of pipe line from existing pipe line of Kanksa Zone-II PH-II W/s Scheme to combat draught like situation in Kanksa block to providing FHTC at Debipur mouza JL-87 ,Sharmapara ,Singh para under DWSD,PHE Dte. | 1606/DWSD | 12/11/2021 | 20 | M/S. D. PALIT & CO. | 18.1 | 18.1 | 100 | 0
1000 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Continuation order for the work of supplying fitting fixing and installation of Sluice Valve for O & Mtc of Kanksa (Zone-II/II) piped W/s Scheme of command areas of Panaghar ,Prayagpur mouza under DWSD, PHE Dte | 682/DWSD | 27/04/2022 | 15 | TARA CONSTRUCTION | 4.94 | 0 | 0 | 0
1001 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Acceptance cum formal order for the work of Construction of Guard wall at Madhabmat pukur par of Kanksa (Zone-II) piped W/s Scheme under DWSD, PHE Dte (SL-01) | 405/DWSD | 30/03/2022 | 10 | TARA CONSTRUCTION | 4.38 | 2.71 | 100 | 100
1002 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Acceptance cum formal order for the work of Sinking of 06 Nos 300X200 mm dia Tube well with 210 mtr Depth by DR rig method using UPVC pipe (CD and UPVC deep well screen (RDS) at Kanksa (Zone-II) Part-B,C tube well site of Augmentation of Kanksa Zone-II(Part-B & C) piped W/s Scheme under DWSD ,PHE Dte (SL-02) | 254/DWSD | 15/02/2023 | 60 | JOY GURU ENTERPRISE | 94.05 | 46.1 | 100 | 0
1003 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Formal order for the work of Laying and aligning of distribution pipe line from zero point to Jhanjra more and allied works under Augmentation of Kanksa Zone-II/Part-B) piped W/s Scheme under DWSD ,PHE Dte. | 302/DWSD | 20/02/2023 | 20 | BABA LOKENATH ENTERPRISE | 13.91 | 13.91 | 100 | 0
1004 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Formal order for the work of Balance work of Augmentation of Kanksa (Zone-II/Part-B) piped W/s Scheme with construction of boundary wall renovation of all existing structure ,repairing of all water retaining structure ,let-out LDS,FHTC,Re connection of FHTC at Kanksa (Part) ,Debipur(Part),Paragraph (Part), Prayagpur(Part) mouzas of JL No-86,88,87,88 of Kanksa block under DWSD ,PHE Dte | 238/DWSD | 08/02/2023 | 90 | MD AAMIR KHAN | 181.79 | 180.81 | 99.99 | 100
1005 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Acceptance cum formal order for the work of Electrical wiring and other allied works for modernization of Gopalpur for Laboratory NABL accreditation of sub-District Water Testing Lab at Kanksa of Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme under DWSD,PHE Dte | 764/DWSD | 22/05/2023 | 15 | BASANTI TRADERS | 1.72 | 1.72 | 100 | 100
1006 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Material Requisition To Resource Division | 327/DWSD | 15/03/2022 | 0 | Resource Division | 6.6 | 0 | 0 | 0
1007 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Service connection quotation money for Kanksa Zone- Part-B TW-3 | BP-2023-24-103 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.13 | 0 | 0 | 0
1008 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Road restoration at Panagarh Silampur Road (ch 2.5 KM to 3.5 KM) to be executed by Executive Engineer, Asansol Highway Division, PWD Roads directorate for the work of repairing of damaged at Panagarh Silampur | BP-2023-24-221 | 21/09/2023 | 0 | EXECUTIVE ENGINEER , ASANSOL HIGHWAY DIVISION, PWD ROADS | 17.96 | 0 | 0 | 0
1009 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Electricity connection quotation fees for Kanksa Zone-II Part-B TW-2 | BP-2023-24-102 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.01 | 0 | 0 | 0
1010 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Quotation money for electrification service charges for Kanksa Zone-II/Part-B TW-I | BP-2023-24-101 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.56 | 0 | 0 | 0
1011 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1, 2 & 3 at Augmentation of Kanksa Zone - II/B Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2572/CMD | 06/06/2023 | 30 | JAL PRAVAHIKA PVT LTD | 29.1 | 18.56 | 63.78 | 98
1012 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangement at Kanksa zone-II/Part-B) under Augmentation of Kanksa (Zone-II) (Part-B) piped W/S Scheme under DWSD,PHE Dte | 1291/DWSD | 07/08/2023 | 45 | PRAKRITI CONSTRUCTION | 5.74 | 0 | 0 | 10
1013 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangement at Kanksa zone-II/Part-B) under Augmentation of Kanksa (Zone-II) (Part-B) piped W/S Scheme under DWSD,PHE Dte | 1292/DWSD | 07/08/2023 | 45 | PRAKRITI CONSTRUCTION | 6.02 | 0 | 0 | 100
1014 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Supply & Installation of Kiosk box and other allied work for Tube well No: 2 & 3 at Augmentation of Kanksa Zone -II/B water supply scheme under Central Mechanical Division PHE, Dte. | 131/DIC/BMSD(D) | 29/02/2024 | 15 | JAL PRAVAHIKA PVT LTD | 0.58 | 0.58 | 100 | 100
1015 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Supply & laying of cable for actuator of Tube well No ¿ 2 at Augmentation of Kanksa Zone -II/B water supply scheme under Central Mechanical Division PHE, Dte. | 130/DIC/BMSD(D) | 29/02/2024 | 7 | JAL PRAVAHIKA PVT LTD | 0.86 | 0.86 | 100 | 100
1016 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) , SM/10212 | Augmentation | Laying & aligning of DI K9 rising main pipe line and interconnection of TW No-3 with OHR and other allied works of Augmentation of Kanksa Zone-II/Part-B piped W/s Scheme under DWSD ,PHE Dte (Pat-A) | 1295/DWSD | 07/08/2023 | 657 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 16.23 | 0 | 0 | 70
1017 | PASCHIM BARDHAMAN | Durgapur W/S Division | KOTALPUKUR PIPED WATER SUPPLY SCHEME , SM/10996 | New | Formal order for the work of Additional work of laying of HDPE distribution pipe line 75/90 mm dia and providing FHTC at Kotalpukur (JL-30),Nimtakuri(JL-32) & Masna(JL-31) mouzas of Kotalpukur piped W/s Scheme under DWSD,PHE Dte (SL-03) | 1426/DWSD | 08/10/2022 | 10 | JOY GURU ENTERPRISE | 12.21 | 8.7 | 100 | 0
1018 | PASCHIM BARDHAMAN | Durgapur W/S Division | KOTALPUKUR PIPED WATER SUPPLY SCHEME , SM/10996 | New | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at Kotalpukur,Masna,Nimtikuri mouzas of Kotalpukur piped W/s Scheme under DWSD, PHE Dte under DWSD, PHE Dte (Part-A ,B & C) (SL-02) | 773/DWSD | 17/05/2022 | 45 | JOY GURU ENTERPRISE | 41.01 | 35.36 | 100 | 0
1019 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 A) , SM/12221 | Augmentation | Material Requisition To Resource Division | 2951/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1020 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 A) , SM/12221 | Augmentation | Acceptance cum Work Order for Additional work for distribution network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-9A(Segment-III) under RCFA Division-I. PHE Dte. | 1016/RCD-I | 16/03/2024 | 45 | UNITED CONSTRUCTION | 35.76 | 19.29 | 53.94 | 70
1021 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 A) , SM/12221 | Augmentation | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I Phe Dte. (Zone-9A) | 1760/RCD I | 16/05/2023 | 839 | ASHA CONSTRUCTION | 345.86 | 145.44 | 42.05 | 80
1022 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 A) , SM/12221 | Augmentation | Acceptance cum Work Order for Repairing of Boundary Wall for 45 mtr at Chora OHR Site of RCFA Part-II (Zone- 9, 9A and 9B) PWSS Block-Pandabeswar under RCFA Division-I PHE Dte. (Sl No. 01) | 1144/RCD-1 | 24/03/2023 | 15 | N.R. CONSTRUCTION | 4.61 | 1.86 | 100 | 100
1023 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 A) , SM/12221 | Augmentation | Acceptance cum work order for Balance work and crossing road by trenchless technology in different site connection with distribution network including FHTC & allied work at Andal Block of Augmentation PWSS RCFA Part-II (Zone-9A) under RCFA Division-I PHE, Dte | 2420/RCD-I | 26/09/2024 | 45 | MACHINO TECHNO | 69.72 | 18.46 | 20.94 | 100
1024 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptance cum work order for Construction of Store Room at Chora of Pandabeswar Block for Augmentation of RCFA Part-II (Zone-9) Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 25) | 1168/RCD I | 24/03/2023 | 90 | M/S S.K. ENTERPRISE | 4.61 | 0 | 0 | 0
1025 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Material Requisition To Resource Division | 2949/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1026 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptance cum work order for Construction of Pump House at Dendua for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 487/RCDI | 03/02/2023 | 90 | D.S. ENTERPRISE | 30.3 | 23.52 | 77.62 | 77
1027 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptence cum work order for Dedicated line towards Paharpur village, Kallya village and necessary repairing including supply of valve construction of valve chamber etc. within Distribution Network of Dabor OHR under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | 2577/RCD-I | 07/09/2023 | 15 | DHRUBA ENTERPRISE | 9.05 | 7.3 | 80.66 | 100
1028 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptance cum work order for Repair and renovation works of one no RCC Elevated Reservoir of capacity 1362 cum at Chora for RCFA Part-II (Zone-9, 9A & 9B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 12) | 1078/RCD I | 23/03/2023 | 270 | ASHA CONSTRUCTION | 17.06 | 14.88 | 100 | 100
1029 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir at (Zone-XI) of Barabani Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3148/RCD-I | 12/12/2022 | 7 | AMAR CONSTRUCTION | 0.98 | 0.98 | 100 | 100
1030 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptance cum work order for Laying of 110 mm dia and 90 mm dia HDPE pipe line including chokage cleaning and other allied works of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | 3432/RCD-1 | 24/11/2023 | 30 | JAI MAHARAJ ENTERPRISE | 6.86 | 6.86 | 49.87 | 100
1031 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptance cum work order for 2 nos Emergency repairing work of 450mm dia rising main at Basu Vata and Jamdoba under RCFA Part-II water supply scheme under RCFA Div-I, PHE Dte | 3376/RCD-I | 21/11/2023 | 15 | KHEPI MAA TRADERS | 2.16 | 2.16 | 49.97 | 100
1032 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Emergency repairing work 750 mm dia Rising main at Kalyaneswari Dendua road under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Camp_02_Kalyaneswari_AE_I | 06/10/2023 | 15 | MD AAMIR KHAN | 2.75 | 2.67 | 100 | 100
1033 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptance cum work order for Protecting apparatus of collecting main including other allied works under RCFA Part-II PWSS (Zone-9) under RCFA Division-I PHE Dte. | 1516/RCD-I | 14/06/2024 | 15 | MAKALI ENGINEERING CORPORATION | 99.5 | 99.5 | 100 | 100
1034 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptance cum work order for Supply of different dia Sluice valve, including C.I. / D.I. Specials to the Searsole Store of RCFA Part-II (Zone-9) PWSS under RCFA Division-I PHE Dte. | 1518/RCD-I | 14/06/2024 | 15 | MAKALI ENGINEERING CORPORATION | 77.57 | 77.57 | 100 | 100
1035 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptance cum work order for Additional work related to shifting Rising main, laying of distribution network, Road restoration and other allied work for Ondal Block of Augmentation PWSS of RCFA Part-II (Zone - 9) under RCFA Division-I PHE Dte. | 2457/RCD-I | 01/10/2024 | 30 | M/S UNIT CONSTRUCTION | 45.22 | 0 | 0 | 100
1036 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-08 at Andal under Augmentation of RCFA Part-II (Zone-9) under RCFA Division-I PHE Dte | 46/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 4.81 | 0 | 0 | 0
1037 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-10 under Augmentation of RCFA Part-II (Zone-9) under RCFA Division-I PHE Dte | 68/24-25 | 30/05/2024 | 0 | EASTERN RAILWAY | 4.73 | 0 | 0 | 0
1038 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptance cum work order for Distribution Network for RCFA Part-II Piped Water Supply Scheme including FHTC & allied works under RCFA Division-I PHE Dte.(Zone-9) Parshkol (Part-B)(Sl No. 16) | 1081/RCD I | 23/03/2023 | 90 | ALOKESH BANERJEE | 40.44 | 13.78 | 34.08 | 35
1039 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Formal work order for Distribution Network for RCFA Prt-II Pipe Water Supply scheme including FHTC & allied ork under RCFA Division-I PHE Dte. (Zone-9) Parshkol (Part-A) | 1607/RCD I | 25/04/2023 | 90 | MD AAMIR KHAN | 107.46 | 50.4 | 46.9 | 70
1040 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptance cum work order for Laying of different dia HDPE pipe line at Pure Jambad Hattala Zone, Real Jambad under Bahula (CT) (Jl No. 30, Block-Pandabeswar under Improvement of RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | 3299/RCD I | 20/12/2022 | 60 | GITA CONSTRUCTION | 78.64 | 21.9 | 100 | 90
1041 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptance cum work order for Allied work of laying dia HDPE Pipe line and allied works at Raghunathchak, Raniganj Chati, Baliapur and adjacent area under Zone-9 for Augmentation of RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | 2868/RCD-I | 06/10/2023 | 453 | MACHINO TECHNO | 89.05 | 23.11 | 26.78 | 50
1042 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) , SM/12222 | Augmentation | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at Chora of Pandabeswar Block for Augmentation of RCFA Part-II (Zone-9) Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (2nd Call) | 212/RCD-I | 29/01/2024 | 90 | KALYAN DAWN | 4.57 | 0 | 0 | 100
1043 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 04 nos location (Bus stand/Taxi stand Domohani Bazar, Rural more, Near Domohani Electric Supply Office, BDO Office More) of Barabani Block under Improvement of RCFA Part-I (Zone-11, Part-6) PWSS under RCFA Division-I PHE Dte. | 2229/RCD-I | 17/07/2023 | 30 | UMA ENTERPRISE | 30.82 | 0 | 0 | 0
1044 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Acceptance cum work order for Additional Supplying E.R.M.S Black pipe of approved quality including carring, stacking at works site and other allied works for Improvement RCFA Part-I Water Supply Scheme within command area of Zone VIII under RCFA Div-I PHE Dte. | 3612/RCD-1 | 20/12/2023 | 15 | SWATI CORPORATION | 2.78 | 0 | 0 | 0
1045 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Acceptance cum work order for Supplying E.R.M.S Black pipe of approved quality including carring, stacking at works site and other allied works for crossing of 07 nos (Node Point :139-140,153-3,42-43,86-87,60-61, and 38-40 culvert/canal of by the side of PWD road under Improvement RCFA Part-I water Supply scheme within command area of Zone VIII under RCFA Div-I PHE Dte. | 3614/RCD-I | 20/12/2023 | 15 | TARA CONSTRUCTION | 3.32 | 0 | 0 | 0
1046 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Acceptance cum work order for Additional extra cutting Laterate/sandstone of distribution of pipe line at Augmentation of RCFA Part-II (Zione-8) within command area under RCFA Division-I PHE Dte. | 2880/RCD-I | 06/10/2023 | 90 | SWATI CORPORATION | 10.6 | 10.6 | 100 | 100
1047 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Material Requisition To Resource Division | 2948/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1048 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Acceptance cum Work Order for Balance work for laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte. | 2455/RCD-I | 12/02/2024 | 45 | M/S SINGH & KONAR CONSTRUCTION | 45.53 | 0 | 0 | 0
1049 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Formal work order for Laying distribution system including FHTC for 5 (Two) nos uncovered village viz. Namokeshia and Jorbari within Salanpur Block under Augmentation of RCFA Part-II (zone-10) PWSS under RCFA Division-I PHE Dte. | 806/RCD-I | 13/03/2024 | 90 | UMA ENTERPRISE | 107.86 | 0 | 0 | 0
1050 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Acceptance cum Work Order for Emergent dismantling of RCC Elevated Reservoir capacity 682 cum staging height 20 meter at Mohishila OHR within Asansol Municipal Corporation area of Augmentation PWSS of RCFA Part-II (Zone-8) under RCFA Division-I PHE Dte. | 519/RCD-I | 16/02/2024 | 45 | GITA CONSTRUCTION | 17.37 | 17.35 | 100 | 100
1051 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Acceptance cum work order for Supply & Delivery of GI pipe including loading , unloading and carriage to Searsole store under RCFA Part-II PWSS under RCFA Division-I PHE Dte. | 626/RCD-I | 27/02/2024 | 20 | MAKALI ENGINEERING CORPORATION | 93.69 | 93.69 | 100 | 100
1052 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Way leave permission for water supply poipe line for JJM carrier pipe dia 250 mm at Pandabeswar under Augmentation of RCFA PART-II (ZONE-8) under RCFA Div-I PHE Dte. | 398/24-25 | 29/10/2024 | 0 | EASTERN RAILWAY | 1.19 | 0 | 0 | 0
1053 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Acceptance cum work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-8) with Construction of 250 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District Paschim Bardhaman, (Sl No. 07). | 1402 RCD I | 12/04/2023 | 365 | PINKI ENTERPRISE | 95.85 | 86.37 | 90.1 | 65
1054 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-1 Distribution Segment) under RCFA Division-I PHE Dte. | 2367/RCD-I | 04/08/2023 | 30 | R B ENTERPRISE | 47.39 | 40.66 | 85.79 | 86
1055 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Acceptance cum work order for Construction of Pump Houses (Size 14 mtr x 10 mtr x 8 mtr) under at Madanpur H/W Site under AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) under RCFA Division-I PHE Dte. | 3611/RCD-1 | 20/12/2023 | 567 | D.S.C. CONCERN | 35.91 | 16.6 | 46.22 | 50
1056 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Sub Soil Investigation for 250 cum capacity RCC Over Head Reservoir at (Zone-8) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3355/RCDI | 23/12/2022 | 777 | MOYTEC | 0.49 | 0.49 | 100 | 100
1057 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Acceptance cum work order for Construction of MS pipe carrier bridge, additional (Extra line) supplying, aligning & laying HDPE pipe line and other works of RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Div-I PHE Dte. | 2368/RCD-I | 04/08/2023 | 60 | SWATI CORPORATION | 28.11 | 26.64 | 100 | 100
1058 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. , SM/12028 | Augmentation | Acceptence cum work order for Additional (Extra line Node no. 550-550A, 555-548, 554-547, 527-321, 378-296, 397-423, 423-441) supplying, aligning & laying HDPE pipe line of RCFA Part-I Water Supply Scheme within command area of Zone-VII (Part-E) under RCFA Division-I PHE Dte | 2588/RCD-I | 07/09/2023 | 15 | TARA CONSTRUCTION | 7.55 | 7.46 | 100 | 100
1059 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Sub Soil investigation for 350 cum capacity RCC Over Head Reservoir at (zone-IX) of Barabani Block for Improvement of RCFA Part-I Piped water Supply Scheme under RCFA Division-I PHE Dte. In the District Paschim Bardhaman. | 2695/RCD-I | 27/09/2023 | 7 | MALLICK ENTERPRISE | 0.98 | 0 | 0 | 0
1060 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-XIII) of Barabani Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. In the District of Paschim Bardhaman. | 2696/RCD-I | 27/09/2023 | 7 | JOY HIND TUBEWELLS | 0.98 | 0 | 0 | 0
1061 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Material Requisition To Resource Division | 2955/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1062 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Chora (1135Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3025/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100 | 100
1063 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Rupnarayanpur (1182 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3015/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.98 | 4.98 | 100 | 100
1064 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of DP Colony (450 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3022/RCD-1 | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.93 | 4.93 | 100 | 100
1065 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Jitpur Uttarrampur and surrounding villages within Jitpur Uttarrampur Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte. | 3451/RCD-I | 24/11/2023 | 15 | DIP ENTERPRISE | 4.49 | 4.38 | 100 | 100
1066 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum work order for Additional work for laying and distribution system for Improvement of RCFA Part-I Water Supply Scheme under Command area of Zone-VII under RCFA Division-I PHE Dte. | 3472/RCD-I | 28/11/2023 | 30 | GITA CONSTRUCTION | 95.09 | 70.58 | 81.55 | 100
1067 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum work order for Laying of different dia HDPE pipe line (left out portion) including adopting trench less technologies and other allied works at Moul Danga village under Barabani Block of Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | 3284/RCD-1 | 08/11/2023 | 30 | SRI KRISHNA ENTERPRISE | 19.21 | 16.46 | 100 | 100
1068 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum work order for Construction of Guard Wall arrangement to project 450 mm dia the Rising Main at Bidyanandapur of ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | 3377/RCD-I | 21/11/2023 | 15 | SIMA ENTERPRISE | 4.03 | 2.23 | 100 | 100
1069 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-I) under RCFA Division-I PHE Dte | 1115/ RCD I | 23/03/2023 | 90 | M/S B.K. CONSTRUCTION | 86.29 | 32 | 37.09 | 38
1070 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-VI) under RCFA Division-I PHE Dte. | 1108/RCD-I | 23/03/2023 | 90 | VISUVIOUS | 54.47 | 47.84 | 87.83 | 90
1071 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum Work Order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-V) under RCFA Division-I PHE Dte. (Sl No. 07) | 1110/RCD-I | 23/03/2023 | 90 | DIP CONSTRUCTION | 90.17 | 31.53 | 34.97 | 35
1072 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-III) under RCFA Division-I PHE Dte. | 1112/ RCD I | 23/03/2023 | 90 | UNITED CONSTRUCTION | 86.38 | 65.24 | 75.53 | 75
1073 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-II) under RCFA Division-I PHE Dte. | 1113/ RCD I | 23/03/2023 | 1174 | M/S KONAR CONSTRUCTION | 84.65 | 11.07 | 13.08 | 50
1074 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-IV) under RCFA Division-I PHE Division-I PHE Dte. (Sl No. 08). | 1706/ RCD I | 03/05/2023 | 90 | DURGADAS MONDAL | 85.16 | 45.25 | 53.13 | 55
1075 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-10) with Construction of 350 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District-Paschim Bardhaman. | 1845/RCD-I | 31/05/2023 | 365 | RUBY CONSTRUCTION | 126.43 | 42.18 | 33.36 | 20
1076 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir at (Zone-10) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3356/RCDI | 23/12/2022 | 782 | MOYTEC | 0.49 | 0 | 0 | 100
1077 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. , SM/12029 | Augmentation | Acceptance cum Work Order for Balance Work of different work to Amritnagar Zone-I under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | 506/RCD-I | 12/02/2024 | 30 | MACHINO TECHNO | 82.78 | 82.05 | 100 | 100
1078 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. , SM/12030 | Augmentation | Material Requisition To Resource Division | 2946/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1079 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. , SM/12030 | Augmentation | Restoration work for laying of under ground water supply line (400 mm dia) Ch. 0.100 kmp to ch 1.350 on Ukhra Haripur (0-5) road in the district of Pachim Bardhaman | 235/23-24 | 29/08/2023 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 32.64 | 0 | 0 | 0
1080 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. , SM/12030 | Augmentation | Formal work order for distributionn network for RCFA Part-II piped Water Supply Including FHTC & allied works under RCFA Div-I, PHE Dte. (Zone-12B)(Segment-1) | 931/RCDI | 14/03/2023 | 60 | ARISTOCON ENGINEER'S CO-OP. SOCIETY LTD. | 157.79 | 128.25 | 81.28 | 82
1081 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. , SM/12030 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Pancgachia (240 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3017/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.92 | 4.92 | 100 | 100
1082 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. , SM/12030 | Augmentation | Formal work order Distribution Network including FHTC & alied work at Ondal Block of RCFA Part-II (Zone-12A) Piped Water Supply Scheme Under RCFA Division-I PHE Dte. | 1764/RCD I | 16/05/2023 | 962 | MRITYUNJOY MUKHERJEE & CO. | 610.49 | 195.98 | 32.1 | 70
1083 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. , SM/12030 | Augmentation | Sub Soil Investigation for 1000 cum capacity RCC Over Head Reservoir at (Zone-12A) of Ondal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3366/RCDI | 23/12/2022 | 782 | MOYTEC | 0.49 | 0 | 0 | 100
1084 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. , SM/12030 | Augmentation | Formal work for Construction of 1000 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connetion and cost of pipes,specials at Ondal Block (Zone-12A) for Augmentation of RCFA Part-II Piped Water Supply Scheme including Soil investigation and chlorine Room (4.50 X 3.50 m) under RCFA Division-I PHE Dte. in District Paschim Bardhaman. | 1847/RCD-I | 31/05/2023 | 366 | M/S PIONEER CONSTRUCTION | 203.2 | 203.2 | 100 | 100
1085 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. , SM/12031 | Augmentation | Material Requisition To Resource Division | 2945/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1086 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. , SM/12031 | Augmentation | Acceptance cum work order for Allied work of Distribution Network including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-12 A) Piped Water Scheme under RCFA Division-I PHE Dte. | 3436/RCD-1 | 24/11/2023 | 60 | MRITYUNJOY MUKHERJEE & CO. | 81.28 | 48.77 | 60 | 65
1087 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. , SM/12031 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Barabani (910 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3018/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.95 | 4.95 | 100 | 100
1088 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. , SM/12031 | Augmentation | 100 mm dia water pipe line with 600 mm dia MS Casing pipe line (Jal Jeevan Mission) by R.C.F.A Division-1, PHE DTE, Asansol in between Parasia Siding ¿ New Jambad Siding at Km. CB-2/15-16 in Asansol Division of Eastern Railway under AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | 396/24-25 | 28/10/2024 | 0 | EASTERN RAILWAY | 4.58 | 0 | 0 | 0
1089 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. , SM/12031 | Augmentation | Formal Work Order for Distribution network for RCFA Part-II piped Water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-12B)(Segment-2). | 485/RCDI | 03/02/2023 | 60 | M/S SINGH & KONAR CONSTRUCTION | 155.21 | 92 | 59.27 | 80
1090 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. , SM/12031 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Shankarpur under Pandabeswar H/W Site within Pandabeswar Block for Augmentation of PWSS of RCFA Part-II (Zone-12B) under RCFA Division-I PHE Dte. | 162/RCD-I | 08/01/2025 | 90 | DIP CONSTRUCTION | 34.75 | 0 | 0 | 0
1091 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. , SM/12031 | Augmentation | Acceptance cum Work Order for Additional work of allied items at Andal OHR Site under Phase-II/B under RCFA Division-I PHE Dte. AUGMENTATION PWSS OF RCFA PART-II (Zone-12B) | 1647/RCD-I | 04/07/2024 | 15 | AMAR CONSTRUCTION | 5.25 | 5.25 | 100 | 100
1092 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. , SM/12031 | Augmentation | Acceptance cum work order for Allied works of laying distribution system of balance work of supply & laying of HDPE pipe under Augmentation of sub-surface water based PWSS for Amritnagar Zone-II under RCFA Division-I PHE Dte. | 498/RCD-I | 12/02/2024 | 45 | MACHINO TECHNO | 78.67 | 76.89 | 100 | 100
1093 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. , SM/12031 | Augmentation | Acceptance cum work order for Allied work Balance work of Road restoration in connection with laying distribution system to Accommodate FHTC and providing FHTC including supplying laying fittings fixing of 15 mm NB PVC pipe with all necessary work specials saddle piece etc. all complete for Augmentation of sub-surface water based PWSS for Amritnagar Zone-II under RCFA Division-I PHE Dte. | 500/RCD-I | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 54.54 | 54.54 | 100 | 100
1094 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. , SM/12031 | Augmentation | Acceptance cum work order for Construction of restoration approach road in Amritnagar Zone-I for Augmentation of RCFA Part-II under RCFA Division-I PHE Dte. (Part-B) | 499/RCDI | 12/02/2024 | 30 | MACHINO TECHNO | 24.72 | 24.7 | 100 | 100
1095 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. , SM/12041 | Augmentation | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-15) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3357/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0 | 0 | 0
1096 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. , SM/12041 | Augmentation | Formal work order for Augmentation of RCFA Part-II Pipe Water Supply Scheme (Zone-15) with Construction of 450 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with under Jamuria Block, District Paschim Bardhaman. | 1843/RCD-I | 31/05/2023 | 365 | GITA CONSTRUCTION | 150.65 | 0 | 0 | 0
1097 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. , SM/12041 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 100 cum & allied work at Bagdiha under Augmentation of RCFA Part-II (Zone-15) under RCFA Division-I PHE Dte. | 2877/RCD-I | 06/10/2023 | 90 | M/S KALYANI ENTERPRISE | 18.69 | 0 | 0 | 0
1098 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. , SM/12041 | Augmentation | Material Requisition To Resource Division | 2940/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1099 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. , SM/12041 | Augmentation | Way leave track crossing proposal with application ID - ER-ASN-2024-WL-57 Payment of wayleave facility charges. | 273/24-25 | 05/09/2024 | 0 | EASTERN RAILWAY | 9.09 | 0 | 0 | 0
1100 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. , SM/12041 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-92 at Ukhra under Augmentation of RCFA Part-II (Zone-15) under RCFA Division-I PHE Dte | 48/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 16.46 | 0 | 0 | 0
1101 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. , SM/12041 | Augmentation | Restoration work for laying of 450 mm D.I. K9 pipeline under JJM work within the paved carriageway from Ch. 0.000 km to Ch. kmp at Right Side, Ch 03.006 km to Ch. 3.206 kmp at left side & ch. 4.570 km to Ch. 5.000 kmp at left side of Ukhra-Haripur Road under Asansol Division, PWD in the district of Paschim Bardhaman | 401/24-25 | 11/11/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 24.61 | 0 | 0 | 0
1102 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. , SM/12041 | Augmentation | Supplying, fitting, fixing and fabrication of sign board including printing and carriage to different area with necessary allied works in connection with Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Camp-02-Sign-Board-AE-II | 30/06/2023 | 20 | UNITED CONSTRUCTION | 17.51 | 15.83 | 90.41 | 70
1103 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. , SM/12041 | Augmentation | Acceptance cum work order for Allied work for bridge at Chalbalpur in connection with the laying distribution system for Amritnagar Zone-II under Augmentation of RCFA Part-II (Zone-15) under RCFA Division-I PHE Dte. | 2865/RCD-I | 06/10/2023 | 90 | MRITYUNJOY MUKHERJEE & CO. | 70.4 | 52.84 | 75.06 | 100
1104 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. , SM/12041 | Augmentation | Formal Work Order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-15) | 2299/RCD-I | 24/07/2023 | 892 | SWATI CORPORATION | 516.27 | 197.04 | 92.27 | 100
1105 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Material Requisition To Resource Division | 3126 | 09/12/2022 | 0 | Resource Division | 86.94 | 0 | 0 | 0
1106 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Formal work order for Laying of Distribution System to Accommodate FHTC and Providing FHTC including Supplying laying, fitting, fixing of 15 mm NB PVC (Schedule 80) 20 mm OD HDPE (PE 100, PN 6) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | 2455./RCD-I | 02/11/2022 | 180 | MACHINO TECHNO | 130.76 | 104.24 | 79.72 | 90
1107 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Detailed Route Survey, Design Drawing & DPR Preparation for Amritnagar Zone-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. (sL no. 01) | 500/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.04 | 4.04 | 100 | 0
1108 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Providing and Installation of Electro-Mechanical Equipments and allied Works at Damalia under Augmentation of Amritnagar Zone-I Water Supply Scheme, Block : Raniganj, Dist -Paschim Bardhaman. | 484/AMD | 22/02/2023 | 365 | ORIENTAL ENGINEERING CO. | 114.65 | 72.08 | 62.87 | 100
1109 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Acceptance cum Work Order for Pipe line crossing adopting trench less Technology (e.g. Jack Pushing method etc.) near Deshbandhu Park, Chittaranjan Road, Joadbari Rupnarayanpur from node no 921 to 924 RCFA Part-I PWSS within command area of Zone-VII under RCFA Division-I PHE Dte. | 494/RCD-I | 12/02/2024 | 15 | KONAR CONSTRUCTION | 6.55 | 6.55 | 100 | 100
1110 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at New Damalia Pump House under Amritnagar Zone-I, within RCFA Part-II Area Water Supply Scheme. | 1204/AMD | 07/08/2024 | 45 | M/S JIT ENTERPRISE | 4.09 | 3.95 | 100 | 100
1111 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Formal work order for laying of distribution system to accommodate FHTC and providing FHTC including supplying, laying, fitting, fixing of 15 mm NB PVC (schedule 80)/20 mm OD HDPE (PE100,PN6) pipe with all necessary specials, saddle piece etc. all complete at Egara, Amkula and part of Nimcha Mouza Part-B) for Augmnentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-I under RCFA Division I, PHE Dte.under RCFA Division I,PHE Dte. | 37/RCD I | 11/01/2023 | 760 | TARAPRASAD SARKAR | 164.7 | 43.33 | 26.31 | 50
1112 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Formal work order for laying of distribution system to accommodate FHTC and proving FHTC including supplying, laying,fitting, fixing of 15 mm NB PVC (schedule 80)/20 mm OD HDPE (PE100,PN6) pipe wth all necessary specials, saddle piece etc all complete at Murgasole mouza for augmentation of Sub surface Water Based Piped Water Supply Scheme for Amritnagar Zone-I under RCFA Div-I, PHE Dte. under RCFA Div-I, PHE Dte. | 35/RCD I | 11/01/2023 | 90 | DAS & CHAKRABORTY | 113.18 | 45.55 | 40.25 | 0
1113 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Formal work order for Construction of 900 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I, PHE Dte. in the District of Paschim Bardhaman. | 1902/RCD-I | 09/06/2023 | 245 | M/S SANTANU PALIT & CO. | 182.7 | 73.08 | 57.14 | 70
1114 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Acceptance cum Work Order for Balance work for laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte | 481/RCD-I | 12/02/2024 | 45 | M/S SINGH & KONAR CONSTRUCTION | 45.53 | 32.24 | 70.8 | 80
1115 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Acceptance cum Work Order for Balance work for Laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-B) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte. | 478/RCD-I | 12/02/2024 | 45 | TARAPRASAD SARKAR | 44.86 | 31.52 | 70.25 | 80
1116 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Acceptance cum Work Order for Additional work for laying of DI pipe under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | 473/RCD-I | 12/02/2024 | 15 | M/S SINGH & KONAR CONSTRUCTION | 8.65 | 2.84 | 32.78 | 80
1117 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Acceptance cum work order Additional work for supply and laying HDPE pipe instead of DI pipe for the work of laying distribution system under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte. | 501/RCD-I | 12/02/2024 | 45 | M/S SINGH & KONAR CONSTRUCTION | 30.11 | 15.98 | 53.06 | 50
1118 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Acceptance cum work order for Sinking of 4 (Four) nos. 200 mm dia river bed tube well in river Damodar including laying of collecting main (HDPE & MS) of Augmentation of Amritnagar Water Supply Scheme (Phase-I & II) under RCFA Division-I PHE Dte. 2nd Call | 2875/RCD-I | 07/11/2022 | 30 | NIYATI CONSTRUCTION | 24.5 | 17.68 | 100 | 0
1119 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Acceptance work order for sinking of 6 nos river bed 200 dia tube well including laying of collecting main for augmentation of sub surface water based piped water supply scheme for Amritnagar Zone-I within RCFA Part-II area under RCFA Div-I, PHE Dte. | 3272/RCDI | 20/12/2022 | 30 | M/S MONDAL CONSTRUCTION | 13.37 | 13.37 | 100 | 100
1120 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Acceptence cum work order for Dismantling & reconstruction of flooring of pump house, CWR and other allied works at H/W site of Tirat Colliery under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte | 2584/RCD-I | 07/09/2023 | 15 | MS KALYAN ENTERPRISE | 5.16 | 5.1 | 100 | 100
1121 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Acceptance cum work order for Emergency Sinking of 04 (Four) nos. 200 mm dia river bed tube well including collecting main for in the river Damodar of Amritnagar Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2575/RCD-I | 07/09/2023 | 323 | M/S UNITED CONSTRUCTION | 6.75 | 6.13 | 92.38 | 100
1122 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Laying of distribution system to accommodation FHTC and providing FHTC including supplying, laying, fitting fixing of 15mm NB PVC (schedule 80) /20 mm OD HDPE (PE ,PN6) pipe with all necessary specials.saddle piece etc all complete at Egara, Amkula and part of Nimcha mouza for Improvement of RCFA Part-II Water Supply Scheme under RCFA Div-I, PHE Dte. under RCFA Div-I, PHE Dte. | 36/RCD I | 11/01/2023 | 45 | M/S SINGH & KONAR CONSTRUCTION | 167.84 | 31.26 | 100 | 55
1123 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC , SM/13418 | Augmentation | Acceptance cum work order for Additional work for adopting trench less technology (e.g. Jack Pushing Method etc) at i) Opposite Amritnagar OHR, ii) near Nimcha Kata More, iii) near Mincha Rail gate and allied MS work, supply of valves, specials etc at Murgathole Mouza under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | 3421/RCD-1 | 24/11/2023 | 147 | DAS & CHAKRABORTY | 33.99 | 0 | 0 | 100
1124 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Acceptance cum formal order for the work of modernization of the existing Gopalpur Lab for NABL accreditation of Sub-district water testing lab at Kanksa of Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte | 87/DWSD | 27/01/2022 | 15 | BASANTI TRADERS | 4.39 | 4.12 | 93.83 | 100
1125 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Formal order for the work of Supplying & aligning of HDPE distribution pipe line and allied works including Functional House Holds Tap connectin (FHTC ) and connection providing to Jamdoba Mouza-40 and Telipara Mouza- JL-41 of Telipara block -Kanksa under TELIPARA piped W/s Scheme under DWSD, PHE Dte (SL-03) | 648/DWSD | 21/04/2022 | 25 | M/S SANTANU PALIT & CO. | 127.01 | 20.48 | 48.83 | 75
1126 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at DHOBARU mouza of Dhobaru piped W/s Scheme under DWSD, PHE Dte (Part-A ,B and C) (SL-01) | 774/DWSD | 17/05/2022 | 45 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 44.99 | 2.01 | 51.53 | 100
1127 | PASCHIM BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Telipara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3143/CMD | 29/11/2022 | 30 | M/S. SWAPAN BANERJEE | 9.56 | 9.22 | 96.47 | 100
1128 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Acceptance cum formal order for the work of Balance work for supplying laying and aligning of HDPE distribution pipe line and allied works including FHTC and connection providing to JAMDOBA mouzas JL-40 and Paschim Telipara mouzas JL-41 of Augmentation of Telipara W/s Scheme under DWSD under | 501/DWSD | 27/03/2023 | 60 | M/S SANTANU PALIT & CO. | 93.42 | 16.88 | 18.07 | 80
1129 | PASCHIM BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 2 at Telipara Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | 1576/CMD | 04/04/2023 | 30 | C.M. ENTERPRISE | 9.49 | 9.26 | 97.5 | 100
1130 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Balance work for installation of solar pumping machineries including solar pannel and other allied works for 6 Nos ICDS/AWC/School at Labnapara Bouripara,Pratabpur ICDS ,Jamgora Nichupara Bagdipara,Pratabpur Bus stands and pangar FP school ICDS and Kailashpur 52 ICDS under providng running water supply to ICDS/School ,HCF and other Public Ins of Kanksa and Durgapur-Faridpur Block under Retrofitting of Jemua Piped W/S Scheme. | 1059/DWSD | 12/07/2023 | 30 | JOY GURU ENTERPRISE | 19.4 | 0 | 0 | 0
1131 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Acceptance cum formal order for the work of Supplying aligning and laying of 150/250 mm dia MS pipe at Telipara under Augmentation of Telipara piped W/s Scheme under DWSD ,PHE Dte | 1560/DWSD | 20/09/2023 | 10 | M/S MONDAL ENTERPRISE | 3.55 | 0 | 0 | 0
1132 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Formal order for the work of Balance work for supplying laying and aligning of HDPe distribution pipe line and allied works including FHTC and connection providing to Raghunathpur mouzas JL-39 and Paschim Gangarampur mouzas JL-92 of Augmentation of Telipara W/s Scheme under DWSD under DWSD ,PHE Dte (SL-15) | 713/DWSD | 11/05/2023 | 60 | M/S PROCHESTA ENTERPRISE | 171.21 | 145.6 | 100 | 100
1133 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Acceptance cum formal order for the work of 1(One) No PWD road crossing at JAMDOBA under command area of Telipara distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Telipara piped W/s Scheme under DWSD ,PHE Dte (Part-C) | 1273/DWSD | 07/08/2023 | 15 | SK. ALIM | 8.74 | 8.74 | 100 | 100
1134 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Continuation order for the work of additional number of FHTC in connection with JJM Ichhapur(Mouza-91) with extension of branch pipe line of command area of Gourbazar-Ichhapur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte | 1631/DWSD | 18/11/2021 | 15 | SHWET BARANI | 3.99 | 0 | 0 | 100
1135 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Acceptance cum formal order for the work of Balance work for supplying laying and aligning of HDPE distribution pipeline and allied works including FHT C and connection providing to Jamdoba mouzaJLNo-40 andTelipara MouzaJL-41of Telipara W/s Scheme udner DWSD ,PHE Dte | 1089/DWSD. | 13/07/2023 | 45 | MAK CONSTRUCTION CO. | 93.52 | 90.71 | 100 | 100
1136 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Supplying aligning and laying of 150/250 mm dia MS pipe at Telipara under Augmentation of Telipara piped W/s Scheme under DWSD ,PHE Dte | 1559/DWSD | 20/09/2023 | 10 | M/S MONDAL ENTERPRISE | 3.55 | 1.01 | 100 | 100
1137 | PASCHIM BARDHAMAN | RCFA Division -I | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Acceptance cum work order for Allied work of laying distribution system, New FHTC and re connection of FHTC at Shibpur of Augmentation of Telipara PWSS under RCFA Division-I PHE Dte. | 2010/RCD-I | 11/07/2025 | 30 | M/S KALYANI ENTERPRISE | 18.97 | 0 | 0 | 0
1138 | PASCHIM BARDHAMAN | RCFA Division -I | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Acceptance cum work order for additional work of supplying ,laying and aligning of HDPE Distribution pipeline & allied works including functional household tap connection (FHTC) at Pathanpara command area for Augmentation of Ground Water Based Water Supply Scheme for Telipara under RCFA Division-I PHE Dte. | 1759/RCDI | 18/06/2025 | 166 | MAK CONSTRUCTION CO | 76.14 | 0 | 0 | 50
1139 | PASCHIM BARDHAMAN | RCFA Division -I | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16250 | Augmentation | Acceptance cum work order for Construction of Switch Room (5.4 m x 3.6 m) at Shibpur of Augmentation of Telipara PWSS under RCFA Division-I PHE Dte. | 2011/RCD-I | 11/07/2025 | 90 | MOUMITA ENTERPRISE | 6.73 | 0 | 0 | 0
1140 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Formal work order for creating separate zone for Adibasipara near WTP Panagarh, supplying, laying of 160 mm dia HDPE distribution pipe line and other allied works at Anandapur, Repairing of existing cement concrete road restoration and other allied works (Part- A & B), at Bistupur and Dannay. Mohal & Sinking of 2 Nos 300 X 200 MM dia RBT tube well at Silampur under Augmentation of Kanksha (Zone-I & II), Augmentation of RCFA Part-III (Zone-II), Augmentation of ground water based water supply scheme Napara under RCFA Division-I, PHE Dte. | 662/RCD-I | 29/02/2024 | 90 | SARASWATI ENTERPRISE | 119.89 | 105.01 | 87.59 | 100
1141 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Trial run and special Maintenance of Rising main and Distribution system with operating of valve within command area under Augmentation of Telipara PWSS, JJM under RCFA Division-I PHE Dte. 6 (Six) Months | 684_RCD-1 | 29/02/2024 | 184 | MALLICK ENTERPRISE | 1.64 | 0 | 0 | 0
1142 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Addition work for Laying of HDPE pipeine and Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission at of Arra Mouza JL No 89 Under command area of Augumentation of Napara piped W/S Scheme,under D.W.S.D., P.H.E. Dte. | 327/DWSD | 20/02/2023 | 35 | DARPAN DAS & CO | 70.42 | 66.42 | 94.33 | 75
1143 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Acceptance cum formal order for the work of Additional pipe line work with concrete cutting at Shilampur mouza for providing FHTC in connection with Jal Jeevan mission for Shilampur Mouza(JL90) under Augmentation of Napara Piped W/s Scheme at Kanksa block under DWSD, PHE Dte (SL-18) | 1014/DWSD | 12/07/2023 | 20 | MUKHERJEE ENTERPRISE | 96.46 | 0 | 0 | 0
1144 | PASCHIM BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Napara Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | 2517/CMD | 02/06/2023 | 30 | SOUNAK ENTERPRISE | 23.32 | 22.49 | 100 | 100
1145 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Formal order for the work of Balance work of supplying and laying of HDPE distribution system with construction of 02 Nos Pump house ,Construction of 350 M3 OHR of 20 mtr staging height as per Deptt drawing laying aligning of Rising main and providing of FHTC connection of all mouzas under command area of Augmentation of Napara piped W/s Scheme under DWSD ,PHE Dte . | 712/DWSD | 11/05/2023 | 60 | SK. ALIM | 307.16 | 264.06 | 100 | 100
1146 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Sinking of 2 Nos tube well 300 mm X 200 mm tube well of 210 mtrs depth by Direct rotary rig method using UPVC Piped CD and UPVC Deep well screen RDS filter at Napara site under Block-Kanksa under Augmentation of Napara piped W/s Scheme under DWD ,PHE Dte | 1301/DWSD | 07/08/2023 | 30 | SK. ALIM | 31.47 | 19.19 | 100 | 100
1147 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Acceptance cum formal order for the work of construction of pump house cum chlorine room at Silampur pump house No-I H/W site for of Kanksa (Zone-I) Under Augmentation of Napara P piped W/s Scheme under DWSD,PHE Dt | 1279_DWSD | 07/08/2023 | 45 | MUKHERJEE ENTERPRISE | 6.41 | 6.41 | 100 | 100
1148 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Quotation as per WBSEDCL Procedure-A (2010) ON Turn key/ Full deposit basis for the site of Napara Sukhna Pump House no-4, under Kanksa Block under Panagarh CCC supply office | BP-2024-25-13 | 17/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.77 | 0 | 0 | 0
1149 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Acceptance cum work order for Construction of Separate Zone at Sukna with Boundary wall, Pump House & other allied works of Augmentation of ground water based water supply scheme for Napara under RCFA Division-I PHE Dte. | 2625/RCD-I | 14/11/2024 | 137 | UNITED CONSTRUCTION | 27.73 | 9.41 | 33.93 | 60
1150 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 500 cum & allied work at Pansuili Head Works Site under Augmentation of Ground Water Based Water Supply Scheme for Napara W/S Scheme under RCFA Division-I PHE Dte | 2851/RCD-I | 04/12/2024 | 362 | BABA LOKNATH ENTERPRISE | 63.91 | 5.82 | 9.1 | 40
1151 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 (Dhobi Ghat) & TUBE WELL NO-4 (Sukna) AT NAPARA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | 1816/AMD | 29/10/2024 | 214 | SINHA ELECTRICALS | 25.96 | 0 | 0 | 100
1152 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Acceptance cum work order for Construction of Separate Zone at Dhobaghata with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Napara PWSS under RCFA Division-I PHE Dte. | 2848/RCD-I | 04/12/2024 | 309 | UNITED CONSTRUCTION | 54.09 | 0 | 0 | 60
1153 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA , SM/15657 | Augmentation | Acceptance cum work order for Construction of RCC Conduit for crossing of HDPE Rising Main across the Kunur river at Jemua Augmentation of Ground Water Based Water Supply Scheme for Napara under RCFA Division-I PHE Dte. | 2542/RCD-I | 29/10/2024 | 90 | ASHA CONSTRUCTION | 64.49 | 0 | 0 | 50
1154 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09063 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Gourbazar Village, Block-Barabani under Gourbazar Water supply scheme under RCFA Division-I, P.H.E. Dte. | 1865/RCD-I | 28/10/2021 | 30 | M/S S.K. ENTERPRISE | 13.17 | 12.21 | 100 | 0
1155 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09063 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Putulia (Part), Block-Barabani under Gourbazar Water supply scheme under RCFA Division-I, P.H.E. Dte. | 1866/RCD-I | 28/10/2021 | 30 | VISUVIOUS | 12.85 | 10.95 | 100 | 0
1156 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09063 | Retrofitting | Extension of different dia HDPE pipe line for providing FHTC at Putulia (Part), Kharboni, Jamjuri and allied villages under Gourbazar W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | 1437/RCD I | 27/06/2022 | 45 | VISUVIOUS | 2.75 | 0 | 0 | 0
1157 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09063 | Retrofitting | Extension of different dia HDPE pipe line for providing FHTC at Gourbazar, Bindudihi, Hosenpara villages under Gourbazar W/S Scheme under RCFA Division-I PHE Dte. (Sl NO. 05) | 1436/RCD I | 27/06/2022 | 45 | M/S S.K. ENTERPRISE | 4.97 | 4.48 | 100 | 0
1158 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09063 | Retrofitting | Material Requisition To Resource Division | 437/RCD-I | 21/02/2022 | 0 | Resource Division | 2.75 | 0 | 0 | 0
1159 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09063 | Retrofitting | Installation of Jio Fiber connection for Six months under RCFA Division-I PHE Dte. | 153/24-25 | 19/07/2024 | 0 | MUKHERJEE TRADERS | 0.07 | 0 | 0 | 0
1160 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. , SM/09064 | Retrofitting | Acceptance cum work order for Supply and delivery of C.I. Sluice valve and D.I Specials under Improvement of RCFA part-I Piped water Supply Scheme under RCFA Division-I PHE Dte. | 1729/RCD-1 | 08/05/2023 | 10 | SSPR VALVE MANUFACTURING PVT LTD | 45.31 | 45.31 | 100 | 100
1161 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. , SM/09064 | Retrofitting | Acceptance cum work order for Requirement of different type water regulating apparatus including water leakage protection apparatus etc. for Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | 1730/RCD-1 | 08/05/2023 | 10 | MAKALI ENGINEERING CORPORATION | 45.99 | 45.99 | 100 | 0
1162 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. , SM/09064 | Retrofitting | Acceptance cum work order Construction of stand post on emergency basis at Rupnarayanpur, Rangamati area of Rupnarayanpur Zone under 4 Nos. retrofitting PWSS under RCFA Division-I PHE Dte. | 1266/RCD-1 | 27/03/2023 | 15 | B.B. CONSTRUCTION | 2.8 | 2.78 | 99.62 | 0
1163 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. , SM/09064 | Retrofitting | Acceptance cum work order for Additional work for laying of 450 mm dia distribution main under Lalganj Bridge by concrete conduit and allied MS work in connection to distribution network of Zone-XI (Part-1) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2237/RCD-1 | 17/07/2023 | 30 | R B ENTERPRISE | 16.06 | 13.45 | 100 | 100
1164 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. , SM/09064 | Retrofitting | Acceptance cum work order Additional work for laying & pushing of 600 to 1000 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) and MS pipe including supply of collar and allied work at Ethora Nuni more Panchgachiya and Lalganj more in connection to rising main Part-B under Improvement of RCFA Part-I (Zone-11, Part-9) PWSS under RCFA Division-I PHE Dte | 2224/RCD-I | 17/07/2023 | 30 | M/S MONDAL ENTERPRISE | 30.17 | 25.6 | 100 | 100
1165 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. , SM/09064 | Retrofitting | Acceptance cum work order for Route Survey and Preparation of DPR for Augmentation of Churulia Piped Water Supply Scheme, Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block., District-Paschim Bardhaman. | 3373/RCD-1 | 21/11/2023 | 15 | APEX ENGINEERING | 3.61 | 3.61 | 100 | 100
1166 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Acceptance cum formal order for the work of Construction of Guard room cum rest shed at Kanksa Ijjatganj 2nd Pump house site of Augmentation of Kaksa (Zone-II) /Part-C) piped W/S Scheme under DWSD,PHE Dte (SL-09) | 785/DWSD | 18/05/2022 | 15 | BASANTI TRADERS | 4.99 | 4.05 | 100 | 0
1167 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Augmentation of Kanksa [Zone-II / C ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman | 978/CMD | 14/06/2022 | 30 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 8.94 | 8.61 | 100 | 0
1168 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Augmentation of Kanksa [Zone-II / C ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman | 735/CMD | 29/04/2022 | 30 | STANDARD ELECTRICALS | 9.22 | 8.99 | 100 | 0
1169 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Augmentation of Kanksa [Zone-II / C ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman | 979/CMD | 14/06/2022 | 30 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 8.94 | 8.67 | 100 | 0
1170 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Quotation for Kanksa Zone-II/Part-C Pump house no -03 | BP-2022-23-99 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.33 | 0 | 0 | 0
1171 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Quotation for Kanksa Zone-II/Part-C Pump house no -02 | BP-2022-23-98 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.33 | 0 | 0 | 0
1172 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Quotation for Kanksa Zone-II/Part-C Pump house no -01 | BP-2022-23-97 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.43 | 0 | 0 | 0
1173 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Formal order for the work of laying of distribution system and providing FHTC including reconnection of exiting FHTC from AC pipe line to newly laid different dia HDPE pipe line for Augmentation of Kanksa (Zone-II/Part-C) piped W/S Scheme under DWSD ,PHE Dte (SL-05) | 1161/DWSD | 01/08/2022 | 4 | BRINDABAN KONAR | 216.66 | 187.07 | 100 | 80
1174 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Acceptance order for the work of Laying and aligning rising main pipe line supplying of DI specials ,valves and allied works at Akandara under command area of Augmentation of Kanksa (Zone-II/C)(Part-B) piped W/s Scheme under DWSD ,PHE Dte. | 298/DWSD | 20/02/2023 | 30 | MAK CONSTRUCTION CO. | 92.36 | 91.71 | 99.29 | 0
1175 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Repairing and renovation of pump house with sanitary arrangement as well as boundary wall at H/W site (Ijjatganj OHR) of Augmentation of Kaksa (Zone-II/Pt-C) piped W/s Scheme | 1198/DWSD | 27/07/2023 | 30 | MAITO MAA ENTERPRISE | 14.93 | 0 | 0 | 0
1176 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Acceptance cum formal order for the work of Construction of boundary wall at Kanksa (Zone-II & Ph-I W/s Scheme pump house No-II at Ijjatganj under DWSD ,PHE Dte (SL-04) | 186/DWSD | 04/02/2021 | 45 | M/S BADAL GHOSH | 4.92 | 4.68 | 100 | 0
1177 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Formal order for the work of Details route survey, drawing design of distribution network & preparation of estimates and DPR in connection with the JJM (FHTC) of Augmentation of Kanksa (Zone-II) piped W/S Scheme DWSD,PHE Dte.(SL-05) | 1601/DWSD | 12/11/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 19.55 | 19.55 | 100 | 0
1178 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Formal order for the work of Additional work for providing FHTC in connection with JJM for Kanksa mouzza (JL-89) under command area of Kanksa (Zone-II) Ph-II W/s Scheme at Kanksa block under DWSD ,PHE Dte (SL-03) | 199/DWSD | 16/02/2022 | 15 | GITA CONSTRUCTION | 9.72 | 9.01 | 100 | 0
1179 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Formal order for the work of Additional FHTC in connection with JJM for Prayagpur (CT) mouza (JL-88) under command area of Kanksa (Zone-II)(Ph-II) W/S Scheme at Kanksa block under DWSD PHE Dte . | 1766/DWSD | 16/12/2021 | 30 | B. T. M. CONCERN | 19.37 | 19.61 | 100 | 0
1180 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Acceptance cum formal order for the work of Providing water supply to Birudiha High school under Kanksa block covered by Kanksa (Zone-II) having electricity but uncovered by PWSS under DWSD, PHE Dte (SL-26) | 120/DWSD | 01/02/2022 | 20 | BASANTI TRADERS | 2.11 | 0 | 0 | 0
1181 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Continuation order for the work of supplying fitting fixing and installation of Sluice Valve for O & Mtc of Kanksa (Zone-II/II) piped W/s Scheme of command areas of Panaghar ,Prayagpur mouza under DWSD, PHE Dte | 682/DWSD | 27/04/2022 | 15 | TARA CONSTRUCTION | 4.94 | 0 | 0 | 0
1182 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Acceptance cum formal order Additional work for providing FHTC tap connection with JJM at Kanksa mouza-89 and its adjoing are a under command area of Augmentation of Kanksa Zone-II/C W/s Scheme at Kanksa block under DWSD ,PHE Dte (SL-04) | 1024/DWSD | 04/07/2022 | 10 | QUICK PAL SUPPLIERS | 4.98 | 4.98 | 100 | 0
1183 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Acceptance cum formal order for the work of Repairing of MS structural and supplying hoisting 2000 Liters PVC water storage tank and others allied works at Kanksa of Augmentation of Kanksa (Zone-II/C) W/s Scheme under DWSD,PHE Dte (SL-07) | 1062/DWSD | 08/07/2022 | 25 | SWATI CORPORATION | 3.53 | 3.24 | 100 | 100
1184 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Formal-Order for the work of Laying and aligning of distribution network of command area of Kanksa (Zone-II/C) and other allied works under Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme | 301/DWSD | 20/02/2023 | 20 | BABA LOKENATH ENTERPRISE | 16.09 | 16.09 | 100 | 0
1185 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Acceptance cum formal order for the work of Sinking of 06 Nos 300X200 mm dia Tube well with 210 mtr Depth by DR rig method using UPVC pipe (CD and UPVC deep well screen (RDS) at Kanksa (Zone-II) Part-B,C tube well site of Augmentation of Kanksa Zone-II(Part-B & C) piped W/s Scheme under DWSD ,PHE Dte (SL-02) | 254/DWSD | 15/02/2023 | 60 | JOY GURU ENTERPRISE | 94.05 | 46.1 | 100 | 0
1186 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Material Requisition To Resource Division | 328/DWSD | 15/03/2022 | 0 | Resource Division | 6.86 | 0 | 0 | 0
1187 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Replacement of damaged PCC pole with allied work. | BP-2023-24-24 | 17/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.69 | 0 | 0 | 0
1188 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Acceptance cum formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI specials ,valves and allied work at Kanchanpur and Kanksa under command area of Augmentation of Kanksa Zone-II/C piped W/s Scheme under DWSD ,PHE Dte | 677/DWSD | 03/05/2023 | 673 | JOY GURU ENTERPRISE | 29.76 | 28.62 | 96.16 | 100
1189 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangement at Kanchanpur of Kanksa Block under Augmentation of Kanksa (Zone-II) (Part-C) piped W/S Scheme under DWSD,PHE Dte | 1293/DWSD | 07/08/2023 | 45 | MAJI DEVELOPERS | 6.09 | 0 | 0 | 100
1190 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied works at Pump House No-01 under Kanksa Zone-II/C (Madhabmath) Water Supply Scheme, Block- Kanksa, Dist.- Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | 1808/AMD | 29/10/2024 | 30 | SUDIKSHA CONSTRUCTION | 2.96 | 0 | 0 | 0
1191 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Acceptance cum work order for Trial run and special Maintenance of Rising main and Distribution system with operating of valve within command area under Augmentation of Kanksa Zone-II (Part-D) PWSS, JJM under RCFA Division-I PHE Dte. 6 (Six) Months | 688/RCD-1 | 29/02/2024 | 184 | AMARANJALI CONSTRUCTION | 1.79 | 0 | 0 | 0
1192 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Acceptance cum formal order for the work of construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangemnt at Kanksa of Kanksa Block under Augmentation of Kanksa (Zone-II) (Part-C) piped W/S Scheme under DWSD,PHE Dte | 1277/DWSD | 07/08/2023 | 45 | PRADIP CHOUDHARY | 5.83 | 0 | 0 | 100
1193 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | 1(One) No PWD road crossing SH-34 at Mini bazar more under command area of Kanksa Zone-II/Pt-C distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Kanksa Zone-II/Part-C piped W/s Scheme under DWSD ,PHE Dte | 1286/DWSD | 07/08/2023 | 633 | MACHINO TECHNO | 10.92 | 0 | 0 | 100
1194 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Acceptance cum formal order for the work of 1(One) No PWD road crossing SH-34 at kanksa underpass under command area of Kanksa Zone-II/Pt-C distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Kanksa Zone-II/Part-C piped W/s Scheme under DWSD ,PHE Dte | 1274/DWSD | 07/08/2023 | 633 | MRITYUNJOY MUKHERJEE AND CO | 12.05 | 0 | 0 | 100
1195 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10209 | Augmentation | Acceptance cum work order for Separate connection for Ijjatgunj OHR Kanksa Zone-II (Part-C) under RCFA Division - I PHE Dte. | 2245/RCD-I | 11/09/2024 | 30 | COMPUTER MEDIA | 6.62 | 0 | 0 | 70
1196 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Providing FHTC of different ICDS centre & extension of HDPE line under Jamuria Block of different Water Supply Scheme under RCFA Division-I PHE Dte.(sl no 01) | 1978/RCD I | 24/08/2022 | 15 | MS KALYAN ENTERPRISE | 4.98 | 4.94 | 100 | 0
1197 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Baidyanathpur GP under Pandabeswar Block under RCFA Div-I PHE Dte. | 2851/RCDI | 02/11/2022 | 15 | SOMNATH SAMANTA | 2.31 | 0 | 0 | 0
1198 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Nabagram GP under Pandabeswar Block under RCFA Div-I PHE Dte. | 2850/RCDI | 02/11/2022 | 15 | SOMNATH GOSWAMI | 5.07 | 0 | 0 | 0
1199 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Bahula GP under Pandabeswar Block under RCFA Div-I PHE Dte. | 2852/RCDI | 02/11/2022 | 15 | SIMA ENTERPRISE | 10.22 | 0 | 0 | 0
1200 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Kendra GP under Pandabeswar Block under RCFA Div-I PHE Dte. | 2849/RCD I | 02/11/2022 | 15 | GOPAL CONSTRUCTION | 4.74 | 1.29 | 27.17 | 0
1201 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Acceptance cum work order for Water Supply Connection to School and Anganwari through Retrofitting from existing near by PWSS under Barabani Block under RCFA Division-I PHE Dte. | 373/RCDI | 30/01/2023 | 30 | SRI KRISHNA ENTERPRISE | 12.66 | 0 | 0 | 0
1202 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Acceptance cum work order for Water Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Harirpur GP under Pandabeswar Block under RCFA Division-I PHE Dte.( Sl No.-13) | 1157/ RCD I | 24/03/2023 | 30 | SUKHENDU MAJUMDAR | 3.98 | 0 | 0 | 0
1203 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Acceptance cum work order Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Baidyanathpur GP under Pandabeswar Block under RCFA Division-I PHE Dte. (Sl No. 16) | 1160/RCD-I | 24/03/2023 | 30 | M/S KALYANI ENTERPRISE | 1.99 | 0 | 0 | 0
1204 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Acceptance cum work order for Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Khandra GP under Ondal Block under RCFA Division-I PHE Dte. (Sl. No. 11) | 1155/ RCD I | 24/03/2023 | 30 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 4.13 | 3.31 | 80.04 | 80
1205 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Acceptance cum work order for Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Dakhin Khanda GP under Ondal Block under RCFA Division-I PHE Dte. (Sl. No. 12) | 1156/ RCD I | 24/03/2023 | 30 | GOPAL CONSTRUCTION | 3.66 | 0 | 0 | 0
1206 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Acceptance cum Work Order for Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Chora GP under Pandabeswar Block under RCFA Division-I PHE Dte. (Sl No. 10) | 1154/RCD-1 | 24/03/2023 | 30 | JUBILEE CONSTRUCTION | 4.91 | 0 | 0 | 0
1207 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Preparation of DPR for Augumentation of Itapara Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 02) | 2346/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 2.82 | 0 | 0 | 0
1208 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Water supply connection to School and Anganwari through Retrofitting from existing near by PWSS at Ukhra Area under Andal Block under RCFA Div-I PHE Dte. (Sl No. 19) | 231/RCD I | 01/02/2022 | 10 | RANJIB GHATAK | 4.5 | 3.61 | 100 | 0
1209 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Laying of different dia UPVC pipe line and connection to 4 nos ICDS at Dhandadihi Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 12) | 1989/RCD I | 24/08/2022 | 15 | MD. JAWED KHAN | 3.03 | 0 | 0 | 0
1210 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Aligning laying of pipe line connection including construction of platform of different ICDS Center & extension of HDPE line under Raniganj Block of different W/S Scheme under RCFA Division-I PHE Dte. (Part-B) (Sl No. 07) | 1984/RCD I | 24/08/2022 | 15 | MS KALYAN ENTERPRISE | 3.7 | 3.66 | 100 | 0
1211 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Aligning laying of pipe line connection including construction of platform of different ICDS Center & extension of HDPE line under Raniganj Block of different W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | 1983/RCD I | 24/08/2022 | 15 | MS KALYAN ENTERPRISE | 3.51 | 3.51 | 100 | 0
1212 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Dakshin Khanda GP under Ondal Block under RCFA Div-I PHE Dte. | 2854/RCD I | 02/11/2022 | 15 | DAS & SARKAR ENTERPRISE | 4.27 | 1.61 | 100 | 0
1213 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Supplying, laying and aligning distribution branch and pipe line connection to ICDS centre under Egara GP under RCFA Division-I PHE Dte. (Raniganj Block)(Sl No. 11) | 2228/RCD-1 | 15/09/2022 | 15 | DIP CONSTRUCTION | 4.9 | 4.9 | 100 | 0
1214 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Water supply connection to School and Anganwari through Retrofitting from existing near by PWSS at Baidyanathpur Area under Pandabeswar Block under RCFA Div-I PHE Dte. (Sl No. 16) | 228/RCD I | 01/02/2022 | 7 | SOMNATH SAMANTA | 2.07 | 2.05 | 100 | 0
1215 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Khandra GP under Ondal Block under RCFA Div-I PHE Dte. | 2855/RCD I | 02/11/2022 | 15 | M/S MONDAL CONSTRUCTION | 4.81 | 1.76 | 36.48 | 80
1216 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Acceptance cum work order of Water Supply Connection to School and Anganwari through Retrofitting from existing nearby PWSS at Samdi, Kallya, Jitpur-Uttarrampur, Fulberia Bolkunda GP under Salanpur Block under RCFA Division-I PHE Dte. | 488/RCD I | 03/02/2023 | 30 | SUBHADEEP DAS | 22.11 | 14.86 | 100 | 100
1217 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Providing FHTC of different ICDS centre & extension of HDPE line under Raniganj Block of different Water Supply Scheme under RCFA Division-I PHE Dte.(Sl no 02) | 1979/RCDI | 24/08/2022 | 15 | MS KALYAN ENTERPRISE | 4.76 | 3.84 | 80.68 | 0
1218 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Chhora GP under Pandabeswar Block under RCFA Div-I PHE Dte. | 2847/RCD I | 02/11/2022 | 15 | DHRUBA ENTERPRISE | 5.69 | 4.22 | 74.09 | 0
1219 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Haripur GP under Pandabeswar Block under RCFA Div-I PHE Dte. | 2848/RCDI | 02/11/2022 | 15 | N.R. CONSTRUCTION | 4.61 | 0 | 0 | 100
1220 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Water Supply Connection to School and Anganwari through Retrofitting from existing near by PWSS at Ondal, Srirampur & Madanpur GP under Ondal Block under RCFA Div-I PHE Dte. | 2853/RCD I | 02/11/2022 | 1064 | MD SARFARAZ ALAM | 14.61 | 9.16 | 62.66 | 80
1221 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Acceptance cum work order for Providing FHTC different ICDS Centre & extension of HDPE line under Jamuria Block of different Water Supply Scheme under RCFA Division-I PHE Dte. | 1956/RCD-I | 24/08/2022 | 45 | D.S.C. CONCERN | 14.66 | 8.8 | 100 | 100
1222 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Water Supply connection to School and Anganwari through retrofitting from existing nearby PWSS Ondal, Srirampur, Madanpur GP under Ondal Block under RCFA Division-I PHE Dte. | 3291/RCDI | 20/12/2022 | 30 | ALOKESH BANERJEE | 12.6 | 12.49 | 100 | 100
1223 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Acceptance cum work order for Providing FHTC of different ICDS Centre & Extension of HDPE & PVC line under Raniganj Block of different Water Supply Scheme under RCFA Division-I PHE Dte. | 394/RCD I | 30/01/2023 | 30 | MS KALYAN ENTERPRISE | 16.68 | 16.64 | 100 | 100
1224 | PASCHIM BARDHAMAN | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. , SM/10287 | School | Acceptance cum work order for Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Nabagram GP under Pandabeswar Block under RCFA Division-I PHE Dte. (Sl. No. 15) | 1159/RCDI | 24/03/2023 | 30 | M/S SOUMYADWIP ENTERPRISE | 4.38 | 4.3 | 100 | 100
1225 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Formal order for the work of Supplying ,laying and aligning of HDPE distribution pipe line and allied works at Railpar Saradapally Mouza under command area of Augmentation of Kanksa (Zone-II/D) under DWSD ,PHE Dte (Part-D) (SL-02) | 187/DWSD | 15/02/2022 | 30 | SAIKAT RAY | 85.77 | 87.48 | 100 | 0
1226 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Formal order for the work of Supplying ,laying and aligning of HDPE distribution pipe line and allied works at Railpar Saradapally Mouza under command area of Augmentation of Kanksa (Zone-II/D) under DWSD ,PHE Dte (Part-B) | 201/DWSD | 17/02/2022 | 30 | AMARANJALI CONSTRUCTION | 94.15 | 75.19 | 79.87 | 0
1227 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal order for the work of Construction of pump house cum chlorine room at Railpar Sarada Pally H/W site pump house No-3 tube well No-03(for Augmentation of Kanksa (Zone-II/D) pipe W/s Scheme under DWSD ,PHE Dte (SL-03) | 242/DWSD | 25/02/2022 | 45 | CHATTERJEE CONSTRUCTION | 4.89 | 3.76 | 76.86 | 0
1228 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Formal order for the work of Providing functional house hold tap connection (FHTC) in connection with JJM at Railpar Nepali Para of Prayagpur Mouza(JL-89) under command area of Augmentation of Kanksa (Zone-II /P-D) piped W/s Scheme (SL-01) | 747/DWSD | 10/05/2022 | 10 | MAK CONSTRUCTION CO. | 37.33 | 25.1 | 67.25 | 0
1229 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal order for the work of Additional work for supplying laying and aligning of HDPE distribution pipe line and allied works at Railpar Sarada Pally of Prayagpur Mouza under command area of Augmentation of Kanksa (Zone-II/D) piped W/S Scheme under DWSD,PHE Dte (Part-C) (SL-05) | 819/DWSD | 23/05/2022 | 30 | MD AAMIR KHAN | 76.63 | 76.81 | 100 | 0
1230 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal order for the work of Additional FHTC work at Kanksa block and supplying laying and aligning of HDPE distribution pipe line and allied works at Railpar Sarada Pally and Prayagpur Mouza under command area of Augmentation of Kanksa (Zone-II/Part-D) Piped W/s Scheme under DWSD ,PHE Dte. (SL-04) | 816/DWSD | 21/05/2022 | 30 | SAIKAT RAY | 80.17 | 76.74 | 95.73 | 0
1231 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Formal order for the work of Supplying, laying and aligning of 160 mm dia HDPE distribution pipe line and allied works at Railpar Saradapally of Prayagpur mouza under command areas under Augmentation of Kanksa (Zone-II/Part-D) piped W/s Scheme under DWSD, PHE Dte (SL-05) | 752/DWSD | 11/05/2022 | 15 | SAIKAT RAY | 16.19 | 16.06 | 99.25 | 0
1232 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Formal order for the work of Sinking of 1No(300X200 mm) dia tube well 210 mtr deep by direct rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at Tube well No-02 site at Railpar Saradapally near DVC branch canal for Augmentation of ground water base Kanksa (Zone-II/D) piped W/s Scheme under DWSD ,PHE Dte. | 198/DWSD | 16/02/2022 | 30 | RANJIB GHATAK | 10.3 | 10.26 | 100 | 0
1233 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Formal order for the work of Sinking of 1No(300X200 mm) dia tube well 210 mtr deep by direct rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at Tube well No-01 site at Railpar Saradapally near DVC branch canal for Augmentation of ground water base Kanksa (Zone-II/D) piped W/s Scheme under DWSD ,PHE Dte. | 202/DWSD | 17/02/2022 | 30 | JOY GURU ENTERPRISE | 10.3 | 10.26 | 100 | 0
1234 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Formal order for the work Sinking of 1No(300X200 mm) dia tube well 210 mtr deep by direct rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at Tube well No-03 site at Railpar Saradapally near DVC branch canal for Augmentation of ground water base Kanksa (Zone-II/D) piped W/s Scheme under DWSD ,PHE Dte. | 188/DWSD | 15/02/2022 | 30 | AHS R INFRA PRIVATE LIMITED | 10.3 | 10.26 | 100 | 0
1235 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and allied works at Rail par Sarada Pally of Prayagpur Mouza under command area of Augmentation of Kanksa (Zone-II/D) W/S Scheme under DWSD ,PHE Dte (Part-C)(SL-01) | 185/DWSD | 11/02/2022 | 30 | MD AAMIR KHAN | 80.93 | 80.83 | 100 | 0
1236 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Augmentation of Kanksa [Zone-II / D ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim -Bardhaman. | 732/CMD | 29/04/2022 | 30 | JAGANNATH ENTERPRISE | 9.67 | 9.44 | 100 | 0
1237 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal order for the work of Additional bore for sinking of 01 Nos (300X200 mm dia) tube well of 210 mtr deep by DR drilling method using PVC pipe and fiber glass reinforced epoxy resin slotted at Tube well No-I at Railpar Sarod Pally near DVC branch canal under Augmentation of Kanksa (Zone-II/Part-D) piped W/s Scheme under DWSD ,PHE Dte.(SL-01) | 376/DWSD | 24/03/2022 | 7 | JOY GURU ENTERPRISE | 4.4 | 2.92 | 100 | 0
1238 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal order for the work of Additional bore for sinking of 01 Nos (300X200 mm dia) tube well of 210 mtr deep by DR drilling method using PVC pipe and fiber glass reinforced epoxy resin slotted at Tube well No-II at Railpar Sarada Pally near DVC branch canal under Augmentation of Kanksa (Zone-II/Part-D) piped W/s Scheme under DWSD ,PHE Dte. (SL-02) | 377/DWSD | 24/03/2022 | 7 | RANJIB GHATAK | 4.39 | 3.78 | 100 | 0
1239 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal order for the work of Additional bore for sinking of 01 Nos (300X200 mm dia) tube well of 210 mtr deep by DR drilling method using PVC pipe and fiber glass reinforced epoxy resin slotted at Tube well No-III at Railpar Sarada Pally near DVC branch canal under Augmentation of Kanksa (Zone-II/Part-D) piped W/s Scheme under DWSD ,PHE Dte.(SL-03) | 378/DWSD | 24/03/2022 | 7 | AHS R INFRA PRIVATE LIMITED | 4.4 | 3.29 | 100 | 0
1240 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Continuation order for the work of soil investigation for demining the safe bearing capacity and other relevant parameters of soil for the work of construction of RCC Elevated at Sarada Pally reservoir site of Augmentation of Kaksa Zone-II/D piped W/s Scheme under DWSD ,.PHE Dte | 287/DWSD | 08/03/2022 | 25 | MABCO CONSULTANT | 1.2 | 1.2 | 100 | 0
1241 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Augmentation of Kanksa [Zone-II / D ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman | 912/CMD | 31/05/2022 | 30 | DELTA ENGINEERING ENTERPRISE | 9.88 | 9.72 | 100 | 0
1242 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Formal order for the work of Making of concrete RCC pier and supplying laying of MS water carrier pipe and 600 mm dia NP 3 Hume pipe with crossing of road and culvert of distribution system Kanksa (Zone--II/D) at Railpar Sarada Pally of Prayagpur mouza under command area of Augmentation of Kanksa (Zone-II/D W/s Scheme under DWSD ,PHE Dte (Part-C) | 1159/DWSD | 01/08/2022 | 30 | MD AAMIR KHAN | 44.11 | 44.28 | 100 | 0
1243 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal order for the work of Additional work for providing FHTC tap connection with JJM at Panagarh mouza-88 and its adjoing area under command area of Augmentation of Kanksa (Zone-II/Part-D) piped W/s Scheme under DWSD, PHE Dte (SL-06) | 1026/DWSD | 04/07/2022 | 10 | QUICK PAL SUPPLIERS | 4.89 | 4.89 | 100 | 0
1244 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal order for the work of Sinking of 1 Nos tube well 300 mm X 200 mm tube well 150 mtr depth by Direct rotary Rig method using PVC pipe and fiber galss reinforced epoxy resin slotted at existing tube well no-02 at near Railine under Augmentation of Kanksa (Z-II/Part-D) piped W/s Scheme under DWSD ,PHE Dte (SL-13) | 1262/DWSD | 25/08/2022 | 15 | JOY GURU ENTERPRISE | 10.99 | 10.48 | 100 | 0
1245 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Augmentation of Kanksa [Zone-II / D ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim -Bardhaman. | 733/CMD | 29/04/2022 | 30 | CHATTERJEE ENTERPRISE | 9.65 | 9.4 | 100 | 0
1246 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Formal for the work of Extension of pipe line from exisitng pipe line of Kanksa (Zone-II) (Ph-II) W/S scheme at Panagarh Bazar and east canal par in Kanksa block to providing FHTC at Kanksa mouza(JL-89) under DWSD PHE Dte | 1773/DWSD | 20/12/2021 | 30 | M/S PIONEER CONSTRUCTION | 13.23 | 13.02 | 100 | 0
1247 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Quotation for Kanksa Zone-II/Part-D Pump house no -03 | BP-2022-23-102 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.4 | 0 | 0 | 0
1248 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Quotation for Kanksa Zone-II/Part-D Pump house no -01 | BP-2022-23-100 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.77 | 0 | 0 | 0
1249 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Quotation for Kanksa Zone-II/Part-D Pump house no -02 | BP-2022-23-101 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.4 | 0 | 0 | 0
1250 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-B) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-03) | 1433/DWSD | 28/12/2020 | 60 | SUJAY KUMAR RAY | 42.78 | 39.52 | 100 | 0
1251 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI specials ,valves and allied work under command area of Kanksa under Augmentation of Kanksa (Zone-II/Part-D) piped W/s Scheme under DWSD, PHE Dte (SL-04) | 751/DWSD | 11/05/2022 | 7 | CHATTERJEE CONSTRUCTION | 9.77 | 1.88 | 19.26 | 0
1252 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Formal order for the work of Construction of 400 M3 capacity ,20 mtr staging height of RCC OHR for Kanksa Zone-II/Part-D piped W/s Scheme under DWSD,PHE Dte(SL-03) | 788/DWSD | 18/05/2022 | 184 | RANJIB GHATAK | 88.59 | 0 | 0 | 0
1253 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-C) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte | 1435/DWSD | 28/12/2020 | 60 | ASHOK KUMAR GHOSH | 42.78 | 38.48 | 100 | 0
1254 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal order for the work of Construction of pump house cum chlorine room at Railpar Sarada Pally H/W site pump house No-1 tube well No-01(OHR) for Augmentation of Kanksa (Zone-II/D) pipe W/s Scheme under DWSD ,PHE Dte (SL-01) | 240/DWSD | 25/02/2022 | 45 | GHOSH & ROY ENTERPRISE | 4.89 | 4.76 | 100 | 100
1255 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Continuation order for the work of supplying fitting fixing and installation of Sluice Valve for O & Mtc of Kanksa (Zone-II/II) piped W/s Scheme of command areas of Panaghar ,Prayagpur mouza under DWSD, PHE Dte | 682/DWSD | 27/04/2022 | 15 | TARA CONSTRUCTION | 4.94 | 0 | 0 | 0
1256 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Material Requisition To Resource Division | 329/DWSD | 15/03/2022 | 0 | Resource Division | 45.86 | 0 | 0 | 0
1257 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal order for the work of Construction of pump house cum chlorine room at Railpar Sarada Pally H/W site pump house No-2 tube well No-02 for Augmentation of Kanksa (Zone-II/D) pipe W/s Scheme under DWSD ,PHE Dte (SL-02) | 241/DWSD | 25/02/2022 | 45 | MUKHERJEE ENTERPRISE | 4.89 | 3.76 | 100 | 100
1258 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum Formal work-Order for the work of ---Sanitary arrangement and plumbing works at Sarada Pally H/W Site Pump house No-3 for Augmentation of Kanksa (Zone-II/D) pipe W/S Scheme under DWSD,PHE Dte (SL-04) | 1054/DWSD | 07/07/2022 | 25 | CHATTERJEE CONSTRUCTION | 4.82 | 3.08 | 100 | 100
1259 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) , SM/10210 | Augmentation | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works plinth protection ,roof treatment ,drain and other allied works at Sarada Pally H/W Site Pump house No-1 &T.W-01(OHR site) for Augmentation of Kanksa (Zone-II/D) pipe W/S Scheme under DWSD,PHE Dte (SL-05) | 1060/DWSD | 08/07/2022 | 25 | GHOSH & ROY ENTERPRISE | 4.82 | 3.08 | 100 | 100
1260 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Formal order for the work of Laying of collecting main for sinking of 2 Nos river bed tube well and making of manifold in river Ajoy at Bhaburia H/W site under Jamgora-Jagannathpur and Gourbazar-Ichhapur piped W/s Scheme for combat flood damaged under DWSD,PHE Dte.(Part-B) | 136/DWSD | 02/02/2022 | 7 | MD AAMIR KHAN | 17.58 | 17.58 | 100 | 0
1261 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 12 nos AWC for having no electricity (for 350 Nos Students) Blocks ¿ Kanksa , GP Amlajora aand Tilacchandrapur , under Durgapur Water Supply Division PHE Dte with out PWSS 1) Barodoba adibasipara kuldiha ICDS 2) Kuldiha solaipara ICDS 3) Hariki ICDS 4) rakhitpur adibasipara ICDS 5) chua baagaanpara ICDs 5) jaambuni ICDS 6) lohaguri adibasipara ICDS with PWSD 7) Bansole 8) Jabbarpally 02 9) chapabandi 111 10) Ichhapur Baddyakar para ICDSs) 11) aratai 2 12) araati paschim para (SL-26) | 607/DWSD | 21/04/2022 | 20 | TARA CONSTRUCTION | 46.13 | 45.52 | 100 | 0
1262 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 12 nos AWC for having no electricity (for 350 Nos Students) Blocks ¿ Kanksa , under Durgapur Water Supply Division PHE Dte 1) Bandra Bauripara ICDS 2) Birudiha canal par ICDS 3) Brindabanpur ICDS 4) rajhat General para ICDS 5) Amlouka 74 ICDS 6) Amlouka Muslim para ICDS 7) Mollapara math para , 8) Debipur kritibus para , 9) Mirepara , 10) Serpur I ICDSs) 11) mollapara Rajar math ICDSs) 12) Shialpur samity (SL-31) | 608/DWSD | 21/04/2022 | 20 | M/S BADAL GHOSH | 46.14 | 45.67 | 100 | 0
1263 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 06 nos AWC for having without electricity ( Students up to 350) without PWSS Blocks ¿Kanksa , under Durgapur Water Supply Division PHE Dte 1) Shilampur Ppurba para ICDS no 327 2) amlajora Lohar para IICDS no 114 3) Natungram goshpara ICDS and with PWSS 4) Tilack chandrapur 1 . 5)Tilack chandrapur 2 , 6)Tilack chandrapur bagdipara (SL-37) | 609/DWSD | 21/04/2022 | 20 | D. S. ENTERPRISE | 23.02 | 22.74 | 100 | 0
1264 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work Water Supply arrangement to 06 nos AWC for having without electricity ( Students up to 350) Blocks ¿ Kanksa , under Durgapur Water Supply Division PHE Dte without PWSS 1) Keten ICDS 2) napara choudhory paraa ICDDS 3 ) Rajbanddh dakshin Railpar ICDS . and with PWSS 4) bankati ICDSs) 5) Sundiyara colony para ICDS s 6) tilabani adibasi para ICDS s (SL-36) | 612/DWSD | 21/04/2022 | 20 | RANAJOY ENTERPRISE | 23.07 | 22.89 | 100 | 0
1265 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 12 nos AWC for having no electricity (for 350 Nos Students) Blocks ¿ Kanksa under Durgapur Water Supply Division PHE Dte 1) jatgariaa adibasi para 2) Fuljhuri adibasipara ICDS 3 ) Shibhpur lohaarpara ICDS 04) amaidanga 05) adibasipara icds 06) south canalpar icds no 228 7) Labnapara.8) Labnapara 02, 9) gopendanga 10) labnapara adibasipara ICDSs) 11) Jagannathpur adibasipara, 12) koilashpur azimpara (SL-28) | 606/DWSD | 21/04/2022 | 20 | SWATI CORPORATION | 46.12 | 45.48 | 100 | 0
1266 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 06 nos AWC for having without electricity ( Students up to 350) Blocks ¿ Durgapur Faridpur , under Durgapur Water Supply Division PHE Dte without PWSS 1) Tilack Chandrapur danga para 2) gangbil danga ICDS 3) Manicara canaalpar ICDS and with PWSS 4) Borobigha adibasi para , 5) domra baganpara , 6) Domra bagdipara (SL-34) | 590/DWSD | 21/04/2022 | 20 | BISHAL ENTERPRISE | 23.07 | 22.9 | 100 | 0
1267 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 12 nos AWC for having no electricity (for 350 Nos Students) Blocks ¿ Kanksa , GP Amlajora and Tilacchandrapur , under Durgapur Water Supply Division PHE Dte without PWSS 1) Ayma Goshpara ICDS Rajbandh uttarpara 3) rajbandh dakhin railpar ICDS no 295 ,4) Mobarakganj kalitala ICDS 5) Babnabera Ruidas para ICDS 6)Ayma bagddipara ICDS no 125 and with PWSS 7) sreekrisnapur 2 , 8) sreekrisnapur majhipara, 9) Bhabanandapur 10) Gythulia Bauripara ICDSs 11) Arati 1 12) Arati 162 (SL-25) | 592/DWSD | 21/04/2022 | 20 | JAYANTA DATTA | 46.05 | 45.41 | 100 | 0
1268 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 12 nos AWC for having no electricity (for 350 Nos Students) Blocks ¿ Kanksa , GP Amlajora aand Tilacchandrapur , under Durgapur Water Supply Division PHE Dte without PWSS 1) telipara kanthaaldanga ICDS ,2) Shyambazar narkeldaanga ICDS 3) Raghunathpur ICDS 4) raghunathpur kaladangaa ICDS 5) telipara bandher danga ICDS 6) gangarampur Beldanga ICDS and with PWSS 7) Ichhapur Dhibar para 8) Ichhapur 1 , 9) Kendua 103 10) Bansia 2 ,11) Bansia 99 , 12) Bansia bagdipara (SL-27) | 593/DWSD | 21/04/2022 | 20 | M/S PROCHESTA ENTERPRISE | 46.03 | 45.57 | 100 | 0
1269 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 12 nos AWC for having no electricity (for 350 Nos Students) Blocks ¿ Kanksa under Durgapur Water Supply Division PHE Dte 1) Birudiha annapurnatala ICDS panagarh railpar ICDS no 223 . 2) Seikhpara ruidaspara 3) railpar locopaara 4) Anuragpur ICDS 5) poralpara loharpaara ICDS 6) South canalpar icds no 10 and with PWSS 7) 3 no colony Kalimandir ,8) Railpar tanki tala , 9) randiha more 10) Gourtala bouripara , 11) Jhinukgor natinpara 12 ),jhinukgor (SL-30) | 594/DWSD | 21/04/2022 | 20 | MD AAMIR KHAN | 46.14 | 45.5 | 100 | 0
1270 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal for the work of Water Supply arrangement to 12 nos AWC for having no electricity (for 350 Nos Students) Blocks ¿ Kanksa under Durgapur Water Supply Division PHE Dte without PWSS 1) Dhobaaru ranisayer ICDS 2) Gram paanagarh Pathanpara ICDS 3) Gangbil purbapara 4) Ijjatganj Setarbandh ICDS 5) Rajkusum Hazradanga ICDS 6) Domra Bagdipara ICDS and with PWSS 7) Jamgora 53 8) jamgora 54 , 9) Kailashpur 52 , 10) Labanapara 51 ICDSs) 11) pratappur 98 12) Panagarh hindi high school ICDS no 19 (SL-29) | 597/DWSD | 21/04/2022 | 20 | JOY GURU ENTERPRISE | 46.13 | 45.49 | 100 | 0
1271 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) Chetodanga Adibasipara SSK 2) Telipara BO SSK 3) Nimtikuri FP School 4) Paschim gangarampur FP School And With PWSS 1) amdohi FP School 2) sreekrisnapur FP school 3) Gourbazar Ananda ashram SISu sikha niketen 4) Sreekrisnapur MSK 5)dangal basudha MSK (SL-18) | 638/DWSD | 21/04/2022 | 20 | M/S KALYANI ENTERPRISE | 13.91 | 13.57 | 100 | 0
1272 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 12 nos AWC for having no electricity (for 350 Nos Students) Blocks ¿ Kanksa , GP Kaanksa , under Durgapur Water Supply Division PHE Dte with out PWSS ( 1) Natunpara Jhupri para ICDS No 8, (2)Sharama para ICDS no 198, (3) railpar sarada pally ICDS 7, (4)GOURTALA CANAAL PAR , (5) Panagarh bazar 02 no (6) Seikhpara Baarupara and with PWSS- 7) Amdohi Bauripara, 8) amdohi muslim para .9) madhaiganj , 10) Gourbazar Badyakarpara 11) Madhaganj busstand , 12 )Gourbazar Godown.(SL-23) | 600/DWSD | 21/04/2022 | 20 | SHWET BARANI | 46.15 | 45.89 | 100 | 0
1273 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of 3 Nos trial bore by direct rotary method of drilling using rig machine at Nabaghanpur village ,Nakrakonda village and Sarpi Village to provide water supply to School and ICDS centres under DWSD ,PHE Dte (SL-05) | 584/DWSD | 21/04/2022 | 7 | JOY GURU ENTERPRISE | 3.92 | 3.92 | 100 | 0
1274 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 12 nos AWC for having no electricity (for 350 Nos Students) Blocks ¿ Kanksa , under Durgapur Water Supply Division PHE Dte 1) Patseura 1 ICDS 2) 1) Patseura 2 ICDS 3) Jemua 2 bauripara ICDS 4) Jemua 1 dangapara ICDS 5) Jemua 4 Bagdipara ICDS 6) Jemua Chapadanga ICDS with PWSS--- 7) Gourtala canel par , 8) east canal par , 9) sherpur II , 10) gourtala bouripara ICDSs) 11) Shilampur bakur tala , 12) shilampur muslim para (SL-32) | 627/DWSD | 21/04/2022 | 20 | PRAVAT SARKAR | 45.68 | 45.21 | 100 | 0
1275 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 03 nos AWC without electricity (For Students up to 350) Blocks ¿Kanksa , with out PWSS under Durgapur Water Supply Division PHE Dte 1) Bidbihar ruiddaspara and with PWSS --2) Basudevpur Dompara 3) Basudevpur Ruidas para ICDS (SL-48) | 624/DWSD | 21/04/2022 | 20 | JUBILEE CONSTRUCTION | 8.75 | 8.67 | 100 | 0
1276 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 03 nos AWC without electricity (For Students up to 350) Blocks ¿Kanksa , with out PWSS under Durgapur Water Supply Division PHE Dte 1) Lohaguri ICDS and with PWSS 2) Kajladihi haripara ICDs 3 ) ajoy pally kajladihi (SL-41) | 618/DWSD | 21/04/2022 | 20 | M/S MONDAL ENTERPRISE | 8.77 | 8.74 | 100 | 0
1277 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement at Shyambazar & its adjacent village for AWC & Schools without electricity & other allied works ( For Students up to 350) Blocks ¿ Kanksa_Bankati panchayet , under Durgapur Water Supply Division PHE Dte. (SL-50) | 589/DWSD | 21/04/2022 | 20 | JOY GURU ENTERPRISE | 11.55 | 11.45 | 100 | 0
1278 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 12 nos AWC for having no electricity (for 350 Nos Students) Blocks ¿ Kanksa , GP Kaanksa , under Durgapur Water Supply Division PHE Dte without PWSS 1) beharpur Goshpaara ICDS no 288 , 2) Amlajora Ruidaspara ICDS 3) Biharpur bauripara ICDS 5) Anandapur ICDs 6) Anandapur Bagdipara ICDS with PWSS --7) Amdohi Bauripara, 8) amdohi muslim para 9) madhaiganj , 10) Gourbazar Badyakarpara 11) Gourbazar Gouranga mandir , 12) sreekrisnapur 1 ICDSs) | 619/DWSD | 21/04/2022 | 20 | AMAR CONSTRUCTION | 46.05 | 45.79 | 100 | 0
1279 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance for the work of Additional work for providing of FHTC from Solar tube well (Stand alone) at Radhamohanpur mouza JL-36 of Bonkati GP and Kanksa block under DWSD,PHE Dte (SL-02) | 1080/DWSD | 14/07/2022 | 15 | JOY GURU ENTERPRISE | 4.98 | 5.01 | 100 | 0
1280 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Supplying UPVC pipe for laying additional branch pipe line at Bonkati Village to provide FHTC at Bankati mouza of Basudha piped W/s Scheme under DWSD,PHE Dte (SL-02) | 953/DWSD | 16/06/2022 | 10 | BISHAL ENTERPRISE | 4.73 | 4.71 | 100 | 0
1281 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement at Radhamohanpur & its adjacent village for AWC & Schools without electricity & other allied works ( For Students up to 350) Blocks ¿ Kanksa_Bankati panchayet , under Durgapur Water Supply Division PHE Dte. | 596/DWSD | 21/04/2022 | 20 | JOY GURU ENTERPRISE | 11.55 | 11.41 | 100 | 0
1282 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) mankara DVC para SSK 2 ) amlajora AB SSK 3) amlajora FP School 4) Shokna natun gram HS School And With PWSS 1) Panagarh RLy colony Jhupripara HINDI FP School 2) Panagarh bazar girls Jr High school 3) Kanksa Fp school 4) panagarh railpar SSK 5) pangarh bazar railpar FP school (SL-03) | 637/DWSD | 21/04/2022 | 20 | M/S KALYANI ENTERPRISE | 13.91 | 13.57 | 100 | 0
1283 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 06 nos AWC without electricity (For Students up to 350) Blocks ¿Kanksa , with out PWSS under Durgapur Water Supply Division PHE Dte 1) Nayakaanchanpur Haripara ICDS 2) jamdoha Dompara ICDS 3) jatgaria danga para 4) nabagram majhiara 5) sutadanga adibasipara ICDS and with PWSS 6) Nabagram majhipara ICDS (SL-49) | 625/DWSD | 21/04/2022 | 20 | B. T. M. CONCERN | 34.06 | 0 | 0 | 0
1284 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 06 nos AWC without electricity for Students up to 350 Blocks_Kanksa , with out PWSS 1 ) Sokna bauripara 2) Amlajora dharmaraajtala 3) )rajkusum tilakdanga ICDS and with PWSS 4) srirampur bangalpara 5 ) nabagram gouratala 6) krisnapur ICDS (SL-38) | 639/DWSD | 21/04/2022 | 20 | M/S KALYANI ENTERPRISE | 23.07 | 0 | 0 | 0
1285 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 03 nos AWC without electricity (For Students up to 350) Blocks ¿Kanksa , with out PWSS under Durgapur Water Supply Division PHE Dte 1) Paschim gangrampur ICDS and with PWSS ---2) ) dubrajpur ranipur 3) jatgaria muslim para (SL-46) | 629/DWSD | 21/04/2022 | 20 | AMITABHA PAUL | 8.78 | 0 | 0 | 0
1286 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order Sinking of 2 Nos tube well 300 mm X 200 mm tube well 210 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter to combat draught like situation and providing drinking water to habitations ,School,AWC etc under DWSD ,PHE Dte (SL-06) | 1243/DWSD | 18/08/2022 | 30 | JOY GURU ENTERPRISE | 27.94 | 25.87 | 92.58 | 0
1287 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water supply arrangement at Bargoria ICDS for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under 189 Nos of AWC W/S Scheme under DWSD ,PHE Dte | 296/DWSD | 17/02/2023 | 10 | JAYANTA DATTA | 6.95 | 6.95 | 100 | 0
1288 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Emergency provision of AC photovoltaic submersible solar pump set within the bore well tube well along with 2400 watt peak capacity solar photovoltaic array on MS structure with sinking of 150 mm dia Tube well of 120 mtr depth by DR rig bore method using PVC pipe and fiber glass reinforced epoxy resin slotted to combat draught like situation at JABUNA gram under Ichhapur panchayat of Durgapur-Faridpur block under DWSD ,PHE Dte. | 297/DWSD | 17/02/2023 | 15 | SATYAM POWER | 14.32 | 14.32 | 99.98 | 0
1289 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Emergency provision of AC photovoltaic submersible solar pump set within bore well /tube well along with 2400 peak watt capacity solar photovoltaic array on MS structure with sinking of 150 mm dia Tube well 150 mtr deep by DR ring method using PVC pipe and fiber glass reinforced epoxy resin slotted to meet up water demand during summer season at Nabaghanapur under Loudoha GP of Durgapur-Faridpur Block for (1 No) mini W/s Scheme under DWSD ,PHE Dte (SL-01) | 138/DWSD | 28/01/2021 | 30 | JOY GURU ENTERPRISE | 13.56 | 13.43 | 100 | 0
1290 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Formal order for the work of Emergency provision of AC photovoltaic submersible solar pum set within bore well /tube well along with 2400 peak watt capacity solar photovoltaic array on MS structure with sinking of 150 mm dia Tube well 150 mtr deep by DR ring method using PVC pipe and fiber glass reinforced epoxy resin slotted to meet up water demand during summer season at Haradanga Adibasipara under Tilakchandrapur GP of Kanksa Block under DWSD ,PHE Dte (SL-05) | 786/DWSD | 11/05/2021 | 30 | SAIKAT RAY | 13.59 | 13.48 | 100 | 0
1291 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 06 nos AWC for having without electricity ( Students up to 350) Blocks _ Kanksa & Durgapur-Faridpur under Durgapur Water Supply Division PHE Dte with out PWSS Jemua Dakhinpara ICDS Jemua Muslim dangapara ICDS 3) Jemua Ruidaspara ICDS & with PWSS --4) basudha old mete para 5) satkahania Bilpara , 6) Shilampur bauripara (SL-33). | 622/DWSD | 21/04/2022 | 20 | BISHAL ENTERPRISE | 23.07 | 22.8 | 100 | 0
1292 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 06 nos AWC for having without electricity ( Students up to 350) Blocks ¿ Kanksa , under Durgapur Water Supply Division PHE Dte with out PWSS 1) sokna das para ICDs 2) Dhobaghata daspara ICDs 3) Napara danga ICDS and with PWSS 4) Piyariganj ruidas para , 5) Piaryganj , 6) Sundiara ruidas para (SL-35) | 626/DWSD | 21/04/2022 | 20 | RANAJOY ENTERPRISE | 23.07 | 22.97 | 100 | 0
1293 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water Supply arrangement to 03 nos AWC without electricity (For Students up to 350) Blocks ¿Kanksa with out PWSS under Durgapur Water Supply Division PHE Dte 1) Banagram ICDs with PWSS 2) Radhanagar ICDS 3) Sashipur Jhaudanga Dompara ICDs (SL-47) | 621/DWSD | 21/04/2022 | 20 | MUKHERJEE ENTERPRISE | 8.77 | 0 | 0 | 0
1294 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Emergency provision of AC photovoltaic submersible solar pump set within the bore well tube well along with 2400 watt peak capacity solar photovoltaic array on M.S. structure with sinking of 150 mm dia Tube well of 120 mtr depth by DR rig bore method using PVC pipe and fiber glass reinforced epoxy resin slotted to combat draught like situation at Molandighi gram panchayat office of Kanksa block under DWSD ,PHE Dte. | 260/DWSD | 15/02/2023 | 15 | JOY GURU ENTERPRISE | 14.21 | 14.15 | 100 | 0
1295 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water supply arrangement at Basudha old metepara ICDS and Shilampur Bouipara ICDS for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under 189 Nos of AWC W/S Scheme under DWSD ,PHE Dte | 288/DWSD | 16/02/2023 | 15 | BISHAL ENTERPRISE | 13.91 | 13.83 | 100 | 0
1296 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Emergency provision of AC photovoltaic submersible solar pump set within the bore well tube well along with 2400 watt peak capacity solar photovoltaic array on MS structure with sinking of 150 mm dia Tube well of 120 mtr depth by DR rig bore method using PVC pipe and fiber glass reinforced epoxy resin slotted to combat draught like situation at Baguraman Basudha under Bankati gram panchayat of Kanksa block under DWSD ,PHE Dte | 261/DWSD | 15/02/2023 | 15 | MUKHERJEE ENTERPRISE | 14.31 | 14.32 | 100 | 0
1297 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Emergency provision of AC photovoltaic submersible solar pump set within the bore well Tube well along with 2400 watt peak capacity solar photovoltaic array on MS structure with sinking of 150 mm dia Tube well of 120 mtr depth by DR rig bore method using PVC pipe and fiber glass reinforced epoxy resin slotted to combat draught like situation at Protapur High School under Pratabpur Gram Panchayat of Durgapur-Faridpur block under DWSD ,PHE Dt | 286/DWSD | 16/02/2023 | 15 | GHOSH & ROY ENTERPRISE | 14.24 | 14.32 | 100 | 0
1298 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Water supply arrangement at Amluka Village near Majid to provide water supply to Schools ,AWC/ICDS of Durgapur-Faridpur Block under 189 Nos of AWC W/S Scheme under DWSD ,PHE Dte | 262/DWSD | 15/02/2023 | 15 | BISHAL ENTERPRISE | 4.46 | 4.38 | 100 | 0
1299 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Formal order for the work of Emergency provision of AC photovoltaic submersible solar pum set within bore well /tube well along with 2400 peak watt capacity solar photovoltaic array on MS structure with sinking of 150 mm dia Tube well 150 mtr deep by DR ring method using PVC pipe and fiber glass reinforced epoxy resin slotted to meet up water demand during summer season at Piariganj and Adibasi para under Trilackchandrapur GP of Kanksa Block to combat draught like situation and providing drinking water to habitations ,School,AWC etc under DWSD ,PHE Dte | 1601/DWSD | 11/11/2022 | 30 | MD AAMIR KHAN | 13.53 | 0 | 0 | 80
1300 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman , SM/10372 | Anganwadi | Acceptance cum formal order for the work of Balance work for installation of solar pumping machineries including solar panel and other allied works for 12 Nos ICDS/AWC/School at Kanksa block ICDS under providing running water supply to ICDS(189 Nos) ,HCF and other Public Ins of Kanksa and Durgapur-Faridpur Block under DWSD,PHE Dte. | 1080/DWSD | 12/07/2023 | 905 | BISHAL ENTERPRISE | 40.03 | 0 | 0 | 100
1301 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman , SM/12226 | Augmentation | Acceptance cum work order for Laying & Pushing by adopting trench less technology (e.g. Jack Pushing Method etc0 at Bagdiha to Sidhapur Road and Bagdiha OHR to Bahadurpur under Jamuria Block under Augmentation of Bagdiha PWSS under RCFA Division-I PHE Dte. | 3282/RCD-I | 08/11/2023 | 15 | SIMA ENTERPRISE | 6.34 | 6.02 | 100 | 100
1302 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman , SM/12226 | Augmentation | Material Requisition To Resource Division | 2956/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1303 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman , SM/12226 | Augmentation | Acceptance cum work order Distribution Network and allied work for Ukhra area of RCFA Part-II Piped Water Supply Scheme allied work under RCFA Division-I PHE Dte. (Zone-2A)(Sl. No. 13) | 1080/RCD-I | 23/03/2023 | 90 | GITASREE FABRICATION | 97.2 | 0 | 0 | 80
1304 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman , SM/12226 | Augmentation | Acceptance cum work order for construction of chlorine room of size (4.50 X 3.50 m) at (Zone-XIII) of Baraboni block for Improvement of RCFA Pt-I piped Water Supply under RCFA Div-I, PHE Dte. in the district of Paschim Bardhaman. | 677/RCDI | 24/02/2023 | 15 | ZEROTH CONTROL SYSTEM | 4.61 | 3.89 | 100 | 100
1305 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman , SM/12226 | Augmentation | Acceptance cum work order for Laying & pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Srirampur Workshop road near Railway Workshop under Ondal Block under RCFA Division-I PHE Dte. | 3437/RCD-1 | 24/11/2023 | 15 | M/S UNIT CONSTRUCTION | 9.31 | 9.31 | 100 | 100
1306 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman , SM/12226 | Augmentation | Acceptance cum work order Concrete road cutting and mending work for laying distribution pipe line at Das Para (Sansad-XIX) at Ukhra area Block ¿ Andal and Pandabeswar under Augmentation of RCFA Part-II (Zone-2A) PWSS under RCFA Division-I PHE Dte. (Sl No. 17) | 1161/RCD-I | 24/03/2023 | 15 | JYOGOMAYA ENTERPRISE | 2.01 | 1.94 | 96.69 | 100
1307 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman , SM/12226 | Augmentation | Formal work order for Additional work for allied work in connection with in connection supply, laying fitting, fixing of 15 mm NB PVC (Schedule 80) / 2020 mm OD HDPE (PE 80, PN 6) pipe with all necessary specials piece etc. all complete for Augmentation of Sub-Station Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | 158/RCD-I | 22/01/2024 | 435 | MRITYUNJOY MUKHERJEE & CO. | 213.03 | 182.47 | 85.65 | 85
1308 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman , SM/12226 | Augmentation | Acceptance cum Work Order for Additional works of Concrete dismantling, Concrete restoration, Bolder cutting and other allied works at distribution network of Augmentation PWSS of RCFA Part-II (Zone-2A) under RCFA Div-I,PHE Dte. | 1743/RCD-I | 18/07/2024 | 255 | SWATI CORPORATION | 67.64 | 21.06 | 31.13 | 30
1309 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman , SM/12226 | Augmentation | Acceptance cum work order for Left out part at Banbahal village distribution pipe line Zone-4A under Pandabeswar Block for smooth running of water supply near Shankarpur area of Augmentation PWSS of RCFA Part-II (Zone-2A) under RCFA Division-I PHE Dte. | 1460/RCD-I | 15/05/2025 | 30 | BABA LOKNATH ENTERPRISE | 18.07 | 0 | 0 | 80
1310 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman , SM/12226 | Augmentation | Acceptance cum work order Concrete road cutting mending works for laying of distribution pipe line at Kankardanga Part (Sansad-VIII) at Ukhra area Block-Andal and Pandabeswar under Augmentation of RCFA Part-II (Zone-2A) PWSS under RCFA Division-I PHE Dte. (Sl No. 19) | 1163/RCD-I | 24/03/2023 | 15 | MS KALYAN ENTERPRISE | 2.77 | 2.71 | 100 | 100
1311 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 B) , SM/12225 | Augmentation | Material Requisition To Resource Division | 2953/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1312 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 B) , SM/12225 | Augmentation | Acceptance cum work order Repair and renovation works of One no RCC Elevated Reservoir of Capacity 1362 cum at Khandra for Augmentation RCFA Part-II (Zone-9B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2234/RCD-I | 17/07/2023 | 30 | UNITED CONSTRUCTION | 16.43 | 16.29 | 100 | 100
1313 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 B) , SM/12225 | Augmentation | Formal work order for distribution network for RCFA Part-II piped Water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte. (Zone-9B)(Part-A) | 486/RCDI | 03/02/2023 | 30 | M/S MONDAL ENTERPRISE | 156.13 | 71.14 | 45.57 | 70
1314 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 B) , SM/12225 | Augmentation | Formal work order for Distribution Network for RCFA Part-II Piped Water Supply Scheme Including FHTC & allied work under RCFA Division-I PHE Dte. (Zone 9B) (Part-B) | 1348/RCD-I | 04/04/2023 | 30 | M/S SANTANU PALIT & CO. | 156.13 | 33.23 | 21.29 | 30
1315 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 B) , SM/12225 | Augmentation | Acceptance cum work order for Sinking of 06 (Six) nos. river bed tube wells including collecting main, sluice valve chamber & other allied works at Shyamlya H/W site at Ajoy river under Shyamla Water Supply Scheme under RCFA Division-I PHE Dte. | 2241/RCD-1 | 17/07/2023 | 30 | MAA ENTERPRISE. | 33.68 | 32.87 | 100 | 100
1316 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 B) , SM/12225 | Augmentation | Acceptance cum work order for Allied work of making spout and Platform with other allied work at Amritnagar Zone -1 under Augmentation PWSS of RCFA Part-II (Zone - 9 B) under RCFA Division 1 PHE Dte. | 2421/RCD-I | 26/09/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 41.77 | 0 | 0 | 100
1317 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Detailed Route Survey, Design Drawing & DPR Preparation for Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 05) | 504/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.23 | 4.23 | 100 | 0
1318 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Material Requisition To Resource Division | 2925/RCD-I | 17/11/2022 | 0 | Resource Division | 356.25 | 0 | 0 | 0
1319 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Material Requisition To Resource Division | 3129 | 09/12/2022 | 0 | Resource Division | 60.34 | 0 | 0 | 0
1320 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum wor order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Amritnagar under Augmentation of Sub Surface Water Supply Scheme of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 3283/RCDI | 20/12/2022 | 90 | SOMNATH SAMANTA | 22.04 | 14 | 67.54 | 100
1321 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum work order for Additional work for Road crossing of 250 mm dia Rising Main for under Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under Raniganj Block under RCFA Division-I PHE Dte. | 2122/RCD-I | 27/08/2024 | 30 | MD. JAWED KHAN | 8.41 | 8.59 | 100 | 100
1322 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum Work Order for Construction of Boundary Wall with Gate at OHR Site (Length-80 mtrs) at Amritnagar H/W Site (Damalia village) of Raniganj Block for Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 03) | 1147/RCD-1 | 24/03/2023 | 892 | M/S MONDAL CONSTRUCTION | 7.04 | 6.94 | 98.56 | 100
1323 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum Work Order for Land development with approach road including internal drain at Head Works Site for Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No.- 05) | 1149/RCD-1 | 24/03/2023 | 948 | ZEROTH CONTROL SYSTEM | 6.5 | 0 | 0 | 40
1324 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum Work Order for Special Repair & Renovation of existing High Lift Pump House, Boundary Wall, Guard Room, CWR, Switch Room etc. and allied works at H/W Site of Amritnagar Piped Water Supply Scheme. | 1145/RCD-1 | 24/03/2023 | 30 | RUBY CONSTRUCTION | 9.83 | 9.59 | 97.58 | 0
1325 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum work order for Balance work of OHR and Construction of new boundary wall, Land developing and Path way and other allied works at Saora mouza, Plot No:2787 at R.C.C over Head Site of Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under Raniganj Block under RCFA Division-I, PHE Dte. | 2550/RCD-I | 29/10/2024 | 154 | DAS & CHAKRABORTY | 26.19 | 13.58 | 51.86 | 80
1326 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum work order of rising main for Amritnagar Zone-II Water Supply Scheme for Ranoganj Block under RCFA Div-I, PHE Dte. | 2513/RCD I | 20/10/2022 | 30 | MD. JAWED KHAN | 38.5 | 38.44 | 100 | 100
1327 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Laying of Distribution System to Accommodate FHTC and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN6) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division I, PHE Dte.under RCFA Division I, PHE Dte. | 2455/RCD-I | 13/10/2022 | 536 | MACHINO TECHNO | 366.55 | 235.84 | 91.43 | 100
1328 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum work order for supplying 90 mm dia HDPE pipe line at Murgathol Adibasipara and Old Egera Including repairing different dia pipe line in different places within Amritnagar Distribution Zone under Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division- IPHE Dte. | 410/RCD-I | 30/01/2023 | 20 | DAS & CHAKRABORTY | 9.23 | 9.18 | 100 | 0
1329 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum work order for Additional work of laying distribution system for Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | 2253/RCD-1 | 17/07/2023 | 30 | MRITYUNJOY MUKHERJEE & CO. | 62.23 | 62.13 | 100 | 100
1330 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum work order for Balance work of laying distribution system to Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | 2255/RCD-1 | 17/07/2023 | 30 | MACHINO TECHNO | 28.24 | 28.13 | 100 | 100
1331 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptence cum work order for Additional Work for crossing Nunia River through the riverbed and allied works of Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte | 2580/RCD-I | 07/09/2023 | 15 | MD. JAWED KHAN | 7.58 | 7.43 | 100 | 100
1332 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum work order for Balance work of Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Dhunabaid of Dendua for distribution system within command area of Zone-I (Dendua OHR Site) under Augmentation of sub surface water supply scheme for Amritnagar Zone-II under RCFA, Division-1,P.H.E.Dte. | 2124/RCD-I | 27/08/2024 | 30 | DAS & CHAKRABORTY | 12.7 | 0 | 0 | 100
1333 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum work order for Balance work of Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Pathan Dahwra of Murgasole Mouza under Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA, Division-1, P.H.E. Dte. | 2126/RCD-I | 27/08/2024 | 25 | DAS & CHAKRABORTY | 7.38 | 5.26 | 42.23 | 100
1334 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman , SM/11986 | Augmentation | Acceptance cum work order for Additional works of Sinking of 6 (Six) nos. river bed tube wells including collecting main & other allied works at Damalia H/W under RCFA part II at Damodar river under Amritnagar Zone II water supply scheme under RCFA Division-I PHE Dte. | 2136/RCD-I | 27/08/2024 | 216 | M/S MONDAL CONSTRUCTION | 12.6 | 0 | 0 | 30
1335 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. , SM/12042 | Augmentation | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-16) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 31) | 1175/RCD I | 24/03/2023 | 90 | N.R. CONSTRUCTION | 4.61 | 0 | 0 | 0
1336 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. , SM/12042 | Augmentation | Material Requisition To Resource Division | 2939/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1337 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. , SM/12042 | Augmentation | Sub Soil Investigation for 600 cum capacity RCC Over Head Reservoir at (Zone-16) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3353/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0.49 | 100 | 100
1338 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. , SM/12042 | Augmentation | Acceptance cum work order for Balance work for laying of HDPE pipeline and PVC pipeline and allied works at Nabagram, Ukhra (Sansad-VI) Chatterjee para and Bahula Colony under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | 3453/RCD-I | 24/11/2023 | 15 | MD AAMIR KHAN | 4.36 | 4.24 | 100 | 100
1339 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. , SM/12042 | Augmentation | Acceptance cum work order for Additional Supplying aligning laying HDPE pipe Mechanical fitting supplying sluice valve and other allied works at (Mouza-Sahenganj) under Zone-16 Part-II W/S Scheme under RCFA Division-I PHE Dte. | 572/RCD-I | 23/02/2024 | 30 | KRISHNA KUMAR TODI HUF | 36.45 | 36.45 | 100 | 100
1340 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. , SM/12042 | Augmentation | Formal work word for Distribution Network for RCFA Part-II Pipe Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-16). | 1606/RCD I | 25/04/2023 | 251 | JOY HIND TUBEWELLS | 488.35 | 417.76 | 85.55 | 100
1341 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. , SM/12042 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-II Water Supply Scheme within command area of Zone-16 including FHTC work (Part-A) under RCFA Div-I PHE Dte. (Mouza-Sahebganj) | 3160/RCD-I | 13/12/2022 | 30 | KRISHNA KUMAR TODI HUF | 88.68 | 79.11 | 100 | 100
1342 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. , SM/12042 | Augmentation | Formal work order for Construction of 600 cum capacity 20 mtr. Staging height RCC Over head Reservoir (pipe connection and cost of pipes, special at Raniganj Block (Zone-16) for Augmentation of RCFA Division-II piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/2012 (Sheet No. 1 & 2) | 1899/RCD-I | 09/06/2023 | 366 | ASHA CONSTRUCTION | 154.85 | 93.83 | 54.79 | 45
1343 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. , SM/12042 | Augmentation | Acceptance cum work order for Crossing 600 mm dia MS pipes under the Railway track by jack pushing technology at different spots and pushing diff. dia M.S pipes throgh 600 mm dia MS pipes in connection with the work for the laying distribution system for Augmentation of Sub - Surface water based piped water supply scheme for Amritnagar Zone -II for Augmentation of PWSS RCFA Part-II (Zone-16) Under RCFA Division -I PHE. Dte. | 2419/RCD-I | 26/09/2024 | 187 | MRITYUNJOY MUKHERJEE & CO. | 40.11 | 34.45 | 95.38 | 70
1344 | PASCHIM BARDHAMAN | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/11932 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle) of Assistant Engineer for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.03.2023 to 31.08.2023). (Sl-01) | 134/DWSD | 31/01/2023 | 181 | BIPLAB BANERJEE | 0.82 | 2.4 | 100 | 80
1345 | PASCHIM BARDHAMAN | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/11932 | New | Acceptance cum formal order for the work of Dismantling of concrete road for laying distribution system rising main construction of 350 M3 reservoir with 20 mtr staging height including soil investigation construction of pump house (5.40 X 3.60 m) with sanitary and construction of pump house 3.60 X 3.00 m) for Napara piped W/s Scheme under DWSD ,PHE Dte | 489/DWSD | 23/03/2023 | 20 | SK. ABDUL HALIM | 4.39 | 4.39 | 99.97 | 0
1346 | PASCHIM BARDHAMAN | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/11932 | New | Formal order for the work of laying distribution system, Rising main construction of 350 M3 Over Head Reservoir with 20 Mtr staging height including soil investigation ,construction of Pump House (5.4X3.6mtr) with Sanitary and water supply arrangement & construction of Pump house (3.6X3.00 m) with FHTC for NAPARA piped W/s Scheme under DWSD,PHE Dte ,Dist.-Paschim Bardhhaman. | 1174/DWSD | 02/08/2022 | 12 | SK. ALIM | 522.15 | 514.4 | 100 | 100
1347 | PASCHIM BARDHAMAN | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/11932 | New | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Napara piped W/s Scheme under DWSD ,PHE Dte (SL-08) | 1255/DWSD | 23/08/2022 | 15 | SK. ALIM | 14.76 | 14.73 | 100 | 0
1348 | PASCHIM BARDHAMAN | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/11932 | New | Material Requisition To Resource Division | 789/DWSD | 25/05/2023 | 0 | Resource Division | 7.07 | 0 | 0 | 0
1349 | PASCHIM BARDHAMAN | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/11932 | New | Quotation for Napara W/S Scheme, P.H. No - 1, Gopalpur CCC | BP-2022-23-329 | 15/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.02 | 0 | 0 | 0
1350 | PASCHIM BARDHAMAN | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/11932 | New | Quotation for Napara W/S Scheme, P.H. No - 02, Gopalpur CCC | BP-2022-23-330 | 15/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.8 | 0 | 0 | 0
1351 | PASCHIM BARDHAMAN | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/11932 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle) of Assistant Engineer for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.09.2023 to 29.02.2024). (Sl-01) | 1397/DWSD | 17/08/2023 | 184 | BIPLAB BANERJEE | 0.82 | 0.8 | 100 | 30
1352 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09062 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Roshna (Part) Block-Barabani under Roshna Water supply scheme under RCFA Division-I, P.H.E. Dte. | 1863/RCD-I | 28/10/2021 | 30 | SRI KRISHNA ENTERPRISE | 12.81 | 9.39 | 73.27 | 0
1353 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09062 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Parulberia Mouza Block-Barabani under Roshna Water supply scheme under RCFA Division-I, P.H.E. Dte. | 1864/RCD-I | 28/10/2021 | 30 | MAK CONSTRUCTION CO. | 20.28 | 17.74 | 87.44 | 0
1354 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09062 | Retrofitting | Extension of different dia HDPE pipe line for providing FHTC at Parulberia and allied villages (Part-B) under Roshna W/S Scheme under RCFA Division-I PHE Dte. | 1432/RCD I | 27/06/2022 | 45 | MD SARFARAZ ALAM | 4.98 | 4.65 | 93.25 | 0
1355 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09062 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Daskeary Village Block-Barabani under Roshna Water supply scheme under RCFA Division-I, P.H.E. Dte. | 1862/RCD-I | 28/10/2021 | 30 | M/S MONI TRADERS | 39.47 | 35.31 | 89.47 | 0
1356 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09062 | Retrofitting | Supplying, aligning & Laying of different dia HDPE pipe line for providing FHTC at Parulberia and allied villages (Part-A) under Roshna W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | 1434/RCD I | 27/06/2022 | 45 | MD AAMIR KHAN | 5 | 4 | 46.32 | 0
1357 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09062 | Retrofitting | Extension of different dia HDPE pipe line for providing FHTC at Roshna & Baspahari villages under Roshna W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | 1438/RCD I | 27/06/2022 | 45 | SHREE DURGA ENTERPRISE | 3.22 | 3.1 | 100 | 0
1358 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09062 | Retrofitting | Material Requisition To Resource Division | 438/RCD-I | 21/02/2022 | 0 | Resource Division | 8.25 | 0 | 0 | 0
1359 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09062 | Retrofitting | Car bill may 23 and june 23 | 234/2/23-24 | 05/09/2023 | 0 | NIRMALA TRADERS | 0.78 | 0 | 0 | 0
1360 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. , SM/09062 | Retrofitting | Acceptance cum work order for Additional work for Distribution Network including supply of Hume pipe, G.I. pipe Sluice Valve and allied works for Augmentation of Roshna PWS (Part-D) under RCFA Division-I PHE Dte. | 2251/RCD-1 | 17/07/2023 | 30 | JYOGOMAYA ENTERPRISE | 10.86 | 5.29 | 100 | 100
1361 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. , SM/13685 | Retrofitting | Acceptance cum formal order for the work of providing FHTC connection and connection providing to Jemua Mouza (JL-80) under Jemua piped W/S Scheme under DWSD,PHE Dte (SM/06274) (Part-A) | 1065/DWSD | 12/07/2023 | 25 | B.M. SARKAR | 9.67 | 0 | 0 | 0
1362 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. , SM/13685 | Retrofitting | Acceptance cum formal order for the work of providing FHTC connection and connection providing to Jemua Mouza (JL-80) under Jemua piped W/S Scheme under DWSD,PHE Dte (SM/06274)(Part-C) | 1058/DWSD | 12/07/2023 | 25 | B.M. SARKAR | 9.82 | 0 | 0 | 0
1363 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. , SM/13685 | Retrofitting | Acceptance cum formal order for the work of Construction of boundary wall at Akandara Pump house site TW No-2 site under Jemua piped W/s Scheme under DWSD ,PHE Dte | 332/DWSD | 20/02/2023 | 30 | DARPAN DAS & CO. | 15.05 | 8.45 | 100 | 100
1364 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. , SM/13685 | Retrofitting | Acceptance cum formal order for the work of Sinking of 2 Nos 300X200 mm dia TW 210 mtr deep by DR rig method using UPVC pipe CD and UPVC deep well screen (RDS) at Jemua H/W site and 1 No TW site of Faridpur block of retrofitting of Jemua piped W/s Scheme under DWSD ,PHE Dte (SL-19) | 757/DWSD | 19/05/2023 | 20 | M/S BADAL GHOSH | 31.47 | 22.07 | 100 | 100
1365 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. , SM/13685 | Retrofitting | Acceptance cum formal order for the work of additional work for providing FHTC in connection with JJM for Nachan Mouza(JL-47) under Retrofitting of Jemua piped W/s Scheme under DWSD,PHE Dte (SM/13685) | 1064/DWSD | 12/07/2023 | 25 | M/S MONDAL ENTERPRISE | 14.55 | 13.65 | 100 | 100
1366 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. , SM/13685 | Retrofitting | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of Jemua PWSS under Durgapur-Faridpur Development Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No-01) | 914/DWSD | 22/06/2023 | 7 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
1367 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. , SM/13685 | Retrofitting | Additional repairing and replacement and restoration due to pipe line laying and pavers block and making platform including extra deapth of TW at Jamuna village and other allied works under providing water supply under Retrofitting of Jemua piped W/s Scheme under DWSD,PHE Dte | 1445/DWSD | 25/08/2023 | 15 | SATYAM POWER | 3.43 | 3.43 | 100 | 100
1368 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. , SM/13685 | Retrofitting | Acceptance cum formal order for the work of Construciton of 5.4 m X 3.60 m swtich room with plinth height (600 mm to 20000 mm ) with sanityary and water supply arrangment at Jemua tube well no -III site of retrofitting of Jemua Piped W/s Scheme under DWSD ,PHE Dte | 678/DWSD | 03/05/2023 | 30 | SIL ENTERPRISE | 6.92 | 6.92 | 100 | 100
1369 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. , SM/13685 | Retrofitting | Acceptance cum formal order for the work of Sinking of 2 Nos 300X200 mm dia TW 210 mtr deep by DR rig mehtod using UPVC pipe CD and UPVC deep well screen (RDS) at Jemua H/W site and 1 No TW site of Faridpur block of retrofitting of Jemua piped W/s Scheme under DWSD ,PHE Dte | 680/DWSD | 03/05/2023 | 474 | RANJIB GHATAK | 31.43 | 30.86 | 100 | 100
1370 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. , SM/13685 | Retrofitting | Acceptance cum formal order for the work of providing FHTC connection and connection providing to Jemua Mouza (JL-80) under Jemua piped W/S Scheme under DWSD,PHE Dte (SM/06274) (Part-B) | 1068/DWSD | 12/07/2023 | 20 | ASHA CONSTRUCTION | 10.5 | 0 | 0 | 100
1371 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. , SM/13685 | Retrofitting | Acceptance cum formal order for the work of Construction of 5.4 m X 3.60 m swtich room with plinth height (600 mm to 20000 mm ) with sanitary and water supply arrangement at Jemua tube well no -II site of retrofitting of Jemua Piped W/s Scheme under DWSD ,PHE Dte | 681/DWSD | 03/05/2023 | 811 | RANA ENTERPRISE | 6.84 | 0 | 0 | 51
1372 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18888 | Augmentation | Acceptance cum formal order for the work of Creating a separate zone for PATHANPARA and Bagdipara of Kanksa (Zone-II/Part-C) with construction of Pump house /Chlorine room Sinking of 150 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Paragraph Mouza under Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme under DWSD, PHE Dte | 1139/DWSD | 20/07/2023 | 45 | JOY GURU ENTERPRISE | 95.5 | 0 | 0 | 0
1373 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18888 | Augmentation | Repairing and replacement and installation of Water supply arrangement at Kanchanpur FP School to provide water supply to school ,Block-Kanksa,Dist-Paschim Bardhhaman under Augmentation of Kanchanpur piped W/s Scheme under DWSD, PHE Dte | 1619/DWSD | 03/10/2023 | 30 | BISHAL ENTERPRISE | 2.23 | 2.23 | 100 | 100
1374 | PASCHIM BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18888 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for tube well No. - 3 at Kanchanpur Water Supply Scheme of (Kanksa Block, Paschim-Bardhaman) | 17/CMD | 03/01/2024 | 30 | S.P. CONSTRUCTION | 12.36 | 0 | 0 | 100
1375 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18888 | Augmentation | Acceptance cum work order for additional work of construction of IEP, drain and platform and other allied works at Kanchanpur under Augmentation of Kanchanpur Piped water supply scheme under RCFA Division-I PHE Dte. | 1761/RCDI | 18/06/2025 | 30 | RUPALI ELECTRONICS | 15.48 | 0 | 0 | 0
1376 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18888 | Augmentation | SUPPLY & INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING AT KANCHANPUR PIPED WATER SUPPLY SCHEME FOR TUBE WELL NO-4 UNDER ASSANSOL MECHANICAL DIVISION, PHE DTE., BLOCK-KANKSHA, DIST.- PASCHIM-BARDHAMAN | 1675/AMD | 04/10/2024 | 119 | M/S. S. S. ENTERPRISE | 13.33 | 0 | 0 | 100
1377 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18888 | Augmentation | Acceptance cum Work Order for Additional Work for distribution main pipe line Panagarh Gram Shibtola of Kanksa Zone-II Part-B of Augmentation of Kanchanpur W/S Scheme under RCFA Division-I PHE Dte. | 3106/RCD-I | 13/12/2024 | 60 | MD AAMIR KHAN | 37.68 | 20.56 | 35.75 | 100
1378 | PASCHIM BARDHAMAN | Asansol Mechanical | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. , SM/18889 | Augmentation | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head Works Site Under RCFA Part-III (Zone-II) Water Supply Scheme, Block: Pandabeswar, Dist. Paschim Bardhaman. | 8/AMD | 02/01/2024 | 366 | R.N.S TRADING | 145.04 | 0 | 0 | 0
1379 | PASCHIM BARDHAMAN | Asansol Mechanical | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. , SM/18889 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house & Substation Buliding with Yard lighting arrangement and other allied works at Mahal & ECL Pump House under RCFA Part-III(Zone-II) Water Supply Scheme. | 2116/AMD | 16/12/2024 | 30 | SUNRISE ENGINEERING CORPORATION | 20.39 | 0 | 0 | 0
1380 | PASCHIM BARDHAMAN | Asansol Mechanical | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. , SM/18889 | Augmentation | Deposition of earnest money for the proposed enhancement of the load at your premises at Dalurbandh, Pandabeswar | BP-2024-25-7 | 24/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
1381 | PASCHIM BARDHAMAN | Asansol Mechanical | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. , SM/18889 | Augmentation | Allied Works Corresponding to "Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head Works Site Under RCFA Part-III (Zone-II) Water Supply Scheme, Block: Pandabeswar, Dist. Paschim Bardhaman. | 145/AMD | 05/02/2025 | 30 | BENGAL CONSTRUCTION | 8.18 | 0 | 0 | 0
1382 | PASCHIM BARDHAMAN | Asansol Mechanical | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. , SM/18889 | Augmentation | Providing & Installation of Sub-Mersible Pumping Machineries at RBTW No-20,21,22 & 23 other allied works at Ramnagar Pump House under RCFA Part-III(Zone-II) Water Supply Scheme. | 2098/AMD | 12/12/2024 | 253 | SUNRISE ENGINEERING CORPORATION | 12.41 | 0 | 0 | 100
1383 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07559 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | 956/RCD-I | 07/06/2021 | 30 | SUMIT BANERJEE | 23.02 | 38.36 | 158 | 0
1384 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07559 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | 957/RCD-I | 07/06/2021 | 30 | BABA LOKNATH ENTERPRISE | 23.01 | 43.71 | 176.01 | 0
1385 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07559 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-D] | 958/RCD-I | 07/06/2021 | 30 | KHEPI MAA TRADERS | 22.98 | 5.31 | 100 | 0
1386 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07559 | Retrofitting | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Chotkara (Part) for providing FHTC under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 16) | 258/RCD-I | 01/02/2022 | 15 | JAYANTA DATTA | 2.59 | 2.48 | 100 | 0
1387 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07559 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-C] (3rd Call) | 1147/RCD-I | 22/07/2021 | 30 | GITASHREE FABRICATION | 21.97 | 21.9 | 50.09 | 0
1388 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07559 | Retrofitting | Acceptance cum work order for Additional work of Morum cutting, concrete cutting, Hard rock cutting, Bituminus Road cutting different dia DI (K-7) & HDPE pipe line with other allied works from Dabor OHR Zone-II (Pahargara, Mohanpur, Partabpur, Bolkundi etc) distribution under Retrofitting Chotkara-Kanskuli W/S Scheme Zone II under RCFA Division-I PHE Dte. | 1586/RCD-I | 07/09/2021 | 30 | DAS & CHAKRABORTY | 11.29 | 10.88 | 100 | 0
1389 | PASCHIM BARDHAMAN | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. , SM/09242 | School | Acceptance cum formal order for the work of Providing water supply to Dubrajpur F.P. school under Kanksa block covered by Kanksa (Zone-II) PWSS having Electricity but uncovered by PWSS under DWSD, PHE Dte | 119/DWSD | 01/02/2022 | 20 | BASANTI TRADERS | 2.12 | 1.96 | 100 | 0
1390 | PASCHIM BARDHAMAN | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. , SM/09242 | School | Acceptance cum formal order for the work of Providing water supply to Shibpur F.P. school under Kanksa block covered by Kanksa (Zone-II) PWSS under DWSD, PHE Dte | 118/DWSD | 01/02/2022 | 15 | M/S MONDAL ENTERPRISE | 2.12 | 2.03 | 100 | 0
1391 | PASCHIM BARDHAMAN | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. , SM/09242 | School | Acceptance cum formal order for the work of Providing water supply to Birudiha High school under Kanksa block covered by Kanksa (Zone-II) having electricity but uncovered by PWSS under DWSD, PHE Dte (SL-26) | 120/DWSD | 01/02/2022 | 20 | BASANTI TRADERS | 2.11 | 2.06 | 100 | 0
1392 | PASCHIM BARDHAMAN | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. , SM/09242 | School | Acceptance cum formal order for the work of Providing water supply to Pratabpur high school under Durgapur -Faridpur block covered by Jamgora-Jagannathpur PWSS under DWSD, PHE Dte (SL-20) | 115/DWSD | 01/02/2022 | 20 | M/S MONDAL ENTERPRISE | 1.1 | 1.1 | 100 | 0
1393 | PASCHIM BARDHAMAN | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. , SM/09242 | School | Acceptance cum formal order for the work of Providing water supply to Ijjatganj Junior high school under Kanksa block covered by Kanksa (Zone-II) PWSS under DWSD, PHE Dte | 116/DWSD | 01/02/2022 | 15 | M/S MONDAL ENTERPRISE | 1.1 | 0.38 | 100 | 0
1394 | PASCHIM BARDHAMAN | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. , SM/09242 | School | Acceptance cum formal order for the work of Providing water supply to Kanksa Poral para F.P. school under Kanksa block covered by Kanksa (Zone-II) PWSS under DWSD, PHE Dte | 117/DWSD | 01/02/2022 | 15 | BABA LOKENATH ENTERPRISE | 1.1 | 1.1 | 100 | 0
1395 | PASCHIM BARDHAMAN | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. , SM/09242 | School | Acceptance cum formal order for the work of providing water supply to panagarh bazar high school under Kanksa block covered by Kanksa (Zone-II) PWSS having electricity but uncovered by PWSS under DWSD ,PHE Dte (Sl-24) | 121/DWSD | 20/01/2022 | 15 | BABA LOKENATH ENTERPRISE | 2.12 | 2.08 | 100 | 0
1396 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order for laying of HDPE Pipe line from Panuria Bazar to Shirikhad Para under Jamgram Panuria W/S Scheme under RCFA Division-I PHE Dte. | 344/RCD I | 30/01/2023 | 15 | SHREE DURGA ENTERPRISE | 1.35 | 1.34 | 100 | 0
1397 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Preparation of DPR for Augumentation of Jamgram Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte.(sl no 03) | 2347/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 2.88 | 2.88 | 100 | 0
1398 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Material Requisition To Resource Division | 2350/RCD-I | 28/09/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1399 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | New Connection at Jamgram Water Supply Scheme. | BP-2022-23-28 | 31/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0 | 0
1400 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (length-160 mtr) at Jamgram OHR site of Augmentation of Jamgram Piped Water Supply Scheme under Barabani Block under RCFA Division-I PHE Dte. | 2479/RCD-I | 23/08/2023 | 30 | SRI KRISHNA ENTERPRISE | 36.83 | 0 | 0 | 5
1401 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE Dte. (Part-C) | 1271/RCD-I | 02/06/2022 | 90 | ALOKESH BANERJEE | 23.92 | 23.08 | 52 | 80
1402 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-D) | 1272/RCD-I | 02/06/2022 | 90 | B.T.M CONCERN | 55.19 | 55.16 | 100 | 100
1403 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-B) | 1270/RCD-I | 02/06/2022 | 90 | M/S S.K. ENTERPRISE | 24.81 | 23.46 | 100 | 100
1404 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Jamuria Rural-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3138/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100 | 100
1405 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order for rising Main for Augmentation of Jamgram Piped Water Supply Scheme at Baraboni Block Under RCFA - Div - I PHE Dte. | 3278/RCD I | 20/12/2022 | 21 | DEBI PRASAD MAJI | 15.63 | 11.07 | 100 | 100
1406 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at Gourbazar Pump House under Augmentation of Jamgram Piped Water Supply Scheme. | 1319/AMD | 21/08/2024 | 45 | INDUSTRIAL ELECTRICAL CORPORATION | 2.79 | 0 | 0 | 100
1407 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Supply, delivery & installation of Pumping Machineries and other Electro-Mechanical equipment at Jamgram Piped Water Supply Scheme under Asansol Mechanical Division, P.H.E Dte. Block- Barabani, District-Paschim Bardhaman. | 360/AMD | 09/02/2023 | 90 | INDUSTRIAL ELECTRICAL CORPORATION | 46.39 | 45.36 | 97.78 | 100
1408 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order for Construction of 200 cum capacity 20 mtr. Staging height RCC Over Head Reservoir (pipe connection and cost of pipes, speciials at jamgram Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. | 1403 RCD I | 12/04/2023 | 366 | SRI KRISHNA ENTERPRISE | 72.48 | 72.48 | 100 | 99
1409 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme including FHTC work Block Barabani, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. (Part-A) | 1053/RCD-I | 23/03/2023 | 30 | SRI KRISHNA ENTERPRISE | 90.22 | 34.13 | 37.83 | 55
1410 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order Additional work for Distribution Network including adopting trench less technology at two places under Augmentation of Jamgram Water Supply Scheme under RCFA Division-I PHE Dte. | 2223/RCD-I | 17/07/2023 | 30 | B.T.M CONCERN | 39.15 | 35.84 | 91.54 | 92
1411 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum Work Order for Balance work of Laying distribution system within distribution network for Augmentation of Jamgram PWSS under RCFA Div- I, PHE Dte. (Part-D) | 927/RCD-I | 15/03/2024 | 45 | B.T.M. CONCERN | 35.23 | 34.38 | 97.58 | 89
1412 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Providing FHTC through retrofitting under Augmentation of Jamgram PWSS (Part-I) under RCFA Div-I, PHE Dte. | 2520/RCDI | 20/10/2022 | 30 | B.T.M CONCERN | 50.77 | 26.46 | 50.97 | 65
1413 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Providing FHTC through retrofitting under Augmentation of Jamgram PWSS (Part-I) under RCFA Div-I, PHE Dte. | 2519/RCDI | 20/10/2022 | 712 | MAA ENTERPRISE | 22.6 | 14.53 | 86.42 | 60
1414 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order for Construction of Pump House at Jamgram for Augmentation of Jamgarm Piped Water Supply Scheme under RCFA, Division-I, PHE Dte. | 3279/RCDI | 20/12/2022 | 468 | R B ENTERPRISE | 20.73 | 18.51 | 90.95 | 100
1415 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Providing FHTC through retrofitting under Augmentation of Jamgram PWSS (Part-III) under RCFA Div-I, PHE Dte. | 3274/RCDI | 20/12/2022 | 623 | M/S S.K. ENTERPRISE | 22.96 | 20.69 | 100 | 50
1416 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order Ground Level Reservoir of capacity 105 cum for Augmentation Jamgram & its Adjoining Mouza Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1062/RCD-I | 23/03/2023 | 375 | SUBHADEEP DAS | 12.25 | 11.43 | 93.26 | 100
1417 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order for Emergency Repairing of 750 mm dia Rising main with supply of leak repairing clamp and allied works related to supply of CI/DI specials etc, under Augmentation of Itapara Water Supply Scheme under RCFA Division-I PHE Dte. | 2612/RCD-I | 12/09/2023 | 20 | MAKALI ENGINEERING CORPORATION | 98.81 | 98.81 | 100 | 100
1418 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order Sinking of 4 (Four) nos river bed tube wells including collecting main & other allied works at Unionpara H/W under RCFA Part-II at Damodar river under Unionpara Water Supply Scheme under RCFA Division-I PHE Dte. | 2483/RCD-I | 23/08/2023 | 30 | T.R. ENTERPRISE | 11.42 | 11.08 | 100 | 100
1419 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order for Additional work for laying 110 mm dia HDPE pipe with construction of piller for crossing a water body within Jamgram PWSS Part-C under Augmentation of Jamgram PWSS under RCFA Division-I PHE Dte. | 3458/RCD-1 | 24/11/2023 | 15 | ALOKESH BANERJEE | 3.39 | 2.53 | 100 | 100
1420 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Additional work like Horizonal Augar boring, dismantaling concrete and allied works in releted to part-B of Augmentation of jamgram PWSS under RCFA division-I PHE Dte. | 3394/RCD-I | 23/11/2023 | 7 | M/S S.K. ENTERPRISE | 0.8 | 0.8 | 100 | 100
1421 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum Work Order for Construction of Switch room and balance work of approach road towards Gourbazar Head Works Site under Augmentation of Jamgram PWSS under RCFA Division-I PHE Dte | 921/RCD-I | 15/03/2024 | 60 | R B ENTERPRISE | 8.42 | 8.25 | 100 | 100
1422 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. , SM/10643 | Augmentation | Acceptance cum work order for Additional by constructing pillar for water body crossing including adopting trench less technology (e.g. Jack Pushing Method etc) at Three nos location including MS work and allied works related to rising main of Itapara and adjoining mouzas under Augmentation of Jamgram Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 502/RCD-I | 12/02/2024 | 232 | DURGA DAS MONDAL | 38.11 | 36.63 | 100 | 100
1423 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Formal order for the work of Supplying and laying of different dia UPVC pipe line with necessary allied works at Rangamatia (JL-10),Benebandhi(JL-11) Maheshpur(JL-12) Mouza of Augmentation of RCFA Part-III Piped W/s Scheme (Zone-I) (Part-B) W/s Scheme under DWSD,PHE Dte (SL-07) | 874/DWSD | 26/05/2022 | 25 | BASANTI TRADERS | 22.24 | 18.46 | 82.99 | 0
1424 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal work order for the work of Withdrawing existing damaged 150 mm dia AC pipe line and laying 160 mm dia (OD) HDPE pipe in the same trench from Madhaiganj OHR site towards Rangamati village under RCFA Pt-III W/S Scheme under DWSD, PHE Dte (SL-24) | 69/DWSD | 13/01/2021 | 15 | KARMAKAR CONSTRUCTION | 2.31 | 2.31 | 100 | 0
1425 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Formal order for the work of Construction of 500 M3 capacity 20 mtr staging height RCC Over Head Reservoir (OHR) at Mohal under Augmentation of RCFA Part-III (Zone-I/Part-B) W/s Scheme under DWSD, PHE Dte (SL_14) | 278/DWSD | 16/05/2022 | 184 | RANJIB GHATAK | 96.93 | 82.66 | 85.28 | 85
1426 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Supplying and laying of different dia UPVC pipe line with necessary allied works at Rangamatia (JL-10),Benebandhi(JL-11) ,Maheshpur(JL-12) mouza of Augmentation of RCFA Part-III W/s Scheme (Zone-I)/Part-A) W/S Scheme under DWSD,PHE Dte.(SL-02) | 1005/DWSD | 28/06/2022 | 15 | KIRON ENTERPRISE | 19.46 | 16.77 | 86.18 | 85
1427 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle for site vigit against JJM related scheme) for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.01.2023 to 30.06.2023).(Sl-01) | 1801/DWSD | 30/12/2022 | 182 | PRAMIT CHATTERJEE | 0.82 | 0.8 | 100 | 0
1428 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Providing And Installation of Submersible pumping Machineries, PDB-Cum-MCC Panel and other Electro-Mechanical accessories at Head Works site at Pansuli under Augmentation of RCFA Part-III (Zone-I) Water Supply Scheme, Block-Faridpur-Durgapur, Dist.-Paschim Bardhaman. | 252/AMD | 02/02/2023 | 30 | INDUSTRIAL ELECTRICAL CORPORATION | 33.68 | 30.8 | 91.44 | 0
1429 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Additional work for rest portion UPVC pipe line and FHTC at Benabandhi (JL-11) and Maheshpur(JL-12) mouza under Augmentaiton of RAFA Part-III Zone-I piped W/S Scheme under DWSD,PHE Dte | 739/DWSD | 22/05/2023 | 60 | KIRON ENTERPRISE | 51.72 | 48.44 | 93.67 | 100
1430 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Formal order for the work of Construction of 150 M3 capacity 20 mtr staging height RCC over Head Reservoir (OHR) at Nutandanga under Augmentation of RCFA Part-III W/s Scheme (Zone-I/Part-B) under DWSD, PHE Dte (SL-13) | 875/DWSD | 26/05/2022 | 184 | M/S PROCHESTA ENTERPRISE | 64.33 | 56.33 | 87.56 | 0
1431 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Laying of CI Pipe line ,sluice valves ,UPVC pipe line and allied works at Madhaiganj H/W Site under Modified RCFA Part-III W/s Scheme under DWSD, PHE Dte (SL-03) | 75/DWSD | 21/01/2022 | 15 | KARMAKAR CONSTRUCTION | 2.57 | 2.5 | 100 | 0
1432 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Continuation order for the work of extension of pipe line from the existing pipe line from command area of Gourbazar-Ichhapur piped W/s Scheme of Ichhapur area fro providing of FHTC at Ichhapur mouza(JL-50) under DWSD ,PHE Dte | 192/DWSD | 15/02/2022 | 15 | SHWET BARANI | 4.45 | 4.45 | 100 | 100
1433 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Additional work at RCC OHR site at NUTANDANGA under Augmentation of RCFA Part-III (Zone-I) Piped W/s Scheme under DWSD,PHE Dte | 766/DWSD | 22/05/2023 | 15 | M/S PROCHESTA ENTERPRISE | 4.49 | 4.48 | 100 | 100
1434 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 16,17,18 Ext ) to combat drought like situation at Pansiuli head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-02) | 11/SPOT/DWSD | 16/06/2023 | 4 | KARMAKAR CONSTRUCTION | 1 | 1 | 100 | 100
1435 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No -11,12 Ext & 4 New ) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-03) | 12/SPOT/DWSD | 16/06/2023 | 4 | KARMAKAR CONSTRUCTION | 1 | 1 | 100 | 100
1436 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 7,9,10 Ext) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-03) | 06/SPOT/DWSD | 16/06/2023 | 4 | KARMAKAR CONSTRUCTION | 1 | 1 | 100 | 100
1437 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Laying additional distribution pipeline with necessary allied works for providing FHTC work under Durgapur-Faridpur Block of Augmentation of RCFA Part-III W/s Scheme (Zone-I) under DWSD,PHE Dte | 1146/DWSD. | 04/07/2022 | 20 | SHWET BARANI | 5.69 | 5.64 | 100 | 100
1438 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Instalation of Water Level Indicater at Loudoha head work site under RCFA,Part-III ,Zone -I W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-07) | 16/SPOT/DWSD | 16/06/2023 | 7 | KARMAKAR CONSTRUCTION | 0.77 | 0.77 | 100 | 100
1439 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Drawing ,design and surveying work for proposed piped W/s Scheme of Sarpi W/S Scheme under DWSD, PHE Dte(SL-02) | 1022/DWSD | 04/07/2022 | 10 | APEX ENGINEERING | 4.09 | 4.09 | 100 | 100
1440 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No -10,13 Ext & 14 New ) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-04) | 13/SPOT/DWSD | 16/06/2023 | 4 | KARMAKAR CONSTRUCTION | 1 | 1 | 100 | 100
1441 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 1,3,4 Ext) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-01) | 1254/DWSD | 02/08/2023 | 10 | KARMAKAR CONSTRUCTION | 1 | 1 | 100 | 100
1442 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 3,4,5 Ext) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-01) | 04/SPOT/DWSD | 16/06/2023 | 4 | KARMAKAR CONSTRUCTION | 1 | 1 | 100 | 100
1443 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of RCFA Part - III Zone - I (PART - B) under Durgapur Faridpur Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No - 03) | 1201/DWSD | 27/07/2023 | 7 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
1444 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Material Requisition To Resource Division | 255/A/DWSD | 15/02/2023 | 0 | Resource Division | 30.8 | 0 | 0 | 0
1445 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Material Requisition To Resource Division | 1377/DWSD | 22/09/2022 | 0 | Resource Division | 61.6 | 0 | 0 | 0
1446 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Material Requisition To Resource Division | 256/DWSD | 15/02/2023 | 0 | Resource Division | 61.6 | 0 | 0 | 0
1447 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Material Requisition To Resource Division | 1228/DWSD | 17/08/2022 | 0 | Resource Division | 9.52 | 0 | 0 | 0
1448 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Urgent Repairing of 250 dia pipe line with necessary alid works at Nabaghanapur to Jhanjra Project Portion under Augmentation 0f RCFA ,Pt-III, Zone -I W/S Scheme (JJM) Under Durgapur Water Supply Division, P.H.E. Dte. (Sl-02) | 838/DWSD | 05/06/2023 | 15 | RUBY CONSTRUCTION | 0.75 | 0 | 0 | 100
1449 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Providing FHTC work at Rangamati Mouza(JL-10) under Augmentation of RCFA Part-III(Zone-I) piped W/S Scheme under DWSD,PHE Dte (SM/11454) | 1066/DWSD | 12/07/2023 | 30 | BASANTI TRADERS | 18.67 | 11.68 | 62.53 | 50
1450 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Additioinal work for rest portion UPVC pipe line at Rangamati mouza under Augmentation of RCFA Part-III(Zone-I) piped W/S Scheme under DWSD,PHE Dte (SM/11454) | 1073/DWSD | 12/07/2023 | 25 | BASANTI TRADERS | 9.56 | 6.54 | 68.35 | 100
1451 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for Additional work for laying MS pipe and allied works including Adopting trench less technology (e.g. jack Pushing Method etc) for crossing of NH-60 near Pandabeswar H/W Site to carry 350 mm dia distribution & 250 mm dia rising main pipe line under RCFA Part-III Zone-I under RCFA Division-I PHE Dte. | 1521/RCD-I | 14/06/2024 | 45 | HIRANMAY GHOSH | 14.09 | 0 | 0 | 0
1452 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Formal order for the work of Sinking of 4 Nos 200 mm dia river bed tube wells with collecting main in river Ajoy at Pansuili H/W under Augmentation of RCFA Part-III(Zone-I)(Part-B) W/S Scheme under DWSD,PHE Dte. (SL_09) | 856/DWSD | 24/05/2022 | 10 | RANAJOY ENTERPRISE | 19.57 | 14.03 | 100 | 100
1453 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Formal order for the work of of Sinking of 4 Nos 200 mm dia river bed tube wells with collecting main in river Ajoy at Pansuili H/W under Augmentation of RCFA Part-III(Zone-I)(Part-A) W/S Scheme under DWSD,PHE Dte. (SL_15) | 857/DWSD | 24/05/2022 | 15 | RANAJOY ENTERPRISE | 18.48 | 14.81 | 100 | 100
1454 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Formal order for the work of Augmentation of RCFA Part-III )Zone-I/Part-B) piped W/s Scheme by construction of 250 M3 RCC OHR of 20 mtr staging height with necessary interconnection soil investigation including laying distribution network and Functional House Tap Connection (FHTC) under DWSD,PHE Dte ,Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (Sl-01 | 1779/DWSD | 23/12/2022 | 12 | UMWELT ENGINEER PVT LTD | 919.36 | 917.39 | 100 | 90
1455 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Continuation order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle for site vigit against JJM related scheme) for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.07.2023 to 31.12.2023).(Sl-01) | 944/DWSD | 28/06/2023 | 183 | PRAMIT CHATTERJEE | 0.82 | 2.38 | 100 | 100
1456 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Quotation for natundanga O.H.R. under RCFA-III(Zone-I) Water supply scheme. | BP-2024-25-43 | 05/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.09 | 0 | 0 | 0
1457 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Formal order for the work of augmentation at Madhaiganj of RCFA Part-III (Zone-I/C) piped W/s Scheme including laying distribution network and functional household tap connection (FHTC) under Durgapur W/S Division, PHE Dte Block-Durgapur-Faridpur ,Dist.-Paschim Bardhhaman. | 05/DWSD | 02/01/2023 | 120 | IJABUL SEKH | 279.99 | 236.03 | 84.3 | 100
1458 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum Work Order for Construction of Sub-Station Building at Ramnagar H/W Site within Pandabeswar Block under RCFA Part-III (Zone-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 3101/RCD-I | 13/12/2024 | 292 | RANJIB GHATAK | 36.86 | 0 | 0 | 90
1459 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for Sinking of 4 (Four) nos 200 mm dia Horizontal River Bed Tube Well with fitting of 200 mm dia Strainer (12.2 mtr) in river Ajay & Collecting line under RCFA Part-III Zone-I Water Supply Scheme under RCFA Division-I PHE Dte. | 1523/RCD-I | 14/06/2024 | 45 | T M CONCRETE CREATION PVT.LTD | 14.42 | 0 | 0 | 100
1460 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for Laying of Rising main and other allied works from Panshuili H/W Site to Natundanga OHR of Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA Division-I PHE Dte. | 2556/RCD-I | 29/10/2024 | 180 | UNITED CONSTRUCTION | 36.87 | 2.57 | 6.96 | 70
1461 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for Additional pipe line with of HDPE pipe with at Pratappur and Kalikapur with re-connection of existing FHTC and other allied works of Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA Division-I PHE Dte. | 2628/RCD-I | 14/11/2024 | 182 | SIMA ENTERPRISE | 57.5 | 9.31 | 16.19 | 80
1462 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for Allied work of Replacement of A.C pipe of Main Distribution pipeline from Madhaiganj OHR to RANGAMATI Village including ROAD Restoration of Rangamati Village Of Augmentation of RCFA part III Zone I under RCFA Div- I, PHE Dte. | 2547/RCD-I | 29/10/2024 | 154 | BASANTI TRADERS | 32.79 | 4.65 | 14.17 | 40
1463 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for HDPE distribution pipe line laying for Gourbazar and Bhabanandapur village and other allied works under Augmentation of RCFA Part-III (Zone-I) PWSS under RCFA Davison-I PHE Dte. | 1485/RCD-I | 15/05/2025 | 120 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 34.41 | 0 | 0 | 80
1464 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for Supplying laying HDPE distribution pipe line at JhanjraPaschim Para at Durgapur Faridpur Block under Augmentation of RCFA Part-III Zone-I under RCFA Division-I PHE Dte. | 1511/RCD-I | 20/05/2025 | 87 | UNITED CONSTRUCTION | 22.25 | 0 | 0 | 60
1465 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Formal order for the work of Augmentation at Natundanga of RCFA Part-III (Zone--I/A) piped W/s Scheme including laying distribution network (LDS) and functinal household tap connection (FHTC) under Durgapur W/s Division, PHE Dte ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman (SL-02) | 1778/DWSD | 23/12/2022 | 739 | ALOK ENTERPRISE | 634.56 | 448.32 | 70.75 | 75
1466 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum formal order for the work of Additional Wash out work for 200 mm dia River Bed Tube Wells in River Ajoy at PANSULI Head Works Site under Augmentation of RCFA, Pt-III, Zone - I Part -A Water Supply Scheme under DWSE, PHE Dte. (Sl-05) | 14/SPOT/DWSD | 16/06/2023 | 631 | AMARANJALI CONSTRUCTION | 0.61 | 0.6 | 100 | 100
1467 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for Additional work for laying MS pipe and allied works including Adopting trench less technology (e.g. Jack Pushing Method etc) for crossing of Railway Track near Fulbagan more DVC para to carry 250 mm dia distribution line of Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA Division-I PHE Dte. | 2635/RCD-I | 14/11/2024 | 60 | RUBY CONSTRUCTION | 19.07 | 0 | 0 | 100
1468 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for Repairing and renovation of Laudoha OHR site at Laudoha under RCFA Part-III Water Supply Scheme within Durgapur Faridpur Block under RCFA Division-I PHE Dte. | 1021/RCD-I | 16/03/2024 | 45 | M/S A G CONSTRUCTION | 8.87 | 8.84 | 100 | 100
1469 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum Work Order for Balance work of distribution pipe line including allied works at Sarpi village under Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme under RCFA Division-I PHE Dte. | 3108/RCD-I | 13/12/2024 | 45 | UNITED CONSTRUCTION | 30.42 | 11.6 | 30.07 | 100
1470 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for Improvement & Overhauling of 5 nos Iron Removal Plant (pressure type), each capacity 50 cum/Hr at Bhaburia H/W Site under Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA W/S Division-I, PHE Dte. | 2615/RCD-I | 13/11/2024 | 30 | SREE ENTREPRENEUR | 24.71 | 6.31 | 20.94 | 100
1471 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for Repairing and renovation of Pansiuli OHR site under Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme within Durgapur Faridpur Block under RCFA Division-I PHE Dte. | 1022/RCD-I | 16/03/2024 | 564 | SHWET BARANI | 13.3 | 0 | 0 | 100
1472 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for Additional work for laying MS pipe and allied works including adopting trench less technology(e.g. Jack Pushing Method etc)of 03(Three) nos. location at Sarpi Maji para, Shyamsundarpur More and Kumardihi gram near stadium under Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme under RCFA Div-I, PHE Dte. | 137/RCD-I | 08/01/2025 | 30 | MAK CONSTRUCTION CO | 22.97 | 0 | 0 | 100
1473 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) , SM/11454 | Augmentation | Acceptance cum work order for Sinking of 4 nos 200 mm dia River bed tube wells with collecting main and allied work in the river Ajoy at Pansuili Head Works Site under Augmentation of RCFA Part-III (Zone-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1405/RCD-I | 15/05/2025 | 25 | AMARANJALI CONSTRUCTION | 11.04 | 0 | 0 | 100
1474 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Kanksa zone -II Ph-I W/s Scheme to combat draught like situation at in Kaksa Block to providing FHTC at Ijjatganj Mouza (JL-79) under DWSD,PHE Dte..(SL-04) | 273/DWSD | 26/02/2021 | 25 | RANJIB GHATAK | 4.97 | 0 | 0 | 0
1475 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal work-order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jotbalaram & Amdohi mouza (JL-08 & 25) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-14) | 1317/DWSD | 09/12/2020 | 45 | JOY GURU ENTERPRISE | 25.99 | 3.37 | 100 | 0
1476 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of laying of distribution pipe line with necessary allied work at Domra and Piariganj mouza under Tilakchandrapur W/s Scheme for FHTC under DWSD, PHE Dte. | 422/DWSD | 30/03/2022 | 10 | AMARANJALI CONSTRUCTION | 4.74 | 4.73 | 100 | 0
1477 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing restoration of distribution system of Nachan OHR (Part-B) from Nachan More to Dhaboni Lobnapara under Jamgora-Jagannathpur piped W/s Scheme under DWSD ,PHE Dte.(SL-05) | 412/DWSD | 30/03/2022 | 15 | PAYAL CONSTRUCTION | 4.63 | 1.64 | 100 | 0
1478 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road for extension of pipe line from existing pipe line of Kanksa (Zone-II) (Phase-II) W/s Scheme to laying branch pipe line in Kanksa block to providing FHTC at Kanksa Mouza (JL-89) at Jhinuk Raia Hotel para ,Duck bungalow colony para under DWSD, PHE Dte.(SL-16) | 431/DWSD | 30/03/2022 | 15 | GITA CONSTRUCTION | 4.95 | 4.95 | 100 | 0
1479 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Additional work for providing FHTC tap connection with JJM at Radhamohanpur mouza-36 and its adjoining area under command area of Basudha piped W/s Scheme under DWSD,PHE Dte (SL-02) | 581/DWSD | 21/04/2022 | 7 | JOY GURU ENTERPRISE | 4.77 | 4.83 | 100 | 0
1480 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Withdrawing of damaged 160 mm dia UPVC pipe and laying of additional length of pipe at Basudha and Ajodhya and repairing of damaged pipe due to newly constructed WBSRDA road and others allied works of Basudha W/s Scheme under DWSD,PHE Dte (SL-08) | 1074/DWSD | 12/07/2022 | 15 | MAK CONSTRUCTION CO. | 4.26 | 4.24 | 100 | 0
1481 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Formal order for the work of Restoration of exiting house hold tap connection (Damaged) and re connection of the same in connection of JJM and changes of defective pipe line of 90/110/125/140/200 mm dia UPVC pipe line at different places of distribution main command area of Basudha Piped W/s Scheme under DWSD,PHE Dte (SL-08) | 1160/DWSD | 01/08/2022 | 10 | MD AAMIR KHAN | 5.04 | 4.99 | 100 | 0
1482 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Continuation order for the work of providing functional household tap connection (FHTC) in connection with JJM at Kajladihi mouza(JL-26) under command area of Krishnapur Piped W/S Scheme ,Block-Kanksa under DWSD,PHE Dte. | 346/DWSD | 17/03/2022 | 15 | THE STAR & CO | 2.72 | 0 | 0 | 0
1483 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Construction of boundary wall at Kanksa (Zone-II & Ph-I W/s Scheme pump house No-II at Ijjatganj under DWSD ,PHE Dte (SL-04) | 186/DWSD | 04/02/2021 | 45 | M/S BADAL GHOSH | 4.92 | 0 | 0 | 0
1484 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Panagarh mouza(JL-85) of Pal para,Hazra bera,Kumar para ,near Tilakchandrpaur Panchayat near Panagarh bypass under DWSD,PHE Dte (SL-12) | 1104/DWSD | 30/07/2021 | 15 | GITA CONSTRUCTION | 4.98 | 4.98 | 100 | 0
1485 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Kanksa mouza(JL-89) at Kanksa Jhinuk Garia and Kanksa Hotal para under DWSD,PHE Dte (SL-13) | 1105/DWSD | 30/07/2021 | 15 | GITA CONSTRUCTION | 4.82 | 4.82 | 100 | 0
1486 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum form order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Kanksa mouza(JL-89) at Kanksa Duck Bunglow and Kanksa colony para under DWSD,PHE Dte (SL-14) | 1106/DWSD | 30/07/2021 | 15 | GITA CONSTRUCTION | 4.98 | 4.98 | 100 | 0
1487 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Replace damaged 250 mtr 150 mm dai AC pipe with the UPVC 160 mm dia pipe line at Panagarh Baruipara ,Ijjatganj OHR cleaning leakage bursting at Ijjatganj and others allied works of Kanksa Zone-II ph-II W/s Scheme under DWSD,PHE Dte (SL_06) | 1408/DWSD | 29/09/2021 | 15 | RANJIB GHATAK | 4.2 | 4.2 | 100 | 0
1488 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Formal order for the work of Sinking of 2 Nos (300X200 mm) dia tube well 120 mtr deep by DR rig method using PVC pipe and fiber glass reinforced epoxy resin slotted at tube well No-01 & 02) Molandighi of Bistupur piped W/s Scheme under Durgapur W/s Division, PHE Dte (SL-03) | 1676/DWSD | 30/11/2021 | 35 | M/S. D. PALIT & CO. | 18.62 | 1.29 | 100 | 100
1489 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road for extension of pipe line from existing pipe line of Kanksa (Z-II)(Ph-II) W/s Scheme to laying branch pipe line in kanksa block for providing FHTC at PanagarhJL_85) at Palpara ,Hazra Para ,Kumanrpara near TC pur Panchayat ,Panagarh bypass under DWSD PHE Dte (Sl-04) | 78/DWSD | 24/01/2022 | 15 | GITA CONSTRUCTION | 3.46 | 3.39 | 100 | 0
1490 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Providing water supply of office of the deputy inspector General of Police group center at Radhamohanpur under Kanksa and Bonkati GP having with electricity but uncovered by PWSS under DWSD,PHE Dte (SL-03) | 582/DWSD | 21/04/2022 | 7 | JOY GURU ENTERPRISE | 2.12 | 2.12 | 100 | 0
1491 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Supplying and laying of 200 mm dia UPVC pipe line from Hetedoba OHR to Zero point towards SARPI more road of Improvement of Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte (SL-06) | 723/DWSD | 06/05/2022 | 15 | BABA LOKENATH ENTERPRISE | 30.27 | 5.38 | 100 | 0
1492 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Formal order for the work of Laying of 110/90/75 mm dia HDPE pipe line with necessary allied works at Annandapur mouza ICDS to Dompara under Kanksa (Zone-I ) W/s Scheme for upcoming combat draught like situation in Kanksa block under DWSD,PHE Dte (SL-04) | 832/DWSD | 24/05/2021 | 15 | M/S KALYANI ENTERPRISE | 5.12 | 0.74 | 100 | 0
1493 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Kanksa mouza(JL-89) at Kanksa Adibashipara and Kanksa 3 No colony under DWSD,PHE Dte (SL-15) | 1107/DWSD | 30/07/2021 | 15 | GITA CONSTRUCTION | 4.89 | 4.89 | 100 | 0
1494 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07519 | Retrofitting | Acceptance cum work order for Re-connection of FHTC & additional Functional Household Tap Connection (FHTC) for Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC for new pipe line laying under RCFA Division-I PHE Dte. | 2630/RCD-I | 14/11/2024 | 135 | SHWET BARANI | 23.56 | 0 | 0 | 100
1495 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15663 | Augmentation | Formal order for the work of Additional work of laying of HDPE distribution pipe line 75/90 mm dia and providing FHTC at Kotalpukur (JL-30),Nimtakuri(JL-32) & Masna(JL-31) mouzas of Kotalpukur piped W/s Scheme under DWSD,PHE Dte (SL-03) | 1426/DWSD | 08/10/2022 | 10 | JOY GURU ENTERPRISE | 12.21 | 3.51 | 99.97 | 0
1496 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15663 | Augmentation | Acceptance cum formal order for the work of Route survey and preparation of DPr for Augmentation of Garkilla-Kherobari,Banagram, Kotalpur, Dhobaru piped W/s Scheme under DWSD, PHE Dte | 525/DWSD | 29/03/2023 | 15 | MEASURE LAND | 9.24 | 9.24 | 100 | 0
1497 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15663 | Augmentation | Quotation for Kotalpukur W/S Scheme , Pump House No- 01 , Panagarh CCC | BP-2022-23-339 | 17/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.47 | 0 | 0 | 0
1498 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15663 | Augmentation | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at Kotalpukur,Masna,Nimtikuri mouzas of Kotalpukur piped W/s Scheme under DWSD, PHE Dte under DWSD, PHE Dte (Part-A ,B & C) (SL-02) | 773/DWSD | 17/05/2022 | 45 | JOY GURU ENTERPRISE | 41.01 | 0 | 0 | 0
1499 | PASCHIM BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15663 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and internal House Wiring for Tube Well No. -01 at Kotalpukur (Nimtikuri) Water Supply Scheme under CMD, PHE Dte., Paschim-Bardhaman. | 1575/CMD | 04/04/2023 | 30 | SAIKAT ENTERPRISE | 8.99 | 8.48 | 100 | 100
1500 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15663 | Augmentation | Formal order for the work of Balance work of construction of Pump house /Chlorine room sinking of 150X80 X120 mm depth tube well supplying laying of HDPE distribution pipe in and providing FHTC at Kotalpukur(JL-30) ,Nimtakuri(JL-30),Masna(JL-31) mouzas of Kotalpukur piped W/S scheme under DWSD,PHE Dte (SL-22) | 733/DWSD | 15/05/2023 | 535 | JOY GURU ENTERPRISE | 146.29 | 94.38 | 66.02 | 100
1501 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15663 | Augmentation | Supply delivery and installation of submersible pumping machinery, chlorination system and internal house wiring for tube well no-2 at augmentation of ground water based water supply scheme for Kotalpukur under Asansol Mechanical Division. PHE Dte. | 2202/AMD | 27/12/2024 | 102 | SAIKET SINHA | 5.93 | 0 | 0 | 100
1502 | PASCHIM BARDHAMAN | Asansol Mechanical | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. , SM/16775 | Augmentation | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site at Pansuli under RCFA-III(Zone-I) Water Supply Scheme, Block: Faridpur-Durgapur, Dist. Paschim Bardhaman. | 873/AMD | 04/04/2023 | 366 | INDUSTRIAL ELECTRICAL CORPORATION | 137.21 | 136.29 | 100 | 73
1503 | PASCHIM BARDHAMAN | Asansol Mechanical | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. , SM/16775 | Augmentation | Withdrawing and lowering of Submersible pumping machineries at RBTW No-9 & 14 with Other allied works at Pansuli Head Works Site under RCFA Part-III(Zone-I) Water Supply Scheme. | 1036/AMD | 16/07/2024 | 30 | CIEMENICS | 4.05 | 4 | 100 | 100
1504 | PASCHIM BARDHAMAN | Asansol Mechanical | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. , SM/16775 | Augmentation | Providing of lighting luminaries, with yard lighting arrangement of Laudoha O.H.R. premises under Improvement of RCFA Part-I W/S Scheme. | 1131/AMD | 30/07/2024 | 167 | V. P. CONCERN | 3.84 | 0 | 0 | 100
1505 | PASCHIM BARDHAMAN | Asansol Mechanical | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. , SM/16775 | Augmentation | Supply, delivery & installation of Electro-Mechanical equipment and other allied works at Pansuli Head Works Site under improvement of RCFA Part-III(Zone-I) Water Supply Scheme, Asansol Mechanical Division, P.H.E Dte. Block-Faridpur-Durgapur, District-Paschim Bardhaman. | 1814/AMD | 29/10/2024 | 277 | SUNRISE ENGINEERING CORPORATION | 48.22 | 0 | 0 | 100
1506 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16902 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of DHOBARU (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No - 02) | 1194/DWSD | 25/07/2023 | 7 | CARTO | 0.78 | 0.78 | 100 | 100
1507 | PASCHIM BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16902 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Dhobaru Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | 1578/CMD | 04/04/2023 | 30 | DUTTA ENTERPRISE | 8.97 | 8.5 | 100 | 100
1508 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16902 | Augmentation | Formal order for the work of Balance work of construction of Pump house /Chlorine room sinking of 150X80 X120 mm depth tube well supplying laying of HDPE distribution pipe in and providing FHTC at Dhobaru mouzas of Dhobaru piped W/S scheme under DWSD,PHE Dte | 1133/DWSD | 20/07/2023 | 30 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 109.55 | 70.62 | 100 | 80
1509 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16902 | Augmentation | Additional quotation for effecting NSC under revised estimate for Dhobaru W/S Scheme | BP-2023-24-366 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.76 | 0 | 0 | 0
1510 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Quotation money for New Connection at Darbardanga | BP-2023-24-17 | 05/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.48 | 0 | 0 | 0
1511 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Acceptance cum work order Sinking of 03 (Three) Nos river bed tube wells including collecting main, Sluice Valve chamber & other allied work at Darbardanga H/W at Ajoy River under Augmentation of Jamuria Rural (Zone I & II) Water Supply Scheme under RCFA Division-I PHE Dte. | 1076/RCD-I | 23/03/2023 | 90 | MAA ENTERPRISE. | 19.58 | 8.87 | 100 | 100
1512 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 03 (Three) nos. location at Lalganj Domohani Road, Kelejhora Health Centre More to Puchra Road, Puchra to Natudihi Road under Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | 2217/RCD-I | 17/07/2023 | 30 | VISUVIOUS | 30.35 | 30.36 | 100 | 100
1513 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Formal work order for distribution network for augmentation of Jamuria (Rural)(Zone-I) pipe water Supply Scheme including FHTC allied work wthin Jamuria Block under RCFA Div-I PHE Dte.(Part-B) | 813/RCD I | 10/03/2023 | 30 | DIP CONSTRUCTION | 151.47 | 43.68 | 28.83 | 20
1514 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Formal work order for Distribution Network for Augmentation of Jamuri (Rural) (Zone-I) RCFA Part-II Piped Water Supply Scheme including FHTC & allied work within Jamuria Block under RCFA Division-I PHE Dte. (Part-A). | 1613/RCD I | 25/04/2023 | 30 | M/S B.K. CONSTRUCTION | 132.16 | 76.95 | 58.22 | 65
1515 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Preparation of DPR & Route Survey for augumentation of Jamuria (Rural) (Zone-I) piped water supply scheme block-Jamuria, dist- Paschim Barddhaman under RCFA Division-I PHE Dte. (Sl No. 32) | 2247/RCD I | 15/09/2022 | 15 | APEX ENGINEERING | 3.43 | 3.43 | 100 | 0
1516 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Providing and Installation of Electro-Mechanical Equipments and allied works under Augmentation of Jamuria (Rural) Zone - I & II Water Supply Scheme, Block : Jamuria, Dist -Paschim Bardhaman. | 491/AMD | 22/02/2023 | 731 | SUNRISE ENGINEERING CORPORATION | 145.5 | 94.72 | 65.11 | 100
1517 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Formal Work Order for Construction of Water sample collection cum Laboratory cum ISA & DPMU activity center as well as training hall etc. in the premises of RCFA office building under Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | 2008/RCD-I | 26/06/2023 | 564 | M/S CHANDI CHARAN ROY | 241.14 | 151.22 | 55.6 | 67
1518 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Acceptance cum work order for Laying 200 mm dia MS water pipe line with 600 mm dia MS casing pipe for Railway crossing in between KM 27/21-23 and between Barabani (BBI) and Jamuria (JMA) Station in Asansol Division under JJM under RCFA Division-I PHE Dte. | 2335/RCD-I | 01/08/2023 | 15 | M/S MONDAL ENTERPRISE | 36.29 | 34.64 | 100 | 100
1519 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Acceptence cum work order for Additional Supplying, Laying and Aligning HDPE pipe line, construction of street stand post and allied works under Ballavpur W/S Scheme under RCFA Division-I PHE Dte. | 2585/RCD-I | 07/09/2023 | 15 | TARA CONSTRUCTION | 6.32 | 6.15 | 100 | 100
1520 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Acceptance cum work order for Laying of 200 mm dia rising main for the proposed of Shyamla for Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | 3285/RCD-1 | 08/11/2023 | 30 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 12.63 | 11.21 | 100 | 85
1521 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 150 cum & allied work at Jamuria under Jamuria Rural-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 3656/RCD-1 | 28/12/2023 | 330 | MD SARFARAZ ALAM | 23.33 | 20.38 | 100 | 70
1522 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at Jamuria Pump House under Augmentation of Jamuria Rural Zone-I Piped Water Supply Scheme. | 1199/AMD | 07/08/2024 | 45 | SUNRISE ENGINEERING CORPORATION | 6.08 | 0 | 0 | 100
1523 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Supply & Installation of submersible pumping machineries and other allied Works at Low Lift RBTW for Augmentation of Jamuria (Rural) Zone - I & II Water Supply Scheme, Block : Jamuria, Dist -Paschim Bardhaman. | 2101/AMD | 12/12/2024 | 30 | SUNRISE ENGINEERING CORPORATION | 13.89 | 0 | 0 | 100
1524 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Acceptance cum work order for Additional estimate for concrete conduit for water body crossing at 4 (Four) nos location including adopting trench less technology (e.g. Jack Pushing Method etc) at Three nos location including MS work, Supply of valve, hard rock cutting, valve chamber and allied works related to distribution network at Churulia, Rakhakura, Joynagar, Chinchurbil etc villages under Augmentation of Jamuria Rural (Zone-1) PWSS under RCFA Division-I PHE Dte. | 468/RCD-1 | 12/02/2024 | 45 | ASHA CONSTRUCTION | 39.4 | 38.15 | 100 | 100
1525 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. , SM/15654 | Augmentation | Providing of lighting luminaries inconnection with yard lighting arrangement of newly constructed Pump House premises under Augmentation of Jamuria Rural (Zone-I) Water Supply Scheme. | 2179/AMD | 26/12/2024 | 166 | SASTIK ENTERPRISE | 12.05 | 0 | 0 | 100
1526 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15659 | Augmentation | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at Garkilla-Kherobari,Gourangapur(28) mouzas of Garkilla-Kherobari piped W/s Scheme under DWSD, PHE Dte under DWSD, PHE Dte (Part-A ,B & C) (SL-5) | 764/DWSD | 13/05/2022 | 45 | BABA LOKENATH ENTERPRISE | 28.84 | 4.29 | 100 | 100
1527 | PASCHIM BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15659 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Garkilla Khorobari Water Supply Scheme of Paschim Bardhaman under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1222/CMD | 16/03/2023 | 30 | SOUVIK HALDER | 10.21 | 8.74 | 85.61 | 70
1528 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15659 | Augmentation | Formal order for the work of Balance work of construction of Pump house /Chlorine room sinking of 150X80 X120 mm depth tube well supplying laying of HDPE distribution pipe in and providing FHTC at Garkilla -Kherobari (JL-27),Gourangapur(JL-28) mouzas of Garkilla-Kherobari piped W/S scheme under DWSD,PHE Dte | 735/DWSD | 15/05/2023 | 60 | BABA LOKENATH ENTERPRISE | 104.15 | 103.23 | 100 | 85
1529 | PASCHIM BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15659 | Augmentation | Supply & Delivery of Pump Motor Set at TW No: 01 of Garkilla Khorobari water supply scheme under CMD, PHE, | 110/DIC/BMSD(D) | 04/10/2023 | 15 | SOUVIK HALDER | 0.52 | 0.52 | 100 | 100
1530 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Emergent sinking of one no 200 x 165 mm dia rig bore tube well at ESI Hospital near staff quarter Kali Mandir, Paschim Bardhaman under RCFA Division-I PHE Dte. | Camp_02_ESI_Hospital_AE_I | 16/04/2024 | 7 | M/S CHANDI CHARAN ROY | 8.1 | 0 | 0 | 100
1531 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs no-13 at Surjanagar Low lift Pump House under ASTA W/S Scheme. | 1135/AMD | 30/07/2024 | 60 | M/S S.G.ENTERPRISE | 9.75 | 0 | 0 | 0
1532 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well no-9 and 10 at Narayankuri Pump House under Source Augmentation of RCFA Part-II Water Supply Scheme. | 2096/AMD | 12/12/2024 | 30 | PREMNATH MITRA | 9.89 | 0 | 0 | 0
1533 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-7 at Tirat Colliery Lowlift Pump House under Tirat Colliery Water Supply Scheme. | 1133/AMD | 30/07/2024 | 60 | PESTCO INDIA | 8.93 | 8.87 | 100 | 100
1534 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-6 at Tirat Colliery Low lift Pump House under Tirat Colliery Water Supply Scheme. | 1202/AMD | 07/08/2024 | 45 | PESTCO INDIA | 4.97 | 4.92 | 100 | 100
1535 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Continuation work order for Sinking of 6 (Six) nos 200 mm dia river bed tube well including collecting main in the river of Damodar at Surjanagar under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | 295/A/RCD-I | 06/02/2024 | 30 | MAK CONSTRUCTION CO | 22.57 | 17.67 | 100 | 100
1536 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-5 at Tirat Colliery Lowlift Pump House under Tirat Colliery Water Supply Scheme. | 1037/AMD | 16/07/2024 | 45 | PESTCO INDIA | 8.93 | 8.87 | 100 | 100
1537 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries in the Newly sunk RBTWs Harvanga-13 & 14 to Tirat Mouza Pump House under Tirat Mouza Water Supply Scheme. | 1134/AMD | 30/07/2024 | 60 | M/S. SOMA ENTERPRISE | 8.55 | 6.95 | 81.86 | 100
1538 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs from 07-11 at Surjanagar Low lift Pump House under ASTA W/S Scheme. | 1201/AMD | 07/08/2024 | 45 | M/S JIT ENTERPRISE | 8.85 | 8.83 | 100 | 100
1539 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 4 (Four) nos river bed tube wells including collecting main and other allied works at Damodar river under (Part-II) Unionpara Water Supply Scheme under RCFA Division-I PHE Dte. | 492/RCD-I | 12/02/2024 | 30 | TARA MA ENTERPRISE | 13.02 | 2.87 | 22.03 | 100
1540 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-14 at Baidyanathpur Pump house under Ukhra Water Supply Scheme. | 1039/AMD | 16/07/2024 | 291 | EASTERN INDIA SALES AND SERVICE | 8.15 | 0 | 0 | 100
1541 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Supply & Installation of submersible pumping machineries at Newly sunk 8 Nos Low Lift RBTWs at Madanpur Lowlift under Source Augmentation of RCFA Part-II Water Supply Scheme. | 944/AMD | 16/05/2025 | 30 | BENGAL CONSTRUCTION | 24.61 | 0 | 0 | 0
1542 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Installation of transformer(315 KVA), Supply, delivery and installation S/M, Pump-Motor set, and other allied works at Madanpur Head Works Site under RCFA Part-II Water Supply Scheme. | 1108/AMD | 16/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 37.68 | 0 | 0 | 0
1543 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum work order for Sinking of 4 (Four) nos 200 mm dia river bed tube wells in the river Ajoy at Baidyanathpur for Baidyanathpur Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2336/RCD-I | 01/08/2023 | 530 | MD AAMIR KHAN | 43.86 | 21.67 | 50.95 | 50
1544 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum work order for Sinking of 6 (Six) nos 200 mm dia river bed tube wells in the river Ajoy at Kendra Khottamdihi for Kendra Khottamdihi Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2337/RCD-I | 01/08/2023 | 30 | M/S MONI TRADERS | 42.45 | 41.38 | 100 | 55
1545 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 5 (Five) nos 200 mm dia river bed tube well including collecting main in the river Damodar at Surjanagar H/W site for ASTA of Source Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | 480/RCD-I | 12/02/2024 | 30 | MD. JAWED KHAN | 15.82 | 8.15 | 100 | 100
1546 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Providing and installation of submersible pumping machineries at newly sunk river bed tube well No-31 & 32 and other allied works at Kalajharia Water Works under source Augmentation of RCFA-II Water Supply Scheme. | 2100/AMD | 12/12/2024 | 30 | EASTERN INDIA SALES AND SERVICE | 28.6 | 0 | 0 | 100
1547 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum work order for Hydro-Geological study of Sub-Surface Water Flow with Sinking of Tube Well in Damodar & Ajay River bed and Bank Position of Source Augmentation of RCFA Part-II Water Supply Scheme by installing River bed tube well under RCFA Division-I PHE Dte. | 2435/RCD-I | 26/09/2024 | 15 | ENVIROTECH SOLUTIONS | 95 | 25.16 | 20.94 | 100
1548 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs from 01-06 at Surjanagar Lowlift Pump House under ASTA W/S Scheme. | 1041/AMD | 16/07/2024 | 45 | BENGAL CONSTRUCTION | 10.6 | 0 | 0 | 100
1549 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-15 at Baidyanathpur Pump house under Ukhra Water Supply Scheme. | 1206/AMD | 07/08/2024 | 288 | INDUSTRIAL ELECTRICAL CORPORATION | 8.18 | 0 | 0 | 100
1550 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum work order for Sinking of 6 (Six) nos. 200 mm dia river bed tube well including 3 nos. collecting main in the river Ajoy at Runakuraghat H/W site for Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | 2123/RCD-I | 27/08/2024 | 25 | MAA ENTERPRISE | 13.24 | 12.75 | 100 | 100
1551 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries in the Newly sunk RBTWs Amkula-5 to Tirat Mouza Pump House under Tirat Mouza Water Supply Scheme. | 1038/AMD | 16/07/2024 | 180 | SUNRISE ENGINEERING CORPORATION | 8.47 | 0 | 0 | 100
1552 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries for Newly Sunk RBTW No-03 for CWR at Ajoy Ghat Pumping Station under Churulia Water Supply Scheme. | 1040/AMD | 16/07/2024 | 511 | PREMNATH MITRA | 10.27 | 0 | 0 | 100
1553 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 6 (Six) nos 200 mm dia river bed tube well in the river Damodar at Madanpur Head Works Site for Madanpur Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 477/RCD-I | 12/02/2024 | 30 | NIYATI CONSTRUCTION | 29.98 | 23.43 | 100 | 100
1554 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 5 (Five) nos 200 mm dia river bed tube well including collecting main in the river Damodar at Surjanagar H/W site for ASTA Source Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | 479/RCD-I | 12/02/2024 | 30 | M/S MONDAL ENTERPRISE | 15.54 | 8.02 | 100 | 100
1555 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 3 (Three) nos river bed tube wells including collecting main manifold sluice valve chamber reinforcement and other allied works at Damalia H/W under RCFA Part-II at Damodar river under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. (Part-A) | 485/RCD-I | 12/02/2024 | 25 | SOMNATH SAMANTA | 19.46 | 19.45 | 100 | 100
1556 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 2 (Two) nos river bed tube wells including collecting main & other allied works at Damodar river under Tirat Colliery Water Supply Scheme under RCFA Division-I PHE Dte. | 895/RCD-I | 15/03/2024 | 15 | MAA ENTERPRISE | 4.51 | 4.42 | 100 | 100
1557 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 1 (One) no river bed tube wells including collecting main & other allied works at Damalia Damodar river under Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. | 894/RCD-I | 15/03/2024 | 15 | MAA ENTERPRISE | 3.05 | 2.99 | 100 | 100
1558 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum Work Order for Additional work of Emergent laying of Collecting Main for sinking of 4 nos river bed tube well and making of manifold with in addition of connecting of 10 nos tube well in River Ajoy at Bhaburia Head Works Site under RBT Type Sarpi, Jamgora Jagannathpur and Gourbazar-Ichapur Water Supply Scheme for Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | 3099/RCD-I | 13/12/2024 | 45 | MD AAMIR KHAN | 46.32 | 0 | 0 | 100
1559 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum work order for Balanced work Sinking of 03 (Three) nos. 200 mm dia river bed tube well in the river of Ajoy (Pandabeswar H/W Site) for Source Augmentation of RCFA Part-II W/S Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | 2108/RCD-I | 27/08/2024 | 278 | B.T.M. CONCERN | 23.41 | 11.92 | 51.57 | 70
1560 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well No-8 at Union Para Low Lift under Ballavpur Water Supply Scheme. | 1132/AMD | 30/07/2024 | 369 | HINDUSTHAN CONSULTANT FIRM | 4.84 | 0 | 0 | 100
1561 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries in Newly sunk RBTW No- 8 for CWR at Ajoyghat Pumping Station under source Augmentation of RCFA part-II Water Supply Scheme. | 2097/AMD | 12/12/2024 | 30 | M/S. SOMA ENTERPRISE | 5.6 | 0 | 0 | 100
1562 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum Work Order for Flow control of Rising main and different dia distribution system by different regulating apparatus of Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | 267/RCD-I | 04/02/2025 | 30 | MAKALI ENGINEERING CORPORATION | 87.75 | 0 | 0 | 100
1563 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well no- 7 & 8 at Narayankuri Pump House under Narayankuri Water Supply Scheme. | 1812/AMD | 29/10/2024 | 216 | HINDUSTHAN CONSULTANT FIRM | 11.21 | 0 | 0 | 100
1564 | PASCHIM BARDHAMAN | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well No-7 at Union Para Low Lift under Ballavpur Water Supply Scheme. | 1813/AMD | 29/10/2024 | 306 | M/S S.G.ENTERPRISE | 5.28 | 0 | 0 | 100
1565 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum Work Order for Flow control of Rising main and different dia distribution system by different regulating apparatus Source of Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | 266/RCD-I | 04/02/2025 | 30 | MAKALI ENGINEERING CORPORATION | 78.96 | 39.09 | 33.11 | 100
1566 | PASCHIM BARDHAMAN | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. , SM/18891 | Augmentation | Acceptance cum work order for Supply and laying 240 sqmm 3.5 core cable at Kalajharia complex for searching of infiltration gallery of Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | 1388/RCD-I | 15/05/2025 | 10 | MRITYUNJOY MUKHERJEE & CO. | 27.6 | 0 | 0 | 100
1567 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18826 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of SHYAMBAZAR (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -06) | 1238/DWSD | 31/07/2023 | 7 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
1568 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18826 | Augmentation | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied work at Pump House No- 01 under Shymbazar Water Supply Scheme, Block-Kanksa, Dist- Paschim Bardhaman under Asansol Mechanical Division,P.H.E Dte. | 1676/AMD | 04/10/2024 | 30 | M/S JIT ENTERPRISE | 4.11 | 0 | 0 | 100
1569 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18826 | Augmentation | Acceptance cum formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area Shyambazar under Augmentation Shyambazar piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-14) | 795/DWSD | 12/09/2023 | 30 | MAJI DEVELOPERS | 98.7 | 95.14 | 100 | 100
1570 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18826 | Augmentation | Acceptance cum work order for Allied works of Gopalpur site office including construction of pump house, premises development under Augmentation of Shyambazar water supply scheme of RCFA Division-I, PHE Dte. | 2111/RCD-I | 27/08/2024 | 181 | BASANTI TRADERS | 33.72 | 4.06 | 12.03 | 65
1571 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18826 | Augmentation | Supply & Installation Of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System And Internal House Wiring For Tube Well No-3 At Augmentation Of Ground water based water supply scheme for Shyambazar Under Asansol Mechanical Division, Phe Dte., Block- Kanksa, Dist- Paschim Bardhaman. | 952/AMD | 16/05/2025 | 30 | PESTCO INDIA | 11.61 | 0 | 0 | 0
1572 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18826 | Augmentation | Supplying laying and testing of HDPE pipeline and other allied works from Ajodhya village to Satkahania under Augmentation of Shyambazar piped W/s Scheme under DWSD,PHE Dte | 1617/DWSD | 03/10/2023 | 607 | BASANTI TRADERS | 9.94 | 0 | 0 | 100
1573 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18826 | Augmentation | Formal order for the work of Balance work of supplying and laying of HDPE distribution system with construction 02 Nos pump house construction of 150 M3 OHR of 20 Mtr staging height as per Deptt drawing laying aligning of rising main and providing FHTC connection of all mouzas under Command area of Augmentation Shyambazar piped W/s Scheme under DWSD, PHE Dte. | 1527/DWSD | 13/09/2023 | 1463 | DUTTA ENTERPRISE | 208.13 | 174.64 | 85.77 | 100
1574 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Continuation work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in Salanpur at KM SLS/1136 and SLS/1138 on Bemjomary siding Railway line in Asansol Division under JJM under RCFA Division-I PHE Dte. | 3297/RCD-I | 10/11/2023 | 15 | MD AAMIR KHAN | 24.44 | 23.98 | 100 | 100
1575 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Emergency repairing of 50 sqmm x 4 core Al Armoured damaged cable line and other allied Electrical works at Executive Engineer office building, SE office building, rest room & B type quarter under RCFA Division-I PHE Dte. | 3573_RCD/1 | 12/12/2023 | 15 | T R ENTERPRISE | 6.82 | 6.8 | 100 | 100
1576 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Continuation order for Hiring of Diesel driven Maxi cabs for official use of the Assistant Engineer-I under Asansol Mechanical Division, P.H Engineering. Dte. | 1091/AMD | 25/04/2023 | 365 | EASTERN INDIA SALES AND SERVICE | 1.79 | 0.84 | 46.85 | 83
1577 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Continuation order for Hiring of Diesel driven Maxi cabs for official use of the Assistant Engineer-II under Asansol Mechanical Division, P.H Engineering. Dte. | 1092/AMD | 25/04/2023 | 365 | EASTERN INDIA SALES AND SERVICE | 1.79 | 0.88 | 49.32 | 83
1578 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Continuation order for Hiring of Diesel driven Maxi cabs for official use of the Executive Engineer under Asansol Mechanical Division, P.H Engineering. Dte. | 1099/AMD | 26/04/2023 | 365 | SUNRISE ENGINEERING CORPORATION | 1.79 | 0.87 | 48.77 | 67
1579 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Providing & Installation of Electrical Equipments For Sub-Station at Mohishila Boosting Station (GLR-I & II), Searsole Boosting Station (GLR-I & II), Sankarpur Clear Water Boosting Station and Banshra Clear Water Boosting Station and Gaseous Chlorination system at different OHR sites with illumination under Augmentation of RCFA Part-II Piped Water Supply Scheme. | 1492/AMD | 04/08/2023 | 366 | ORIENTAL ENGINEERING CO. | 1965.22 | 1393.7 | 70.92 | 71
1580 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Laying of pipe line from Domhani Asansol main Road near BDO Office to Domohani PHC and construction of stand post at different places at Domohani Bazar under Barabani Development Block under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | 458/RCD-1 | 12/02/2024 | 20 | UNITED CONSTRUCTION | 6.71 | 4.03 | 60.08 | 62
1581 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Emergency repairing work of CI rising main (500 mm dia, 200 mm dia & 150 mm dia ) at Chotdola more, Dhasal more and new Kenda and Searsole H/W site near Pump House under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | 504/RCD-I | 12/02/2024 | 30 | DAWN CONSTRUCTION | 8.84 | 0 | 0 | 0
1582 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum Work Order for Additional for Distribution Network for Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Part-4) Block-Andal, Dist-Paschim Bardhaman under RCFA Div-I PHE Dte. | 1741/RCD-I | 18/07/2024 | 45 | UNITED CONSTRUCTION | 30.14 | 29.22 | 96.93 | 85
1583 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Supply of GI pipes to Searsole Store under Augmentation of RCFA Part-II (Zone-17) PWSS under RCFA Division-I PHE Dte. | 217/RCD-I | 29/01/2024 | 20 | MAKALI ENGINEERING CORPORATION | 90.4 | 90.4 | 100 | 100
1584 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Supply of GI pipes to Searsole Store under Augmentation of RCFA Part-II (Zone-15) PWSS under RCFA Division-I PHE Dte. | 216/RCD-I | 29/01/2024 | 20 | INDIA PIPE FITTING CO | 89.25 | 89.23 | 100 | 100
1585 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Laying of 110 mm dia HDPE pipeline including pushing of 600 mm dia RCC (NP3) hume pipe by adopting trench less technology at Health World Hospital, Asansol Paschim Bardhaman under RCFA Division-I PHE Dte. Extension work. | Camp-02_Health_World_AE-I | 21/02/2024 | 20 | M/S CHANDI CHARAN ROY | 18.54 | 18.06 | 100 | 100
1586 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Balance work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS and FHTC work under RCFA Division-I PHE Dte. | 455/RCD-1 | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 21.29 | 19.26 | 100 | 100
1587 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Laying 300 mm dia MS water pipe line with 600 mm dia MS cashing pipe for Railway crossing in Salanpur in between KM 231/16-18 and Salanpur (SLS) Rupnarayanpur (RNPR) Station in Asansol Diviion under JJM under RCFA Division-I PHE Dte. | 456/RCD-1 | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 37.06 | 36.88 | 100 | 100
1588 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Adopting trench less technology (e.g. Jack Pushing Method etc.) at 3 (Three) nos location within laying distribution system of Amritnagar (Part-B) under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | 457/RCD-1 | 12/02/2024 | 45 | M/S SINGH & KONAR CONSTRUCTION | 23.02 | 23.02 | 100 | 100
1589 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Allied work Balance Work of Road restoration in connection with formal work order Distribution network including FHTC and allied work at Ondal Block of Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | 452/RCD-1 | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 43.94 | 38.19 | 100 | 100
1590 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum Work Order for Supply and erection of Information Boards (31 nos) having M.S Channel/Angle posts and 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Salanpur ,Barabani, Andal ,Pandabeswar ,Raniganj and Durgapur Faridpur Block Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | 1746/RCD-I | 18/07/2024 | 15 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 6.1 | 5.12 | 100 | 100
1591 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum Work Order for Supply and erection of Information Boards(43 nos)having M.S Channel/Angle posts and 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Jamuria Block Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | 1748/RCD-I | 18/07/2024 | 15 | UNITED CONSTRUCTION | 8.48 | 7.78 | 100 | 100
1592 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for construction work and Interior Decoration of Office Building in Asansol under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | 2513/RCD-I | 04/10/2024 | 45 | M/S KALYANI ENTERPRISE | 41.78 | 5.37 | 11.44 | 100
1593 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum Work Order for Protecting apparatus of collecting main including other allied works under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | 1751/RCD-I | 18/07/2024 | 20 | INDIA PIPE FITTING CO | 93.63 | 93.56 | 100 | 100
1594 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Providing of different dia of water regulating apparatus and other allied works (Part-A) under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | 2451/RCD-I | 30/09/2024 | 15 | MAKALI ENGINEERING CORPORATION | 78.04 | 78.04 | 100 | 100
1595 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Construction of Visiter room and driver rest room at office premises Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | 2155/RCD-I | 29/08/2024 | 90 | G. CONSTRUCTION | 18.48 | 15.51 | 90.63 | 100
1596 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Protecting apparatus of collecting main including other allied works under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | 1750/RCD-I | 18/07/2024 | 20 | MAKALI ENGINEERING CORPORATION | 94.91 | 94.91 | 100 | 100
1597 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Material Requisition To Resource Division | 1178/RCD-I | 03/04/2024 | 0 | Resource Division | 337.92 | 0 | 0 | 0
1598 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Quotation for Earnest Money Deposit at Sankarpur Boosting Station, Chhora under Augmentation of RCFA II WS Scheme. | BP-2023-24-63 | 28/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
1599 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-67 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 560/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 10.41 | 0 | 0 | 0
1600 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-71 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 562/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 7.84 | 0 | 0 | 0
1601 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-65 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 563/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 17.21 | 0 | 0 | 0
1602 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Bill for Diesel Driven Maxi Cab for Official Use of The AE-II, under AMD, PHE Dte for the month of April, 2024. | BP-2024-25-33/3 | 23/08/2024 | 0 | RANAJIT AUTO | 0.15 | 0 | 0 | 0
1603 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Earnest Money Deposit for Bulk Power Supply at Intake sub-station Sarkuri Salanpur under Augmentation of RCFA Part II WS Scheme. | BP-2023-24-66 | 02/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
1604 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Quotation for Earnest Money Deposit at Bansra Boosting Station, Kunustoria under Augmentation of RCFA II WS Scheme. | BP-2023-24-61 | 28/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
1605 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-69 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 561/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 6.97 | 0 | 0 | 0
1606 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-68 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 565/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 6.97 | 0 | 0 | 0
1607 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-66 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 559/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 16.52 | 0 | 0 | 0
1608 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Shifting of overhead line inside the premises of benali boosting station | BP-2024-25-14 | 17/05/2024 | 0 | INDIA POWER CORPN. LTD. | 2.84 | 0 | 0 | 0
1609 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-91 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 624/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0 | 0
1610 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Charges for the Cab of AE-I under AMD, PHE Dte. for the month of JANUARY, 2024 | BP-2024-25-30 | 06/08/2024 | 0 | RANAJIT AUTO | 0.26 | 0 | 0 | 0
1611 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Bill for the Cab of The Executive Engineer, under AMD, PHE Dte., for the month of March,2024. | BP-2024-25-34/5 | 23/08/2024 | 0 | RANAJIT AUTO | 0.25 | 0 | 0 | 0
1612 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Charges for the Cab of AE-II under AMD, PHE Dte. for the month of NOVEMBER, 2023. | BP-2024-25-27 | 30/07/2024 | 0 | RANAJIT AUTO | 0.2 | 0 | 0 | 0
1613 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Charges for the Cab of AE-II under AMD, PHE Dte. for the month of FEBRUARY, 2024 | BP-2024-25-30/3 | 06/08/2024 | 0 | RANAJIT AUTO | 0.23 | 0 | 0 | 0
1614 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Charges for the Cab of AE-II under AMD, PHE Dte. for the month of JANUARY, 2024 | BP-2024-25-30/2 | 06/08/2024 | 0 | RANAJIT AUTO | 0.25 | 0 | 0 | 0
1615 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Earnest Money Deposit for Bulk Power Supply at Mohishila Boosting Station under Augmentation of RCFA Part II WS Scheme. | BP-2023-24-65 | 02/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
1616 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-90 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 626/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0 | 0
1617 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | DIVERSION OF 33KV S/C PHE FEEDER INSIDE THE PREMISES OF THE PHE DUE TO PROPOSED WTP,KALYNESWARI FOR M/S PHE DIRECTORATE,ASANSOL | BP-2024-25-4 | 23/04/2024 | 0 | CHIEF ACCOUNTS OFFICER, DAMODAR VALLEY CORPORATION | 2.8 | 0 | 0 | 0
1618 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Bill for Diesel Driven Maxi Cab for Official Use of The AE-I, under AMD, PHE Dte for the month of April, 2024. | BP-2024-25-33/7 | 23/08/2024 | 0 | RANAJIT AUTO | 0.22 | 0 | 0 | 0
1619 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Bill for the Cab of The Executive Engineer, under AMD, PHE Dte., for the month of Jan, 2024. | BP-2024-25-34/1 | 23/08/2024 | 0 | RANAJIT AUTO | 0.25 | 0 | 0 | 0
1620 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Charges for the Cab of AE - I under AMD, PHE Dte. for the month of DECEMBER, 2023 | BP-2024-25-27/3 | 30/07/2024 | 0 | RANAJIT AUTO | 0.26 | 0 | 0 | 0
1621 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-70 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 564/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 7.84 | 0 | 0 | 0
1622 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Bulk Power Supply at Mohishila Boosting Station under Augmentation of RCFA Part II. | BP-2023-24-77 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 22.75 | 0 | 0 | 0
1623 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-72 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 566/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 6.97 | 0 | 0 | 0
1624 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Charges for the Cab of AE-I under AMD, PHE Dte. for the month of FEBRUARY, 2024. | BP-2024-25-30/1 | 06/08/2024 | 0 | RANAJIT AUTO | 0.27 | 0 | 0 | 0
1625 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Charges for the Cab of AE-II under AMD, PHE Dte. for the month of DECEMBER, 2023 | BP-2024-25-27/1 | 30/07/2024 | 0 | RANAJIT AUTO | 0.24 | 0 | 0 | 0
1626 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Bill for the Cab of The Executive Engineer, under AMD, PHE Dte., for the month of Feb, 2024. | BP-2024-25-34/3 | 23/08/2024 | 0 | RANAJIT AUTO | 0.22 | 0 | 0 | 0
1627 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-08 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 625/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.08 | 0 | 0 | 0
1628 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-92 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 627/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.28 | 0 | 0 | 0
1629 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Installation Charge and Security Deposit for Bulk Power Supply at Intake Sub-Station Sarkuri Salanpur Under Augmentation of RCFA Part-II | BP-2024-25-2 | 15/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 54.89 | 0 | 0 | 0
1630 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Charges for the Cab of AE-I under AMD, PHE Dte. for the month of NOVEMBER, 2023 | BP-2024-25-27/2 | 30/07/2024 | 0 | RANAJIT AUTO | 0.22 | 0 | 0 | 0
1631 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | License Fees for five (05) years for 6-lanning of Barwa Adda - Panagarh section of NH-2 from km 398.240 to km 521.120 including Panagarh Bypass in the state of Jharkhand & West Bengal under NHDP Phase -V on BOT (Toll) on DBFOT pattern - Permission for laying of water pipeline along NH-2 from Kalla more (km 462+080) to Harishpur (km+918) and 7 nos crossing across NH-2 in the state of West Bengal under Augmentatin of RCFA Pt II Volume -II under RCFA Division-I PHE Dte. | 282/24-25 | 09/09/2024 | 0 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 164.48 | 0 | 0 | 0
1632 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Quotation for Earnest Money Deposit at Searsole Boosting Station, Ranisayer under Augmentation of RCFA II WS Scheme. | BP-2023-24-62 | 28/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
1633 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Bulk Power Supply at Searsole Boosting Station under Augmentation of RCFA Part II. | BP-2023-24-76 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 93.38 | 0 | 0 | 0
1634 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-93 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 623/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.08 | 0 | 0 | 0
1635 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Bill for Diesel Driven Maxi Cab for Official Use of The AE-I, under AMD, PHE Dte for the month of March, 2024. | BP-2024-25-33/5 | 23/08/2024 | 0 | RANAJIT AUTO | 0.25 | 0 | 0 | 0
1636 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Payment of Security Deposite & Remaining Earnest Money for Bansra Boosting Station (Consumer ID- 950085633) under Asansol Mechanical Division, P.H.E. Dte. | BP-2024-25-24 | 29/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 24.84 | 0 | 0 | 0
1637 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Quotation Money for Earnest Money Deposition for Bulk Power supply at Kalyaneswari under Augmentation of RCFA Part II WS Scheme. | BP-2023-24-69 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.2 | 0 | 0 | 0
1638 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-95 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | 628/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.08 | 0 | 0 | 0
1639 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Bill for Diesel Driven Maxi Cab for Official Use of The AE-II, under AMD, PHE Dte for the month of March, 2024. | BP-2024-25-33/1 | 23/08/2024 | 0 | RANAJIT AUTO | 0.23 | 0 | 0 | 0
1640 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Charges for the Cab of EE under AMD, PHE Dte. for the month of NOV, 2023. | BP-2024-25-27/4 | 30/07/2024 | 0 | RANAJIT AUTO | 0.09 | 0 | 0 | 0
1641 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Charges for the Cab of EE under AMD, PHE Dte. for the month of DECEMBER, 2023. | BP-2024-25-27/5 | 30/07/2024 | 0 | RANAJIT AUTO | 0.23 | 0 | 0 | 0
1642 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | PAYMENT OF SECURITY DEPOSIT & EARNEST MONEY FOR BULK POWER SUPPLY AT SHANKARPUR BOOSTING STATION. | BP-2024-25-63 | 28/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 22.9 | 0 | 0 | 0
1643 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Fuel Bill for the Cab of The Executive Engineer, under AMD, PHE Dte., for the month of April, 2024. | BP-2024-25-62 | 28/10/2024 | 0 | RANAJIT AUTO | 0.22 | 0 | 0 | 0
1644 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Formal Work Order for Laying of different dia HDPE pipe line and allied works at Raghunathchak, Raniganj Chati, Baliapur and adjacent area under Zone-IX for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | 2383/RCD-I | 07/08/2023 | 90 | DAWN CONSTRUCTION | 105.48 | 90.97 | 86.24 | 100
1645 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Renovation work at Kalyaneswari Inspection Bungalow & WTP under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | 3610/RCD-1 | 20/12/2023 | 540 | M/S KALYANI ENTERPRISE | 81.82 | 7.51 | 9.18 | 100
1646 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Operation and regulatiing of different dia S/V of Distribution system and rising main for FHTC work for Mdira, Dighalpahari, Chotkara and Kanskuli villages under administrative contingency of JJM under RCFA Division -I PHE Dte. | 101/RCD-1 | 09/01/2024 | 239 | SRI KRISHNA ENTERPRISE | 2.91 | 0 | 0 | 100
1647 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum Work Order for Realtime Water Quality Monitoring including 1 year maintenance for the OHR as hereunder RCFA Division-I PHE Dte. | 2033/RCD-I | 21/08/2024 | 455 | MAXBRIDGE SOLUTIONS LLP | 33.46 | 0 | 0 | 55
1648 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Continuation work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in between KM 227/27-29 and between Salanpur (SLS) Rupnarayanpur (RNPR) inAsansol Division under JJM under RCFA Division-I PHE Dte. | 3298/RCD-1 | 10/11/2023 | 15 | MAK CONSTRUCTION CO | 45.92 | 45.77 | 100 | 100
1649 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Supply of different dia Sluice Valve, Air Valve, NRV including C.I./D.I Specials to the Searsole Store of Augmentation of RCFA Part-II (Zone-18) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 215/RCD-I | 29/01/2024 | 20 | SSPR VALVE MANUFACTURING PVT LTD | 49.92 | 49.92 | 100 | 100
1650 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Construction of restoration approach road in Chalbalpur at Amritnagar Zone-I under RCFA Part-II under RCFA Division-I PHE Dte. | 453/RCD-1 | 12/02/2024 | 30 | MRITYUNJOY MUKHERJEE & CO. | 20.62 | 20.5 | 100 | 100
1651 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum Work Order for Additional work of Laying and pushing of 600 mm dia RCC (NP3) hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) with 400 mm dia and 300 mm dia MS water carrier pipe line at Node point (82-83) and (74-75) for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | 487/RCD-I | 12/02/2024 | 25 | SWATI CORPORATION | 17.43 | 16.96 | 100 | 100
1652 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum Work Order for Laying of rising main at Surjanagar Head Works Site to High lift site under ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | 476/RCD-I | 12/02/2024 | 45 | MAK CONSTRUCTION CO | 58.51 | 58.43 | 100 | 100
1653 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Allied work of laying distribution system of Improvement of RCFA Part-I Commanded area of Zone-V with LDS FHTC work under RCFA Division-I PHE Dte. | 451/RCD-1 | 12/02/2024 | 30 | MRITYUNJOY MUKHERJEE & CO. | 25.84 | 25.44 | 100 | 100
1654 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum Work Order for Supplying of different pipe specials for Ondal (Phase-I) under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II for providing FHTC under Andal Block | 1006/RCD-I | 16/03/2024 | 15 | M/S UNIT CONSTRUCTION | 12.5 | 10.91 | 100 | 100
1655 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Modification, Improvement of storage, documents with seating arrangement of entire Central Circle, PHE Dte. at Purta Bhawan in the District of Purba Bardhhaman. | 932/RCD-I | 15/03/2024 | 196 | SHIVAM UN-EMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28.53 | 0 | 0 | 100
1656 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Emergency repairing work of 110 mm dia HDPE distribution main and G.I. line of Health World Hospital of Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Camp-02_Health-World/AE/2 | 22/08/2024 | 10 | M/S CHANDI CHARAN ROY | 4.2 | 4.18 | 100 | 100
1657 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Additional work for approach concrete road, room and toilet repairing, materials shifting and stacking and etc allied works at Searsole Stack yard under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | 1525/RCD-I | 14/06/2024 | 45 | M/S MONDAL ENTERPRISE | 16.4 | 14.01 | 100 | 100
1658 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Additional work of laying 250 mm dia HDPE pipe line and PWD road crossing from Semalya to Kendra Khottamdihi intake pump house site under Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II | 1642/RCD-I | 04/07/2024 | 497 | UMA ENTERPRISE | 71.29 | 0 | 0 | 100
1659 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum Work Order for Supply and erection of Information Boards (49 nos) having M.S Channel/Angle posts and 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Kanksa Block Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | 1747/RCD-I | 18/07/2024 | 15 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 9.69 | 8.45 | 100 | 100
1660 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. , SM/18468 | Augmentation | Acceptance cum work order for Providing of different dia of water regulating apparatus and other allied works (Part-B) under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte | 2452/RCD-I | 30/09/2024 | 15 | MAKALI ENGINEERING CORPORATION | 81.71 | 21.64 | 20.94 | 100
1661 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. , SM/09061 | Retrofitting | Material Requisition To Resource Division | 1857/RCD-I | 31/05/2023 | 0 | Resource Division | 1.76 | 0 | 0 | 0
1662 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. , SM/09061 | Retrofitting | Acceptance cum work order for Additional Providing FHTC of retrofitting at Kumardiha village (left out portion) of Kumardiha Mouza, Retrofitting of Madantore PWSS for providing FHTC under RCFA Division-I PHE Dte. | 2619/RCD-I | 14/11/2024 | 20 | D.S.C. CONCERN | 6.57 | 0 | 0 | 0
1663 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. , SM/09061 | Retrofitting | Acceptance cum work order for supplying, aligning, laying of PVC & HDPE Pipeline, Construction of Sluice valve chamber and supplying, aligning, laying of G.I Pipe under Retrofitting of Madantore PWSS scheme under RCFA Division-I PHE Dte. | 405/RCD-I | 30/01/2023 | 15 | M/S S.K. ENTERPRISE | 5.17 | 5.17 | 100 | 0
1664 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. , SM/09061 | Retrofitting | Acceptance cum work order Sinking of 5 (Five nos. 200mm dia river bed tube wells including collecting main instead of defunct tube well at river Damodar (intake well Site ) Kalajharia Under Omprovement of RCFS part-II W/S Scheme under RCFA Division-I PHE Dte. (Part-G). | 402/RCDI | 30/01/2023 | 15 | DURGADAS MONDAL | 8.43 | 7.68 | 91.05 | 0
1665 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. , SM/09061 | Retrofitting | Acceptance cum work order Repairing & shifting work of DI pipes, repairing of 350 mm dia MS pipe and allied repairing at Madanpur W/S Scheme under RCFA Division-I PHE Dte. | 1278/ RCD I | 27/03/2023 | 15 | MD. JAWED KHAN | 4.78 | 4.69 | 98.2 | 100
1666 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. , SM/09061 | Retrofitting | Acceptance cum work order for Repairing and restoration of pipe line including supply of valve, construction of valve chamber, restoration of FHTC etc. at Bathan Bari, Sidhabari, Kalyaneswari and adjoining area Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block under RCFA Division-I PHE Dte. | 116/RCD-I | 08/01/2025 | 45 | DIP CONSTRUCTION | 13.76 | 0 | 0 | 100
1667 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ A) | 2124/RCD-I | 29/11/2021 | 30 | A.K.CONSTRUCTION | 14.4 | 14.4 | 100 | 0
1668 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ B) | 2125/RCD-I | 29/11/2021 | 30 | UNITED CONSTRUCTION | 14.36 | 14.36 | 100 | 0
1669 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C) | 2126/RCD-I | 29/11/2021 | 30 | DURGADAS MONDAL | 14.37 | 14.26 | 100 | 0
1670 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ D) | 2127/RCD-I | 29/11/2021 | 30 | SIMA ENTERPRISE | 14.42 | 14.42 | 100 | 0
1671 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Acceptance cum work for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ E) | 2128/RCD-I | 29/11/2021 | 30 | M/S KALYANI ENTERPRISE | 14.45 | 14.44 | 100 | 0
1672 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Laying of 25 mm dia PVC pipe line at Ukhra Adarsha Hindi High School and installation of Street stand post and etc. allied works at Dakshin Khanda area under RCFA Division-I PHE Dte. (Sl No. 12) | 224/RCD I | 01/02/2022 | 15 | UNITED CONSTRUCTION | 4.63 | 4.63 | 100 | 0
1673 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ F) | 2129/RCD-I | 29/11/2021 | 30 | M/S SUBHRADEEP | 16.51 | 16.51 | 100 | 0
1674 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Jamgram Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3139/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100 | 100
1675 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3142/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100 | 100
1676 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Sub Soil Investigation for 300 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Sarisatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3141/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100 | 100
1677 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Churulia Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3144/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100 | 100
1678 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Material Requisition To Resource Division | 2281/RCD-I | 12/12/2021 | 0 | Resource Division | 10.17 | 0 | 0 | 0
1679 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Arrangeme of tiffin packets for DWSM meeting held on 27.07.2024 at ADDA Conferene hall, Asansol, Paschim Bardhaman | 241/24-25 | 23/08/2024 | 0 | BLESSING ENTERPRISE | 0.09 | 0 | 0 | 0
1680 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Installation of quick Heal Anti Viru for 3 years under RCFA Diivison-I PHE Dte. | 245/24-25 | 27/08/2024 | 0 | MUKHERJEE TRADERS | 0.09 | 0 | 0 | 0
1681 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Arrangement of breakfast (Tea with snacks) for DWSM meeting held on 27.07.2024 at ADDA Conference hall, Asansol Paschim Bardhaman under RCFA Division-I PHE Dte. | 240/24-25 | 23/08/2024 | 0 | BLESSING ENTERPRISE | 0.08 | 0 | 0 | 0
1682 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09389 | Retrofitting | Acceptance cum work order for Laying and interconnection work of different dia HDPE pipe line unde Dakshin Khanda area Khandra Zone under RCFA Pt-II W/S Scheme under RCFA Division-I PHE Dte. | 118/RCD-I | 20/01/2022 | 30 | UNITED CONSTRUCTION | 13.96 | 10.91 | 100 | 0
1683 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Formal order for the work of Supplying& laying of different dia HDPE pipe line with necessary allied works at Anandapur Mouza(JL-89),Block -Kanksa under Augmentation of Kanksa (Zone-I W/s Scheme under DWSD ,PHE Dte | 197/DWSD | 16/02/2022 | 30 | AMAR CONSTRUCTION | 27.51 | 15.36 | 55.85 | 0
1684 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Annandapur mouza (JL-89) under command area of Kanksa Zone-I piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-24) | 1324/DWSD | 09/12/2020 | 45 | M/S KALYANI ENTERPRISE | 18.17 | 18.25 | 100 | 0
1685 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Formal order for the work of Sinking of 1No(300X200 mm) dia tube well 150 mtr deep by direct rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at Tube well No-03 site at Anandapur under Kanksa block (Zone-I) for Augmentation of ground water base Kanksa (Zone-I) piped W/s Scheme under DWSD ,PHE Dte | 196/DWSD | 16/02/2022 | 30 | RANJIB GHATAK | 10.43 | 10.22 | 100 | 0
1686 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Construction of pump house cum chlorine room at AnandaPur H/W site of ground water base Kanksa(Zone-I) pipe W/s Scheme under DWSD ,PHE Dte (SL-04) | 241/A/DWSD | 25/02/2022 | 45 | CHANDAN HAZRA | 4.99 | 4.89 | 100 | 0
1687 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Formal order for the work of Sinking of 1 No Tube well 250 mm X 150 mm big dia Tube well 150 mtr deapth direct rotary rig method using PVC pipe & fiber glass rein forced epoxy resin slotted TW No-1 Part-A site at Shilampur Pump house under Kanksa block (Zone-I) for Kanksa piped W/s Scheme (Zone-I) under DWSD, PHE Dte (SL-11) | 748/DWSD | 10/05/2022 | 10 | RANJIB GHATAK | 10.68 | 10.67 | 100 | 0
1688 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Rearing of pump house -I boundary wall and plinth protection at Silampur under Kanksa (Zone-I) for Augmentation of ground water based Kanksa (Zone-I) piped W/s Scheme under DWSD, PHE Dte.(SL-13) | 428/DWSD | 30/03/2022 | 15 | BASANTI TRADERS | 4.84 | 1.46 | 100 | 0
1689 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Trail bore for 2 Nos (300x200 mm dia) tube well by direct rotary method at Annandapur and Shilampur pump house at Kanksa (Zone-I) for Augmentation of ground water of Kanksa (Zone-I) piped W/s Scheme under DWSD, PHE Dte (SL-04) | 583/DWSD | 21/04/2022 | 7 | RANJIB GHATAK | 3.91 | 3.91 | 100 | 0
1690 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Urgent repairing of 250 mm dia pipe line and UPVC pipe line with necessary allied works at Silampur ,Gungbill an Aymma Biswanathpur distribution area under Kanksa (Zone-I) Pipe W/s Scheme under DWSD, PHE Dte. | 426/DWSD | 30/03/2022 | 10 | MD AAMIR KHAN | 4.82 | 4.76 | 100 | 0
1691 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Quatation for Kanksa Zone -I Pump house no -03 | BP-2022-23-103 | 02/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.97 | 0 | 0 | 0
1692 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of KRISHNAPUR PWSS under KANKSA Development Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No - 05) | 918/DWSD | 22/06/2023 | 7 | CARTO | 0.78 | 0 | 0 | 0
1693 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of KANCHANPUR (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -08) | 1236/DWSD | 31/07/2023 | 7 | MEASURE LAND | 0.78 | 0 | 0 | 0
1694 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of KRISHNAPUR (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -07) | 1237/DWSD | 31/07/2023 | 7 | MEASURE LAND | 0.78 | 0 | 0 | 0
1695 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of KANCHANPUR PWSS under KANKSA Development Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No - 03) | 916/DWSD | 22/06/2023 | 7 | CARTO | 0.78 | 0 | 0 | 0
1696 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of TILAKCHANDRAPUR PWSS under KANKSA Development Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No-04) | 917/DWSD | 22/06/2023 | 7 | MEASURE LAND | 0.78 | 0 | 0 | 0
1697 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Formal order for the work Supplying ,laying and aligning of HDPE distribution pipe line and allied works at Railpar Saradapally Mouza under command area of Augmentation of Kanksa (Zone-II/D) under DWSD ,PHE Dte (Part-A) | 184/DWSD | 11/02/2022 | 30 | M/S S. CHOUDHURY | 96.45 | 37.88 | 47.85 | 100
1698 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Formal order for the work of Supplying & laying of different dia HDPE pipe line with necessary allied works at Silampur mouza(JL-90) block -Kanksa under Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD, PHE Dte (SL-01) | 651/DWSD | 22/04/2022 | 25 | MD AAMIR KHAN | 91.75 | 82.05 | 89.42 | 60
1699 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works at Molandighi H/W site Pump house No-1 Tube well No-01 for Bistupur pipe W/S Scheme under DWSD,PHE Dte (SL-10) | 1076/DWSD | 12/07/2022 | 25 | CHATTERJEE CONSTRUCTION | 4.82 | 1.16 | 66.55 | 100
1700 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works and other allied works at Sarada Pally H/W Site Pump house No-2 &T.W-02 for Augmentation of Kanksa (Zone-II/D) pipe W/S Scheme under DWSD,PHE Dte (SL-09) | 1075/DWSD | 12/07/2022 | 25 | MUKHERJEE ENTERPRISE | 4.82 | 1.37 | 78.45 | 100
1701 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Additional work at RCC O HR site at Silampur under Augmentation of Kanksa (Zone-I) Piped W/s Scheme under DWSD,PHE Dte | 763/DWSD. | 22/05/2023 | 20 | MD AAMIR KHAN | 6.88 | 2.84 | 41.24 | 80
1702 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Additional work of supplying and laying of different dia HDPE pipe line with necessary allied works at Aymabiswanath ,Gangbill mouza(JL-82,83) block-Kanksa under Augmentation of Kanksa Zone-I piped W/S scheme under DWSD,PHE Dte (SM/10208) | 1067/DWSD | 12/07/2023 | 30 | TARA PRASAD SARKAR | 96.72 | 74.03 | 76.54 | 100
1703 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Supplying , fitting , fixing and fabrication of sign board With Necessary allied Work at different Placeses of ongoing New PWSS &Augamentation Scheme (As per Departmental Approved drawing & Direction) in connection with Augmentation of Kanksa Zone - I Pipe W/S Scheme ( JJM) Work under Durgapur Water Supply Division ,PHE Dte. (Sl - 06) | 15/SPOT/DWSD | 16/06/2023 | 7 | AMARANJALI CONSTRUCTION | 0.96 | 0 | 0 | 0
1704 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance order for the work of Details route survey ,drawing design of distribution network & preparation of estimates and DPR in connection with the JJM (FHTC) of Augmentation of Kanksa (Zone-I) piped W/S Scheme DWSD,PHE Dte (Sl-04) | 1420/DWSD | 27/09/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5.52 | 5.52 | 100 | 0
1705 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Formal order for the work of Replaying of 160 mm /110 mm dia HDPE main pipe line at Panagarh to Shilampur road of Kanksa (Zone-I) W/s Scheme under DWSD, PHE Dte | 1708/DWSD | 08/12/2021 | 30 | MAK CONSTRUCTION CO. | 9.64 | 9.83 | 100 | 0
1706 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Laying of 90 mm dia HDPE pipe line and withdrawing of 90 mm dia UPVC and laying the same in opposite flank of road with necessary allied works at Anandapur mouza,ICDS to Dompara under Kanksa (Z-I) W/s Scheme ,Block -Kanksa for cambat of upcoming drought unde DWSD , PHE Dte . (SL-01) | 73/DWSD | 21/01/2022 | 10 | RANJIB GHATAK | 1.78 | 1.79 | 100 | 0
1707 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Formal order for the work of Supplying & laying of different dia HDPE pipe line with necessary allied works at Ayma Biswanathpur and Gangbil Mouza (JL-82/83) block -Kanksa under Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD, PHE Dte (SL-02) | 658/DWSD | 22/04/2022 | 25 | TARA PRASAD SARKAR | 77.97 | 77.17 | 100 | 100
1708 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Formal order for the work of Construction of 350 M3 capacity , 20 mtr staging height RCC Over head Reservoir (OHR) at Silampur Pump House No-1 of Augmentation of Kaksa piped W/s Scheme under Durgapur W/S Division, PHE Dte | 652/DWSD | 22/04/2022 | 184 | MD AAMIR KHAN | 83.27 | 74.24 | 100 | 85
1709 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Construction boundary wall at Shilampur pump house No-1 under Augmentation of ground water base Kanksa (Zone-I) piped W/s Scheme under DWSD ,PHE Dte (SL-16) | 818/DWSD | 23/05/2022 | 20 | BASANTI TRADERS | 10.89 | 9.18 | 100 | 100
1710 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum Formal work-Order for the work of ---Sanitary arrangement and plumbing works at Sarada Pally H/W Site Pump house No-3 for Augmentation of Kanksa (Zone-II/D) pipe W/S Scheme under DWSD,PHE Dte (SL-04) | 1054/DWSD | 07/07/2022 | 25 | CHATTERJEE CONSTRUCTION | 4.82 | 1.36 | 100 | 100
1711 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Additional FHTC and necessary allied works at Silampur(JL-90) mouza of Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD,PHE Dte (SL-01) | 1574/DWSD | 02/11/2022 | 15 | MD AAMIR KHAN | 7.26 | 7.12 | 100 | 100
1712 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Additional FHTC and necessary allied works at Ayma Biswanathpur(JL-82),Ganbil(JL-83) mouza of Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD,PHE Dte (SL-02) | 1575/DWSD | 02/11/2022 | 15 | TARA PRASAD SARKAR | 23.21 | 23.2 | 100 | 100
1713 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance order for the work of Supplying and laying of 150 mm dia DIC (K9) & 150 mm dia HDPE pipe line with necessary allied works at Kanksa block of Anandpur to Silampur under Augmentation of Kanksa (Zone-I) piped W/s Scheme (JJM) under DWSD ,PHE Dte | 108/DWSD | 24/01/2023 | 20 | A.K.D. ENTERPRISE | 4.96 | 4.78 | 100 | 100
1714 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Construction of boundary wall at railpar Saroda Pally head works site pump house No-III WT_3 for Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD ,PHE Dte | 721/DWSD | 11/05/2023 | 25 | CHATTERJEE CONSTRUCTION | 14.8 | 9.48 | 100 | 100
1715 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Construction of boundary wall at Railpar Saroda Pally H/W site pump house no-2/TW-II for Augmentation of Kanksa Zone-I) piped W/s Scheme under DWSD ,PHE Dte . | 1106/DWSD | 14/07/2023 | 40 | MUKHERJEE ENTERPRISE | 14.79 | 9.46 | 100 | 100
1716 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Supply, delivery & installation of Poly vinayle laminated board including framework for different Head Work site of New PWSs (JJM) under Kanksa Zone- I W/S Scheme under EE/DWSD/ PHE Dte. (Sl- 04) | 1189/DWSD | 25/07/2023 | 15 | JOY GURU ENTERPRISE | 0.82 | 0.82 | 100 | 100
1717 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Additional trail bore by direct Rotary method drilling using Rig machin at Kanchanpur/Basdebpur H/W Site for newly sinking of Well No-I and II under Augmentation of Kanksa (Zone-I) piped W/s scheme under DWSD, PHE Dte | 1280/DWSD | 07/08/2023 | 10 | JOY GURU ENTERPRISE | 2.27 | 2.27 | 100 | 100
1718 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of repairing of office room and necessary allied works under Augmentation of Kanksa Zone-I piped W/s Scheme under DWSD, PHE Dte | 1271/DWSD | 07/08/2023 | 15 | A.K.D. ENTERPRISE | 4.9 | 1.74 | 100 | 100
1719 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Dismantling of concrete road and bituminous road of Augmentation of Kanksa zone I/B piped W/s Scheme with construction of boundary wall renovation of all existing structure repairing of all retaining structure left out LDS FHTC Reconnection of FHTC at Kanksa (Part),Debipur(Part),Panagarh(Part) ,Prayagpur(Part) mouza of JL-86,87,88 of Kanksa Block under DWSD ,PHE Dte | 1090/DWSD | 13/07/2023 | 30 | MAK CONSTRUCTION CO. | 23.98 | 23.91 | 100 | 100
1720 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of Kanksa Zone - I (PART - B) under Kanksa Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No - 05) | 1239/DWSD | 31/07/2023 | 7 | CARTO | 0.78 | 0.78 | 100 | 100
1721 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Replacement of existing pipeline for Physical certificate of HarGhar Jal IN connection of JJM of Augmentation of Kanksa (Zone-I ) piped W/s Scheme under DWSD ,PHE Dte | 1092/DWSD | 13/07/2023 | 30 | MD AAMIR KHAN | 36.07 | 34.74 | 100 | 100
1722 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Material Requisition To Resource Division | 399/DWSD | 03/03/2023 | 0 | Resource Division | 7.39 | 0 | 0 | 0
1723 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Road restoration at Panagarh Silampur Road (ch 2.5 KM to 3.5 KM) to be executed by Executive Engineer, Asansol Highway Division, PWD Roads directorate for the work of repairing of damaged at Panagarh Silampur | BP-2022-23-333 | 15/03/2023 | 0 | EXECUTIVE ENGINEER , ASANSOL HIGHWAY DIVISION, PWD ROADS | 18 | 0 | 0 | 0
1724 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of Kanksa Zone - I Water Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | 2570/CMD | 06/06/2023 | 30 | MS DAS ELECTRIC CO | 19.35 | 9.41 | 48.64 | 46
1725 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of construction of pump house cum chlorine room at Silampur pump house No-I H/W site for Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD,PHE Dte | 1279/DWSD | 07/08/2023 | 45 | MUKHERJEE ENTERPRISE | 6.41 | 0 | 0 | 100
1726 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied works at Pump House No-01 under Augmentation of Kanksa Zone-I Water Supply Scheme, Block- Kanksa, Dist.- Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | 1809/AMD | 29/10/2024 | 30 | M/S A.D.ENTERPRISE | 2.97 | 0 | 0 | 0
1727 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Construction of latrine and boundary wall of pump house cum chlorine room and necessary allied works at Anandpur H/W site for Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD, PHE Dte | 767/DWSD | 22/05/2023 | 15 | CHANDAN HAZRA | 6.76 | 6.56 | 100 | 100
1728 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Continuation for the work of Providing functional house hold tap connection (FHTC) in connection with JJM for Domra mouza-68 under command area of Trilakchandrapur piped W/s Scheme at Kanksa Block under DWSD, PHE Dte | 347/DWSD | 17/03/2022 | 1110 | AMARANJALI CONSTRUCTION | 3.03 | 0 | 0 | 100
1729 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) , SM/10208 | Augmentation | Acceptance cum formal order for the work of Additional work for supplying and laying of different dia HDPE pipe line with FHTC and necessary allied Works at Anandapur (JL-89) mouza of Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD,PHE Dte. (SL-03) | 1576/DWSD | 02/11/2022 | 847 | RANJIB GHATAK | 12.79 | 0 | 0 | 100
1730 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Water Supply arrangement to 03 nos AWC without electricity (For Students up to 350) Blocks ¿Kanksa , with out PWSS under Durgapur Water Supply Division PHE Dte 1) Bishnupur adibasipaara ICDs and with PWSS -- 2) kanchanpur adibasipara 3) nayakanchanpur adibasipara (SL-43) | 623/DWSD | 21/04/2022 | 20 | SAIKAT RAY | 8.78 | 8.69 | 99.04 | 0
1731 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Water Supply arrangement to 03 nos AWC without electricity (For Students up to 350) Blocks ¿Kanksa , with out PWSS under Durgapur Water Supply Division PHE Dte 1) Chua ICDS and with PWSS 2) dubarajpur colony ICDS 3) binodepur dompara (SL-45) | 630/DWSD | 21/04/2022 | 20 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 8.71 | 8.6 | 100 | 0
1732 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) Kherobari FP school 2) Raghunathpur FP School 3) 1) Kanthal danga FP School 4) Andharsuli FP School And With PWSS 1) sreekrisnapur majhipara SSk 2) Madhaganj FP school 3) madhaganj SSk 4) Gourbzar FP school 5) joyrampur FP School (SL-19) | 599/DWSD | 21/04/2022 | 20 | GHOSH & ROY ENTERPRISE | 13.91 | 13.68 | 100 | 0
1733 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) Fhulihari FP School 2) Fhulihari Purba Adibasi para SSK 3) Shibpur Suta danga SSK 4) Shibpur Jr HS And With PWSS 1) Bonkati Bouripara SSK 2) ajyodha Ruidas para SSK 3) satkahania FP school 4) dangal NC SSK 5) Rampur dangal adibasi FP School (SL-16) | 615/DWSD | 21/04/2022 | 20 | BABA LOKENATH ENTERPRISE | 13.91 | 13.68 | 100 | 0
1734 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . With PWSS 1) Modan ramnath samity FP school 2) kantaberia FP school 3) dhabani FP school 4) bar goria FP school 5) Labnapara High school 6) Pratapur KT Vidyapith 7) Pratappur FP school 8) Labnapara FP school 9) jamgora adibasipara SSk 10) jamgora FP school. (SL-13) | 742/DWSD | 06/05/2022 | 15 | CHANDAN HAZRA | 10.88 | 10.59 | 100 | 0
1735 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) Napara CP SSK 2) Rajbandh Uttar para ssk 3) ) babnabera MSK 4) babnabera SSK . And With PWSS 1) 1) Anandapur FP School 2) gangbil Hindi Jr High school 3) Gangbil Lalbaba SSK 4) gangbil FP School 5) gangbil tanty para SSk | 613/DWSD | 21/04/2022 | 20 | SHILPA UDDYOG ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 13.77 | 13.41 | 100 | 0
1736 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) rakhitpur dompara SSK 2) molandighi dangapara SSK 3) sahid sukumar banerjee Memorial school 4) Molandighi durgadas vidyamandir And With PWSS 1) prayagpur SSK 2) panagarh bauripara Metepara FP 3) panagarh gram FP School 4) Piarignaj Chara chandra HS 5) peariganj FP school (SL_09) | 598/DWSD | 21/04/2022 | 20 | KIRON ENTERPRISE | 13.88 | 13.56 | 100 | 0
1737 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) kanksa Mirpara SSK 2) garadha FP school 3) dhobaru FP school 4) hazra danga AP SSK And With PWSS amandanga adibasi FP school 2) kanksa mollapara SSK 3) Kanksa mollapara Fp school 4). setar bandh Sk 5) Tilaboni SSk.(SL-07) | 602/DWSD | 21/04/2022 | 20 | CHATTERJEE CONSTRUCTION | 13.91 | 13.72 | 100 | 0
1738 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) Araichan adibasi para SSk 2) Nonagara FP school 3) Kuldiha Adibasi FP School 4) Kuldiha FP School And With PWSS 1) kanchhanpur FP school 2) kanchanpur Jr High school 3) nayakanchanpur FP School 4) nayakanchanpur SSK 5)Rautdihi SSK (SL-13) | 603/DWSD | 21/04/2022 | 20 | CHATTERJEE CONSTRUCTION | 13.91 | 12.26 | 100 | 0
1739 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) Moldanga adibasipara SSk 2) Molandighi FP School 3) Lohaguri FP school 4) rakhit Pur FP school And With PWSS 1) Kanksa camp FP school 2) sundiara FP school 3) sree ramkrisna sebasram vidyappith 4) Tilack chandrapur JS high school 5) borobandh adibasipara SSK (SL-10) | 604/DWSD | 21/04/2022 | 20 | M/S MONDAL ENTERPRISE | 13.9 | 13.67 | 100 | 0
1740 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) Aduria danga SSK 2) Bishnupur FP school 3) Hariki FP school 4) rakhitpur majhipara FP school And With PWSS 1) Roopganj FP school 2) Krisnapur Fp school 3) krisnapur MSK 4) kajladihi FP School 5)ajoypally FP school | 605/DWSD | 21/04/2022 | 20 | QUICK PAL SUPPLIERS | 13.91 | 13.54 | 100 | 0
1741 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Repairing of distribution pipe line drain kanchha road and others necessary allied work at front gate way of staff room of Hetedoba H/W site under Gourbazar-Ichhapur piped W/s Scheme under DWSD, PHE Dte.(SL-17) | 432/DWSD | 30/03/2022 | 15 | MD AAMIR KHAN | 4.83 | 4.77 | 100 | 0
1742 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . With PWSS 1) kailashpur FP school 2) jagannathpur FP school 3) gopendanfa FP school 4) kantaberia FP School 5) Kalikapur FP school 6) bansol FP school 7) BM Plot SSk 8) Bansgora Maji para SSK 9) bansgora FP School 10) Ichhapur gangamata FP school (SL-22) | 591/DWSD | 21/04/2022 | 20 | M/S BADAL GHOSH | 10.89 | 10.6 | 100 | 0
1743 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) Thakuranibazar SSK 2) jatgoria FP School 3) jatgaria Jr HS 4) Jambon FP School And With PWSS 1) Bill para SSK 2) Radhamohanpur FP School 3) Baganpara Adibasi FP School 4) Bonkati FP School 5) Basudevpur Jr HS (SL-15) | 611/DWSD | 21/04/2022 | 20 | BASANTI TRADERS | 13.89 | 13.46 | 100 | 0
1744 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) rajhat FP School 2) Raghunathpur kala danga Adibasipara SSK 3) Jamdoba SSK 4) Brambhangram FP School And With PWSS 1) shyamsundarpur SSK 2) Ghutulia Bhabanandapur SSk 3) Gourbazar shyamsundar Fp School 4) badyanathpur FP school 5)basudha FP school (SL-17) | 614/DWSD | 21/04/2022 | 20 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 13.8 | 13.37 | 100 | 0
1745 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1)chua FP school 2) Akandara FP School 3) Ghatak danga adibasi FP School 4) Saraswatiganj FP school And With PWSS 1) domra FP school 2) rajar danga Majhipara FP school 3) Arrah FP school 4) Arrah kalinagar FP School 5) Arrah bagdipara SSK (SL-11) | 631/DWSD | 21/04/2022 | 20 | BABA LOKENATH ENTERPRISE | 13.91 | 13.68 | 100 | 0
1746 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS Telipara FP School 2) Banagram Adibasi FP School And With PWSS 1) gourbazar ramapada HIGH School 2) Netaji FP school 3) kalinagar Fp school 4) Kendula FP School 5) bagura adibasi FP school | 633/DWSD | 21/04/2022 | 20 | M/S. A. G. CONSTRUCTION | 13.91 | 13.51 | 100 | 0
1747 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) Molandighi danga para SSk 2) rakhitpur HS 3) Bamunara Adibasi FP School 4) farash danga FP school And With PWSS 1) Murgoboni SSk 2) Pryagpur FP school 3) Rajkusum FP school 4) Gorai SM sikhsa Niketan HS 5) rajkusum TD SSK 5) harakrisnapally SSK (SL-08) | 634/DWSD | 21/04/2022 | 20 | DIP CONSTRUCTION | 13.9 | 13.57 | 100 | 0
1748 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) mobarakganj FP School 2) Mobarakganj PBP SSK 3) Aymadanga bagdipara SSK 4 ) Setar bandh SSk And With PWSS 1) shilampur kantabagan SSK 2) Madhammath FP School 3) Shilampur Purba para FP school 4) shilampur High school 5) Shilampur FP School (SL-02) | 635/DWSD | 21/04/2022 | 20 | RUBY CONSTRUCTION | 13.9 | 13.81 | 100 | 0
1749 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Water Supply arrangement to 06 nos AWC without electricity (For Students up to 350) Blocks ¿Kanksa , under Durgapur Water Supply Division PHE Dte with out PWSS 1) Rakhitpur ICDS 2) Rakhitpur bagdipara ICDS 3) Kuldiha Adibasipara ICDS and with PWSS 4) rautdihi Bagdipara 5) Kanchanpur ruidas para 6) kanchanpur palpara ICDs no 313.(SL-40) | 601/DWSD | 21/04/2022 | 20 | KIRON ENTERPRISE | 23.04 | 22.85 | 100 | 0
1750 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Water Supply arrangement to 03 nos AWC without electricity (For Students up to 350) Blocks ¿Kanksa , with out PWSS under Durgapur Water Supply Division PHE Dte 1) Ghatakdanga adibasipara ICDS and with PWSS-- 2) ajoypally paschim para ICDS 3) ajoypally purba para ICDS (SL-42) | 616/DWSD | 21/04/2022 | 20 | BABA LOKENATH ENTERPRISE | 8.78 | 8.68 | 100 | 0
1751 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1) Dhobaghata FP school 2) Napara Swamiui FP school 3) sokna bauripara FP school 4) natungram FP school And With PWSS 1) Panagarh bazar South canal para SSK 2) kanksa HS School 3) Kanksa Mollapara Paschim SSK 4) kanksa Seikh para SSK 5) Tilackhandrapur Fp school (SL-06) | 617/DWSD | 21/04/2022 | 20 | DARPAN DAS & CO. | 13.91 | 13.52 | 100 | 0
1752 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS1) rajbandh Netaji Vidyapith FP 2) Amlajora HIGH School 3) rajbandh JR Basic school 4) Keten FP School And With PWSS 1) Panagarh Sisu bikas vidyalaya 2) Kanksa Mollapara FP School 3) Jhinuk Goria majhipara FP school 4) panagarh rail colony FP school 5) panagarh rail colony HS school (SL-04) | 610/DWSD | 21/04/2022 | 20 | CHATTERJEE CONSTRUCTION | 13.91 | 13.5 | 100 | 0
1753 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS nababeta FP School 2) jamdaha HIGH School 3) jamdaha FP school 4) jatgaria SSK And With PWSS 1) Itadanga FP School 2) sashipur FP School 3) binodepur Dompara SSK 4) basudevpur FP School 5) Nabagram Adibasi FP school (SL-14) | 620/DWSD | 21/04/2022 | 20 | TARA PRASAD SARKAR | 13.89 | 11.68 | 100 | 0
1754 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Water Supply arrangement to 06 nos AWC without electricity (For Students up to 350) Blocks_Kanksa , under Durgapur Water Supply Division PHE Dte with out PWSS 1)manikaraa ankurepara ICDS 2) Murgabani adibasi para 3) Dhobaru ICDS and with PWSS 4) Tilack chandrapur Adibasipara ICDS s 5) Kajla dihi ICDS 6) Bargoria 58 ICDS (SL-39) | 595/DWSD | 21/04/2022 | 20 | RANJIB GHATAK | 23.02 | 22.81 | 100 | 0
1755 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Water Supply arrangement to 03 nos AWC without electricity (For Students up to 350) Blocks Kanksa with out PWSS under Durgapur Water Supply Division PHE Dte 1) saraswatiganj ICDS and with PWSS --2) sundipur adibadibasipara 3 ) Talbahari adibassipara (SL-44) | 621/(A)/DWSD | 21/04/2022 | 20 | SUJAY KUMAR RAY | 8.77 | 8.67 | 100 | 0
1756 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1)manikara FP school 2) beharpur FP school 3) Beharpur bagdipara SSK 4) Babnebera FP school And With PWSS 1) Panagarh bazar hindi FP School 2) Panagarh bazar Fp school 3) panagarh bazar purba para HINDI 4) Madhammath Metepara SSK 5)kanksa Singh para SSk (SL-05) | 632/DWSD | 21/04/2022 | 20 | MAK CONSTRUCTION CO. | 13.91 | 13.89 | 100 | 0
1757 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal for the work of Additional work for providing of FHTC from Solar tube well stand alone at Basudha mouza and Shyambazar mouza of Bonkati GP and kanksa block under DWSD ,PHE Dte (SL-10) | 1030/DWSD | 04/07/2022 | 10 | JOY GURU ENTERPRISE | 4.97 | 5.08 | 100 | 0
1758 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Repairing of exiting house hold tap connection (Damaged) and re connection of the same repairing of 90/110/125/140/200 mm dia UPVC pipe line at different place of command area of Gourbazar water supply ,distribution system from Gourbazar OHR under Gourbazar piped W/S Scheme (Sl-07) | 1027/DWSD | 04/07/2022 | 15 | JOY GURU ENTERPRISE | 4.13 | 4.07 | 100 | 0
1759 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Supplying UPVC pipe for laying of additional branch pipe line at Arati Village to provide FHTC at Arati mouza (JL-54) of Durgapur-Faridpur block of Improvement of Gourbazar-Ichhapur piped W/s Scheme under DWSD, PHE Dte.(SL-01)(SL-01) | 1021/DWSD | 04/07/2022 | 10 | BISHAL ENTERPRISE | 4.79 | 4.8 | 100 | 0
1760 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to all Schools under Kanksa Block Durgapur W/S Division PHE Dte . Without PWSS 1)chua FP school 2) Akandara FP School 3) Ghatak danga adibasi FP School 4) Saraswatiganj FP school And With PWSS 1) domra FP school 2) rajar danga Majhipara FP school 3) Arrah FP school 4) Arrah kalinagar FP School 5) Arrah bagdipara SSK (SL-11) | 635/DWSD. | 21/04/2022 | 20 | BABA LOKENATH ENTERPRISE | 10.48 | 0 | 0 | 0
1761 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to Dubrajpur F.P. school under Kanksa block covered by Kanksa (Zone-II) PWSS having Electricity but uncovered by PWSS under DWSD, PHE Dte | 119/DWSD | 01/02/2022 | 20 | BASANTI TRADERS | 2.12 | 0 | 0 | 0
1762 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to Shibpur F.P. school under Kanksa block covered by Kanksa (Zone-II) PWSS under DWSD, PHE Dte | 118/DWSD | 01/02/2022 | 15 | M/S MONDAL ENTERPRISE | 2.12 | 0 | 0 | 0
1763 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Providing water supply to Ijjatganj Junior high school under Kanksa block covered by Kanksa (Zone-II) PWSS under DWSD, PHE Dte | 116/DWSD | 01/02/2022 | 15 | M/S MONDAL ENTERPRISE | 1.1 | 0.73 | 100 | 0
1764 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Water Supply arrangement to 03 nos AWC without electricity (For Students up to 350) Blocks ¿Kanksa with out PWSS under Durgapur Water Supply Division PHE Dte 1) Banagram ICDs with PWSS 2) Radhanagar ICDS 3) Sashipur Jhaudanga Dompara ICDs (SL-47) | 621/DWSD | 21/04/2022 | 20 | MUKHERJEE ENTERPRISE | 8.77 | 8.76 | 100 | 0
1765 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of providing water supply to panagarh bazar high school under Kanksa block covered by Kanksa (Zone-II) PWSS having electricity but uncovered by PWSS under DWSD ,PHE Dte (Sl-24) | 121/DWSD | 20/01/2022 | 15 | BABA LOKENATH ENTERPRISE | 2.12 | 0 | 0 | 0
1766 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman , SM/10373 | School | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Banerjee of Domra mouza to combat draught like situation and providing drinking water to habitations ,School,AWC etc. under DWSD ,PHE Dte (SL-14) | 1266/DWSD | 25/08/2022 | 986 | AMARANJALI CONSTRUCTION | 6.55 | 0 | 0 | 100
1767 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Preparation of DPR for Augumentation of Roshna Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 05) | 2349/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 3.03 | 3.03 | 100 | 0
1768 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Sub Soil Investigation for 300 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3140/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 0 | 50
1769 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Providing And Installation of Electro-Mechanical Equipments and Allied Works at Gourandi under Augmentation of Roshna Piped Water Supply Scheme, Block-Baraboni, Dist.-Paschim Bardhaman. | 606/AMD | 03/03/2023 | 90 | M/S SWAPAN BANERJEE | 32.53 | 21.61 | 66.44 | 70
1770 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Material Requisition To Resource Division | 2349/RCD-I | 28/09/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1771 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Material Requisition To Resource Division | 1638/RCD-I | 27/04/2023 | 0 | Resource Division | 30.48 | 0 | 0 | 0
1772 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Providing and Installation of Electro-Mechanical Equipments and Allied Works at Panuria under Augmentation of Panuria Itapara Water Supply Scheme, Block-Baraboni, Dist.-Paschim Bardhaman. | 488/AMD | 22/02/2023 | 365 | BENGAL CONSTRUCTION | 180 | 0 | 0 | 68
1773 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order for Construction of 1.5 mtrs Height Boundary Wall with double column after 15 mtrs interval along with 750 mm Height 3 layer Barbed Wire around Roshna Head Works Site under Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl. No. 09) | 1131/ RCD I | 24/03/2023 | 30 | SRI KRISHNA ENTERPRISE | 27.16 | 25.57 | 94.15 | 95
1774 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order forLaying of different dia HDPE pipe line including concrete cutting and mending work at Khyerbaid, Amdiha area Zone-IX under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. (Sl. No. 26) | 1092/RCD-I | 23/03/2023 | 60 | SRI KRISHNA ENTERPRISE | 24.69 | 13.18 | 53.4 | 80
1775 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Lowering of Submersible Pumping Machineries in Newly sunk RBTW No-6 & 7 for CWR at Roshna Pump House under Roshna Water Supply Scheme. | 1811/AMD | 29/10/2024 | 30 | M/S SAJAHAN CHOWDHURY | 12.12 | 0 | 0 | 0
1776 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Hiring of SUV (A.C) (Non Airconditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. for the Office Use of the Deputy Superintending Engineer, RCFA W/S Circle, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.03.2024 to 31.08.2024) (Sl No. 02) | 718C/RCD-I | 01/03/2024 | 184 | SHYAMAL MAJI | 0.9 | 0.6 | 66.67 | 10
1777 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Roshna Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-D) | 1275/RCD-I | 02/06/2022 | 90 | JYOGOMAYA ENTERPRISE | 28.02 | 28.01 | 100 | 100
1778 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order for Repairing of Boundary wall, dismantling & reconstruction of flooring of Pump House, CWR and other allied work at H/W site of Ballavpur Hospital under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | 2324/RCD-I | 01/08/2023 | 21 | SUBHADEEP DAS | 7.46 | 7.4 | 50 | 100
1779 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Lowering of Submersible Pumping Machineries for Newly Sunk RBTWs under Panuria Water Supply Scheme. | 552/AMD | 14/03/2024 | 30 | BENGAL CONSTRUCTION | 6.28 | 6.28 | 100 | 100
1780 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum Work Order for Balance work of construction of CWR at Runakuraghat for Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1590/RCD-I | 27/06/2024 | 45 | SAMIR KUMAR ROY CHOWDHURY | 9.92 | 9.07 | 100 | 100
1781 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order for Additional Laying of 200 mm dia rising main for the Augmentation of Roshna Piped Water Supply Scheme . under RCFA Division-I PHE Dte. | 462/RCD-1 | 12/02/2024 | 30 | T R ENTERPRISE | 12.98 | 12.18 | 100 | 100
1782 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Fuel bill in favor of Ranjit Auto for the month of March 2024 for 1 no. Vehicle for Office of the Deputy Superintending Engineer, RCFA W/S Circle, PHE Dte, Govt. of West Bengal | 109/24-25 | 21/06/2024 | 0 | RANAJIT AUTO | 0.2 | 0 | 0 | 0
1783 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | fuel bill infavor of Ranjit Auto for one no vechile for affiliated of the Deputy superintending Engineer RCFA W/S circle PHE Dte Govt of west bengal | 257/24-25 | 28/08/2024 | 0 | RANAJIT AUTO | 0.25 | 0 | 0 | 0
1784 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Fuel bill in favor of Ranjit Auto for the month of April 2024 for 1 no. Vehicle for Office of the Deputy Superintending Engineer, RCFA W/S Circle, PHE Dte, Govt. of West Bengal | 110/24-25 | 21/06/2024 | 0 | RANAJIT AUTO | 0.19 | 0 | 0 | 0
1785 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | fuel bill infavor of Ranjit Auto for one no vechile for affiliated of the Deputy superintending Engineer RCFA W/S circle PHE Dte Govt of west bengal | 255/24-25 | 28/08/2024 | 0 | RANAJIT AUTO | 0.24 | 0 | 0 | 0
1786 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order for Sinking of 2 (Two) no. 200 mm dia river bed tube well in the river Ajoy of Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte.(SL No 08) | 1282/RCDI | 02/06/2022 | 30 | SRI KRISHNA ENTERPRISE | 21.96 | 10.24 | 46.64 | 100
1787 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum Work Order for Additional laying of 90 mm dia HDPE pipe of distribution network at Aliganj and surrounding area for Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | 1151/RCD-1 | 24/03/2023 | 30 | RUBY CONSTRUCTION | 5.99 | 4.63 | 77.37 | 50
1788 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order for laying of 200 mm dia rising main for Roshna OHR from Gourandi CWR under Augmentation of Roshna Piped water Supply Scheme under RCFA Div-I, PHE Dte. | 1034/RCDI | 23/03/2023 | 60 | SRI KRISHNA ENTERPRISE | 11.44 | 8.64 | 75.54 | 60
1789 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Formal work order for construction of CWR 150 cum, sub station building of H/W site, pump house, chlorine room and other allied work (Bank of Ajoy river) under Semalya Water Supply Scheme under RCFA Division-I PHE Dte. | 1216_1_RCD-I | 24/03/2023 | 120 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 72.59 | 0 | 0 | 0
1790 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order for Repairing, Renovation, renewing & overhauling & obsolete i) for 2 nos. Iron Removal Plant (Pressure type) each capacity 45 cum/Hr at Churulia Head Works Site for Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. (Part-A) ii) for 3 Nos. Iron Removal Plant (Pressure type of capacity 50 cum/hr 1no. & 75cum/hr ¿ 2nos) at Madantore Head works site for Madantore W/S Scheme under RCFA Division-I PHE Dte. (Part-B) iii) for 4 nos. Iron removal Plant (Pressure type) each capacity 20 cum/hr at Pandabeswar Head Works Site for Pandabeswar W/S Scheme under RCFA Division-I PHE Dte. (Part-C) iv) for 2 nos. Iron Removal Plant (Pressure type) each capacity 50 cum/hr at Madanpur Head Works Site under RCFA Division-I PHE Dte. (Part-D) | 1391_I_RCD_I | 11/04/2023 | 60 | TARAPRASAD SARKAR | 52.19 | 46.97 | 90 | 70
1791 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Roshna Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-B) | 1273/RCD-I | 02/06/2022 | 90 | SRI KRISHNA ENTERPRISE | 75.81 | 74.68 | 100 | 100
1792 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Roshna Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-C) | 1274/RCD-I | 02/06/2022 | 670 | RUBY CONSTRUCTION | 41.7 | 37.77 | 91.84 | 80
1793 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Roshna Piped Water Supply Scheme including FHTC Work and Construction of 300 cum capacity 20 Mtr staging height RCC Over Head Reservoir Block Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Part-A) | 1607/RCD-I | 06/07/2022 | 180 | SRI KRISHNA ENTERPRISE | 163.56 | 163.51 | 100 | 100
1794 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order Additional work for the laying of 315 mm dia HDPE pipe instead of 300 mm dia D.I. pipe of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-6 Distribution Segment) Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1140/RCD-I | 24/03/2023 | 30 | UMA ENTERPRISE | 71.96 | 70.46 | 100 | 30
1795 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order for Extension of pipe line for providing 60 nos FHTC at different area of Kendra for Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | 2861/RCD-I | 06/10/2023 | 30 | TARA CONSTRUCTION | 26.79 | 23.92 | 100 | 100
1796 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum work order for Additional work for laying and pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Aliganj within distribution system Part-C of Roshna under Augmentation of Roshna PWSS under RCFA Division-I PHE Dte. | 472/RCD-1 | 12/02/2024 | 25 | RUBY CONSTRUCTION | 11.75 | 0 | 0 | 100
1797 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roshna Piped Water Supply Scheme . , SM/10642 | Augmentation | Acceptance cum Work Order for Additional work for Additional work including Adopting Trench less technology (e.g. Jack Pushing Method etc) at 04(Four) nos. location at (i)Churulia Main Road, (ii)Nazrul Academy Road Crossing (iii)Likapur Road Crossing (iv)Madhudanga OHR and allied MS work including open cut at pump house and existing OHR site including supply of Hume pipe in related to rising main of Churulia and Madantore under Augmentation of Roshna PWSS under RCFA Division ¿I PHE Dte | 1020/RCD-I | 16/03/2024 | 30 | T R ENTERPRISE | 40.55 | 39.86 | 100 | 100
1798 | PASCHIM BARDHAMAN | Durgapur W/S Division | DHOBARU PIPED WATER SUPPLY SCHEME , SM/10999 | New | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at DHOBARU mouza of Dhobaru piped W/s Scheme under DWSD, PHE Dte (Part-A ,B and C) (SL-01) | 774/DWSD | 17/05/2022 | 45 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 44.99 | 41.09 | 100 | 100
1799 | PASCHIM BARDHAMAN | Durgapur W/S Division | DHOBARU PIPED WATER SUPPLY SCHEME , SM/10999 | New | Quotation for Dhobaru W/S Scheme , Pump House No- 01 , Panagarh CCC | BP-2022-23-335 | 17/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.47 | 0 | 0 | 0
1800 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. , SM/10640 | Augmentation | Formal work order for augmentation of Jamuria (Rural)(zone-I) piped water supply scheme including FHTC & allied work within Jamuria Block under RCFA Div-I, PHE Dte.(Part-B) | 16/RCD I | 05/01/2023 | 30 | DIP CONSTRUCTION | 0 | 0 | 0 | 0
1801 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. , SM/10640 | Augmentation | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Jamuria Rural-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3137/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 0 | 0
1802 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. , SM/10640 | Augmentation | Preparation of DPR & Route Survey for Augmentation of Jamuria (Rural) (Zone-II) Piped Water Supply Scheme Block-Jamuria, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 13) | 2230/RCD I | 15/09/2022 | 15 | APEX ENGINEERING | 3.58 | 3.58 | 100 | 0
1803 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. , SM/10640 | Augmentation | Material Requisition To Resource Division | 2345/RCD-I | 28/09/2022 | 0 | Resource Division | 9.24 | 0 | 0 | 0
1804 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. , SM/10640 | Augmentation | Acceptance cum work order for Construction of High Lift Pump House at Riverside H/W site under Augmentation of Jamuria Rural (Zone I & II) Water Supply Scheme under RCFA Division-I PHE Dte. | 3282/RCDI | 20/12/2022 | 90 | GLOBAL CONSTRUCTION | 31.24 | 27.01 | 86.48 | 90
1805 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. , SM/10640 | Augmentation | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural- II Piped Water Supply Scheme including FHTC work (Segment- I) under Jamuria Block in the district of Paschim Bardhaman Under RCFA Division - I PHE Dte. | 2120/RCD-I | 27/08/2024 | 60 | SIMA ENTERPRISE | 46.06 | 0 | 0 | 40
1806 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. , SM/10640 | Augmentation | Distribution network for Augmentation of Jamuria Rural-II Piped Water Scheme including FHTC work Block Jamuria, Dist Paschim Bardhaman under RCFA Div-I PHE Dte. | 2449/RCD-I | 13/10/2022 | 180 | JOY HIND TUBEWELLS | 236.71 | 59.28 | 25.04 | 100
1807 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. , SM/10640 | Augmentation | Acceptance cum Work Order for Rising Main of Augmentation of Jamuria Rural (Zone-I & II) under RCFA Division-I PHE Dte (sl.no-14) | 805/RCD-I | 06/03/2023 | 60 | M/S MONDAL ENTERPRISE | 22.77 | 8.18 | 35.93 | 40
1808 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. , SM/10640 | Augmentation | Acceptance cum work order for Additional work of Distribution Network for Augmentation of Jamuria (Rural) (Zone-II) Piped Water Supply Scheme including FHTC & allied work within Jamuria Block under RCFA Division-I PHE Dte. (Part- A) | 2133/RCD-I | 27/08/2024 | 146 | M/S B.K. CONSTRUCTION | 20.94 | 10.82 | 51.67 | 65
1809 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. , SM/10640 | Augmentation | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural- II Piped Water Supply Scheme including FHTC work (Segment- II) under Jamuria Block in the district of Paschim Bardhaman under RCFA Division - I PHE Dte. | 2117/RCD-I | 27/08/2024 | 804 | MS SAMANTA CONSTRUCTION | 48.54 | 0 | 0 | 100
1810 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. , SM/10640 | Augmentation | Acceptance cum work order for Construction of 150 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Augmentation of Jamuria Rural (Zone-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (2nd Call) | 1631/RCD-I | 26/04/2023 | 366 | UNITED CONSTRUCTION | 69.15 | 48.41 | 100 | 100
1811 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Formal order for the work of Hire & labour charges for staging and scaffolding bamboo barricading and removal of rubbish for dismantling of RCC elevated 350 M3 OHR of 20 mtr staging height at Gopalpur H/W Site under DWSD ,PHE Dte | 1765/DWSD | 17/12/2021 | 30 | TARA CONSTRUCTION | 12.55 | 0 | 0 | 0
1812 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI Specials valves and allied works under command area of Gopalpur mouza for Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte | 1758/DWSD | 16/12/2021 | 30 | RANJIB GHATAK | 15.53 | 0 | 0 | 0
1813 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Repairing and renovation of pump house with sanitary arrangement at Gopalpur mouza for Augmentation of Gopalpur W/S Scheme under DWSD,PHE Dte.(SL-01) | 1661/DWSD | 25/11/2021 | 25 | M/S UNIQUE | 4 | 3.68 | 92.04 | 0
1814 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Repairing of leakage bursting and chokage cleaning at Gopalpur distribution system & Its all command areas of Augmentation of Gopalpur piped W/s Scheme under DWSD ,PHE Dte (SL-07) | 586/DWSD | 21/04/2022 | 7 | QUICK PAL SUPPLIERS | 4.82 | 4.39 | 91 | 0
1815 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Supplying, laying and aligning of HDPE/DI distribution pipe line and allied works including FHTC and connection providing to ICDS ,Health Centre, Govt Building ,School under command area of Gopalpur Mouza of Augmentation of Gopalpur piped W/S Scheme under DWSD,PHE Dte . (SL-17) | 817/DWSD | 21/05/2022 | 184 | MACHINO TECHNO | 77.49 | 51.75 | 66.78 | 0
1816 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Formal order for the work of Repairing as well as extension of boundary wall with supply fitting fixing of ornamental Gate at Gopalpur H/W site of Gopalpur Mouza for Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte | 1767/DWSD | 17/12/2021 | 30 | D. S. ENTERPRISE | 8.1 | 7.18 | 100 | 0
1817 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of rising main & distribution system of Gopalpur Piped W/s Scheme under DWSD, PHE Dte | 65/DWSD | 19/01/2022 | 30 | EXECUTIVE ENGINEER , RESOURCES DIVISION, PHE DTE. | 34.25 | 34.28 | 100 | 0
1818 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of dismantling of abandoned existing structure at Gopalpur H/W site of Augmentation of Gopalpur W/S Scheme under DWSD,PHE Dte.(SL-02) | 1660/DWSD | 25/11/2021 | 20 | QUICK PAL SUPPLIERS | 3.94 | 3.87 | 100 | 0
1819 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Distribution of abandoned existing structure at Gopalpur H/W site and others Pump House site under Augmentation of Gopalpur W/s Scheme of DWSD,PHE Dte (SL-08) | 587/DWSD | 21/04/2022 | 7 | CHATTERJEE CONSTRUCTION | 2.16 | 2.07 | 100 | 0
1820 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Formal order for the work of Dismantling of existing boundary wall and reconstruction of balance portion boundary wall at Gopalpur H/W site (OHR) site of Augmentation of Gopalpur piped W/s Scheme under DWSD ,PHE Dte (SL-09) | 750/DWSD | 10/05/2022 | 10 | D. S. ENTERPRISE | 29.41 | 29.22 | 100 | 0
1821 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Continuation for the work of soil investigation for demining the safe bearing capacity and other relevant parameters of soil for the work of construction of RCC Elevated at Gopalpur Reservoir site of Augmentation of Gopalpur W/s Scheme under DWSD ,PHEDte | 353/DWSD | 21/03/2022 | 25 | MABCO CONSULTANT | 1.2 | 1.2 | 100 | 0
1822 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Construction of temporary approach road at Gopalpur H/W site of Gopalpur piped W/s Scheme under DWSD ,PHE Dte(SL-07) | 975/DWSD | 22/06/2022 | 15 | AMAR CONSTRUCTION | 4.11 | 3.97 | 100 | 0
1823 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Land development at Gopalpur H/W site and back filling along the boundary wall of Augmentation of Gopalpur piped W/s Scheme under DWSD ,PHE Dte (SL-12) | 979/DWSD | 22/06/2022 | 15 | AMAR CONSTRUCTION | 4.63 | 4.39 | 100 | 0
1824 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Quotation for Gopalpur Pump house no -02 | BP-2022-23-93 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.48 | 0 | 0 | 0
1825 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Quotation for Gopalpur Pamp House No 1 | BP-2021-22-208 | 15/03/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.77 | 0 | 0 | 0
1826 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Quotation for Gopalpur Pump house no -03 | BP-2022-23-94 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.81 | 0 | 0 | 0
1827 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Formal order for the work of Sinking 3(Three) Nos 300X200 mm dia Tube well 210 mtr deep by DR ring method using PVC pipe and fibber glass reinforced epoxy resin slotted at Gopalpur H/W site under Augmentation of Gopalpur piped W/s Scheme under Durgapur W/S Division, PHE Dte. | 1749/DWSD | 15/12/2021 | 30 | M/S. D. PALIT & CO. | 42.11 | 27.75 | 65.9 | 100
1828 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance for the work fabrication and erection of MS structural bridge used to cross 600 mm dia rising main pipe line near Bankura more under surface based W/s Scheme for Panagarh Industrial Park under DWSD,PHE Dte (SL-03) | 1715/DWSD | 09/12/2021 | 40 | MACHINO TECHNO | 68.77 | 0 | 0 | 0
1829 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Continuation order for the work of Hiring of Luxury diesel Ambassador car including higher model -2012 on wards of diesel Ambassador or equivalent for official use of the Assistant Engineer of EE/DWSD/PHE Dte for the use of the Office of the EE/DWSD/PHE Dte ADDA Adm: Building EPIP Complex ,Banskopa ,Durgapur-713212(w.e.f 01.05.2022 to 30.04.2023) (Vehicle No-WB37D6848) | 687/DWSD | 28/04/2022 | 365 | PRAMIT CHATTERJEE | 1.65 | 4.36 | 182.42 | 0
1830 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 3 at Augmentation of Gopalpur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1243/CMD | 12/07/2022 | 30 | GOENKA ENTERPRISE | 10.21 | 10.09 | 98.86 | 0
1831 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle for site vigit against JJM related scheme) for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.01.2023 to 30.06.2023).(Sl-01) | 1801/DWSD | 30/12/2022 | 182 | PRAMIT CHATTERJEE | 0.82 | 1.6 | 100 | 0
1832 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Continuation order for the work of Hiring of Luxury diesel Ambassador car including higher model -2012 on wards of diesel Ambassador or equivalent for official use of the Assistant Engineer of EE/DWSD/PHE Dte for the use of the Office of the EE/DWSD/PHE Dte ADDA Adm: Building EPIP Complex ,Banskopa ,Durgapur-713212(w.e.f 01.05.2023 to 31.10.2023) (Vehicle No-WB37D6848) | 654/DWSD | 27/04/2023 | 183 | PRAMIT CHATTERJEE | 0.82 | 2.36 | 119.84 | 100
1833 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Formal order for the work of Repairing and renovation of PH with sanitary arrangement as well as boundary wall at PH site (T.No-II & III) of crackly nature of soil according to Deptt drawing no GWSS/EC/PHE Dte /DRG-3/7-8 ,Size-5.9X4.10 m out to out) at Gopalpur mouza for Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte | 1737/DWSD | 13/12/2021 | 45 | CHANDAN HAZRA | 25.78 | 24.35 | 100 | 100
1834 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Supplying fitting fixing of PCC precast pillar and fencing with barbed wire errection of Govt sign board 03 nos place for protection of vest land at Molandighi of Bistupur W/s Scheme of 03 Nos at Gopalpur of Augmentation of Gopal pur piped W/s Scheme | 84/DWSD | 25/01/2022 | 15 | MD JAWED KHAN | 2.33 | 2.33 | 100 | 0
1835 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Electric wiring and other allied works for modernization of the existing Gopalpur lab for NABL accreditation of Sub-District Water test ing lab at Kanksa of Jamgora-Jagannathpur piped W/s Scheme under DWSD ,PHE Dte | 100/DWSD | 31/01/2022 | 15 | BASANTI TRADERS | 1.65 | 1.57 | 100 | 0
1836 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Details route survey, drawing design of distribution network & preparation of estimates and DPR in connection with the JJM (FHTC) of Augmentation of Gopalpur piped W/S Scheme DWSD, PHE Dte.(SL-02) | 1685/DWSD | 02/12/2021 | 30 | M/S R.DUTTA AND CO. | 8.48 | 8.48 | 100 | 0
1837 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Construction of pump house cum chlorine room at Railpar Sarada Pally H/W site pump house No-2 tube well No-02 for Augmentation of Kanksa (Zone-II/D) pipe W/s Scheme under DWSD ,PHE Dte (SL-02) | 241/DWSD | 25/02/2022 | 45 | MUKHERJEE ENTERPRISE | 4.89 | 1.01 | 100 | 100
1838 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 1 of Gopalpur Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim Bardhaman. | 477/CMD | 28/03/2022 | 30 | RNS TRADING | 9.64 | 9.48 | 100 | 0
1839 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 2 at Augmentation of Gopalpur Water Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 911/CMD | 31/05/2022 | 30 | INDIA ENTERPRISE | 9.16 | 8.95 | 100 | 0
1840 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Extension of existing Gopalpur sub district laboratory at Kanksa of Augmentation of Gopalpur piped W/s Scheme under DWD ,PHE Dte (SL-13) | 980/DWSD | 22/06/2022 | 15 | BASANTI TRADERS | 4.94 | 3.9 | 100 | 100
1841 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex,Banskopa,DGP-12 (w.e.f 18.08.2022 to 17.02.2023). (SL-02) | 1237/DWSD | 17/08/2022 | 184 | PRAMIT CHATTERJEE | 0.82 | 2.38 | 100 | 0
1842 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle) of Assistant Engineer for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.09.2022 to 28.02.2023). (Sl-01) | 1236/DWSD | 17/08/2022 | 184 | BIPLAB BANERJEE | 0.82 | 2.4 | 100 | 0
1843 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Formal order for the work of Laying of 600 mm dia RCC (NP3) Hume pipe by modern Hydraulic Jack pushing method including laying 150 mm dia MS pipe line at DVC More over Suri road (NH-60) for ROB under Augmentation of RCFA Part-III W/s Scheme (Zone-II) under DWSD, PHE Dte (SL_12) | 872/DWSD | 26/05/2022 | 15 | RANJIB GHATAK | 13.63 | 0 | 100 | 100
1844 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Water supply arrangement at Kajladighi ICDS Centre of Bibihar GP having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Aug: of Gopalpur piped W/s Scheme under DWSD ,PHE Dte | 294/DWSD | 17/02/2023 | 15 | RANJIB GHATAK | 6.95 | 6.95 | 100 | 100
1845 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Formal order for the work Laying and aligning of distribution pipe line from Bonsol to towards Jhajra Majipara and allied works under Augmentation of Gopalpur piped W/s Scheme under DWSD ,PHE Dte. | 300/DWSD | 20/02/2023 | 15 | BABA LOKENATH ENTERPRISE | 6.27 | 6.27 | 100 | 0
1846 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance order for the work of Balance work for construction of boundary wall at Gopalpur H/W site (OHR) site of Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte | 111/DWSD | 24/01/2023 | 15 | D. S. ENTERPRISE | 4.36 | 4.34 | 100 | 0
1847 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Concreting of exiting dismantled road of Augmentation of Gopalpur piped W/S Scheme under DWSD,PHE Dte (Part-B) | 771/DWSD. | 22/05/2023 | 10 | GHOSH & ROY ENTERPRISE | 4.83 | 4.83 | 100 | 100
1848 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Concreting of exiting dismantled road of Augmentation of Gopalpur piped W/S Scheme under DWSD,PHE Dte (Part-A) | 768/DWSD | 22/05/2023 | 10 | SAIKAT RAY | 4.96 | 4.96 | 100 | 100
1849 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Replacement of existing pipe line at Nachan OHR to Protapur gram for Physical certification of HarGhar Jal in connection with JJM of Augmentation Gopalpur piped W/s Scheme under DWSD ,PHE Dte (SL-03) | 758/DWSD | 19/05/2023 | 20 | GHOSH & ROY ENTERPRISE | 9.66 | 9.64 | 100 | 100
1850 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Replacement of existing pipe line and extended the same of total command area of distribution network for physical certification of Har Ghat Jal in connection with JJM of Augmentation of Gopalpur piped W/S Scheme under DWSD ,PHE Dte. | 1135/DWSD | 20/07/2023 | 30 | MD AAMIR KHAN | 25.46 | 23.4 | 100 | 100
1851 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block under Augmentation of Gopalpur piped W/s Scheme (Part-A, B) | 1275/DWSD | 07/08/2023 | 15 | JOY GURU ENTERPRISE | 8.95 | 8.94 | 100 | 100
1852 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block under Augmentation of Roopganj piped W/s Scheme (Part-A, B) | 1276/DWSD | 07/08/2023 | 15 | JOY GURU ENTERPRISE | 8.95 | 8.95 | 100 | 100
1853 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Formal for the work of Construction of 500 M3 capacity ,20 Mtr staging height RCC Elevated Over Head Reservoir at Gopalpur under Augmentation of Gopalpur piped W/s Scheme under DWSD, PHE Dte.(SL-02) | 1745/DWSD | 15/12/2021 | 184 | AMAR CONSTRUCTION | 92 | 78.97 | 100 | 0
1854 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Material Requisition To Resource Division | 1815/DWSD | 30/12/2021 | 0 | Resource Division | 19.8 | 0 | 0 | 0
1855 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Material Requisition To Resource Division | 65/DWSD | 19/01/2022 | 0 | Resource Division | 34.32 | 0 | 0 | 0
1856 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Material Requisition To Resource Division | 1751/DWSD | 16/12/2021 | 0 | Resource Division | 1.27 | 0 | 0 | 0
1857 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation |  | BP-2023-24-121 | 07/08/2023 | 0 | P C FORMS & STATIONERY | 0.19 | 0 | 0 | 0
1858 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Continuation order for the work of Hiring of Luxury diesel Ambassador car including higher model -2012 on wards of diesel Ambassador or equivalent for official use of the Assistant Engineer of EE/DWSD/PHE Dte for the use of the Office of the EE/DWSD/PHE Dte ADDA Adm: Building EPIP Complex ,Banskopa ,Durgapur-713212(w.e.f 01.11.2023 to 30.04.2024) (Vehicle No-WB37D6848) | 1702/DWSD | 31/10/2023 | 182 | PRAMIT CHATTERJEE | 0.82 | 1.57 | 190.61 | 60
1859 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Continuation order for supplying laying and aligning of UPVC distribution pipe line and allied works including FHTC and connection providing to Akandara (JL-47) ,Molandighi (JL-48),Kandarakona (JL-51),Rakhitpur (JL-42) ,Chua(JL-43),Bhagaabanpur (JL-45),Hariki(JL-50) Mouzas under command area of Bistupur distributin system (Part-A) of Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte | 702/DWSD | 29/04/2022 | 25 | MACHINO TECHNO | 67.7 | 67.42 | 99.58 | 100
1860 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Formal order for the work of Supplying ,laying and aligning of HDPE/DI distribution pipe line and allied works including functinal household tap connection (FHTC) and connection provided to ICDS ,Health Centre ,Govt Bioldings school under the command area of Gopalpur mouza of Augmentation of Gopalpur piped W/s Scheme under Durgapur W/S Division, PHE Dte. | 68/DWSD | 19/01/2022 | 180 | MRITYUNJOY MUKHERJEE AND CO | 494.51 | 304.99 | 66.69 | 100
1861 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block under Augmentation of Gopalpur piped W/s Scheme. | 1302/DWSD | 07/08/2023 | 15 | V.C.CONSTRUCTION | 4.75 | 4.71 | 100 | 100
1862 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Continuation order for the work of Supplying ,laying and aligning of HDPE/DI distribution pipe line and allied works including functinal household tap connection (FHTC) and connection provided to ICDS ,Health Centre ,Govt Bioldings school under the command area of Gopalpur mouza of Augmentation of Gopalpur piped W/s Scheme under Durgapur W/S Division, PHE Dte. | 700/DWSD | 29/04/2022 | 90 | MRITYUNJOY MUKHERJEE AND CO | 66.45 | 65.8 | 100 | 100
1863 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Additional work for restoration and repairing of pipe line and construction of Sluice Valve chamber and cement concrete and other allied works for Augmentation of Gopalpur W/S Scheme under DWSD ,PHE Dte . | 1561/DWSD | 20/09/2023 | 685 | AMAR CONSTRUCTION | 5.15 | 0 | 0 | 100
1864 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Implememntation of Har Ghar Jal for Providing FHTC in connection with JJM for Pratapur, Nachan mouza ,Dhabani mouza (JL-48) under Retrofitting of Jemua piped W/s Scheme, Augmentation of Bistupur water supply scheme, Augmentation of Gopalpur, water supply scheme, Augmentation of Roopganj Water supply scheme of Durgapur-Faridpur Block (SM/16249) | 1074/DWSD | 12/07/2023 | 20 | MUKHERJEE ENTERPRISE | 18.4 | 18.19 | 100 | 100
1865 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte , SM/09875 | Augmentation | Acceptance cum formal order for the work of Construction of boundary wall at OHR site approach road ,drain blower room and plantation and other allied works of Jemua W/S Scheme under Augmentation of Gopalpur W/s Scheme of Durgapur-Faridpur Block under DWSD, PHE Dte | 587/DWSD | 11/04/2023 | 45 | GITA CONSTRUCTION | 61.45 | 58.7 | 100 | 100
1866 | PASCHIM BARDHAMAN | Durgapur W/S Division | Shyambazar Piped water Supply Scheme , SM/11228 | New | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Shyambazar piped W/s Scheme under DWSD ,PHE Dte (SL-01) | 1233/DWSD | 17/08/2022 | 15 | M/S. D. PALIT & CO. | 14.76 | 13.63 | 100 | 0
1867 | PASCHIM BARDHAMAN | Durgapur W/S Division | Shyambazar Piped water Supply Scheme , SM/11228 | New | Acceptance cum formal order for the work of Route survey and preparation of DPR for Augmentation of Shyambazar ,Telipara piped W/s Scheme under DWSD, PHE Dte | 527/DWSD | 29/03/2023 | 15 | MEASURE LAND | 5 | 5 | 100 | 0
1868 | PASCHIM BARDHAMAN | Central Mechanical | Shyambazar Piped water Supply Scheme , SM/11228 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 2 at Shambazar Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | 1580/CMD | 04/04/2023 | 30 | A.S. ENTERPRISE | 9.3 | 8.81 | 100 | 100
1869 | PASCHIM BARDHAMAN | Durgapur W/S Division | Shyambazar Piped water Supply Scheme , SM/11228 | New | Material Requisition To Resource Division | 255/C/DWSD | 15/02/2023 | 0 | Resource Division | 5.32 | 0 | 0 | 0
1870 | PASCHIM BARDHAMAN | Durgapur W/S Division | Shyambazar Piped water Supply Scheme , SM/11228 | New | Material Requisition To Resource Division | 1231/DWSD | 17/08/2022 | 0 | Resource Division | 18.93 | 0 | 0 | 0
1871 | PASCHIM BARDHAMAN | Durgapur W/S Division | Shyambazar Piped water Supply Scheme , SM/11228 | New | Quotation for Shyambazar W/S Scheme , Pump House No- 01 , Panagarh CCC | BP-2022-23-340 | 17/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.65 | 0 | 0 | 0
1872 | PASCHIM BARDHAMAN | Durgapur W/S Division | Shyambazar Piped water Supply Scheme , SM/11228 | New | Quotation for Shyambazar W/S Scheme, P.H. No - 02, Panagarh CCC | BP-2022-23-331 | 15/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.36 | 0 | 0 | 0
1873 | PASCHIM BARDHAMAN | Central Mechanical | Shyambazar Piped water Supply Scheme , SM/11228 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Shambazar Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | 1579/CMD | 04/04/2023 | 30 | MS DAS ELECTRIC CO | 9.3 | 8.87 | 100 | 100
1874 | PASCHIM BARDHAMAN | Durgapur W/S Division | Shyambazar Piped water Supply Scheme , SM/11228 | New | Formal order for the work of laying distribution system ,rising main construction of 150 M3 with 20 mtr staging height including soil investigation construction of Pump house (5.4X3.6 m) with sanitary and Water supply arrangement and construction of pump house (3.6X3.00 mtr) for Shyambazar W/s Scheme under DWSD ,PHE Dte (New Scheme) | 1648/DWSD | 02/12/2022 | 2190 | DUTTA ENTERPRISE | 213.72 | 194.67 | 91.09 | 100
1875 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Detailed Route Survey, Design Drawing & DPR Preparation for Ondal (Phase-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | 502/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.54 | 4.54 | 100 | 0
1876 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Material Requisition To Resource Division | 3131 | 09/12/2022 | 0 | Resource Division | 106.94 | 0 | 0 | 0
1877 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Quotation for enhancement of load at 11 KV from 200 KVA to 305 KVA to your premises at Ramprasadpur,Andal, Paschim Burdwan. |  | 23/02/2023 | 0 | W.B.S.E.D.C.L | 11.28 | 0 | 0 | 0
1878 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Quotation for enhancement of load at Basudebpur under Augmentation of Andal. | BP-2023-24-33 | 14/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.32 | 0 | 0 | 0
1879 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Quotation Money for Load Enhancement at Andal | BP-2023-24-5 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.28 | 0 | 0 | 0
1880 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Deposit for Earnest Money Application | BP-2023-24-22 | 25/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
1881 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Deposition of the Earnest Money for the proposed enhancement of the load at Ramprasadpur Andal BDN | BP-2022-23-27 | 31/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
1882 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-II/A) Piped Water Supply Scheme (Part-2) Block Andal, Dist-Paschim Bardhaman under RCFA Div-I PHE Dte. | 2213/RCD-I | 17/07/2023 | 30 | SOMNATH SAMANTA | 11.57 | 6.78 | 58.58 | 100
1883 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Ramprasadpur H/W Site under Augmentation of Sub Surface Water Supply Scheme of Ondal Phase-II/A Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 3284/RCDI | 20/12/2022 | 90 | SOMNATH SAMANTA | 22.05 | 22.01 | 100 | 70
1884 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Acceptance cum work order for Balance work for pushing 300 mm dia MS Rising main through 600 mm Dia RCC pipe road crossing trenchless method under NH-19 at front topline more under OCP based Kajora site Augmentation of sub surface water supply scheme ondal phase-II/A under RCFA Division-I PHE Dte. | 2427/RCD-I | 26/09/2024 | 30 | T M CONCRETE CREATION PVT.LTD | 12.98 | 0 | 0 | 100
1885 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Ondal (Phase ¿ II/A) Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part - 3) | 2211/RCD-I | 14/09/2022 | 45 | UNITED CONSTRUCTION | 88.03 | 74.93 | 85.12 | 90
1886 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Acceptance cum work order of distribution network for augmentation Of Ondal (Phase-II/A) piped Water Supply scheme including FHTC & allied works Ondal Block under RCFA Div-I PHE Dte.(Part-2) | 2483/RCD I | 17/10/2022 | 45 | SOMNATH SAMANTA | 89.8 | 65.01 | 72.39 | 90
1887 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Acceptance cum work order of distribution network for augmentation of Ondal (Phase II/A) piped water supply scheme including FHTC & allied work within Ondal Block under RCFA Div-I, PHE Dte. (Part-I) | 2482/RCD I | 17/10/2022 | 45 | SIMA ENTERPRISE | 89.81 | 71.28 | 79.37 | 90
1888 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-II/A) Piped Water Supply Scheme (Part-1) Block- Andal Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 08) | 1129/ RCD I | 24/03/2023 | 30 | SIMA ENTERPRISE | 13.76 | 9.36 | 68.05 | 80
1889 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-II/A) Piped Water Supply Scheme (Part-3) Block Andal, Dist-Paschim Bardhaman under RCFA Div-I PHE Dte. | 2214/RCD-I | 17/07/2023 | 30 | UNITED CONSTRUCTION | 56.6 | 24.99 | 44.16 | 50
1890 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC , SM/11575 | Augmentation | Acceptance cum work order for Repair and renovation works of One no. RCC Elevated Reservoir of capacity 550 cum at Dignala for Augmentation of Ondal Phase-II/A Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | 1124/ RCD I | 24/03/2023 | 90 | M/S SUBHRADEEP | 11 | 9.25 | 100 | 100
1891 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. , SM/12039 | Augmentation | Acceptance cum work order for Additional work for distribution network including supply of Hume pipe, G.I. pipe and adopting trench less technologies at 02 (Two) locations in connection to Zone-I Part-A Dendua OHR for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | 2365/RCD-I | 04/08/2023 | 30 | ASHA CONSTRUCTION | 15.08 | 14.43 | 100 | 100
1892 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. , SM/12039 | Augmentation | Material Requisition To Resource Division | 2942/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1893 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. , SM/12039 | Augmentation | Acceptance cum work order for Sinking of 03 (Three) nos. 200 mm dia river bed tube well including laying of 250 mm dia HDPE pipe line in the river of Ajoy for Ukhra Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 3546/RCD-1 | 07/12/2023 | 30 | B.T.M. CONCERN | 21.19 | 1.96 | 9.27 | 10
1894 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. , SM/12039 | Augmentation | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Kallya and surrounding villages within Kallya Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte. | 3452/RCD-I | 24/11/2023 | 15 | JAI MAHARAJ ENTERPRISE | 3.71 | 3.69 | 100 | 100
1895 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. , SM/12039 | Augmentation | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-14B) | 1761/RCD I | 16/05/2023 | 961 | MD AAMIR KHAN | 409.77 | 65.24 | 15.92 | 15
1896 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. , SM/12039 | Augmentation | Acceptance cum work order for Shifting of existing rising main for construction of new Pump House at Dendua OHR Campus under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 3281/RCD-I | 08/11/2023 | 90 | D.S.ENTERPRISE | 12.45 | 12.26 | 100 | 100
1897 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. , SM/12039 | Augmentation | Acceptance cum work order for Laying & pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines at Railway Gate (Node No 116 to 128) under AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) under RCFA Division-I PHE Dte | 3431/RCD-1 | 24/11/2023 | 90 | SINGHA ROY & CO. | 44.79 | 37.7 | 100 | 100
1898 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. , SM/12039 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 150 cum & allied work at Baidyanathpur under AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) under RCFA Division-I PHE Dte. | 3473/RCD-I | 28/11/2023 | 551 | MAA ENTERPRISE | 23.33 | 20.84 | 90.73 | 25
1899 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. , SM/12039 | Augmentation | Acceptance cum work order of additional works of Dismantling & concrete works, Jack Pushing Supplying, Aligning and laying and other allied works at distribution system Networks for Shyamlya in Nimsa mouza under Shyamlya Gram Panchayat under Jamuria Block of Augmentation of PWSS RCFA Part-II (Zone-14B) under R.C.F.A Division-I PHE Dte. | 2883/RCD-I | 06/10/2023 | 543 | A CONSTRUCTION CO | 37.4 | 14.4 | 66.92 | 100
1900 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. , SM/12039 | Augmentation | Acceptance cum work order for Balance and other allied works for construction of store room at work site for(Zone-4A) of Pandabeswar and Andal Block for Augmentation of RCFA Part-II (Zone-14B) PWSS under RCFA Division-I PHE Dte. | 145/RCD-I | 08/01/2025 | 90 | RANJIB GHATAK | 20.29 | 0 | 0 | 70
1901 | PASCHIM BARDHAMAN | Durgapur W/S Division | GARADAHA PIPED WATER SUPPLY SCHEME. , SM/11934 | New | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distributing pipe line and providing FHTC at Garadaha Mouza of Garadaha piped W/s Scheme under DWSD, PHE Dte (Part-A ,B & C) (SL-03) | 775/DWSD | 17/05/2022 | 45 | SHWET BARANI | 38.51 | 34 | 88.27 | 0
1902 | PASCHIM BARDHAMAN | Durgapur W/S Division | GARADAHA PIPED WATER SUPPLY SCHEME. , SM/11934 | New | Quotation for Garadaha W/S Scheme, P.H. No - 01, Panagarh CCC | BP-2022-23-328 | 15/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.75 | 0 | 0 | 0
1903 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF SEMALYA PWSS FOR PROVIDING FHTC WITHIN JAMURIA BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION I PHE DTE , SM/12024 | Retrofitting | Material Requisition To Resource Division | 1854/RCD-I | 31/05/2023 | 0 | Resource Division | 7.25 | 0 | 0 | 0
1904 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF SEMALYA PWSS FOR PROVIDING FHTC WITHIN JAMURIA BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION I PHE DTE , SM/12024 | Retrofitting | Formal Work Order for Supplying, laying and aligning of distribution system including FHTC for Shyamla W/S Scheme in Syamla and Bhuri Mouza, Block ¿ Jamuria, Dist ¿ Bardhaman under Shyamla W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C) | 2029/RCD-I | 30/08/2022 | 1030 | SWATI CORPORATION | 337.77 | 234.46 | 69.41 | 85
1905 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF SEMALYA PWSS FOR PROVIDING FHTC WITHIN JAMURIA BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION I PHE DTE , SM/12024 | Retrofitting | Acceptance cum work order for Construction of 250 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Samlya for Samlya Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Ref Drawing No. PC-I/OHR/10/2012 (Sheet No. 1 & 2) | 2934/RCD-I | 17/11/2022 | 12 | M/S CHANDI CHARAN ROY | 80.02 | 24.01 | 100 | 100
1906 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF SEMALYA PWSS FOR PROVIDING FHTC WITHIN JAMURIA BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION I PHE DTE , SM/12024 | Retrofitting | Continuation work order for Supplying, laying and aligning of distribution system for Part of Kendra Khottamdihi Mouza (JL No. 001), Bajari (Jl No. 023) & Sonpur (Jl No. 022) for Kendra Khottamdihi W/S Scheme (Zone-I) , Block:-Pandabeswar under RCFA Division-I PHE Dte. (Part-A) under JJM (RCFA Part-II) | 800/RCD-I | 06/03/2023 | 90 | MRITYUNJOY MUKHERJEE & CO. | 95.19 | 83.15 | 100 | 100
1907 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. , SM/12216 | Augmentation | Material Requisition To Resource Division | 2957/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1908 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. , SM/12216 | Augmentation | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & Aallied work under RCFA Division-I PHE Dte. (Zone-19) (Part-B). | 1611/RCD I | 25/04/2023 | 180 | UMA ENTERPRISE | 195.63 | 64.28 | 32.86 | 65
1909 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. , SM/12216 | Augmentation | Acceptance cum work order for Additional work for Distribution Network for Augmentation of RCFA Part-II (Zone-19) (Part-A) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1644/RCD-I | 04/07/2024 | 20 | A CONSTRUCTION CO | 9.41 | 9.41 | 100 | 100
1910 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. , SM/12216 | Augmentation | Acceptance cum Work Order for Additional work for laying MS pipe and allied works including Adopting trench less technology (e.g. Jack Pushing Method etc) of 03 ( Three) Nos. location at Bankola Rail gate, Bankola Siding ECL & Bankola Water Supply Gate under Augmentation of RCFA Part-II Zone 19 PWSS under RCFA,Division-I,P.H.E.Dte. | 919/RCD-I | 15/03/2024 | 30 | A CONSTRUCTION CO | 42.4 | 42.34 | 100 | 100
1911 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. , SM/12216 | Augmentation | Acceptance cum Work Order for Interconnection at Baliapur OHR Site (02 nos. OHR), Barabani OHR and Barabani Railway crossing of RCFA Part-II Zone-19 PWSS under RCFA Division-I PHE Dte | 925/RCD-I | 15/03/2024 | 30 | M/S MONDAL ENTERPRISE | 22.75 | 22.33 | 100 | 100
1912 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. , SM/12216 | Augmentation | Acceptance cum work order for Additional work of Construction of Rigid Pavement for the approach road from the main road towards Head Work Site and Laying of Pipe line for Pandebeswar Block of Augmentation PWSS of RCFA Part-II (Zone-19) under RCFA Division-I P.H.E Dte. in the District of Paschim Bardhaman | 2127/RCD-I | 27/08/2024 | 30 | SWATI CORPORATION | 10.61 | 0 | 0 | 100
1913 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. , SM/12216 | Augmentation | Formal work order of laying of 200 mm dia HDPE pipe line from Semalya to kendra Khottamdihi intake pump house site under Kendra Khottamdihi Water Supply Scheme under RCFA Div-I, PHE Dte. | 14/RCDI | 05/01/2023 | 452 | UMA ENTERPRISE | 157.45 | 156.69 | 99.51 | 100
1914 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. , SM/12216 | Augmentation | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied Work under RCFA Division-I PHE Dte. (Zone-19)(Part-A) | 1605/RCD I | 25/04/2023 | 180 | A. CONSTRUCTION CO. | 233.19 | 92.45 | 39.65 | 70
1915 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. , SM/12216 | Augmentation | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-19) with Construction of 600 cumcapacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District -Paschim Bardhaman. | 1830/RCD-I | 29/05/2023 | 365 | SWATI CORPORATION | 181.97 | 169.89 | 93.36 | 40
1916 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. , SM/12216 | Augmentation | Sub Soil Investigation for 600 cum capacity RCC Over Head Reservoir at (Zone-19) of Pandabeswar Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3349/RCDI | 23/12/2022 | 782 | MOYTEC | 0.49 | 0 | 0 | 100
1917 | PASCHIM BARDHAMAN | Asansol Mechanical | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Providing and Installation of Electro-Mechanical Equipments and allied works under Augmentation of Bagdiha Water Supply Scheme, Block : Jamuria, Dist -Paschim Bardhaman. | 492/AMD | 22/02/2023 | 365 | PREMNATH MITRA | 126.31 | 31.11 | 24.63 | 25
1918 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Acceptance cum work order for Construction of boundary wall Gate at OHR Site (Length-60 mtrs) at Bagdiha of Jamuria Block for Augmentation of Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. in District Paschim Bardhaman (Sl No. 20) | 1164/ RCD I | 24/03/2023 | 60 | M/S KALYANI ENTERPRISE | 5.31 | 0 | 0 | 0
1919 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Acceptance cum work order Construction of Pump House at River side H/W for Augmentation Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 1867/RCD-1 | 01/06/2023 | 180 | M/S KALYANI ENTERPRISE | 19.55 | 0 | 0 | 0
1920 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Acceptance cum work order for Sinking of 03 (Three) nos. river bed tube wells including collecting main, sluice valve chamber, reinforcement & other allied works at Bagdiha H/W site at Ajoy river under Augmentation of Bagdiha Water Supply Scheme under RCFA Division-I PHE Dte. | 2240/RCD-I | 17/07/2023 | 30 | M/S KALYANI ENTERPRISE | 24.44 | 0 | 0 | 0
1921 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Preparation of DPR & Route Survey for augumentation of Bagdiha piped water supply scheme block-Jamuria, dist- Paschim Barddhaman under RCFA Division-I PHE Dte. | 2246/RCD I | 15/09/2022 | 15 | APEX ENGINEERING | 3.43 | 3.43 | 100 | 0
1922 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Material Requisition To Resource Division | 2029/RCD-I | 30/06/2023 | 0 | Resource Division | 127.95 | 0 | 0 | 0
1923 | PASCHIM BARDHAMAN | Asansol Mechanical | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | New Connection Charge at Bagdiha Water Supply Scheme | BP-2022-23-29 | 31/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.15 | 0 | 0 | 0
1924 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Acceptance cum work order Sinking of 3 (Three) nos 200 mm dia river bed tube wells including collecting main in the river Ajoy at Bagdiha under Augmentation of Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 2484/RCD-I | 23/08/2023 | 30 | M/S KALYANI ENTERPRISE | 24.12 | 0 | 0 | 0
1925 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Acceptance cum work order Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block Including FHTC & allied work under RCFA Division-I PHE Dte. (Part-C) | 1069/RCD-I | 23/03/2023 | 90 | M/S S.K. ENTERPRISE | 61.35 | 21.2 | 34.56 | 35
1926 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Acceptance cum work order for Rising Main for Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | 1067/RCD I | 23/03/2023 | 1105 | D.S.C. CONCERN | 12.64 | 0 | 0 | 100
1927 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Acceptance cum work order Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block Including FHTC & allied work under RCFA Division-I PHE Dte. (Part-D) | 1071/RCD-I | 23/03/2023 | 90 | TARA MA ENTERPRISE | 54.95 | 15.27 | 27.8 | 0
1928 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Acceptance cum work order for Plastering, painting works of Boundary Wall, Pump House, Chlorine Room CWR and other allied works and other allied works under Bagdiha W/S Scheme under RCFA Division-I PHE Dte. | 1280/RCD-I | 27/03/2023 | 15 | M/S KALYANI ENTERPRISE | 5.04 | 5.04 | 100 | 0
1929 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Acceptance cum work order for Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block Including FHTC & allied work under RCFA Division-I PHE Dte. (Part-E)( Sl No. 10) | 1072/RCD-I | 23/03/2023 | 90 | R B ENTERPRISE | 68.85 | 31.93 | 46.38 | 50
1930 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Formal work order for Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block including FHTC & allied work under RCFA Division-I PHE Dte. (Part-A) | 1616/RCD I | 25/04/2023 | 180 | SIMA ENTERPRISE | 115.57 | 81.84 | 70.82 | 75
1931 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Formal Work Order for Construction of 350 cum capacity 20 mtr. staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Bagdiha for Augmentation of Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/12/2012 (Sheet No. 1 & 2) | 2042/RCD-I | 04/07/2023 | 366 | DHANANJOY DUTTA | 108 | 59.72 | 55.3 | 50
1932 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Acceptance cum work order for Laying & Pushing by adopting trench less technology (e.g. Jack Pushing Method etc) and allied works at Bagdiha to Sidhapur Road and Bagdiha OHR to Bahadurpur under Jamuria Block under Augmentation of Bagdiha PWSS under RCFA Division-I PHE Dte. | 2333/RCD-I | 01/08/2023 | 15 | SIMA ENTERPRISE | 46.6 | 36.04 | 77.32 | 77
1933 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Continuation work order for Hiring of SUV (A.C) (Non Airconditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. for the Office Use of the Deputy Superintending Engineer, RCFA W/S Circle, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.09.2024 to 28.02.2025) (Sl No. 02) | 2164_RCD-I | 30/08/2024 | 182 | SHYAMAL MAJI | 0.9 | 0 | 0 | 33
1934 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Acceptance cum work order for Bye pass connection including supplying, aligning, laying of HDPE pipe and other allied works at Bagdiha Head Works Site to Bagdiha Siddapur High School under Bagdiha W/S Scheme under RCFA Division-I PHE Dte. | 393/RCDI | 30/01/2023 | 30 | BABA LOKNATH ENTERPRISE | 30.27 | 17.57 | 100 | 100
1935 | PASCHIM BARDHAMAN | RCFA Division -I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman , SM/13416 | Augmentation | Acceptance Cum work order Laying of different dia distribution pipe line and concrete road cutting and mending works at Bagdi para, Dangal Para, Telipara etc adjacent area Dakshin Khanda area under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | 2221/RCD-I | 17/07/2023 | 30 | M/S KALYANI ENTERPRISE | 10.09 | 8.45 | 100 | 100
1936 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18887 | Augmentation | Supply and Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube Well No-03 At augmentation of Krishnapur Piped Water Supply Scheme under Asansol Mechanical Division, PHE Dte, Block- Kanksa, Dist- Paschim Bardhaman. | 1982/AMD | 27/11/2024 | 30 | M/S JIT ENTERPRISE | 11.63 | 0 | 0 | 0
1937 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18887 | Augmentation | Acceptance cum Work Order for Construction of Boundary wall and allied works at Krishnapur tube well No-02 under Augmentation of Krishnapur Piped water Supply scheme under Kanksa Block under RCFA Division-I,PHE Dte | 1007/RCD-I | 16/03/2024 | 30 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 7.12 | 5.54 | 77.78 | 80
1938 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18887 | Augmentation | Acceptance cum work order for Creating separate zone with pipe line & additional FHTC including Water sources at Sibpur Ruidaspara under Augmentation of Krishnapur Water Supply Scheme under RCFA Division-I PHE Dte | 3066/RCD-I | 10/12/2024 | 90 | HIRANMAY GHOSH | 26.47 | 17.27 | 65.44 | 100
1939 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18887 | Augmentation | Supply Delivery and Installation Of Voltage Stabilizer, PDB Cum MCC Panel and other Allied Electrical Works For Tube Well No- I & II At Augmentation Of Krishnapur Water Supply Scheme Under Asansol Mechanical Division, PHE. Dte. | 2120/AMD | 16/12/2024 | 30 | SINHA ELECTRICALS | 14.52 | 0 | 0 | 100
1940 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Formal order for the work of Balance work for providing FHTC in connection with JJM for Bansia mouza(JL-31) under command area of Jamgora-Jagannathpur W/s Scheme at Durgapur Faridpur Block under DWSD, PHE Dte (SL-05) | 796/DWSD | 12/05/2021 | 15 | BABA LOKENATH ENTERPRISE | 12.9 | 0 | 0 | 0
1941 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Formal order for the work of Repairing ,extension as well as replace of damage AC pipe line and allied works at Colony Bouri para ,Upper Bagdi para ,Adibasi para under Jamgora(Mouza-23) under command area of Jamgora-Jagannathpur W/s Scheme for combat upcoming drought like situation under DWSD, PHE Dte (SL-07) | 829/DWSD | 24/05/2021 | 10 | RANJIB GHATAK | 7.26 | 0 | 0 | 0
1942 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work of additional pipe line work with concrete cutting at Bansia mouza for providing functional house hold tap connection (FHTC) in connection with JJM for Bansia mouza (JL-31) under command area of Jamgora-Jaggannathpur W/s Scheme at Durgapur-Faridpur block under DWSD, PHE Dte. (SL-04) | 719/DWSD | 29/04/2021 | 25 | BABA LOKENATH ENTERPRISE | 4.99 | 0 | 0 | 0
1943 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line of different dia UPVC pipe at Kalikapur mouza to combat draught like situation in Durgapur-Faridpur block to providing FHTC at Kalikapur mouza(JL-30) under Jamgora-Jagannathpur W/s Scheme under DWSD, PHE Dte (SL-08) | 722/DWSD | 29/04/2021 | 30 | M/S MONDAL ENTERPRISE | 4.99 | 0 | 0 | 0
1944 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing and restoration of distributing system from Nachan OHR to Jamgora ,Nachan more to jamgora samshan distribution main road crossing at Nachan with Hume pipe ,Bansia pratabpur and extension of pipe at different places of Pratabpur gram of Jamgora-Jagannathpur piped W/s Scheme under DWSD ,PHE Dte | 781/DWSD | 18/05/2022 | 15 | M/S MONDAL ENTERPRISE | 4.56 | 0 | 0 | 0
1945 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing restoration and chokage cleaning of distribution system of Hetedoba OHR from Hetedoba OHR to Sarpi more of Gourbazar-Ichhapur piped W.S Scheme under DWSD,PHE Dte | 112/DWSD | 01/02/2022 | 20 | PAYAL CONSTRUCTION | 3.24 | 0 | 0 | 0
1946 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Continuation order for the work of Providing functional house hold tap connection in connection with JJM at Shyamsundarpur Mouza(JL-07) ,block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte. | 239/DWSD | 25/02/2022 | 15 | PRAVAT SARKAR | 4.92 | 4.39 | 100 | 0
1947 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work of Making interconnection of Over flow line and laying of additonal distribution pipe line with necessary allied works for FHTC purpose at Jagnnathpur gram under Jamgora-Jagannathpur W/S Scheme under DWSD PHE Dte (SL-06) | 421/DWSD | 30/03/2022 | 10 | M/S BADAL GHOSH | 3.69 | 3.68 | 100 | 0
1948 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work of Laying of distribution pipe line for (FHTC) in connection with JJM and additional work of Solar Tube well site and necessary allied work at Huchukdanga village ,Paschim Bardhaman under DWSD, PHE Dte (SL-10) | 425/DWSD | 30/03/2022 | 10 | RANJIB GHATAK | 3.81 | 3.8 | 100 | 0
1949 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Formal order for the work of Emegency repairng and restoration of distribution system from command area of Gourbazar OHR {(Srikrishnapur, Kailashpur (Part)} under Gourbazar-Ichhapur piped W/s Scheme under DWSD, PHE Dte (SL-11) | 1780/DWSD | 20/12/2021 | 10 | JOY GURU ENTERPRISE | 5.6 | 4.97 | 100 | 0
1950 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work of Laying of collecting main necessary repairing works in river Ajoy at Bhaburia H/w Site under Jamgora-Jagannathpur and Gourbazar-Ichhapur W/s Scheme for combat flood damaged under DWSD, PHE Dte | 97/DWSD | 28/01/2022 | 15 | RANAJOY ENTERPRISE | 3.29 | 0 | 0 | 50
1951 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work of Surging of 5 Nos tube well including withdrawing pumping machinery setting the same correcting cable line and other allied works due to flood damaged at Bhaburia H/W site under Jamgora-Jagannathpur & Gourbazar-Ichhapur piped W/s Scheme.(Part-B) | 101/DWSD | 31/01/2022 | 20 | RANAJOY ENTERPRISE | 1.8 | 0 | 0 | 50
1952 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Continuation order for the work of Providing functional house hold tap connection in connection with JJM at Shyamsundarpur Mouza(JL-07) ,block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte. | 245/DWSD | 28/02/2022 | 15 | PRAVAT SARKAR | 4.97 | 0 | 0 | 50
1953 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Formal order for the work of Supplying and laying of 110 mm and 90 mm dia UPVC pipe at Bansgora (Main road to Akhrapara) for providing FHTC of Bansgora Mouza JL-38 of Jamgora-Jagannathpur W/s Scheme under DWSD PHE Dte | 1775/DWSD | 20/12/2021 | 25 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 7.57 | 7.63 | 100 | 0
1954 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Continuation order for the work of the work of Providing functional house hold tap connection (FHTC ) in connection with JJM for Huchuk Danga Jamgora-Jagannathpur piped W/S Scheme Mouza-Dannaya /Jamgora(JL-23) block-Durgapur-Faridpur ,Paschim Bardhaman under DWSD,PHE Dte | 25/DWSD | 06/01/2022 | 15 | RANJIB GHATAK | 3.49 | 3.51 | 100 | 0
1955 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Formal order for the work of Extension of pipe line from the existing pipe line from command area of Gourbazar-Ichhapur piped W/s Scheme of Ichhapur area for providing of FHTC at Ichhapur mouza(JL-50) under DWSD,PHE Dte (SL-05) | 140/DWSD | 03/02/2022 | 7 | SHWET BARANI | 13.62 | 13.6 | 100 | 0
1956 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Continuation order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shyamsundarpur mouza (JL-07) under command area of Gourbazar-Ichhapur W/s Scheme of Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (Part-C). | 1735/DWSD | 13/12/2021 | 10 | PRAVAT SARKAR | 4.97 | 4.97 | 100 | 0
1957 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work of Laying of collection main necessary repairing works in river Ajoy at Bhaburia H/W site under Jamgora -Jagannathpur piped W/s Scheme and Gourbazar-Ichhapur piped W/s Scheme.(Part-A) | 79/DWSD | 24/01/2022 | 15 | RANAJOY ENTERPRISE | 3.85 | 0 | 0 | 0
1958 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work of Laying of distribution pipe line with necessary allied works for FHTC purpose at Maheshpur village Muchipara,Chasa para Moheshpur Mouza(JL-12),Durgapur-Faridpur block under DWSD PHE Dte | 88/DWSD | 27/01/2022 | 15 | M/S BADAL GHOSH | 4.87 | 4.92 | 100 | 0
1959 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work Providing FHTC in connection with JJM at Shayamsundarpur mouza(JL-07) ,Block-Durgapur-Fardipur Block ,Dist-Paschim Bardhman under Gourbazar-Ichhapur piped W/s Scheme PHE Dte (P-C) | 10/DWSD | 04/01/2022 | 15 | PRAVAT SARKAR | 4.84 | 4.84 | 100 | 0
1960 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work of Surging of 12 Nos tube well including withdrawing pumping machinery setting the same correcting cable line and other allied works due to flood damaged at Bhaburia H/W site under Jamgora-Jagannathpur & Gourbazar-Ichhapur piped W/s Scheme.(Part-A) | 113/DWSD | 01/02/2022 | 20 | RANAJOY ENTERPRISE | 4.31 | 0 | 0 | 0
1961 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Constinuation order for the work of Providing functional houe hold tap connection (FHTC) in connection with JJM at Shyamsundarpur mouza(JL-07) block-Durgapur-Faridpur , Dist Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte | 1643/DWSD | 23/11/2021 | 10 | PRAVAT SARKAR | 4.96 | 3.64 | 100 | 0
1962 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Continuation for the work of balance work for providing functional household tap connection (FHTC) in connection with JJM at Jagannathpur mouza (JL-26) under command area of Jamgora -Jagannathpur piped W/s Scheme under Durgapur-Faridpur block of DWSD,PHE Dte | 244/DWSD | 22/02/2022 | 25 | M/S BADAL GHOSH | 2.09 | 1.99 | 100 | 0
1963 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Acceptance cum formal order for the work of Supplying and laying of 200 mm dia UPVC pipe line from Hetedoba OHR to Zero point towards SARPI more road of Improvement of Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte (SL-06) | 723/DWSD | 06/05/2022 | 15 | BABA LOKENATH ENTERPRISE | 30.27 | 24.89 | 53.28 | 0
1964 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. , SM/07524 | Retrofitting | Formal order for the work of Laying of additional distribution pipe line with necessary allied works at Patsaora mouza under Gourbazar-Ichhapur piped W/S Scheme for FHT C work under DWSD, PHE Dte.(SL-03) | 1146/DWSD | 28/07/2022 | 20 | SHWET BARANI | 5.69 | 0 | 0 | 0
1965 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Formal work order for Providing FHTC through Retrofitting at Bahula (CT) (JL no. 30, Block - Pandabeswar) of RCFA Pt-II W/S Scheme under RCFA Division-I, PHE Dte. (Part-A) | 2143/RCD-I | 29/11/2021 | 120 | GITA CONSTRUCTION | 81.14 | 61.82 | 76.18 | 0
1966 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Formal work order for Providing FHTC through Retrofitting at Bahula (CT) (JL no. 30, Block - Pandabeswar) of RCFA Pt-II W/S Scheme under RCFA Division-I, PHE Dte. (Part-B) | 2144/RCD-I | 29/11/2021 | 120 | MD AAMIR KHAN | 81 | 59.89 | 73.94 | 0
1967 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Hiring of Maxi Cab (Non Air-conditioned)(Bharat stage-III/BS-III purchased on or after 01.05.2008 with Diesel/LPG/CNG Engine. as when required basis for supervision of FHTC related works under JJM) of RCFA Div-I, PHE Dte Govt, of West Bengal (w.e.f 16.08.2022 to 15.08.2023) | 1907/RCDI | 12/08/2022 | 12 | PRAMIT CHATTERJEE | 1.8 | 0.79 | 44.12 | 0
1968 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Acceptance cum work order Repairing laying PVC pipe line and allied work at Asansol District Hospital under RCFA Division-I PHE Dte. (Sl. No. 34) | 1751/RCD I | 12/05/2023 | 15 | UNITED CONSTRUCTION | 3.23 | 3.23 | 99.99 | 0
1969 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Cleaning compound premises, painting works and preparing approched road with sand and stone dust and other allied works at Kalyaneswari Inspection bunglow under Bahual Retrofitting under RCFA Division-I PHE Dte. (Sl No. 13) | 225/RCDI | 01/02/2022 | 7 | JYOGOMAYA ENTERPRISE | 1.81 | 1.81 | 100 | 100
1970 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Material Requisition To Resource Division | 2280/RCD-I | 12/12/2021 | 0 | Resource Division | 20.23 | 0 | 0 | 0
1971 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Fuel bill for WB37D0482 for the month of Sept 2023 | 339/1/23-24 | 17/10/2023 | 0 | RANAJIT AUTO | 0.22 | 0 | 0 | 0
1972 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting |  | 149/1/23-24 | 21/07/2023 | 0 | RANAJIT AUTO | 0.17 | 0 | 0 | 0
1973 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Hire charges and fuel bill for Executive Engineer RCFA Division-I PHE Dte | 291/23-24 | 10/10/2023 | 0 | NIRMALA TRADERS | 0.06 | 0 | 0 | 0
1974 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Fuel bill of Ranajit auto against vehicle no WB 37D 0482 for the month of May | 116/1/23-24 | 03/07/2023 | 0 | RANAJIT AUTO | 0.23 | 0 | 0 | 0
1975 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Bhaluka & Sonepur Bazari under Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. | 204/23-24 | 18/08/2023 | 0 | MACHINO TECHNO | 19.87 | 0 | 0 | 0
1976 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Hire charges and fuel bill for the month of July 2023 to Sept 2023 | 338/23-24 | 17/10/2023 | 0 | NIRMALA TRADERS | 1.2 | 0 | 0 | 0
1977 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | April 2023 | 77/23-24 | 06/06/2023 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0 | 0
1978 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | fuel bill april 2023 shyamal maji | 77/1/23-24 | 06/06/2023 | 0 | RANAJIT AUTO | 0.2 | 0 | 0 | 0
1979 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Hire charge and fuel bill for the month of July 2023 to September 2023 | 339/23-24 | 17/10/2023 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0 | 0
1980 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Arrangement of brakfast and lunch box, etc. for DWSM meeting held on 22.06.2024 at ADDA conference hall | 121/24-25 | 03/07/2024 | 0 | MUKHERJEE TRADERS | 0.28 | 0 | 0 | 0
1981 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Acceptance cum work order Supply and installation of sluice valve, shifting of household connection instead of old AC pipe line to distribution branch and etc allied works at Baidyanathpur Namopara, Bouripara and adjacent area under Baidyanathpur W/S Scheme under RCFA Division-I PHE Dte. | 1258/ RCD I | 27/03/2023 | 15 | SOMNATH SAMANTA | 2.5 | 2.49 | 99.59 | 0
1982 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. For the office Use of the Deputy Superintending Engineer Engineer, RCFA W/S Circle, PHE Dte Govt. of West Bengal (w.e.f 01.02.2023 to 31.07.2023) | 455/RCDI | 31/01/2023 | 181 | SHYAMAL MAJI | 0.9 | 0.3 | 33.33 | 80
1983 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Acceptance cum work order Laying of 90 mm dia HDPE pipe line and etc allied works at Baidyanathpur Namopara, Bouripara under Baidyanathpur W/S Scheme under RCFA Division-I PHE Dte. | 1264/RCD-I | 27/03/2023 | 15 | SOMNATH SAMANTA | 2.72 | 2.59 | 95.28 | 0
1984 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Acceptance cum work order Laying of different dia distribution pipe line at Baidyanathpur Namopara, Bouripara and adjacent area under Baidyanathpur W/S Scheme under RCFA Division-I PHE Dte. | 1276/RCD-I | 27/03/2023 | 15 | SOMNATH SAMANTA | 3.61 | 3.48 | 96.53 | 0
1985 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Construction of guard wall on emergency basis near Kalyaneswari I.B. gate under Retrofitting Bahula mouza RCFA Division-I PHE Dte. (Sl No. 12) | 1111/RCDI | 13/05/2022 | 30 | R B ENTERPRISE | 4.7 | 4.47 | 100 | 100
1986 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Emergency basis construction of culvert near Kalyaneswari I.B. gate under Retrofitting Bahula mouza W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 17) | 1116/RCDI | 13/05/2022 | 45 | R B ENTERPRISE | 4.93 | 4.92 | 100 | 100
1987 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Continuation work order for Probable Office expenditure of office of the Executive Engineer to meet up day to day various office & site expenses under RCFA Div-I PHE Dte (w.e.f 01.02.2023 to 31.07.2023) | 3439/RCD-I | 30/12/2022 | 182 | M/S KALYANI ENTERPRISE | 4.51 | 4.51 | 100 | 100
1988 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Supply of Computer and accessories for Office use under RCFA Division-I PHE Dte. District - Paschim Bardhaman | 2040/RCD-I | 30/06/2023 | 7 | MUKHERJEE TRADERS | 0.86 | 0.86 | 100 | 100
1989 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Acceptance cum work order Cleaning compound premises of Ballavpur Hospital & Unionpara Head Works Site under RCFA Part-II W/S Scheme under RCFA Div-I PHE Dte. | 2452/RCD-I | 18/08/2023 | 15 | SWATI CORPORATION | 0.97 | 0.96 | 100 | 100
1990 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Emergent sinking of one no 200 X 165 mm dia rig bore tube well at ESI Hospital, Asansole, Paschim Bardhaman under RCFA Division-I PHE Dte. | Camp-2-ESI-Hospital-AE-II | 27/09/2023 | 3 | M/S CHANDI CHARAN ROY | 7.84 | 7.68 | 100 | 100
1991 | PASCHIM BARDHAMAN | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. , SM/09388 | Retrofitting | Emergent sinking of one no 200 X 165 mm dia rig bore tube well at Health World Hospital, Asansole, Paschim Bardhaman under RCFA Division-I PHE Dte. | Camp-02-Health-World-Hosp | 27/09/2023 | 3 | M/S CHANDI CHARAN ROY | 7.77 | 7.65 | 100 | 100
1992 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and allied works under command area o Roopganj mouza of Augmentation of Roopganj piped W/s Scheme under DWSD, PHE Dte (SL-07) | 1165/DWSD | 01/08/2022 | 30 | M/S BADAL GHOSH | 60.68 | 59.5 | 98.06 | 0
1993 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Repairing and renovation of pump house with sanitary arrangement at Roopganj near tube well under Augmentation of Roopganj piped W/s Scheme under DWSD, PHE Dte (SL-08) | 1028/DWSD | 04/07/2022 | 7 | R.C.ENTERPRISE | 4.01 | 0 | 0 | 0
1994 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Construction of Pump house cum Chlorine room at ARRAH bazar T.No-III Pump house & tube well no-3 for Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-03) | 954/DWSD | 16/06/2022 | 45 | KIRON ENTERPRISE | 4.87 | 2.44 | 50.16 | 0
1995 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Formal order for the work of Replacement of damaged AC pipe with 90 mm dia HDPE from Roopganj more to Araichand gram of Augmentation of Roopganj Piped W/s Scheme under DWSD ,PHE Dte(SL-01) | 334/DWSD | 15/03/2022 | 15 | M/S KALYANI ENTERPRISE | 10.23 | 10.25 | 100 | 0
1996 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Sinking of 1 No (250 mm X 150 mm dia) 210 mtr depth Direct Rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at ARRAH BAZAR (T.No-03) under Augmentation of Roopganj piped W/S Scheme under DWSD, PHE Dte.(SL-11) | 812/DWSD | 21/05/2022 | 10 | JOY GURU ENTERPRISE | 11.86 | 11 | 100 | 0
1997 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Sinking of 1 No(300X200 mm dia)-Sinking of 1 No (300 mm X 200 mm dia) 210 mtr depth Direct Rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at ARRAH SIBTALA (T.No-01) under Augmentation of Roopganj piped W/S Scheme under DWSD, PHE Dte (SL-10) | 811/DWSD | 21/05/2022 | 10 | JOY GURU ENTERPRISE | 13.78 | 12.81 | 100 | 0
1998 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and Other allied works under command area of ARRAH Mouza (Part-C) under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-03) | 402/DWSD | 29/03/2022 | 25 | M/S KALYANI ENTERPRISE | 26.32 | 27.01 | 100 | 0
1999 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Quatation for Roopganj Pump house no -03 | BP-2022-23-92 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.29 | 0 | 0 | 0
2000 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Quotation for Roopganj Pump house no -04 | BP-2022-23-104 | 02/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.68 | 0 | 0 | 0
2001 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Construction of 5.40 X3.60 mtr switch room with plinth height (600X 2000 mm) with sanitary and water supply arrangemnt at PH No-3 TW No-3 site of Augmentation of Roopganj piped W/S Scheme under DWSD ,PHE Dte. | 329/DWSD | 20/02/2023 | 30 | MAA KHEPIMAYER CHARANE | 6.9 | 0 | 0 | 0
2002 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Formal order for the work of Restoration of drain PCC road at Roopganj and Arrah repairing of valve chamber ,construction of masonry community tank with supply of 2000 Ltrs PVC tank at Arrah Samshan supply fitting fixing and installation of sluice valve under DWSD,PHE Dte (SL-01) | 1640/DWSD | 23/11/2021 | 45 | M/S KALYANI ENTERPRISE | 12.12 | 10.04 | 87.58 | 0
2003 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and Other allied works under command area of ARRAH Mouza (Part-A) under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-01) | 404/DWSD | 29/03/2022 | 25 | DARPAN DAS & CO. | 63.18 | 49.67 | 78.62 | 0
2004 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Formal order for the work of Construction of 350 M3 capacity Over Head Reservoir having 20 Mtr staging height of RCC OHR at Roopganj H/W site under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-05) | 416/A/DWSD | 30/03/2022 | 180 | AMARANJALI CONSTRUCTION | 83.6 | 47.35 | 56.63 | 75
2005 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and Other allied works under command area of ARRAH Mouza (Part-B) under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-02) | 401/DWSD | 29/03/2022 | 30 | M/S KALYANI ENTERPRISE | 92.48 | 87.5 | 94.61 | 0
2006 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Construction of pump house cum Chlorine room at Roopganj H/W site near TW-1/2/3 pf Augmentation of Roopganj piped W/S Scheme under DWSD ,PHE Dte (SL-09) | 1029/DWSD | 04/07/2022 | 15 | R.C.ENTERPRISE | 4.45 | 3.23 | 72.65 | 0
2007 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Sinking of 01 Nos 300X200 mm dia Tube well with 210 mtr deapth by DR rig method using UPVC pipe (CD and UPVC deep well screen (RDS) at Roogganj H/W site of Kanksa Block of Augmentation of Roopganj piped W/s Scheme udner DWSD ,PHE Dte | 308/DWSD | 20/02/2023 | 15 | M/S BADAL GHOSH | 15.73 | 13.44 | 85.43 | 0
2008 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Re-connection of exiting FHTC from AC pipe line to newly laid different dia pipe line FHTC and also few new connection with JJM for Roopganj mouza (JL-54) under command area of Augmentation of Roopganj W/s Scheme,Block-Kanksa under DWSD ,PHE Dte. | 317/DWSD | 20/02/2023 | 25 | M/S BADAL GHOSH | 57.68 | 50.62 | 87.75 | 0
2009 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Balance work for laying of HDPE pipe line for providing FHTC in connection with JJM at Arrah mouza (JL-89) part-C under command area of Augmentation of Roopganj piped W/s Scheme under DWSD ,PHE Dte | 319/DWSD | 20/02/2023 | 20 | M/S BADAL GHOSH | 97.2 | 73.7 | 75.82 | 100
2010 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Emergent work of concreting of exiting dismantalled road at Roopganj under Augmentation of Roopganj piped W/s Scheme (SM/10203) | 1076/DWSD | 12/07/2023 | 25 | CHATTERJEE CONSTRUCTION | 4.69 | 0 | 0 | 0
2011 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and Other allied works under command area of ARRAH Mouza (Part-D) under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-04) | 397/DWSD | 28/03/2022 | 30 | M/S BADAL GHOSH | 74.2 | 71 | 95.68 | 0
2012 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Arrah mouza (JL-91) (Pt-A) under command area of Rupganj W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte | 144/DWSD | 28/01/2021 | 45 | M/S KALYANI ENTERPRISE | 28.83 | 28.84 | 100 | 0
2013 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of 2 Nos trial bore by direct rotary method drilling using rig machine at Roopganj H/W Site ,Tube well No-I &II of Augmentation of Roopganj piped W/s Scheme under DWSD ,PHE Dte(SL-16) | 1803/DWSD | 28/12/2021 | 10 | M/S KALYANI ENTERPRISE | 2.32 | 1.16 | 100 | 0
2014 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work details route survey, drawing design of distribution network & preparation of estimates and DPR in connection with the JJM (FHTC) of Augmentation of Roopganj Piped W/s Scheme under, DWSD, PHE Dte.(SL-01) | 1684/DWSD | 02/12/2021 | 30 | M/S R.DUTTA AND CO. | 6.39 | 6.39 | 100 | 0
2015 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of water supply arrangement at different places to combat water crisis at Kanksa block of Arrah ,Roopganj and Araichand under Roopganj piped W/s Scheme under DWSD ,PHE Dte (SL-11) | 1797/DWSD | 24/12/2021 | 7 | M/S KALYANI ENTERPRISE | 4.99 | 4.99 | 100 | 0
2016 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Repairing of leakage bursting and chokage cleaning at Arrah Distribution main and other allied work for Roopganj piped W/s Scheme all command area of Roopganj W/s Scheme under DWSD, PHE Dte.(SL-05) | 420/DWSD | 30/03/2022 | 15 | M/S KALYANI ENTERPRISE | 4.1 | 4.09 | 100 | 100
2017 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Additional FHT work of Arrah mouza and Roopganj mouza part under command area of Augmentation of Roopganj Piped W/S Scheme under DWSD ,PHE Dte(SL-03) | 1023/DWSD | 04/07/2022 | 10 | QUICK PAL SUPPLIERS | 4.98 | 4.98 | 100 | 0
2018 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Sanitary arrangement and plumbing work at Molandighi H/W site pump house no-II tube wno II for Bistupur piped W/S Scheme under DWSD, PHE Dte(SL-04) | 961/DWSD | 17/06/2022 | 10 | BABA LOKENATH ENTERPRISE | 4.8 | 3.91 | 100 | 100
2019 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 3 at Rupganj Water Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1244/CMD | 12/07/2022 | 30 | DEY ENTERPRISE | 9.86 | 9.52 | 100 | 80
2020 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Formal order for the work of Laying and aligning of distribution pipe line from Hetedoba OHR,DI Specials ,Valves and allied works under Augmentation of Roopganj piped W/s Scheme under DWSD ,PHE Dte. | 299/DWSD | 20/02/2023 | 20 | BABA LOKENATH ENTERPRISE | 16.32 | 16.06 | 100 | 0
2021 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Emergent work of Concreting of exiting dismantled road of Augmentation of Roopganj piped W/S Scheme under DWSD,PHE Dte | 769/DWSD | 18/04/2023 | 10 | M/S BADAL GHOSH | 4.78 | 4.76 | 100 | 100
2022 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Emergency work of concreting of exiting dismantled road at ARRAH mouza of Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte | 742/DWSD | 16/05/2023 | 15 | M/S BADAL GHOSH | 4.78 | 4.75 | 100 | 100
2023 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Repairing of existing concrete road restoration and other allied works under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (Part-D) | 1288/DWSD | 07/08/2023 | 20 | CHANDAN HAZRA | 8.69 | 8.66 | 100 | 100
2024 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Material Requisition To Resource Division | 331/DWSD | 15/03/2022 | 0 | Resource Division | 41.84 | 0 | 0 | 0
2025 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Electricity service connection rupganj piped W/s Scheme | BP-2023-24-94 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.95 | 0 | 0 | 0
2026 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum formal order for the work of Laying ,aligning of DI K9 rising main pipe and interconnection between 3 TW with OHR and other allied works of Augmentation of Roopganj piped W/S Scheme under DWSD ,PHE Dte | 325/DWSD | 20/02/2023 | 25 | M/S KALYANI ENTERPRISE | 24.33 | 13.25 | 54.47 | 100
2027 | PASCHIM BARDHAMAN | Asansol Mechanical | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Supply & installation of Submersible Pumping Machineries, Voltage Stabilizer, Chlorination System and internal House wiring for Rupganj Water Supply Scheme, P/H No-05 under Asansol Mechanical Division, P.H.E Dte. | 532/AMD | 12/03/2024 | 90 | M/S S.G.ENTERPRISE | 11.47 | 10.79 | 94.06 | 100
2028 | PASCHIM BARDHAMAN | Central Mechanical | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 4 at Rupganj Water Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1242/CMD | 12/07/2022 | 30 | AHALYA ENGINEERING WORKS | 10.2 | 9.8 | 100 | 100
2029 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Replacement of existing pipe line at Nachan OHR to Bansia gram for Physical certification of Har Ghar Jal in connection with JJM of Augmentation Roopganj piped W/s Scheme under DWSD ,PHE Dte | 719/DWSD | 11/05/2023 | 25 | CHANDAN HAZRA | 23.76 | 23.59 | 100 | 100
2030 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at kanchanpur of kanksa block under Augmentation of Roopganj Piped W/S Scheme under DWSD PHE Dte. | 1293/DWSD | 07/08/2023 | 45 | MAJI DEVELOPERS | 6.09 | 6.09 | 100 | 100
2031 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at Kanksa Zone II/Part C under Augmentation of Roopganj Piped W/S Scheme. | 1277_DWSD | 07/08/2023 | 45 | PRADIP CHOUDHARY | 5.83 | 5.83 | 100 | 100
2032 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Proposal for diversion of forest land for consytruction of OHR Capacity 350 cum of Augmentation of Roopganj Piped water supply scheme (JJM Work) under Durgapur W/S Division, PHE Directoreate - Demand note for payment of NPV, CA, Boundary demarcation witll pillar fencing etc. :- Cost of Boundary demarcation with pillar | 66/24-25 | 28/05/2024 | 0 | DIVISIONAL FOREST OFFICER, BURDWAN DIVISION | 0.3 | 0 | 0 | 0
2033 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Proposal for diversion of forest land for consytruction of OHR Capacity 350 cum of Augmentation of Roopganj Piped water supply scheme (JJM Work) under Durgapur W/S Division, PHE Directoreate - Demand note for payment of NPV, CA, Boundary demarcation witll pillar fencing etc. | 53/24-25 | 20/05/2024 | 0 | DIVISIONAL FOREST OFFICER, BURDWAN DIVISION | 0.8 | 0 | 0 | 0
2034 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum work order for Sinking of 2 nos of 300 x 200 mm dia tube well 210 mtr deep by D.R. Rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) at Bandra village and Roopganj of Augmentation of Roopganj PWSS under RCFA Division-I PHE Dte. | 2009/RCD-I | 11/07/2025 | 20 | M/S KALYANI ENTERPRISE | 27.78 | 0 | 0 | 100
2035 | PASCHIM BARDHAMAN | RCFA Division -I | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte , SM/10203 | Augmentation | Acceptance cum work order for Balance work of Rising Main from Tube Well to OHR at Roopganj Water Supply Scheme under RCFA Division-I PHE Dte. | 1646/RCD-I | 04/07/2024 | 242 | M/S KALYANI ENTERPRISE | 12.36 | 7.58 | 64.84 | 100
2036 | PASCHIM BARDHAMAN | Central Mechanical | BAMUNARA PIPED WATER SUPPLY SCHEME. , SM/11227 | New | Supply & Installation of Submersible Pumping Machinery, Voltages Stabilizer , Chlorination system and internal House wiring for Tube well for Tube well no:- 1 & 2 at Bamunara water supply scheme under CMD PHE Dte, Dist: Paschim Bardhaman. | 1656/CMD | 06/04/2023 | 30 | D.K. ELECTRIC | 22.77 | 22.04 | 96.79 | 100
2037 | PASCHIM BARDHAMAN | Durgapur W/S Division | BAMUNARA PIPED WATER SUPPLY SCHEME. , SM/11227 | New | Acceptance cum formal order for the work of Route survey and preparation of DPR for Augmentation of Bistupur ,Bamunara piped W/s Scheme under DWSD, PHE Dte | 526/DWSD | 29/03/2023 | 15 | MEASURE LAND | 8.11 | 7.62 | 93.88 | 0
2038 | PASCHIM BARDHAMAN | Durgapur W/S Division | BAMUNARA PIPED WATER SUPPLY SCHEME. , SM/11227 | New | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Bamunara piped W/s Scheme under DWSD ,PHE Dte (SL-05) | 1242/DWSD | 18/08/2022 | 15 | AHS R INFRA PRIVATE LIMITED | 14.76 | 13.36 | 100 | 0
2039 | PASCHIM BARDHAMAN | Durgapur W/S Division | BAMUNARA PIPED WATER SUPPLY SCHEME. , SM/11227 | New | Material Requisition To Resource Division | 1230/DWSD | 17/08/2022 | 0 | Resource Division | 46.44 | 0 | 0 | 0
2040 | PASCHIM BARDHAMAN | Durgapur W/S Division | BAMUNARA PIPED WATER SUPPLY SCHEME. , SM/11227 | New | Material Requisition To Resource Division | 255/D/DWSD | 15/02/2023 | 0 | Resource Division | 17.04 | 0 | 0 | 0
2041 | PASCHIM BARDHAMAN | Durgapur W/S Division | BAMUNARA PIPED WATER SUPPLY SCHEME. , SM/11227 | New | Service charges for new electricity connection at BamunnaraH/W site under Bamunara piped W/S Scheme | BP-2023-24-95 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.76 | 0 | 0 | 0
2042 | PASCHIM BARDHAMAN | Durgapur W/S Division | BAMUNARA PIPED WATER SUPPLY SCHEME. , SM/11227 | New | Electricity Service connection for Bamunnara TW-II H/W site under Bamunnara piped W/s Scheme | BP-2023-24-96 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.35 | 0 | 0 | 0
2043 | PASCHIM BARDHAMAN | Durgapur W/S Division | BAMUNARA PIPED WATER SUPPLY SCHEME. , SM/11227 | New | Formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and allied works construction 400 M3 OHR with 20 mtr staging height including soil investigation and construction of pump house (5.40 m X 3.60 m) with sanitary and water supply arrangement and construction of pump house (3.60X3.00 m) with FHTC for Bamunara piped water Supply scheme under DWSD ,PHE Dte (NS) | 1438/DWSD | 13/10/2022 | 1024 | HANNAN BUILDERS PVT. LTD. | 658.55 | 515.69 | 79.04 | 100
2044 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum work order for Construction of Store Room at Head Works Site for (Zone-4A) of Pandabeswar and Andal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. (Sl No. 29) | 1173/RCD I | 24/03/2023 | 90 | RANJIB GHATAK | 4.61 | 0 | 0 | 0
2045 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum work order for construction of Chlorine Room of Size (4.50 x 3.50 m) at (Zone-VII) of Salanpur Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman | 356/RCDI | 30/01/2023 | 15 | DAS & SARKAR ENTERPRISE | 4.6 | 3.78 | 100 | 100
2046 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Material Requisition To Resource Division | 2934/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
2047 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of ASTA (1135 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3021/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.98 | 4.98 | 100 | 100
2048 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Dendua(1135Cum) and ancillary structure sconducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3014/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.98 | 4.98 | 100 | 100
2049 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum work order for Construction for Additional works of MS manifold including interconnection in beetween CWR and pump house and etc allied works at Samlya H/W under Samlya W/S Scheme under RCFA Division-I PHe Dte. | 2869/RCD-I | 06/10/2023 | 15 | MAA ENTERPRISE | 6.41 | 6.16 | 100 | 100
2050 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Laying of distribution system at Khottamdihi village including FHTC works under Kendra Khottamdihi W/S Scheme under RCFA Div-I, PHE dte. | 2643/RCDI | 28/10/2022 | 225 | JAYANTA DATTA | 100 | 0 | 0 | 100
2051 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-B)(Sl No. 12) | 1116/RCD-I | 23/03/2023 | 90 | BABA LOKNATH ENTERPRISE | 71.02 | 48.63 | 68.48 | 80
2052 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-C) | 1118/RCD-I | 23/03/2023 | 90 | UNITED CONSTRUCTION | 81.57 | 75.71 | 92.81 | 90
2053 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-E) | 1120/RCD-I | 23/03/2023 | 800 | JAYANTA DATTA | 91.65 | 20.35 | 22.21 | 70
2054 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-A). | 1604/RCD I | 25/04/2023 | 180 | PINKI ENTERPRISE | 115.02 | 87.84 | 76.37 | 85
2055 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-D) (Sl No. 14) | 1707/ RCD I | 03/05/2023 | 90 | MD. JAWED KHAN | 69.87 | 49.08 | 70.25 | 80
2056 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum work order for Construction of Chlorine Room (Size 4.1 m x 3.5 m out to out) at Shankarpur OHR Site for Augmentation of RCFA part-II (Zone-4A and 4B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 27) | 1171/RCD I | 24/03/2023 | 277 | RANJIB GHATAK | 4.61 | 0 | 0 | 100
2057 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Continuation work order for Providing FHTC through Retrofitting at Bhaluka & Sonepur Bazari under Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. under JJM (RCFA Part-II) | 801/RCD-I | 06/03/2023 | 30 | MACHINO TECHNO | 67.77 | 65.09 | 100 | 100
2058 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum work order for Approach road and others necessary allied works at Front Gate to village road for Shankarpur OHR Site (Zone-4A and 4B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No 28) | 1172/RCD I | 24/03/2023 | 60 | RANJIB GHATAK | 3.78 | 3.7 | 100 | 100
2059 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Searsole (900 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | 3024/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.95 | 4.95 | 100 | 100
2060 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum Work Order for Additional work for laying MS pipe and allied works including adopting trench less technology b(e.g. Jack Pushing Method etc) of 02 (Two) nos location at Sankarpur (near Footbal ground ) and Shankarpur GP office under Augmentation of RCFA Part-II (Zone-4A) PWSS (Part-C ) under RCFA Division-I PHE Dte. (2nd Call) | 213/RCD-I | 29/01/2024 | 15 | UNITED CONSTRUCTION | 13.08 | 11.74 | 100 | 100
2061 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. , SM/12219 | Augmentation | Acceptance cum Work Order for Allied work for bridge, road and other allied work at Amritnagar Zone-I under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | 508/RCD-I | 12/02/2024 | 30 | MACHINO TECHNO | 81.93 | 81.91 | 100 | 100
2062 | PASCHIM BARDHAMAN | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. , SM/11933 | New | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Jatgoria piped W/s Scheme under DWSD ,PHE Dte(SL-07) | 1254/DWSD | 23/08/2022 | 15 | RANJIB GHATAK | 14.75 | 14.03 | 100 | 100
2063 | PASCHIM BARDHAMAN | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. , SM/11933 | New | Material Requisition To Resource Division | 255/E/DWSD | 15/02/2023 | 0 | Resource Division | 3.88 | 0 | 0 | 0
2064 | PASCHIM BARDHAMAN | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. , SM/11933 | New | Material Requisition To Resource Division | 694/DWSd | 08/05/2023 | 0 | Resource Division | 21.35 | 0 | 0 | 0
2065 | PASCHIM BARDHAMAN | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. , SM/11933 | New | New service connection charges for jatgoria piped W/s Scheme | BP-2023-24-54 | 08/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.22 | 0 | 0 | 0
2066 | PASCHIM BARDHAMAN | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. , SM/11933 | New | New service connection charges for jatgoria water supply scheme TW-2 | BP-2023-24-55 | 08/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.17 | 0 | 0 | 0
2067 | PASCHIM BARDHAMAN | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. , SM/11933 | New | Formal order for the work laying distribution system rising main ,construction of 100M3 reservoir with 20mtr staging height including soil investigation construction of pump house (5.40X3.60 m) with sanitary and water supply arrangement and construction of pump house (3.6 X 3.00 m) for Jatgoria W/s Scheme ,Kanksa block under DWSD,PHE Dte (NS) | 1656/DWSD | 05/12/2022 | 365 | SUPER SKILL | 170.87 | 109.73 | 64.22 | 45
2068 | PASCHIM BARDHAMAN | Central Mechanical | JATGARIA PIPED WATER SUPPLY SCHEME. , SM/11933 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Jatgaria Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | 1655/CMD | 06/04/2023 | 30 | CHOUDHURY ENTERPRISE | 21.07 | 20.29 | 100 | 40
2069 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. , SM/12026 | Augmentation | Material Requisition To Resource Division | 2952/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
2070 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. , SM/12026 | Augmentation | Acceptance cum work order for Supply fitting and allining of 250 mm dia non return valve and 80 mm dia air valve and etc allied works at Bilpahari OCP area on distribution main under Kendra Khottamdihi water supply scheme under RCFA Div-I, PHE Dte. | 2896_RCD-I | 06/10/2023 | 30 | M/S UNIT CONSTRUCTION | 2.42 | 0 | 0 | 0
2071 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. , SM/12026 | Augmentation | Acceptance cum work order for Laying & pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Srirampur Workshop road near Railway Workshop under Ondal Block under RCFA Division-I PHE Dte. | 3437_RCD_I | 24/11/2023 | 15 | M/S UNIT CONSTRUCTION | 9.31 | 0 | 0 | 0
2072 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. , SM/12026 | Augmentation | Acceptance cum work order for Laying and Pushing by adopting trench less technology(e.g.Jack Pushing Method etc) at Kunustoria for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I.PHE Dte.(Zone-7) Segment-5 | 1017/RCD-I | 16/03/2024 | 15 | B.T.M. CONCERN | 22.8 | 21.52 | 94.41 | 100
2073 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. , SM/12026 | Augmentation | Continuation work order for Probable Office expenditure of office of the Executive Engineer to meet up day to day various office & site expenses under RCFA div-I PHE Dte (w.e.f 01.08.2023 to 31.01.2024) | 2319_RCD-I | 31/07/2023 | 184 | M/S KALYANI ENTERPRISE | 4.49 | 0 | 0 | 0
2074 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. , SM/12026 | Augmentation | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology at 4 nos location (Dabor more, Achhra Road, Rupnarayanpur Phari, Rupnarayanpur Chittaranjan Road) of Salanpur Block under Improvement of RCFA Part-I (Zone-7, Part-F) PWSS under RCFA Division-I PHE Dte. | 2338/RCD-I | 01/08/2023 | 15 | GITA CONSTRUCTION | 67.97 | 63.53 | 100 | 100
2075 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. , SM/12026 | Augmentation | Acceptance cum work order for Construction of Guard room with toilet at Dendua under Salanpur Block for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | 3280/RCD-I | 08/11/2023 | 90 | D.S.ENTERPRISE | 7.61 | 7.29 | 100 | 100
2076 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. , SM/12026 | Augmentation | Acceptance cum work order for Allied work Balance Work of Road restoration in connection with Distribution Network including FHTC and allied work at Ondal Block of RCFA Part-II (Zone-6) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 454/RCD-1 | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 45.34 | 43.8 | 100 | 50
2077 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. , SM/12026 | Augmentation | Formal work order for Distribution Network Including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-6) Piped Water Supply Scheme Under RCFA Division-I PHE Dte. | 1763/RCD I | 16/05/2023 | 962 | MACHINO TECHNO | 541.2 | 167.23 | 30.9 | 30
2078 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. , SM/12026 | Augmentation | Acceptance cum work order for Crossing 600 mm dia MS Pipes under the Railway track by jack pushing technology at different spots and pushing different dia MS Pipes through 600 mm dia MS pipes in connection with the work of estimates for the laying distribution system for Amritnagar Zone-II under Augmentation of RCFA Part-II (Zone- under RCFA Division-I PHE Dte. (Part-B). | 2867/RCD-I | 06/10/2023 | 15 | MACHINO TECHNO | 41.98 | 38.27 | 91.37 | 100
2079 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. , SM/12026 | Augmentation | Formal work order for construction of 600 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connection and cost of pipes, specials at Ondal Block (Zone-6) for Augmentation of RCFA Part_II Piped Water Supply Scheme including Soil investigation and Chlorine Room (4.50 X 3.50 m) under RCFA Division-I PHE Dte. In District Paschim Bardhaman.(2nd Call). | 558/RCD-I | 21/02/2024 | 366 | MRITYUNJOY MUKHERJEE & CO. | 151 | 75.5 | 50 | 42
2080 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. , SM/12026 | Augmentation | Acceptance cum Work Order for Additional work for laying distribution pipe line of providing FHTC at Harispur Taldanga under Madanpur Gram Panchayat of Andal Block of JJM work AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) under RCFA Division-I.PHE Dte. | 1008/RCD-I | 16/03/2024 | 15 | M/S MONDAL ENTERPRISE | 5.56 | 5.55 | 100 | 100
2081 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum work order for Additional works of extra cutting Laterate/sand stone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-17) | 2871/RCD-1 | 06/10/2023 | 90 | TARA CONSTRUCTION | 24.96 | 24.82 | 100 | 100
2082 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Material Requisition To Resource Division | 2938/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
2083 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Sub Soil Investigation for 500 cum capacity RCC Over Head Reservoir at (Zone-17) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | 3352/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0.49 | 100 | 100
2084 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc.) at Amdiha more towards Itapara village Surrounding area (Zone-IX) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | 2332/RCD-I | 01/08/2023 | 15 | SRI KRISHNA ENTERPRISE | 19.97 | 18.86 | 100 | 100
2085 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum work order for Repairing and providing FHTC painting of H/W site for Dhandardihi Piped water supply Scheme Block-Andal, Dist-Paschim Bardhaman under RCFA Div-I, PHE Dte. | 3369/RCD-1 | 21/11/2023 | 15 | MD. JAWED KHAN | 3.12 | 2.97 | 100 | 100
2086 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum work order for Crossing 600 mm dia MS Pipes under the Railway track by jack pushing technology at different spots and pushing different dia MS Pipes through 600 mm dia MS pipes in connection with the work of estimates for the laying distribution system for Amritnagar Zone-II under Augmentation of RCFA Part-II (Zone-17) under RCFA Division-I PHE Dte. (Part-A). | 2866/RCD-I | 06/10/2023 | 30 | MACHINO TECHNO | 88.08 | 88.08 | 100 | 100
2087 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum work order for Construction of Guard room with toilet at Shyamla Over Head site under Augmentation of RCFA Part-II (Zone-17) under RCFA Division-I PHE Dte. | 2879/RCD-I | 06/10/2023 | 90 | G. CONSTRUCTION | 5.48 | 5.35 | 100 | 100
2088 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum work order for Repairing of UPVC pipe line supply fitting and fixing of valves and allied works under Dhandardihi water supply scheme under RCFA Division -I PHE Dte | 3375/RCD-I | 21/11/2023 | 15 | MD. JAWED KHAN | 3.61 | 3.55 | 100 | 100
2089 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum work order for Construction of Guard Room, extension of Boundary Wall, Land Development, approached road and allied works under Augmentation of RCFA Part-II (Zone-17) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | 3416/RCD-1 | 24/11/2023 | 60 | DIP CONSTRUCTION | 25.93 | 25.88 | 50 | 100
2090 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Restoration work for laying D.I pipeline along the Hard Shoulder from Ch. 3.67 Km to Ch. 8.50 kmp at left side and from ch. 3.00 to Ch. 4.50 kmp (ICDS more to Maira colliary ) at right side of Andal - Ukhra Road under Asansol Division, PWD in the district of Paschim Bardhaman | 112/24-25 | 21/06/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 20.4 | 0 | 0 | 0
2091 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Formal work order for distribution network for RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-17) | 997/RCDI | 22/03/2023 | 855 | TARA CONSTRUCTION | 342.78 | 139.59 | 40.72 | 75
2092 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum work order Construction of Pump House at Damalia H/W site for Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. | 3280/RCDI | 20/12/2022 | 45 | B.T.M CONCERN | 30.19 | 30.03 | 100 | 70
2093 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-17) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 30) | 1174/RCD I | 24/03/2023 | 739 | N.R. CONSTRUCTION | 4.61 | 0 | 0 | 100
2094 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Formal work order for Augmentation of construction of 500 cum capacity 20 mtr. staging height RCC Over Head Reservoir (piped connection and cost of pipes, specials at Raniganj Block (Zone-17) for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/2012 (Sheet No. 1 & 2) | 1829/RDC-i | 29/05/2023 | 366 | SWATI CORPORATION | 131.06 | 131.06 | 100 | 100
2095 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum work order for Laying & pushing of 600 mm dia RCC Hume pipe (NP3) by adopting trench less technology (e.g. Jack pushing method), MS water carrier pipe and other allied works at distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-17) | 2863/RCD-I | 06/10/2023 | 573 | TARA CONSTRUCTION | 38.14 | 32.73 | 90.94 | 90
2096 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum work order for Additional works of concrete dismantling & re-concreting with other allied works at distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-17) | 2876/RCD-1 | 06/10/2023 | 30 | TARA CONSTRUCTION | 76.37 | 40.54 | 100 | 100
2097 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum work order for Laying of 110 mm dia and 90 mm dia HDPE pipe line including chokage cleaning and other allied works of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | 3433/RCD-1 | 24/11/2023 | 30 | JAI MAHARAJ ENTERPRISE | 6.6 | 6.6 | 100 | 100
2098 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Additional work for supply and delivery of CI/DI specials including hard rock cutting, restoration of drain and supply of MS pipe (500 mm dia) and allied works within Zone-I Part-B under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | 464/RCD-1 | 12/02/2024 | 20 | SWATI CORPORATION | 18.11 | 17.86 | 100 | 100
2099 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum Work Order for Additional works for construction of boundary wall with gate at OHR site (length 150 mtr) and land development with approach road including internal drain at Head Work Site for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-17) | 934/RCD-I | 15/03/2024 | 15 | SWATI CORPORATION | 20.16 | 17.76 | 100 | 100
2100 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. , SM/12218 | Augmentation | Acceptance cum Work Order for Additional works of extra cutting laterate / sandstone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Div-I PHE Dte. (Zone-17) | 488/RCD-I | 12/02/2024 | 45 | TARA CONSTRUCTION | 9.16 | 8.81 | 100 | 100
2101 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Continuation order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Domra mouza (JL-68) under command area of Tilakchandrapur piped W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte | 1663/DWSD | 25/11/2021 | 10 | AMARANJALI CONSTRUCTION | 4.97 | 0 | 0 | 0
2102 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Providing additional number of FHTC and laying of branch pipe line from existing pipe line in connection with JJM for Basuhda Mouza (JL_35) under command area of Basudha W/s Scheme at Kanksa block under DWSD ,PHE Dte (SL-06) | 1376/DWSD | 17/09/2021 | 60 | M/S S. CHOUDHURY | 38.92 | 40.02 | 100 | 0
2103 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Supplying and laying of 140 mm dia UPVC pipe line from Hetedoba OHR to Jhajra more for water supply of Sarpi more ,Jhanjra gram and Adibasipara of Jamgora under Jamgora-Jagannathpur piped W/s Scheme.(SL-07) | 1371/DWSD | 17/09/2021 | 20 | MD AAMIR KHAN | 23.48 | 0 | 0 | 0
2104 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line and replace old damaged AC pipe line with HDPE pipe of Kanksa Zone-I W/s Scheme to combat draught like situation in Kanksa block to providing FHTC at Shilampur Gosh Para Mouza JL-89 under DWSD ,PHE Dte (SL-10) | 1320/DWSD | 14/09/2021 | 15 | MAK CONSTRUCTION CO. | 4.91 | 9.83 | 200 | 0
2105 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Supplying ,fitting and fixing of CI special ,valve construction of Sluice valve chamber & others allied work for distribution system of entire command area of Gourbazar OHR site under Gourbazar-Ichhapur piped W/S Scheme under DWSD,PHE Dte (SL-16) | 1177/DWSD | 02/08/2021 | 15 | JOY GURU ENTERPRISE | 4.36 | 0 | 0 | 0
2106 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Supply fitting fixing and installation of sluice valve for O & Mtc of Kanksa (Zone-II (Ph-II) W/s Scheme command area of Panagarh ,Prayagpur Mouza under DWSD ,PHE Dte. (SL-13) | 1322/DWSD | 14/09/2021 | 15 | TARA CONSTRUCTION | 4.93 | 0 | 0 | 0
2107 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Emergent supply fitting ,fixing of sluice valve for repairing and maintenance of pipe line under command area of Jamgora-Jagannathpur W/s Scheme under DWSD, PHE Dte(SL-30). | 1184/DWSD | 06/08/2021 | 20 | TARA CONSTRUCTION | 3.86 | 0 | 0 | 0
2108 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Emegent supply ,fitting -fixing of Sluice valve for repairing and maintenance of pipe line under command area from Sarpi village,Amlouka,Patseura,Arati,Jabuna areas of Gourbazar-Ichhapur piped W/s Scheme under DWSD ,PHE Dte (SL-01) | 1338/DWSD | 14/09/2021 | 15 | MD AAMIR KHAN | 4.56 | 0 | 0 | 0
2109 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the Work of Emergent supplying, fitting fixing of Sluice valve for repairing and maintenance of ppe line under command are a of Ichhapur areas of Gourbazar-Ichhapur piped W/s Scheme under DWSD ,PHE Dte (SL-02) | 1339/DWSD | 14/09/2021 | 20 | MD AAMIR KHAN | 4.42 | 0 | 0 | 0
2110 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Cleaning the chokage of AC Pipe line of 80 /100/150 mm dia for providing water supply to Arrah Mouza & other allied works for providing FHTC of Roopgnaj W/s Scheme under DWSD ,PHE Dte (SL-34) | 1336/DWSD | 14/09/2021 | 10 | M/S KALYANI ENTERPRISE | 4.14 | 0 | 0 | 0
2111 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Jamgora-Jagannathpur W/s Scheme to combat draught like situation in Durgapur-Faridpur block to provide FHTC at Banerjeepara,Mukherjee para ,Bouri Para ,Harimandir ,Durgamandir of Nachan Gram from Nachan bypass of Nachan Mouza (JL-39) (Part-B) under DWSD, PHE Dte(SL-18) | 1326/DWSD | 14/09/2021 | 15 | BABA LOKENATH ENTERPRISE | 4.5 | 0 | 0 | 0
2112 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Continuation order for the work of Additional work for providing FHTC in connection with JJM at Jamgora (JL-23) block-Durgapur-Faridpur,Pachim Bardhaman under Jamgora-Jagannathpur piped W/s Scheme under DWD, PHE Dte (Part-A) | 1273/DWSD | 02/09/2021 | 15 | RANJIB GHATAK | 4.21 | 0 | 0 | 0
2113 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Continuation for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sarpi mouza (JL-35) (Pt-A) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-29) | 1225/DWSD | 19/08/2021 | 10 | KIRON ENTERPRISE | 1.22 | 2.27 | 100 | 0
2114 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Continuation order for the work of Continuation for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sarpi mouza (JL-35) (Pt-A) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-29) | 1214/DWSD | 17/08/2021 | 15 | KIRON ENTERPRISE | 4.84 | 9.72 | 100 | 0
2115 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Additional functional house hod tap connection FHTC in connection with JJM at Nachan mouza (JL-39) under command area of Jamgora-Jagannathpur piped W/s Scheme block -Durgapur-Faridpur under DWSD, PHE Dte (SL-03) | 1634/DWSD | 22/11/2021 | 30 | BABA LOKENATH ENTERPRISE | 11.05 | 11.1 | 48.29 | 0
2116 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing and restoration of distribution system of Nachan ,Bansia, Dhabani Labnapara for providing sufficient water to every house hold of Gourbazar -Ichhapur piped W/s Scheme under DWSD ,PHE Dte(SL-01) | 1162/DWSD | 02/08/2021 | 15 | M/S MONDAL ENTERPRISE | 4.75 | 0 | 0 | 0
2117 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal for the work of Additional FHTC in connection with JJM at Hetedoba Mouza under command area of Gourbazar-Ichhapur piped W/S Scheme of Durgapur-Faridpur block under DWSD PHE Dte . | 1779/DWSD | 21/12/2021 | 25 | RANAJOY ENTERPRISE | 9.62 | 8.76 | 47.67 | 0
2118 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Providing additional number of FHTC in connection with JJM for Roopganj mouza(JL-91) with extension of branch pipe line at Roopganj and Arrah under command are a of Roopganj W/S Scheme at Kanksa block under DWSD ,PHE Dte | 1783/DWSD | 21/12/2021 | 30 | M/S KALYANI ENTERPRISE | 17.08 | 17.39 | 50.45 | 0
2119 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at different places to combat water crisis at Bonsal,Hetedoba,Jabber Pally & Hetedoba, block - Durgapur-Faridpur of Ichhapur GP under DWSD, PHE Dte . (SL-28) | 1183/DWSD | 06/08/2021 | 15 | JOY GURU ENTERPRISE | 3.21 | 0 | 0 | 0
2120 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Bypass connection from existing R/M at Gopalpur OHR site and jungle cutting at head work site Pump house Site -II and III of Gopalpur W/s Scheme under DWSD,PHE Dte .(SL-29) | 1333/DWSD | 14/09/2021 | 15 | QUICK PAL SUPPLIERS | 4.94 | 0 | 0 | 0
2121 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of sinking 1 No. 250 mm X 150 mm dia tube well 90 mtr deep by DR method using PVC pipe and fiber glass reinforced epoxy resin slotted at Krishnapur H/W site (OHR) under Krishnapur W/s Scheme under Durgapur W/s Division, PHE Dte | 41/DWSD | 13/01/2021 | 10 | AMARANJALI CONSTRUCTION | 7.02 | 0 | 0 | 0
2122 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Matwangini more to Bhabandapur village road of Gourbazar-Ichhapur piped W/S Scheme under DWSD,PHE Dte | 74/DWSD | 21/01/2022 | 20 | R.K.ENTERPRISE | 4.99 | 0 | 0 | 0
2123 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Emergency repairing and restoration of distribution system from command are a of Jagannathpur OHR (Gopendanga ,Kalinagar,Jagannathpur,Kailashpur part) Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte. | 1778/DWSD | 20/12/2021 | 20 | M/S BADAL GHOSH | 5.54 | 0 | 0 | 0
2124 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Continuation order for the work of Additional work for providing FHTC in connection with JJM at Jamgora (JL-23) block-Durgapur-Faridpur,Pachim Bardhaman under Jamgora-Jagannathpur piped W/s Scheme under DWD, PHE Dte (Part-C) | 1290/DWSD | 07/09/2021 | 15 | RANJIB GHATAK | 3.75 | 3.75 | 49.95 | 0
2125 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing and restoration of distribution system from command area of Gourbazar OHR (Gourbazar-Srikrishanapur,Kailashpur(Part) for providing sufficient Water to every house holds under Gourbazar-Ichhapur piped W/s Scheme under DWSD ,PHE Dte (Part-B) (SL-03) | 1164/DWSD | 02/08/2021 | 15 | JOY GURU ENTERPRISE | 3.49 | 0 | 0 | 0
2126 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Continuation order for the work of Additional work for providing FHTC in connection with JJM at Jamgora (JL-23) block-Durgapur-Faridpur,Pachim Bardhaman under Jamgora-Jagannathpur piped W/s Scheme under DWD, PHE Dte (part-B) | 1283/DWSD | 06/09/2021 | 15 | RANJIB GHATAK | 4.12 | 3.86 | 48.31 | 0
2127 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Bansal Kamala Park, DMC area of Vivekananda Nagar under retrofitting's of Gourbazar -Ichhapur piped W/S scheme under DWSD ,PHE Dte (Part-C) (SL No-06) | 1792/DWSD | 23/12/2021 | 15 | JOY GURU ENTERPRISE | 4.96 | 4.93 | 100 | 0
2128 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Protapur mouza (JL-40) under Jamgora-Jagannathpur Piped W/s Scheme under DWSD,PHE Dte (SL-07) | 1793/DWSD | 23/12/2021 | 15 | JAYANTA DATTA | 4.56 | 4.54 | 100 | 0
2129 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Additional work for providing FHTC in connection with JJM for Radhamohanpur Mouza(JL-36) under command area of Basudha piped W/S Scheme ,Block-Kanksa under DWSD,PHE Dte (SL-04) | 1706/DWSD | 08/12/2021 | 30 | MD AAMIR KHAN | 24.05 | 24.6 | 50.57 | 0
2130 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Bansal Kamala Park ,Majhipara and Bouri Para under retrofitting's of Gourbazar -Ichhapur piped W/S scheme under DWSD ,PHE Dte (Part-B)(SL-05) | 1791/DWSD | 23/12/2021 | 15 | JOY GURU ENTERPRISE | 4.93 | 4.92 | 100 | 0
2131 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Additional work for providing FHTC in connection with JJM for Shilampur Mouza(JL-90) under command area of Kanksa (Zone-I) piped W/S Scheme ,Block-Kanksa under DWSD,PHE Dte | 1707/DWSD | 08/12/2021 | 30 | MD AAMIR KHAN | 42.05 | 43.15 | 50.64 | 0
2132 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of additional laying of pipe line and repairing of damage road with concrete work at Sarpi (Mouza-35) under command area of retrofitting of improvement of Gourbazar-Ichhapur W/s Scheme under DWSD ,PHE Dte (SL-02) | 1553/DWSD | 27/10/2021 | 20 | K.M. ENTERPRISE | 2.3 | 0 | 0 | 0
2133 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of repairing of existing distribution pipe line with 110 mm UPVC line and necessary allied works at Nakrakonda village under RCFA Pt-III W/s Scheme under DWSD, PHE Dte (SL-12) | 98/DWSD | 28/01/2022 | 15 | RANAJOY ENTERPRISE | 1.25 | 0 | 0 | 0
2134 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Jabber Pally ,Bansal Vadupara under retrofitting's of Gourbazar -Ichhapur piped W/S scheme under DWSD ,PHE Dte (Part-A)(SL-04) | 1790/DWSD | 23/12/2021 | 15 | JOY GURU ENTERPRISE | 5 | 5 | 100 | 0
2135 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Supplying and laying of laying 75 mm dia HDPE pipe line at Prayagpur canal per in Kanksa block to providing FHTC at Prayagpur mouza (JL-88) (Part-A) under DWSD ,PHE Dte (SL-10) | 1796/DWSD | 24/12/2021 | 15 | CHATTERJEE CONSTRUCTION | 4.98 | 5.01 | 100 | 0
2136 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Replacement of damage existing distribution pipe line with 75 mm UPVC line and necessary allied works at Loudoha village Palpara,Ghosh Para & Banerjee para under RCFA Pt-III W/s Scheme under DWSD ,PHE Dte (SL-3) | 1575/DWSD | 27/10/2021 | 15 | D. S. ENTERPRISE | 4.67 | 0 | 0 | 0
2137 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal for the work of Emergency provision of AC phtovoltaic submersible solar pump set within bore well tube well along with 2400 peak watt capacity soalr photovoltaic array on Ms structure with sinking of 150 mm dia tube well 90 mtr deep by DR ring method using PVC pipe and fiber glass reinforced epoxy resin slotted to meet up water demand during summer season at Kalinagar under GP-Pratabpur Block-Durgapur-Faridpur under DWSD, PHE Dte | 1776/DWSD | 20/12/2021 | 30 | M/S BADAL GHOSH | 11.69 | 0 | 0 | 0
2138 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at Maheshpur village within Durgapur-Faridpur Block to combat waters crisis and protection of RCC Columns within Tumuni river near Jagannathpur village under DWSD, PHE Dte(SL-5) | 1572/DWSD | 27/10/2021 | 15 | M/S BADAL GHOSH | 1.98 | 0 | 0 | 0
2139 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Continuation order for the work of Balance work for Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Gopendanga mouza (JL-94) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte. | 1662/DWSD | 25/11/2021 | 10 | BADAL GHOSH | 1.91 | 1.91 | 100 | 0
2140 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Continuation order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Mahespur mouza (JL-12) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte. | 1746/DWSD | 15/12/2021 | 10 | BADAL GHOSH | 3.96 | 3.96 | 100 | 0
2141 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Continuation for the work of providing functional household tap connection (FHTC) in connection with JJM at Srikrishnapur mouza (JL No-09),Baidayanathpur and Kailashpur(JL No-09/20/22) under Retrofitting of Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte. | 266/DWSD | 04/03/2022 | 15 | JOY GURU ENTERPRISE | 3.6 | 3.58 | 100 | 0
2142 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of laying 75 mm dia HDPE pipe line at Prayagpur canal Par in Kanksa block to providing FHTC at Prayagpur mouza (JL-88) (Part-B) under DWSD ,PHE Dte (SL-09) | 1795/DWSD | 24/12/2021 | 15 | CHATTERJEE CONSTRUCTION | 3.26 | 3.33 | 100 | 0
2143 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Additional distribution pipe line with necessary allied works for FHTC purpose at Jagannathpur gram,Jagganathpur Dangal para to Kailashpur upper para ,Kalinagar main road to upper para ,Gopendanga main road to Bagdi para under Improvement of Jamgora-Jagannathpur Piped W/s Scheme under DWSD,PHE Dte | 1802/DWSD | 27/12/2021 | 20 | M/S BADAL GHOSH | 3.99 | 3.99 | 100 | 0
2144 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Banguri mouza (JL-52) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-01) | 142/DWSD | 28/01/2021 | 30 | SUBHADEEP DAS | 7.7 | 6.82 | 100 | 0
2145 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Supplying laying of 90 mm dia UPVC pipe bypass connection for Amlouka gram from Banguri more of Improvement of Jamgora-Jagannathpur W/s Scheme under DWSD ,PHE Dte (SL-02) | 135/DWSD | 02/02/2022 | 15 | MD JAWED KHAN | 6.6 | 0 | 0 | 50
2146 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal work- order for the work of ----Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Basudebpur mouza (JL-5)under command area of Kanchanpur W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-03) | 930/DWSD | 22/09/2020 | 45 | MACHINO TECHNO | 15.79 | 26.46 | 83.7 | 0
2147 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Arrah mouza (JL-91) (Pt-B) under command area of Roopganj W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte | 145/DWSD | 28/01/2021 | 50 | M/S KALYANI ENTERPRISE | 36.43 | 32.48 | 47.13 | 0
2148 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Debipur mouza (JL-87) (Pt-B) under command area of Kanksa Zone-II (Ph-II) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-08) | 1437/DWSD | 28/12/2020 | 60 | M/S. D. PALIT & CO. | 42.74 | 57.64 | 69.02 | 0
2149 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Satkahania mouza (JL-34) under command area of Basudha W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-12) | 1440/DWSD | 28/12/2020 | 25 | SUBHADEEP DAS | 8.66 | 15.2 | 100 | 0
2150 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Dubrajpur,Sashipur,Benodpur,Sundipur,Talbahari,Srirampur Mouzas (JL-9,8,6,4,3,1)under command area of Kanchanpur W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte | 1443/DWSD | 28/12/2020 | 30 | MACHINO TECHNO | 27.32 | 45.74 | 100 | 0
2151 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Panagarh mouza (JL-85) (Part-B) under command area of Kanksa Zone-II(Ph-II) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte | 1445/DWSD | 28/12/2020 | 25 | GITA CONSTRUCTION | 17.07 | 27.86 | 100 | 0
2152 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-E) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-01) | 1431/DWSD | 28/12/2020 | 60 | SWATI CORPARATION | 42.78 | 87.48 | 101.08 | 0
2153 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal workorder for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-F) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-05) | 1434/DWSD | 28/12/2020 | 45 | TARA CONSTRUCTION | 27.72 | 56.89 | 101.25 | 0
2154 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shyamsundarpur mouza (JL-07) (Pt-B) under command area of Gourbazar-Ichhapur W/s Scheme of Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte .(SL-02) | 171/DWSD | 03/02/2021 | 25 | PRAVAT SARKAR | 37.43 | 63.5 | 124.84 | 0
2155 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Kanchanpur mouza (JL-02) under command area of Kanchanpur piped W/s Scheme of Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-15) | 1318/DWSD | 09/12/2020 | 45 | MRITYUNJOY MUKHERJEE AND CO | 17.56 | 29.42 | 83.1 | 0
2156 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Ayma Biswanathpur & Gangbil mouza (JL-82 & 83) under command area of Kanksa Zone-I piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte (SL-22) | 1363/DWSD | 10/12/2020 | 45 | MD AAMIR KHAN | 41.61 | 83.23 | 99.98 | 0
2157 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Basudha mouza (JL-35) under command area of Basudha piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte (SL-18) | 1321/DWSD | 09/12/2020 | 45 | M/S S. CHOUDHURY | 42.77 | 82.12 | 94.87 | 0
2158 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Pryagpur mouza (JL-88) under command area of Kanksa Zone-II(Ph-II) (Pt-A) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte.(Sl-19) | 1322/DWSD | 09/12/2020 | 45 | DAS & CHAKRABORTY | 43.55 | 87.22 | 194.98 | 0
2159 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Debipur mouza (JL-87) under command areaof Kanksa Zone-II(Ph-II) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-21) | 1313/DWSD | 09/12/2020 | 45 | M/S. D. PALIT & CO. | 43.64 | 82.83 | 94.97 | 0
2160 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-A) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-18) | 1448/DWSD | 28/12/2020 | 60 | GITA CONSTRUCTION | 42.61 | 76.74 | 88.57 | 0
2161 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Prayagpur mouza (JL-88) (Pt-B) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte | 1439/DWSD | 28/12/2020 | 25 | DAS & CHAKRABORTY | 7.24 | 7.33 | 50.3 | 0
2162 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Basudha mouza (JL-35) (Pt-B)under command area of Basudha W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte | 1442/DWSD | 28/12/2020 | 25 | SAIKAT RAY | 17.42 | 33.88 | 158.51 | 0
2163 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Kanksa (Zone-II) Ph-II W/s Scheme to combat draught like situation in Kanksa block to providing FHTC at Prayagpur Mouza(JL-88)(Part-C) under DWSD,PHE Dte | 317/DWSD | 26/02/2021 | 30 | B. T. M. CONCERN | 4.98 | 4.98 | 100 | 0
2164 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Laying of additional distribution pipe line with necessary allied works at Domra and Piariganj mouza distribution zone under Tilakchandrapur W/s Scheme under DWSD ,PHE Dte (SL-05) | 990/DWSD | 05/07/2021 | 20 | AMARANJALI CONSTRUCTION | 11.94 | 23.82 | 200 | 0
2165 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Extension of existing pipe line of Kanchanpur to combat drought like situation in Kanksa block to providng FHTC at Kanchanpur,Sashipu,Benodpur,Dubrajpur,Basudebpur,Talbahari mouzas repiring of leakage bursting 160 to 90 mm dia at different places ,restoration of drain village road supply of hume pipe at pump house No-II and others allied works of cmmand area under Kanchanpur piped W/s Scheme (SL-02) | 1291/DWSD | 07/09/2021 | 20 | MRITYUNJOY MUKHERJEE AND CO | 12.82 | 12.7 | 100 | 0
2166 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Additional work for providing functional houehold tap connection (FHTC) in connection with JJM at Bonsol Mouza(JL_49) ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur W/s Scheme of Durgapur W/s Division, PHE Dte.(SL-01) | 1272/DWSD | 02/09/2021 | 60 | JOY GURU ENTERPRISE | 22.47 | 22.45 | 100 | 0
2167 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal for the work of Providing functional household tap connection (FHTC) in connection with JJM at Shyamsundarpur Mouza(JL_07) ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur W/s Scheme of Durgapur W/s Division, PHE Dte.(Part-C) (SL-03) | 1254/DWSD | 27/08/2021 | 60 | PRAVAT SARKAR | 27.33 | 27.3 | 49.9 | 0
2168 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Additional work for providing functional household tap connection (FHTC) in connection with JJM at Bhadrapur Mouza & Basgora Mouza ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur W/s Scheme of Durgapur W/s Division, PHE Dte. | 1253/DWSD | 27/08/2021 | 60 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 6.7 | 6.66 | 49.82 | 0
2169 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Additional work for provding FHTC in connection with JJM and Jal Swapna at Ijjatganj mouza (JL_71) under command area of kanksa (Zone-II) W/s Scheme of block-Durgapur-Fardipur under DWSD ,PHE Dte (SL-08) | 1375/DWSD | 17/09/2021 | 45 | RANJIB GHATAK | 33.78 | 34.4 | 100 | 0
2170 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing kanksa Zone-I(Ijjatganj) Phase-I W/s Scheme pipe line of entire command area for providing sufficient water to every house hold to Kanksa mouza, Ijjatganj and Prayagpur mouza under DWSD,PHE Dte(SL-02) | 1404/DWSD | 23/09/2021 | 20 | DAS & CHAKRABORTY | 4.91 | 4.59 | 100 | 0
2171 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Additional work for providing functional house hold tap connection (FHTC) in connection with JJM at Tilakchandrapur Mouza(JL_63) & Sundiara(JL-67),Block-Kanksa ,Dist.-Paschim Bardhaman under Tilakchandrapur W/s Scheme of Durgapur W/s Division, PHE Dte.(SL-05) | 1229/DWSD | 23/08/2021 | 45 | S K ALIM | 15.03 | 15.01 | 100 | 0
2172 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Connection provide to different Govt offices ,Schools,(Kanksa Thana,Kanksa Girls high Schools,Kanksa GP,TC Pur GP & 6 Nos ICDS at Kanksa mouza under DWSD,PHE Dte (SL-01) | 1403/DWSD | 23/09/2021 | 15 | SWATI CORPORATION | 3.03 | 0 | 0 | 0
2173 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road at Prayagpur mouza for laying of branch line under command area of Kanksa Zone-II W/s Scheme for providing of FHTC under DWSD ,PHE Dte (SL-03) | 1405/DWSD | 23/09/2021 | 15 | B. T. M. CONCERN | 4.55 | 1.63 | 26.42 | 0
2174 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Additional work for providing FHTC in connection with JJM at Dhabani(JL-43) Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Jamgora-Jagannathpur piped W/s Scheme under DWSD,PHE Dte (SL-01) | 1093/DWSD | 30/07/2021 | 15 | RANJIB GHATAK | 4.44 | 8.87 | 200 | 0
2175 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Emergency provision of AC photovoltaic submersible solar pum set within bore well /tube well along with 2400 peak watt capacity solar photovoltaic array on MS structure with sinking of 150 mm dia Tube well 150 mtr deep by DR ring method using PVC pipe and fiber glass reinforced epoxy resin slotted to meet up water demand during summer season at near DVC School Para under Pandebaswar Block under DWSD ,PHE Dte (SL-12) | 1596/DWSD | 08/11/2021 | 30 | RANJIB GHATAK | 13.56 | 0 | 0 | 0
2176 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of 2 Nos trial bore by direct rotary method drilling using rig machine at Roopganj H/W Site ,Tube well No-I &II of Augmentation of Roopganj piped W/s Scheme under DWSD ,PHE Dte(SL-16) | 1803/DWSD | 28/12/2021 | 10 | M/S KALYANI ENTERPRISE | 2.32 | 0 | 0 | 0
2177 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Extension of pipe line from the existing pipe line from command area of Gourbazar-Ichhapur piped W/s Scheme of Ichhapur area for providing of FHTC at Ichhapur mouza(JL-50) under DWSD,PHE Dte (SL-05) | 140/DWSD | 03/02/2022 | 7 | SHWET BARANI | 13.62 | 0 | 0 | 0
2178 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Continuation order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shyamsundarpur mouza (JL-07) under command area of Gourbazar-Ichhapur W/s Scheme of Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (Part-C). | 1735/DWSD | 13/12/2021 | 10 | PRAVAT SARKAR | 4.97 | 0 | 0 | 0
2179 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Additional work for providing FHTC in connection with JJM for Kanksa mouzza (JL-89) under command area of Kanksa (Zone-II) Ph-II W/s Scheme at Kanksa block under DWSD ,PHE Dte (SL-03) | 199/DWSD | 16/02/2022 | 15 | GITA CONSTRUCTION | 9.72 | 0 | 0 | 0
2180 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work Providing FHTC in connection with JJM at Shayamsundarpur mouza(JL-07) ,Block-Durgapur-Fardipur Block ,Dist-Paschim Bardhman under Gourbazar-Ichhapur piped W/s Scheme PHE Dte (P-C) | 10/DWSD | 04/01/2022 | 15 | PRAVAT SARKAR | 4.84 | 0 | 0 | 0
2181 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Constinuation order for the work of Providing functional houe hold tap connection (FHTC) in connection with JJM at Shyamsundarpur mouza(JL-07) block-Durgapur-Faridpur , Dist Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte | 1643/DWSD | 23/11/2021 | 10 | PRAVAT SARKAR | 4.96 | 1.32 | 100 | 0
2182 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Continuation for the work of balance work for providing functional household tap connection (FHTC) in connection with JJM at Jagannathpur mouza (JL-26) under command area of Jamgora -Jagannathpur piped W/s Scheme under Durgapur-Faridpur block of DWSD,PHE Dte | 244/DWSD | 22/02/2022 | 25 | M/S BADAL GHOSH | 2.09 | 0 | 0 | 0
2183 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Supplying and laying of additional 90 mm /75 mm dia HDPE pipe line with concrete works and necessary works at Gangbill and Ayma Biswanathpur near Itvata More of Ayma Biswanathpur Mouza(JL-82 & 83) under Kanksa (Zone-I) W/s Scheme Block-Kanksa under DWSD,PHE Dte (Part-A)(SL-25) | 1330/DWSD | 14/09/2021 | 20 | MAK CONSTRUCTION CO. | 4.91 | 9.76 | 200 | 0
2184 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Bankati mouza (JL-33)under command area of Basudha W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte(SL-18) | 1159/DWSD | 28/10/2020 | 45 | BISHAL ENTERPRISE | 14.6 | 26.56 | 176.75 | 0
2185 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of additional 90 mm dia HDPE pipe line with necessary allied works at Ayma Biswanathpur Mouza (JL-82) Balighat towards Ketan of Ayama Biswanthpur under Kanksa (Zone-I) W/s Scheme Block-Kanksa under DWSD,PHE Dte.(SL-26) | 1331/DWSD | 14/09/2021 | 20 | MAK CONSTRUCTION CO. | 4.85 | 9.65 | 200 | 0
2186 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing and restoration of distribution system of Protapur ,Kalikapur and Jamgora village under command area of Nachan OHR of Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte (SL-02) | 1163/DWSD | 02/08/2021 | 20 | RANJIB GHATAK | 4.85 | 0 | 0 | 100
2187 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Laying of UPVC pipe line and other allied works at Kanksa under Pass to Molla para under Kanksa W/s Scheme under DWSD,PHE Dte.(SL-26) | 1044/DWSD | 09/10/2020 | 15 | M/S KALYANI ENTERPRISE | 4.94 | 9.84 | 200 | 0
2188 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | FORMAL WORK ORDER FOR the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Rajkusum mouza (JL-72) under command area of Rajkusum W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-01) | 875/DWSD | 15/09/2020 | 45 | RANJIB GHATAK | 31.99 | 15.07 | 37.67 | 0
2189 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work-order for the work of replacement of AC pipe line with UPVC pipe line at Mollapara More to Kansa Gangulipara under Kanksa W/S Scheme under DWSD, PHE Dte (SL-07) | 918/DWSD | 22/09/2020 | 20 | RANJIB GHATAK | 4.85 | 9.86 | 200 | 0
2190 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of --Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for RUPGANGANJ mouza (JL-54)under command area of Rupganj W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(Sl-02) | 1355/DWSD | 09/12/2020 | 45 | M/S KALYANI ENTERPRISE | 13.97 | 28.47 | 100.95 | 0
2191 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal work-order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Srikrishnapur mouza (JL No-09) under command area of Gourbazar-Ichhapur W/s Scheme Durgapur-Faridpur Block, Paschim Bardhaman under Durgapur W/S Division, PHE Dte. | 897/DWSD | 22/09/2020 | 45 | JOY GURU ENTERPRISE | 19.09 | 37.94 | 100 | 0
2192 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal work-order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Kajladihi mouza (JL-26) under command area of Krishnapur W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-01) | 902/DWSD | 22/09/2020 | 45 | THE STAR & CO | 16.5 | 32.83 | 200 | 0
2193 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of --Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shilampur mouza (JL-90)under command area of Kanksa Zone-I W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-06) | 932/DWSD | 25/09/2020 | 45 | MD AAMIR KHAN | 43.86 | 90.26 | 101.42 | 0
2194 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Bansol mouza (JL-49) under command area of Gourbazar-Ichhapru piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-28) | 1329/DWSD | 09/12/2020 | 45 | JOY GURU ENTERPRISE | 29.98 | 59.92 | 159.11 | 0
2195 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shyamsundarpur mouza (JL-07) (Pt-A) under command area of Gourbazar-Ichhapur W/s Scheme of Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (SL-30) | 1331/DWSD | 09/12/2020 | 45 | PRAVAT SARKAR | 33.89 | 67.46 | 160.31 | 0
2196 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Arati mouza (JL-54) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-09) | 1310/DWSD | 09/12/2020 | 45 | BISHAL ENTERPRISE | 26.15 | 52.59 | 100.26 | 0
2197 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Pratappur mouza (JL-40) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-25) | 1325/DWSD | 09/12/2020 | 45 | JAYANTA DATTA | 18.89 | 37.73 | 88.36 | 0
2198 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Kendua mouza (JL-36) & Chapabandhi (JL-37) under command area of Gourbazar-Ichhapru piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (SL-27) | 1328/DWSD | 09/12/2020 | 45 | CHANDAN HAZRA | 11.53 | 19.43 | 91.43 | 0
2199 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of cutting of concrete road with supplying ,laying of 160 mm dia OD HDPE pipe from Pump house to pond providing water to Roopganj and Arrah mouza and others allied works for providing FHTC of roopganj W/s Scheme under DWSD ,PHE Dte (SL-18) | 1350/DWSD | 09/12/2020 | 15 | M/S KALYANI ENTERPRISE | 3.09 | 6.16 | 100 | 0
2200 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work-order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jamgora mouza (JL-23) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-01) | 1332/DWSD | 09/12/2020 | 45 | RANJIB GHATAK | 24.63 | 49.21 | 99.85 | 0
2201 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Radhamohanpur mouza (JL-36) under command area of Basudha W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte | 1441/DWSD | 28/12/2020 | 25 | MD AAMIR KHAN | 13.53 | 27.39 | 200 | 0
2202 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Arrah mouza (JL-91) (Pt-C) under command area of Roopganj W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte | 146/DWSD | 28/01/2021 | 45 | DARPAN DAS & CO. | 24.19 | 48.27 | 99.88 | 0
2203 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Domra mouza (JL-68) under command area of Trilakchandrapur piped W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-06) | 155/DWSD | 28/01/2021 | 45 | AMARANJALI CONSTRUCTION | 21.66 | 43.26 | 200 | 0
2204 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Patsaora mouza (JL-53) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-13) | 1316/DWSD | 09/12/2020 | 45 | SHWET BARANI | 19.08 | 30.69 | 135.64 | 50
2205 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Ijjatganj mouza (JL-71) (Pt-B) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-06) | 1436/DWSD | 28/12/2020 | 25 | QUICK PAL SUPPLIERS | 5.93 | 11.78 | 200 | 0
2206 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Panagarh mouza (JL-85) under command area of Kanksa Zone-II(Ph-II) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-20) | 1314/DWSD | 09/12/2020 | 45 | UMWELT ENGINEER PVT LTD | 43.6 | 89.47 | 87.86 | 0
2207 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Additional pipe line work with concrete cutting at Shilampur mouza for providing FHTC in connection with Jal Jeevan mission for Shilampur Mouza(JL-90) under command area of Kanksa (Zone-I) W/s Scheme at Kanksa block under DWSD, PHE Dte (SL-18) | 72/DWSD | 13/01/2021 | 25 | MAK CONSTRUCTION CO. | 4.98 | 10.04 | 200 | 0
2208 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sibpur mouza (JL-20) under command area of within Bidbhar GP, Kanksa Block of Krishnapur piped W/s Scheme under Durgapur W/S Division, PHE Dte.(SL-10) | 1311/DWSD | 09/12/2020 | 45 | RANJIB GHATAK | 21.43 | 41.64 | 98.56 | 0
2209 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work-order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jotbalaram & Amdohi mouza (JL-08 & 25) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-14) | 1317/DWSD | 09/12/2020 | 45 | JOY GURU ENTERPRISE | 25.99 | 44.23 | 200 | 0
2210 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Bhadrapur(JL-34) & Banshgara mouza (JL-38) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-26) | 1326/DWSD | 09/12/2020 | 45 | GHOSH ENTERPRISE | 12.83 | 25.55 | 200 | 0
2211 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sarpi mouza (JL-35) (Pt-A) under command area of Gourbazar-Ichhapru piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte. (SL-29) | 1330/DWSD | 09/12/2020 | 45 | KIRON ENTERPRISE | 29.51 | 58.92 | 67.88 | 0
2212 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work-order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Hetedoba mouza (JL-48) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-06) | 1308/DWSD | 09/12/2020 | 45 | AMARANJALI CONSTRUCTION | 12.32 | 24.45 | 200 | 0
2213 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jabuna mouza (JL-55) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-11) | 1312/DWSD | 09/12/2020 | 45 | D. S. ENTERPRISE | 11.37 | 22.72 | 87.96 | 0
2214 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Sundiara mouza (JL-67) under command area of Trilockchandrapur piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte. under Durgapur W/S Division, PHE Dte.(SL-15) | 1319/DWSD | 09/12/2020 | 45 | S K ALIM | 14.52 | 28.98 | 67.64 | 0
2215 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Ichhapur mouza (JL-50) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-12) | 1315/DWSD | 09/12/2020 | 45 | SHWET BARANI | 25.79 | 45.26 | 200 | 0
2216 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Ijjatganj mouza (JL-71) under command area of Kanksa Zone-II(Ph-I) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte. (SL-17) | 1320/DWSD | 09/12/2020 | 45 | RANJIB GHATAK | 42.68 | 85.03 | 99.69 | 0
2217 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work-order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Banshia mouza (JL-31) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-03) | 1305/DWSD | 09/12/2020 | 45 | BABA LOKNATH ENTERPRISE | 17.74 | 36.51 | 200 | 0
2218 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Gopendanga mouza (JL-94) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-06) | 1307/DWSD | 09/12/2020 | 45 | M/S BADAL GHOSH | 6.63 | 11.82 | 200 | 0
2219 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Krishnapur mouza (JL-23) within Bidbahar GP under command area of Krishnapur W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte | 1447/DWSD | 28/12/2020 | 20 | THE STAR & CO | 5.63 | 11.17 | 200 | 0
2220 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Balance work for Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jagannathpur mouza (JL-26) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte. | 1449/DWSD | 28/12/2020 | 25 | M/S BADAL GHOSH | 14.76 | 26.44 | 200 | 0
2221 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Nabagram mouza (JL-22) having habitations Nabagram and Jambon within Bidbahar GP under command area of Krishnapur W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte | 143/DWSD | 28/01/2021 | 30 | RANJIB GHATAK | 13.2 | 12.03 | 200 | 0
2222 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jagannathpur mouza (JL-26) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-14) | 1156/DWSD | 28/10/2020 | 45 | M/S BADAL GHOSH | 10.15 | 18.01 | 200 | 0
2223 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Tilakchandrapur mouza (JL-63)under command area of Tilakchandrapur W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-15) | 1157/DWSD | 28/10/2020 | 45 | S K ALIM | 22.47 | 44.88 | 159.89 | 0
2224 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Rautdihi mouza (JL-25) under command area of Bidbahar GP Krishnapur piped W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(sl-17) | 1158/DWSD | 28/10/2020 | 45 | THE STAR & CO | 5.59 | 11.08 | 200 | 0
2225 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sarpi mouza (JL-35) (Pt-B) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-01) | 170/DWSD | 03/02/2021 | 45 | RANJIB GHATAK | 26.91 | 48.03 | 200 | 0
2226 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Kanksa zone -II Ph-II W/s Scheme to combat draught like situation in Kaksa Block to providing FHTC at Debipur Mouza (JL-87)(Part-D) under DWSD,PHE Dte (SL-56) | 301/DWSD | 26/02/2021 | 30 | MANAS KUMAR SAHA | 4.31 | 8.62 | 200 | 0
2227 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work Extension of pipe line from existing pipe line of Kanksa zone -II Ph-II W/s Scheme to combat draught like situation in Kaksa Block to providing FHTC at Debipur Mouza (JL-87)(Part-E) under DWSD,PHE Dte(SL-57) | 302/DWSD | 26/02/2021 | 30 | MANAS KUMAR SAHA | 4.98 | 9.96 | 200 | 0
2228 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Supplying of extra UPVC pipe line at different places of Kendua Hazra para ,Bouri para and Chapabandhi in connection of FHTC under Gourbazar-Ichhapur piped W/s Scheme of DWSD,PHE Dte.(SL-06) | 275/DWSD | 26/02/2021 | 20 | CHANDAN HAZRA | 2.89 | 5.08 | 200 | 0
2229 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line for providing FHTC in connection with JJM for Basudha mouza(JL-35(Part-B) under command area of Basudha W/s Scheme at Kanksa Block under DWSD, PHE Dte (SL-06) | 715/DWSD | 29/04/2021 | 20 | S.S.CONSTRUCTION | 4.98 | 9.97 | 200 | 0
2230 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Roopganj W/S Scheme to combat draught like situation in Kanksa block to providing FHTC at Roopganj mouza (JL-54) under DWSD, PHE Dte (SL-07) | 716/DWSD | 29/04/2021 | 25 | M/S KALYANI ENTERPRISE | 4.96 | 9.91 | 200 | 0
2231 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line for providing FHTC in connection with JJM for Basudha mouza(JL-35(Part-A) under command area of Basudha W/s Scheme at Kanksa Block under DWSD, PHE Dte(Sl-05) | 718/DWSD | 29/04/2021 | 25 | M/S S. CHOUDHURY | 4.85 | 9.72 | 200 | 0
2232 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of laying of PVC pipe line at Kailashpur village within Jagannathpur Mouza in connection with FHTC under Jamgora-Jagannathpur W/s Scheme under DWSD, PHE Dte(SL-07) | 276/DWSD | 26/02/2021 | 10 | M/S BADAL GHOSH | 2.07 | 4.13 | 200 | 0
2233 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of PVC pipe line at Shibpur Mouza (JL-20) and Nabagram Mouza (JL 22) in connection with FHTC under Krishnapur W/s Scheme under DWSD, PHE Dte.(SL-02) | 271/DWSD | 26/02/2021 | 10 | RANJIB GHATAK | 2.23 | 4.47 | 200 | 0
2234 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Balance work for providing FHTC in connection with JJM for Bansia mouza(JL-31) under command area of Jamgora-Jagannathpur W/s Scheme at Durgapur Faridpur Block under DWSD, PHE Dte (SL-05) | 796/DWSD | 12/05/2021 | 15 | BABA LOKENATH ENTERPRISE | 12.9 | 25.24 | 200 | 0
2235 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Additional work for providing functional house hold Tap connection (FHTC) in connection with JJM for Kalikapur mouza(JL-30) under command area of Jamgora-Jagannathpur W/S Scheme under DWSD, PHE Dte (SL-06) | 794/DWSD | 12/05/2021 | 15 | M/S MONDAL ENTERPRISE | 11.05 | 22.53 | 200 | 0
2236 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of additional pipe line work with concrete cutting at Bansia mouza for providing functional house hold tap connection (FHTC) in connection with JJM for Bansia mouza (JL-31) under command area of Jamgora-Jaggannathpur W/s Scheme at Durgapur-Faridpur block under DWSD, PHE Dte. (SL-04) | 719/DWSD | 29/04/2021 | 25 | BABA LOKENATH ENTERPRISE | 4.99 | 9.94 | 200 | 0
2237 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Laying of additional distribution pipe line with necessary allied works at Sarpi Adibasipara,Dhibarpara ,Bouripara,Ruidaspara, Mondalpara,Karmakarpara under Gourbazar-Ichhapur piped W/S Scheme under DWSD,PHE Dte (SL-01) | 1055/DWSD | 22/07/2021 | 15 | RANJIB GHATAK | 8.27 | 16.49 | 200 | 0
2238 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Additional work for providing FHTC in connection with JJM at Jabuna (JL-55) Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme of DWSD,PHE Dte (SL-06) | 1098/DWSD | 30/07/2021 | 10 | D. S. ENTERPRISE | 0.63 | 1.26 | 100 | 0
2239 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme with concrete cutting and re-concreting to combat draught like situation in Kaksa block to providing FHTC at Debipur mouza(JL-87)(Part-D) under DWSD,PHE Dte(SL-10) | 1102/DWSD | 30/07/2021 | 15 | MANAS KUMAR SAHA | 3.97 | 7.83 | 200 | 0
2240 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance order for the work of Additional work for providing functional household tap connection (FHTC) in connection with JJM at Ichhapur Mouza ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur W/s Scheme of Durgapur W/s Division, PHE Dte.(SL-08) | 1195/DWSD | 11/08/2021 | 60 | SHWET BARANI | 22.71 | 22.74 | 100 | 0
2241 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Debipur mouza(JL-87)(Part-F) under DWSD,PHE Dte (SL-11). | 1103/DWSD | 30/07/2021 | 15 | MANAS KUMAR SAHA | 4.85 | 9.7 | 200 | 0
2242 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Additional work for providing FHTC in connection with JJM at Pratappur(JL-40) Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte (SL-03) | 1095/DWSD | 30/07/2021 | 15 | JAYANTA DATTA | 4.2 | 8.07 | 200 | 0
2243 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Repairing ,extension as well as replace of damaged pipe line and allied works at Sarpi mouza (JL-35) under command area of Gourbazar-Ichhapur W/s Scheme under DWSD ,PHE Dte (SL-09) | 1300/DWSD | 09/09/2021 | 20 | KIRON ENTERPRISE | 6.59 | 13.15 | 200 | 0
2244 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from exisitn pipe line Kanksa (Zone-II (Ph-II) W/s Scheme to combat draught like situation in Kanksa block to providing FHTC at Kanksa mouza (JL_89) under DWSD ,PHE Dte at Poral para,Khadra para under DWSD,PHE Dte (SL-19) | 1111/DWSD | 30/07/2021 | 15 | SWATI CORPARATION | 4.95 | 10.06 | 200 | 0
2245 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal order for the work of Additional pipe line work with concrete cutting at Nachan mouza for provding FHTC in connection with JJM for Nachan mouza(JL-39) (Part-A) under command are aof Jamgora-Jagannathpur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte (SL-24) | 1116/DWSD | 30/07/2021 | 15 | BABA LOKENATH ENTERPRISE | 4.59 | 9.39 | 200 | 0
2246 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work-order for the work providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Kalikapur mouza (JL-30) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (SL-02) | 1304/DWSD | 09/12/2020 | 45 | M/S MONDAL ENTERPRISE | 11.59 | 23.85 | 101.29 | 0
2247 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal work-order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Piariganj mouza (JL-93) under command area of Tilakchandrapur piped W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte. (SL-11) | 1356/DWSD | 09/12/2020 | 45 | AMARANJALI CONSTRUCTION | 13.52 | 26.96 | 200 | 0
2248 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Formal order for the work of Replace of damaged AC pipe line with HDPE pipe from Kanksa under pass towards Kanksa PS of Kanksa (Zone-II & Ph-II) W/S Scheme under DWSD,PHE Dte (SL-06) | 1374/DWSD | 17/09/2021 | 20 | SWATI CORPARATION | 9.71 | 19.78 | 200 | 0
2249 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Kalinagar mouza (JL-27) under command area Durgapur-Faridpur Block of Jamgora-Jagnnathpur piped W/s Scheme of under Durgapur W/S Division, PHE Dte (SL-23) | 1323/DWSD | 09/12/2020 | 45 | M/S BADAL GHOSH | 5.52 | 10.49 | 200 | 0
2250 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. , SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Radhanagar mouza (JL-24) within Bidbahar GP under command area of Krishnapur W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-09) | 1338/DWSD | 28/12/2020 | 20 | THE STAR & CO | 5.48 | 10.92 | 200 | 0
2251 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07560 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | 960/RCD-I | 07/06/2021 | 30 | M/S MONDAL ENTERPRISE | 23 | 40.38 | 170.48 | 0
2252 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07560 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | 959/RCD-I | 07/06/2021 | 30 | JAYANTA DATTA | 23.01 | 4.02 | 100 | 0
2253 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07560 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-C] (3rd Call) | 1148/RCD-I | 22/07/2021 | 30 | GITA CONSTRUCTION | 22.58 | 45.26 | 183.75 | 0
2254 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07560 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-D] | 961/RCD-I | 07/06/2021 | 30 | S. CHAKRABORTY & CO. | 22.97 | 45.64 | 188.74 | 0
2255 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07560 | Retrofitting | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kirtansala (part) and Dharaspur village for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl 11) | 254/RCD-I | 01/02/2022 | 20 | DIP CONSTRUCTION | 4.95 | 4.76 | 100 | 0
2256 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07560 | Retrofitting | Emergency for providing balance FHTC through retrofitting at Shamdi G.P. area and Chayanpur and adjacent villages under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte.(Sl no 03) | 1980/RCD I | 24/08/2022 | 15 | KHEPI MAA TRADERS | 4.54 | 4.04 | 88.98 | 0
2257 | PASCHIM BARDHAMAN | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District , SM/07560 | Retrofitting | Formal Work Order for Pipe line crossing by adopting trench less technology (e.g. Jack Pushing Method etc) near Kanskuli DAM for dedicated pipe line towards Kanskuli village under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | 1772/RCD-I | 18/05/2023 | 15 | SRI KRISHNA ENTERPRISE | 4.37 | 4.37 | 100 | 0
2258 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of laying and aligning of DI K9 R/M pipe line supplying DI specials valves and allied works under Command area of Kataberia piped W/s Scheme under DWSD ,PHE Dte | 500/DWSD | 27/03/2023 | 30 | KANJILAL & CO. | 18.3 | 4.08 | 22.27 | 60
2259 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Constructions of 5.40 X 3.6 m switch room with plinth height (600 X 2000 mm ) with sanitary and water supply arrangement at Kataberia TW no -II of Kataberia piped W/s Scheme under DWSD PHE Dte | 495/DWSD | 24/03/2023 | 45 | M/S MONDAL ENTERPRISE | 6.84 | 0 | 0 | 0
2260 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Balance work for water supply arrangement for 1(One) No SLWM center at Bargoria and burning ghat at Bargoria ,Block-Durgapur-Faridpur for having no electricity with solar power connection including pipe line works and other allied works under proposed piped W/S Scheme for Kataberia under DWSD,PHE Dte | 770/DWSD | 22/05/2023 | 30 | BHUMIKA ENTERPRISE | 7.46 | 7.46 | 100 | 0
2261 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and allied works including FHTC and connection providing to Khatgoria mouzas JL-29 (Part-B) under command area of Kataberia piped W/s Scheme under DWSD ,PHE Dte | 580/DWSD | 10/04/2023 | 40 | SAIKAT RAY | 96.67 | 76.26 | 100 | 100
2262 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Sinking of 2 (Two) Nos 300X200X210 m depth by Direct reverse rotary method using UPVC pipe (CD) deep well screen (RDS) at Kataberia H/W site TW No-I site of Durgapur-Faridpur Block under PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM(SM/16249) | 1072/DWSD | 12/07/2023 | 30 | KIRON ENTERPRISE | 29.66 | 28.23 | 100 | 60
2263 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Supplying installation of 4(Four) Nos Centrifugal pumping machinery of 1 Hp for providing port water for existing Stand alon at Labnapara under Kataberia piped W/s Scheme under DWSD,PHE Dte. (Sl- 01) | 1179/DWSD | 24/07/2023 | 15 | GHOSH & ROY ENTERPRISE | 1 | 1 | 100 | 100
2264 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Supplying installation of 4(Four) Nos Centrifugal pumping machinery of 1 Hp for providing port water for existing Stand alon at Kataberia under Kataberia piped W/s Scheme under DWSD,PHE Dte. (Sl- 02) | 1191/DWSD | 25/07/2023 | 15 | GHOSH & ROY ENTERPRISE | 1 | 1 | 100 | 100
2265 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Supplying installation of 4(Four) Nos Centrifugal pumping machinery of 1 Hp for providing port water for existing Stand alon at Jamgora under Kataberia piped W/s Scheme under DWSD,PHE Dte. (Sl- 03) | 1178/DWSD | 24/07/2023 | 15 | GOUTAM GHOSH | 1 | 1 | 100 | 100
2266 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Sinking of 1 no Tubewell for Triat Bore 150 mm. big dia. Tube wel 90 mtr deep by Direct Rotary Rig methed at Akandara for Jem Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte.(Sl-02) | 48-SPOT/DWSD | 03/07/2023 | 15 | M/S BADAL GHOSH | 1 | 1 | 100 | 100
2267 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Cleaning the chokage of different dia pipeline at Gourbazar area under Durgapur W/S Divn,PHE Dte (Sl- 02) | 1392/DWSD | 16/08/2023 | 10 | GHOSH & ROY ENTERPRISE | 0.99 | 0.99 | 100 | 100
2268 | PASCHIM BARDHAMAN | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | QUOTATION MONEY FOR NEW CONNECTION AT KHATGORIA | BP-2023-24-4 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.39 | 0 | 0 | 0
2269 | PASCHIM BARDHAMAN | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | QUOTATION MONEY FOR NEW CONNECTION AT KANTABERIA. | BP-2023-24-3 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.3 | 0 | 0 | 0
2270 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Supplying ,laying and aligning of Hoped distribution pipe line and allied works including FHTC tap connection and connection & providing to Khatgoria Mouzas JL-29 (Part-C) under Command area of Kataberia pipe W/s Scheme under DWSD ,PHE Dte | 586/DWSD | 11/04/2023 | 45 | TARA PRASAD SARKAR | 94.91 | 80.73 | 85.07 | 80
2271 | PASCHIM BARDHAMAN | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Providing of lighting luminaries, electrical wiring of chlorine room with yard lighting arrangement of Kantaberia O.H.R. premises under Katabera W/S Scheme. | 1673/AMD | 04/10/2024 | 30 | SARVATAH PROJECTS PRIVATE LIMITED | 6.28 | 0 | 0 | 0
2272 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Construction of boundary wall at Khatgoria of Kataberia piped W/s Scheme pump house -II under DWSD ,PHE Dte | 585/DWSD | 11/04/2023 | 45 | SIL ENTERPRISE | 14.8 | 14.74 | 100 | 100
2273 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Constructions of 5.40 X 3.6 m witch room with plinth height (600 X 2000 mm ) with sanitary and water supply arrangement at Kataberia TW no -I of Kataberia piped W/s Scheme under DWSD PHE Dte | 581/DWSD | 10/04/2023 | 45 | MAJI DEVELOPERS | 6.92 | 0 | 0 | 100
2274 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Construction of boundary wall at Khatgoria H/W (OHR) site of land development approach road and others allied works of Kantaberia Piped W/s Scheme under DWSD ,PHE Dte | 491/DWSD | 24/03/2023 | 45 | GHOSH & ROY ENTERPRISE | 33.88 | 33.34 | 100 | 100
2275 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Constructions of 5.40 X 3.6 m switch room with plinth height (600 X 2000 mm ) with sanitary and water supply arrangement at Kataberia TW no -II of Kataberia piped W/s Scheme under DWSD PHE Dte (SL-11) | 578/DWSD | 10/04/2023 | 45 | M/S MANDAL ENTERPRISE | 6.84 | 6.84 | 100 | 100
2276 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and allied works including FHTC and connection providing to Kataberia mouzas JL-50 part-A under command area of augmentation of Kantaberia & Bistupur piped W/s Scheme under DWSD ,PHE Dte | 504/A/DWSD | 28/03/2023 | 40 | BISHAL ENTERPRISE | 78.86 | 74.88 | 100 | 100
2277 | PASCHIM BARDHAMAN | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Service Connection Charge at Khatagoria under Katabera. | BP-2023-24-85 | 14/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.75 | 0 | 0 | 0
2278 | PASCHIM BARDHAMAN | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | New Connection at Kantabeira RBTW | BP-2024-25-74 | 09/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.37 | 0 | 0 | 0
2279 | PASCHIM BARDHAMAN | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Service Connection Charge at Kantaberia. | BP-2023-24-84 | 14/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.28 | 0 | 0 | 0
2280 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Acceptance cum formal order for the work of Supplying laying and aligning of HDPE distribution system with construction of 150 M3 capacity 20 mtr staging height RCC OHR including pipe connection and soil investigation at Kataberia piped W/s Scheme under DWSD PHE Dte (SL-9) | 499/DWSD | 27/03/2023 | 827 | M/S K.B.CONSTRUCTION | 99.75 | 50.33 | 50.46 | 55
2281 | PASCHIM BARDHAMAN | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | SUPPLY & INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-05 AND OTHER ALLIED WORKS FOR T/W-01 AT KANTABERIA PIPED WATER SUPPLY SCHEME UNDER ASSANSOL MECHANICAL DIVISION, PHE DTE.,BLOCK-DURGAPUR-FARIDPUR, DIST.- PASCHIM-BARDHAMAN | 1680/AMD | 04/10/2024 | 157 | M/S SWAPAN BANERJEE | 18.46 | 0 | 0 | 90
2282 | PASCHIM BARDHAMAN | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Supply, delivery & installation of Submersible Pumping Machineries, Chlorinator and other allied materials for TubeWell No-I, II under Kantaberia Piped Water Supply Scheme, Block-Faridpur-Durgapur, District-Paschim Bardhaman. | 1023/AMD | 19/04/2023 | 714 | M/S SWAPAN BANERJEE | 22.85 | 5.66 | 45.3 | 100
2283 | PASCHIM BARDHAMAN | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | SUPPLY, DELIVERY AND INSTALLATIONF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-6 AT AUGMENTATION KANTABERIA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | 1924/AMD | 19/11/2024 | 293 | R.M.D. TRADING | 11.76 | 0 | 0 | 100
2284 | PASCHIM BARDHAMAN | RCFA Division -I | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM , SM/16249 | New | Shifting of office of the Executive Engineer, Durgapur W/s Division, PHE Dte, ADDA Administrative Building, EPIP Complex, Banskopa, Durgapur-12 to Nababhat, PHE Complex, Purba Bandhaman under Augmentation of Kataberia PWSS, Augmentation of Telipara under RCFA Division-I, PHE Dte. | 3516/RCD-I | 01/12/2023 | 15 | AMARANJALI CONSTRUCTION | 3.83 | 3.83 | 100 | 100
2285 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15639 | Augmentation | Acceptance cum formal order for the work of Dismantling of concrete road for laying distribution system rising main construction of 350 M3 reservoir with 20 mtr staging height including soil investigation construction of pump house (5.40 X 3.60 m) with sanitary and construction of pump house 3.60 X 3.00 m) for Amlajora piped W/s Scheme under DWSD ,PHE Dte | 488/DWSD | 23/03/2023 | 15 | RANADHIR SINHA | 5.99 | 5.99 | 100 | 0
2286 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15639 | Augmentation | Dismantling of concrete road and bitumunious road for balance work of laying distribution system ,RM construction of 250 M3 OHR including soil investigation ,construction of Pump house (5.40X3.60 with sanitary and water supply arrangment etc of pump house (3.6X3m) for Amlajora W/s scheme of DWSD,PHE Dte(SM/11937) | 1070/DWSD | 12/07/2023 | 20 | RANADHIR SINHA | 28.91 | 28.9 | 100 | 100
2287 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15639 | Augmentation | Laying and aligining rising main pipe line supplying DI Specials valves and other allied works at Amlajora of Augmentation of Amlajora piped W/s Scheme (SM/11937) | 1075/DWSD | 12/07/2023 | 30 | RANADHIR SINHA | 35.91 | 34.69 | 100 | 100
2288 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15639 | Augmentation | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 (Near Canalpar) , TUBE WELL NO-4 (Biharpur) and TUBE WELL NO-5 AT AMLAJORA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | 1889/AMD | 12/11/2024 | 30 | DEY ENTERPRISE | 37.85 | 0 | 0 | 0
2289 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15639 | Augmentation | Addition work for Laying of HDPE pipeine and Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission at of Arra Mouza JL No 89 Under command area of AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | 326/DWSD | 20/02/2023 | 30 | BISHAL ENTERPRISE | 81.29 | 81.06 | 100 | 100
2290 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15639 | Augmentation | Quotation from WBSEDCL for new service connection for Shilampur under Augmentation of Amlajora PWSS ,Kaksa | BP-2023-24-367 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.27 | 0 | 0 | 0
2291 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15639 | Augmentation | Implememntation of Har Ghar Jal for Providing FHTC in connection with JJM for Pratapur, Nachan mouza ,Dhabani mouza (JL-48) underAUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | 1074/DWSD | 12/07/2023 | 20 | MUKHERJEE ENTERPRISE | 18.4 | 0 | 0 | 0
2292 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15639 | Augmentation | Formal work order for Additional work for covering isolated area beyond the NH2 by creating a 2 (Two) nos separate zone under command area of Amlajora PWSS at the embankment of Durgapur Panagarh DVC branch canal situated in between DVC branch canal to Kol-Del Railway track and Biharpur Gram with sinking of 2 nos tube well 300 x 200 mm dia, Construction of Pump House cum/Switch room 5.4 m x 3.6 and laying of LDS with necessary inter connection including all others works of Amlajora PWSS under Augmentation of Amlajora Piped W/S Scheme under RCFA Division-I PHE Dte. | 3191/RCD-I | 23/12/2024 | 90 | RANADHIR SINHA | 156.64 | 0 | 0 | 40
2293 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15639 | Augmentation | Acceptance cum Work Order for Additional works for distribution network for RBTW water based water supply scheme for Sarpi and its joining mouza (Part-C) at Arati village including FHTC & allied works AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II Durgapur-Faridpur Block under RCFA Division-I PHE Dte. | 1795/RCD-I | 24/07/2024 | 45 | M/S BADAL GHOSH | 44.53 | 37.53 | 84.28 | 100
2294 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15639 | Augmentation | Acceptance cum work order for Balance work of laying distribution system, rising main, construction of 250 cum reservoir with 20 mtr staging height including soil investigation, construction of pump house (5.40 m x 3.60 m) with sanitary & W/S arrangement & construction of pump house (3.60 m x 3.00 m) for Amlajora W/S Scheme under RCFA Division-I PHE Dte. | 1424/RCD-I | 15/05/2025 | 90 | RANADHIR SINHA | 59.19 | 0 | 0 | 70
2295 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15639 | Augmentation | Formal order for the work of balance work of supplying and laying of HDPE distribution system with construction of 02 Nos Pump house ,Construction of 450 M3 OHR of 20 mtr staging height including soil testing construction of pump house (5.40X 3.60 m) with Sanitary arrangement and construction of pump house )3.60 X 3.00 m) of Augmentation of Amlajora piped W/s Scheme under DWSD ,PHE Dte . | 785/DWSD | 23/05/2023 | 678 | RANADHIR SINHA | 387.89 | 375.86 | 96.54 | 100
2296 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/15639 | Augmentation | Acceptance cum work order for Additional pipe line from Madhaiganj to Jamdoba Adibasi Para including re-connection of FHTC under Augmentation of Amlajora Water Supply Scheme under RCFA Division-I PHE Dte. | 2629/RCD-I | 14/11/2024 | 90 | M/S BADAL GHOSH | 37.59 | 9.44 | 20.94 | 100
2297 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16900 | Augmentation | Supply and Installation of Submersible Pumping Machinery and Internal House Wiring for Tube Well No-02 At augmentation of Garadaha Piped Water Supply Scheme under Asansol Mechanical Division, PHE Dte, Block- Kanksa, Dist- Paschim Bardhaman. | 2115/AMD | 16/12/2024 | 30 | V. P. CONCERN | 4.93 | 0 | 0 | 0
2298 | PASCHIM BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16900 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Garadaha Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | 1577/CMD | 04/04/2023 | 30 | RAJIB COMPANY | 8.97 | 8.17 | 100 | 100
2299 | PASCHIM BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16900 | Augmentation | Supply & Delivery of Pump Motor Set at TW No: 01 of Garadaha water supply scheme under CMD, PHE, Dte. | 112/DIC/BMSD(D) | 04/10/2023 | 15 | RAJIB COMPANY | 0.52 | 0.52 | 100 | 100
2300 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16900 | Augmentation | Formal order for the work of Balance work of construction of Pump house /Chlorine room sinking of 150X80 X120 mm depth tube well supplying laying of HDPE distribution pipe in and providing FHTC at Garadaha mouzas of Garadaha piped W/S scheme under DWSD,PHE Dte | 734/DWSD | 15/05/2023 | 687 | SHWET BARANI | 102.39 | 44.95 | 44.16 | 45
2301 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DANDESHWAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16901 | Augmentation | Acceptance cum formal order for the work of Route survey and preparation of DPR for Augmentation of Jatgoria ,Napara and Dandeswar piped W/s Scheme and Kataberia PWSS under DWSD, PHE Dte | 529/DWSD | 29/03/2023 | 15 | MEASURE LAND | 6.74 | 6.74 | 100 | 0
2302 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DANDESHWAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16901 | Augmentation | Acceptance cum formal order for the work of balance work for supplying and laying of HDPE distribution pipe line construction of pipe carrying structure and allied works at Railpar of Prayagpur mouza under AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DANDESHWAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | 320/DWSD | 20/02/2023 | 20 | SAIKAT RAY | 87.4 | 72.2 | 82.61 | 100
2303 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DANDESHWAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16901 | Augmentation | Acceptance cum formal order for the work of Additional work for laying of HDPE pipe line and providing FHTC in connection with JJM at Arrah mouza (JL-89) under command area of Augmentation of Dandeswar piped W/s Scheme under DWSD ,PHE Dte (Part-B) | 326/DWSD | 20/02/2023 | 30 | BISHAL ENTERPRISE | 81.29 | 0 | 0 | 50
2304 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DANDESHWAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/16901 | Augmentation | Formal order for the work of Balance work of supplying and laying of HDPE distribution system with construction 02 Nos pump house construction of 150 M3 OHR of 20 Mtr staging height as per Deptt drawing laying aligning of rising main and providing FHTC connection of all mouzas under Command area of Augmentation Dandeswar piped W/s Scheme under DWSD, PHE Dte. | 796/DWSD | 24/05/2023 | 678 | POWER TOOLS AND ENGINEERING | 122.46 | 94.34 | 78.58 | 80
2305 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18877 | Augmentation | SUPPLY, DELIVERY AND INSTALLATIONOF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 AT AUGMENTATION OF BASUDHA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | 1818/AMD | 29/10/2024 | 30 | M/S A.D.ENTERPRISE | 11.61 | 0 | 0 | 0
2306 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18877 | Augmentation | Formal work order for sinking of 02(two) nos TW. FHTC,laying Rising main & laying distribution system(LDS) construction of boundary wall, pump house and restoration of road & and other allied works for Augmentation of ground water based W/S scheme for Basudha under RCFA Division-I, PHE Dte. Block-Kanksa, Dist- Paschim Bardhaman, | 559/RCD-I | 21/02/2024 | 130 | MRITYUNJOY MUKHERJEE & CO. | 209.86 | 164.5 | 78.38 | 90
2307 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18877 | Augmentation | Quotation Payment for Basudha T/W No-3, under Kanksa Block, Paschim Bardhaman as per WBSEDCL Procedure-A(2010) on Turn-Key/Full Deposit Basis. | BP-2024-25-6 | 24/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.7 | 0 | 0 | 0
2308 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18877 | Augmentation | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied works at Basudha Pump House No-03 (OHR Site) under Augmentation of Basudha Water Supply Scheme, Block-Kanksa, Dist.- Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | 946/AMD | 16/05/2025 | 30 | CIEMENICS | 4.4 | 0 | 0 | 0
2309 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18877 | Augmentation | Acceptance cum work order for Sinking of 4 nos 200 mm dia River bed tube wells in the river Ajoy at Bhaburia Head Work Site under Augmentation of ground water based water supply scheme for Basudha Piped Water Supply Scheme (JJM) under RCFA Division-I PHE Dte. (Part-A) | 2443/RCD-I | 30/09/2024 | 166 | MACHINO TECHNO | 12.11 | 3.04 | 20.94 | 100
2310 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18877 | Augmentation | Supply and installation of submersible pumping machinery, voltage stabilizer, chlorination system and internal house wiring of augmentation of basudha water supply scheme p/h no-03 under Asansol Mechanical Division, PHE Dte., Dist.- Paschim Bardhaman. | 1321/AMD | 21/08/2024 | 133 | PESTCO INDIA | 12.03 | 0 | 0 | 100
2311 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18877 | Augmentation | Acceptance cum work order for Improvement & Overhauling of 2 nos Iron Removal Plant (pressure type), each capacity 50 cum/Hr at Basusha H/W site & at Krishnapur of Augmentation of Ground Water Based Water Supply Scheme for Basudha under RCFA W/S Division-I, PHE Dte. | 2614/RCD-I | 13/11/2024 | 30 | RUPALI ELECTRONICS | 12.85 | 12.78 | 100 | 100
2312 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Acceptance cum formal order for the work of Construction of boundary wall at Arrah H/W site OHR site ,Land development ,approach road and other allied works of Bamunara piped W/s Scheme under DWSD ,PHE Dte | 328/DWSD | 20/02/2023 | 35 | AMARANJALI CONSTRUCTION | 30.43 | 0 | 0 | 0
2313 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Additional work of supplying and laying of different dia HDPE pipe line with necessary allied works at Silampur(JL-90) block-Kanksa under Augmentation of Kanksa Zone-I piped W/S scheme under DWSD,PHE Dte (SM/10208) | 1077/DWSD | 12/07/2023 | 35 | MAK CONSTRUCTION CO. | 96.46 | 5.3 | 9.39 | 45
2314 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Acceptance cum formal order for the work of Creating a separate zone for PATHANPARA and Bagdipara of Kanksa (Zone-II/Part-C) with construction of Pump house /Chlorine room Sinking of 150 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Paragraph Mouza under Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme under DWSD, PHE Dte | 1139/DWSD | 20/07/2023 | 45 | JOY GURU ENTERPRISE | 95.5 | 0 | 0 | 0
2315 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works plinth protection ,roof treatment ,drain and other allied works at Sarada Pally H/W Site Pump house No-1 &T.W-01(OHR site) for Augmentation of Kanksa (Zone-II/D) pipe W/S Scheme under DWSD,PHE Dte (SL-05) | 1060/DWSD | 08/07/2022 | 25 | GHOSH & ROY ENTERPRISE | 4.82 | 1.5 | 100 | 100
2316 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Acceptance cum formal order for the work of Approach road & others necessary allied works at Madhabmat front gate to village road for Kanksa Zone-II/A W/s Scheme under DWSD ,PHE Dte | 679/DWSD | 03/05/2023 | 45 | SAIKAT RAY | 28.31 | 27.4 | 100 | 100
2317 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Special renovation work for modifying of existing structure under JJM at Ijjatganj 2 No pump house site including go down and guard room as well as boundary wall of Augmentation of Kanksa Zone-II/C piped W/s Scheme under DWSD ,PHE Dte | 1196/DWSD | 27/07/2023 | 30 | MUKHERJEE ENTERPRISE | 15.31 | 12.32 | 100 | 100
2318 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Acceptance cum formal order for the work of Repairing of existing concrete road restoration and other allied works under Augmentation of Bamunnara piped W/s Scheme under DWSD,PHE Dte (Part-E) | 1283/DWSD | 07/08/2023 | 15 | AHS R INFRA PRIVATE LIMITED | 9.13 | 9.13 | 100 | 100
2319 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of BAMUNARA (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No-01) | 1193/DWSD | 25/07/2023 | 7 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
2320 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Material Requisition To Resource Division | 1557/DWSD | 20/09/2023 | 0 | Resource Division | 20.93 | 0 | 0 | 0
2321 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 (Rajmath Uttarpara), TUBE WELL NO-4 (Banskopa) , and TUBE WELL NO-5 (Rajbandh) AT BAMUNARA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | 1817/AMD | 29/10/2024 | 30 | M/S SAJAHAN CHOWDHURY | 34.88 | 0 | 0 | 0
2322 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Acceptance cum formal order for the work of Construction of 5.40 X3.60 mtr switch room with plinth height (600X 2000 mm) with sanitary and water supply arrangement at OHR site Arrah Shibtala of Augmentation of Bamunara piped W/S Scheme under DWSD ,PHE Dte | 323/DWSD | 20/02/2023 | 30 | NANDADULAL KONAR | 6.92 | 6.92 | 100 | 100
2323 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Quotation as per WBSEDCL Procedure-A (2010) for the site of Bamunara TW No.-03, Rajbandh Uttarpara. | BP-2024-25-66 | 28/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.91 | 0 | 0 | 0
2324 | PASCHIM BARDHAMAN | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Quotation payment as per WBSEDCL Procedure-A (2010) for Pump House No 5, under Augmentation of Bamunara Water Supply Scheme, near Rajbadh Choti, Block- Kanksa, Paschim Bardhaman. | BP-2024-25-71 | 03/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.75 | 0 | 0 | 0
2325 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Acceptance cum formal order for the work of Additional work for supplying ,laying and alinging of HDPE distribution pipe line and allied works at Railpar Saroda Pally of Kanksa mouza under command area of Augmentation of Kanksa piped W/s Scheme under DWSD ,PHE Dte (Part-B) | 318/DWSD | 20/02/2023 | 800 | AMARANJALI CONSTRUCTION | 60.53 | 24.4 | 40.31 | 80
2326 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Acceptance cum formal order for the work of creating a separate zone for BAMUNNARA of Bamunara piped W/S Scheme with construction of Pump house /Chlorine room Sin king of 1500 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Amlajora (64), Gopalpur(CT)(65) Mouza under Augmentation of BAMUNNARA piped W/s Scheme under DWSD, PHE Dte | 1141/DWSD | 20/07/2023 | 866 | AHS R INFRA PRIVATE LIMITED | 96.38 | 91.18 | 94.6 | 100
2327 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Acceptance cum work order for Additional work for Construction of 350 cum OHR at Arrah Sibtala, Block-Kanksa Dist - Paschim Bardhaman under Augmentation of Bamunara W/S Scheme under RCFA Division-I PHE Dte. | 210/RCD-I | 29/01/2024 | 60 | AMARANJALI CONSTRUCTION | 39.01 | 7.74 | 19.85 | 65
2328 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Formal work order for Acceptance order for Sinking of 02 (Two) no.s TW, FHTC, Laying Rising main & laying distribution system(LDS) construction of boundary wall, Pump House and restoration of road & other allied works for Augmentation of ground water based Bamunara PWSS under RCFA Division-I, PHE Dte. | 809/RCD-I | 14/03/2024 | 413 | RANJIB GHATAK | 91.37 | 0 | 0 | 90
2329 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Formal work order for Creating at 3 (Three) nos Separate Zone of Bamunara PWSS at Banskopa Toll Plaza to Rajbundh Railway Station, Rajbundh Choti, EPIP area of Banskopa mouza and Gopalpur mouza part (40%) situated between NH2 to Kolkata ¿ Delhi Railway track with sinking of 2 nos 300 x 200 mm dia, 01 no 150 x 150 mm dia Tubewell, Construction of Pump House cum Switch Room 5.40 x 3.60 mtr and LDS with necessary interconnection including all others works of Bamunara PWSS under Augmentation of Bamunara Piped Water Scheme under RCFA Division-I PHE Dte. | 3190/RCD-I | 23/12/2024 | 180 | HANNAN BUILDERS PVT. LTD. | 216.57 | 0 | 0 | 45
2330 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Formal order for the work of Balance work of supplying and laying of HDPE distribution system with construction of 02 Nos Pump house ,Construction of 450 M3 OHR of 20 mtr staging height including soil testing construction of pump house (5.40X 3.60 m) with Sanitary arrangement and construction of pump house )3.60 X 3.00 m) of Augmentation of Bamunara piped W/s Scheme under DWSD ,PHE Dte . | 1148/DWSD | 20/07/2023 | 573 | HANNAN BUILDERS PVT. LTD. | 498.67 | 426 | 86.65 | 100
2331 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN , SM/18467 | Augmentation | Restoration of Concrete road of Gopalpur & surrounding area under RCFA Division-I PHE Dte. | Camp-02-Gopalpur-AE-2024- | 02/09/2024 | 10 | M/S CHANDI CHARAN ROY | 9.5 | 9.49 | 100 | 100
2332 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum formal order for the work of Supplying, laying & aligning of UPVC distribution pipe line (Distribution system Part-A) and allied works including functional house holds tap connection (FHTC) and connection providing to Akandara(JL No-47) ,Molandighi(JL No-48),Kandarakona (JL_51),Rakhitpur(JL-42,Chua(JL-43),Bhagaabanpur(JL-45),Hariki(JL No-50) Mouzas under command area of Aug of Bistupur piped W/s Scheme under DWSD,PHE Dte | 81/DWSD | 25/01/2022 | 65 | MACHINO TECHNO | 377.99 | 0 | 0 | 0
2333 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance order for the work of Construction of of 500 M3 capacity ,20 Mtr staging height RCC Over Head Reservoir at Molandighi of Bistupur piped W/S Scheme under Durgapur W/S Division, PHE Dte .(SL-01) | 1650/DWSD | 25/11/2021 | 120 | MRITYUNJOY MUKHERJEE AND CO | 92.97 | 18.1 | 50.59 | 100
2334 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Formal order for the work of laying of distribution system and providing FHTC including reconnection of exiting FHTC from AC pipe line to newly laid different dia HDPE pipe line for Augmentation of Kanksa (Zone-II/Part-C) piped W/S Scheme under DWSD ,PHE Dte (SL-05) | 1161/DWSD | 01/08/2022 | 4 | BRINDABAN KONAR | 216.66 | 15.54 | 52.52 | 80
2335 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum formal order for the work of Construction of boundary wall at Bistupur H/W Site PH No-1 ,TW No-1 site under Augmentation Bistupur piped W/s Scheme under DWSD ,PHE Dte | 334/DWSD | 20/02/2023 | 20 | M/S SHYAM KANTA GHOSH | 27.51 | 0 | 0 | 0
2336 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Balance work for installation of solar pumping machineries including solar pannel and other allied works for 6 Nos ICDS/AWC/School at Labnapara Bouripara,Pratabpur ICDS ,Jamgora Nichupara Bagdipara,Pratabpur Bus stands and pangar FP school ICDS and Kailashpur 52 ICDS under providng running water supply to ICDS/School ,HCF and other Public Ins of Kanksa and Durgapur-Faridpur Block under Retrofitting of Jemua Piped W/S Scheme. | 1059/DWSD | 12/07/2023 | 30 | JOY GURU ENTERPRISE | 19.4 | 0 | 0 | 0
2337 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum formal order for the work of Creating a separate zone for PATHANPARA and Bagdipara of Kanksa (Zone-II/Part-C) with construction of Pump house /Chlorine room Sinking of 150 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Paragraph Mouza under Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme under DWSD, PHE Dte | 1139/DWSD | 20/07/2023 | 45 | JOY GURU ENTERPRISE | 95.5 | 0 | 0 | 0
2338 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Balance work for laying and alinging of DI K9 rising main pipe line supplying DI specials valves andallied works under command area of Bistupur piped W/s Scheme under DWSD ,PHE Dte | 720/DWSD | 11/05/2023 | 30 | MAK CONSTRUCTION CO. | 21.57 | 19.05 | 100 | 100
2339 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum formal order for the work of 1(One) No PWD road crossing at Bistupur under command area of Bistupur distribution main by modern trenches less technology through JACK Pushing method Note- 46 and node point 64,65 under Augmentation of Bistupur piped W/s Scheme under DWSD ,PHE Dte (Part-C) | 1282/DWSD | 07/08/2023 | 15 | MRITYUNJOY MUKHERJEE AND CO | 10.92 | 10.92 | 100 | 100
2340 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum formal order for the work of Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block under Augmentation of Bistupur piped W/s Scheme (Part-A & B) | 1284/DWSD | 07/08/2023 | 15 | AHS R INFRA PRIVATE LIMITED | 9.08 | 9.04 | 100 | 100
2341 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | 1(One) No PWD road crossing at Bistupur under command area of Bistupur distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Augmentation of Bistupur piped W/s Scheme under DWSD ,PHE Dte (Part-B) | 1285/DWSD | 07/08/2023 | 15 | MACHINO TECHNO | 10.92 | 10.92 | 100 | 100
2342 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | 1(One) No PWD road crossing at Bistupur under command area of Bistupur distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Augmentation of Bistupur piped W/s Scheme under DWSD ,PHE Dte (Part-A) | 1294/DWSD | 07/08/2023 | 15 | MRITYUNJOY MUKHERJEE AND CO | 10.91 | 10.91 | 100 | 100
2343 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum formal order for the work for installation and fabrication of MS structural work and solar panel at Biharpur and Babnabera FP school under Augmentation of Bistupur piped W/s Scheme under DWSD, PHE Dte | 1454/DWSD | 25/08/2023 | 15 | M/S MONDAL ENTERPRISE | 5.35 | 5.35 | 100 | 100
2344 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Road restoration with demand of fund for different road stretches within Bistupur under Augmentation of Bistupur piped W/s Scheme under Durgapur W/S Division, PHE Dte | BP-2023-24-114 | 28/07/2023 | 0 | EXECUTIVE ENGINEER , ASANSOL HIGHWAY DIVISION, PWD ROADS | 28.83 | 0 | 0 | 0
2345 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Additional work of supplying and laying of different dia HDPE distribution pipe line and allied works under command area of Augmentation of Bistupur piped W/S scheme under DWSD,PHE Dte (SM/08877) | 1079/DWSD | 12/07/2023 | 30 | MRITYUNJOY MUKHERJEE AND CO | 9.9 | 9.75 | 98.51 | 99
2346 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Additional work of supplying and laying of different dia HDPE distribution pipe line and allied works under command area of Augmentation of Bistupur piped W/S scheme under DWSD,PHE Dte (SM/08877) (Part-B) | 1078/DWSD | 12/07/2023 | 20 | MRITYUNJOY MUKHERJEE AND CO | 9.91 | 9.86 | 99.45 | 99
2347 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Additional works for supplying laying of HDPE pipe line including MS pipe lying and fabricating and other allied works at Bistupur under Augmentation of Bistupur piped W/s Scheme under DWSD,PHEDte . | 1453/DWSD | 25/08/2023 | 25 | MRITYUNJOY MUKHERJEE AND CO | 18.95 | 18.93 | 99.89 | 100
2348 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Balance work of Laying distribution system within distribution network for Rangamati of Augmentation of Ground Water Based Water Supply Scheme for Bistupur under Division-I PHE Dte. | 1645/RCD-I | 04/07/2024 | 45 | BASANTI TRADERS | 18.35 | 4.71 | 25.67 | 50
2349 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum Work Order for Construction Boundary Wall at Bistupur H/W Site Pump House no 1 Tube well No. 1 under Augmentation of Bistupur Water Supply Scheme under RCFA Division-I PHE Dte. | 3104/RCD-I | 13/12/2024 | 60 | RANA ENTERPRISE | 15.43 | 0 | 0 | 0
2350 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Formal order for the work of Supplying, laying & aligning of UPVC distribution pipe line (Distribution system Part-A) and allied works including functional house holds tap connection (FHTC) and connection providing to Akandara(JL No-47) ,Molandighi(JL No-48),Kandarakona (JL_51),Rakhitpur(JL-42,Chua(JL-43),Bhagaabanpur(JL-45),Hariki(JL No-50) Mouzas under command area of Bistupur piped W/s Scheme under DWSD,PHE Dte (SL-01) | 149/DWSD | 07/02/2022 | 65 | MACHINO TECHNO | 377.24 | 133.19 | 100 | 100
2351 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Continuation order for the work of Providing FHTC in connection with JJM for Gourbazar-Ichhapur W/s Scheme mouza-Patsaora(JL-53) Part-A block-Durgapur-Faridpur block, Dist.- Paschim Bardhaman under DWSD, PHE Dte | 1596/DWSD | 08/11/2021 | 10 | SHWET BARANI | 4.52 | 4.46 | 100 | 100
2352 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Continuation order for the work of additional number of FHTC in connection with JJM Ichhapur(Mouza-91) with extension of branch pipe line of command area of Gourbazar-Ichhapur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte | 1632/DWSD | 18/11/2021 | 15 | SHWET BARANI | 3.99 | 3.99 | 100 | 100
2353 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Continuation order for the work of additional number of FHTC in connection with JJM Ichhapur(Mouza-91) with extension of branch pipe line of command area of Gourbazar-Ichhapur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte | 179/DWSD | 11/02/2022 | 15 | SHWET BARANI | 3.99 | 3.99 | 100 | 100
2354 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Water supply arrangement for guard shed with solar power connection to provide water supply block -Kanksa under Augmentation of Bistupur Piped W/s scheme under DWSD,PHE Dte | 1290/DWSD | 07/08/2023 | 20 | SUNDAR CONSTRUCTION | 5.95 | 5.95 | 100 | 100
2355 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Balance work of providing water supply to Molandighi Junior Grills H.S. Molandighi Adivasi para SSK Arraha library and Bistupur brahmin para ICDS for providing Water supply to school under Durgapur-Faridpur/Kanksa Block under DWSD, PHE Dte | 1297/DWSD | 07/08/2023 | 15 | MUKHERJEE ENTERPRISE | 3.94 | 3.94 | 100 | 100
2356 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum formal order for the work of Sinking of 1 No tube well 250 mm X 150 mm tube well of 210 mtrs depth by Direct rotary rig method using PVC pipe and prepacked resin bonded gravel filter at Tilackchandrapur barobandh Adibasipara,Block-Kanksa under Augmentation of Bistupur piped W/s Scheme under DWD ,PHE Dte | 1303/DWSD | 07/08/2023 | 30 | MONDAL PRECISION PVT LTD | 10.8 | 10.71 | 100 | 100
2357 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum formal order for the work of renovation and modification of administrative office at PHE complex Nababhat (2nd Floor) in connection with Augmentation of Bistupur PWSS under DWSD,PHE Dte. | 1510/DWSD | 07/09/2023 | 25 | SANDIPAN SENGUPTA | 14.99 | 13.91 | 100 | 80
2358 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at Kanksa Zone II/Part B under Augmentation of Bistupur Piped W/S Scheme. | 1292/DWSD | 07/08/2023 | 45 | PRAKRITI CONSTRUCTION | 6.02 | 6.02 | 100 | 100
2359 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Formal work order for creating separate zone for Amlajora, supplying, laying of HDPE distribution pipeline and other allied works at Sarpi, Repairing of existing cement concrete road restoration and other allied works (Part- A & B), construction of 5.40 X 3.6 meter switch room including additional concreting of exition dismantled road after extension of pipeline and retrofitting of existing distribution system under RBT Sarpi PWSS, Augmentation of Gopalpur & Bistupur PWSS and Amlajora PWSS under RCFA Division-I PHE Dte. | 548/RCD-I | 20/02/2024 | 599 | HIRANMAY GHOSH | 200.38 | 59.65 | 29.77 | 40
2360 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Construction of Separate Zone at Rakshitpur with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | 2627/RCD-I | 14/11/2024 | 352 | MACHINO TECHNO | 70.46 | 0 | 0 | 20
2361 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Creating separate zone with pipe & additional FHTC including Water sources at Chua Adhibasipara under Augmentation of Bistupur Water Supply Scheme under RCFA Division-I PHE Dte. | 2639/RCD-I | 14/11/2024 | 352 | MRITYUNJOY MUKHERJEE & CO. | 20.41 | 2.35 | 11.53 | 50
2362 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Formal Work Order for Construction of 450 cum OHR, Laying, Aligning of DI (K9) Rising main (22 km) Pipe line and interconnection between rising main with OHR 2 nos House at Madhaiganj and Bhaburia H/W site and other allied works of RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC under Augmentation of Bistupur PWSS in Durgapur-Faridpur Block, Dist-Paschim Bardhaman under Durgapur W/S Division PHE Dte. | 126_RCD_I | 16/01/2024 | 834 | GITA CONSTRUCTION | 305.57 | 124.71 | 40.81 | 100
2363 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Construction of Separate Zone at Pathardiha with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | 3097/RCD-I | 13/12/2024 | 313 | T M CONCRETE CREATION PVT.LTD | 45.89 | 0 | 0 | 40
2364 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Construction of Separate Zone at Keshabpur with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | 318/RCD-I | 12/02/2025 | 262 | MRITYUNJOY MUKHERJEE & CO. | 22.9 | 0 | 0 | 80
2365 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Additional work of Supplying, laying and aligning of HDPE distribution pipe line / rising main & allied works at Bistupur Head Works Site and Saraswatingunj command area of Bistupr PWSS under RCFA Division-I PHE Dte. | 1468/RCD-I | 15/05/2025 | 170 | MRITYUNJOY MUKHERJEE & CO. | 79.35 | 0 | 0 | 70
2366 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Additional work of supplying laying and aligning of HDPE distribution pipe line & allied works including Function House Hold Tap Connection (FHTC) and re concoction at Ghatakdanga, Akandara and Saraswatigunj under command area of Bistupur under Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | 1488/RCD-I | 15/05/2025 | 170 | MACHINO TECHNO | 44.86 | 0 | 0 | 50
2367 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Additional 1 no sinking of 300 x 200 mm dia& distribution pipe line with interconnection for GopalpurNamoparaAdibasipara at ChatallidangaGosaidanga, Dangapara, Dhoadanga for Augmentation of Ground Water Based Water Supply Scheme for Bistupur under RCFA Division-I PHE Dte. | 1478/RCD-I | 15/05/2025 | 60 | RANJIB GHATAK | 73.79 | 0 | 0 | 0
2368 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum formal order for the work of Balance work of providing FHTC in connection with JJM for Kanksa (Zone-II) Part-B for Augmentation of BISTUPUR W/S Scheme (JJM) under DWSD,PHE Dte. | 1563/DWSD | 20/09/2023 | 681 | MD AAMIR KHAN | 30.61 | 0 | 0 | 100
2369 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Construction of Separate Zone at Kuldiha with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | 2551/RCD-I | 28/10/2024 | 240 | TARA CONSTRUCTION | 50.54 | 0 | 0 | 25
2370 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum Work Order for Construction of CWR (200 cum capacity) and allied work at Madhaiganj OHR site under Augmentation of Ground Water Based Water Supply Scheme for Bistupur under RCFA Division-I PHE Dte | 1538/RCD-I | 19/06/2024 | 286 | B.T.M. CONCERN | 37.18 | 0 | 0 | 100
2371 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Additional work for separate distribution pipe line with inter connection for Gopalpur Left including Paschim Para Bauripara General para of Gopalpur W/S Scheme for Augmentation of ground water based supply scheme for Bistupur under RCFA Division-I PHE Dte. | 1516/RCD-I | 20/05/2025 | 60 | UNITED CONSTRUCTION | 70.8 | 0 | 0 | 100
2372 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Separate distribution pipe with interconnection for Gopalpur Bazar (Left Side) of Gopalpur W/S Scheme for Augmentation of ground water based water supply scheme for Bistupur under RCFA Division-I PHE Dte. | 1363-RCD-I | 15/05/2025 | 78 | DAWN CONSTRUCTION | 40.06 | 0 | 0 | 100
2373 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Additional work for separate distribution pipe line with inter connection for Gopalpur Right including Paschim Para Bauripara General para of Gopalpur W/S Scheme for Augmentation of ground water based water supply scheme of Bistupur under RCFA Division-I PHE Dte. | 1362-RCD-I | 15/05/2025 | 60 | UNITED CONSTRUCTION | 61.57 | 0 | 0 | 100
2374 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Additional work for laying of pipe line (Left out) with HDPE pipe including FHTC within command area of Kanksa Zone-I PWSS with reconnection of existing FHTC and other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | 445/RCD-I | 12/03/2025 | 60 | MAK CONSTRUCTION CO | 78.15 | 0 | 0 | 72
2375 | PASCHIM BARDHAMAN | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN , SM/18469 | Augmentation | Acceptance cum work order for Crossing 200 mm dia MS pipes under Highway by Jack Pushing Technology at different spots pushing different dia MS pipe at Bistupur under Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | 1487/RCD-I | 15/05/2025 | 60 | MRITYUNJOY MUKHERJEE & CO. | 67.58 | 0 | 0 | 100
2376 | PASCHIM BARDHAMAN | RCFA Division -I | Providing service by assigning resource person for a period of 3 month supervision of process of preparation for NABL recognition for chemical testing of potable water of sub-District level water quality testing laboratory including supply, installation o , SM/16428 | Support-WQMSP | Chemicals, consumbles for the Laudoha sub District water Testing laboratory, Gopalpur Sub District water Testing Laboratory & Paschim Bardhaman District water Tasting Laboratory under RCFA Division-I PHE Dte. | Camp-02/Laboratory/AE-II/ | 15/02/2024 | 7 | M/S. BANDANA ENTERPRISE | 2.89 | 2.89 | 100 | 100
2377 | PASCHIM BARDHAMAN | RCFA Division -I | Providing service by assigning resource person for a period of 3 month supervision of process of preparation for NABL recognition for chemical testing of potable water of sub-District level water quality testing laboratory including supply, installation o , SM/16428 | Support-WQMSP | Chemical and materials for Paschim Bardhaman Water Testing district Laboratory under RCFA Division-I PHE Dte. | 3764/RCD-I | 31/12/2023 | 7 | M/S. BANDANA ENTERPRISE | 0.97 | 0.96 | 100 | 100
2378 | PASCHIM BARDHAMAN | RCFA Division -I | Providing service by assigning resource person for a period of 3 month supervision of process of preparation for NABL recognition for chemical testing of potable water of sub-District level water quality testing laboratory including supply, installation o , SM/16428 | Support-WQMSP | Chemical and materials for Paschim Bardhaman Water Testing district Laboratoty under RCFA Division-I PHE Dte. | 3763/RCD-I | 31/12/2023 | 7 | BABA LOKNATH ENTERPRISE | 0.9 | 0.9 | 100 | 100
2379 | PASCHIM BARDHAMAN | RCFA Division -I | Supply, delivery and installation of Desktop computers and other allied accessories (through GeM portal) under Central Circle, PHE Directorate. , SM/13406 | Support-MIS | HP INTEL CORE i5 ALL IN ONE PC WITH 23.8 INCH DISPLAY WINDOW PROFESSIONAL |  | 24/05/2023 | 0 | EASY DAY ENTERPRISE | 0.78 | 0 | 0 | 0
2380 | PASCHIM BARDHAMAN | RCFA Division -I | Supply, delivery and installation of Desktop computers and other allied accessories (through GeM portal) under Central Circle, PHE Directorate. , SM/13406 | Support-MIS | Brother Laser Mono Computer Printer for A4 paper size | 78/23-24 | 07/06/2023 | 0 | IONET | 0.31 | 0 | 0 | 0
2381 | PASCHIM BARDHAMAN | RCFA Division -I | Supply, delivery and installation of Desktop computers and other allied accessories (through GeM portal) under Central Circle, PHE Directorate. , SM/13406 | Support-MIS | Brother Multifunction Machines Mfm on site OEM Warranty 3 year | 78/23-24 | 07/06/2023 | 0 | IONET | 0.25 | 0 | 0 | 0
2382 | PASCHIM BARDHAMAN | RCFA Division -I | Supply, delivery and installation of Desktop computers and other allied accessories (through GeM portal) under Central Circle, PHE Directorate. , SM/13406 | Support-MIS | Supply of microtek line interactive UPS with AVR of Rating 0.65 KVA with Warranty of 3 years | 78/23-24 | 07/06/2023 | 0 | IONET | 0.16 | 0 | 0 | 0
2383 | PASCHIM BARDHAMAN | RCFA Division -I | Supply, delivery and installation of Desktop computers and other allied accessories (through GeM portal) under Central Circle, PHE Directorate. , SM/13406 | Support-MIS | EPSON Multifunction Machines Mfm. on site OEM Warranty 1 year |  | 24/05/2023 | 0 | IONET | 0.25 | 0 | 0 | 0
2384 | PASCHIM BARDHAMAN | RCFA Division -I | Supply, delivery and installation of Desktop computers and other allied accessories (through GeM portal) under Central Circle, PHE Directorate. , SM/13406 | Support-MIS | Supply of 6 nos battery (Microtech) |  | 21/07/2023 | 0 | IONET | 0.23 | 0 | 0 | 0
2385 | PASCHIM BARDHAMAN | RCFA Division -I | Supply, delivery and installation of Desktop computers and other allied accessories (through GeM portal) under Central Circle, PHE Directorate. , SM/13406 | Support-MIS | Formujet HP 88A Black Original LaserJet Tonner Cartridge Class Compatible | 78/23-24 | 07/06/2023 | 0 | IONET | 0.02 | 0 | 0 | 0
2386 | PASCHIM BARDHAMAN | RCFA Division -I | Supply, delivery and installation of Desktop computers and other allied accessories (through GeM portal) under Central Circle, PHE Directorate. , SM/13406 | Support-MIS | HP Intel Core i5 All in one PC with 23.8 inch Display / windows 11 professional | 78/23-24 | 07/06/2023 | 0 | IONET | 1.6 | 0 | 0 | 0
2387 | PASCHIM BARDHAMAN | RCFA Division -I | Supply, delivery and installation of Desktop computers and other allied accessories (through GeM portal) under Central Circle, PHE Directorate. , SM/13406 | Support-MIS | HP Intel Core i5 12400 8 GB/1000 GB HDD windows 11 professional |  | 24/05/2023 | 0 | IONET | 4.2 | 0 | 0 | 0
2388 | PASCHIM BARDHAMAN | RCFA Division -I | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission under RCFA Division-I PHE Dte. District - Paschim Bardhaman , SM/13358 | Support-WQMSP | Continuation work order for Engaging 1 (One) no. Chemist / Bacteriologist, 1 no. Laboratory Assistant & 1 no.Laboratory Attandant for testing of water from different water supply schemes, makig report, communicating with the facilitators of different Gram Panchayet etc. at Water Testing laboratory under RCFA Division-I, P.H.E. Dte. (01.07.2022 to 31.08.2022) | 1530/RCD-I | 30/06/2022 | 60 | MUKUL HAZARI | 0.71 | 0.71 | 100 | 0
2389 | PASCHIM BARDHAMAN | RCFA Division -I | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission under RCFA Division-I PHE Dte. District - Paschim Bardhaman , SM/13358 | Support-WQMSP | Acceptance cum work order for Chemical and materials for Paschim Bardhaman Water Testing District Laboratory under RCFA Division-I PHE Dte. | 3547/RCD-I | 07/12/2023 | 7 | MUKUL HAZARI | 3.12 | 3.12 | 100 | 100
2390 | PASCHIM BARDHAMAN | RCFA Division -I | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission under RCFA Division-I PHE Dte. District - Paschim Bardhaman , SM/13358 | Support-WQMSP | Acceptance cum work order for engaging 1(one)no. chemist(one)no Bacteriologist ,1 no laboratory Assistant & 1(one) of Laboratory Attendant for testing of water from different water supply schemes ,making report communicating with the facilitators of different gram panchyat etc at Paschim Bardhaman water Testing District laboratory under RCFA Div-I ,PHE Dte | 383_RCD-I | 30/01/2023 | 365 | M/S. BANDANA ENTERPRISE | 1.61 | 1.61 | 100 | 100
2391 | PASCHIM BARDHAMAN | Durgapur W/S Division | Supply and Delivery of Chemicals, Consumbles, Glassware etc. required for smooth running of Laudoha Sub-District laboratory. , SM/06638 | Support-WQMSP | Supply ,delivery of different type of laboratory chemical with regent for loudoha sub-district testing laboratory under DWSD, PHE Dte(SL-01) | 1012/DWSD | 08/10/2020 | 15 | BABA LOKNATH ENTERPRISE | 1.96 | 3.93 | 100 | 0
2392 | PASCHIM BARDHAMAN | Durgapur W/S Division | Supply and Delivery of Chemicals, Consumbles, Glassware etc. required for smooth running of Laudoha Sub-District laboratory. , SM/06638 | Support-WQMSP | Supply ,delivery of different type of laboratory chemical with regent for Gopalpur sub-district testing laboratory under DWSD, PHE Dte(SL-02) | 1013/DWSD | 08/10/2020 | 15 | BABA LOKNATH ENTERPRISE | 1.81 | 3.62 | 100 | 0
2393 | PASCHIM BARDHAMAN | RCFA Division -I | Supply delivery and installation of desktop computers and other allied accessories (through GeM portal) under RCFA Division-I PHE Dte. , SM/10680 | Support-MIS | Supply of Intel core i5 10500 8 GB / 1000 GB HDD /Windows 11 Professional | GEMC-511687747522764 | 22/11/2022 | 30 | SUN SYSTEMS | 3.56 | 3.56 | 100 | 0
2394 | PASCHIM BARDHAMAN | RCFA Division -I | Supply delivery and installation of desktop computers and other allied accessories (through GeM portal) under RCFA Division-I PHE Dte. , SM/10680 | Support-MIS | Supply HP LASER MONO COMPUTER PRINTER FOR A4 PAPER UNDER RCFA DIVISION -I PHE DTE | GEMC-511687714891660 | 22/11/2022 | 30 | DIGICOM INFOTECH | 0.43 | 0.43 | 100 | 0
2395 | PASCHIM BARDHAMAN | RCFA Division -I | Supply delivery and installation of desktop computers and other allied accessories (through GeM portal) under RCFA Division-I PHE Dte. , SM/10680 | Support-MIS | BPE Line interactive UPS with AVR of rrating 1.0 KVA with warranty of 3 years | GEMC-511687748612059 | 22/11/2022 | 30 | STIMULUS INFOSYSTEMS PRIVATE LIMITED | 0.27 | 0.27 | 100 | 0
2396 | PASCHIM BARDHAMAN | RCFA Division -I | Supply delivery and installation of desktop computers and other allied accessories (through GeM portal) under RCFA Division-I PHE Dte. , SM/10680 | Support-MIS | Supply and delivery of Canon Multifunction Machine at Office of the Executive Engineer, RCFA Divisoin-I, PHE Dte | GEM/2022/B/2737175 | 01/12/2022 | 45 | AGEIS SOLUTION | 2.66 | 2.66 | 100 | 0
2397 | PASCHIM BARDHAMAN | RCFA Division -I | Supply delivery and installation of desktop computers and other allied accessories (through GeM portal) under RCFA Division-I PHE Dte. , SM/10680 | Support-MIS | Supply of Computers | 152/23-24 | 25/07/2023 | 0 | IONET | 4.04 | 0 | 0 | 0
2398 | PASCHIM BARDHAMAN | RCFA Division -I | Operational Charges of PHED Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission under RCFA Division-I PHE Dte. , SM/19257 | Support-WQMSP | Acceptance cum work order for Work Engaging expert 1(one) no Chemist,1(One) no Bacteriologist and 1(One)no Lab Assistant for the testing of water from different PWSS making different types of Testing Report,Communicated with the facilitator of different Gram Panchayat under Kanksa Block of Sub District NABL laboratory under RCFA Div-I PHE Dte.(365 days) (01.11.2024 to 31.10.2025) | 2562/RCD-I | 30/10/2024 | 365 | BABA LOKNATH ENTERPRISE | 7.24 | 3.5 | 48.39 | 100
2399 | PASCHIM BARDHAMAN | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Paschim Barddhaman District. , SM/08984 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Paschim Bardhaman | 5774/RS | 09/11/2022 | 365 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 172.07 | 170.6 | 100 | 74
2400 | PASCHIM BARDHAMAN | RCFA Division -I | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Paschim Barddhaman District. , SM/08984 | Support-M&E | Margdarshika colour print with spiral binding (62 nos) under RCFA Division-I PHE Dte. | 2291/RCD-I | 20/07/2023 | 2 | MUKHERJEE TRADERS | 0.68 | 0 | 0 | 100
2401 | PASCHIM BARDHAMAN | Durgapur W/S Division | Operation charges of 2 Two) Nos Sub-District Laboratories under Durgapur Water Supply Division,PHE Dte ,Dist-Paschim Bardhaman related to Water quality monitoring and surveillance programme under Jal jeevan Mission. , SM/13908 | Support-WQMSP | Continuation order for the work of Engaging 1(One) No Chemist /Bacteriologist and 1 No Lab Assistant for the testing of water from different W/s Scheme making report, communicating with the facilitators of different gram panchayats etc at Gopalpur Lab, PHE Dte (w.e.f 01.02.2023 to 31/05/2023) | 156/DWSD | 31/01/2023 | 120 | RANAJOY ENTERPRISE | 1.09 | 0 | 0 | 100
2402 | PASCHIM BARDHAMAN | RCFA Division -I | DRINKING WATER SAMPLES COLLECTION, TESTING OF DRINKING WATER SAMPLES THROUGH FTK & UPLOADING CHARGES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JJM FROM FEB 22 TO MAR 23 , SM/11817 | Support-WQMSP | Drinking water samples collection testing of drinking water samples through FTK and uploading charges related to water quality monitoring and surveillance under JJM | 15182-15204/MC/LABS/00000 | 18/07/2022 | 365 | CMOH | 46.12 | 0 | 0 | 0
2403 | PASCHIM BARDHAMAN | RCFA Division -I | DRINKING WATER SAMPLES COLLECTION, TESTING OF DRINKING WATER SAMPLES THROUGH FTK & UPLOADING CHARGES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JJM FROM FEB 22 TO MAR 23 , SM/11817 | Support-WQMSP | Drinking water samples collection testing of drinking water samples through FTK and uploading charges related to water quality monitoring and surveillance under JJM | 391/22-23 | 25/08/2022 | 0 | CMOH | 13 | 0 | 0 | 0
2404 | PASCHIM BARDHAMAN | Asansol Mechanical | Procurement of Computer and Peripherals for the office use in Asansol Mechanical Division, Kalyaneswari Water Testing Laboratory, P.H.E. Dte., District:- Paschim Bardhaman. , SM/17412 | Support-MIS | Procurement of 02 Nos Printer for The Office of the Executive Engineer , Asansol Mechanical Division , PHE Dte. | BP-2024-25-10 | 25/04/2024 | 0 | IONET | 3.2 | 0 | 0 | 0
2405 | PASCHIM BARDHAMAN | Asansol Mechanical | Procurement of Computer and Peripherals for the office use in Asansol Mechanical Division, Kalyaneswari Water Testing Laboratory, P.H.E. Dte., District:- Paschim Bardhaman. , SM/17412 | Support-MIS | Procurement of Computer and Peripherals for the office use in Asansol Mechanical Division, Kalyaneswari Water Testing Laboratory, P.H.E. Dte., District:- Paschim Bardhaman. | BP-2023-24-86 | 18/03/2024 | 0 | IONET | 8.29 | 0 | 0 | 0
Total | [9 empty] | 96350.31 | 52369.35 | 54.35