## Work Order Tracking (Rs. in Lak
Work Order Tracking (Rs. in Lakh)
SL. No. | Division | Scheme | Scheme Sm Code | Sanctioned Cost | No. of Work Orders | Work Value | Payment
1 | Birbhum Division | Retrofitting works of Kot Water Supply Scheme under Mayureswar-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07154 | 99.92 | 4 | 85.6 | 83.72
2 | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | 97.37 | 10 | 50.21 | 24.56
3 | Birbhum Division | Retrofitting works of Harisara under Nalhati - I Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | SM/06951 | 72.24 | 4 | 107.05 | 36.12
4 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | 99.59 | 24 | 100.81 | 69.64
5 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. | SM/09491 | 149.02 | 4 | 118.93 | 105.48
6 | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07153 | 99.72 | 8 | 89.63 | 76.2
7 | Birbhum Division | Augmentation of Nagari Piped Water Supply Scheme | SM/10312 | 272.8 | 6 | 236.09 | 95.18
8 | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | 921.39 | 12 | 796.28 | 438.68
9 | Birbhum Division | Ekpara Piped Water Supply Scheme. | SM/12690 | 289.55 | 4 | 270.53 | 0
10 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Aligarh Water supply scheme (Phase-III) | SM/12637 | 34.45 | 1 | 32.89 | 0
11 | Birbhum Division | Deoash and Adjoining Mouzas PWSS | SM/12670 | 643 | 3 | 597.79 | 163.26
12 | Birbhum Division | Lakshmi Narayanpur and Adjoining Mouzas PWSS | SM/12696 | 846.97 | 4 | 716.24 | 0
13 | Birbhum Division | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | 386.92 | 3 | 342.85 | 17.37
14 | Birbhum Division | ANDHARGRAM PIPED WATER SUPPLY SCHEME. | SM/12676 | 300.02 | 3 | 300.48 | 144.18
15 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR KATUNIA AND OTHER 2 NOS. MOUZAS UNDER MD. BAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11909 | 102 | 1 | 69.56 | 47.87
16 | Birbhum Division | Monoharpur Piped Water Supply Scheme. | SM/13511 | 391.63 | 3 | 391.68 | 0
17 | Birbhum Division | Sadanandapur piped water supply scheme. | SM/13648 | 448.06 | 3 | 382.9 | 80.93
18 | Birbhum Division | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | 477.52 | 13 | 516.31 | 105.75
19 | Birbhum Division | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | 900.37 | 5 | 573.98 | 171.1
20 | Birbhum Division | BANSANKHA PIPED WATER SUPPLY SCHEME. | SM/12889 | 386.07 | 3 | 397.06 | 0
21 | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | 600.79 | 4 | 394.58 | 2.28
22 | Birbhum Division | BENGA CHATRA PIPED WATER SUPPLY SCHEME | SM/13408 | 716.72 | 3 | 100.22 | 4.16
23 | Birbhum Division | Kukutia piped water supply scheme. | SM/13601 | 549.6 | 2 | 120.71 | 0
24 | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | 911.87 | 2 | 77.31 | 0
25 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Baliharpur(Phase-I) PWSS | SM/07648 | 99.48 | 7 | 119.02 | 75.48
26 | Birbhum Division | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division | SM/13982 | 698.94 | 5 | 465.89 | 4.06
27 | Birbhum Division | Bagahola Piped Water Supply Scheme | SM/14084 | 389.21 | 3 | 305.8 | 0
28 | Birbhum Division | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14125 | 1110.9 | 5 | 727.85 | 5.91
29 | Birbhum Division | Patalpur Piped Water Supply Scheme | SM/14955 | 209.38 | 3 | 148.31 | 0
30 | Birbhum Division | Demurtita Piped Water Supply Scheme. | SM/14981 | 279.34 | 3 | 221.85 | 0
31 | Birbhum Division | BALIARA PIPED WATER SUPPLY SCHEME | SM/14847 | 709.05 | 4 | 468.27 | 2.09
32 | Birbhum Division | Palashbuni Piped Water Supply Scheme (Khoyrasole Block) | SM/14851 | 475.95 | 3 | 364.73 | 10.92
33 | Birbhum Division | Haripur Piped Water Supply Scheme | SM/14853 | 934.11 | 4 | 734.1 | 0
34 | Birbhum Division | Chandrapur Piped Water Supply Scheme | SM/14893 | 653.22 | 3 | 578.11 | 48.84
35 | Birbhum Division | PARULIA PIPED WATER SUPPLY SCHEME. | SM/14538 | 1104.48 | 3 | 1002.78 | 0
36 | Birbhum Division | Dhamara Piped Water Supply Scheme. | SM/14898 | 471.2 | 3 | 378.52 | 83.37
37 | Birbhum Division | SHEKHAMPUR PIPED WATER SUPPLY SCHEME | SM/14956 | 744.62 | 2 | 107.65 | 0
38 | Birbhum Division | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. | SM/14960 | 715.34 | 3 | 278.42 | 0
39 | Birbhum Division | FARIDPUR PIPED WATER SUPPLY SCHEME | SM/14971 | 725.24 | 2 | 151.05 | 0
40 | Birbhum Division | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/14208 | 407.65 | 3 | 39.52 | 2.38
41 | Birbhum Division | MASTALI PIPED WATER SUPPLY SCHEME | SM/16275 | 486.59 | 2 | 387.99 | 0
42 | Birbhum Division | Budhigram Piped Water Supply Scheme | SM/16762 | 763.84 | 4 | 74.13 | 15.21
43 | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | 1188.4 | 4 | 131.76 | 0
44 | Birbhum Division | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. | SM/18787 | 880.39 | 8 | 600.6 | 0
45 | Birbhum Division | Chormara Piped Water Supply Scheme. | SM/14030 | 402.81 | 3 | 348.5 | 0
46 | Birbhum Division | Bahadurpur Piped Water Supply Scheme. | SM/12681 | 749.3 | 3 | 431.13 | 0
47 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ALALCHAK AND OTHER 28 NOS. MOUZAS UNDER DUBRAJPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/12074 | 998 | 1 | 944 | 78.49
48 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Aligarh PWSS (Phase-I) | SM/06733 | 99.93 | 3 | 74.52 | 77.83
49 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | 896.76 | 10 | 426.18 | 0
50 | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme | SM/10313 | 766.3 | 8 | 654.81 | 419.67
51 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | 771.82 | 45 | 457.88 | 301.99
52 | Birbhum Division | PAKURIA PIPED WATER SUPPLY SCHEME. | SM/12596 | 578.57 | 3 | 547.02 | 16.67
53 | Birbhum Division | Kamarkhul Piped Water Supply Scheme. | SM/12693 | 766.32 | 3 | 400.7 | 6.45
54 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Kot Phase-II Water Supply Scheme. | SM/12661 | 43.64 | 1 | 24.29 | 0
55 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Basudebpur Phase-II Water Supply Scheme. | SM/12662 | 42.93 | 1 | 7.57 | 0
56 | Birbhum Division | Chanchali piped water supply scheme. | SM/12683 | 1034.33 | 3 | 788.83 | 0
57 | Birbhum Division | Paikpara Piped Water Supply Scheme. | SM/12669 | 355.1 | 3 | 334.61 | 20.63
58 | Birbhum Division | Asenga Piped Water Supply Scheme. | SM/12680 | 617.4 | 3 | 534.1 | 90.39
59 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR SIMJURI AND OTHER 19 NOS. MOUZAS UNDER KHOYRASOLE BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/12072 | 712 | 1 | 658 | 0
60 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR DHEKA AND OTHER 21 NOS. MOUZAS UNDER MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11910 | 840 | 1 | 783.35 | 0
61 | Birbhum Division | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division | SM/13630 | 903.87 | 5 | 685.47 | 15.45
62 | Birbhum Division | Paratpur Piped Water Supply Scheme. | SM/13474 | 806.88 | 4 | 664.23 | 0
63 | Birbhum Division | Kendangal Piped Water Supply Scheme. | SM/13642 | 620.79 | 3 | 603.54 | 0
64 | Birbhum Division | Sekupur piped water supply scheme. | SM/13650 | 349.5 | 2 | 37.14 | 0
65 | Birbhum Division | Purba Anantapur Piped Water Supply Scheme | SM/13715 | 586.12 | 5 | 366.78 | 59.66
66 | Birbhum Division | Paniara Piped Water Supply Scheme. | SM/12907 | 124.83 | 2 | 34.7 | 4.54
67 | Birbhum Division | Shankarpur Piped Water Scheme | SM/14082 | 717.8 | 6 | 569.64 | 10.7
68 | Birbhum Division | PURBA BANKATI PIPED WATER SUPPLY SCHEME. | SM/13470 | 178.79 | 3 | 179.81 | 53.26
69 | Birbhum Division | Charkalgram Piped Water Supply Scheme | SM/13481 | 953.48 | 2 | 92.13 | 0
70 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | 293.51 | 11 | 318.3 | 284.96
71 | Birbhum Division | Modapa Piped Water Supply Scheme. | SM/13517 | 346.07 | 3 | 307.95 | 7.6
72 | Birbhum Division | Palsa piped water supply scheme. | SM/12906 | 549.14 | 3 | 329.14 | 6.09
73 | Birbhum Division | Simgram Piped Water Supply Scheme. | SM/12908 | 125.88 | 3 | 105.82 | 0
74 | Birbhum Division | Naoadangal and Adjoining Mouzas PWSS | SM/12904 | 722.04 | 7 | 748.97 | 19.86
75 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Tarapith Phase-II Water Supply Scheme. | SM/13375 | 34.41 | 0 | 0 | 0
76 | Birbhum Division | Khamedda Piped Water Supply Scheme | SM/13980 | 737.11 | 5 | 407.79 | 23.52
77 | Birbhum Division | BHUBANESWAR PIPED WATER SUPPLY SCHEME | SM/13387 | 911.71 | 5 | 791.67 | 0
78 | Birbhum Division | Shitalgram Piped Water Supply Scheme | SM/14087 | 585.33 | 4 | 416.99 | 13.68
79 | Birbhum Division | RANIBAZAR PIPED WATER SUPPLY SCHEME | SM/14850 | 646 | 3 | 80.83 | 3.89
80 | Birbhum Division | Hazaripur Piped Water Supply Scheme | SM/14679 | 764.93 | 4 | 510.11 | 20.71
81 | Birbhum Division | Sekedda Piped Water Supply Scheme. | SM/14683 | 2443.77 | 4 | 666.52 | 0
82 | Birbhum Division | Ruppur and adjoining mouzas Piped Water Supply Scheme. | SM/14686 | 1387.78 | 4 | 1382.86 | 0
83 | Birbhum Division | Banior Piped Water Supply Scheme. | SM/14688 | 2842.94 | 4 | 2397.31 | 162.07
84 | Birbhum Division | Paduma Piped Water Supply Scheme. | SM/14544 | 1611.92 | 2 | 1039.11 | 0
85 | Birbhum Division | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | 326.46 | 5 | 225.03 | 127.36
86 | Birbhum Division | Majhkanda Piped Water Supply Scheme. | SM/14896 | 653.84 | 2 | 41.06 | 0
87 | Birbhum Division | DULA SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14746 | 999.21 | 2 | 112 | 0
88 | Birbhum Division | BHATRA PIPED WATER SUPPLY SCHEME | SM/14958 | 785.97 | 2 | 157.54 | 55.98
89 | Birbhum Division | Chora Piped Water Supply Scheme | SM/15523 | 248.08 | 4 | 179.24 | 0
90 | Birbhum Division | RANIPARA PIPED WATER SUPPLY SCHEME | SM/16276 | 540.82 | 1 | 85.44 | 0
91 | Birbhum Division | Nichinta Piped Water Supply Scheme (Khoyrasole Block) | SM/16271 | 145.99 | 3 | 138.12 | 0
92 | Birbhum Division | Shrirampur Piped Water Supply Scheme (Khoyrasole Block) | SM/16272 | 249.14 | 3 | 222.66 | 0
93 | Bolpur Mechanical Division | Solarisation for NET metering of different PWSS at different Blocks under Bolpur Mechanical Division,PHED | SM/16381 | 0 | 1 | 107.85 | 0
94 | Birbhum Division | Chhora Piped Water Supply Scheme. | SM/16761 | 497.37 | 2 | 41.23 | 0
95 | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07155 | 94.45 | 8 | 66.01 | 91.7
96 | Birbhum Division | Charicha Piped Water Supply Scheme. | SM/18512 | 1514.48 | 4 | 1341.72 | 0
97 | Birbhum Division | HATIKRA PIPED WATER SUPPLY SCHEME. | SM/12893 | 460.73 | 3 | 459.25 | 18.98
98 | Birbhum Division | Gulalgachi Piped Supply Scheme | SM/18419 | 1267.58 | 3 | 1176.97 | 0
99 | Birbhum Division | Sahapur Piped water Supply Scheme. | SM/13649 | 988.96 | 5 | 777.13 | 0
100 | Birbhum Division | Radipur Piped Water Supply Scheme. | SM/14027 | 519.73 | 2 | 40.68 | 0
101 | Birbhum Division | Kashtagara Piped Water Supply Scheme. | SM/18733 | 1262.41 | 4 | 76 | 0
102 | Birbhum Division | PAIKPARA WATER SUPPLY SCHEME. | SM/12836 | 924.31 | 3 | 496.19 | 61.58
103 | Birbhum Division | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area | SM/06945 | 98.81 | 5 | 78.43 | 66.49
104 | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | 99.28 | 12 | 86.52 | 87.57
105 | Birbhum Division | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | SM/06950 | 99.83 | 5 | 97.88 | 96.92
106 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Hazarpur PWSS(Phase-I) | SM/06739 | 96.06 | 2 | 85.79 | 85.25
107 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | 82.04 | 13 | 93.05 | 52.57
108 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08895 | 94.58 | 4 | 43.01 | 35.46
109 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09366 | 181.79 | 8 | 144.59 | 103.56
110 | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | 679.4 | 11 | 714.5 | 414.29
111 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum | SM/08171 | 97.14 | 6 | 83.57 | 17.12
112 | Birbhum Division | SAMSA PIPED WATER SUPPLY SCHEME. | SM/12597 | 552.71 | 3 | 556.28 | 21.5
113 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMDAHARA AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11902 | 754 | 1 | 700 | 0
114 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR SABASIDANGA AND OTHER 4 NOS. MOUZAS UNDER NALHATI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11904 | 189 | 1 | 135 | 0
115 | Birbhum Division | Madhura and Adjoining mouzas PWSS | SM/12671 | 780.79 | 3 | 608.41 | 1.74
116 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Haridaspur(Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | SM/12666 | 99.4 | 2 | 56.31 | 18.79
117 | Birbhum Division | Dumugram piped water supply scheme. | SM/12689 | 894.92 | 3 | 556.66 | 0
118 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ARAZI TAKIPUR AND OTHER 11 NOS. MOUZAS UNDER SURI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11900 | 448 | 1 | 394 | 57.22
119 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Kurumgram (Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | SM/12668 | 11.63 | 0 | 0 | 0
120 | Birbhum Division | Dakshin Madanpur Piped Water Supply Scheme. | SM/12687 | 473.11 | 2 | 86.85 | 0
121 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR UJALPUR AND OTHER 6 NOS. MOUZAS UNDER LABPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/12069 | 291 | 1 | 237 | 0
122 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BISERGHATA AND OTHER 23 NOS. MOUZAS UNDER BOLPUR SRINIKETAN BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/12070 | 901 | 1 | 847 | 0
123 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR UTTAR BHAGABATIPUR AND OTHER 8 NOS. MOUZAS UNDER MAYURESWAR-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/12071 | 343 | 1 | 289 | 0
124 | Birbhum Division | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13475 | 445.39 | 6 | 315.57 | 65.3
125 | Birbhum Division | Kayera Water Supply Scheme | SM/13641 | 488.23 | 4 | 433.52 | 0
126 | Birbhum Division | MATIKONA PIPED WATER SUPPLY SCHEME | SM/13643 | 860.82 | 4 | 702.22 | 0
127 | Birbhum Division | SHIRSHA PIPED WATER SUPPLY SCHEME | SM/13647 | 974.04 | 5 | 874.4 | 0
128 | Birbhum Division | Sandhyajol Piped Water Supply Scheme | SM/13981 | 775.21 | 3 | 94.59 | 2.29
129 | Birbhum Division | KASHERHAT PIPED WATER SUPPLY SCHEME. | SM/12903 | 578.88 | 3 | 559.89 | 9.98
130 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GOPALPUR AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/14037 | 831.2 | 1 | 777.2 | 0
131 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Sekhpur Phase-II Water Supply Scheme. | SM/13374 | 14.22 | 0 | 0 | 0
132 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR TALA AND OTHER 25 NOS. MOUZAS UNDER LABPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/14039 | 974.91 | 1 | 920.91 | 0
133 | Birbhum Division | Barua Gopalpur Piped Water Supply Scheme. | SM/14421 | 1288.16 | 3 | 982.94 | 0
134 | Birbhum Division | Kanduri Piped Water Supply Scheme. | SM/14824 | 543.12 | 2 | 37.12 | 0
135 | Birbhum Division | Bhadulia Piped Water Supply Scheme | SM/14674 | 474.51 | 3 | 362.5 | 17.86
136 | Birbhum Division | NAWADA PALANDI PIPED WATER SUPPLY SCHEME | SM/14682 | 1029.06 | 2 | 89.18 | 0
137 | Birbhum Division | PAPURI PIPED WATER SUPPLY SCHEME | SM/14691 | 889.54 | 2 | 101.91 | 0
138 | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | 271.5 | 6 | 176.28 | 24.24
139 | Birbhum Division | Bautia piped water supply scheme | SM/14536 | 1467.55 | 3 | 549.64 | 0
140 | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area | SM/06949 | 99.96 | 6 | 97.4 | 75.63
141 | Birbhum Division | Penchalia Piped Water Supply Scheme | SM/16282 | 389.54 | 3 | 320.41 | 0
142 | Birbhum Division | Dhitora Right side and adjoining mouzas piped water supply scheme. | SM/17633 | 445.95 | 3 | 253.59 | 69.7
143 | Birbhum Division | Chinpai Piped Water Supply Scheme. | SM/18462 | 1443.97 | 5 | 1093.29 | 75.06
144 | Birbhum Division | Masra Piped Water Supply Scheme. | SM/18463 | 1206.76 | 3 | 71.38 | 0
145 | Birbhum Division | Dadpur Piped Water Supply Scheme. | SM/12684 | 593.51 | 3 | 374.78 | 33.71
146 | Birbhum Division | BANGJITA PIPED WATER SUPPLY SCHEME. | SM/12829 | 489.13 | 3 | 565.03 | 2.71
147 | Birbhum Division | Ekura Piped Water Supply Scheme. | SM/13949 | 461.93 | 3 | 376.61 | 0
148 | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | SM/06948 | 99.22 | 11 | 142.26 | 87.09
149 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS | SM/06736 | 99.68 | 9 | 82.23 | 81.58
150 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | SM/06737 | 95.3 | 11 | 79.92 | 93.59
151 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area DERIAPUR WATER SUPPLY SCHEME of Sainthia Block under Birbhum Division, PHE Dte. | SM/08894 | 148.29 | 5 | 128.77 | 71.72
152 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | 259.6 | 13 | 170.85 | 126.86
153 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sekhpur PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09363 | 188.82 | 4 | 183.5 | 51.97
154 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Hajrapur PWSS within Dubrajpur Block District Birbhum under Birbhum Division, PHE Dte. | SM/09369 | 77.81 | 2 | 59.37 | 25.18
155 | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Panchra PWSS within Khoyrasole Block District Birbhum under Birbhum Division, PHE Dte. | SM/09490 | 299.8 | 2 | 94.75 | 0
156 | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | 1265.98 | 13 | 1517.96 | 725.17
157 | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | 6683.63 | 71 | 4497.35 | 3073.95
158 | Birbhum Division | Abhirampur and Adjoining Mouzas PWSS | SM/12536 | 377.57 | 3 | 373.25 | 16.55
159 | Birbhum Division | Gaganpur piped water supply scheme. | SM/12691 | 913.35 | 3 | 556.61 | 0
160 | Birbhum Division | Majhara piped water supply scheme | SM/12698 | 443.6 | 5 | 333.7 | 0
161 | Birbhum Division | NETURI PIPED WATER SUPPLY SCHEME. | SM/12656 | 496.1 | 5 | 493.63 | 42.49
162 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Danghara (Phase-II) Water Supply Scheme of Murarai-II Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | SM/12665 | 17.6 | 0 | 0 | 0
163 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Jhikadda Phase-II Water Supply Scheme. | SM/12667 | 24.91 | 2 | 19.43 | 6.98
164 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHICHUNRI AND OTHER 3 NOS. MOUZAS UNDER RAMPURHAT-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11906 | 127 | 1 | 94.31 | 0
165 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMRITAPUR AND MAJHARA MOUZAS UNDER MURARAI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11908 | 85 | 1 | 31 | 0
166 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR PARKANDI AND OTHER 7 NOS. MOUZAS UNDER RAMPURHAT-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11935 | 313 | 1 | 259 | 0
167 | Birbhum Division | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. | SM/13626 | 478.35 | 3 | 477.06 | 3.64
168 | Birbhum Division | Ikshudhara piped water supply scheme. | SM/13639 | 997.9 | 4 | 1018.65 | 22.15
169 | Birbhum Division | Nabagram Piped Water Supply Scheme. | SM/13646 | 628.41 | 6 | 434.68 | 12.32
170 | Birbhum Division | Kasba Piped Water Supply Scheme. | SM/13713 | 779.81 | 3 | 628.45 | 0
171 | Birbhum Division | RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/13950 | 800.41 | 2 | 70.16 | 4.66
172 | Birbhum Division | Bergram Piped Water Supply Scheme. | SM/13482 | 527.4 | 4 | 511.01 | 0
173 | Birbhum Division | FEUGRAM PIPED WATER SUPPLY SCHEME | SM/13477 | 813.8 | 3 | 91.71 | 2.37
174 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raghunathpur(Phase-II) Water Supply Scheme | SM/13372 | 20.61 | 1 | 20.01 | 9.7
175 | Birbhum Division | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09370 | 145.06 | 4 | 101.04 | 98.55
176 | Birbhum Division | MONACHITURA PIPED WATER SUPPLY SCHEME | SM/14450 | 846.93 | 1 | 88.12 | 0
177 | Birbhum Division | Noapara Piped Water Supply Scheme (Khoyrasole G.P.) | SM/14854 | 582.15 | 3 | 458.09 | 0
178 | Birbhum Division | SAJNOR PIPED WATER SUPPLY SCHEME | SM/14678 | 872.23 | 2 | 81.64 | 0
179 | Birbhum Division | Siur Piped Water Supply Scheme. | SM/14537 | 1169.86 | 5 | 1153.95 | 31.1
180 | Birbhum Division | THIBA PIPEED WATER SUPPLY SCHEME | SM/14968 | 538.07 | 2 | 105.44 | 0
181 | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | 1185.64 | 4 | 680.19 | 0
182 | Birbhum Division | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME | SM/14534 | 1071.04 | 2 | 107.11 | 0
183 | Birbhum Division | Sagarbhanga Piped Water Supply Scheme (Khoyrasole Block) | SM/16270 | 153.88 | 3 | 146.35 | 0
184 | Birbhum Division | MANIKPUR PIPED WATER SUPPLY SCHEME | SM/18509 | 1125.72 | 3 | 978.29 | 0
185 | Birbhum Division | Kankalitala piped water supply scheme. | SM/18518 | 1174.7 | 4 | 1195.68 | 33.71
186 | Birbhum Division | Bhabani Water Supply Scheme | SM/18351 | 1451.76 | 4 | 1155.13 | 0
187 | Birbhum Division | CHHATAR BANDI PIPED WATER SUPPLY SCHEME | SM/18354 | 1021.7 | 5 | 850.21 | 0
188 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR HARISHCHANDRAPUR AND OTHER 14 NOS. MOUZAS UNDER ILLAMBAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/14015 | 570 | 1 | 516 | 0
189 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS | SM/06734 | 94.74 | 8 | 72.52 | 68.47
190 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | 99.84 | 17 | 120.45 | 95.63
191 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum | SM/07530 | 296.93 | 7 | 287.7 | 241.52
192 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | 206.39 | 20 | 290.64 | 160.8
193 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | 99.46 | 19 | 102.97 | 23.33
194 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. | SM/08896 | 206.23 | 6 | 102.77 | 79.09
195 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09367 | 453.12 | 14 | 361.94 | 180.71
196 | Birbhum Division | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. | SM/12591 | 544.87 | 3 | 376.21 | 1.8
197 | Birbhum Division | KUSHIPUR PIPES WATER SUPPLY SCHEME. | SM/12599 | 667.02 | 3 | 462.79 | 21.52
198 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme | SM/12663 | 108.02 | 2 | 51.38 | 51.38
199 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Amdole Phase-II Water Supply Scheme | SM/12664 | 58.66 | 1 | 56.95 | 0
200 | Birbhum Division | KANAIPUR and Adjoining Mouzas PWSS | SM/12672 | 844.4 | 3 | 616.81 | 2.89
201 | Birbhum Division | KAMARDANGAL PIPED WATER SUPPLY SCHEME. | SM/12675 | 238.09 | 3 | 253.53 | 3.09
202 | Birbhum Division | Dakshin Kasila Piped Water Supply Scheme. | SM/12686 | 909.45 | 3 | 564.39 | 0
203 | Birbhum Division | NARAYANPUR PIPED WATER SUPPLY SCHEME. | SM/13625 | 525.66 | 2 | 97.58 | 27.66
204 | Birbhum Division | Gokrui Piped Water Supply Scheme. | SM/13631 | 426.79 | 2 | 106.74 | 0
205 | Birbhum Division | Majuria Piped Water Supply Scheme. | SM/13632 | 998.5 | 2 | 268.17 | 0
206 | Birbhum Division | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division | SM/13634 | 336.69 | 5 | 259.7 | 68.08
207 | Birbhum Division | Tilai piped water supply scheme. | SM/13127 | 404.7 | 2 | 39.61 | 0
208 | Birbhum Division | BHEPUR PIPED WATER SUPPLY SCHEME | SM/13759 | 705.69 | 3 | 75.83 | 2.05
209 | Birbhum Division | Jashoda Piped Water Supply Scheme. | SM/12891 | 363.96 | 6 | 384.9 | 33.17
210 | Birbhum Division | JIUI PIPED WATER SUPPLY SCHEME. | SM/12902 | 599.1 | 3 | 577.61 | 15.86
211 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. | SM/13371 | 33.38 | 5 | 23.75 | 17.65
212 | Birbhum Division | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13376 | 794.01 | 5 | 493.88 | 2.31
213 | Birbhum Division | Rupaspur Piped Water Supply Scheme. | SM/14081 | 436.17 | 3 | 344.16 | 14.47
214 | Birbhum Division | Bhaddi Piped Water Supply Scheme | SM/14114 | 422.65 | 3 | 317.6 | 0
215 | Birbhum Division | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | 1516.41 | 5 | 961.01 | 0
216 | Birbhum Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME | SM/14895 | 777.41 | 3 | 87.03 | 4.53
217 | Birbhum Division | KURUMBA PIPED WATER SUPPLY SCHEME | SM/14743 | 674.03 | 4 | 583.31 | 0
218 | Birbhum Division | Albandha Piped Water Supply Scheme. | SM/14533 | 1247.73 | 4 | 1169.09 | 20.14
219 | Birbhum Division | Barshal piped water supply scheme. | SM/14535 | 1768.83 | 6 | 1582.55 | 0
220 | Birbhum Division | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/16373 | 751.53 | 6 | 525.86 | 68.76
221 | Birbhum Division | Amlachaturi Piped Water Supply Scheme | SM/16387 | 904.87 | 3 | 640.22 | 17.58
222 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Rasa Phase-II water supply scheme, Block-Khoyrasole, District- Birbhum | SM/18783 | 99.79 | 3 | 124.49 | 0
223 | Birbhum Division | Aliat Piped Water Supply Scheme | SM/14083 | 414.62 | 3 | 311.28 | 0
224 | Birbhum Division | Ayas Piped Water Supply Scheme. | SM/18669 | 2251.52 | 3 | 404.66 | 14.32
225 | Birbhum Division | Retrofitting works of Kalhua(Phase-II) Water Supply Scheme under Rampurhat-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07152 | 65.97 | 3 | 53.3 | 53.3
226 | Birbhum Division | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area | SM/06943 | 97.5 | 5 | 95.29 | 94.61
227 | Birbhum Division | Retrofitting works of Hazarpur (Phase-II) water supply scheme under Rampurhat-II Block PWSS for providing Functional Household Tap Connection(FHTC) within command area | SM/06946 | 97.74 | 3 | 39.5 | 38.5
228 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) | SM/06743 | 97.37 | 8 | 127.33 | 52
229 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | 190.61 | 22 | 227.37 | 183.75
230 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. | SM/08898 | 147.83 | 5 | 89.39 | 85.77
231 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09364 | 234.01 | 4 | 160.48 | 112.31
232 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09371 | 105.12 | 6 | 105.16 | 98.52
233 | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | 762.27 | 30 | 778.66 | 399.11
234 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | 93.68 | 14 | 79.17 | 56.14
235 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | 68.88 | 9 | 51.53 | 50.97
236 | Birbhum Division | Augmentation of Tejhati PWSS | SM/10166 | 367.8 | 10 | 386.27 | 109.79
237 | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | 11639.45 | 141 | 13248.7 | 9020.92
238 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Datababa mazar water supply scheme | SM/10665 | 58.24 | 3 | 60.46 | 49.55
239 | Birbhum Division | JOGAI PIPED WATER SUPPLY SCHEME. | SM/12593 | 514.78 | 3 | 296.91 | 3.2
240 | Birbhum Division | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. | SM/12595 | 886.16 | 3 | 438.67 | 3.16
241 | Birbhum Division | Meherpur and Adjoining Mouzas PWSS | SM/12457 | 488.08 | 2 | 49.85 | 8.91
242 | Birbhum Division | Melanpur Piped Water Supply Scheme. | SM/12699 | 522.74 | 3 | 460.46 | 7.81
243 | Birbhum Division | Monai Piped Water Supply Scheme. | SM/12701 | 437.26 | 3 | 365.61 | 1.98
244 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. | SM/12657 | 23.91 | 4 | 16.74 | 15.6
245 | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | 661.51 | 9 | 221.25 | 11.66
246 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BAMUNDIHA AND OTHER 14 NOS. MOUZAS UNDER MD BAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/12068 | 541 | 1 | 487 | 0
247 | Birbhum Division | Math Basori Piped Water Supply Scheme. | SM/13627 | 564.3 | 3 | 394.3 | 0
248 | Birbhum Division | Kurumsaha Piped Water Supply Scheme. | SM/13628 | 301.71 | 7 | 327.7 | 25.84
249 | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | 979.98 | 5 | 663.95 | 0
250 | Birbhum Division | Madhupur Water Supply Scheme | SM/13644 | 676.32 | 5 | 406.01 | 4.01
251 | Birbhum Division | Kachujore Piped Water Supply Scheme. | SM/13016 | 173.49 | 3 | 186.69 | 2.01
252 | Birbhum Division | Shaspur Piped Water Supply Scheme. | SM/13651 | 794.81 | 5 | 508.27 | 14.58
253 | Birbhum Division | Taloan Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13653 | 537.6 | 3 | 356.39 | 1.57
254 | Birbhum Division | BHEJENA PIPED WATER SUPPLY SCHEME. | SM/12833 | 244.52 | 3 | 259.47 | 0
255 | Birbhum Division | Bidhyadharpur Piped Water Supply Scheme. | SM/13708 | 621.16 | 3 | 495.68 | 0
256 | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | 1170.21 | 4 | 747.43 | 0
257 | Birbhum Division | KOGRAM PIPED WATER SUPPLY SCHEME. | SM/12894 | 721.43 | 3 | 498.57 | 45.23
258 | Birbhum Division | PANCHPARA PIPED WATER SUPPLY SCHEME | SM/13951 | 639.73 | 1 | 88.12 | 0
259 | Birbhum Division | SEHANA PIPED WATER SUPPLY SCHEME. | SM/12890 | 526.76 | 3 | 520.74 | 17.36
260 | Birbhum Division | Khanpur piped water supply scheme. | SM/13539 | 875.43 | 3 | 685.88 | 23.06
261 | Birbhum Division | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District | SM/14016 | 191.26 | 6 | 170.73 | 83.26
262 | Birbhum Division | Rajpur Piped Water Supply Scheme | SM/14026 | 732.55 | 4 | 505.76 | 0
263 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ALALPUR AND OTHER 5 NOS. MOUZAS UNDER NALHATI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/14038 | 225 | 1 | 171 | 0
264 | Birbhum Division | Khanpur Piped Water Supply Scheme. | SM/14085 | 846.77 | 3 | 533.62 | 32.46
265 | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | 913.88 | 5 | 621.9 | 0
266 | Birbhum Division | HATKALUA PIPED WATER SUPPLY SCHEME | SM/14115 | 674.17 | 3 | 551.71 | 0
267 | Birbhum Division | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | 399.02 | 6 | 286.19 | 19.16
268 | Birbhum Division | BHETER PIPED WATER SUPPLY SCHEME | SM/14848 | 507.47 | 3 | 93.11 | 1.57
269 | Birbhum Division | Parsundi Piped Water Supply Scheme | SM/14855 | 506.23 | 4 | 399.19 | 0
270 | Birbhum Division | KHAYERBANI PIPED WATER SUPPLY SCHEME | SM/14677 | 522.91 | 2 | 105 | 0
271 | Birbhum Division | Moubelia Piped Water Supply Scheme. | SM/14899 | 409.66 | 4 | 350.18 | 157.52
272 | Birbhum Division | HANSAN PIPED WATER SUPPLY SCHEME | SM/14900 | 900.67 | 5 | 83.3 | 0
273 | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | 996.36 | 3 | 853.43 | 0
274 | Birbhum Division | RAGHABPUR PIPED WATER SUPPLY SCHEME | SM/14747 | 379.11 | 4 | 294.36 | 0
275 | Birbhum Division | RAYEN PIPED WATER SUPPLY SCHEME | SM/14957 | 452.46 | 3 | 78.77 | 2.61
276 | Birbhum Division | GOALDIHI PIPED WATER SUPPLY SCHEME | SM/15528 | 523.1 | 3 | 72.37 | 1.52
277 | Birbhum Division | Salan Piped Water Supply Scheme. | SM/14207 | 778.17 | 3 | 755.41 | 0
278 | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | 1122.66 | 4 | 155.47 | 0
279 | Birbhum Division | Augmentation of Margram piped water supply scheme. | SM/18372 | 1979.65 | 6 | 124.7 | 87.11
280 | Birbhum Division | BILASPUR PIPED WATER SUPPLY SCHEME. | SM/12594 | 862.54 | 3 | 479.99 | 3.95
281 | Birbhum Division | DHANASAHA PIPED WATER SUPPLY SCHEME | SM/18352 | 1202.1 | 5 | 985.08 | 0
282 | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. | SM/18366 | 1040.7 | 5 | 922.01 | 0
283 | Birbhum Division | KAHINAGAR PIPED WATER SUPPLY SCHME | SM/12887 | 807.08 | 3 | 525.68 | 0
284 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) | SM/06732 | 99.79 | 5 | 95.7 | 74.2
285 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) | SM/06735 | 99.99 | 8 | 94.06 | 89.09
286 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | 99.97 | 13 | 55.89 | 85.28
287 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-III) | SM/07647 | 64.73 | 2 | 1.72 | 0
288 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | 99.95 | 12 | 111.93 | 83.56
289 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08891 | 176.25 | 6 | 103.05 | 25.42
290 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | 96.68 | 11 | 69.04 | 65.98
291 | Birbhum Division | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | 466.85 | 3 | 446.98 | 16.7
292 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Harisara Phase-II Water Supply Scheme | SM/12658 | 13.68 | 0 | 0 | 0
293 | Birbhum Division | Abdullahpur Piped Water Supply Scheme. | SM/12679 | 799.1 | 3 | 542.53 | 0
294 | Birbhum Division | Balijuri Piped Water Supply Scheme. | SM/12682 | 940.28 | 2 | 218.61 | 0
295 | Birbhum Division | Dakshin Chandipur Piped Water Supply Scheme. | SM/12685 | 556.73 | 3 | 497.18 | 0
296 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR NISHPARUN AND OTHER 4 NOS. MOUZAS UNDER RAMPURHAT-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11901 | 206 | 1 | 104.19 | 0
297 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GANUTIA AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11903 | 849 | 1 | 795 | 0
298 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GHOGAN AND OTHER 11 NOS. MOUZAS UNDER NANOOR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11905 | 458 | 1 | 404 | 95.27
299 | Birbhum Division | Gaytha Piped Water Supply Scheme | SM/13712 | 533.16 | 6 | 293.76 | 14.55
300 | Birbhum Division | CHUNPALASHI PIPED WATER SUPPLY SCHEME | SM/13637 | 740.04 | 4 | 657.85 | 0
301 | Birbhum Division | Chakpara piped water supply scheme. | SM/13638 | 640.93 | 4 | 546.2 | 0
302 | Birbhum Division | Kanaipur piped water supply scheme. | SM/13640 | 801.2 | 5 | 713.83 | 20.85
303 | Birbhum Division | NOHNA PIPED WATER SUPPLY SCHEME | SM/13645 | 813.39 | 4 | 778.62 | 0
304 | Birbhum Division | Srikantapur piped water supply scheme. | SM/13652 | 774.31 | 2 | 54.72 | 0
305 | Birbhum Division | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | 574.46 | 3 | 403.91 | 72.65
306 | Birbhum Division | MAJHKALITHA PIPED WATER SUPPLY SCHEME. | SM/12838 | 999.45 | 3 | 501.74 | 2.3
307 | Birbhum Division | RAUTARA PIPED WATER SUPPLY SCHEME. | SM/12888 | 247.15 | 3 | 249.05 | 16.89
308 | Birbhum Division | PHULUR PIPED WATER SUPPLY SCHEME. | SM/12901 | 653.75 | 3 | 637.13 | 0.27
309 | Birbhum Division | SARIHA PIPED WATER SUPPLY SCHEME | SM/12900 | 807.12 | 3 | 603.58 | 0
310 | Birbhum Division | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | 447.36 | 6 | 334.91 | 13.68
311 | Birbhum Division | Nawapara Piped Water Supply Scheme | SM/13479 | 720.04 | 4 | 473 | 22.15
312 | Birbhum Division | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/13480 | 534.51 | 6 | 344.47 | 11.79
313 | Birbhum Division | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/13516 | 288.36 | 2 | 250.49 | 0
314 | Birbhum Division | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13476 | 754.73 | 5 | 462.26 | 2.2
315 | Birbhum Division | BENAGRAM PIPED WATER SUPPLY SCHEME | SM/13377 | 624.74 | 3 | 104.25 | 3.62
316 | Birbhum Division | DELORA PIPED WATER SUPPLY SCHEME | SM/13600 | 388.22 | 3 | 373.6 | 0
317 | Birbhum Division | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14141 | 1206.94 | 4 | 721.04 | 0
318 | Birbhum Division | Banhat Piped Water Supply Scheme. | SM/14029 | 484.07 | 4 | 377.36 | 128.91
319 | Birbhum Division | KADOA PIPED WAYER SUPPLY SCHEME | SM/14668 | 594.33 | 2 | 116.31 | 0
320 | Birbhum Division | Ahmadpur Piped Water Supply Scheme | SM/14889 | 896.86 | 4 | 706.08 | 59.55
321 | Birbhum Division | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. | SM/15236 | 738.45 | 5 | 690.95 | 24.24
322 | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/15253 | 649.94 | 3 | 116.7 | 0
323 | Birbhum Division | MAHESWARPUR PIPED WATER SUPPLY SCHEME | SM/15254 | 471.69 | 4 | 446.15 | 0
324 | Birbhum Division | MADDA PIPED WATER SUPPLY SCHEME | SM/15255 | 639.56 | 2 | 66.53 | 1.86
325 | Birbhum Division | Mayandal Piped Water Supply Scheme | SM/16273 | 158.49 | 3 | 136.46 | 0
326 | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | SM/18514 | 1186.83 | 7 | 651.95 | 8.44
327 | Birbhum Division | KANAIPUR PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/18489 | 814.18 | 3 | 498.39 | 0
328 | Birbhum Division | Tamra Piped Water Supply Scheme | SM/18739 | 284.35 | 3 | 200.99 | 0
329 | Birbhum Division | Beloa Piped Water Supply Scheme | SM/18522 | 1076.07 | 4 | 781.33 | 20.77
330 | Birbhum Division | Daskalgram Piped Water Supply Scheme | SM/18353 | 1197.31 | 2 | 140.19 | 0
331 | Birbhum Division | LAYEKPUR PIPED WATER SUPPLY SCHEME | SM/18361 | 1217.25 | 1 | 132.46 | 0
332 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | 95.12 | 12 | 260.85 | 68.41
333 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bansjore PWSS (Phase-I) | SM/07006 | 99.48 | 3 | 118.88 | 94.51
334 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | 179.67 | 7 | 185.18 | 86.86
335 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block | SM/07650 | 53.59 | 9 | 53.09 | 33.28
336 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08897 | 109.18 | 4 | 93.73 | 71.71
337 | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | 120.18 | 12 | 119.32 | 32.24
338 | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09368 | 68.35 | 6 | 64.05 | 26.19
339 | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | 416.43 | 39 | 378.4 | 114.59
340 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) | SM/06742 | 98.25 | 7 | 59.06 | 57
341 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | 865 | 29 | 820.07 | 772.89
342 | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | 7907.91 | 55 | 5381.88 | 2398.67
343 | Birbhum Division | PURBA SIUR PIPED WATER SUPPLY SCHEME. | SM/12598 | 497.79 | 4 | 496.16 | 19.52
344 | Birbhum Division | DALIMA PIPED WATER SUPPLY SCHEME. | SM/12592 | 662.48 | 3 | 444.62 | 0
345 | Birbhum Division | Kamdebnala piped water supply scheme. | SM/12694 | 476.19 | 3 | 321.23 | 34.6
346 | Birbhum Division | Kulara Piped Water Supply Scheme. | SM/12695 | 481.59 | 5 | 305.65 | 25.89
347 | Birbhum Division | Harinduba Piped Water Supply Scheme. | SM/12692 | 739.16 | 3 | 454.43 | 0
348 | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. | SM/12659 | 149.48 | 2 | 81.58 | 0
349 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Belera Phase-II Water Supply Scheme. | SM/12660 | 21.01 | 1 | 17.31 | 6.8
350 | Birbhum Division | Behira and Adjoining Mouzas PWSS | SM/12456 | 313.84 | 3 | 297.54 | 0
351 | Birbhum Division | Mahurapur and Adjoining Mouzas PWSS | SM/12697 | 1066.63 | 4 | 649.96 | 0
352 | Birbhum Division | Metegaon and Adjoining Mouzas PWSS | SM/12700 | 653.76 | 4 | 609.03 | 0
353 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BABUPUR AND OTHER 5 NOS. MOUZAS UNDER SURI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11899 | 222 | 1 | 172.42 | 0
354 | Birbhum Division | Nanubazar Piped Water Supply Scheme | SM/12673 | 615.54 | 2 | 144.46 | 0
355 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR MAJURIA AND OTHER 19 NOS. MOUZAS UNDER DUBRAJPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/12073 | 775 | 1 | 721 | 0
356 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMLACHATURI AND OTHER 10 NOS. MOUZAS UNDER RAJNAGAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11936 | 394 | 1 | 340 | 0
357 | Birbhum Division | ULANDI PIPED WATER SUPPLY SCHEME | SM/13654 | 626.02 | 3 | 102.03 | 0
358 | Birbhum Division | Podda Piped Water Supply Scheme | SM/13714 | 424.09 | 7 | 283.2 | 14.44
359 | Birbhum Division | BHALIAN PIPED WATER SUPPLY SCHME. | SM/12834 | 573.21 | 4 | 572.18 | 5
360 | Birbhum Division | BIRSINGHA PIPED WATER SUPPLY SCHEME. | SM/12830 | 411.72 | 5 | 419.89 | 22.07
361 | Birbhum Division | Prasadpur Piped Water Supply Scheme | SM/13478 | 833.6 | 4 | 567.44 | 12.06
362 | Birbhum Division | Nohana and Adjoining Mouzas PWSS | SM/12905 | 301.26 | 5 | 295.8 | 0
363 | Birbhum Division | Haridaspur Piped Water Supply Scheme. | SM/14028 | 977.13 | 5 | 830.17 | 0.49
364 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR CHANDANPUR AND OTHER 5 NOS. MOUZAS UNDER MURARAI-I & NALHATI-I BLOCKS UNDER BIRBHUM DIVISION, PHE DTE. | SM/14043 | 217 | 1 | 108.18 | 0
365 | Birbhum Division | TATINAPARA PIPED WATER SUPPLY SCHEME | SM/13979 | 880.48 | 2 | 694.73 | 0
366 | Birbhum Division | Ninga Piped Water Supply Scheme | SM/14089 | 844.34 | 5 | 115.31 | 0
367 | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme | SM/10315 | 283.04 | 6 | 206.17 | 170.39
368 | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | 950.21 | 5 | 574.14 | 0
369 | Birbhum Division | Baraban Piped Water Supply Scheme (Khoyrasole Block) | SM/14852 | 585.66 | 3 | 458.23 | 0
370 | Birbhum Division | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14676 | 435.64 | 5 | 304.23 | 2.54
371 | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/14897 | 727.26 | 3 | 599.85 | 0
372 | Birbhum Division | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | 907.13 | 7 | 325.93 | 14.35
373 | Birbhum Division | Dhalla Piped Water Supply Scheme | SM/15256 | 960.39 | 5 | 112.86 | 0
374 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS | SM/06738 | 99.99 | 6 | 88.14 | 86.87
375 | Birbhum Division | Hatikata Piped Water Supply Scheme | SM/16198 | 290.59 | 3 | 245.43 | 0
376 | Birbhum Division | Atkulia Piped Water Supply Scheme | SM/18301 | 1007.63 | 4 | 798.3 | 30.8
377 | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR NAYIT AND OTHER 3 NOS. MOUZAS UNDER MURARAI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11907 | 151 | 1 | 152.34 | 0
378 | Birbhum Division | Loba Piped Water Supply Scheme. | SM/18511 | 2382.48 | 3 | 1772 | 198.88
379 | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Sadasibpur (Phase-II) Water Supply Scheme of Murarai-II Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | SM/13373 | 13.41 | 0 | 0 | 0
380 | Birbhum Division | Kusumba Piped Water Supply Scheme. | SM/18362 | 1173.23 | 3 | 69.95 | 0
381 | Birbhum Division | Dakhalbati Piped Water Supply Scheme. | SM/18363 | 2553.67 | 2 | 163.65 | 0
382 | Birbhum Division | Dhananjaypur Piped Water Supply Scheme. | SM/12688 | 701.06 | 2 | 48.08 | 0
383 | Birbhum Division | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte | SM/18425 | 4901.98 | 3 | 4549.9 | 49.02
384 | Birbhum Division | Mostala Piped Water Supply Scheme. | SM/18519 | 1209.99 | 4 | 1235.21 | 53.61
385 | Birbhum Division | Sahapur Piped Water Supply Scheme. | SM/18520 | 1609.49 | 7 | 233.46 | 9.76
386 | Birbhum Division | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/18521 | 1043.88 | 5 | 688.05 | 0
387 | Birbhum Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. | SM/08981 | 0 | 0 | 0 | 19.21
388 | Bolpur Mechanical Division | Procurement of Computer and Peripherals for the office use in Bolpur Mechanical Division, AE-III Central Mechanical Division, Birbhum Mechanical Sub-Division (Drilling) PHE Dte. | SM/18141 | 0 | 0 | 0 | 7.96
389 | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | 0 | 2 | 57.81 | 36.75
390 | Bolpur Mechanical Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratory. | SM/06628 | 0 | 1 | 4.83 | 4.41
391 | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. | SM/06632 | 0 | 17 | 43.13 | 68.1
392 | Birbhum Division | New Pipe Testing Laboratory for testing of UPVC and HDPE pipes at Suri, Birbhum under Birbhum Division. | SM/16483 | 0 | 1 | 94.98 | 0
393 | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM | SM/15636 | 0 | 2 | 18.63 | 0
394 | Birbhum Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19083 | 0 | 0 | 0 | 0
395 | Birbhum Division | Preparation of DPR for Drinking Water Supply Schemes within the different blocks of Birbhum District under Birbhum Division, PHE Dte. | SM/18987 | 0 | 0 | 0 | 0
396 | Birbhum Division | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. | SM/09199 | 0 | 10 | 7.91 | 7.65
397 | Birbhum Division | Supply and delivery of Desktop Computer and Multifunction machine (Printer including Scanner) under Birbhum Division P.H.E. Dte. | SM/18278 | 0 | 0 | 0 | 2.39
398 | Birbhum Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Birbhum District. | SM/09198 | 0 | 0 | 0 | 242.04
Total |  |  |  | 254849.18 | 0 | 168799.05 | 28104.1